## PMP_All_Data
No | Question. 번역, 코드,Web으로 만들기 | A | B | C | D | E | Answer | Explanation(Changed) | 2021 ECO Domain | 2021 ECO Task | PMBOK7 Performance Domain | PMBOK7 Principle | Methodology | Methodology detail | 2026 ECO Domain | 2026 ECO Task | PMBOK8 Performance Domain | PMBOK8 Focus Area | PMBOK8 Principle | PMBOK8 Process | PMBOK8 New Topics | Question_KR | A_KR | B_KR | C_KR | D_KR | E_KR | Answer | Explanation_KR
1 | A company is engaged in a mining project. There are some external stakeholders who have no familiarity with the mining industry. How should the project manager communicate the organizational culture and project goal to these stakeholders? | Ask a team member to directly address the information needs of the stakeholders. | Prepare a report outlining the organizational structure and project parameters. | Hire a company to advertise the project and company through a media outlet. | Take the stakeholders out informally and verbally brief them about the organization and project. |  | B | When external stakeholders lack familiarity with the industry, the PM should communicate organizational culture and project objectives through a formal, written report. This format delivers a structured, comprehensive overview of the project context, scope, objectives, deliverables, and stakeholder roles and responsibilities. Among the alternatives, delegating communication to a team member (A) is too indirect, hiring a media company (C) is disproportionate for this purpose, and an informal verbal briefing (D) lacks the formality and thoroughness needed for external stakeholders with no industry background. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 한 회사가 광산 프로젝트를 진행하고 있다. 광산 산업에 대한 배경지식이 전혀 없는 외부 이해관계자들이 있다. 프로젝트 관리자는 이 이해관계자들에게 조직 문화와 프로젝트 목표를 어떻게 전달해야 하는가? | 팀원에게 이해관계자들의 정보 요구사항을 직접 해결하도록 요청한다. | 조직 구조와 프로젝트 매개변수를 설명하는 보고서를 작성한다. | 미디어 매체를 통해 프로젝트와 회사를 홍보할 업체를 고용한다. | 이해관계자들을 비공식적으로 만나 조직과 프로젝트에 대해 구두로 브리핑한다. |  | B | 외부 이해관계자들이 해당 산업에 대한 배경지식이 없을 때, PM은 공식적인 서면 보고서를 통해 조직 문화와 프로젝트 목표를 전달해야 한다. 이 형식은 프로젝트 배경, 범위, 목표, 산출물, 이해관계자 역할 및 책임에 대한 체계적이고 포괄적인 개요를 제공한다. 다른 대안들 중, 팀원에게 의사소통을 위임하는 것(A)은 너무 간접적이고, 미디어 회사를 고용하는 것(C)은 이 목적에 비해 과도하며, 비공식 구두 브리핑(D)은 산업 배경지식이 없는 외부 이해관계자에게 필요한 공식성과 철저함이 부족하다.
2 | A newly formed project team includes team members who have been working in the company for a long time as well as team members who are new to the company. The project team members discovered that there is a gap in communication between these two groups, and they are finding it hard to collaborate with one another. What should the project manager do? | Organize networking sessions to allow the team members to get to know one another. | Ask the experienced members to lead the junior members to facilitate skill transfer. | Ask the team to self-organize and escalate any issues to the project manager. | Encourage team members to focus on delivering results with their specialized skills. |  | A | When experienced and new team members have a communication gap making collaboration difficult, the project manager should organize networking sessions to allow team members to get to know one another. Building interpersonal relationships bridges communication gaps and establishes trust. Asking experienced members to lead juniors (B) creates hierarchy. Asking the team to self-organize and escalate (C) provides insufficient support. Encouraging focus on specialized skills (D) reinforces silos. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 새로 구성된 프로젝트 팀에는 회사에서 오랫동안 근무한 팀원들과 회사에 새로 합류한 팀원들이 포함되어 있다. 프로젝트 팀원들은 두 그룹 간에 의사소통 격차가 있음을 발견했으며, 서로 협업하는 데 어려움을 겪고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀원들이 서로를 알아갈 수 있도록 네트워킹 세션을 조직한다. | 경험 많은 팀원들이 주니어 팀원들을 이끌어 기술 이전을 촉진하도록 요청한다. | 팀이 자기 조직화하고 문제가 있으면 프로젝트 관리자에게 에스컬레이션하도록 요청한다. | 팀원들이 전문 기술로 결과를 도출하는 데 집중하도록 격려한다. |  | A | 경험 많은 팀원과 새로운 팀원 간에 의사소통 격차가 있어 협업이 어려울 때, 프로젝트 관리자는 팀원들이 서로를 알아갈 수 있도록 네트워킹 세션을 조직해야 한다. 대인관계 구축은 의사소통 격차를 해소하고 신뢰를 형성한다. 경험 많은 팀원에게 주니어를 이끌도록 요청하는 것(B)은 위계를 만든다. 팀에게 자기 조직화하고 에스컬레이션하도록 요청하는 것(C)은 불충분한 지원이다. 전문 기술에 집중하도록 격려하는 것(D)은 사일로를 강화한다.
3 | The change control board (CCB) has approved a change request to add a new component within a product. The operations manager discovers the change after its approval and complains that the implementation of the change will cause significant disruption to the production line. What should the project manager do first? | Escalate the issue to the project sponsor, as the decision to add the component bringsmany benefits even though it will be disruptive to the production line. | Lead a root cause analysis workshop with the design team to identify the failures thatled to the decision to add a component that was not compatible with the productionline. | Formally acknowledge the operation manager ' s concerns and raise a new risk that theproject may deliver late and over budget due to manufacturing difficulties. | Meet with the operations manager to explain the background for the change andunderstand the operation manager ' s concerns about the change. |  | D | When the operations manager discovers an approved change will disrupt the production line, the project manager should first meet with the operations manager to explain the change background and understand their concerns. Direct engagement enables collaborative problem-solving before escalation. Escalating to the sponsor (A) bypasses direct resolution. Leading a root cause analysis on design failures (B) is premature and misdirected. Formally acknowledging concerns and raising a risk (C) documents but does not resolve the issue. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 변경통제위원회(CCB)가 제품 내 새로운 구성요소를 추가하는 변경 요청을 승인했다. 운영 관리자는 승인 후 이 변경을 발견하고, 변경 구현이 생산 라인에 심각한 혼란을 초래할 것이라고 불만을 제기했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 생산 라인에 혼란을 줄 수 있지만 구성요소 추가 결정이 많은 이점을 가져오므로, 프로젝트 스폰서에게 문제를 에스컬레이션한다. | 생산 라인과 호환되지 않는 구성요소를 추가하기로 한 결정의 실패 원인을 파악하기 위해 설계팀과 근본 원인 분석 워크숍을 진행한다. | 운영 관리자의 우려를 공식적으로 인정하고, 제조 어려움으로 인해 프로젝트가 지연되고 예산을 초과할 수 있다는 새로운 리스크를 제기한다. | 운영 관리자를 만나 변경의 배경을 설명하고, 변경에 대한 운영 관리자의 우려 사항을 파악한다. |  | D | 운영 관리자가 승인된 변경이 생산 라인에 혼란을 초래할 것을 발견했을 때, 프로젝트 관리자는 먼저 운영 관리자를 만나 변경 배경을 설명하고 그들의 우려를 파악해야 한다. 직접적인 소통은 에스컬레이션 전에 협력적 문제 해결을 가능하게 한다. 스폰서에게 에스컬레이션하는 것(A)은 직접 해결을 우회한다. 설계 실패에 대한 근본 원인 분석을 진행하는 것(B)은 시기상조이며 방향이 잘못되었다. 우려를 공식적으로 인정하고 리스크를 제기하는 것(C)은 문서화하지만 문제를 해결하지는 않는다.
4 | During the final iteration of the execution phase, the project has a cost performance index (CPI) of 0.9 and a schedule performance index (SPI) of 1.0. How should the project manager avoid a budget shortfall? | Look for cost-saving opportunities. | Submit a change request to add to the management reserve. | Reduce the team effort utilization. | Follow the risk management plan. |  | A | When the project has a CPI of 0.9 (over budget) and SPI of 1.0 (on schedule) during the final iteration, the project manager should look for cost-saving opportunities. Cost recovery is the priority when over budget but on time. Submitting a change request for management reserve (B) adds budget rather than managing costs. Reducing team effort (C) may delay the project. Following the risk management plan (D) is general, not targeted. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 실행 단계의 마지막 이터레이션에서 프로젝트의 CPI(원가성과지수)가 0.9이고 SPI(일정성과지수)가 1.0이다. 프로젝트 관리자는 예산 부족을 어떻게 피해야 하는가? | 비용 절감 기회를 찾는다. | 관리 예비비에 추가하기 위한 변경 요청을 제출한다. | 팀의 노력 활용률을 줄인다. | 리스크 관리 계획을 따른다. |  | A | 프로젝트의 CPI가 0.9(예산 초과)이고 SPI가 1.0(일정 준수)인 마지막 이터레이션에서, 프로젝트 관리자는 비용 절감 기회를 찾아야 한다. 예산 초과이지만 일정이 맞을 때는 비용 회수가 우선이다. 관리 예비비에 대한 변경 요청(B)은 비용 관리가 아닌 예산 추가이다. 팀 노력 감소(C)는 프로젝트를 지연시킬 수 있다. 리스크 관리 계획 준수(D)는 일반적이며 목표가 불명확하다.
5 | A high-tech borehole project was initiated with the goal of providing water for a rural community of 1,500 villagers located in an arid region. The project was completed with a cost performance index (CPI) of 1.09 and a schedule performance index (SPI) of 0.93. Six months after its completion, it is determined that the villagers could not access water. What caused this situation to occur? | The project was delivered above budget. | The requirements gathering was inadequate. | The risk analysis was inadequate. | The project was completed behind schedule. |  | B | When a borehole project completed with CPI 1.09 (under budget) and SPI 0.93 (behind schedule) but villagers cannot access water six months later, the cause was inadequate requirements gathering. The project delivered on cost and schedule metrics but failed to capture the actual user needs. Being above budget (A) is incorrect since CPI > 1.0. Inadequate risk analysis (C) is plausible but secondary to the requirements failure. Being behind schedule (D) is true but did not cause the access problem. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Schedule Management | Process | Plan and Manage Schedule | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 건조 지역에 위치한 1,500명 주민의 농촌 공동체에 물을 공급하기 위한 첨단 시추공 프로젝트가 시작되었다. 프로젝트는 CPI 1.09, SPI 0.93으로 완료되었다. 완료 6개월 후, 주민들이 물에 접근할 수 없는 것으로 확인되었다. 이 상황을 초래한 원인은 무엇인가? | 프로젝트가 예산을 초과하여 납품되었다. | 요구사항 수집이 부적절했다. | 리스크 분석이 부적절했다. | 프로젝트가 일정보다 늦게 완료되었다. |  | B | CPI 1.09(예산 이하)와 SPI 0.93(일정 지연)으로 완료된 시추공 프로젝트에서 주민들이 물에 접근할 수 없다면, 원인은 부적절한 요구사항 수집이다. 프로젝트는 비용과 일정 지표를 충족했지만 실제 사용자 요구를 파악하지 못했다. 예산 초과(A)는 CPI > 1.0이므로 틀렸다. 부적절한 리스크 분석(C)은 가능하지만 요구사항 실패에 비해 부차적이다. 일정 지연(D)은 사실이지만 접근 문제의 원인은 아니다.
6 | A large multinational company works on a project in an emerging-economy country. All business matters are conducted in local currency. During the course of the project, the budget becomes the primary concern due to currency instability in the country. What should the project manager do next? | Ask for additional budget from the client | Escalate the risk to the project sponsor | Evaluate the situation with the team 1246 | Use the project ' s contingency reserve |  | B | When currency instability threatens the budget of a project conducted in local currency, the project manager should escalate the risk to the project sponsor. Currency risk is beyond the team's control and requires senior guidance. Asking for additional budget (A) may be premature. Evaluating with the team (C) does not address the governance level needed. Using contingency reserve (D) may not cover currency risk. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 대규모 다국적 기업이 신흥 경제 국가에서 프로젝트를 수행하고 있다. 모든 비즈니스 업무는 현지 통화로 진행된다. 프로젝트 진행 중 국가의 통화 불안정으로 인해 예산이 주요 관심사가 되었다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 고객에게 추가 예산을 요청한다. | 프로젝트 스폰서에게 리스크를 에스컬레이션한다. | 팀과 함께 상황을 평가한다. | 프로젝트의 우발사태 예비비를 사용한다. |  | B | 현지 통화로 수행되는 프로젝트에서 통화 불안정이 예산을 위협할 때, 프로젝트 관리자는 프로젝트 스폰서에게 리스크를 에스컬레이션해야 한다. 통화 리스크는 팀의 통제 범위를 벗어나며 고위 경영진의 지침이 필요하다. 추가 예산 요청(A)은 시기상조일 수 있다. 팀과 평가(C)는 필요한 거버넌스 수준을 충족하지 못한다. 우발사태 예비비 사용(D)은 통화 리스크를 충당하지 못할 수 있다.
7 | A business transformation project has a four-phase delivery plan. The project team has successfully delivered one phase of the project. To further enhance team performance and empower team members, which two actions should the project manager take? (Choose two) | Vet all of the decisions before execution. | Organize and assign team members to tasks where they have strengths. | Allow team members to make limited decisions. | Encourage team members to cross-check decisions with the project manager. | Support team members to make decisions in their areas of strength. | B, D | To enhance team performance and empower members after successfully delivering a project phase, the project manager should take two actions: organize and assign team members to tasks where they have strengths (B), and encourage team members to cross-check decisions with the project manager (D). Strength-based assignment leverages individual capabilities, while cross-checking with the PM ensures alignment and quality during the growth phase. Vetting all decisions before execution (A) undermines empowerment. Allowing only limited decisions (C) restricts autonomy. Supporting decisions in areas of strength (E) is positive but less structured than cross-checking for a team still building confidence. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 비즈니스 혁신 프로젝트가 4단계 납품 계획을 가지고 있다. 프로젝트 팀은 한 단계를 성공적으로 납품했다. 팀 성과를 더욱 향상시키고 팀원들에게 권한을 부여하기 위해 프로젝트 관리자가 취해야 할 두 가지 조치는? (2개 선택) | 실행 전에 모든 결정을 검토한다. | 팀원들을 그들이 강점을 가진 업무에 조직하고 배치한다. | 팀원들이 제한된 결정을 내릴 수 있도록 허용한다. | 팀원들이 프로젝트 관리자와 결정을 교차 확인하도록 권장한다. | 팀원들이 자신의 강점 분야에서 결정을 내리도록 지원한다. | B, D | 프로젝트 단계를 성공적으로 납품한 후 팀 성과를 향상시키고 권한을 부여하기 위해, 프로젝트 관리자는 두 가지 조치를 취해야 한다: 팀원들을 강점이 있는 업무에 배치하고(B), 팀원들이 프로젝트 관리자와 의사결정을 교차 확인하도록 장려한다(D). 강점 기반 배치는 개인 역량을 활용하고, PM과의 교차 확인은 성장 단계에서 정렬과 품질을 보장한다. 실행 전 모든 결정 검토(A)는 권한 부여를 약화시킨다. 제한된 결정만 허용(C)은 자율성을 제한한다. 강점 분야 결정 지원(E)은 긍정적이나 교차 확인보다 구조적이지 않다.
8 | A project manager is overseeing a project as part of a program geared toward a major technology disruption. The team is comprised of brilliant young professionals who have worked on different projects for the organization in the past. However, the team complained that they previously experienced a lack of direction during project execution and are afraid of the same issue in this project. Which two actions should the project manager take to ensure that this issue does not occur in this project? (Choose two) | Set a clear vision for the project and ensure it is visible to all stakeholders. | Encourage the team to do a brainstorming session and provide a mitigation plan. | Keep the team engaged and focused on the project ' s direction. | Focus on the resource management plan and track project progress, | Organize a team-bonding activity and invite an external manager to speak to the team. | C, E | When brilliant team members fear lack of direction based on past experience, the project manager should take two actions: keep the team engaged and focused on the project's direction (C), and organize a team-bonding activity and invite an external manager to speak to the team (E). Sustained engagement ensures focus on project goals, while team-bonding with external perspectives builds confidence and cohesion. Setting a clear vision (A) is valuable but is a one-time action that does not sustain engagement. Brainstorming mitigation plans (B) is reactive rather than proactive. Focusing on resource management and tracking (D) is administrative and does not address the team's directional concerns. | Business Environment | Evaluate & Address External Environment Changes | Uncertainty | Navigate Complexity | Agile | Agile General Practices | Business Environment | Evaluate External Environment | Schedule | Monitoring & Controlling | Adopt a Holistic View | Control Schedule | Traditional PM | 프로젝트 관리자가 주요 기술 혁신을 위한 프로그램의 일부로 프로젝트를 감독하고 있다. 팀은 과거 조직 내 다양한 프로젝트에서 일한 경험이 있는 우수한 젊은 전문가들로 구성되어 있다. 그러나 팀은 이전 프로젝트 실행 중 방향성 부재를 경험했으며 이번 프로젝트에서도 같은 문제가 발생할까 우려하고 있다. 이 문제가 발생하지 않도록 프로젝트 관리자가 취해야 할 두 가지 조치는? (2개 선택) | 프로젝트에 대한 명확한 비전을 설정하고 모든 이해관계자에게 보이도록 한다. | 팀에게 브레인스토밍 세션을 진행하고 완화 계획을 제공하도록 권장한다. | 팀이 프로젝트 방향에 참여하고 집중하도록 유지한다. | 자원 관리 계획에 집중하고 프로젝트 진행 상황을 추적한다. | 팀 빌딩 활동을 조직하고 외부 관리자를 초청하여 팀에게 강연하게 한다. | C, E | 뛰어난 팀원들이 과거 경험으로 방향성 부재를 우려할 때, PM은 두 가지 조치를 취해야 한다: 팀이 프로젝트 방향에 참여하고 집중하도록 유지하고(C), 팀 결속 활동을 조직하고 외부 관리자를 초청하여 팀에게 강연하게 한다(E). 지속적 참여는 프로젝트 목표에 대한 집중을 보장하고, 외부 관점을 통한 팀 결속은 자신감과 응집력을 구축한다. 명확한 비전 설정(A)은 가치 있지만 참여를 지속시키지 못하는 일회성 조치이다. 완화 계획 브레인스토밍(B)은 능동적이지 않고 반응적이다. 자원 관리와 추적에 집중(D)은 행정적이며 팀의 방향성 우려를 해결하지 않는다.
9 | A project manager is leading a long-term project, executed in stages, to set up a complex communications network in many rural areas. The project is being executed in stages. What should the project manager do to ensure that monetized business value is generated as planned? | Evaluate the net promoter score (NPS) benefits against the project business plan | Evaluate the generated benefits at project milestones against the project business plan | Compare the benefits of the throughput analysis against the project business plan | Compare the estimate to complete (ETC) benefits against the project business plan |  | B | In a long-term, multi-stage project to set up a complex communications network, the project manager should evaluate generated benefits at project milestones against the project business plan. This ensures continuous alignment between project delivery and intended business value at key decision points throughout the project lifecycle. Comparing estimate to complete benefits (A) focuses on cost/time remaining, not realized value. Comparing throughput analysis benefits (C) is a lean metric not directly tied to business value realization. Evaluating the net promoter score (D) measures customer satisfaction but may not correlate directly with monetized business value. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Lean | Business Environment | Define and Establish Governance | Schedule | Monitoring & Controlling | Focus on Value | Control Schedule | Traditional PM | 프로젝트 관리자가 여러 농촌 지역에 복잡한 통신 네트워크를 구축하는 장기 프로젝트를 단계별로 이끌고 있다. 프로젝트 관리자는 계획대로 화폐화된 비즈니스 가치가 창출되고 있는지 확인하기 위해 무엇을 해야 하는가? | NPS(순추천지수) 혜택을 프로젝트 비즈니스 계획과 비교 평가한다. | 프로젝트 마일스톤에서 창출된 혜택을 프로젝트 비즈니스 계획과 비교 평가한다. | 처리량 분석의 혜택을 프로젝트 비즈니스 계획과 비교한다. | ETC(완료 시 추정치) 혜택을 프로젝트 비즈니스 계획과 비교한다. |  | B | 장기적, 다단계 통신 네트워크 구축 프로젝트에서, 프로젝트 관리자는 프로젝트 마일스톤에서 창출된 혜택을 프로젝트 비즈니스 계획과 비교 평가해야 한다. 이는 프로젝트 수명주기 전반의 핵심 의사결정 시점에서 프로젝트 납품과 의도한 비즈니스 가치 간의 지속적인 정렬을 보장한다. ETC 혜택 비교(A)는 비용/남은 시간에 초점을 맞추며 실현된 가치는 아니다. 처리량 분석 혜택 비교(C)는 린 지표로 비즈니스 가치 실현과 직접 연결되지 않는다. NPS 평가(D)는 고객 만족도를 측정하지만 화폐화된 비즈니스 가치와 직접 상관하지 않을 수 있다.
10 | A company's project management office (PMO) has been trying to implement an adaptive approach in the project management framework and a project manager has been asked to use adaptive tools in their next project. This is not the first time the request has been made and the previous project failed when adaptive tools were implemented. What should the project manager do? | Recommend to the PMO that it is not the right time to start implementing adaptive tools in projects | Conduct individual interviews with key stakeholders in order to understand all concerns, then prepare a communications management plan | Prepare a change request and seek approval from the steering committee regarding the new project framework | Bring in a third party company to develop and implement a hybrid framework for this specific project. |  | B | When the PMO asks for adaptive tool implementation after a previous failed attempt, the project manager should conduct individual interviews with key stakeholders to understand all concerns, then prepare a communications management plan. Understanding stakeholder concerns addresses the root causes of prior failure. Recommending against adaptive tools (A) avoids organizational direction. Preparing a change request for the steering committee (C) is procedural without stakeholder understanding. Bringing in a third-party company (D) is expensive and unnecessary. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Hybrid/Tailoring | 회사의 PMO가 프로젝트 관리 프레임워크에 적응형 접근법을 구현하려 하고 있으며, 프로젝트 관리자에게 다음 프로젝트에서 적응형 도구를 사용하도록 요청했다. 이 요청은 처음이 아니며, 이전 프로젝트에서 적응형 도구를 구현했을 때 실패했다. 프로젝트 관리자는 어떻게 해야 하는가? | PMO에 프로젝트에서 적응형 도구를 구현하기에 적절한 시기가 아니라고 권고한다. | 주요 이해관계자들과 개별 인터뷰를 수행하여 모든 우려사항을 파악한 후, 의사소통 관리 계획을 준비한다. | 새로운 프로젝트 프레임워크에 대해 운영위원회의 승인을 구하는 변경 요청을 준비한다. | 이 특정 프로젝트를 위한 하이브리드 프레임워크를 개발하고 구현할 제3자 회사를 투입한다. |  | B | 이전 실패 후 PMO가 적응형 도구 구현을 요청할 때, 프로젝트 관리자는 주요 이해관계자들과 개별 인터뷰를 수행하여 모든 우려사항을 파악한 후 의사소통 관리 계획을 준비해야 한다. 이해관계자 우려사항 파악은 이전 실패의 근본 원인을 다룬다. 적응형 도구에 반대 권고(A)는 조직의 방향을 회피한다. 운영위원회에 변경 요청(C)은 이해관계자 이해 없이 절차적이다. 제3자 회사 투입(D)은 비용이 많이 들고 불필요하다.
11 | A project manager just started managing agile projects. The project manager realizes that due to the lack of a clear definition of project objectives and definition of done (DoD), their colleague's projects have had many difficulties. Sponsors keep asking for more features and the projects have yet to be completed. What should the project manager do to avoid these issues? | Schedule meetings with key stakeholders to build the agile project charter and set clear expectations for the project | Convince the project sponsor to incorporate quality experts so the product can be tested and accepted as completed. | Arrange meetings to ensure every necessary task to complete the project is included in the project management plan | Convince the product owner to approach the team and look for options to find a solution to the problem |  | A | When previous projects failed due to lack of clear objectives and definition of done leading to endless feature requests, the project manager should schedule meetings with key stakeholders to build the agile project charter and set clear expectations. The charter establishes vision, scope boundaries, and success criteria. Convincing the sponsor to add quality experts (B) addresses testing, not objectives. Ensuring tasks are in the plan (C) is detail-level, not strategic. Convincing the product owner to find solutions (D) is reactive. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 막 애자일 프로젝트 관리를 시작했다. 프로젝트 관리자는 명확한 프로젝트 목표와 DoD(완료 정의)의 부재로 동료의 프로젝트들이 많은 어려움을 겪었음을 인식했다. 스폰서들은 계속 더 많은 기능을 요청하고 프로젝트는 아직 완료되지 않았다. 이러한 문제를 피하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 주요 이해관계자들과 회의를 예약하여 애자일 프로젝트 헌장을 작성하고 프로젝트에 대한 명확한 기대치를 설정한다. | 프로젝트 스폰서에게 품질 전문가를 투입하여 제품을 테스트하고 완료로 승인받을 수 있도록 설득한다. | 프로젝트를 완료하기 위해 필요한 모든 작업이 프로젝트 관리 계획에 포함되도록 회의를 준비한다. | 제품 소유자에게 팀에 접근하여 문제 해결 방안을 찾도록 설득한다. |  | A | 명확한 목표와 DoD 부재로 끝없는 기능 요청이 발생하여 이전 프로젝트가 실패했을 때, 프로젝트 관리자는 주요 이해관계자들과 회의를 예약하여 애자일 프로젝트 헌장을 작성하고 명확한 기대치를 설정해야 한다. 헌장은 비전, 범위 경계, 성공 기준을 수립한다. 스폰서에게 품질 전문가 추가 설득(B)은 테스트를 다루지 목표는 다루지 않는다. 계획에 작업 포함 확인(C)은 세부 수준이며 전략적이지 않다. 제품 소유자에게 해결책 찾기 설득(D)은 사후 대응적이다.
12 | A project manager is leading a complex project. The team is being challenged with frequent, incremental, and uncontrolled changes to the project. What should the project manager do? | Establish a detailed schedule management plan. | Establish a detailed risk management plan. | Establish a detailed scope management plan. | Establish a detailed quality management plan. |  | C | When a project faces frequent, incremental, uncontrolled changes, the project manager should establish a detailed scope management plan. This defines how requirements are collected, how scope is validated, and—critically—how scope is controlled through formal change management. A schedule management plan (A) addresses timelines, not scope changes. A risk management plan (B) addresses uncertainty. A quality management plan (D) addresses standards and processes. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 관리자가 복잡한 프로젝트를 이끌고 있다. 팀은 빈번하고, 점진적이며, 통제되지 않는 변경에 도전받고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 상세한 일정 관리 계획을 수립한다. | 상세한 리스크 관리 계획을 수립한다. | 상세한 범위 관리 계획을 수립한다. | 상세한 품질 관리 계획을 수립한다. |  | C | 프로젝트가 빈번하고, 점진적이며, 통제되지 않는 변경에 직면할 때, 프로젝트 관리자는 상세한 범위 관리 계획을 수립해야 한다. 이는 요구사항을 어떻게 수집하고, 범위를 어떻게 검증하며, 특히 공식적인 변경 관리를 통해 범위를 어떻게 통제하는지를 정의한다. 일정 관리 계획(A)은 일정을 다루며 범위 변경은 아니다. 리스크 관리 계획(B)은 불확실성을 다룬다. 품질 관리 계획(D)은 표준과 프로세스를 다룬다.
13 | A project using a hybrid approach to migrate from a current system to a new and enhanced system is underway. The plan is to migrate the system in stages. However, the operations team is complaining that they are not ready to start supporting the new system. How should the project manager effectively approach this situation? | Change the project management plan to add a final stage for product handoff to the operations team. | Prepare detailed documentation to be shared with the operations team during project closure. | Create a lessons learned register to include operations team training for future projects. | Include knowledge transfer sessions between the project and operations teams at every stage. |  | D | When the operations team is not ready to support a new system being migrated in stages using a hybrid approach, the project manager should include knowledge transfer sessions between the project and operations teams at every stage. Continuous knowledge transfer builds readiness throughout. Creating a lessons learned register (C) is retrospective. Changing the plan for a final handoff stage (A) is too late. Preparing documentation at closure (B) does not ensure operational readiness. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Closing | Build an Empowered Culture | Close Project or Phase | Hybrid/Tailoring | 현재 시스템에서 새롭고 향상된 시스템으로의 마이그레이션을 위해 하이브리드 접근법을 사용하는 프로젝트가 진행 중이다. 계획은 시스템을 단계별로 마이그레이션하는 것이다. 그러나 운영팀은 새로운 시스템을 지원할 준비가 되지 않았다고 불만을 제기하고 있다. 프로젝트 관리자는 이 상황에 어떻게 효과적으로 접근해야 하는가? | 운영팀에 제품 인도를 위한 최종 단계를 추가하도록 프로젝트 관리 계획을 변경한다. | 프로젝트 종료 시 운영팀과 공유할 상세 문서를 준비한다. | 향후 프로젝트를 위해 운영팀 교육을 포함하는 교훈 등록부를 작성한다. | 매 단계마다 프로젝트팀과 운영팀 간 지식 이전 세션을 포함한다. |  | D | 하이브리드 접근법으로 단계별 마이그레이션 중인 프로젝트에서 운영팀이 새 시스템을 지원할 준비가 되지 않았을 때, 프로젝트 관리자는 매 단계마다 프로젝트팀과 운영팀 간 지식 이전 세션을 포함해야 한다. 지속적인 지식 이전이 전반에 걸쳐 준비도를 구축한다. 교훈 등록부 작성(C)은 회고적이다. 최종 인도 단계를 위한 계획 변경(A)은 너무 늦다. 종료 시 문서 준비(B)는 운영 준비도를 보장하지 않는다.
14 | A company has appointed a supplier to deliver software and has assigned an internal project manager. The supplier states that no technical development or testing is required from the customer. The project manager would like to confirm this with all of the stakeholders. What should the internal project manager do first? | Develop a user acceptance testing plan to ensure the quality of the deliverables. | Host an alignment session with stakeholders to formalize the project requirements. | Communicate to the supplier that customer testing is required. | Distribute the project plan to all of the interested parties. |  | B | When a supplier claims no customer testing is required but the PM wants stakeholder confirmation, the first step should be to host an alignment session with stakeholders to formalize project requirements. This ensures all parties have a common understanding of scope, responsibilities, and deliverables before proceeding. Developing a UAT plan (A) is premature without first confirming requirements. Communicating testing requirements to the supplier (C) assumes the outcome before stakeholder alignment. Distributing the project plan (D) is informational but does not actively verify requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 회사가 소프트웨어 납품을 위해 공급업체를 선정하고 내부 프로젝트 관리자를 배정했다. 공급업체는 고객 측에서 기술 개발이나 테스트가 필요하지 않다고 명시했다. 프로젝트 관리자는 모든 이해관계자와 이를 확인하고 싶다. 내부 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 산출물의 품질을 보장하기 위한 UAT(사용자 수용 테스트) 계획을 수립한다. | 이해관계자들과 정렬 세션을 개최하여 프로젝트 요구사항을 공식화한다. | 공급업체에게 고객 테스트가 필요하다고 통보한다. | 프로젝트 계획을 모든 이해관계자에게 배포한다. |  | B | 공급업체가 고객 테스트가 필요 없다고 주장하지만 PM이 이해관계자 확인을 원할 때, 첫 번째 단계는 이해관계자들과 정렬 세션을 개최하여 프로젝트 요구사항을 공식화하는 것이다. 이는 모든 당사자가 범위, 책임, 산출물에 대해 공통된 이해를 갖도록 보장한다. UAT 계획 수립(A)은 요구사항 확인 전에 시기상조이다. 공급업체에 테스트 요구 통보(C)는 이해관계자 정렬 전에 결과를 가정한다. 프로젝트 계획 배포(D)는 정보 전달일 뿐 요구사항을 적극적으로 검증하지 않는다.
15 | A scrum master is receiving conflicting status updates for the same task. How should an accurate status be obtained from the team? | Review the deliverable carefully and determine the right status | Encourage team members to work together | Establish a clear definition of done (DoD) for each task | Assign one person to be responsible for the task |  | C | A clear Definition of Done (DoD) ensures the entire team shares a common understanding of what 'complete' means. Conflicting status updates for the same task typically indicate team members have different completion criteria. Establishing and consistently applying a clear DoD resolves ambiguity, produces accurate status updates, and reduces conflicts about task completion. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 스크럼 마스터가 같은 작업에 대해 상충되는 상태 업데이트를 받고 있다. 팀으로부터 정확한 상태를 어떻게 얻어야 하는가? | 산출물을 주의 깊게 검토하고 올바른 상태를 판단한다. | 팀원들이 함께 작업하도록 권장한다. | 각 작업에 대한 명확한 DoD(완료 정의)를 수립한다. | 한 사람을 작업 담당자로 지정한다. |  | C | 명확한 DoD는 팀 전체가 '완료'의 의미에 대해 공통된 이해를 공유하도록 보장한다. 같은 작업에 대한 상충되는 상태 업데이트는 일반적으로 팀원들이 서로 다른 완료 기준을 가지고 있음을 나타낸다. 명확한 DoD를 수립하고 일관되게 적용하면 모호성이 해소되고, 정확한 상태 업데이트가 산출되며, 작업 완료에 대한 갈등이 줄어든다.
16 | A company is helping their client launch an innovative product. During the sprint review, the product owner identifies that the product does not include key features that were previously prioritized as part of the product backlog. What should the project manager do next? | Initiate the change request process to include these missing features. | Collaborate with the product owner and the team to plan the following sprint | Inform the product owner that this issue needs to be escalated to the executive level. | Extend the sprint timeline so the learn can work on the missing feature. |  | B | When the product owner identifies missing key features during the sprint review that were previously in the backlog, the project manager should collaborate with the product owner and team to plan the following sprint. Sprint planning addresses what to deliver next. Initiating a formal change request (A) is not standard in agile. Escalating to the executive level (C) is unnecessary. Extending the sprint timeline (D) violates time-boxing. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 회사가 고객의 혁신 제품 출시를 돕고 있다. 스프린트 리뷰 중 제품 소유자가 제품에 이전에 제품 백로그의 일부로 우선순위가 매겨졌던 핵심 기능이 포함되어 있지 않음을 확인했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 누락된 기능을 포함하기 위한 변경 요청 프로세스를 시작한다. | 제품 소유자 및 팀과 협력하여 다음 스프린트를 계획한다. | 제품 소유자에게 이 문제를 경영진 수준으로 에스컬레이션해야 한다고 알린다. | 팀이 누락된 기능을 작업할 수 있도록 스프린트 일정을 연장한다. |  | B | 스프린트 리뷰 중 제품 소유자가 이전에 백로그에 있던 누락된 핵심 기능을 확인했을 때, 프로젝트 관리자는 제품 소유자 및 팀과 협력하여 다음 스프린트를 계획해야 한다. 스프린트 계획은 다음에 무엇을 납품할지 다룬다. 공식적인 변경 요청 시작(A)은 애자일에서 표준이 아니다. 경영진 수준으로 에스컬레이션(C)은 불필요하다. 스프린트 일정 연장(D)은 타임박싱을 위반한다.
17 | A project manager works for a company that has a reputation of delivering environmentally sustainable projects. During the half-yearly review of the project, the project manager raises serious concerns with the project sponsor regarding the project's viability and success. There are some stakeholders who oppose this project on the grounds of compromising land erosion. What should the project manager do? | Calculate earned value (EV) because the project manager is forecasting a loss for this project in the yearly review. | Request additional resources from the business unit manager due to the project ' s complexity. | Propose to close the project because it no longer fits the business values of the organization. | Calculate float on the project because it has severely affected the project ' s major critical path. |  | C | When stakeholders oppose a project on environmental grounds and the project manager has viability concerns for a company known for sustainable projects, the project manager should propose to close the project because it no longer fits the business values. Alignment with organizational values is paramount. Calculating earned value (A) assesses financial performance, not alignment. Requesting additional resources (B) does not address stakeholder opposition. Calculating float (D) addresses schedule, not viability. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Governance | Executing | Integrate Sustainability | Direct and Manage Project Work | Sustainability | 프로젝트 관리자가 환경적으로 지속 가능한 프로젝트를 납품하는 것으로 유명한 회사에서 일하고 있다. 프로젝트 반기 검토 중 프로젝트 관리자는 프로젝트의 실행 가능성과 성공에 대해 프로젝트 스폰서에게 심각한 우려를 제기했다. 토양 침식을 약화시킨다는 이유로 이 프로젝트에 반대하는 이해관계자들이 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 관리자가 연간 검토에서 이 프로젝트의 손실을 예측하고 있으므로 EV(획득가치)를 계산한다. | 프로젝트의 복잡성으로 인해 사업부 관리자에게 추가 자원을 요청한다. | 프로젝트가 더 이상 조직의 비즈니스 가치에 부합하지 않으므로 프로젝트 종료를 제안한다. | 프로젝트의 주요 크리티컬 패스에 심각한 영향을 주었으므로 여유 기간(Float)을 계산한다. |  | C | 이해관계자들이 환경적 이유로 프로젝트에 반대하고 프로젝트 관리자가 실행 가능성에 우려를 가지며, 지속 가능한 프로젝트로 유명한 회사일 때, 프로젝트 관리자는 프로젝트가 더 이상 조직의 비즈니스 가치에 부합하지 않으므로 종료를 제안해야 한다. 조직 가치와의 정렬이 가장 중요하다. EV 계산(A)은 재무 성과를 평가하며 정렬은 아니다. 추가 자원 요청(B)은 이해관계자 반대를 다루지 않는다. 여유 기간 계산(D)은 일정을 다루며 실행 가능성은 아니다.
18 | A project manager just completed a successful deployment and is preparing to transition the project to an operational state before starting closeout actions. What should the project manager do to ensure that the project is ready to move to an operational state? | Refer to the project's work in progress (WIP) reports to ensure that there is no additional work in the backlog. | Meet with the project team to review the work breakdown structure (WBS) and confirm deliverables have been delivered. | Review the project approval requirements in the project charter and confirm who will be approving the project. | Develop a plan to repay the technical debt incurred during the project and ensure that the project sponsor agrees with the plan. |  | B | When transitioning a project to an operational state after deployment, the project manager should meet with the team to review the WBS and confirm all deliverables have been delivered. Verification ensures completeness. Checking WIP reports (A) may miss completed items. Reviewing charter approval requirements (C) addresses governance, not deliverable completion. Developing a technical debt plan (D) addresses code quality, not transition readiness. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | WBS/Decomposition | Process | Develop and Manage Scope | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 프로젝트 관리자가 성공적인 배포를 완료하고 종료 조치를 시작하기 전에 프로젝트를 운영 상태로 전환할 준비를 하고 있다. 프로젝트가 운영 상태로 전환할 준비가 되었는지 확인하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트의 WIP(진행 중 작업) 보고서를 참조하여 백로그에 추가 작업이 없는지 확인한다. | 프로젝트 팀과 만나 WBS(작업분류체계)를 검토하고 산출물이 납품되었는지 확인한다. | 프로젝트 헌장의 프로젝트 승인 요구사항을 검토하고 누가 프로젝트를 승인할지 확인한다. | 프로젝트 중 발생한 기술 부채를 상환할 계획을 수립하고 프로젝트 스폰서가 계획에 동의하도록 한다. |  | B | 배포 후 프로젝트를 운영 상태로 전환할 때, 프로젝트 관리자는 팀과 만나 WBS를 검토하고 모든 산출물이 납품되었는지 확인해야 한다. 검증은 완전성을 보장한다. WIP 보고서 확인(A)은 완료된 항목을 놓칠 수 있다. 헌장 승인 요구사항 검토(C)는 거버넌스를 다루며 산출물 완료는 아니다. 기술 부채 계획 수립(D)은 코드 품질을 다루며 전환 준비도는 아니다.
19 | A key stakeholder for a construction project has been spending a lot of time at the site and interrupting the team's efforts. What should the project manager do in this situation? | Arrange an ad hoc meeting to address the key stakeholder ' s concerns with team members | Escalate the situation to the project sponsor because the key stakeholder ' s behavior is impacting progress | Work to understand the key stakeholder ' s concerns and provide feedback in regular project status reports | Reinforce with the key stakeholder that the project is performing on schedule\ |  | C | When a key construction stakeholder is spending excessive time at the site and interrupting the team, the project manager should work to understand the stakeholder's concerns and provide feedback in regular status reports. Addressing underlying concerns reduces interruptions. Arranging an ad hoc meeting (A) reacts without understanding. Escalating to the sponsor (B) is premature. Reinforcing schedule performance (D) does not address the stakeholder's real concerns. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 건설 프로젝트의 핵심 이해관계자가 현장에서 많은 시간을 보내며 팀의 업무를 방해하고 있다. 이 상황에서 프로젝트 관리자는 어떻게 해야 하는가? | 팀원들과 함께 핵심 이해관계자의 우려사항을 다루기 위한 임시 회의를 마련한다. | 핵심 이해관계자의 행동이 진행에 영향을 미치고 있으므로 프로젝트 스폰서에게 상황을 에스컬레이션한다. | 핵심 이해관계자의 우려사항을 파악하고 정기 프로젝트 상태 보고서에서 피드백을 제공한다. | 핵심 이해관계자에게 프로젝트가 일정대로 수행되고 있음을 재확인한다. |  | C | 건설 현장의 핵심 이해관계자가 과도한 시간을 보내며 팀을 방해할 때, 프로젝트 관리자는 이해관계자의 우려사항을 파악하고 정기 상태 보고서에서 피드백을 제공해야 한다. 근본적인 우려사항 해결이 방해를 줄인다. 임시 회의 마련(A)은 이해 없이 반응하는 것이다. 스폰서에게 에스컬레이션(B)은 시기상조이다. 일정 성과 재확인(D)은 이해관계자의 실제 우려사항을 다루지 않는다.
20 | During a project planning phase, the project manager realizes that project performance will be measured based on budget deviation and revenue, but without consideration for the overall project schedule. What should the project manager do? | Develop a lime. cost, and scope tracking method exclusively for this project. | Adopt a formal change management process for the project | Review and update the project schedule according to performance | Review the schedule baseline and consider adopting a schedule performance indicator |  | D | When project performance measurement excludes schedule consideration, the project manager should review the schedule baseline and consider adopting a schedule performance indicator. Adding schedule tracking ensures balanced performance measurement. Developing an exclusive time-cost-scope tracking method (A) reinvents existing frameworks. Adopting a formal change management process (B) addresses changes, not measurement gaps. Reviewing and updating the schedule per performance (C) is corrective but does not establish a measurement indicator. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Baseline & Change Control | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 계획 단계에서 프로젝트 관리자는 프로젝트 성과가 예산 편차와 매출을 기준으로 측정되지만 전체 프로젝트 일정은 고려되지 않는다는 것을 인식했다. 프로젝트 관리자는 어떻게 해야 하는가? | 이 프로젝트를 위한 시간, 비용, 범위 추적 방법을 독자적으로 개발한다. | 프로젝트에 대한 공식적인 변경 관리 프로세스를 채택한다. | 성과에 따라 프로젝트 일정을 검토하고 업데이트한다. | 일정 기준선을 검토하고 SPI(일정성과지수) 도입을 고려한다. |  | D | 프로젝트 성과 측정에서 일정이 고려되지 않을 때, 프로젝트 관리자는 일정 기준선을 검토하고 SPI 도입을 고려해야 한다. 일정 추적 추가는 균형 잡힌 성과 측정을 보장한다. 독자적인 시간-비용-범위 추적 방법 개발(A)은 기존 프레임워크를 재발명한다. 공식적 변경 관리 프로세스 채택(B)은 변경을 다루며 측정 격차는 아니다. 성과에 따른 일정 검토 및 업데이트(C)는 시정적이지만 측정 지표를 수립하지는 않는다.
21 | During a project to develop a new pharmaceutical product, the project manager was informed that there has been a change in government regulations regarding the materials of the project. What should the project manager do? | Update the contingency plan to take this issue into account. | Meet with the stakeholders to update the risk register and risk management plan. | Review the procurement documentation and modify requirements as needed. | Study the new regulations with the team and evaluate if there is any impact on theproject variables. |  | D | When government regulations change regarding project materials during pharmaceutical product development, the project manager should study the new regulations with the team and evaluate impact on project variables. Impact assessment enables informed response. Updating the contingency plan (A) is premature without evaluation. Meeting stakeholders to update the risk register (B) is reactive. Reviewing procurement documentation (C) is narrow. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 신약 제품 개발 프로젝트 중 프로젝트 관리자는 프로젝트 재료에 대한 정부 규정이 변경되었다는 통보를 받았다. 프로젝트 관리자는 어떻게 해야 하는가? | 이 문제를 고려하여 우발사태 계획을 업데이트한다. | 이해관계자들과 만나 리스크 등록부와 리스크 관리 계획을 업데이트한다. | 조달 문서를 검토하고 필요에 따라 요구사항을 수정한다. | 팀과 함께 새로운 규정을 연구하고 프로젝트 변수에 영향이 있는지 평가한다. |  | D | 제약 제품 개발 중 프로젝트 재료에 대한 정부 규정이 변경되었을 때, 프로젝트 관리자는 팀과 함께 새로운 규정을 연구하고 프로젝트 변수에 대한 영향을 평가해야 한다. 영향 평가가 정보에 기반한 대응을 가능하게 한다. 우발사태 계획 업데이트(A)는 평가 없이 시기상조이다. 이해관계자들과 만나 리스크 등록부 업데이트(B)는 사후 대응적이다. 조달 문서 검토(C)는 범위가 좁다.
22 | A company recently used desktop research for a feasibility study, which showed that the project is behind schedule. The project team also has concerns about the impact of scope changes on the project schedule. What should the project manager do to keep the project on schedule while still meeting project objectives? | Update the scope and add more resources to the project | Submit a change request to the CCB and update the schedule | Update the scope and move on to the next project milestone | Collaborate with the change control board (CCB) to review the scope and submit any change requests |  | D | When a feasibility study shows the project is behind schedule and the team is concerned about scope changes, the project manager should collaborate with the change control board (CCB) to review the scope and submit any change requests. Formal change control ensures scope changes are evaluated and authorized while keeping the project aligned with objectives. Updating the scope and adding resources (A) bypasses governance. Submitting a change request and updating the schedule (B) does not include CCB collaboration. Updating scope and moving to the next milestone (C) ignores the schedule impact. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 회사가 최근 실현 가능성 조사를 위한 데스크톱 리서치를 사용했는데, 프로젝트가 일정보다 지연되고 있음을 보여주었다. 프로젝트 팀도 범위 변경이 프로젝트 일정에 미치는 영향에 대해 우려하고 있다. 프로젝트 목표를 충족하면서 프로젝트를 일정에 맞추기 위해 프로젝트 관리자는 어떻게 해야 하는가? | 범위를 업데이트하고 프로젝트에 더 많은 자원을 추가한다. | CCB에 변경 요청을 제출하고 일정을 업데이트한다. | 범위를 업데이트하고 다음 프로젝트 마일스톤으로 넘어간다. | CCB와 협력하여 범위를 검토하고 변경 요청을 제출한다. |  | D | 실현 가능성 조사에서 프로젝트가 일정 지연이고 팀이 범위 변경을 우려할 때, 프로젝트 관리자는 CCB와 협력하여 범위를 검토하고 변경 요청을 제출해야 한다. 공식적 변경 통제는 범위 변경이 평가되고 승인되어 프로젝트가 목표와 정렬되도록 보장한다. 범위 업데이트 및 자원 추가(A)는 거버넌스를 우회한다. 변경 요청 제출 및 일정 업데이트(B)는 CCB 협력을 포함하지 않는다. 범위 업데이트 후 다음 마일스톤 이동(C)은 일정 영향을 무시한다.
23 | A project manager is using a centralized management and leadership style for a project. The project design does not meet the expected outcomes at later stages of the project. What is the most important action the project manager should have taken to prevent this? | Engaged with the design leader to quantify the requirements. | Empowered the project team to define the scope prior to execution. | Created a procurement plan that was approved by the sponsor. | Provided the equipment vendor with accurate specifications. |  | B | When a centralized management style leads to design that does not meet expected outcomes, the most important preventive action would have been to empower the project team to define the scope prior to execution. Centralized management can limit collaboration, ownership, and input from those closest to the work. Empowering the team improves scope clarity, shared understanding, and alignment with expected results. Engaging the design leader to quantify requirements (A) is too narrow. Creating an approved procurement plan (C) addresses procurement, not design quality. Providing the vendor with accurate specifications (D) focuses on one supplier relationship rather than the broader team engagement issue. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 프로젝트에 중앙집권적 관리 및 리더십 스타일을 사용하고 있다. 프로젝트 설계가 후반 단계에서 예상된 결과를 충족하지 못한다. 이를 방지하기 위해 프로젝트 관리자가 취했어야 할 가장 중요한 조치는 무엇인가? | 설계 리더와 협력하여 요구사항을 정량화했다. | 실행 전에 프로젝트 팀에게 범위를 정의할 권한을 부여했다. | 스폰서가 승인한 조달 계획을 작성했다. | 장비 공급업체에 정확한 사양을 제공했다. |  | B | 중앙집권적 관리 스타일로 인해 설계가 예상 결과를 충족하지 못할 때, 가장 중요한 예방 조치는 실행 전에 프로젝트 팀에게 범위를 정의할 권한을 부여하는 것이었다. 중앙집권적 관리는 협업, 주인의식, 작업에 가장 가까운 사람들의 입력을 제한할 수 있다. 팀에게 권한을 부여하면 범위 명확성, 공유 이해, 예상 결과와의 정렬이 향상된다. 설계 리더와 요구사항 정량화 협력(A)은 범위가 너무 좁다. 승인된 조달 계획 작성(C)은 조달을 다루며 설계 품질은 아니다. 공급업체에 정확한 사양 제공(D)은 하나의 공급업체 관계에 초점을 맞추며 광범위한 팀 참여 문제는 다루지 않는다.
24 | A team is delivering features to a customer at every iteration. After completing each iteration, the customer is invited for a review. However, the customer is frequently not available and the review is often delayed, which results in increased rework for the team. What should the project manager do? | Request the customer to clarify all requirements at the start of each iteration. | Plan ahead and define the best way to review the deliverables with the customer. | Ask the customer to review the deliverables in each iteration based on their availability. | Include the customer in daily project activities to gain the required guidance. |  | B | When a customer is frequently unavailable for iteration reviews, causing delays and rework, the project manager should plan ahead and define the best way to review deliverables with the customer. This proactive approach establishes a review process that accommodates the customer's availability—such as advance scheduling, fixed time slots, or asynchronous feedback methods. Requesting requirement clarification at iteration start (A) does not address the review availability issue. Asking the customer to review based on availability (C) is reactive. Including the customer in daily activities (D) is excessive and impractical. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 팀이 매 이터레이션마다 고객에게 기능을 납품하고 있다. 각 이터레이션 완료 후 고객을 리뷰에 초대한다. 그러나 고객이 자주 참석할 수 없어 리뷰가 종종 지연되며, 이로 인해 팀의 재작업이 증가하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 각 이터레이션 시작 시 고객에게 모든 요구사항을 명확히 해달라고 요청한다. | 사전에 계획을 세우고 고객과 산출물을 리뷰할 최선의 방법을 정의한다. | 고객의 가용성에 따라 각 이터레이션의 산출물을 리뷰해 달라고 요청한다. | 필요한 지침을 얻기 위해 고객을 일일 프로젝트 활동에 포함시킨다. |  | B | 고객이 이터레이션 리뷰에 자주 참석할 수 없어 지연과 재작업이 발생할 때, 프로젝트 관리자는 사전에 계획을 세우고 고객과 산출물을 리뷰할 최선의 방법을 정의해야 한다. 이 선제적 접근은 고객의 가용성을 수용하는 리뷰 프로세스를 수립한다. 이터레이션 시작 시 요구사항 명확화 요청(A)은 리뷰 가용성 문제를 다루지 않는다. 가용성 기반 리뷰 요청(C)은 사후 대응적이다. 일일 활동에 고객 포함(D)은 과도하고 비현실적이다.
25 | A project's planning process is finished, and all resources were budgeted for and approved by senior management. Just before the kickoff meeting, a member of the production department realizes that the plan does not meet the requirements for their area. What should the project manager have done during the planning process? | Distributed the resource estimates to all areas during the planning process | Included all functional managers in the planning process | Developed a good resource estimation in the planning process | Monitored the budget variations during the planning process |  | B | The correct answer is B. Included all functional managers in the planning process. Resource management includes ensuring team members have the necessary skills, tools, and support to perform their work effectively. The PM should identify gaps and take proactive steps to address them through training, mentoring, or other appropriate measures. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Scope | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트의 계획 프로세스가 완료되었고, 모든 자원이 예산에 포함되어 고위 경영진의 승인을 받았다. 킥오프 회의 직전, 생산부 직원이 계획이 자신의 영역의 요구사항을 충족하지 못한다는 것을 인식했다. 계획 프로세스 중 프로젝트 관리자가 했어야 할 것은 무엇인가? | 계획 프로세스 중 모든 영역에 자원 추정치를 배포했다. | 계획 프로세스에 모든 기능 관리자를 포함시켰다. | 계획 프로세스에서 좋은 자원 추정을 개발했다. | 계획 프로세스 중 예산 변동을 모니터링했다. |  | B | 정답은 B이다. 계획 프로세스에 모든 기능 관리자를 포함시켰다. 자원 관리는 팀원들이 업무를 효과적으로 수행하는 데 필요한 기술, 도구, 지원을 갖추도록 보장하는 것을 포함한다. PM은 격차를 파악하고 교육, 멘토링 또는 기타 적절한 조치를 통해 이를 선제적으로 해결해야 한다.
26 | Due to a recent budget reduction, two team members were released from an agile team. The customer is still expecting early results for the project. Which two actions should the project manager take to align customer expectations? (Choose two) | Review the impediments log with the customer. | Ask the product owner to review the prioritized backlog with the customer. | Ask the agile team to review and update the quality management plan with thecustomer. | Ask the agile team to review the updated sprint velocity with the customer. | Send a detailed project management plan to the customer. | D, E | When two team members are released due to budget cuts and the customer expects early results, the project manager should take two actions: ask the agile team to review the updated sprint velocity with the customer (D) to transparently show the capacity impact, and send a detailed project management plan to the customer (E) to provide comprehensive visibility into the adjusted timeline and deliverables. Reviewing velocity manages expectations with data, while providing the detailed plan gives the customer full context for revised planning. Reviewing the impediments log with the customer (A) exposes internal issues inappropriately. Asking the product owner to review the prioritized backlog (B) is useful internally but may overwhelm the customer with backlog details. Reviewing the quality management plan (C) is unrelated to the capacity issue. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 최근 예산 삭감으로 인해 애자일 팀에서 두 명의 팀원이 방출되었다. 고객은 여전히 프로젝트의 조기 결과를 기대하고 있다. 고객 기대치를 정렬하기 위해 프로젝트 관리자가 취해야 할 두 가지 조치는? (2개 선택) | 고객과 함께 장애물 로그를 검토한다. | 제품 소유자에게 고객과 함께 우선순위가 지정된 백로그를 검토하도록 요청한다. | 애자일 팀에게 고객과 함께 품질 관리 계획을 검토하고 업데이트하도록 요청한다. | 애자일 팀에게 고객과 함께 업데이트된 스프린트 벨로시티를 검토하도록 요청한다. | 고객에게 상세한 프로젝트 관리 계획을 보낸다. | D, E | 예산 삭감으로 두 명의 팀원이 방출되고 고객이 조기 결과를 기대할 때, PM은 두 가지 조치를 취해야 한다: 애자일 팀에게 고객과 업데이트된 스프린트 벨로시티를 검토하도록 요청하여(D) 역량 영향을 투명하게 보여주고, 고객에게 상세한 프로젝트 관리 계획을 전송하여(E) 수정된 일정과 산출물에 대한 포괄적 가시성을 제공한다. 벨로시티 검토는 데이터로 기대치를 관리하고, 상세 계획은 수정된 계획을 위한 전체 맥락을 제공한다. 장애물 로그 검토(A)는 내부 문제를 부적절하게 노출한다. 제품 소유자에게 백로그 검토 요청(B)은 내부적으로 유용하지만 고객에게 백로그 세부사항으로 부담을 줄 수 있다. 품질 관리 계획 검토(C)는 역량 문제와 무관하다.
27 | A year after implementing a policy change to improve diversity and inclusion within two teams, there is growing conflict within the company. What should have been done to prevent this conflict? | The critical departments in the organization should have been involved in this exercise | The organization should have introduced the concept of diversity broadly | The leadership team should have worked closely with the marketing team to get insight on diversity | Organization-wide diversity training should have been provided to the workforce |  | D | Diversity and inclusion extend beyond demographics—they require building a culture of respect, belonging, and empowerment. To prevent conflicts stemming from different backgrounds, perspectives, or preferences, the organization should provide training and education across the entire workforce, not just selected teams. This raises awareness, fosters mutual understanding, and promotes constructive behaviors. Proactive training helps the organization leverage the benefits of diversity—including enhanced innovation, stronger collaboration, and improved stakeholder satisfaction—while minimizing potential friction. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 두 팀의 다양성과 포용성을 개선하기 위한 정책 변경을 시행한 지 1년 후, 회사 내 갈등이 커지고 있다. 이 갈등을 방지하기 위해 무엇을 했어야 했는가? | 조직의 핵심 부서들이 이 활동에 참여했어야 했다. | 조직이 다양성 개념을 광범위하게 도입했어야 했다. | 리더십 팀이 마케팅 팀과 긴밀히 협력하여 다양성에 대한 인사이트를 얻었어야 했다. | 조직 전체에 다양성 교육이 제공되었어야 했다. |  | D | 다양성과 포용성은 인구통계를 넘어 존중, 소속감, 권한 부여의 문화를 구축하는 것을 요구한다. 다양한 배경, 관점, 선호에서 비롯되는 갈등을 방지하기 위해, 조직은 선택된 팀만이 아닌 전체 인력에게 교육을 제공해야 한다. 이는 인식을 높이고 상호 이해를 촉진하며 건설적 행동을 촉진한다.
28 | A project leader of an agile team realizes that one team member is unmotivated, which is affecting the whole team. What should the project leader do to improve the situation? | Send the unmotivated team member to another team. | Invest in developing the team ' s emotional intelligence. | Reduce the number of daily and retrospective meetings. | Ask the unmotivated team member to take a short leave. |  | B | When a team member's lack of motivation is affecting the entire agile team, the project leader should invest in developing the team's emotional intelligence. Emotional intelligence—the ability to perceive, understand, and manage one's own and others' emotions—fosters collaboration, trust, and communication within the team. This approach addresses the root cause rather than the symptom. Sending the team member to another team (A) removes the individual without resolving the underlying issue. Reducing the number of meetings (C) does not address the motivation problem. Asking the team member to take a leave (D) is avoidant and does not help improve their engagement. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 애자일 팀의 프로젝트 리더가 한 팀원의 동기 부족이 팀 전체에 영향을 미치고 있음을 인식했다. 상황을 개선하기 위해 프로젝트 리더는 어떻게 해야 하는가? | 동기 부족한 팀원을 다른 팀으로 보낸다. | 팀의 감성 지능 개발에 투자한다. | 데일리 및 회고 회의 횟수를 줄인다. | 동기 부족한 팀원에게 단기 휴가를 내도록 요청한다. |  | B | 팀원의 동기 부족이 애자일 팀 전체에 영향을 미칠 때, 프로젝트 리더는 팀의 감성 지능 개발에 투자해야 한다. 감성 지능—자신과 타인의 감정을 인식하고, 이해하고, 관리하는 능력—은 팀 내 협업, 신뢰, 의사소통을 촉진한다. 이 접근단은 증상이 아닌 근본 원인을 다룬다. 팀원을 다른 팀으로 보내는 것(A)은 근본적인 문제를 해결하지 않고 개인을 제거한다. 회의 횟수 감소(C)는 동기 문제를 다루지 않는다. 팀원에게 휴가 요청(D)은 회피적이며 참여 개선에 도움이 되지 않는다.
29 | A project team began working on a complex project that involves new technology as a product. The team is new to the technology and the proposed approach. Additionally, the customer is apprehensive about how the product will be received in the market. What should the project manager do to help the team and the customer? | Work closely with the marketing team on market research and product segments | Manage the risks associated with the proposed approach. | Assist the team with identifying the minimum viable product (MVP) to validate assumptions. | Coordinate with the business unit to get detailed requirements. |  | C | When the team is new to technology and the customer is apprehensive about market reception, the project manager should assist the team with identifying the MVP to validate assumptions. MVP development enables early feedback and reduces risk. Working with marketing on research (A) is one input but not the primary action. Managing risks (B) is ongoing but does not address team and customer needs directly. Getting detailed requirements from the business unit (D) delays value delivery. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 새로운 기술을 제품으로 하는 복잡한 프로젝트에 착수했다. 팀은 기술과 제안된 접근방식에 익숙하지 않다. 또한 고객은 제품이 시장에서 어떻게 받아들여질지 우려하고 있다. 팀과 고객을 돕기 위해 프로젝트 관리자는 어떻게 해야 하는가? | 마케팅 팀과 긴밀히 협력하여 시장 조사 및 제품 세그먼트를 진행한다. | 제안된 접근방식과 관련된 리스크를 관리한다. | 가정을 검증하기 위해 팀이 MVP(최소 기능 제품)를 식별하도록 지원한다. | 사업부와 협조하여 상세 요구사항을 확보한다. |  | C | 팀이 기술에 익숙하지 않고 고객이 시장 반응을 우려할 때, 프로젝트 관리자는 가정을 검증하기 위해 팀이 MVP를 식별하도록 지원해야 한다. MVP 개발은 조기 피드백을 가능하게 하고 리스크를 줄인다. 마케팅과 조사 협력(A)은 하나의 입력이지만 주요 조치는 아니다. 리스크 관리(B)는 지속적이지만 팀과 고객 요구를 직접 다루지 않는다. 사업부에서 상세 요구사항 확보(D)는 가치 전달을 지연시킨다.
30 | An agile team completes a deliverable that is to be certified by another expert team. The second team does not take the deliverable for many months. What should the servant leader do? | Review the process and remove the impediment | Remove the certification need from the project scope | Escalate this to the project director for a resolution | Escalate this to the agile lead of the second team |  | A | When a certifying team delays taking a completed deliverable for months, the servant leader should review the process and remove the impediment. In agile, the servant leader's core responsibility is to facilitate the team's work by identifying and removing obstacles that hinder progress. This may involve facilitating inter-team communication, adjusting processes, or finding alternative solutions. Removing the certification requirement from scope (B) eliminates a necessary quality gate. Escalating to the project director (C) or the agile lead of the second team (D) may become necessary but should follow the servant leader's own efforts to resolve the impediment. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 애자일 팀이 다른 전문가 팀이 인증해야 할 산출물을 완성했다. 두 번째 팀이 몇 달 동안 산출물을 인수하지 않고 있다. 서번트 리더는 어떻게 해야 하는가? | 프로세스를 검토하고 장애물을 제거한다. | 프로젝트 범위에서 인증 필요성을 제거한다. | 해결을 위해 프로젝트 디렉터에게 에스컬레이션한다. | 두 번째 팀의 애자일 리드에게 에스컬레이션한다. |  | A | 인증 팀이 완성된 산출물을 몇 달 동안 인수하지 않을 때, 서번트 리더는 프로세스를 검토하고 장애물을 제거해야 한다. 애자일에서 서번트 리더의 핵심 책임은 진행을 방해하는 장애물을 식별하고 제거하여 팀의 작업을 촉진하는 것이다. 범위에서 인증 요구사항 제거(B)는 필요한 품질 게이트를 제거한다. 프로젝트 디렉터(C)나 두 번째 팀의 애자일 리드(D)에게 에스컬레이션은 필요할 수 있지만 서번트 리더 자체의 장애물 해결 노력이 우선이다.
31 | Throughout an entire project, the project manager took notes at every meeting with team members. These notes provided useful insights from key stakeholders, which later resulted in increased value to the project. The project manager thought it would be helpful to keep these notes as a future reference for other project managers within the organization. Where should the notes be located? | Lessons learned | Enterprise environmental factors (EEFs) | Project management plan | Organizational process assets (OPAs) |  | D | When a project manager has valuable meeting notes with stakeholder insights that benefited the project, the notes should be stored as organizational process assets (OPAs). OPAs include historical information and knowledge bases for future reference. Lessons learned (A) capture retrospective insights, not ongoing notes. EEFs (B) are external factors. The project management plan (C) is project-specific. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Resources | Executing | Focus on Value | Acquire Resources | Traditional PM | 프로젝트 전체에 걸쳐 프로젝트 관리자는 팀원들과의 모든 회의에서 메모를 했다. 이 메모는 주요 이해관계자들로부터 유용한 인사이트를 제공했으며, 이로 인해 프로젝트의 가치가 증가했다. 프로젝트 관리자는 이 메모를 조직 내 다른 프로젝트 관리자들의 향후 참고 자료로 보관하는 것이 유용할 것이라 생각했다. 메모는 어디에 보관해야 하는가? | 교훈 사항(Lessons learned) | EEF(기업 환경 요인) | 프로젝트 관리 계획 | OPA(조직 프로세스 자산) |  | D | 프로젝트 관리자가 프로젝트에 도움이 된 이해관계자 인사이트가 담긴 가치 있는 회의 메모를 가지고 있을 때, 메모는 OPA로 저장해야 한다. OPA는 향후 참조를 위한 역사적 정보와 지식 기반을 포함한다. 교훈 사항(A)은 회고적 인사이트를 포착하며 지속적인 메모는 아니다. EEF(B)는 외부 요인이다. 프로젝트 관리 계획(C)은 프로젝트별 문서이다.
32 | A project manager for a construction site realizes the importance of stakeholder relations, especially with the local community. The project manager and the project team strive to build effective relationships with these key stakeholders in order to prevent obstacles in the future. What should the project manager do to customize the stakeholder engagement plan? | Assess the need to collaborate with the community | Analyze the need to negotiate with the community. | Assess the information requirements of the community | Analyze stakeholder diversity in the community. |  | C | To customize the stakeholder engagement plan for a construction project where community relations are critical, the project manager should assess the information requirements of the community. Understanding what information the community needs, how they prefer to receive it, and how frequently they need updates enables effective, targeted engagement. Assessing the need to collaborate (A) is too general. Analyzing the need to negotiate (B) assumes conflict. Analyzing stakeholder diversity (D) provides demographic insight but not specific information requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 건설 현장의 프로젝트 관리자가 이해관계자 관계, 특히 지역 커뮤니티와의 관계의 중요성을 인식하고 있다. 프로젝트 관리자와 팀은 향후 장애물을 방지하기 위해 이 핵심 이해관계자들과 효과적인 관계를 구축하려 노력하고 있다. 이해관계자 참여 계획을 맞춤화하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 커뮤니티와 협력할 필요성을 평가한다. | 커뮤니티와 협상할 필요성을 분석한다. | 커뮤니티의 정보 요구사항을 평가한다. | 커뮤니티의 이해관계자 다양성을 분석한다. |  | C | 커뮤니티 관계가 중요한 건설 프로젝트의 이해관계자 참여 계획을 맞춤화하기 위해, 프로젝트 관리자는 커뮤니티의 정보 요구사항을 평가해야 한다. 커뮤니티가 어떤 정보를 필요로 하는지, 어떤 방식으로 받기를 선호하는지, 얼마나 자주 업데이트가 필요한지 파악하면 효과적이고 목표적인 참여가 가능해진다. 협력 필요성 평가(A)는 너무 일반적이다. 협상 필요성 분석(B)은 갈등을 전제한다. 이해관계자 다양성 분석(D)은 인구통계적 인사이트를 제공하지만 구체적인 정보 요구사항은 아니다.
33 | During a standup meeting, a team member raises the issue that they have blockers and impediments preventing them from moving on to the next task. How should the project lead handle this situation? | Allocate the blockers and impediments to the product owner to resolve. | Add any blockers or impediments to the risk register, | Insist that the person who raised the blockers and impediments take ownership. | Support the team member by removing the blockers and impediments. |  | D | When a team member raises blockers and impediments during a standup meeting, the project lead should support the team member by removing the blockers and impediments. In agile methodologies, a core responsibility of the project lead or scrum master is to remove obstacles that prevent the team from progressing. Allocating blockers to the product owner (A) assigns them to the wrong role. Adding them to the risk register (B) documents them but does not resolve them. Insisting the person who raised them take ownership (C) undermines the servant leadership model. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 스탠드업 회의 중 팀원이 다음 작업으로 넘어가는 것을 방해하는 블로커와 장애물이 있다고 문제를 제기했다. 프로젝트 리드는 이 상황을 어떻게 처리해야 하는가? | 블로커와 장애물을 제품 소유자에게 해결하도록 할당한다. | 블로커나 장애물을 리스크 등록부에 추가한다. | 블로커와 장애물을 제기한 사람이 소유권을 가지도록 주장한다. | 팀원을 지원하여 블로커와 장애물을 제거한다. |  | D | 스탠드업 회의에서 팀원이 블로커와 장애물을 제기할 때, 프로젝트 리드는 팀원을 지원하여 블로커와 장애물을 제거해야 한다. 애자일 방법론에서 프로젝트 리드 또는 스크럼 마스터의 핵심 책임은 팀의 진행을 방해하는 장애물을 제거하는 것이다. 제품 소유자에게 블로커 할당(A)은 잘못된 역할에 배정한다. 리스크 등록부에 추가(B)는 문서화하지만 해결하지는 않는다. 제기자에게 소유권 주장(C)은 서번트 리더십 모델을 약화시킨다.
34 | During the execution of a project, the project manager notices that only one team member has one of the technical skills needed to build the product. The project manager is afraid this might have a future impact on the quality and schedule because most of the upcoming activities will require at least three people with this specific skill. What two actions should the project manager take to prevent the team from being unqualified? (Choose two) | Exclude the activities from the roadmap | Encourage working in pairs and knowledge sharing | Teach the entire team the new skill. | Facilitate a training event with an external trainer | Increase the time estimates on the activities that require such abilities | B, D | When only one team member has a critical technical skill needed for upcoming activities, the project manager should take two actions: encourage working in pairs and knowledge sharing to transfer the skill through collaboration, and facilitate a training event with an external trainer for formal skill development. Excluding activities from the roadmap (A) reduces scope. Teaching the entire team (C) may not be feasible. Increasing time estimates (E) delays the project without building capability. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 실행 중 프로젝트 관리자는 제품을 만드는 데 필요한 기술 중 하나를 가진 팀원이 한 명뿐임을 발견했다. 프로젝트 관리자는 향후 활동 대부분이 이 특정 기술을 가진 최소 3명을 필요로 하기 때문에 품질과 일정에 영향을 미칠 수 있다고 우려하고 있다. 팀이 자격 미달이 되지 않도록 프로젝트 관리자가 취해야 할 두 가지 조치는? (2개 선택) | 로드맵에서 해당 활동을 제외한다. | 페어 작업과 지식 공유를 장려한다. | 팀 전체에게 새로운 기술을 가르친다. | 외부 트레이너와 함께 교육 이벤트를 진행한다. | 해당 능력이 필요한 활동의 시간 추정치를 늘린다. | B, D | 핵심 기술 보유자가 한 명뿐일 때, PM은 두 가지 조치를 취해야 한다: 페어 작업과 지식 공유를 장려하여 협업을 통한 기술 이전을 촉진하고, 외부 트레이너와 함께 교육 이벤트를 진행하여 공식적인 역량 개발을 한다. 로드맵에서 활동 제외(A)는 범위를 줄인다. 팀 전체에게 가르치기(C)는 실현 가능하지 않을 수 있다. 시간 추정치 증가(E)는 역량 구축 없이 프로젝트를 지연시킨다.
35 | An agile team is in the early phases of the development cycle for a project; however, they have already begun delivering functionality to the customer. The team has identified risks to the project and are working on developing the mitigation strategy. What should the project manager do next? | Determine if any of the new risks have any financial impact. | Implement the risk mitigation strategy according to the highest impact. | Incorporate and prioritize the risks in the risk register according to impact. | Escalate the risk to the project sponsor and steering committee. |  | C | After identifying risks in an agile project, the next step is to record them in the risk register and prioritize them by their potential impact. This structured approach ensures the most critical risks receive attention first. Agile methodologies reinforce continuous risk review and management throughout the project lifecycle, treating risk management as an iterative process rather than a one-time activity. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 애자일 팀이 프로젝트 개발 주기의 초기 단계에 있지만 이미 고객에게 기능을 납품하기 시작했다. 팀은 프로젝트에 대한 리스크를 식별했으며 완화 전략을 개발하고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 새로운 리스크가 재무적 영향을 미치는지 판단한다. | 가장 큰 영향에 따라 리스크 완화 전략을 실행한다. | 리스크를 리스크 등록부에 영향도에 따라 통합하고 우선순위를 지정한다. | 리스크를 프로젝트 스폰서와 운영위원회에 에스컬레이션한다. |  | C | 애자일 프로젝트에서 리스크를 식별한 후 다음 단계는 리스크 등록부에 기록하고 잠재적 영향도에 따라 우선순위를 지정하는 것이다. 이 체계적 접근은 가장 중요한 리스크가 먼저 주목받도록 보장한다. 애자일 방법론은 프로젝트 수명주기 전반에 걸쳐 지속적인 리스크 검토와 관리를 강화하며, 리스크 관리를 일회성 활동이 아닌 반복적 프로세스로 취급한다.
36 | A project manager is assigned to work on a complex and innovative project. The technology being used and developed is new and complicated, and most of the stakeholders are unfamiliar with it. Which approach should the project manager use as a servant leader? | Escalate the issue with upper management to find a novel solution for this situation. | Allocate resources to provide training about the new technology to the stakeholders. | Ask stakeholders to find and self-fund education about this new technology. | Contact the project sponsor to get those stakeholders removed from the project. |  | B | As a servant leader, the PM should prioritize stakeholder and team development. When technology is new and complex, ensuring all stakeholders have sufficient understanding to make informed decisions is essential. Allocating resources for training reflects servant leadership principles—empowering and growing team members and stakeholders rather than making decisions on their behalf. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 복잡하고 혁신적인 프로젝트에 배정되었다. 사용되고 개발되는 기술이 새롭고 복잡하며, 대부분의 이해관계자가 이에 익숙하지 않다. 서번트 리더로서 프로젝트 관리자는 어떤 접근방식을 사용해야 하는가? | 상위 경영진에게 이슈를 에스컬레이션하여 새로운 해결책을 찾는다. | 이해관계자들에게 새로운 기술에 대한 교육을 제공하기 위해 자원을 배분한다. | 이해관계자들에게 새로운 기술에 대한 교육을 스스로 찾아서 자비로 받으라고 요청한다. | 프로젝트 스폰서에게 연락하여 해당 이해관계자들을 프로젝트에서 제거하도록 한다. |  | B | 서번트 리더로서 PM은 이해관계자와 팀의 개발을 우선시해야 한다. 기술이 새롭고 복잡할 때, 모든 이해관계자가 정보에 입각한 결정을 내릴 수 있도록 충분한 이해를 갖추게 하는 것이 필수적이다. 교육을 위한 자원 배분은 서번트 리더십 원칙—팀원과 이해관계자를 대신 결정하는 것이 아니라 역량을 강화하고 성장시키는 것—을 반영한다.
37 | A project is delayed due to an undelivered component, which was caused by a conflict between the procurement lead and the contracts manager. The project manager schedules a meeting with the two stakeholders to resolve the issue. What role does the project manager play in this situation? | Accommodator | Arbitrator | Mediator | Conciliator |  | C | When scheduling a meeting between two conflicting stakeholders to resolve a procurement issue causing project delay, the project manager plays the role of a mediator. A mediator facilitates discussion as a neutral third party to help reach a mutually acceptable solution. An accommodator (A) yields to others' demands. An arbitrator (B) makes binding decisions. A conciliator (D) acts as an informal go-between. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Traditional PM | 납품되지 않은 구성요소로 인해 프로젝트가 지연되었으며, 이는 조달 리드와 계약 관리자 간의 갈등으로 인해 발생했다. 프로젝트 관리자는 두 이해관계자와 회의를 잡아 이슈를 해결하려 한다. 이 상황에서 프로젝트 관리자는 어떤 역할을 하는가? | 수용자(Accommodator) | 중재자(Arbitrator) | 조정자(Mediator) | 화해자(Conciliator) |  | C | 프로젝트 지연을 초래한 조달 이슈를 해결하기 위해 갈등하는 두 이해관계자 간 회의를 잡을 때, 프로젝트 관리자는 조정자(Mediator) 역할을 한다. 조정자는 중립적인 제3자로서 상호 수용 가능한 해결책에 도달하도록 논의를 촉진한다. 수용자(A)는 타인의 요구에 양보한다. 중재자(B)는 구속력 있는 결정을 내린다. 화해자(D)는 비공식적인 중간 역할을 한다.
38 | A project manager is starting a project using a hybrid approach and notices some team members only have knowledge of predictive approaches. What does the project manager need to do first in order to have good project performance? | Deliver hybrid training to all team members | Assess the required training per team member. | Coach those team members lacking hybrid knowledge to learn on the job. | Change the team to include hybrid experts |  | B | When starting a hybrid project and some team members only have predictive knowledge, the project manager should first assess the required training per team member. This assessment identifies individual knowledge gaps and skills needs relative to the hybrid approach, enabling targeted and efficient training plans. Delivering broad hybrid training to everyone (A) may be inefficient if some already have the needed skills. Coaching on the job without assessment (C) lacks structure and may miss critical gaps. Changing the team to include hybrid experts (D) replaces team members rather than developing existing ones. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Align Stakeholder Expectations | Resources | Executing | Build an Empowered Culture | Acquire Resources | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 접근방식으로 프로젝트를 시작하고 있으며, 일부 팀원들이 예측형 접근방식에 대한 지식만 가지고 있음을 발견했다. 좋은 프로젝트 성과를 위해 프로젝트 관리자가 먼저 해야 할 일은? | 모든 팀원에게 하이브리드 교육을 실시한다. | 팀원별 필요한 교육을 평가한다. | 하이브리드 지식이 부족한 팀원들을 현장에서 배우도록 코칭한다. | 하이브리드 전문가를 포함하도록 팀을 변경한다. |  | B | 하이브리드 프로젝트를 시작할 때 일부 팀원이 예측형 지식만 가지고 있다면, PM은 먼저 팀원별 필요한 교육을 평가해야 한다. 이 평가는 하이브리드 접근방식에 대한 개인별 지식 격차와 기술 요구를 파악하여 효율적이고 목표 지향적인 교육 계획을 수립할 수 있게 한다. 모든 사람에게 광범위한 하이브리드 교육 실시(A)는 이미 필요한 기술을 가진 사람이 있으면 비효율적이다. 평가 없이 현장 코칭(C)은 구조가 부족하다. 하이브리드 전문가로 팀 변경(D)은 기존 팀원을 개발하지 않고 교체한다.
39 | A mandatory compliance requirement that will impact the project software is introduced during the execution phase of an iterative project. The team is aware of the compliance requirement. What should the project manager do next? | Escalate the issue of project impact to the product owner. | Update the product backlog item with this new requirement. | Update the stakeholder register to include the requirement owner. | Escalate the issue of project impact to the project sponsor. |  | D | When a mandatory compliance requirement impacts project software during execution of an iterative project, the project manager should update the product backlog item with the new requirement. The backlog is the living document for all requirements. Escalating to the PO (A) delegates instead of acting. Updating the stakeholder register (C) is administrative. Escalating to the sponsor (D) bypasses agile mechanisms. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 반복형 프로젝트의 실행 단계 중 프로젝트 소프트웨어에 영향을 미치는 의무적 컴플라이언스 요구사항이 도입되었다. 팀은 이 컴플라이언스 요구사항을 알고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 영향 이슈를 제품 소유자에게 에스컬레이션한다. | 이 새로운 요구사항으로 제품 백로그 항목을 업데이트한다. | 요구사항 소유자를 포함하도록 이해관계자 등록부를 업데이트한다. | 프로젝트 영향 이슈를 프로젝트 스폰서에게 에스컬레이션한다. |  | D | 반복형 프로젝트 실행 중 의무적 컴플라이언스 요구사항이 프로젝트 소프트웨어에 영향을 미칠 때, PM은 이 새로운 요구사항으로 제품 백로그 항목을 업데이트해야 한다. 백로그는 모든 요구사항을 위한 살아있는 문서이다. PO에게 에스컬레이션(A)은 행동 대신 위임한다. 이해관계자 등록부 업데이트(C)는 행정적이다. 스폰서에게 에스컬레이션(D)은 애자일 메커니즘을 우회한다.
40 | A project manager has two projects that are being executed at the same time. The duration of the critical project must be reduced, but the project manager does not have enough resources to achieve this goal. In addition, the schedule does not have activities that can be overlapped. What should the project manager do? | Use resource optimization to justify requesting more resources for the critical project. | Provide schedule optimization training to the project teams to improve their skills. | Apply fast-tracking techniques to compress the schedule of the critical project | Analyze both projects to determine the most effective use of common resources |  | D | When a critical project's duration must be reduced but resources are insufficient and fast-tracking is not possible, the project manager should analyze both projects to determine the most effective use of common resources. This allows optimal resource allocation and balancing across projects, potentially freeing resources for the critical project. Fast-tracking (C) is not possible since activities cannot be overlapped. Using resource optimization to request more resources (A) may not be realistic given constraints. Schedule optimization training (B) does not have immediate impact on the current situation. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 동시에 실행 중인 두 개의 프로젝트를 담당하고 있다. 중요 프로젝트의 기간을 단축해야 하지만 이 목표를 달성할 충분한 자원이 없다. 또한 일정에 겹칠 수 있는 활동이 없다. 프로젝트 관리자는 어떻게 해야 하는가? | 자원 최적화를 사용하여 중요 프로젝트에 대한 추가 자원 요청을 정당화한다. | 프로젝트 팀에게 일정 최적화 교육을 제공하여 기술을 향상시킨다. | 중요 프로젝트의 일정을 압축하기 위해 패스트트래킹 기법을 적용한다. | 두 프로젝트를 분석하여 공통 자원의 가장 효과적인 사용 방법을 결정한다. |  | D | 중요 프로젝트의 기간을 단축해야 하지만 자원이 부족하고 패스트트래킹이 불가능할 때, PM은 두 프로젝트를 분석하여 공통 자원의 가장 효과적인 사용 방법을 결정해야 한다. 이를 통해 프로젝트 간 최적의 자원 배분과 균형이 가능해지며, 중요 프로젝트에 자원을 확보할 수 있다. 패스트트래킹(C)은 활동을 겹칠 수 없으므로 불가능하다. 추가 자원 요청을 위한 자원 최적화(A)는 제약 조건에서 현실적이지 않을 수 있다. 일정 최적화 교육(B)은 현 상황에 즉각적인 영향이 없다.
41 | During execution of the third sprint in a project, a project team is uncertain about the frequent updates on the vendor's platform. The team is concerned about how the updates will impact the rest of the backlog. What should the project manager do to minimize the uncertainty? | Schedule a spike meeting, conduct risk assessments, and incorporate them into the backlog to help with risk mitigation. | Explain to the project team that the vendor ' s updates are something unpredictable, and the team must continue working on the project. | Schedule a retrospective meeting and conduct a risk assessment with the team, implementing mitigation tasks before the next sprint. | Speak with the vendor and explain that constant updates are impacting the project and request an action plan to minimize the changes. |  | A | The correct answer is A. Schedule a spike meeting, conduct risk assessments, and incorporate them into the backlog to help with risk mitigation. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 프로젝트의 세 번째 스프린트 실행 중 프로젝트 팀이 벤더 플랫폼의 빈번한 업데이트에 대해 불확실해하고 있다. 팀은 업데이트가 나머지 백로그에 어떤 영향을 미칠지 우려하고 있다. 불확실성을 최소화하기 위해 프로젝트 관리자는 어떻게 해야 하는가? | 스파이크 회의를 예약하고 리스크 평가를 수행하여 리스크 완화를 위해 백로그에 반영한다. | 벤더의 업데이트는 예측할 수 없는 것이므로 팀이 계속 프로젝트를 진행해야 한다고 설명한다. | 회고 회의를 예약하고 팀과 리스크 평가를 수행하여 다음 스프린트 전에 완화 작업을 실행한다. | 벤더와 대화하여 지속적인 업데이트가 프로젝트에 영향을 미치고 있음을 설명하고 변경을 최소화할 실행 계획을 요청한다. |  | A | 정답은 A이다. 스파이크 회의를 예약하고 리스크 평가를 수행하여 리스크 완화를 위해 백로그에 반영한다. 애자일 관행은 반복적 납품, 팀 역량 강화, 지속적 개선을 강조한다. PM은 협업을 촉진하고 장애물을 제거하며 팀이 효과적으로 가치를 전달할 수 있도록 해야 한다.
42 | A project is implementing an agile strategy, and a minimum viable product (MVP) was agreed upon. After the first iteration review, the customer explained that the first deliverable is not of great value. What should the project manager have done differently? | Invited the customer to the daily meetings | Changed the duration of iterations to deliver more value | Validated the iteration goals with the customer | Helped the team redefine the MVP |  | C | In agile projects, the PM should validate iteration goals with the customer to ensure alignment with their vision and value expectations. This validation is a core agile practice—emphasizing customer collaboration and iterative refinement to deliver a product that genuinely meets customer needs. Failure to validate early leads to misaligned deliverables and wasted effort. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 프로젝트가 애자일 전략을 시행하고 있으며 MVP(최소 기능 제품)에 합의했다. 첫 번째 이터레이션 리뷰 후 고객이 첫 번째 산출물이 큰 가치가 없다고 설명했다. 프로젝트 관리자는 무엇을 다르게 했어야 하는가? | 고객을 데일리 회의에 초대했어야 한다. | 더 많은 가치를 전달하기 위해 이터레이션 기간을 변경했어야 한다. | 고객과 이터레이션 목표를 검증했어야 한다. | 팀이 MVP를 재정의하도록 도왔어야 한다. |  | C | 애자일 프로젝트에서 PM은 고객의 비전과 가치 기대치에 부합하도록 고객과 이터레이션 목표를 검증해야 한다. 이 검증은 핵심 애자일 관행으로—고객 협업과 반복적 개선을 강조하여 고객의 요구를 진정으로 충족하는 제품을 전달한다. 조기 검증 실패는 산출물의 불일치와 노력 낭비로 이어진다.
43 | A project manager is working on a critical path activity and notices a delay in product delivery due to an anticipated event. What should the project manager do first? | Update the risk register | Use the contingency fund | Prepare a change request | Follow the risk response plan |  | D | The PM should first follow the risk response plan, which describes agreed-upon actions and owners for each identified risk. Executing planned risk responses is the priority before using contingency funds (B), preparing change requests (C), or updating the risk register (D). Contingency funds should be used only after response actions are implemented and residual impact is assessed. Change requests follow impact analysis. Risk register updates come after evaluating response outcomes. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Critical Path/Schedule Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 크리티컬 패스 활동을 수행 중이며 예상된 이벤트로 인해 제품 납품이 지연되고 있음을 발견했다. 프로젝트 관리자가 먼저 해야 할 일은? | 리스크 등록부를 업데이트한다. | 우발사태 예비비를 사용한다. | 변경 요청을 준비한다. | 리스크 대응 계획을 따른다. |  | D | PM은 먼저 리스크 대응 계획을 따라야 한다. 이 계획은 식별된 각 리스크에 대해 합의된 조치와 담당자를 기술한다. 계획된 리스크 대응 실행이 우발사태 예비비 사용(B), 변경 요청 준비(C), 리스크 등록부 업데이트(A) 이전에 우선이다. 우발사태 예비비는 대응 조치가 실행되고 잔여 영향이 평가된 후에만 사용해야 한다. 변경 요청은 영향 분석 후에 이어진다. 리스크 등록부 업데이트는 대응 결과를 평가한 후에 이루어진다.
44 | Clients are complaining about the delay on a product delivery timeline. It is confirmed that the issue is related to the product inventory and availability. What should the project manager do to engage the stakeholders? | Escalate the issue raised by the clients to the project sponsor, | Work with the team and the product owner to define the next steps. | Develop a solution with the team to identify the inventory level. | Ask the team to work on the complaint raised by the clients. |  | B | When clients are complaining about product delivery delays related to inventory and availability issues, the project manager should work with the team and the product owner to define the next steps. This collaborative approach ensures all parties understand the issue and can contribute to the solution while maintaining transparency and trust with stakeholders. Escalating to the project sponsor (A) is premature before the team has developed an action plan. Developing a solution for inventory levels (C) jumps to a specific technical solution without first involving the product owner in defining priorities. Asking the team to work on the complaint directly (D) lacks the structure and stakeholder alignment needed for effective resolution. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 고객들이 제품 납품 일정 지연에 대해 불만을 제기하고 있다. 이 문제가 제품 재고와 가용성과 관련된 것으로 확인되었다. 이해관계자를 참여시키기 위해 프로젝트 관리자는 어떻게 해야 하는가? | 고객이 제기한 이슈를 프로젝트 스폰서에게 에스컬레이션한다. | 팀과 제품 소유자와 협력하여 다음 단계를 정의한다. | 재고 수준을 파악하기 위한 해결책을 팀과 함께 개발한다. | 팀에게 고객이 제기한 불만에 대해 작업하도록 요청한다. |  | B | 고객이 재고와 가용성 문제로 인한 납품 지연에 불만을 제기할 때, PM은 팀과 제품 소유자와 협력하여 다음 단계를 정의해야 한다. 이 협력적 접근은 모든 당사자가 이슈를 이해하고 해결에 기여하며 이해관계자와의 투명성과 신뢰를 유지한다. 스폰서에게 에스컬레이션(A)은 팀이 실행 계획을 수립하기 전에 시기상조이다. 재고 수준 해결책 개발(C)은 제품 소유자 참여 없이 특정 기술적 해결책으로 뛰어든다. 팀에게 불만 작업 요청(D)은 효과적 해결에 필요한 구조와 이해관계자 정렬이 부족하다.
45 | A railroad construction project is in the planning stage. During a monthly progress meeting, an external project manager from the sponsoring organization mentioned there is a potential delay in the design completion date. The external project manager wants to know the impact of this delay on the overall project completion date in the next monthly meeting. Which three actions should the internal project manager take next? (Choose 3) | Perform variance analysis. | Establish what-if scenario analysis. | Validate the critical path method (CPM). | Determine the schedule performance index (SPI). | Execute a Monte Carlo simulation. | A, B, C | When facing a potential delay in a railroad construction project, the project manager should take three actions: perform variance analysis (A) to identify deviations from the baseline schedule, establish what-if scenario analysis (B) to evaluate different possible outcomes and develop contingency plans, and validate the critical path method (C) to ensure the project's critical activities and dependencies are accurately identified. Together, these three techniques provide comprehensive schedule management. Determining the SPI (D) is a measurement tool but does not address corrective actions. Executing a Monte Carlo simulation (E) is a probabilistic technique that may be useful but is more complex than needed for initial assessment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 철도 건설 프로젝트가 계획 단계에 있다. 월간 진행 회의 중 스폰서 조직의 외부 PM이 설계 완료 일정에 잠재적 지연이 있다고 언급했다. 외부 PM은 다음 월간 회의에서 이 지연이 전체 프로젝트 완료 일정에 미치는 영향을 알고 싶어 한다. 내부 PM이 다음에 취해야 할 세 가지 조치는? (3개 선택) | 편차 분석을 수행한다. | What-if 시나리오 분석을 수립한다. | 크리티컬 패스 방법(CPM)을 검증한다. | SPI(일정성과지수)를 산출한다. | 몬테카를로 시뮬레이션을 실행한다. | A, B, C | 철도 건설 프로젝트에서 잠재적 지연에 직면했을 때, 프로젝트 관리자는 세 가지 조치를 취해야 한다: 기준 일정에서의 편차를 식별하기 위한 편차 분석(A), 다양한 가능한 결과를 평가하고 비상 계획을 수립하기 위한 가정(What-if) 시나리오 분석(B), 프로젝트의 주요 활동과 종속성이 정확히 식별되도록 주공정선(CPM) 검증(C). 이 세 가지 기법이 함께 포괄적인 일정 관리를 제공한다. SPI 결정(D)은 측정 도구이지만 시정 조치를 다루지 않는다. 몬테카를로 시뮬레이션(E)은 확률적 기법으로 유용할 수 있으나 초기 평가에는 필요 이상으로 복잡하다.
46 | A project to develop an enterprise resource system for a university is in the planning phase. The project has internal stakeholders such as operational departments, students, and academic staff, as well as global stakeholders who receive information from the university on a regular basis. All the stakeholders have very different expectations and needs from the system. What should the project manager do to ensure effective communication? | Plan to implement a united communication platform, where all information about the project will be shared and updated regularly. | Ensure all the information about the project implementation is provided to all of the different stakeholders in a unified communication format. | Define communication target groups and provide information, messages, channels, and the frequency of communication for each group. | Arrange an information session for all of the stakeholders about the plans for handling their various communication needs. |  | C | Managing diverse stakeholders with varying communication needs requires segmenting them into target groups and tailoring communication plans for each. This includes selecting appropriate channels, message content, frequency, and format for each group. Generic communication approaches (A) or one-size-fits-all strategies (B) are ineffective with diverse audiences. A limited-scope approach (D) fails to establish the ongoing communication structure needed for sustained stakeholder engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 대학을 위한 ERP(전사적 자원 관리 시스템) 개발 프로젝트가 계획 단계에 있다. 프로젝트에는 운영 부서, 학생, 교직원 등 내부 이해관계자와 대학으로부터 정기적으로 정보를 받는 글로벌 이해관계자가 있다. 모든 이해관계자는 시스템에 대해 매우 다른 기대치와 요구를 가지고 있다. 효과적인 의사소통을 보장하기 위해 PM은 어떻게 해야 하는가? | 프로젝트에 대한 모든 정보를 공유하고 정기적으로 업데이트하는 통합 커뮤니케이션 플랫폼을 구현할 계획을 수립한다. | 프로젝트 실행에 대한 모든 정보를 통합된 커뮤니케이션 형식으로 모든 이해관계자에게 제공한다. | 커뮤니케이션 대상 그룹을 정의하고 각 그룹에 대한 정보, 메시지, 채널, 커뮤니케이션 빈도를 제공한다. | 모든 이해관계자를 대상으로 다양한 커뮤니케이션 요구를 처리하기 위한 계획에 대한 정보 세션을 마련한다. |  | C | 다양한 커뮤니케이션 요구를 가진 이해관계자를 관리하려면 대상 그룹으로 세분화하고 각 그룹에 맞춤형 커뮤니케이션 계획을 수립해야 한다. 이는 각 그룹에 적합한 채널, 메시지 내용, 빈도, 형식을 선택하는 것을 포함한다. 일반적인 커뮤니케이션 접근(A)이나 통합 전략(B)은 다양한 대상에게 비효과적이다. 제한적인 정보 세션 접근(D)은 지속적인 이해관계자 참여에 필요한 지속적인 커뮤니케이션 구조를 수립하지 못한다.
47 | A company has decided to implement a new archiving system. A data breach occurred during the implementation of the project. What should the project manager do first? | Review possible alternative documentation methods with team | Implement the planned risk response to handle the issue. | Ask the team to fix the system to resolve the issue | Update the risk register with the risk and proposed impact. |  | B | When a data breach occurs during a project implementation, the project manager should first implement the planned risk response to handle the issue. A data breach is a serious threat that should have been anticipated in the risk management plan, with predefined response strategies ready for activation. Reviewing alternative documentation methods (A) is irrelevant to the breach. Updating the risk register (D) is important but should follow the immediate response. Asking the team to fix the system (C) is insufficient—the PM must also coordinate with security, legal, the customer, and senior management. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 회사가 새로운 아카이빙 시스템을 구현하기로 결정했다. 프로젝트 구현 중 데이터 침해가 발생했다. 프로젝트 관리자가 먼저 해야 할 일은? | 팀과 함께 가능한 대안 문서화 방법을 검토한다. | 계획된 리스크 대응을 실행하여 이슈를 처리한다. | 팀에게 시스템을 수정하여 이슈를 해결하도록 요청한다. | 리스크와 제안된 영향을 리스크 등록부에 업데이트한다. |  | B | 프로젝트 구현 중 데이터 침해가 발생하면, PM은 먼저 계획된 리스크 대응을 실행해야 한다. 데이터 침해는 리스크 관리 계획에서 예상했어야 할 심각한 위협이며, 사전 정의된 대응 전략이 활성화될 준비가 되어 있어야 한다. 대안 문서화 방법 검토(A)는 침해와 무관하다. 리스크 등록부 업데이트(D)는 중요하지만 즉각적인 대응 후에 이루어져야 한다. 팀에게 시스템 수정 요청(C)은 불충분하다—PM은 보안, 법무, 고객, 고위 경영진과도 조율해야 한다.
48 | A project manager is implementing an enterprise-wide software project. The project has a great business impact and is fully supported by senior management. However, the project manager is facing difficulties getting the support of several key departments. What should the project manager do? | Hire a project management consultant to help resolve the issue | Ask senior management to communicate with these departments. | Understand the user concerns and revisit the stakeholder engagement plan | Convince senior management to introduce rewards to resisting departments. |  | C | When facing resistance from key departments despite senior management support for an enterprise-wide software project, the project manager should understand the user concerns and revisit the stakeholder engagement plan. Addressing the departments' underlying concerns through targeted engagement strategies is more effective than top-down pressure. Hiring a consultant (A) adds cost without addressing the root cause. Asking senior management to communicate (B) relies on authority rather than understanding. Introducing rewards for compliance (D) is superficial and may not address genuine concerns. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트 관리자가 전사적 소프트웨어 프로젝트를 실행하고 있다. 프로젝트는 큰 비즈니스 영향력이 있으며 고위 경영진의 전적인 지원을 받고 있다. 그러나 PM은 여러 핵심 부서의 지원을 받는 데 어려움을 겪고 있다. PM은 어떻게 해야 하는가? | 이슈 해결을 돕기 위해 프로젝트 관리 컨설턴트를 고용한다. | 고위 경영진에게 해당 부서들과 소통해 달라고 요청한다. | 사용자 우려사항을 이해하고 이해관계자 참여 계획을 재검토한다. | 고위 경영진을 설득하여 저항하는 부서에 보상을 도입하도록 한다. |  | C | 전사적 소프트웨어 프로젝트에 대해 고위 경영진 지원에도 불구하고 핵심 부서의 저항이 있을 때, PM은 사용자 우려사항을 이해하고 이해관계자 참여 계획을 재검토해야 한다. 목표적인 참여 전략을 통해 부서의 근본적인 우려를 해결하는 것이 하향식 압력보다 더 효과적이다. 컨설턴트 고용(A)은 근본 원인을 다루지 않고 비용을 추가한다. 고위 경영진 소통 요청(B)은 이해보다 권위에 의존한다. 저항 부서에 보상 도입(D)은 피상적이며 진정한 우려를 다루지 못할 수 있다.
49 | A project manager is attending a progress meeting with a client. The client requests a design change which might potentially add value to the project. What action should the project manager take? | Consult with team members and allow them to make a decision | Convince the client not to make changes to the project | Make transactional decisions focusing on the project goals | Accommodate the change request to serve the client ' s needs |  | C | When a client requests a design change that might add value, the project manager should make transactional decisions focusing on project goals. This means assessing the change's feasibility and priority through the change management process before committing. Consulting team members for a decision (A) bypasses formal change control. Convincing the client not to change (B) dismisses potential value. Accommodating the change immediately (D) bypasses impact analysis. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 고객과의 진행 회의에 참석하고 있다. 고객이 프로젝트에 잠재적으로 가치를 추가할 수 있는 설계 변경을 요청한다. 프로젝트 관리자는 어떤 조치를 취해야 하는가? | 팀원들과 상의하고 그들이 결정을 내리도록 한다. | 고객이 프로젝트를 변경하지 않도록 설득한다. | 프로젝트 목표에 초점을 맞춰 거래적 결정을 내린다. | 고객의 요구를 충족하기 위해 변경 요청을 수용한다. |  | C | 고객이 가치를 추가할 수 있는 설계 변경을 요청할 때, PM은 프로젝트 목표에 초점을 맞춰 거래적 결정을 내려야 한다. 이는 커밋하기 전에 변경 관리 프로세스를 통해 변경의 실현 가능성과 우선순위를 평가하는 것을 의미한다. 팀원과 상의하여 결정을 내리는 것(A)은 공식적 변경 통제를 우회한다. 고객에게 변경하지 말라고 설득(B)은 잠재적 가치를 무시한다. 변경을 즉시 수용(D)은 영향 분석을 우회한다.
50 | One-on-one interviews with members of an agile team reveal that they distrust an expert member. Their explanations seem to point to the expert's communication style in daily coordination meetings, which team members interpret as avoiding accountability. What two actions should the project manager take to address the situation? (Choose 2) | Encourage the team to respectfully ask questions to promote clear communication. | Help the expert member feel secure enough to communicate more freely. | Help the team gain trust in the expert by describing the expert's experience. | Instruct the expert member to avoid phrases that make the team uncomfortable. | Remind the team that all communications are valid and worthy of trust. | A, D | When team members distrust an expert due to their communication style in daily meetings, the project manager should take two actions: encourage the team to respectfully ask questions to promote clear communication (A), and instruct the expert member to avoid phrases that make the team uncomfortable (D). Encouraging questions fosters open dialogue, while direct coaching on communication style addresses the root cause of distrust. Helping the expert feel secure (B) is supportive but does not directly address the problematic communication patterns. Describing the expert's experience (C) relies on authority rather than behavior change. Reminding the team to trust all communications (E) is unrealistic without behavioral improvement. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 팀원들과의 일대일 인터뷰에서 팀원들이 전문가 팀원을 불신하고 있음이 드러났다. 설명을 들으면 전문가의 데일리 조정 회의에서의 커뮤니케이션 스타일이 책임 회피로 해석되고 있는 것으로 보인다. 이 상황을 해결하기 위해 PM이 취해야 할 두 가지 조치는? (2개 선택) | 팀이 명확한 의사소통을 촉진하기 위해 정중하게 질문하도록 장려한다. | 전문가 팀원이 더 자유롭게 소통할 수 있도록 안전하다고 느끼게 돕는다. | 전문가의 경험을 설명하여 팀이 전문가를 신뢰하도록 돕는다. | 전문가 팀원에게 팀이 불편해하는 표현을 피하도록 지시한다. | 팀에게 모든 커뮤니케이션은 유효하며 신뢰할 가치가 있다고 상기시킨다. | A, D | 팀원들이 커뮤니케이션 스타일로 인해 전문가를 불신할 때, PM은 두 가지 조치를 취해야 한다: 팀이 명확한 의사소통을 촉진하기 위해 정중하게 질문하도록 장려하고(A), 전문가 팀원에게 팀을 불편하게 하는 표현을 피하도록 지시한다(D). 질문 장려는 개방적 대화를 촉진하고, 커뮤니케이션 스타일에 대한 직접적 코칭은 불신의 근본 원인을 해결한다. 전문가가 안전하다고 느끼게 돕기(B)는 지지적이나 문제적 커뮤니케이션 패턴을 직접 해결하지 않는다. 전문가 경험 설명(C)은 행동 변화가 아닌 권위에 의존한다. 모든 커뮤니케이션 신뢰 상기(E)는 행동 개선 없이는 비현실적이다.
51 | An agile project manager notices that one of the team members is developing extensive knowledge in a specific matter. Other team members are likely to require this knowledge in the future. What should the agile project manager do? | Ask the team member to record highlights the team may want to know. | Ask the team member to provide a training session for the rest of the team. | Ask the team member to produce a lessons learned document and share it with the team. | Ask the team member to develop more expertise and become a subject matter expert (SME). |  | B | When an agile team member develops extensive specialized knowledge that others will need, the project manager should ask the team member to provide a training session for the rest of the team. This promotes knowledge sharing, collaboration, and team resilience. Asking them to record highlights (A) is passive. Asking them to create a lessons learned document (C) is retrospective rather than proactive. Encouraging further expertise development (D) does not address the team's knowledge gap. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 애자일 PM이 팀원 중 한 명이 특정 분야에서 괰5범위한 지식을 개발하고 있음을 발견했다. 다른 팀원들은 향후 이 지식이 필요할 가능성이 높다. 애자일 PM은 어떻게 해야 하는가? | 팀원에게 팀이 알고 싶어 할 주요 내용을 기록하도록 요청한다. | 팀원에게 나머지 팀을 위한 교육 세션을 제공하도록 요청한다. | 팀원에게 교훈 사항 문서를 작성하여 팀과 공유하도록 요청한다. | 팀원에게 더 많은 전문성을 개발하여 SME(주제 전문가)가 되도록 요청한다. |  | B | 애자일 팀원이 다른 팀원들이 필요로 할 전문 지식을 개발했을 때, PM은 팀원에게 나머지 팀을 위한 교육 세션을 제공하도록 요청해야 한다. 이는 지식 공유, 협업, 팀 회복력을 촉진한다. 주요 내용 기록 요청(A)은 수동적이다. 교훈 사항 문서 작성 요청(C)은 선제적이라기보다 회고적이다. 추가 전문성 개발 요청(D)은 팀의 지식 격차를 다루지 않는다.
52 | A project manager is assigned to a project that is in the execution phase that has different types of stakeholders. Some of the stakeholders are very interested in the project, whereas others do not show the same level of interest. What should the project manager do to assure the project finishes correctly? | Look at the stakeholder assessment matrix to find stakeholders ' interests and make updates if necessary. | Review the user person definitions to find the interests of the stakeholders and make updates if necessary. | Invite the most interested stakeholders to risk assessment sessions and assure the less interested stakeholders agree with the requirements. | Create a stakeholder assessment plan to manage stakeholder engagement and took at stakeholders ' approvals. |  | A | To ensure a project with mixed stakeholder interest levels finishes correctly, the project manager should review the stakeholder assessment matrix to understand each stakeholder's interests, influence, and engagement level, and make updates as needed. Regular review of this matrix ensures all stakeholders are appropriately engaged throughout the project. Reviewing user persona definitions (B) focuses on end users, not project stakeholders. Inviting only interested stakeholders to risk sessions (C) excludes less engaged stakeholders who may still need involvement. Creating a stakeholder assessment plan (D) is vague and does not leverage the existing assessment tool. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 다양한 유형의 이해관계자가 있는 실행 단계의 프로젝트에 배정되었다. 일부 이해관계자는 프로젝트에 매우 관심이 많은 반면, 다른 이해관계자는 같은 수준의 관심을 보이지 않는다. 프로젝트가 올바르게 완료되도록 하기 위해 PM은 어떻게 해야 하는가? | 이해관계자 평가 매트릭스를 살펴보고 이해관계자들의 관심사를 파악하며 필요시 업데이트한다. | 사용자 페르소나 정의를 검토하여 이해관계자들의 관심사를 파악하고 필요시 업데이트한다. | 가장 관심 있는 이해관계자를 리스크 평가 세션에 초대하고, 관심 적은 이해관계자가 요구사항에 동의하도록 한다. | 이해관계자 승인을 평가하고 이해관계자 참여를 관리하기 위한 이해관계자 평가 계획을 작성한다. |  | A | 다양한 이해관계자 관심 수준을 가진 프로젝트가 올바르게 완료되도록 하려면, PM은 이해관계자 평가 매트릭스를 검토하여 각 이해관계자의 관심, 영향력, 참여 수준을 파악하고 필요시 업데이트해야 한다. 이 매트릭스를 정기적으로 검토하면 프로젝트 전반에 걸쳐 모든 이해관계자가 적절히 참여하도록 보장한다. 사용자 페르소나 정의 검토(B)는 프로젝트 이해관계자가 아닌 최종 사용자에 초점을 맞춘다. 관심 많은 이해관계자만 리스크 세션에 초대(C)는 참여가 적은 이해관계자를 배제한다. 이해관계자 평가 계획 작성(D)은 모호하며 기존 평가 도구를 활용하지 않는다.
53 | A junior staff member was recently assigned to the team. The new team member tells the project manager that they are confused because they are not familiar with what is expected of them on the project. What should the project manager do to assist the new team member? | Advise the new team member to enroll in project management training. | Review the resource management plan and provide mentoring to the new team member if necessary | Advise the new team member to review the project charter and stakeholder engagement plan. | Instruct the new team member to review the responsible, accountable consult, and inform (RACI) matrix before asking for help |  | B | When a new team member is confused about expectations, the project manager should review the resource management plan and provide mentoring if necessary. The resource management plan defines roles, responsibilities, and required skills for project activities, directly clarifying the new member's expectations. Mentoring supports their integration and development. Advising project management training (A) is too general. Instructing them to review the RACI matrix (D) is dismissive without context. Advising review of the charter and stakeholder engagement plan (C) provides background but not role-specific guidance. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Resources | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 주니어 직원이 최근 팀에 배정되었다. 새 팀원은 프로젝트에서 자신에게 기대되는 것이 무엇인지 익숙하지 않아 혼란스럽다고 PM에게 말한다. PM은 새 팀원을 돕기 위해 어떻게 해야 하는가? | 새 팀원에게 프로젝트 관리 교육을 받도록 조언한다. | 자원 관리 계획을 검토하고 필요시 새 팀원에게 멘토링을 제공한다. | 새 팀원에게 프로젝트 헌장과 이해관계자 참여 계획을 검토하도록 조언한다. | 새 팀원에게 도움을 요청하기 전에 RACI 매트릭스를 검토하도록 지시한다. |  | B | 새 팀원이 기대치에 대해 혼란스러울 때, PM은 자원 관리 계획을 검토하고 필요시 멘토링을 제공해야 한다. 자원 관리 계획은 프로젝트 활동에 대한 역할, 책임, 필요 기술을 정의하여 새 팀원의 기대치를 직접적으로 명확히 한다. 멘토링은 통합과 성장을 지원한다. PM 교육 조언(A)은 너무 일반적이다. RACI 매트릭스 검토 지시(D)는 맥락 없이 무시하는 태도이다. 헌장과 이해관계자 계획 검토 조언(C)은 배경 정보를 제공하지만 역할별 구체적 안내는 아니다.
54 | A project manager is working on the implementation of new phases in the production process of a regulated industry. Which two stakeholders can help the project manager determine and address compliance requirements? (Choose two) | Functional managers | Board of directors | Risk steering committee | Advisory team panel | Chief executive officer | A, B | When implementing new phases in a regulated industry's production process, two stakeholders who can help determine and address compliance requirements are functional managers (A) and the board of directors (B). Functional managers provide resources, expertise, and organizational alignment for compliance. The board of directors provides governance oversight and strategic direction to ensure regulatory compliance at the highest level. The risk steering committee (C) oversees organizational risk but not project-level compliance. The advisory team panel (D) offers expert guidance but may lack the authority to enforce compliance. The CEO (E) operates at an executive level and typically delegates compliance to the board and functional management. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Stakeholders | Initiating | Embed Quality | Identify Stakeholders | Traditional PM | 프로젝트 관리자가 규제 산업의 생산 공정에서 새로운 단계 구현 작업을 하고 있다. 컴플라이언스 요구사항을 결정하고 해결하는 데 도움을 줄 수 있는 두 명의 이해관계자는? (2개 선택) | 기능 관리자 | 이사회 | 리스크 운영 위원회 | 자문 팀 패널 | 최고경영자(CEO) | A, B | 규제 산업의 생산 공정에서 새로운 단계를 구현할 때, 컴플라이언스 요구사항을 결정하고 해결하는 데 도움을 줄 수 있는 두 이해관계자는 기능 관리자(A)와 이사회(B)이다. 기능 관리자는 컴플라이언스를 위한 자원, 전문성, 조직적 정렬을 제공한다. 이사회는 최고 수준에서 규제 준수를 보장하기 위한 거버넌스 감독과 전략적 방향을 제공한다. 리스크 운영 위원회(C)는 조직 리스크를 감독하지만 프로젝트 수준 컴플라이언스는 아니다. 자문 팀 패널(D)은 전문적 지침을 제공하지만 컴플라이언스를 강제할 권한이 부족할 수 있다. CEO(E)는 경영진 수준에서 운영하며 일반적으로 컴플라이언스를 이사회와 기능 관리에 위임한다.
55 | A project manager has been working with the same group of stakeholders for 3 years using a predictive approach. The stakeholders have invested in many projects and are familiar with the approach. Recently, the organization has strongly encouraged all project managers to adopt an agile approach. This was announced 2 weeks before the project manager planned to kick off a large, complex project with the same group of stakeholders. What should the project manager do? | Share and discuss the pros and cons of adopting agile with the stakeholders and choose the approach they prefer for the new project | Continue to use the predictive approach m the new project since it is the approach the stakeholders are familiar with using | Share the pros and cons of adopting an agile approach for the new project only with the team and ask them to decide which approach to use | Use the agile approach in the new project and schedule agile training for those stakeholders who are new to this approach |  | A | The PM should engage stakeholders in a collaborative discussion about the best approach for the project—explaining benefits and challenges of both predictive and agile methods. Imposing a new approach without stakeholder input leads to resistance and dissatisfaction. Excluding stakeholders from the decision ignores their perspectives and needs. Facilitating collaborative agreement demonstrates leadership, communication, and stakeholder management skills. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Hybrid/Tailoring | PM이 3년간 예측형 접근법을 사용하여 같은 이해관계자 그룹과 일해왔다. 이해관계자들은 많은 프로젝트에 투자했으며 이 접근법에 익숙하다. 최근 조직이 모든 PM에게 애자일 접근법 채택을 강력히 권고했다. 이 발표는 PM이 같은 이해관계자 그룹과 대규모 복잡한 프로젝트를 시작하기 2주 전에 이루어졌다. PM은 어떻게 해야 하는가? | 이해관계자들과 애자일 채택의 장단점을 공유하고 논의하여 새 프로젝트에 선호하는 접근법을 선택한다. | 이해관계자들이 익숙한 접근법이므로 새 프로젝트에서도 예측형 접근법을 계속 사용한다. | 애자일 접근법의 장단점을 팀에게만 공유하고 어떤 접근법을 사용할지 결정하도록 요청한다. | 새 프로젝트에서 애자일 접근법을 사용하고 애자일에 익숙하지 않은 이해관계자를 위한 교육을 일정에 포함한다. |  | A | PM은 이해관계자와 협력적으로 예측형과 애자일 방법의 장점과 과제를 설명하며 프로젝트에 최적인 접근법에 대해 논의해야 한다. 이해관계자 의견 없이 새로운 접근법을 강요하면 저항과 불만을 초래한다. 이해관계자를 결정에서 배제하면 그들의 관점과 요구를 무시하는 것이다. 협력적 합의를 촉진하는 것은 리더십, 커뮤니케이션, 이해관계자 관리 역량을 보여준다.
56 | A project manager is leading a complex project that requires integrating several components from different suppliers. During execution, the project team reports that some components are not being delivered to the site on time, impacting the project schedule. What should the project manager do to address this concern? | Review the project schedule with project team members and the suppliers. | Advise the procurement department to develop a new supplier strategy. | Register the issue as a risk with the project team members. | Use the procurement and risk management plans to manage this issue. |  | D | The PM should leverage procurement and risk management plans to address schedule concerns from delayed deliveries. Effective schedule management requires proactive monitoring and timely corrective actions. The PM should analyze the schedule impact of the delivery delays, evaluate available options (alternative suppliers, schedule adjustments, risk responses), and implement appropriate measures to keep the project on track. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | PM이 여러 공급업체의 구성요소를 통합해야 하는 복잡한 프로젝트를 이끌고 있다. 실행 중 프로젝트 팀이 일부 구성요소가 현장에 제때 납품되지 않아 프로젝트 일정에 영향을 미치고 있다고 보고했다. 이 문제를 해결하기 위해 PM은 어떻게 해야 하는가? | 프로젝트 팀원 및 공급업체와 함께 프로젝트 일정을 검토한다. | 조달 부서에 새로운 공급업체 전략을 개발하도록 조언한다. | 이 이슈를 프로젝트 팀원들과 함께 리스크로 등록한다. | 조달 및 리스크 관리 계획을 활용하여 이 이슈를 관리한다. |  | D | PM은 납품 지연으로 인한 일정 문제를 해결하기 위해 조달 및 리스크 관리 계획을 활용해야 한다. 효과적인 일정 관리는 선제적 모니터링과 적시의 시정 조치를 요구한다. PM은 납품 지연의 일정 영향을 분석하고, 가용한 옵션(대체 공급업체, 일정 조정, 리스크 대응)을 평가하며, 프로젝트를 정상 궤도에 유지하기 위한 적절한 조치를 실행해야 한다.
57 | At a project meeting, a business analyst requires input from a marketing consultant to continue working on a task. The business analyst has tried to contact the consultant but has been told that the consultant does not have the time to discuss the project. What should the project manager do to move the project forward? | Escalate the issues about the consultant to the functional manager so the consultant dedicates the necessary time to the project. | Discuss the request with the consultant and set up time with the business analyst and consultant to discuss the project requirements. | Include a new project risk into the risk register and allocate the consultant as the risk owner as it is their responsibility to provide input. | Urge the business analyst to continue contacting the consultant to discuss the project since this is the responsibility of the business analyst. |  | B | When a business analyst cannot get the marketing consultant's time for project input, the project manager should discuss the request with the consultant and set up time for both to discuss requirements. Active facilitation removes blockers. Escalating to the functional manager (A) may be needed later but direct engagement should come first. Including a risk with the consultant as owner (C) is passive. Urging the BA to keep contacting the consultant (D) perpetuates the problem. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Schedule Management | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 회의에서 비즈니스 분석가가 작업을 계속하기 위해 마케팅 컨설턴트의 의견이 필요하다. 비즈니스 분석가가 컨설턴트에게 연락을 시도했지만 컨설턴트가 프로젝트를 논의할 시간이 없다는 답변을 받았다. 프로젝트를 진행하기 위해 PM은 어떻게 해야 하는가? | 컨설턴트에 대한 이슈를 기능 관리자에게 에스컬레이션하여 컨설턴트가 프로젝트에 필요한 시간을 할애하도록 한다. | 컨설턴트와 요청 사항을 논의하고 비즈니스 분석가와 컨설턴트가 프로젝트 요구사항을 논의할 시간을 설정한다. | 새로운 프로젝트 리스크를 리스크 등록부에 포함하고 의견 제공이 컨설턴트의 책임이므로 리스크 소유자로 배정한다. | 비즈니스 분석가의 책임이므로 컨설턴트에게 계속 연락하여 프로젝트를 논의하도록 촉구한다. |  | B | 비즈니스 분석가가 마케팅 컨설턴트의 시간을 확보하지 못할 때, PM은 컨설턴트와 요청을 논의하고 양측이 요구사항을 논의할 시간을 설정해야 한다. 능동적 촉진이 장애물을 제거한다. 기능 관리자에게 에스컬레이션(A)은 나중에 필요할 수 있지만 직접적 참여가 먼저다. 컨설턴트를 리스크 소유자로 등록(C)은 소극적이다. 비즈니스 분석가에게 계속 연락하도록 촉구(D)는 문제를 지속시킨다.
58 | A project manager entered into a contract with a vendor to build a new system. During the acceptance test stage, the project manager noticed that the system quality was not satisfactory. How should the project manager support their claim to the vendor? | Provide the failed test results along with the agreed-upon acceptance criteria | Show that the acceptance criteria were changed by the vendor without approval. 1313 | Document in the risk log that the issues in the system were already identified | Share unsuccessful results from previous projects with a similar scope |  | A | When the system quality is unsatisfactory during acceptance testing, the project manager should provide the failed test results along with the agreed-upon acceptance criteria to support the claim. Documented evidence against contractual standards is the strongest basis. Showing changed acceptance criteria (B) requires proof of unauthorized changes. Documenting in the risk log (C) does not address the vendor claim. Sharing previous project failures (D) is irrelevant. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 새 시스템 구축을 위해 벤더와 계약을 체결했다. 인수 테스트 단계에서 PM이 시스템 품질이 만족스럽지 않음을 발견했다. PM은 벤더에 대한 클레임을 어떻게 뒷받침해야 하는가? | 실패한 테스트 결과와 합의된 인수 기준을 함께 제공한다. | 인수 기준이 승인 없이 벤더에 의해 변경되었음을 보여준다. | 시스템의 이슈가 이미 식별되었음을 리스크 로그에 문서화한다. | 유사한 범위의 이전 프로젝트에서의 실패 결과를 공유한다. |  | A | 인수 테스트에서 시스템 품질이 불만족스러울 때, PM은 실패한 테스트 결과와 합의된 인수 기준을 함께 제공하여 클레임을 뒷받침해야 한다. 계약 기준에 대한 문서화된 증거가 가장 강력한 근거이다. 변경된 인수 기준 제시(B)는 무단 변경의 증거가 필요하다. 리스크 로그 문서화(C)는 벤더 클레임을 다루지 않는다. 이전 프로젝트 실패 공유(D)는 무관하다.
59 | In a global project, the project manager has to plan and manage communication between the team members and stakeholders in order to ensure the project will remain on track and achieve its goals. What should the project manager do? | Conduct an integration meeting among all stakeholders. | Understand how political aspects can affect the project. | Schedule communication training for management-level stakeholders. | Consider cultural differences among stakeholders. |  | D | The correct answer is D. Consider cultural differences among stakeholders. Stakeholder engagement requires proactive communication and alignment. The PM should understand stakeholder needs, maintain transparency, and address concerns to ensure project success. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 글로벌 프로젝트에서 PM은 프로젝트가 정상 궤도를 유지하고 목표를 달성하도록 팀원과 이해관계자 간의 커뮤니케이션을 계획하고 관리해야 한다. PM은 어떻게 해야 하는가? | 모든 이해관계자 간의 통합 회의를 실시한다. | 정치적 측면이 프로젝트에 어떻게 영향을 미칠 수 있는지 이해한다. | 관리급 이해관계자를 위한 커뮤니케이션 교육을 일정에 포함한다. | 이해관계자 간의 문화적 차이를 고려한다. |  | D | 정답은 D이다. 이해관계자 간의 문화적 차이를 고려한다. 이해관계자 참여는 선제적 커뮤니케이션과 정렬을 요구한다. PM은 이해관계자 요구를 이해하고, 투명성을 유지하며, 우려를 해결하여 프로젝트 성공을 보장해야 한다.
60 | A project manager is in a team meeting and the project team requires a decision to be made about a new suggested timeline due to an impact from a potential scope change. What should the project manager do? | Follow the stakeholder engagement plan | Review the stakeholder map along with the organizational chart and delegate the most senior person to make the decision | Schedule a project decision meeting with all stakeholders to discuss the decision. | Make the decision on behalf of the organization |  | A | When the project team requires a decision about a new timeline due to a potential scope change impact, the project manager should follow the stakeholder engagement plan. This plan defines how stakeholders are involved in decisions, ensuring the timeline decision is made transparently and collaboratively with appropriate stakeholder input. Reviewing the stakeholder map and delegating to the most senior person (B) relies on hierarchy rather than process. Scheduling a decision meeting with all stakeholders (C) may be unnecessary if the engagement plan already defines decision-making protocols. Making the decision unilaterally (D) bypasses stakeholder involvement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | PM이 팀 회의 중이며 프로젝트 팀이 잠재적 범위 변경의 영향으로 새로운 제안 일정에 대한 결정을 내려야 한다. PM은 어떻게 해야 하는가? | 이해관계자 참여 계획을 따른다. | 이해관계자 맵과 조직도를 검토하고 최고위 인사에게 결정을 위임한다. | 모든 이해관계자와의 프로젝트 의사결정 회의를 일정에 포함한다. | 조직을 대신하여 결정을 내린다. |  | A | 잠재적 범위 변경 영향으로 새로운 일정에 대한 결정이 필요할 때, PM은 이해관계자 참여 계획을 따라야 한다. 이 계획은 이해관계자가 의사결정에 어떻게 참여하는지를 정의하여, 일정 결정이 적절한 이해관계자 의견과 함께 투명하고 협력적으로 이루어지도록 보장한다. 이해관계자 맵을 검토하고 최고위 인사에게 위임(B)은 프로세스가 아닌 위계에 의존한다. 모든 이해관계자와 결정 회의(C)는 참여 계획이 이미 의사결정 프로토콜을 정의한 경우 불필요할 수 있다. 일방적 결정(D)은 이해관계자 참여를 우회한다.
61 | A project manager is leading a large-scale project that involves 70 stakeholders. The project manager has heard various comments and expectations from the customers, some of which are contradictory. Consequently, some requirements are not clear. What should the project manager do to build consensus regarding the requirements? | Create a survey template to collect feedback from stakeholders to reach an agreement | Escalate the issue to the management team for their review and guidance | Leverage expert judgment to determine the requirements that should be considered | Organize a face-to-face meeting with all stakeholders to understand their interests and concerns. |  | D | When 70 stakeholders have contradictory expectations and unclear requirements, the project manager should organize a face-to-face meeting with all stakeholders to understand their interests and concerns. This consensus-building approach facilitates communication, collaboration, and respectful dialogue to resolve conflicts and reach a common understanding of requirements. Creating a survey (A) is useful for data collection but lacks the interactive dialogue needed for consensus. Escalating to management (B) delegates the PM's responsibility for stakeholder management. Leveraging expert judgment (C) provides input but does not involve stakeholders in the consensus-building process. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 70명의 이해관계자가 참여하는 대규모 프로젝트를 이끌고 있다. PM은 고객으로부터 다양한 의견과 기대를 들었으며, 일부는 상충된다. 결과적으로 일부 요구사항이 명확하지 않다. 요구사항에 대한 합의를 구축하기 위해 PM은 어떻게 해야 하는가? | 이해관계자로부터 피드백을 수집하여 합의에 도달하기 위한 설문 템플릿을 만든다. | 이슈를 경영진에게 에스컬레이션하여 검토와 지침을 받는다. | 전문가 판단을 활용하여 고려해야 할 요구사항을 결정한다. | 모든 이해관계자와 대면 회의를 조직하여 그들의 관심사와 우려를 이해한다. |  | D | 70명의 이해관계자가 상충되는 기대와 불명확한 요구사항을 가질 때, PM은 모든 이해관계자와 대면 회의를 조직하여 그들의 관심사와 우려를 이해해야 한다. 이 합의 구축 접근법은 갈등을 해결하고 요구사항에 대한 공통 이해에 도달하기 위한 소통, 협업, 존중 있는 대화를 촉진한다. 설문 작성(A)은 데이터 수집에 유용하지만 합의에 필요한 상호 대화가 부족하다. 경영진에게 에스컬레이션(B)은 이해관계자 관리에 대한 PM의 책임을 위임한다. 전문가 판단 활용(C)은 의견을 제공하지만 합의 구축 과정에 이해관계자를 참여시키지 않는다.
62 | A project manager is made aware that there are defects in the parts provided by a supplier, which are causing delays in the testing phase. The supplier claims that all parts have been delivered as per the contract. If the defects are not fixed by the supplier within one week, the product release will be impacted. What should the project manager do? | Request a cancellation of the procurement contract with the supplier and impose a penalty. | Request a revision of the procurement contract to include specifications for the parts. | Review the procurement contract and ask the supplier to negotiate a solution. | Escalate this issue to senior management, as the supplier is not following the procurement contract. |  | C | When a supplier's defective parts are causing testing delays and the supplier claims contract compliance, the project manager should review the procurement contract and ask the supplier to negotiate a solution. Contract review identifies obligations. Canceling the contract with penalties (A) is extreme. Revising the contract for specifications (B) changes terms mid-project. Escalating to senior management (D) bypasses direct negotiation. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 공급업체가 제공한 부품에 결함이 있어 테스트 단계에 지연을 초래하고 있음을 인지했다. 공급업체는 모든 부품이 계약에 따라 납품되었다고 주장한다. 1주일 내에 공급업체가 결함을 수정하지 않으면 제품 출시에 영향을 미칠 것이다. PM은 어떻게 해야 하는가? | 공급업체와의 조달 계약 취소를 요청하고 페널티를 부과한다. | 부품 사양을 포함하도록 조달 계약 수정을 요청한다. | 조달 계약을 검토하고 공급업체에게 해결책을 협상하도록 요청한다. | 공급업체가 조달 계약을 따르지 않으므로 이 이슈를 고위 경영진에게 에스컬레이션한다. |  | C | 공급업체의 결함 부품이 테스트 지연을 초래하고 공급업체가 계약 준수를 주장할 때, PM은 조달 계약을 검토하고 공급업체에게 해결책을 협상하도록 요청해야 한다. 계약 검토로 의무사항을 파악한다. 계약 취소 및 페널티(A)는 극단적이다. 사양을 위한 계약 수정(B)은 프로젝트 중간에 조건을 변경한다. 고위 경영진 에스컬레이션(D)은 직접 협상을 우회한다.
63 | During a requirements review session with a customer, a team member gets upset when questioned by the customer and responds angrily. What should the project manager do next? | Follow up with the whole team to find the best approach | Provide the team member with space to manage their emotions | Discuss with the whole team the root cause of this issue | Meet with the team member to reset expectations |  | D | When a team member responds angrily to a customer during a requirements review, the project manager should meet with the team member to reset expectations. Direct one-on-one dialogue addresses behavior privately and professionally. Following up with the whole team (A) may embarrass the individual publicly. Providing space for emotions (B) avoids addressing the issue. Discussing root cause with the team (C) is broader than needed for an individual behavior issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 요구사항 검토 세션 중 고객의 질문에 팀원이 화가 나서 분노하며 응답했다. PM이 다음에 해야 할 일은? | 전체 팀과 후속 조치를 취하여 최선의 접근법을 찾는다. | 팀원에게 감정을 관리할 공간을 제공한다. | 전체 팀과 이 이슈의 근본 원인을 논의한다. | 팀원과 만나 기대치를 재설정한다. |  | D | 요구사항 검토 중 팀원이 고객에게 분노하며 응답했을 때, PM은 팀원과 만나 기대치를 재설정해야 한다. 직접적인 일대일 대화가 행동을 사적이고 전문적으로 다룬다. 전체 팀과 후속 조치(A)는 개인을 공개적으로 당혹스럽게 할 수 있다. 감정 관리 공간 제공(B)은 이슈 해결을 회피한다. 팀과 근본 원인 논의(C)는 개인 행동 이슈에 비해 범위가 너무 넓다.
64 | During project initiation meetings, the project manager of a 9-month project states that a specific task would be out of schedule. At the project kick-off meeting, a key project stakeholder strongly objects, stating that this task is the key value of the project and should be completed on time. What should the project manager do to reduce the chances of having a strong rejection from stakeholders during the project initiation stage? | Send a letter to the stakeholders to inform them about the project scope and start date. | Develop a stakeholder-by-stakeholder engagement assessment matrix. | Schedule meetings with key stakeholders in advance to gather feedback on the project scope. | Identify stakeholder rejection as a risk in the project risk register. |  | C | When a key stakeholder strongly objects during the kick-off meeting about a task being out of schedule, the project manager should have scheduled meetings with key stakeholders in advance to gather feedback on scope. Early engagement prevents surprises. Sending a letter about scope (A) is one-directional. Developing a stakeholder engagement matrix (B) is a tool but not the direct action. Identifying rejection as a risk (D) is reactive. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 9개월 프로젝트의 PM이 프로젝트 착수 회의에서 특정 작업이 일정에 맞추지 못할 것이라고 발표했다. 프로젝트 킥오프 회의에서 핵심 이해관계자가 이 작업이 프로젝트의 핵심 가치이며 제때 완료되어야 한다고 강력히 반대했다. 프로젝트 착수 단계에서 이해관계자의 강한 거부를 줄이기 위해 PM은 어떻게 했어야 하는가? | 이해관계자에게 프로젝트 범위와 시작일에 대해 알리는 서한을 보낸다. | 이해관계자별 참여 평가 매트릭스를 개발한다. | 핵심 이해관계자와 사전 회의를 예약하여 프로젝트 범위에 대한 피드백을 수집한다. | 이해관계자 거부를 프로젝트 리스크 등록부에 리스크로 식별한다. |  | C | 킥오프 회의에서 핵심 이해관계자가 일정 문제에 강력히 반대할 때, PM은 핵심 이해관계자와 사전 회의를 예약하여 범위에 대한 피드백을 수집했어야 했다. 조기 참여는 기습을 방지한다. 범위에 대한 서한 발송(A)은 일방향적이다. 이해관계자 참여 매트릭스 개발(B)는 도구이지만 직접적인 조치는 아니다. 거부를 리스크로 식별(D)은 사후 대응이다.
65 | A project manager is involved with a project to remodel a long-used product. There are no proper records for the original design and execution of the original product. The stakeholders doubt that the remodel can be accomplished without this information and are hesitant to provide support for the project. What should the project manager do? | Acknowledge the stakeholders' concerns with open dialogues and realign the project with 1069 stakeholder requirements and past lessons learned. | Solicit a larger reserve for cost and time and manage the stakeholders' expectations. | Share the threats of not updating old solutions and ask stakeholders to be patient with any inconveniences. | Create a plan to inform stakeholders on the progress so they are able to see that the project can succeed, |  | A | When stakeholders doubt a product remodel can succeed without original design records, the project manager should acknowledge concerns through open dialogues and realign the project with stakeholder requirements and past lessons learned. Transparent engagement builds trust. Soliciting larger reserves (B) addresses risk but not stakeholder concerns. Sharing threats and asking for patience (C) does not actively engage. Creating a progress reporting plan (D) informs but does not address uncertainty. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Risk & Issue Management | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | PM이 오래 사용된 제품의 리모델링 프로젝트에 참여하고 있다. 원래 제품의 설계 및 실행에 대한 적절한 기록이 없다. 이해관계자들은 이 정보 없이 리모델링을 달성할 수 있을지 의심하며 프로젝트 지원을 주저하고 있다. PM은 어떻게 해야 하는가? | 이해관계자들의 우려를 열린 대화로 인정하고, 프로젝트를 이해관계자 요구사항과 과거 교훈 사항에 맞추어 재정렬한다. | 비용과 일정에 대한 더 큰 예비비를 요청하고 이해관계자들의 기대치를 관리한다. | 오래된 솔루션을 업데이트하지 않을 때의 위협을 공유하고 이해관계자들에게 불편을 감수해 달라고 요청한다. | 이해관계자들에게 진행 상황을 알려 프로젝트가 성공할 수 있음을 확인할 수 있는 계획을 수립한다. |  | A | 이해관계자들이 원래 설계 기록 없이 제품 리모델링 성공을 의심할 때, PM은 열린 대화를 통해 우려를 인정하고 프로젝트를 이해관계자 요구사항 및 과거 교훈에 맞추어 재정렬해야 한다. 투명한 참여가 신뢰를 구축한다. 더 큰 예비비 요청(B)은 리스크를 다루지만 이해관계자 우려는 다루지 않는다. 위협 공유 및 인내 요청(C)은 능동적으로 참여시키지 않는다. 진행 보고 계획 수립(D)은 정보를 제공하지만 불확실성을 해결하지 않는다.
66 | A project manager recently finished a project and started managing a new project with a different supervisor. As part of the early project activities, the supervisor from the original project is assigned to the team as a nonsupervisory resource and immediately begins challenging all decisions made by the current supervisor. What should the project manager do to resolve this conflict? | Immediately remove the resource from the project team. | Ensure the new supervisor takes the lead when being challenged. | Give the project team time to work through the issues with the new supervisor. | Communicate with the resource on the roles and responsibilities of this project. |  | D | To resolve conflict between a former supervisor now serving as a non-supervisory resource and the current supervisor, the PM should communicate directly with the former supervisor to clarify roles and responsibilities within the new project structure. Clear role definition and communication prevent misunderstandings and maintain team harmony during transitions. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 최근 프로젝트를 마무리하고 다른 상사와 새로운 프로젝트를 관리하기 시작했다. 초기 프로젝트 활동의 일환으로, 원래 프로젝트의 상사가 비감독 자원으로 팀에 배정되어 현재 상사의 모든 결정에 즉시 이의를 제기하기 시작했다. 이 갈등을 해결하기 위해 PM은 어떻게 해야 하는가? | 해당 자원을 프로젝트 팀에서 즉시 제거한다. | 새로운 상사가 도전받을 때 주도권을 잡도록 보장한다. | 팀에게 새로운 상사와의 이슈를 스스로 해결할 시간을 준다. | 해당 자원과 소통하여 이 프로젝트에서의 역할과 책임을 명확히 한다. |  | D | 이전 상사가 비감독 자원으로 배정되어 현재 상사의 결정에 이의를 제기하는 갈등을 해결하기 위해, PM은 해당 자원과 직접 소통하여 새 프로젝트 구조에서의 역할과 책임을 명확히 해야 한다. 명확한 역할 정의와 커뮤니케이션은 전환 시 오해를 방지하고 팀 조화를 유지한다.
67 | A project manager has been authorized to begin a project and realizes that an effective high-performing team is needed to finish the project successfully. What should the project manager do next? | Hold early kick-off meetings and regular weekly meetings | Select members for their skill or potential | Establish the project scope and set clear team objectives | Set performance standards and direction |  | B | After being authorized to begin a project, the project manager should select team members based on their skills or potential to contribute to the project's success. Building the right team is the critical first step before other project activities can begin effectively. Holding kick-off meetings and weekly meetings (A) requires a team to be assembled first. Establishing project scope and team objectives (C) is important but depends on having the team. Setting performance standards (D) follows team formation. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 프로젝트를 시작할 권한을 부여받았으며, 프로젝트를 성공적으로 마무리하기 위해 효과적인 고성과 팀이 필요하다는 것을 인식하고 있다. PM이 다음에 해야 할 일은? | 조기 킥오프 회의와 정기 주간 회의를 개최한다. | 팀원을 기술이나 잠재력을 기준으로 선발한다. | 프로젝트 범위를 수립하고 명확한 팀 목표를 설정한다. | 성과 기준과 방향을 설정한다. |  | B | 프로젝트 시작 권한을 받은 후, PM은 프로젝트 성공에 기여할 수 있는 기술이나 잠재력을 기준으로 팀원을 선발해야 한다. 적절한 팀 구성이 다른 프로젝트 활동보다 단원한 첫 단계이다. 킥오프 회의와 주간 회의 개최(A)는 먼저 팀이 구성되어야 한다. 프로젝트 범위와 팀 목표 수립(C)은 중요하지만 팀 구성에 달려 있다. 성과 기준 설정(D)은 팀 구성 후에 이루어진다.
68 | The marketing team is moving from predictive to hybrid approaches for their projects. The marketing director is not familiar with hybrid approaches and does not support the new direction. What should the project manager do? | Train the marketing team and keep their director informed. | Mentor the marketing director on the approaches. | Advise the marketing director to receive formal training. | Ask the marketing team members to coach their director. |  | A | When the marketing team is transitioning from predictive to hybrid approaches and the director does not support the change, the project manager should train the marketing team and keep the director informed. Building team competence while maintaining director awareness enables gradual acceptance. Advising the director to receive formal training (C) may not be practical. Asking team members to coach their director (D) is inappropriate. Mentoring the director (B) assumes a relationship that may not exist. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Align Stakeholder Expectations | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Hybrid/Tailoring | 마케팅 팀이 프로젝트에서 예측형에서 하이브리드 접근법으로 전환하고 있다. 마케팅 이사는 하이브리드 접근법에 익숙하지 않으며 새로운 방향을 지지하지 않는다. PM은 어떻게 해야 하는가? | 마케팅 팀을 교육하고 이사에게 진행 상황을 계속 알린다. | 마케팅 이사에게 접근법에 대해 멘토링한다. | 마케팅 이사에게 공식 교육을 받도록 조언한다. | 마케팅 팀원들에게 이사를 코칭하도록 요청한다. |  | A | 마케팅 팀이 예측형에서 하이브리드로 전환하고 이사가 변화를 지지하지 않을 때, PM은 팀을 교육하고 이사에게 진행 상황을 계속 알려야 한다. 팀 역량을 구축하면서 이사의 인식을 유지하면 점진적 수용이 가능해진다. 공식 교육 조언(C)은 실용적이지 않을 수 있다. 팀원에게 이사 코칭 요청(D)은 부적절하다. 이사 멘토링(B)은 존재하지 않을 수 있는 관계를 전제한다.
69 | A member of the board of directors has asked the project manager for the estimated cost of the minimum viable product (MVP). The estimated cost is needed in order to get formal approval for this project. How should the project manager report this cost? | Calculate the budget at completion (BAC) based on the completed and planned features | Estimate user story points and forecast a budget for that deliverable | Determine the control accounts and use a top bottom estimate | Consider the cost performance index (CPl) based on earned value (EV) divided by costs |  | B | When a board member needs the estimated cost of an MVP for formal project approval, the project manager should estimate user story points and forecast a budget for that deliverable. Story point estimation with forecasting provides agile-appropriate cost projections. Calculating BAC from completed and planned features (A) assumes fixed scope. Determining control accounts with top-down estimation (C) is a traditional method less suited for MVP. Considering CPI from earned value (D) requires project progress data not yet available. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 이사회 임원이 PM에게 MVP(최소 기능 제품)의 예상 비용을 요청했다. 예상 비용은 프로젝트의 공식 승인을 받기 위해 필요하다. PM은 이 비용을 어떻게 보고해야 하는가? | 완료된 기능과 계획된 기능을 기반으로 BAC(완료 시 예산)를 산출한다. | 사용자 스토리 포인트를 추정하고 해당 산출물에 대한 예산을 예측한다. | 통제 계정을 결정하고 하향식 추정을 사용한다. | EV(획득가치)를 비용으로 나누어 산출한 CPI(비용성과지수)를 고려한다. |  | B | 이사회 임원이 공식 프로젝트 승인을 위해 MVP 예상 비용이 필요할 때, PM은 사용자 스토리 포인트를 추정하고 해당 산출물에 대한 예산을 예측해야 한다. 스토리 포인트 추정과 예측은 애자일에 적합한 비용 예측을 제공한다. 완료 및 계획 기능 기반 BAC 산출(A)은 고정 범위를 전제한다. 하향식 추정으로 통제 계정 결정(C)은 MVP에 덜 적합한 전통적 방법이다. 획득가치 기반 CPI 고려(D)는 아직 가용하지 않은 프로젝트 진행 데이터가 필요하다.
70 | A project manager has recently been assigned to a new project. When the project manager first meets the project team, the team tells the project manager that all of the management plans and documents for the project are missing. What should the project manager do? | Create the project management plans with the project team and share the documents with the stakeholders. | Adapt the project management plans and documents from previous executed projects in order to save time. | Continue working on scheduled tasks to avoid delaying the project and leave the development of project artifacts for later. | Ask the stakeholders to develop all of the project artifacts so the project team can continue their scheduled activities. |  | A | When all management plans and documents for a project are missing, the project manager should create the project management plans with the project team and share documents with stakeholders. Collaborative plan development ensures completeness and buy-in. Adapting plans from previous projects (B) may not fit the current project's needs. Continuing tasks and leaving artifacts for later (C) risks unguided execution. Asking stakeholders to develop artifacts (D) misassigns responsibility. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | General | Stakeholder & Communication Mgmt | Process | Evaluate Project Status | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | PM이 최근 새 프로젝트에 배정되었다. PM이 프로젝트 팀을 처음 만났을 때, 팀은 프로젝트의 모든 관리 계획과 문서가 없다고 말했다. PM은 어떻게 해야 하는가? | 프로젝트 팀과 함께 프로젝트 관리 계획을 작성하고 문서를 이해관계자와 공유한다. | 시간을 절약하기 위해 이전에 실행된 프로젝트의 관리 계획과 문서를 적용한다. | 프로젝트 지연을 피하기 위해 예정된 작업을 계속 진행하고 프로젝트 산출물 개발은 나중으로 미룬다. | 이해관계자에게 모든 프로젝트 산출물을 개발하도록 요청하여 프로젝트 팀이 예정된 활동을 계속할 수 있도록 한다. |  | A | 프로젝트의 모든 관리 계획과 문서가 없을 때, PM은 프로젝트 팀과 함께 계획을 작성하고 문서를 이해관계자와 공유해야 한다. 협력적 계획 개발은 완전성과 동의를 보장한다. 이전 프로젝트 계획 적용(B)은 현재 프로젝트 요구에 맞지 않을 수 있다. 작업 계속 및 산출물 나중 개발(C)은 안내 없는 실행의 위험이 있다. 이해관계자에게 산출물 개발 요청(D)은 책임을 잘못 배정한다.
71 | A team working on a close deployment waits to receive critical information from the customer. The customer keeps postponing sending the information, which is delaying the deployment. What should the project manager have done to prevent the delay? | Involved the customer in the deployment process | Used the sample data already in place | Obtained all critical information ahead of time | Involved upper management in the process |  | C | To prevent delays caused by waiting for critical information from the customer, the project manager should have obtained all critical information ahead of time. Proactive information management—identifying necessary inputs early and establishing clear timelines for delivery—mitigates risks associated with stakeholder dependencies. Involving the customer in the deployment process (A) improves collaboration but does not ensure timely information delivery. Using sample data already in place (B) may lead to inaccurate results. Involving upper management (D) escalates without first addressing the root cause of the information gap. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Scope | Planning | Adopt a Holistic View | Collect Requirements | Traditional PM | 배포가 임박한 팀이 고객으로부터 중요한 정보를 받기를 기다리고 있다. 고객이 정보 제공을 계속 연기하여 배포가 지연되고 있다. 지연을 방지하기 위해 PM은 어떻게 했어야 했는가? | 고객을 배포 프로세스에 참여시켰다. | 이미 준비된 샘플 데이터를 사용했다. | 모든 중요 정보를 사전에 확보했다. | 고위 경영진을 프로세스에 참여시켰다. |  | C | 고객의 중요 정보 대기로 인한 지연을 방지하려면, PM은 사전에 모든 중요 정보를 확보했어야 했다. 선제적 정보 관리—필요한 입력을 조기에 식별하고 납품 일정을 명확히 하는 것—은 이해관계자 의존성과 관련된 리스크를 완화한다. 고객을 배포 프로세스에 참여시키는 것(A)은 협업을 개선하지만 정시 정보 제공을 보장하지 않는다. 샘플 데이터 사용(B)은 부정확한 결과를 초래할 수 있다. 고위 경영진 참여(D)는 정보 격차의 근본 원인을 먼저 해결하지 않고 에스컬레이션한다.
72 | A company is developing a new product. During project planning, a stakeholder from the legal department does not attend any of the project meetings and is not interested in the product design. How should the project manager deal with this situation? | Review the product requirements and update the stakeholder register. | Escalate the issue to the project sponsor and seek assistance. | Review the stakeholder engagement plan and communication strategy. | Engage the project stakeholder and ensure all requirements are captured. |  | C | When a legal department stakeholder does not attend meetings and shows no interest in product design, the project manager should review the stakeholder engagement plan and communication strategy. These documents guide appropriate engagement levels for different stakeholders. Reviewing product requirements and updating the stakeholder register (A) does not address engagement approach. Escalating to the sponsor (B) may be unnecessary. Engaging the stakeholder to capture requirements (D) may not be needed if they have no relevant requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 회사가 새로운 제품을 개발하고 있다. 프로젝트 계획 중 법무부서의 이해관계자가 프로젝트 회의에 참석하지 않으며 제품 설계에 관심이 없다. PM은 이 상황을 어떻게 처리해야 하는가? | 제품 요구사항을 검토하고 이해관계자 등록부를 업데이트한다. | 프로젝트 스폰서에게 이슈를 에스컬레이션하고 지원을 구한다. | 이해관계자 참여 계획과 커뮤니케이션 전략을 검토한다. | 프로젝트 이해관계자를 참여시키고 모든 요구사항이 수집되도록 한다. |  | C | 법무부서 이해관계자가 회의에 참석하지 않고 제품 설계에 관심이 없을 때, PM은 이해관계자 참여 계획과 커뮤니케이션 전략을 검토해야 한다. 이 문서들은 다양한 이해관계자에 대한 적절한 참여 수준을 안내한다. 제품 요구사항 검토 및 등록부 업데이트(A)는 참여 접근법을 다루지 않는다. 스폰서에게 에스컬레이션(B)은 불필요할 수 있다. 요구사항 수집을 위한 이해관계자 참여(D)는 관련 요구사항이 없는 경우 필요하지 않을 수 있다.
73 | The project lead is very concerned about the quality of a specific design feature and how the product will perform. What should the project lead focus on to ensure project success and customer satisfaction? | Confirm that the deliverable will meet the defined acceptance criteria. | Update acceptance criteria while the deliverable is being developed. | Ask stakeholders to test against the defined acceptance criteria. | Plan extra tests if acceptance criteria are not met. |  | A | The correct answer is A. Confirm that the deliverable will meet the defined acceptance criteria. Quality management ensures deliverables meet defined acceptance criteria and standards. The PM should implement appropriate quality processes, conduct reviews, and take corrective actions when quality issues arise. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 프로젝트 리드가 특정 설계 기능의 품질과 제품 성능에 대해 매우 우려하고 있다. 프로젝트 성공과 고객 만족을 보장하기 위해 프로젝트 리드는 무엇에 초점을 맞춰야 하는가? | 산출물이 정의된 인수 기준을 충족할 것인지 확인한다. | 산출물이 개발되는 동안 인수 기준을 업데이트한다. | 이해관계자에게 정의된 인수 기준에 대해 테스트하도록 요청한다. | 인수 기준이 충족되지 않을 경우 추가 테스트를 계획한다. |  | A | 정답은 A이다. 산출물이 정의된 인수 기준을 충족할 것인지 확인한다. 품질 관리는 산출물이 정의된 인수 기준과 표준을 충족하도록 보장한다. PM은 적절한 품질 프로세스를 구현하고, 검토를 수행하며, 품질 이슈 발생 시 시정 조치를 취해야 한다.
74 | A customer complains that the user stories released so far contain too much jargon and do not reflect the expectations of the product. What should the project manager do next? | Ask the senior developer to rewrite all the stories. | Rewrite the stories to include the technical vision of the product. | Engage with the customer and rewrite all the stories. | Request approval from the company director to conduct training for the team. |  | C | When a customer complains that user stories contain too much jargon and do not reflect product expectations, the project manager should engage with the customer and rewrite all the stories. Customer collaboration ensures stories reflect their perspective. Asking the senior developer to rewrite (A) maintains technical bias. Rewriting to include the technical vision (B) addresses the wrong concern. Requesting director approval for training (D) delays resolution. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 고객이 지금까지 릴리스된 사용자 스토리에 전문 용어가 너무 많고 제품의 기대치를 반영하지 못한다고 불만을 제기했다. PM이 다음에 해야 할 일은? | 시니어 개발자에게 모든 스토리를 다시 작성하도록 요청한다. | 제품의 기술적 비전을 포함하도록 스토리를 다시 작성한다. | 고객과 협력하여 모든 스토리를 다시 작성한다. | 회사 이사에게 팀 교육 실시를 위한 승인을 요청한다. |  | C | 고객이 사용자 스토리에 전문 용어가 너무 많고 제품 기대치를 반영하지 못한다고 불만할 때, PM은 고객과 협력하여 모든 스토리를 다시 작성해야 한다. 고객 협업은 스토리가 고객 관점을 반영하도록 보장한다. 시니어 개발자에게 다시 작성 요청(A)은 기술적 편향을 유지한다. 기술적 비전 포함 재작성(B)은 잘못된 우려를 다룬다. 이사에게 교육 승인 요청(D)은 해결을 지연시킨다.
75 | During an iteration review session, some product features are at risk of being canceled due to high operational costs when the product is launched into a production environment. What type of analysis should the project lead have conducted to avoid this situation? | Risk analysis | Benefits analysis | Capacity analysis | Gap analysis |  | A | When product features risk cancellation due to high operational costs in production, the project lead should have conducted a risk analysis to identify and evaluate potential threats—including cost impacts—before they materialized. Risk analysis addresses uncertainty and exposure early. Benefits analysis (B) evaluates value but not threats. Capacity analysis (C) assesses team throughput. Gap analysis (D) compares current versus desired states. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | 이터레이션 리뷰 세션 중 일부 제품 기능이 생산 환경에서의 높은 운영 비용으로 인해 취소될 위험에 처해 있다. 이 상황을 피하기 위해 프로젝트 리드는 어떤 유형의 분석을 수행했어야 하는가? | 리스크 분석 | 편익 분석 | 용량 분석 | 걸 분석 |  | A | 제품 기능이 생산 환경에서의 높은 운영 비용으로 취소 위험에 처할 때, 프로젝트 리드는 리스크 분석을 수행하여 비용 영향을 포함한 잠재적 위협을 식별하고 평가했어야 했다. 리스크 분석은 불확실성과 노출을 조기에 다룬다. 편익 분석(B)은 가치를 평가하지만 위협은 다루지 않는다. 용량 분석(C)은 팀 처리량을 평가한다. 걸 분석(D)은 현재와 바람직한 상태를 비교한다.
76 | An agile team has been struggling to keep up with the planned pace, which is frequently resulting in sprint failures. What should the project manager do to help avoid this situation in the future? | Ask the project sponsor to approve overtime to compensate for the lack of performance while adjusting the plan | Replace junior team members with more experienced ones and negotiate the project scope to compensate for the budget gap | Review the velocity of the team over the last several sprnts and adjust the plan accordingly | Switch to a Kanban approach, implementing features on a first-come, first-serve basis, fostering a sustainable pace |  | C | When an agile team struggles to keep pace with frequent sprint failures, the project manager should review the velocity over the last several sprints and adjust the plan accordingly. Data-driven planning sets realistic expectations. Approving overtime (A) is unsustainable. Replacing junior members (B) disrupts the team. Switching to Kanban (D) changes methodology without addressing velocity issues. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Kanban | Business Environment | Plan and Manage Risk | Risk | Planning | Integrate Sustainability | Identify Risks | Sustainability | 애자일 팀이 계획된 속도를 따라가는 데 어려움을 겪고 있으며, 스프린트 실패가 빈번하게 발생하고 있다. 향후 이 상황을 피하기 위해 PM은 어떻게 해야 하는가? | 프로젝트 스폰서에게 성과 부족을 보상하기 위한 초과 근무를 승인해 달라고 요청하며 계획을 조정한다. | 주니어 팀원을 경험 많은 팀원으로 교체하고 예산 격차를 보전하기 위해 프로젝트 범위를 협상한다. | 지난 여러 스프린트의 팀 벨로시티를 검토하고 계획을 적절히 조정한다. | 칸반 접근법으로 전환하여 선착순 방식으로 기능을 구현하며 지속 가능한 속도를 조성한다. |  | C | 애자일 팀이 빈번한 스프린트 실패로 속도를 따라가지 못할 때, PM은 지난 여러 스프린트의 벨로시티를 검토하고 계획을 적절히 조정해야 한다. 데이터 기반 계획이 현실적인 기대치를 설정한다. 초과 근무 승인(A)은 지속 불가능하다. 주니어 교체(B)는 팀을 혼란시킨다. 칸반으로 전환(D)은 벨로시티 문제를 해결하지 않고 방법론을 변경한다.
77 | A scrum master noticed that one of the team members is afraid to ask questions, does not like to collaborate with other team members, and avoids taking responsibility for their actions. What is the likely reason that would cause a team member to behave that way? | Fear of conflict | Lack of experience | Lack of technical skills | Company culture |  | A | The correct answer is A. Fear of conflict. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 스크럼 마스터가 팀원 중 한 명이 질문하기를 두려워하고, 다른 팀원들과 협업을 싫어하며, 자신의 행동에 대한 책임을 회피한다는 것을 발견했다. 팀원이 이렇게 행동하는 원인으로 가장 가능성이 높은 것은? | 갈등에 대한 두려움 | 경험 부족 | 기술적 스킬 부족 | 회사 문화 |  | A | 정답은 A이다. 갈등에 대한 두려움. 애자일 실무는 반복적 제공, 팀 역량 강화, 지속적 개선을 강조한다. PM은 협업을 촉진하고, 장애물을 제거하며, 팀이 효과적으로 가치를 제공할 수 있도록 보장해야 한다.
78 | During the testing phase of a project, the project manager is made aware that components delivered from a specific vendor have defects. However, the vendor refuses to fix the defects because it will incur additional costs for them. What should the project manager do next? | Ask the vendor for revised timelines and cost needs. | Request cancellation of the contract with the vendor. | Review the acceptance criteria defined with the vendor. | Communicate with the vendor for contract changes. |  | C | When deliverable quality is disputed, the PM should first review the contract and defined acceptance criteria. These agreed-upon standards establish the baseline for evaluating whether deliverables meet requirements. If components fail to meet acceptance criteria, it may constitute a breach of contract. Renegotiating terms (A) is premature without first confirming the breach. Negotiation (C) bypasses verification of the original agreement. Legal action (D) is an extreme measure reserved for after formal confirmation and escalation. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 테스트 단계에서 PM이 특정 벤더가 납품한 구성요소에 결함이 있음을 인지했다. 그러나 벤더는 추가 비용이 발생하므로 결함 수정을 거부한다. PM이 다음에 해야 할 일은? | 벤더에게 수정된 일정과 비용 요구를 요청한다. | 벤더와의 계약 취소를 요청한다. | 벤더와 정의된 인수 기준을 검토한다. | 계약 변경을 위해 벤더와 소통한다. |  | C | 산출물 품질이 분쟁될 때, PM은 먼저 계약과 정의된 인수 기준을 검토해야 한다. 이 합의된 기준이 산출물이 요구사항을 충족하는지 평가하는 기준선을 수립한다. 구성요소가 인수 기준을 충족하지 못하면 계약 위반에 해당할 수 있다. 조건 재협상(A)은 먼저 위반 확인 없이 시기상조이다. 협상(D)은 원래 합의의 검증을 우회한다. 법적 조치(B)는 공식적 확인과 에스컬레이션 후에 예약된 극단적 조치이다.
79 | A project manager has been assigned to a new project. The project sponsor has requested a detailed timeline, but the project includes some deliverables that are not yet clearly defined. Which project management approach should the project manager advise using? | As the project appears to have both agile and predictive elements, a hybrid approach is the best option. | As the project includes elements that are not yet clearly defined, a predictive approach is the best option. | As the project includes elements that are not yet clearly defined, an agile approach is the best option. | As the project sponsor has requested a detailed timeline up front, an agile approach is the best option. |  | A | The correct answer is A. As the project appears to have both agile and predictive elements, a hybrid approach is the best option. Schedule management requires proactive monitoring and timely corrective actions. The PM should analyze schedule impacts, evaluate options, and implement appropriate responses to keep the project on track. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | Scope & Requirements Mgmt | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | PM이 새 프로젝트에 배정되었다. 프로젝트 스폰서가 상세 일정을 요청했지만, 프로젝트에는 아직 명확히 정의되지 않은 산출물이 일부 포함되어 있다. PM이 어떤 프로젝트 관리 접근법을 사용하도록 조언해야 하는가? | 프로젝트에 애자일과 예측형 요소가 모두 있으므로 하이브리드 접근법이 최선의 옵션이다. | 프로젝트에 아직 명확히 정의되지 않은 요소가 있으므로 예측형 접근법이 최선의 옵션이다. | 프로젝트에 아직 명확히 정의되지 않은 요소가 있으므로 애자일 접근법이 최선의 옵션이다. | 프로젝트 스폰서가 사전에 상세 일정을 요청했으므로 애자일 접근법이 최선의 옵션이다. |  | A | 정답은 A이다. 프로젝트에 애자일과 예측형 요소가 모두 있으므로 하이브리드 접근법이 최선의 옵션이다. 일정 관리는 선제적 모니터링과 시의적절한 시정 조치를 요구한다. PM은 일정 영향을 분석하고, 옵션을 평가하며, 프로젝트를 정상 궤도에 유지하기 위한 적절한 대응을 실행해야 한다.
80 | A customer asks the project manager about opportunities to create business value. What should the project manager do first in order to provide the customer with an appropriate response? | Examine the business value throughout the project. | Meet with the product owner to review the backlog. | Ask the team to organize a spike to identify more value. | Meet with the sponsor to review the business case. |  | D | When a customer asks about opportunities to create business value, the project manager should first meet with the sponsor to review the business case. The business case defines value justification and strategic alignment. Examining value throughout the project (A) is ongoing, not a first action. Reviewing the backlog with the PO (B) is tactical. Organizing a spike (C) is an agile exploration technique, not a first response to business value questions. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 고객이 PM에게 비즈니스 가치를 창출할 기회에 대해 문의했다. 고객에게 적절한 응답을 제공하기 위해 PM이 먼저 해야 할 일은? | 프로젝트 전반에 걸쳐 비즈니스 가치를 검토한다. | 제품 소유자와 만나 백로그를 검토한다. | 팀에게 더 많은 가치를 식별하기 위한 스파이크를 조직하도록 요청한다. | 스폰서와 만나 비즈니스 케이스를 검토한다. |  | D | 고객이 비즈니스 가치 창출 기회에 대해 문의할 때, PM은 먼저 스폰서와 만나 비즈니스 케이스를 검토해야 한다. 비즈니스 케이스는 가치 정당성과 전략적 정렬을 정의한다. 프로젝트 전반 가치 검토(A)는 지속적이지만 첫 번째 조치는 아니다. 제품 소유자와 백로그 검토(B)는 전술적이다. 스파이크 조직(C)은 애자일 탐색 기법이지 비즈니스 가치 질문에 대한 첫 번째 대응은 아니다.
81 | A project is ending its fifth out of six iterations. During the iteration review, a customer adds a new regulatory feature that exceeds the capacity of the remaining iteration. What should the project lead do? | Estimate the management to replace the customer service manager. | Register an issue and escalate it to the project sponsor. | Increase the team capacity to finish the project on time. | Invite the stakeholders to discuss a new prioritization. |  | D | When a customer introduces a new regulatory feature that exceeds the capacity of the remaining iteration, the project lead should invite stakeholders to discuss a new prioritization. Agile principles emphasize collaboration, customer feedback, and responding to change—the lead should facilitate a meeting to determine the most valuable features and adjust the scope of the final iteration accordingly. Estimating management to replace the customer service manager (A) is irrelevant to the situation. Registering an issue and escalating to the sponsor (B) is reactive and bypasses the agile team's problem-solving capability. Increasing team capacity to finish on time (C) may not be feasible and does not address the need to reprioritize within existing constraints. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트가 6번의 이터레이션 중 5번째를 마무리하고 있다. 이터레이션 리뷰 중 고객이 남은 이터레이션의 용량을 초과하는 새로운 규제 기능을 추가했다. 프로젝트 리드는 어떻게 해야 하는가? | 고객 서비스 매니저 교체를 위한 관리 비용을 산정한다. | 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션한다. | 제시간에 프로젝트를 마무리하기 위해 팀 용량을 증가시킨다. | 이해관계자를 초대하여 새로운 우선순위를 논의한다. |  | D | 고객이 남은 이터레이션 용량을 초과하는 새 규제 기능을 도입할 때, 프로젝트 리드는 이해관계자를 초대하여 새로운 우선순위를 논의해야 한다. 애자일 원칙은 협업, 고객 피드백, 변화 대응을 강조하며—리드는 가장 가치 있는 기능을 결정하고 최종 이터레이션의 범위를 조정하는 회의를 촉진해야 한다. 고객 서비스 매니저 교체 비용 산정(A)은 상황과 무관하다. 스폰서에게 에스컬레이션(B)은 사후적이며 애자일 팀의 문제 해결 능력을 우회한다. 팀 용량 증가(C)는 실현 불가능할 수 있으며 기존 제약 내 우선순위 재설정의 필요성을 다루지 않는다.
82 | A project manager at a large corporation has been assigned to oversee a customer experience project. Within the project, customer satisfaction is a big issue and there are many unresolved customer queries on a daily basis. The project manager has been informed that the customer service team is overwhelmed with these unresolved queries. Which two actions should the project manager take to correct this problem? (Choose two) | Confirm the issues truly exist by conducting a survey and other analyses that may detect the real issue. | Deploy solutions that will track, prioritize, and resolve queries as soon as possible. | Ask senior management to replace the customer service manager with a more qualified one. | Contact the customers in batches and inform them that the issues are being worked on currently. | Request that the customer service team prioritizes work on queries that are received this week. | A, C | When facing a customer experience project with many unresolved queries, the project manager should take two actions: confirm the issues truly exist by conducting a survey and analysis to detect the real problems (A), and ask senior management to replace the customer service manager with a more qualified one (C). Data-driven confirmation ensures targeted problem identification, while replacing the underperforming manager addresses the leadership gap causing unresolved queries. Deploying tracking solutions (B) treats symptoms without addressing root cause leadership issues. Contacting customers about work in progress (D) manages expectations but does not resolve underlying issues. Prioritizing only this week's queries (E) is too narrow in scope. | Process | Manage Project Issues | Project Work | Navigate Complexity | Agile | Agile General Practices | Business Environment | Remove Impediments and Manage Issues | Governance | Monitoring & Controlling | Embed Quality | Monitor and Control Project Performance | Traditional PM | 대기업의 PM이 고객 경험 프로젝트를 감독하도록 배정되었다. 프로젝트 내에서 고객 만족이 큰 이슈이며 매일 많은 미해결 고객 질의가 있다. PM은 고객 서비스 팀이 이 미해결 질의로 과부하 상태임을 통보받았다. 이 문제를 해결하기 위해 PM이 취해야 할 두 가지 조치는? (2개 선택) | 설문 조사 및 기타 분석을 실시하여 실제 이슈를 확인한다. | 가능한 한 빨리 질의를 추적, 우선순위화, 해결할 솔루션을 배포한다. | 고위 경영진에게 고객 서비스 매니저를 더 능력 있는 사람으로 교체해 달라고 요청한다. | 고객에게 일괄적으로 연락하여 이슈가 현재 처리 중임을 알린다. | 고객 서비스 팀에게 이번 주에 들어온 질의를 우선적으로 처리하도록 요청한다. | A, C | 고객 경험 프로젝트에서 많은 미해결 질의가 있을 때, PM은 두 가지 조치를 취해야 한다: 설문 조사 및 분석을 실시하여 실제 문제를 확인하고(A), 고위 경영진에게 더 자격이 있는 사람으로 고객 서비스 매니저를 교체할 것을 요청한다(C). 데이터 기반 확인은 목표에 맞는 문제 식별을 보장하고, 실적이 저조한 관리자 교체는 미해결 질의를 야기하는 리더십 격차를 해결한다. 추적 솔루션 배포(B)는 근본 원인인 리더십 문제를 해결하지 않고 증상만 치료한다. 고객에게 진행 중 연락(D)은 기대치를 관리하지만 근본 이슈를 해결하지 않는다. 이번 주 질의만 우선화(E)는 범위가 너무 좁다.
83 | A project manager wants to ensure that the project acceptance criteria are met for all project deliverables. What should the project manager do to accomplish this? | Discuss project acceptance criteria with the project sponsor before the execution phase. | Schedule regular meetings with project stakeholders to make sure they are satisfied. | Include project stakeholder expectations and needs while creating project acceptance criteria. | Create a statement of work (SOW) and ensure it remains unchanged during the project life cycle. |  | C | To ensure project acceptance criteria are met for all deliverables, the project manager should include project stakeholder expectations and needs while creating acceptance criteria. Stakeholder input ensures deliverables meet agreed standards and satisfy requirements. Discussing criteria only with the sponsor (A) excludes other stakeholders. Scheduling regular stakeholder satisfaction meetings (B) monitors but does not define criteria. Creating an unchangeable SOW (D) is rigid and impractical. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | PM이 모든 프로젝트 산출물의 프로젝트 인수 기준이 충족되도록 보장하고자 한다. 이를 달성하기 위해 PM은 어떻게 해야 하는가? | 실행 단계 전에 프로젝트 스폰서와 프로젝트 인수 기준을 논의한다. | 프로젝트 이해관계자와 정기적으로 만나 만족도를 확인한다. | 프로젝트 인수 기준을 만들 때 프로젝트 이해관계자의 기대치와 요구를 포함한다. | SOW(작업기술서)를 작성하고 프로젝트 수명 주기 동안 변경되지 않도록 보장한다. |  | C | 모든 산출물의 프로젝트 인수 기준이 충족되도록 보장하려면, PM은 인수 기준을 만들 때 프로젝트 이해관계자의 기대치와 요구를 포함해야 한다. 이해관계자 의견이 산출물이 합의된 기준을 충족하고 요구를 만족시키도록 보장한다. 스폰서와만 기준 논의(A)는 다른 이해관계자를 배제한다. 정기 이해관계자 만족도 회의(B)는 모니터링하지만 기준을 정의하지 않는다. 변경 불가한 SOW 작성(D)은 경직되고 비현실적이다.
84 | A project manager assigned to an engineering construction project is receiving questions from the site engineers. Several questions are related to carrying out activities to meet timelines that compromise the work crew's safety. When reviewing these questions, the project manager realizes that the engineers do not feel empowered to make decisions. How should the project manager address this? | Reinforce to all engineers the company vision of a safety-first approach to project activities. | Email the company vision to the engineers and tell them they need to meet deadlines | Ensure all engineers are aware that questions should only be submitted in their weekly reports. | Consult the previous project manager to discuss how they managed these questions. |  | A | The PM should remind engineers that safety is a priority and that they have both the authority and responsibility to raise concerns about unsafe practices. Creating a collaborative environment where team members feel empowered to speak up is essential. The PM should also communicate with stakeholders to ensure the project schedule doesn't compromise quality and safety standards. Empowering decision-making at the team level is a core PMI principle. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Quality Management | People | Lead the Project Team | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 엔지니어링 건설 프로젝트에 배정된 프로젝트 관리자가 현장 엔지니어들로부터 질문을 받고 있다. 여러 질문이 작업 인력의 안전을 저해하면서 일정을 맞추기 위한 활동 수행에 관한 것이다. 이러한 질문을 검토하면서 프로젝트 관리자는 엔지니어들이 의사결정 권한이 있다고 느끼지 못한다는 것을 깨닫는다. 프로젝트 관리자는 이를 어떻게 해결해야 하는가? | 모든 엔지니어에게 프로젝트 활동에 대한 안전 최우선 접근 방식이라는 회사 비전을 재강조한다. | 엔지니어들에게 회사 비전을 이메일로 보내고 마감일을 맞춰야 한다고 말한다. | 모든 엔지니어에게 질문은 주간 보고서에서만 제출해야 한다는 것을 인지시킨다. | 이전 프로젝트 관리자와 상담하여 이러한 질문을 어떻게 관리했는지 논의한다. |  | A | PM은 엔지니어들에게 안전이 최우선이며 안전하지 않은 관행에 대해 우려를 제기할 권한과 책임이 있음을 상기시켜야 한다. 팀원이 자유롭게 발언할 수 있는 협업 환경 조성이 필수적이다. PM은 또한 이해관계자에게 프로젝트 일정이 품질과 안전 기준을 저해하지 않도록 소통해야 한다. 팀 수준의 의사결정 권한 부여는 PMI 핵심 원칙이다.
85 | A project manager is managing an agile project for the first time. Early on, the project manager discovers the team is struggling to agree on the scope of a feature during a sprint. How should the project manager help the team resolve the issue? | Ask the team to log the story in the product backlog and move on to the next feature. | Encourage the team to collaborate to resolve their understanding of the feature. | Discuss this with the team and decide what the scope of the feature should be. | Direct the senior-most member to determine the scope on behalf of the team. |  | B | When an agile team struggles to agree on feature scope during a sprint, the project manager should encourage the team to collaborate to resolve their understanding of the feature. Agile emphasizes teamwork, open communication, and shared understanding—the PM's role is to facilitate a collaborative environment where all voices are heard. Logging the story in the backlog and moving on (A) avoids the issue. Discussing and deciding the scope as a group with the PM directing (C) involves too much PM control. Directing the senior-most member to decide (D) undermines team self-organization. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 처음으로 애자일 프로젝트를 관리하고 있다. 초기에 프로젝트 관리자는 팀이 스프린트 중 기능의 범위에 대해 합의하지 못하고 있음을 발견한다. 프로젝트 관리자는 팀이 이 문제를 해결하도록 어떻게 도와야 하는가? | 팀에게 스토리를 제품 백로그에 기록하고 다음 기능으로 넘어가도록 요청한다. | 팀이 협력하여 기능에 대한 이해를 해결하도록 격려한다. | 팀과 이를 논의하고 기능의 범위를 결정한다. | 가장 선임인 팀원에게 팀을 대신하여 범위를 결정하도록 지시한다. |  | B | 애자일 팀이 스프린트 중 기능 범위에 대해 합의하지 못할 때, 프로젝트 관리자는 팀이 협력하여 기능에 대한 이해를 해결하도록 격려해야 한다. 애자일은 팀워크, 열린 소통, 공유된 이해를 강조하며—PM의 역할은 모든 목소리가 들리는 협업 환경을 촉진하는 것이다. 백로그에 기록하고 넘어가기(A)는 문제를 회피한다. PM이 범위를 결정(C)하는 것은 PM의 과도한 통제이다. 선임에게 결정 지시(D)는 팀의 자기 조직화를 훼손한다.
86 | A company is engaged in a transformation journey, and the project manager for this endeavor is new to the project. During one of the project status update meetings, a key stakeholder, who is also the project manager's functional manager, is dissatisfied with the work in progress and points to the project manager. What should the project manager do? | Listen carefully and show understanding of the growing needs of the functional manager. | Show the functional manager that the progress is on time based on the schedule. | Admit that the functional manager is right and promise to rectify the situation immediately. | Schedule a one-on-one meeting with the functional manager to prove the project is on time. |  | A | When a key stakeholder who is also the PM's functional manager expresses dissatisfaction with work in progress during a status update, the project manager should listen carefully and show understanding of the functional manager's growing needs. Active listening demonstrates emotional intelligence and helps identify the real concern behind the dissatisfaction. Showing the project is on time (B) is defensive and may miss the stakeholder's actual concern. Admitting fault and promising to rectify immediately (C) is premature without understanding the issue. Scheduling a one-on-one to prove the project is on time (D) is also defensive. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 회사가 변혁 여정에 참여하고 있으며, 이 사업의 프로젝트 관리자는 프로젝트에 새로 합류했다. 프로젝트 상태 업데이트 회의 중 핵심 이해관계자이자 프로젝트 관리자의 기능 관리자가 진행 중인 작업에 불만을 표시하며 프로젝트 관리자를 지목한다. 프로젝트 관리자는 어떻게 해야 하는가? | 주의 깊게 경청하고 기능 관리자의 증가하는 요구에 대한 이해를 보여준다. | 기능 관리자에게 일정 기준으로 진행이 정상임을 보여준다. | 기능 관리자가 옳다고 인정하고 상황을 즉시 시정하겠다고 약속한다. | 기능 관리자와 일대일 회의를 예약하여 프로젝트가 정상 진행 중임을 증명한다. |  | A | 핵심 이해관계자이자 PM의 기능 관리자가 상태 업데이트 중 진행 작업에 불만을 표시할 때, 프로젝트 관리자는 주의 깊게 경청하고 기능 관리자의 증가하는 요구에 대한 이해를 보여야 한다. 적극적 경청은 감성지능을 입증하고 불만 뒤의 실제 우려를 파악하는 데 도움이 된다. 정상 진행임을 보여주기(B)는 방어적이며 이해관계자의 실제 우려를 놓칠 수 있다. 잘못 인정하고 즉시 시정 약속(C)은 문제를 이해하지 않은 채 성급하다. 일대일로 정상 진행 증명(D)도 방어적이다.
87 | A project manager is assigned to a project where a vendor has been engaged to build a new system. One week before user acceptance testing (UAT) is scheduled, the vendor informs the project manager that they can only deliver half of the promised functions by the UAT start date. What should the project manager do next? | Communicate with the vendor and project team and explore possibilities lor resolving the issue | Escalate to management and prepare tor project closure by canceling the contract with this vendor | Adjust the protect schedule to accommodate the current development progress of the vendor | Wait until the vendor cannot deliver and then invoke liquidated damages based on the contract |  | A | When a vendor informs the PM one week before UAT that they can only deliver half of the promised functions, the project manager should communicate with the vendor and project team to explore possibilities for resolving the issue. Collaborative problem-solving may yield options such as negotiating a new delivery schedule, modifying scope, or finding alternatives to meet objectives. Escalating to management and canceling the contract (B) is premature and destructive. Adjusting the schedule to accommodate the vendor (C) accepts the delay without exploring solutions. Waiting to invoke liquidated damages (D) is passive and risks further delay. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 벤더가 새 시스템 구축에 참여한 프로젝트에 배정되어 있다. 사용자 인수 테스트(UAT) 예정일 1주 전에 벤더가 프로젝트 관리자에게 UAT 시작일까지 약속한 기능의 절반만 인도할 수 있다고 알린다. 프로젝트 관리자가 다음에 해야 할 일은? | 벤더 및 프로젝트 팀과 소통하여 문제 해결 가능성을 탐색한다. | 경영진에게 에스컬레이션하고 이 벤더와의 계약을 취소하여 프로젝트 종료를 준비한다. | 벤더의 현재 개발 진행에 맞게 프로젝트 일정을 조정한다. | 벤더가 인도하지 못할 때까지 기다린 후 계약에 따른 손해배상금을 적용한다. |  | A | 벤더가 UAT 1주 전에 약속한 기능의 절반만 인도할 수 있다고 알릴 때, 프로젝트 관리자는 벤더 및 프로젝트 팀과 소통하여 문제 해결 가능성을 탐색해야 한다. 협업적 문제 해결은 새 인도 일정 협상, 범위 수정, 목표 달성을 위한 대안 모색 등의 옵션을 만들 수 있다. 경영진에 에스컬레이션 및 계약 취소(B)는 성급하고 파괴적이다. 벤더에 맞춰 일정 조정(C)은 해결책 탐색 없이 지연을 수용한다. 손해배상금 적용 대기(D)는 소극적이며 추가 지연을 초래한다.
88 | After a project review meeting, a key stakeholder tells another stakeholder that they do not trust the project status report. The second stakeholder approaches the project manager and mentions the conversation. What should the project manager do? | Request that the sponsor ask the key stakeholder to be attentive during the project review meeting. | Email the status report to all stakeholders and ask them to review it and provide feedback. | Schedule a meeting with the key stakeholder to address the issue and obtain direct feedback. | Present the status report in a chart and assume that everyone understands the report. |  | C | When a key stakeholder tells another stakeholder they do not trust the project status report, the project manager should schedule a meeting with the key stakeholder to address the issue and obtain direct feedback. Direct engagement identifies whether the problem is content, format, timing, or interpretation of the report. Asking the sponsor to intervene (A) is indirect and escalatory. Emailing the report to all stakeholders for feedback (B) changes the format without understanding the concern. Presenting the report as a chart (D) assumes the format is the issue without confirming. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 검토 회의 후, 핵심 이해관계자가 다른 이해관계자에게 프로젝트 상태 보고서를 신뢰하지 않는다고 말했다. 두 번째 이해관계자가 프로젝트 관리자에게 그 대화를 언급했다. 프로젝트 관리자는 어떻게 해야 하는가? | 스폰서에게 핵심 이해관계자가 프로젝트 검토 회의 중 주의를 기울이도록 요청해 달라고 한다. | 모든 이해관계자에게 상태 보고서를 이메일로 보내고 검토 후 피드백을 요청한다. | 핵심 이해관계자와 회의를 예약하여 문제를 다루고 직접 피드백을 받는다. | 상태 보고서를 차트로 제시하고 모든 사람이 보고서를 이해한다고 가정한다. |  | C | 핵심 이해관계자가 다른 이해관계자에게 프로젝트 상태 보고서를 신뢰하지 않는다고 말했을 때, 프로젝트 관리자는 핵심 이해관계자와 회의를 예약하여 문제를 다루고 직접 피드백을 받아야 한다. 직접적인 참여가 문제가 내용인지, 형식인지, 시기인지, 해석인지를 파악한다. 스폰서에게 개입 요청(A)은 간접적이고 에스컬레이션이다. 전 이해관계자에게 이메일 피드백 요청(B)은 우려를 확인하지 않고 형식을 바꾼다. 차트로 제시(D)는 확인 없이 형식이 문제라고 가정한다.
89 | A project manager has team members around the world in many different time zones. Project work frequently stalls because people in one office need to wait until another office is awake to have questions answered. What should the project manager have done to avoid this? | Planned and scheduled tasks and work packages to overcome geographical and time zone challenges | Used communication tools, such as video conferencing so different offices could communicate. | Ensured that the project would be the highest priority for all team members | Learned more about how each team member prefers to communicate before assigning project work |  | A | When project work stalls because teams in different time zones must wait for answers, the project manager should have planned and scheduled tasks and work packages to overcome geographical and time zone challenges. Proactive scheduling minimizes dependencies. Using video conferencing (B) improves communication tools, not task planning. Making the project highest priority (C) does not address scheduling. Learning communication preferences (D) helps but does not solve workflow dependency. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자의 팀원이 전 세계 여러 시간대에 분포해 있다. 한 사무실의 사람들이 질문에 대한 답변을 받기 위해 다른 사무실이 업무를 시작할 때까지 기다려야 하기 때문에 프로젝트 작업이 자주 중단된다. 프로젝트 관리자가 이를 피하기 위해 무엇을 했어야 하는가? | 지리적 및 시간대 문제를 극복하기 위해 작업 및 작업 패키지를 계획하고 일정을 수립한다. | 다른 사무실이 소통할 수 있도록 화상 회의 같은 커뮤니케이션 도구를 사용한다. | 프로젝트가 모든 팀원에게 최우선 순위가 되도록 보장한다. | 프로젝트 작업을 배정하기 전에 각 팀원이 선호하는 소통 방식을 더 많이 파악한다. |  | A | 서로 다른 시간대의 팀이 답변을 기다려야 해서 프로젝트 작업이 중단될 때, 프로젝트 관리자는 지리적 및 시간대 문제를 극복하기 위해 작업 및 작업 패키지를 계획하고 일정을 수립했어야 한다. 사전 일정 수립이 의존성을 최소화한다. 화상 회의 사용(B)은 커뮤니케이션 도구를 개선하지만 작업 계획이 아니다. 최우선 순위로 만들기(C)는 일정 수립을 해결하지 않는다. 소통 선호도 파악(D)은 도움이 되지만 워크플로 의존성을 해결하지 않는다.
90 | A project manager leads an agile development project. During the sprint planning meeting, the development team expresses concerns that the proposed scope of the next sprint is much larger than expected given the current resource allocation. The project manager believes the scope is essential to meet the project milestones. How should the project manager approach negotiating an agreement with the team to ensure the project remains on track? | Allocate additional resources to the development team to ensure the original scope can be completed on time. | Suggest prioritizing the most critical features for the next sprint as well as reevaluating the remaining scope. | Insist on keeping the original scope and explain the importance of meeting all the project milestones on time. | Agree on reducing the scope to match the team ' s resources and plan to add the removed items to future sprints. |  | B | When the development team expresses concerns that the next sprint scope is too large for current resource allocation, the project manager should suggest prioritizing the most critical features for the next sprint and reevaluating remaining scope. Agile prioritization focuses on value delivery within capacity. Allocating additional resources mid-sprint (A) contradicts agile principles. Insisting on the original scope (C) ignores team capacity. Reducing scope without prioritization (D) lacks strategic thinking. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 프로젝트 관리자가 애자일 개발 프로젝트를 이끌고 있다. 스프린트 계획 회의 중 개발팀이 현재 자원 배정을 고려할 때 다음 스프린트의 제안된 범위가 예상보다 훨씬 크다는 우려를 표명한다. 프로젝트 관리자는 범위가 프로젝트 마일스톤 달성에 필수적이라고 생각한다. 프로젝트 관리자는 프로젝트가 정상 궤도에 있도록 팀과의 합의 협상에 어떻게 접근해야 하는가? | 개발팀에 추가 자원을 배정하여 원래 범위를 정시에 완료할 수 있도록 한다. | 다음 스프린트를 위해 가장 중요한 기능의 우선순위를 정하고 나머지 범위를 재평가하도록 제안한다. | 원래 범위를 유지하고 모든 프로젝트 마일스톤을 정시에 달성하는 것의 중요성을 설명한다. | 팀의 자원에 맞게 범위를 축소하기로 합의하고 제외된 항목을 향후 스프린트에 추가할 계획을 세운다. |  | B | 개발팀이 다음 스프린트 범위가 현재 자원 배정에 비해 너무 크다고 우려를 표명할 때, 프로젝트 관리자는 다음 스프린트를 위해 가장 중요한 기능의 우선순위를 정하고 나머지 범위를 재평가하도록 제안해야 한다. 애자일 우선순위 지정은 역량 내 가치 전달에 초점을 맞춘다. 스프린트 중간에 추가 자원 배정(A)은 애자일 원칙에 반한다. 원래 범위 고수(C)는 팀 역량을 무시한다. 우선순위 없이 범위 축소(D)는 전략적 사고가 부족하다.
91 | A supplier is hired to provide information security services for a project. The supplier has decided not to provide this service any longer since they have not been paid on time. Their services are critical and this decision will affect the outcome of the project. What should the project manager do to address this issue? | inform the relevant stakeholders of this challenge and seek their support | Negotiate the payments with the supplier and remind them of their long-term association | Penalize the supplier according to the contract ' s service level agreement (SLA) | Hire another information security supplier and incentivize them for speedy delivery |  | A | When a critical information security supplier stops service due to late payments and the project outcome is at risk, the project manager should inform relevant stakeholders of the challenge and seek their support. Transparent communication with sponsors, customers, and functional managers enables collaborative resolution and exploration of alternatives. Negotiating payments while reminding of long-term association (B) may not resolve the underlying payment issue. Penalizing per the SLA (C) escalates conflict. Hiring a replacement supplier with incentives (D) may be costly and time-consuming. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 공급업체가 프로젝트에 정보 보안 서비스를 제공하기 위해 고용되었다. 공급업체는 적시에 지급받지 못했기 때문에 더 이상 이 서비스를 제공하지 않기로 결정했다. 그들의 서비스는 필수적이며 이 결정은 프로젝트 결과에 영향을 미칠 것이다. 프로젝트 관리자가 이 문제를 해결하기 위해 해야 할 일은? | 관련 이해관계자에게 이 과제를 알리고 그들의 지원을 구한다. | 공급업체와 지급을 협상하고 장기적 관계를 상기시킨다. | 계약의 서비스 수준 협약(SLA)에 따라 공급업체에 벌칙을 부과한다. | 다른 정보 보안 공급업체를 고용하고 신속한 인도를 위해 인센티브를 제공한다. |  | A | 필수적인 정보 보안 공급업체가 지급 지연으로 서비스를 중단하고 프로젝트 결과가 위험에 처할 때, 프로젝트 관리자는 관련 이해관계자에게 과제를 알리고 그들의 지원을 구해야 한다. 스폰서, 고객, 기능 관리자와의 투명한 소통이 협업적 해결과 대안 모색을 가능하게 한다. 장기 관계 상기하며 지급 협상(B)은 근본적인 지급 문제를 해결하지 못할 수 있다. SLA에 따른 벌칙 부과(C)는 갈등을 고조시킨다. 인센티브 부여로 대체 공급업체 고용(D)은 비용이 많이 들고 시간이 소요될 수 있다.
92 | A project manager recently took over an ongoing project. Within a few weeks on the project, the project manager discovers that there are continuous change requests from different project end users. What is the probable cause for this? | Undefined change control process | Incomplete requirements | Unidentified project risks | Improper work breakdown structure (WBS) |  | B | When continuous change requests come from multiple end users, the probable cause is incomplete requirements. Gaps in initial requirements elicitation drive users to discover missing needs as they see deliverables. An undefined change control process (A) allows changes but does not explain why they arise. Unidentified risks (C) cause issues but not widespread scope changes. An improper WBS (D) results from poor requirements, not the other way around. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 프로젝트 관리자가 최근 진행 중인 프로젝트를 인수했다. 프로젝트에 합류한 지 몇 주 내에 프로젝트 관리자는 여러 프로젝트 최종 사용자로부터 지속적인 변경 요청이 있음을 발견한다. 이에 대한 가능한 원인은 무엇인가? | 정의되지 않은 변경 통제 프로세스 | 불완전한 요구사항 | 식별되지 않은 프로젝트 리스크 | 부적절한 작업 분류 체계(WBS) |  | B | 여러 최종 사용자로부터 지속적인 변경 요청이 올 때, 가능한 원인은 불완전한 요구사항이다. 초기 요구사항 도출의 공백이 사용자가 인도물을 보면서 누락된 요구를 발견하게 만든다. 정의되지 않은 변경 통제 프로세스(A)는 변경을 허용하지만 왜 발생하는지 설명하지 않는다. 식별되지 않은 리스크(C)는 문제를 야기하지만 광범위한 범위 변경은 아니다. 부적절한 WBS(D)는 부족한 요구사항의 결과이지 그 반대가 아니다.
93 | During a regular review, the project manager of an agile project realizes that a key stakeholder is missing critical information about some features being developed. In order to improve communications and reduce the risk of deploying the wrong features, what should the project manager do? | Invite the stakeholder to the regular " show and tell " sessions so the stakeholder is aware of project progress and feedback can be gathered. | Include the stakeholder on regular project communications so that decisions can be followed up closely. | Conduct stakeholder remapping, evaluate stakeholders by their level of influence and interest on the project, and communicate accordingly. | Assess the stakeholder ' s needs and communication style and propose a tailored approach with regular status reports and progress meetings. |  | A | When a key stakeholder is missing critical information about features being developed in an agile project, the project manager should invite the stakeholder to regular "show and tell" sessions. Sprint reviews provide direct visibility into features and enable feedback. Including them on regular communications (B) provides updates but not interactive feedback. Conducting stakeholder remapping (C) does not involve the stakeholder in delivery. Assessing needs and proposing tailored reports (D) may help but lacks the interactive element. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Hybrid/Tailoring | 정기 검토 중 애자일 프로젝트의 프로젝트 관리자는 핵심 이해관계자가 개발 중인 일부 기능에 대한 중요한 정보를 놓치고 있음을 인식한다. 잘못된 기능 배포 리스크를 줄이고 커뮤니케이션을 개선하기 위해 프로젝트 관리자가 해야 할 일은? | 이해관계자를 정기 '시연(show and tell)' 세션에 초대하여 프로젝트 진행 상황을 인지하고 피드백을 수집할 수 있도록 한다. | 이해관계자를 정기 프로젝트 커뮤니케이션에 포함하여 의사결정을 면밀히 추적할 수 있도록 한다. | 이해관계자 재매핑을 실시하고, 프로젝트에 대한 영향력과 관심 수준별로 이해관계자를 평가하고 그에 따라 소통한다. | 이해관계자의 요구와 소통 스타일을 평가하고 정기 상태 보고서와 진행 회의를 포함한 맞춤형 접근 방식을 제안한다. |  | A | 애자일 프로젝트에서 핵심 이해관계자가 개발 중인 기능에 대한 중요한 정보를 놓치고 있을 때, 프로젝트 관리자는 이해관계자를 정기 '시연(show and tell)' 세션에 초대해야 한다. 스프린트 리뷰는 기능에 대한 직접적인 가시성을 제공하고 피드백을 가능하게 한다. 정기 커뮤니케이션에 포함(B)은 업데이트를 제공하지만 상호작용적 피드백은 아니다. 이해관계자 재매핑(C)은 이해관계자를 인도에 참여시키지 않는다. 요구 평가 및 맞춤 보고서 제안(D)은 도움이 될 수 있지만 상호작용적 요소가 부족하다.
94 | Project team member A has a conflict with project team member B. The project manager believes project team member A's behavior is unacceptable. However, project team member A believes their behavior is appropriate. What should the project manager do? | Add an agenda item to the next team meeting to manage the conflict. | Ask the project team member to review the team charter and follow up with a one-on-one meeting. | Review the resource requirements to determine if the project team member is a good fit. | Review the roles and responsibilities of each team member with the team. |  | B | When two team members are in conflict and one exhibits behavior they consider appropriate while the PM considers it unacceptable, the project manager should ask the team member to review the team charter and follow up with a one-on-one meeting. The team charter defines behavioral norms, values, and conflict resolution procedures, providing an objective reference point. The private meeting allows the PM to address the behavior directly without public escalation. Adding an agenda item to a team meeting (A) risks publicly escalating the issue. Reviewing resource requirements for fit (C) is premature and avoids addressing the behavioral concern. Reviewing roles and responsibilities with the team (D) is generic and does not target the specific conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 팀원 A가 프로젝트 팀원 B와 갈등을 겪고 있다. 프로젝트 관리자는 프로젝트 팀원 A의 행동이 수용 불가하다고 본다. 그러나 프로젝트 팀원 A는 자신의 행동이 적절하다고 생각한다. 프로젝트 관리자는 어떻게 해야 하는가? | 다음 팀 회의에 안건을 추가하여 갈등을 관리한다. | 프로젝트 팀원에게 팀 헌장을 검토하도록 요청하고 일대일 회의로 후속 조치한다. | 자원 요구사항을 검토하여 해당 프로젝트 팀원이 적합한지 판단한다. | 팀과 함께 각 팀원의 역할과 책임을 검토한다. |  | B | 두 팀원이 갈등을 겪고 한 명이 자신의 행동이 적절하다고 생각하지만 PM이 수용 불가하다고 볼 때, 프로젝트 관리자는 팀원에게 팀 헌장을 검토하도록 요청하고 일대일 회의로 후속 조치해야 한다. 팀 헌장은 행동 규범, 가치, 갈등 해결 절차를 정의하여 객관적 기준점을 제공한다. 비공개 회의는 공개적 에스컬레이션 없이 행동을 직접 다룰 수 있게 한다. 팀 회의에 안건 추가(A)는 공개적 에스컬레이션 위험이 있다. 적합성 판단을 위한 자원 요구사항 검토(C)는 성급하며 행동 우려를 회피한다. 팀 전체와 역할/책임 검토(D)는 일반적이며 특정 갈등을 겨냥하지 않는다.
95 | An agile project started 6 months ago. Since the beginning of the project, there have been disagreements among team members regarding daily meetings since some of the team members are not available at the same time. The project manager is convinced an agile team should be self-organizing, and that meeting times should be worked out by the team. What should the project manager do? | Establish a project schedule | Recognize the team ' s contributions | Establish a team charter | Assign a team leader |  | C | When an agile team has had 6 months of disagreements about daily meeting times and the PM believes in self-organization, the project manager should establish a team charter. A team charter formalizes agreements including meeting norms. Establishing a project schedule (A) is broader. Recognizing contributions (B) does not address the scheduling disagreement. Assigning a team leader (D) undermines self-organization. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 프로젝트가 6개월 전에 시작되었다. 프로젝트 시작 이래로 일부 팀원이 같은 시간에 참석할 수 없어 일일 회의에 대한 팀원 간 의견 충돌이 있었다. 프로젝트 관리자는 애자일 팀이 자기 조직화되어야 하며 회의 시간은 팀이 스스로 정해야 한다고 확신한다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 일정을 수립한다. | 팀의 기여를 인정한다. | 팀 헌장을 수립한다. | 팀 리더를 지정한다. |  | C | 애자일 팀이 6개월 동안 일일 회의 시간에 대한 의견 충돌이 있고 PM이 자기 조직화를 믿을 때, 프로젝트 관리자는 팀 헌장을 수립해야 한다. 팀 헌장은 회의 규범을 포함한 합의를 공식화한다. 프로젝트 일정 수립(A)은 더 광범위하다. 기여 인정(B)은 일정 의견 충돌을 다루지 않는다. 팀 리더 지정(D)은 자기 조직화를 훼손한다.
96 | One of a project manager's team members is continuously improving. This team member has been a role model and mentor to others in the organization. How should the project manager acknowledge this team member's commitment? | Send this person to a meeting to negotiate the scope with the client | Appreciate this team member's performance throughout the project life cycle | Promote this team member to a coaching role after this project is completed | Document it in the team member's end of year performance review |  | B | When a team member continuously improves and serves as a role model and mentor, the project manager should appreciate their performance throughout the project life cycle. Ongoing recognition motivates continued excellence. Sending them to negotiate scope (A) is unrelated to acknowledgment. Promoting to a coaching role after the project (C) delays recognition. Documenting in the year-end review (D) is too late and formal. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자의 팀원 중 한 명이 지속적으로 발전하고 있다. 이 팀원은 조직 내 다른 사람들에게 롤모델이자 멘토였다. 프로젝트 관리자는 이 팀원의 헌신을 어떻게 인정해야 하는가? | 이 사람을 클라이언트와의 범위 협상 회의에 보낸다. | 프로젝트 수명 주기 전반에 걸쳐 이 팀원의 성과를 인정한다. | 이 프로젝트 완료 후 이 팀원을 코칭 역할로 승진시킨다. | 팀원의 연말 성과 평가에 기록한다. |  | B | 팀원이 지속적으로 발전하고 롤모델이자 멘토 역할을 할 때, 프로젝트 관리자는 프로젝트 수명 주기 전반에 걸쳐 그의 성과를 인정해야 한다. 지속적인 인정이 지속적인 우수성을 동기부여한다. 범위 협상에 보내기(A)는 인정과 무관하다. 프로젝트 후 코칭 역할 승진(C)은 인정을 지연시킨다. 연말 성과 평가에 기록(D)은 너무 늦고 공식적이다.
97 | A global and complex project is in the execution phase. Recently, there were executive board changes, and the executive sponsor is transitioning to a new role. The outgoing sponsor asked the project manager to speed up project completion of the current phase to ensure successful onboarding of the new sponsor. What should the project manager do? | Review the stakeholder engagement plan and determine the best course of action to take. | Use the contingency budget to implement compression techniques to finish the current project phase early. | Notify the outgoing sponsor that the project needs to be put on hold until the new sponsor is onboarded. | Submit a change request to the change control board (CCB) to modify the end date of the current phase. |  | A | The correct answer is A. Review the stakeholder engagement plan and determine the best course of action to take. The project sponsor provides strategic direction and support. The PM should maintain effective communication and alignment with the sponsor to ensure project success. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | General | General PM Principles | Business Environment | Support Organizational Change | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 글로벌하고 복잡한 프로젝트가 실행 단계에 있다. 최근 경영 이사회 변경이 있었고, 임원 스폰서가 새로운 역할로 전환 중이다. 퇴임하는 스폰서가 프로젝트 관리자에게 새 스폰서의 성공적인 온보딩을 보장하기 위해 현재 단계의 프로젝트 완료를 가속화해 달라고 요청했다. 프로젝트 관리자는 어떻게 해야 하는가? | 이해관계자 참여 계획을 검토하고 최선의 조치 방향을 결정한다. | 예비 예산을 사용하여 현재 프로젝트 단계를 조기에 완료하기 위한 일정 압축 기법을 시행한다. | 퇴임하는 스폰서에게 새 스폰서가 온보딩될 때까지 프로젝트를 보류해야 한다고 알린다. | 현재 단계의 종료일을 수정하기 위해 변경통제위원회(CCB)에 변경 요청을 제출한다. |  | A | 정답은 A이다. 이해관계자 참여 계획을 검토하고 최선의 조치 방향을 결정한다. 프로젝트 스폰서는 전략적 방향과 지원을 제공한다. PM은 프로젝트 성공을 보장하기 위해 스폰서와 효과적인 커뮤니케이션과 정렬을 유지해야 한다.
98 | A junior team member escalates an issue to the project manager about another member's interpersonal skills causing the team to be less effective. What should the project manager do first? | Have the team members resolve the issue on their own. | Highlight the impact of their behavior and motivate the team member to make improvements. | Document the escalated issue and address it at the end of the project. | Gather information and find the root cause of the problem. |  | D | When a junior team member escalates an issue about another member's interpersonal skills affecting team effectiveness, the project manager should first gather information and find the root cause of the problem. Understanding the nature and extent of the issue enables informed, fair corrective action. Having the team resolve it themselves (A) may lead to further escalation. Highlighting behavior impact immediately (B) is premature without investigation. Documenting and deferring to project end (C) ignores the issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 주니어 팀원이 다른 팀원의 대인관계 기술이 팀의 효과성을 저하시키고 있다는 이슈를 프로젝트 관리자에게 에스컬레이션했다. 프로젝트 관리자가 먼저 해야 할 일은? | 팀원들이 스스로 문제를 해결하게 한다. | 그의 행동이 미치는 영향을 강조하고 개선하도록 동기부여한다. | 에스컬레이션된 이슈를 문서화하고 프로젝트 종료 시 처리한다. | 정보를 수집하고 문제의 근본 원인을 파악한다. |  | D | 주니어 팀원이 다른 팀원의 대인관계 기술이 팀 효과성에 영향을 미치고 있다고 에스컬레이션할 때, 프로젝트 관리자는 먼저 정보를 수집하고 문제의 근본 원인을 파악해야 한다. 문제의 성격과 범위를 이해하면 정보에 기반한 공정한 시정 조치가 가능하다. 팀이 자체 해결하게 하기(A)는 추가 에스컬레이션으로 이어질 수 있다. 행동 영향 즉시 강조(B)는 조사 없이 성급하다. 문서화 후 프로젝트 종료 시 처리(C)는 문제를 방치한다.
99 | A product owner has returned from a meeting with a few key stakeholders, who expressed interest in learning more about the project progress. The product owner is seeking the project manager's recommendation on how to approach this request. What should the project manager do to help the product owner? | Invite the product owner to future demonstrations where they can provide feedback. | Remind the product owner of stakeholder accountability, and ask the product owner to determine the appropriate next steps. | Provide an overview of the completed functionalities and release plan, and capture expectations for future stakeholder involvement. 1033 | Provide access to the latest user acceptance test (UAT) environment so they can see the solution. |  | C | When key stakeholders express interest in learning about project progress and the product owner seeks the PM's recommendation, the project manager should provide an overview of completed functionalities and the release plan, and capture expectations for future stakeholder involvement. Comprehensive engagement sets clear expectations. Inviting to demos (A) is one approach but limited. Reminding the PO of accountability (B) deflects. Providing UAT access (D) is premature for stakeholder overview. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 제품 소유자가 몇몇 핵심 이해관계자와의 회의에서 돌아왔다. 이해관계자들은 프로젝트 진행 상황에 대해 더 알고 싶다는 관심을 표명했다. 제품 소유자가 이 요청에 대한 접근 방법에 대해 프로젝트 관리자의 추천을 구하고 있다. 프로젝트 관리자가 제품 소유자를 돕기 위해 해야 할 일은? | 제품 소유자를 향후 시연에 초대하여 피드백을 제공할 수 있게 한다. | 제품 소유자에게 이해관계자 책임을 상기시키고, 제품 소유자가 적절한 다음 단계를 결정하도록 요청한다. | 완료된 기능과 릴리스 계획에 대한 개요를 제공하고, 향후 이해관계자 참여에 대한 기대를 파악한다. | 이해관계자가 솔루션을 볼 수 있도록 최신 사용자 인수 테스트(UAT) 환경에 대한 접근 권한을 제공한다. |  | C | 핵심 이해관계자가 프로젝트 진행에 관심을 표명하고 제품 소유자가 PM의 추천을 구할 때, 프로젝트 관리자는 완료된 기능과 릴리스 계획에 대한 개요를 제공하고 향후 이해관계자 참여에 대한 기대를 파악해야 한다. 포괄적인 참여가 명확한 기대를 설정한다. 시연에 초대(A)는 한 가지 접근법이지만 제한적이다. PO에게 책임 상기(B)는 책임을 전가한다. UAT 접근 제공(D)은 이해관계자 개요에는 시기상조이다.
100 | During a project's execution phase, two team members are having conflicts with other team members within the team on technical and interpersonal levels. Which two actions should the project manager take first to address this conflict? (Choose two) | Address the conflict during team meetings for the entire team to participate and find solutions. | Discuss the conflict early among the affected team members using a direct, collaborative approach. | Arrange individual meetings with the team members who cannot work together effectively. | Ask human resources (HR) to intervene before it escalates and affects the team ' s performance. | Plan to resolve the team members ' conflicts after the sprint and focus on achieving the goal. | B, D | When two team members have conflicts at both technical and interpersonal levels, the project manager should take two immediate actions: discuss the conflict early among the affected members using a direct, collaborative approach (B), and ask human resources (HR) to intervene before it escalates and affects the team's performance (D). Early direct communication establishes a collaborative problem-solving foundation, while HR involvement brings professional mediation expertise for complex interpersonal conflicts. Addressing conflicts in front of the entire team (A) may embarrass individuals and escalate tensions. Arranging individual meetings (C) addresses symptoms separately but may not resolve the underlying interpersonal dynamic between the conflicting parties. Deferring resolution until after the sprint (E) allows the issue to fester. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 단계 중 두 명의 팀원이 기술적 및 대인관계 수준에서 다른 팀원들과 갈등을 겪고 있다. 프로젝트 관리자가 이 갈등을 해결하기 위해 먼저 취해야 할 두 가지 조치는? (2개 선택) | 전체 팀이 참여하여 해결책을 찾을 수 있도록 팀 회의에서 갈등을 다룬다. | 영향을 받는 팀원들 사이에서 직접적이고 협력적인 접근 방식으로 갈등을 조기에 논의한다. | 효과적으로 함께 일하지 못하는 팀원들과 개별 회의를 주선한다. | 에스컬레이션되어 팀 성과에 영향을 미치기 전에 인사부(HR)에 개입을 요청한다. | 스프린트 후에 팀원의 갈등을 해결할 계획을 세우고 목표 달성에 집중한다. | B, D | 두 팀원이 기술적 및 대인관계 수준에서 갈등을 겪을 때, 프로젝트 관리자는 두 가지 즉각적인 조치를 취해야 한다: 영향을 받는 팀원들 사이에서 직접적이고 협력적인 접근 방식으로 갈등을 조기에 논의하고(B), 팀 성과에 영향을 미치기 전에 인사부(HR)에 개입을 요청한다(D). 조기 직접 소통은 협력적 문제 해결 기반을 마련하고, HR 참여는 복잡한 대인관계 갈등에 전문적 중재 전문성을 제공한다. 전체 팀 앞에서 갈등 다루기(A)는 개인을 당황하게 하고 긴장을 고조시킬 수 있다. 개별 회의 주선(C)은 증상을 별도로 다루지만 갈등 당사자 간의 근본적 대인관계 역학을 해결하지 못할 수 있다. 스프린트 후로 해결 연기(E)는 문제를 방치한다.
101 | A project manager noticed that the functional manager is not cooperating with staff assignment schedules and is always finding excuses not to release the requested staff. What should the project manager do first? | Evaluate the impact caused by the delay of forming the team and confront the functional manager. | Ask the leadership team for help obtaining the needed staff. | Have a direct talk with the functional manager to understand the reasons behind their attitude. | Check with human resources (HR) regarding the availability of staff. |  | C | When a functional manager consistently refuses to release requested staff, the project manager should first have a direct talk with the functional manager to understand the reasons behind their attitude. Direct, private communication is the recommended approach for conflict resolution—understanding the root cause enables collaborative problem-solving. Evaluating the impact and confronting them (A) is more aggressive than necessary as a first step. Asking leadership for help (B) escalates before the PM has attempted direct resolution. Checking with HR about availability (D) investigates the problem indirectly without engaging the functional manager. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 기능 관리자가 인력 배정 일정에 협조하지 않고 항상 요청된 인력을 배출하지 않는 핑계를 찾고 있음을 발견했다. 프로젝트 관리자가 먼저 해야 할 일은? | 팀 구성 지연으로 인한 영향을 평가하고 기능 관리자에게 맞선다. | 리더십 팀에게 필요한 인력 확보에 도움을 요청한다. | 기능 관리자와 직접 대화하여 그 태도의 이유를 파악한다. | 인사부(HR)에 인력 가용성을 확인한다. |  | C | 기능 관리자가 지속적으로 요청된 인력 배출을 거부할 때, 프로젝트 관리자는 먼저 기능 관리자와 직접 대화하여 그 태도의 이유를 파악해야 한다. 직접적이고 비공개적인 소통이 갈등 해결의 권장 접근법이며—근본 원인을 이해하면 협력적 문제 해결이 가능하다. 영향 평가 후 맞서기(A)는 첫 단계로는 필요 이상으로 공격적이다. 리더십에 도움 요청(B)은 PM이 직접 해결을 시도하기 전에 에스컬레이션하는 것이다. HR에 가용성 확인(D)은 기능 관리자를 참여시키지 않고 간접적으로 문제를 조사한다.
102 | An organization's management system is being upgraded by an agile team. Although the project was scoped thoroughly, the functional requirements were handed over to the project team and there is no subject matter expert (SME) available to work on the project continuously. The project manager is concerned that the team's progress will be hindered by their lack of knowledge. Which two project events will assist the project manager to ascertain if this is the case? (Choose two) | Sprint planning | Retrospective | Requirements analysis | Standup | Backlog refinement | B, E | When an agile project lacks a continuously available SME and the PM is concerned about knowledge gaps, two project events that help assess this are (B) retrospective and (E) backlog refinement. Retrospectives surface process and knowledge issues; backlog refinement reveals unclear requirements. Sprint planning (A) focuses on commitment. Requirements analysis (C) is an upfront activity. Standup (D) is too brief for deep assessment. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 조직의 관리 시스템이 애자일 팀에 의해 업그레이드되고 있다. 프로젝트의 범위가 철저히 설정되었지만, 기능 요구사항이 프로젝트 팀에 전달되었고 프로젝트에 지속적으로 참여할 수 있는 주제 전문가(SME)가 없다. 프로젝트 관리자는 팀의 지식 부족으로 진행이 방해받을 것을 우려한다. 어떤 두 가지 프로젝트 이벤트가 이것이 사실인지 확인하는 데 도움이 되는가? (2개 선택) | 스프린트 계획 | 회고 | 요구사항 분석 | 스탠드업 | 백로그 정제 | B, E | 애자일 프로젝트에 지속적으로 참여하는 SME가 없고 PM이 지식 격차를 우려할 때, 이를 평가하는 데 도움이 되는 두 가지 프로젝트 이벤트는 (B) 회고와 (E) 백로그 정제이다. 회고는 프로세스 및 지식 이슈를 표면화하고, 백로그 정제는 불명확한 요구사항을 드러낸다. 스프린트 계획(A)은 약속에 초점을 맞춘다. 요구사항 분석(C)은 초기 활동이다. 스탠드업(D)은 심층 평가에는 너무 짧다.
103 | A senior developer working on a large artificial intelligence (AI) project has worked hard and shown excellent results. The project manager is very happy with the developer's contribution and thinks that the developer deserves a reward. What should the project manager do? | Reward the developer according to their motivations and interests | Print a recognition certificate and present it to the developer during a meeting | Create an opportunity (or the project team to recognize this developer | Send a recognition email to the team and copy management |  | A | When a senior developer has shown excellent results and deserves a reward, the project manager should reward them according to their motivations and interests. Personalized recognition is most effective. Printing a certificate (B) is generic. Creating a team recognition opportunity (C) dilutes individual acknowledgment. Sending a recognition email copying management (D) may not align with the developer's preferences. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Help Ensure Knowledge Transfer | Governance | Executing | Build an Empowered Culture | Manage Project Knowledge | AI | 대규모 인공지능(AI) 프로젝트에서 일하는 시니어 개발자가 열심히 일하고 우수한 결과를 보여주었다. 프로젝트 관리자는 개발자의 기여에 매우 만족하며 보상을 받을 자격이 있다고 생각한다. 프로젝트 관리자는 어떻게 해야 하는가? | 개발자의 동기부여와 관심사에 맞게 보상한다. | 인정 인증서를 인쇄하여 회의 중에 개발자에게 수여한다. | 프로젝트 팀이 이 개발자를 인정할 수 있는 기회를 만든다. | 팀에게 인정 이메일을 보내고 경영진에게 참조한다. |  | A | 시니어 개발자가 우수한 결과를 보여주고 보상을 받을 자격이 있을 때, 프로젝트 관리자는 그의 동기부여와 관심사에 맞게 보상해야 한다. 맞춤형 인정이 가장 효과적이다. 인증서 인쇄(B)는 일반적이다. 팀 인정 기회 만들기(C)는 개인적 인정을 희석시킨다. 경영진 참조 인정 이메일(D)은 개발자의 선호와 맞지 않을 수 있다.
104 | A project manager identifies a risk that has a high probability of occurring. How should the project manager manage this risk? | Ask the team to monitor the risk and provide an alert if it becomes an issue. | Assign a qualified team member to be the risk manager for the project. | Remove the user stories associated to that risk and avoid the impact to the project deliverables. | Submit a change request to transfer the risk to a third party in case it becomes an issue. |  | A | When a risk has a high probability of occurring, the project manager should ask the team to monitor the risk and provide an alert if it becomes an issue. Continuous monitoring with clear escalation ensures timely response. Assigning a dedicated risk manager (B) may be excessive for a single risk. Removing associated user stories (C) avoids the risk but may sacrifice scope. Submitting a change request for risk transfer (D) is a response strategy but not the primary monitoring action. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자가 발생 확률이 높은 리스크를 식별했다. 프로젝트 관리자는 이 리스크를 어떻게 관리해야 하는가? | 팀에게 리스크를 모니터링하고 이슈가 되면 경고를 제공하도록 요청한다. | 프로젝트의 리스크 관리자가 될 자격 있는 팀원을 지정한다. | 해당 리스크와 관련된 사용자 스토리를 제거하여 프로젝트 산출물에 대한 영향을 피한다. | 이슈가 될 경우 리스크를 제3자에게 전가하기 위한 변경 요청을 제출한다. |  | A | 리스크의 발생 확률이 높을 때, 프로젝트 관리자는 팀에게 리스크를 모니터링하고 이슈가 되면 경고를 제공하도록 요청해야 한다. 명확한 에스컬레이션을 통한 지속적인 모니터링은 적시 대응을 보장한다. 전담 리스크 관리자를 지정하는 것(B)은 단일 리스크에 대해 과도할 수 있다. 관련 사용자 스토리를 제거하는 것(C)은 리스크를 회피하지만 범위를 희생할 수 있다. 리스크 전가를 위한 변경 요청(D)은 대응 전략이지 주요 모니터링 활동이 아니다.
105 | A project manager is creating the quality management plan for deliverables with very precise requirements. The project manager is uncertain about how to create quality standards so the suppliers can show conformity when delivering the product. Which two actions should the project manager take first? (Choose 2) | Evaluate industry standards of similar products to determine which apply to this project. | Review the conformity management plan to ensure the requirements are clearly defined. | Reference the quality management plans from old projects to determine if they apply to these deliverables. | Add a conformity team member to inspect each deliverable upon receipt from the supplier. | Ask the suppliers to create a statement of conformity when the product is delivered. | B, D | When creating a quality management plan for deliverables with precise requirements, the project manager should first take two actions: review the conformity management plan to ensure the requirements are clearly defined (B), and add a conformity team member to inspect each deliverable upon receipt from the supplier (D). Clear requirement definitions provide the foundation for quality standards, while having a dedicated conformity inspector ensures that each deliverable is verified against those standards upon delivery. Evaluating industry standards of similar products (A) is useful context but is secondary to establishing internal requirements and inspection processes first. Referencing old quality plans (C) may not apply to current deliverables with unique precision requirements. Requesting supplier conformity statements (E) occurs during execution and relies on the quality standards already being established. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 매우 정밀한 요구사항을 가진 산출물에 대한 품질 관리 계획을 작성하고 있다. 프로젝트 관리자는 공급업체가 제품 납품 시 적합성을 증명할 수 있도록 품질 표준을 어떻게 만들어야 할지 확신이 없다. 프로젝트 관리자가 먼저 취해야 할 두 가지 조치는 무엇인가? (2개 선택) | 유사 제품의 산업 표준을 평가하여 이 프로젝트에 적용되는 것을 결정한다. | 요구사항이 명확하게 정의되었는지 적합성 관리 계획을 검토한다. | 과거 프로젝트의 품질 관리 계획을 참조하여 이 산출물에 적용 가능한지 판단한다. | 공급업체로부터 산출물을 수령할 때 각 산출물을 검사할 적합성 팀원을 추가한다. | 제품이 납품될 때 공급업체에게 적합성 명세서를 작성하도록 요청한다. | B, D | 정밀한 요구사항을 가진 산출물에 대한 품질 관리 계획을 작성할 때, 프로젝트 관리자는 먼저 두 가지 조치를 취해야 한다: 요구사항이 명확하게 정의되었는지 적합성 관리 계획을 검토하고(B), 공급업체로부터 산출물 수령 시 각 산출물을 검사할 적합성 팀원을 추가한다(D). 명확한 요구사항 정의는 품질 표준의 기초를 제공하고, 전담 적합성 검사원 배치는 각 산출물이 납품 시 해당 표준에 따라 검증되도록 보장한다. 유사 제품의 산업 표준 평가(A)는 유용한 맥락이지만 내부 요구사항과 검사 프로세스 수립보다 부차적이다. 과거 품질 계획 참조(C)는 고유한 정밀 요구사항을 가진 현재 산출물에 적용되지 않을 수 있다. 공급업체 적합성 명세서 요청(E)은 실행 단계에서 발생하며 이미 수립된 품질 표준에 의존한다.
106 | A project team is preparing a report for the stakeholders. The team gathers and collates a large amount of data to be included in the status report. What should the project manager do next? | Ensure the team follows standard operating procedures (SOP) for creating a stakeholder report. | Instruct the team to conduct a meeting with the stakeholders before finalizing the report. | Instruct the team to make only a graphical representation of all the data for the report. | Instruct the team to analyze and interpret the data before including it in the report. |  | D | When a team gathers a large amount of data for a stakeholder report, the project manager should instruct the team to analyze and interpret the data before including it. Raw data without interpretation is not useful. Following SOPs for report creation (A) may help format but not content quality. Meeting stakeholders before finalizing (B) adds a step before data is interpreted. Making graphical representations only (C) may oversimplify. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 팀이 이해관계자를 위한 보고서를 준비하고 있다. 팀은 현황 보고서에 포함할 대량의 데이터를 수집하고 정리했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 팀이 이해관계자 보고서 작성을 위한 표준 운영 절차(SOP)를 따르도록 한다. | 보고서를 최종 확정하기 전에 팀에게 이해관계자와 회의를 진행하도록 지시한다. | 팀에게 보고서의 모든 데이터를 그래픽 표현으로만 작성하도록 지시한다. | 팀에게 데이터를 보고서에 포함하기 전에 분석하고 해석하도록 지시한다. |  | D | 팀이 이해관계자 보고서를 위해 대량의 데이터를 수집했을 때, 프로젝트 관리자는 팀에게 데이터를 포함하기 전에 분석하고 해석하도록 지시해야 한다. 해석 없는 원시 데이터는 유용하지 않다. 보고서 작성을 위한 SOP 준수(A)는 형식에는 도움이 되지만 내용 품질에는 아니다. 최종 확정 전 이해관계자 회의(B)는 데이터 해석 전 단계를 추가한다. 그래픽 표현만 작성(C)은 지나치게 단순화할 수 있다.
107 | A project involves exporting 150 packages to the customer. However, only 30 packages have been cleared by the customer for shipment. The logistics manager provided details to the customer 2 weeks ago and set up a weekly conference call to effectively communicate with them, but the customer has not been participating in the calls. How should the project manager handle this situation? | Request a delivery date extension from the customer | Inform the customer that subsequent packages cannot be manufactured. | Find the root cause of the issue and discuss the customer ' s current engagement. | Request a change in the contract to include the shipment in the project managementplan. |  | C | When 120 of 150 packages are uncleared and the customer is not participating in weekly calls, the project manager should find the root cause of the issue and discuss the customer's current engagement. Understanding why the customer is disengaged addresses the core problem. Requesting a delivery extension (A) does not address engagement. Informing packages cannot be manufactured (B) is escalatory. Requesting a contract change (D) is premature. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트는 고객에게 150개의 패키지를 수출하는 것을 포함한다. 그러나 고객이 선적을 승인한 패키지는 30개에 불과하다. 물류 관리자는 2주 전에 고객에게 세부 정보를 제공하고 효과적인 의사소통을 위해 주간 전화 회의를 설정했지만, 고객은 통화에 참여하지 않고 있다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 고객에게 납기 연장을 요청한다. | 고객에게 후속 패키지를 제조할 수 없다고 알린다. | 문제의 근본 원인을 파악하고 고객의 현재 참여 상태를 논의한다. | 프로젝트 관리 계획에 선적을 포함하도록 계약 변경을 요청한다. |  | C | 150개 패키지 중 120개가 미승인 상태이고 고객이 주간 통화에 참여하지 않을 때, 프로젝트 관리자는 문제의 근본 원인을 파악하고 고객의 현재 참여 상태를 논의해야 한다. 고객이 참여하지 않는 이유를 이해하는 것이 핵심 문제를 해결한다. 납기 연장 요청(A)은 참여 문제를 해결하지 않는다. 패키지 제조 불가 통보(B)는 에스컬레이션적이다. 계약 변경 요청(D)은 시기상조이다.
108 | A team is using an agile approach to maintain the project backlog. A new project obstacle was identified as a blocker and added to the backlog list. The team is facing challenges to remove this obstacle. What should the project manager do next? | Escalate the obstacle to a servant leader for resolution. | Focus on generating business value despite the obstacle | Make changes to reprioritize the backlog because of the obstacle. | Ignore the obstacle and present the partial solution to the customer |  | C | When a new obstacle identified as a blocker challenges the agile team, the project manager should make changes to reprioritize the backlog because of the obstacle. Reprioritizing allows the team to focus on the most critical value-delivering items while managing the blocker—consistent with the agile principle of responding to change. Escalating to a servant leader (A) delegates rather than acts. Focusing on business value despite the obstacle (B) ignores the blocker's impact. Ignoring the obstacle and presenting a partial solution (D) is irresponsible. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 팀이 프로젝트 백로그를 유지하기 위해 애자일 접근 방식을 사용하고 있다. 새로운 프로젝트 장애물이 블로커로 식별되어 백로그 목록에 추가되었다. 팀이 이 장애물을 제거하는 데 어려움을 겪고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 해결을 위해 서번트 리더에게 장애물을 에스컬레이션한다. | 장애물에도 불구하고 비즈니스 가치 창출에 집중한다. | 장애물로 인해 백로그를 재우선순위화하도록 변경한다. | 장애물을 무시하고 고객에게 부분적 솔루션을 제시한다. |  | C | 새로운 장애물이 블로커로 식별되어 애자일 팀에게 도전이 될 때, 프로젝트 관리자는 장애물로 인해 백로그를 재우선순위화해야 한다. 재우선순위화는 팀이 블로커를 관리하면서 가장 중요한 가치 전달 항목에 집중할 수 있게 하며, 이는 변화에 대응하는 애자일 원칙과 일치한다. 서번트 리더에게 에스컬레이션(A)은 위임이지 행동이 아니다. 장애물에도 불구하고 비즈니스 가치에 집중(B)은 블로커의 영향을 무시한다. 장애물을 무시하고 부분적 솔루션 제시(D)는 무책임하다.
109 | A project manager is starting a new project, and the project team is located in different countries. The team was going to use a specific tool to hold virtual meetings. However, that tool is not available in one team member's country. How should the project manager deal with this situation? | Start the project and use email to communicate with the team member until the tool is available. | Investigate alternative tools for virtual meetings that are available to all team members. | Ask the team member to move to another location where the tool is available. | Contact the project sponsor to have the team member removed from the project. |  | B | When a specific virtual meeting tool is unavailable in one team member's country, the project manager should investigate alternative tools that are available to all team members. Inclusive tool selection ensures full team participation regardless of location. Starting with email as a workaround (A) limits collaboration. Asking the team member to relocate (C) is unreasonable. Removing the team member from the project (D) is extreme. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 관리자가 새 프로젝트를 시작하고 있으며, 프로젝트 팀은 여러 국가에 분산되어 있다. 팀은 가상 회의를 위해 특정 도구를 사용할 예정이었다. 그러나 한 팀원의 국가에서는 해당 도구를 사용할 수 없다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 프로젝트를 시작하고 도구가 사용 가능해질 때까지 해당 팀원과 이메일로 소통한다. | 모든 팀원이 사용할 수 있는 가상 회의용 대체 도구를 조사한다. | 해당 도구를 사용할 수 있는 다른 위치로 팀원에게 이동을 요청한다. | 프로젝트 스폰서에게 연락하여 해당 팀원을 프로젝트에서 제외하도록 한다. |  | B | 특정 가상 회의 도구가 한 팀원의 국가에서 사용 불가할 때, 프로젝트 관리자는 모든 팀원이 사용할 수 있는 대체 도구를 조사해야 한다. 포용적인 도구 선택은 위치에 관계없이 전체 팀 참여를 보장한다. 이메일을 임시방편으로 사용(A)하면 협업이 제한된다. 팀원에게 이전 요청(C)은 비합리적이다. 프로젝트에서 팀원 제외(D)는 극단적이다.
110 | A major project is unable to access the US$12 million funding allocated for the project. This prevents the start of the procurement process and is already leading to costly delays. What should the project manager do? | Review the project requirements. | Invite the finance department to the next project demo. | Escalate to the project steering committee. | Use the currently available resources. |  | C | When a major project cannot access its $12 million funding allocation, preventing procurement and causing delays, the project manager should escalate to the project steering committee. The steering committee has authority to resolve high-level funding issues. Reviewing project requirements (A) does not address the funding problem. Inviting finance to the next demo (B) is indirect. Using currently available resources (D) is a workaround that does not resolve the root cause. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 대규모 프로젝트가 프로젝트에 할당된 1,200만 달러의 자금에 접근할 수 없다. 이로 인해 조달 프로세스 시작이 불가능하며 이미 비용이 많이 드는 지연이 발생하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 요구사항을 검토한다. | 재무 부서를 다음 프로젝트 데모에 초대한다. | 프로젝트 운영위원회에 에스컬레이션한다. | 현재 사용 가능한 자원을 활용한다. |  | C | 대규모 프로젝트가 1,200만 달러 자금 할당에 접근할 수 없어 조달이 불가하고 지연이 발생할 때, 프로젝트 관리자는 프로젝트 운영위원회에 에스컬레이션해야 한다. 운영위원회는 고수준의 자금 문제를 해결할 권한이 있다. 프로젝트 요구사항 검토(A)는 자금 문제를 해결하지 않는다. 재무 부서를 데모에 초대(B)는 간접적이다. 현재 사용 가능한 자원 활용(D)은 근본 원인을 해결하지 않는 임시방편이다.
111 | During sprint planning, the product owner wants to prioritize items with high business value. However, the project team is concerned about technical debt and infrastructure dependencies to deliver the expected value. How should the project manager handle this issue? | Support the product owner so only items with high business value are included in the next sprint. | Support the project sponsor so the decision is made top-down and the team follows the provided direction. | Support the project team so technical debt and infrastructure dependencies are included in the next sprint. | Support a voting exercise so all team members can express their opinion and the reason behind their vote. |  | D | When the product owner wants high-value items but the team is concerned about technical debt and infrastructure dependencies, the project manager should support a voting exercise so all team members can express their opinion and reasoning. Collaborative decision-making balances business value with technical sustainability. Supporting only the product owner (A) ignores technical concerns. Supporting top-down decisions from the sponsor (B) overrides team input. Supporting only the team's concerns (C) ignores business value priorities. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Risk | Monitoring & Controlling | Build an Empowered Culture | Monitor Risks | Traditional PM | 스프린트 계획 중 제품 책임자는 높은 비즈니스 가치를 가진 항목의 우선순위를 정하고 싶어 한다. 그러나 프로젝트 팀은 기대하는 가치를 전달하기 위한 기술 부채와 인프라 종속성에 대해 우려하고 있다. 프로젝트 관리자는 이 문제를 어떻게 처리해야 하는가? | 제품 책임자를 지원하여 다음 스프린트에 높은 비즈니스 가치를 가진 항목만 포함한다. | 프로젝트 스폰서를 지원하여 하향식으로 결정을 내리고 팀이 제공된 방향을 따르도록 한다. | 프로젝트 팀을 지원하여 기술 부채와 인프라 종속성을 다음 스프린트에 포함한다. | 투표 활동을 지원하여 모든 팀원이 의견과 그 이유를 표현할 수 있도록 한다. |  | D | 제품 책임자가 높은 가치 항목을 원하지만 팀이 기술 부채와 인프라 종속성에 대해 우려할 때, 프로젝트 관리자는 모든 팀원이 의견과 그 이유를 표현할 수 있도록 투표 활동을 지원해야 한다. 협력적 의사결정은 비즈니스 가치와 기술적 지속 가능성 간의 균형을 맞춘다. 제품 책임자만 지원(A)하면 기술적 우려를 무시한다. 스폰서의 하향식 결정 지원(B)은 팀의 의견을 무시한다. 팀의 우려만 지원(C)하면 비즈니스 가치 우선순위를 무시한다.
112 | During daily team standup meetings, team members constantly ask about which tasks they should focus on first. How should the project manager ensure the team is fully productive? | Work with the product owner to ensure the project backlog is prioritized. | Ensure team members are working according to the project plan. | Encourage project team members to prioritize the product backlog. | Review the project backlog during the team ' s standup meeting. |  | A | When team members constantly ask which tasks to focus on during standups, the project manager should work with the product owner to ensure the backlog is prioritized. Clear prioritization eliminates confusion. Ensuring work follows the project plan (B) is predictive, not agile. Encouraging team members to prioritize the backlog (C) confuses roles. Reviewing the backlog during standups (D) extends the meeting beyond its purpose. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 일일 팀 스탠드업 미팅에서 팀원들이 어떤 작업에 먼저 집중해야 하는지 끊임없이 질문한다. 프로젝트 관리자는 팀이 완전히 생산적이 되도록 어떻게 해야 하는가? | 제품 책임자와 협력하여 프로젝트 백로그의 우선순위가 지정되도록 한다. | 팀원들이 프로젝트 계획에 따라 작업하도록 한다. | 프로젝트 팀원들이 제품 백로그의 우선순위를 지정하도록 격려한다. | 팀의 스탠드업 미팅 중에 프로젝트 백로그를 검토한다. |  | A | 팀원들이 스탠드업에서 어떤 작업에 집중해야 하는지 끊임없이 질문할 때, 프로젝트 관리자는 제품 책임자와 협력하여 백로그의 우선순위가 지정되도록 해야 한다. 명확한 우선순위 지정은 혼란을 제거한다. 프로젝트 계획에 따른 작업 보장(B)은 예측적이며 애자일이 아니다. 팀원에게 백로그 우선순위 지정 격려(C)는 역할을 혼동한다. 스탠드업 중 백로그 검토(D)는 미팅 목적을 넘어선다.
113 | A project team created user stories after understanding the customer requirements. As the project progresses, the project manager observes that there are too many change requests. The team feels that the outcomes they are working on are not aligned with the customer requirements. What should the project manager do? | Refer to the configuration management knowledge base for similar projects delivered in the past. | Acknowledge that the current team needs improvement and hire more qualified team members. | Arrange for a workshop with the customer to understand the business values expected from the outcomes. | Include a representative from the customer to work collaboratively with the team. |  | C | When the team faces numerous change requests and feels misaligned with customer requirements, the project manager should arrange a workshop with the customer to understand the business values expected from the outcomes. Direct engagement realigns expectations and reduces future change requests. Referring to the configuration management knowledge base (A) reviews past work but does not engage the customer. Hiring more qualified team members (B) does not address requirement misalignment. Including a customer representative (D) is helpful long-term but does not immediately clarify current misalignment. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 프로젝트 팀이 고객 요구사항을 이해한 후 사용자 스토리를 작성했다. 프로젝트가 진행되면서 프로젝트 관리자는 변경 요청이 너무 많다는 것을 관찰했다. 팀은 작업 중인 결과물이 고객 요구사항과 일치하지 않는다고 느낀다. 프로젝트 관리자는 어떻게 해야 하는가? | 과거 유사 프로젝트에 대한 형상 관리 지식 기반을 참조한다. | 현재 팀이 개선이 필요함을 인정하고 더 자격 있는 팀원을 고용한다. | 결과물에서 기대되는 비즈니스 가치를 이해하기 위해 고객과 워크숍을 준비한다. | 팀과 협력적으로 작업할 고객 대표를 포함한다. |  | C | 팀이 수많은 변경 요청에 직면하고 고객 요구사항과 불일치를 느낄 때, 프로젝트 관리자는 결과물에서 기대되는 비즈니스 가치를 이해하기 위해 고객과 워크숍을 준비해야 한다. 직접적인 참여는 기대치를 재정렬하고 향후 변경 요청을 줄인다. 형상 관리 지식 기반 참조(A)는 과거 작업을 검토하지만 고객과 소통하지 않는다. 더 자격 있는 팀원 고용(B)은 요구사항 불일치를 해결하지 않는다. 고객 대표 포함(D)은 장기적으로 도움이 되지만 현재 불일치를 즉시 명확히 하지는 않는다.
114 | In a product development project, the project manager is constantly receiving complaints from stakeholders about functionalities being delivered, but not required by the business departments. The project sponsor wants to know if the project resources are being used effectively. What should the project manager have done to avoid delivering work that is not adding value to the business? | Document the stakeholders ' needs, review them during the retrospective, and create improvement plans. | Define a product scope and ask the stakeholders to not deviate from it. | Ask the stakeholders to document their complaints in change requests. | Encourage the product owner to meet with the stakeholders and create a product backlog based on their needs. |  | B | To avoid delivering functionalities not required by business departments, the project manager should have documented stakeholders' needs, reviewed them during retrospectives, and created improvement plans. This iterative feedback loop ensures continuous alignment between delivered features and actual business value. Defining a product scope and restricting deviations (B) is rigid and does not account for evolving business needs. Asking stakeholders to submit change requests (C) is bureaucratic and shifts the burden to stakeholders rather than proactively managing scope. Encouraging the product owner to create a backlog from stakeholder needs (D) is helpful but insufficient without the retrospective review cycle to validate alignment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 제품 개발 프로젝트에서 프로젝트 관리자는 이해관계자들로부터 비즈니스 부서에서 요구하지 않은 기능이 전달되고 있다는 불만을 지속적으로 받고 있다. 프로젝트 스폰서는 프로젝트 자원이 효과적으로 사용되고 있는지 알고 싶어 한다. 프로젝트 관리자는 비즈니스에 가치를 더하지 않는 작업의 전달을 피하기 위해 무엇을 했어야 하는가? | 이해관계자의 요구사항을 문서화하고, 회고 중에 검토하며, 개선 계획을 수립한다. | 제품 범위를 정의하고 이해관계자에게 이를 벗어나지 않도록 요청한다. | 이해관계자에게 불만 사항을 변경 요청으로 문서화하도록 요청한다. | 제품 책임자가 이해관계자를 만나 그들의 요구에 기반한 제품 백로그를 작성하도록 격려한다. |  | B | 비즈니스 부서에서 요구하지 않은 기능의 전달을 피하기 위해, 프로젝트 관리자는 이해관계자의 요구사항을 문서화하고, 회고에서 검토하며, 개선 계획을 수립했어야 한다. 이 반복적 피드백 루프는 전달 기능과 실제 비즈니스 가치 간의 지속적 정렬을 보장한다. 제품 범위를 정의하고 벗어나지 못하게 하는 것(B)은 경직되어 변화하는 비즈니스 요구를 반영하지 못한다. 변경 요청 문서화 요청(C)은 관료적이며 범위를 능동적으로 관리하지 않는다. 제품 책임자의 백로그 작성 격려(D)는 도움이 되지만 정렬 검증을 위한 회고 검토 주기 없이는 불충분하다.
115 | During a meeting to define project scope, a stakeholder tells the project manager that the main requested feature in the contract is not applicable, and this is documented in the lessons learned. What should the project manager do? | Meet with the sponsor to ask for their support | Check that this information was documented correctly | Ask the sponsor to close the project and pay the contracted penalty. | Check with the team to learn what can be done, and consult an expert |  | D | When a stakeholder reports that the main contracted feature is not applicable and this is documented in lessons learned, the project manager should check with the team to learn what can be done and consult an expert. Understanding the impact before acting ensures informed decisions. Meeting with the sponsor for support (A) is premature. Asking the sponsor to close the project (C) is drastic. Simply checking documentation accuracy (B) does not address the scope change impact. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Scope | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트 범위를 정의하는 회의 중, 이해관계자가 프로젝트 관리자에게 계약서의 주요 요청 기능이 적용 불가하며 이것이 교훈에 문서화되어 있다고 말했다. 프로젝트 관리자는 어떻게 해야 하는가? | 스폰서를 만나 지원을 요청한다. | 이 정보가 정확하게 문서화되었는지 확인한다. | 스폰서에게 프로젝트를 종료하고 계약된 위약금을 지불하도록 요청한다. | 팀에 확인하여 무엇을 할 수 있는지 알아보고 전문가에게 자문한다. |  | D | 이해관계자가 주요 계약 기능이 적용 불가하며 교훈에 문서화되어 있다고 보고할 때, 프로젝트 관리자는 팀에 확인하여 무엇을 할 수 있는지 알아보고 전문가에게 자문해야 한다. 행동하기 전에 영향을 이해하면 정보에 입각한 결정을 내릴 수 있다. 스폰서에게 지원 요청(A)은 시기상조이다. 프로젝트 종료 요청(C)은 극단적이다. 문서 정확성만 확인(B)하는 것은 범위 변경의 영향을 다루지 않는다.
116 | A project manager is leading a product feature rollout that will gain more subscribers for a video-streaming application. During the backlog grooming phase, the business stakeholders were unable to understand the feature integration with the product and raised concerns. What can the project manager do to demonstrate the feature integration? | Review the backlog in detail with the business stakeholders. | Include the business stakeholders in the iteration review. | Involve business stakeholders in the iteration retrospective. | Create a task for the iteration review and add it to the backlog. |  | B | When business stakeholders cannot understand feature integration during backlog grooming, the project manager should include them in the iteration review. Reviews demonstrate working functionality directly. Reviewing the backlog in detail (A) provides information but not demonstration. Including stakeholders in retrospectives (C) is for team reflection. Creating a backlog task for the review (D) adds overhead. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 비디오 스트리밍 애플리케이션의 구독자를 늘릴 제품 기능 출시를 주도하고 있다. 백로그 정리 단계에서 비즈니스 이해관계자들이 제품과의 기능 통합을 이해하지 못하고 우려를 제기했다. 프로젝트 관리자는 기능 통합을 보여주기 위해 무엇을 할 수 있는가? | 비즈니스 이해관계자와 함께 백로그를 상세히 검토한다. | 비즈니스 이해관계자를 이터레이션 리뷰에 포함시킨다. | 비즈니스 이해관계자를 이터레이션 회고에 참여시킨다. | 이터레이션 리뷰를 위한 작업을 생성하여 백로그에 추가한다. |  | B | 백로그 정리 중 비즈니스 이해관계자가 기능 통합을 이해하지 못할 때, 프로젝트 관리자는 이터레이션 리뷰에 포함시켜야 한다. 리뷰는 작동하는 기능을 직접 시연한다. 백로그 상세 검토(A)는 정보를 제공하지만 시연은 아니다. 이해관계자를 회고에 포함(C)시키는 것은 팀 성찰을 위한 것이다. 리뷰를 위한 백로그 작업 생성(D)은 오버헤드를 추가한다.
117 | A project manager is preparing to start a new project in which the team members are distributed geographically across different countries. The project manager is using the communications management plan to engage the team members and find a communication method that suits everyone. How should the project manager continually evaluate the effectiveness of the virtual team's engagement? | Hold meetings in accordance with the team members' preferences and availability. 1229 | Establish periodic face-to-face meetings and address the communication topic. | Collect feedback from the team to discuss alternatives to enhance the communication. | Conduct individual meetings to create a trusting environment with team members. |  | C | When evaluating virtual team engagement effectiveness across different countries, the project manager should collect feedback from the team to discuss alternatives to enhance communication. Feedback drives continuous improvement. Holding meetings per preferences (A) addresses scheduling but not evaluation. Periodic face-to-face meetings (B) may not be feasible. Individual meetings (D) assess but do not improve collectively. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 여러 국가에 지리적으로 분산된 팀원들과 새 프로젝트를 시작할 준비를 하고 있다. 프로젝트 관리자는 의사소통 관리 계획을 사용하여 팀원들을 참여시키고 모든 사람에게 적합한 의사소통 방법을 찾고 있다. 프로젝트 관리자는 가상 팀의 참여 효과성을 어떻게 지속적으로 평가해야 하는가? | 팀원의 선호도와 가용성에 따라 회의를 진행한다. | 주기적인 대면 회의를 설정하고 의사소통 주제를 다룬다. | 팀으로부터 피드백을 수집하여 의사소통 향상을 위한 대안을 논의한다. | 팀원과의 신뢰 환경을 조성하기 위해 개별 회의를 진행한다. |  | C | 여러 국가에 분산된 가상 팀의 참여 효과성을 평가할 때, 프로젝트 관리자는 팀으로부터 피드백을 수집하여 의사소통 향상을 위한 대안을 논의해야 한다. 피드백은 지속적인 개선을 이끈다. 선호도에 따른 회의 진행(A)은 일정 문제를 다루지만 평가는 아니다. 주기적 대면 회의(B)는 실현 가능하지 않을 수 있다. 개별 회의(D)는 평가하지만 집단적으로 개선하지는 않는다.
118 | The project manager is having difficulty obtaining approval of the project requirements because there is disagreement among the project stakeholders. This issue is putting the project schedule at risk. What should the project manager do first to facilitate the approval of project requirements? | Hold a team-building event | Identify the source of the disagreement | Review the project charter | Perform a stakeholder analysis |  | B | The first step to resolve stakeholder disagreement on requirements is identifying the source of that disagreement. Understanding the root cause—whether it stems from conflicting interests, miscommunication, or different expectations—enables the PM to select the appropriate conflict resolution technique (collaborating, compromising, smoothing, forcing, or withdrawing). Reviewing the charter (A), performing stakeholder analysis (B), or holding team-building events (C) don't directly address the specific disagreement source. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 프로젝트 관리자는 프로젝트 이해관계자 간의 의견 불일치로 인해 프로젝트 요구사항 승인을 받는 데 어려움을 겪고 있다. 이 문제는 프로젝트 일정을 위험에 빠뜨리고 있다. 프로젝트 관리자는 프로젝트 요구사항 승인을 촉진하기 위해 먼저 무엇을 해야 하는가? | 팀 빌딩 이벤트를 개최한다. | 의견 불일치의 원인을 파악한다. | 프로젝트 헌장을 검토한다. | 이해관계자 분석을 수행한다. |  | B | 요구사항에 대한 이해관계자 의견 불일치를 해결하기 위한 첫 번째 단계는 해당 불일치의 원인을 파악하는 것이다. 근본 원인이 상충하는 이해관계, 의사소통 오류, 또는 다른 기대에서 비롯되는지 이해하면 PM이 적절한 갈등 해결 기법(협력, 타협, 완화, 강제, 회피)을 선택할 수 있다. 헌장 검토(A), 이해관계자 분석 수행(B), 또는 팀 빌딩 이벤트 개최(C)는 특정 불일치의 원인을 직접 다루지 않는다.
119 | A project manager is leading a multiyear project that involves internal and external stakeholders. As the project manager begins to gather requirements, additional business stakeholders express interest in being involved. Which three actions should the project manager take to ensure proper stakeholder involvement? (Choose three) | Include all stakeholders in the stakeholder engagement plan and provide the same level of communication. | Perform a stakeholder assessment to align with the project objectives. | Prioritize stakeholders based on the project phase and need. | Develop a stakeholder impact influence matrix to determine the level of engagement | Classify and rank stakeholders based on their positions in the organization. | B, C, D | When additional stakeholders express interest in a multiyear project, the project manager should take three actions: perform a stakeholder assessment to align with project objectives (B), prioritize stakeholders based on the project phase and need (C), and develop a stakeholder impact influence matrix to determine the level of engagement (D). These actions ensure structured, appropriate engagement based on actual influence and interest. Including all stakeholders with equal communication (A) is inefficient—different stakeholders have different needs. Classifying by organizational position (E) may not reflect actual influence or interest in the project. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 관리자가 내부 및 외부 이해관계자가 참여하는 다년 프로젝트를 이끌고 있다. 프로젝트 관리자가 요구사항을 수집하기 시작하면서 추가 비즈니스 이해관계자들이 참여에 관심을 표명했다. 프로젝트 관리자가 적절한 이해관계자 참여를 보장하기 위해 취해야 할 세 가지 조치는 무엇인가? (3개 선택) | 모든 이해관계자를 이해관계자 참여 계획에 포함시키고 동일한 수준의 의사소통을 제공한다. | 프로젝트 목표에 맞추기 위한 이해관계자 평가를 수행한다. | 프로젝트 단계와 필요에 따라 이해관계자의 우선순위를 정한다. | 참여 수준을 결정하기 위한 이해관계자 영향력 매트릭스를 개발한다. | 조직 내 직위에 따라 이해관계자를 분류하고 순위를 매긴다. | B, C, D | 다년 프로젝트에서 추가 이해관계자가 관심을 표명할 때, 프로젝트 관리자는 세 가지 조치를 취해야 한다: 프로젝트 목표에 맞추기 위한 이해관계자 평가 수행(B), 프로젝트 단계와 필요에 따라 이해관계자 우선순위 지정(C), 참여 수준 결정을 위한 이해관계자 영향력 매트릭스 개발(D). 이 조치들은 실제 영향력과 관심에 기반한 체계적이고 적절한 참여를 보장한다. 모든 이해관계자에게 동일한 의사소통 제공(A)은 비효율적이다—다른 이해관계자는 다른 요구를 가진다. 조직 직위에 따른 분류(E)는 프로젝트에 대한 실제 영향력이나 관심을 반영하지 않을 수 있다.
120 | A project manager is managing a hybrid project that is using a contractor for a few key deliverables. The contractor has been hired to perform an important delivery, but has not yet confirmed that they can meet the required schedule. What should the project manager do? | Plan the task delivery with the contractor or vendor, highlighting the criticality of the current situation, | Review the project scope with the stakeholders and remove the potentially delayed item from the scope. | Check with procurement to see if there is another previously used contractor who can develop the task. | Escalate the issue to the procurement team as the final delivery date of the project will be impacted. |  | A | When a contractor hired for a key deliverable has not confirmed they can meet the schedule, the project manager should plan task delivery with the contractor, highlighting the criticality of the situation. Proactive engagement manages risk. Removing the item from scope (B) loses value. Checking with procurement for alternatives (C) may help but is not the first action. Escalating to procurement (D) is premature. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Hybrid/Tailoring | 프로젝트 관리자가 몇 가지 핵심 산출물을 위해 계약업체를 사용하는 하이브리드 프로젝트를 관리하고 있다. 계약업체가 중요한 산출물 수행을 위해 고용되었지만, 아직 요구 일정을 충족할 수 있는지 확인하지 않았다. 프로젝트 관리자는 어떻게 해야 하는가? | 현재 상황의 중요성을 강조하면서 계약업체와 작업 인도 계획을 수립한다. | 이해관계자와 프로젝트 범위를 검토하고 잠재적으로 지연되는 항목을 범위에서 제거한다. | 조달 부서에 확인하여 해당 작업을 수행할 수 있는 기존 계약업체가 있는지 알아본다. | 프로젝트의 최종 납기일이 영향을 받을 것이므로 조달 팀에 문제를 에스컬레이션한다. |  | A | 핵심 산출물을 위해 고용된 계약업체가 일정 충족을 확인하지 않았을 때, 프로젝트 관리자는 상황의 중요성을 강조하면서 계약업체와 작업 인도 계획을 수립해야 한다. 능동적인 참여가 리스크를 관리한다. 범위에서 항목 제거(B)는 가치를 잃는다. 조달에 대체 업체 확인(C)은 도움이 될 수 있지만 첫 번째 조치는 아니다. 조달 팀에 에스컬레이션(D)은 시기상조이다.
121 | A large, multinational organization is reevaluating its policy on project management approaches. Team members are complaining about having different processes for each project they are on. Currently, predictive, agile, and hybrid methodologies are being used. A project manager is now part of a team working on standard criteria for approach selection for new projects. What should the project manager recommend? | Determine the types of projects, constraints, and resources to initiate standard tailoring. | Identify the most commonly used methodology currently and apply that to all future projects. | Simplify the approaches to use either a single agile or a single predictive methodology. | Incorporate both structure and flexibility through custom tailoring for all projects. |  | A | When standardizing project management approaches across a large organization using predictive, agile, and hybrid, the project manager should recommend determining the types of projects, constraints, and resources to initiate standard tailoring. Context-based tailoring criteria enable appropriate methodology selection. Identifying the most common methodology (B) ignores project variability. Simplifying to a single methodology (C) lacks flexibility. Incorporating custom tailoring for all (D) sounds flexible but lacks the systematic criteria that tailoring guidance requires. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Hybrid | Tailored Approach | People | Lead the Project Team | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Hybrid/Tailoring | 대규모 다국적 조직이 프로젝트 관리 접근 방식에 대한 정책을 재평가하고 있다. 팀원들은 참여하는 각 프로젝트마다 다른 프로세스를 사용하는 것에 대해 불만을 제기하고 있다. 현재 예측형, 애자일, 하이브리드 방법론이 사용되고 있다. 프로젝트 관리자가 새 프로젝트를 위한 접근 방식 선택 표준 기준을 작업하는 팀의 일원이 되었다. 프로젝트 관리자는 무엇을 권장해야 하는가? | 프로젝트 유형, 제약 조건, 자원을 파악하여 표준 테일러링을 시작한다. | 현재 가장 일반적으로 사용되는 방법론을 파악하고 모든 향후 프로젝트에 적용한다. | 단일 애자일 또는 단일 예측형 방법론을 사용하도록 접근 방식을 단순화한다. | 모든 프로젝트에 대해 맞춤형 테일러링을 통해 구조와 유연성을 모두 통합한다. |  | A | 예측형, 애자일, 하이브리드를 사용하는 대규모 조직에서 프로젝트 관리 접근 방식을 표준화할 때, 프로젝트 관리자는 프로젝트 유형, 제약 조건, 자원을 파악하여 표준 테일러링을 시작하도록 권장해야 한다. 맥락 기반 테일러링 기준은 적절한 방법론 선택을 가능하게 한다. 가장 일반적인 방법론 식별(B)은 프로젝트 가변성을 무시한다. 단일 방법론으로 단순화(C)는 유연성이 부족하다. 모든 프로젝트에 맞춤 테일러링 통합(D)은 유연해 보이지만 테일러링 지침이 요구하는 체계적 기준이 부족하다.
122 | A project manager is confused when the operational results from previous iteration solutions have not been acceptable to the client. Team members have already delivered all previous solutions, which were accepted by the client as complete. What should the project manager do? | Recommend a change in the project methodology or the approach. | Determine the criteria and measuring systems for objective success. | Allocate more time for mentoring project team members. | Develop and execute a stakeholder engagement strategy. |  | B | The correct answer is B. Determine the criteria and measuring systems for objective success. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration and ensure value delivery while adhering to agile principles. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자는 이전 이터레이션 솔루션의 운영 결과가 고객에게 수용되지 않아 혼란스러워하고 있다. 팀원들은 이미 모든 이전 솔루션을 전달했으며, 고객은 이를 완료로 수락했다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 방법론 또는 접근 방식의 변경을 권장한다. | 객관적 성공을 위한 기준과 측정 시스템을 결정한다. | 프로젝트 팀원 멘토링에 더 많은 시간을 할당한다. | 이해관계자 참여 전략을 개발하고 실행한다. |  | B | 정답은 B이다. 객관적 성공을 위한 기준과 측정 시스템을 결정한다. 애자일 관행은 반복적 전달, 팀 역량 강화, 지속적 개선을 강조한다. PM은 협업을 촉진하고 애자일 원칙을 준수하면서 가치 전달을 보장해야 한다.
123 | A project manager sent the first communication about the project management plan to the team. The next day, two field engineers were asking about their roles and the project schedule. What should the project manager have done? | Briefed each team member on their roles before sending the project management plan | Confirmed that the communication was understood and solicited feedback from the team | Sent the roles and responsibilities matrix along with the project management plan | Discussed the roles with the managers to help explain them to their team members |  | B | When field engineers ask about roles and project schedule after receiving the project management plan, the project manager should have confirmed that the communication was understood and solicited feedback from the team. Ensuring comprehension prevents confusion. Briefing each member before sending (A) is proactive but does not confirm receipt understanding. Sending the RACI matrix (C) provides information but does not verify understanding. Discussing with managers (D) is indirect. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Schedule Management | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 프로젝트 관리자가 프로젝트 관리 계획에 대한 첫 번째 의사소통을 팀에 보냈다. 다음 날, 두 명의 현장 엔지니어가 자신들의 역할과 프로젝트 일정에 대해 질문하고 있었다. 프로젝트 관리자는 무엇을 했어야 하는가? | 프로젝트 관리 계획을 보내기 전에 각 팀원에게 역할을 브리핑한다. | 의사소통이 이해되었는지 확인하고 팀으로부터 피드백을 요청한다. | 프로젝트 관리 계획과 함께 역할 및 책임 매트릭스를 보낸다. | 관리자들과 역할을 논의하여 팀원들에게 설명하는 것을 돕도록 한다. |  | B | 현장 엔지니어들이 프로젝트 관리 계획을 받은 후 역할과 일정에 대해 질문할 때, 프로젝트 관리자는 의사소통이 이해되었는지 확인하고 팀으로부터 피드백을 요청했어야 한다. 이해 확인은 혼란을 방지한다. 보내기 전 각 팀원 브리핑(A)은 능동적이지만 수신 후 이해를 확인하지는 않는다. RACI 매트릭스 전송(C)은 정보를 제공하지만 이해를 검증하지 않는다. 관리자와 논의(D)는 간접적이다.
124 | A project manager manages a bridge construction project. The project manager has received a major change request from a regulatory stakeholder to add one branch of the bridge to the engineering design. The project manager prepared a change request, which was reviewed and accepted by the change control board (CCB). What should the project manager do now? | Communicate the decision to the stakeholder who requested the change. | Evaluate the adjustments to the project management plan. | Include the new branch of the bridge in the design. | Notify the project team about the change request ' s approval. |  | A | After a change request is approved by the CCB to add a bridge branch to the engineering design, the project manager should communicate the decision to the stakeholder who requested the change. Transparent communication maintains trust. Evaluating adjustments to the project plan (B) is a subsequent step. Including the branch in design (C) follows communication. Notifying the project team (D) is important but the requesting stakeholder should be informed first. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 매니저가 교량 건설 프로젝트를 관리하고 있다. 규제 이해관계자로부터 공학 설계에 교량 분기선 하나를 추가해 달라는 주요 변경 요청을 받았다. 프로젝트 매니저가 변경 요청서를 작성했고, 변경통제위원회(CCB)가 이를 검토하여 승인했다. 프로젝트 매니저가 지금 해야 할 일은? | 변경을 요청한 이해관계자에게 결정 사항을 전달한다. | 프로젝트 관리 계획서의 조정 사항을 평가한다. | 새로운 교량 분기선을 설계에 포함한다. | 프로젝트 팀에게 변경 요청 승인을 알린다. |  | A | CCB가 교량 분기선 추가 변경 요청을 승인한 후, 프로젝트 매니저는 변경을 요청한 이해관계자에게 결정 사항을 전달해야 한다. 투명한 커뮤니케이션은 신뢰를 유지한다. 프로젝트 계획 조정 평가(B)는 후속 단계이다. 설계에 분기선 포함(C)은 커뮤니케이션 이후에 수행한다. 프로젝트 팀 통보(D)도 중요하나, 요청한 이해관계자에게 먼저 알려야 한다.
125 | In a software development project, the product owner and development team agree on a sprint backlog. The highest priority in the backlog is to build a payment module. The team worked on the module during the first half of the sprint, but now two developers want to spend the rest of the sprint focusing on refactoring another feature that might create issues in the future. What should the project manager do? | Escalate the issue to the developers' functional managers | Restate to the developers the importance of focusing and meeting the sprint goal. | Let the developers focus on the refactoring work and discuss it in the retrospective | Praise the developers for their proactivity and focus on quality. |  | B | When developers want to spend the rest of the sprint on refactoring instead of completing the highest-priority payment module, the project manager should restate the importance of focusing on and meeting the sprint goal. Sprint commitment must be honored. Escalating to functional managers (A) bypasses agile self-organization. Letting them refactor and discussing in retrospective (C) abandons the sprint goal. Praising proactivity (D) rewards deviation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 소프트웨어 개발 프로젝트에서 제품 소유자와 개발 팀이 스프린트 백로그에 합의했다. 백로그에서 가장 높은 우선순위는 결제 모듈 구축이다. 팀은 스프린트 전반부에 이 모듈을 작업했으나, 이제 두 명의 개발자가 나머지 스프린트 기간에 향후 문제를 일으킬 수 있는 다른 기능의 리팩토링에 집중하고 싶어 한다. 프로젝트 매니저는 어떻게 해야 하는가? | 개발자들의 기능 관리자에게 이슈를 에스컬레이션한다. | 개발자들에게 스프린트 목표에 집중하고 달성하는 것의 중요성을 재강조한다. | 개발자들이 리팩토링 작업에 집중하도록 하고 회고에서 논의한다. | 개발자들의 선제적 대응과 품질 집중을 칭찬한다. |  | B | 개발자들이 최우선순위인 결제 모듈 완료 대신 리팩토링에 나머지 스프린트를 보내려 할 때, 프로젝트 매니저는 스프린트 목표에 집중하고 달성하는 것의 중요성을 재강조해야 한다. 스프린트 약속은 반드시 지켜야 한다. 기능 관리자에게 에스컬레이션(A)은 애자일 자기 조직화를 우회한다. 리팩토링을 허용하고 회고에서 논의(C)는 스프린트 목표를 포기하는 것이다. 선제적 대응 칭찬(D)은 이탈을 보상하는 것이다.
126 | A project manager has recently moved to an organization to lead a key project. The project manager notices that team performance is below the target, and the tasks assigned are not delivered on time. Team commitment is also not at the expected level. What should the project manager do? | Hire a project team leader who can influence the project team members. | Study and determine the appropriate leadership style suitable for the team. | Apply an agile approach to help improve team performance. | Schedule a meeting and communicate the performance concern to the team. |  | B | Effective PMs must be able to shift between leadership styles based on the situation. Studying the team dynamics and determining the appropriate leadership style is essential for improving team performance and commitment. Different situations demand different approaches—from directive to collaborative to delegative—and the PM's flexibility in this regard directly impacts team motivation and project outcomes. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Develop a Common Vision | Schedule | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 매니저가 최근 한 조직으로 이동하여 핵심 프로젝트를 이끌게 되었다. 팀 성과가 목표에 미치지 못하고, 배정된 업무가 제때 완료되지 않는 것을 발견했다. 팀의 헌신도 또한 기대 수준에 미치지 못한다. 프로젝트 매니저는 어떻게 해야 하는가? | 프로젝트 팀원들에게 영향력을 행사할 수 있는 프로젝트 팀 리더를 고용한다. | 팀에 적합한 리더십 스타일을 연구하고 결정한다. | 팀 성과 향상을 위해 애자일 접근법을 적용한다. | 회의를 잡고 팀에게 성과 우려 사항을 전달한다. |  | B | 효과적인 PM은 상황에 따라 리더십 스타일을 전환할 수 있어야 한다. 팀 역학을 연구하고 적절한 리더십 스타일을 결정하는 것은 팀 성과와 헌신을 개선하는 데 필수적이다. 상황에 따라 지시형에서 협력형, 위임형까지 다른 접근이 필요하며, PM의 유연성은 팀 동기 부여와 프로젝트 성과에 직접적인 영향을 미친다.
127 | A project manager is overseeing a 10-mile piping installation project that was supposed to spend US$15,000 per mile of piping installation and should complete the project exactly 20 weeks from its start. The project manager just found out that only 80% of the work has been completed. What is the budget at completion (BAC)? | 150000 | 100000 | 250000 | 300000 |  | A | Budget at completion (BAC) is the total planned value of the project. It is calculated by multiplying the number of work units by the cost per unit: BAC = 10 miles × $15,000 per mile = $150,000. The 80% completion rate is irrelevant to this calculation—BAC represents the original total planned budget, not the earned value or actual cost to date. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 매니저가 10마일 배관 설치 프로젝트를 감독하고 있다. 마일당 US$15,000를 지출할 계획이며 착수일로부터 정확히 20주 내에 프로젝트를 완료해야 한다. 프로젝트 매니저는 방금 작업의 80%만 완료되었다는 것을 알게 되었다. 완료 시 예산(BAC)은 얼마인가? | 150000 | 100000 | 250000 | 300000 |  | A | 완료 시 예산(BAC)은 프로젝트의 총 계획 가치이다. 작업 단위 수에 단위당 비용을 곱하여 계산한다: BAC = 10마일 × $15,000/마일 = $150,000. 80% 완료율은 이 계산과 무관하다. BAC는 원래 총 계획 예산을 나타내며, 획득 가치나 현재까지의 실제 비용이 아니다.
128 | One of the key stakeholders on the project team reaches out with an additional requirement that may impact the overall schedule. A discussion with another stakeholder suggests that this might just be a small task. What should the project manager do? | Manage the engagement of this stakeholder. | Request further clarification of the requirement | Perform a qualitative risk analysis | Coordinate design document preparation |  | B | When a key stakeholder introduces an additional requirement and another stakeholder suggests it is a small task, the project manager should request further clarification of the requirement. Thorough understanding ensures accurate impact assessment before action. Managing stakeholder engagement (A) addresses the relationship, not the requirement. Performing qualitative risk analysis (C) is premature without understanding the requirement. Coordinating design documents (D) acts before clarification. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 팀의 핵심 이해관계자 중 한 명이 전체 일정에 영향을 줄 수 있는 추가 요구사항을 가지고 연락해 왔다. 다른 이해관계자와의 논의에서 이것은 단지 작은 업무일 수 있다고 한다. 프로젝트 매니저는 어떻게 해야 하는가? | 이 이해관계자의 참여를 관리한다. | 요구사항에 대한 추가 명확화를 요청한다. | 정성적 리스크 분석을 수행한다. | 설계 문서 준비를 조율한다. |  | B | 핵심 이해관계자가 추가 요구사항을 제시하고 다른 이해관계자가 작은 업무라고 할 때, 프로젝트 매니저는 요구사항에 대한 추가 명확화를 요청해야 한다. 철저한 이해가 조치 전 정확한 영향 평가를 보장한다. 이해관계자 참여 관리(A)는 관계를 다루지 요구사항을 다루지 않는다. 정성적 리스크 분석(C)은 요구사항 이해 없이 시기상조이다. 설계 문서 조율(D)은 명확화 전에 행동하는 것이다.
129 | A project manager is leading a large-scale project to be deployed in another country, for an external company. After working with the project team, the project manager learns there are many stakeholders from the project manager's organization, the client organization, and the local community. What should the project manager do after identifying the stakeholders? | Prioritize the stakeholders that are more interested in the success of the project. | Prioritize stakeholders from the client ' s organization and the local community. | Prioritize stakeholders from the project manager ' s own organization. | Prioritize the stakeholders that may have more impact on the development of the project. |  | D | After identifying many stakeholders from the PM's organization, client organization, and local community on a large-scale international project, the project manager should prioritize stakeholders that may have more impact on the development of the project. Influence-based prioritization ensures effective engagement. Prioritizing interested stakeholders (A) ignores power dynamics. Prioritizing the client's organization and community (B) is biased. Prioritizing the PM's own organization (C) is internally focused. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 매니저가 외부 회사를 위해 다른 나라에 배포될 대규모 프로젝트를 이끌고 있다. 프로젝트 팀과 작업한 후, 프로젝트 매니저 조직, 고객 조직, 현지 커뮤니티의 많은 이해관계자가 있음을 알게 되었다. 이해관계자를 식별한 후 프로젝트 매니저가 해야 할 일은? | 프로젝트 성공에 더 관심 있는 이해관계자를 우선순위로 정한다. | 고객 조직과 현지 커뮤니티의 이해관계자를 우선순위로 정한다. | 프로젝트 매니저 자체 조직의 이해관계자를 우선순위로 정한다. | 프로젝트 개발에 더 큰 영향을 미칠 수 있는 이해관계자를 우선순위로 정한다. |  | D | 대규모 국제 프로젝트에서 PM 조직, 고객 조직, 현지 커뮤니티의 많은 이해관계자를 식별한 후, 프로젝트 매니저는 프로젝트 개발에 더 큰 영향을 미칠 수 있는 이해관계자를 우선순위로 정해야 한다. 영향력 기반 우선순위 지정은 효과적인 참여를 보장한다. 관심 있는 이해관계자 우선(A)은 권력 역학을 무시한다. 고객과 커뮤니티 우선(B)은 편향적이다. 자체 조직 우선(C)은 내부 중심적이다.
130 | A drone manufacturing company is designing its first drone. The new project architect has called the project manager to review the project scope. The architect wants to reshuffle the scope and schedule to test the drone functionality first. The project team disagrees because the scope has already been approved and any change might affect the timelines set by the CEO. What should the project manager recommend? | Agree to review the architect ' s new proposal to assess the impact on the timelines set by the CEO. | Register an issue in the log regarding the timeline delay to the CEO ' s approved plans before agreeing to change the project scope. | Review the timelines with the architect and invite the CEO to the meeting to make sure all the stakeholders are involved. | Reject the review as the completed project timeline is set by the company ' s CEO and has already been approved. |  | A | When the project architect wants to reshuffle scope to test drone functionality first while the team worries about CEO-approved timelines, the project manager should agree to review the architect's proposal and assess timeline impact. Evaluating the proposal allows informed decision-making. Registering an issue before agreeing (B) is premature. Reviewing timelines with the CEO present (C) escalates prematurely. Rejecting the review (D) closes off potentially valuable input. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 드론 제조 회사가 첫 번째 드론을 설계하고 있다. 새로운 프로젝트 아키텍트가 프로젝트 매니저에게 프로젝트 범위를 검토하자고 연락했다. 아키텍트는 드론 기능을 먼저 테스트하기 위해 범위와 일정을 재조정하고 싶어 한다. 프로젝트 팀은 범위가 이미 승인되었고 변경 시 CEO가 설정한 일정에 영향을 줄 수 있어 반대한다. 프로젝트 매니저의 권고 사항은? | 아키텍트의 새 제안을 검토하여 CEO가 설정한 일정에 미치는 영향을 평가하는 데 동의한다. | CEO가 승인한 계획의 일정 지연에 관한 이슈를 로그에 등록한 후 프로젝트 범위 변경에 동의한다. | 아키텍트와 일정을 검토하고 모든 이해관계자가 참여하도록 CEO를 회의에 초대한다. | 완료된 프로젝트 일정은 회사 CEO가 설정하고 이미 승인되었으므로 검토를 거부한다. |  | A | 프로젝트 아키텍트가 드론 기능 우선 테스트를 위해 범위를 재조정하려 하고 팀이 CEO 승인 일정을 우려할 때, 프로젝트 매니저는 아키텍트의 제안을 검토하고 일정 영향을 평가하는 데 동의해야 한다. 제안 평가는 정보에 기반한 의사결정을 가능하게 한다. 동의 전 이슈 등록(B)은 시기상조이다. CEO를 포함한 일정 검토(C)는 조기 에스컬레이션이다. 검토 거부(D)는 잠재적으로 가치 있는 의견을 차단한다.
131 | In a marine construction project, the project manager is informed by the marine authority that the work permit will not be issued until certain environmental reinforcement work has been completed. After reviewing the project management plan, the reinforcement work is not included in the project scope. What should the project manager do? | Organize a meeting with the team and update the work breakdown structure (WBS). | Communicate with an officer in the environmental protection department to check if it is 1103 necessary. | Start the organization ' s change control process via a change request. | Raise this issue, and review and update the progress report for the next monthly project meeting. |  | C | When the marine authority requires environmental reinforcement work not included in project scope before issuing a work permit, the project manager should start the organization's change control process via a change request. Formal change control integrates new scope systematically. Organizing a meeting to update the WBS (A) bypasses change control. Checking with the environmental department (B) is not the PM's decision. Raising it at the next monthly meeting (D) delays action. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Finance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 해양 건설 프로젝트에서 해양 당국이 특정 환경 보강 작업이 완료될 때까지 작업 허가를 발급하지 않겠다고 프로젝트 매니저에게 알렸다. 프로젝트 관리 계획서를 검토한 결과, 보강 작업은 프로젝트 범위에 포함되어 있지 않다. 프로젝트 매니저는 어떻게 해야 하는가? | 팀과 회의를 조직하고 작업 분류 체계(WBS)를 업데이트한다. | 환경보호부서 담당자와 소통하여 필요 여부를 확인한다. | 변경 요청을 통해 조직의 변경 통제 프로세스를 시작한다. | 이 이슈를 제기하고, 다음 월간 프로젝트 회의를 위한 진행 보고서를 검토하고 업데이트한다. |  | C | 해양 당국이 프로젝트 범위에 없는 환경 보강 작업을 작업 허가 발급 전에 요구할 때, 프로젝트 매니저는 변경 요청을 통해 조직의 변경 통제 프로세스를 시작해야 한다. 공식적인 변경 통제는 새로운 범위를 체계적으로 통합한다. WBS 업데이트 회의(A)는 변경 통제를 우회한다. 환경부서 확인(B)은 PM의 결정이 아니다. 월간 회의에서 제기(D)는 조치를 지연시킨다.
132 | An IT project manager has been referred to a new, highly rated vendor that provides quality assurance professional services. The project manager plans to engage the quality assurance vendor on a new project, but their rates do not fit into what was budgeted for the project. What should the project manager do next? | Engage the procurement team. | Engage the project stakeholders. | Discuss the issue with the management team. | Update the contract with a lower rate, |  | B | When a highly rated vendor's rates exceed the project budget, the project manager should engage the project stakeholders. Stakeholders can provide input on alternative vendors, additional funding, or negotiation strategies while ensuring transparency and buy-in. Engaging the procurement team (A) is narrower. Discussing with management (C) is one stakeholder group. Updating the contract with a lower rate (D) assumes unilateral negotiation power. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | IT 프로젝트 매니저가 품질 보증 전문 서비스를 제공하는 높은 평가를 받는 새 벤더를 소개받았다. 프로젝트 매니저는 새 프로젝트에 이 품질 보증 벤더를 참여시키려 하지만, 벤더의 요율이 프로젝트 예산에 맞지 않는다. 프로젝트 매니저가 다음으로 해야 할 일은? | 조달 팀을 참여시킨다. | 프로젝트 이해관계자를 참여시킨다. | 관리팀과 이슈를 논의한다. | 더 낮은 요율로 계약을 업데이트한다. |  | B | 높은 평가를 받는 벤더의 요율이 프로젝트 예산을 초과할 때, 프로젝트 매니저는 프로젝트 이해관계자를 참여시켜야 한다. 이해관계자는 대안 벤더, 추가 자금, 또는 협상 전략에 대한 의견을 제공하면서 투명성과 동의를 보장할 수 있다. 조달 팀 참여(A)는 범위가 좁다. 관리팀과 논의(C)는 하나의 이해관계자 그룹이다. 낮은 요율로 계약 업데이트(D)는 일방적인 협상력을 가정한다.
133 | An investment company is interested in unifying direction and control criteria in one of its principal projects. The project manager was advised to enforce the main framework of this initiative. What should the project manager do first? | Identify and interview all of the relevant stakeholders. | Get direction and control framework requirements from stakeholders. | Develop an engagement plan to achieve consensus. | Document the direction and control framework into the project charter. |  | B | The correct answer is B. Get direction and control framework requirements from stakeholders. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 투자 회사가 주요 프로젝트 중 하나에서 방향과 통제 기준을 통합하는 데 관심이 있다. 프로젝트 매니저는 이 이니셔티브의 주요 프레임워크를 시행하라는 조언을 받았다. 프로젝트 매니저가 먼저 해야 할 일은? | 모든 관련 이해관계자를 식별하고 면담한다. | 이해관계자로부터 방향과 통제 프레임워크 요구사항을 수집한다. | 합의를 달성하기 위한 참여 계획을 개발한다. | 방향과 통제 프레임워크를 프로젝트 헌장에 문서화한다. |  | B | 정답은 B이다. 이해관계자로부터 방향과 통제 프레임워크 요구사항을 수집한다. 이 접근법은 상황을 효과적으로 다루고, 적절한 프로세스를 유지하며, 이해관계자 기대와 프로젝트 목표와의 일치를 보장하는 프로젝트 관리 모범 사례를 따른다.
134 | During a documentation audit of an international company, it was identified that the last version of the project schedule was from one month ago even though the project manager knew it was recently updated. How should the project manager have handled documentation for the project? | Updated the project management plan regularly and had it securely shared with all stakeholders | Reviewed the risk register to identify a response plan for the audit | Assigned a project team member to ensure all project documentation was updated | Kept documentation in the project management information system (PMIS) and shared it with appropriate stakeholders |  | D | When a documentation audit reveals the project schedule is a month old despite being recently updated, the project manager should have kept documentation in the PMIS and shared it with appropriate stakeholders. PMIS ensures centralized, current, accessible documentation. Updating the plan regularly and sharing (A) is partial. Reviewing the risk register for audit response (B) is reactive. Assigning a team member for updates (C) is insufficient without a proper system. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 국제 회사의 문서 감사 중, 프로젝트 매니저가 최근 업데이트했음을 알고 있음에도 프로젝트 일정의 최신 버전이 1개월 전 것으로 확인되었다. 프로젝트 매니저는 프로젝트 문서를 어떻게 관리했어야 했는가? | 프로젝트 관리 계획서를 정기적으로 업데이트하고 모든 이해관계자와 안전하게 공유했다. | 감사에 대한 대응 계획을 식별하기 위해 리스크 등록부를 검토했다. | 모든 프로젝트 문서가 업데이트되도록 프로젝트 팀원을 배정했다. | 문서를 프로젝트 관리 정보 시스템(PMIS)에 보관하고 적절한 이해관계자와 공유했다. |  | D | 문서 감사에서 최근 업데이트했음에도 프로젝트 일정이 1개월 전 것으로 나타날 때, 프로젝트 매니저는 PMIS에 문서를 보관하고 적절한 이해관계자와 공유했어야 한다. PMIS는 중앙 집중적이고 최신이며 접근 가능한 문서 관리를 보장한다. 정기적 업데이트와 공유(A)는 부분적이다. 감사 대응 리스크 등록부 검토(B)는 반응적이다. 팀원 배정(C)은 적절한 시스템 없이는 불충분하다.
135 | During daily team coordination meetings, team members constantly ask which tasks they should focus on first. How should the project manager ensure the team is fully productive? | Review the project backlog during the team's coordination meeting | Encourage team members to prioritize the product backlog 1289 | Work with the product owner to ensure the product backlog is prioritized | Ensure team members are working according to the project management plan |  | C | When team members constantly ask which tasks to focus on first during coordination meetings, the project manager should work with the product owner to ensure the product backlog is prioritized. Clear prioritization provides direction. Reviewing the backlog during meetings (A) is repetitive. Encouraging team members to prioritize (B) blurs roles. Following the project management plan (D) is too rigid for evolving work. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 일일 팀 조율 회의에서 팀원들이 어떤 업무를 먼저 집중해야 하는지 계속 묻는다. 프로젝트 매니저는 팀이 완전히 생산적이 되도록 어떻게 해야 하는가? | 팀 조율 회의에서 프로젝트 백로그를 검토한다. | 팀원들이 제품 백로그의 우선순위를 정하도록 권장한다. | 제품 소유자와 협력하여 제품 백로그의 우선순위가 정해져 있도록 한다. | 팀원들이 프로젝트 관리 계획서에 따라 작업하도록 한다. |  | C | 팀원들이 조율 회의에서 어떤 업무를 먼저 해야 하는지 계속 물을 때, 프로젝트 매니저는 제품 소유자와 협력하여 제품 백로그의 우선순위가 정해져 있도록 해야 한다. 명확한 우선순위는 방향을 제시한다. 회의에서 백로그 검토(A)는 반복적이다. 팀원에게 우선순위 설정 권장(B)은 역할을 흐린다. 프로젝트 관리 계획서 따르기(D)는 진화하는 작업에 너무 경직되다.
136 | A new stakeholder is unaware of the existence of the project a few weeks before the final deliverable and project completion. What should the project manager do first? | Analyze this stakeholder's interest and impact. | Communicate the full details of the project activities to the stakeholder and solicit input. | Share the summary of the project activities with the stakeholder and conclude the project. | Escalate this issue to the project sponsor. |  | A | When a new stakeholder appears a few weeks before project completion, the project manager should first analyze this stakeholder's interest and impact. Assessment determines the appropriate engagement approach before acting. Communicating full project details and soliciting input (B) risks last-minute scope changes without understanding relevance. Sharing a summary and concluding (C) may jeopardize acceptance. Escalating to the sponsor (D) is premature without analysis. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 새로운 이해관계자가 최종 인도물과 프로젝트 완료 몇 주 전에 프로젝트의 존재를 알지 못하고 있다. 프로젝트 매니저가 먼저 해야 할 일은? | 이 이해관계자의 관심과 영향력을 분석한다. | 이해관계자에게 프로젝트 활동의 전체 세부 사항을 전달하고 의견을 구한다. | 이해관계자에게 프로젝트 활동 요약을 공유하고 프로젝트를 마무리한다. | 이 이슈를 프로젝트 스폰서에게 에스컬레이션한다. |  | A | 프로젝트 완료 몇 주 전에 새로운 이해관계자가 나타날 때, 프로젝트 매니저는 먼저 이 이해관계자의 관심과 영향력을 분석해야 한다. 평가는 조치 전에 적절한 참여 접근방식을 결정한다. 전체 세부 사항 전달과 의견 구하기(B)는 관련성 파악 없이 막바지 범위 변경 위험이 있다. 요약 공유 후 마무리(C)는 수용을 위태롭게 할 수 있다. 스폰서에게 에스컬레이션(D)은 분석 없이 시기상조이다.
137 | An experienced project manager has been assigned to a hybrid project that requires an extensive amount of information to be updated. Which tool should the project manager use along with the team? | SharePoint | Pareto chart | Excel files | Kanban board |  | D | The correct answer is D. Kanban board. A hybrid approach leverages the strengths of both predictive and agile methodologies. The PM should tailor the approach to the project's unique characteristics and organizational environment. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Predictive-Agile Blend | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 경험 많은 프로젝트 매니저가 대량의 정보 업데이트가 필요한 하이브리드 프로젝트에 배정되었다. 프로젝트 매니저가 팀과 함께 사용해야 할 도구는? | SharePoint | 파레토 차트 | Excel 파일 | 칸반 보드 |  | D | 정답은 D이다. 칸반 보드. 하이브리드 접근법은 예측형과 애자일 방법론의 장점을 활용한다. PM은 프로젝트의 고유한 특성과 조직 환경에 맞게 접근법을 맞춤화해야 한다.
138 | The project leader for an agile team has discovered that a certain team member has been struggling with an impediment that is hindering the team's progress. The project is now at risk of completing later than expected. What should the project leader do? | Identify the impediment during the retrospective | Escalate the impediment and associated risks to the business sponsor. | Identify the impediment and associated risks at the daily standup. | Report the impediment to the functional manager. |  | C | When a team member is struggling with an impediment that puts the project at risk of late completion, the project leader should identify the impediment and associated risks at the daily standup. The standup surfaces blockers for immediate team attention. Identifying during retrospective (A) delays action. Escalating to the sponsor (B) bypasses team-level resolution. Reporting to the functional manager (D) is outside the agile team structure. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | 애자일 팀의 프로젝트 리더가 특정 팀원이 팀의 진행을 방해하는 장애물로 어려움을 겪고 있음을 발견했다. 프로젝트가 예상보다 늦게 완료될 위험에 처해 있다. 프로젝트 리더는 어떻게 해야 하는가? | 회고 시 장애물을 식별한다. | 장애물과 관련 리스크를 비즈니스 스폰서에게 에스컬레이션한다. | 일일 스탠드업에서 장애물과 관련 리스크를 식별한다. | 장애물을 기능 관리자에게 보고한다. |  | C | 팀원이 프로젝트 늦은 완료 위험을 초래하는 장애물로 어려움을 겪을 때, 프로젝트 리더는 일일 스탠드업에서 장애물과 관련 리스크를 식별해야 한다. 스탠드업은 즉각적인 팀 주목을 위해 장애물을 표면화한다. 회고에서 식별(A)은 조치를 지연시킨다. 스폰서에게 에스컬레이션(B)은 팀 수준 해결을 우회한다. 기능 관리자에게 보고(D)는 애자일 팀 구조 외부이다.
139 | A project manager has been assigned a low-priority project that includes new team members with no previous formal project experience. The project team has requested deadline extensions for the first development increment twice already. What should the project manager do to support the team? | Create a change request to extend the project ' s duration and costs. | Include buffer time in the schedule to absorb future delays. | Escalate the impact on the schedule to the project sponsor. | Provide feedback to the team using project performance evaluations. |  | B | When a low-priority project with inexperienced team members has already requested two deadline extensions, the project manager should include buffer time in the schedule to absorb future delays. Buffer provides realistic planning for uncertainty. Creating a change request (A) formalizes extensions but does not prevent recurrence. Escalating to the sponsor (C) is premature. Performance evaluations (D) address individuals, not schedule planning. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 매니저가 이전 공식 프로젝트 경험이 없는 새 팀원이 포함된 낮은 우선순위 프로젝트에 배정되었다. 프로젝트 팀은 첫 번째 개발 증분의 마감 연장을 이미 두 번 요청했다. 팀을 지원하기 위해 프로젝트 매니저는 어떻게 해야 하는가? | 프로젝트 기간과 비용을 연장하는 변경 요청을 작성한다. | 향후 지연을 흡수할 수 있도록 일정에 버퍼 시간을 포함한다. | 일정에 대한 영향을 프로젝트 스폰서에게 에스컬레이션한다. | 프로젝트 성과 평가를 사용하여 팀에게 피드백을 제공한다. |  | B | 경험이 부족한 팀원이 포함된 낮은 우선순위 프로젝트에서 마감 연장을 이미 두 번 요청했을 때, 프로젝트 매니저는 향후 지연을 흡수할 수 있도록 일정에 버퍼 시간을 포함해야 한다. 버퍼는 불확실성에 대한 현실적인 계획을 제공한다. 변경 요청(A)은 연장을 공식화하지만 재발을 방지하지 못한다. 스폰서에게 에스컬레이션(C)은 시기상조이다. 성과 평가(D)는 개인을 다루지 일정 계획을 다루지 않는다.
140 | A team has been consistently delivering outcomes. However, based on their current performance, it was discovered that their velocity has decreased by 30%. What should the project manager do to ensure the velocity is under control? | Ask the product owner to look at a minimum of four to eight iterations and replan the velocity for the next iteration based on the team ' s current performance. | Ask the scrum master to plug gaps in the team ' s performance by adding a team member to compensate for the velocity decrease. | Request the team to improve the lead time, cycle time, and response time individually and track closure. | Request that the team improve their cycle time to compensate for the velocity decrease. |  | A | When team velocity has decreased by 30%, the project manager should ask the product owner to review a minimum of four to eight iterations and replan the velocity for the next iteration based on the team's current performance. Using a longer sample of iterations provides a more reliable indicator of sustainable velocity, allowing for realistic scope and schedule adjustments. Adding a team member to compensate (B) introduces new dynamics that may not immediately improve velocity. Requesting individual improvements in lead time, cycle time, and response time (C) is fragmented and does not address team-level velocity planning. Requesting improved cycle time (D) focuses on one metric without the broader context. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 팀이 지속적으로 성과를 내왔다. 그러나 현재 성과를 기반으로 벨로시티가 30% 감소한 것이 발견되었다. 프로젝트 매니저는 벨로시티가 통제 하에 있도록 어떻게 해야 하는가? | 제품 소유자에게 최소 4~8개 이터레이션을 검토하고 팀의 현재 성과를 기반으로 다음 이터레이션의 벨로시티를 재계획하도록 요청한다. | 스크럼 마스터에게 벨로시티 감소를 보상하기 위해 팀원을 추가하여 성과 격차를 메우도록 요청한다. | 팀에게 리드 타임, 사이클 타임, 응답 시간을 개별적으로 개선하고 종료를 추적하도록 요청한다. | 팀에게 벨로시티 감소를 보상하기 위해 사이클 타임을 개선하도록 요청한다. |  | A | 팀 벨로시티가 30% 감소했을 때, 프로젝트 매니저는 제품 소유자에게 최소 4~8개 이터레이션을 검토하고 팀의 현재 성과를 기반으로 다음 이터레이션의 벨로시티를 재계획하도록 요청해야 한다. 더 긴 이터레이션 샘플을 사용하면 지속 가능한 벨로시티의 더 신뢰할 수 있는 지표를 제공하여 현실적인 범위와 일정 조정을 가능하게 한다. 팀원 추가(B)는 벨로시티를 즉각 개선하지 못할 수 있는 새로운 동타을 도입한다. 리드 타임, 사이클 타임, 응답 시간의 개별 개선 요청(C)은 단편적이며 팀 수준 벨로시티 계획을 다루지 않는다. 사이클 타임 개선 요청(D)은 더 넓은 맥락 없이 하나의 지표에 집중한다.
141 | A project manager for an iterative project noticed that retrospective items indicate that the team is not fully conversant with the principles of iterative development. The team meets to analyze the gaps in the training that recently concluded with a third-party trainer. What should the project manager do next? | Mentor and coach the team to meet the project needs. | Let the project team self-organize and develop their skills. | Review the training contract to determine the next steps, | Initiate hybrid development as an interim approach. |  | A | When retrospective items indicate the team is not fully conversant with iterative development principles despite recent training, the project manager should mentor and coach the team to meet project needs. Hands-on guidance from the PM addresses gaps that formal training missed and develops practical competence. Letting the team self-organize (B) assumes skills they have not yet demonstrated. Reviewing the training contract (C) addresses the vendor relationship but not the team's current knowledge gap. Initiating hybrid development as an interim approach (D) changes methodology rather than building capability. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 반복형 프로젝트의 프로젝트 매니저가 회고 항목에서 팀이 반복형 개발 원칙에 충분히 익숙하지 않다는 것을 알아차렸다. 팀은 제3자 트레이너와 최근 완료한 교육의 격차를 분석하기 위해 모였다. 프로젝트 매니저가 다음으로 해야 할 일은? | 프로젝트 요구에 맞게 팀을 멘토링하고 코칭한다. | 프로젝트 팀이 자기 조직화하여 스킬을 개발하도록 한다. | 다음 단계를 결정하기 위해 교육 계약을 검토한다. | 임시 접근법으로 하이브리드 개발을 시작한다. |  | A | 회고 항목에서 최근 교육에도 불구하고 팀이 반복형 개발 원칙에 충분히 익숙하지 않음을 나타낼 때, 프로젝트 매니저는 프로젝트 요구에 맞게 팀을 멘토링하고 코칭해야 한다. PM의 실질적인 지도는 공식 교육이 놓친 격차를 해소하고 실무 역량을 개발한다. 자기 조직화(B)는 아직 입증되지 않은 스킬을 가정한다. 교육 계약 검토(C)는 벤더 관계를 다루지 팀의 현재 지식 격차를 다루지 않는다. 임시 하이브리드 개발 시작(D)은 역량 구축이 아닌 방법론 변경이다.
142 | While working with the project team on planning project resources, the project manager discovers that a critical resource will be assigned at the same time to another project in the organization. The project team explains to the project manager that this resource cannot be replaced by another resource. What should the project manager do first? | Ask the project team to reschedule the project tasks that will demand the use of this critical resource. | Meet with the project lead of the other project to evaluate how to best allocate the critical resource in both projects. | Discuss the resource management plan with the project team for effective utilization of critical resources. | Contact the human resources (HR) department to find new resources to replace this critical resource. |  | B | When a critical, irreplaceable resource is assigned simultaneously to another project, the project manager should first meet with the other project's lead to evaluate how to best allocate the resource across both projects. Collaborative coordination optimizes shared resources. Asking the team to reschedule (A) acts unilaterally. Discussing the resource plan with the team (C) is planning-level. Contacting HR for replacements (D) contradicts the irreplaceable constraint. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 팀과 프로젝트 자원 계획을 수립하던 중, 프로젝트 매니저가 핵심 자원이 조직 내 다른 프로젝트에 동시에 배정될 것임을 발견했다. 프로젝트 팀은 이 자원이 다른 자원으로 대체될 수 없다고 설명한다. 프로젝트 매니저가 먼저 해야 할 일은? | 프로젝트 팀에게 이 핵심 자원이 필요한 프로젝트 작업을 재일정하도록 요청한다. | 다른 프로젝트의 프로젝트 리드와 만나 두 프로젝트에서 핵심 자원을 최적으로 배치하는 방법을 평가한다. | 프로젝트 팀과 핵심 자원의 효과적 활용을 위해 자원 관리 계획을 논의한다. | 인사(HR) 부서에 연락하여 이 핵심 자원을 대체할 새로운 자원을 찾는다. |  | B | 핵심적이고 대체 불가능한 자원이 다른 프로젝트에 동시 배정될 때, 프로젝트 매니저는 먼저 다른 프로젝트의 리드와 만나 두 프로젝트에서 자원을 최적으로 배치하는 방법을 평가해야 한다. 협력적 조율은 공유 자원을 최적화한다. 팀에게 재일정 요청(A)은 일방적으로 행동한다. 팀과 자원 계획 논의(C)는 계획 수준이다. HR에 대체 자원 연락(D)은 대체 불가 제약에 모순된다.
143 | A project manager is assigned to a large complex project with cross-functional dependencies. The project enters a new phase requiring new stakeholders to be added with conflicting priorities. How should the project manager ensure successful engagement with the stakeholders? | Invite all stakeholders to status meetings. | Interact individually with the stakeholders. | Identify and categorize the stakeholders. | Recognize the diversity of the stakeholders. |  | C | When new stakeholders with conflicting priorities join a complex cross-functional project, the project manager should identify and categorize the stakeholders. Structured analysis of influence, interest, and impact enables targeted engagement strategies. Inviting all to status meetings (A) is inefficient. Individual interaction (B) is ad hoc without analysis. Recognizing diversity (D) is important but not an actionable first step. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 매니저가 교차 기능 의존성이 있는 대규모 복잡한 프로젝트에 배정되었다. 프로젝트가 새로운 단계에 진입하면서 상충하는 우선순위를 가진 새로운 이해관계자를 추가해야 한다. 프로젝트 매니저는 이해관계자와의 성공적인 참여를 어떻게 보장해야 하는가? | 모든 이해관계자를 상태 회의에 초대한다. | 이해관계자와 개별적으로 상호작용한다. | 이해관계자를 식별하고 분류한다. | 이해관계자의 다양성을 인정한다. |  | C | 상충하는 우선순위를 가진 새로운 이해관계자가 복잡한 교차 기능 프로젝트에 합류할 때, 프로젝트 매니저는 이해관계자를 식별하고 분류해야 한다. 영향력, 관심, 영향에 대한 구조화된 분석은 목표 지향적인 참여 전략을 가능하게 한다. 모두 상태 회의 초대(A)는 비효율적이다. 개별 상호작용(B)은 분석 없이 임의적이다. 다양성 인정(D)은 중요하지만 실행 가능한 첫 단계가 아니다.
144 | A company's CEO complains about the frequency of project communications. The CEO receives five project reports each week by email but does not have enough time to review them. In addition, the information that the CEO receives is not relevant in that it does not explain the project status. What should the project manager do first? | Meet with the team and decide the type and frequency of the reports to send to the CEO. | Review the communications management plan. | Send the CEO one executive summary per week instead of five reports per week. | Review the stakeholder engagement plan. |  | B | When the CEO complains about too-frequent and irrelevant project reports, the project manager should first review the communications management plan. The plan defines communication requirements and strategies. Meeting with the team to decide report types (A) acts without reviewing what was planned. Sending one summary per week (C) assumes the solution. Reviewing the stakeholder engagement plan (D) focuses on engagement, not communication content. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 회사 CEO가 프로젝트 커뮤니케이션의 빈도에 대해 불만을 제기한다. CEO는 매주 이메일로 5건의 프로젝트 보고서를 받지만 검토할 시간이 충분하지 않다. 또한 CEO가 받는 정보가 프로젝트 상태를 설명하지 못해 관련성이 없다. 프로젝트 매니저가 먼저 해야 할 일은? | 팀과 만나 CEO에게 보낼 보고서의 유형과 빈도를 결정한다. | 커뮤니케이션 관리 계획서를 검토한다. | 매주 5건의 보고서 대신 하나의 경영진 요약을 CEO에게 보낸다. | 이해관계자 참여 계획서를 검토한다. |  | B | CEO가 너무 빈번하고 관련성 없는 프로젝트 보고서에 불만을 제기할 때, 프로젝트 매니저는 먼저 커뮤니케이션 관리 계획서를 검토해야 한다. 이 계획서는 커뮤니케이션 요구사항과 전략을 정의한다. 팀과 만나 보고서 유형 결정(A)은 계획 검토 없이 행동하는 것이다. 주간 요약 하나 보내기(C)는 해결책을 가정한다. 이해관계자 참여 계획서 검토(D)는 커뮤니케이션 내용이 아닌 참여에 초점을 맞춘다.
145 | A team member has indicated their user story will not be finished until the end of the iteration as their functional manager has requested they assist in resolving a high-priority production issue. What should the project manager do? | Tell the project team member not to work on the production issue and to inform their manager. | Meet with the team member ' s functional manager to try to remove the impediment. | Discuss with the product owner that the user story will not be completed this iteration. | Escalate the issue to the project sponsor to resolve and adjust the project burndown chart. |  | B | When a team member's user story will be delayed because their functional manager pulled them to a production issue, the project manager should meet with the functional manager to try to remove the impediment. Direct negotiation addresses the resource conflict. Telling the member not to work on the issue (A) is impractical. Discussing with the PO about incomplete stories (C) accepts the delay. Escalating to the sponsor (D) is premature. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 한 팀원이 기능 관리자가 높은 우선순위의 운영 이슈 해결을 지원하라고 요청하여 이터레이션 종료까지 사용자 스토리를 완료할 수 없다고 알렸다. 프로젝트 매니저는 어떻게 해야 하는가? | 프로젝트 팀원에게 운영 이슈 작업을 하지 말고 관리자에게 알리라고 말한다. | 팀원의 기능 관리자와 만나 장애물을 제거하려고 한다. | 제품 소유자와 이번 이터레이션에서 사용자 스토리가 완료되지 않을 것임을 논의한다. | 이슈를 프로젝트 스폰서에게 에스컬레이션하고 프로젝트 번다운 차트를 조정한다. |  | B | 팀원의 사용자 스토리가 기능 관리자가 운영 이슈에 투입시켜 지연될 때, 프로젝트 매니저는 기능 관리자와 만나 장애물을 제거하려고 해야 한다. 직접 협상은 자원 충돌을 해결한다. 이슈 작업을 하지 말라고 하기(A)는 비현실적이다. PO와 미완료 스토리 논의(C)는 지연을 수용한다. 스폰서에게 에스컬레이션(D)은 시기상조이다.
146 | A company has always acquired very specialized services from local companies for its projects. During the planning stage for a regulatory project, the project manager learns that local vendors would not be able to operate due to an unexpected major event. There is an option to hire the same services from companies in other countries. What should the project manager do in this situation? | Plan to execute the procurement tasks in a virtual environment. | Review organizational process assets (OPAs) for similar projects. | Ask the project sponsor to put the project on hold. | Create a change request to extend the duration of the project. |  | A | When local vendors become unavailable and international alternatives exist, the PM should plan procurement tasks for a virtual environment. This involves determining the procurement strategy, contract types, source selection criteria, and management plan. Virtual procurement offers access to a broader vendor pool, reduced travel costs, and increased flexibility. However, it also introduces challenges including cultural differences, legal considerations, security risks, communication barriers, and quality control complexity. Careful planning that accounts for project objectives, stakeholder expectations, risk factors, and virtual team management best practices is essential for success. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 한 회사가 항상 프로젝트를 위해 지역 업체로부터 매우 전문적인 서비스를 조달해 왔다. 규제 프로젝트의 계획 단계에서 프로젝트 매니저는 예상치 못한 중대한 사건으로 인해 지역 벤더가 운영할 수 없게 되었음을 알게 된다. 다른 국가의 업체에서 동일한 서비스를 고용할 수 있는 옵션이 있다. 이 상황에서 프로젝트 매니저는 어떻게 해야 하는가? | 가상 환경에서 조달 업무를 수행할 계획을 세운다. | 유사 프로젝트에 대한 조직 프로세스 자산(OPA)을 검토한다. | 프로젝트 스폰서에게 프로젝트를 보류하도록 요청한다. | 프로젝트 기간을 연장하는 변경 요청을 작성한다. |  | A | 지역 벤더가 이용 불가하고 국제적 대안이 있을 때, PM은 가상 환경에서 조달 업무를 수행할 계획을 세워야 한다. 이는 조달 전략, 계약 유형, 공급원 선정 기준, 관리 계획을 결정하는 것을 포함한다. 가상 조달은 더 넓은 벤더 풀 접근, 여행 비용 절감, 유연성 증가를 제공한다. 그러나 문화적 차이, 법적 고려사항, 보안 위험, 커뮤니케이션 장벽, 품질 관리 복잡성과 같은 과제도 있다. 프로젝트 목표, 이해관계자 기대, 위험 요소, 가상 팀 관리 모범 사례를 고려한 신중한 계획이 성공에 필수적이다.
147 | A project manager is assigned to an ongoing complex project. The team is delivering value each iteration. However, the deliverables are internal and the customers are unaware of the deliverables. Which action should the project manager take? | Inform the customer about the progress and update them on the final deliverables | Evaluate various delivery options in order to immediately demonstrate value to the customer | Wait for an important milestone to complete and then inform the customer of the progress | Ask the internal sales team to keep the customer informed of the delivered value |  | B | When the team delivers value each iteration but customers are unaware of the deliverables, the project manager should evaluate various delivery options to immediately demonstrate value to the customer. Proactive value demonstration enables feedback and validates alignment. Informing the customer about progress and final deliverables (A) focuses on outcomes, not ongoing value. Waiting for a milestone (C) delays feedback. Asking the sales team to keep the customer informed (D) delegates stakeholder engagement. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 프로젝트 매니저가 진행 중인 복잡한 프로젝트에 배정되었다. 팀은 매 이터레이션마다 가치를 제공하고 있다. 그러나 인도물은 내부적이며 고객은 인도물을 인지하지 못하고 있다. 프로젝트 매니저가 취해야 할 조치는? | 고객에게 진행 상황을 알리고 최종 인도물에 대해 업데이트한다. | 고객에게 즉시 가치를 입증하기 위해 다양한 인도 옵션을 평가한다. | 중요한 마일스톤이 완료될 때까지 기다린 후 고객에게 진행 상황을 알린다. | 내부 영업팀에게 고객에게 전달된 가치를 알리도록 요청한다. |  | B | 팀이 매 이터레이션마다 가치를 제공하지만 고객이 인도물을 인지하지 못할 때, 프로젝트 매니저는 고객에게 즉시 가치를 입증하기 위해 다양한 인도 옵션을 평가해야 한다. 선제적 가치 입증은 피드백을 가능하게 하고 정렬을 검증한다. 진행 상황과 최종 인도물 알리기(A)는 지속적 가치가 아닌 결과에 초점을 맞춘다. 마일스톤 대기(C)는 피드백을 지연시킨다. 영업팀에게 알리기 요청(D)은 이해관계자 참여를 위임한다.
148 | An important project to build a new airport was suddenly stopped because of the complaints from residents in the surrounding communities. The residents stated that they were not consulted and that the project would cause ecological and pollution damage. What should the project manager have done first in order to avoid this situation? | Identified the stakeholders and their expectations | Added this situation to the risk register | Added these requests to the project scope statement | Presented the project to the community |  | A | The correct answer is A. Identified the stakeholders and their expectations. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | General PM Principles | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 새 공항 건설을 위한 중요한 프로젝트가 주변 커뮤니티 주민들의 민원으로 인해 갑자기 중단되었다. 주민들은 자신들과 상의하지 않았으며 프로젝트가 생태계 및 오염 피해를 야기할 것이라고 말했다. 이 상황을 피하기 위해 프로젝트 매니저가 먼저 했어야 할 일은? | 이해관계자와 그들의 기대를 식별했다. | 이 상황을 리스크 등록부에 추가했다. | 이러한 요청을 프로젝트 범위 기술서에 추가했다. | 커뮤니티에 프로젝트를 발표했다. |  | A | 정답은 A이다. 이해관계자와 그들의 기대를 식별했다. 이 접근법은 상황을 효과적으로 다루면서 적절한 프로세스와 이해관계자 정렬을 유지하는 프로젝트 관리 모범 사례를 따른다.
149 | The project team is experiencing schedule delays due to issues arising with suppliers. Some of the tasks are on the critical path. What should the project manager do in this situation? | Escalate the supplier-related issues to the sponsor for resolution. | Review the work breakdown structure (WBS) with the suppliers. | Review the critical path with the stakeholders to define next steps. | Discuss the critical path issues with the purchasing department. |  | C | When supplier issues cause schedule delays on critical path tasks, the project manager should review the critical path with stakeholders to define next steps. Collaborative review with the project team, suppliers, and sponsor enables informed decision-making about mitigation strategies. Escalating to the sponsor alone (A) limits input. Reviewing the WBS with suppliers (B) addresses scope but not schedule impact. Discussing with the purchasing department (D) focuses on procurement rather than schedule resolution. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Risk | Planning | Build an Empowered Culture | Plan Risk Management | Traditional PM | 프로젝트 팀이 공급업체와 관련된 이슈로 인해 일정 지연을 겪고 있다. 일부 작업은 주공정선(critical path)에 있다. 이 상황에서 프로젝트 매니저는 어떻게 해야 하는가? | 공급업체 관련 이슈를 해결을 위해 스폰서에게 에스컬레이션한다. | 공급업체와 함께 작업 분류 체계(WBS)를 검토한다. | 이해관계자와 함께 주공정선을 검토하여 다음 단계를 정의한다. | 주공정선 이슈를 구매부서와 논의한다. |  | C | 공급업체 이슈가 주공정선 작업의 일정 지연을 야기할 때, 프로젝트 매니저는 이해관계자와 함께 주공정선을 검토하여 다음 단계를 정의해야 한다. 프로젝트 팀, 공급업체, 스폰서와의 협력적 검토는 완화 전략에 대한 정보 기반 의사결정을 가능하게 한다. 스폰서에게만 에스컬레이션(A)은 의견을 제한한다. 공급업체와 WBS 검토(B)는 범위를 다루지만 일정 영향은 다루지 않는다. 구매부서와 논의(D)는 일정 해결보다 조달에 초점을 맞춘다.
150 | During the course of a project, the team develops negative group behaviors and becomes unmotivated and unproductive. What should the project manager do to improve the project team's performance? | Conduct a root cause analysis session | Define and analyze performance metrics | Escalate poor performance to functional managers | Update the stakeholder engagement plan |  | A | When the team develops negative behaviors and becomes unmotivated and unproductive, the project manager should conduct a root cause analysis session. RCA identifies underlying causes and enables targeted corrective actions through collaborative problem-solving. Defining performance metrics (B) measures but does not solve the issue. Escalating to functional managers (C) is punitive. Updating the stakeholder engagement plan (D) does not address internal team dynamics. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 프로젝트 진행 중 팀에서 부정적인 그룹 행동이 나타나고 동기가 저하되며 비생산적으로 변했다. 프로젝트 팀의 성과를 개선하기 위해 프로젝트 매니저는 어떻게 해야 하는가? | 근본 원인 분석 세션을 수행한다. | 성과 지표를 정의하고 분석한다. | 저조한 성과를 기능 관리자에게 에스컬레이션한다. | 이해관계자 참여 계획서를 업데이트한다. |  | A | 팀에서 부정적인 행동이 나타나고 동기가 저하되며 비생산적으로 변할 때, 프로젝트 매니저는 근본 원인 분석 세션을 수행해야 한다. RCA는 근본적인 원인을 식별하고 협력적 문제 해결을 통해 목표 지향적인 시정 조치를 가능하게 한다. 성과 지표 정의(B)는 측정하지만 문제를 해결하지 않는다. 기능 관리자에게 에스컬레이션(C)은 징벌적이다. 이해관계자 참여 계획서 업데이트(D)는 내부 팀 역학을 다루지 않는다.
151 | A team has individual daily start times for each team member. Sometimes the overlap between team member working hours is short. During those times, the interactions and work as a team are reduced and ineffective. What should the project manager do? | Ask the team to define a team charter and agree on core working hours. | Allocate the overlap time for each team member and ask them to adhere to the schedule. | Ask the team to start at the same time to obtain the maximum number of team working hours. | Inform the team members who are joining late to join early and work together. |  | A | When team members have varying start times with short overlap periods, the project manager should ask the team to define a team charter and agree on core working hours. A team charter establishes shared norms and a specific window when all members are available, maximizing collaboration. Allocating overlap time per individual (B) is top-down. Asking everyone to start at the same time (C) ignores individual constraints. Informing late joiners to join early (D) is one-sided. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 팀원마다 일일 시작 시간이 다르다. 때때로 팀원 간 근무 시간 겹침이 짧다. 그 시간 동안 상호작용과 팀 작업이 줄어들고 비효과적이다. 프로젝트 매니저는 어떻게 해야 하는가? | 팀에게 팀 헌장을 정의하고 핵심 근무 시간에 합의하도록 요청한다. | 각 팀원에게 겹침 시간을 배분하고 일정을 준수하도록 요청한다. | 팀에게 최대 팀 작업 시간을 확보하기 위해 같은 시간에 시작하도록 요청한다. | 늦게 합류하는 팀원들에게 일찍 합류하여 함께 일하라고 알린다. |  | A | 팀원들의 시작 시간이 다르고 겹침 시간이 짧을 때, 프로젝트 매니저는 팀에게 팀 헌장을 정의하고 핵심 근무 시간에 합의하도록 요청해야 한다. 팀 헌장은 공유 규범과 모든 구성원이 이용 가능한 특정 시간대를 설정하여 협업을 극대화한다. 개인별 겹침 시간 배분(B)은 하향식이다. 모두 같은 시간 시작 요청(C)은 개인적 제약을 무시한다. 늦는 사람에게 일찍 오라고 알리기(D)는 일방적이다.
152 | During the planning stage of a project, the project manager realizes that a standard stakeholder engagement approach will not suffice. One of the client representatives, who is not a key decision maker, is extremely opinionated. This client representative could become a roadblock to progress due to their perceived level of authority during meetings. How should the project manager handle this moving forward? | Update the risk register to consider the possible project impacts | Update the project schedule to cater to this particular stakeholder | Allocate time to gain buy-in from the stakeholder prior to key decision meetings. | Ask that only key decision makers attend the project meetings. |  | C | When an opinionated non-decision-making client representative may become a roadblock due to perceived authority, the project manager should allocate time to gain buy-in from the stakeholder prior to key decision meetings. Proactive engagement builds trust, addresses concerns, and prevents disruption. Updating the risk register (A) documents but does not resolve the issue. Updating the schedule for one stakeholder (B) is disruptive. Restricting meetings to decision-makers only (D) alienates the stakeholder. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 프로젝트 계획 단계에서 프로젝트 매니저는 표준 이해관계자 참여 접근법이 충분하지 않을 것임을 깨닫는다. 핵심 의사결정자가 아닌 고객 대표 중 한 명이 매우 강한 의견을 가지고 있다. 이 고객 대표는 회의 중 인식된 권한 수준으로 인해 진행에 장애물이 될 수 있다. 프로젝트 매니저는 향후 이를 어떻게 처리해야 하는가? | 가능한 프로젝트 영향을 고려하여 리스크 등록부를 업데이트한다. | 이 특정 이해관계자를 수용하기 위해 프로젝트 일정을 업데이트한다. | 주요 의사결정 회의 전에 이해관계자의 동의를 얻기 위해 시간을 할당한다. | 주요 의사결정자만 프로젝트 회의에 참석하도록 요청한다. |  | C | 의견이 강한 비의사결정권자 고객 대표가 인식된 권한으로 인해 장애물이 될 수 있을 때, 프로젝트 매니저는 주요 의사결정 회의 전에 이해관계자의 동의를 얻기 위해 시간을 할당해야 한다. 선제적 참여는 신뢰를 구축하고, 우려를 해소하며, 방해를 방지한다. 리스크 등록부 업데이트(A)는 문서화하지만 문제를 해결하지 않는다. 한 이해관계자를 위한 일정 업데이트(B)는 파괴적이다. 의사결정자만 회의 참석 제한(D)은 이해관계자를 소외시킨다.
153 | During a project meeting, the project manager expressed the importance of delivering reports on time. These individual reports will be consolidated into a single report. One of the team member's reports was not delivered on time and therefore the report could not be integrated with the other reports. This demonstrates a lack of teamwork and impacts project success. What should the project manager do to resolve this issue? | Assign the task to someone else on the team. | Discuss this matter during the project meeting. | Include this item in the risk register. | Discuss it with the team member in confidence. |  | D | The PM should discuss the matter with the team member privately and in confidence. This enables open dialogue and gives the team member an opportunity to explain any obstacles that prevented timely delivery. Private discussion prevents potential embarrassment or defensiveness that could arise in a public setting. This method supports trust development and maintains a positive team environment—both crucial for project success. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Risk | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 회의에서 프로젝트 매니저가 보고서를 제때 전달하는 것의 중요성을 강조했다. 이 개별 보고서들은 하나의 보고서로 통합될 예정이다. 한 팀원의 보고서가 제때 전달되지 않아 다른 보고서와 통합할 수 없었다. 이는 팀워크 부족을 보여주며 프로젝트 성공에 영향을 미친다. 이 이슈를 해결하기 위해 프로젝트 매니저는 어떻게 해야 하는가? | 팀의 다른 사람에게 작업을 배정한다. | 프로젝트 회의에서 이 문제를 논의한다. | 이 항목을 리스크 등록부에 포함한다. | 해당 팀원과 비공개로 논의한다. |  | D | PM은 해당 팀원과 비공개로 개인적으로 논의해야 한다. 이를 통해 열린 대화가 가능하고 팀원이 적시 전달을 방해한 장애물을 설명할 기회를 준다. 비공개 논의는 공개 석상에서 발생할 수 있는 당혹감이나 방어적 태도를 방지한다. 이 방법은 프로젝트 성공에 핵심적인 신뢰 개발과 긍정적인 팀 환경 유지를 지원한다.
154 | During the project planning phase, the customer explained the importance of delivering the project results proposed in the scope as soon as possible. What should the project manager do first to address this issue? | Assess the opportunities to deliver project value incrementally. | Gather all of the requirements details and schedule a refinement meeting. | Approve a change request to change the project approach to agile. | Prepare a project management plan for the full scope using an agile approach. |  | A | When a customer emphasizes the importance of receiving project results as soon as possible, the project manager should first assess whether the scope can be broken into increments that deliver usable value earlier. Incremental delivery enables stakeholders to realize benefits sooner rather than waiting for the entire project to complete, and it supports better adaptation when priorities evolve. Gathering requirements and scheduling a refinement meeting (B) is useful but does not directly address early value delivery. Approving a change request to switch to agile (C) is premature before evaluating whether incremental delivery is practical within the current project framework. Preparing a full agile project management plan (D) assumes agile is the answer without first assessing the delivery options available. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 계획 단계에서 고객이 범위에 제시된 프로젝트 결과를 가능한 한 빨리 제공하는 것이 중요하다고 설명했다. 이 이슈를 해결하기 위해 프로젝트 매니저가 먼저 해야 할 일은? | 점진적으로 프로젝트 가치를 제공할 기회를 평가한다. | 모든 요구사항 세부 사항을 수집하고 정제 회의를 예약한다. | 프로젝트 접근법을 애자일로 변경하는 변경 요청을 승인한다. | 애자일 접근법을 사용하여 전체 범위에 대한 프로젝트 관리 계획서를 준비한다. |  | A | 고객이 프로젝트 결과를 가능한 한 빨리 받는 것을 강조할 때, 프로젝트 매니저는 먼저 범위를 더 이른 사용 가능한 가치를 제공하는 증분으로 나눈 수 있는지 평가해야 한다. 점진적 인도는 이해관계자가 전체 프로젝트 완료를 기다리지 않고 더 빨리 혜택을 실현할 수 있게 하며, 우선순위가 변할 때 더 나은 적응을 지원한다. 요구사항 수집과 정제 회의 예약(B)은 유용하지만 조기 가치 제공을 직접 다루지 않는다. 애자일로 전환하는 변경 요청 승인(C)은 점진적 인도가 현재 프로젝트 프레임워크에서 실현 가능한지 평가하기 전에 시기상조이다. 전체 애자일 프로젝트 관리 계획서 준비(D)는 먼저 인도 옵션을 평가하지 않고 애자일이 답이라고 가정한다.
155 | A defect is identified during user acceptance testing that could significantly impact the system's performance. The project team has advised that this defect puts the delivery date at risk. Which risk management process should be performed? | Perform Quantitative Risk Analysis, to outline the details of the system performance issues | Monitor Risks, to install system performance monitoring tools and update the risk register | Plan Risk Responses, to outline the possible options to bypass the system performance issue | Perform Qualitative Risk Analysis, to assess the extent of the system performance impact |  | B | When a significant defect identified during user acceptance testing threatens the delivery date, the appropriate risk management process is Plan Risk Responses. This process develops options, selects strategies, and agrees on actions to address both individual project risks and overall risk exposure. The goal is determining how to approach, plan, and execute risk management activities for the situation. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 사용자 인수 테스트 중 시스템 성능에 중대한 영향을 미칠 수 있는 결함이 발견되었다. 프로젝트 팀은 이 결함이 납기를 위험에 빠트린다고 조언했다. 어떤 리스크 관리 프로세스를 수행해야 하는가? | 시스템 성능 이슈의 세부 사항을 설명하기 위해 정량적 리스크 분석을 수행한다. | 시스템 성능 모니터링 도구를 설치하고 리스크 등록부를 업데이트하기 위해 리스크 감시를 수행한다. | 시스템 성능 이슈를 우회할 수 있는 옵션을 설명하기 위해 리스크 대응 계획을 수립한다. | 시스템 성능 영향의 정도를 평가하기 위해 정성적 리스크 분석을 수행한다. |  | B | 사용자 인수 테스트 중 발견된 중대한 결함이 납기를 위협할 때, 적절한 리스크 관리 프로세스는 리스크 대응 계획 수립이다. 이 프로세스는 옵션을 개발하고, 전략을 선택하며, 개별 프로젝트 리스크와 전체 리스크 노출을 다루기 위한 조치에 합의한다. 목표는 상황에 대한 리스크 관리 활동에 접근하고, 계획하고, 실행하는 방법을 결정하는 것이다.
156 | A team is given an agile project to build a conceptual product for a new customer. While planning, the project manager is trying to determine the best way to show value to the customer, as the technical requirements are not very detailed. What should the project manager do to help the client understand the value delivered during project execution? | Conduct a customer demonstration at the end of each build cycle. | Include a planned value (PV) calculation in the sprint report for each build cycle. | Show the customer a sprint burndown chart for each build cycle. | Provide the customer with the refined specification during each build cycle. |  | A | When building a conceptual product with vague technical requirements in an agile project, the project manager should conduct a customer demonstration at the end of each build cycle. Live demonstrations show tangible value and solicit actionable feedback. Including a planned value calculation (B) provides financial metrics, not product understanding. Showing a burndown chart (C) indicates progress, not product value. Providing refined specifications (D) communicates requirements, not delivered value. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 애자일 프로젝트에서 팀이 새로운 고객을 위한 컨셉 제품을 만들어야 한다. 계획 중 프로젝트 매니저는 기술적 요구사항이 매우 상세하지 않아 고객에게 가치를 보여주는 최선의 방법을 결정하려고 한다. 프로젝트 실행 중 제공된 가치를 고객이 이해하도록 돕기 위해 프로젝트 매니저는 어떻게 해야 하는가? | 각 빌드 사이클 끝에 고객 데모를 수행한다. | 각 빌드 사이클의 스프린트 보고서에 계획 가치(PV) 계산을 포함한다. | 각 빌드 사이클의 스프린트 번다운 차트를 고객에게 보여준다. | 각 빌드 사이클에서 고객에게 정제된 사양을 제공한다. |  | A | 모호한 기술적 요구사항으로 애자일 프로젝트에서 컨셉 제품을 만들 때, 프로젝트 매니저는 각 빌드 사이클 끝에 고객 데모를 수행해야 한다. 라이브 데모는 실질적인 가치를 보여주고 실행 가능한 피드백을 이끌어낸다. 계획 가치 계산 포함(B)은 재무 지표를 제공하지만 제품 이해는 안 된다. 번다운 차트 보여주기(C)는 진행 상황을 나타내지만 제품 가치는 아니다. 정제된 사양 제공(D)은 요구사항을 전달하지만 제공된 가치는 아니다.
157 | A company wants to increase the commercial value of one of its products in a highly competitive market. In order to do this, the company commissions a project to create a prototype. The team constructs the prototype incrementally. Which action should the project manager take as a priority? | Implement a plan-do-check-act (PDCA) cycle | Deliver business value as soon as possible | Emphasize the use of Kanban methodology. | Ensure the project sponsor is aware of the go-to market date |  | B | When a company commissions a project to create an incrementally-built prototype to increase commercial value in a competitive market, the project manager should prioritize delivering business value as soon as possible. Early value delivery enables feedback, validation, and market responsiveness. Implementing PDCA (A) is a process improvement framework, not a delivery priority. Emphasizing Kanban (C) is a tool choice, not a priority action. Ensuring sponsor awareness of go-to-market date (D) is communication, not delivery. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Kanban | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 회사가 높은 경쟁이 있는 시장에서 제품 중 하나의 상업적 가치를 높이고자 한다. 이를 위해 회사는 프로토타입을 만드는 프로젝트를 의뢰했다. 팀은 프로토타입을 점진적으로 구축한다. 프로젝트 매니저가 우선적으로 취해야 할 조치는? | PDCA(계획-실행-검증-조치) 사이클을 구현한다. | 가능한 한 빨리 비즈니스 가치를 제공한다. | 칸반 방법론 사용을 강조한다. | 프로젝트 스폰서가 시장 출시 날짜를 알고 있도록 한다. |  | B | 경쟁이 치열한 시장에서 상업적 가치를 높이기 위해 점진적으로 구축되는 프로토타입 프로젝트를 의뢰할 때, 프로젝트 매니저는 가능한 한 빨리 비즈니스 가치를 제공하는 것을 우선시해야 한다. 조기 가치 제공은 피드백, 검증, 시장 대응력을 가능하게 한다. PDCA 구현(A)은 프로세스 개선 프레임워크이지 인도 우선순위가 아니다. 칸반 강조(C)는 도구 선택이지 우선순위 조치가 아니다. 스폰서의 시장 출시일 인지(D)는 커뮤니케이션이지 인도가 아니다.
158 | A project manager who takes over halfway through a project determines that the cost performance index (CPI) is 0.65. A detailed audit identifies that the project cost was analogously estimated, and the audit team thinks that something was missing in the way the estimates were done. What should have been done to avoid this problem? | Used bottom-up estimating | Utilized three-point estimates | Validated the schedule performance index (SPI) to evaluate deviation | Included lessons learned from past projects |  | A | When a CPI of 0.65 results from analogous estimation with something missing, the project should have used bottom-up estimating. This method estimates individual work packages in detail and aggregates them for total project cost, providing greater accuracy than analogous estimating. Three-point estimates (B) improve accuracy for individual activities but do not address comprehensive decomposition. Validating SPI (C) evaluates schedule, not cost estimation. Including lessons learned (D) is helpful but does not fix the estimation methodology. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 프로젝트 중간에 인수한 프로젝트 매니저가 원가 성과 지수(CPI)가 0.65임을 확인했다. 상세 감사를 통해 프로젝트 원가가 유사 추정법으로 산정되었으며, 감사팀은 추정 방식에 무언가 빠져 있다고 판단했다. 이 문제를 피하기 위해 무엇을 했어야 하는가? | 상향식 추정법을 사용했다. | 3점 추정법을 활용했다. | 편차를 평가하기 위해 일정 성과 지수(SPI)를 검증했다. | 과거 프로젝트의 교훈을 포함했다. |  | A | CPI 0.65가 유사 추정의 결함에서 비롯될 때, 프로젝트는 상향식 추정법을 사용했어야 한다. 이 방법은 개별 작업 패키지를 상세히 추정하고 이를 합산하여 총 프로젝트 비용을 산출하며, 유사 추정보다 더 높은 정확도를 제공한다. 3점 추정(B)은 개별 활동의 정확도를 높이지만 포괄적 분해를 다루지 않는다. SPI 검증(C)은 일정을 평가하지 비용 추정은 평가하지 않는다. 교훈 포함(D)은 도움이 되지만 추정 방법론 자체를 수정하지는 않는다.
159 | A software development project is about to begin. The product owner and project manager cannot agree on which programming language to use from the two available options. The company lacks experienced developers in the product owner's preferred language; however, they are highly skilled in the other language. What should the project manager do? | Coordinate programming language training for the developers. | Plan according to the requirement from the product owner. | Hire a vendor with the necessary skills to quickly fill the gap in resources. | Persuade the product owner to use the language preferred by the developers. |  | D | The PM should work to persuade the product owner to adopt the programming language preferred by the development team. Resource management involves ensuring team members have the skills, tools, and support necessary to perform effectively. When a capability gap exists, the PM should proactively identify it and take appropriate steps—such as training, mentoring, or adjusting the approach—to address the shortfall. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Adopt a Holistic View | Monitor and Control Project Performance | Traditional PM | 소프트웨어 개발 프로젝트가 시작되려고 한다. 제품 소유자와 프로젝트 매니저가 두 가지 사용 가능한 옵션 중 어떤 프로그래밍 언어를 사용할지 합의하지 못하고 있다. 회사에는 제품 소유자가 선호하는 언어의 경험 있는 개발자가 부족하지만, 다른 언어에는 매우 능숙하다. 프로젝트 매니저는 어떻게 해야 하는가? | 개발자들을 위한 프로그래밍 언어 교육을 조율한다. | 제품 소유자의 요구사항에 따라 계획한다. | 자원 격차를 빠르게 메우기 위해 필요한 스킬을 가진 벤더를 고용한다. | 제품 소유자에게 개발자들이 선호하는 언어를 사용하도록 설득한다. |  | D | PM은 제품 소유자에게 개발 팀이 선호하는 프로그래밍 언어를 채택하도록 설득해야 한다. 자원 관리는 팀원들이 효과적으로 수행하는 데 필요한 스킬, 도구, 지원을 갖추도록 보장하는 것을 포함한다. 역량 격차가 존재할 때, PM은 이를 사전에 식별하고 부족함을 해소하기 위해 교육, 멘토링, 또는 접근법 조정 등 적절한 조치를 취해야 한다.
160 | A project manager is leading the development and delivery of a strategic product that must be delivered on time. The project is facing technical issues that could significantly impact the budget and ability to deliver some of the product features. What should the project manager do first to resolve the issue? | Assess the impact of the feature on the project and ask for a contingency. | Develop a quality management plan to clearly identify how features should be classified. | Record the situation in the risk register and communicate it to stakeholders. | Schedule a meeting with the team and management to discuss options. |  | A | The correct answer is A. Assess the impact of the feature on the project and ask for a contingency. Cost management requires careful planning, monitoring, and control. The PM should track budget variations and work with stakeholders to address financial challenges appropriately. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 매니저가 제때 인도되어야 하는 전략적 제품의 개발과 납품을 이끌고 있다. 프로젝트가 예산과 일부 제품 기능 인도 능력에 중대한 영향을 미칠 수 있는 기술적 이슈에 직면해 있다. 이슈를 해결하기 위해 프로젝트 매니저가 먼저 해야 할 일은? | 프로젝트에 대한 기능의 영향을 평가하고 예비비를 요청한다. | 기능을 어떻게 분류해야 하는지 명확히 식별하는 품질 관리 계획서를 개발한다. | 상황을 리스크 등록부에 기록하고 이해관계자에게 전달한다. | 팀과 경영진과 회의를 잡아 옵션을 논의한다. |  | A | 정답은 A이다. 프로젝트에 대한 기능의 영향을 평가하고 예비비를 요청한다. 비용 관리는 신중한 계획, 모니터링, 통제가 필요하다. PM은 예산 변동을 추적하고 이해관계자와 협력하여 재정적 과제를 적절히 해결해야 한다.
161 | A project manager was assigned to lead a global project with a virtual team that is globally dispersed. The project manager has difficulties communicating with the team members and there seems to be frequent misunderstandings and conflicts. What should the project manager do? | Ask the team members to refamiliarize themselves with the communications management plan. | Model servant leadership by adapting to team requirements. | Organize effective communication training for team members. | Listen to team members actively and change the communication practices accordingly. |  | D | When a global virtual team has frequent misunderstandings and conflicts, the project manager should listen to team members actively and change communication practices accordingly. Adaptive servant leadership addresses root causes. Asking members to review the communications plan (A) assumes the plan is adequate. Organizing communication training (C) may help but does not address current issues. Modeling servant leadership (B) is the broader concept; active listening is the specific action. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 매니저가 글로벌에 분산된 가상 팀으로 글로벌 프로젝트를 이끌도록 배정되었다. 프로젝트 매니저가 팀원들과의 커뮤니케이션에 어려움을 겪고 있으며 빈번한 오해와 갈등이 있는 것으로 보인다. 프로젝트 매니저는 어떻게 해야 하는가? | 팀원들에게 커뮤니케이션 관리 계획서를 다시 숙지하도록 요청한다. | 팀 요구사항에 적응하여 서번트 리더십을 모델링한다. | 팀원들을 위한 효과적인 커뮤니케이션 교육을 조직한다. | 팀원들의 의견을 적극적으로 경청하고 커뮤니케이션 관행을 그에 맞게 변경한다. |  | D | 글로벌 가상 팀에서 빈번한 오해와 갈등이 있을 때, 프로젝트 매니저는 팀원들의 의견을 적극적으로 경청하고 커뮤니케이션 관행을 그에 맞게 변경해야 한다. 적응적 서번트 리더십은 근본 원인을 해결한다. 커뮤니케이션 계획서 검토 요청(A)은 계획이 적절하다고 가정한다. 커뮤니케이션 교육 조직(C)은 도움이 될 수 있지만 현재 이슈를 해결하지 않는다. 서번트 리더십 모델링(B)은 더 넓은 개념이고, 적극적 경청이 구체적인 조치이다.
162 | A project manager wants to make sure that similar projects in the future use the project's performance data as a reference. However, the project manager is not sure how to accomplish this. What should the project manager do? | Keep project artifacts up-to-date and accessible to all stakeholders. | Share project documentation in a repository with exclusive access. | Schedule weekly knowledge-sharing sessions with key stakeholders. | Send periodic emails to senior management with the latest project updates. |  | A | The PM should keep project artifacts—including performance data—up-to-date and accessible to all stakeholders. This ensures knowledge and experience from the current project can serve as reference material for similar future projects, improving organizational efficiency and effectiveness over time. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 매니저가 향후 유사한 프로젝트에서 이 프로젝트의 성과 데이터를 참고자료로 사용하고 싶다. 그러나 프로젝트 매니저는 이를 어떻게 실현할지 확신하지 못한다. 프로젝트 매니저는 어떻게 해야 하는가? | 프로젝트 산출물을 최신 상태로 유지하고 모든 이해관계자가 접근할 수 있게 한다. | 프로젝트 문서를 독점 접근 권한이 있는 저장소에 공유한다. | 핵심 이해관계자와 주간 지식 공유 세션을 예약한다. | 고위 경영진에게 최신 프로젝트 업데이트를 정기적으로 이메일로 보낸다. |  | A | PM은 성과 데이터를 포함한 프로젝트 산출물을 최신 상태로 유지하고 모든 이해관계자가 접근할 수 있게 해야 한다. 이는 현재 프로젝트의 지식과 경험이 향후 유사 프로젝트의 참고 자료로 활용될 수 있도록 보장하여 조직의 효율성과 효과성을 시간이 지남에 따라 개선한다.
163 | A customer initiated a minor scope change and expects this to be completed without delays or additional costs. The project manager believes that they have adequate authorization to make the decision themselves but is not quite sure. What should the project manager do next? | Use the Perform Integrated Change Control process and submit this to the change control board (CCB) for approval. | Keep the change pending and decide to take this up as part of final settlement at the end of the project. | Exploit this change opportunity and calculate the cost, risk, and time, then add a reasonable margin and submit to the customer. | Use the project contingency and implement the change without charging the customer, since the customer ' s satisfaction is top priority. |  | A | Even when the project manager believes they have adequate authorization, the correct course of action for a scope change is to use the Perform Integrated Change Control process and submit the change to the change control board (CCB) for approval. This process ensures that all change requests are properly evaluated for impact on scope, schedule, cost, and quality before being approved or rejected. Keeping the change pending until project end (B) delays necessary action and creates risk. Exploiting the change as a revenue opportunity (C) shifts the focus from proper change management to commercial motives. Using project contingency without CCB authorization (D) bypasses established governance, regardless of customer satisfaction considerations. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 고객이 사소한 범위 변경을 시작했으며 이것이 지연이나 추가 비용 없이 완료되기를 기대한다. 프로젝트 매니저는 스스로 결정할 충분한 권한이 있다고 믿지만 완전히 확신하지는 못한다. 프로젝트 매니저가 다음으로 해야 할 일은? | 통합 변경 통제 수행 프로세스를 사용하여 변경통제위원회(CCB)에 승인을 위해 제출한다. | 변경을 보류하고 프로젝트 마무리 시 최종 정산의 일부로 처리하기로 결정한다. | 이 변경 기회를 활용하여 비용, 리스크, 시간을 계산한 후 합리적인 마진을 추가하여 고객에게 제출한다. | 프로젝트 예비비를 사용하여 고객에게 비용을 청구하지 않고 변경을 구현한다. 고객 만족이 최우선이기 때문이다. |  | A | 프로젝트 매니저가 충분한 권한이 있다고 믿더라도, 범위 변경에 대한 올바른 조치는 통합 변경 통제 수행 프로세스를 사용하여 CCB에 승인을 위해 제출하는 것이다. 이 프로세스는 승인 또는 거부 전에 모든 변경 요청이 범위, 일정, 비용, 품질에 대한 영향을 적절히 평가받도록 보장한다. 프로젝트 마무리까지 변경 보류(B)는 필요한 조치를 지연시키고 위험을 만든다. 변경을 수익 기회로 활용(C)은 적절한 변경 관리에서 상업적 동기로 초점을 이동시킨다. CCB 승인 없이 프로젝트 예비비 사용(D)은 고객 만족 고려와 관계없이 설정된 거버넌스를 우회한다.
164 | A project manager is managing a very important business transformation project. The goal of the project is to extend a desktop application with a mobile application module. The marketing department believes that a main competitor is working on a similar product. Which delivery approach should the project manager use for this project? | Traditional delivery, to ensure high quality and that the product meets market demands | Iterative delivery, to ensure that user feedback is incorporated into the second iteration | Extreme Programming (XP) delivery, to mitigate the high risk related to a new product | Incremental delivery, to ensure that mobile capability is released fast to the users |  | D | When a competitor is working on a similar product, the project manager should use incremental delivery to ensure that mobile capability is released fast to users. Incremental delivery allows rapid release of functional portions, gaining competitive advantage through early market presence and user feedback. Traditional delivery (A) delays market entry. Iterative delivery (B) focuses on refinement through feedback cycles but may not release to users as quickly. Extreme Programming (C) addresses technical risk but is not primarily about speed to market. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Hybrid/Tailoring | 프로젝트 관리자가 매우 중요한 비즈니스 혁신 프로젝트를 관리하고 있다. 프로젝트의 목표는 데스크톱 애플리케이션에 모바일 애플리케이션 모듈을 추가하는 것이다. 마케팅 부서는 주요 경쟁사가 유사한 제품을 개발 중이라고 판단한다. 프로젝트 관리자는 이 프로젝트에 어떤 인도 방식을 사용해야 하는가? | 전통적 인도 방식으로, 높은 품질과 제품이 시장 수요를 충족하도록 보장한다 | 반복적 인도 방식으로, 사용자 피드백이 두 번째 이터레이션에 반영되도록 보장한다 | 익스트림 프로그래밍(XP) 인도 방식으로, 신규 제품과 관련된 높은 리스크를 완화한다 | 점진적 인도 방식으로, 모바일 기능이 사용자에게 빠르게 출시되도록 보장한다 |  | D | 경쟁사가 유사한 제품을 개발 중일 때, 프로젝트 관리자는 점진적 인도 방식을 사용하여 모바일 기능을 사용자에게 빠르게 출시해야 한다. 점진적 인도는 기능적 부분을 신속하게 출시하여 조기 시장 진입과 사용자 피드백을 통해 경쟁 우위를 확보할 수 있다. 전통적 인도(A)는 시장 진입을 지연시킨다. 반복적 인도(B)는 피드백 주기를 통한 개선에 초점을 맞추지만 사용자에게 빠르게 출시하지 못할 수 있다. XP(C)는 기술적 리스크를 다루지만 시장 속도가 주요 목적이 아니다.
165 | A project manager is assigned to deliver an innovative solution that is part of a brand new offering. The project manager reviews the request for proposal (RFP) and realizes that key terms are restricted to technical resource assignments. There is also a gap in addressing compliance. How should the project manager bridge the gap and ensure the project delivers the expected business value? | Determine the critical requirements. | Create a project scope statement. | Document the risks and mitigations. | Define the project schedule. |  | A | When an RFP for an innovative solution has restricted technical terms and a compliance gap, the project manager should determine the critical requirements. Identifying essential requirements bridges the gap between the RFP and expected business value. Creating a scope statement (B) formalizes scope before understanding critical needs. Documenting risks (C) follows requirement identification. Defining the schedule (D) is premature without clear requirements. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 프로젝트 관리자가 완전히 새로운 서비스의 일부인 혁신적 솔루션을 제공하도록 배정되었다. 프로젝트 관리자가 제안요청서(RFP)를 검토한 결과, 핵심 조건이 기술 자원 배정으로 제한되어 있다. 또한 컴플라이언스 대응에도 격차가 있다. 프로젝트 관리자는 어떻게 격차를 해소하고 프로젝트가 기대하는 비즈니스 가치를 제공하도록 보장해야 하는가? | 핵심 요구사항을 결정한다 | 프로젝트 범위 기술서를 작성한다 | 리스크와 완화 방안을 문서화한다 | 프로젝트 일정을 정의한다 |  | A | 혁신적 솔루션을 위한 RFP에 제한된 기술 조건과 컴플라이언스 격차가 있을 때, 프로젝트 관리자는 핵심 요구사항을 결정해야 한다. 필수 요구사항을 파악하면 RFP와 기대 비즈니스 가치 간의 격차를 해소할 수 있다. 범위 기술서 작성(B)은 핵심 요구를 이해하기 전에 범위를 공식화하는 것이다. 리스크 문서화(C)는 요구사항 파악 이후에 이루어진다. 일정 정의(D)는 명확한 요구사항 없이는 시기상조이다.
166 | A government agency is developing a new connectivity policy. The assigned project manager is a famous economist with international recognition. The team is eager to work with the project manager, but feels intimidated. The project manager realizes that a junior economist, whose tasks are behind schedule, is especially intimidated by the situation. What should the project manager do first? | Evaluate the performance of the junior economist in the upcoming months. | Reassign some of the junior economist ' s tasks to other economists. | Consider organizing paired work sessions for the junior and senior economists. | Request to replace the junior economist with a more experienced economist. |  | C | When a junior economist is intimidated by the project manager's reputation and falling behind schedule, the project manager should first consider organizing paired work sessions with senior economists. Paired work fosters mentoring, knowledge transfer, and confidence-building in a supportive, non-threatening environment. Evaluating performance over upcoming months (A) is reactive and delayed. Reassigning tasks (B) reduces the junior economist's workload but does not build their capability. Requesting a replacement (D) demoralizes the individual and disrupts team dynamics. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 정부 기관이 새로운 연결성 정책을 개발하고 있다. 배정된 프로젝트 관리자는 국제적으로 인정받는 유명 경제학자이다. 팀은 프로젝트 관리자와 함께 일하고 싶어하지만, 위축감을 느끼고 있다. 프로젝트 관리자는 일정이 지연되고 있는 주니어 경제학자가 특히 이 상황에 위축되어 있음을 알게 되었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 앞으로 몇 개월간 주니어 경제학자의 성과를 평가한다 | 주니어 경제학자의 일부 업무를 다른 경제학자에게 재배정한다 | 주니어와 시니어 경제학자의 페어 작업 세션을 조직하는 것을 고려한다 | 주니어 경제학자를 더 경험 있는 경제학자로 교체 요청한다 |  | C | 주니어 경제학자가 프로젝트 관리자의 명성에 위축되어 일정이 지연될 때, 프로젝트 관리자는 먼저 시니어 경제학자와의 페어 작업 세션을 조직하는 것을 고려해야 한다. 페어 작업은 지원적이고 위협적이지 않은 환경에서 멘토링, 지식 이전, 자신감 구축을 촉진한다. 향후 성과 평가(A)는 수동적이고 지연된 대응이다. 업무 재배정(B)은 작업량을 줄이지만 역량을 키우지 않는다. 교체 요청(D)은 개인의 사기를 저하시키고 팀 역학을 해친다.
167 | During a sprint, the product owner requested a change in the features to be delivered in the same sprint. According to the product owner, the request from the customer is due to regulatory reasons and they have a deadline to meet. What should the project manager do? | Submit the feature changes to the change control board (CCB) so they can evaluate and approve. | Discuss with the stakeholders about the possibility of accommodating the feature changes. | Follow the plan by delivering the features and handle the change later in the project. | Perform the change only if it has a higher or equivalent priority of the current remaining features. |  | B | The correct answer is B. Discuss with the stakeholders about the possibility of accommodating the feature changes. The product owner manages backlog priorities and defines requirements. The PM should support the product owner's role while facilitating team collaboration and maintaining agile practices. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 스프린트 중에 제품 소유자가 같은 스프린트에서 인도할 기능의 변경을 요청했다. 제품 소유자에 따르면, 고객의 요청은 규제상의 이유이며 충족해야 할 기한이 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 기능 변경을 변경통제위원회(CCB)에 제출하여 평가 및 승인을 받는다 | 이해관계자들과 기능 변경 수용 가능성에 대해 논의한다 | 계획대로 기능을 인도하고 변경은 프로젝트 후반에 처리한다 | 현재 남은 기능보다 우선순위가 높거나 동등한 경우에만 변경을 수행한다 |  | B | 정답은 B이다. 이해관계자들과 기능 변경 수용 가능성에 대해 논의한다. 제품 소유자는 백로그 우선순위를 관리하고 요구사항을 정의한다. PM은 제품 소유자의 역할을 지원하면서 팀 협업을 촉진하고 애자일 관행을 유지해야 한다.
168 | A project manager is leading a software development project. At the start of the project, the project team decides that iterations are the best way to run the project and deliver value to the customer more quickly. Which three actions should the project manager take? (Choose 3) | Develop the application as requested by the customer, based on the approved project requirements. | Plan a minimum viable product (MVP) to get early feedback from the customer. | Develop the project management plan based on the requirements requested by the customer. | Facilitate a focus group to assess the functionality before development. | Use an agile approach to deliver the product based on sprints. | B, D, E | When the team decides iterations are the best way to deliver value quickly in a software project, the project manager should (B) plan an MVP for early customer feedback, (D) facilitate a focus group to assess functionality before development, and (E) use an agile approach based on sprints. These align with iterative delivery. Developing as requested based on approved requirements (A) and developing a traditional project plan (C) align with predictive approaches. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 소프트웨어 개발 프로젝트를 이끌고 있다. 프로젝트 시작 시 프로젝트 팀은 이터레이션이 프로젝트를 운영하고 고객에게 더 빠르게 가치를 제공하는 최선의 방법이라고 결정했다. 프로젝트 관리자가 취해야 할 세 가지 조치는 무엇인가? (3개 선택) | 승인된 프로젝트 요구사항에 따라 고객이 요청한 대로 애플리케이션을 개발한다 | 고객으로부터 조기 피드백을 받기 위해 최소 기능 제품(MVP)을 계획한다 | 고객이 요청한 요구사항에 기반하여 프로젝트 관리 계획서를 개발한다 | 개발 전 기능을 평가하기 위해 포커스 그룹을 진행한다 | 스프린트 기반으로 제품을 인도하기 위해 애자일 접근법을 사용한다 | B, D, E | 팀이 이터레이션이 가치를 빠르게 제공하는 최선의 방법이라고 결정했을 때, 프로젝트 관리자는 (B) 고객 조기 피드백을 위한 MVP를 계획하고, (D) 개발 전 기능 평가를 위한 포커스 그룹을 진행하며, (E) 스프린트 기반 애자일 접근법을 사용해야 한다. 이는 반복적 인도에 부합한다. 승인된 요구사항에 따른 개발(A)과 전통적 프로젝트 계획 개발(C)은 예측형 접근에 해당한다.
169 | An enthusiastic, newly hired vice-president has been assigned as the product owner for a digital transformation project. The project manager advises the product owner that some of the functional requirements are not aligned with the chief information technology officer's (CTO) strategy. The product owner tells the project manager that the CTO is not part of the project and should not be engaged at this moment. What should the project manager do? | Review the organizational process assets (OPAs) for historical information from similar 774 projects. | Continue building the backlog since they are functional requirements. | Influence the product owner to review the engagement needed from other stakeholders. | Advise the CTO about the possible impacts caused by the project. |  | C | When functional requirements are not aligned with the CTO's strategy and the product owner dismisses the need for CTO engagement, the project manager should influence the product owner to review the engagement needed from other stakeholders. Ensuring proper stakeholder engagement aligns the project with organizational strategy. Reviewing OPAs (A) provides historical information but does not resolve the engagement gap. Continuing to build the backlog (B) ignores the misalignment. Advising the CTO about impacts (D) bypasses the product owner's role. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Digital Transformation | 열정적인 신규 부사장이 디지털 전환 프로젝트의 제품 소유자로 배정되었다. 프로젝트 관리자는 일부 기능 요구사항이 최고정보기술책임자(CTO)의 전략과 일치하지 않는다고 제품 소유자에게 알린다. 제품 소유자는 CTO가 프로젝트의 일부가 아니며 현재 참여시킬 필요가 없다고 말한다. 프로젝트 관리자는 어떻게 해야 하는가? | 유사한 774개 프로젝트의 이력 정보를 위해 조직 프로세스 자산(OPA)을 검토한다 | 기능 요구사항이므로 백로그 구축을 계속한다 | 제품 소유자에게 다른 이해관계자의 참여 필요성을 검토하도록 영향력을 행사한다 | 프로젝트로 인한 잠재적 영향에 대해 CTO에게 알린다 |  | C | 기능 요구사항이 CTO 전략과 일치하지 않고 제품 소유자가 CTO 참여의 필요성을 무시할 때, 프로젝트 관리자는 제품 소유자에게 다른 이해관계자의 참여 필요성을 검토하도록 영향력을 행사해야 한다. 적절한 이해관계자 참여는 프로젝트를 조직 전략에 맞추어 준다. OPA 검토(A)는 이력 정보를 제공하지만 참여 격차를 해결하지 않는다. 백로그 구축 계속(B)은 불일치를 무시한다. CTO에게 영향 알림(D)은 제품 소유자의 역할을 우회한다.
170 | A project manager has been assigned to a hybrid project. The project manager needs to ensure all team members are collaborating and are aware of the project's ongoing changes. What should the project manager do? | Distribute a project newsletter that includes any project changes and required project information. | Meet daily with the project team and include a monthly report on the risks and issues. | Encourage collaboration on a daily basis, facilitating different communication channels. | Send out daily emails with the project status and task lists to all team members. |  | C | In a hybrid project requiring team collaboration and change awareness, the project manager should encourage collaboration on a daily basis, facilitating different communication channels. This ensures real-time updates, immediate feedback, and transparency across methodologies. Distributing a project newsletter (A) is periodic, not daily collaboration. Meeting daily with monthly risk reports (B) is inconsistent. Sending daily status emails (D) is one-directional and does not foster true collaboration. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 프로젝트에 배정되었다. 프로젝트 관리자는 모든 팀원이 협업하고 프로젝트의 지속적인 변경 사항을 인지하도록 해야 한다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 변경 사항과 필요한 프로젝트 정보를 포함하는 프로젝트 뉴스레터를 배포한다 | 매일 프로젝트 팀과 회의하고 리스크 및 이슈에 대한 월간 보고서를 포함한다 | 매일 다양한 커뮤니케이션 채널을 활용하여 협업을 장려한다 | 모든 팀원에게 프로젝트 상태와 업무 목록이 담긴 일일 이메일을 발송한다 |  | C | 팀 협업과 변경 인지가 필요한 하이브리드 프로젝트에서, 프로젝트 관리자는 매일 다양한 커뮤니케이션 채널을 활용하여 협업을 장려해야 한다. 이는 실시간 업데이트, 즉각적 피드백, 방법론 간 투명성을 보장한다. 뉴스레터 배포(A)는 주기적이며 일일 협업이 아니다. 일일 회의와 월간 리스크 보고(B)는 일관성이 없다. 일일 상태 이메일(D)은 단방향이며 진정한 협업을 촉진하지 않는다.
171 | Five vendors are contributing to a project with an impending deadline. Two vendors are behind on their deliverables and rarely provide status updates. What should the project manager do? | Find replacements for the two vendors to complete the project in a timely manner | Extend the project schedule and inform the vendors it was due to their poor performance | Begin daily check-ins with the two vendors to recover time at their own expense | Reduce the two vendors' pay due to poor performance and lack of communication |  | C | When two of five vendors are behind on deliverables with poor communication near a deadline, the project manager should begin daily check-ins with the two vendors to recover time at their own expense. Increased monitoring provides visibility, removes blockers, and tracks progress against recovery commitments. Finding replacement vendors (A) is risky near a deadline due to onboarding time. Extending the schedule (B) weakens urgency and is premature. Reducing vendor pay (D) is a contractual matter and not the first response to a communication problem. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 5개 벤더가 마감이 임박한 프로젝트에 기여하고 있다. 2개 벤더가 인도물에 뒤처져 있으며 상태 업데이트를 거의 제공하지 않는다. 프로젝트 관리자는 어떻게 해야 하는가? | 2개 벤더를 대체하여 프로젝트를 적시에 완료한다 | 프로젝트 일정을 연장하고 벤더들에게 저조한 성과 때문이라고 알린다 | 2개 벤더와 일일 점검을 시작하여 벤더 비용으로 시간을 만회한다 | 저조한 성과와 커뮤니케이션 부족으로 2개 벤더의 대가를 삭감한다 |  | C | 마감이 임박한 상태에서 5개 중 2개 벤더가 인도물과 커뮤니케이션이 부족할 때, 프로젝트 관리자는 2개 벤더와 일일 점검을 시작하여 벤더 비용으로 시간을 만회해야 한다. 모니터링 강화는 가시성을 제공하고 장애물을 제거하며 회복 이행을 추적한다. 벤더 교체(A)는 마감 임박 시 온보딩 시간으로 위험하다. 일정 연장(B)은 긴급성을 약화시키며 시기상조이다. 대가 삭감(D)은 계약적 문제이며 커뮤니케이션 문제에 대한 첫 번째 대응이 아니다.
172 | During regular project progress review meetings, one team member shares bad news that has a significant impact on the project schedule. How should the project manager react to ensure the project remains successful? | Thank the team member for raising this issue, log it, and move on to the next topic. | Focus the discussion on recovery and ways to get back on track. | Punish the team member for providing negative data that will affect the team ' s morale. | Act in a way to highlight the criticality of the situation. |  | B | When a team member shares bad news significantly impacting the schedule, the project manager should focus the discussion on recovery and ways to get back on track. Solution-oriented leadership maintains momentum. Thanking and moving on (A) acknowledges but does not address the impact. Punishing the team member (C) discourages transparency. Highlighting criticality (D) creates panic without solutions. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Schedule Management | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 정기 프로젝트 진행 검토 회의 중, 한 팀원이 프로젝트 일정에 중대한 영향을 미치는 나쁜 소식을 공유한다. 프로젝트 관리자는 프로젝트 성공을 보장하기 위해 어떻게 대응해야 하는가? | 이 문제를 제기해 준 팀원에게 감사하고, 기록한 후 다음 안건으로 넘어간다 | 회복과 정상 궤도 복귀 방안에 대해 논의에 집중한다 | 팀의 사기에 영향을 줄 부정적 데이터를 제공한 팀원을 처벌한다 | 상황의 심각성을 부각하는 방식으로 행동한다 |  | B | 팀원이 일정에 중대한 영향을 미치는 나쁜 소식을 공유할 때, 프로젝트 관리자는 회복과 정상 궤도 복귀 방안에 대해 논의에 집중해야 한다. 솔루션 중심의 리더십은 추진력을 유지한다. 감사 후 넘어가기(A)는 인정하지만 영향을 다루지 않는다. 팀원 처벌(C)은 투명성을 저해한다. 심각성 부각(D)은 솔루션 없이 공포감을 조성한다.
173 | A client is structured as a matrix organization for an agile project. The project manager is working on-site with key stakeholders from different parts of the organization. How should the project manager handle the different stakeholders? | All stakeholders are important, so the project manager should follow directions provided by management and key stakeholders | The project manager is working on the client ' s premises, so follow the directions of all the key stakeholders | This is an agile project, so listen only to the directions of the project manager ' s supervisor and the functional managers of the organization | Because there are different perspectives perform a stakeholder analysis and act based on the outcome. |  | D | When working on-site with key stakeholders from different parts of a matrix organization on an agile project, the project manager should perform a stakeholder analysis and act based on the outcome. Structured analysis identifies each stakeholder's interests, influence, and engagement needs. Following management and key stakeholder directions (A) is passive. Following all key stakeholders' directions (B) is reactive. Listening only to the supervisor and functional managers (C) ignores agile stakeholder collaboration principles. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 고객이 애자일 프로젝트를 위해 매트릭스 조직으로 구성되어 있다. 프로젝트 관리자는 조직의 다양한 부서에서 온 주요 이해관계자들과 함께 현장에서 근무하고 있다. 프로젝트 관리자는 다양한 이해관계자들을 어떻게 다루어야 하는가? | 모든 이해관계자가 중요하므로, 프로젝트 관리자는 경영진과 주요 이해관계자가 제공하는 지시를 따라야 한다 | 프로젝트 관리자가 고객 현장에서 근무하고 있으므로, 모든 주요 이해관계자의 지시를 따른다 | 이것은 애자일 프로젝트이므로, 프로젝트 관리자의 상사와 조직의 기능 관리자의 지시만 따른다 | 다양한 관점이 있으므로 이해관계자 분석을 수행하고 그 결과에 따라 행동한다 |  | D | 매트릭스 조직의 애자일 프로젝트에서 다양한 부서의 주요 이해관계자와 현장에서 근무할 때, 프로젝트 관리자는 이해관계자 분석을 수행하고 그 결과에 따라 행동해야 한다. 구조화된 분석은 각 이해관계자의 관심사, 영향력, 참여 필요성을 파악한다. 경영진과 이해관계자 지시 따르기(A)는 수동적이다. 모든 주요 이해관계자 지시 따르기(B)는 반응적이다. 상사와 기능 관리자 지시만 따르기(C)는 애자일 이해관계자 협업 원칙을 무시한다.
174 | In an industrial plant, the owner has decided to add more capacity to the plant by installing a new machine and updating the software used in production. This capacity enlargement will occur while the plant is still functioning and producing. The software update will be accomplished using an agile approach in order to minimize risk. The machine procurement, installation, and integration will be accomplished using predictive approaches. What types of communications will the project manager have to design into the schedule management plan to ensure the project will be on schedule? | Weekly one-on-one meetings with each of the relevant stakeholders | Weekly colocated meetings with the relevant stakeholders | Biweekly written status reports from the relevant stakeholders | Biweekly conference calls with the relevant stakeholders |  | B | In a hybrid project combining predictive machine procurement with agile software development, the project manager should design weekly colocated meetings with relevant stakeholders into the schedule management plan. Regular face-to-face meetings in hybrid environments enable effective cross-stream coordination. Weekly one-on-one meetings (A) lack group coordination. Biweekly written reports (C) are too infrequent and one-directional. Biweekly conference calls (D) may not be frequent enough for hybrid coordination. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Hybrid/Tailoring | 산업 플랜트에서 소유자가 새 기계를 설치하고 생산에 사용되는 소프트웨어를 업데이트하여 플랜트에 용량을 추가하기로 결정했다. 이 용량 확장은 플랜트가 여전히 가동 중이고 생산 중인 상태에서 이루어진다. 소프트웨어 업데이트는 리스크를 최소화하기 위해 애자일 접근법으로 수행된다. 기계 조달, 설치 및 통합은 예측형 접근법으로 수행된다. 프로젝트 관리자는 프로젝트가 일정대로 진행되도록 일정 관리 계획에 어떤 유형의 커뮤니케이션을 설계해야 하는가? | 각 관련 이해관계자와 주간 일대일 회의 | 관련 이해관계자와 주간 동일 장소 회의 | 관련 이해관계자로부터 격주 서면 상태 보고서 | 관련 이해관계자와 격주 화상 회의 |  | B | 예측형 기계 조달과 애자일 소프트웨어 개발을 결합한 하이브리드 프로젝트에서, 프로젝트 관리자는 일정 관리 계획에 관련 이해관계자와의 주간 동일 장소 회의를 설계해야 한다. 하이브리드 환경에서 정기적인 대면 회의는 효과적인 교차 스트림 조정을 가능하게 한다. 주간 일대일 회의(A)는 그룹 조정이 부족하다. 격주 서면 보고(C)는 빈도가 너무 낮고 단방향이다. 격주 화상 회의(D)는 하이브리드 조정에 충분히 빈번하지 않을 수 있다.
175 | A project sponsor is replaced during a hybrid project closure. The new project sponsor wants to change all of the project documentation to reflect a fully predictive approach. What should the project manager do next? | Set up a meeting with the new project sponsor to understand their concerns. | Review the key existing project documents with the new project sponsor. | Address the issue during the lessons learned session of the closing phase. | Ask the team to estimate the time it will take to update the documentation. |  | A | The correct answer is A. Set up a meeting with the new project sponsor to understand their concerns. A hybrid approach leverages the strengths of both predictive and agile methodologies. The PM should tailor the approach to the project's unique characteristics and organizational environment. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Evaluate Project Status | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Hybrid/Tailoring | 하이브리드 프로젝트 종료 중에 프로젝트 스폰서가 교체되었다. 새 프로젝트 스폰서는 모든 프로젝트 문서를 완전한 예측형 접근법을 반영하도록 변경하고 싶어한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 새 프로젝트 스폰서와 만나 그들의 우려 사항을 파악한다 | 새 프로젝트 스폰서와 기존 주요 프로젝트 문서를 검토한다 | 종료 단계의 교훈 세션에서 이 문제를 다룬다 | 팀에게 문서 업데이트에 걸리는 시간을 추정하도록 요청한다 |  | A | 정답은 A이다. 새 프로젝트 스폰서와 만나 그들의 우려 사항을 파악한다. 하이브리드 접근법은 예측형과 애자일 방법론의 장점을 활용한다. PM은 프로젝트의 고유한 특성과 조직 환경에 맞게 접근법을 맞춤화해야 한다.
176 | A project manager is asked to manage an agile project, allowing the company to comply with a new upcoming regulation. After the project kickoff, the scope is modified to have the project team work on specific tasks, while a global team will manage the program for several countries in parallel. The project management plan has not yet been shared, and the deadline to complete the project is fixed. What should the project manager do to handle the scope change? | Create a risk entry in the risk management plan due to the lack of a global project management plan. | Define an initial backlog and start working on the clearest tasks, then incrementally refine the scope. | Review the organizational process assets (OPAs) from past projects with similar scope changes. | Formalize the change in the scope with the project sponsor to limit accountability for the specific tasks. |  | B | The correct answer is B. Define an initial backlog and start working on the clearest tasks, then incrementally refine the scope. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 애자일 프로젝트를 관리하도록 요청받았으며, 이를 통해 회사가 곧 시행되는 새로운 규정을 준수하게 된다. 프로젝트 킥오프 후, 프로젝트 팀이 특정 작업을 수행하도록 범위가 수정되었고, 글로벌 팀이 여러 국가에서 동시에 프로그램을 관리하게 되었다. 프로젝트 관리 계획서는 아직 공유되지 않았으며, 프로젝트 완료 기한은 고정되어 있다. 프로젝트 관리자는 범위 변경을 어떻게 처리해야 하는가? | 글로벌 프로젝트 관리 계획 부재로 인해 리스크 관리 계획에 리스크 항목을 생성한다 | 초기 백로그를 정의하고 가장 명확한 작업부터 작업을 시작한 후 점진적으로 범위를 구체화한다 | 유사한 범위 변경이 있었던 과거 프로젝트의 조직 프로세스 자산(OPA)을 검토한다 | 특정 작업에 대한 책임을 제한하기 위해 프로젝트 스폰서와 범위 변경을 공식화한다 |  | B | 정답은 B이다. 초기 백로그를 정의하고 가장 명확한 작업부터 작업을 시작한 후 점진적으로 범위를 구체화한다. 애자일 환경에서 PM은 팀 협업 촉진, 장애물 제거, 애자일 원칙과 세리머니를 존중하면서 지속적인 가치 제공에 집중해야 한다.
177 | A project manager is working on an agile project. The organization decided to implement the Scrum framework. The project manager organized a workshop to explain the differences between traditional project artifacts and the Scrum approach. The most frequent question raised is what artifact will replace the project schedule. What should be the project manager's response? | Sprint plan and product roadmap | Product roadmap and sprint backlog | Product backlog and scrum board | Sprint backlog and scrum board |  | A | In the Scrum framework, the traditional project schedule is replaced by the sprint plan and product roadmap. The sprint plan outlines work for each sprint iteration, while the product roadmap provides the strategic long-term view of product direction and milestones. Product roadmap and sprint backlog (B) partially overlaps but is less precise. Product backlog and scrum board (C) address work items and flow, not scheduling. Sprint backlog and scrum board (D) cover execution, not strategic planning. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 프로젝트 관리자가 애자일 프로젝트에서 일하고 있다. 조직은 스크럼 프레임워크를 도입하기로 결정했다. 프로젝트 관리자는 전통적 프로젝트 산출물과 스크럼 접근법의 차이를 설명하기 위해 워크숍을 조직했다. 가장 빈번하게 제기된 질문은 어떤 산출물이 프로젝트 일정을 대체할 것인가이다. 프로젝트 관리자의 답변은 무엇이어야 하는가? | 스프린트 계획과 제품 로드맵 | 제품 로드맵과 스프린트 백로그 880 | 제품 백로그와 스크럼 보드 | 스프린트 백로그와 스크럼 보드 |  | A | 스크럼 프레임워크에서 전통적 프로젝트 일정은 스프린트 계획과 제품 로드맵으로 대체된다. 스프린트 계획은 각 스프린트 이터레이션의 작업을 개요하고, 제품 로드맵은 제품 방향과 마일스톤의 전략적 장기 관점을 제공한다. 제품 로드맵과 스프린트 백로그(B)는 부분적으로 겹치지만 덜 정확하다. 제품 백로그와 스크럼 보드(C)는 작업 항목과 흐름을 다루지 일정이 아니다. 스프린트 백로그와 스크럼 보드(D)는 실행을 다루지 전략적 계획이 아니다.
178 | In an agile project, the team planned to complete 40 story points in an iteration, but only completed 30 story points. What is the schedule performance index (SPI)? | 40/30 | 40/70 | 30/70 | 30/40 |  | D | The schedule performance index (SPI) is calculated as earned value divided by planned value. The team planned 40 story points (PV) and completed 30 (EV). SPI = EV/PV = 30/40 = 0.75. In the given format, 30/40 is the correct expression. 40/30 (A) inverts the ratio. 40/70 (B) and 30/70 (C) use incorrect values. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 애자일 프로젝트에서 팀이 이터레이션에서 40 스토리 포인트를 완료할 계획이었으나, 30 스토리 포인트만 완료했다. 일정성과지수(SPI)는 얼마인가? | 40/30 | 40/70 | 30/70 | 30/40 |  | D | 일정성과지수(SPI)는 획득가치를 계획가치로 나누어 계산한다. 팀이 40 스토리 포인트를 계획(PV)하고 30을 완료(EV)했다. SPI = EV/PV = 30/40 = 0.75. 주어진 형식에서 30/40이 올바른 표현이다. 40/30(A)은 비율이 반전되어 있다. 40/70(B)과 30/70(C)은 잘못된 값을 사용한다.
179 | A project team needs to follow regulatory compliance guidelines that are mandatory for the project. What should the project manager do to ensure compliance adherence? | Assess compliance when there is time in the project. | Review compliance adherence at the end of the project. | Include compliance within the development tools. | Assign a project team member to ensure compliance. |  | C | To ensure compliance adherence with mandatory regulatory guidelines, the project manager should include compliance within the development tools. Integrating compliance into the daily workflow enables continuous, proactive monitoring—making compliance checks a natural part of the development process rather than a separate activity. Assessing compliance only when there is time (A) is reactive and risks non-compliance. Reviewing adherence only at the end (B) is too late to catch and correct issues. Assigning a single team member to ensure compliance (D) creates a bottleneck and does not embed compliance into the team's processes. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 프로젝트 팀은 프로젝트에 필수적인 규제 준수 지침을 따라야 한다. 프로젝트 관리자는 준수 이행을 보장하기 위해 무엇을 해야 하는가? | 프로젝트에 시간이 있을 때 준수를 평가한다 | 프로젝트 종료 시 준수 이행을 검토한다 | 개발 도구 내에 준수를 포함한다 | 준수를 보장할 프로젝트 팀원을 지정한다 |  | C | 필수 규제 준수 지침의 이행을 보장하기 위해, 프로젝트 관리자는 개발 도구 내에 준수를 포함해야 한다. 준수를 일상 업무에 통합하면 지속적이고 사전 예방적인 모니터링이 가능해져 준수 검사가 개발 프로세스의 자연스러운 부분이 된다. 시간이 있을 때만 평가(A)는 수동적이며 미준수 위험이 있다. 종료 시에만 검토(B)는 문제를 발견하고 수정하기에 너무 늦다. 단일 팀원 지정(D)은 병목을 만들며 팀 프로세스에 준수를 내장하지 않는다.
180 | For an agile pilot project, the sponsor arranged an early product demonstration for the customer. During the meeting, the customer realizes that a new feature will significantly improve the product. After collecting the new requirements, what should the project manager do? | Assess the impact of the new requirements and initiate the change request process. | Work with the product manager and the rest of the team to update the project backlog. | Follow the change management plan to update the risk register so It accounts for the added scope. | Assess the impact and communicate the updated product roadmap to the stakeholders. |  | B | When a customer identifies a valuable new feature during an agile pilot product demonstration, the project manager should work with the product manager and the rest of the team to update the project backlog. In agile, the backlog is the living document for incorporating feedback and new requirements. Assessing impact and initiating change requests (A) follows predictive methodology. Following the change management plan for the risk register (C) mixes concerns. Communicating the updated product roadmap (D) is a later step after backlog update. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Tailored Approach | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 애자일 파일럿 프로젝트에서 스폰서가 고객을 위한 조기 제품 시연을 마련했다. 회의 중 고객은 새로운 기능이 제품을 크게 개선할 것이라고 인식한다. 새로운 요구사항을 수집한 후, 프로젝트 관리자는 무엇을 해야 하는가? | 새로운 요구사항의 영향을 평가하고 변경 요청 프로세스를 시작한다 | 제품 관리자 및 나머지 팀과 함께 프로젝트 백로그를 업데이트한다 | 변경 관리 계획을 따라 추가된 범위를 고려하여 리스크 등록부를 업데이트한다 | 영향을 평가하고 업데이트된 제품 로드맵을 이해관계자에게 전달한다 |  | B | 애자일 파일럿 제품 시연 중 고객이 가치 있는 새 기능을 식별했을 때, 프로젝트 관리자는 제품 관리자 및 나머지 팀과 함께 프로젝트 백로그를 업데이트해야 한다. 애자일에서 백로그는 피드백과 새로운 요구사항을 통합하기 위한 살아있는 문서이다. 영향 평가 및 변경 요청 시작(A)은 예측형 방법론을 따른다. 리스크 등록부를 위한 변경 관리 계획 따르기(C)는 관심사를 혼합한다. 업데이트된 제품 로드맵 전달(D)은 백로그 업데이트 이후의 단계이다.
181 | A project manager is newly appointed to lead a project team that will be working remotely. The project manager decided to use a set of tools that worked well for previous projects. However, a few team members are not happy with this plan. What should the project manager have done to avoid this? | Met with the project team to determine their collaboration needs and identified tools that will work best. | Delegated the responsibility of selecting the collaboration tools to the project ' s technical lead. | Asked the project sponsor for approval to purchase the newest collaboration tool on the market. | Allowed the project team members to use the tools that will work best for them for this project. |  | A | When team members are unhappy with the PM's pre-selected remote collaboration tools, the project manager should have met with the project team to determine their collaboration needs and identified tools that work best. Involving the team in tool selection ensures suitability and fosters ownership. Delegating to the technical lead (B) excludes team input. Requesting sponsor approval for the newest tool (C) is arbitrary. Allowing everyone to use their own tools (D) creates inconsistency. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 원격으로 근무할 프로젝트 팀을 이끌도록 새로 임명되었다. 프로젝트 관리자는 이전 프로젝트에서 잘 작동했던 도구 세트를 사용하기로 결정했다. 그러나 일부 팀원이 이 계획에 만족하지 않는다. 프로젝트 관리자는 이를 피하기 위해 무엇을 했어야 하는가? | 프로젝트 팀과 만나 협업 요구사항을 파악하고 가장 적합한 도구를 식별했어야 한다 | 협업 도구 선택 책임을 프로젝트 기술 리드에게 위임했어야 한다 | 프로젝트 스폰서에게 시장에서 가장 최신 협업 도구 구매 승인을 요청했어야 한다 | 프로젝트 팀원들이 이 프로젝트에 가장 적합한 도구를 각자 사용하도록 허용했어야 한다 |  | A | 팀원들이 PM이 사전 선택한 원격 협업 도구에 불만족할 때, 프로젝트 관리자는 프로젝트 팀과 만나 협업 요구사항을 파악하고 가장 적합한 도구를 식별했어야 한다. 도구 선택에 팀을 참여시키면 적합성을 보장하고 주인의식을 촉진한다. 기술 리드에게 위임(B)은 팀 의견을 배제한다. 최신 도구 구매 승인 요청(C)은 임의적이다. 각자 도구 사용 허용(D)은 일관성이 없어진다.
182 | A project manager is managing a megaproject. The project stakeholders are from different geographical areas and have diverse cultural and social backgrounds. The project manager wants to improve team productivity to realize more effective and efficient results. Which action should the project manager take? | Empower team members to participate in decision-making and take ownership of actions. | Implement a flexible work schedule policy to eliminate the time zone problems among stakeholders. | Encourage team members to network so that they know each other ' s cultural backgrounds. | Provide a relaxed work schedule policy and encourage team members to work from home . |  | A | When managing a megaproject with stakeholders from different geographical areas and diverse cultural backgrounds, the project manager should empower team members to participate in decision-making and take ownership of actions. Empowerment increases motivation, creativity, and accountability. Implementing flexible schedules (B) addresses logistics, not productivity. Encouraging networking for cultural understanding (C) builds awareness, not productivity. Providing relaxed schedules and work-from-home (D) does not directly address productivity. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 메가 프로젝트를 관리하고 있다. 프로젝트 이해관계자는 서로 다른 지리적 지역에 있으며 다양한 문화적, 사회적 배경을 가지고 있다. 프로젝트 관리자는 더 효과적이고 효율적인 결과를 실현하기 위해 팀 생산성을 향상시키고 싶어한다. 프로젝트 관리자는 어떤 조치를 취해야 하는가? | 팀원들이 의사결정에 참여하고 행동에 대한 주인의식을 갖도록 권한을 부여한다 | 이해관계자 간의 시간대 문제를 제거하기 위해 유연한 근무 일정 정책을 시행한다 | 팀원들이 서로의 문화적 배경을 알 수 있도록 네트워킹을 장려한다 | 여유로운 근무 일정 정책을 제공하고 팀원들이 재택근무하도록 장려한다 |  | A | 서로 다른 지리적 지역의 다양한 문화적 배경을 가진 이해관계자가 있는 메가 프로젝트를 관리할 때, 프로젝트 관리자는 팀원들이 의사결정에 참여하고 행동에 대한 주인의식을 갖도록 권한을 부여해야 한다. 권한 부여는 동기부여, 창의성, 책임감을 높인다. 유연한 일정 시행(B)은 물류 문제를 다루지 생산성이 아니다. 문화적 이해를 위한 네트워킹 장려(C)는 인식을 높이지 생산성이 아니다. 여유로운 일정과 재택근무 제공(D)은 생산성을 직접적으로 다루지 않는다.
183 | A team has just adopted an agile approach. During daily standup meetings, the team expressed concerns about task delays. The project leader worked with the product owner to get clarity on the features. The project leader asked the team to fast-track all product features to ensure delivery. Sprints are being completed but with either fewer features or low quality. What should the project leader have done to ensure success? | Suggested to the team to add impediments as work items in the product backlog to be fixed in the next sprints | Directed teams to possible solutions that help in removing the impediments and contribute to a timely delivery | Empowered the team to improve their processes, tools, and interactions to be more effective in delivery and removing impediments | Asked the team to create an impediment log and keep it updated for use in the next sprint planning |  | C | When a newly agile team completes sprints with fewer features or low quality after the project leader directed fast-tracking, the project leader should have empowered the team to improve their processes, tools, and interactions for more effective delivery and impediment removal. Team empowerment fosters sustainable improvement. Suggesting impediments as backlog items (A) delays resolution. Directing teams to solutions (B) removes team ownership. Creating an impediment log for sprint planning (D) documents but does not empower. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Integrate Sustainability | Identify Risks | Sustainability | 팀이 막 애자일 접근법을 채택했다. 일일 스탠드업 회의에서 팀이 작업 지연에 대한 우려를 표현했다. 프로젝트 리더는 제품 소유자와 함께 기능에 대한 명확성을 얻기 위해 작업했다. 프로젝트 리더는 팀에게 인도를 보장하기 위해 모든 제품 기능을 공정 단축하도록 요청했다. 스프린트가 완료되고 있지만 기능이 적거나 품질이 낮다. 프로젝트 리더는 성공을 보장하기 위해 무엇을 했어야 하는가? | 팀에게 장애물을 다음 스프린트에서 수정할 작업 항목으로 제품 백로그에 추가하도록 제안했어야 한다 | 장애물 제거와 적시 인도에 기여하는 가능한 솔루션으로 팀을 안내했어야 한다 | 팀이 인도와 장애물 제거에서 더 효과적이 되도록 프로세스, 도구, 상호작용을 개선하도록 권한을 부여했어야 한다 | 팀에게 장애물 로그를 만들고 다음 스프린트 계획에 사용하도록 업데이트를 유지하도록 요청했어야 한다 |  | C | 프로젝트 리더가 공정 단축을 지시한 후 새로 애자일을 채택한 팀이 적은 기능 또는 낮은 품질로 스프린트를 완료할 때, 프로젝트 리더는 팀이 인도와 장애물 제거에서 더 효과적이 되도록 프로세스, 도구, 상호작용을 개선하도록 권한을 부여했어야 한다. 팀 권한 부여는 지속 가능한 개선을 촉진한다. 장애물을 백로그 항목으로 제안(A)은 해결을 지연시킨다. 솔루션으로 팀 안내(B)는 팀 주인의식을 제거한다. 스프린트 계획을 위한 장애물 로그 생성(D)은 문서화하지만 권한을 부여하지 않는다.
184 | In a fixed time and budget project, the customer wants the development of a core component to be based on agile practices, as the final scope of the requirement has not yet been fully developed. The project manager is participating in contract development with the sales team and wants to ensure that development costs do not impact the profitability of the project. Which two controls should the project manager incorporate into the contract to specifically address the development of the core component? (Choose two) | Tier the contract for fixed and agile components | Limit the number of iterations for development in the contract. | Establish a governance committee to review the contract delivery | Provide alternatives to scope change at specific project phases within the contract. | Require that only internal resources be utilized for this project | A, D | For a fixed time and budget project with an agile core component whose scope is not fully developed, the project manager should take two actions: tier the contract for fixed and agile components (A) to separate pricing models appropriate for each approach, and provide alternatives to scope change at specific project phases within the contract (D) to give the customer structured options for managing scope evolution. Tiering addresses the hybrid nature of the project, while scope change alternatives provide flexibility within governance. Limiting iterations (B) constrains agile delivery without addressing the underlying scope uncertainty. Installing a governance committee (C) adds oversight but not direct cost control. Requiring only internal resources (E) restricts flexibility without addressing scope uncertainty. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 고정 시간 및 예산 프로젝트에서, 고객은 핵심 구성요소의 개발을 애자일 관행에 기반하길 원한다. 요구사항의 최종 범위가 아직 완전히 개발되지 않았기 때문이다. 프로젝트 관리자는 영업팀과 함께 계약 개발에 참여하고 있으며 개발 비용이 프로젝트 수익성에 영향을 마치지 않도록 보장하고 싶어한다. 프로젝트 관리자는 핵심 구성요소 개발을 구체적으로 다루기 위해 계약에 어떤 두 가지 통제를 포함해야 하는가? (2개 선택) | 고정형과 애자일 구성요소를 계층화하여 계약한다 | 계약에서 개발을 위한 이터레이션 횟수를 제한한다 | 계약 인도를 검토할 거버넌스 위원회를 설치한다 | 계약 내 특정 프로젝트 단계에서 범위 변경에 대한 대안을 제공한다 | 프로젝트에 내부 자원만 활용하도록 요구한다 | A, D | 고정 시간과 예산의 프로젝트에서 범위가 완전히 개발되지 않은 애자일 핵심 구성요소가 있을 때, PM은 두 가지 조치를 취해야 한다: 고정 및 애자일 구성요소에 대해 계약을 계층화하고(A), 계약 내 특정 프로젝트 단계에서 범위 변경에 대한 대안을 제공한다(D). 계층화는 프로젝트의 하이브리드 특성을 다루고, 범위 변경 대안은 거버넌스 내에서 유연성을 제공한다. 반복 횟수 제한(B)은 근본적인 범위 불확실성을 해결하지 않고 애자일 전달을 제약한다. 거버넌스 위원회 설치(C)는 감독을 추가하지만 직접적인 비용 통제는 아니다. 내부 자원만 요구(E)는 범위 불확실성을 해결하지 않고 유연성을 제한한다.
185 | During the execution stage, the project manager discovered that one team member is not able to complete their work on time and is running later than expected. This delay may potentially impact a project milestone. What should the project manager do first? | Discuss with the team and assess the reasons that led to the delay. | Assign more resources form other teams on the late work. | Discuss with senior management and seek their guidance. | Request the team member ' s manager to find a solution. |  | A | When a team member is running late and the delay may impact a milestone, the project manager should first discuss with the team and assess the reasons that led to the delay. Understanding root causes through team engagement enables informed, collaborative problem-solving. Assigning more resources (B) acts without understanding the cause. Seeking senior management guidance (C) escalates prematurely. Requesting the team member's manager find a solution (D) delegates the PM's responsibility. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 실행 단계에서 프로젝트 관리자는 한 팀원이 제시간에 작업을 완료할 수 없고 예상보다 늦어지고 있음을 발견했다. 이 지연은 프로젝트 마일스톤에 잘재적 영향을 미칠 수 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 팀과 논의하고 지연을 초래한 원인을 평가한다 | 다른 팀의 자원을 지연된 작업에 추가 배정한다 | 고위 경영진과 논의하고 지침을 구한다 | 팀원의 관리자에게 해결책을 찾도록 요청한다 |  | A | 팀원이 지연되고 그 지연이 마일스톤에 영향을 줄 수 있을 때, 프로젝트 관리자는 먼저 팀과 논의하고 지연을 초래한 원인을 평가해야 한다. 팀 참여를 통한 근본 원인 이해는 정보에 입각한 협력적 문제 해결을 가능하게 한다. 자원 추가 배정(B)은 원인을 이해하지 않고 행동하는 것이다. 고위 경영진 지침 구하기(C)는 조기에 상부로 에스컬레이션하는 것이다. 팀원 관리자에게 해결 요청(D)은 PM의 책임을 위임하는 것이다.
186 | During the initial stage of a project, the team estimated activities for the next iteration in story points. It was agreed that each story point would be assumed to be equal to one day of effort during project execution. There are some activities estimated as two story points and others estimated as 100 story points. What should the project manager ask the team to do next? | Execute the smaller estimated activities. | Resize the story points. | Negotiate the estimation so it gets smaller. | Break down the larger activities into smaller ones. |  | D | When some activities are estimated at 2 story points and others at 100 story points, the project manager should ask the team to break down the larger activities into smaller ones. Large stories are too big to be actionable within a sprint and should be decomposed. Executing smaller activities first (A) ignores the oversized stories. Resizing story points (B) does not address the underlying complexity. Negotiating estimates smaller (C) misuses the estimation process. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Hybrid/Tailoring | 프로젝트 초기 단계에서, 팀이 다음 이터레이션의 활동을 스토리 포인트로 추정했다. 프로젝트 실행 중 각 스토리 포인트는 하루 노력과 동일하다고 합의되었다. 2 스토리 포인트로 추정된 활동도 있고 100 스토리 포인트로 추정된 활동도 있다. 프로젝트 관리자는 팀에게 다음에 무엇을 하도록 요청해야 하는가? | 더 작게 추정된 활동을 실행한다 | 스토리 포인트 크기를 조정한다 | 추정치가 더 작아지도록 협상한다 | 더 큰 활동을 더 작은 활동으로 분해한다 |  | D | 일부 활동이 2 스토리 포인트로, 다른 활동이 100 스토리 포인트로 추정될 때, 프로젝트 관리자는 팀에게 더 큰 활동을 더 작은 활동으로 분해하도록 요청해야 한다. 큰 스토리는 스프린트 내에서 실행 가능하도록 분해되어야 한다. 작은 활동부터 실행(A)은 과대 크기의 스토리를 무시한다. 스토리 포인트 크기 조정(B)은 근본적인 복잡성을 다루지 않는다. 추정치 협상(C)은 추정 프로세스를 오용한다.
187 | A company starts implementing Scrum. About halfway through the first sprint, communication issues develop. Some project team members are not in sync with other team members. What is the cause for this communication gap? | The project sprint board has not been updated | Daily standup meetings were not held or enforced | The project status dashboard has not been updated | The communications management plan has not been developed |  | B | When communication issues develop halfway through the first sprint with some team members out of sync, the cause is that daily standup meetings were not held or enforced. Standups provide daily synchronization, transparency, and impediment identification. An unupdated sprint board (A) is a symptom, not a cause. An unupdated dashboard (C) affects reporting, not team sync. A missing communications management plan (D) is broader than the immediate Scrum practice gap. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 회사가 스크럼을 도입하기 시작한다. 첫 번째 스프린트 중반쯤에 커뮤니케이션 문제가 발생한다. 일부 프로젝트 팀원이 다른 팀원과 동기화되지 않는다. 이 커뮤니케이션 격차의 원인은 무엇인가? | 프로젝트 스프린트 보드가 업데이트되지 않았다 | 일일 스탠드업 회의가 개최되지 않거나 시행되지 않았다 | 프로젝트 상태 대시보드가 업데이트되지 않았다 | 커뮤니케이션 관리 계획이 개발되지 않았다 |  | B | 첫 번째 스프린트 중반에 일부 팀원이 동기화되지 않는 커뮤니케이션 문제가 발생할 때, 원인은 일일 스탠드업 회의가 개최되지 않거나 시행되지 않았기 때문이다. 스탠드업은 일일 동기화, 투명성, 장애물 식별을 제공한다. 업데이트되지 않은 스프린트 보드(A)는 증상이지 원인이 아니다. 업데이트되지 않은 대시보드(C)는 보고에 영향을 미치지 팀 동기화가 아니다. 누락된 커뮤니케이션 관리 계획(D)은 즉각적인 스크럼 관행 격차보다 광범위한 문제이다.
188 | A project manager has been assigned to a new project that is similar to a project that was closed last year. There is no schedule baseline, but the project manager received the activity list and wants to prepare a reasonable schedule. What should the project manager do? | Create a draft schedule based on the activity list and the historical data from the closed project. | Evaluate each activity duration and build a new project schedule. | inform the sponsor that the activity list is not adequate for creating a schedule baseline. | Adopt the same timeframe as the closed project for the current project. |  | A | When assigned to a new project similar to one closed last year with no schedule baseline but an activity list, the project manager should create a draft schedule based on the activity list and historical data from the closed project. Leveraging analogous estimation provides a reasonable starting point. Evaluating each activity duration individually (B) requires more information than available. Informing the sponsor that the activity list is inadequate (C) is premature. Adopting the same timeframe (D) assumes identical conditions without analysis. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 관리자가 작년에 종료된 프로젝트와 유사한 새 프로젝트에 배정되었다. 일정 기준선은 없지만 프로젝트 관리자는 활동 목록을 받았으며 합리적인 일정을 준비하고자 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 활동 목록과 종료된 프로젝트의 이력 데이터를 기반으로 초안 일정을 작성한다 | 각 활동 기간을 평가하고 새 프로젝트 일정을 수립한다 | 스폰서에게 활동 목록이 일정 기준선 작성에 적합하지 않다고 알린다 | 종료된 프로젝트와 동일한 시간 프레임을 현재 프로젝트에 적용한다 |  | A | 작년에 종료된 유사 프로젝트가 있고 일정 기준선 없이 활동 목록만 있을 때, 프로젝트 관리자는 활동 목록과 종료된 프로젝트의 이력 데이터를 기반으로 초안 일정을 작성해야 한다. 유사 추정을 활용하면 합리적인 출발점을 제공한다. 각 활동 기간 개별 평가(B)는 가용한 정보보다 많은 정보가 필요하다. 스폰서에게 활동 목록 부적합 알림(C)은 시기상조이다. 동일한 시간 프레임 적용(D)은 동일한 조건을 분석 없이 가정한다.
189 | In a project using a hybrid approach, the performance of the team was consistently excellent during the predictive stages. When the iterations began, however, the team members started to show signs of low commitment, conflicts, and confusion, resulting in low morale. What should the project manager do to handle this situation? | Give team members more authority to make decisions. | Perform team-building activities and enhance collaboration. 1218 | Coach the team members on agile processes and knowledge. | Identify the team members who are impacting low morale. |  | B | When a hybrid project team shows low commitment, conflicts, and confusion after transitioning from predictive to iterative stages, the project manager should perform team-building activities and enhance collaboration. Team-building addresses trust and cohesion during transitions. Giving more authority (A) does not address the root cause. Identifying individuals impacting morale (C) creates blame. Coaching on agile processes (D) helps but does not build team relationships. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Hybrid/Tailoring | 하이브리드 접근법을 사용하는 프로젝트에서, 예측형 단계 동안 팀의 성과는 일관되게 우수했다. 그러나 이터레이션이 시작되자 팀원들이 낮은 헌신, 갈등, 혼란의 징후를 보이며 사기가 저하되었다. 프로젝트 관리자는 이 상황을 처리하기 위해 무엇을 해야 하는가? | 팀원에게 더 많은 의사결정 권한을 부여한다 | 팀 빌딩 활동을 수행하고 협업을 강화한다 | 팀원에게 애자일 프로세스와 지식을 코칭한다 | 낮은 사기에 영향을 주는 팀원을 식별한다 |  | B | 하이브리드 프로젝트 팀이 예측형에서 반복적 단계로 전환한 후 낮은 헌신, 갈등, 혼란을 보일 때, 프로젝트 관리자는 팀 빌딩 활동을 수행하고 협업을 강화해야 한다. 팀 빌딩은 전환 기간 동안 신뢰와 응집력을 다룬다. 더 많은 권한 부여(A)는 근본 원인을 다루지 않는다. 낮은 사기 영향 팀원 식별(C)은 비난을 조성한다. 애자일 프로세스 코칭(D)은 도움이 되지만 팀 관계를 구축하지 않는다.
190 | During a sprint, the team is experiencing conflict because the customer asks for additional features that increase the complexity. The scrum master is trying to resolve the conflict. Which approach should the scrum master use? | Approach the product owner to determine the next course of action and update the backlog. | Discuss the definition of done (DoD) with the customer. | Perform backlog prioritization to ensure that everyone is working on the highest value features. | Discuss the acceptance criteria with customer. |  | A | When a customer requests additional features mid-sprint increasing complexity, the scrum master should approach the product owner to determine the next course of action and update the backlog. Only the product owner has authority to manage backlog priorities. Discussing the definition of done (B) clarifies quality, not scope changes. Discussing acceptance criteria (D) applies to existing items. Performing backlog prioritization (C) is the product owner's responsibility. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 스프린트 중에 고객이 추가 기능을 요청하여 복잡성이 증가하면서 팀이 갈등을 겪고 있다. 스크럼 마스터가 갈등을 해결하려고 한다. 스크럼 마스터는 어떤 접근법을 사용해야 하는가? | 제품 소유자에게 다음 행동 방침을 결정하고 백로그를 업데이트하도록 접근한다 | 고객과 완료 정의(DoD)를 논의한다 | 모든 사람이 가장 높은 가치의 기능에 작업하도록 백로그 우선순위를 수행한다 | 고객과 인수 기준을 논의한다 |  | A | 고객이 스프린트 중간에 복잡성을 높이는 추가 기능을 요청할 때, 스크럼 마스터는 제품 소유자에게 다음 행동 방침을 결정하고 백로그를 업데이트하도록 접근해야 한다. 제품 소유자만이 백로그 우선순위를 관리할 권한이 있다. 완료 정의 논의(B)는 품질을 명확히 하지 범위 변경이 아니다. 인수 기준 논의(D)는 기존 항목에 적용된다. 백로그 우선순위 수행(C)은 제품 소유자의 책임이다.
191 | Halfway through the execution of a project, a key team member resigns from the company and will leave in 2 weeks. What should the project manager do next? | Work together on the knowledge transfer plan for the remaining team members. | Persuade the team member to delay their resignation until the project is completed. | Plan for the team member to finalize their assigned project tasks before leaving. | Ask human resources (HR) to start looking for the team member's replacement. |  | A | When a key team member resigns and will leave in 2 weeks midway through execution, the project manager should work together on a knowledge transfer plan for the remaining team members. Knowledge preservation ensures continuity. Persuading delay (B) oversteps boundaries. Planning task finalization before departure (C) addresses output but not knowledge. Asking HR for a replacement (D) may take longer than 2 weeks. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Manage Conflicts | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 중간에 핵심 팀원이 회사를 퇴사하고 2주 후에 떠난다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 남은 팀원들을 위한 지식 이전 계획을 함께 수립한다 | 프로젝트가 완료될 때까지 퇴사를 연기하도록 설득한다 | 퇴사 전에 팀원이 배정된 프로젝트 작업을 마무리하도록 계획한다 | 인사부(HR)에 팀원 교체자를 찾기 시작하도록 요청한다 |  | A | 핵심 팀원이 실행 중간에 퇴사하고 2주 후 떠난 때, 프로젝트 관리자는 남은 팀원들을 위한 지식 이전 계획을 함께 수립해야 한다. 지식 보전은 연속성을 보장한다. 퇴사 연기 설득(B)은 경계를 넘는 것이다. 퇴사 전 작업 마무리 계획(C)은 산출물을 다루지만 지식은 다루지 않는다. HR에 교체 요청(D)은 2주보다 오래 걸릴 수 있다.
192 | The CFO has stated in a conversation with a project team member that they do not believe the project will be a success due to the high cost of implementation. What should the project manager do? | Ask the project team to look for opportunities to cut project costs. | Meet with the CFO one-on-one to fully understand their cost concerns. | Carry out a benefit analysis to present at the next project team meeting. | Meet with the CFO and team to remind them of the project ' s key success measures. |  | B | When a key executive like the CFO expresses concerns about project viability due to high implementation costs, the project manager should meet with the CFO one-on-one to fully understand the specific concerns. This direct engagement builds trust, clarifies any misunderstandings, and allows the PM to explore potential solutions or adjustments. Asking the team to cut costs (A) is premature without understanding the specifics of the CFO's concern. Carrying out a benefit analysis for the team meeting (C) may be useful later but does not address the CFO's immediate objection. Reminding the CFO and team of key success measures (D) could come across as dismissive if the cost concerns are not first acknowledged and understood. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | CFO가 프로젝트 팀원과의 대화에서 높은 구현 비용으로 인해 프로젝트가 성공하지 못할 것이라고 말했다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 팀에게 프로젝트 비용 절감 기회를 찾도록 요청한다 | CFO와 일대일로 만나 그들의 비용 우려를 완전히 이해한다 | 다음 프로젝트 팀 회의에서 제시할 편익 분석을 수행한다 | CFO와 팀을 만나 프로젝트의 주요 성공 측정 기준을 상기시킨다 |  | B | CFO와 같은 주요 임원이 높은 구현 비용으로 프로젝트 실행 가능성에 대한 우려를 표할 때, 프로젝트 관리자는 CFO와 일대일로 만나 구체적인 우려를 완전히 이해해야 한다. 직접적인 참여는 신뢰를 구축하고 오해를 해소하며 잘재적 해결책을 탐색할 수 있게 한다. 팀에게 비용 절감 요청(A)은 CFO의 구체적 우려를 이해하기 전에는 시기상조이다. 팀 회의용 편익 분석 수행(C)은 나중에 유용할 수 있지만 CFO의 즉각적 반대를 다루지 않는다. 성공 측정 기준 상기(D)는 비용 우려를 먼저 인정하지 않으면 무시하는 것으로 보일 수 있다.
193 | A project manager is presented with a roadmap that excludes most of their recommendations. The content source of the roadmap is an influential stakeholder who disagrees with the use of specific procedures and practices. The project sponsor deems the roadmap acceptable. Which two actions should the project manager take first? (Choose 2) | Request to have the roadmap reviewed by the project management office (PMO). | Align deliverables based on the roadmap and documented results. | Align the roadmap within the project framework and perform a risk analysis. | Request reassignment to another project to avoid conflict with the stakeholder. | Discuss the reasoning behind the roadmap with the stakeholder. | C, E | When the roadmap excludes the PM's recommendations due to an influential stakeholder and the sponsor deems it acceptable, the project manager should first (C) align the roadmap within the project framework and perform a risk analysis, and (E) discuss the reasoning behind the roadmap with the stakeholder. These actions ensure governance alignment and stakeholder engagement. Requesting PMO review (A) escalates prematurely. Aligning deliverables without risk analysis (B) can embed avoidable issues. Requesting reassignment (D) avoids accountability. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자에게 대부분의 권고사항이 제외된 로드맵이 제시되었다. 로드맵의 출처는 특정 절차와 관행의 사용에 반대하는 영향력 있는 이해관계자이다. 프로젝트 스폰서는 로드맵이 수용 가능하다고 판단한다. 프로젝트 관리자가 먼저 취해야 할 두 가지 조치는 무엇인가? (2개 선택) | 프로젝트 관리 사무소(PMO)에 로드맵 검토를 요청한다 | 로드맵에 따라 인도물을 정렬하고 결과를 문서화한다 | 프로젝트 프레임워크 내에서 로드맵을 정렬하고 리스크 분석을 수행한다 | 이해관계자와의 갈등을 피하기 위해 다른 프로젝트로 재배정을 요청한다 | 이해관계자와 로드맵 배경의 논거를 논의한다 | C, E | 로드맵이 영향력 있는 이해관계자로 인해 PM의 권고사항을 제외하고 스폰서가 수용 가능하다고 판단할 때, 프로젝트 관리자는 먼저 (C) 프로젝트 프레임워크 내에서 로드맵을 정렬하고 리스크 분석을 수행하며, (E) 이해관계자와 로드맵 배경의 논거를 논의해야 한다. 이러한 조치는 거버넌스 정렬과 이해관계자 참여를 보장한다. PMO 검토 요청(A)은 조기에 상부로 에스컬레이션한다. 리스크 분석 없이 인도물 정렬(B)은 회피 가능한 문제를 내장할 수 있다. 재배정 요청(D)은 책임을 회피한다.
194 | An agile team recently started working on a project for a financial institution. The project sponsor is concerned that an agile approach will not provide enough support for the organization's compliance standards. In order to mitigate this risk and avoid problems, what should the project manager do? | Propose using a compliance review board that will be responsible for approving allproduct features prior to their release to the public. | Meet with the compliance team and make sure that their requirements are covered in thedefinition of done (DoD) for each story. | Liaison with the compliance group, making them responsible for understanding therequirements and keeping them prioritized in the backlog. | Ensure that the peer review process also covers compliance requirements, creating asecond layer of security for the project. |  | B | When the sponsor is concerned about compliance standards in an agile project, the project manager should meet with the compliance team and ensure their requirements are covered in the definition of done (DoD) for each story. Embedding compliance in DoD ensures every increment meets standards. Using a compliance review board (A) adds bureaucratic overhead. Liaising with the compliance group for backlog management (C) shifts responsibility. Ensuring peer review covers compliance (D) is a secondary layer, not the primary mechanism. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 애자일 팀이 최근 금융 기관의 프로젝트에서 작업을 시작했다. 프로젝트 스폰서는 애자일 접근법이 조직의 컴플라이언스 표준을 충분히 지원하지 못할 것이라고 우려한다. 이 리스크를 완화하고 문제를 피하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 모든 제품 기능을 공개 전에 승인할 준수 검토 위원회 사용을 제안한다 | 컴플라이언스 팀과 만나 그들의 요구사항이 각 스토리의 완료 정의(DoD)에 포함되도록 보장한다 | 컴플라이언스 그룹과 연락하여 그들이 요구사항을 이해하고 백로그에서 우선순위를 유지하도록 책임을 지운다 | 피어 리뷰 프로세스가 컴플라이언스 요구사항도 포함하도록 보장하여 프로젝트의 두 번째 보안 계층을 만든다 |  | B | 스폰서가 애자일 프로젝트에서 컴플라이언스 표준을 우려할 때, 프로젝트 관리자는 컴플라이언스 팀과 만나 그들의 요구사항이 각 스토리의 완료 정의(DoD)에 포함되도록 보장해야 한다. DoD에 컴플라이언스를 내장하면 모든 증분이 표준을 충족한다. 준수 검토 위원회 사용(A)은 관료적 부담을 추가한다. 컴플라이언스 그룹에 백로그 관리 책임 전가(C)는 책임을 전가한다. 피어 리뷰가 컴플라이언스를 포함하도록 보장(D)은 보조 계층이지 주요 메커니즘이 아니다.
195 | A project team needs to create artifacts for an upcoming steering committee. What should the project manager do first? | Surveying peers to understand what templates they have used. | Use templates from an existing project. | Lead the project team in finding the best templates. | Ask the project management office (PMO) for guidance. |  | D | When creating artifacts for an upcoming steering committee, the project manager should first ask the PMO for guidance. The PMO maintains standard templates and documentation requirements, ensuring alignment with organizational standards and committee expectations. Surveying peers (A) may yield inconsistent results. Using templates from an existing project (B) may not match current standards. Leading the team to find templates (C) may waste time if established templates exist. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Scope | Monitoring & Controlling | Be an Accountable Leader | Validate Scope | Traditional PM | 프로젝트 팀이 다가오는 운영 위원회를 위한 산출물을 만들어야 한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 동료들에게 설문조사하여 어떤 템플릿을 사용했는지 파악한다 | 기존 프로젝트의 템플릿을 사용한다 | 가장 적합한 템플릿을 찾도록 프로젝트 팀을 이끌다 | 프로젝트 관리 사무소(PMO)에 지침을 요청한다 |  | D | 다가오는 운영 위원회를 위한 산출물을 만들 때, 프로젝트 관리자는 먼저 PMO에 지침을 요청해야 한다. PMO는 표준 템플릿과 문서화 요구사항을 유지하여 조직 표준과 위원회 기대에 부합하도록 보장한다. 동료 설문조사(A)는 일관되지 않은 결과를 낳을 수 있다. 기존 프로젝트 템플릿 사용(B)은 현재 표준과 맞지 않을 수 있다. 팀이 템플릿 찾도록 이끌기(C)는 확립된 템플릿이 있으면 시간 낭비일 수 있다.
196 | A project manager is in the middle of executing the construction of a high-rise plaza when the government regulatory agency announces an increase in the price of fuel. The project still has seven months left on the schedule. What should the project manager do first? | Implement crashing to mitigate the impact on the budget. | Review the organizational process assets (OPAs) as a reference. | Meet with the vendors to evaluate the impact on the budget. | Request the release of management reserve for the project. 1196 |  | C | The correct answer is C. Meet with the vendors to evaluate the impact on the budget. Risk and compliance management require proactive identification and assessment. The PM should evaluate impacts, follow proper processes, and implement appropriate response strategies. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Schedule Management | Process | Plan and Manage Schedule | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 고층 플라자 건설을 실행하는 중에 정부 규제 기관이 연료 가격 인상을 발표한다. 프로젝트는 일정에 7개월이 남아있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 예산에 대한 영향을 완화하기 위해 공정 단축을 구현한다 | 조직 프로세스 자산(OPA)을 참조자료로 검토한다 | 벤더들과 만나 예산에 대한 영향을 평가한다 | 프로젝트를 위한 관리 예비비 방출을 요청한다 |  | C | 정답은 C이다. 벤더들과 만나 예산에 대한 영향을 평가한다. 리스크 및 컴플라이언스 관리는 사전 예방적 식별과 평가를 요구한다. PM은 영향을 평가하고, 적절한 프로세스를 따르며, 적절한 대응 전략을 실행해야 한다.
197 | A project manager is leading a major water pipeline project and realizes midway into the project that the project completion date is not achievable. Local farmers who rely on the water for irrigation may be affected due to the delay. The project manager is afraid of their displeasure and reaction, which will affect the project. How should the project manager plan the communication to the stakeholders? | Document and accept this risk and communicate this decision to the project sponsor. | Propose a solution to the stakeholders and communicate it to the local farmers. | Deliver the information to the stakeholders with the project management office ' s (PMO)assistance. | Collect feedback from the farmers and keep the information within the project team. |  | C | When a major water pipeline project faces an unachievable completion date affecting local farmers, the project manager should deliver the information to stakeholders with the PMO's assistance. The PMO provides guidance, support, and coordination to ensure consistent, transparent communication across all stakeholder groups. Documenting and accepting the risk (A) hides the issue. Proposing a solution before consulting stakeholders (B) bypasses their input. Collecting farmer feedback and keeping it internal (D) lacks transparency. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 주요 상수도 파이프라인 프로젝트를 이끌고 있으며, 프로젝트 중간에 프로젝트 완료일이 달성 불가능하다는 것을 깨닫는다. 관개용 물에 의존하는 지역 농민들이 지연으로 인해 영향을 받을 수 있다. 프로젝트 관리자는 그들의 불만과 반응이 프로젝트에 영향을 줄 것을 우려한다. 프로젝트 관리자는 이해관계자에게 커뮤니케이션을 어떻게 계획해야 하는가? | 이 리스크를 문서화하고 수용하며 이 결정을 프로젝트 스폰서에게 전달한다 | 이해관계자에게 해결책을 제안하고 지역 농민들에게 전달한다 | PMO의 지원을 받아 이해관계자에게 정보를 전달한다 | 농민들로부터 피드백을 수집하고 정보를 프로젝트 팀 내에만 보관한다 |  | C | 주요 상수도 파이프라인 프로젝트가 달성 불가능한 완료일로 지역 농민에게 영향을 줄 때, 프로젝트 관리자는 PMO의 지원을 받아 이해관계자에게 정보를 전달해야 한다. PMO는 모든 이해관계자 그룹에 걸쳐 일관되고 투명한 커뮤니케이션을 보장하는 지침, 지원, 조정을 제공한다. 리스크 문서화 및 수용(A)은 문제를 숨긴다. 이해관계자와 상의 없이 해결책 제안(B)은 그들의 의견을 우회한다. 농민 피드백 수집 후 내부 보관(D)은 투명성이 부족하다.
198 | During a project status meeting with senior managers, the project manager gives an update about the status of a deliverable. Some of the senior managers claim not to know about the deliverable. What should the project manager do next? | Meet with these stakeholders to review the project charter. | Check if these stakeholders attend regular project meetings. | Validate if the project charter changed from the original one. | Review the project charter to validate this claim. |  | A | When senior managers claim not to know about a deliverable mentioned in a status meeting, the project manager should meet with these stakeholders to review the project charter. The charter contains information on key deliverables and objectives, addressing the communication gap. Checking if stakeholders attend regular meetings (B) identifies the gap but does not resolve it. Validating if the charter changed (C) assumes the charter was modified. Reviewing the charter alone (D) does not engage the stakeholders. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 프로젝트 상태 회의에서 고위 관리자들에게 인도물 상태를 업데이트하던 중, 프로젝트 관리자가 인도물에 대해 업데이트한다. 일부 고위 관리자들은 해당 인도물에 대해 몰랐다고 주장한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 이들 이해관계자와 만나 프로젝트 헌장을 검토한다 | 이들 이해관계자가 정기 프로젝트 회의에 참석하는지 확인한다 | 프로젝트 헌장이 원래 것에서 변경되었는지 확인한다 | 프로젝트 헌장을 검토하여 이 주장을 확인한다 |  | A | 고위 관리자들이 상태 회의에서 언급된 인도물에 대해 몰랐다고 주장할 때, 프로젝트 관리자는 이들 이해관계자와 만나 프로젝트 헌장을 검토해야 한다. 헌장에는 주요 인도물과 목표에 대한 정보가 포함되어 있어 커뮤니케이션 격차를 해결한다. 회의 참석 여부 확인(B)은 격차를 식별하지만 해결하지 않는다. 헌장 변경 여부 확인(C)은 헌장이 수정되었다고 가정한다. 헌장만 검토(D)는 이해관계자를 참여시키지 않는다.
199 | A project manager has been assigned to a project where the budget is very tight. Incurring extra costs is not an option. What should the project manager do to manage this situation? | Ask the project resources to finish their assignments in less time than originally planned. | Ask the accounting department to forward all project expenses to the project manager ' s email. | Monitor the budget for the project continually and anticipate any issues if possible. | File a change request to make the customer billable for all extra costs incurred for the project. |  | C | With a very tight budget where extra costs are not an option, the project manager should monitor the budget continually and anticipate issues proactively. Continuous monitoring enables early identification of potential overruns, allowing the PM to take corrective action before problems escalate. Asking resources to finish faster (A) may compromise quality and is unsustainable. Having the accounting department forward expenses (B) provides data but does not constitute active management. Filing a change request to make the customer billable (D) may not be contractually possible and does not address budget management. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 관리자가 예산이 매우 빠듯한 프로젝트에 배정되었다. 추가 비용 발생은 옵션이 아니다. 프로젝트 관리자는 이 상황을 관리하기 위해 무엇을 해야 하는가? | 프로젝트 자원에게 원래 계획보다 더 적은 시간 내에 작업을 마치도록 요청한다 | 회계 부서에 모든 프로젝트 비용을 프로젝트 관리자 이메일로 전달하도록 요청한다 | 프로젝트 예산을 지속적으로 모니터링하고 가능한 이슈를 예측한다 | 모든 추가 비용을 고객 부담으로 하는 변경 요청을 제출한다 |  | C | 예산이 매우 빠듯하고 추가 비용이 옵션이 아닐 때, 프로젝트 관리자는 예산을 지속적으로 모니터링하고 이슈를 사전에 예측해야 한다. 지속적 모니터링은 잘재적 초과를 조기에 식별하여 문제가 확대되기 전에 시정 조치를 취할 수 있게 한다. 자원에게 더 빠른 완료 요청(A)은 품질을 손상시키며 지속 불가능하다. 회계 부서에 비용 전달 요청(B)은 데이터를 제공하지만 적극적 관리가 아니다. 고객 부담 변경 요청 제출(D)은 계약상 불가능할 수 있으며 예산 관리를 다루지 않는다.
200 | As a member of an organizational change management team, a project manager must pass on any changes to the project team. The project manager needs to avoid any misunderstandings or resistance to help ensure that the project team will support any organizational change. What should the project manager do? | Conduct meetings with resistant members to facilitate smooth project implementation | Meet with the team on a regular basis to ensure they are aware of changes. | Influence the team to communicate any changes | Check with the |  | B | As a member of the organizational change management team needing to pass changes to the project team while avoiding misunderstandings, the project manager should meet with the team regularly to ensure they are aware of changes. Regular communication builds understanding and reduces resistance. Meeting only with resistant members (A) is selective. Influencing the team to communicate changes (C) delegates the PM's responsibility. The incomplete option (D) provides no actionable guidance. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 조직 변경 관리 팀의 일원으로서, 프로젝트 관리자는 모든 변경 사항을 프로젝트 팀에 전달해야 한다. 프로젝트 관리자는 프로젝트 팀이 조직 변경을 지원하도록 보장하기 위해 오해나 저항을 피해야 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 저항하는 팀원들과 회의를 진행하여 원활한 프로젝트 실행을 촉진한다 | 팀과 정기적으로 만나 변경 사항을 인지하도록 보장한다 | 팀이 변경 사항을 전달하도록 영향력을 행사한다 |  |  | B | 조직 변경 관리 팀의 일원으로서 변경을 프로젝트 팀에 전달하면서 오해를 피해야 할 때, 프로젝트 관리자는 팀과 정기적으로 만나 변경 사항을 인지하도록 보장해야 한다. 정기적 커뮤니케이션은 이해를 높이고 저항을 줄인다. 저항하는 팀원만 만나기(A)는 선택적이다. 팀이 변경을 전달하도록 영향력 행사(C)는 PM의 책임을 위임한다. 불완전한 옵션(D)은 실행 가능한 지침을 제공하지 않는다.
201 | A project manager has been transferred to another country to work on a key project. The project manager successfully completed the planning phase and has started the execution phase, reporting good progress. During the last meeting with the project sponsor, the project manager was told that some stakeholders have complained that the project manager's emails are very harsh. What should the project manager do to solve this situation? | Adjust the communications management plan to gain stakeholder trust. | Explain 1c the sponsor that the communication model being used is from company headquarters. | Change the communication mode from emails to meetings to reduce stakeholders complaints. | Determine the level of influence of the stakeholders who are complaining. |  | A | When stakeholders in a new country complain about harsh emails, the project manager should adjust the communications management plan to gain stakeholder trust. Adapting communication style to cultural context is essential. Explaining the communication model is from headquarters (B) does not address the issue. Switching from emails to meetings (C) changes the medium without understanding the root cause. Determining stakeholder influence (D) is analytical, not corrective. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Hybrid/Tailoring | 프로젝트 관리자가 핵심 프로젝트를 수행하기 위해 다른 나라로 전근했다. 프로젝트 관리자는 계획 단계를 성공적으로 완료하고 실행 단계를 시작하여 좋은 진행을 보고하고 있다. 프로젝트 스폰서와의 마지막 회의에서, 프로젝트 관리자는 일부 이해관계자가 프로젝트 관리자의 이메일이 매우 강압적이라고 불평했다는 말을 들었다. 프로젝트 관리자는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 이해관계자 신뢰를 얻기 위해 커뮤니케이션 관리 계획을 조정한다 | 스폰서에게 사용 중인 커뮤니케이션 모델이 회사 본사의 것이라고 설명한다 | 커뮤니케이션 방식을 이메일에서 회의로 변경하여 이해관계자 불평을 줄인다 | 불평하는 이해관계자의 영향력 수준을 파악한다 |  | A | 새 나라의 이해관계자가 강압적인 이메일에 대해 불평할 때, 프로젝트 관리자는 이해관계자 신뢰를 얻기 위해 커뮤니케이션 관리 계획을 조정해야 한다. 문화적 맥락에 맞아 커뮤니케이션 스타일을 적응하는 것이 필수적이다. 본사의 커뮤니케이션 모델 설명(B)은 문제를 다루지 않는다. 이메일에서 회의로 변경(C)은 근본 원인을 이해하지 않고 매체를 변경한다. 이해관계자 영향력 파악(D)은 분석적이지 시정 조치가 아니다.
202 | During the execution phase of a healthcare IT project, the project manager finds one stakeholder is very difficult to communicate with and obtain feedback from on project deliverables. What should the project manager do? | Update the stakeholder engagement plan for the stakeholder. | Ask the project sponsor to arrange a meeting with the stakeholder. | Use networking skills to approach the stakeholder. | Share a template with the stakeholder to receive feedback on deliverables. |  | A | When a healthcare IT stakeholder is difficult to communicate with and obtain feedback from, the project manager should update the stakeholder engagement plan for that stakeholder. Tailoring the engagement approach improves interaction. Asking the sponsor to arrange a meeting (B) delegates the responsibility. Using networking skills (C) is informal. Sharing a feedback template (D) provides a tool but does not address the engagement strategy. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 의료 IT 프로젝트 실행 단계에서, 프로젝트 관리자는 한 이해관계자와 의사소통하고 프로젝트 인도물에 대한 피드백을 얻는 것이 매우 어렵다는 것을 알게 된다. 프로젝트 관리자는 어떻게 해야 하는가? | 해당 이해관계자에 대한 이해관계자 참여 계획을 업데이트한다 | 프로젝트 스폰서에게 이해관계자와의 회의를 주선하도록 요청한다 | 네트워킹 기술을 사용하여 이해관계자에게 접근한다 | 이해관계자와 템플릿을 공유하여 인도물에 대한 피드백을 받는다 |  | A | 의료 IT 이해관계자와 의사소통하고 피드백을 얻기 어려울 때, 프로젝트 관리자는 해당 이해관계자에 대한 이해관계자 참여 계획을 업데이트해야 한다. 참여 접근방식을 맞춤화하면 상호작용이 개선된다. 스폰서에게 회의 주선 요청(B)은 책임을 위임한다. 네트워킹 기술 사용(C)은 비공식적이다. 피드백 템플릿 공유(D)는 도구를 제공하지만 참여 전략을 다루지 않는다.
203 | A project manager holds periodic progress review meetings to discuss issues. What should the project manager do first on the agenda? | Produce lessons learned documentation. | Elaborate the risk mitigation strategy and risk register. | Update resolution approaches and action assignments. | Formulate project management plan integration. |  | C | In periodic progress review meetings, the project manager should first update resolution approaches and action assignments on the agenda. Starting with action items ensures accountability and drives progress. Producing lessons learned (A) is for project closure. Elaborating risk mitigation (B) is one agenda item but not the first. Formulating project management plan integration (D) is not a meeting agenda item. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트 관리자가 이슈를 논의하기 위해 정기적인 진행 검토 회의를 개최한다. 프로젝트 관리자는 안건에서 먼저 무엇을 해야 하는가? | 교훈 문서를 작성한다 | 리스크 완화 전략과 리스크 등록부를 상세히 설명한다 | 해결 접근법과 조치 할당을 업데이트한다 | 프로젝트 관리 계획 통합을 수립한다 |  | C | 정기적인 진행 검토 회의에서, 프로젝트 관리자는 안건에서 먼저 해결 접근법과 조치 할당을 업데이트해야 한다. 조치 항목으로 시작하면 책임감을 보장하고 진전을 이끌다. 교훈 작성(A)은 프로젝트 종료 시 해당된다. 리스크 완화 상세 설명(B)은 하나의 안건 항목이지만 첨 번째 항목이 아니다. 프로젝트 관리 계획 통합 수립(D)은 회의 안건 항목이 아니다.
204 | A project manager is leading a new agile project. The requirements for the first sprint have been defined and the work is about to start. What should the project manager do next? | Ask the team to self-organize and manage the work assigned. | Assign the tasks to the resources based on their expertise. | Ensure that the priority of each task is clear to the team. | Tell the team which task to focus on at the next daily standup. |  | A | When sprint requirements are defined and work is about to start in an agile project, the project manager should ask the team to self-organize and manage the assigned work. Self-organization is a core agile principle where the team decides how to plan and execute the sprint. Assigning tasks based on expertise (B) imposes direction. Ensuring task priority is clear (C) is helpful but secondary. Directing the team at daily standups (D) undermines self-organization. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 프로젝트 관리자가 새로운 애자일 프로젝트를 이끌고 있다. 첫 번째 스프린트의 요구사항이 정의되었고 작업이 곧 시작될 예정이다. 프로젝트 관리자가 다음에 해야 할 일은? | 팀에게 자기 조직화하여 배정된 작업을 관리하도록 요청한다. | 전문성에 따라 자원에게 작업을 배정한다. | 각 작업의 우선순위를 팀에게 명확히 한다. | 다음 일일 스탠드업에서 어떤 작업에 집중할지 팀에게 지시한다. |  | A | 애자일 프로젝트에서 스프린트 요구사항이 정의되고 작업이 시작되려 할 때, 프로젝트 관리자는 팀에게 자기 조직화하여 배정된 작업을 관리하도록 요청해야 한다. 자기 조직화는 팀이 스프린트를 어떻게 계획하고 실행할지 결정하는 핵심 애자일 원칙이다. 전문성에 따른 작업 배정(B)은 지시적이다. 작업 우선순위 명확화(C)는 도움이 되지만 부차적이다. 일일 스탠드업에서 지시(D)는 자기 조직화를 저해한다.
205 | A project manager receives feedback from the customer's leadership team regarding their annoyance about the frequency of email updates. What should the project manager have done first to prevent this? | Understood the customer ' s company culture | Analyzed customer interest and engagement | Updated the communications management plan | Scheduled weekly update meetings |  | A | When a customer's leadership team is annoyed by the frequency of email updates, the project manager should first have understood the customer's company culture. Company culture determines communication preferences, frequency expectations, and tone—enabling the PM to tailor their approach appropriately from the start. Analyzing interest and engagement (B) is useful but follows cultural understanding. Updating the communications plan (C) is a corrective action, not the first preventive step. Scheduling weekly meetings (D) assumes a specific method without understanding preferences. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Hybrid/Tailoring | 프로젝트 관리자가 고객 리더십 팀으로부터 이메일 업데이트 빈도에 대한 불만 피드백을 받았다. 이를 방지하기 위해 프로젝트 관리자가 먼저 했어야 할 일은? | 고객 회사의 문화를 이해한다. | 고객의 관심도와 참여도를 분석한다. | 커뮤니케이션 관리 계획을 업데이트한다. | 주간 업데이트 회의를 예약한다. |  | A | 고객 리더십 팀이 이메일 업데이트 빈도에 불만일 때, 프로젝트 관리자는 먼저 고객 회사의 문화를 이해했어야 한다. 회사 문화는 커뮤니케이션 선호도, 빈도 기대치, 톤을 결정하여 PM이 처음부터 적절히 접근할 수 있게 한다. 관심도/참여도 분석(B)은 유용하지만 문화 이해 후에 온다. 커뮤니케이션 계획 업데이트(C)는 시정 조치이지 예방이 아니다. 주간 회의 예약(D)은 선호도 이해 없이 특정 방법을 가정한다.
206 | A risk was identified at the beginning of a project, and a response plan was established. Unforeseen consequences resulted in a higher level of risk. The project manager has an idea that could address the new risk in an efficient way, but the response is different from the original risk mitigation plan. What should the project manager do? | Obtain management approval prior to implementing the new risk response. | Use the management reserve to mitigate the risk. | Submit the new response plan to the stakeholders for their review. | Implement the new response to address the risk. |  | A | When unforeseen consequences increase a risk beyond the original mitigation plan and the PM has an efficient new idea, the project manager should obtain management approval prior to implementing the new risk response. Approval ensures governance compliance. Using management reserve (B) addresses funding, not the response plan. Submitting to stakeholders for review (C) is broader than needed. Implementing without approval (D) bypasses governance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 초기에 리스크가 식별되어 대응 계획이 수립되었다. 예상치 못한 결과로 리스크 수준이 더 높아졌다. 프로젝트 관리자가 새로운 리스크를 효율적으로 해결할 수 있는 아이디어가 있지만, 이 대응은 원래 리스크 완화 계획과 다르다. 프로젝트 관리자가 해야 할 일은? | 새로운 리스크 대응을 시행하기 전에 경영진 승인을 받는다. | 관리 예비비를 사용하여 리스크를 완화한다. | 새로운 대응 계획을 이해관계자에게 검토를 위해 제출한다. | 리스크를 해결하기 위해 새로운 대응을 시행한다. |  | A | 예상치 못한 결과로 리스크가 원래 완화 계획을 초과하고 PM이 효율적인 새 아이디어를 가지고 있을 때, 프로젝트 관리자는 새로운 리스크 대응 시행 전에 경영진 승인을 받아야 한다. 승인은 거버넌스 준수를 보장한다. 관리 예비비 사용(B)은 자금 문제이지 대응 계획이 아니다. 이해관계자 검토 제출(C)은 필요 이상으로 광범위하다. 승인 없이 시행(D)은 거버넌스를 우회한다.
207 | A team realizes that there is no access to data that the project depends on to complete the current iteration. This dependency was known; however, the team is unsure of the available options to remove this obstacle. What should the project manager do next? | Guide the team to determine alternatives. | Escalate the issue to the company ' s IT manager. | Escalate the issue to the project sponsor. | Move the dependent task to the next iteration. |  | A | When the team faces a known dependency blocking the current iteration and is unsure of available options, the project manager should guide the team to determine alternatives. Facilitating collaborative problem-solving leverages collective expertise to identify solutions. Escalating to the IT manager (B) may be premature before exploring options. Escalating to the project sponsor (C) is appropriate only if team-level solutions fail. Moving the task to the next iteration (D) accepts the delay without attempting resolution. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | 팀이 현재 이터레이션을 완료하는 데 필요한 데이터에 접근할 수 없음을 알게 되었다. 이 의존성은 알려져 있었지만, 팀은 이 장애물을 제거할 수 있는 옵션이 무엇인지 확신하지 못한다. 프로젝트 관리자가 다음에 해야 할 일은? | 팀이 대안을 결정하도록 안내한다. | 회사 IT 관리자에게 이슈를 상위 보고한다. | 프로젝트 스폰서에게 이슈를 상위 보고한다. | 의존 작업을 다음 이터레이션으로 이동한다. |  | A | 팀이 현재 이터레이션을 차단하는 알려진 의존성에 직면하고 사용 가능한 옵션을 모를 때, 프로젝트 관리자는 팀이 대안을 결정하도록 안내해야 한다. 협력적 문제 해결 촉진은 집단 전문성을 활용하여 해결책을 찾는다. IT 관리자에게 상위 보고(B)는 옵션 탐색 전에는 시기상조이다. 스폰서에게 상위 보고(C)는 팀 수준 해결이 실패한 경우에만 적절하다. 다음 이터레이션으로 이동(D)은 해결 시도 없이 지연을 수용한다.
208 | A project manager is leading a project that is kicking off next month. The project manager realizes that there are many stakeholders that need updates on different aspects of the project at different frequencies. What should the project manager do first to ensure each stakeholder has the information they need? | Develop a communications management plan that reflects the needs of the stakeholder community. | Determine the most appropriate mechanisms to leverage when communications are necessary. | Create a responsible, accountable, consulted, and informed (RACI) chart based on the stakeholders and their communications needs. | Engage with each stakeholder to determine their information needs related to the project. |  | D | When many stakeholders need updates on different aspects at different frequencies, the project manager should first engage with each stakeholder to determine their information needs related to the project. Understanding needs before planning ensures tailored communication. Developing a communications plan (A) comes after gathering information. Determining communication mechanisms (B) is a tactic that follows need identification. Creating a RACI chart (C) defines roles, not communication needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 관리자가 다음 달 시작될 프로젝트를 이끌고 있다. 여러 이해관계자가 프로젝트의 다양한 측면에 대해 서로 다른 빈도로 업데이트가 필요하다는 것을 인식했다. 각 이해관계자가 필요한 정보를 갖도록 프로젝트 관리자가 먼저 해야 할 일은? | 이해관계자 커뮤니티의 요구를 반영한 커뮤니케이션 관리 계획을 개발한다. | 커뮤니케이션이 필요할 때 활용할 가장 적절한 메커니즘을 결정한다. | 이해관계자와 커뮤니케이션 요구에 기반한 RACI 차트를 작성한다. | 각 이해관계자와 소통하여 프로젝트 관련 정보 요구사항을 파악한다. |  | D | 많은 이해관계자가 다양한 측면에 대해 서로 다른 빈도로 업데이트가 필요할 때, 프로젝트 관리자는 먼저 각 이해관계자와 소통하여 프로젝트 관련 정보 요구사항을 파악해야 한다. 계획 전 요구 파악이 맞춤형 커뮤니케이션을 보장한다. 커뮤니케이션 계획 개발(A)은 정보 수집 후에 한다. 커뮤니케이션 메커니즘 결정(B)은 요구 파악 후의 전술이다. RACI 차트 작성(C)은 역할 정의이지 커뮤니케이션 요구가 아니다.
209 | A project manager is assigned to oversee the deployment of a new product that will be used by the entire organization. A key success factor for the project is the timely and successful adoption of the new solution by all entities. What should the project manager do to ensure the success of this critical project? | Given the size of the organization and the multiple parties involved, discuss thelaunch date with the CEO and then communicate it to all entities. | Ask the project sponsor to issue a directive requesting all business entities toaccept the date set for the new solution launch. | Engage in creative and iterative negotiations with the leaders of each entity toagree on the launch date. | Considering the project scope and the multiple entities impacted by the 408 solution,communicate with the stakeholders and ask them to adhere to the date. |  | C | For a project requiring timely adoption across the entire organization, the project manager should engage in creative and iterative negotiations with leaders of each entity to agree on the launch date. Negotiation fosters collaboration, trust, and commitment among all parties, increasing the likelihood of successful adoption. Discussing only with the CEO (A) bypasses entity leaders who must support implementation. Issuing a sponsor directive (B) imposes a date without buy-in. Simply communicating the date and asking for adherence (D) lacks the negotiation needed for genuine commitment. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Schedule | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 전 조직이 사용할 새 제품 배포를 감독하도록 배정되었다. 프로젝트의 핵심 성공 요소는 모든 부서의 적시 및 성공적인 신규 솔루션 채택이다. 이 중요한 프로젝트의 성공을 보장하기 위해 프로젝트 관리자가 해야 할 일은? | 조직 규모와 여러 관계자를 고려하여 CEO와 출시일을 논의한 후 모든 부서에 전달한다. | 프로젝트 스폰서에게 신규 솔루션 출시일 수용을 모든 사업 부서에 지시하도록 요청한다. | 각 부서 리더와 창의적이고 반복적인 협상을 통해 출시일에 합의한다. | 프로젝트 범위와 영향받는 여러 부서를 고려하여 이해관계자와 소통하고 날짜를 준수하도록 요청한다. |  | C | 전 조직의 적시 채택이 필요한 프로젝트에서 프로젝트 관리자는 각 부서 리더와 창의적이고 반복적인 협상을 통해 출시일에 합의해야 한다. 협상은 모든 당사자 간 협력, 신뢰, 헌신을 촉진하여 성공적 채택 가능성을 높인다. CEO와만 논의(A)는 실행을 지원해야 할 부서 리더를 우회한다. 스폰서 지시(B)는 합의 없이 날짜를 강요한다. 단순히 날짜를 전달하고 준수를 요청(D)하는 것은 진정한 헌신에 필요한 협상이 부족하다.
210 | A project manager is leading a council's project that aims to ensure full compliance with health, ecological, and environmental standards. At the same time, the project's goal is to remain fully adherent to the council's values, policies, and procedures. How should the project manager ensure project success? | Develop the necessary implementation plan and ask the partners to adjust their plans to meet the project manager ' s objectives. | Meet with the stakeholders regularly to share project objectives and mutually agree on common goals and plans. | Enforce the project manager ' s authority over the contracting partner delivering to the council. by | Engage a third-party consulting firm to oversee the project ' s implementation. |  | B | When leading a council project requiring compliance with health, ecological, and environmental standards while adhering to council values, the project manager should meet with stakeholders regularly to share objectives and mutually agree on common goals and plans. Collaborative alignment ensures shared commitment. Developing implementation plans and asking partners to adjust (A) is one-directional. Enforcing authority over contractors (C) is authoritarian. Engaging a third-party firm (D) adds cost without ensuring alignment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 프로젝트 관리자가 건강, 생태, 환경 기준의 완전한 준수를 보장하는 것을 목표로 하는 의회 프로젝트를 이끌고 있다. 동시에 의회의 가치, 정책, 절차를 완전히 준수해야 한다. 프로젝트 관리자가 프로젝트 성공을 보장하려면 어떻게 해야 하는가? | 필요한 실행 계획을 개발하고 파트너에게 프로젝트 관리자의 목표에 맞게 계획을 조정하도록 요청한다. | 이해관계자와 정기적으로 만나 프로젝트 목표를 공유하고 공통 목표와 계획에 상호 합의한다. | 의회에 납품하는 계약 파트너에 대해 프로젝트 관리자의 권한을 행사한다. | 프로젝트 실행을 감독할 제3자 컨설팅 회사를 고용한다. |  | B | 건강, 생태, 환경 기준 준수와 의회 가치 준수가 필요한 의회 프로젝트를 이끌 때, 프로젝트 관리자는 이해관계자와 정기적으로 만나 목표를 공유하고 공통 목표와 계획에 상호 합의해야 한다. 협력적 정렬은 공유된 헌신을 보장한다. 실행 계획을 개발하고 파트너에게 조정 요청(A)은 일방적이다. 계약업체에 대한 권한 행사(C)는 권위주의적이다. 제3자 컨설팅 고용(D)은 정렬 보장 없이 비용만 추가한다.
211 | Many issues have been encountered in a project due to the low competence of the team members. These issues might lead to poor project performance and potentially to project termination. What should the project manager do? | Escalate the issue with the human resource (HR) department to take action, | Invest in coaching and training for all project team members. | Advise the project team on the importance of team engagement, | Organize a brainstorming session with the project team to address the issue. |  | B | When team members' low competence causes issues that may lead to project termination, the project manager should invest in coaching and training for all team members. Building capability addresses the root cause and improves long-term performance. Escalating to HR (A) is punitive. Advising on the importance of engagement (C) is motivational but does not build skills. Organizing a brainstorming session (D) does not address competence gaps. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀원들의 낮은 역량으로 인해 프로젝트에서 많은 이슈가 발생했다. 이러한 이슈는 프로젝트 성과 저하와 잠재적으로 프로젝트 종료로 이어질 수 있다. 프로젝트 관리자가 해야 할 일은? | 인사(HR) 부서에 조치를 취하도록 이슈를 상위 보고한다. | 모든 프로젝트 팀원에 대한 코칭과 교육에 투자한다. | 프로젝트 팀에 팀 참여의 중요성에 대해 조언한다. | 프로젝트 팀과 이슈 해결을 위한 브레인스토밍 세션을 조직한다. |  | B | 팀원의 낮은 역량이 프로젝트 종료로 이어질 수 있는 이슈를 유발할 때, 프로젝트 관리자는 모든 팀원에 대한 코칭과 교육에 투자해야 한다. 역량 구축은 근본 원인을 해결하고 장기 성과를 개선한다. HR에 상위 보고(A)는 징벌적이다. 참여 중요성 조언(C)은 동기 부여이지만 기술을 구축하지 않는다. 브레인스토밍 세션(D)은 역량 격차를 해결하지 않는다.
212 | A project manager has been assigned to an important agile project. During project execution, a vendor was approved to produce the project deliverables. What should the project manager do to ensure project continuity between the vendor and the team? | Submit a change request to extend the vendor ' s contract to provide formal training for the team | Conduct daily knowledge transfer standups to ensure that the team is properly trained | Implement retrospectives with the vendor to gather the required knowledge | Request that the vendor provides a manual with all required knowledge |  | C | When a vendor is approved to produce deliverables on an agile project, the project manager should implement retrospectives with the vendor to gather required knowledge and ensure project continuity. Retrospectives facilitate knowledge transfer, collaboration, and alignment. Submitting a change request for vendor training (A) is formal but slow. Daily knowledge transfer standups (B) may be excessive. Requesting a manual from the vendor (D) is passive and one-directional. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 중요한 애자일 프로젝트에 배정되었다. 프로젝트 실행 중 벤더가 프로젝트 인도물을 생산하도록 승인되었다. 벤더와 팀 간 프로젝트 연속성을 보장하기 위해 프로젝트 관리자가 해야 할 일은? | 벤더 계약을 연장하여 팀에 공식 교육을 제공하도록 변경 요청을 제출한다. | 팀이 적절히 교육받도록 일일 지식 이전 스탠드업을 실시한다. | 벤더와 회고를 시행하여 필요한 지식을 수집한다. | 벤더에게 필요한 모든 지식이 담긴 매뉴얼을 제공하도록 요청한다. |  | C | 애자일 프로젝트에서 벤더가 인도물 생산을 승인받았을 때, 프로젝트 관리자는 벤더와 회고를 시행하여 필요한 지식을 수집하고 프로젝트 연속성을 보장해야 한다. 회고는 지식 이전, 협력, 정렬을 촉진한다. 벤더 교육을 위한 변경 요청(A)은 공식적이지만 느리다. 일일 지식 이전 스탠드업(B)은 과도할 수 있다. 벤더에게 매뉴얼 요청(D)은 수동적이고 일방적이다.
213 | A company started a project to create a new product that will be delivered in iterations. The artwork development plan included extensive consultation and validation before the build. The company changed the focus of the project to speed to market because one of their competitors announced the launch of a similar product. What should the project lead do? | Work with the product owner to assess the impact and reprioritize the product backlog. | Schedule a meeting with the project sponsor to identify and allocate additional resources. | Submit a formal change request and obtain approval from the change control board (CCB). | Meet with the Scrum Master to determine if the development cycle can be reduced. |  | A | When a competitor announces a similar product launch and the company shifts focus to speed to market, the project lead should work with the product owner to assess the impact and reprioritize the product backlog. Backlog reprioritization is the fastest lever in iterative delivery to accelerate value delivery. Scheduling a meeting to allocate additional resources (B) increases cost without guaranteeing speed. Submitting a formal change request (C) is too slow for the urgency. Reducing the development cycle (D) requires prioritization first. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 회사가 이터레이션으로 인도될 새 제품 프로젝트를 시작했다. 아트워크 개발 계획에는 빌드 전 광범위한 협의와 검증이 포함되어 있었다. 경쟁사가 유사 제품 출시를 발표하여 회사가 시장 출시 속도에 초점을 변경했다. 프로젝트 리더가 해야 할 일은? | 제품 소유자와 협력하여 영향을 평가하고 제품 백로그의 우선순위를 재조정한다. | 프로젝트 스폰서와 회의를 잡아 추가 자원을 식별하고 배정한다. | 공식 변경 요청을 제출하고 CCB의 승인을 받는다. | 스크럼 마스터와 만나 개발 주기를 단축할 수 있는지 결정한다. |  | A | 경쟁사가 유사 제품 출시를 발표하고 회사가 시장 출시 속도로 초점을 전환할 때, 프로젝트 리더는 제품 소유자와 협력하여 영향을 평가하고 제품 백로그의 우선순위를 재조정해야 한다. 반복 인도에서 백로그 우선순위 재조정은 가치 인도를 가속화하는 가장 빠른 수단이다. 추가 자원 배정 회의(B)는 속도 보장 없이 비용을 증가시킨다. 공식 변경 요청(C)은 긴급성에 비해 너무 느리다. 개발 주기 단축(D)은 우선순위 조정이 먼저 필요하다.
214 | It is taking several additional iterations for a project team to complete planned backlog items. The project manager notices that some of the features are not meeting the iteration-level definition and must be placed back into the backlog. What should the project manager do? | Extend the iterations to complete the items. | Review and update the acceptance criteria. | Address the required changes in the next release. | Put more emphasis on the definition of done (DoD). |  | D | When features repeatedly fail to meet iteration-level completion standards and are returned to the backlog, the root cause is likely an inconsistent application of the definition of done (DoD). The project manager should put more emphasis on the DoD to ensure all team members build and validate work against the agreed completion criteria before considering items finished. Extending iterations (A) weakens agile cadence and does not address the root cause. Reviewing acceptance criteria (B) may help but is narrower than the comprehensive DoD. Addressing changes in the next release (C) only delays correction and allows the same problem to continue. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Embed Quality | Determine Budget | Traditional PM | 여러 추가 이터레이션을 거쳐도 프로젝트 팀이 계획된 백로그 항목을 완료하지 못하고 있다. 프로젝트 관리자는 일부 기능이 이터레이션 수준 정의를 충족하지 못해 백로그에 다시 넣어야 함을 인지했다. 프로젝트 관리자가 해야 할 일은? | 이터레이션을 연장하여 항목을 완료한다. | 인수 기준을 검토하고 업데이트한다. | 필요한 변경사항을 다음 릴리스에서 처리한다. | DoD(완료 정의)에 더 중점을 둔다. |  | D | 기능이 반복적으로 이터레이션 수준 완료 기준을 충족하지 못하고 백로그로 반환될 때, 근본 원인은 DoD(완료 정의)의 일관되지 않은 적용일 가능성이 높다. 프로젝트 관리자는 DoD에 더 중점을 두어 모든 팀원이 합의된 완료 기준에 따라 작업을 구축하고 검증하도록 해야 한다. 이터레이션 연장(A)은 애자일 주기를 약화시키고 근본 원인을 해결하지 못한다. 인수 기준 검토(B)는 도움이 되지만 포괄적인 DoD보다 범위가 좁다. 다음 릴리스에서 변경 처리(C)는 수정을 지연시키고 동일한 문제가 계속되게 한다.
215 | A project manager is managing a project to deploy new software to 200 end users. During the implementation, there is a missed process that caused some of the users to lose their computer data. What should the project manager do first? | Meet with the team to discuss the root cause and encourage the team to take note of it and continue to focus on the deployment. | Record this case until the final lessons learned session is complete to prevent impacting the team ' s morale during implementation. | Meet with the team members and request they conduct a review of the case by providing feedback as lessons learned. | Invite a consultant to review the process in order not to repeat the same issue and share the results with the team. |  | D | When a missed process during software deployment causes users to lose data, the project manager should first invite a consultant to review the process and share results with the team. Expert assessment identifies the root cause quickly and prevents recurrence. Meeting the team to discuss root cause and continue (A) may not provide sufficient expertise. Recording the case until final lessons learned (B) delays action. Meeting team members for lessons learned feedback (C) is helpful but less immediate than expert review. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 200명의 최종 사용자에게 새 소프트웨어를 배포하는 프로젝트를 관리하고 있다. 구현 중 누락된 프로세스로 인해 일부 사용자의 컴퓨터 데이터가 손실되었다. 프로젝트 관리자가 먼저 해야 할 일은? | 팀과 만나 근본 원인을 논의하고 이를 기록한 후 배포에 계속 집중하도록 독려한다. | 구현 중 팀 사기에 영향을 주지 않기 위해 최종 교훈 세션이 완료될 때까지 이 사례를 기록해 둔다. | 팀원들과 만나 교훈으로서 사례 검토 피드백을 제공하도록 요청한다. | 동일한 문제가 반복되지 않도록 컨설턴트를 초빙하여 프로세스를 검토하고 결과를 팀과 공유한다. |  | D | 소프트웨어 배포 중 누락된 프로세스로 사용자 데이터가 손실되었을 때, 프로젝트 관리자는 먼저 컨설턴트를 초빙하여 프로세스를 검토하고 결과를 팀과 공유해야 한다. 전문가 평가는 근본 원인을 신속히 파악하고 재발을 방지한다. 팀과 근본 원인 논의 후 계속 진행(A)은 충분한 전문성을 제공하지 못할 수 있다. 최종 교훈까지 기록 보류(B)는 조치를 지연시킨다. 팀원에게 교훈 피드백 요청(C)은 도움이 되지만 전문가 검토보다 즉각적이지 않다.
216 | A research and development team is finishing up a two-year initiative. The project manager is focused on the closing activities for the project. Which activity should be considered as a priority? | Release the resources and plan for a project completion celebration. | Ensure that knowledge transfer activities are executed as planned | Hold a steering committee meeting to inform them of the project completion | Mark the product backlog completion status and update the communications management plan. |  | B | When closing a two-year research and development initiative, the priority activity should be ensuring knowledge transfer activities are executed as planned. Knowledge transfer preserves lessons learned, best practices, and institutional knowledge for organizational benefit. Releasing resources and celebrating (A) follows knowledge transfer. Holding a steering committee meeting (C) can occur after knowledge transfer. Updating the product backlog and communications plan (D) belongs to monitoring and controlling. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 연구개발 팀이 2년간의 이니셔티브를 마무리하고 있다. 프로젝트 관리자가 프로젝트 종료 활동에 집중하고 있다. 우선순위로 고려해야 할 활동은? | 자원을 해제하고 프로젝트 완료 축하 행사를 계획한다. | 계획대로 지식 이전 활동이 실행되도록 보장한다. | 운영위원회 회의를 개최하여 프로젝트 완료를 알린다. | 제품 백로그 완료 상태를 표시하고 커뮤니케이션 관리 계획을 업데이트한다. |  | B | 2년간의 연구개발 이니셔티브를 종료할 때, 우선 활동은 계획대로 지식 이전 활동이 실행되도록 보장하는 것이다. 지식 이전은 교훈, 모범 사례, 조직 지식을 보존한다. 자원 해제와 축하(A)는 지식 이전 후에 한다. 운영위원회 회의(C)는 지식 이전 후에 할 수 있다. 백로그 완료 상태 업데이트와 커뮤니케이션 계획 업데이트(D)는 모니터링 및 통제에 해당한다.
217 | A stakeholder on a project has a reputation for being easily angered and unreasonably difficult on projects. The project manager would like to minimize the impact of the stakeholder's behavior on the development team. What training should the project manager choose for their team to help with this situation? | Negotiation training | Communication training | Agile training. | Emotional intelligence training |  | D | When dealing with a stakeholder known for being easily angered and difficult, the project manager should choose emotional intelligence training for the team. EI training builds skills in self-awareness, empathy, self-regulation, and managing difficult interpersonal dynamics—directly addressing the challenge. Negotiation training (A) focuses on deal-making. Communication training (B) is broader than needed. Agile training (C) focuses on methodology, not interpersonal skills. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트의 이해관계자가 쉽게 화를 내고 프로젝트에서 불합리하게 어렵기로 유명하다. 프로젝트 관리자가 이 이해관계자의 행동이 개발 팀에 미치는 영향을 최소화하고 싶다. 이 상황에 도움이 되도록 팀에 어떤 교육을 선택해야 하는가? | 협상 교육 | 커뮤니케이션 교육 | 애자일 교육 | 감성 지능 교육 |  | D | 쉽게 화를 내고 어려운 이해관계자를 다룰 때, 프로젝트 관리자는 팀에 감성 지능 교육을 선택해야 한다. 감성 지능 교육은 자기 인식, 공감, 자기 조절, 어려운 대인 역학 관리 기술을 구축하여 과제에 직접 대응한다. 협상 교육(A)은 거래 체결에 초점을 맞춘다. 커뮤니케이션 교육(B)은 필요 이상으로 광범위하다. 애자일 교육(C)은 방법론에 초점을 맞추지 대인 기술이 아니다.
218 | A project manager was informed by their supplier that there will be an upcoming raw material shortage due to a regulatory change. What should the project manager do? | Seek advice from the legal department and implement penalties. | Tell the supplier that they have an obligation to supply the raw material. | Search for a new supplier that can deliver the same materials on time. | Assess the possible impact of the raw material shortage on the project. |  | D | When a supplier notifies of an upcoming raw material shortage due to regulatory change, the project manager should assess the possible impact on the project. Impact assessment enables informed response planning. Seeking legal advice (A) is premature. Telling the supplier they have an obligation (B) may not resolve the shortage. Searching for a new supplier (C) acts without understanding the impact first. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 프로젝트 관리자가 공급업체로부터 규제 변경으로 인한 원자재 부족이 예상된다는 통보를 받았다. 프로젝트 관리자가 해야 할 일은? | 법무 부서에 자문을 구하고 페널티를 시행한다. | 공급업체에게 원자재 공급 의무가 있음을 알린다. | 동일한 자재를 정시에 납품할 수 있는 새 공급업체를 찾는다. | 원자재 부족이 프로젝트에 미칠 수 있는 영향을 평가한다. |  | D | 공급업체가 규제 변경으로 인한 원자재 부족을 통보했을 때, 프로젝트 관리자는 프로젝트에 미칠 수 있는 영향을 평가해야 한다. 영향 평가는 정보에 기반한 대응 계획을 가능하게 한다. 법적 자문 구하기(A)는 시기상조이다. 공급 의무 알리기(B)는 부족을 해결하지 못할 수 있다. 새 공급업체 찾기(C)는 영향 이해 없이 행동하는 것이다.
219 | A subcontracting company is presenting its feature release. A key stakeholder is asking to add a new feature to the product. How should the project manager deal with the new requirement? | Engage an arbitrator to resolve any conflict while handling the new requirement | Add the change to the next sprint to meet the customer ' s needs | Allocate resources to work on the new feature immediately to complete the request | Follow the change management process and work with procurement if needed |  | D | When a key stakeholder requests a new feature during a subcontractor's release presentation, the project manager should follow the change management process and work with procurement if needed. Formal change control ensures proper evaluation and contractual alignment. Engaging an arbitrator (A) is for disputes, not change requests. Adding the change to the next sprint (B) bypasses change control. Allocating resources immediately (C) disrupts the project plan. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 하도급 회사가 기능 릴리스를 발표하고 있다. 핵심 이해관계자가 제품에 새 기능을 추가해 달라고 요청하고 있다. 프로젝트 관리자가 새 요구사항을 어떻게 처리해야 하는가? | 새 요구사항 처리 시 갈등 해결을 위해 중재자를 참여시킨다. | 고객 요구를 충족하기 위해 다음 스프린트에 변경사항을 추가한다. | 요청을 완료하기 위해 즉시 새 기능 작업에 자원을 배정한다. | 변경 관리 프로세스를 따르고 필요시 조달과 협력한다. |  | D | 하도급업체의 릴리스 발표 중 핵심 이해관계자가 새 기능을 요청할 때, 프로젝트 관리자는 변경 관리 프로세스를 따르고 필요시 조달과 협력해야 한다. 공식 변경 통제는 적절한 평가와 계약적 정렬을 보장한다. 중재자 참여(A)는 분쟁용이지 변경 요청이 아니다. 다음 스프린트에 추가(B)는 변경 통제를 우회한다. 즉시 자원 배정(C)은 프로젝트 계획을 방해한다.
220 | A project manager is managing a project with team members who are working all over the globe. The project manager notices that each team member's deliverables do not meet the requirements. What should the project manager do first? | Discuss the process used to create the noncompliant deliverables with the project team to see if there was a potential misunderstanding. | Assemble the project team via conference call to tell them that disciplinary action will be taken if any more noncompliant deliverables aresubmitted. | Schedule time with the project sponsor to inform them that the project schedule is slipping due to the time it will take to rework thedeliverables. | Meet with the project team to explain that noncompliant deliverables must be reworked and submitted immediately to avoid project delays. |  | A | When team members across the globe are producing noncompliant deliverables, the project manager should first discuss the process used to create those deliverables with the project team to identify potential misunderstandings. Understanding the root cause—whether it is a communication gap, unclear requirements, or process confusion—is essential before taking corrective action. Threatening disciplinary action (B) is counterproductive without understanding the issue. Informing the sponsor about schedule slippage (C) is premature. Demanding immediate rework (D) does not address the underlying cause. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 전 세계에서 일하는 팀원들과 프로젝트를 관리하고 있다. 각 팀원의 인도물이 요구사항을 충족하지 못하는 것을 인지했다. 프로젝트 관리자가 먼저 해야 할 일은? | 부적합한 인도물을 만든 프로세스에 대해 프로젝트 팀과 논의하여 잠재적 오해가 있었는지 확인한다. | 부적합한 인도물이 더 제출되면 징계 조치를 취할 것이라고 화상 회의로 팀에 알린다. | 프로젝트 스폰서에게 인도물 재작업에 소요될 시간으로 인해 일정이 지연되고 있음을 알린다. | 프로젝트 팀과 만나 부적합한 인도물을 즉시 재작업하여 제출해야 프로젝트 지연을 방지할 수 있음을 설명한다. |  | A | 전 세계 팀원들이 부적합한 인도물을 생산할 때, 프로젝트 관리자는 먼저 그 인도물을 만든 프로세스에 대해 팀과 논의하여 잠재적 오해를 파악해야 한다. 근본 원인 이해—커뮤니케이션 격차, 불명확한 요구사항, 프로세스 혼란 여부—는 시정 조치 전에 필수이다. 징계 위협(B)은 문제 이해 없이 역효과를 낸다. 스폰서에게 일정 지연 통보(C)는 시기상조이다. 즉각 재작업 요구(D)는 근본 원인을 해결하지 못한다.
221 | An organization uses a predictive approach but is open to using some agile practices. The project manager was asked to recommend an agile practice to provide business value throughout the project. What should the project manager recommend? | Incremental delivery and frequent backlog refinement based on user feedback | Frequent retrospectives to ensure that lessons learned and improvement actions are implemented | Time-boxed iterations to allow the testing team to thoroughly test the product increments | Iterative development and collection of frequent feedback from project team members |  | A | When an organization using a predictive approach wants to adopt an agile practice for delivering business value throughout the project, the project manager should recommend incremental delivery and frequent backlog refinement based on user feedback. Incremental delivery provides ongoing value with feedback-driven prioritization. Frequent retrospectives (B) focus on process improvement, not direct value delivery. Time-boxed iterations for testing (C) support quality, not business value delivery. Iterative development with team feedback (D) lacks the customer focus. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | 조직이 예측형 접근법을 사용하지만 일부 애자일 실무를 도입할 의향이 있다. 프로젝트 관리자가 프로젝트 전반에 걸쳐 비즈니스 가치를 제공하는 애자일 실무를 추천해 달라는 요청을 받았다. 프로젝트 관리자가 추천해야 할 것은? | 사용자 피드백에 기반한 점진적 인도와 빈번한 백로그 정제 | 교훈과 개선 조치가 시행되도록 빈번한 회고 | 테스트 팀이 제품 증분을 철저히 테스트할 수 있도록 타임박스 이터레이션 | 반복 개발과 프로젝트 팀원들로부터의 빈번한 피드백 수집 |  | A | 예측형 접근법 조직이 비즈니스 가치를 제공하는 애자일 실무를 도입하고자 할 때, 프로젝트 관리자는 사용자 피드백에 기반한 점진적 인도와 빈번한 백로그 정제를 추천해야 한다. 점진적 인도는 피드백 기반 우선순위화와 함께 지속적 가치를 제공한다. 빈번한 회고(B)는 프로세스 개선에 초점이지 직접적 가치 제공이 아니다. 테스트를 위한 타임박스 이터레이션(C)은 품질 지원이지 비즈니스 가치 제공이 아니다. 팀 피드백 기반 반복 개발(D)은 고객 초점이 부족하다.
222 | A subject matter expert (SME) external to the project team provides a suggestion that will save the project delivery time. This SME has available time to support the project, but was not planned to be involved in the current agile iteration. What should the project manager do? | Ask the existing team members to collaborate with the SME and complete the activity. | Direct the team member to ignore the SME ' s changes as they were not planned. | Ask the SME to complete all of the necessary changes, which will save time. | Bring the SME on board immediately and discuss the implications later. |  | A | When an external SME offers a time-saving suggestion and has available capacity, the project manager should ask existing team members to collaborate with the SME and complete the activity. Leveraging available expertise through collaboration aligns with agile principles. Directing the team to ignore the suggestion (B) wastes an opportunity. Asking the SME to complete all changes alone (C) bypasses team ownership. Bringing the SME on board immediately without discussion (D) skips impact assessment. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀 외부의 SME(주제 전문가)가 프로젝트 인도 시간을 절약할 수 있는 제안을 했다. 이 SME는 프로젝트를 지원할 시간이 있지만 현재 애자일 이터레이션에 참여 계획이 없었다. 프로젝트 관리자가 해야 할 일은? | 기존 팀원에게 SME와 협력하여 활동을 완료하도록 요청한다. | SME의 변경사항은 계획되지 않았으므로 무시하도록 팀원에게 지시한다. | SME에게 시간을 절약할 수 있는 모든 필요한 변경을 완료하도록 요청한다. | SME를 즉시 참여시키고 영향은 나중에 논의한다. |  | A | 외부 SME가 시간 절약 제안을 하고 가용 역량이 있을 때, 프로젝트 관리자는 기존 팀원에게 SME와 협력하여 활동을 완료하도록 요청해야 한다. 협력을 통한 가용 전문성 활용은 애자일 원칙에 부합한다. 제안 무시 지시(B)는 기회를 낭비한다. SME에게 모든 변경 완료 요청(C)은 팀 소유권을 우회한다. 논의 없이 즉시 참여(D)는 영향 평가를 건너뛴다.
223 | A new team member joins the project and fails to follow the project-specific quality assurance (QA) processes. What should the project manager have done to prevent this issue? | Made sure that the new team member understood all of the requirements. | Delegated the quality assurance (QA) tasks to the team lead. | Obtained external training in quality assurance (QA) for the new team member. | Ensured that the new team member had access to the quality management plan. |  | D | When a new team member fails to follow project-specific QA processes, the root preventive measure is ensuring they had access to the quality management plan and project documentation before beginning work. Access to the governing plan is the most direct and foundational control. Delegating QA (A) doesn't ensure understanding of the process. External training (C) is excessive unless a broader skills gap exists. A general requirements overview (D) is too broad—the specific failure here concerns QA procedures. Making sure the team has clear access to correct plans, processes, and standards before work begins is the best preventive action. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 새 팀원이 프로젝트에 합류했으나 프로젝트 특정 품질보증(QA) 프로세스를 따르지 않았다. 이 문제를 예방하기 위해 프로젝트 관리자가 했어야 할 일은? | 새 팀원이 모든 요구사항을 이해하도록 했어야 한다. | QA 작업을 팀 리더에게 위임했어야 한다. | 새 팀원에게 외부 QA 교육을 받도록 했어야 한다. | 새 팀원이 품질 관리 계획에 접근할 수 있도록 보장했어야 한다. |  | D | 새 팀원이 프로젝트 특정 QA 프로세스를 따르지 않았을 때, 근본적 예방 조치는 작업 시작 전에 품질 관리 계획과 프로젝트 문서에 접근할 수 있도록 보장하는 것이다. 관리 계획에 대한 접근은 가장 직접적이고 근본적인 통제이다. QA 위임(B)은 프로세스 이해를 보장하지 않는다. 외부 교육(C)은 광범위한 기술 격차가 아닌 한 과도하다. 일반적 요구사항 개요(A)는 너무 광범위하다—여기서 구체적 실패는 QA 절차에 관한 것이다.
224 | A project manager is managing the scope of the project and creating a work breakdown structure (WBS) with the team members. How should the project manager organize the WBS? | Deliverable oriented | Customer oriented | Cost oriented | Team oriented |  | A | The project manager should organize the WBS in a deliverable-oriented way. A deliverable-oriented WBS decomposes the project scope into outputs, products, or results, enabling clear scope definition and management. Customer-oriented (B) structures by stakeholder groups. Cost-oriented (C) structures by budget accounts. Team-oriented (D) structures by roles. None of these alternatives properly decompose scope. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 팀원들과 함께 프로젝트 범위를 관리하고 WBS(작업분류체계)를 작성하고 있다. 프로젝트 관리자가 WBS를 어떻게 구성해야 하는가? | 인도물 중심 | 고객 중심 | 비용 중심 | 팀 중심 |  | A | 프로젝트 관리자는 WBS를 인도물 중심으로 구성해야 한다. 인도물 중심 WBS는 프로젝트 범위를 산출물, 제품, 결과로 분해하여 명확한 범위 정의 및 관리를 가능하게 한다. 고객 중심(B)은 이해관계자 그룹별 구조이다. 비용 중심(C)은 예산 계정별 구조이다. 팀 중심(D)은 역할별 구조이다. 이러한 대안들은 범위를 적절히 분해하지 못한다.
225 | A project manager is working on a global project and realizes that one team member is not performing as expected. The project manager meets with the team member to find out what is causing this low performance. The project manager discovers the team member is experiencing conflict and feels uncomfortable with the team. The team member then asks to be moved to another project. What should the project manager do? | Confront the issue with the rest of the team directly. | Ask other team members to be more welcoming. | Request human resources (HR) to help. | Move the team member to another project. |  | C | The correct answer is C. Request human resources (HR) to help. Effective leadership involves understanding team dynamics, addressing root causes, and creating a supportive environment. The PM should foster collaboration and well-being to maintain high performance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 글로벌 프로젝트를 진행하던 중 한 팀원이 기대에 미치지 못하는 성과를 보이고 있음을 알게 되었다. 팀원과 만나 낮은 성과의 원인을 알아본 결과, 팀원이 갈등을 겪고 있으며 팀에서 불편하다고 느끼고 있었다. 팀원은 다른 프로젝트로 이동을 요청했다. 프로젝트 관리자가 해야 할 일은? | 나머지 팀과 직접 이슈를 대면한다. | 다른 팀원에게 더 환영하도록 요청한다. | 인사(HR) 부서에 도움을 요청한다. | 팀원을 다른 프로젝트로 이동시킨다. |  | C | 정답은 C이다. 인사(HR) 부서에 도움을 요청한다. 효과적인 리더십은 팀 역학을 이해하고 근본 원인을 해결하며 지원적인 환경을 조성하는 것을 포함한다. PM은 높은 성과를 유지하기 위해 협력과 팀원 복지를 촉진해야 한다.
226 | A project just kicked off and management's expectation is to ensure that the deliverable of the first iteration helps the marketing team present the product prototype to potential customers. What should the project manager do? | Ask the sponsor to prioritize some functionalities of the product. | Split the backlog into phases to ensure that the key features are delivered first | Increase the details of the work breakdown structure (WBS) to minimize errors and delays . | Identify the minimum functionality required for the product |  | D | The PM should identify the minimum functionality required for the product—the minimum viable product (MVP). An MVP delivers enough features to satisfy early customers and generate feedback for future development. By collaborating with the sponsor, marketing team, and customers to understand core needs, the PM can focus the first iteration on the features that provide the most value. This approach reduces scope, cost, and time while maximizing quality and customer satisfaction. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Build an Empowered Culture | Plan Scope Management | Traditional PM | 프로젝트가 막 시작되었고 경영진의 기대는 첫 번째 이터레이션의 인도물이 마케팅 팀이 잠재 고객에게 제품 프로토타입을 발표하는 데 도움이 되는 것이다. 프로젝트 관리자가 해야 할 일은? | 스폰서에게 제품의 일부 기능에 우선순위를 매기도록 요청한다. | 핵심 기능이 먼저 인도되도록 백로그를 단계로 나눈다. | WBS의 세부 사항을 늘려 오류와 지연을 최소화한다. | 제품에 필요한 최소 기능을 식별한다. |  | D | PM은 제품에 필요한 최소 기능—최소기능제품(MVP)—을 식별해야 한다. MVP는 초기 고객을 만족시키고 향후 개발을 위한 피드백을 생성하기에 충분한 기능을 제공한다. 스폰서, 마케팅 팀, 고객과 협력하여 핵심 요구를 이해함으로써, PM은 첫 이터레이션을 가장 큰 가치를 제공하는 기능에 집중할 수 있다. 이 접근법은 범위, 비용, 시간을 줄이면서 품질과 고객 만족도를 극대화한다.
227 | During the execution phase of a project, all project team members were forced to work from their homes rather than in person. During this time, the project manager discovered that one team member has made disrespectful remarks about another team member to other team members. How should the project manager handle this situation? | Discuss the issue with the steering committee to determine the proper course of action. | Coordinate a video conference with the offending team member to resolve the issue | Instruct the team members involved to resolve the issue among themselves | Reassign the offending team member to a different project |  | B | When a team member makes disrespectful remarks about another team member while working remotely, the project manager should coordinate a video conference with the offending team member to resolve the issue directly. Direct, professional confrontation addresses the behavior. Discussing with the steering committee (A) escalates unnecessarily. Instructing them to resolve it themselves (C) abdicates responsibility. Reassigning the offender (D) avoids the issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 단계에서 모든 프로젝트 팀원이 대면 대신 재택근무를 하게 되었다. 이 기간 동안 프로젝트 관리자는 한 팀원이 다른 팀원에 대해 무례한 발언을 한 것을 발견했다. 프로젝트 관리자가 이 상황을 어떻게 처리해야 하는가? | 운영위원회와 이슈를 논의하여 적절한 조치 방침을 결정한다. | 문제의 팀원과 화상 회의를 조율하여 이슈를 해결한다. | 관련 팀원에게 자체적으로 이슈를 해결하도록 지시한다. | 문제의 팀원을 다른 프로젝트로 재배치한다. |  | B | 팀원이 원격 근무 중 다른 팀원에 대해 무례한 발언을 했을 때, 프로젝트 관리자는 문제의 팀원과 화상 회의를 조율하여 이슈를 직접 해결해야 한다. 직접적이고 전문적인 대면은 행동을 해결한다. 운영위원회와 논의(A)는 불필요하게 상위 보고한다. 자체 해결 지시(C)는 책임을 회피한다. 재배치(D)는 문제를 회피한다.
228 | During project execution of a new IT solution, the testing of one feature was unsuccessful. The go-live milestone is now impacted due to this delay. Extensive analyses were performed, and there is no way to resolve the defects before the go-live date. What should the project manager do next? | Improve the control quality process by implementing additional testing to minimize the defects before the go-live milestone. | Include additional mitigation actions against feature defects and update the risk management plan. | Assess the relevance of the feature and then analyze the submission of a change request to descope it. | Determine if business value will be delivered without this feature. and try to fix the defects after the go- live milestone. |  | D | When testing reveals unfixable feature defects before the go-live milestone, the project manager should determine if business value can be delivered without this feature and try to fix defects after go-live. Value-driven decision-making preserves the milestone. Improving the quality process (A) does not resolve the current defects. Including additional mitigation actions (B) does not change the timeline. Assessing relevance and descoping (C) is possible but less thorough than value assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 프로젝트 실행 중 새 IT 솔루션의 한 기능 테스트가 실패했다. 가동 마일스톤이 이 지연으로 영향을 받았다. 광범위한 분석이 수행되었으나 가동일 전에 결함을 해결할 방법이 없다. 프로젝트 관리자가 다음에 해야 할 일은? | 가동 마일스톤 전에 결함을 최소화하기 위해 추가 테스트를 구현하여 품질 통제 프로세스를 개선한다. | 기능 결함에 대한 추가 완화 조치를 포함하고 리스크 관리 계획을 업데이트한다. | 기능의 관련성을 평가한 후 범위에서 제외하는 변경 요청 제출을 분석한다. | 이 기능 없이 비즈니스 가치가 제공될 수 있는지 판단하고 가동 후 결함 수정을 시도한다. |  | D | 테스트에서 가동 마일스톤 전에 수정할 수 없는 기능 결함이 발견되었을 때, 프로젝트 관리자는 이 기능 없이 비즈니스 가치가 제공될 수 있는지 판단하고 가동 후 결함 수정을 시도해야 한다. 가치 중심 의사결정은 마일스톤을 보존한다. 품질 프로세스 개선(A)은 현재 결함을 해결하지 못한다. 추가 완화 조치 포함(B)은 일정을 변경하지 못한다. 관련성 평가 후 범위 제외(C)는 가능하지만 가치 평가보다 덜 철저하다.
229 | During iteration two of a project with two teams (A and B), the project manager is concerned that there are two critical activities from team A that must be started in iteration four. Additionally, these two activities are dependent on an activity from team B that has not yet been prioritized. What should the project manager do? | Include the dependent activity in the current iteration for team B. | Cancel the current iteration and reschedule it with the dependent activity. | Ensure team B prioritizes the dependent activity in iteration three. | Assign the two critical activities to team B in iteration two. |  | A | When team A has critical activities in iteration four dependent on an unprioritized team B activity, the project manager should ensure team B prioritizes the dependent activity in iteration three. This aligns the inter-team dependency timeline so team A can proceed as planned. Including the dependency in the current iteration (A) may disrupt team B's current work. Canceling and rescheduling the iteration (B) is excessive. Assigning team A's activities to team B (D) changes scope ownership inappropriately. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 두 팀(A와 B)이 있는 프로젝트의 이터레이션 2 중, 프로젝트 관리자는 이터레이션 4에서 시작해야 하는 팀 A의 두 가지 중요 활동이 있음을 우려하고 있다. 또한 이 두 활동은 아직 우선순위가 지정되지 않은 팀 B의 활동에 의존한다. 프로젝트 관리자가 해야 할 일은? | 팀 B의 현재 이터레이션에 의존 활동을 포함시킨다. | 현재 이터레이션을 취소하고 의존 활동을 포함하여 재일정한다. | 팀 B가 이터레이션 3에서 의존 활동의 우선순위를 지정하도록 보장한다. | 이터레이션 2에서 팀 A의 두 가지 중요 활동을 팀 B에 할당한다. |  | A | 팀 A가 이터레이션 4에서 팀 B의 우선순위 미지정 활동에 의존하는 중요 활동이 있을 때, 프로젝트 관리자는 팀 B가 이터레이션 3에서 의존 활동의 우선순위를 지정하도록 보장해야 한다. 이는 팀 A가 계획대로 진행할 수 있도록 팀 간 의존성 일정을 정렬한다. 현재 이터레이션에 포함(A)은 팀 B의 현재 작업을 방해할 수 있다. 이터레이션 취소 및 재일정(B)은 과도하다. 팀 A 활동을 팀 B에 할당(D)은 범위 소유권을 부적절하게 변경한다.
230 | The product owner decides to launch a product after a couple of releases knowing that the minimum viable product (MVP) lacks some features. One of the key stakeholders, the marketing vice president, is not happy with the results and questioned the release decision. What should the project manager do? | Escalate the issue to the sponsor questioning the authority of the key stakeholder regarding the product launch decision | Assume the responsibility for product releases making the final call on when something is ready for customer launch | Coach the team on the decision-making process, assuming a risk-averse strategy towards product releasing | Support the product owner ' s decision and seek better alignment with this stakeholder in order to avoid this type of issue in the future |  | D | When the marketing VP questions the product owner's decision to launch an MVP lacking some features, the project manager should support the product owner's decision and seek better alignment with the stakeholder for future releases. Respecting PO authority while managing stakeholder relationships is key. Escalating to the sponsor (A) undermines the PO. Assuming release responsibility (B) oversteps the PM's role. Coaching on risk-averse strategy (C) overrides PO judgment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 제품 소유자가 MVP(최소기능제품)에 일부 기능이 부족하다는 것을 알면서도 몇 차례 릴리스 후 제품을 출시하기로 결정했다. 핵심 이해관계자인 마케팅 부사장이 결과에 불만이며 출시 결정에 의문을 제기했다. 프로젝트 관리자가 해야 할 일은? | 스폰서에게 핵심 이해관계자의 제품 출시 결정 권한에 대해 의문을 제기하며 상위 보고한다. | 고객 출시 준비가 완료된 시점에 대한 최종 결정을 내려 제품 릴리스에 대한 책임을 맡는다. | 제품 릴리스에 대해 리스크 회피 전략을 취하는 의사결정 프로세스를 팀에 코칭한다. | 제품 소유자의 결정을 지지하고 향후 이러한 문제를 피하기 위해 이 이해관계자와 더 나은 정렬을 모색한다. |  | D | 마케팅 부사장이 제품 소유자의 MVP 출시 결정에 의문을 제기할 때, 프로젝트 관리자는 제품 소유자의 결정을 지지하고 향후 릴리스를 위해 이 이해관계자와 더 나은 정렬을 모색해야 한다. 제품 소유자 권한을 존중하면서 이해관계자 관계를 관리하는 것이 핵심이다. 스폰서에게 상위 보고(A)는 제품 소유자를 약화시킨다. 릴리스 책임 떠맡기(B)는 PM 역할을 초과한다. 리스크 회피 전략 코칭(C)은 제품 소유자 판단을 재정의한다.
231 | During the execution phase of a project, a new project manager is assigned to replace the previous project manager. As the project manager starts managing the project, they discover that team performance is significantly decreasing, which is impacting the project's key performance indicators (KPIs). This team has delivered good performance on similar projects in the past. What should the project manager do next to improve this situation? | Implement compression techniques to bring the project back on track. | Estimate the baseline impacts and submit a change request. | Review the resource management plan and organizational assets | Call for a team meeting to identify the root cause for the declining performance |  | D | When team performance is significantly decreasing and the team has a track record of good performance on similar projects, the project manager should call a team meeting to identify the root cause of declining performance. Understanding why a previously successful team is struggling enables targeted corrective action. Implementing compression techniques (A) addresses schedule, not performance causes. Estimating baseline impacts and submitting a change request (B) is process-oriented. Reviewing the resource management plan (C) is analytical but does not engage the team. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 단계에서 새 프로젝트 관리자가 이전 프로젝트 관리자를 대체하도록 배정되었다. 프로젝트를 관리하기 시작하면서 팀 성과가 크게 떨어져 프로젝트 KPI에 영향을 미치고 있음을 발견했다. 이 팀은 과거 유사 프로젝트에서 좋은 성과를 보여주었다. 이 상황을 개선하기 위해 프로젝트 관리자가 다음에 해야 할 일은? | 프로젝트를 정상 궤도에 다시 올리기 위해 압축 기법을 구현한다. | 베이스라인 영향을 추정하고 변경 요청을 제출한다. | 자원 관리 계획과 조직 자산을 검토한다. | 팀 회의를 소집하여 성과 저하의 근본 원인을 파악한다. |  | D | 팀 성과가 크게 떨어지고 팀이 유사 프로젝트에서 좋은 성과 이력이 있을 때, 프로젝트 관리자는 팀 회의를 소집하여 성과 저하의 근본 원인을 파악해야 한다. 이전에 성공적이었던 팀이 어려움을 겪는 이유를 이해하면 목표 지향적 시정 조치가 가능하다. 압축 기법(A)은 일정 문제를 해결하지만 성과 원인을 해결하지 못한다. 베이스라인 영향 추정 및 변경 요청(B)은 프로세스 중심이다. 자원 관리 계획 검토(C)는 분석적이지만 팀을 참여시키지 않는다.
232 | A project has a very tight delivery schedule. The project is approaching the delivery date and the project sponsor often sends the project manager alerts to avoid any schedule slippage. The project team has performed at an acceptable level until now, but the project manager wants to ensure the team's performance level is maintained until the end. What action should the project manager take to motivate the project team's performance? | Inform the team about the delivery pressure from the project sponsor | Award certificates of appreciation to encourage the team | Hire a few temporary team members to help with the additional work | Send a formal notice to team members instructing them to maintain performance |  | B | When the sponsor pressures to avoid schedule slippage and the project manager wants to maintain team performance, awarding certificates of appreciation encourages continued effort. Recognition motivates through positive reinforcement. Informing the team of sponsor pressure (A) increases stress. Hiring temporary members (C) adds complexity. Sending formal performance notices (D) implies distrust. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트의 인도 일정이 매우 빡빡하다. 프로젝트 스폰서가 일정 지연을 피하도록 프로젝트 관리자에게 자주 경고를 보내고 있다. 팀은 지금까지 수용 가능한 수준으로 성과를 내왔지만, 프로젝트 관리자는 팀의 성과 수준을 끝까지 유지하고 싶다. 프로젝트 팀의 성과를 동기 부여하기 위해 프로젝트 관리자가 취해야 할 조치는? | 프로젝트 스폰서의 인도 압력에 대해 팀에 알린다. | 팀을 격려하기 위해 감사장을 수여한다. | 추가 작업을 돕기 위해 임시 팀원을 몇 명 고용한다. | 팀원에게 성과 유지를 지시하는 공식 통지를 보낸다. |  | B | 스폰서가 일정 지연 방지를 압박하고 프로젝트 관리자가 팀 성과를 유지하고 싶을 때, 감사장 수여는 지속적인 노력을 격려한다. 인정은 긍정적 강화를 통해 동기를 부여한다. 스폰서 압력 전달(A)은 스트레스를 증가시킨다. 임시 인력 고용(C)은 복잡성을 추가한다. 공식 성과 통지(D)는 불신을 암시한다.
233 | A project team has experienced deliverable delays in the last few iterations. During the retrospective, the team realizes that the quality issues identified are because the quality process is outdated. Who should the project manager ask to update the process? | Quality lead | Project management office (PMO) | Product owner | Project team |  | A | The quality lead should update the outdated quality process. In agile, retrospectives are key ceremonies for continuous improvement—they provide the forum for identifying process issues and driving corrective action. Other options either bypass agile practices or fail to address the root cause of the quality problems effectively. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 최근 몇 차례 이터레이션에서 인도물 지연을 경험했다. 회고 중 팀은 식별된 품질 문제가 품질 프로세스가 구식이기 때문임을 인식했다. 프로젝트 관리자는 누구에게 프로세스 업데이트를 요청해야 하는가? | 품질 리드 | PMO | 제품 소유자 | 프로젝트 팀 |  | A | 품질 리드가 구식인 품질 프로세스를 업데이트해야 한다. 애자일에서 회고는 지속적 개선을 위한 핵심 의식이며, 프로세스 문제를 식별하고 시정 조치를 추진하는 장을 제공한다. 다른 옵션들은 애자일 실무를 우회하거나 품질 문제의 근본 원인을 효과적으로 해결하지 못한다.
234 | A project team is trying to meet the milestone target dates in order to receive a bonus promised by the project sponsor. Unforeseen challenges and poor communication among the team members resulted in mistakes and delays. Tensions are high, and the sponsor is concerned. What should the project manager do? | Request that the sponsor increase the bonus for high performers. | Organize a team meeting to remind the team of the ground rules. | Discuss with the team how the project objectives can be met. | Schedule a team-building activity to boost the team ' s morale. |  | C | When a team chasing a bonus milestone faces mistakes, delays, and high tensions from unforeseen challenges and poor communication, the project manager should discuss with the team how project objectives can be met. Refocusing on objectives through collaborative discussion addresses root causes. Increasing the bonus (A) does not fix communication. Reminding of ground rules (B) is corrective but not constructive. Team-building activities (D) boost morale but do not address delivery. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 팀이 마일스톤 목표 날짜를 맞추어 프로젝트 스폰서가 약속한 보너스를 받으려고 한다. 예상치 못한 도전과 팀원 간 저조한 커뮤니케이션으로 실수와 지연이 발생했다. 긴장감이 높고 스폰서가 우려하고 있다. 프로젝트 관리자가 해야 할 일은? | 스폰서에게 우수 성과자를 위한 보너스 인상을 요청한다. | 팀에게 기본 규칙을 상기시키기 위한 팀 회의를 조직한다. | 팀과 프로젝트 목표를 어떻게 달성할 수 있는지 논의한다. | 팀 사기를 높이기 위한 팀 빌딩 활동을 계획한다. |  | C | 보너스 마일스톤을 쪳는 팀이 예상치 못한 도전, 저조한 커뮤니케이션으로 실수, 지연, 높은 긴장감에 직면할 때, 프로젝트 관리자는 팀과 프로젝트 목표 달성 방법을 논의해야 한다. 협력적 논의를 통해 목표에 재초점하면 근본 원인을 해결한다. 보너스 인상(A)은 커뮤니케이션 문제를 해결하지 못한다. 기본 규칙 상기(B)는 시정적이지만 건설적이지 않다. 팀 빌딩 활동(D)은 사기를 높이지만 인도를 해결하지 않는다.
235 | After an executive-level reorganization, the new project sponsor is not keen on continuing with the project. What should the project manager do? | Request the previous sponsor to discuss changes with the project team. | Ask management to replace the new sponsor with the previous sponsor. | Find ways to bypass the new sponsor and reach management for support. | Explore ways to share the project vision and outcome with the new sponsor. |  | D | When a new project sponsor is not keen on continuing the project after executive reorganization, the project manager should explore ways to share the project vision and outcome with the new sponsor. Demonstrating strategic value builds sponsor commitment. Requesting the previous sponsor to discuss changes (A) bypasses the new authority. Asking management to replace the sponsor (B) is unrealistic. Finding ways to bypass the sponsor (C) is inappropriate. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Stakeholder & Communication Mgmt | Business Environment | Define and Establish Governance | Risk | Monitoring & Controlling | Be an Accountable Leader | Monitor Risks | Traditional PM | 경영진 수준 조직 개편 후 새 프로젝트 스폰서가 프로젝트 진행에 적극적이지 않다. 프로젝트 관리자가 해야 할 일은? | 이전 스폰서에게 프로젝트 팀과 변경사항을 논의하도록 요청한다. | 경영진에게 새 스폰서를 이전 스폰서로 교체해 달라고 요청한다. | 새 스폰서를 우회하여 경영진의 지원을 받을 방법을 찾는다. | 새 스폰서와 프로젝트 비전과 성과를 공유할 방법을 모색한다. |  | D | 조직 개편 후 새 프로젝트 스폰서가 프로젝트 진행에 적극적이지 않을 때, 프로젝트 관리자는 새 스폰서와 프로젝트 비전과 성과를 공유할 방법을 모색해야 한다. 전략적 가치를 보여주면 스폰서의 헌신을 구축한다. 이전 스폰서에게 변경 논의 요청(A)은 새 권한을 우회한다. 스폰서 교체 요청(B)은 비현실적이다. 스폰서 우회(C)는 부적절하다.
236 | A project team is prioritizing the creation of project artifacts and enforcing it rigidly, while they face issues with delays in deliverables. How should the project manager respond? | Implement stricter controls so that project artifact creation is given the utmost importance. | Advise the team that solely focusing on artifacts will not produce successful project deliverables. | Facilitate the implementation of an automated tool for the team to manage project artifacts. | Recognize the team ' s efforts for documenting artifacts and motivate them with an incentive mechanism. |  | B | When a project team rigidly prioritizes artifact creation while facing delivery delays, the project manager should advise the team that solely focusing on artifacts will not produce successful project deliverables. Artifacts support project management but are not substitutes for actual deliverables—the team needs to balance both. Implementing stricter artifact controls (A) worsens the problem. Facilitating an automated tool (C) streamlines artifact management but does not address the priority imbalance. Recognizing artifact efforts with incentives (D) reinforces the wrong behavior. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 프로젝트 팀이 프로젝트 산출물 생성을 우선시하고 엄격하게 시행하면서 인도물 지연 문제에 직면하고 있다. 프로젝트 관리자가 어떻게 대응해야 하는가? | 프로젝트 산출물 생성이 최고 중요도로 부여되도록 더 엄격한 통제를 시행한다. | 산출물에만 집중하는 것은 성공적인 프로젝트 인도물을 만들지 못한다고 팀에 조언한다. | 팀이 프로젝트 산출물을 관리할 자동화 도구를 구현한다. | 산출물 문서화를 위한 팀의 노력을 인정하고 인센티브 메커니즘으로 동기를 부여한다. |  | B | 프로젝트 팀이 산출물 생성을 엄격하게 우선시하면서 인도물 지연에 직면할 때, 프로젝트 관리자는 산출물에만 집중하는 것은 성공적인 프로젝트 인도물을 만들지 못한다고 조언해야 한다. 산출물은 프로젝트 관리를 지원하지만 실제 인도물을 대체하지 않으며—팀은 둘 다 균형 있게 다루어야 한다. 더 엄격한 산출물 통제(A)는 문제를 악화시킨다. 자동화 도구(C)는 산출물 관리를 간소화하지만 우선순위 불균형을 해결하지 못한다. 산출물 노력에 인센티브(D)는 잘못된 행동을 강화한다.
237 | In a hybrid project, 100 new base stations are being added to a 4G mobile network every month. At the end of the first month, the team is behind the target and the operator is losing money. The stakeholders are requesting information on when the base stations can go live and begin to bill. What should the project manager do to get the schedule back on track and accelerate the return on investment (ROI) of the project? | Increase reporting to the business. | Reconsider necessary schedule reserves. | Clarify the agile and predictive modules. | Change the project approach to predictive. |  | B | The PM should reconsider schedule reserves based on progress and performance of each project module. Schedule reserves account for unforeseen risks and delays, calculated from the project's uncertainty and complexity levels. In hybrid projects using both agile and predictive approaches, reassessing reserves helps identify the critical path, prioritize work, and adjust the schedule to recover timeline and accelerate return on investment. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Hybrid/Tailoring | 하이브리드 프로젝트에서 매달 100개의 새 기지국이 4G 모바일 네트워크에 추가되고 있다. 첫 달 말에 팀이 목표에 미치지 못하고 있으며 운영자는 돈을 잃고 있다. 이해관계자들이 기지국이 언제 가동되어 요금 부과를 시작할 수 있는지 정보를 요청하고 있다. 프로젝트 관리자가 일정을 정상화하고 ROI를 가속화하기 위해 해야 할 일은? | 사업부에 대한 보고를 강화한다. | 필요한 일정 예비를 재고려한다. | 애자일 및 예측형 모듈을 명확히 한다. | 프로젝트 접근법을 예측형으로 변경한다. |  | B | PM은 각 프로젝트 모듈의 진행과 성과에 기반하여 일정 예비를 재고려해야 한다. 일정 예비는 예상치 못한 리스크와 지연을 고려하며, 프로젝트의 불확실성과 복잡성 수준에서 산출된다. 애자일과 예측형 접근법을 모두 사용하는 하이브리드 프로젝트에서 예비 재평가는 주공정선을 식별하고 작업 우선순위를 정하고 일정을 조정하여 타임라인을 회복하고 ROI를 가속화하는 데 도움이 된다.
238 | A project manager for a software development company faces a number of financial risks in their project. The project manager needs to frequently check the strength and efficiency of the risk management process. What should the project manager use to accomplish this? | Stakeholder register | Brainstorming session | Assumption log | Audit meeting |  | D | Audit meetings provide a systematic, independent, and documented evaluation of risk management process effectiveness. They assess whether risk management criteria are being met, identify improvement areas, and ensure the process remains robust and adaptable. Regular audits are essential for maintaining the strength and relevance of risk management practices as project conditions evolve. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 소프트웨어 개발 회사의 프로젝트 관리자가 프로젝트에서 여러 재무 리스크에 직면하고 있다. 프로젝트 관리자는 리스크 관리 프로세스의 강도와 효율성을 자주 확인해야 한다. 이를 위해 프로젝트 관리자가 사용해야 할 것은? | 이해관계자 등록부 | 브레인스토밍 세션 | 가정 로그 | 감사 회의 |  | D | 감사 회의는 리스크 관리 프로세스 효과성에 대한 체계적이고 독립적이며 문서화된 평가를 제공한다. 리스크 관리 기준이 충족되고 있는지 평가하고, 개선 영역을 식별하며, 프로세스가 견고하고 적응력 있게 유지되도록 보장한다. 정기적 감사는 프로젝트 조건이 변화함에 따라 리스크 관리 실무의 강도와 적절성을 유지하는 데 필수적이다.
239 | While managing a project, the project manager has just noticed that the last several monthly invoices have been challenged by the client when they were clearly defined. The actual invoice payments received have also been late and were outside of the contracted payment schedule. Recent invoices have only been partially paid. What should the project manager do? | Hold a meeting with the client to address the issue | Conduct a meeting with the project team to update the procurement management plan | Review past projects for payment-related lessons learned | Add nonpayment to the issue log and keep tracking payments |  | A | When a client consistently challenges and delays payments outside the contracted schedule, the project manager should hold a meeting with the client to address the issue. Direct communication identifies root causes and negotiates resolution. Conducting a team meeting to update the procurement plan (B) does not involve the client. Adding to the issue log (D) is passive tracking. Reviewing past lessons learned (C) may provide context but does not resolve the current issue. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 프로젝트를 관리하던 중, 프로젝트 관리자는 최근 몇 개월간의 월간 송장이 명확히 정의되었음에도 고객으로부터 이의를 받았음을 발견했다. 실제 송장 지급도 지연되어 계약된 지급 일정을 벗어났다. 최근 송장은 부분적으로만 지급되었다. 프로젝트 관리자가 해야 할 일은? | 고객과 회의를 개최하여 이슈를 해결한다. | 조달 관리 계획을 업데이트하기 위해 프로젝트 팀과 회의를 진행한다. | 과거 프로젝트에서 지급 관련 교훈을 검토한다. | 미지급을 이슈 로그에 추가하고 지급을 계속 추적한다. |  | A | 고객이 지속적으로 송장에 이의를 제기하고 계약된 일정 외로 지급을 지연할 때, 프로젝트 관리자는 고객과 회의를 개최하여 이슈를 해결해야 한다. 직접 소통은 근본 원인을 파악하고 해결을 협상한다. 조달 계획 업데이트 팀 회의(B)는 고객을 참여시키지 않는다. 이슈 로그 추가(D)는 수동적 추적이다. 과거 교훈 검토(C)는 맥락을 제공하지만 현재 이슈를 해결하지 못한다.
240 | A senior project manager has included a junior project manager as part of the project team. During a coaching session, the junior project manager asks the senior project manager how to be efficient and reduce rework. How should the senior project manager respond? | Monitor resource allocation to ensure that team members work 8 hours per day. | Use a work breakdown structure (WBS) to create a project schedule based on the project and resource requirements. | Assign project tasks to the team regardless of their skills to accomplish the project schedule. | Schedule daily meetings with key stakeholders to assess the effectiveness of the project management plan. |  | B | The senior project manager should advise using a work breakdown structure (WBS) to create a project schedule based on project and resource requirements. The WBS is a hierarchical decomposition of project scope into manageable components, enabling more accurate planning, scheduling, and resource allocation. By breaking work into smaller, well-defined pieces, the team reduces the risk of rework caused by oversight or miscommunication. Monitoring resource allocation for 8-hour days (A) focuses on utilization, not efficiency or rework prevention. Assigning tasks regardless of skills (C) increases rework risk. Scheduling daily stakeholder meetings (D) adds overhead without directly addressing the root cause of rework. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | WBS/Decomposition | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 시니어 프로젝트 관리자가 주니어 프로젝트 관리자를 프로젝트 팀에 포함시켰다. 코칭 세션 중 주니어 프로젝트 관리자가 시니어 프로젝트 관리자에게 효율성을 높이고 재작업을 줄이는 방법을 물었다. 시니어 프로젝트 관리자가 어떻게 답해야 하는가? | 팀원이 하루 8시간 작업하도록 자원 배정을 모니터링한다. | WBS를 사용하여 프로젝트 및 자원 요구사항에 기반한 프로젝트 일정을 작성한다. | 기술에 관계없이 팀에게 프로젝트 작업을 할당하여 일정을 맞춘다. | 프로젝트 관리 계획의 효과성을 평가하기 위해 핵심 이해관계자와 일일 회의를 예약한다. |  | B | 시니어 프로젝트 관리자는 WBS를 사용하여 프로젝트 및 자원 요구사항에 기반한 프로젝트 일정을 작성하도록 조언해야 한다. WBS는 프로젝트 범위를 관리 가능한 구성 요소로 계층적으로 분해하여 더 정확한 계획, 일정 수립, 자원 배정을 가능하게 한다. 작업을 더 작고 잘 정의된 단위로 나눔으로써 팀은 간과나 의사소통 부족으로 인한 재작업 위험을 줄인다. 8시간 작업 모니터링(A)은 활용도에 초점이지 효율성이나 재작업 방지가 아니다. 기술 무관 작업 할당(C)은 재작업 위험을 높인다. 일일 이해관계자 회의(D)는 재작업의 근본 원인을 직접 해결하지 않고 부담을 추가한다.
241 | An agile team has completed an iteration and delivered the agreed features to the customer. In a surprise to the team, the features are not accepted by the customer. The project team conducts a root cause analysis. What should the project manager do to avoid this situation in the future? | Ensure that the team facilitator allocates tasks correctly to team members. | Ensure that the development and quality assurance team members implement the feature correctly. | Ensure that customer requirements do not change from the start of the project. | Ensure that the definition of done (DoD) is well defined and complete for future iterations. |  | D | When an agile team's completed features are unexpectedly rejected by the customer after root cause analysis, the project manager should ensure the definition of done is well defined and complete for future iterations. A clear DoD aligns delivery with customer expectations. Allocating tasks correctly (A) addresses assignment, not acceptance criteria. Implementing features correctly (B) is execution-focused. Ensuring requirements do not change (C) contradicts agile principles. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 애자일 팀이 이터레이션을 완료하고 합의된 기능을 고객에게 인도했다. 팀에게 놓라운 것은 기능이 고객에게 수락되지 않았다는 것이다. 프로젝트 팀이 근본 원인 분석을 실시한다. 프로젝트 관리자가 향후 이러한 상황을 피하기 위해 해야 할 일은? | 팀 퍼실리테이터가 팀원에게 작업을 올바르게 할당하도록 보장한다. | 개발 및 QA 팀원이 기능을 올바르게 구현하도록 보장한다. | 고객 요구사항이 프로젝트 시작부터 변경되지 않도록 보장한다. | DoD(완료 정의)가 향후 이터레이션을 위해 잘 정의되고 완전하도록 보장한다. |  | D | 애자일 팀의 완료된 기능이 근본 원인 분석 후 고객에게 예상치 않게 거부되었을 때, 프로젝트 관리자는 DoD(완료 정의)가 향후 이터레이션을 위해 잘 정의되고 완전하도록 보장해야 한다. 명확한 DoD는 인도와 고객 기대를 정렬한다. 작업 할당 올바르게 하기(A)는 할당 문제이지 수락 기준이 아니다. 기능 올바르게 구현하기(B)는 실행 중심이다. 요구사항 변경 안 되게 하기(C)는 애자일 원칙에 모순된다.
242 | A software development project completed the initiation phase. The technical design was approved by the project steering committee. Later, it was discovered that the design will impact the company's production system. A new technical design must be found and this could delay the project by 3 months. What should the project manager do first? | Log the technical design delay as a risk in the project risk log. | Continue with the approved design so that the project is not delayed. | Ask the steering committee to approve a new technical design. | Set up a steering committee session to review the project delay. |  | C | When the approved technical design is found to impact the production system and may delay the project 3 months, the project manager should first ask the steering committee to approve a new technical design. Steering committee engagement ensures proper change control for significant design changes. Logging the delay as a risk (A) documents but does not resolve the issue. Continuing with the approved design (B) ignores the production impact. Setting up a review session (D) discusses the delay without proposing a solution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 소프트웨어 개발 프로젝트가 착수 단계를 완료했다. 기술 설계가 프로젝트 운영위원회의 승인을 받았다. 이후 이 설계가 회사의 생산 시스템에 영향을 미칠 것으로 발견되었다. 새로운 기술 설계를 찾아야 하며 이로 인해 프로젝트가 3개월 지연될 수 있다. 프로젝트 관리자가 먼저 해야 할 일은? | 기술 설계 지연을 프로젝트 리스크 로그에 리스크로 기록한다. | 프로젝트가 지연되지 않도록 승인된 설계로 계속 진행한다. | 운영위원회에 새로운 기술 설계를 승인해 달라고 요청한다. | 프로젝트 지연을 검토하기 위한 운영위원회 세션을 구성한다. |  | C | 승인된 기술 설계가 생산 시스템에 영향을 미치고 프로젝트가 3개월 지연될 수 있을 때, 프로젝트 관리자는 먼저 운영위원회에 새로운 기술 설계를 승인해 달라고 요청해야 한다. 운영위원회 참여는 중대한 설계 변경에 대한 적절한 변경 통제를 보장한다. 지연을 리스크로 기록(A)은 문서화하지만 해결하지 못한다. 승인된 설계로 계속 진행(B)은 생산 영향을 무시한다. 지연 검토 세션 구성(D)은 해결책을 제시하지 않고 지연을 논의한다.
243 | During a system demo, a project stakeholder rejects the features completed from the most recent user stories. According to the stakeholder, the product does not meet the quality standards required by regulations. What should the project manager have done to avoid this? | Reviewed with the product owner that all the stories worked on in the iteration were in the project backlog | Reviewed with the product owner that all acceptance criteria were met for the stories worked on in the iteration | Ensured the stakeholder concerns were properly addressed in the iteration to avoid future setbacks | Ensured that the project sponsor understood the scope of the project to avoid any future complaints |  | B | To avoid stakeholder rejection of features due to quality standards not meeting regulations during a system demo, the project manager should have reviewed with the product owner that all acceptance criteria were met for the stories worked on in the iteration. Acceptance criteria define the conditions for user story completion, including regulatory quality standards. Reviewing that stories were in the backlog (A) confirms scope but not quality compliance. Addressing stakeholder concerns in the iteration (C) is reactive. Ensuring the sponsor understood scope (D) does not address quality standards verification. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 시스템 데모 중 프로젝트 이해관계자가 최근 사용자 스토리에서 완료된 기능을 거부했다. 이해관계자에 따르면, 제품이 규정에서 요구하는 품질 표준을 충족하지 못한다. 프로젝트 관리자는 이를 피하기 위해 무엇을 했어야 하는가? | 이터레이션에서 작업한 모든 스토리가 프로젝트 백로그에 있는지 제품 책임자와 검토한다. | 이터레이션에서 작업한 스토리의 모든 인수 기준이 충족되었는지 제품 책임자와 검토한다. | 향후 차질을 피하기 위해 이터레이션에서 이해관계자의 우려가 적절히 다루어졌는지 확인한다. | 향후 불만을 피하기 위해 프로젝트 스폰서가 프로젝트 범위를 이해했는지 확인한다. |  | B | 시스템 데모 중 규정 품질 표준 미충족으로 이해관계자가 기능을 거부하는 것을 피하기 위해, 프로젝트 관리자는 이터레이션에서 작업한 스토리의 모든 인수 기준이 충족되었는지 제품 책임자와 검토했어야 한다. 인수 기준은 규정 품질 표준을 포함하여 사용자 스토리 완료 조건을 정의한다. 스토리가 백로그에 있는지 검토(A)하는 것은 범위를 확인하지만 품질 준수는 아니다. 이터레이션에서 이해관계자 우려 해결(C)은 사후 대응적이다. 스폰서가 범위를 이해했는지 확인(D)하는 것은 품질 표준 검증을 다루지 않는다.
244 | A company is launching a new product that has to be ready before the summer season begins. After the discovery process, the team realizes that the requirements are very uncertain. What should the project manager do? | Ask to include some business subject matter experts (SMEs) in the team. | Invite stakeholders to discuss project requirements prioritization. | Assist the team in proposing a minimum viable product (MVP). | Register a risk and define a contingency plan to finish the project on time. |  | C | When requirements are very uncertain for a product that must be ready before summer, the project manager should assist the team in proposing a minimum viable product (MVP). An MVP focuses on essential features and enables iterative refinement. Adding SMEs (A) is helpful but does not address uncertainty. Inviting stakeholders to prioritize (B) is useful but less actionable. Registering a risk with contingency (D) is reactive. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 회사가 여름 시즌 시작 전에 준비해야 하는 새 제품을 출시하고 있다. 발견 프로세스 후 팀은 요구사항이 매우 불확실하다는 것을 깨달았다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀에 비즈니스 주제 전문가(SME)를 포함하도록 요청한다. | 이해관계자를 초대하여 프로젝트 요구사항 우선순위를 논의한다. | 팀이 최소 실행 가능 제품(MVP)을 제안하도록 지원한다. | 리스크를 등록하고 프로젝트를 제시간에 완료하기 위한 비상 계획을 정의한다. |  | C | 여름 전에 준비해야 하는 제품의 요구사항이 매우 불확실할 때, 프로젝트 관리자는 팀이 최소 실행 가능 제품(MVP)을 제안하도록 지원해야 한다. MVP는 핵심 기능에 집중하고 반복적 개선을 가능하게 한다. SME 추가(A)는 도움이 되지만 불확실성을 직접 해결하지 않는다. 이해관계자에게 우선순위 논의 초대(B)는 유용하지만 덜 실행 가능하다. 비상 계획과 함께 리스크 등록(D)은 사후 대응적이다.
245 | A project manager is leading an integration project for a retail company. The project demands a lot of time from the stakeholders to make important business decisions. The project is critical and must be completed on time and within budget. What should the project manager do to ensure that key stakeholders are available for this project? | Schedule meetings with all of the stakeholders to make business decisions whenneeded. | Work with the available stakeholders to make business decisions and keep allunavailable stakeholders informed. | Share the project schedule, milestones, and meeting agendas with the stakeholdersahead of time. | Add time reserve in the project schedule to allow extra time for the stakeholders tomake decisions. |  | C | When a critical integration project demands significant stakeholder time for business decisions and must be completed on time and within budget, the project manager should share the project schedule, milestones, and meeting agendas with stakeholders ahead of time. Advance sharing enables stakeholders to plan their availability. Scheduling meetings whenever needed (A) disrupts. Working only with available stakeholders (B) risks excluding key decision-makers. Adding time reserves (D) increases project duration and cost. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 소매 회사를 위한 통합 프로젝트를 이끌고 있다. 프로젝트는 중요한 비즈니스 결정을 내리기 위해 이해관계자들의 많은 시간을 요구한다. 프로젝트는 중요하며 예산 내에서 제시간에 완료되어야 한다. 프로젝트 관리자는 핵심 이해관계자가 이 프로젝트에 참여할 수 있도록 무엇을 해야 하는가? | 필요할 때 비즈니스 결정을 내리기 위해 모든 이해관계자와 회의를 예약한다. | 가용한 이해관계자와 협력하여 비즈니스 결정을 내리고 참여 불가한 모든 이해관계자에게 정보를 제공한다. | 프로젝트 일정, 마일스톤, 회의 안건을 사전에 이해관계자와 공유한다. | 이해관계자가 결정을 내리기 위한 추가 시간을 허용하도록 프로젝트 일정에 시간 예비를 추가한다. |  | C | 중요한 통합 프로젝트가 이해관계자의 상당한 시간을 요구하고 예산 내에서 제시간에 완료되어야 할 때, 프로젝트 관리자는 프로젝트 일정, 마일스톤, 회의 안건을 사전에 이해관계자와 공유해야 한다. 사전 공유는 이해관계자가 가용성을 계획할 수 있게 한다. 필요할 때 회의 예약(A)은 방해가 된다. 가용한 이해관계자와만 작업(B)은 핵심 의사결정자를 배제할 위험이 있다. 시간 예비 추가(D)는 프로젝트 기간과 비용을 증가시킨다.
246 | An agile team has started a new project. When should the project manager organize their first team retrospective? | When the team completes a release of a monumental increment | When more than a few weeks have passed | When the team reaches a major milestone | When the work is progressing well through the team |  | D | In an agile project, the project manager should organize the first team retrospective when the work is progressing well through the team—meaning after at least one iteration or sprint is complete. Retrospectives enable continuous improvement from the earliest practical point. Waiting for a monumental increment (A) delays learning. Waiting for more than a few weeks (B) is arbitrary. Waiting for a major milestone (C) misses early improvement opportunities. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Embed Quality | Develop Schedule | Traditional PM | 애자일 팀이 새 프로젝트를 시작했다. 프로젝트 관리자는 언제 첫 번째 팀 회고를 조직해야 하는가? | 팀이 중대한 인크리먼트의 릴리스를 완료했을 때 | 몇 주 이상이 지났을 때 | 팀이 주요 마일스톤에 도달했을 때 | 작업이 팀을 통해 잘 진행되고 있을 때 |  | D | 애자일 프로젝트에서 프로젝트 관리자는 작업이 팀을 통해 잘 진행되고 있을 때—즉, 최소한 하나의 이터레이션 또는 스프린트가 완료된 후 첫 번째 팀 회고를 조직해야 한다. 회고는 가장 빠른 실질적 시점부터 지속적 개선을 가능하게 한다. 중대한 인크리먼트를 기다리는 것(A)은 학습을 지연시킨다. 몇 주를 기다리는 것(B)은 자의적이다. 주요 마일스톤을 기다리는 것(C)은 초기 개선 기회를 놓친다.
247 | After a recent status review meeting, the project manager becomes aware that an influential stakeholder is unclear about the purpose and benefits of the project. Consequently, the stakeholder has questioned the viability of continuing the project. What should the project manager do next to address the situation? | Log the stakeholder ' s comments in the risk register as a high-impact threat to the project ' s completion | Consider the stakeholder ' s concerns and review the project charter with the project sponsor. | Speak with the project sponsor to find out if the stakeholder would agree to a one-on-one review session | Note the stakeholder ' s concerns but disregard them with regard to the project activities. |  | B | When an influential stakeholder questions the project's viability due to unclear purpose and benefits, the project manager should consider the stakeholder's concerns and review the project charter with the project sponsor. The charter formally authorizes the project and documents its purpose, objectives, and stakeholder roles. Reviewing it together provides an opportunity to clarify misunderstandings, reaffirm alignment with organizational goals, and restore the stakeholder's confidence. Logging the concern as a risk (A) acknowledges the issue but does not proactively resolve it. Arranging a one-on-one review session (C) may be useful but involves the sponsor's coordination and is not as direct. Disregarding the concerns (D) is inappropriate for an influential stakeholder and risks project failure. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Hybrid/Tailoring | 최근 현황 검토 회의 후, 프로젝트 관리자는 영향력 있는 이해관계자가 프로젝트의 목적과 이점에 대해 불명확하다는 것을 알게 되었다. 결과적으로, 이해관계자는 프로젝트 지속의 타당성에 의문을 제기했다. 프로젝트 관리자는 이 상황을 해결하기 위해 다음에 무엇을 해야 하는가? | 이해관계자의 의견을 프로젝트 완료에 대한 높은 영향도 위협으로 리스크 등록부에 기록한다. | 이해관계자의 우려를 고려하고 프로젝트 스폰서와 함께 프로젝트 헌장을 검토한다. | 프로젝트 스폰서에게 연락하여 이해관계자가 일대일 검토 세션에 동의할지 알아본다. | 이해관계자의 우려를 기록하지만 프로젝트 활동과 관련하여 무시한다. |  | B | 영향력 있는 이해관계자가 불명확한 목적과 이점으로 인해 프로젝트의 타당성에 의문을 제기할 때, 프로젝트 관리자는 이해관계자의 우려를 고려하고 프로젝트 스폰서와 함께 프로젝트 헌장을 검토해야 한다. 헌장은 프로젝트를 공식적으로 승인하고 목적, 목표, 이해관계자 역할을 문서화한다. 함께 검토하면 오해를 해소하고 조직 목표와의 정렬을 재확인하며 이해관계자의 신뢰를 회복할 기회를 제공한다. 우려를 리스크로 기록(A)하는 것은 문제를 인정하지만 능동적으로 해결하지 않는다. 일대일 검토 세션 주선(C)은 유용할 수 있지만 스폰서의 조정이 필요하며 직접적이지 않다. 우려 무시(D)는 영향력 있는 이해관계자에게 부적절하며 프로젝트 실패를 위험에 빠뜨린다.
248 | The project sponsor recently requested that a vendor begins working toward adopting a hybrid approach. In response, the vendor hired a project manager experienced in agile for the project. What does that project manager need to do to make the team work in a collaborative way? | Allocate time to mentor the team. | Update the issue log. | Request the project management office (PMO) for a team of mentors. | Identify any training gaps |  | A | When a vendor hires an agile-experienced project manager for a hybrid project, the PM's priority should be to allocate time to mentor the team on working collaboratively in a hybrid environment. This includes explaining the benefits and challenges of the approach, providing guidance and feedback, facilitating team meetings and retrospectives, and resolving conflicts. Mentoring builds the skills and mindset needed for effective hybrid delivery. Updating the issue log (B) is reactive and does not address team development. Requesting a team of mentors from the PMO (C) outsources the PM's leadership responsibility. Identifying training gaps (D) is useful but is a subset of the broader mentoring and team development effort. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Align Stakeholder Expectations | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 스폰서가 최근 벤더에게 하이브리드 접근 방식을 채택하도록 요청했다. 이에 대응하여, 벤더는 프로젝트를 위해 애자일 경험이 있는 프로젝트 관리자를 고용했다. 그 프로젝트 관리자는 팀이 협력적으로 일하도록 하기 위해 무엇을 해야 하는가? | 팀을 멘토링할 시간을 할당한다. | 이슈 로그를 업데이트한다. | 프로젝트 관리 오피스(PMO)에 멘토 팀을 요청한다. | 교육 격차를 파악한다. |  | A | 벤더가 하이브리드 프로젝트를 위해 애자일 경험이 있는 프로젝트 관리자를 고용했을 때, PM의 우선순위는 하이브리드 환경에서 협력적으로 일하는 것에 대해 팀을 멘토링할 시간을 할당하는 것이어야 한다. 여기에는 접근 방식의 이점과 과제 설명, 지침과 피드백 제공, 팀 회의와 회고 촉진, 갈등 해결이 포함된다. 멘토링은 효과적인 하이브리드 전달에 필요한 기술과 마인드셋을 구축한다. 이슈 로그 업데이트(B)는 사후 대응적이며 팀 개발을 다루지 않는다. PMO에 멘토 팀 요청(C)은 PM의 리더십 책임을 외부화한다. 교육 격차 파악(D)은 유용하지만 더 넓은 멘토링과 팀 개발 노력의 일부이다.
249 | A project manager is working on a cost-reimbursable contract from the client's side. During project execution, the project manager notices a major deliverable is missing. The project manager raises this with the seller but the seller advises the project manager that the subject deliverable is not part of the contract. The project manager remembers negotiating and agreeing to this deliverable during the tender process but cannot find it in the contract. What should the project manager do? | Look to see if the deliverable is described in the statement of work (SOW) | Request a change in the contract in order to add the deliverable | Terminate the contract and commence the closeout process | Add this deliverable to the requirements traceability matrix |  | A | When a seller claims a deliverable is not part of the contract despite the project manager's recollection of negotiating it, the PM should look to see if the deliverable is described in the statement of work (SOW). The SOW documents project scope, deliverables, acceptance criteria, and constraints, and is typically part of the contractual agreement. If the deliverable exists in the SOW, it constitutes a contractual obligation for the seller. Requesting a contract change (B) is premature without first verifying the existing contract documents. Adding it to the requirements traceability matrix (D) does not establish contractual obligation. Terminating the contract (C) is an extreme and disproportionate response. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Finance | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 관리자가 고객 측에서 실비 정산 계약으로 작업하고 있다. 프로젝트 실행 중 프로젝트 관리자는 주요 산출물이 누락되어 있음을 발견한다. 프로젝트 관리자가 판매자에게 이를 제기하지만, 판매자는 해당 산출물이 계약의 일부가 아니라고 조언한다. 프로젝트 관리자는 입찰 과정에서 이 산출물을 협상하고 합의한 것을 기억하지만 계약서에서 찾을 수 없다. 프로젝트 관리자는 어떻게 해야 하는가? | 해당 산출물이 작업 기술서(SOW)에 기술되어 있는지 확인한다. | 산출물을 추가하기 위해 계약 변경을 요청한다. | 계약을 종료하고 종료 프로세스를 시작한다. | 이 산출물을 요구사항 추적 매트릭스에 추가한다. |  | A | 판매자가 PM의 협상 기억에도 불구하고 산출물이 계약의 일부가 아니라고 주장할 때, PM은 해당 산출물이 작업 기술서(SOW)에 기술되어 있는지 확인해야 한다. SOW는 프로젝트 범위, 산출물, 인수 기준, 제약 조건을 문서화하며, 일반적으로 계약의 일부이다. 산출물이 SOW에 존재하면 판매자의 계약 의무를 구성한다. 계약 변경 요청(B)은 기존 계약 문서를 먼저 확인하지 않고는 시기상조이다. 요구사항 추적 매트릭스에 추가(D)는 계약 의무를 설정하지 않는다. 계약 종료(C)는 극단적이고 불균형적인 대응이다.
250 | Five agile teams working together on a product recently performed release planning. Midway through the project, each team showed that their progress was on track. When all of the teams integrated at the product level, many integration issues were observed. The overall product release progress declined with predictions showing the committed content will not be able to be accomplished. What should the project manager have done differently? | Arranged an online session on the integration concept and suggested tools to the teams | Formed a separate quality assurance team to test all items coming from each team at the end of each sprint | Performed a Scrum of Scrums on a regular basis to help the teams remove impediments | Ensured frequent and continuous integration of work to obtain early feedback and continuous learning |  | D | When five agile teams show individual progress but integration at the product level reveals many issues, the project manager should have ensured frequent and continuous integration of work to obtain early feedback and continuous learning. Continuous integration detects problems early. Arranging an online integration session (A) educates but does not ensure practice. Forming a separate QA team (B) creates silos. Performing Scrum of Scrums (C) aids coordination but does not directly address integration. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 하나의 제품에서 함께 작업하는 5개의 애자일 팀이 최근 릴리스 계획을 수행했다. 프로젝트 중간에 각 팀은 진행 상황이 순조로움을 보여주었다. 모든 팀이 제품 수준에서 통합했을 때, 많은 통합 이슈가 관찰되었다. 전체 제품 릴리스 진행이 감소했으며 예측에 따르면 약속된 내용을 달성할 수 없을 것이다. 프로젝트 관리자는 무엇을 다르게 했어야 하는가? | 통합 개념과 팀에 대한 제안 도구에 대해 온라인 세션을 마련한다. | 각 팀에서 나오는 모든 항목을 각 스프린트 끝에 테스트하기 위해 별도의 품질 보증 팀을 구성한다. | 팀이 장애물을 제거하도록 돕기 위해 정기적으로 Scrum of Scrums를 수행한다. | 초기 피드백과 지속적 학습을 얻기 위해 작업의 빈번하고 지속적인 통합을 보장한다. |  | D | 5개의 애자일 팀이 개별적으로 진행 상황을 보여주지만 제품 수준의 통합에서 많은 이슈가 드러날 때, 프로젝트 관리자는 초기 피드백과 지속적 학습을 얻기 위해 작업의 빈번하고 지속적인 통합을 보장했어야 한다. 지속적 통합은 문제를 조기에 감지한다. 온라인 통합 세션 마련(A)은 교육하지만 실행을 보장하지 않는다. 별도 QA 팀 구성(B)은 사일로를 만든다. Scrum of Scrums 수행(C)은 조율에 도움이 되지만 통합을 직접 다루지 않는다.
251 | A project was initiated due to an external business influence. During the course of the project, some of the business parameters considered at the beginning of the project have changed. What should the project manager do? | Request management to update the project requirements accordingly. | Inform management that the agreed-upon scope cannot be changed. | Inform the team not to accept any changes, as it involves significant rework. | Request an update of only new requirements, as other changes involve rework. |  | A | When external business influences change parameters considered at project initiation, the project manager should request management to update project requirements accordingly. Adapting to changing business conditions maintains project relevance. Informing management scope cannot change (B) is rigid. Not accepting changes due to rework (C) ignores business needs. Requesting only new requirements (D) creates an incomplete picture. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 외부 비즈니스 영향으로 인해 프로젝트가 시작되었다. 프로젝트 진행 과정에서, 프로젝트 초기에 고려된 일부 비즈니스 매개변수가 변경되었다. 프로젝트 관리자는 어떻게 해야 하는가? | 경영진에게 프로젝트 요구사항을 그에 맞게 업데이트하도록 요청한다. | 경영진에게 합의된 범위는 변경할 수 없다고 알린다. | 상당한 재작업이 수반되므로 팀에게 어떤 변경도 수용하지 않도록 알린다. | 다른 변경은 재작업이 수반되므로 새로운 요구사항만 업데이트를 요청한다. |  | A | 외부 비즈니스 영향이 프로젝트 시작 시 고려된 매개변수를 변경할 때, 프로젝트 관리자는 경영진에게 프로젝트 요구사항을 그에 맞게 업데이트하도록 요청해야 한다. 변화하는 비즈니스 조건에 적응하면 프로젝트의 관련성이 유지된다. 범위 변경 불가 통보(B)는 경직적이다. 재작업으로 인한 변경 불수용(C)은 비즈니스 요구를 무시한다. 새 요구사항만 요청(D)은 불완전한 그림을 만든다.
252 | In the daily check-in meeting, a team member informs the project team that the licenses for one of the components that will be used will expire in a couple of months. The licensing cost is significant. What should the project manager do next? | Raise a change request to secure the renewal. | Add a spike to the backlog for an alternative design. | Escalate the licensing issue to the product owner. | Evaluate the impact of nonrenewal of the license. |  | D | When a team member reports that licenses for a critical component will expire soon with significant cost implications, the project manager should first evaluate the impact of nonrenewal of the license. This assessment covers risks, costs, potential delays, and whether viable alternatives exist, informing the decision about whether to renew or pursue other options. Raising a change request to secure renewal (A) is premature without understanding the full impact. Adding a spike for an alternative design (B) assumes alternatives are needed before evaluating the situation. Escalating to the product owner (C) delegates the assessment without the PM first understanding the implications. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 일일 체크인 미팅에서, 팀원이 사용될 구성요소 중 하나의 라이선스가 몇 달 후에 만료된다고 프로젝트 팀에 알렸다. 라이선스 비용은 상당하다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 갱신을 확보하기 위한 변경 요청을 제기한다. | 대체 설계를 위한 스파이크를 백로그에 추가한다. | 라이선스 이슈를 제품 책임자에게 에스컬레이션한다. | 라이선스 미갱신의 영향을 평가한다. |  | D | 팀원이 중요한 구성요소의 라이선스가 상당한 비용을 수반하며 곧 만료된다고 보고할 때, 프로젝트 관리자는 먼저 라이선스 미갱신의 영향을 평가해야 한다. 이 평가는 리스크, 비용, 잠재적 지연, 실행 가능한 대안의 존재 여부를 포함하며, 갱신 여부 또는 다른 옵션 추구에 대한 결정을 알려준다. 갱신 확보를 위한 변경 요청(A)은 전체 영향을 이해하지 않고는 시기상조이다. 대체 설계를 위한 스파이크 추가(B)는 상황 평가 전에 대안이 필요하다고 가정한다. 제품 책임자에게 에스컬레이션(C)은 PM이 먼저 영향을 이해하지 않고 평가를 위임한다.
253 | A project manager is using an agile approach. During the sprint planning meeting, the product owner flagged a backlog item as high business value and easy to implement. However, the other team members identified a high dependency between this item and another item that is flagged as low business value and high complexity. What should the project manager do to support the backlog prioritization? | Support the team to move both items to the next sprint when the team will know more. | Facilitate the discussion until the team reaches an agreement about the two items. | Prioritize the item flagged as high business value and low complexity for this sprint. | Prioritize the item flagged as a dependency with low business value and high complexity. |  | B | When a high-business-value, low-complexity backlog item has a high dependency on a low-business-value, high-complexity item, the project manager should facilitate a discussion until the team reaches agreement about both items. This collaborative approach ensures the team considers business value, complexity, and dependencies together to make an informed prioritization decision. Supporting the team to defer both items (A) delays value delivery unnecessarily. Prioritizing only the high-business-value item (C) ignores the critical dependency. Prioritizing only the dependency item (D) sacrifices business value without team consensus. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 프로젝트 관리자가 애자일 접근 방식을 사용하고 있다. 스프린트 계획 미팅에서 제품 책임자가 백로그 항목을 높은 비즈니스 가치와 구현 용이성으로 표시했다. 그러나 다른 팀원들이 이 항목과 낮은 비즈니스 가치와 높은 복잡성으로 표시된 다른 항목 사이에 높은 종속성을 확인했다. 프로젝트 관리자는 백로그 우선순위 지정을 지원하기 위해 무엇을 해야 하는가? | 팀이 더 많이 알게 될 다음 스프린트로 두 항목을 이동하도록 팀을 지원한다. | 두 항목에 대해 팀이 합의에 도달할 때까지 논의를 촉진한다. | 이번 스프린트에 높은 비즈니스 가치와 낮은 복잡성으로 표시된 항목의 우선순위를 정한다. | 낮은 비즈니스 가치와 높은 복잡성의 종속성으로 표시된 항목의 우선순위를 정한다. |  | B | 높은 비즈니스 가치, 낮은 복잡성의 백로그 항목이 낮은 비즈니스 가치, 높은 복잡성 항목에 높은 종속성을 가질 때, 프로젝트 관리자는 두 항목에 대해 팀이 합의에 도달할 때까지 논의를 촉진해야 한다. 이 협력적 접근 방식은 팀이 비즈니스 가치, 복잡성, 종속성을 함께 고려하여 정보에 입각한 우선순위 결정을 내리도록 보장한다. 두 항목 모두 연기 지원(A)은 가치 전달을 불필요하게 지연시킨다. 높은 비즈니스 가치 항목만 우선(C)은 중요한 종속성을 무시한다. 종속성 항목만 우선(D)은 팀 합의 없이 비즈니스 가치를 희생한다.
254 | A project needs to be outlined as a phased approach for multiple product lines with a review gate at the end of each phase. To ensure consistency for this hybrid delivery, what should the project manager do? | Request the project management office (PMO) to review the initial plan | Get agreement from stakeholders on high-level deliverables and requirements. | Ask subject matter experts (SMEs) to provide a detailed plan for each phase. | Commit to a detailed global plan from the initiation phase. |  | B | When outlining a phased approach for multiple product lines with review gates for hybrid delivery, the project manager should get agreement from stakeholders on high-level deliverables and requirements. Stakeholder alignment ensures consistency across phases. Requesting PMO review (A) delegates planning. Asking SMEs for detailed phase plans (C) is premature. Committing to a detailed global plan from initiation (D) is too rigid for hybrid delivery. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Hybrid/Tailoring | 프로젝트는 각 단계 끝에 검토 게이트가 있는 다중 제품 라인을 위한 단계적 접근 방식으로 계획되어야 한다. 이 하이브리드 전달의 일관성을 보장하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 관리 오피스(PMO)에 초기 계획 검토를 요청한다. | 이해관계자로부터 상위 수준의 산출물과 요구사항에 대한 합의를 얻는다. | 주제 전문가(SME)에게 각 단계별 상세 계획을 제공하도록 요청한다. | 착수 단계부터 상세한 글로벌 계획에 전념한다. |  | B | 하이브리드 전달을 위해 검토 게이트가 있는 다중 제품 라인의 단계적 접근 방식을 계획할 때, 프로젝트 관리자는 이해관계자로부터 상위 수준의 산출물과 요구사항에 대한 합의를 얻어야 한다. 이해관계자 정렬은 단계 간 일관성을 보장한다. PMO 검토 요청(A)은 계획을 위임한다. SME에게 상세 단계별 계획 요청(C)은 시기상조이다. 착수 시 상세 글로벌 계획 전념(D)은 하이브리드 전달에 너무 경직적이다.
255 | During project execution, a global project team was using a video conferencing tool to support the daily meetings. However, during these meetings, only a few team members were actively participating. As a result, lots of misunderstandings occurred. What should the project manager do to address this issue? | Use round-robin check-ins to facilitate the meeting so all participants have the opportunity to speak | Identify one team representative to speak up during the daily meeting and share the team updates | Check the ground rules of the meeting to review the initial agreement with the team members | Book one-on-one meetings with the team members who are not speaking up during the daily meetings to get their updates |  | A | When only a few team members actively participate during video conference meetings causing misunderstandings, the project manager should use round-robin check-ins to facilitate meetings so all participants have the opportunity to speak. Structured participation ensures everyone's voice is heard. Identifying one representative (B) limits participation further. Checking ground rules (C) reviews agreements but may not change behavior. Booking one-on-ones (D) gathers updates privately but does not improve meeting dynamics. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 실행 중, 글로벌 프로젝트 팀이 일일 미팅을 지원하기 위해 화상 회의 도구를 사용하고 있었다. 그러나 이 미팅에서 소수의 팀원만 적극적으로 참여하고 있었다. 결과적으로 많은 오해가 발생했다. 프로젝트 관리자는 이 문제를 해결하기 위해 무엇을 해야 하는가? | 모든 참가자가 발언할 기회를 갖도록 라운드 로빈 체크인을 사용하여 미팅을 진행한다. | 일일 미팅에서 발언하고 팀 업데이트를 공유할 한 명의 팀 대표를 지정한다. | 미팅의 기본 규칙을 점검하여 팀원과의 초기 합의를 검토한다. | 일일 미팅에서 발언하지 않는 팀원과 일대일 미팅을 예약하여 업데이트를 받는다. |  | A | 화상 회의 미팅에서 소수의 팀원만 적극적으로 참여하여 오해가 발생할 때, 프로젝트 관리자는 모든 참가자가 발언할 기회를 갖도록 라운드 로빈 체크인을 사용하여 미팅을 진행해야 한다. 구조화된 참여는 모든 사람의 의견이 반영되도록 보장한다. 한 명의 대표 지정(B)은 참여를 더 제한한다. 기본 규칙 점검(C)은 합의를 검토하지만 행동을 변화시키지 못할 수 있다. 일대일 미팅 예약(D)은 비공개로 업데이트를 수집하지만 미팅 역학을 개선하지 않는다.
256 | A project manager assigned team members to work in pairs on a large amount of technical reports. At times, the project manager noticed that important information was not shared properly among the team. This has caused delivery delays and, ultimately, the failure to complete the project. What is the root cause of this issue? | Improper assignment of tasks to team member pairings | Incorrect communication techniques applied during implementation | Team cohesiveness was lost because team members worked in pairs | Lack of team member training on documentation planning |  | B | The root cause of the project failure is incorrect communication techniques applied during implementation. When important information is not shared properly among team members working in pairs, it indicates a breakdown in how communication was conducted—not the pairing structure itself. Effective communication methods are essential to keep all team members aligned and informed. Improper task assignment (A) relates to work distribution, not information flow. Loss of team cohesiveness from working in pairs (C) incorrectly blames the structure rather than the communication methods. Lack of documentation training (D) may contribute but is secondary to the fundamental communication technique failure. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 팀원들을 짝으로 배정하여 대량의 기술 보고서를 작업하게 했다. 때때로 프로젝트 관리자는 중요한 정보가 팀 간에 제대로 공유되지 않는 것을 발견했다. 이로 인해 전달 지연이 발생했고, 궁극적으로 프로젝트 완료에 실패했다. 이 문제의 근본 원인은 무엇인가? | 팀원 짝 배정에 대한 부적절한 작업 배분 | 구현 중 적용된 잘못된 의사소통 기법 | 팀원들이 짝으로 일했기 때문에 팀 응집력이 상실됨 | 문서화 계획에 대한 팀원 교육 부족 |  | B | 프로젝트 실패의 근본 원인은 구현 중 적용된 잘못된 의사소통 기법이다. 짝으로 일하는 팀원들 사이에서 중요한 정보가 제대로 공유되지 않는 것은 짝 구조 자체가 아닌 의사소통 수행 방식의 문제를 나타낸다. 효과적인 의사소통 방법은 모든 팀원을 정렬하고 정보를 공유하는 데 필수적이다. 부적절한 작업 배분(A)은 업무 분배에 관한 것이지 정보 흐름이 아니다. 짝 작업으로 인한 팀 응집력 상실(C)은 의사소통 방법이 아닌 구조를 잘못 비난한다. 문서화 교육 부족(D)은 기여할 수 있지만 근본적인 의사소통 기법 실패에 비해 부차적이다.
257 | A product owner does not regularly attend demonstration ceremonies. As a result, the demonstration ceremonies are constantly rescheduled and the work is impacted in multiple ways. The project manager believes the product owner is not committed to the project. What should the project manager have done to avoid this situation? | Defined a set of external audits that can expose this situation to the project sponsor | Asked another product owner to attend the demonstrations on behalf of the product owner | Set a definition of done (DoD) that considers the work as done if not otherwise specified | Agreed with the product owner on appropriate project governance levels |  | D | The correct answer is D. Agreed with the product owner on appropriate project governance levels. Schedule management requires proactive monitoring and appropriate corrective actions. The PM should analyze impacts and implement suitable responses to maintain project timelines. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 제품 책임자가 데모 세리모니에 정기적으로 참석하지 않는다. 결과적으로 데모 세리모니가 지속적으로 일정 변경되고 작업이 여러 방면에서 영향을 받고 있다. 프로젝트 관리자는 제품 책임자가 프로젝트에 전념하지 않는다고 생각한다. 프로젝트 관리자는 이 상황을 피하기 위해 무엇을 했어야 하는가? | 이 상황을 프로젝트 스폰서에게 노출할 수 있는 외부 감사 세트를 정의한다. | 제품 책임자를 대신하여 데모에 참석할 다른 제품 책임자를 요청한다. | 달리 명시되지 않는 한 작업을 완료로 간주하는 완료의 정의(DoD)를 설정한다. | 제품 책임자와 적절한 프로젝트 거버넌스 수준에 합의한다. |  | D | 정답은 D이다. 제품 책임자와 적절한 프로젝트 거버넌스 수준에 합의한다. 일정 관리는 사전 모니터링과 적절한 시정 조치를 요구한다. PM은 영향을 분석하고 프로젝트 일정을 유지하기 위한 적절한 대응을 시행해야 한다.
258 | A project manager has been hired to help coordinate an ongoing project. Historically, the biggest problem as reported by the company's CEO is that the change request process has been handled by managers who did not have clear information on the project schedule and budget. This information has been inconsistent and handled by finance, risk, and functional subject matter experts (SMEs). What should the project manager do to control this situation? | Review the scope defined in the project charter | Redefine the communications management plan | Document the risk in the project risk register | Develop an integrated change management plan |  | D | When the change request process has been inconsistently handled by managers without clear project information, the project manager should develop an integrated change management plan. This establishes clear processes, roles (including change control board responsibilities), evaluation criteria, approval procedures, and tracking mechanisms for all change requests. Reviewing the charter scope (A) provides high-level overview but not process details. Redefining the communications plan (B) addresses information sharing but not the change process. Documenting risk (C) does not address the systemic process issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 프로젝트 관리자가 진행 중인 프로젝트를 조율하기 위해 고용되었다. 역사적으로 회사 CEO가 보고한 가장 큰 문제는 프로젝트 일정과 예산에 대한 명확한 정보가 없는 관리자들이 변경 요청 프로세스를 처리해 왔다는 것이다. 이 정보는 일관성이 없었으며 재무, 리스크, 기능 주제 전문가(SME)가 처리해 왔다. 프로젝트 관리자는 이 상황을 통제하기 위해 무엇을 해야 하는가? | 프로젝트 헌장에 정의된 범위를 검토한다. | 의사소통 관리 계획을 재정의한다. | 프로젝트 리스크 등록부에 리스크를 문서화한다. | 통합 변경 관리 계획을 개발한다. |  | D | 변경 요청 프로세스가 명확한 프로젝트 정보 없이 관리자들에 의해 일관성 없이 처리되었을 때, 프로젝트 관리자는 통합 변경 관리 계획을 개발해야 한다. 이는 모든 변경 요청에 대한 명확한 프로세스, 역할(변경 통제 위원회 책임 포함), 평가 기준, 승인 절차, 추적 메커니즘을 수립한다. 헌장 범위 검토(A)는 상위 수준 개요를 제공하지만 프로세스 세부 사항은 아니다. 의사소통 계획 재정의(B)는 정보 공유를 다루지만 변경 프로세스는 아니다. 리스크 문서화(C)는 체계적인 프로세스 문제를 해결하지 않는다.
259 | A project sponsor is upset that a vital project might miss an agreed-upon delivery deadline. The sponsor asks the project manager to check whether the project team can do anything to deliver on time. What should the project manager do first? | Work with the team to ensure the project is delivered on time | Increase project team resources to maintain the timeline | Conduct simulations to determine the best way forward to ensure timely delivery | Reduce scope to deliver on time |  | C | When the sponsor asks whether the team can deliver on time for a vital project at risk of missing its deadline, the project manager should first conduct simulations to determine the best way forward. Schedule analysis, what-if scenarios, and critical path assessment provide evidence-based options. Working with the team to deliver on time (A) is too generic. Increasing resources (B) may not be effective without analysis. Reducing scope (D) should follow feasibility assessment, not precede it. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 프로젝트 스폰서가 중요한 프로젝트가 합의된 전달 기한을 놓칠 수 있어 불만이다. 스폰서는 프로젝트 관리자에게 프로젝트 팀이 제시간에 전달하기 위해 무엇이든 할 수 있는지 확인하도록 요청한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트가 제시간에 전달되도록 팀과 협력한다. | 일정을 유지하기 위해 프로젝트 팀 자원을 증가시킨다. | 적시 전달을 보장하기 위한 최선의 방법을 결정하기 위해 시뮬레이션을 수행한다. | 제시간에 전달하기 위해 범위를 축소한다. |  | C | 스폰서가 기한 위험에 처한 중요 프로젝트의 적시 전달 가능 여부를 물을 때, 프로젝트 관리자는 먼저 최선의 방법을 결정하기 위해 시뮬레이션을 수행해야 한다. 일정 분석, 가정 분석, 주요 경로 평가는 근거 기반 옵션을 제공한다. 팀과 협력하여 적시 전달(A)은 너무 일반적이다. 자원 증가(B)는 분석 없이 효과적이지 않을 수 있다. 범위 축소(D)는 타당성 평가 이후에 이루어져야 한다.
260 | A project manager is instructed by the project sponsor to draft the project charter. The project sponsor asks the project manager to involve a particular stakeholder in order to provide necessary resources. However, the stakeholder is refusing to get involved because the stakeholder thinks that there is no benefit in using the project deliverable. What should the project manager do to resolve this? | Consider the stakeholder as a risk and evaluate possible solutions with the project team | Improve communication with the stakeholder to obtain their assistance in the future 1110 | Meet with the stakeholder to discuss the impact of the deliverable | Escalate to the project sponsor due to the political nature of the issue |  | C | When a stakeholder refuses charter involvement because they see no benefit in the deliverable, the project manager should meet with the stakeholder to discuss the impact of the deliverable. Direct engagement addresses the root cause of resistance. Treating as a risk (A) is indirect. Improving future communication (B) is vague. Escalating to the sponsor (D) bypasses direct resolution. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 프로젝트 스폰서로부터 프로젝트 헌장을 작성하라는 지시를 받았다. 프로젝트 스폰서는 필요한 자원을 제공하기 위해 특정 이해관계자를 참여시키도록 프로젝트 관리자에게 요청한다. 그러나 이해관계자는 프로젝트 산출물을 사용하는 데 이점이 없다고 생각하여 참여를 거부하고 있다. 프로젝트 관리자는 이를 해결하기 위해 무엇을 해야 하는가? | 이해관계자를 리스크로 간주하고 프로젝트 팀과 가능한 해결책을 평가한다. | 이해관계자와의 의사소통을 개선하여 향후 지원을 확보한다. | 이해관계자와 만나 산출물의 영향에 대해 논의한다. | 이슈의 정치적 성격으로 인해 프로젝트 스폰서에게 에스컬레이션한다. |  | C | 이해관계자가 산출물에 이점이 없다고 보고 헌장 참여를 거부할 때, 프로젝트 관리자는 이해관계자와 만나 산출물의 영향에 대해 논의해야 한다. 직접적인 참여는 저항의 근본 원인을 다룬다. 리스크로 취급(A)은 간접적이다. 향후 의사소통 개선(B)은 모호하다. 스폰서에게 에스컬레이션(D)은 직접적인 해결을 우회한다.
261 | A project manager primarily works on implementation projects. Depending on the deliverable, the project manager is able to estimate the timeline based on previous projects. The project manager now receives a project that is different from the previous implementation projects. What should the project manager do next? | Ask the project management office (PMO) by when the project can be completed and use that date as the project time line | Refer to the previous protect they worked on and base the estimate on that | Use expert judgment to estimate the schedule and then adjust the schedule as the project progresses | Break down the project into smaller tasks and estimate the durations of the activities |  | D | When receiving a project different from previous implementations where past experience does not directly apply, the project manager should break down the project into smaller tasks and estimate the durations of activities. Decomposition enables more accurate estimation. Asking the PMO for a completion date (A) delegates estimation responsibility. Referring to a previous project (B) applies irrelevant data. Using expert judgment alone (C) may be insufficient for an unfamiliar project type. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 프로젝트 관리자가 주로 구현 프로젝트를 진행한다. 산출물에 따라 프로젝트 관리자는 이전 프로젝트를 기반으로 일정을 추정할 수 있다. 프로젝트 관리자가 이제 이전 구현 프로젝트와 다른 프로젝트를 받았다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 관리 오피스(PMO)에 프로젝트 완료 가능 시점을 물어보고 그 날짜를 프로젝트 일정으로 사용한다. | 이전에 작업한 프로젝트를 참조하여 그것을 기반으로 추정한다. | 전문가 판단을 사용하여 일정을 추정한 다음 프로젝트가 진행됨에 따라 일정을 조정한다. | 프로젝트를 더 작은 작업으로 분해하고 활동의 기간을 추정한다. |  | D | 과거 경험이 직접 적용되지 않는 이전 구현과 다른 프로젝트를 받았을 때, 프로젝트 관리자는 프로젝트를 더 작은 작업으로 분해하고 활동의 기간을 추정해야 한다. 분해는 더 정확한 추정을 가능하게 한다. PMO에 완료일 문의(A)는 추정 책임을 위임한다. 이전 프로젝트 참조(B)는 관련 없는 데이터를 적용한다. 전문가 판단만 사용(C)은 익숙하지 않은 프로젝트 유형에 불충분할 수 있다.
262 | A newly hired project team lead was assigned a project using a hybrid delivery approach. As the project onboards a lot of new team members, the lead feels overwhelmed with the effort of explaining the project delivery process to each new team member. What should the project lead do? | Use Pareto techniques to identify the knowledge required by the majority of the team. | Recommend putting the project temporarily on hold and focus on onboarding and training. | Develop a training curriculum and schedule training delivery throughout the project. | Document the processes and organize a week-long, off-site meeting with the project team. |  | C | The correct answer is C. Develop a training curriculum and schedule training delivery throughout the project. Effective resource management ensures team members have the necessary competencies and support. The PM should identify gaps and address them through training, coaching, or mentoring. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 새로 고용된 프로젝트 팀 리드가 하이브리드 전달 접근 방식을 사용하는 프로젝트에 배정되었다. 프로젝트에 많은 새 팀원이 합류하면서, 리드는 각 새 팀원에게 프로젝트 전달 프로세스를 설명하는 노력에 압도당하고 있다. 프로젝트 리드는 무엇을 해야 하는가? | Pareto 기법을 사용하여 대다수 팀에 필요한 지식을 파악한다. | 프로젝트를 일시적으로 중단하고 온보딩과 교육에 집중할 것을 권고한다. | 교육 커리큘럼을 개발하고 프로젝트 전반에 걸쳐 교육 전달을 계획한다. | 프로세스를 문서화하고 프로젝트 팀과 함께 일주일간의 외부 미팅을 조직한다. |  | C | 정답은 C이다. 교육 커리큘럼을 개발하고 프로젝트 전반에 걸쳐 교육 전달을 계획한다. 효과적인 자원 관리는 팀원이 필요한 역량과 지원을 갖추도록 보장한다. PM은 격차를 파악하고 교육, 코칭 또는 멘토링을 통해 이를 해결해야 한다.
263 | A junior project manager was recently hired to lead a complex project scheduled to kick off in 2 weeks. The junior project manager was introduced to another project manager for mentoring. Which two benefits will the junior project manager realize by being assigned to a mentor? (Choose two) | The junior project manager can discuss certain problems with their mentor without fear of retribution. | The mentor will be involved in the decision-making processes implemented by the junior project manager. | The mentor will be immediately available to take over the project if there are problems or project delays. | The junior project manager reports administratively to their mentor so that human resource (HR) questions can be answered quickly. | The mentor can provide past project documentation with early warning indicators that potential problems could occur. | A, E | When a junior project manager is assigned a mentor, the two key benefits are: (A) the junior PM can discuss problems without fear of retribution — a safe learning environment, and (E) the mentor can provide past project documentation with early warning indicators of potential problems — knowledge transfer. The mentor's involvement in decisions (B) oversteps boundaries. Taking over the project (C) is not mentoring. Reporting to the mentor for HR questions (D) conflates mentoring with administrative reporting. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scaled Agile | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 주니어 프로젝트 관리자가 최근 2주 후에 시작될 복잡한 프로젝트를 이끌기 위해 고용되었다. 주니어 프로젝트 관리자는 멘토링을 위해 다른 프로젝트 관리자에게 소개되었다. 멘토에 배정됨으로써 주니어 프로젝트 관리자가 얻을 두 가지 이점은 무엇인가? (2개 선택) | 주니어 프로젝트 관리자는 보복에 대한 두려움 없이 멘토와 특정 문제를 논의할 수 있다. | 멘토는 주니어 프로젝트 관리자가 시행하는 의사결정 프로세스에 참여할 것이다. | 멘토는 문제나 프로젝트 지연이 있을 경우 즉시 프로젝트를 인수할 수 있다. | 주니어 프로젝트 관리자는 인사(HR) 질문에 빨리 답변할 수 있도록 멘토에게 행정적으로 보고한다. | 멘토는 잠재적 문제가 발생할 수 있는 조기 경고 지표가 있는 과거 프로젝트 문서를 제공할 수 있다. | A, E | 주니어 프로젝트 관리자가 멘토에 배정될 때, 두 가지 주요 이점은: (A) 주니어 PM이 보복에 대한 두려움 없이 문제를 논의할 수 있는 안전한 학습 환경, 그리고 (E) 멘토가 잠재적 문제의 조기 경고 지표가 있는 과거 프로젝트 문서를 제공할 수 있는 지식 전달이다. 멘토의 의사결정 참여(B)는 경계를 넘는다. 프로젝트 인수(C)는 멘토링이 아니다. HR 질문을 위한 멘토 보고(D)는 멘토링과 행정적 보고를 혼동한다.
264 | A project manager is developing the project schedule with the project team. The team members estimate that an optimistic duration is 5 days, the pessimistic duration is 20 days, and the most likely duration is 11 days. What duration should the project manager use? | 11 days | 12.5 days | 12 days | 11.5 days |  | C | Using the PERT formula: Expected Duration = (Optimistic + 4×Most Likely + Pessimistic) ÷ 6 = (5 + 44 + 20) ÷ 6 = 69 ÷ 6 = 11.5, rounded to 12 days. This three-point estimation technique accounts for uncertainty by weighting the most likely estimate. 11 days (A) uses only the most likely value. 12.5 days (B) is an incorrect calculation. 11.5 days (D) is the exact result before rounding. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 관리자가 프로젝트 팀과 함께 프로젝트 일정을 개발하고 있다. 팀원들은 낙관적 기간이 5일, 비관적 기간이 20일, 가장 가능성 높은 기간이 11일로 추정했다. 프로젝트 관리자는 어떤 기간을 사용해야 하는가? | 11일 | 12.5일 | 12일 | 11.5일 |  | C | PERT 공식 사용: 예상 기간 = (낙관적 + 4×가장 가능성 높은 + 비관적) ÷ 6 = (5 + 44 + 20) ÷ 6 = 69 ÷ 6 = 11.5, 반올림하면 12일. 이 3점 추정 기법은 가장 가능성 높은 추정치에 가중치를 두어 불확실성을 반영한다. 11일(A)은 가장 가능성 높은 값만 사용한다. 12.5일(B)은 잘못된 계산이다. 11.5일(D)은 반올림 전 정확한 결과이다.
265 | A project manager has been assigned a project team with members in two different locations. The project manager noticed that the productivity of a senior team member in the other location is much lower than the local junior team members. What should the project manager do to address the issue? | Speak with the senior team member to identify the difficulties. | Share a work performance report with the team member ' s supervisor. | Assign a mentor to work with the senior team member. | Collect feedback from all team members about team performance. |  | A | The correct answer is A. Speak with the senior team member to identify the difficulties. The PM should address team issues proactively by understanding root causes, fostering collaboration, and creating an environment where team members can perform effectively. Building trust and empowering team members are essential leadership skills. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Risk & Issue Management | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 두 개의 다른 지역에 있는 팀원으로 프로젝트 팀을 배정받았다. 프로젝트 관리자는 다른 지역의 시니어 팀원의 생산성이 현지 주니어 팀원보다 훨씬 낮다는 것을 발견했다. 프로젝트 관리자는 이 문제를 해결하기 위해 무엇을 해야 하는가? | 시니어 팀원과 대화하여 어려움을 파악한다. | 팀원의 상사에게 업무 성과 보고서를 공유한다. | 시니어 팀원과 함께 일할 멘토를 배정한다. | 모든 팀원으로부터 팀 성과에 대한 피드백을 수집한다. |  | A | 정답은 A이다. 시니어 팀원과 대화하여 어려움을 파악한다. PM은 근본 원인을 이해하고, 협력을 촉진하며, 팀원이 효과적으로 수행할 수 있는 환경을 조성함으로써 팀 문제를 능동적으로 해결해야 한다. 신뢰 구축과 팀원 역량 강화는 필수적인 리더십 기술이다.
266 | A project manager is leading a hybrid project. The work breakdown structure (WBS) and the schedule were developed, but the project manager is having difficulty assigning specific resources to all of the project tasks. What should the project manager do? | Ignore the unallocated tasks for now and reallocate when the resources are available. | Assign the unallocated tasks to the functional role and then reallocate when the resources are available. | Assign the unallocated tasks to the project management office (PMO) manager and reallocate when the resources are available. | Escalate the issue to the project sponsor and seek their immediate intervention. |  | B | When having difficulty assigning specific resources to all project tasks in a hybrid project, the project manager should assign unallocated tasks to the functional role and then reallocate when resources become available. This maintains project momentum by ensuring accountability at the role level while allowing flexibility for future resource assignment. Ignoring unallocated tasks (A) risks them falling through the cracks. Assigning to the PMO manager (C) misplaces accountability. Escalating to the sponsor (D) is premature for a resource planning challenge. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 프로젝트를 이끌고 있다. 작업 분류 체계(WBS)와 일정이 개발되었지만, 프로젝트 관리자는 모든 프로젝트 작업에 특정 자원을 할당하는 데 어려움을 겪고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 할당되지 않은 작업을 당분간 무시하고 자원이 가용해지면 재할당한다. | 할당되지 않은 작업을 기능 역할에 배정한 다음 자원이 가용해지면 재할당한다. | 할당되지 않은 작업을 프로젝트 관리 오피스(PMO) 관리자에게 배정하고 자원이 가용해지면 재할당한다. | 프로젝트 스폰서에게 문제를 에스컬레이션하고 즉각적인 개입을 요청한다. |  | B | 하이브리드 프로젝트에서 모든 프로젝트 작업에 특정 자원을 할당하는 데 어려움이 있을 때, 프로젝트 관리자는 할당되지 않은 작업을 기능 역할에 배정한 다음 자원이 가용해지면 재할당해야 한다. 이는 역할 수준에서 책임을 보장하면서 향후 자원 배정의 유연성을 허용하여 프로젝트 추진력을 유지한다. 할당되지 않은 작업 무시(A)는 누락 위험이 있다. PMO 관리자에게 배정(C)은 책임을 잘못 배치한다. 스폰서에게 에스컬레이션(D)은 자원 계획 과제에 시기상조이다.
267 | A company routinely outsources resources for specific core activities. Due to a sudden, unforeseen risk, all of the team members are needed to work remotely, including the outsourced ones. How can the project manager address this challenge to ensure outsourced vendors deliver? | Review the coordination and communication costs with the supplier. | Develop a new strategy for communication and management of resources. | Review the risk management plan for the mitigation activities. | Submit a change request to increase the contingency budget. |  | B | When outsourced resources must suddenly work remotely due to an unforeseen risk, the project manager should develop a new strategy for communication and management of resources. A revised strategy addresses the changed working conditions. Reviewing coordination costs (A) is financial, not operational. Reviewing the risk management plan (C) is analytical. Submitting a change request for contingency budget (D) does not address the communication challenge. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 회사가 일상적으로 특정 핵심 활동에 대해 자원을 외주하고 있다. 갑작스러운 예상치 못한 리스크로 인해, 외주 인력을 포함한 모든 팀원이 원격으로 근무해야 한다. 프로젝트 관리자는 외주 벤더가 전달하도록 보장하기 위해 이 과제를 어떻게 해결할 수 있는가? | 공급업체와 조율 및 의사소통 비용을 검토한다. | 의사소통 및 자원 관리를 위한 새로운 전략을 개발한다. | 완화 활동을 위한 리스크 관리 계획을 검토한다. | 비상 예산을 증가시키기 위한 변경 요청을 제출한다. |  | B | 예상치 못한 리스크로 외주 자원이 갑자기 원격으로 근무해야 할 때, 프로젝트 관리자는 의사소통 및 자원 관리를 위한 새로운 전략을 개발해야 한다. 수정된 전략은 변경된 작업 조건을 다룬다. 조율 비용 검토(A)는 재정적이지 운영적이지 않다. 리스크 관리 계획 검토(C)는 분석적이다. 비상 예산 변경 요청(D)은 의사소통 과제를 다루지 않는다.
268 | A project manager is having difficulty obtaining final acceptance of some deliverables from a stakeholder for reasons that seem to be outside of the project acceptance criteria. What should the project manager do? | Obtain final acceptance from another stakeholder who is also familiar with the project | Persuade this stakeholder using emotional intelligence skills to obtain acceptance. | Create a project acceptance waiver noting the stakeholder's concerns so they can be addressed later | Escalate this issue to the project sponsor and ask for support in obtaining final stakeholder acceptance. |  | B | The PM should use interpersonal skills—including emotional intelligence, influencing, and negotiation—to persuade the stakeholder to accept deliverables based on established project acceptance criteria. Emotional intelligence enables the PM to understand and manage emotions in the interaction. Influencing helps change attitudes or behaviors toward a desired outcome. Negotiation facilitates agreement between parties. These skills are more effective than bypassing the stakeholder's authority, creating dependency on the sponsor, or postponing the issue. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트 관리자가 프로젝트 인수 기준 외의 이유로 이해관계자로부터 일부 산출물의 최종 승인을 얻는 데 어려움을 겪고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트에 익숙한 다른 이해관계자로부터 최종 승인을 얻는다. | 감성 지능 기술을 사용하여 이 이해관계자를 설득하여 승인을 얻는다. | 이해관계자의 우려를 기록한 프로젝트 승인 면제를 작성하여 나중에 다룰 수 있도록 한다. | 이 문제를 프로젝트 스폰서에게 에스컬레이션하고 최종 이해관계자 승인을 얻는 데 지원을 요청한다. |  | B | PM은 확립된 프로젝트 인수 기준에 기반하여 이해관계자가 산출물을 승인하도록 감성 지능, 영향력, 협상 등 대인 관계 기술을 사용해야 한다. 감성 지능은 PM이 상호작용에서 감정을 이해하고 관리할 수 있게 한다. 영향력은 원하는 결과를 향한 태도나 행동 변화를 돕는다. 협상은 당사자 간 합의를 촉진한다. 이러한 기술은 이해관계자의 권한을 우회하거나, 스폰서에 대한 의존성을 만들거나, 문제를 연기하는 것보다 효과적이다.
269 | An organization embarking on a significant transformation initiated a project to improve and document business processes. One of the objectives of the project is to implement agile project delivery. What is the main reason for adopting agile? | Projects will be completed faster, saving time and money. | Projects will be delivered with significant cost savings. | Projects will be delivered with very low risk to the organization. | Projects will deliver early and use value based on priority. |  | D | The main reason for adopting agile in a business process improvement project is that projects will deliver early and use value based on priority. Agile enables incremental delivery prioritized by customer and business value, allowing early benefits realization and adaptation. Faster completion (A) is a potential benefit but not the main reason. Significant cost savings (B) is not guaranteed. Very low risk (C) is not a defining agile characteristic. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Agile General Practices | Process | Manage Project Closure | Governance | Closing | Build an Empowered Culture | Close Project or Phase | Traditional PM | 중대한 혁신을 시작하는 조직이 비즈니스 프로세스를 개선하고 문서화하는 프로젝트를 시작했다. 프로젝트의 목표 중 하나는 애자일 프로젝트 전달을 구현하는 것이다. 애자일을 채택하는 주요 이유는 무엇인가? | 프로젝트가 더 빨리 완료되어 시간과 비용을 절약한다. | 프로젝트가 상당한 비용 절감으로 전달된다. | 프로젝트가 조직에 매우 낮은 리스크로 전달된다. | 프로젝트가 조기에 전달되고 우선순위에 따라 가치를 활용한다. |  | D | 비즈니스 프로세스 개선 프로젝트에서 애자일을 채택하는 주요 이유는 프로젝트가 조기에 전달되고 우선순위에 따라 가치를 활용하기 때문이다. 애자일은 고객과 비즈니스 가치에 따라 우선순위가 정해진 점진적 전달을 가능하게 하여 조기 이익 실현과 적응을 허용한다. 더 빠른 완료(A)는 잠재적 이점이지만 주요 이유는 아니다. 상당한 비용 절감(B)은 보장되지 않는다. 매우 낮은 리스크(C)는 애자일의 특징적 특성이 아니다.
270 | Two project managers are competing to assign a key subject matter expert (SME) to their concurrently scheduled projects. Work requiring constant physical presence means the SME can serve on only one project at a time. What should the project managers do first to facilitate allocation of the resource? | Evaluate the associated budget and schedule based on the SME assignment | Assess both projects to determine the business benefits based on the SME assignment | Determine the cost performance index (CPI) based on the SME assignment | Calculate the schedule performance index (SPI) based on the SME assignment |  | B | When two project managers compete for the same non-shareable SME for concurrent projects, they should first assess both projects to determine business benefits based on the SME assignment. Value-based prioritization ensures strategic resource allocation. Evaluating budget and schedule (A) is secondary to value assessment. Calculating CPI (C) or SPI (D) measures execution performance, not forward-looking resource allocation. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Traditional PM | 두 명의 프로젝트 관리자가 동시 예정된 프로젝트에 주요 주제 전문가(SME)를 배정하기 위해 경쟁하고 있다. 지속적인 물리적 입회가 필요한 작업 특성상 SME는 한 번에 한 프로젝트에만 참여할 수 있다. 프로젝트 관리자들은 자원 배분을 촉진하기 위해 먼저 무엇을 해야 하는가? | SME 배정에 따른 관련 예산과 일정을 평가한다. | SME 배정에 따른 비즈니스 이점을 결정하기 위해 두 프로젝트를 평가한다. | SME 배정에 따른 비용 성과 지수(CPI)를 결정한다. | SME 배정에 따른 일정 성과 지수(SPI)를 계산한다. |  | B | 동시 프로젝트에 대해 두 프로젝트 관리자가 공유할 수 없는 동일한 SME를 두고 경쟁할 때, 먼저 SME 배정에 따른 비즈니스 이점을 결정하기 위해 두 프로젝트를 평가해야 한다. 가치 기반 우선순위 지정은 전략적 자원 배분을 보장한다. 예산과 일정 평가(A)는 가치 평가에 부차적이다. CPI 계산(C) 또는 SPI 계산(D)은 실행 성과를 측정하지 미래 지향적 자원 배분은 아니다.
271 | A project charter has been approved and the project manager has been assigned to the project. The project manager is currently working with the project team to subdivide the project work packages. What is the project manager doing? | Decomposition | Resource leveling | Work breakdown structure (WBS) | Network diagram |  | C | When the project manager is working with the team to subdivide project work packages, they are creating a Work Breakdown Structure (WBS). WBS decomposes deliverables into manageable components through decomposition. Resource leveling (B) optimizes resource allocation. A network diagram (D) maps task dependencies. Decomposition (A) is the technique, but the output being created is the WBS. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | WBS/Decomposition | Process | Develop and Manage Scope | Scope | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 헌장이 승인되었고 프로젝트 관리자가 프로젝트에 배정되었다. 프로젝트 관리자는 현재 프로젝트 팀과 함께 프로젝트 작업 패키지를 세분화하는 작업을 하고 있다. 프로젝트 관리자는 무엇을 하고 있는가? | 분해 | 자원 평준화 | 작업 분류 체계(WBS) | 네트워크 다이어그램 |  | C | 프로젝트 관리자가 팀과 함께 프로젝트 작업 패키지를 세분화할 때, 작업 분류 체계(WBS)를 만들고 있는 것이다. WBS는 분해를 통해 산출물을 관리 가능한 구성요소로 분해한다. 자원 평준화(B)는 자원 배분을 최적화한다. 네트워크 다이어그램(D)은 작업 종속성을 매핑한다. 분해(A)는 기법이지만, 만들어지고 있는 산출물은 WBS이다.
272 | A team has developed and tested new software to control airplanes during flights. There are several regulatory requirements that must be met. What should the project manager do to meet these requirements? | Ask human resources (HR) to assign a compliance specialist to the team. | Measure the extent to which the project complies with the regulations. | Validate that the software is compliant with standards and regulations. | Determine potential threats regarding compliance with the regulations. |  | C | When software controlling airplanes must meet several regulatory requirements, the project manager should validate that the software is compliant with standards and regulations. Compliance validation is essential for safety-critical systems. Asking HR to assign a compliance specialist (A) is one support but not the primary action. Measuring compliance extent (B) is part of validation but not the complete action. Determining potential threats (D) is risk identification, not compliance assurance. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Scope & Requirements Mgmt | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | 팀이 비행 중 비행기를 제어하는 새로운 소프트웨어를 개발하고 테스트했다. 충족해야 할 여러 규제 요구사항이 있다. 프로젝트 관리자는 이러한 요구사항을 충족하기 위해 무엇을 해야 하는가? | 인사(HR)에 요청하여 팀에 규정 준수 전문가를 배정한다. | 프로젝트가 규정을 준수하는 정도를 측정한다. | 소프트웨어가 표준 및 규정을 준수하는지 검증한다. | 규정 준수와 관련된 잠재적 위협을 결정한다. |  | C | 비행기를 제어하는 소프트웨어가 여러 규제 요구사항을 충족해야 할 때, 프로젝트 관리자는 소프트웨어가 표준 및 규정을 준수하는지 검증해야 한다. 규정 준수 검증은 안전 중요 시스템에 필수적이다. HR에 규정 준수 전문가 배정 요청(A)은 하나의 지원이지만 주요 조치는 아니다. 준수 정도 측정(B)은 검증의 일부이지만 완전한 조치는 아니다. 잠재적 위협 결정(D)은 리스크 식별이지 규정 준수 보장이 아니다.
273 | A project manager is assigned to a strategic communication project that involves subject matter experts (SMEs), interns, and new recruits. The project manager discovers that the project is not gaining much traction due to knowledge gaps from the interns. The budget for training is exhausted and the project needs to be delivered without delay. Which two actions should the project manager take? (Choose two) | Initiate a project change request for additional budget to train the interns and newrecruits. | Hire more SMEs and inform the human resources manager to lay off thenonperforming interns and new recruits. | Ignore the issues with the project and try to deliver the project successfully withoutasking for training funds. | Identify the sources and specifics of the knowledge gap from the interns and newrecruits. | Put the interns and new recruits into groups and assign a SME as a mentor. | D, E | When knowledge gaps from interns stall a strategic project with an exhausted training budget, the project manager should (D) identify the sources and specifics of the knowledge gap, and (E) put interns and new recruits into groups with SME mentors. Targeted gap analysis and mentoring leverage existing resources. Initiating a change request for budget (A) may not be timely. Hiring more SMEs and laying off interns (B) is disproportionate. Ignoring the issues (C) risks project failure. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Traditional PM | 프로젝트 관리자가 주제 전문가(SME), 인턴, 신규 입사자가 포함된 전략적 커뮤니케이션 프로젝트에 배정되었다. 프로젝트 관리자는 인턴들의 지식 격차로 인해 프로젝트가 많은 추진력을 얻지 못하고 있음을 발견했다. 교육 예산은 소진되었고 프로젝트는 지연 없이 전달되어야 한다. 프로젝트 관리자가 취해야 할 두 가지 조치는 무엇인가? (2개 선택) | 인턴과 신규 입사자를 교육하기 위한 추가 예산을 위한 프로젝트 변경 요청을 시작한다. | 더 많은 SME를 고용하고 성과가 부진한 인턴과 신규 입사자를 해고하도록 인사 관리자에게 알린다. | 프로젝트의 문제를 무시하고 교육 자금을 요청하지 않고 프로젝트를 성공적으로 전달하려고 노력한다. | 인턴과 신규 입사자의 지식 격차의 출처와 세부 사항을 파악한다. | 인턴과 신규 입사자를 그룹으로 묶고 SME를 멘토로 배정한다. | D, E | 인턴의 지식 격차가 교육 예산이 소진된 전략적 프로젝트를 정체시킬 때, 프로젝트 관리자는 (D) 지식 격차의 출처와 세부 사항을 파악하고, (E) 인턴과 신규 입사자를 SME 멘토와 함께 그룹으로 묶어야 한다. 목표 격차 분석과 멘토링은 기존 자원을 활용한다. 예산 변경 요청(A)은 적시성이 없을 수 있다. SME 추가 고용과 인턴 해고(B)는 불균형적이다. 문제 무시(C)는 프로젝트 실패 위험이 있다.
274 | A stakeholder is requesting that the project manager share project status updates on a regular basis. This stakeholder is not included in the regular distribution list. What should the project manager do? | Ask the stakeholder ' s manager if the stakeholder can be added to the list. | Review the stakeholder engagement and communications management plans. | Start sending status updates to this stakeholder based on the request. | Escalate the stakeholder's request to the project sponsor. |  | B | When a stakeholder not on the distribution list requests regular status updates, the project manager should review the stakeholder engagement and communications management plans. These documents guide decisions about stakeholder engagement levels and communication methods. Sending updates based on the request (C) may violate communication protocols. Asking the stakeholder's manager (A) bypasses the stakeholder's preference. Escalating to the sponsor (D) is unnecessary for a routine communication adjustment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 이해관계자가 프로젝트 관리자에게 정기적으로 프로젝트 현황 업데이트를 공유해 달라고 요청하고 있다. 이 이해관계자는 정기 배포 목록에 포함되어 있지 않다. 프로젝트 관리자는 어떻게 해야 하는가? | 이해관계자의 관리자에게 이해관계자를 목록에 추가할 수 있는지 묻는다. | 이해관계자 참여 및 의사소통 관리 계획을 검토한다. | 요청에 따라 이 이해관계자에게 현황 업데이트를 보내기 시작한다. | 이해관계자의 요청을 프로젝트 스폰서에게 에스컬레이션한다. |  | B | 배포 목록에 없는 이해관계자가 정기 현황 업데이트를 요청할 때, 프로젝트 관리자는 이해관계자 참여 및 의사소통 관리 계획을 검토해야 한다. 이러한 문서는 이해관계자 참여 수준과 의사소통 방법에 대한 결정을 안내한다. 요청에 따른 업데이트 발송(C)은 의사소통 프로토콜을 위반할 수 있다. 이해관계자 관리자에게 문의(A)는 이해관계자의 선호를 우회한다. 스폰서에게 에스컬레이션(D)은 일상적인 의사소통 조정에 불필요하다.
275 | A project team consists of members based in country A and subject matter experts (SMEs) based in country B with a 12-hour time difference. What can the project manager do to improve interactions between the team members in both countries? | Identify virtual communication methods and arrange for regular team meetingsaccordingly. | Plan for frequent face-to-face meetings. | Ensure full participation of both the product owner and business SMEs in scopeplanning sessions. | Explore the opportunity to have both teams colocated. |  | A | When team members in countries with a 12-hour time difference need better interaction, the project manager should identify virtual communication methods and arrange regular team meetings accordingly. Structured virtual communication bridges time zones. Planning frequent face-to-face meetings (B) may not be feasible. Ensuring PO and SME participation in scope sessions (C) addresses one aspect. Exploring colocation (D) may not be practical. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀은 A국에 기반을 둔 팀원과 B국에 기반을 둔 주제 전문가(SME)로 구성되어 있으며, 12시간의 시차가 있다. 프로젝트 관리자는 두 국가의 팀원 간 상호작용을 개선하기 위해 무엇을 할 수 있는가? | 가상 의사소통 방법을 파악하고 이에 맞게 정기 팀 회의를 주선한다. | 빈번한 대면 회의를 계획한다. | 제품 책임자와 비즈니스 SME 모두의 범위 계획 세션 전체 참여를 보장한다. | 두 팀의 공동 배치 기회를 탐색한다. |  | A | 12시간 시차가 있는 국가의 팀원이 더 나은 상호작용이 필요할 때, 프로젝트 관리자는 가상 의사소통 방법을 파악하고 이에 맞게 정기 팀 회의를 주선해야 한다. 구조화된 가상 의사소통은 시간대를 연결한다. 빈번한 대면 회의 계획(B)은 실현 불가능할 수 있다. PO와 SME의 범위 세션 참여 보장(C)은 한 가지 측면만 다룬다. 공동 배치 탐색(D)은 실용적이지 않을 수 있다.
276 | Just as a team reaches a mutual consensus on a preferred design, a stakeholder submits a request to add new features that enhance the company's competitive advantage. What should the project manager do? | Encourage the project team to add premium features to impress the client. | Allow all requested changes and bypass the company ' s change control process. | Start the process to include the new features of the product on the next iteration. | Reject all requested changes and bypass the company ' s change control process. |  | C | When a stakeholder requests new features enhancing competitive advantage just after the team reaches design consensus, the project manager should start the process to include the new features in the next iteration. This follows proper change management while keeping the current work intact. Encouraging the team to add premium features (A) bypasses change control. Allowing all changes without change control (B) is undisciplined. Rejecting all changes without evaluation (D) ignores potentially valuable input. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 팀이 선호하는 설계에 대해 상호 합의에 도달한 직후, 이해관계자가 회사의 경쟁 우위를 향상시키는 새로운 기능 추가 요청을 제출한다. 프로젝트 관리자는 어떻게 해야 하는가? | 고객을 감동시키기 위해 프로젝트 팀에게 프리미엄 기능을 추가하도록 권장한다. | 모든 요청된 변경을 허용하고 회사의 변경 통제 프로세스를 우회한다. | 다음 이터레이션에서 제품의 새로운 기능을 포함하는 프로세스를 시작한다. | 모든 요청된 변경을 거부하고 회사의 변경 통제 프로세스를 우회한다. |  | C | 팀이 설계 합의에 도달한 직후 이해관계자가 경쟁 우위를 향상시키는 새 기능을 요청할 때, 프로젝트 관리자는 다음 이터레이션에서 새 기능을 포함하는 프로세스를 시작해야 한다. 이는 현재 작업을 유지하면서 적절한 변경 관리를 따른다. 팀에게 프리미엄 기능 추가 권장(A)은 변경 통제를 우회한다. 변경 통제 없이 모든 변경 허용(B)은 무질서하다. 평가 없이 모든 변경 거부(D)는 잠재적으로 가치 있는 입력을 무시한다.
277 | A project manager's project relies on services from a department that has a new leader. Since the new leader was appointed, the services from their department have been slow, which threatens the project's delivery deadline. What should the project manager do? | Arrange a meeting with the leader to explain the project ' s needs and understand the leader ' s perspective. | Add the issue to the issue log and communicate the issue in the next regular report to project stakeholders. | Escalate the issue to the project sponsor notifying them of the slow services from the department. | Send all service requests to the department earlier in the project to lessen the impact on the delivery date. |  | A | When a new department leader's slow services threaten the project delivery deadline, the project manager should arrange a meeting with the leader to explain the project's needs and understand the leader's perspective. Direct, collaborative engagement addresses the issue at its source. Adding to the issue log and regular reporting (B) defers action. Escalating to the sponsor (C) is premature before direct engagement. Sending requests earlier (D) is a workaround, not a solution. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | 프로젝트 관리자의 프로젝트는 새 리더가 있는 부서의 서비스에 의존한다. 새 리더가 임명된 이후, 해당 부서의 서비스가 느려져 프로젝트의 전달 기한을 위협하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 리더와 미팅을 주선하여 프로젝트의 요구를 설명하고 리더의 관점을 이해한다. | 이슈를 이슈 로그에 추가하고 다음 정기 보고에서 프로젝트 이해관계자에게 이슈를 전달한다. | 부서의 느린 서비스를 프로젝트 스폰서에게 에스컬레이션한다. | 전달 날짜에 대한 영향을 줄이기 위해 모든 서비스 요청을 프로젝트 초기에 부서에 보낸다. |  | A | 새 부서 리더의 느린 서비스가 프로젝트 전달 기한을 위협할 때, 프로젝트 관리자는 리더와 미팅을 주선하여 프로젝트의 요구를 설명하고 리더의 관점을 이해해야 한다. 직접적이고 협력적인 참여는 문제의 근원에서 해결한다. 이슈 로그 추가와 정기 보고(B)는 조치를 지연시킨다. 스폰서에게 에스컬레이션(C)은 직접 참여 전에 시기상조이다. 요청을 더 일찍 보내는 것(D)은 우회책이지 해결책이 아니다.
278 | A team member has encountered a technical issue similar to the one faced in a successfully closed project. However, the team member did not know about the previous project and would like to resolve the issue on their own. What should the project manager do? | Reach out to the project manager of the previous project for assistance | Share the lessons learned from the previous protect with the team member | Allow the team member to work through the issue as a training opportunity | Improve the risk management strategy and risk monitoring |  | B | When a team member encounters a technical issue similar to one resolved in a previous project but is unaware of it, the project manager should share the lessons learned from the previous project with the team member. Leveraging organizational knowledge prevents redundant effort. Reaching out to the previous PM (A) adds a step. Allowing self-resolution as training (C) wastes time on a solved problem. Improving risk management (D) is a process change, not an immediate solution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 팀원이 성공적으로 종료된 프로젝트에서 겪었던 것과 유사한 기술적 문제를 발견했다. 그러나 팀원은 이전 프로젝트에 대해 몰랐으며 스스로 문제를 해결하고 싶어 한다. 프로젝트 관리자는 어떻게 해야 하는가? | 이전 프로젝트의 프로젝트 관리자에게 도움을 요청한다. | 이전 프로젝트의 교훈을 팀원과 공유한다. | 팀원이 훈련 기회로서 문제를 해결하도록 허용한다. | 리스크 관리 전략과 리스크 모니터링을 개선한다. |  | B | 팀원이 이전 프로젝트에서 해결된 것과 유사한 기술적 문제를 발견했지만 이를 모를 때, 프로젝트 관리자는 이전 프로젝트의 교훈을 팀원과 공유해야 한다. 조직 지식을 활용하면 중복 노력을 방지한다. 이전 PM에게 연락(A)은 단계를 추가한다. 훈련으로 자체 해결 허용(C)은 이미 해결된 문제에 시간을 낭비한다. 리스크 관리 개선(D)은 프로세스 변경이지 즉각적인 해결책이 아니다.
279 | A key stakeholder asks the project manager to complete all deliverables sooner than the agreed-upon schedule. The project is halfway complete and currently has a schedule performance index (SPI) of 0.9 and a cost performance index (CPI) of 1. What should the project manager do first before committing to the stakeholder? | Add more resources to complete the remaining deliverables early. | Prioritize critical activities and skip noncritical activities. | Perform several activities in parallel to compress the schedule. | Review and analyze the risks associated with compressing the schedule. |  | D | With an SPI of 0.9 indicating the project is already behind schedule and a CPI of 1.0 showing costs are on plan, the project manager should first review and analyze the risks associated with compressing the schedule before committing to an earlier delivery. Schedule compression can increase risks—including quality issues, rework, and coordination problems—and may affect cost performance. Only after thorough risk analysis can the PM recommend an informed approach. Adding more resources (A) may increase costs and is one possible response, not the first step. Skipping noncritical activities (B) may violate scope or quality commitments. Performing parallel activities (C) is fast-tracking, which should not be chosen without first understanding its risks. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Schedule | Planning | Focus on Value | Define Activities | Traditional PM | 핵심 이해관계자가 프로젝트 관리자에게 합의된 일정보다 앞당겨 모든 산출물을 완료해 달라고 요청한다. 프로젝트는 절반 완료되었으며 현재 일정 성과 지수(SPI)가 0.9이고 비용 성과 지수(CPI)가 1이다. 프로젝트 관리자는 이해관계자에게 약속하기 전에 먼저 무엇을 해야 하는가? | 남은 산출물을 조기에 완료하기 위해 더 많은 자원을 추가한다. | 주요 활동의 우선순위를 정하고 비주요 활동을 건너떴다. | 일정을 압축하기 위해 여러 활동을 병렬로 수행한다. | 일정 압축과 관련된 리스크를 검토하고 분석한다. |  | D | SPI가 0.9로 프로젝트가 이미 일정에 뒤캘어 있고 CPI가 1.0으로 비용이 계획대로일 때, 프로젝트 관리자는 조기 전달에 약속하기 전에 먼저 일정 압축과 관련된 리스크를 검토하고 분석해야 한다. 일정 압축은 품질 문제, 재작업, 조율 문제 등 리스크를 증가시킬 수 있으며 비용 성과에 영향을 미칠 수 있다. 철저한 리스크 분석 후에만 PM이 정보에 입각한 접근 방식을 권고할 수 있다. 자원 추가(A)는 비용을 증가시킬 수 있으며 첫 번째 단계가 아니다. 비주요 활동 건너뛰기(B)는 범위나 품질 약속을 위반할 수 있다. 병렬 활동 수행(C)은 빠른 추적으로, 리스크를 먼저 이해하지 않고 선택해서는 안 된다.
280 | A project manager is hired to work on a very large, complex project that requires the team to complete a significant number of specialized tasks. What strategy should the project manager incorporate to help organize, assign, and monitor these tasks? | Prepare a resource management plan that details all the resources needed to complete the tasks. | Schedule a meeting with the stakeholders to determine which tasks can be eliminated. | Create a list of the tasks and send it to the project sponsor for review and approval. | Develop a work breakdown structure (WBS) that decomposes the project deliverables into work packages. |  | D | When a large complex project has many specialized tasks to organize, assign, and monitor, the project manager should develop a work breakdown structure that decomposes deliverables into work packages. WBS provides a structured scope hierarchy. Preparing a resource management plan (A) supports allocation but not task decomposition. Meeting stakeholders to eliminate tasks (B) is premature. Sending a task list to the sponsor (C) lacks structure. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | WBS/Decomposition | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 프로젝트 관리자가 팀이 상당수의 전문 작업을 완료해야 하는 매우 크고 복잡한 프로젝트에 고용되었다. 프로젝트 관리자는 이러한 작업을 조직하고, 배정하고, 모니터링하는 데 도움이 되는 어떤 전략을 포함시켜야 하는가? | 작업을 완료하는 데 필요한 모든 자원을 상세히 설명하는 자원 관리 계획을 준비한다. | 이해관계자와 회의를 예약하여 제거할 수 있는 작업을 결정한다. | 작업 목록을 만들어 프로젝트 스폰서에게 검토 및 승인을 위해 보낸다. | 프로젝트 산출물을 작업 패키지로 분해하는 작업 분류 체계(WBS)를 개발한다. |  | D | 대규모 복잡한 프로젝트에 조직하고 배정하고 모니터링해야 할 많은 전문 작업이 있을 때, 프로젝트 관리자는 산출물을 작업 패키지로 분해하는 작업 분류 체계를 개발해야 한다. WBS는 구조화된 범위 계층 구조를 제공한다. 자원 관리 계획 준비(A)는 할당을 지원하지만 작업 분해는 아니다. 작업 제거를 위한 이해관계자 회의(B)는 시기상조이다. 스폰서에게 작업 목록 발송(C)은 구조가 부족하다.
281 | A project manager has been assigned to a hybrid project that must receive approval from a government regulator. During the daily standups, one member reported an impediment that requires collaboration from an expert who is assigned to another project. What should the project manager do first in this situation? | Develop the team member ' s capacities through mentoring and training. | Ask the project sponsor to assign a new resource with the necessary expertise to the team. | Check the expert ' s availability within the organization on an as-needed basis. | Review the project ' s key performance indicators (KPIs) to determine the impact of this assignment. |  | A | When a team member reports an impediment requiring collaboration from an expert assigned to another project, the project manager should first develop the team member's capacities through mentoring and training. Building internal capability reduces dependency on external experts and strengthens the team's long-term ability to address similar issues. Asking the sponsor for a new resource (B) may be slow. Checking the expert's availability on an as-needed basis (C) addresses the immediate need but does not build team capability. Reviewing KPIs (D) assesses impact but does not resolve the impediment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 정부 규제 기관의 승인을 받아야 하는 하이브리드 프로젝트에 배정되었다. 일일 스탠드업 중 한 팀원이 다른 프로젝트에 배정된 전문가의 협력이 필요한 장애물을 보고했다. 이 상황에서 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 멘토링과 교육을 통해 팀원의 역량을 개발한다. | 프로젝트 스폰서에게 필요한 전문 지식을 갖춘 새로운 자원을 팀에 배정하도록 요청한다. | 조직 내에서 필요에 따라 전문가의 가용성을 확인한다. | 이 배정의 영향을 결정하기 위해 프로젝트의 핵심 성과 지표(KPI)를 검토한다. |  | A | 팀원이 다른 프로젝트에 배정된 전문가의 협력이 필요한 장애물을 보고할 때, 프로젝트 관리자는 먼저 멘토링과 교육을 통해 팀원의 역량을 개발해야 한다. 내부 역량 구축은 외부 전문가에 대한 의존도를 줄이고 팀의 장기적 대응 능력을 강화한다. 스폰서에게 새 자원 요청(B)은 느릴 수 있다. 필요에 따른 전문가 가용성 확인(C)은 즉각적인 필요를 다루지만 팀 역량을 구축하지 않는다. KPI 검토(D)는 영향을 평가하지만 장애물을 해결하지 않는다.
282 | A project manager has been assigned as the servant leader for an ongoing project that historically has presented unexpected problems. The main stakeholder is hesitant to continue with the rest of the sprints even though there are no open issues or indications of risks at this stage. What should the project manager do to address this concern? | Create a new risk entry to identify the stakeholder as a detractor. | Increase the contingency reserves to cover unknown-unknowns. | Increase the management reserves to convert the known-unknowns. | Implement short cycles for inspection and provide feedback. |  | D | Short inspection and feedback cycles align with both servant leadership and agile principles. Regular iterations enable continuous progress assessment and early detection of potential issues. This approach demonstrates progress to hesitant stakeholders, manages risks proactively, and maintains open communication channels—building confidence through transparency rather than requiring blind trust in the process. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 관리자가 역사적으로 예상치 못한 문제가 있었던 진행 중인 프로젝트의 서반트 리더로 배정되었다. 주요 이해관계자는 이 단계에서 미결 이슈나 리스크 징후가 없음에도 불구하고 나머지 스프린트를 계속하는 것을 망설이고 있다. 프로젝트 관리자는 이 우려를 해결하기 위해 무엇을 해야 하는가? | 이해관계자를 반대자로 식별하는 새로운 리스크 항목을 생성한다. | 알려지지 않은 알려지지 않은 것(unknown-unknowns)을 커버하기 위해 예비비를 증가시킨다. | 알려진 알려지지 않은 것(known-unknowns)을 전환하기 위해 관리 예비비를 증가시킨다. | 짧은 주기로 검사하고 피드백을 제공한다. |  | D | 짧은 검사 및 피드백 주기는 서반트 리더십과 애자일 원칙 모두에 부합한다. 정기적인 이터레이션은 지속적인 진행 평가와 잠재적 문제의 조기 감지를 가능하게 한다. 이 접근 방식은 망설이는 이해관계자에게 진행 상황을 보여주고, 리스크를 능동적으로 관리하며, 개방적인 의사소통 채널을 유지하여—프로세스에 대한 맹목적 신뢰를 요구하지 않고 투명성을 통해 신뢰를 구축한다.
283 | A project to add metro stations is being executed, with seven out of eight stations currently in place. Suddenly, a notification from the local community is received, demanding that the project be stopped. What should the project manager do first? | Estimate the cost of changing the project location. | Meet with the project stakeholders to define a mitigation plan. | Execute the contingency plan defined in the risk management plan. | Register the issue and escalate it to the project sponsor. |  | D | When a local community demands a project stoppage, this represents an active issue—not merely a risk—requiring immediate formal documentation and escalation. The PM should register the issue and escalate it to the project sponsor, as halting public infrastructure likely exceeds the PM's decision-making authority. Contingency plans (B) apply to identified risks, not active issues. Meetings (C) may follow but shouldn't precede formal documentation. Relocating (D) is premature before governance intervention. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 지하철역 추가 프로젝트가 실행 중이며, 8개 역 중 7개가 현재 완성되었다. 갑자기 지역 커뮤니티로부터 프로젝트 중단을 요구하는 통보가 접수되었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트 위치 변경 비용을 추정한다. | 프로젝트 이해관계자와 만나 완화 계획을 정의한다. | 리스크 관리 계획에 정의된 비상 계획을 실행한다. | 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션한다. |  | D | 지역 커뮤니티가 프로젝트 중단을 요구할 때, 이는 단순한 리스크가 아닌 활성 이슈로서 즉각적인 공식 문서화와 에스컬레이션이 필요하다. PM은 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션해야 한다. 공공 인프라 중단은 PM의 의사결정 권한을 초과할 수 있기 때문이다. 비상 계획(B)은 식별된 리스크에 적용되며 활성 이슈에는 아니다. 미팅(C)은 후속 조치이지 공식 문서화에 선행해서는 안 된다. 이전(D)은 거버넌스 개입 전에 시기상조이다.
284 | A technical lead has complained to the project manager about a team member's performance. The team member has repeatedly missed tasks that have put sprint commitments at risk. What should the project manager do? | Meet with the team member to understand the situation and provide feedback. | Remove the learn member from the team and hue a more skilled one | Ask the technical lead to provide more training to the team member | Ask the technical lead to discuss performance directly with the team member |  | A | When a technical lead reports a team member repeatedly missing tasks and risking sprint commitments, the project manager should meet with the team member to understand the situation and provide feedback. Direct, empathetic engagement addresses root causes. Removing the team member (B) is extreme without investigation. Asking the lead to provide more training (C) assumes the issue is skill-based. Asking the lead to discuss performance directly (D) delegates the PM's responsibility. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Help Ensure Knowledge Transfer | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 기술 리드가 프로젝트 관리자에게 팀원의 성과에 대해 불만을 제기했다. 팀원이 반복적으로 작업을 누락하여 스프린트 약속을 위험에 빠뜨리고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀원과 만나 상황을 이해하고 피드백을 제공한다. | 팀원을 팀에서 제거하고 더 숙련된 사람을 고용한다. | 기술 리드에게 팀원에게 더 많은 교육을 제공하도록 요청한다. | 기술 리드에게 팀원과 직접 성과에 대해 논의하도록 요청한다. |  | A | 기술 리드가 팀원이 반복적으로 작업을 누락하고 스프린트 약속을 위험에 빠뜨린다고 보고할 때, 프로젝트 관리자는 팀원과 만나 상황을 이해하고 피드백을 제공해야 한다. 직접적이고 공감적인 참여는 근본 원인을 다룬다. 팀원 제거(B)는 조사 없이 극단적이다. 리드에게 더 많은 교육 제공 요청(C)은 문제가 기술 기반이라고 가정한다. 리드에게 직접 성과 논의 요청(D)은 PM의 책임을 위임한다.
285 | A high-performing team is involved in a project with a new domain. The team is unable to deliver as expected. What should the project manager do? | Support the team in identifying the area of development and address the gap. | Set up a clear expectation that the team is to deliver as in their previous projects. | Dissolve the team and include the team members in other existing teams. | Identify the struggling team members and move them out of the team. |  | A | When a high-performing team is unable to deliver as expected in a new domain, the project manager should support the team in identifying the area of development and address the gap. Targeted development leverages existing team strengths. Setting expectations based on past performance (B) ignores the new domain challenges. Dissolving the team (C) wastes talent. Identifying and removing struggling members (D) undermines team cohesion. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 고성과 팀이 새로운 도메인의 프로젝트에 참여하고 있다. 팀은 기대만큼 전달하지 못하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀이 개발 영역을 식별하고 격차를 해소하도록 지원한다. | 이전 프로젝트에서처럼 전달하도록 팀에 명확한 기대치를 설정한다. | 팀을 해체하고 팀원을 다른 기존 팀에 포함시킨다. | 어려움을 겪는 팀원을 식별하여 팀에서 제외한다. |  | A | 고성과 팀이 새로운 도메인에서 기대만큼 전달하지 못할 때, 프로젝트 관리자는 팀이 개발 영역을 식별하고 격차를 해소하도록 지원해야 한다. 목표 개발은 기존 팀 강점을 활용한다. 과거 성과 기반 기대치 설정(B)은 새로운 도메인의 도전을 무시한다. 팀 해체(C)는 인재를 낭비한다. 어려움을 겪는 팀원 식별 및 제거(D)는 팀 응집력을 약화시킨다.
286 | A large multi-year project requires highly skilled staff for successful deployment. The management team and the project sponsor have analyzed the resource requirements and agreed to have permanent staff hired for the project to avoid potential budget overrun. However, there is a risk of staff turnover during the course of the project, which may have an impact on the delivery. Which two actions should the project manager take to mitigate this risk? (Choose two) | Meet with management to discuss dividing the project into smaller projects | Introduce a recognition program to motivate and reward resource performance | Enhance the competencies of the project team through training, mentoring and coaching. | Increase the trained staff to create back-up for resources | Convince senior management to hire third-party staff | B, C | To mitigate the risk of staff turnover during a large multi-year project with permanent staff, the project manager should take two actions: introduce a recognition program to motivate and reward resource performance (B), and enhance competencies through training, mentoring, and coaching (C). Recognition increases satisfaction and loyalty, while skill development provides growth opportunities that reduce turnover motivation. Increasing trained staff as backup (D) creates redundancy and potential confusion. Dividing into smaller projects (A) may affect scope and benefits. Hiring third-party staff (E) increases complexity and may not improve retention. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Help Ensure Knowledge Transfer | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 대규모 다년 프로젝트는 성공적인 배포를 위해 고도로 숙련된 직원이 필요하다. 경영진과 프로젝트 스폰서는 잠재적인 예산 초과를 피하기 위해 프로젝트에 정규 직원을 고용하기로 자원 요구사항을 분석하고 합의했다. 그러나 프로젝트 진행 중 직원 이직의 리스크가 있으며, 이는 전달에 영향을 미칠 수 있다. 프로젝트 관리자가 이 리스크를 완화하기 위해 취해야 할 두 가지 조치는 무엇인가? (2개 선택) | 프로젝트를 더 작은 프로젝트로 분할하는 것에 대해 경영진과 논의한다. | 자원 성과를 동기 부여하고 보상하기 위한 인정 프로그램을 도입한다. | 교육, 멘토링, 코칭을 통해 프로젝트 팀의 역량을 강화한다. | 자원의 백업을 만들기 위해 훈련된 직원을 늘린다. | 고위 경영진에게 외부 직원을 고용하도록 설득한다. | B, C | 정규 직원이 있는 대규모 다년 프로젝트에서 직원 이직 리스크를 완화하기 위해, 프로젝트 관리자는 두 가지 조치를 취해야 한다: 자원 성과를 동기 부여하고 보상하기 위한 인정 프로그램 도입(B), 그리고 교육, 멘토링, 코칭을 통한 역량 강화(C). 인정은 만족도와 충성도를 높이고, 기술 개발은 이직 동기를 줄이는 성장 기회를 제공한다. 백업을 위한 직원 증가(D)는 중복과 혼란을 초래한다. 더 작은 프로젝트로 분할(A)은 범위와 이점에 영향을 줄 수 있다. 외부 직원 고용(E)은 복잡성을 증가시키고 유지에 도움이 되지 않을 수 있다.
287 | In the planning phase of a software implementation project, two of the team members disagree on how to approach end-user training. The discussion has intensified and the team members are not able to agree. What should the project manager do next? | Remove one of the team members from the project to improve team dynamics. | Make a decision based on expert judgment as a project manager. | Consider the view of each team member about the issue in order to reach consensus. | Remove both team members since they are not productively adding to the team. |  | C | When two team members disagree intensely on the training approach during planning, the project manager should consider the view of each team member about the issue to reach consensus. Collaborative resolution values both perspectives and produces better solutions. Removing one team member (A) is punitive. Making a decision based on expert judgment alone (B) ignores team input. Removing both members (D) is extreme and destructive. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 소프트웨어 구현 프로젝트의 계획 단계에서 두 명의 팀원이 최종 사용자 교육 접근 방식에 대해 의견이 맞지 않는다. 논의가 격화되었고 팀원들은 합의에 도달하지 못하고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 팀 역학을 개선하기 위해 팀원 중 한 명을 프로젝트에서 제거한다. | 프로젝트 관리자로서 전문가 판단에 기반하여 결정을 내린다. | 합의에 도달하기 위해 각 팀원의 의견을 고려한다. | 두 팀원 모두 팀에 생산적으로 기여하지 않으므로 제거한다. |  | C | 계획 중 두 팀원이 교육 접근 방식에 대해 격렬하게 의견이 다를 때, 프로젝트 관리자는 합의에 도달하기 위해 각 팀원의 의견을 고려해야 한다. 협력적 해결은 양쪽 관점을 존중하고 더 나은 솔루션을 만든다. 팀원 한 명 제거(A)는 징벌적이다. 전문가 판단만으로 결정(B)은 팀 입력을 무시한다. 두 팀원 모두 제거(D)는 극단적이고 파괴적이다.
288 | An important national project is in the execution phase. A time-constraint activity must be conducted on-site by a specialist from another country. Due to travel restrictions, the specialist cannot perform the activity on-site. The activity cannot be completed without the specialist's expertise. The project team is actively seeking assistance in order to complete the job on time. What should the project manager do to help the project team? | Seek additional budget to train the project team on the required skill set. | Refer to the organization ' s lessons learned repository and find an alternative solution. | Reschedule the project until the local travel restrictions are lifted. | Schedule virtual sessions with the specialist to guide the team in completing the activity. |  | D | When a specialist cannot travel on-site due to restrictions for a time-constrained activity, the project manager should schedule virtual sessions with the specialist to guide the team in completing the activity. Virtual collaboration maintains progress within time constraints. Seeking budget for team training (A) takes too long. Referring to lessons learned (B) may not provide the specific expertise needed. Rescheduling until restrictions lift (C) causes unacceptable delay. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Develop a Common Vision | Stakeholders | Initiating | Focus on Value | Identify Stakeholders | Traditional PM | 중요한 국가 프로젝트가 실행 단계에 있다. 시간 제약이 있는 활동이 다른 나라의 전문가에 의해 현장에서 수행되어야 한다. 여행 제한으로 인해 전문가가 현장에서 활동을 수행할 수 없다. 전문가의 전문 지식 없이는 활동을 완료할 수 없다. 프로젝트 팀은 적시에 작업을 완료하기 위해 적극적으로 지원을 구하고 있다. 프로젝트 관리자는 프로젝트 팀을 돕기 위해 무엇을 해야 하는가? | 프로젝트 팀에 필요한 기술 세트를 교육하기 위한 추가 예산을 구한다. | 조직의 교훈 저장소를 참조하여 대안적 솔루션을 찾는다. | 현지 여행 제한이 해제될 때까지 프로젝트 일정을 변경한다. | 전문가와 가상 세션을 예약하여 팀이 활동을 완료하도록 안내한다. |  | D | 여행 제한으로 전문가가 시간 제약이 있는 활동을 위해 현장에 올 수 없을 때, 프로젝트 관리자는 전문가와 가상 세션을 예약하여 팀이 활동을 완료하도록 안내해야 한다. 가상 협업은 시간 제약 내에서 진행을 유지한다. 팀 교육을 위한 예산 확보(A)는 시간이 너무 오래 걸린다. 교훈 참조(B)는 필요한 특정 전문 지식을 제공하지 못할 수 있다. 제한 해제까지 일정 변경(C)은 허용할 수 없는 지연을 초래한다.
289 | A project manager is leading a project that involves on-site and remote team members. One task that was assigned to a team member in another country appears to be behind schedule. When the project manager inquires about this, the team member claims that the task was completed and that this was reported to the team lead via a telephone conversation. What should the project manager do? | Penalize the project team lead for not updating the project documentation properly. | Issue guidance to the team member about reporting directly to the project manager | Review this issue with the team lead for possible ways to resolve this situation | Communicate the ground rules, principles and reporting methods to the project stakeholders |  | C | When a task appears behind schedule but the team member claims it was completed and reported to the team lead via phone, the project manager should review this issue with the team lead to find possible ways to resolve the situation. Investigating the communication breakdown addresses the root cause. Penalizing the team lead (A) is punitive without investigation. Issuing guidance to report directly to the PM (B) bypasses the team structure. Communicating ground rules and reporting methods (D) is broader than necessary for this specific issue. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 관리자가 현장 및 원격 팀원이 포함된 프로젝트를 이끌고 있다. 다른 나라의 팀원에게 배정된 한 작업이 일정에 뒤처진 것으로 보인다. 프로젝트 관리자가 이에 대해 문의하자, 팀원은 작업이 완료되었으며 전화 통화로 팀 리드에게 보고했다고 주장한다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 문서를 제대로 업데이트하지 않은 프로젝트 팀 리드에게 불이익을 준다. | 팀원에게 프로젝트 관리자에게 직접 보고하도록 지침을 발행한다. | 이 상황을 해결할 수 있는 방법을 찾기 위해 팀 리드와 이 이슈를 검토한다. | 기본 규칙, 원칙 및 보고 방법을 프로젝트 이해관계자에게 전달한다. |  | C | 작업이 일정에 뒤처진 것처럼 보이지만 팀원이 완료되었으며 전화로 팀 리드에게 보고했다고 주장할 때, 프로젝트 관리자는 상황을 해결할 수 있는 방법을 찾기 위해 팀 리드와 이 이슈를 검토해야 한다. 의사소통 단절을 조사하는 것이 근본 원인을 다룬다. 팀 리드에게 불이익(A)은 조사 없이 징벌적이다. PM에게 직접 보고 지침 발행(B)은 팀 구조를 우회한다. 기본 규칙과 보고 방법 전달(D)은 이 특정 이슈에 필요 이상으로 광범위하다.
290 | A new project manager has been assigned to an ongoing project because of the promotion of their predecessor. The new project manager needs to understand the levels of decision-making authority on the team. Which document should the incoming project manager review? | Communications management plan | Stakeholder engagement plan | Resource management plan | Information management plan |  | C | The correct answer is C. Resource management plan. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 새 프로젝트 관리자가 전임자의 승진으로 인해 진행 중인 프로젝트에 배정되었다. 새 프로젝트 관리자는 팀의 의사결정 권한 수준을 이해해야 한다. 신임 프로젝트 관리자는 어떤 문서를 검토해야 하는가? | 의사소통 관리 계획 | 이해관계자 참여 계획 | 자원 관리 계획 | 정보 관리 계획 |  | C | 정답은 C이다. 자원 관리 계획. 이 접근 방식은 상황을 효과적으로 해결하고, 적절한 프로세스를 유지하며, 이해관계자 기대 및 프로젝트 목표와의 정렬을 보장하는 프로젝트 관리 모범 사례를 따른다.
291 | In an organizational upper-level management meeting, the CEO shows interest in a project of which they were not previously aware. After the meeting, what should the project manager do to ensure the CEO's support? | Send the updated project management plan and documents to the CEO. | Meet with the CEO to review the current deliverables for the project. | Identify the CEO ' s preferred method of communication. | Update the stakeholder engagement plan to include the CEO. |  | D | The correct answer is D. Update the stakeholder engagement plan to include the CEO. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 조직의 상위 경영진 회의에서 CEO가 이전에 알지 못했던 프로젝트에 관심을 보인다. 회의 후, 프로젝트 관리자는 CEO의 지원을 확보하기 위해 무엇을 해야 하는가? | 업데이트된 프로젝트 관리 계획과 문서를 CEO에게 보낸다. | CEO와 만나 프로젝트의 현재 산출물을 검토한다. | CEO가 선호하는 의사소통 방법을 파악한다. | CEO를 포함하도록 이해관계자 참여 계획을 업데이트한다. |  | D | 정답은 D이다. CEO를 포함하도록 이해관계자 참여 계획을 업데이트한다. 이 접근 방식은 상황을 효과적으로 해결하고, 적절한 프로세스를 유지하며, 이해관계자 기대 및 프로젝트 목표와의 정렬을 보장하는 프로젝트 관리 모범 사례를 따른다.
292 | Two experienced team members in a hybrid project are having a conflict about a technical solution. The project manager has already spoken individually to the two team members without successfully resolving the conflict. What should the project manager do next? | Contact the functional managers of each team member. | Schedule a meeting with both team members. | Replace the two team members with other resources. | Discuss the topic with the team members in a team meeting. |  | B | The PM should schedule a meeting with both team members to understand the root cause of their conflict and facilitate resolution. Addressing issues proactively, fostering collaboration, and creating an environment where team members can perform effectively are essential leadership skills. Building trust and empowering team members strengthens overall team performance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 하이브리드 프로젝트에서 두 명의 경험 많은 팀원이 기술 솔루션에 대해 갈등을 겪고 있다. 프로젝트 관리자는 이미 두 팀원과 개별적으로 대화했지만 갈등을 성공적으로 해결하지 못했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 각 팀원의 기능 관리자에게 연락한다. | 두 팀원과 함께 미팅을 예약한다. | 두 팀원을 다른 자원으로 교체한다. | 팀 미팅에서 팀원들과 해당 주제를 논의한다. |  | B | PM은 두 팀원과 함께 미팅을 예약하여 갈등의 근본 원인을 이해하고 해결을 촉진해야 한다. 이슈를 능동적으로 해결하고, 협력을 촉진하며, 팀원이 효과적으로 수행할 수 있는 환경을 조성하는 것은 필수적인 리더십 기술이다. 신뢰를 구축하고 팀원에게 권한을 부여하는 것은 전체 팀 성과를 강화한다.
293 | A project manager notices during project meetings that some team members repeatedly threaten to resign when they do not agree with something. Which phase of conflict escalation is the project in? | Beginning | Intensification | Resolution | Final |  | B | The correct answer is B. Intensification. Effective leadership involves understanding team dynamics, addressing root causes, and creating a supportive environment. The PM should foster collaboration and well-being to maintain high performance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 프로젝트 미팅 중 일부 팀원들이 동의하지 않을 때 반복적으로 사직하겠다고 위협하는 것을 발견한다. 프로젝트는 갈등 에스컬레이션의 어떤 단계에 있는가? | 시작 | 강화 | 해결 | 최종 |  | B | 정답은 B이다. 강화. 효과적인 리더십은 팀 역학을 이해하고, 근본 원인을 다루며, 지원적인 환경을 조성하는 것을 포함한다. PM은 높은 성과를 유지하기 위해 협력과 웰빙을 증진해야 한다.
294 | Early in the execution phase, a project manager discovers that recent changes in enterprise environmental factors (EEFs) will severely reduce the implementation cost and shorten the project schedule. How should the project manager address this situation? | Meet with the project team to decide how the remaining budget will be spent. | Keep the extra budget as management reserve until project closeout | Follow the project escalation policy and communications management plan | Give the team extra time to finish tasks within the original timeline |  | C | When changes in EEFs reduce implementation cost and shorten the schedule, the project manager should follow the project escalation policy and communications management plan. Proper communication ensures stakeholders are informed of favorable changes. Meeting with the team about remaining budget (A) is narrow. Keeping extra budget as reserve (B) is secretive. Giving extra time (D) is unnecessary if the schedule shortened. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 실행 단계 초기에 프로젝트 관리자가 기업 환경 요인(EEF)의 최근 변화가 구현 비용을 크게 줄이고 프로젝트 일정을 단축할 것임을 발견한다. 프로젝트 관리자는 이 상황을 어떻게 다루어야 하는가? | 남은 예산을 어떻게 사용할지 결정하기 위해 프로젝트 팀과 만난다. | 프로젝트 종료시까지 추가 예산을 관리 예비비로 유지한다. | 프로젝트 에스컬레이션 정책과 의사소통 관리 계획을 따른다. | 원래 일정 내에 작업을 완료하도록 팀에게 추가 시간을 준다. |  | C | EEF 변화가 구현 비용을 줄이고 일정을 단축할 때, 프로젝트 관리자는 프로젝트 에스컬레이션 정책과 의사소통 관리 계획을 따라야 한다. 적절한 의사소통은 이해관계자가 유리한 변화에 대해 정보를 받도록 보장한다. 남은 예산에 대한 팀 미팅(A)은 좋다. 예비비로 추가 예산 유지(B)는 은밀하다. 추가 시간 부여(D)는 일정이 단축된 경우 불필요하다.
295 | During project execution, an important stakeholder threatens to withdraw support for the project, citing a lack of transparency and accountability in the way the project is being executed. What should the project manager do to handle this situation? | Escalate the issue to the project management office (PMO). | Consult the risk management plan. | Approach the stakeholder to address the concerns. | Refer the stakeholder to the project sponsor. |  | C | When a stakeholder threatens to withdraw project support, the PM should engage them directly to understand their concerns and resolve the issue. Using active listening, empathy, and problem-solving techniques, the PM can reach a mutually acceptable agreement and restore trust. Consulting the risk management plan (B) identifies potential responses but doesn't resolve the immediate situation. Escalating to the PMO (C) shifts responsibility. Referring to the sponsor (D) bypasses the PM's direct engagement responsibility. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | 프로젝트 실행 중, 중요한 이해관계자가 프로젝트 실행 방식의 투명성과 책임성 부족을 이유로 프로젝트 지원을 철회하겠다고 위협한다. 프로젝트 관리자는 이 상황을 처리하기 위해 무엇을 해야 하는가? | 프로젝트 관리 오피스(PMO)에 이슈를 에스컬레이션한다. | 리스크 관리 계획을 참조한다. | 이해관계자에게 접근하여 우려를 해결한다. | 이해관계자를 프로젝트 스폰서에게 안내한다. |  | C | 이해관계자가 프로젝트 지원 철회를 위협할 때, PM은 이해관계자에게 직접 접근하여 우려를 이해하고 문제를 해결해야 한다. 적극적 경청, 공감, 문제 해결 기법을 사용하여 PM은 상호 수용 가능한 합의에 도달하고 신뢰를 회복할 수 있다. 리스크 관리 계획 참조(B)는 잠재적 대응을 식별하지만 즉각적인 상황을 해결하지 않는다. PMO에 에스컬레이션(C)은 책임을 전가한다. 스폰서에게 안내(D)는 PM의 직접 참여 책임을 우회한다.
296 | A project manager is leading a team that is delivering new software to a finance team. The new software will streamline the finance team's monthly closing activities and reporting. What should the project manager use to promote knowledge transfer for the new solution? | End-user training | User handbook | Support portal | Project documents |  | A | When delivering new software to a finance team, the project manager should use end-user training to promote knowledge transfer. Training is interactive, allows users to ask questions, and ensures practical understanding of how to use the solution in real work scenarios—directly supporting adoption and reducing misuse risk. A user handbook (B) is passive and may not ensure comprehension. A support portal (C) provides ongoing assistance but is not the primary knowledge transfer method. Project documents (D) are not designed for end-user adoption. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Align Stakeholder Expectations | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 관리자가 재무 팀에게 새로운 소프트웨어를 제공하는 프로젝트을 이끌고 있다. 새로운 소프트웨어는 재무 팀의 월별 마감 활동과 보고를 간소화할 것이다. 프로젝트 관리자는 새로운 솔루션의 지식 전달을 촉진하기 위해 무엇을 사용해야 하는가? | 최종 사용자 교육 | 사용자 핸드북 | 지원 포털 | 프로젝트 문서 |  | A | 재무 팀에게 새로운 소프트웨어를 제공할 때, 프로젝트 관리자는 최종 사용자 교육을 사용하여 지식 전달을 촉진해야 한다. 교육은 상호작용적이며, 사용자가 질문할 수 있고, 실제 업무 시나리오에서 솔루션 사용법에 대한 실용적 이해를 보장하여 도입을 직접 지원하고 오용 위험을 줄인다. 사용자 핸드북(B)은 수동적이며 이해를 보장하지 않을 수 있다. 지원 포털(C)은 지속적인 지원을 제공하지만 주요 지식 전달 방법은 아니다. 프로젝트 문서(D)는 최종 사용자 도입을 위해 설계되지 않았다.
297 | A team member has escalated an issue to the project manager, stating that they have done their part of the job. Their concern is that there is still no response from the other party in the service level agreement (SLA). The team member is eager to find a resolution for the reported issue. What should the project manager advise the team member to do to ensure that the project escalation mechanism is effective? | Escalate to the other party ' s management and inform the steering committee. | Reach out to peer managers for similar escalation situations and follow past experiences. | Review the established project escalation process and take the appropriate action. | Involve all of the stakeholders in the escalation by setting up a conference call. |  | C | The correct answer is C. Review the established project escalation process and take the appropriate action. Resource management includes ensuring the team has adequate skills, capacity, and support. The PM should address resource gaps and challenges proactively to maintain project delivery. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Risk & Issue Management | People | Lead the Project Team | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | 팀원이 프로젝트 관리자에게 이슈를 에스컬레이션하며, 자신의 업무 부분은 완료했다고 말한다. 우려되는 것은 서비스 수준 협약(SLA)의 상대방으로부터 아직 응답이 없다는 것이다. 팀원은 보고된 이슈의 해결을 찾고 싶어 한다. 프로젝트 에스컬레이션 메커니즘이 효과적이도록 프로젝트 관리자는 팀원에게 무엇을 하도록 조언해야 하는가? | 상대방 경영진에 에스컬레이션하고 운영 위원회에 알린다. | 유사한 에스컬레이션 상황에 대해 동료 관리자에게 연락하고 과거 경험을 따른다. | 수립된 프로젝트 에스컬레이션 프로세스를 검토하고 적절한 조치를 취한다. | 회의 통화를 설정하여 모든 이해관계자를 에스컬레이션에 참여시킨다. |  | C | 정답은 C이다. 수립된 프로젝트 에스컬레이션 프로세스를 검토하고 적절한 조치를 취한다. 자원 관리는 팀이 적절한 기술, 역량, 지원을 갖추도록 보장하는 것을 포함한다. PM은 프로젝트 전달을 유지하기 위해 자원 격차와 과제를 능동적으로 해결해야 한다.
298 | A project manager is appointed to simultaneously deploy a new solution to branches located in different countries. Deployment teams in each country will integrate and deploy the solution. The project manager discovers that the deployment teams each encounter similar issues. However, each team addresses the issues separately. What should the project manager do to help ensure more collaboration between the teams? | Ask the project sponsor to appoint new managers for the deployment teams | Organize regular meetings with all of the deployment teams to share issues and solutions | Ask each deployment team to provide a very detailed schedule and action plan | Propose that some of the teams delay deployments in their countries |  | B | When deployment teams in different countries encounter similar issues but address them separately, the project manager should organize regular meetings with all deployment teams to share issues and solutions. Collaborative meetings enable knowledge sharing and reduce duplicate effort. Appointing new managers (A) disrupts teams without addressing collaboration. Requesting detailed schedules (C) adds documentation without enabling collaboration. Delaying some deployments (D) slows the project. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 여러 국가에 위치한 지점에 새로운 솔루션을 동시에 배포하도록 임명되었다. 각 국가의 배포 팀이 솔루션을 통합하고 배포할 것이다. 프로젝트 관리자는 배포 팀들이 각각 유사한 문제에 직면한다는 것을 발견한다. 그러나 각 팀은 문제를 별도로 다루고 있다. 프로젝트 관리자는 팀 간 협력을 보장하기 위해 무엇을 해야 하는가? | 프로젝트 스폰서에게 배포 팀에 새로운 관리자를 임명하도록 요청한다. | 모든 배포 팀과 정기 회의를 조직하여 문제와 솔루션을 공유한다. | 각 배포 팀에 매우 상세한 일정과 실행 계획을 제공하도록 요청한다. | 일부 팀이 해당 국가에서 배포를 지연하도록 제안한다. |  | B | 다른 국가의 배포 팀들이 유사한 문제에 직면하지만 별도로 해결할 때, 프로젝트 관리자는 모든 배포 팀과 정기 회의를 조직하여 문제와 솔루션을 공유해야 한다. 협력적 회의는 지식 공유를 가능하게 하고 중복 노력을 줄인다. 새 관리자 임명(A)은 협력을 다루지 않고 팀을 혼란시킨다. 상세 일정 요청(C)은 협력 없이 문서를 추가한다. 일부 배포 지연(D)은 프로젝트를 느리게 한다.
299 | A project manager is assigned to a new project to deliver a product at the end of the year. The project manager was informed by the vendor that a core component could not be shipped on time, which will impact the schedule. What should the project manager do next to minimize the impact on the project? | Add an item to the next status review to make stakeholders aware of the vendor issue. | Replace the vendor with a new vendor who can offer the component on time | Review and update the issue log and determine if any alternative components can be offered | Schedule a meeting with all stakeholders to extend the project deadline |  | C | When a vendor's core component delivery is delayed, the PM should review and update the issue log to document the situation and determine if alternative components are available from the vendor or other sources. The issue resolution process involves identifying and evaluating possible solutions, selecting the best option, and implementing the agreed action. Extending the deadline is premature, replacing the vendor is risky, and status reporting alone doesn't address resolution. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 프로젝트 관리자가 연말까지 제품을 전달하는 새 프로젝트에 배정되었다. 프로젝트 관리자는 벤더로부터 핵심 구성 요소가 제시간에 배송될 수 없어 일정에 영향을 미칠 것이라는 통보를 받았다. 프로젝트에 대한 영향을 최소화하기 위해 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 다음 현황 검토에 항목을 추가하여 이해관계자에게 벤더 이슈를 알린다. | 구성 요소를 제시간에 제공할 수 있는 새 벤더로 교체한다. | 이슈 로그를 검토하고 업데이트하며 대안 구성 요소를 제공할 수 있는지 확인한다. | 모든 이해관계자와 미팅을 예약하여 프로젝트 기한을 연장한다. |  | C | 벤더의 핵심 구성 요소 전달이 지연될 때, PM은 이슈 로그를 검토하고 업데이트하여 상황을 문서화하고 벤더나 다른 출처에서 대안 구성 요소가 가능한지 확인해야 한다. 이슈 해결 프로세스는 가능한 솔루션을 식별하고 평가하고, 최선의 옵션을 선택하며, 합의된 조치를 실행하는 것을 포함한다. 기한 연장은 시기상조이고, 벤더 교체는 위험하며, 현황 보고만으로는 해결을 다루지 않는다.
300 | A project manager with global teams is managing a project that is progressing as expected. However, recently the project manager has learned of some team members missing the daily meetings. After investigating the issue, the project manager realizes different time zones is the main cause of the issue. What should the project manager do next? | Schedule a meeting and ask all teams to sort the issues and move ahead with full 1145 participation. | Share the time-overlap schedule with the team to make meeting scheduling convenient. | Schedule a team-building workshop involving all teams to support better communication. | Ask everyone to only invite team members in different parts of the world as necessary. |  | B | When team members in different time zones miss daily meetings, the project manager should share the time-overlap schedule with the team to make scheduling convenient. Identifying overlap windows enables participation. Asking all teams to resolve issues themselves (A) is unclear. Team-building workshops (C) address relationships, not scheduling. Limiting invitations (D) fragments communication. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 글로벌 팀을 관리하는 프로젝트 관리자가 예상대로 진행되는 프로젝트를 관리하고 있다. 그러나 최근 프로젝트 관리자는 일부 팀원이 일일 미팅에 불참하는 것을 알게 되었다. 문제를 조사한 후, 프로젝트 관리자는 다른 시간대가 주요 원인임을 깨닫는다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 미팅을 예약하고 모든 팀에게 문제를 해결하고 전체 참여로 진행하도록 요청한다. | 팀과 시간 중복 일정을 공유하여 미팅 일정을 편리하게 한다. | 더 나은 의사소통을 지원하기 위해 모든 팀을 포함한 팀 빌딩 워크숍을 예약한다. | 세계 다른 지역의 팀원은 필요한 경우에만 초대하도록 요청한다. |  | B | 다른 시간대의 팀원이 일일 미팅에 불참할 때, 프로젝트 관리자는 팀과 시간 중복 일정을 공유하여 미팅 일정을 편리하게 해야 한다. 중복 시간대를 파악하면 참여가 가능해진다. 모든 팀에게 문제 해결 요청(A)은 불명확하다. 팀 빌딩 워크숍(C)은 관계를 다루지 일정을 다루지 않는다. 초대 제한(D)은 의사소통을 단절시킨다.
301 | A company just started managing a project using an agile approach. Due to this change, the general manager is worried about the scope definition process for upcoming projects. What should the project manager do to ensure the project scope is fully defined? | Help sponsors and stakeholders craft the product vision, and bring the team and product owner together to clarify expectations | Ask for a budget increase to implement a double-check process to ensure every business need is included in the requirements | Meet with the general manager and convince them to return to using predictive approaches to avoid any risk | Ask the general manager to review every requirement to ensure an projects will deliver the requested products |  | A | In agile environments, scope is not fixed but regularly reviewed and adapted based on stakeholder feedback and project progress. The PM should facilitate collaboration among sponsors, stakeholders, and the team to ensure a shared understanding of the product vision and to clarify expectations. This aligns with the agile principle of welcoming changing requirements and prioritizing customer collaboration. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | 회사가 애자일 접근 방식을 사용하여 프로젝트를 관리하기 시작했다. 이 변경으로 인해 총괄 이사는 향후 프로젝트의 범위 정의 프로세스에 대해 우려하고 있다. 프로젝트 범위가 완전히 정의되도록 프로젝트 관리자는 무엇을 해야 하는가? | 스폰서와 이해관계자가 제품 비전을 수립하도록 돕고, 팀과 제품 책임자를 함께 모아 기대치를 명확히 한다. | 모든 비즈니스 요구가 요구사항에 포함되도록 이중 검사 프로세스를 구현하기 위한 예산 증액을 요청한다. | 총괄 이사와 만나 리스크를 피하기 위해 예측적 접근 방식으로 돌아가도록 설득한다. | 모든 프로젝트가 요청된 제품을 전달하도록 총괄 이사에게 모든 요구사항을 검토하도록 요청한다. |  | A | 애자일 환경에서 범위는 고정되지 않고 이해관계자 피드백과 프로젝트 진행에 따라 정기적으로 검토하고 조정된다. PM은 스폰서, 이해관계자, 팀 간 협력을 촉진하여 제품 비전에 대한 공유 이해를 보장하고 기대치를 명확히 해야 한다. 이는 변화하는 요구사항을 환영하고 고객 협력을 우선시하는 애자일 원칙에 부합한다.
302 | A project manager assigned to an agile project realizes that after iteration demos, new user stories to fix issues reported by the product owner are not included in prioritization of the following sprint. This has led to a high number of unprioritized stories in the backlog and will lead to delay of the product release. What should the project manager do? | Ask the team to include the user stories as spikes in the next iteration to bring the project back on schedule. | Ask the team and product owner to reprioritize the user stories in the backlog for an updated iteration schedule. | Review the minimum viable product (MVP) user stories and ensure all related stories are 619 prioritized. | Add additional iterations to the schedule to accommodate for the work required on the stories. |  | B | When user stories fixing demo issues are not being prioritized in subsequent sprints, creating a growing unprioritized backlog, the project manager should ask the team and product owner to reprioritize user stories in the backlog for an updated iteration schedule. Collaborative reprioritization is the core agile practice for addressing backlog management. Reviewing MVP user stories for prioritization (C) is narrower. Using spikes (A) misapplies the concept—spikes are for research, not unplanned work. Adding iterations (D) extends scope rather than addressing prioritization. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 애자일 프로젝트에 배정된 프로젝트 관리자가 이터레이션 데모 후, 제품 책임자가 보고한 문제를 수정하기 위한 새로운 사용자 스토리가 다음 스프린트의 우선순위 지정에 포함되지 않는 것을 알게 된다. 이로 인해 백로그에 우선순위가 지정되지 않은 스토리가 많이 쌓였고 제품 출시 지연으로 이어질 것이다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트를 일정에 맞추기 위해 다음 이터레이션에서 사용자 스토리를 스파이크로 포함하도록 팀에 요청한다. | 업데이트된 이터레이션 일정을 위해 팀과 제품 책임자에게 백로그의 사용자 스토리를 재우선순위화하도록 요청한다. | 최소 기능 제품(MVP) 사용자 스토리를 검토하고 모든 관련 스토리의 우선순위가 지정되었는지 확인한다. | 스토리에 필요한 작업을 수용하기 위해 일정에 추가 이터레이션을 추가한다. |  | B | 데모 이슈를 수정하는 사용자 스토리가 후속 스프린트에서 우선순위가 지정되지 않아 우선순위 미지정 백로그가 증가할 때, 프로젝트 관리자는 팀과 제품 책임자에게 업데이트된 이터레이션 일정을 위해 백로그의 사용자 스토리를 재우선순위화하도록 요청해야 한다. 협력적 재우선순위화는 백로그 관리를 위한 핵심 애자일 실행이다. MVP 사용자 스토리 검토(C)는 더 좋다. 스파이크 사용(A)은 개념을 잘못 적용한다—스파이크는 연구를 위한 것이지 계획되지 않은 작업이 아니다. 이터레이션 추가(D)는 우선순위 지정을 다루지 않고 범위를 확장한다.
303 | A construction project for a nuclear power plant will reduce the region's energy dependence on external electricity supplies. The project manager has received support for the project from several leaders in the region. However, some people from the government want to stop this project to focus on developing renewable energy sources. Which stakeholders should the project manager include in the stakeholder engagement plan? | Stakeholders who are selected by the project sponsor who have a potential impact on the project. | Stakeholders who have been identified and who have needs and a potential impact on the project. | Stakeholders who disagree with the project so as to proactively manage their expectations. | Stakeholders who are supporting the project in order to obtain additional resources. |  | B | The stakeholder engagement plan should include all stakeholders who have been identified as having needs and a potential impact on the project—including both supporters and opponents. For a nuclear power plant project with regional leaders supporting it and government officials opposing it, comprehensive stakeholder identification and engagement is essential. Including only sponsor-selected stakeholders (A) may miss important voices. Including only those who disagree (C) ignores supporters who need ongoing engagement. Including only supporters for additional resources (D) creates blind spots regarding opposition. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 원자력 발전소 건설 프로젝트는 해당 지역의 외부 전력 공급 의존도를 줄일 것이다. 프로젝트 관리자는 지역의 여러 리더로부터 프로젝트 지원을 받았다. 그러나 정부의 일부 사람들은 재생 에너지원 개발에 집중하기 위해 이 프로젝트를 중단하기를 원한다. 프로젝트 관리자는 이해관계자 참여 계획에 어떤 이해관계자를 포함시켜야 하는가? | 프로젝트에 잠재적 영향을 미칠 수 있는, 프로젝트 스폰서가 선정한 이해관계자. | 식별되었으며 요구사항과 프로젝트에 잠재적 영향을 가진 이해관계자. | 기대치를 능동적으로 관리하기 위해 프로젝트에 동의하지 않는 이해관계자. | 추가 자원을 얻기 위해 프로젝트를 지원하는 이해관계자. |  | B | 이해관계자 참여 계획에는 요구사항과 프로젝트에 잠재적 영향을 가진 것으로 식별된 모든 이해관계자—지지자와 반대자 모두—를 포함해야 한다. 원자력 발전소 프로젝트에서 지역 리더가 지지하고 정부 관리가 반대하는 상황에서 포괄적인 이해관계자 식별과 참여가 필수적이다. 스폰서 선정 이해관계자만 포함(A)은 중요한 목소리를 놓칠 수 있다. 반대자만 포함(C)은 지속적인 참여가 필요한 지지자를 무시한다. 자원 확보를 위한 지지자만 포함(D)은 반대에 대한 사각지대를 만든다.
304 | A project manager is working on a product development project. When the product is delivered, there are major issues that require rework and delay new feature development. Which action should the project manager take to resolve the quality issues? | Discuss adding additional test cases with the product owner. | Discuss adding business scenario tests with the customer. | Plan for continuous validation of the product. | Add more test scenarios based on the issues found. |  | C | When a delivered product has major quality issues requiring rework and delaying new features, the project manager should plan for continuous validation of the product. Ongoing quality checks throughout development catch issues early. Discussing additional test cases with the product owner (A) is incremental. Adding business scenario tests with the customer (B) expands testing but is not systematic. Adding more test scenarios based on found issues (D) is reactive, not preventive. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 제품 개발 프로젝트를 진행하고 있다. 제품이 전달되었을 때, 재작업이 필요하고 새로운 기능 개발을 지연시키는 주요 문제가 있다. 프로젝트 관리자는 품질 문제를 해결하기 위해 어떤 조치를 취해야 하는가? | 제품 책임자와 추가 테스트 케이스 추가에 대해 논의한다. | 고객과 비즈니스 시나리오 테스트 추가에 대해 논의한다. | 제품의 지속적인 검증을 계획한다. | 발견된 문제를 기반으로 더 많은 테스트 시나리오를 추가한다. |  | C | 전달된 제품에 재작업이 필요하고 새 기능을 지연시키는 주요 품질 문제가 있을 때, 프로젝트 관리자는 제품의 지속적인 검증을 계획해야 한다. 개발 전반에 걸친 지속적인 품질 검사는 문제를 조기에 발견한다. 제품 책임자와 추가 테스트 케이스 논의(A)는 점진적이다. 고객과 비즈니스 시나리오 테스트 추가(B)는 테스트를 확장하지만 체계적이지 않다. 발견된 문제 기반 테스트 시나리오 추가(D)는 반응적이지 예방적이지 않다.
305 | A project manager is working on a complex project with a significant degree of change. What strategy should the project manager adopt to ensure a successful project completion? | Schedule a regular risk review with the project management team. | Increase the active engagement and participation of key stakeholders. | Update the project management plan to reduce the possibility of scope creep. | Create a project change roadmap to keep track of all unforeseen changes. |  | B | When facing a project with significant and ongoing change, the most effective strategy is to increase active stakeholder engagement and participation. Involving stakeholders in decision-making helps manage their expectations, surfaces valuable insights, and builds a sense of ownership across all parties. This collaborative approach also enables early identification of emerging risks and changes, supporting a more adaptive and responsive project management style. The other options—regular risk reviews, updating the project plan to reduce scope creep, or creating a change roadmap—are useful but secondary to active stakeholder engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 관리자가 상당한 수준의 변경이 있는 복잡한 프로젝트를 진행하고 있다. 프로젝트를 성공적으로 완료하기 위해 프로젝트 관리자는 어떤 전략을 채택해야 하는가? | 프로젝트 관리 팀과 정기적인 리스크 검토를 예약한다. | 주요 이해관계자의 적극적인 참여와 참여를 높인다. | 범위 변경의 가능성을 줄이기 위해 프로젝트 관리 계획을 업데이트한다. | 모든 예상치 못한 변경을 추적하기 위한 프로젝트 변경 로드맵을 생성한다. |  | B | 상당하고 지속적인 변경이 있는 프로젝트에 직면할 때, 가장 효과적인 전략은 주요 이해관계자의 적극적인 참여를 높이는 것이다. 의사결정에 이해관계자를 참여시키면 기대치 관리에 도움이 되고, 가치 있는 통찰력을 끌어내며, 모든 당사자에게 주인의식을 구축한다. 이 협력적 접근 방식은 또한 새로운 리스크와 변경의 조기 식별을 가능하게 한다. 다른 옵션들—정기 리스크 검토, 범위 변경 감소를 위한 계획 업데이트, 변경 로드맵 생성—은 유용하지만 적극적 이해관계자 참여에 부차적이다.
306 | A project manager and project team have brought a project back on track after mapping and removing impediments. During the current sprint, the team reported that an impediment that previously caused major delays has appeared again. The team tried implementing the same mitigation tasks that worked previously. However, the tasks are not having the same result with the impediment. What should the project manager do? | Reassess the issue as part of monitoring and controlling | Use the contingency budget to implement schedule compression | Implement the mitigation plans listed in the organizational process assets (OPAs) | Escalate the issue with an impediment to the project sponsor |  | A | When a previously resolved impediment reappears and the earlier mitigation strategies are not effective, the project manager should reassess the issue as part of monitoring and controlling. This involves re-evaluating the root cause, identifying new contributing factors, and developing updated mitigation strategies. Using the contingency budget for schedule compression (B) addresses symptoms rather than the root cause. Implementing mitigation plans from OPAs (C) applies generic solutions that may not fit the current context. Escalating to the project sponsor (D) is premature before the PM has completed a thorough reassessment. | Process | Manage Project Issues | Project Work | Navigate Complexity | Agile | Scrum | Business Environment | Remove Impediments and Manage Issues | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | Traditional PM | 프로젝트 관리자와 프로젝트 팀이 장애물을 매핑하고 제거한 후 프로젝트를 다시 정상 궤도에 올려놓았다. 현재 스프린트 동안 팀은 이전에 주요 지연을 유발한 장애물이 다시 나타났다고 보고했다. 팀은 이전에 효과적이었던 동일한 완화 작업을 구현하려 했다. 그러나 작업이 장애물에 동일한 결과를 내지 못하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 모니터링 및 통제의 일부로 이슈를 재평가한다. | 일정 압축을 구현하기 위해 비상 예산을 사용한다. | 조직 프로세스 자산(OPA)에 나열된 완화 계획을 구현한다. | 장애물 이슈를 프로젝트 스폰서에게 에스컬레이션한다. |  | A | 이전에 해결된 장애물이 다시 나타나고 이전 완화 전략이 효과적이지 않을 때, 프로젝트 관리자는 모니터링 및 통제의 일부로 이슈를 재평가해야 한다. 이는 근본 원인을 재평가하고, 새로운 기여 요인을 식별하며, 업데이트된 완화 전략을 개발하는 것을 포함한다. 일정 압축을 위한 비상 예산 사용(B)은 근본 원인이 아닌 증상을 다룬다. OPA의 완화 계획 구현(C)은 현재 상황에 맞지 않을 수 있는 일반적 솔루션을 적용한다. 스폰서에게 에스컬레이션(D)은 PM이 철저한 재평가를 완료하기 전에 시기상조이다.
307 | An agile project is completing its second sprint and products are being finished. However, two groups with different levels of expertise disagree on the backlog priority. What should the project manager do first to resolve this dispute? | Ask the functional managers of both groups to help find a workable solution. | Escalate to the project sponsor to provide a solution to the conflict. | Apply a compromising resolution approach, involving both groups. | Interpret the source and stage of the conflict and select a resolution approach. |  | D | When two groups disagree on backlog priority, the project manager should first interpret the source and stage of the conflict and then select an appropriate resolution approach. Effective conflict management begins with understanding the underlying cause—whether it stems from differing expertise levels, competing priorities, or miscommunication—before choosing a technique such as collaboration, compromise, or accommodation. Asking functional managers to intervene (A) escalates before the PM has analyzed the situation. Escalating to the project sponsor (B) bypasses the agile team's empowerment and problem-solving structure. Applying a compromising approach directly (C) assumes a resolution technique without first understanding the problem. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 애자일 프로젝트가 두 번째 스프린트를 완료하고 있으며 제품이 완성되고 있다. 그러나 다른 수준의 전문성을 가진 두 그룹이 백로그 우선순위에 대해 동의하지 않는다. 프로젝트 관리자는 이 분쟁을 해결하기 위해 먼저 무엇을 해야 하는가? | 두 그룹의 기능 관리자에게 실행 가능한 솔루션을 찾도록 도움을 요청한다. | 갈등에 대한 솔루션을 제공하도록 프로젝트 스폰서에게 에스컬레이션한다. | 두 그룹을 포함하는 타협적 해결 접근 방식을 적용한다. | 갈등의 원인과 단계를 해석하고 해결 접근 방식을 선택한다. |  | D | 두 그룹이 백로그 우선순위에 대해 동의하지 않을 때, 프로젝트 관리자는 먼저 갈등의 원인과 단계를 해석하고 적절한 해결 접근 방식을 선택해야 한다. 효과적인 갈등 관리는 근본 원인—다른 전문성 수준, 경쟁적 우선순위, 또는 의사소통 오류—을 이해한 후에 협력, 타협, 또는 수용 같은 기법을 선택하는 것에서 시작된다. 기능 관리자 개입 요청(A)은 PM이 상황을 분석하기 전에 에스컬레이션한다. 스폰서에게 에스컬레이션(B)은 애자일 팀의 권한과 문제 해결 구조를 우회한다. 타협적 접근 방식 직접 적용(C)은 문제를 먼저 이해하지 않고 해결 기법을 가정한다.
308 | A project manager has been selected to deliver one of an organization's key flagship solutions. Critical success factors include agility, market adaptation, and a quick response to market offerings. What is one of the key activities that the project manager should undertake to ensure company success? | Request more funding from the project sponsor to hire additional skilled resourcesand to incorporate additional quality in the project delivery approach and outcome | Conduct periodical reviews of the project plans, objectives, and deliverables to ensure all relevant data are captured to continue making informed project decisions | Create a business case after performing a market review, and then submit it to the sponsor to modify the project deliverable to meet the newly defined objectives | Review the project objectives with the project sponsor to agree on more realistic and achievable project plans and deliverables |  | B | For a flagship solution requiring agility, market adaptation, and quick response to market offerings, the project manager should conduct periodical reviews of project plans, objectives, and deliverables to ensure all relevant data are captured for informed decision-making. This iterative monitoring and evaluation approach aligns with operating in a dynamic environment where continuous adaptation is critical. Reviewing objectives with the sponsor for more realistic plans (D) is a one-time adjustment, not an ongoing adaptive activity. Requesting more funding for additional resources (A) is reactive and may not be feasible. Creating a business case after a market review (C) delays delivery and may not reflect current market conditions. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Resources | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 조직의 주요 플래그십 솔루션 중 하나를 전달하도록 선정되었다. 중요한 성공 요인에는 바이러스성, 시장 적응력, 시장 제공에 대한 빠른 대응이 포함된다. 프로젝트 관리자가 회사 성공을 보장하기 위해 수행해야 하는 주요 활동 중 하나는 무엇인가? | 추가 숙련 자원을 고용하고 프로젝트 전달 접근 방식과 결과에 추가 품질을 포함하기 위해 프로젝트 스폰서에게 더 많은 자금을 요청한다. | 정보에 입각한 프로젝트 결정을 계속 내리기 위해 모든 관련 데이터가 포착되도록 프로젝트 계획, 목표, 산출물을 주기적으로 검토한다. | 시장 검토를 수행한 후 비즈니스 케이스를 작성한 다음, 새로 정의된 목표를 충족하도록 프로젝트 산출물을 수정하기 위해 스폰서에게 제출한다. | 더 현실적이고 달성 가능한 프로젝트 계획과 산출물에 합의하기 위해 프로젝트 스폰서와 프로젝트 목표를 검토한다. |  | B | 바이러스성, 시장 적응력, 시장 제공에 대한 빠른 대응이 필요한 플래그십 솔루션의 경우, 프로젝트 관리자는 정보에 입각한 결정을 위해 모든 관련 데이터가 포착되도록 프로젝트 계획, 목표, 산출물을 주기적으로 검토해야 한다. 이 반복적 모니터링 및 평가 접근 방식은 지속적 적응이 중요한 역동적 환경에서 운영하는 것과 일치한다. 스폰서와 더 현실적인 계획 검토(D)는 일회성 조정이지 지속적인 적응 활동이 아니다. 추가 자원을 위한 자금 요청(A)은 반응적이며 실현 불가능할 수 있다. 시장 검토 후 비즈니스 케이스 작성(C)은 전달을 지연시키고 현재 시장 상황을 반영하지 못할 수 있다.
309 | Developers spend most of the sprint writing code for user stories, leaving little time for testing. As a result, user stories cannot be tested in time and the stories remain unfinished by the end of the iteration, resulting in poor metrics. What should the scrum master do first in this situation? | Increase the number of developers on the team so stories are completed faster. | Request the developers work overtime to ensure the testers have enough time to perform their tests. | Divide the user stories into two categories: development stories and test stories. | Revalidate the team ' s velocity to ensure development and testing can be completed within the iteration. |  | D | When developers spend most of the sprint writing code leaving insufficient testing time, resulting in unfinished stories, the scrum master should first revalidate the team's velocity to ensure development and testing fit within the iteration. Right-sizing velocity addresses the root cause. Dividing stories into dev and test categories (A) defeats cross-functional work. Increasing developers (B) does not address the testing bottleneck. Requesting overtime (C) is unsustainable. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 개발자들이 스프린트의 대부분을 사용자 스토리의 코드 작성에 소비하여 테스트 시간이 부족하다. 결과적으로 사용자 스토리를 제시간에 테스트할 수 없고 이터레이션 종료 시 스토리가 미완료 상태로 남아 저조한 메트릭을 초래한다. 스크럼 마스터는 이 상황에서 먼저 무엇을 해야 하는가? | 스토리가 더 빨리 완료되도록 팀의 개발자 수를 늘린다. | 테스터가 테스트를 수행할 충분한 시간을 확보하도록 개발자에게 초과 근무를 요청한다. | 사용자 스토리를 개발 스토리와 테스트 스토리의 두 가지 범주로 나눈다. | 이터레이션 내에서 개발과 테스트가 완료될 수 있도록 팀의 벨로시티를 재검증한다. |  | D | 개발자가 스프린트 대부분을 코드 작성에 소비하여 테스트 시간이 부족하고 스토리가 미완료될 때, 스크럼 마스터는 먼저 이터레이션 내에서 개발과 테스트가 완료될 수 있도록 팀의 벨로시티를 재검증해야 한다. 벨로시티 적정화는 근본 원인을 다룬다. 스토리를 개발과 테스트 범주로 나누는 것(A)은 교차 기능 작업을 무력화한다. 개발자 증원(B)은 테스트 병목을 해결하지 않는다. 초과 근무 요청(C)은 지속 불가능하다.
310 | A project management office (PMO) has been trying to implement an adaptive approach for the project management framework. The project manager has been asked to use adaptive tools in the next project. Awareness of adaptive tools is very low in the company, and many stakeholders are concerned about moving to a hybrid approach. What should the project manager do? | Prepare a change request and seek approval from the steering committee regarding the new project framework. | Recommend to the PMO that it is not the right time to start implementing new tools for projects. | Include the use of tools and monitoring of their benefits in regular status reports and the communications management plan. | Bring in a third-party company to develop and implement a hybrid framework for this specific project. |  | C | When implementing new tools in a project environment, the PM should include their usage and benefit monitoring in regular status reports and the communications management plan. This gives stakeholders visibility into the tools' benefits in action, helping alleviate concerns and build comfort with the new approach. Transparent reporting of adaptive tool performance supports organizational acceptance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Hybrid/Tailoring | 프로젝트 관리 오피스(PMO)가 프로젝트 관리 프레임워크에 적응형 접근 방식을 구현하려고 하고 있다. 프로젝트 관리자는 다음 프로젝트에서 적응형 도구를 사용하도록 요청받았다. 회사에서 적응형 도구에 대한 인식이 매우 낮으며, 많은 이해관계자가 하이브리드 접근 방식으로의 전환에 대해 우려하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 변경 요청을 준비하고 새로운 프로젝트 프레임워크에 대해 운영 위원회의 승인을 구한다. | 프로젝트에 새로운 도구를 구현하기 시작할 적절한 시기가 아니라고 PMO에 권고한다. | 도구 사용과 그 이점 모니터링을 정기 현황 보고서와 의사소통 관리 계획에 포함한다. | 이 특정 프로젝트를 위한 하이브리드 프레임워크를 개발하고 구현하도록 제3자 회사를 초빙한다. |  | C | 프로젝트 환경에서 새로운 도구를 구현할 때, PM은 도구 사용과 이점 모니터링을 정기 현황 보고서와 의사소통 관리 계획에 포함해야 한다. 이는 이해관계자에게 실제 작동 중인 도구의 이점을 보여주어 우려를 해소하고 새로운 접근 방식에 대한 편안함을 높이는 데 도움이 된다. 적응형 도구 성과의 투명한 보고는 조직적 수용을 지원한다.
311 | A self-organized project team is sharing facilitator responsibilities, with each person on the core team taking turns serving as facilitator to enable communication, collaboration, and engagement. One of the team members acting as facilitator missed an email from the project client regarding an important change. This oversight caused a project delay and significant rework. Where does the accountability for this oversight reside? | The working agreement should be accountable since it did not cover situations involving oversight. | The team member facilitator who missed the email should be held accountable. | The team should take accountability based on the decentralized project management style. | The project sponsor who approved the decentralized project management style should be held accountable. |  | C | When a team member acting as rotating facilitator misses an important client email causing delays and rework in a self-organized team, the team as a whole should take accountability based on the decentralized management style. Self-organizing teams share collective responsibility for outcomes. The working agreement (A) is a tool, not an accountable entity. The individual facilitator (B) made the error but accountability is collective. The sponsor (D) approved the model but is not accountable for execution. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 자체 조직화된 프로젝트 팀이 퍼실리테이터 책임을 공유하며, 핵심 팀의 각 사람이 교대로 퍼실리테이터 역할을 하여 의사소통, 협력, 참여를 가능하게 하고 있다. 퍼실리테이터 역할을 하는 팀원 중 한 명이 중요한 변경에 관한 프로젝트 고객의 이메일을 놓쳤다. 이 간과로 인해 프로젝트 지연과 상당한 재작업이 발생했다. 이 간과에 대한 책임은 어디에 있는가? | 간과와 관련된 상황을 다루지 않았으므로 작업 합의서가 책임져야 한다. | 이메일을 놓친 팀원 퍼실리테이터가 책임져야 한다. | 분산화된 프로젝트 관리 스타일에 따라 팀이 책임져야 한다. | 분산화된 프로젝트 관리 스타일을 승인한 프로젝트 스폰서가 책임져야 한다. |  | C | 자체 조직화된 팀에서 로테이션 퍼실리테이터가 중요한 고객 이메일을 놓첨 지연과 재작업이 발생했을 때, 분산화된 관리 스타일에 기반하여 팀 전체가 책임져야 한다. 자체 조직화된 팀은 결과에 대한 집단적 책임을 공유한다. 작업 합의서(A)는 도구이지 책임 주체가 아니다. 개별 퍼실리테이터(B)는 오류를 범했지만 책임은 집단적이다. 스폰서(D)는 모델을 승인했지만 실행에 대한 책임은 없다.
312 | A new project includes important product features that should be delivered as soon as they are completed during the following quarter. The project team consists of junior and senior technicians. Which two actions should the project manager take to deliver product features as soon as possible? (Choose 2) | Empower the team to self-organize. | Align on clear and proper accountability levels. | Instruct the senior technicians to lead the junior technicians. | Conduct a detailed work review of the junior technicians. | Review a detailed plan with the senior technicians. | A, B | To deliver product features as soon as possible with junior and senior technicians, the project manager should (A) empower the team to self-organize and (B) align on clear and proper accountability levels. Self-organization maximizes efficiency while accountability ensures quality. Instructing seniors to lead juniors (C) creates hierarchy. Conducting detailed work reviews of juniors (D) is micromanaging. Reviewing detailed plans with seniors (E) limits team autonomy. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새로운 프로젝트에 다음 분기 동안 완료되는 대로 전달되어야 하는 중요한 제품 기능이 포함되어 있다. 프로젝트 팀은 주니어 및 시니어 기술자로 구성되어 있다. 프로젝트 관리자가 제품 기능을 가능한 한 빨리 전달하기 위해 취해야 할 두 가지 조치는 무엇인가? (2개 선택) | 팀이 자체 조직화하도록 권한을 부여한다. | 명확하고 적절한 책임 수준에 맞춘다. | 시니어 기술자에게 주니어 기술자를 이끌도록 지시한다. | 주니어 기술자의 작업에 대한 상세 검토를 수행한다. | 시니어 기술자와 상세 계획을 검토한다. | A, B | 주니어 및 시니어 기술자로 제품 기능을 가능한 한 빨리 전달하기 위해, 프로젝트 관리자는 (A) 팀이 자체 조직화하도록 권한을 부여하고 (B) 명확하고 적절한 책임 수준에 맞춰야 한다. 자체 조직화는 효율성을 극대화하고 책임은 품질을 보장한다. 시니어에게 주니어 리드 지시(C)는 계층 구조를 만든다. 주니어 작업 상세 검토(D)는 미시적 관리이다. 시니어와 상세 계획 검토(E)는 팀 자율성을 제한한다.
313 | A project manager with agile experience is part of an organization that is transitioning to agile. The project manager was assigned to the first agile project by the project management office (PMO). The PMO manager asked the project manager if an existing governance from a previous project would be suitable to use in the current agile project. How should the project manager respond? | This framework is not appropriate for agile. | An agile approach is different. | This is a learning experience for the agile team. | An agile approach is easily adaptable. |  | D | The correct answer is D. An agile approach is easily adaptable. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 애자일 경험이 있는 프로젝트 관리자가 애자일로 전환 중인 조직의 일원이다. 프로젝트 관리자는 프로젝트 관리 오피스(PMO)에 의해 첫 번째 애자일 프로젝트에 배정되었다. PMO 관리자가 프로젝트 관리자에게 이전 프로젝트의 기존 거버넌스가 현재 애자일 프로젝트에 적합한지 물었다. 프로젝트 관리자는 어떻게 응답해야 하는가? | 이 프레임워크는 애자일에 적합하지 않다. | 애자일 접근 방식은 다르다. | 이것은 애자일 팀을 위한 학습 경험이다. | 애자일 접근 방식은 쉽게 적응할 수 있다. |  | D | 정답은 D이다. 애자일 접근 방식은 쉽게 적응할 수 있다. 애자일 실천은 반복적 전달, 팀 권한 부여, 지속적 개선을 강조한다. PM은 협력을 촉진하고, 장애물을 제거하며, 팀이 효과적으로 가치를 전달할 수 있도록 보장해야 한다.
314 | A project manager assigned to an education project needs to train a workforce in application development. The customer is responsible for providing the training center, and the deadline to start the first training is in 2 weeks. The customer calls to say that the center will not be available in 2 weeks due to some unforeseen problems. What should the project manager do next? | Apply the terms and conditions of the contract with penalties. | Update the project schedule with the new date for training. | Issue a change request to reflect the anticipated date for training. | Help the customer find an alternative location to start the training. |  | D | When the customer's training center will not be available in 2 weeks as planned, the project manager should help the customer find an alternative location to start training. Proactive problem-solving maintains the schedule. Applying contract penalties (A) damages the relationship. Updating the schedule with a new date (B) accepts the delay. Issuing a change request (C) formalizes the delay without solving it. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 교육 프로젝트에 배정된 프로젝트 관리자가 애플리케이션 개발 인력을 교육해야 한다. 고객은 교육 센터를 제공할 책임이 있으며, 첫 교육 시작 기한은 2주 후이다. 고객이 예상치 못한 문제로 인해 센터가 2주 후에 사용 불가능하다고 연락했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 계약 조건을 적용하여 위약금을 부과한다. | 새로운 교육 날짜로 프로젝트 일정을 업데이트한다. | 예상 교육 날짜를 반영하기 위해 변경 요청을 발행한다. | 고객이 교육을 시작할 대안 장소를 찾도록 돕는다. |  | D | 고객의 교육 센터가 계획대로 2주 후에 사용 불가능할 때, 프로젝트 관리자는 고객이 교육을 시작할 대안 장소를 찾도록 도와야 한다. 능동적 문제 해결은 일정을 유지한다. 계약 위약금 적용(A)은 관계를 손상시킨다. 새 날짜로 일정 업데이트(B)는 지연을 수용한다. 변경 요청 발행(C)은 해결 없이 지연을 공식화한다.
315 | A newly appointed product owner is working with a project team that is using agile for the first time. The product owner is constantly disrupting various team members throughout the day to discuss progress. This has resulted in the team feeling micromanaged and frustrated because of the constant disruptions. How should the project manager proceed? | Invite the product owner to attend daily standup meetings so they can assessprogress. | Invite the product owner ' s functional manager to a feedback session to escalate theissue. | Set up a feedback session with the product owner once a week so they can 138 assessprogress. | Instruct the team to refer the product owner to the project manager for information. |  | A | Inviting the product owner to daily standup meetings allows them to assess progress without disrupting team members throughout the day. Standups provide brief, focused updates on project status, issues, and plans. This fosters collaboration and trust between the PO and team while satisfying the PO's information needs. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 새로 임명된 제품 책임자가 처음으로 애자일을 사용하는 프로젝트 팀과 함께 작업하고 있다. 제품 책임자는 하루 종일 다양한 팀원을 방해하며 진행 상황을 논의하고 있다. 이로 인해 팀은 마이크로매니지를 받는다고 느끼고 지속적인 방해로 인해 좌절감을 느끼고 있다. 프로젝트 관리자는 어떻게 진행해야 하는가? | 제품 책임자를 일일 스탠드업 미팅에 참석하도록 초대하여 진행 상황을 평가할 수 있도록 한다. | 이슈를 에스컬레이션하기 위해 제품 책임자의 기능 관리자를 피드백 세션에 초대한다. | 제품 책임자가 진행 상황을 평가할 수 있도록 일주일에 한 번 피드백 세션을 설정한다. | 팀에게 정보를 위해 제품 책임자를 프로젝트 관리자에게 안내하도록 지시한다. |  | A | 제품 책임자를 일일 스탠드업 미팅에 초대하면 하루 종일 팀원을 방해하지 않고 진행 상황을 평가할 수 있다. 스탠드업은 프로젝트 상태, 이슈, 계획에 대한 간략하고 집중된 업데이트를 제공한다. 이는 PO와 팀 간의 협력과 신뢰를 촉진하는 동시에 PO의 정보 요구를 충족시킨다.
316 | A project manager finds out that the required project status reports have not been filled out by most team members. These status reports are urgently needed to compile a comprehensive status report for the project sponsor. What should the project manager do to address this situation? | Quickly put together a report that will satisfy the project sponsor. | Discuss the issue with the team members at fault. | Reprimand the team members who did not fill out the status reports. | Justify the team members ' behavior to the project sponsor. |  | B | When team members have not filled out required status reports urgently needed for the sponsor, the project manager should discuss the issue with the team members at fault to find the root cause and remind them of the reports' importance. Understanding why reports are missing enables targeted corrective action. Quickly compiling a report (A) may contain inaccurate information. Reprimanding team members (C) damages morale without understanding the cause. Justifying their behavior to the sponsor (D) is dishonest and unproductive. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Lead the Project Team | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 대부분의 팀원이 필요한 프로젝트 현황 보고서를 작성하지 않았다는 것을 알게 된다. 이 현황 보고서는 프로젝트 스폰서를 위한 포괄적인 현황 보고서를 컴파일하기 위해 긴급히 필요하다. 프로젝트 관리자는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 프로젝트 스폰서를 만족시킬 보고서를 빠르게 작성한다. | 잘못한 팀원들과 이슈를 논의한다. | 현황 보고서를 작성하지 않은 팀원들을 질책한다. | 프로젝트 스폰서에게 팀원들의 행동을 정당화한다. |  | B | 팀원들이 스폰서에게 긴급히 필요한 현황 보고서를 작성하지 않았을 때, 프로젝트 관리자는 잘못한 팀원들과 이슈를 논의하여 근본 원인을 찾고 보고서의 중요성을 상기시켜야 한다. 보고서가 누락된 이유를 이해하면 목표적인 시정 조치가 가능해진다. 빠른 보고서 컴파일(A)은 부정확한 정보를 포함할 수 있다. 팀원 질책(C)은 원인을 이해하지 않고 사기를 저하시킨다. 스폰서에게 행동 정당화(D)는 부정직하고 비생산적이다.
317 | During a documentation audit of an international company, it was identified that the last version of the project schedule was from one month ago even though the project manager knew it was recently updated. How should the project manager have handled documentation for the project? | Assigned a project team member to ensure all project documentation was updated | Updated the project management plan regularly and had it securely shared with all stakeholders | Kept documentation in the project management information system (PMIS), and shared it with appropriate stakeholders | Reviewed the risk register to identify a response plan for the audit |  | C | When an audit found the project schedule was outdated despite being recently updated, the project manager should have kept documentation in the project management information system (PMIS) and shared it with appropriate stakeholders. A centralized system ensures version control and accessibility. Assigning a team member to update documents (A) is ad hoc. Updating the project management plan regularly (B) is important but does not ensure centralized access. Reviewing the risk register (D) is unrelated to the documentation issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 국제 회사의 문서 감사 중 프로젝트 일정의 마지막 버전이 프로젝트 관리자가 최근 업데이트되었다는 것을 알고 있음에도 불구하고 1개월 전 것임이 확인되었다. 프로젝트 관리자는 프로젝트의 문서를 어떻게 관리했어야 했는가? | 모든 프로젝트 문서가 업데이트되도록 프로젝트 팀원을 배정했어야 했다. | 프로젝트 관리 계획을 정기적으로 업데이트하고 모든 이해관계자와 안전하게 공유했어야 했다. | 문서를 프로젝트 관리 정보 시스템(PMIS)에 보관하고 적절한 이해관계자와 공유했어야 했다. | 감사에 대한 대응 계획을 식별하기 위해 리스크 등록부를 검토했어야 했다. |  | C | 감사에서 프로젝트 일정이 최근 업데이트되었음에도 오래된 것으로 확인되었을 때, 프로젝트 관리자는 문서를 프로젝트 관리 정보 시스템(PMIS)에 보관하고 적절한 이해관계자와 공유했어야 했다. 중앙 시스템은 버전 관리와 접근성을 보장한다. 문서 업데이트를 위한 팀원 배정(A)은 임시적이다. 프로젝트 관리 계획의 정기적 업데이트(B)는 중요하지만 중앙화된 접근을 보장하지 않는다. 리스크 등록부 검토(D)는 문서 이슈와 관련이 없다.
318 | There is a conflict on an agile project about following organizational processes, many of which do not add any value to the project. To resolve this, which one of the following should be regarded with the highest priority? | Needs of the project manager | Needs of the agile lead | Needs of the customer | Needs of the organization |  | C | In agile, the highest priority is satisfying the customer through early and continuous delivery of valuable software. When organizational processes don't add project value, conflicts should be resolved by focusing on customer needs. This aligns with agile principles of customer collaboration over contract negotiation and responding to change over following a plan. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트에서 조직 프로세스 준수에 대한 갈등이 있으며, 많은 프로세스가 프로젝트에 어떤 가치도 추가하지 않는다. 이를 해결하기 위해 다음 중 가장 높은 우선순위로 고려해야 할 것은 무엇인가? | 프로젝트 관리자의 요구 | 애자일 리드의 요구 | 고객의 요구 | 조직의 요구 |  | C | 애자일에서 가장 높은 우선순위는 가치 있는 소프트웨어의 조기 및 지속적인 전달을 통해 고객을 만족시키는 것이다. 조직 프로세스가 프로젝트 가치를 추가하지 않을 때, 갈등은 고객 요구에 초점을 맞춰 해결되어야 한다. 이는 계약 협상보다 고객 협력을, 계획 준수보다 변화 대응을 우선시하는 애자일 원칙에 부합한다.
319 | The project manager of a hybrid project learns that a stakeholder has approached a team member directly to request a change. This change will impact the project in a significant way. The project manager should tell the stakeholder that the correct procedure for new requirements is to provide a request directly to whom? | Project manager | Change control board (CCB) | Project sponsor | Product owner |  | D | In a hybrid project, new requirements and change requests should be directed to the product owner, who is responsible for defining and prioritizing the product backlog. The PO evaluates each request and decides whether to incorporate it. The change control board (CCB) is used in traditional projects but not typically for hybrid projects following agile principles. The project sponsor provides financial support but doesn't own product requirements. The PM manages project work but doesn't define or prioritize the backlog. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Hybrid/Tailoring | 하이브리드 프로젝트의 프로젝트 관리자가 이해관계자가 팀원에게 직접 접근하여 변경을 요청한 것을 알게 된다. 이 변경은 프로젝트에 상당한 영향을 미칠 것이다. 프로젝트 관리자는 이해관계자에게 새로운 요구사항의 올바른 절차는 요청을 누구에게 직접 제공하는 것인지 알려야 한다. | 프로젝트 관리자 | 변경 통제 위원회(CCB) | 프로젝트 스폰서 | 제품 책임자 |  | D | 하이브리드 프로젝트에서 새로운 요구사항과 변경 요청은 제품 백로그를 정의하고 우선순위를 지정하는 제품 책임자에게 전달되어야 한다. PO는 각 요청을 평가하고 포함 여부를 결정한다. 변경 통제 위원회(CCB)는 전통적 프로젝트에서 사용되지만 애자일 원칙을 따르는 하이브리드 프로젝트에서는 일반적이지 않다. 프로젝트 스폰서는 재정 지원을 제공하지만 제품 요구사항을 소유하지 않는다. PM은 프로젝트 작업을 관리하지만 백로그를 정의하거나 우선순위를 지정하지 않는다.
320 | A company is starting a critical project with a strict deadline. During the first planning meeting, the team realizes that the list of requirements has too many items to allow on-time delivery. What should the project manager do first? | Update the risk register and present a contingency plan to meet the deadline. | Suggest to the customer to reduce the backlog to meet the date. | Increase the capacity of the team to finish the project on time. | Ask the team to propose a minimum viable product (MVP) to meet the date. |  | D | When a critical project with a strict deadline has too many requirements for on-time delivery, the project manager should first ask the team to propose a minimum viable product (MVP) to meet the date. MVP focuses on delivering maximum value within constraints. Updating the risk register (A) documents but does not resolve the issue. Reducing the backlog (B) should be customer-driven. Increasing team capacity (C) may exceed budget. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Embed Quality | Define Scope | Traditional PM | 회사가 엄격한 기한이 있는 중요한 프로젝트를 시작하고 있다. 첫 번째 계획 회의 중 팀이 요구사항 목록에 정시 전달을 허용하기에 너무 많은 항목이 있다는 것을 알게 된다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 리스크 등록부를 업데이트하고 기한을 맞추기 위한 비상 계획을 제시한다. | 고객에게 날짜를 맞추기 위해 백로그를 줄이도록 제안한다. | 프로젝트를 제시간에 완료하기 위해 팀의 역량을 늘린다. | 팀에게 날짜를 맞추기 위한 최소 기능 제품(MVP)을 제안하도록 요청한다. |  | D | 엄격한 기한이 있는 중요한 프로젝트에 요구사항이 너무 많아 정시 전달이 어려울 때, 프로젝트 관리자는 먼저 팀에게 날짜를 맞추기 위한 최소 기능 제품(MVP)을 제안하도록 요청해야 한다. MVP는 제약 조건 내에서 최대 가치 전달에 집중한다. 리스크 등록부 업데이트(A)는 문서화하지만 이슈를 해결하지 않는다. 백로그 축소(B)는 고객 주도여야 한다. 팀 역량 증가(C)는 예산을 초과할 수 있다.
321 | The product backlog has been completed and prioritized, and the first sprint has begun. A team member advised that during the daily standup there is a delay in having an external vendor contract signed. What is the project manager's priority in this situation? | Assist with the removal of impediments and blockers so that the project can continue | Take over contract negotiations for the team member to speed up the process | Determine a mitigation strategy to move the project forward | Request that the team member gel the contract signed as soon as possible |  | A | When a team member reports during the daily standup that an external vendor contract signing is delayed, the project manager's priority should be to assist with the removal of impediments and blockers so the project can continue. Removing blockers is a core servant leadership responsibility. Taking over contract negotiations (B) oversteps the team member's role. Determining a mitigation strategy (C) is secondary to removing the immediate blocker. Requesting the team member speed up (D) does not address the external dependency. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 제품 백로그가 완료되고 우선순위가 지정되었으며 첫 번째 스프린트가 시작되었다. 팀원이 일일 스탠드업에서 외부 벤더 계약 체결이 지연되고 있다고 알렸다. 이 상황에서 프로젝트 관리자의 우선순위는 무엇인가? | 프로젝트가 계속될 수 있도록 장애물과 차단 요소 제거를 지원한다. | 프로세스를 신속히 하기 위해 팀원을 대신하여 계약 협상을 인수한다. | 프로젝트를 전진시키기 위한 완화 전략을 결정한다. | 팀원에게 가능한 한 빨리 계약을 체결하도록 요청한다. |  | A | 팀원이 일일 스탠드업에서 외부 벤더 계약 체결 지연을 보고할 때, 프로젝트 관리자의 우선순위는 프로젝트가 계속될 수 있도록 장애물과 차단 요소 제거를 지원하는 것이다. 차단 요소 제거는 핵심적인 서번트 리더십 책임이다. 계약 협상 인수(B)는 팀원의 역할을 침범한다. 완화 전략 결정(C)은 즉각적인 차단 요소 제거에 부차적이다. 빠른 체결 요청(D)은 외부 의존성을 다루지 않는다.
322 | During the third iteration of a project, the product owner requests another mandatory feature. This also happened in the previous two sprints, which resulted in failure and caused frustration within the team. What should the project manager do next? | Ask the product owner to prioritize the backlog with the project team. | Request the scrum team to prioritize the product backlog. | Incorporate the changes in the last sprint before the first release. | Call for an internal meeting to discuss the changes and their value. |  | A | When the product owner repeatedly adds mandatory features mid-sprint causing failures and frustration, the project manager should ask the product owner to prioritize the backlog with the project team. Collaborative prioritization prevents sprint disruption. Requesting the scrum team to prioritize (B) bypasses the product owner's role. Incorporating changes in the last sprint before release (C) risks overload. Calling an internal meeting to discuss changes and value (D) may help but does not address the prioritization process. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 프로젝트의 세 번째 이터레이션 중, 제품 책임자가 또 다른 필수 기능을 요청한다. 이는 이전 두 스프린트에서도 발생하여 실패와 팀 내 좌절감을 유발했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 제품 책임자에게 프로젝트 팀과 함께 백로그 우선순위를 지정하도록 요청한다. | 스크럼 팀에게 제품 백로그의 우선순위를 지정하도록 요청한다. | 첫 번째 릴리스 전 마지막 스프린트에 변경 사항을 포함한다. | 변경 사항과 그 가치를 논의하기 위한 내부 회의를 소집한다. |  | A | 제품 책임자가 스프린트 중간에 반복적으로 필수 기능을 추가하여 실패와 좌절을 유발할 때, 프로젝트 관리자는 제품 책임자에게 프로젝트 팀과 함께 백로그 우선순위를 지정하도록 요청해야 한다. 협력적 우선순위 지정은 스프린트 혼란을 방지한다. 스크럼 팀에게 우선순위 지정 요청(B)은 제품 책임자의 역할을 우회한다. 마지막 스프린트에 변경 포함(C)은 과부하 위험이 있다. 변경과 가치 논의를 위한 내부 회의(D)는 도움이 될 수 있지만 우선순위 지정 프로세스를 다루지 않는다.
323 | A project manager is facilitating a project steering committee meeting where the prioritization of work items in the backlog is being discussed. The engineering executive wants to prioritize features based on level of effort, completing the smallest items first. The quality executive wants to complete the most complex tasks first to have adequate time to ensure a quality product is delivered. The compliance officer wants to complete items with associated regulatory components as they are essential items. How should the project manager prioritize the work items? | Complete the smaller tasks first to allow the team opportunities to prototype and evaluate development processes. | Ensure that the project value is within the quality guidelines by prioritizing and completing intricate tasks earlier in the project. | Ensure that the team assesses opportunities to deliver the highest business value items incrementally. | Complete tasks associated with regulatory components as the team cannot deliver business value that does not adhere to complianceregulations. |  | C | When executives disagree on backlog prioritization—smallest items first, most complex first, or regulatory first—the project manager should ensure the team assesses opportunities to deliver the highest business value items incrementally. Value-driven prioritization balances all perspectives while maximizing stakeholder benefit. Completing smallest items first (A) ignores value and risk. Prioritizing complex items first (B) may delay quick wins. Completing only regulatory items first (D) ignores business value optimization. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Business Environment | Plan and Manage Compliance | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 프로젝트 관리자가 프로젝트 운영 위원회 미팅을 진행하며 백로그의 작업 항목 우선순위 지정이 논의되고 있다. 엔지니어링 임원은 노력 수준에 따라 기능의 우선순위를 정하고 가장 작은 항목부터 완료하기를 원한다. 품질 임원은 품질 제품을 보장할 충분한 시간을 확보하기 위해 가장 복잡한 작업부터 완료하기를 원한다. 컴플라이언스 담당자는 필수 항목인 규제 구성 요소가 관련된 항목을 완료하기를 원한다. 프로젝트 관리자는 작업 항목의 우선순위를 어떻게 정해야 하는가? | 팀이 프로토타입을 만들고 개발 프로세스를 평가할 기회를 제공하기 위해 작은 작업부터 완료한다. | 프로젝트 초기에 복잡한 작업을 우선 완료하여 프로젝트 가치가 품질 가이드라인 내에 있도록 보장한다. | 팀이 가장 높은 비즈니스 가치 항목을 점진적으로 전달할 기회를 평가하도록 보장한다. | 컴플라이언스 규정을 준수하지 않는 비즈니스 가치는 전달할 수 없으므로 규제 구성 요소와 관련된 작업을 완료한다. |  | C | 임원들이 백로그 우선순위—가장 작은 항목 우선, 가장 복잡한 것 우선, 또는 규제 우선—에 대해 동의하지 않을 때, 프로젝트 관리자는 팀이 가장 높은 비즈니스 가치 항목을 점진적으로 전달할 기회를 평가하도록 보장해야 한다. 가치 중심 우선순위 지정은 모든 관점의 균형을 맞추면서 이해관계자 이익을 극대화한다. 가장 작은 항목 우선 완료(A)는 가치와 리스크를 무시한다. 복잡한 항목 우선(B)은 빠른 성과를 지연시킬 수 있다. 규제 항목만 우선 완료(D)는 비즈니스 가치 최적화를 무시한다.
324 | In a project management team meeting, one of the team members always argues with the project manager about the objective, timeline, and deliverable of any assigned task. What should the project manager do to manage this conflict? | Schedule a one-on-one meeting with the team member to talk about it and get theircooperation. | Schedule a meeting with the team member and their manager to discuss the issue. | Talk to the project sponsor about the team member ' s attitude. | Find another person to replace this team member. |  | A | The project manager should schedule a one-on-one meeting with the argumentative team member to discuss the issue and seek their cooperation. This problem-solving approach confronts the conflict directly and cooperatively, aiming for a mutually acceptable resolution. Meeting with the team member and their manager (B) may create distrust and resentment by escalating the issue. Talking to the project sponsor about the attitude (C) further escalates the conflict and damages the PM-team member relationship. Replacing the team member (D) disrupts the project schedule, budget, and scope, and should only be a last resort. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 관리 팀 미팅에서 한 팀원이 항상 프로젝트 관리자와 할당된 작업의 목표, 일정, 산출물에 대해 논쟁한다. 프로젝트 관리자는 이 갈등을 관리하기 위해 무엇을 해야 하는가? | 팀원과 일대일 미팅을 예약하여 이야기하고 협력을 얻는다. | 팀원과 그 관리자와 미팅을 예약하여 이슈를 논의한다. | 프로젝트 스폰서에게 팀원의 태도에 대해 이야기한다. | 이 팀원을 대체할 다른 사람을 찾는다. |  | A | 프로젝트 관리자는 논쟁적인 팀원과 일대일 미팅을 예약하여 이슈를 논의하고 협력을 구해야 한다. 이 문제 해결 접근 방식은 갈등을 직접적이고 협력적으로 대면하여 상호 수용 가능한 해결에 도달하는 것을 목표로 한다. 팀원과 관리자와의 미팅(B)은 이슈를 에스컬레이션하여 불신과 분노를 야기할 수 있다. 스폰서에게 태도에 대해 이야기(C)는 갈등을 더 에스컬레이션하고 PM-팀원 관계를 손상시킨다. 팀원 교체(D)는 프로젝트 일정, 예산, 범위를 방해하며 최후의 수단이어야 한다.
325 | A project manager created a contingency plan associated with a risk. The risk was realized, but the client insists on using a new workaround instead. The requested workaround will introduce delays and require additional budget. What should the project manager do? | Discuss the options with the client as part of the change control process | Proceed with the approved risk response plan. | Mitigate risks associated with the workaround to avoid project delays | Request to use the management reserve to keep the schedule |  | A | When the client insists on using a new workaround instead of the approved contingency plan, introducing delays and additional budget, the project manager should discuss the options with the client as part of the change control process. Formal change evaluation ensures informed decision-making. Requesting management reserves (D) acts before change approval. Mitigating workaround risks (C) assumes the workaround is already approved. Proceeding with the approved plan (B) ignores the client's input. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 리스크와 관련된 비상 계획을 만들었다. 리스크가 현실화되었지만, 고객은 새로운 임시 해결책을 사용하길 고집한다. 요청된 임시 해결책은 지연을 초래하고 추가 예산이 필요하다. 프로젝트 관리자는 어떻게 해야 하는가? | 변경 통제 프로세스의 일부로 고객과 옵션을 논의한다. | 승인된 리스크 대응 계획대로 진행한다. | 프로젝트 지연을 피하기 위해 임시 해결책과 관련된 리스크를 완화한다. | 일정을 유지하기 위해 관리 예비비 사용을 요청한다. |  | A | 고객이 승인된 비상 계획 대신 지연과 추가 예산을 초래하는 새로운 임시 해결책을 사용하길 고집할 때, 프로젝트 관리자는 변경 통제 프로세스의 일부로 고객과 옵션을 논의해야 한다. 공식적인 변경 평가는 정보에 입각한 의사결정을 보장한다. 관리 예비비 요청(D)은 변경 승인 전에 행동한다. 임시 해결책 리스크 완화(C)는 임시 해결책이 이미 승인되었다고 가정한다. 승인된 계획대로 진행(B)은 고객의 의견을 무시한다.
326 | In a project, one core team member tends to do all the work and ensures all tasks are completed. This core team member is soon leaving the project, which may make the project vulnerable. What should the project manager do? | Assess a mechanism for knowledge transfer among the team members. | Ask human resources (HR) to counsel the team member to balance the workload. | Motivate the team member to stay by providing them with incentives. | Ensure the activities of this team member are distributed across the project team. |  | A | When a core team member who handles a disproportionate amount of work is leaving the project, the project manager should assess a mechanism for knowledge transfer among team members. A structured knowledge transfer approach—through documentation, training sessions, and hands-on collaboration before departure—ensures critical knowledge and skills are preserved within the team. Asking HR to counsel the team member (B) does not address the knowledge gap. Motivating them to stay with incentives (C) may not be feasible and does not address the underlying vulnerability. Distributing the team member's activities (D) reallocates work but does not transfer the expertise needed to perform it effectively. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Help Ensure Knowledge Transfer | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트에서 한 핵심 팀원이 모든 작업을 수행하고 모든 과제가 완료되도록 보장하는 경향이 있다. 이 핵심 팀원이 곧 프로젝트를 떠날 예정이어서 프로젝트가 취약해질 수 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀원 간 지식 전달을 위한 메커니즘을 평가한다. | 인사부(HR)에 팀원에게 업무량 균형을 맞추도록 상담하도록 요청한다. | 인센티브를 제공하여 팀원이 남도록 동기를 부여한다. | 이 팀원의 활동을 프로젝트 팀 전체에 분배한다. |  | A | 불균형적으로 많은 작업을 처리하는 핵심 팀원이 프로젝트를 떠날 때, 프로젝트 관리자는 팀원 간 지식 전달을 위한 메커니즘을 평가해야 한다. 문서화, 교육 세션, 출발 전 실습 협력을 통한 구조적 지식 전달 접근 방식은 중요한 지식과 기술이 팀 내에서 보존되도록 보장한다. HR에 상담 요청(B)은 지식 격차를 다루지 않는다. 인센티브로 잔류 동기 부여(C)는 실현 불가능할 수 있으며 근본적인 취약성을 다루지 않는다. 팀원 활동 분배(D)는 작업을 재배분하지만 효과적으로 수행하는 데 필요한 전문성을 전달하지 않는다.
327 | A team is finishing the third release to present to the stakeholder as part of a demonstration. The company that subcontracts the developers has communicated that there is a cash flow problem and the company will not be able to provide the same resources for the next iterations. What should the project manager do next? | Escalate the situation to the project sponsor for a possible resolution. | Work with the project owner to prioritize the product backlog. | Create a risk register to track the risks and request additional budget. | Analyze the impact against the release plan if the blocker is not addressed. |  | D | When a subcontractor announces cash flow problems preventing the same resources for future iterations, the project manager should analyze the impact against the release plan if the blocker is not addressed. Impact assessment enables informed decisions. Escalating to the sponsor (A) is premature before analysis. Prioritizing the backlog (B) does not address the resource issue. Creating a risk register and requesting budget (C) responds without first understanding the impact. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 팀이 이해관계자에게 데모의 일부로 제시할 세 번째 릴리스를 완료하고 있다. 개발자를 하도급하는 회사가 현금 흐름 문제가 있어 다음 이터레이션에 동일한 자원을 제공할 수 없을 것이라고 전달했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 가능한 해결을 위해 프로젝트 스폰서에게 상황을 에스컬레이션한다. | 제품 책임자와 함께 제품 백로그의 우선순위를 지정한다. | 리스크를 추적하고 추가 예산을 요청하기 위한 리스크 등록부를 작성한다. | 차단 요소가 해결되지 않을 경우 릴리스 계획에 대한 영향을 분석한다. |  | D | 하도급업체가 현금 흐름 문제로 향후 이터레이션에 동일한 자원을 제공할 수 없다고 발표할 때, 프로젝트 관리자는 차단 요소가 해결되지 않을 경우 릴리스 계획에 대한 영향을 분석해야 한다. 영향 평가는 정보에 입각한 결정을 가능하게 한다. 스폰서에게 에스컬레이션(A)은 분석 전에 시기상조이다. 백로그 우선순위 지정(B)은 자원 이슈를 다루지 않는다. 리스크 등록부 작성과 예산 요청(C)은 영향을 먼저 파악하지 않고 대응한다.
328 | A client comes to the company asking to copy a project that was executed 2 years ago in the same city, with the expectation that the new project will have the same cost and duration. While finalizing the project management plan, the project manager realizes that the baseline costs are much higher than the original project. What could the project manager have done to avoid this? | Assigned the same project resources to this project | Verified applicable budget inputs related to this project | Estimated a budget for the project ' s quality management | Determined a budget reserve for this project |  | B | When a project copied from a previous one has much higher baseline costs than expected, the project manager could have avoided this by verifying applicable budget inputs related to the project. Validating current cost factors ensures accurate estimates. Assigning the same resources (A) does not account for cost changes. Estimating a quality management budget (C) is one factor, not comprehensive. Determining a budget reserve (D) plans for overruns without preventing them. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 고객이 2년 전 같은 도시에서 실행된 프로젝트를 복제해 달라고 회사에 요청하며, 새 프로젝트가 동일한 비용과 기간을 가질 것으로 기대한다. 프로젝트 관리 계획을 최종 확정하는 동안 프로젝트 관리자는 기준 비용이 원래 프로젝트보다 훨씬 높다는 것을 알게 된다. 프로젝트 관리자가 이를 피하기 위해 무엇을 할 수 있었는가? | 이 프로젝트에 동일한 프로젝트 자원을 배정했어야 했다. | 이 프로젝트와 관련된 적용 가능한 예산 입력을 확인했어야 했다. | 프로젝트의 품질 관리를 위한 예산을 추정했어야 했다. | 이 프로젝트를 위한 예산 예비비를 결정했어야 했다. |  | B | 이전 프로젝트에서 복제된 프로젝트의 기준 비용이 예상보다 훨씬 높을 때, 프로젝트 관리자는 프로젝트와 관련된 적용 가능한 예산 입력을 확인함으로써 이를 피할 수 있었다. 현재 비용 요인의 검증은 정확한 추정을 보장한다. 동일 자원 배정(A)은 비용 변화를 고려하지 않는다. 품질 관리 예산 추정(C)은 하나의 요소이지 포괄적이지 않다. 예산 예비비 결정(D)은 초과를 방지하지 않고 초과에 대비한다.
329 | A project schedule's risk level continues to increase during project execution because sprints are consistently delivering less than the intended results. The project manager becomes concerned that the deliverable will be delayed and cost more than the project sponsor intended. What should the project manager do first? | Engage with the project team to understand the schedule risk problem and present a solution to the project sponsor. | Schedule a meeting with the scrum master to explain that adding additional sprints is necessary to reduce risks. | Conduct a risk review meeting to gain a better understanding of the schedule, then document the results. | Notify the project sponsor of the schedule risk and request support to increase the project budget. |  | C | The correct answer is C. Conduct a risk review meeting to gain a better understanding of the schedule, then document the results. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 실행 중 프로젝트 일정의 리스크 수준이 계속 증가하고 있으며 스프린트가 지속적으로 의도한 결과보다 적게 전달하고 있다. 프로젝트 관리자는 산출물이 지연되고 프로젝트 스폰서가 의도한 것보다 더 많은 비용이 들 것을 우려한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 일정 리스크 문제를 이해하기 위해 프로젝트 팀과 소통하고 프로젝트 스폰서에게 솔루션을 제시한다. | 리스크를 줄이기 위해 추가 스프린트가 필요하다는 것을 설명하기 위해 스크럼 마스터와 미팅을 예약한다. | 일정에 대한 더 나은 이해를 위해 리스크 검토 미팅을 실시한 후 결과를 문서화한다. | 프로젝트 스폰서에게 일정 리스크를 알리고 프로젝트 예산 증액을 위한 지원을 요청한다. |  | C | 정답은 C이다. 일정에 대한 더 나은 이해를 위해 리스크 검토 미팅을 실시한 후 결과를 문서화한다. 애자일 환경에서 PM은 팀 협력을 촉진하고, 장애물을 제거하며, 애자일 원칙을 준수하면서 지속적인 가치 전달을 보장해야 한다.
330 | A project manager works for a large software development company that has multiple strategic business groups. The project manager has been assigned to develop maintenance planning software for a power plant. The project manager heard that a similar project that was executed by another business group in the company recently failed. The project manager is concerned about the project's performance and wants to take steps to help the project succeed. What should the project manager do? | Evaluate the project risk and try to replace the project with another one within the organization. | Continue executing the project using the project manager ' s usual methods as all projects are unique. | Inform the project sponsor about the risk and try to convince them to withdraw the project. | Study and apply the lessons learned from the failed project so that this project does not follow the same pattern. |  | D | When a similar project recently failed in another business group, the project manager should study and apply lessons learned from the failed project. Learning from past failures prevents repeating mistakes. Evaluating risk and trying to replace the project (A) abandons the initiative. Continuing with usual methods (B) ignores relevant experience. Informing the sponsor to withdraw (C) is premature without learning from the failure. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 여러 전략적 사업 그룹을 가진 대형 소프트웨어 개발 회사에서 근무한다. 프로젝트 관리자는 발전소용 유지보수 계획 소프트웨어를 개발하도록 배정되었다. 프로젝트 관리자는 회사 내 다른 사업 그룹이 실행한 유사한 프로젝트가 최근 실패했다는 것을 들었다. 프로젝트 관리자는 프로젝트 성과에 대해 우려하며 프로젝트 성공을 위한 조치를 취하고 싶어 한다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 리스크를 평가하고 조직 내 다른 프로젝트로 대체하려 한다. | 모든 프로젝트는 고유하므로 프로젝트 관리자의 일반적인 방법을 사용하여 프로젝트를 계속 실행한다. | 프로젝트 스폰서에게 리스크를 알리고 프로젝트를 철회하도록 설득하려 한다. | 실패한 프로젝트의 교훈을 연구하고 적용하여 이 프로젝트가 같은 패턴을 따르지 않도록 한다. |  | D | 다른 사업 그룹에서 유사한 프로젝트가 최근 실패했을 때, 프로젝트 관리자는 실패한 프로젝트의 교훈을 연구하고 적용해야 한다. 과거 실패로부터의 학습은 실수 반복을 방지한다. 리스크 평가 후 프로젝트 대체 시도(A)는 이니셔티브를 포기한다. 일반적인 방법으로 계속(B)은 관련 경험을 무시한다. 스폰서에게 철회를 알리는 것(C)은 실패로부터의 학습 없이 시기상조이다.
331 | A project scope statement has been approved, and the project manager and core team have been assigned to the project. Suddenly, the project manager takes a temporary leave of absence due to a medical emergency. While the project manager is on leave, the team develops the project schedule. When the project manager returns, a detailed schedule is almost complete. What should the project manager do? | Escalate the compliance issue to the project management office (PMO). | Congratulate the team and move on to the execution phase. | Ensure that the schedule is aligned with the vision and objectives. | Develop a new detailed schedule with the team and project sponsor. |  | C | When a project manager returns from leave to find a nearly complete schedule developed by the team, the priority should be to ensure the schedule is aligned with the project vision and objectives. This verifies that the team's work adheres to the approved scope statement and project goals. Escalating to the PMO (A) is unnecessary if alignment can be verified directly. Congratulating the team and proceeding (B) skips essential verification. Developing a new schedule (D) wastes the team's work without first checking alignment. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | 프로젝트 범위 기술서가 승인되었고, 프로젝트 관리자와 핵심 팀이 프로젝트에 배정되었다. 갑자기 프로젝트 관리자가 의료 응급 상황으로 일시적 휴직을 한다. 프로젝트 관리자가 휴직 중인 동안 팀이 프로젝트 일정을 개발한다. 프로젝트 관리자가 복귀했을 때 상세 일정이 거의 완성되었다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 관리 오피스(PMO)에 컴플라이언스 이슈를 에스컬레이션한다. | 팀을 축하하고 실행 단계로 넘어간다. | 일정이 비전 및 목표와 일치하는지 확인한다. | 팀과 프로젝트 스폰서와 함께 새로운 상세 일정을 개발한다. |  | C | 프로젝트 관리자가 휴직에서 복귀하여 팀이 개발한 거의 완성된 일정을 발견했을 때, 우선순위는 일정이 프로젝트 비전 및 목표와 일치하는지 확인하는 것이다. 이는 팀의 작업이 승인된 범위 기술서와 프로젝트 목표를 준수하는지 검증한다. PMO에 에스컬레이션(A)은 정렬이 직접 검증될 수 있다면 불필요하다. 팀을 축하하고 진행(B)은 필수 검증을 건너뛴다. 새 일정 개발(D)은 먼저 정렬을 확인하지 않고 팀의 작업을 낭비한다.
332 | How should the project manager develop the project management plan to ensure that the project continually delivers the expected benefits? | Perform integration testing of each release | Clarify project benefits with the sponsor. | Include the entire project team in testing | Identify the goal of each work product |  | D | When developing the project management plan to ensure continual delivery of expected benefits, the project manager should identify the goal of each work product. Aligning deliverables with benefit goals ensures value delivery. Clarifying benefits with the sponsor (A) is input, not plan development. Integration testing (B) is quality assurance. Including the entire team in testing (C) is execution, not planning. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 지속적으로 기대 이익을 전달하도록 프로젝트 관리자는 프로젝트 관리 계획을 어떻게 개발해야 하는가? | 각 릴리스의 통합 테스트를 수행한다. | 스폰서와 프로젝트 이익을 명확히 한다. | 전체 프로젝트 팀을 테스트에 포함시킨다. | 각 작업 산출물의 목표를 식별한다. |  | D | 프로젝트가 지속적으로 기대 이익을 전달하도록 프로젝트 관리 계획을 개발할 때, 프로젝트 관리자는 각 작업 산출물의 목표를 식별해야 한다. 산출물과 이익 목표의 정렬은 가치 전달을 보장한다. 스폰서와 이익 명확히(A)는 입력이지 계획 개발이 아니다. 통합 테스트(B)는 품질 보증이다. 전체 팀을 테스트에 포함(C)은 실행이지 계획이 아니다.
333 | A project manager works with a global virtual team. The team is facing difficulty in communicating with each other and often misses important messages. This difficulty leads to missed deadlines. What should the project manager do to enhance project team effectiveness? | Initiate daily communication of project progress | Implement team colocation to improve communication. | Schedule a communications control board meeting | Identify the root cause of communication issues |  | D | When a global virtual team faces communication difficulties causing missed deadlines, the project manager should identify the root cause of communication issues. Root-cause analysis enables targeted solutions. Initiating daily progress communication (A) increases volume without fixing underlying problems. Implementing colocation (B) is not feasible for a global team. Scheduling a communications control board meeting (C) monitors the plan but does not address effectiveness. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 프로젝트 관리자가 글로벌 가상 팀과 함께 작업한다. 팀은 서로 소통하는 데 어려움을 격고 있으며 종종 중요한 메시지를 놓친다. 이 어려움으로 마감일을 놓치게 된다. 프로젝트 팀의 효과성을 높이기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 진행 상황의 일일 커뮤니케이션을 시작한다. | 커뮤니케이션을 개선하기 위해 팀 콜로케이션을 구현한다. | 커뮤니케이션 통제 위원회 미팅을 예약한다. | 커뮤니케이션 이슈의 근본 원인을 식별한다. |  | D | 글로벌 가상 팀이 커뮤니케이션 어려움으로 마감일을 놓칠 때, 프로젝트 관리자는 커뮤니케이션 이슈의 근본 원인을 식별해야 한다. 근본 원인 분석은 목표적인 솔루션을 가능하게 한다. 일일 진행 커뮤니케이션 시작(A)은 근본적인 문제를 해결하지 않고 량만 늘린다. 콜로케이션 구현(B)은 글로벌 팀에서는 실현 불가능하다. 커뮤니케이션 통제 위원회 미팅(C)은 계획을 모니터링하지만 효과성을 다루지 않는다.
334 | A project team is transitioning from a predictive to an agile approach. The project manager is trying to minimize the support issues that the product has had in production. One particular pain point is the transition to operations, where the issues usually arise. What should the project manager do to improve this scenario? | Increase the focus on backlog items that cover support requirements, as well as product manuals and operation guides. | Engage the operation teams in the retrospectives and demo sessions and incorporate their feedback on project activities. | Ask the support/operation team to participate in the daily standup meetings to contribute to the project ' s progress. | Foster stakeholder participation by engaging them early on the backlog discussions. |  | B | When transitioning from predictive to agile and the main pain point is transition to operations, the project manager should engage the operation teams in retrospectives and demo sessions and incorporate their feedback. Direct involvement ensures operational concerns are addressed during development. Increasing focus on support backlog items (A) addresses documentation, not collaboration. Asking operations to join daily standups (C) may be excessive. Fostering early stakeholder participation in backlog discussions (D) is broad, not operations-specific. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Schedule | Closing | Build an Empowered Culture | Close Project or Phase | Traditional PM | 프로젝트 팀이 예측형에서 애자일 접근 방식으로 전환하고 있다. 프로젝트 관리자는 제품이 운영 환경에서 가지고 있는 지원 이슈를 최소화하려 하고 있다. 특히 운영으로의 전환이 이슈가 발생하는 주요 문제점이다. 프로젝트 관리자는 이 시나리오를 개선하기 위해 무엇을 해야 하는가? | 지원 요구사항을 다루는 백로그 항목과 제품 매뉴얼 및 운영 가이드에 대한 집중을 높인다. | 운영 팀을 회고 및 데모 세션에 참여시키고 프로젝트 활동에 대한 피드백을 반영한다. | 지원/운영 팀에게 프로젝트 진행에 기여하도록 일일 스탠드업 미팅에 참여하도록 요청한다. | 백로그 논의 초기에 이해관계자 참여를 촉진한다. |  | B | 예측형에서 애자일로 전환하며 운영으로의 전환이 주요 문제점일 때, 프로젝트 관리자는 운영 팀을 회고 및 데모 세션에 참여시키고 피드백을 반영해야 한다. 직접적인 참여는 개발 중 운영 우려사항이 해결되도록 보장한다. 지원 백로그 항목에 대한 집중 강화(A)는 문서화를 다루지만 협력을 다루지 않는다. 운영 팀의 일일 스탠드업 참여(C)는 과도할 수 있다. 이해관계자 조기 참여 촉진(D)은 광범위하며 운영에 특정되지 않는다.
335 | A project team has two members with conflicting personalities. This is affecting the rest of the team's performance. What should the project manager do? | Seek a solution during the daily coordination meeting. | Conduct an analysis to measure missed targets. | Organize a team-building activity for the team. | Understand the viewpoint of each team member. |  | D | When two team members with conflicting personalities are affecting overall team performance, the project manager should first understand the viewpoint of each team member. Active listening and empathy help identify the root cause of the conflict, which is essential before attempting resolution or escalation. Seeking solutions during a daily coordination meeting (A) risks exposing sensitive interpersonal conflict in an open forum. Conducting analysis of missed targets (B) is reactive and does not address the cause of the conflict. Organizing a team-building activity (C) may help team cohesion generally but does not directly resolve the specific interpersonal issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 팀에 성격이 충돌하는 두 명의 멤버가 있다. 이는 나머지 팀의 성과에 영향을 미치고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 일일 조정 미팅에서 해결책을 모색한다. | 누락된 목표를 측정하기 위한 분석을 수행한다. | 팀을 위한 팀 빌딩 활동을 조직한다. | 각 팀원의 관점을 이해한다. |  | D | 성격이 충돌하는 두 팀원이 전체 팀 성과에 영향을 미칠 때, 프로젝트 관리자는 먼저 각 팀원의 관점을 이해해야 한다. 적극적 경청과 공감은 갈등의 근본 원인을 파악하는 데 도움이 되며, 이는 해결이나 에스컬레이션 전에 필수적이다. 일일 조정 미팅에서 해결책 모색(A)은 민감한 대인관계 갈등을 공개 포럼에 노출할 위험이 있다. 누락 목표 분석(B)은 반응적이며 갈등 원인을 다루지 않는다. 팀 빌딩 활동(C)은 일반적인 팀 결속력에 도움이 될 수 있지만 특정 대인관계 이슈를 직접 해결하지 않는다.
336 | In an iteration-based marketing project, a product is scheduled to be launched at the sixth iteration. In the third iteration demo, the marketing team expressed that they need five iterations to launch the product and they have not started yet. What should the project team have done to avoid this issue? | Asked the marketing team to start working on the product immediately | Confirmed marketing requirements and constraints when adding to the backlog | Scheduled a demo presentation of the product during the first reason | Held a touchpoint with marketing before the demo to discuss any impediments |  | D | When the marketing team revealed during the third iteration demo that they needed five iterations but had not started, the project team should have held a touchpoint with marketing before the demo to discuss any impediments. Early, frequent collaboration with dependent stakeholders identifies misalignments and blockers before they become critical. Asking marketing to start immediately (A) does not address the planning gap. Confirming requirements when adding to the backlog (B) is correct practice but was not specific to the marketing dependency. Scheduling a first-iteration demo (C) is too early for marketing-specific coordination. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 이터레이션 기반 마케팅 프로젝트에서 제품이 여섯 번째 이터레이션에 출시될 예정이다. 세 번째 이터레이션 데모에서 마케팅 팀이 제품 출시에 5회의 이터레이션이 필요하며 아직 시작하지 않았다고 표현했다. 프로젝트 팀은 이 이슈를 피하기 위해 무엇을 했어야 하는가? | 마케팅 팀에게 즉시 제품 작업을 시작하도록 요청했어야 했다. | 백로그에 추가할 때 마케팅 요구사항과 제약을 확인했어야 했다. | 첫 번째 이터레이션에서 제품의 데모 프레젠테이션을 예약했어야 했다. | 장애물을 논의하기 위해 데모 전에 마케팅과 접점을 마련했어야 했다. |  | D | 마케팅 팀이 세 번째 이터레이션 데모에서 5회 이터레이션이 필요하지만 시작하지 않았다고 밝혔을 때, 프로젝트 팀은 데모 전에 마케팅과 접점을 마련하여 장애물을 논의했어야 했다. 의존성 있는 이해관계자와의 조기적이고 빈번한 협력은 불일치와 차단 요소가 심각해지기 전에 식별한다. 마케팅에게 즉시 시작 요청(A)은 계획 격차를 다루지 않는다. 백로그 추가 시 요구사항 확인(B)은 올바른 실천이지만 마케팅 의존성에 특정되지 않았다. 첫 이터레이션 데모 예약(C)은 마케팅 특화 조정에는 너무 이르다.
337 | A project manager determines that a critical path activity is going to be delayed. The team proposes a fallback plan that could get the project back on track; however, the plan would require an additional cost to an already tight budget. What should the project manager do? | Add additional resources to the project to fast track certain activities and reduce delays. | Evaluate the fallback plan proposed by the team and submit a change request, if required. | Communicate the delay to stakeholders and maintain the existing budget baseline. | Use the existing budget for executing the fallback plan and update the baseline. |  | B | When a critical path activity faces a delay and the team proposes a fallback plan requiring additional cost, the project manager should evaluate the fallback plan proposed by the team and submit a change request if required. This ensures the proposed changes are thoroughly assessed for impact on scope, time, cost, and quality, and formally approved before implementation. Adding resources to fast-track (A) may help but should not be done without evaluating the specific plan first. Communicating the delay and maintaining the baseline (C) accepts the delay without attempting corrective action. Using existing budget without formal approval (D) bypasses the change control process. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 크리티컬 패스 활동이 지연될 것으로 판단한다. 팀은 프로젝트를 다시 정상 궤도에 올릴 수 있는 대체 계획을 제안하지만, 이미 빠듯한 예산에 추가 비용이 필요하다. 프로젝트 관리자는 어떻게 해야 하는가? | 특정 활동을 빨리 진행하고 지연을 줄이기 위해 프로젝트에 추가 자원을 추가한다. | 팀이 제안한 대체 계획을 평가하고 필요시 변경 요청을 제출한다. | 이해관계자에게 지연을 알리고 기존 예산 기준선을 유지한다. | 대체 계획 실행을 위해 기존 예산을 사용하고 기준선을 업데이트한다. |  | B | 크리티컬 패스 활동이 지연에 직면하고 팀이 추가 비용이 필요한 대체 계획을 제안할 때, 프로젝트 관리자는 팀이 제안한 대체 계획을 평가하고 필요시 변경 요청을 제출해야 한다. 이는 제안된 변경이 범위, 시간, 비용, 품질에 미치는 영향을 철저히 평가하고 구현 전에 공식적으로 승인받도록 보장한다. 빠른 진행을 위한 자원 추가(A)는 특정 계획을 먼저 평가하지 않고 할 수 있지만 안 된다. 지연을 알리고 기준선 유지(C)는 시정 조치 없이 지연을 수용한다. 공식 승인 없이 기존 예산 사용(D)은 변경 통제 프로세스를 우회한다.
338 | A project manager has been using predictive methodology for more than 10 years and is switching to an agile project. The team members have not previously worked together. After two sprints of work, the team has not achieved any outcome and there is a lot of pressure to get work done. What kind of leadership style should the project manager use at this stage? | A leadership style that coaches people who want help and fosters greater team 642 collaboration | A passive leadership style that allows the team to self-organize until the norming stage is reached | A democratic style that uses techniques where majority opinion prevails | A directive style that makes decisions for the group to reach early outcomes |  | A | When an agile project team has not achieved outcomes after two sprints with pressure mounting and members who have not worked together before, the project manager should use a coaching leadership style that helps people who want assistance and fosters greater team collaboration. Coaching supports both agile self-organization and team development. A passive style (B) provides insufficient guidance. A democratic style (C) is decision-focused, not development-focused. A directive style (D) contradicts agile principles. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 10년 이상 예측형 방법론을 사용해왔으며 애자일 프로젝트로 전환하고 있다. 팀원들은 이전에 함께 작업한 적이 없다. 두 스프린트의 작업 후 팀이 어떤 결과도 달성하지 못했고 작업을 완료해야 한다는 많은 압박이 있다. 프로젝트 관리자는 이 단계에서 어떤 리더십 스타일을 사용해야 하는가? | 도움을 원하는 사람들을 코칭하고 더 큰 팀 협력을 촉진하는 리더십 스타일 | 노밍 단계에 도달할 때까지 팀이 자체 조직화하도록 허용하는 수동적 리더십 스타일 | 다수결 의견이 우세한 기법을 사용하는 민주적 스타일 | 조기 결과에 도달하기 위해 그룹을 위해 의사결정을 내리는 지시적 스타일 |  | A | 애자일 프로젝트 팀이 두 스프린트 후 결과를 달성하지 못하고 압박이 증가하며 이전에 함께 작업한 적이 없는 멤버들로 구성된 경우, 프로젝트 관리자는 도움을 원하는 사람들을 코칭하고 더 큰 팀 협력을 촉진하는 리더십 스타일을 사용해야 한다. 코칭은 애자일 자체 조직화와 팀 발전을 모두 지원한다. 수동적 스타일(B)은 불충분한 지침을 제공한다. 민주적 스타일(C)은 의사결정 중심이지 발전 중심이 아니다. 지시적 스타일(D)은 애자일 원칙에 모순된다.
339 | A company has transitioned and is now delivering projects using a hybrid approach instead of a predictive approach. The distributed project team's knowledge of agile is varied. The project manager feels this new methodology will impact the timely delivery of the project. What should the project manager do? | Use the predictive approach for team members who are not knowledgeable in agile project delivery practices. | Plan for training on agile tools and techniques used in the defined hybrid methodologyfor consistent application by all team members. | Ask to execute the project with a predictive approach since there is a budget and schedule risk. | Use crashing to reduce the critical path to ensure enough buffer to include the impact of the agile methodology update. |  | B | When transitioning to a hybrid approach with a distributed team of varying agile knowledge, the project manager should plan for training on the agile tools and techniques used in the defined hybrid methodology. Consistent training ensures all team members can effectively apply the methodology, reducing the risk of delivery delays from inconsistent practices. Using predictive approaches for some team members (A) fragments the methodology and defeats the purpose of transitioning. Reverting to a predictive approach entirely (C) abandons the transition. Using crashing to add schedule buffer (D) addresses symptoms with costly schedule compression rather than building team capability. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Resources | Executing | Adopt a Holistic View | Acquire Resources | Hybrid/Tailoring | 회사가 예측형 접근 방식 대신 하이브리드 접근 방식을 사용하여 프로젝트를 전달하도록 전환했다. 분산된 프로젝트 팀의 애자일 지식은 다양하다. 프로젝트 관리자는 이 새로운 방법론이 프로젝트의 적시 전달에 영향을 미칠 것이라고 느낌다. 프로젝트 관리자는 어떻게 해야 하는가? | 애자일 프로젝트 전달 실천에 대한 지식이 없는 팀원에게 예측형 접근 방식을 사용한다. | 정의된 하이브리드 방법론에서 사용되는 애자일 도구 및 기법에 대한 교육을 계획하여 모든 팀원이 일관되게 적용하도록 한다. | 예산 및 일정 리스크가 있으므로 예측형 접근 방식으로 프로젝트를 실행하도록 요청한다. | 애자일 방법론 업데이트의 영향을 포함할 충분한 버퍼를 확보하기 위해 크래싱을 사용하여 크리티컬 패스를 단축한다. |  | B | 다양한 애자일 지식을 가진 분산 팀으로 하이브리드 접근 방식으로 전환할 때, 프로젝트 관리자는 정의된 하이브리드 방법론에서 사용되는 애자일 도구 및 기법에 대한 교육을 계획해야 한다. 일관된 교육은 모든 팀원이 방법론을 효과적으로 적용할 수 있도록 보장하며, 비일관적인 실천으로 인한 전달 지연 위험을 줄인다. 일부 팀원에게 예측형 접근 사용(A)은 방법론을 분해하고 전환 목적을 상실시킨다. 예측형으로 전체 복귀(C)는 전환을 포기한다. 일정 버퍼 추가를 위한 크래싱(D)은 팀 역량을 구축하는 대신 비용이 많은 일정 압축으로 증상을 해결한다.
340 | During the forming phase of a project team, a project manager implements several team-building initiatives and decides it would be fun to have improvisational theater activities. After the sessions, the project manager received feedback from some key team members who felt that although the activity was fun, it was not appropriate for the purpose of team building. What should the project manager have done to avoid this negative feedback? | Sent the activity details to everyone involved prior to the session | Communicated the decision to conduct this activity to the key team stakeholders | Assessed and analyzed personality indicators from the project team | Selected a vendor for the activity according to the procurement management plan |  | C | When improvisational theater team-building activities receive negative feedback from key team members during the forming phase, the project manager should have assessed and analyzed personality indicators from the project team. Understanding personality types helps tailor activities to team preferences. Sending activity details in advance (A) improves awareness but not suitability. Communicating the decision to stakeholders (B) informs but does not validate appropriateness. Selecting a vendor per the procurement plan (D) addresses logistics, not team fit. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 팀의 형성 단계에서 프로젝트 관리자가 여러 팀 빌딩 이니셔티브를 구현하고 즉흥 연극 활동이 재미있을 것이라고 결정한다. 세션 후 프로젝트 관리자는 활동이 재미있었지만 팀 빌딩 목적에 적절하지 않았다고 느낀 몇몇 핵심 팀원으로부터 피드백을 받았다. 프로젝트 관리자는 이 부정적 피드백을 피하기 위해 무엇을 했어야 하는가? | 세션 전에 모든 관련자에게 활동 세부 사항을 보냈어야 했다. | 이 활동을 수행하겠다는 결정을 핵심 팀 이해관계자에게 알렸어야 했다. | 프로젝트 팀의 성격 지표를 평가하고 분석했어야 했다. | 조달 관리 계획에 따라 활동을 위한 벤더를 선정했어야 했다. |  | C | 형성 단계에서 즉흥 연극 팀 빌딩 활동이 핵심 팀원으로부터 부정적 피드백을 받았을 때, 프로젝트 관리자는 프로젝트 팀의 성격 지표를 평가하고 분석했어야 했다. 성격 유형을 이해하면 팀 선호도에 맞는 활동을 맞춤화하는 데 도움이 된다. 사전에 활동 세부 사항 전송(A)은 인식을 높이지만 적합성은 아니다. 이해관계자에게 결정 전달(B)은 알리지만 적절성을 검증하지 않는다. 조달 계획에 따른 벤더 선정(D)은 물류를 다루지 팀 적합성은 다루지 않는다.
341 | A project manager is assigned to a large construction project with more than 100 project team members. The project manager is having a hard time keeping the project on track and deriving the planned benefits. The project manager wants to make sure that each requirement is linked to the business and project objective. What should the project manager do? | Understand the project management plan. | Implement a requirements traceability matrix. | Review the requirements on a weekly basis. | Add the requirements to the project charter. |  | B | When managing a large construction project and needing to link each requirement to business objectives, the project manager should implement a requirements traceability matrix (RTM). An RTM maps requirements to project work and objectives, ensuring alignment and trackability. Understanding the project management plan (A) is too broad. Reviewing requirements weekly (C) monitors but does not create linkage. Adding requirements to the project charter (D) is inappropriate for detailed traceability. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 프로젝트 관리자가 100명 이상의 프로젝트 팀원이 있는 대형 건설 프로젝트에 배정된다. 프로젝트 관리자는 프로젝트를 정상 궤도에 올리고 계획된 이익을 도출하는 데 어려움을 격고 있다. 프로젝트 관리자는 각 요구사항이 비즈니스 및 프로젝트 목표와 연결되도록 하고 싶다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 관리 계획을 이해한다. | 요구사항 추적 매트릭스를 구현한다. | 요구사항을 주간 단위로 검토한다. | 요구사항을 프로젝트 헌장에 추가한다. |  | B | 대형 건설 프로젝트를 관리하며 각 요구사항을 비즈니스 목표와 연결해야 할 때, 프로젝트 관리자는 요구사항 추적 매트릭스(RTM)를 구현해야 한다. RTM은 요구사항을 프로젝트 작업 및 목표에 매핑하여 정렬과 추적성을 보장한다. 프로젝트 관리 계획 이해(A)는 너무 광범위하다. 요구사항 주간 검토(C)는 모니터링하지만 연결을 생성하지 않는다. 프로젝트 헌장에 요구사항 추가(D)는 상세 추적성에 부적절하다.
342 | A company has started developing a new product. During execution, the project team notices that another competitor has launched a product with very similar functionalities and a cheaper market price. What should have been done differently to avoid this scenario? | The Kanban method should have been utilized to optimize the work in progress (WIP). | An iterative life cycle approach should have been adopted. | More backlog refinement meetings should have been scheduled. | A minimum viable product (MVP) should have been released to get feedback from the market. |  | D | When a competitor launches a similar product at a cheaper price during execution, the team should have released a minimum viable product to get early market feedback. MVP validates market demand quickly. Using Kanban (A) optimizes workflow, not market strategy. Scheduling more backlog refinement (C) improves planning, not speed to market. An iterative life cycle (B) helps but does not specifically target market validation. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 회사가 새로운 제품을 개발하기 시작했다. 실행 중 프로젝트 팀이 다른 경쟁사가 매우 유사한 기능과 더 저렴한 시장 가격으로 제품을 출시한 것을 알게 된다. 이 시나리오를 피하기 위해 무엇을 다르게 했어야 하는가? | 진행 중인 작업(WIP)을 최적화하기 위해 칸반 방법을 활용했어야 했다. | 반복적 생애 주기 접근 방식을 채택했어야 했다. | 더 많은 백로그 정제 미팅을 예약했어야 했다. | 시장으로부터 피드백을 받기 위해 최소 기능 제품(MVP)을 출시했어야 했다. |  | D | 실행 중 경쟁사가 더 저렴한 가격으로 유사한 제품을 출시할 때, 팀은 조기 시장 피드백을 받기 위해 최소 기능 제품을 출시했어야 했다. MVP는 시장 수요를 빠르게 검증한다. 칸반 사용(A)은 워크플로를 최적화하지 시장 전략이 아니다. 백로그 정제 추가 예약(C)은 계획을 개선하지 시장 출시 속도는 아니다. 반복적 생애 주기(B)는 도움이 되지만 특별히 시장 검증을 목표로 하지 않는다.
343 | A team is working on implementing a communications system when the client says that they are considering closing the project. The project manager schedules an urgent meeting with the client to understand why the project is at risk. Which two tools or techniques can the project manager use to influence the client's decision to keep the project active? (Choose two) | Multi-criteria decision making | Voting | Alternatives analysis | Cost-benefit analysis | Autocratic decision making | C, D | When a client considers closing a project, the project manager can use two tools to influence the decision: alternatives analysis and cost-benefit analysis. Alternatives analysis generates and compares different courses of action, showing the client the pros and cons of continuing versus closing. Cost-benefit analysis demonstrates the project's return on investment and how benefits outweigh costs. Together, these provide factual, rational information to support the client's decision-making. Multi-criteria decision making (A) is broader than needed. Voting (B) is a team decision technique, not a client influence tool. Autocratic decision making (E) removes collaborative input. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 팀이 커뮤니케이션 시스템을 구현하는 작업을 하는 중 고객이 프로젝트 종료를 고려하고 있다고 말한다. 프로젝트 관리자는 프로젝트가 위험에 처한 이유를 이해하기 위해 고객과의 긴급 미팅을 예약한다. 프로젝트를 활성 상태로 유지하려는 고객의 결정에 영향을 미치기 위해 프로젝트 관리자가 사용할 수 있는 두 가지 도구 또는 기법은? (2개 선택) | 다기준 의사결정 | 투표 | 대안 분석 | 비용 편익 분석 | 독재적 의사결정 | C, D | 고객이 프로젝트 종료를 고려할 때, 프로젝트 관리자는 대안 분석과 비용 편익 분석이라는 두 가지 도구를 사용할 수 있다. 대안 분석은 다양한 행동 방침을 생성하고 비교하여 고객에게 계속 vs 종료의 장단점을 보여준다. 비용 편익 분석은 프로젝트의 투자 수익률과 이익이 비용을 초과하는 방법을 보여준다. 다기준 의사결정(A)은 필요 이상으로 광범위하다. 투표(B)는 팀 의사결정 기법이지 고객 영향 도구가 아니다. 독재적 의사결정(E)은 협력적 입력을 제거한다.
344 | The operations director complains to the CEO about the outcome of a project's first sprint. The operations department will not be able to support a new product due to poor performance indicators. The project team facilitator asks for feedback from the project team and is informed that performance information is available in the application server log. How should this complaint be addressed? | Invite a member of the operations team to be part of the validation and sprint meetings | Add the complaint to the product backlog to be addressed in the next sprint | Request that the issue be included in the next board of directors meeting to explain all of the needs | Ask the operations director to define the acceptance criteria to make clear the delivery is correct |  | A | When the operations director complains about the first sprint's outcome because of poor performance indicators, and the team confirms performance data is available in application server logs, the project manager should invite an operations team member to join validation and sprint meetings. This ensures operations requirements are incorporated into the development process, enabling real-time feedback and alignment. Adding the complaint to the backlog for the next sprint (B) delays resolution. Requesting a board of directors meeting (C) escalates unnecessarily. Asking the operations director to define acceptance criteria (D) is helpful but reactive—ongoing involvement is more effective. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 운영 이사가 프로젝트 첫 번째 스프린트 결과에 대해 CEO에게 불만을 제기한다. 운영 부서는 낮은 성능 지표로 인해 새 제품을 지원할 수 없다. 프로젝트 팀 퍼실리테이터가 프로젝트 팀에 피드백을 요청하며 성능 정보가 애플리케이션 서버 로그에 있다는 정보를 받는다. 이 불만은 어떻게 해결되어야 하는가? | 운영 팀의 멤버를 검증 및 스프린트 미팅에 참여하도록 초대한다. | 다음 스프린트에서 다루도록 불만을 제품 백로그에 추가한다. | 모든 요구 사항을 설명하기 위해 다음 이사회에 이슈를 포함하도록 요청한다. | 운영 이사에게 전달이 올바른지 명확히 하기 위해 수락 기준을 정의하도록 요청한다. |  | A | 운영 이사가 낮은 성능 지표로 첫 스프린트 결과에 불만을 제기하고 팀이 성능 데이터가 애플리케이션 서버 로그에 있다고 확인할 때, 프로젝트 관리자는 운영 팀 멤버를 검증 및 스프린트 미팅에 참여하도록 초대해야 한다. 이는 운영 요구사항이 개발 프로세스에 통합되어 실시간 피드백과 정렬을 가능하게 한다. 다음 스프린트 백로그에 불만 추가(B)는 해결을 지연시킨다. 이사회 미팅 요청(C)은 불필요한 에스컬레이션이다. 운영 이사에게 수락 기준 정의 요청(D)은 도움이 되지만 반응적이며 지속적인 참여가 더 효과적이다.
345 | A project manager has been assigned to an emergency project that must be completed within the next few weeks. The project manager realizes this will have an impact on the local community. As the work is near a school, the project manager has engaged with them to understand their needs. How should the project manager ensure the work continues smoothly? | Advise the school to close (or the duration of the project work | Continue the work as planned and inform the school when the project team arrives on-site | Postpone the required work on the project until school holidays begin | Liaise with the school to include nonworking project hours during school start and finish times |  | D | When project execution may impact a local community (especially a school), the PM should liaise with the affected parties to schedule non-working project hours during sensitive times (such as school start and finish). This minimizes disruption and demonstrates consideration for external stakeholders' needs—a hallmark of good project management practice. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트 관리자가 몇 주 내에 완료해야 하는 등 긴급 프로젝트에 배정되었다. 프로젝트 관리자는 이것이 지역 사회에 영향을 미칠 것임을 인식한다. 작업이 학교 근처이므로 프로젝트 관리자는 학교의 요구를 이해하기 위해 학교와 소통했다. 프로젝트 관리자는 작업이 원활하게 계속되도록 어떻게 보장해야 하는가? | 프로젝트 작업 기간 동안 학교에 휴교를 권고한다. | 계획대로 작업을 계속하고 프로젝트 팀이 현장에 도착할 때 학교에 알린다. | 학교 방학이 시작될 때까지 프로젝트의 필요한 작업을 연기한다. | 학교 등하교 시간에 프로젝트 비작업 시간을 포함하도록 학교와 연락한다. |  | D | 프로젝트 실행이 지역 사회(특히 학교)에 영향을 미칠 수 있을 때, PM은 영향을 받는 당사자와 연락하여 민감한 시간(학교 등하교 시간 등)에 비작업 시간을 예약해야 한다. 이는 혼란을 최소화하고 외부 이해관계자의 요구에 대한 배려를 보여주는 좋은 프로젝트 관리 실천의 특징이다.
346 | A company has selected a cross-functional team to develop an innovative digital product to drive the digital transformation project for the business. What should the project manager do to ensure business value is delivered early? | Break down the deliverables into sprints and deliver value incrementally. | Fast track the project and monitor tasks closely to ensure timely delivery. | Create robust incentives to the team members to encourage speedy delivery. | Create a detailed project plan and escalate delays to the functional managers. |  | A | To ensure early business value delivery for a digital transformation project, the project manager should break deliverables into sprints and deliver value incrementally. This agile approach enables quick wins, early feedback, and adaptive development focused on the most critical features. Fast tracking and monitoring (B) increases risk without ensuring early value delivery. Creating robust incentives (C) motivates speed but not value prioritization. Creating a detailed plan and escalating delays (D) follows a predictive approach that may delay value realization. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Build an Empowered Culture | Monitor and Control Project Performance | Digital Transformation | 회사가 비즈니스의 디지털 전환 프로젝트를 추진하기 위해 혁신적인 디지털 제품을 개발할 교차 기능 팀을 선정했다. 프로젝트 관리자는 비즈니스 가치가 조기에 전달되도록 무엇을 해야 하는가? | 산출물을 스프린트로 분해하고 점진적으로 가치를 전달한다. | 프로젝트를 불트래킹하고 적시 전달을 보장하기 위해 작업을 면밀히 모니터링한다. | 신속한 전달을 장려하기 위해 팀원에게 강력한 인센티브를 만든다. | 상세 프로젝트 계획을 작성하고 지연을 기능 관리자에게 에스컬레이션한다. |  | A | 디지털 전환 프로젝트에서 조기 비즈니스 가치 전달을 보장하기 위해, 프로젝트 관리자는 산출물을 스프린트로 분해하고 점진적으로 가치를 전달해야 한다. 이 애자일 접근 방식은 빠른 성과, 조기 피드백, 가장 중요한 기능에 집중한 적응적 개발을 가능하게 한다. 빨리 진행 및 모니터링(B)은 조기 가치 전달을 보장하지 않고 리스크를 높인다. 강력한 인센티브 제공(C)은 속도를 동기 부여하지만 가치 우선순위 지정은 아니다. 상세 계획 작성 및 지연 에스컬레이션(D)은 가치 실현을 지연시킬 수 있는 예측형 접근을 따른다.
347 | During a retrospective, one of the team members reports that a functional manager wants to be involved in task allocation. What should the project manager do? | Inform the functional manager that task allocation is the responsibility of the product owner. | Confirm with the team members that the functional manager is responsible for the delivery . | Inform the functional manager that self-organization includes task allocation. | Ask the product owner to clarify the roles and responsibilities of the project team. |  | C | When a functional manager wants to be involved in task allocation on an agile project, the project manager should inform the functional manager that self-organization includes task allocation. In agile, teams are empowered to determine how to accomplish their work, including distributing tasks. This supports team autonomy and accountability. Informing that the product owner allocates tasks (A) is incorrect—the product owner prioritizes, not allocates. Confirming the functional manager is responsible for delivery (B) contradicts agile principles. Asking the product owner to clarify roles (D) delegates a conversation the PM should lead. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 회고 중 팀원 중 한 명이 기능 관리자가 작업 할당에 참여하기를 원한다고 보고한다. 프로젝트 관리자는 어떻게 해야 하는가? | 기능 관리자에게 작업 할당은 제품 책임자의 책임이라고 알린다. | 팀원에게 기능 관리자가 전달에 책임이 있다고 확인한다. | 기능 관리자에게 자체 조직화에는 작업 할당이 포함된다고 알린다. | 제품 책임자에게 프로젝트 팀의 역할과 책임을 명확히 하도록 요청한다. |  | C | 기능 관리자가 애자일 프로젝트에서 작업 할당에 참여하기를 원할 때, 프로젝트 관리자는 기능 관리자에게 자체 조직화에는 작업 할당이 포함된다고 알려야 한다. 애자일에서 팀은 작업 분배를 포함하여 작업을 어떻게 수행할지 결정할 권한을 가진다. 이는 팀의 자율성과 책임을 지원한다. 제품 책임자가 작업을 할당한다고 알리는 것(A)은 틀림—제품 책임자는 우선순위를 지정하지 할당하지 않는다. 기능 관리자가 전달에 책임이 있다고 확인(B)은 애자일 원칙에 모순된다. 제품 책임자에게 역할 명확화 요청(D)은 PM이 주도해야 할 대화를 위임한다.
348 | A project with a hard timeline is starting its first iteration out of six. The project team is lacking the necessary skills to execute. What should the project manager do? | Invite stakeholders to discuss a mitigation plan to finish on time. | Allow the team to proceed as they attempt to meet the timeline. | Fill the skill gap personally to execute the project. | Add a subject matter expert (SME) to the project team. |  | D | When a project team lacks necessary skills with a hard timeline and six iterations ahead, the project manager should add a subject matter expert (SME) to the project team. An SME provides immediate specialized knowledge. Inviting stakeholders to discuss mitigation (A) does not address the skill gap directly. Allowing the team to proceed (B) risks failure. Filling the gap personally (C) is unsustainable for a PM. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Traditional PM | 엄격한 일정을 가진 프로젝트가 6회 중 첫 번째 이터레이션을 시작하고 있다. 프로젝트 팀이 실행에 필요한 역량이 부족하다. 프로젝트 관리자는 어떻게 해야 하는가? | 이해관계자를 초대하여 제시간에 완료하기 위한 완화 계획을 논의한다. | 팀이 일정을 맞추도록 시도하면서 진행하도록 허용한다. | 프로젝트를 실행하기 위해 개인적으로 기술 격차를 메운다. | 프로젝트 팀에 주제 전문가(SME)를 추가한다. |  | D | 프로젝트 팀이 엄격한 일정과 6회 이터레이션 앞두고 필요한 역량이 부족할 때, 프로젝트 관리자는 프로젝트 팀에 주제 전문가(SME)를 추가해야 한다. SME는 즉각적인 전문 지식을 제공한다. 이해관계자를 초대하여 완화 논의(A)는 기술 격차를 직접 해결하지 않는다. 팀이 진행하도록 허용(B)은 실패 위험이 있다. 개인적으로 격차 메우기(C)는 PM에게 지속 불가능하다.
349 | A project manager is working directly with a vice president who is also the project sponsor. The project is an organizational transformation for a company that primarily works on predictive projects. The project manager has been asked to use a hybrid approach to deliver before a defined date by using sprints. What should the project manager do first? | Set the project ' s purpose, mission, and vision. | Review similar projects in the company. | Carry out the product backlog creation. | Formalize the product owner assignment. |  | A | In a hybrid project involving organizational transformation, the project manager should first set the project's purpose, mission, and vision. This foundational step provides a guiding framework that aligns all subsequent activities—including sprint planning—with the organization's objectives and transformation goals. Reviewing similar projects (B) may provide useful context but does not establish the strategic direction. Creating the product backlog (C) is premature without first defining the project's overarching purpose. Formalizing the product owner assignment (D) is important for governance but secondary to establishing clarity on what the project aims to achieve. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Predictive-Agile Blend | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Hybrid/Tailoring | 프로젝트 관리자가 프로젝트 스폰서이기도 한 부사장과 직접 협력하고 있다. 프로젝트는 주로 예측형 프로젝트를 수행하는 회사의 조직 전환이다. 프로젝트 관리자는 스프린트를 사용하여 정해진 날짜 전에 전달하기 위해 하이브리드 접근 방식을 사용하도록 요청받았다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트의 목적, 사명, 비전을 설정한다. | 회사 내 유사한 프로젝트를 검토한다. | 제품 백로그 생성을 수행한다. | 제품 책임자 배정을 공식화한다. |  | A | 조직 전환을 포함하는 하이브리드 프로젝트에서 프로젝트 관리자는 먼저 프로젝트의 목적, 사명, 비전을 설정해야 한다. 이 기초적인 단계는 스프린트 계획을 포함한 모든 후속 활동을 조직의 목표와 전환 목표에 정렬하는 지침 프레임워크를 제공한다. 유사 프로젝트 검토(B)는 유용한 맥락을 제공할 수 있지만 전략적 방향을 설정하지 않는다. 제품 백로그 생성(C)은 프로젝트의 포괄적 목적을 먼저 정의하지 않으면 시기상조이다. 제품 책임자 배정 공식화(D)는 거버넌스에 중요하지만 달성 목표에 대한 명확성 확립에 부차적이다.
350 | A project is in the execution phase. During a few planning sessions, the team brought up dependencies and risks based on their knowledge of other projects. The project manager also received questions from the company in terms of how and when the team planned to perform acceptance testing and training activities. What should the project manager do next? | Add contingency m the schedule to account for dependencies and risks then review rt with the team | Document the project management plans and share them with the company and all team members via email for review | Engage with the company and the project team to determine the best course of action | Create a log to track risks assumptions issues and dependencies and establish a periodic review with the stakeholders |  | D | When the team identifies dependencies and risks during planning sessions and the company asks about acceptance testing and training activities, the project manager should create a log to track risks, assumptions, issues, and dependencies (RAID) and establish periodic stakeholder reviews. This comprehensive tracking mechanism with regular communication ensures all critical factors are monitored. Adding schedule contingency (A) addresses risk but not the broader tracking need. Documenting plans and emailing for review (B) is passive. Engaging stakeholders for best course of action (C) is collaborative but lacks the structured tracking framework. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트가 실행 단계에 있다. 몇 번의 계획 세션 동안 팀이 다른 프로젝트에 대한 지식을 바탕으로 의존성과 리스크를 제기했다. 프로젝트 관리자는 팀이 수락 테스트와 교육 활동을 언제 어떻게 수행할 계획인지에 대해 회사로부터 질문도 받았다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 의존성과 리스크를 고려하여 일정에 여유 시간을 추가한 후 팀과 검토한다. | 프로젝트 관리 계획을 문서화하고 검토를 위해 회사와 모든 팀원에게 이메일로 공유한다. | 회사와 프로젝트 팀과 소통하여 최선의 행동 방침을 결정한다. | 리스크, 가정, 이슈, 의존성을 추적하는 로그를 작성하고 이해관계자와의 정기적 검토를 설정한다. |  | D | 팀이 계획 세션에서 의존성과 리스크를 식별하고 회사가 수락 테스트와 교육 활동에 대해 물을 때, 프로젝트 관리자는 리스크, 가정, 이슈, 의존성(RAID)을 추적하는 로그를 작성하고 정기적인 이해관계자 검토를 설정해야 한다. 정기적 커뮤니케이션을 포함한 포괄적 추적 메커니즘은 모든 중요 요소가 모니터링되도록 보장한다. 일정 여유 추가(A)는 리스크를 다루지만 더 광범위한 추적 요구는 아니다. 계획 문서화 및 이메일 공유(B)는 수동적이다. 이해관계자와 최선 방침 논의(C)는 협력적이지만 구조화된 추적 프레임워크가 부족하다.
351 | A project team is reviewing solved project issues from the last phase of a project. The lead risk analyst points out that the next phase of the project includes a critical element with some reserves needed. What should the project manager do to successfully complete the next phase? | Update the risk response plan to include the needed reserve | Perform a schedule network analysis to avoid any critical path delays | Review the risk response plan to verify inclusion of the needed reserve | Request a reserve analysis and update the risk management plan |  | D | When the next project phase includes a critical element requiring reserves, the project manager should request a reserve analysis and update the risk management plan. Reserve analysis ensures adequate contingency for identified risks. Updating the risk response plan with reserves (A) is partial. Performing schedule network analysis (B) addresses timing, not reserves. Reviewing the risk response plan for existing reserves (C) is verification, not action. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 프로젝트 팀이 프로젝트 이전 단계에서 해결된 프로젝트 이슈를 검토하고 있다. 리스크 리드 애널리스트가 프로젝트의 다음 단계에 필요한 예비비가 있는 중요한 요소가 포함되어 있다고 지적한다. 프로젝트 관리자는 다음 단계를 성공적으로 완료하기 위해 무엇을 해야 하는가? | 필요한 예비비를 포함하도록 리스크 대응 계획을 업데이트한다. | 크리티컬 패스 지연을 피하기 위해 일정 네트워크 분석을 수행한다. | 필요한 예비비의 포함을 확인하기 위해 리스크 대응 계획을 검토한다. | 예비비 분석을 요청하고 리스크 관리 계획을 업데이트한다. |  | D | 프로젝트의 다음 단계에 예비비가 필요한 중요한 요소가 포함될 때, 프로젝트 관리자는 예비비 분석을 요청하고 리스크 관리 계획을 업데이트해야 한다. 예비비 분석은 식별된 리스크에 대한 충분한 비상 대책을 보장한다. 예비비를 포함하도록 리스크 대응 계획 업데이트(A)는 부분적이다. 일정 네트워크 분석 수행(B)은 시점을 다루지 예비비는 아니다. 기존 예비비를 위한 리스크 대응 계획 검토(C)는 검증이지 조치가 아니다.
352 | A project manager is working toward a deadline to prepare a client report. The project manager prepared a meeting agenda but not a single meeting has gone according to plan. Meetings always end in arguments and no action items come out of it. The project manager is very frustrated and seeks help from the project sponsor. What should the project manager have created to prevent this situation? | Work breakdown structure (WBS) | Team charter | Resource breakdown structure | Project charter |  | B | When meetings consistently devolve into arguments with no action items despite having an agenda, the project manager should have created a team charter. A team charter establishes behavioral expectations, decision-making processes, and team norms that prevent unproductive meetings. A WBS (A) defines project scope, not team behavior. A resource breakdown structure (C) organizes resources. A project charter (D) authorizes the project but does not govern team interactions. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 프로젝트 관리자가 고객 보고서 준비 기한을 향해 작업하고 있다. 프로젝트 관리자는 회의 의제를 준비했지만 회의가 계획대로 진행된 적이 한 번도 없다. 회의는 항상 논쟁으로 끝나고 어떤 조치 항목도 나오지 않는다. 프로젝트 관리자는 매우 좌절하며 프로젝트 스폰서에게 도움을 구한다. 프로젝트 관리자가 이 상황을 예방하기 위해 무엇을 만들었어야 하는가? | 작업 분류 체계(WBS) | 팀 헌장 | 자원 분류 체계 | 프로젝트 헌장 |  | B | 의제가 있음에도 회의가 지속적으로 논쟁으로 변질되고 조치 항목이 나오지 않을 때, 프로젝트 관리자는 팀 헌장을 만들었어야 했다. 팀 헌장은 행동 기대, 의사결정 프로세스, 비생산적인 회의를 방지하는 팀 규범을 설정한다. WBS(A)는 프로젝트 범위를 정의하지 팀 행동을 정의하지 않는다. 자원 분류 체계(C)는 자원을 조직한다. 프로젝트 헌장(D)은 프로젝트를 승인하지만 팀 상호작용을 관장하지 않는다.
353 | A project manager received several complaints from different project team members related to an unnecessary additional step the functional lead implemented as a preference. The project team members' work has been affected by this and they have missed a few deadlines. What should the project manager do to address this concern? | Advise the team that the functional lead ' s preference should be taken into consideration. | Document the additional step from the functional lead and adjust the timelines to accommodate the change. | Recommend the functional lead meet with the project team members to convince them to accept the change. | Ask the functional lead to remove this additional step as it is not vital to the project. |  | D | The correct answer is D. Ask the functional lead to remove this additional step as it is not vital to the project. Schedule management requires proactive monitoring and timely corrective actions. The PM should analyze schedule impacts, evaluate options, and implement appropriate responses to keep the project on track. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 기능 리드가 선호도에 따라 구현한 불필요한 추가 단계와 관련하여 여러 프로젝트 팀원으로부터 불만을 받았다. 프로젝트 팀원들의 작업이 영향을 받았고 몇 가지 마감일을 놓쳤다. 프로젝트 관리자는 이 우려를 해결하기 위해 무엇을 해야 하는가? | 기능 리드의 선호도를 고려해야 한다고 팀에 조언한다. | 기능 리드의 추가 단계를 문서화하고 변경을 수용하기 위해 일정을 조정한다. | 기능 리드가 변경을 수락하도록 프로젝트 팀원을 설득하기 위해 만나도록 권고한다. | 기능 리드에게 프로젝트에 필수적이지 않으므로 이 추가 단계를 제거하도록 요청한다. |  | D | 정답은 D이다. 기능 리드에게 프로젝트에 필수적이지 않으므로 이 추가 단계를 제거하도록 요청한다. 일정 관리는 사전 예방적 모니터링과 적시 시정 조치를 요구한다. PM은 일정 영향을 분석하고 옵션을 평가하며 프로젝트를 정상 궤도에 유지하기 위해 적절한 대응을 구현해야 한다.
354 | Construction work is preventing the project team members from entering the building where their offices are located. What should the project manager do next? | Continue business as usual since the construction work is not related to the project. | Select the next action to be taken according to the risk management plan. | Communicate with the stakeholders about the construction and ask for direction. | Inform the authorities so that they are aware of the situation and can take appropriate action. |  | B | Construction work preventing access to team offices represents the realization of an external risk. The project manager should select the next action according to the risk management plan, which defines pre-approved response strategies for identified risks. Following the established plan ensures a structured response rather than ad hoc decision-making. Continuing business as usual (A) ignores the disruption's impact on team productivity. Communicating with stakeholders and asking for direction (C) defers action instead of using the pre-approved plan. Informing authorities (D) may be necessary in specific cases but is not the PM's primary responsibility unless required by safety regulations. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 건설 작업으로 인해 프로젝트 팀원들이 사무실이 있는 건물에 입장할 수 없다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 건설 작업은 프로젝트와 관련이 없으므로 평상시와 같이 업무를 계속한다. | 리스크 관리 계획에 따라 취할 다음 조치를 선택한다. | 이해관계자에게 건설에 대해 알리고 방향을 요청한다. | 당국에 상황을 알리고 적절한 조치를 취할 수 있도록 한다. |  | B | 건설 작업으로 인해 팀 사무실 접근이 차단된 것은 외부 리스크의 실현을 나타낸다. 프로젝트 관리자는 식별된 리스크에 대한 사전 승인된 대응 전략을 정의하는 리스크 관리 계획에 따라 다음 조치를 선택해야 한다. 확립된 계획을 따르면 임의적 의사결정보다 구조화된 대응이 보장된다. 평상시와 같이 계속(A)은 팀 생산성에 대한 방해의 영향을 무시한다. 이해관계자와 소통하며 방향 요청(C)은 사전 승인된 계획을 사용하는 대신 조치를 지연시킨다. 당국에 알리기(D)는 특정 경우 필요할 수 있지만 안전 규정이 요구하지 않는 한 PM의 주요 책임이 아니다.
355 | A project manager finds that there are knowledge gaps in the project team relating to the core competencies required to deliver the desired results. What should the project manager do to achieve the desired results? | Communicate the situation to the customer and inform them about potential delays in delivery. | Communicate the situation to the team and plan for the necessary training and coaching arrangements | Plan to hire more experienced team members and lay off a few of the existing team members. | Report the situation back to upper management and request to have the scope changed |  | B | When knowledge gaps exist in the project team, the PM should communicate the situation transparently and arrange appropriate training and coaching. This addresses the root cause and helps the team improve their performance. Reporting to upper management for scope changes (A) may not be feasible. Replacing team members (B) disrupts dynamics and morale. Informing the customer about delays (D) damages trust without solving the underlying problem. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Scope & Requirements Mgmt | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 프로젝트 관리자가 원하는 결과를 전달하는 데 필요한 핵심 역량과 관련하여 프로젝트 팀에 지식 격차가 있음을 발견한다. 프로젝트 관리자는 원하는 결과를 달성하기 위해 무엇을 해야 하는가? | 고객에게 상황을 알리고 전달 지연 가능성을 알린다. | 팀에게 상황을 알리고 필요한 교육 및 코칭 준비를 계획한다. | 더 경험 있는 팀원을 고용하고 기존 팀원 일부를 해고할 계획을 세운다. | 상급 경영진에게 상황을 보고하고 범위 변경을 요청한다. |  | B | 프로젝트 팀에 지식 격차가 있을 때, PM은 상황을 투명하게 알리고 적절한 교육 및 코칭을 준비해야 한다. 이는 근본 원인을 해결하고 팀의 성과 개선을 돕는다. 범위 변경을 위해 상급 경영진에 보고(A)는 실현 불가능할 수 있다. 팀원 교체(B)는 팀 역학과 사기를 저해한다. 고객에게 지연 알림(D)은 근본 문제를 해결하지 않고 신뢰를 손상시킨다.
356 | A project manager prepared the base budget model to deliver a highly customizable software solution. The solution will be delivered in multiple countries with significantly different cultures and will be staged over phases. What should the project manager do next? | Apply the company ' s operational budgeting model. | Review the base model with the team leaders in each country to establish anindependent budget for each phase. | Ask the project management office (PMO) to review the draft budget. | Overestimate costs and underestimate revenues to include the impacts of differentcultural elements. |  | B | After preparing the base budget model for a multi-country, multi-phase customizable software solution, the project manager should review the base model with team leaders in each country to establish an independent budget for each phase. This accounts for variations in requirements, constraints, assumptions, risks, and cultural factors across countries and phases. Applying the company's operational budgeting model (A) may not capture the project's specific characteristics. Asking the PMO to review (C) is premature without country-level input. Overestimating costs and underestimating revenues (D) is unreliable and may waste resources or reduce profitability. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Baseline & Change Control | Process | Plan and Optimize Quality | Finance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 높은 맞춤형 소프트웨어 솔루션을 전달하기 위한 기본 예산 모델을 준비했다. 솔루션은 문화가 크게 다른 여러 국가에서 단계별로 전달될 예정이다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 회사의 운영 예산 모델을 적용한다. | 각 국가의 팀 리더와 기본 모델을 검토하여 각 단계에 대한 독립적인 예산을 수립한다. | 프로젝트 관리 오피스(PMO)에 초안 예산을 검토하도록 요청한다. | 다양한 문화적 요소의 영향을 포함하기 위해 비용을 과대 추정하고 수익을 과소 추정한다. |  | B | 다국가, 다단계 맞춤형 소프트웨어 솔루션의 기본 예산 모델을 준비한 후, 프로젝트 관리자는 각 국가의 팀 리더와 기본 모델을 검토하여 각 단계에 대한 독립적인 예산을 수립해야 한다. 이는 국가 및 단계 간 요구사항, 제약, 가정, 리스크, 문화적 요소의 차이를 반영한다. 회사의 운영 예산 모델 적용(A)은 프로젝트의 특성을 포착하지 못할 수 있다. PMO 검토 요청(C)은 국가별 입력 없이는 시기상조이다. 비용 과대 및 수익 과소 추정(D)은 신뢰할 수 없고 자원 낭비 또는 수익성 감소를 초래할 수 있다.
357 | An international client contacted a software development company to build out a software product, and an agile project manager was assigned. At one of the review meetings, the client complains that a feature mentioned at the initial debriefing was not implemented. What should the project manager do? | Review the original project documentation to confirm. | Assign a team member to immediately start working on that feature. | Treat it as a change request and assess the effect on the project ' s goals. | Include the mentioned feature in the prioritized requirements list. |  | C | When an international client complains that a feature from the initial debriefing was not implemented, the project manager should treat it as a change request and assess the effect on the project's goals. Formal change management evaluates impact. Reviewing original documentation (A) verifies history but does not resolve the issue. Assigning immediate work (B) bypasses change control. Adding to the prioritized list (D) skips assessment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 국제 고객이 소프트웨어 개발 회사에 소프트웨어 제품 구축을 연락했고 애자일 프로젝트 관리자가 배정되었다. 검토 회의 중 고객이 초기 브리핑에서 언급된 기능이 구현되지 않았다고 불만을 제기한다. 프로젝트 관리자는 어떻게 해야 하는가? | 확인하기 위해 원래 프로젝트 문서를 검토한다. | 팀원을 배정하여 즉시 해당 기능 작업을 시작하도록 한다. | 변경 요청으로 처리하고 프로젝트 목표에 대한 영향을 평가한다. | 언급된 기능을 우선순위가 지정된 요구사항 목록에 포함한다. |  | C | 국제 고객이 초기 브리핑 기능이 구현되지 않았다고 불만을 제기할 때, 프로젝트 관리자는 변경 요청으로 처리하고 프로젝트 목표에 대한 영향을 평가해야 한다. 공식적인 변경 관리는 영향을 평가한다. 원래 문서 검토(A)는 이력을 확인하지만 이슈를 해결하지 않는다. 즉시 작업 배정(B)은 변경 통제를 우회한다. 우선순위 목록 추가(D)는 평가를 건너떴다.
358 | A project manager is leading a project with strict time constraints. In team meetings, one of the team members is always silent. The project manager determines that this team member is not knowledgeable about the technology solution. The project manager is concerned that this problem will impact productivity. What should the project manager do? | Arrange formal training for this member to gain sufficient knowledge to reduce the impact on team performance. | Assign an experienced team member to work with this member on a daily basis in order to become knowledgeable about the technology. | Let this team member understand the urgency and encourage them to spend extra time to become knowledgeable about the technology. | Let the team lead the meeting discussions so that every member has a chance to prepare and speak up. |  | A | When a silent team member lacks knowledge about the technology under strict time constraints, the project manager should arrange formal training. Structured training ensures sufficient knowledge gain. Assigning a daily mentor (B) is less structured. Encouraging extra personal time (C) is not the PM's approach. Letting the team lead discussions (D) does not address the individual knowledge gap. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Help Ensure Knowledge Transfer | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 관리자가 엄격한 시간 제약이 있는 프로젝트를 이끄고 있다. 팀 회의에서 팀원 중 한 명이 항상 침묵한다. 프로젝트 관리자는 이 팀원이 기술 솔루션에 대한 지식이 없다고 판단한다. 프로젝트 관리자는 이 문제가 생산성에 영향을 미칠 것을 우려한다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀 성과에 대한 영향을 줄이기 위해 이 팀원을 위한 공식 교육을 준비한다. | 기술에 대해 익숙해지도록 매일 경험 있는 팀원을 배정하여 함께 작업하도록 한다. | 이 팀원에게 긴급성을 이해시키고 기술에 대해 익숙해지도록 추가 시간을 투자하도록 권장한다. | 모든 팀원이 준비하고 발언할 기회를 가지도록 팀이 회의 토론을 이끄도록 한다. |  | A | 엄격한 시간 제약 하에서 침묵하는 팀원이 기술에 대한 지식이 부족할 때, 프로젝트 관리자는 공식 교육을 준비해야 한다. 구조화된 교육은 충분한 지식 습득을 보장한다. 일일 멘토 배정(B)은 덜 구조화되어 있다. 추가 개인 시간 투자 권장(C)은 PM의 접근 방식이 아니다. 팀이 토론을 이끄도록 하는 것(D)은 개인의 지식 격차를 해결하지 않는다.
359 | A strategic project using international funds for a government agency is going through the execution phase. The government transition will take place in 1 month, and authorities will change. There is a risk that the project will be suspended or team members will be removed. The project manager wants to ensure that the project will continue despite these changes. Which action should the project manager take to address this situation? | Stop the project until the government transition has taken place. | Ask the sponsor to send a communication to the president-elect team with the progress of 148 the project. | Accept the risk as these changes are part of the organizational culture. | Ask the main stakeholders to document their progress on the project before the transition. |  | B | During political transitions affecting government-funded projects, proactive stakeholder engagement is essential for continuity. The project sponsor has the influence and position to communicate with the incoming administration about the project's progress, strategic value, and alignment with broader goals. Delaying activities (A) is wasteful. Documentation (C) supports but doesn't ensure continuity. Passive waiting (D) ignores risk mitigation opportunities. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 정부 기관의 국제 자금을 사용하는 전략 프로젝트가 실행 단계를 진행 중이다. 1개월 후 정부 전환이 이루어지며 당국이 변경된다. 프로젝트가 중단되거나 팀원이 제거될 위험이 있다. 프로젝트 관리자는 이러한 변화에도 불구하고 프로젝트가 계속되도록 보장하고 싶다. 프로젝트 관리자는 이 상황을 해결하기 위해 어떤 조치를 취해야 하는가? | 정부 전환이 이루어질 때까지 프로젝트를 중단한다. | 스폰서에게 프로젝트 진행 상황을 담은 커뮤니케이션을 차기 대통령 당선 팀에 보내도록 요청한다. | 이러한 변화는 조직 문화의 일부이므로 리스크를 수용한다. | 전환 전에 주요 이해관계자에게 프로젝트 진행 상황을 문서화하도록 요청한다. |  | B | 정부 자금 프로젝트에 영향을 미치는 정치적 전환 시, 사전 예방적 이해관계자 참여가 연속성에 필수적이다. 프로젝트 스폰서는 새 정부에 프로젝트의 진행 상황, 전략적 가치, 광범위한 목표와의 정렬을 알릴 수 있는 영향력과 지위를 가지고 있다. 활동 지연(A)은 낭비이다. 문서화(C)는 지원하지만 연속성을 보장하지 않는다. 수동적 대기(D)는 리스크 완화 기회를 무시한다.
360 | A project manager discovers that the project team is spending a large amount of time delivering several reporting formats for the same project updates to multiple stakeholders. What should the project manager do to reduce the time spent on these activities? | Segment the types of communications to be delivered to different stakeholders. | Hold biweekly status meetings to deliver information to all stakeholders at once. | Update the communications management plan to remove less influential stakeholders. | Delegate all of the stakeholder communications activities to a project team member. |  | A | When the team spends excessive time creating multiple reporting formats for the same updates, the project manager should segment the types of communications to be delivered to different stakeholders. Tailored communication reduces redundancy and effort. Holding biweekly status meetings (B) does not eliminate format proliferation. Removing less influential stakeholders (C) is exclusionary. Delegating all communications (D) shifts the burden without solving it. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 프로젝트 팀이 동일한 프로젝트 업데이트를 여러 이해관계자에게 여러 보고 형식으로 제공하는 데 많은 시간을 투자하고 있음을 발견한다. 프로젝트 관리자는 이러한 활동에 소요되는 시간을 줄이기 위해 무엇을 해야 하는가? | 다른 이해관계자에게 전달할 커뮤니케이션 유형을 세분화한다. | 모든 이해관계자에게 한 번에 정보를 전달하기 위해 격주 상태 회의를 개최한다. | 덜 영향력 있는 이해관계자를 제거하도록 커뮤니케이션 관리 계획을 업데이트한다. | 모든 이해관계자 커뮤니케이션 활동을 프로젝트 팀원에게 위임한다. |  | A | 팀이 동일한 업데이트를 여러 보고 형식으로 작성하는 데 과도한 시간을 소비할 때, 프로젝트 관리자는 다른 이해관계자에게 전달할 커뮤니케이션 유형을 세분화해야 한다. 맞춤형 커뮤니케이션은 중복과 노력을 줄인다. 격주 상태 회의 개최(B)는 형식 범람을 제거하지 않는다. 덜 영향력 있는 이해관계자 제거(C)는 배타적이다. 모든 커뮤니케이션 위임(D)은 문제를 해결하지 않고 부담을 전가한다.
361 | The project manager has observed that two team members have been arguing with each other openly at meetings. To push their ideas through, each team member individually spoke with the sponsor directly and made decisions without informing the project manager or other team members. What two actions should the project manager take? (Choose two) | Reiterate ground rules at the next meeting and ensure that all team members are clear about these rules. | Address the behavioral issue with each team member | Discuss this situation with other project managers and ask for advice | Ask the team members to work it out themselves | Discuss the behavior directly with their managers and request them to correct the behavior. | A, B | When two team members argue openly, bypass the PM to influence the sponsor, and make unilateral decisions, the project manager should take two actions: reiterate ground rules at the next meeting to clarify expected behavior, and address the behavioral issue with each team member individually. Ground rules reinforce norms while individual conversations address root causes. Asking them to work it out themselves (C) abdicates responsibility. Discussing with other PMs (D) breaches confidentiality. Discussing with their managers (E) escalates before direct engagement. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자는 두 팀원이 회의에서 공개적으로 다투고 있는 것을 관찰했다. 자신의 아이디어를 관철시키기 위해 각 팀원이 개별적으로 스폰서와 직접 대화하며 프로젝트 관리자나 다른 팀원에게 알리지 않고 결정을 내렸다. 프로젝트 관리자는 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 다음 회의에서 기본 규칙을 다시 언급하고 모든 팀원이 이러한 규칙을 명확히 이해하도록 보장한다. | 각 팀원과 행동 이슈를 다룬다. | 다른 프로젝트 관리자들과 이 상황을 논의하고 조언을 구한다. | 팀원들에게 스스로 해결하도록 요청한다. | 팀원들의 관리자와 직접 행동을 논의하고 행동을 바로잡도록 요청한다. | A, B | 두 팀원이 공개적으로 다투고 PM을 우회하여 스폰서에게 영향을 주며 일방적 결정을 내릴 때, 프로젝트 관리자는 두 가지 조치를 취해야 한다: 다음 회의에서 기본 규칙을 다시 언급하여 기대 행동을 명확히 하고, 각 팀원과 개별적으로 행동 이슈를 다룬다. 기본 규칙은 규범을 강화하고 개별 대화는 근본 원인을 다룬다. 스스로 해결하도록 요청(C)은 책임을 포기한다. 다른 PM과 논의(D)는 기밀을 침해한다. 관리자와 논의(E)는 직접 참여 전에 에스컬레이션한다.
362 | A project is ready to deliver the first batch of the product when a quality control check rejects the product as unfit for delivery. The root cause analysis (RCA) shows that a component added as part of the latest change request was not tested throughout the development cycle. What should the project manager do next? | Review the quality management process with the project management office (PMO) to ensure compliance with best practices. | Review the quality management process and perform a process audit as part of ongoing quality assurance. | Review the communications management plan to ensure change requests are communicated to the affected team members. | Review the change control process to ensure quality management artifacts are updated as part of the change. |  | D | When a quality control check rejects a product because a component from a change request was not tested, the project manager should review the change control process to ensure quality management artifacts are updated as part of future changes. The root cause is a gap where the change was not integrated into quality testing. Reviewing quality management with the PMO (A) is broader than needed. Performing a process audit (B) overlaps but does not specifically target the change control gap. Reviewing the communications plan (C) addresses information flow but not the quality-change integration issue. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Change Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 첫 번째 제품 배치를 전달할 준비가 되었을 때 품질 관리 검사에서 제품이 전달에 부적합하다고 거부한다. 근본 원인 분석(RCA)에 따르면 최신 변경 요청의 일부로 추가된 컴포넌트가 개발 주기 전체에서 테스트되지 않았다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 모범 사례 준수를 보장하기 위해 프로젝트 관리 오피스(PMO)와 품질 관리 프로세스를 검토한다. | 품질 관리 프로세스를 검토하고 지속적인 품질 보증의 일부로 프로세스 감사를 수행한다. | 변경 요청이 영향을 받는 팀원에게 전달되도록 커뮤니케이션 관리 계획을 검토한다. | 변경의 일부로 품질 관리 산출물이 업데이트되도록 변경 통제 프로세스를 검토한다. |  | D | 품질 관리 검사에서 변경 요청의 컴포넌트가 테스트되지 않아 제품을 거부할 때, 프로젝트 관리자는 향후 변경 시 품질 관리 산출물이 업데이트되도록 변경 통제 프로세스를 검토해야 한다. 근본 원인은 변경이 품질 테스트에 통합되지 않은 격차이다. PMO와 품질 관리 검토(A)는 필요 이상으로 광범위하다. 프로세스 감사 수행(B)은 격치지만 변경 통제 격차를 특정적으로 대상으로 하지 않는다. 커뮤니케이션 계획 검토(C)는 정보 흐름을 다루지만 품질-변경 통합 이슈는 다루지 않는다.
363 | An insurance company is planning to make a big change to its core application. The project manager realizes there is resistance to change from the sales agents since they are accustomed to taking orders manually and entering them in the system at the end of the day. With the new change, they will use point-of-sale devices to take orders online. What should the project manager do to get commitment from the sales agents? | Explain the change benefits to the sales agents ' manager to get their support. | Use a business case to model a sales pitch and gain consensus from the sponsors. | Escalate the issue to senior management to gain team buy-in | Request help from the project sponsor to get support from the sales agents. |  | D | When sales agents resist changing from manual order entry to point-of-sale devices, the project manager should request help from the project sponsor to get support from the sales agents. Sponsor influence facilitates organizational change adoption. Explaining benefits to the agents' manager (A) is indirect. Using a business case for a sales pitch (B) does not engage the agents directly. Escalating to senior management (C) bypasses the sponsor. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | General | General PM Principles | Process | Manage Project Closure | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 보험 회사가 핵심 애플리케이션에 큰 변경을 계획하고 있다. 프로젝트 관리자는 영업 사원들이 수동으로 주문을 받고 하루 끝에 시스템에 입력하는 데 익숙하기 때문에 변경에 대한 저항이 있음을 인식한다. 새로운 변경으로 그들은 POS 단말기를 사용하여 온라인으로 주문을 받게 된다. 프로젝트 관리자는 영업 사원들의 헌신을 얻기 위해 무엇을 해야 하는가? | 영업 사원 관리자에게 변경 이점을 설명하여 지원을 얻는다. | 비즈니스 케이스를 사용하여 영업 프레젤테이션을 모델링하고 스폰서들의 합의를 얻는다. | 팀의 동의를 얻기 위해 상급 경영진에게 이슈를 에스컬레이션한다. | 영업 사원들의 지원을 얻기 위해 프로젝트 스폰서에게 도움을 요청한다. |  | D | 영업 사원들이 수동 주문 입력에서 POS 단말기로의 변경에 저항할 때, 프로젝트 관리자는 영업 사원들의 지원을 얻기 위해 프로젝트 스폰서에게 도움을 요청해야 한다. 스폰서의 영향력은 조직 변화 도입을 촉진한다. 사원 관리자에게 이점 설명(A)은 간접적이다. 비즈니스 케이스로 영업 프레젤테이션(B)은 사원들을 직접 참여시키지 않는다. 상급 경영진 에스컬레이션(C)은 스폰서를 우회한다.
364 | The current incremental revenue expected by a project deliverable is not fulfilling the business case requirement. The deliverable was already closed and handed over to the operations team. Which two actions should the project manager take? (Choose two) | Report the issue to the product manager and business segments | Discuss the issue with the operations team to assess expense overruns | Analyze the business benefits criteria and assumptions | Review the issue with project sponsor and submit a change request | Schedule a project review meeting to analyze the root cause | C, E | When a delivered project is not meeting business case requirements, the PM should analyze the business benefits criteria and assumptions to identify any initial planning discrepancies, and schedule a project review meeting to investigate root causes. This combination addresses both the strategic alignment question (were the benefits assumptions correct?) and the operational question (what went wrong in execution?). Together, these actions provide the insight needed for corrective measures or future improvements. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Stakeholders | Monitoring & Controlling | Focus on Value | Monitor Stakeholder Engagement | Traditional PM | 프로젝트 산출물에 의해 예상되는 현재 점진적 수익이 비즈니스 케이스 요구사항을 충족하지 못하고 있다. 산출물은 이미 종료되어 운영 팀에 인계되었다. 프로젝트 관리자는 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 제품 관리자와 비즈니스 부문에 이슈를 보고한다. | 운영 팀과 비용 초과를 평가하기 위해 이슈를 논의한다. | 비즈니스 혜택 기준과 가정을 분석한다. | 프로젝트 스폰서와 이슈를 검토하고 변경 요청을 제출한다. | 근본 원인을 분석하기 위한 프로젝트 검토 회의를 예약한다. | C, E | 전달된 프로젝트가 비즈니스 케이스 요구사항을 충족하지 못할 때, PM은 비즈니스 혜택 기준과 가정을 분석하여 초기 계획 불일치를 식별하고, 근본 원인을 조사하기 위한 프로젝트 검토 회의를 예약해야 한다. 이 조합은 전략적 정렬 질문(혜택 가정이 올바른가?)과 운영적 질문(실행에서 무엇이 잘못되었는가?)을 모두 다룬다. 이 조치들은 시정 조치 또는 향후 개선에 필요한 통찰력을 제공한다.
365 | A project is nearing completion when a critical resource can no longer work on the project. A temporary replacement is brought in from an external company to take over the role; however, complaints are soon received from other team members about this person's unprofessional conduct and behavior. What should the project manager do first? | Hold one-on-one meetings with the new team member and the rest of the team members to align the team charter. | Ask the contracting agency to replace the temporary team member. | Report the new team member to human resources (HR) for disciplinary actions. 1320 | Discuss the team charter with the new team member to align them with the agreed-upon conduct within the team. |  | D | When a temporary replacement team member exhibits unprofessional conduct near project completion, the project manager should first discuss the team charter with the new member to align them with agreed-upon conduct. Setting expectations addresses the behavior directly. One-on-one meetings with everyone (A) is time-consuming. Asking the agency to replace (B) causes further disruption. Reporting to HR (C) escalates prematurely. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트가 완료에 가까울 때 중요한 자원이 더 이상 프로젝트에 참여할 수 없게 된다. 외부 회사에서 임시 대체자가 투입되어 역할을 인수하지만, 곳 다른 팀원들로부터 이 사람의 비전문적인 행동과 행동에 대한 불만이 접수된다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 새 팀원 및 나머지 팀원들과 1:1 미팅을 개최하여 팀 헌장을 정렬한다. | 계약 업체에 임시 팀원을 교체하도록 요청한다. | 새 팀원을 징계 조치를 위해 인사부(HR)에 보고한다. | 새 팀원과 팀 헌장을 논의하여 팀 내에서 합의된 행동에 정렬한다. |  | D | 임시 대체 팀원이 프로젝트 완료 근처에서 비전문적인 행동을 보일 때, 프로젝트 관리자는 먼저 새 팀원과 팀 헌장을 논의하여 합의된 행동에 정렬해야 한다. 기대치를 설정하면 행동을 직접 다룬다. 모든 사람과 1:1 미팅(A)은 시간이 많이 걸린다. 업체에 교체 요청(B)은 추가 혼란을 초래한다. HR 보고(C)는 성급하게 에스컬레이션한다.
366 | A product owner presented the backlog to the team, and the team raised concerns over implementing some of the features due to various impediments. What should the project manager suggest that the product owner do next? | Begin to remove the impediments, starting with the easiest ones first, to foster team accomplishment | Capture the impediments and inform management that their assistance is neededin resolving the impediments | Ensure that the impediments are captured and prioritized based upon the highest valued features | Estimate the financial impact of the impediments and request additional funding |  | C | When the team raises concerns about impediments to implementing backlog features, the project manager should suggest the product owner ensure impediments are captured and prioritized based on the highest valued features. Aligning impediment resolution with value delivery addresses the most critical blockers first. Removing the easiest impediments first (A) does not maximize value. Capturing and escalating to management (B) delays resolution. Estimating financial impact and requesting funding (D) may be premature. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 제품 책임자가 팀에게 백로그를 제시했고, 팀이 다양한 장애물로 인해 일부 기능 구현에 대한 우려를 제기했다. 프로젝트 관리자는 제품 책임자에게 다음에 무엇을 하도록 제안해야 하는가? | 팀 성취감을 장려하기 위해 가장 쉬운 것부터 장애물 제거를 시작한다. | 장애물을 기록하고 해결에 도움이 필요하다고 경영진에 알린다. | 장애물을 기록하고 가장 높은 가치의 기능에 기반하여 우선순위를 매긴다. | 장애물의 재정적 영향을 추정하고 추가 자금을 요청한다. |  | C | 팀이 백로그 기능 구현에 대한 장애물 우려를 제기할 때, 프로젝트 관리자는 제품 책임자에게 장애물을 기록하고 가장 높은 가치의 기능에 기반하여 우선순위를 매기도록 제안해야 한다. 장애물 해결을 가치 전달에 맞추면 가장 중요한 차단 요소를 먼저 해결한다. 가장 쉬운 장애물부터 제거(A)는 가치를 극대화하지 않는다. 경영진에게 기록 및 에스컬레이션(B)은 해결을 지연시킨다. 재정적 영향 추정 및 추가 자금 요청(D)은 성급할 수 있다.
367 | A project manager writes to the receiving organization to inform them that all acceptance activities are completed with success and it is time to initiate handover. The receiving manager replies that the team will not be ready for the handover procedure for another two weeks. What should the project manager do? | Issue an internal change request to secure the resources for an additional two weeks. | Inform the project sponsor of the two-week delay and replan activities to minimizedelays. | Deliver to the receiving manager on time, who can then make a knowledge transfer totheir team. | Request that the receiving manager issue a change request to prolong the project bytwo weeks. |  | D | When the receiving organization is not ready for handover for two more weeks after all acceptance activities are complete, the project manager should request that the receiving manager issue a change request to prolong the project by two weeks. The requesting party should initiate the change. Issuing an internal change request (A) is unilateral. Informing the sponsor and replanning (B) bypasses formal change control. Delivering on time regardless (C) risks poor knowledge transfer. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 모든 수락 활동이 성공적으로 완료되었으며 인계를 시작할 시간이라고 수신 조직에 서면으로 알린다. 수신 관리자는 팀이 2주 동안 인계 절차를 준비할 수 없다고 답변한다. 프로젝트 관리자는 어떻게 해야 하는가? | 추가 2주간 자원을 확보하기 위한 내부 변경 요청을 발행한다. | 프로젝트 스폰서에게 2주 지연을 알리고 지연을 최소화하기 위해 활동을 재계획한다. | 수신 관리자에게 제시간에 전달하고 팀에게 지식 이전을 하도록 한다. | 수신 관리자에게 프로젝트를 2주 연장하는 변경 요청을 발행하도록 요청한다. |  | D | 모든 수락 활동 완료 후 수신 조직이 2주간 인계를 준비할 수 없을 때, 프로젝트 관리자는 수신 관리자에게 프로젝트를 2주 연장하는 변경 요청을 발행하도록 요청해야 한다. 요청 당사자가 변경을 개시해야 한다. 내부 변경 요청 발행(A)은 일방적이다. 스폰서에게 알리고 재계획(B)은 공식적 변경 통제를 우회한다. 무조건 제시간 전달(C)은 부실한 지식 이전을 위험한다.
368 | At the daily project meeting, team members are complaining about receiving emails from their functional managers to support other nonproject-related tasks. This is having a negative effect on the team's productivity. What should the project manager do next? | Ask the product owner to speak with the functional managers to ensure future requirements come through the product owner. | Schedule a meeting with all of the functional managers to resolve the resource conflicts. | Log this as a risk in the risk register and continue to monitor the issue at subsequent meetings. | Address this concern with the functional managers to ensure there will be no further delays. |  | D | The PM should address the resource conflict directly with the functional managers to prevent further project delays. Functional managers hold authority over team member assignments and are responsible for balancing organizational priorities. The PM should communicate the impact of non-project tasks on team productivity and negotiate to ensure team members remain focused on project priorities. If needed, the PM should seek support from the project sponsor or senior management to resolve resource allocation conflicts. Routing the issue through the product owner (A) is ineffective since the PO handles product requirements, not resource management. Simply logging it as a risk (C) without taking action is insufficient. Scheduling a large group meeting (D) may be unnecessarily complex when direct individual communication with each functional manager is more efficient. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 일일 프로젝트 회의에서 팀원들이 기능 관리자들로부터 프로젝트와 관련 없는 다른 작업을 지원하라는 이메일을 받는 것에 대해 불만을 제기하고 있다. 이는 팀의 생산성에 부정적인 영향을 미치고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 향후 요구사항이 제품 책임자를 통해 들어오도록 기능 관리자와 대화하도록 제품 책임자에게 요청한다. | 자원 충돌을 해결하기 위해 모든 기능 관리자와 회의를 예약한다. | 이것을 리스크 레지스터에 리스크로 기록하고 후속 회의에서 이슈를 계속 모니터링한다. | 추가 지연이 없도록 기능 관리자들과 이 우려를 직접 다룬다. |  | D | PM은 프로젝트 지연을 방지하기 위해 기능 관리자들과 자원 충돌을 직접 다루어야 한다. 기능 관리자는 팀원 배정에 대한 권한을 가지며 조직적 우선순위 균형에 책임이 있다. PM은 비프로젝트 작업이 팀 생산성에 미치는 영향을 전달하고 팀원들이 프로젝트 우선순위에 집중하도록 협상해야 한다. 제품 책임자를 통한 라우팅(A)은 PO가 제품 요구사항을 다루지 자원 관리는 다루지 않으므로 비효과적이다. 리스크로만 기록(C)은 조치 없이 불충분하다. 대규모 그룹 회의 예약(D)은 각 기능 관리자와의 직접적 개별 소통이 더 효율적일 때 불필요하게 복잡할 수 있다.
369 | Three months after creating a project schedule, the scope of a project significantly changed, resulting in a schedule rebaselining. One month after rebaselining, the project is two weeks behind schedule with a cost performance index (CPI) of 0.93. What should the project manager do to help get the project back on schedule? | Meet with the project stakeholders and inform them that the project is going to be delayed. | Manage the schedule's critical path, as this was an approved scheduling change. | Crash the project with two additional contract resources for the newly identified tasks. | Review the project schedule and find ways to fast-track the overall project schedule. |  | D | When a project is two weeks behind schedule with CPI of 0.93 after a rebaseline, the project manager should review the project schedule and find ways to fast-track the overall schedule. Fast-tracking compresses the schedule by overlapping activities. Meeting stakeholders to report delay (A) communicates but does not recover. Managing the critical path (B) is ongoing, not a specific recovery action. Crashing with additional resources (C) increases cost, worsening the already poor CPI. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Earned Value Management | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트 일정을 만든 지 3개월 후, 프로젝트 범위가 크게 변경되어 일정 재기준선화가 이루어졌다. 재기준선화 1개월 후, 프로젝트가 일정보다 2주 뒤캘지며 비용 성과 지수(CPI)가 0.93이다. 프로젝트 관리자는 프로젝트를 다시 일정에 맞추기 위해 무엇을 해야 하는가? | 프로젝트 이해관계자와 만나 프로젝트가 지연될 것임을 알린다. | 승인된 일정 변경이므로 일정의 크리티컬 패스를 관리한다. | 새로 식별된 작업에 대해 2명의 추가 계약 자원으로 프로젝트를 크래싱한다. | 프로젝트 일정을 검토하고 전체 프로젝트 일정을 빨리 진행할 방법을 찾는다. |  | D | 재기준선화 후 프로젝트가 일정보다 2주 뒤캘지고 CPI가 0.93일 때, 프로젝트 관리자는 프로젝트 일정을 검토하고 전체 일정을 빨리 진행할 방법을 찾아야 한다. 빨리 진행은 활동을 중첩하여 일정을 압축한다. 이해관계자와 만나 지연 보고(A)는 소통하지만 회복하지 않는다. 크리티컬 패스 관리(B)는 지속적이지 특정 회복 조치가 아니다. 추가 자원으로 크래싱(C)은 이미 낮은 CPI를 악화시키면서 비용을 증가시킨다.
370 | A project manager is working with a team that is demotivated and tired, as the project has been changing direction due to budget cuts from the sponsor. What should the project manager do first? | Remind the team of their commitment with the client and the need to adapt to the client ' s needs. | Meet with the team to define together a plan that would help them deliver despite the budget cuts. | Call the sponsor and ask for a meeting to clarify the scope before working any further on the project. | Work with the team to understand what can motivate them to try and complete the project. |  | B | When a team is demotivated and tired from project direction changes due to budget cuts, the project manager should first meet with the team to collaboratively define a plan to deliver despite the cuts. Participative planning empowers the team and rebuilds ownership. Working to understand individual motivations (D) is helpful but not the first step. Reminding them of client commitment (A) is dismissive of their state. Calling the sponsor for clarity (C) is premature without first engaging the team. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 스폰서의 예산 삭감으로 프로젝트가 방향을 계속 바꿨 탓에 의욱이 저하되고 피곤한 팀과 함께 작업하고 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 팀에게 고객과의 약속과 고객의 요구에 적응해야 할 필요성을 상기시킨다. | 팀과 만나 예산 삭감에도 불구하고 전달할 수 있는 계획을 함께 정의한다. | 스폰서에게 전화하여 작업을 더 진행하기 전에 범위를 명확히 하기 위한 회의를 요청한다. | 팀과 함께 프로젝트를 완료하도록 동기 부여할 수 있는 것이 무엇인지 이해하기 위해 팀과 협력한다. |  | B | 스폰서의 예산 삭감으로 프로젝트 방향 변경으로 팀이 의욱이 저하되고 피곤할 때, 프로젝트 관리자는 먼저 팀과 만나 예산 삭감에도 불구하고 전달할 계획을 협력적으로 정의해야 한다. 참여적 계획은 팀에 권한을 부여하고 주인의식을 재건한다. 개인 동기 이해(D)는 도움이 되지만 첫 번째 단계는 아니다. 고객 약속 상기(A)는 팀의 상태를 무시한다. 스폰서에게 명확화 요청(C)은 단계가 맞지만 팀을 먼저 참여시키지 않으면 시기상조이다.
371 | A project manager at a company is considering a high-performing junior member of the organization to be the new project manager for a current project. What should the project manager do to prepare for a recommendation to senior management? | Calculate the health of the projects on which the team member has worked | Compile key highlights featuring the team member from the meeting minutes. | Gather project artifacts that demonstrate the team member ' s high performance | Ask the team member to write a short biography listing their qualifications |  | C | When considering a high-performing junior team member for a project manager role, the project manager should gather project artifacts that demonstrate the member's high performance. Evidence-based recommendations are persuasive. Calculating project health (A) assesses projects, not individuals. Compiling meeting minute highlights (B) is narrow. Asking for a biography (D) is subjective and self-reported. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Predictive | Baseline & Change Control | Process | Evaluate Project Status | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 회사의 프로젝트 관리자가 조직의 고성능 주니어 멤버를 현재 프로젝트의 새로운 프로젝트 관리자로 고려하고 있다. 프로젝트 관리자는 상급 경영진에대한 추천을 준비하기 위해 무엇을 해야 하는가? | 팀원이 참여한 프로젝트의 건강성을 계산한다. | 회의록에서 팀원의 주요 하이라이트를 정리한다. | 팀원의 높은 성과를 보여주는 프로젝트 산출물을 수집한다. | 팀원에게 자격을 나열하는 짧은 약력을 작성하도록 요청한다. |  | C | 고성능 주니어 팀원을 프로젝트 관리자 역할로 고려할 때, 프로젝트 관리자는 팀원의 높은 성과를 보여주는 프로젝트 산출물을 수집해야 한다. 증거 기반 추천이 설득력이 있다. 프로젝트 건강성 계산(A)은 프로젝트를 평가하지 개인을 평가하지 않는다. 회의록 하이라이트 정리(B)는 범위가 좁다. 약력 작성 요청(D)은 주관적이고 자기 보고식이다.
372 | Which three of the following scenarios are impediments to which a scrum master should pay attention? (Choose three) | A team member talking about a user story that is not on the Scrum board | A team member talking about a user story that is on the Scrum board | A lack of team empowerment and an inability to self-organize | A technology that blocks agile capabilities | A review of the backlog at daily standup meetings | A, C, D | The three scenarios that are impediments a scrum master should address are: a team member discussing a user story not on the Scrum board (A)—indicating lack of focus on the Sprint Goal; a technology that blocks agile capabilities (D)—preventing delivery of working increments; and a lack of team empowerment and inability to self-organize (C)—restricting the team's decision-making and productivity. A team member discussing a user story on the board (B) is normal Sprint work and collaboration. Reviewing the backlog at daily standups (E) is a legitimate practice for plan adaptation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 다음 세 가지 시나리오 중 스크럼 마스터가 주의를 기울여야 할 장애물은? (3개 선택) | 스크럼 보드에 없는 사용자 스토리에 대해 이야기하는 팀원 | 스크럼 보드에 있는 사용자 스토리에 대해 이야기하는 팀원 | 팀 권한 부여의 부족과 자체 조직화 불능 | 애자일 역량을 차단하는 기술 | 일일 스탠드업 회의에서의 백로그 검토 | A, C, D | 스크럼 마스터가 다루어야 할 세 가지 장애물은: 스크럼 보드에 없는 사용자 스토리를 논의하는 팀원(A)—스프린트 목표에 대한 집중 부족을 나타냄; 애자일 역량을 차단하는 기술(D)—작동하는 증분 전달을 방해함; 팀 권한 부여의 부족과 자체 조직화 불능(C)—팀의 의사결정과 생산성을 제한함. 보드에 있는 사용자 스토리 논의(B)는 정상적인 스프린트 작업과 협력이다. 일일 스탠드업에서 백로그 검토(E)는 계획 적응을 위한 합당한 실천이다.
373 | The project team finds that the latest delivery from a vendor is missing a critical component, which will likely delay the project in spite of corrective measures. What should the project manager do to communicate this message? | Contact department managers who are identified as stakeholders, solicit concern, and provide updates to the situation | Ask the vendor to identify the stakeholders affected, create an action plan and determine an implementation date | Draft a warning letter to the vendor ask internal stakeholders to comment, and solicit stakeholder support to hold the vendor accountable | Identify the worst-case scenario, put it into the project risk register, share the register with all project stakeholders, and raise an alert. |  | A | When a vendor delivery is missing a critical component likely to delay the project despite corrective measures, the project manager should contact department managers identified as stakeholders, solicit concern, and provide updates. Transparent stakeholder communication enables coordinated response. Asking the vendor to identify stakeholders and plan (B) delegates PM responsibility. Drafting a warning letter (C) is adversarial. Adding to the risk register and alerting all stakeholders (D) is overly broad. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 공급업체의 최신 납품에서 중요한 구성요소가 누락되어 시정 조치에도 불구하고 프로젝트가 지연될 가능성이 있음을 발견한다. 프로젝트 관리자는 이 메시지를 전달하기 위해 무엇을 해야 하는가? | 이해관계자로 식별된 부서 관리자에게 연락하여 우려를 구하고 상황에 대한 업데이트를 제공한다. | 공급업체에게 영향을 받는 이해관계자를 식별하고 실행 계획을 수립하며 구현 날짜를 결정하도록 요청한다. | 공급업체에게 경고 서한을 작성하고 내부 이해관계자에게 의견을 요청하며 공급업체의 책임을 묻기 위한 이해관계자 지원을 구한다. | 최악의 시나리오를 식별하고 프로젝트 리스크 레지스터에 등록하며 모든 프로젝트 이해관계자와 레지스터를 공유하고 경보를 발령한다. |  | A | 공급업체 납품에 중요 구성요소가 누락되어 시정 조치에도 프로젝트가 지연될 가능성이 있을 때, 프로젝트 관리자는 이해관계자로 식별된 부서 관리자에게 연락하여 우려를 구하고 업데이트를 제공해야 한다. 투명한 이해관계자 커뮤니케이션이 조율된 대응을 가능하게 한다. 공급업체에게 이해관계자 식별 및 계획 요청(B)은 PM 책임을 위임한다. 경고 서한 작성(C)은 적대적이다. 리스크 레지스터에 등록 및 모든 이해관계자 경보(D)는 지나치게 광범위하다.
374 | A project team member identified a procurement risk and sent an email to the project sponsor highlighting the risk. The sponsor forwarded the email to the project manager asking for further details. After speaking with the sponsor, the project manager decided to take preventive action. Which document should the project manager review with their team? | Procurement management plan | Communications management plan | Quality management plan | Risk management plan |  | D | When a procurement risk is identified and the project manager decides to take preventive action, they should review the risk management plan with the team. The risk management plan defines processes and procedures for identifying, analyzing, and responding to risks. The procurement management plan (A) addresses procurement processes, not risk response. The communications management plan (B) governs information distribution. The quality management plan (C) addresses quality standards. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 프로젝트 팀원이 조달 리스크를 식별하고 리스크를 강조하는 이메일을 프로젝트 스폰서에게 보냈다. 스폰서는 추가 세부 사항을 요청하며 이메일을 프로젝트 관리자에게 전달했다. 스폰서와 대화한 후 프로젝트 관리자는 예방 조치를 취하기로 결정했다. 프로젝트 관리자는 팀과 어떤 문서를 검토해야 하는가? | 조달 관리 계획 | 커뮤니케이션 관리 계획 | 품질 관리 계획 | 리스크 관리 계획 |  | D | 조달 리스크가 식별되고 프로젝트 관리자가 예방 조치를 취하기로 결정할 때, 팀과 리스크 관리 계획을 검토해야 한다. 리스크 관리 계획은 리스크 식별, 분석, 대응을 위한 프로세스와 절차를 정의한다. 조달 관리 계획(A)은 조달 프로세스를 다루지 리스크 대응은 다루지 않는다. 커뮤니케이션 관리 계획(B)은 정보 배포를 관장한다. 품질 관리 계획(C)은 품질 기준을 다룬다.
375 | In the past year, a company paid US$60,000 to an external subcontractor for an ongoing project. The project manager has been asked to evaluate if the project can be delivered more cost effectively this year by using internal labor. The project manager used an optimistic term of 4 months, a pessimistic term of 6 months, and a most expected term of 5 months, and has concluded that the service can be delivered with the following resources: Two engineers (monthly salary of US$700 each), one project manager (monthly salary of US$1,600), additional estimated monthly expenses of US$2,000. The project manager used the program evaluation and review technique (PERT) to calculate the savings if the project is delivered with in-house resources. How much money will the project manager estimate the company can save? | 40000 | 35000 | 30000 | 20000 |  | A | Using PERT: estimated duration = (4 + 4×5 + 6) / 6 = 5 months. Monthly cost = 2 engineers × $700 + $1,600 PM + $2,000 expenses = $6,000. Total in-house cost = 5 × $6,000 = $30,000. Savings = $60,000 − $30,000 = $30,000. Option B ($35,000) and D ($20,000) use incorrect calculations. Option A ($40,000) likely uses a 4-month estimate. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 지난 한 해 동안 회사가 진행 중인 프로젝트를 위해 외부 하도급업체에 60,000달러를 지불했다. 프로젝트 관리자는 내부 인력을 사용하여 올해 프로젝트를 더 비용 효율적으로 전달할 수 있는지 평가하라는 요청을 받았다. 프로젝트 관리자는 낙관적 기간 4개월, 비관적 기간 6개월, 가장 예상되는 기간 5개월을 사용했으며, 다음 자원으로 서비스를 전달할 수 있다고 결론지었다: 엔지니어 2명(월급 각 700달러), 프로젝트 관리자 1명(월급 1,600달러), 추가 예상 월간 경비 2,000달러. 프로젝트 관리자는 PERT를 사용하여 내부 자원으로 프로젝트를 전달할 경우 절감액을 계산했다. 프로젝트 관리자는 회사가 얼마나 절감할 수 있다고 추정하는가? | 40000 | 35000 | 30000 | 20000 |  | A | PERT 사용: 예상 기간 = (4 + 4×5 + 6) / 6 = 5개월. 월간 비용 = 엔지니어 2명 × $700 + PM $1,600 + 경비 $2,000 = $6,000. 내부 총 비용 = 5 × $6,000 = $30,000. 절감액 = $60,000 − $30,000 = $30,000. 옵션 B($35,000)와 D($20,000)는 잘못된 계산을 사용한다. 옵션 A($40,000)는 4개월 추정치를 사용한 것으로 보인다.
376 | An oil and gas project started without having acquired full funding for the project. The remaining funds were to be acquired during project execution. The acquisition of the remaining funds was delayed several months, resulting in a suspension of work by all contractors. What should the project manager have done to prevent this from happening? | Ensured the project team monitored and reviewed the project risk register periodically. | Ensured the stakeholder anticipated obstacles to achieving financial closure on the 669 remaining funds. | Ensured the stakeholder who was providing additional funds remained interested in the project. | Ensured the risk was adequately assessed and mitigated by the appropriate stakeholders. |  | D | When a project starts without full funding and remaining acquisition is delayed, the project manager should have ensured the risk was adequately assessed and mitigated by appropriate stakeholders. Proactive risk management for funding uncertainty prevents work suspension. Monitoring the risk register periodically (A) is ongoing but not specific enough. Ensuring stakeholder anticipation of obstacles (B) is helpful but indirect. Maintaining stakeholder interest (C) does not mitigate the financial risk. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Focus on Value | Plan Risk Management | Traditional PM | 석유 및 가스 프로젝트가 프로젝트의 전액 자금을 확보하지 못한 상태로 시작되었다. 나머지 자금은 프로젝트 실행 중 확보할 예정이었다. 나머지 자금 확보가 수개월 지연되어 모든 계약자의 작업이 중단되었다. 프로젝트 관리자는 이를 방지하기 위해 무엇을 했어야 하는가? | 프로젝트 팀이 프로젝트 리스크 레지스터를 주기적으로 모니터링하고 검토하도록 보장했어야 한다. | 이해관계자가 나머지 자금의 재무적 마감 달성에 대한 장애물을 예상하도록 보장했어야 한다. | 추가 자금을 제공하는 이해관계자가 프로젝트에 대한 관심을 유지하도록 보장했어야 한다. | 리스크가 적절한 이해관계자에 의해 적절히 평가되고 완화되도록 보장했어야 한다. |  | D | 프로젝트가 전액 자금 없이 시작되고 나머지 확보가 지연될 때, 프로젝트 관리자는 리스크가 적절한 이해관계자에 의해 적절히 평가되고 완화되도록 보장했어야 한다. 자금 불확실성에 대한 사전 예방적 리스크 관리가 작업 중단을 방지한다. 리스크 레지스터 주기적 모니터링(A)은 지속적이지만 충분히 구체적이지 않다. 장애물 예상 보장(B)은 도움이 되지만 간접적이다. 이해관계자 관심 유지(C)는 재무적 리스크를 완화하지 않는다.
377 | In an organization transitioning to agile, the project team is in the norming phase. Team members became uncomfortable when the project manager assigned reporting responsibilities to the newest team member. Team members began questioning the project manager's decision. What should the project manager do? | Remind team members that administrative decisions are the project manager ' s duties. | Revoke the delegated responsibilities to keep the team members harmonious. | Explain the rationale for delegating responsibilities to team members. | Invite team members to volunteer for roles for which they feel qualified. |  | C | The correct answer is C. Explain the rationale for delegating responsibilities to team members. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 애자일로 전환 중인 조직에서 프로젝트 팀이 노밍(Norming) 단계에 있다. 프로젝트 관리자가 최신 팀원에게 보고 책임을 배정하자 팀원들이 불편해했다. 팀원들이 프로젝트 관리자의 결정에 의문을 제기하기 시작했다. 프로젝트 관리자는 어떻게 해야 하는가? | 팀원들에게 관리적 결정은 프로젝트 관리자의 업무임을 상기시킨다. | 팀원들의 조화를 유지하기 위해 위임된 책임을 철회한다. | 팀원들에게 책임 위임의 근거를 설명한다. | 팀원들이 자신이 적합하다고 느끼는 역할에 자원하도록 초대한다. |  | C | 정답은 C이다. 팀원들에게 책임 위임의 근거를 설명한다. 애자일 환경에서 PM은 팀 협업을 촉진하고 장애물을 제거하며 애자일 원칙과 의식을 존중하면서 지속적인 가치 전달을 보장해야 한다.
378 | A project manager presents the project schedule to the customer, including the detailed phases for the whole project. The customer complains that the project timeline is longer than expected and does not want to wait until the end to see results. What should the project manager do first? | Adjust the project schedule to include additional resources for all project tasks. | Submit a change request to extend the project timeline. | Apply crashing techniques to all activities in the project schedule. | Evaluate the impact of changing the project framework to an incremental approach. |  | D | When the customer is unhappy about waiting until the end to see results and the timeline is longer than expected, the project manager should first evaluate the impact of changing the project framework to an incremental approach. Incremental delivery enables earlier value realization by breaking work into smaller releases with visible progress throughout the project. Adding resources (A) or crashing all activities (D) are schedule compression techniques that increase cost and risk without addressing the customer's core desire for earlier results. Submitting a change request to extend the timeline (B) moves opposite to the customer's need. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트 관리자가 세부 단계를 포함한 전체 프로젝트 일정을 고객에게 제시한다. 고객이 프로젝트 일정이 예상보다 길며 끝날 때까지 기다려 결과를 보고 싶지 않다고 불만을 제기한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 모든 프로젝트 작업에 추가 자원을 포함하도록 프로젝트 일정을 조정한다. | 프로젝트 일정을 연장하는 변경 요청을 제출한다. | 프로젝트 일정의 모든 활동에 크래싱 기법을 적용한다. | 프로젝트 프레임워크를 점진적 접근 방식으로 변경하는 영향을 평가한다. |  | D | 고객이 끝날 때까지 기다려 결과를 보는 것에 불만이고 일정이 예상보다 길 때, 프로젝트 관리자는 먼저 프로젝트 프레임워크를 점진적 접근 방식으로 변경하는 영향을 평가해야 한다. 점진적 전달은 작업을 더 작은 릴리스로 나누어 프로젝트 전반에 걸쳐 가시적인 진행으로 조기 가치 실현을 가능하게 한다. 자원 추가(A) 또는 모든 활동 크래싱(D)은 비용과 리스크를 증가시키며 고객의 조기 결과 요구를 해결하지 못한다. 일정 연장 변경 요청 제출(B)은 고객의 요구와 반대로 간다.
379 | A project manager is assigned to a project that has a tight schedule. Due to recent market changes, the marketing team has identified that a few features that were initially in the scope are no longer required. What should the project manager do? | Escalate the issue to the project management office (PMO) and make sure they understand the impact on the schedule due to the change | Advise the marketing team that at this stage of the project changes to the scope are no longer accepted | Review the change request with the project stakeholders and evaluate the impact of the scope reduction | Update the risk register with input from marketing and sales and highlight the benefits of the features m discussion |  | C | When the marketing team identifies features no longer required due to market changes on a tight schedule, the project manager should review the change request with stakeholders and evaluate the impact of the scope reduction. Stakeholder review ensures alignment. Escalating to the PMO (A) delegates ownership. Advising that changes are no longer accepted (B) ignores valid business input. Updating the risk register (D) is secondary. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 빠듯한 일정의 프로젝트에 배정되었다. 최근 시장 변화로 인해 마케팅 팀이 초기 범위에 있던 몇 가지 기능이 더 이상 필요하지 않다고 식별했다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 관리 오피스(PMO)에 이슈를 에스컬레이션하고 변경으로 인한 일정 영향을 이해시킨다. | 이 단계에서는 범위 변경이 더 이상 수락되지 않는다고 마케팅 팀에 조언한다. | 프로젝트 이해관계자와 변경 요청을 검토하고 범위 축소의 영향을 평가한다. | 마케팅 및 영업의 입력으로 리스크 레지스터를 업데이트하고 논의 중인 기능의 이점을 강조한다. |  | C | 시장 변화로 마케팅 팀이 빠듯한 일정에서 더 이상 필요하지 않은 기능을 식별할 때, 프로젝트 관리자는 이해관계자와 변경 요청을 검토하고 범위 축소의 영향을 평가해야 한다. 이해관계자 검토는 정렬을 보장한다. PMO 에스컬레이션(A)은 소유권을 위임한다. 변경이 수락되지 않는다고 조언(B)은 유효한 비즈니스 입력을 무시한다. 리스크 레지스터 업데이트(D)는 부차적이다.
380 | A company's project management office (PMO) has started to implement iterative tools. The project manager is starting a new project and has identified an opportunity to use the new tools. There is disagreement among stakeholders about the use of the adaptive tool. What should the project manager do first? | Schedule training sessions for the stakeholders on the benefits of the adaptive tools. | Investigate the reasons for the disagreement to understand the gap among the stakeholders and search for consensus. | Discuss the situation with the stakeholders to evaluate other adaptive tools for the project. | Update the risk register and escalate the disagreement to the project sponsor and distribute the status to the team. |  | B | When there is stakeholder disagreement about using an adaptive tool on a new project, the project manager should first investigate the reasons for the disagreement to understand the gap and search for consensus. Understanding perspectives enables resolution. Scheduling training (A) assumes the tool is the right choice. Discussing other adaptive tools (C) redirects rather than addresses concerns. Updating the risk register and escalating (D) escalates prematurely. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 회사의 프로젝트 관리 오피스(PMO)가 반복적 도구를 구현하기 시작했다. 프로젝트 관리자가 새 프로젝트를 시작하며 새로운 도구를 사용할 기회를 식별했다. 적응형 도구의 사용에 대해 이해관계자 간 의견 불일치가 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 이해관계자를 대상으로 적응형 도구의 이점에 대한 교육 세션을 예약한다. | 의견 불일치의 이유를 조사하여 이해관계자 간 격차를 파악하고 합의를 찾는다. | 프로젝트를 위한 다른 적응형 도구를 평가하기 위해 이해관계자와 상황을 논의한다. | 리스크 레지스터를 업데이트하고 의견 불일치를 프로젝트 스폰서에게 에스컬레이션하며 팀에 상태를 배포한다. |  | B | 새 프로젝트에서 적응형 도구 사용에 대한 이해관계자 의견 불일치가 있을 때, 프로젝트 관리자는 먼저 의견 불일치의 이유를 조사하여 격차를 파악하고 합의를 찾아야 한다. 관점을 이해하면 해결이 가능해진다. 교육 예약(A)은 도구가 올바른 선택이라고 가정한다. 다른 적응형 도구 논의(C)는 우려를 해결하지 않고 전환한다. 리스크 레지스터 업데이트 및 에스컬레이션(D)은 성급하게 에스컬레이션한다.
381 | The project manager has learned that the project sponsor is unhappy with the development of the project requirements. In order to realign the project with the sponsor's expectations, what should the project manager do? | Confirm which templates the team should be using | Review the risk management plan | Perform a stakeholder evaluation | Review the project goal diagram with the team. |  | C | When the project sponsor is unhappy with project requirements development, the project manager should perform a stakeholder evaluation. Understanding the sponsor's needs, expectations, and concerns enables realignment. Confirming templates (A) addresses format, not content. Reviewing the risk management plan (B) is unrelated to requirement satisfaction. Reviewing the project goal diagram (D) may not reflect the sponsor's current concerns. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자는 프로젝트 스폰서가 프로젝트 요구사항 개발에 불만이라는 것을 알게 되었다. 프로젝트를 스폰서의 기대에 재정렬하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 팀이 사용해야 할 템플릿을 확인한다. | 리스크 관리 계획을 검토한다. | 이해관계자 평가를 수행한다. | 팀과 함께 프로젝트 목표 다이어그램을 검토한다. |  | C | 프로젝트 스폰서가 프로젝트 요구사항 개발에 불만일 때, 프로젝트 관리자는 이해관계자 평가를 수행해야 한다. 스폰서의 요구, 기대, 우려를 이해하면 재정렬이 가능해진다. 템플릿 확인(A)은 형식을 다루지 내용은 다루지 않는다. 리스크 관리 계획 검토(B)는 요구사항 만족과 무관하다. 프로젝트 목표 다이어그램 검토(D)는 스폰서의 현재 우려를 반영하지 않을 수 있다.
382 | Early prototypes developed in a project show an unacceptably high defect rate. The quality management plan calls for a cause-and-effect analysis to address quality problems as they arise. What is the project manager's first step in addressing the problem? | Form a brainstorming team from project team members selected for their relevant technical analytical and management knowledge | Create a problem-solving team from quality assurance subject matter experts (SMEs) experienced in this type of analysis | Communicate the issue to the change control board (CCB) and relevant stakeholders identified in the stakeholder engagement plan | Form a brainstorming team with stakeholders from all of the functional departments involved in the project |  | B | When early prototypes show an unacceptably high defect rate and the quality plan calls for cause-and-effect analysis, the project manager's first step should be to create a problem-solving team from quality assurance SMEs experienced in this type of analysis. Expert analysis ensures proper root-cause identification. Forming a team from project members (A) may lack specialized quality expertise. Communicating to the CCB (C) escalates before understanding the cause. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 초기 프로토타입이 허용할 수 없을 정도로 높은 결함률을 보인다. 품질 관리 계획에서는 품질 문제가 발생하면 원인-결과 분석을 수행하도록 요구한다. 문제를 해결하기 위한 프로젝트 관리자의 첫 번째 단계는 무엇인가? | 관련 기술적, 분석적, 관리적 지식으로 선발된 프로젝트 팀원으로 브레인스토밍 팀을 구성한다. | 이 유형의 분석에 경험이 있는 품질 보증 주제 전문가(SME)로 문제 해결 팀을 구성한다. | 변경 통제 위원회(CCB)와 이해관계자 참여 계획에서 식별된 관련 이해관계자에게 이슈를 전달한다. | 프로젝트에 관련된 모든 기능 부서의 이해관계자로 브레인스토밍 팀을 구성한다. |  | B | 초기 프로토타입이 허용할 수 없을 정도로 높은 결함률을 보이고 품질 계획이 원인-결과 분석을 요구할 때, 프로젝트 관리자의 첫 단계는 이 유형의 분석에 경험이 있는 품질 보증 SME로 문제 해결 팀을 구성하는 것이다. 전문가 분석은 적절한 근본 원인 식별을 보장한다. 프로젝트 팀원으로 팀 구성(A)은 전문적인 품질 전문성이 부족할 수 있다. CCB에 전달(C)은 원인을 이해하기 전에 에스컬레이션한다.
383 | A project team has deployed an email marketing campaign across different countries. In one country, the end users have been opting out of the campaign because they think the email is spam. What should the project manager do first? | Conduct a retrospective meeting to identify what went well and what went wrong. | Schedule additional country-specific user testing to reduce email opt out. | Review the email marketing standards of that country with the stakeholders. | Schedule a meeting with project team members to identify the root cause. |  | C | When end users in one country opt out of an email marketing campaign believing it is spam, the project manager should first review the email marketing standards of that country with stakeholders. Country-specific regulations and cultural expectations directly affect campaign compliance and perception. Conducting a retrospective (A) is internal and may miss external factors. Scheduling additional user testing (B) tests without fixing the root cause. Scheduling a root cause meeting (D) should be informed by external standards first. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Embed Quality | Manage Communications | Traditional PM | 프로젝트 팀이 여러 국가에 걸쳐 이메일 마케팅 캠페인을 배포했다. 한 국가에서 최종 사용자들이 이메일을 스팸으로 생각하여 캠페인에서 탈퇴하고 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 무엇이 잘 되었고 무엇이 잘못되었는지 파악하기 위해 회고 회의를 실시한다. | 이메일 탈퇴를 줄이기 위해 추가적인 국가별 사용자 테스트를 예약한다. | 이해관계자와 함께 해당 국가의 이메일 마케팅 표준을 검토한다. | 근본 원인을 파악하기 위해 프로젝트 팀원과 회의를 예약한다. |  | C | 한 국가에서 최종 사용자가 이메일을 스팸으로 여겨 캠페인에서 탈퇴할 때, 프로젝트 관리자는 먼저 이해관계자와 함께 해당 국가의 이메일 마케팅 표준을 검토해야 한다. 국가별 규정과 문화적 기대는 캠페인 준수와 인식에 직접 영향을 미친다.
384 | A project manager starts to receive emails from different stakeholders requesting information about the project status. What should the project manager do to avoid this in the future? | Designate a team member to respond to the emails from these stakeholders. | Include the stakeholders' emails in all of the project status communications. | Include the project stakeholders' needs while planning the project communications strategy. | Schedule weekly project status meetings with all stakeholders including the customer and internal resources. |  | C | When stakeholders email the project manager requesting status information, the project manager should include the stakeholders' needs while planning the project communications strategy. A comprehensive communications plan that addresses each stakeholder's information requirements, preferred methods, and frequency prevents ad hoc requests. Designating a team member to respond (A) is a stopgap, not a systemic solution. Including stakeholder emails in all communications (B) may overwhelm them with irrelevant information. Scheduling weekly status meetings with all stakeholders (D) may not match everyone's availability or information needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 프로젝트 상태에 대한 정보를 요청하는 여러 이해관계자로부터 이메일을 받기 시작했다. 향후 이를 방지하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자의 이메일에 응답할 팀원을 지정한다. | 모든 프로젝트 상태 커뮤니케이션에 이해관계자의 이메일을 포함한다. | 프로젝트 커뮤니케이션 전략을 계획할 때 이해관계자의 요구를 포함한다. | 고객과 내부 자원을 포함한 모든 이해관계자와 주간 프로젝트 상태 회의를 예약한다. |  | C | 이해관계자가 상태 정보를 요청하는 이메일을 보낼 때, 프로젝트 관리자는 프로젝트 커뮤니케이션 전략을 계획할 때 이해관계자의 요구를 포함해야 한다. 각 이해관계자의 정보 요구, 선호 방법, 빈도를 다루는 포괄적인 커뮤니케이션 계획은 임시 요청을 방지한다.
385 | The project management office (PMO) has recently adopted some agile practices. During an iteration, a key stakeholder in the business is concerned with the benefits management plan in the project document repository and mentions that some benefits have not been updated. What should the project manager do first? | Update the risk register in order to add the issue. | Revise the benefits management plan | Review the issue log regarding the concern | Assess the repository to check for inconsistencies. |  | D | When a key stakeholder raises concerns about outdated benefits in the project document repository during an iteration, the project manager should first assess the repository to check for inconsistencies. Understanding the current state precedes updates. Updating the risk register (A) treats it as a risk without verifying. Revising the benefits management plan (B) acts before understanding the scope of the issue. Reviewing the issue log (C) checks existing issues, not the repository. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | Traditional PM | 프로젝트 관리 오피스(PMO)가 최근 일부 애자일 실천법을 도입했다. 반복 중 비즈니스의 주요 이해관계자가 프로젝트 문서 저장소의 혜택 관리 계획에 우려를 표명하며 일부 혜택이 업데이트되지 않았다고 언급한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 이슈를 추가하기 위해 리스크 레지스터를 업데이트한다. | 혜택 관리 계획을 수정한다. | 우려 사항에 대해 이슈 로그를 검토한다. | 불일치를 확인하기 위해 저장소를 평가한다. |  | D | 반복 중 주요 이해관계자가 프로젝트 문서 저장소의 오래된 혜택에 대한 우려를 제기할 때, 프로젝트 관리자는 먼저 불일치를 확인하기 위해 저장소를 평가해야 한다. 현재 상태를 이해하는 것이 업데이트에 선행한다.
386 | A project manager is reviewing the team's Kanban board for an iteration with 16 tasks in progress. All the tasks are equally sized with an estimate of 8 man-hours of effort needed to complete each task. The team is made up of five cross-functional members. The normal working calendar is 8 hours per day; however, two of the team members will only work at 50% capacity. The project manager has a maximum of one week to deliver these tasks in progress due to government regulations. Will the project manager meet this objective? | No, it will take 7 days to complete all these tasks based on the estimate. | No, it will take 6 days to complete all these tasks based on the estimate. | Yes, it will take 4 working days to complete these tasks based on the estimate. | Yes, it will take 5 working days to complete these tasks based on the estimate. |  | C | The calculation: 16 tasks × 8 hours = 128 total hours. Team capacity: 3 full-time members (24 hours/day) + 2 half-time members (8 hours/day) = 32 hours/day. Required time: 128 ÷ 32 = 4 working days. The team can complete all tasks within the one-week constraint with capacity to spare. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Kanban | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 관리자가 진행 중인 16개 작업이 있는 반복의 팀 칸반 보드를 검토하고 있다. 모든 작업은 동일한 크기이며 완료하는 데 8인시의 노력이 필요하다. 팀은 5명의 교차 기능 멤버로 구성되어 있다. 정상 근무 일정은 하루 8시간이지만 팀원 중 2명은 50% 가용률로만 근무한다. 프로젝트 관리자는 정부 규정으로 인해 진행 중인 작업을 최대 1주일 내에 전달해야 한다. 프로젝트 관리자는 이 목표를 달성할 수 있는가? | 아니오, 추정치에 따르면 이 모든 작업을 완료하는 데 7일이 걸릴 것이다. | 아니오, 추정치에 따르면 이 모든 작업을 완료하는 데 6일이 걸릴 것이다. | 예, 추정치에 따르면 이 작업을 완료하는 데 4근무일이 걸릴 것이다. | 예, 추정치에 따르면 이 작업을 완료하는 데 5근무일이 걸릴 것이다. |  | C | 계산: 16개 작업 × 8시간 = 총 128시간. 팀 가용률: 풀타임 3명(24시간/일) + 하프타임 2명(8시간/일) = 32시간/일. 필요 시간: 128 ÷ 32 = 4근무일. 팀은 1주일 제약 내에 여유를 두고 모든 작업을 완료할 수 있다.
387 | The team lead on a project has left the organization and management wants to promote engineer A to this position. The project manager is confident that selecting engineer A will add problems to the project and believes that engineer B would better fit this role. The project manager discussed all of the arguments with management but their decision remains unchanged. What should the project manager do? | Help engineer A to become familiar with this new role and ensure engineer B stays motivated. | Coach engineer B to be prepared to perform this role if and when engineer A fails. | Request management approval that engineer B will be promoted if engineer A fails in this role. | Promote engineer B instead since the project manager has the authority to make this decision. |  | A | When management promotes engineer A despite the PM's preference for engineer B, the project manager should help engineer A become familiar with the new role and ensure engineer B stays motivated. Supporting management decisions while maintaining team morale is professional. Coaching engineer B as a backup (B) undermines engineer A. Requesting approval for B if A fails (C) signals lack of support. Promoting B unilaterally (D) overrides management authority. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Cost & Resource Management | People | Help Ensure Knowledge Transfer | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트의 팀 리드가 조직을 떠났고 경영진이 엔지니어 A를 이 직책으로 승진시키려 한다. 프로젝트 관리자는 엔지니어 A를 선택하면 프로젝트에 문제가 추가될 것이라고 확신하며 엔지니어 B가 이 역할에 더 적합하다고 믿는다. 프로젝트 관리자가 경영진과 모든 논거를 논의했지만 결정은 변경되지 않았다. 프로젝트 관리자는 어떻게 해야 하는가? | 엔지니어 A가 새 역할에 익숙해지도록 돕고 엔지니어 B의 동기를 유지한다. | 엔지니어 A가 실패할 경우에 대비하여 엔지니어 B가 이 역할을 수행할 준비를 하도록 코칭한다. | 엔지니어 A가 이 역할에서 실패하면 엔지니어 B가 승진할 것이라는 경영진 승인을 요청한다. | 프로젝트 관리자가 이 결정을 내릴 권한이 있으므로 대신 엔지니어 B를 승진시킨다. |  | A | 경영진이 PM의 선호에도 불구하고 엔지니어 A를 승진시킬 때, 프로젝트 관리자는 엔지니어 A가 새 역할에 익숙해지도록 돕고 엔지니어 B의 동기를 유지해야 한다. 팀 사기를 유지하면서 경영진 결정을 지원하는 것이 전문적이다.
388 | A project manager is part of a global project team and is in charge of managing the scope defined by their country. There is a clear division regarding which pieces of the scope should be handled by global and local teams. During the last sprints, the project manager has been receiving requests that the global team should manage. What should the project manager do in this situation? | Assess the team ' s capacity to absorb the workload. | Evaluate and understand the cause of the conflict. | Escalate the situation to the project sponsor. | Reject the workload back to the global team. |  | D | When receiving out-of-scope requests meant for the global team, the PM should evaluate and understand the root cause of the misdirection. This involves analyzing why requests are being directed to the local team instead of the appropriate global team—whether due to miscommunication, unclear scope boundaries, or process gaps. Addressing the root cause enables a resolution that aligns with the project's defined scope division and responsibilities. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 글로벌 프로젝트 팀의 일원이며 자국이 정의한 범위를 관리하고 있다. 글로벌 팀과 로컬 팀이 처리해야 할 범위에 대한 명확한 구분이 있다. 지난 스프린트 동안 프로젝트 관리자가 글로벌 팀이 관리해야 할 요청을 받고 있다. 이 상황에서 프로젝트 관리자는 무엇을 해야 하는가? | 업무량을 흡수할 팀의 역량을 평가한다. | 충돌의 원인을 평가하고 이해한다. | 프로젝트 스폰서에게 상황을 에스컬레이션한다. | 업무량을 글로벌 팀에게 반려한다. |  | D | 글로벌 팀이 관리해야 할 범위 밖의 요청을 받을 때, PM은 잘못된 방향의 근본 원인을 평가하고 이해해야 한다. 이는 요청이 적절한 글로벌 팀 대신 로컬 팀으로 전달되는 이유를 분석하는 것을 포함한다. 근본 원인을 해결하면 프로젝트의 정의된 범위 구분과 책임에 부합하는 해결이 가능해진다.
389 | In a weak matrix environment, two key team members are falling behind with their tasks, which will affect the success of the project. Further investigation by the project manager reveals that they have unresolved issues with each other. The project manager asks them to find a way to resolve the issues, but this is unsuccessful. The project manager then holds a meeting with them to work out a permanent solution to the issues, but this is also unsuccessful. What should the project manager do next? | Suspend the two key team members immediately. | Put the issue on the agenda for the next team meeting. | Escalate the issue to a higher authority. | Reassign one of the key team members to a different task. |  | C | After exhausting collaborative conflict resolution approaches—problem solving and compromise—without success in a weak matrix environment, the PM should escalate the issue to a higher authority (functional manager, sponsor, or steering committee). These parties have greater power and influence to resolve the conflict and protect project objectives. Smoothing avoids the core issue, forcing imposes a solution that may create resentment, and withdrawing postpones the conflict without resolution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | 약한 매트릭스 환경에서 두 명의 핵심 팀원이 작업에 뒤쳄지고 있어 프로젝트 성공에 영향을 미칠 것이다. 프로젝트 관리자의 추가 조사 결과 서로 간에 미해결 문제가 있음이 밝혀졌다. 프로젝트 관리자가 문제를 해결할 방법을 찾도록 요청했지만 성공하지 못했다. 그 후 영구적인 해결책을 찾기 위해 회의를 개최했지만 이것도 성공하지 못했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 두 핵심 팀원을 즉시 정직시킨다. | 다음 팀 회의 안건에 이슈를 올린다. | 이슈를 상위 권한자에게 에스컬레이션한다. | 핵심 팀원 중 한 명을 다른 작업에 재배정한다. |  | C | 약한 매트릭스 환경에서 문제 해결과 타협의 협력적 갈등 해결 접근 방식을 모두 소진한 후 성공하지 못했을 때, PM은 상위 권한자(기능 관리자, 스폰서, 또는 운영위원회)에게 이슈를 에스컬레이션해야 한다. 이들은 갈등을 해결하고 프로젝트 목표를 보호할 더 큰 권한과 영향력을 가지고 있다.
390 | Just as a team reaches a mutual consensus on a preferred design, a stakeholder submits a request to add new features that enhance the company's competitive advantage. What should the project manager do? | Encourage the project team to add premium features to impress the client. | Reject all requested changes and bypass the company's change control process. | Start the process to include the new features of the product in the next iteration. | Allow all requested changes and bypass the company's change control process. |  | C | When a stakeholder submits a request for new features that enhance competitive advantage just as the team reaches consensus on a design, the project manager should start the process to include the new features in the next iteration. This respects the current iteration's agreed work while properly evaluating and planning the requested changes through the delivery cadence. Encouraging the team to add premium features informally (A) bypasses controls. Rejecting all changes and bypassing change control (B) is inappropriate. Allowing all changes and bypassing change control (D) undermines governance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 팀이 선호하는 디자인에 대해 상호 합의에 도달한 직후, 이해관계자가 회사의 경쟁 우위를 강화하는 새로운 기능 추가 요청을 제출한다. 프로젝트 관리자는 무엇을 해야 하는가? | 고객에게 인상을 주기 위해 프리미엄 기능을 추가하도록 프로젝트 팀을 격려한다. | 모든 요청된 변경을 거부하고 회사의 변경 통제 프로세스를 우회한다. | 다음 반복에 제품의 새 기능을 포함하는 프로세스를 시작한다. | 모든 요청된 변경을 허용하고 회사의 변경 통제 프로세스를 우회한다. |  | C | 팀이 디자인에 대한 합의에 도달한 직후 이해관계자가 경쟁 우위를 강화하는 새 기능을 요청할 때, 프로젝트 관리자는 다음 반복에 새 기능을 포함하는 프로세스를 시작해야 한다. 이는 전달 주기를 통해 요청된 변경을 적절히 평가하고 계획하면서 현재 반복의 합의된 작업을 존중한다.
391 | During a monthly review meeting, a high-performing team member raised a concern about the quality feedback mechanism. The team member expressed that they are not able to deliver high-quality output. What should the project manager do first? | Discuss this with the team and review the quality process. | Assign the work based on the skill sets of team members. | Assign the work in consultation with the functional manager. | Request feedback from stakeholders about the quality delivery. |  | A | When a high-performing team member raises concerns about the quality feedback mechanism and their ability to deliver high-quality output, the project manager should first discuss this with the team and review the quality process. Collaborative discussion identifies root causes of quality issues. Assigning work based on skill sets (B) reallocates rather than addresses the process. Consulting the functional manager (C) is not a first step. Requesting stakeholder feedback (D) is external-facing, not process-focused. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 월간 검토 회의 중 고성과 팀원이 품질 피드백 메커니즘에 대한 우려를 제기했다. 팀원은 고품질 산출물을 전달할 수 없다고 표현했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 팀과 논의하고 품질 프로세스를 검토한다. | 팀원의 기술 세트에 기반하여 작업을 배정한다. | 기능 관리자와 상의하여 작업을 배정한다. | 품질 전달에 대한 이해관계자 피드백을 요청한다. |  | A | 고성과 팀원이 품질 피드백 메커니즘과 고품질 산출물 전달 능력에 대한 우려를 제기할 때, 프로젝트 관리자는 먼저 팀과 논의하고 품질 프로세스를 검토해야 한다. 협력적 논의가 품질 이슈의 근본 원인을 파악한다.
392 | A project manager is working for an organization in country A and has been tasked with opening the first brick-and-mortar store in country B. The sponsor has identified the city for the store and wants to minimize any potential issues with the local government. Which action should the project manager take to address the sponsor's request? | Work with the organization ' s real estate department and reach out to the local government to identify the best location for the store. | Work with the organization ' s project management office (PMO) to build a project team of residents located in the city. | Work with the local government to build the profiles of employees that will be working in the store. | Work with the organization ' s legal department to identify local regulations to ensure project compliance. |  | D | When tasked with opening a store in a new country while minimizing government issues, the project manager should work with the organization's legal department to identify local regulations to ensure project compliance. Legal compliance is the foundation for avoiding government conflicts. Working with real estate and local government (A) addresses location but not compliance. Building a project team of local residents (B) addresses staffing, not regulatory issues. Working with local government on employee profiles (C) focuses on hiring rather than project compliance. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 관리자가 A국의 조직에서 근무하며 B국에 첫 번째 오프라인 매장을 여는 임무를 맡았다. 스폰서가 매장 도시를 선정했으며 지방 정부와의 잠재적 문제를 최소화하고 싶어한다. 스폰서의 요청을 해결하기 위해 프로젝트 관리자는 어떤 조치를 취해야 하는가? | 조직의 부동산 부서와 협력하고 지방 정부에 연락하여 매장의 최적 위치를 파악한다. | 조직의 프로젝트 관리 오피스(PMO)와 협력하여 해당 도시에 거주하는 프로젝트 팀을 구성한다. | 지방 정부와 협력하여 매장에서 근무할 직원의 프로필을 구축한다. | 조직의 법무 부서와 협력하여 프로젝트 준수를 보장하기 위한 현지 규정을 파악한다. |  | D | 새로운 국가에 매장을 열면서 정부 문제를 최소화해야 할 때, 프로젝트 관리자는 조직의 법무 부서와 협력하여 프로젝트 준수를 보장하기 위한 현지 규정을 파악해야 한다. 법적 준수는 정부 갈등을 피하기 위한 기초이다.
393 | A project sponsor wants to develop software that would have 30 features and would be used in 10 different countries. The team feels overwhelmed with the amount of work to be done. What should the project manager do? | Encourage and motivate the team with project incentives | Support the team to find and execute the minimum viable product (MVP) | Organize project execution to satisfy the project sponsor s request | Subdivide the team to handle different aspects of the project |  | B | When a team feels overwhelmed by a 30-feature software product for 10 countries, the project manager should support the team to find and execute the MVP. MVP focuses on core value and enables iterative improvement. Encouraging with incentives (A) does not reduce scope complexity. Organizing execution for the sponsor (C) does not address team overwhelm. Subdividing the team (D) fragments without strategic focus. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Lean | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Hybrid/Tailoring | 프로젝트 스폰서가 30개 기능을 가지고 10개국에서 사용할 소프트웨어를 개발하고자 한다. 팀이 해야 할 작업량에 압도당하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 인센티브로 팀을 격려하고 동기를 부여한다. | 팀이 최소 기능 제품(MVP)을 찾아 실행하도록 지원한다. | 프로젝트 스폰서의 요청을 충족시키기 위해 프로젝트 실행을 조직한다. | 프로젝트의 다양한 측면을 처리하기 위해 팀을 세분화한다. |  | B | 30개 기능의 10개국 소프트웨어 제품에 팀이 압도당할 때, 프로젝트 관리자는 팀이 MVP를 찾아 실행하도록 지원해야 한다. MVP는 핵심 가치에 집중하고 반복적 개선을 가능하게 한다. 인센티브로 격려(A)는 범위 복잡성을 줄이지 않는다. 스폰서를 위한 실행 조직(C)은 팀의 압도감을 해결하지 않는다. 팀 세분화(D)는 전략적 초점 없이 분산시킨다.
394 | A product owner is complaining about the team's performance. The developers are highly skilled, and most of the issues were caused by dependencies. The developers provide a formal status report every day, but it is clear that the other team members are not satisfied with this. What should the project lead do? | Ask the developers to use peer programming. | Build a task board on a large wall using sticky notes. | Build a detailed schedule and describe each task in detail. | Ask the product owner to reprioritize the backlog. |  | B | The correct answer is B. Build a task board on a large wall using sticky notes. The PM should address team issues proactively by understanding root causes, building trust, and creating an environment that fosters collaboration and high performance. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 제품 책임자가 팀의 성과에 대해 불만을 제기하고 있다. 개발자들은 높은 기술력을 가지고 있으며, 대부분의 문제는 의존성으로 인해 발생했다. 개발자들은 매일 공식 상태 보고서를 제공하지만, 다른 팀원들이 이에 만족하지 않는 것이 분명하다. 프로젝트 리더는 무엇을 해야 하는가? | 개발자들에게 페어 프로그래밍을 사용하도록 요청한다. | 큰 벽에 스티키 노트를 사용하여 작업 보드를 구축한다. | 상세한 일정을 수립하고 각 작업을 상세하게 기술한다. | 제품 책임자에게 백로그를 재우선순위화하도록 요청한다. |  | B | 정답은 B이다. 큰 벽에 스티키 노트를 사용하여 작업 보드를 구축한다. PM은 근본 원인을 이해하고, 신뢰를 구축하며, 협업과 높은 성과를 촉진하는 환경을 만들어 팀 이슈를 사전 예방적으로 해결해야 한다.
395 | A project manager was suddenly asked to take over an ongoing project without any handover. During the first meeting, the project sponsor raised concerns about whether the project was on track to deliver the intended benefits. What should the new project manager do first? | Discuss the items in the requirements register with the project team. | Initiate a rebaselining of the project based on the project sponsor ' s concerns. | Meet with the project stakeholders to understand the project sponsor ' s concerns. | Review the business case to gather information about the project. |  | D | When taking over a project without handover and the sponsor raises concerns about intended benefits, the new project manager should first review the business case to gather information. The business case defines expected benefits and strategic alignment. Discussing the requirements register (A) is detailed work before context. Rebaselining (B) is premature. Meeting stakeholders to understand concerns (C) is valuable but comes after understanding the project foundation. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Business Environment | Define and Establish Governance | Stakeholders | Monitoring & Controlling | Be an Accountable Leader | Monitor Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 인수인계 없이 갑자기 진행 중인 프로젝트를 인수하도록 요청받았다. 첫 번째 회의에서 프로젝트 스폰서가 프로젝트가 의도된 혜택을 전달할 수 있는 궤도에 있는지 우려를 제기했다. 새로운 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트 팀과 요구사항 레지스터의 항목을 논의한다. | 프로젝트 스폰서의 우려에 기반하여 프로젝트 재기준선화를 시작한다. | 프로젝트 이해관계자와 만나 프로젝트 스폰서의 우려를 이해한다. | 프로젝트에 대한 정보를 수집하기 위해 비즈니스 케이스를 검토한다. |  | D | 인수인계 없이 프로젝트를 인수하고 스폰서가 의도된 혜택에 대해 우려를 제기할 때, 새 프로젝트 관리자는 먼저 비즈니스 케이스를 검토하여 정보를 수집해야 한다. 비즈니스 케이스는 예상 혜택과 전략적 정렬을 정의한다. 요구사항 레지스터 논의(A)는 맥락 파악 전의 세부 작업이다. 재기준선화(B)는 시기상조이다. 이해관계자와 만나 우려 이해(C)는 가치 있지만 프로젝트 기반을 이해한 후에 해야 한다.
396 | During the sprint planning of a project, the team members have a disagreement about the comparative size of the backlog items and if they would fit into the next sprint. Considering a hybrid approach, what should the project manager do? | Remove the items from the product backlog since the size couldn ' t be estimated. | Facilitate the discussion so that the team members can reach a consensus. | Ask an external technical leader to provide input and plan the sprint. | Make the decision about the backlog items based on what makes more sense. |  | B | In a hybrid approach, when team members disagree about backlog item sizing and sprint fit, the project manager should facilitate the discussion so the team can reach a consensus. Facilitation enables collaborative estimation, aligns team understanding, and ensures commitment to the sprint plan. Removing items from the backlog (A) is an extreme response that discards potentially valuable work. Asking an external technical leader (C) undermines the team's self-organization and ownership. Making the decision unilaterally (D) bypasses team engagement and contradicts agile principles of collaborative planning. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트의 스프린트 계획 중 팀원들이 백로그 항목의 상대적 크기와 다음 스프린트에 맞는지에 대해 의견 불일치가 있다. 하이브리드 접근 방식을 고려할 때, 프로젝트 관리자는 무엇을 해야 하는가? | 크기를 추정할 수 없으므로 제품 백로그에서 항목을 제거한다. | 팀원들이 합의에 도달할 수 있도록 토론을 촉진한다. | 외부 기술 리더에게 의견을 구하고 스프린트를 계획한다. | 더 합리적인 것에 기반하여 백로그 항목에 대한 결정을 내린다. |  | B | 하이브리드 접근 방식에서 팀원들이 백로그 항목 크기와 스프린트 적합성에 대해 의견 불일치가 있을 때, 프로젝트 관리자는 팀이 합의에 도달할 수 있도록 토론을 촉진해야 한다. 촉진은 협력적 추정을 가능하게 하고, 팀의 이해를 정렬시키며, 스프린트 계획에 대한 헌신을 보장한다. 백로그에서 항목 제거(A)는 잠재적으로 가치 있는 작업을 버리는 극단적 대응이다. 외부 기술 리더에게 요청(C)은 팀의 자기 조직화와 주인의식을 약화시킨다. 일방적 결정(D)은 팀 참여를 우회하고 협력적 계획의 애자일 원칙에 반한다.
397 | A project manager is assigned to an automotive product development project in the middle of the pilot phase. According to the test lab, a durability test was completed with good results 6 weeks ago but there were no reports left behind by the test engineer who left the organization the previous month. What should the previous project manager have done to prevent this issue? | Led a technical benchmark workshop every month to share state-of-the-art technology trends and ask all team members to attend the workshop | Contracted with a third-party test lab to outsource all testing processes and required that they produce all test reports | Built a pair-engineering environment so that experienced engineers always work with junior engineers to assist in knowledge transfer | Built a shared repository for the project in the internal server and asked the team to create record and save all project deliverables to the server |  | D | When a test engineer leaves without producing reports for a completed durability test, the previous project manager should have built a shared repository on the internal server requiring the team to record and save all deliverables. Centralized documentation prevents knowledge loss. Monthly benchmark workshops (A) share knowledge but do not ensure documentation. Outsourcing testing (B) transfers responsibility but does not address internal documentation. Pair-engineering (C) supports knowledge transfer but not formal recordkeeping. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자가 파일럿 단계 중간에 자동차 제품 개발 프로젝트에 배정되었다. 시험실에 따르면 6주 전에 내구성 테스트가 좋은 결과로 완료되었지만, 전달에 조직을 떠난 시험 엔지니어가 보고서를 남기지 않았다. 이전 프로젝트 관리자는 이 문제를 방지하기 위해 무엇을 했어야 하는가? | 최신 기술 동향을 공유하기 위해 매월 기술 벤치마크 워크숍을 이끄고 모든 팀원이 참석하도록 한다. | 모든 테스트 프로세스를 아웃소싱하고 모든 시험 보고서를 작성하도록 요구하기 위해 제3자 시험실과 계약한다. | 경험 있는 엔지니어가 항상 주니어 엔지니어와 함께 작업하여 지식 이전을 돕는 페어 엔지니어링 환경을 구축한다. | 내부 서버에 프로젝트 공유 저장소를 구축하고 팀에게 모든 프로젝트 산출물을 기록하고 저장하도록 요청한다. |  | D | 시험 엔지니어가 완료된 내구성 테스트에 대한 보고서를 작성하지 않고 떠날 때, 이전 프로젝트 관리자는 내부 서버에 공유 저장소를 구축하고 팀에게 모든 산출물을 기록하고 저장하도록 요구했어야 한다. 중앙 집중식 문서화는 지식 손실을 방지한다. 월간 벤치마크 워크숍(A)은 지식을 공유하지만 문서화를 보장하지 않는다. 테스트 아웃소싱(B)은 책임을 전가하지만 내부 문서화를 해결하지 않는다. 페어 엔지니어링(C)은 지식 이전을 지원하지만 공식 기록 보관은 아니다.
398 | A project manager is in the middle of an agile project comprised of 100 user stories broken down into five iterations. Each user story is worth US$50. The actual expenditure is US$2,000 and 50 user stories have been delivered. Which statement is true? | The project is over budget and behind schedule. | The project is under budget and behind schedule. | The project is under budget and on schedule. | The project is on budget and on schedule. |  | C | With 100 user stories at $50 each, the total budget is $5,000. At mid-project, 50 stories are delivered (EV = $2,500) against actual expenditure of $2,000 (AC = $2,000). CPI = EV/AC = 2,500/2,000 = 1.25 (under budget). SPI = EV/PV = 2,500/2,500 = 1.0 (on schedule). The project is under budget and on schedule. Over budget and behind (A) is incorrect. Under budget and behind (B) is incorrect. On budget and on schedule (D) understates cost performance. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 프로젝트 관리자가 100개의 사용자 스토리를 5번의 이터레이션으로 나눈 애자일 프로젝트 중간에 있다. 각 사용자 스토리의 가치는 50달러이다. 실제 지출은 2,000달러이고 50개의 사용자 스토리가 전달되었다. 어떤 진술이 올바른가? | 프로젝트는 예산 초과이고 일정 지연이다. | 프로젝트는 예산 절감이고 일정 지연이다. | 프로젝트는 예산 절감이고 일정 대로이다. | 프로젝트는 예산 대로이고 일정 대로이다. |  | C | 100개 사용자 스토리에 각 $50이면, 총 예산은 $5,000이다. 프로젝트 중간에 50개 스토리가 전달되었으므로 EV = $2,500, 실제 지출 AC = $2,000이다. CPI = EV/AC = 2,500/2,000 = 1.25 (예산 절감). SPI = EV/PV = 2,500/2,500 = 1.0 (일정 대로). 프로젝트는 예산 절감이고 일정 대로이다. 예산 초과 및 일정 지연(A)은 잘못되었다. 예산 절감 및 일정 지연(B)은 잘못되었다. 예산 대로 및 일정 대로(D)는 비용 성과를 과소평가한다.
399 | A project manager is approached by two new product owners who were instructed by their managers to join a new agile team. Both product owners were told they could start working with the new agile team immediately. What should the project manager do to advise both product owners? | Reiterate that having one product owner will improve clarity and accountability. | Confirm that two product owners are necessary and that both will report to an overarching chief product owner. | Present the product owners ' product backlogs and prioritize the team ' s assigned requirements. | Modify the communications management plan to integrate the new product owners into the teams effectively. |  | A | When two product owners are assigned to one agile team, the project manager should reiterate that having one product owner will improve clarity and accountability. Single PO ownership prevents conflicting priorities. Confirming two POs with a chief PO (B) adds complexity. Presenting both backlogs and prioritizing (C) creates confusion. Modifying the communications plan (D) does not address the structural issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 두 명의 새로운 제품 책임자로부터 접근을 받았는데, 그들은 관리자들로부터 새 애자일 팀에 합류하라는 지시를 받았다. 두 제품 책임자 모두 새 애자일 팀과 즉시 작업을 시작할 수 있다고 들었다. 프로젝트 관리자는 두 제품 책임자에게 어떻게 조언해야 하는가? | 한 명의 제품 책임자가 명확성과 책임성을 개선할 것이라고 재언급한다. | 두 명의 제품 책임자가 필요하며 둘 다 상위 치프 제품 책임자에게 보고할 것임을 확인한다. | 제품 책임자들의 제품 백로그를 제시하고 팀에 배정된 요구사항의 우선순위를 정한다. | 새 제품 책임자를 팀에 효과적으로 통합하기 위해 커뮤니케이션 관리 계획을 수정한다. |  | A | 두 명의 제품 책임자가 한 애자일 팀에 배정될 때, 프로젝트 관리자는 한 명의 제품 책임자가 명확성과 책임성을 개선할 것이라고 재언급해야 한다. 단일 PO 소유권은 충돌하는 우선순위를 방지한다. 치프 PO와 두 PO 확인(B)은 복잡성을 추가한다. 두 백로그 제시 및 우선순위화(C)는 혼란을 야기한다. 커뮤니케이션 계획 수정(D)은 구조적 문제를 해결하지 않는다.
400 | A team has been working for some time on a project with incremental deliveries. The project manager noticed that one of the team members is less engaged in team meetings, yet delivers promptly. While discussing the source of demotivation, the team member informed the project manager that this is due to a feeling of lack of skills in dealing with new tasks. How should the project manager address the issue? | Discuss growth and development needs with the team member and provide learning opportunities accordingly. | Replace the team member with a resource from another team who already has the requisite training and skills needed. | Create a self-paced learning plan with the team member during working hours, with checkpoints on learning progress. | Review which tasks the team member would feel more motivated to work on, then assign those tasks to the team member. |  | A | When a team member feels demotivated due to a perceived lack of skills for new tasks despite delivering promptly, the project manager should discuss growth and development needs and provide learning opportunities. Personalized development addresses skill gaps and motivation. Replacing the team member (B) is extreme. Creating a self-paced learning plan (C) is less engaging than guided discussion. Assigning preferred tasks only (D) avoids addressing the skill gap. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 팀이 점진적 전달 프로젝트에서 한동안 작업해 왔다. 프로젝트 관리자는 팀원 중 한 명이 팀 회의에 덜 참여하지만 제시간에 전달하는 것을 알아차렸다. 동기 저하의 원인을 논의하는 중 팀원은 새로운 작업을 다루는 데 필요한 역량이 부족하다는 느낌 때문이라고 프로젝트 관리자에게 알렸다. 프로젝트 관리자는 이 문제를 어떻게 해결해야 하는가? | 팀원과 성장 및 발전 요구를 논의하고 그에 따른 학습 기회를 제공한다. | 필요한 교육과 역량을 이미 갖춘 다른 팀의 자원으로 팀원을 교체한다. | 근무 시간 중 팀원과 학습 진행 체크포인트가 있는 자기 주도 학습 계획을 수립한다. | 팀원이 더 동기 부여될 작업을 검토하고 해당 작업을 팀원에게 배정한다. |  | A | 팀원이 제시간에 전달함에도 새로운 작업에 대한 역량 부족으로 동기가 저하될 때, 프로젝트 관리자는 성장 및 발전 요구를 논의하고 학습 기회를 제공해야 한다. 개인화된 발전은 역량 격차와 동기를 해결한다. 팀원 교체(B)는 극단적이다. 자기 주도 학습 계획 수립(C)은 안내된 논의보다 덜 상호작용적이다. 선호 작업만 배정(D)은 역량 격차를 해결하지 않는다.
401 | A technical team for a project is managed by the lead who was recently promoted to this role. Inside the team, a mature and experienced engineer is constantly questioning the actions of the team lead and is currently ignoring part of the team lead's decisions. The team lead asks the project manager for help. What should the project manager do? | Suggest to the team lead how to deal with this team member and discuss the situation with the engineer. | Organize a meeting with the project team and discuss the situation and its impact on project delivery. | Suggest to the engineer how to work efficiently with the lead and discuss the situation with the lead ' s functional manager. | Organize a meeting with all of the project stakeholders and inform them about the new risk and its impact on the project. |  | B | When an experienced engineer is questioning and ignoring the newly promoted team lead's decisions, the project manager should organize a meeting with the project team to discuss the situation and its impact on project delivery. This open, collective approach aligns with collaborative conflict resolution—allowing all perspectives to be heard while focusing on project impact. Suggesting to the lead how to deal with the engineer (A) provides private coaching but does not address the team dynamic. Suggesting to the engineer how to work with the lead (C) is one-sided. Informing all stakeholders about the risk (D) escalates unnecessarily. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트의 기술 팀이 최근 이 역할로 승진한 리드에 의해 관리되고 있다. 팀 내 성숙하고 경험 있는 엔지니어가 팀 리드의 행동에 끊임없이 의문을 제기하고 현재 팀 리드의 결정 일부를 무시하고 있다. 팀 리드가 프로젝트 관리자에게 도움을 요청한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀 리드에게 이 팀원을 대하는 방법을 제안하고 엔지니어와 상황을 논의한다. | 프로젝트 팀과 회의를 조직하여 상황과 프로젝트 전달에 대한 영향을 논의한다. | 엔지니어에게 리드와 효율적으로 작업하는 방법을 제안하고 리드의 기능 관리자와 상황을 논의한다. | 모든 프로젝트 이해관계자와 회의를 조직하여 새로운 리스크와 프로젝트에 대한 영향을 알린다. | 380 | B | 경험 있는 엔지니어가 새로 승진한 팀 리드의 결정을 의문 제기하고 무시할 때, 프로젝트 관리자는 프로젝트 팀과 회의를 조직하여 상황과 프로젝트 전달에 대한 영향을 논의해야 한다. 이 개방적이고 집단적인 접근은 협력적 갈등 해결과 일치하며, 모든 관점이 경청되면서 프로젝트 영향에 집중한다. 리드에게 대처법 제안(A)은 비공개적 코칭은 되지만 팀 역학을 해결하지 않는다. 엔지니어에게 작업 방법 제안(C)은 일방적이다. 모든 이해관계자에게 리스크 알림(D)은 불필요하게 에스컬레이션한다.
402 | A contract has just been awarded for an automation project that was supported by the local community. The project manager was warned by the elected officials that the project cannot proceed. Why did this action occur? | Inadequate engagement of the political stakeholders | Lack of competence to manage the automation project | Lack of a proper legal framework in place | Inadequate funds for the automation project |  | C | When elected officials warn that a community-supported automation project cannot proceed despite having an awarded contract, the cause is a lack of a proper legal framework in place. The absence of enabling legislation or regulatory structures creates uncertainty that prevents government officials from authorizing the project. Inadequate political stakeholder engagement (A) may contribute but the root cause is legal. Lack of competence (B) does not explain officials' intervention. Inadequate funds (D) would prevent the contract from being awarded in the first place. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | AI | 지역 커뮤니티의 지원을 받는 자동화 프로젝트에 계약이 막 체결되었다. 프로젝트 관리자는 선출 공무원들로부터 프로젝트를 진행할 수 없다는 경고를 받았다. 이 조치가 발생한 이유는? | 정치적 이해관계자의 부적절한 참여 | 자동화 프로젝트를 관리할 역량 부족 | 적절한 법적 프레임워크의 부재 | 자동화 프로젝트에 대한 부적절한 자금 |  | C | 선출 공무원들이 커뮤니티 지원을 받는 자동화 프로젝트가 계약이 체결되었음에도 진행할 수 없다고 경고할 때, 원인은 적절한 법적 프레임워크의 부재이다. 가능하게 하는 입법이나 규제 구조의 부재는 정부 공무원들이 프로젝트를 승인하는 것을 방해하는 불확실성을 만든다. 부적절한 정치적 이해관계자 참여(A)는 기여할 수 있지만 근본 원인은 법적이다. 역량 부족(B)은 공무원들의 개입을 설명하지 못한다. 부적절한 자금(D)은 애초에 계약이 체결되는 것을 방지했을 것이다.
403 | A project manager has just started a project to build an external web application for customers to track their orders. The project is expected to take 2 years to complete. Customers are very dissatisfied with the timeline and demand the project be completed in 1 year. What should the project manager do to improve delivery? | Review the work packages, schedule, and estimates with the team and consolidate tasks to shorten the schedule. | Review work packages with the team to build a new incremental delivery plan with multiple releases and obtain the customers ' feedback. | Schedule more frequent design reviews with the customers and provide prototypes to demonstrate progress and gather feedback. | Ask the sponsor for additional resources and funding to speed up the work and cover additional labor costs. |  | B | The correct answer is B. Review work packages with the team to build a new incremental delivery plan with multiple releases and obtain the customers ' feedback. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Agile General Practices | Process | Manage Project Closure | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 프로젝트 관리자가 고객이 주문을 추적할 수 있는 외부 웹 애플리케이션을 구축하는 프로젝트를 막 시작했다. 프로젝트는 완료까지 2년이 예상된다. 고객들은 일정에 매우 불만이며 프로젝트를 1년 안에 완료할 것을 요구한다. 프로젝트 관리자는 전달을 개선하기 위해 무엇을 해야 하는가? | 팀과 함께 작업 패키지, 일정, 추정치를 검토하고 작업을 통합하여 일정을 단축한다. | 팀과 함께 작업 패키지를 검토하여 여러 릴리스가 포함된 새로운 점진적 전달 계획을 수립하고 고객의 피드백을 얻는다. | 고객과 더 빈번한 설계 검토를 예약하고 진행 상황을 보여주며 피드백을 수집하기 위해 프로토타입을 제공한다. | 작업을 가속화하고 추가 인건비를 충당하기 위해 스폰서에게 추가 자원과 자금을 요청한다. |  | B | 정답은 B이다. 팀과 함께 작업 패키지를 검토하여 여러 릴리스가 포함된 새로운 점진적 전달 계획을 수립하고 고객의 피드백을 얻는다. 이 접근 방식은 적절한 프로세스와 이해관계자 정렬을 유지하면서 상황을 효과적으로 해결하는 프로젝트 관리 모범 사례를 따른다.
404 | During the development of a project in a dynamic market environment, new unforeseen legal requirements have come into effect. The project manager is not sure if some of the project deliverables will be fully compliant with the new requirements. What should the project manager do? | Agree with the project team that the new requirements will be applied to the next project, not the one already under development. | Evaluate the consequences of noncompliance with relevant stakeholders and update the risk register with agreed actions. | Request the project management office (PMO) to assign a dedicated resource to monitor the external environment to enable more reactiontime. | Stop the project until someone in the organization can identify all the new requirements and how they impact the project. |  | B | When new unforeseen legal requirements emerge and compliance of deliverables is uncertain, the project manager should evaluate consequences of noncompliance with relevant stakeholders and update the risk register with agreed actions. Collaborative assessment and documented risk responses ensure appropriate mitigation. Deferring new requirements to the next project (A) risks noncompliance. Requesting a dedicated monitoring resource (C) is supportive but not the immediate action. Stopping the project (D) is extreme. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 역동적인 시장 환경에서 프로젝트 개발 중, 예상치 못한 새로운 법적 요구사항이 발효되었다. 프로젝트 관리자는 일부 프로젝트 산출물이 새로운 요구사항을 완전히 준수할지 확신이 없다. 프로젝트 관리자는 무엇을 해야 하는가? | 새로운 요구사항은 이미 개발 중인 프로젝트가 아닌 다음 프로젝트에 적용될 것이라고 프로젝트 팀과 합의한다. | 관련 이해관계자와 비준수의 결과를 평가하고 합의된 조치로 리스크 레지스터를 업데이트한다. | 외부 환경을 모니터링하여 더 많은 대응 시간을 확보하기 위해 프로젝트 관리 오피스(PMO)에 전담 자원 배정을 요청한다. | 조직 내 누군가가 모든 새로운 요구사항과 프로젝트에 미치는 영향을 식별할 수 있을 때까지 프로젝트를 중단한다. |  | B | 예상치 못한 새로운 법적 요구사항이 발생하고 산출물의 준수가 불확실할 때, 프로젝트 관리자는 관련 이해관계자와 비준수의 결과를 평가하고 합의된 조치로 리스크 레지스터를 업데이트해야 한다. 협력적 평가와 문서화된 리스크 대응이 적절한 완화를 보장한다. 새로운 요구사항을 다음 프로젝트로 연기(A)하면 비준수 위험이 있다. 전담 모니터링 자원 요청(C)은 지원적이지만 즉각적인 조치가 아니다. 프로젝트 중단(D)은 극단적이다.
405 | In a financial company, a strategic project has been planned to use a predictive approach. During project planning, the product leader requests that milestones be submitted for review. There is a defined scope and an established deadline to conclude the project. What should the project manager do first to meet the product leader's expectations? | Inform the product leader that they must wait until the end of the project. | Meet with the software team to review the possibility of monthly milestone reviews. | Change the project charter to indicate that the approach will be different. | Modify the project management plan to use an agile framework to incorporate milestones. |  | B | When the product leader requests milestone submissions for review in a predictive project with defined scope and deadline, the project manager should first meet with the software team to review the possibility of monthly milestone reviews. Collaborative discussion determines feasibility before committing. Informing the leader to wait until project end (A) ignores the request. Changing the charter to a different approach (C) is excessive. Modifying the plan to use agile (D) changes methodology unnecessarily. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | Traditional Plan-Driven | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 금융 회사에서 예측형 접근 방식을 사용하기로 계획된 전략 프로젝트가 있다. 프로젝트 계획 중 제품 리더가 마일스톤을 검토를 위해 제출하도록 요청한다. 정의된 범위와 프로젝트를 마무리할 확정된 마감일이 있다. 제품 리더의 기대를 충족하기 위해 프로젝트 관리자가 먼저 해야 할 것은? | 제품 리더에게 프로젝트가 끝날 때까지 기다려야 한다고 알린다. | 소프트웨어 팀과 만나 월간 마일스톤 검토의 가능성을 검토한다. | 접근 방식이 다를 것임을 나타내기 위해 프로젝트 헌장을 변경한다. | 마일스톤을 통합하기 위해 애자일 프레임워크를 사용하도록 프로젝트 관리 계획을 수정한다. |  | B | 정의된 범위와 마감일이 있는 예측형 프로젝트에서 제품 리더가 마일스톤 제출을 요청할 때, 프로젝트 관리자는 먼저 소프트웨어 팀과 만나 월간 마일스톤 검토의 가능성을 검토해야 한다. 협력적 논의가 약속 전에 실현 가능성을 결정한다. 프로젝트 끝까지 기다리라고 알리기(A)는 요청을 무시한다. 다른 접근 방식으로 헌장 변경(C)은 과도하다. 애자일 사용으로 계획 수정(D)은 불필요하게 방법론을 변경한다.
406 | A project manager is working with the team to deliver a project in a company that uses different delivery methods. The project manager is concerned about the communication channels currently suggested by the project management office (PMO) because some information is taking too much time to reach the team members, causing negative consequences for delivery. How should the project manager prevent this situation in the future? | Agree with the project team on a suitable collaboration and make sure information is shared at all times | Refer to the policies and frameworks used at the company enterprise level and inform the project team members. | Use the same methods until the end of the current delivery and suggest new ones during the retrospective. | Tell the sponsor that the project manager will use their own communication model to ensure on-time delivery. |  | A | Effective communication is critical for project success. When current communication channels cause delays, the PM should collaborate with the team to agree on suitable communication methods ensuring prompt and effective information sharing. This proactive approach prevents delivery consequences from information bottlenecks. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 프로젝트 관리자가 다양한 전달 방법을 사용하는 회사에서 팀과 함께 프로젝트를 전달하고 있다. 프로젝트 관리자는 프로젝트 관리 오피스(PMO)가 현재 제안한 커뮤니케이션 채널에 대해 우려하고 있는데, 일부 정보가 팀원에게 도달하는 데 너무 오래 걸려 전달에 부정적인 결과를 초래하고 있기 때문이다. 프로젝트 관리자는 향후 이 상황을 방지하기 위해 어떻게 해야 하는가? | 프로젝트 팀과 적합한 협업에 합의하고 정보가 항상 공유되도록 한다. | 회사 전사 수준에서 사용되는 정책과 프레임워크를 참조하고 프로젝트 팀원에게 알린다. | 현재 전달이 끝날 때까지 동일한 방법을 사용하고 회고에서 새로운 방법을 제안한다. | 스폰서에게 정시 전달을 보장하기 위해 프로젝트 관리자 자신의 커뮤니케이션 모델을 사용할 것이라고 말한다. |  | A | 효과적인 커뮤니케이션은 프로젝트 성공에 필수적이다. 현재 커뮤니케이션 채널이 지연을 초래할 때, PM은 팀과 협력하여 신속하고 효과적인 정보 공유를 보장하는 적합한 커뮤니케이션 방법에 합의해야 한다. 이 사전 예방적 접근 방식은 정보 병목으로 인한 전달 결과를 방지한다.
407 | The velocity of the team is decreasing at every iteration. The project team members are complaining that the user stories are being rejected by the quality assurance team. Which three actions should the project manager take? (Choose three) | Conduct a root cause analysis (RCA) and identify a solution. | Elaborate on the plan to implement a solution and execute it. | Negotiate with the teams involved to manage team dependencies. | Increase the working time to recover the lost time. | Evaluate the effectiveness of the proposed solution. | A, B, E | When the team's velocity is decreasing and user stories are being rejected by QA, the project manager should take three actions: conduct a root cause analysis and identify a solution (A), elaborate on the plan to implement the solution and execute it (B), and evaluate the effectiveness of the proposed solution (E). This follows a systematic problem-solving approach—diagnose, plan and act, then verify results. Negotiating with teams to manage dependencies (C) may be relevant but does not address the quality rejection root cause. Increasing working time (D) violates sustainable pace principles and does not address the underlying quality issues. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 팀의 속도가 매 반복마다 감소하고 있다. 프로젝트 팀원들은 사용자 스토리가 품질 보증 팀에 의해 거부되고 있다고 불만을 제기하고 있다. 프로젝트 관리자가 취해야 할 세 가지 조치는? (3개 선택) | 근본 원인 분석(RCA)을 수행하고 해결책을 식별한다. | 해결책을 구현하기 위한 계획을 수립하고 실행한다. | 팀 의존성을 관리하기 위해 관련 팀과 협상한다. | 손실된 시간을 복구하기 위해 작업 시간을 늘린다. | 제안된 해결책의 효과성을 평가한다. | A, B, E | 팀 속도가 감소하고 사용자 스토리가 QA 팀에 의해 거부될 때, 프로젝트 관리자는 세 가지 조치를 취해야 한다: 근본 원인 분석을 수행하고 해결책을 식별하고(A), 해결책을 구현하기 위한 계획을 정교화하고 실행하며(B), 제안된 해결책의 효과를 평가한다(E). 이는 체계적인 문제 해결 접근법—진단, 계획 및 실행, 결과 검증—을 따른다. 팀 종속성 관리를 위한 협상(C)은 관련될 수 있으나 품질 거부의 근본 원인을 해결하지 않는다. 근무 시간 증가(D)는 지속 가능한 속도 원칙을 위반하며 근본적인 품질 문제를 해결하지 않는다.
408 | During the closing process, the project manager learns that one deliverable is not meeting customer expectations. How should the project manager proceed? | Meet with the customer to reach agreement on the scope of the deliverable that will satisfy both parties | Review the deliverable requirements, check the customer approval criteria, and proceed accordingly | Contact the project sponsor and ask for help in negotiating the closing of the project with the customer | Ask the customer to issue a change request with the information to analyze and provide a solution. |  | B | When a deliverable does not meet customer expectations during the closing process, the project manager should review the deliverable requirements, check the customer approval criteria, and proceed accordingly. Objective evaluation against acceptance criteria drives proper closure. Meeting with the customer to renegotiate scope (A) reopens planning during closing. Contacting the sponsor for negotiation help (C) escalates prematurely. Asking for a change request (D) implies scope is not finalized. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 종료 프로세스 중 프로젝트 관리자가 하나의 산출물이 고객 기대를 충족하지 못한다는 것을 알게 된다. 프로젝트 관리자는 어떻게 진행해야 하는가? | 고객과 만나 양측을 만족시킬 산출물의 범위에 대해 합의에 도달한다. | 산출물 요구사항을 검토하고, 고객 승인 기준을 확인하며, 그에 따라 진행한다. | 프로젝트 스폰서에게 연락하여 고객과의 프로젝트 종료 협상에 도움을 요청한다. | 고객에게 분석하고 해결책을 제공하기 위한 정보가 담긴 변경 요청을 발행하도록 요청한다. |  | B | 종료 프로세스 중 산출물이 고객 기대를 충족하지 못할 때, 프로젝트 관리자는 산출물 요구사항을 검토하고, 고객 승인 기준을 확인하며, 그에 따라 진행해야 한다. 인수 기준에 대한 객관적 평가가 적절한 종료를 이끈다. 고객과 범위 재협상(A)은 종료 중에 계획을 재개한다. 스폰서에게 협상 도움 요청(C)은 성급하게 에스컬레이션한다. 변경 요청 요구(D)는 범위가 확정되지 않았음을 암시한다.
409 | On a transformational project, the project manager is confronted with resistance from the stakeholders. To overcome this and gain acceptance of the change, what should the project manager do first? | Review the stakeholder engagement plan. | Update the issue log. | Neutralize the negative stakeholders. | Escalate the issue to the project sponsor. |  | A | When facing stakeholder resistance on a transformational project, the project manager should first review the stakeholder engagement plan. This plan identifies strategies and actions for promoting productive stakeholder involvement in project decisions and activities. Reviewing it helps the PM assess current engagement levels and identify gaps that need to be addressed to overcome resistance. Updating the issue log (B) documents the problem but does not address it. Neutralizing negative stakeholders (C) is adversarial and counterproductive. Escalating to the project sponsor (D) should be a last resort after the PM has attempted to manage engagement directly. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 변혁적 프로젝트에서 프로젝트 관리자가 이해관계자의 저항에 직면하고 있다. 이를 극복하고 변경에 대한 수용을 얻기 위해 프로젝트 관리자가 먼저 해야 할 것은? | 이해관계자 참여 계획을 검토한다. | 이슈 로그를 업데이트한다. | 부정적인 이해관계자를 무력화한다. | 이슈를 프로젝트 스폰서에게 에스컬레이션한다. |  | A | 변혁적 프로젝트에서 이해관계자 저항에 직면할 때, 프로젝트 관리자는 먼저 이해관계자 참여 계획을 검토해야 한다. 이 계획은 프로젝트 결정과 활동에 생산적인 이해관계자 참여를 촉진하기 위한 전략과 조치를 식별한다. 검토를 통해 PM은 현재 참여 수준을 평가하고 저항을 극복하기 위해 해결해야 할 격차를 식별할 수 있다. 이슈 로그 업데이트(B)는 문제를 문서화하지만 해결하지 않는다. 부정적 이해관계자 무력화(C)는 적대적이고 비생산적이다. 스폰서에게 에스컬레이션(D)은 PM이 직접 참여 관리를 시도한 후의 최후 수단이어야 한다.
410 | A project manager was appointed to lead an already approved project. While reviewing the benefits management plan, the project manager finds out that the information about the forecasted value of the project may not be accurate. What should the project manager do? | Develop scope alternatives to achieve the forecasted project value in the event that project benefits information is inaccurate. | Ask the organization to cancel the project because the project manager is unable to confirm that the project will deliver the forecasted value. | Proceed with execution of the project whether the information about the forecasted value is right or not because the project is already approved. | Meet with the project sponsor and key stakeholders to confirm that the information about 1276 the forecasted project value is accurate. |  | D | When the benefits management plan contains potentially inaccurate forecasted value information, the project manager should meet with the sponsor and key stakeholders to confirm accuracy. Validation ensures sound decision-making. Developing scope alternatives (A) is premature. Canceling the project (B) is extreme. Proceeding regardless (C) ignores the risk. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Schedule | Monitoring & Controlling | Be an Accountable Leader | Control Schedule | Traditional PM | 프로젝트 관리자가 이미 승인된 프로젝트를 이끌도록 임명되었다. 혜택 관리 계획을 검토하면서 프로젝트의 예측 가치에 대한 정보가 정확하지 않을 수 있음을 발견한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 혜택 정보가 부정확한 경우 예측된 프로젝트 가치를 달성하기 위한 범위 대안을 개발한다. | 프로젝트 관리자가 예측 가치를 전달할 수 있음을 확인할 수 없으므로 조직에 프로젝트 취소를 요청한다. | 프로젝트가 이미 승인되었으므로 예측 가치에 대한 정보가 맞든 틀리든 프로젝트 실행을 진행한다. | 프로젝트 스폰서 및 주요 이해관계자와 만나 예측된 프로젝트 가치에 대한 정보가 정확한지 확인한다. |  | D | 혜택 관리 계획에 잠재적으로 부정확한 예측 가치 정보가 포함되어 있을 때, 프로젝트 관리자는 스폰서 및 주요 이해관계자와 만나 정확성을 확인해야 한다. 검증이 건전한 의사결정을 보장한다. 범위 대안 개발(A)은 시기상조이다. 프로젝트 취소(B)는 극단적이다. 무관하게 진행(C)은 리스크를 무시한다.
411 | In an agile project, the team decided to have a rotating group of facilitators for the daily scrum. Overall, most of the facilitators have grown and done well in this role; however, a few of them tend to run inefficient daily scrums. What should the project manager do next? | Ask the facilitators who are doing well to continue and recommend that the others stop facilitating. | Praise the team for self-organizing and growing, then work one-on-one with the facilitators, as needed. | Return to using the scrum master as the facilitator for the daily scrums now that the trial period is over. | Retrain all team members on daily scrum facilitation to ensure there is consistency in the approach. |  | B | When rotating daily scrum facilitators show uneven performance — most doing well but a few running inefficient scrums — the project manager should praise the team for self-organizing and growing, then work one-on-one with facilitators as needed. Targeted coaching preserves self-organization. Keeping only good facilitators (A) discourages growth. Returning to the scrum master (C) abandons the experiment. Retraining everyone (D) is inefficient when most are performing well. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트에서 팀이 일일 스크럼의 순환 진행자 그룹을 두기로 결정했다. 전반적으로 대부분의 진행자들이 이 역할에서 성장하고 잘 수행했지만, 몇몇은 비효율적인 일일 스크럼을 진행하는 경향이 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 잘하고 있는 진행자들은 계속하게 하고 나머지에게는 진행을 중단하도록 권장한다. | 팀의 자기 조직화와 성장을 칭찬한 다음, 필요에 따라 진행자들과 1:1로 작업한다. | 시범 기간이 끝났으므로 스크럼 마스터를 일일 스크럼 진행자로 복귀시킨다. | 접근 방식의 일관성을 보장하기 위해 모든 팀원에게 일일 스크럼 진행 교육을 다시 실시한다. |  | B | 순환 일일 스크럼 진행자의 성과가 고르지 않을 때—대부분은 잘하지만 몇몇이 비효율적인 스크럼을 진행할 때—프로젝트 관리자는 팀의 자기 조직화와 성장을 칭찬한 다음 필요에 따라 진행자들과 1:1로 작업해야 한다. 맞춤형 코칭이 자기 조직화를 보존한다. 좋은 진행자만 유지(A)는 성장을 저해한다. 스크럼 마스터로 복귀(C)는 실험을 포기한다. 모든 사람 재교육(D)은 대부분이 잘하고 있을 때 비효율적이다.
412 | During project execution, a conflict occurs between the project manager and one of the team members at every project team meeting. The ongoing conflict is preventing tasks and deliverables from being completed. The project manager contemplates changing their leadership style. What should the project manager do? | Escalate the situation to the project sponsor | Avoid the team member to prevent further conflicts | Review the personnel skill documents | Review the set of responsibilities with the team member |  | D | When ongoing conflict between the project manager and a team member prevents task completion, the project manager should review the set of responsibilities with the team member. Clarifying roles and expectations reduces friction. Escalating to the sponsor (A) is premature. Avoiding the team member (B) worsens the situation. Reviewing skill documents (C) does not address the conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 실행 중 프로젝트 관리자와 한 팀원 사이에 매 프로젝트 팀 회의마다 갈등이 발생한다. 지속적인 갈등이 작업과 산출물 완성을 방해하고 있다. 프로젝트 관리자는 리더십 스타일을 변경하는 것을 고려하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 상황을 프로젝트 스폰서에게 에스컬레이션한다. | 추가 갈등을 방지하기 위해 해당 팀원을 회피한다. | 인사 기술 문서를 검토한다. | 해당 팀원과 함께 책임 범위를 검토한다. |  | D | 프로젝트 관리자와 팀원 간의 지속적인 갈등이 작업 완성을 방해할 때, 프로젝트 관리자는 해당 팀원과 함께 책임 범위를 검토해야 한다. 역할과 기대를 명확히 하면 마찰이 줄어든다. 스폰서에게 에스컬레이션(A)은 시기상조이다. 팀원 회피(B)는 상황을 악화시킨다. 기술 문서 검토(C)는 갈등을 해결하지 않는다.
413 | At the end of a third planning meeting, the client and a functional manager requested additional meetings to add more features to the product. What should the project manager do to start building the product faster? | Explain that more features can be planned in upcoming Iterations and begin building the product. | Allow the sponsor to determine how long the planning phase should last. | Allow the client ta determine how long the planning phase should last. | Ask the functional manager to work with the team to finalize planning and begin building the product. |  | A | When the client and functional manager request more features during a third planning meeting, the project manager should explain that more features can be planned in upcoming iterations and begin building the product. This aligns with agile's iterative approach—delivering value incrementally while capturing additional features in the backlog. Allowing the sponsor to determine planning duration (B) surrenders PM responsibility. Allowing the client to determine (C) similarly defers the decision. Asking the functional manager to finalize (D) delegates planning authority. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 세 번째 기획 회의가 끝날 때 고객과 기능 관리자가 제품에 더 많은 기능을 추가하기 위한 추가 회의를 요청했다. 프로젝트 관리자는 제품 구축을 더 빨리 시작하기 위해 무엇을 해야 하는가? | 향후 반복(Iteration)에서 더 많은 기능을 계획할 수 있다고 설명하고 제품 구축을 시작한다. | 스폰서가 기획 단계의 기간을 결정하도록 허용한다. | 고객이 기획 단계의 기간을 결정하도록 허용한다. | 기능 관리자에게 팀과 협력하여 기획을 마무리하고 제품 구축을 시작하도록 요청한다. |  | A | 고객과 기능 관리자가 세 번째 기획 회의에서 더 많은 기능을 요청할 때, 프로젝트 관리자는 향후 반복에서 더 많은 기능을 계획할 수 있다고 설명하고 제품 구축을 시작해야 한다. 이는 애자일의 반복적 접근 방식과 일치한다—백로그에 추가 기능을 캡처하면서 점진적으로 가치를 전달한다. 스폰서가 기획 기간을 결정하도록 허용(B)하면 PM의 책임을 포기한다. 고객이 결정하도록 허용(C)도 마찬가지로 결정을 미룬다. 기능 관리자에게 마무리를 요청(D)하면 기획 권한을 위임한다.
414 | During the initial phase of a construction project, the team is unclear about the safety requirements it needs to consider during implementation. The project manager recently met with the client to define the project scope. How should the project manager share this information? | Modify the project charter by including the safety requirements | Meet with the team and present the scope of the safety requirements | Distribute the safety requirements during the project execution phase | Send an email to the team with the details of the safety requirements |  | B | Safety requirements in construction must be clearly communicated early to prevent accidents, rework, compliance violations, and work stoppages. The most effective approach is a direct team meeting to present the requirements—enabling two-way communication, confirming understanding, answering questions, and ensuring alignment on implementation and monitoring. Email (C) is one-way and risks misunderstanding on high-stakes safety topics. Waiting until execution (A) is too late since safety planning influences methods, sequencing, permits, and training from the start. Updating the charter (B) is inappropriate—detailed safety requirements belong in the project management plan and safety documentation, not the charter. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 건설 프로젝트의 초기 단계에서 팀이 실행 중 고려해야 할 안전 요구사항에 대해 불명확하다. 프로젝트 관리자가 최근 고객과 만나 프로젝트 범위를 정의했다. 프로젝트 관리자는 이 정보를 어떻게 공유해야 하는가? | 안전 요구사항을 포함하도록 프로젝트 헌장을 수정한다. | 팀과 만나 안전 요구사항의 범위를 발표한다. | 프로젝트 실행 단계에서 안전 요구사항을 배포한다. | 팀에게 안전 요구사항의 세부 사항이 포함된 이메일을 보낸다. |  | B | 건설에서 안전 요구사항은 사고, 재작업, 규정 위반, 작업 중단을 방지하기 위해 조기에 명확하게 전달되어야 한다. 가장 효과적인 접근 방식은 요구사항을 발표하는 직접 팀 회의이다—양방향 소통을 가능하게 하고 이해를 확인하며 질문에 답하고 구현 및 모니터링에 대한 정렬을 보장한다. 이메일(C)은 일방향이며 높은 위험의 안전 주제에 대한 오해 위험이 있다. 실행까지 기다리기(A)는 안전 기획이 처음부터 방법, 순서, 허가, 교육에 영향을 미치므로 너무 늦다. 헌장 업데이트(B)는 부적절하다—상세한 안전 요구사항은 프로젝트 관리 계획과 안전 문서에 속하며 헌장에 속하지 않는다.
415 | A large project requires new equipment to support the project execution. The procurement manager communicated to the project manager that the delivery of the newly purchased equipment will be delayed. The project manager is concerned that this will directly affect the project schedule. What should the project manager do next? | Validate the information and update the risk management plan. | Update the sponsor of the potential issue and ask for any suggestions. | Source second-hand equipment in order to prepare for any delivery delays. | Update the risk register and discuss it with the project stakeholders. b |  | D | When the procurement manager communicates that new equipment delivery will be delayed, the project manager should update the risk register and discuss it with project stakeholders. Documenting the risk and seeking stakeholder input enables collaborative response planning. Validating information and updating the risk management plan (A) is procedural without stakeholder engagement. Updating the sponsor alone (B) excludes other stakeholders. Sourcing second-hand equipment (C) acts before risk assessment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 대형 프로젝트에 프로젝트 실행을 지원하기 위한 새 장비가 필요하다. 조달 관리자가 프로젝트 관리자에게 새로 구매한 장비의 납품이 지연될 것이라고 전달했다. 프로젝트 관리자는 이것이 프로젝트 일정에 직접 영향을 미칠 것을 우려한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 정보를 검증하고 리스크 관리 계획을 업데이트한다. | 스폰서에게 잠재적 이슈를 업데이트하고 제안을 요청한다. | 납품 지연에 대비하여 중고 장비를 조달한다. | 리스크 레지스터를 업데이트하고 프로젝트 이해관계자와 논의한다. |  | D | 조달 관리자가 새 장비 납품 지연을 전달할 때, 프로젝트 관리자는 리스크 레지스터를 업데이트하고 프로젝트 이해관계자와 논의해야 한다. 리스크를 문서화하고 이해관계자 의견을 구하면 협력적 대응 계획이 가능해진다. 정보 검증 및 리스크 관리 계획 업데이트(A)는 이해관계자 참여 없이 절차적이다. 스폰서만 업데이트(B)는 다른 이해관계자를 배제한다. 중고 장비 조달(C)은 리스크 평가 전에 행동한다.
416 | An intern is replacing a critical resource midway through a sprint. To help the intern get up to speed, the project manager assigns a senior engineer in the team as the intern's mentor. Two months later, the project goes into critical status, delaying the release milestone by a month. What should the project manager have done to avoid this scenario? | Requested an experienced resource as a replacement | Negotiated additional time to complete the project | Allocated additional time for mentoring | Convinced the critical resource to remain on the project. |  | C | When an intern replacing a critical resource causes project delays despite having a senior mentor assigned, the project manager should have allocated additional time for mentoring. Adequate mentoring time ensures effective knowledge transfer and accelerates the intern's readiness for the critical role. Requesting an experienced replacement (A) may not have been available. Negotiating additional project time (B) does not address the capability gap. Convincing the critical resource to stay (D) may not have been feasible. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 인턴이 스프린트 중간에 핵심 자원을 대체하고 있다. 인턴이 빨리 적응할 수 있도록 프로젝트 관리자가 팀의 시니어 엔지니어를 인턴의 멘토로 배정했다. 2개월 후 프로젝트가 위기 상태에 들어가 릴리스 마일스톤이 1개월 지연되었다. 프로젝트 관리자는 이 시나리오를 방지하기 위해 무엇을 했어야 하는가? | 경험 있는 자원을 대체자로 요청했어야 한다. | 프로젝트를 완료하기 위해 추가 시간을 협상했어야 한다. | 멘토링을 위한 추가 시간을 배정했어야 한다. | 핵심 자원이 프로젝트에 남도록 설득했어야 한다. |  | C | 인턴이 핵심 자원을 대체하면서 시니어 멘토가 배정되었음에도 프로젝트가 지연될 때, 프로젝트 관리자는 멘토링을 위한 추가 시간을 배정했어야 한다. 충분한 멘토링 시간은 효과적인 지식 이전을 보장하고 인턴의 핵심 역할 준비를 가속화한다. 경험 있는 대체자 요청(A)은 가용하지 않았을 수 있다. 추가 프로젝트 시간 협상(B)은 역량 격차를 해결하지 않는다. 핵심 자원 잔류 설득(D)은 실행 가능하지 않았을 수 있다.
417 | A project management plan needs to be updated due to recent product requirements changes, but the latest version of the document is missing. What should the project manager do to prevent this from happening again? | Ensure the lessons learned register is up to date | Register an issue for the missing documents | Improve the configuration management process | Review the quality assurance (QA) processes |  | C | A missing latest version of the project management plan indicates weak document control. To prevent recurrence, the project manager should improve the configuration management process. Configuration management governs how project documents are identified, versioned, approved, stored, and retrieved—ensuring a single source of truth with audit trails and controlled access. Registering an issue (B) addresses the symptom but does not prevent recurrence. Keeping lessons learned current (A) is valuable but does not solve version control. Reviewing QA processes (D) may help indirectly but configuration management is the specific discipline that prevents document versioning problems. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Risk & Issue Management | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 최근 제품 요구사항 변경으로 프로젝트 관리 계획을 업데이트해야 하지만 문서의 최신 버전이 없어졌다. 프로젝트 관리자는 이런 일이 다시 발생하지 않도록 무엇을 해야 하는가? | 교훈 레지스터가 최신 상태인지 확인한다. | 누락된 문서에 대한 이슈를 등록한다. | 형상 관리 프로세스를 개선한다. | 품질 보증(QA) 프로세스를 검토한다. |  | C | 프로젝트 관리 계획의 최신 버전이 없어진 것은 문서 통제가 약함을 나타낸다. 재발을 방지하기 위해 프로젝트 관리자는 형상 관리 프로세스를 개선해야 한다. 형상 관리는 프로젝트 문서의 식별, 버전 관리, 승인, 저장, 검색 방법을 관장하여—감사 추적과 통제된 접근으로 단일 진실 소스를 보장한다. 이슈 등록(B)은 증상을 다루지만 재발을 방지하지 않는다. 교훈 최신화(A)는 가치 있지만 버전 관리를 해결하지 않는다. QA 프로세스 검토(D)는 간접적으로 도움이 될 수 있지만 형상 관리가 문서 버전 관리 문제를 방지하는 특정 분야이다.
418 | After meeting with stakeholders, a project manager working at a computer gaming company is creating a project management plan for the company's newest offering. The project manager learns that the company's main competitor is scheduled to release a similar offering leveraging the newest technology. The project manager fears that the competitor's offering is better in multiple ways compared to the project manager's project. What should the project manager do? | Meet with the project team to discuss the concerns and determine how to ensure the project ' s deliverable can compete with the competitor ' s. | Note this concern in the risk register and meet with the sales team to identify mitigation options factoring in the competitor ' s offerings. | Perform a Kano analysis factoring in the competitor ' s offering and present it to the stakeholders. | Meet with the development team to see what changes will improve the project compared to the competition ' s deliverable. |  | A | When the PM learns a competitor will release a similar product with newer technology, the project manager should meet with the project team to discuss concerns and determine how to ensure the deliverable can compete. Team collaboration addresses competitive threats holistically. Noting in the risk register and meeting sales only (B) excludes the project team. Performing a Kano analysis (C) prioritizes customer requirements, not competitive response. Meeting only with the development team (D) excludes other valuable perspectives. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | 컴퓨터 게임 회사에서 일하는 프로젝트 관리자가 이해관계자와 만난 후 회사의 최신 제품을 위한 프로젝트 관리 계획을 작성하고 있다. 프로젝트 관리자는 회사의 주요 경쟁사가 최신 기술을 활용한 유사한 제품을 출시할 예정임을 알게 되었다. 프로젝트 관리자는 경쟁사의 제품이 여러 면에서 자신의 프로젝트보다 우수하다고 우려한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 팀과 만나 우려를 논의하고 프로젝트 산출물이 경쟁사와 경쟁할 수 있도록 하는 방법을 결정한다. | 이 우려를 리스크 레지스터에 기록하고 영업팀과 만나 경쟁사의 제품을 고려한 완화 옵션을 식별한다. | 경쟁사의 제품을 고려한 카노(Kano) 분석을 수행하고 이해관계자에게 발표한다. | 개발팀과 만나 경쟁사의 산출물과 비교하여 프로젝트를 개선할 변경 사항을 확인한다. |  | A | PM이 경쟁사가 최신 기술로 유사한 제품을 출시할 예정임을 알게 되면, 프로젝트 관리자는 프로젝트 팀과 만나 우려를 논의하고 산출물의 경쟁력을 확보하는 방법을 결정해야 한다. 팀 협업은 경쟁 위협을 포괄적으로 다룬다. 리스크 레지스터에 기록하고 영업팀만 만나기(B)는 프로젝트 팀을 배제한다. 카노 분석 수행(C)은 고객 요구사항을 우선시하지 경쟁 대응은 아니다. 개발팀만 만나기(D)는 다른 가치 있는 관점을 배제한다.
419 | A company has undertaken a large transformation project in preparation for the changing economy. During the planning of the transformation project, the key resource from human resources (HR) refuses to approve the proposed project plan. What should the project manager do to gain an understanding of the cause for the resource's refusal? | Speak with their colleague. | Communicate with their supervisor. | Speak directly with the resource. | Organize a team meeting. |  | C | When a key HR resource refuses to approve the proposed project plan for a transformation project, the project manager should speak directly with the resource to understand their concerns. Direct communication enables firsthand information gathering and collaborative problem-solving. Speaking with their colleague (A) is indirect. Communicating with their supervisor (B) escalates before direct engagement. Organizing a team meeting (D) is too broad for a one-on-one concern. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 회사가 변화하는 경제에 대비하여 대규모 전환 프로젝트를 착수했다. 전환 프로젝트 기획 중 인사부(HR)의 핵심 자원이 제안된 프로젝트 계획 승인을 거부한다. 프로젝트 관리자는 자원의 거부 원인을 이해하기 위해 무엇을 해야 하는가? | 동료와 대화한다. | 상급자와 소통한다. | 해당 자원과 직접 대화한다. | 팀 회의를 조직한다. |  | C | 핵심 HR 자원이 전환 프로젝트의 제안된 프로젝트 계획 승인을 거부할 때, 프로젝트 관리자는 해당 자원과 직접 대화하여 우려를 이해해야 한다. 직접적인 소통은 일차 정보 수집과 협력적 문제 해결을 가능하게 한다. 동료와 대화(A)는 간접적이다. 상급자와 소통(B)은 직접 참여 전에 에스컬레이션한다. 팀 회의 조직(D)은 일대일 우려에 대해 너무 광범위하다.
420 | An agile project is running its fifth iteration out of 10. After the last retrospective, the team members realize that they had to work extra hours to deliver the committed work. What should the project manager do? | Conduct a focused retrospective to help the team to discover the root cause | Ask for additional team members to maintain the velocity | Ask the team to have a lower commitment for the next iteration | Implement a checkpoint in the iteration to verify if the team is on track |  | A | Regular retrospectives enable the team to reflect on work processes, identify successes and areas for improvement, and plan corrective actions. When team members work extra hours to meet commitments, a focused retrospective helps identify root causes—such as overcommitment, unclear requirements, or process inefficiencies—and develop strategies to avoid the issue in future iterations. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 애자일 프로젝트가 10개 중 다섯 번째 반복(Iteration)을 진행하고 있다. 마지막 회고(Retrospective) 후 팀원들이 약속한 작업을 전달하기 위해 추가 근무를 해야 했음을 깨달았다. 프로젝트 관리자는 무엇을 해야 하는가? | 근본 원인을 발견할 수 있도록 팀을 돕기 위해 집중 회고를 실시한다. | 속도(velocity)를 유지하기 위해 추가 팀원을 요청한다. | 팀에게 다음 반복에서 더 낮은 약속을 하도록 요청한다. | 팀이 궤도에 있는지 확인하기 위해 반복 중간에 체크포인트를 구현한다. |  | A | 정기 회고는 팀이 작업 프로세스를 성찰하고, 성공과 개선 영역을 식별하며, 시정 조치를 계획할 수 있게 한다. 팀원들이 약속을 충족하기 위해 추가 근무할 때, 집중 회고는 근본 원인—과다 약속, 불명확한 요구사항, 프로세스 비효율성 등—을 식별하고 향후 반복에서 문제를 방지할 전략을 개발하는 데 도움이 된다.
421 | As part of the strategic plan, a company decides to implement a new software platform to manage a centralized document repository. Some requirements are clear and some need more detail. What should the project manager do first to decide how to manage this project? | Split the requirements, put them into two separate projects, and apply different approaches | Register all requirements into a backlog for further detailed analysis. | Determine the most appropriate life cycle approach for the project | Select a predictive development life cycle based on the team ' s experience |  | C | When some requirements are clear and others need more detail for a new software platform, the project manager should first determine the most appropriate lifecycle approach for the project. This assessment considers project objectives, complexity, uncertainty, stakeholder involvement, and team preferences before deciding on predictive, agile, or hybrid methodology. Splitting requirements into two projects (A) may be premature without lifecycle assessment. Registering all requirements in a backlog (B) assumes an agile approach. Selecting predictive based on team experience (D) ignores project characteristics. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 전략 계획의 일환으로 회사가 중앙 집중식 문서 저장소를 관리하기 위한 새로운 소프트웨어 플랫폼을 구현하기로 결정했다. 일부 요구사항은 명확하고 일부는 더 자세한 내용이 필요하다. 프로젝트 관리자는 이 프로젝트를 어떻게 관리할지 결정하기 위해 먼저 무엇을 해야 하는가? | 요구사항을 분리하여 두 개의 별도 프로젝트에 넣고 다른 접근 방식을 적용한다. | 모든 요구사항을 추가 상세 분석을 위해 백로그에 등록한다. | 프로젝트에 가장 적합한 생명주기 접근 방식을 결정한다. | 팀의 경험에 기반하여 예측형 개발 생명주기를 선택한다. |  | C | 새로운 소프트웨어 플랫폼에서 일부 요구사항은 명확하고 다른 것은 더 자세한 내용이 필요할 때, 프로젝트 관리자는 먼저 프로젝트에 가장 적합한 생명주기 접근 방식을 결정해야 한다. 이 평가는 프로젝트 목표, 복잡성, 불확실성, 이해관계자 참여, 팀 선호도를 고려한 후 예측형, 애자일, 하이브리드 방법론을 결정한다. 요구사항을 두 프로젝트로 분리(A)는 생명주기 평가 없이 시기상조일 수 있다. 모든 요구사항을 백로그에 등록(B)은 애자일 접근 방식을 가정한다. 팀 경험에 기반한 예측형 선택(D)은 프로젝트 특성을 무시한다.
422 | A contractor has been making small changes to the engineering specifications without submitting change requests. The contractor and the technical team did not discuss the changes with the project manager, and the modifications do not affect the budget and quality of the deliverable. What should the project manager do? | Ask the quality control team to evaluate the modifications, but take no actionbecause the associated quality risks are insignificant. | Update the change management plan to define the level of control required forthese types of modifications. | Request the engineering team to update the specifications to reflect the modifications made by the contractor. | Report the violation to the change control board (CCB) and seek comprehensiveapproval for these modifications. |  | B | When a contractor makes small specification changes without change requests but the modifications do not affect budget or quality, the project manager should update the change management plan to define the level of control required for such modifications. Process improvement prevents recurrence. Asking QC to evaluate without action (A) is inconsistent. Requesting engineering updates (C) accepts unauthorized changes. Reporting to the CCB (D) may escalate unnecessarily. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 계약자가 변경 요청을 제출하지 않고 엔지니어링 사양에 작은 변경을 가하고 있다. 계약자와 기술팀은 프로젝트 관리자와 변경 사항을 논의하지 않았으며, 수정 사항은 산출물의 예산과 품질에 영향을 미치지 않는다. 프로젝트 관리자는 무엇을 해야 하는가? | 품질 관리팀에게 수정 사항을 평가하도록 요청하지만, 관련 품질 리스크가 미미하므로 조치를 취하지 않는다. | 이러한 유형의 수정에 필요한 통제 수준을 정의하도록 변경 관리 계획을 업데이트한다. | 엔지니어링팀에게 계약자가 수행한 수정 사항을 반영하도록 사양을 업데이트하도록 요청한다. | 변경 통제 위원회(CCB)에 위반 사항을 보고하고 이러한 수정에 대한 포괄적인 승인을 구한다. |  | B | 계약자가 변경 요청 없이 작은 사양 변경을 하지만 수정이 예산이나 품질에 영향을 미치지 않을 때, 프로젝트 관리자는 이러한 유형의 수정에 필요한 통제 수준을 정의하도록 변경 관리 계획을 업데이트해야 한다. 프로세스 개선은 재발을 방지한다. QC에게 평가를 요청하되 조치를 취하지 않음(A)은 일관성이 없다. 엔지니어링 업데이트 요청(C)은 무단 변경을 수용한다. CCB에 보고(D)는 불필요하게 에스컬레이션할 수 있다.
423 | A project manager is leading a contract for a new market that was awarded to their company. The client wants to jump-start the market with the informal sector traders. What should the project manager do? | Execute the projects simultaneously following the project schedule and the communications management plan. | Gather requirements and convert them into backlog items to quickly deliver value to the client. | Plan the project in phases, starting with the informal sector, to deliver business value to the client quickly. | Divide the project team into groups to execute the project as small parallel projects, including the informal sector. |  | C | When a client wants to jump-start a new market with informal sector traders, the project manager should plan the project in phases, starting with the informal sector, to deliver business value quickly. Phased delivery prioritizes immediate market impact. Executing simultaneously (A) does not prioritize. Gathering requirements for backlog (B) is a step but not the delivery approach. Dividing into parallel small projects (D) adds complexity without strategic focus. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Focus on Value | Plan Finance Management | Hybrid/Tailoring | 프로젝트 관리자가 자사에 수주된 새로운 시장을 위한 계약을 이끌고 있다. 고객이 비공식 부문 상인들과 함께 시장을 빠르게 시작하고 싶어한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 일정과 커뮤니케이션 관리 계획에 따라 프로젝트를 동시에 실행한다. | 요구사항을 수집하고 백로그 항목으로 변환하여 고객에게 빠르게 가치를 전달한다. | 비공식 부문부터 시작하여 단계별로 프로젝트를 계획하여 고객에게 빠르게 비즈니스 가치를 전달한다. | 비공식 부문을 포함하여 프로젝트 팀을 그룹으로 나누어 소규모 병렬 프로젝트로 실행한다. |  | C | 고객이 비공식 부문 상인들과 시장을 빠르게 시작하고 싶을 때, 프로젝트 관리자는 비공식 부문부터 시작하여 단계별로 프로젝트를 계획하여 빠르게 비즈니스 가치를 전달해야 한다. 단계별 전달은 즉각적인 시장 영향을 우선시한다. 동시 실행(A)은 우선순위를 정하지 않는다. 백로그를 위한 요구사항 수집(B)은 단계이지만 전달 접근 방식은 아니다. 소규모 병렬 프로젝트로 분할(D)은 전략적 초점 없이 복잡성을 추가한다.
424 | A senior manager attends one of the project review meetings and raises a concern that the project will not meet the quality standards. What should the project manager do? | Estimate the backlog items to forecast quality. | Ask the senior manager to approve the user acceptance testing (UAT) plan. | Review the quality management plan with the senior manager. | Inform the senior manager that there are approved quality standards. |  | C | When quality concerns are raised by a senior manager, the PM should review the quality management plan together with the manager to ensure alignment on quality objectives, standards, and procedures. This collaborative review identifies any gaps or misunderstandings and enables both parties to agree on corrective actions. Regular quality assessments and audits are essential practices for verifying that project activities comply with defined quality standards. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 고위 관리자가 프로젝트 검토 회의에 참석하여 프로젝트가 품질 표준을 충족하지 못할 것이라는 우려를 제기한다. 프로젝트 관리자는 무엇을 해야 하는가? | 품질을 예측하기 위해 백로그 항목을 추정한다. | 고위 관리자에게 사용자 수락 테스트(UAT) 계획을 승인하도록 요청한다. | 고위 관리자와 함께 품질 관리 계획을 검토한다. | 고위 관리자에게 승인된 품질 표준이 있음을 알린다. |  | C | 고위 관리자가 품질 우려를 제기할 때, PM은 관리자와 함께 품질 관리 계획을 검토하여 품질 목표, 표준 및 절차에 대한 정렬을 보장해야 한다. 이 협력적 검토는 격차나 오해를 식별하고 양측이 시정 조치에 합의할 수 있게 한다. 정기적인 품질 평가와 감사는 프로젝트 활동이 정의된 품질 표준을 준수하는지 확인하는 필수적인 실천이다.
425 | A project manager receives a suggestion from a team member for improving the product attributes without impacting the schedule or cost. This will add value to the project and the customer. What should the project manager do? | Ask the team member to submit a formal change request. | Ask another team member to validate the impacts of the suggestion. | Accept the suggestion as it has no impact on the project. | Reject the suggestion and ask the team member to focus on executing the plan. |  | A | When a team member suggests improving product attributes without impacting schedule or cost, the project manager should ask the team member to submit a formal change request. Even beneficial changes must go through the change management process to ensure proper analysis, documentation, and approval. Asking another team member to validate impacts (B) is informal and bypasses governance. Accepting the suggestion without a formal process (C) could introduce unforeseen risks. Rejecting it outright (D) dismisses a potentially valuable improvement. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트 관리자가 팀원으로부터 일정이나 비용에 영향을 주지 않으면서 제품 속성을 개선하는 제안을 받았다. 이는 프로젝트와 고객에게 가치를 더할 것이다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원에게 공식 변경 요청을 제출하도록 요청한다. | 다른 팀원에게 제안의 영향을 검증하도록 요청한다. | 프로젝트에 영향이 없으므로 제안을 수락한다. | 제안을 거부하고 팀원에게 계획 실행에 집중하도록 요청한다. |  | A | 팀원이 일정이나 비용에 영향 없이 제품 속성 개선을 제안할 때, 프로젝트 관리자는 팀원에게 공식 변경 요청을 제출하도록 요청해야 한다. 유익한 변경도 적절한 분석, 문서화 및 승인을 보장하기 위해 변경 관리 프로세스를 거쳐야 한다. 다른 팀원에게 영향 검증 요청(B)은 비공식적이며 거버넌스를 우회한다. 공식 프로세스 없이 제안 수락(C)은 예상치 못한 리스크를 도입할 수 있다. 즉시 거부(D)는 잠재적으로 가치 있는 개선을 무시한다.
426 | In a hybrid project, the customer decided on a major change for the project design. This change was approved and the impact on schedule and budget is known. The software team leader, who is supposed to develop the software, refuses to commit to delivery dates claiming that they work using an agile approach and cannot commit to a final delivery date. The hardware team depends on this software to develop their part of the product. What should the project manager do? | Add this risk to the risk register and monitor it according to the risk management plan | Impose the delivery dates on the software team leader and notify the functional manager about the situation | Ask the software team leader to use a predictive approach and commit to a delivery date | Escalate this to higher management and ask for help to resolve the issue. |  | A | When a software team leader in a hybrid project refuses to commit to delivery dates despite an approved change, the project manager should add the risk to the risk register and monitor it per the risk management plan. Formal risk tracking enables proactive management. Imposing dates (B) violates agile principles. Asking the team to switch to predictive (C) may not suit the work. Escalating to management (D) is premature without internal resolution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Hybrid/Tailoring | 하이브리드 프로젝트에서 고객이 프로젝트 설계에 대한 대규모 변경을 결정했다. 이 변경은 승인되었으며 일정과 예산에 대한 영향이 알려져 있다. 소프트웨어를 개발해야 하는 소프트웨어 팀 리더가 애자일 접근 방식을 사용하므로 최종 납기일에 약속할 수 없다며 거부한다. 하드웨어 팀은 제품의 자신들 파트를 개발하기 위해 이 소프트웨어에 의존한다. 프로젝트 관리자는 무엇을 해야 하는가? | 이 리스크를 리스크 레지스터에 추가하고 리스크 관리 계획에 따라 모니터링한다. | 소프트웨어 팀 리더에게 납기일을 부과하고 기능 관리자에게 상황을 알린다. | 소프트웨어 팀 리더에게 예측적 접근 방식을 사용하고 납기일에 약속하도록 요청한다. | 상위 경영진에게 에스컬레이션하고 문제 해결을 위한 도움을 요청한다. |  | A | 하이브리드 프로젝트에서 승인된 변경에도 불구하고 소프트웨어 팀 리더가 납기일 약속을 거부할 때, 프로젝트 관리자는 리스크를 리스크 레지스터에 추가하고 리스크 관리 계획에 따라 모니터링해야 한다. 공식적인 리스크 추적은 사전 예방적 관리를 가능하게 한다. 납기일 부과(B)는 애자일 원칙을 위반한다. 예측적 접근 방식으로 전환 요청(C)은 작업에 적합하지 않을 수 있다. 경영진에게 에스컬레이션(D)은 내부 해결 없이는 시기상조이다.
427 | During a sprint planning meeting, a project team analyzes the effort required to complete some of the tasks before aligning on a sprint commitment. The project team faces issues when trying to estimate the testing effort for the tasks. What should the project manager do first? | Ensure the definition of done (DoD) is understood by all team members. | Involve a quality assurance (QA) expert to support the testing estimation. | Obtain the acceptance criteria from the product owner. | Encourage the team to do pair programming to reduce testing. |  | A | When the team has difficulty estimating testing effort during sprint planning, the project manager should first ensure the definition of done (DoD) is understood by all team members. The DoD establishes shared quality and completeness criteria that enable consistent estimation. Involving a QA expert (B) adds expertise without addressing foundational understanding. Obtaining acceptance criteria from the product owner (C) is story-level, not process-level. Encouraging pair programming (D) reduces defects but does not address estimation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 스프린트 계획 회의 중 프로젝트 팀이 스프린트 약속을 정렬하기 전에 일부 작업 완료에 필요한 노력을 분석한다. 프로젝트 팀이 작업의 테스트 노력을 추정하는 데 어려움을 겪고 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 완료의 정의(DoD)를 모든 팀원이 이해하도록 보장한다. | 테스트 추정을 지원하기 위해 품질 보증(QA) 전문가를 참여시킨다. | 제품 책임자로부터 인수 기준을 확보한다. | 테스트를 줄이기 위해 팀에게 페어 프로그래밍을 하도록 권장한다. |  | A | 스프린트 계획 중 팀이 테스트 노력 추정에 어려움을 겪을 때, 프로젝트 관리자는 먼저 완료의 정의(DoD)를 모든 팀원이 이해하도록 보장해야 한다. DoD는 일관된 추정을 가능하게 하는 공유된 품질 및 완료 기준을 수립한다. QA 전문가 참여(B)는 기초적 이해를 다루지 않고 전문성을 추가한다. 제품 책임자로부터 인수 기준 확보(C)는 스토리 수준이지 프로세스 수준이 아니다. 페어 프로그래밍 권장(D)은 결함을 줄이지만 추정을 다루지 않는다.
428 | During the execution phase of a healthcare IT project, stakeholders made a change request regarding user requirements. There is no remaining budget available to cover that change request. What should the project manager do next? | Ask the sponsor for more funds to cover the change request | Evaluate the change request against the project scope statement | Perform a risk assessment on the required change request. | Discuss approval of the change request in the next project meeting |  | B | Change requests should be evaluated against the project scope statement before any other action. The scope statement defines project objectives, deliverables, requirements, and acceptance criteria—serving as the foundation for change decisions. The PM should assess the change's necessity, feasibility, and benefit relative to scope, then evaluate impacts on schedule, budget, quality, and risk. Meeting discussions (A) may delay decisions. Risk assessment (B) should follow scope evaluation. Requesting additional funds (D) is premature before determining whether the change is justified. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 의료 IT 프로젝트의 실행 단계에서 이해관계자들이 사용자 요구사항에 관한 변경 요청을 했다. 해당 변경 요청을 충당할 잔여 예산이 없다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 변경 요청을 충당하기 위해 스폰서에게 추가 자금을 요청한다. | 프로젝트 범위 기술서에 대해 변경 요청을 평가한다. | 요청된 변경 요청에 대한 리스크 평가를 수행한다. | 다음 프로젝트 회의에서 변경 요청의 승인을 논의한다. |  | B | 변경 요청은 다른 조치를 취하기 전에 프로젝트 범위 기술서에 대해 평가되어야 한다. 범위 기술서는 프로젝트 목표, 산출물, 요구사항 및 인수 기준을 정의하며 변경 결정의 기초가 된다. PM은 범위 대비 변경의 필요성, 실행 가능성 및 이점을 평가한 후 일정, 예산, 품질 및 리스크에 대한 영향을 평가해야 한다. 회의 논의(A)는 결정을 지연시킬 수 있다. 리스크 평가(B)는 범위 평가 후에 해야 한다. 추가 자금 요청(D)은 변경이 정당화되는지 판단하기 전에는 시기상조이다.
429 | At a recent steering committee meeting, the project sponsor asked the project team to add a major feature to the final product. After consulting with the project team, it is determined that the change will cause significant impacts to the original project delivery date and budget. What should the project manager do to assess the priorities and meet the new objective? | Submit a change order request with the new project objective to the project management office (PMO). | Communicate the results and negotiate the needed resources and time with the stakeholder. | Ask the project team to work overtime in order to accommodate the new changes. | Initiate a crashing routine to gain extra time for the added feature. |  | B | When a sponsor requests a major feature that significantly impacts delivery date and budget, the PM should communicate these impacts to stakeholders by presenting impact analysis results and negotiating for necessary resources and time. This ensures stakeholders make informed decisions based on the project's best interest, aligning with PMI's emphasis on stakeholder engagement and communication in effective change management. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 최근 운영위원회 회의에서 프로젝트 스폰서가 프로젝트 팀에게 최종 제품에 주요 기능을 추가하도록 요청했다. 프로젝트 팀과 협의한 결과, 이 변경이 원래 프로젝트 납기일과 예산에 상당한 영향을 미칠 것으로 판단되었다. 우선순위를 평가하고 새로운 목표를 달성하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 새로운 프로젝트 목표와 함께 변경 주문 요청을 프로젝트 관리 오피스(PMO)에 제출한다. | 결과를 전달하고 이해관계자와 필요한 자원 및 시간을 협상한다. | 새로운 변경을 수용하기 위해 프로젝트 팀에게 초과 근무를 요청한다. | 추가된 기능을 위한 여유 시간을 확보하기 위해 크래싱 루틴을 시작한다. |  | B | 스폰서가 납기일과 예산에 상당한 영향을 미치는 주요 기능을 요청할 때, PM은 영향 분석 결과를 이해관계자에게 전달하고 필요한 자원과 시간을 협상해야 한다. 이는 이해관계자가 프로젝트의 최선의 이익에 기반하여 정보에 입각한 결정을 내리도록 보장하며, 효과적인 변경 관리에서 이해관계자 참여와 커뮤니케이션에 대한 PMI의 강조와 일치한다.
430 | Two project team members are having difficulty communicating updates and issues. One team member prefers telephone calls for any kind of urgency, whereas the other team member prefers email communication. This difference results in a lack of understanding between the team members and sometimes hinders timely communication. What should the project manager do? | Provide guidance to the team members to resolve the conflicts. | Ask the team members to resolve this issue themselves. | Ask the team members to follow the ground rules in the project management plan. | Provide these team members with feedback that this issue is causing a delay. |  | C | When two team members have conflicting communication preferences that hinder timely updates, the project manager should ask them to follow the ground rules established in the project management plan. Ground rules set standardized protocols for communication methods and expectations, ensuring consistency across the team. Enforcing these agreed-upon standards resolves the conflict without favoring either preference. Providing general guidance (A) is too vague to resolve a specific communication mismatch. Asking them to resolve it themselves (B) risks continued delays if neither compromises. Providing feedback about the delay (D) identifies the problem but does not prescribe a solution. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 두 프로젝트 팀원이 업데이트와 이슈를 전달하는 데 어려움을 겪고 있다. 한 팀원은 긴급한 경우 전화 통화를 선호하고, 다른 팀원은 이메일 커뮤니케이션을 선호한다. 이 차이로 인해 팀원 간 이해 부족이 발생하고 때때로 적시 커뮤니케이션을 방해한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원들에게 갈등을 해결하도록 지침을 제공한다. | 팀원들에게 스스로 이 문제를 해결하도록 요청한다. | 팀원들에게 프로젝트 관리 계획의 기본 규칙을 따르도록 요청한다. | 팀원들에게 이 문제가 지연을 유발하고 있다는 피드백을 제공한다. |  | C | 두 팀원이 적시 업데이트를 방해하는 커뮤니케이션 선호도 충돌이 있을 때, 프로젝트 관리자는 프로젝트 관리 계획에 수립된 기본 규칙을 따르도록 요청해야 한다. 기본 규칙은 커뮤니케이션 방법과 기대에 대한 표준화된 프로토콜을 설정하여 팀 전체의 일관성을 보장한다. 합의된 표준을 시행하면 어느 쪽 선호도도 편들지 않고 갈등을 해결한다. 일반적 지침 제공(A)은 특정 커뮤니케이션 불일치를 해결하기에 너무 모호하다. 스스로 해결하도록 요청(B)은 어느 쪽도 양보하지 않으면 지연이 계속될 위험이 있다. 지연에 대한 피드백 제공(D)은 문제를 식별하지만 해결책을 제시하지 않는다.
431 | A project manager is leading a project which shows a trend to exceed the cost baseline. What should the project manager do first to manage the budget? | Meet with the project team to analyze the actual cost to determine deviations | Issue a change request including the analysis to increase the budget | Ask the project sponsor for assistance in getting the budget back on track | Inform the stakeholders that the project will be finished over budget. |  | A | When a project shows a trend to exceed the cost baseline, the project manager should first meet with the project team to analyze the actual cost and determine deviations. Understanding the root cause enables informed corrective action. Asking the sponsor for assistance (B) is premature without analysis. Issuing a change request to increase budget (D) is hasty before understanding causes. Informing stakeholders of overbudget (C) communicates without resolution. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 관리자가 비용 기준선을 초과하는 추세를 보이는 프로젝트를 이끌고 있다. 예산을 관리하기 위해 프로젝트 관리자가 먼저 해야 할 일은? | 프로젝트 팀과 만나 실제 비용을 분석하여 편차를 파악한다. | 예산 증액을 위한 분석을 포함한 변경 요청을 발행한다. | 프로젝트 스폰서에게 예산을 정상 궤도에 올리기 위한 도움을 요청한다. | 이해관계자에게 프로젝트가 예산을 초과하여 완료될 것임을 알린다. |  | A | 프로젝트가 비용 기준선을 초과하는 추세를 보일 때, 프로젝트 관리자는 먼저 프로젝트 팀과 만나 실제 비용을 분석하고 편차를 파악해야 한다. 근본 원인을 이해하면 정보에 입각한 시정 조치가 가능해진다. 스폰서에게 도움 요청(B)은 분석 없이는 시기상조이다. 예산 증액을 위한 변경 요청 발행(D)은 원인을 파악하기 전에는 성급하다. 이해관계자에게 예산 초과 알림(C)은 해결 없이 소통만 한다.
432 | A project team is working together for the first time. During the first sprint, the project manager was asked to solve a prioritization conflict between the Scrum Master and the Product Owner related to a feature requested by an important customer. How should the project manager resolve this conflict? | Contact the customer to understand the request in order to make a decision. | Schedule a meeting with the Scrum Master and Product Owner. | Refer to the roles and responsibilities for the agile team. | Emphasize that the Scrum Master has the responsibility to conduct the sprint planning. |  | C | When a Scrum Master and Product Owner conflict over feature prioritization during the first sprint, the project manager should refer to the roles and responsibilities for the agile team. Clarifying that the Product Owner owns backlog prioritization resolves the conflict at its root. Contacting the customer (A) bypasses the agile team structure. Scheduling a meeting (B) may help but misses the fundamental role clarity issue. Emphasizing the Scrum Master conducts sprint planning (D) misattributes prioritization authority. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 처음으로 함께 작업하고 있다. 첫 번째 스프린트에서 프로젝트 관리자가 중요한 고객이 요청한 기능과 관련하여 스크럼 마스터와 제품 책임자 사이의 우선순위 갈등을 해결하도록 요청받았다. 프로젝트 관리자는 이 갈등을 어떻게 해결해야 하는가? | 결정을 내리기 위해 고객에게 연락하여 요청을 이해한다. | 스크럼 마스터와 제품 책임자와의 회의를 예약한다. | 애자일 팀의 역할과 책임을 참조한다. | 스크럼 마스터가 스프린트 계획을 수행할 책임이 있음을 강조한다. |  | C | 첫 번째 스프린트에서 스크럼 마스터와 제품 책임자가 기능 우선순위에 대해 갈등할 때, 프로젝트 관리자는 애자일 팀의 역할과 책임을 참조해야 한다. 제품 책임자가 백로그 우선순위를 소유한다는 것을 명확히 하면 근본적으로 갈등이 해결된다. 고객에게 연락(A)은 애자일 팀 구조를 우회한다. 회의 예약(B)은 도움이 될 수 있지만 근본적인 역할 명확성 문제를 놓친다. 스크럼 마스터가 스프린트 계획을 수행한다고 강조(D)는 우선순위 권한을 잘못 귀속시킨다.
433 | An internal virtual team is meeting daily to review iteration progress, as well as to conduct other technical and follow-up calls with key stakeholders. The team seems to be disengaged. How should the project manager approach this situation? | Schedule one-to-one meetings and team-building meetings. | Reduce the number of internal and external meetings. | Give the team members a few days off to reduce stress. | Review team assignments and reduce the workload. |  | A | When a virtual team appears disengaged, the project manager should schedule one-to-one meetings and team-building meetings. One-on-one conversations provide a safe space for individual team members to express concerns, while team-building activities foster rapport, trust, and a sense of community—all essential for engagement in virtual settings. Reducing the number of meetings (B) may alleviate meeting fatigue but does not address the root cause of disengagement. Giving the team days off (C) provides temporary relief but does not resolve underlying issues. Reviewing assignments and reducing workload (D) assumes overwork is the cause without first understanding individual perspectives. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Scaled Agile | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 내부 가상 팀이 매일 이터레이션 진행 상황을 검토하고 주요 이해관계자와 기술 및 후속 통화를 수행하기 위해 회의를 하고 있다. 팀이 참여하지 않는 것으로 보인다. 프로젝트 관리자는 이 상황에 어떻게 접근해야 하는가? | 1:1 미팅과 팀 빌딩 미팅을 예약한다. | 내부 및 외부 회의 수를 줄인다. | 스트레스를 줄이기 위해 팀원들에게 며칠 휴가를 준다. | 팀 배정을 검토하고 작업량을 줄인다. |  | A | 가상 팀이 참여하지 않는 것으로 보일 때, 프로젝트 관리자는 1:1 미팅과 팀 빌딩 미팅을 예약해야 한다. 1:1 대화는 개별 팀원이 우려를 표현할 수 있는 안전한 공간을 제공하고, 팀 빌딩 활동은 친밀감, 신뢰, 공동체 의식을 조성한다. 회의 수 줄이기(B)는 회의 피로를 완화하지만 참여 저하의 근본 원인을 해결하지 않는다. 휴가 제공(C)은 일시적 완화를 제공하지만 근본 문제를 해결하지 않는다. 배정 검토 및 작업량 감소(D)는 개인적 관점을 먼저 이해하지 않고 과중한 업무가 원인이라고 가정한다.
434 | A project manager is managing an innovation project for a big corporation. The project manager is planning to use email as the main communication channel; however, the product owner prefers to use another approved communication tool instead of email. What should the project manager do? | Suggest to the team to start using the communication tool suggested by the product owner | Request the product owner to use email because using another tool will increase the workload | Contact the sponsor to request direction regarding the communication tool to be used by the project team | Update the communications management plan based on the product owner'spreferences and distribute to the team 1169 |  | D | When the product owner prefers a different approved communication tool over email, the project manager should update the communications management plan based on the product owner's preferences and distribute it to the team. Adapting to stakeholder needs improves communication effectiveness. Suggesting the PO's tool without updating the plan (A) is informal. Requesting the PO use email (B) dismisses stakeholder preferences. Escalating to the sponsor (C) is unnecessary for an approved tool. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 관리자가 대기업의 혁신 프로젝트를 관리하고 있다. 프로젝트 관리자는 이메일을 주요 커뮤니케이션 채널로 사용할 계획이지만, 제품 책임자는 이메일 대신 다른 승인된 커뮤니케이션 도구를 사용하는 것을 선호한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에게 제품 책임자가 제안한 커뮤니케이션 도구를 사용하기 시작하도록 제안한다. | 다른 도구를 사용하면 작업량이 증가하므로 제품 책임자에게 이메일을 사용하도록 요청한다. | 프로젝트 팀이 사용할 커뮤니케이션 도구에 대한 방향을 요청하기 위해 스폰서에게 연락한다. | 제품 책임자의 선호도에 기반하여 커뮤니케이션 관리 계획을 업데이트하고 팀에 배포한다. |  | D | 제품 책임자가 이메일보다 다른 승인된 커뮤니케이션 도구를 선호할 때, 프로젝트 관리자는 제품 책임자의 선호도에 기반하여 커뮤니케이션 관리 계획을 업데이트하고 팀에 배포해야 한다. 이해관계자 요구에 맞춘 적응은 커뮤니케이션 효과를 개선한다. 계획 업데이트 없이 PO의 도구 제안(A)은 비공식적이다. PO에게 이메일 사용 요청(B)은 이해관계자 선호를 무시한다. 스폰서에게 에스컬레이션(C)은 승인된 도구에 대해 불필요하다.
435 | A project manager has just completed a fixed-price project and the stakeholder is unhappy with the result. What should the project manager do? | Review the missed program deliverables with the project team | Speak with the team ' s manager to get extra hours from the team | Explain to the stakeholder that any modifications require additional budget | Review the project charter for the project approval criteria |  | A | When a stakeholder is unhappy with fixed-price project results, the PM should review missed deliverables with the project team to understand what went wrong and how to improve. In fixed-price contracts, the supplier bears the risk of additional costs. Performing out-of-scope work without a formal change order adds unplanned costs to the project. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 프로젝트 관리자가 고정 가격 프로젝트를 방금 완료했고 이해관계자가 결과에 불만이다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 팀과 누락된 프로그램 산출물을 검토한다. | 팀으로부터 추가 시간을 얻기 위해 팀 관리자와 대화한다. | 이해관계자에게 수정 사항은 추가 예산이 필요하다고 설명한다. | 프로젝트 승인 기준을 위해 프로젝트 헌장을 검토한다. |  | A | 이해관계자가 고정 가격 프로젝트 결과에 불만일 때, PM은 무엇이 잘못되었고 어떻게 개선할 수 있는지 이해하기 위해 프로젝트 팀과 누락된 산출물을 검토해야 한다. 고정 가격 계약에서 공급자가 추가 비용의 위험을 부담한다. 공식적인 변경 주문 없이 범위 외 작업을 수행하면 계획되지 않은 비용이 프로젝트에 추가된다.
436 | A company is implementing a growth strategy by constructing a new production facility, which will soon move into the operation phase. Although a governance policy was already in place, the company must comply with new financial regulations that have been recently implemented. Compliance with the regulations will cause a major change in project scope. How should the project manager respond to this requirement? | Directly comply with the financial regulations. | Perform an analysis to assess the impact on the project. | Proceed with the existing company governance policy. 1149 | Escalate the issue to upper management and let them decide. |  | B | When new financial regulations require major scope changes on a construction project nearing operations, the project manager should perform an analysis to assess the impact on the project. Impact analysis informs decisions before action. Directly complying without analysis (A) ignores project consequences. Proceeding with existing governance (C) ignores the new regulations. Escalating to upper management without analysis (D) is premature. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 한 회사가 곧 운영 단계로 이행할 새로운 생산 시설 건설을 통해 성장 전략을 시행하고 있다. 거버넌스 정책이 이미 마련되어 있었지만, 회사는 최근 시행된 새로운 재무 규정을 준수해야 한다. 규정 준수는 프로젝트 범위에 중대한 변경을 초래할 것이다. 프로젝트 관리자는 이 요구사항에 어떻게 대응해야 하는가? | 재무 규정을 직접 준수한다. | 프로젝트에 대한 영향을 평가하기 위해 분석을 수행한다. | 기존 회사 거버넌스 정책으로 진행한다. | 상급 경영진에게 이슈를 에스컬레이션하고 결정하도록 한다. |  | B | 새로운 재무 규정이 운영 단계에 가까운 건설 프로젝트에 중대한 범위 변경을 요구할 때, 프로젝트 관리자는 프로젝트에 대한 영향을 평가하기 위해 분석을 수행해야 한다. 영향 분석은 조치 전에 의사결정에 정보를 제공한다. 분석 없이 직접 준수(A)는 프로젝트 결과를 무시한다. 기존 거버넌스로 진행(C)은 새 규정을 무시한다. 분석 없이 상급 경영진에게 에스컬레이션(D)은 시기상조이다.
437 | A company is using a predictive approach for the development of a particular component as defined in the scope management plan. Due to regularly changing regulatory requirements, the development team has requested to utilize agile approaches. What should the project manager do about the development team's request? | Ask the project sponsor to obtain approval for implementation of the new approach | Analyze the requirements that will need to be addressed under the requested method | Escalate the request for additional financial resources | Forward the request to the project management office (PMO) to amend the organizational process assets |  | B | When the development team requests switching from predictive to agile due to regularly changing regulatory requirements, the project manager should analyze the requirements that will need to be addressed under the requested method. This evaluation assesses the feasibility, benefits, and drawbacks of changing the delivery approach, considering the impact on scope, schedule, cost, quality, risk, and stakeholder satisfaction. Asking the sponsor for approval (A) is premature without first analyzing the implications. Escalating for additional financial resources (C) assumes additional cost before evaluation. Forwarding to the PMO to amend OPAs (D) addresses organizational processes rather than the project-specific decision. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Hybrid/Tailoring | 한 회사가 범위 관리 계획에 정의된 대로 특정 구성요소 개발에 예측형 접근 방식을 사용하고 있다. 정기적으로 변경되는 규제 요구사항으로 인해 개발 팀이 애자일 접근 방식을 활용하도록 요청했다. 프로젝트 관리자는 개발 팀의 요청에 대해 무엇을 해야 하는가? | 새로운 접근 방식 구현에 대한 승인을 얻기 위해 프로젝트 스폰서에게 요청한다. | 요청된 방법론에서 다루어야 할 요구사항을 분석한다. | 추가 재정 자원에 대한 요청을 에스컬레이션한다. | 조직 프로세스 자산을 수정하기 위해 프로젝트 관리 오피스(PMO)에 요청을 전달한다. |  | B | 정기적으로 변경되는 규제 요구사항으로 인해 개발 팀이 예측형에서 애자일로 전환을 요청할 때, 프로젝트 관리자는 요청된 방법론에서 다루어야 할 요구사항을 분석해야 한다. 이 평가는 전달 접근 방식 변경의 실행 가능성, 이점, 단점을 범위, 일정, 비용, 품질, 리스크, 이해관계자 만족도에 대한 영향을 고려하여 평가한다. 스폰서에게 승인 요청(A)은 영향 분석 없이 시기상조이다. 추가 재정 자원 에스컬레이션(C)은 평가 전에 추가 비용을 가정한다. PMO에 OPA 수정 전달(D)은 프로젝트별 결정이 아닌 조직 프로세스를 다룬다.
438 | A project team with members from many different countries is struggling to cooperate. The project manager accepted these difficulties during the storming phase of team development, but the team has not moved to the next phase. The project is beginning to fall behind schedule. What can the project manager do to move the team to the norming phase? | Show the team the schedule impact of their communication issues and encourage them to put their differences aside | Speak with the project sponsor about changing the team composition | Plan social activities to help foster stronger interpersonal relationships and identify shared goals. | Figure out who is behind the issues and apply progressive disciplinary techniques. |  | C | When a multinational team is stuck in the storming phase and falling behind schedule, the project manager should plan social activities to foster stronger interpersonal relationships and identify shared goals. Social bonding accelerates team development. Showing schedule impact (A) pressures without resolving dynamics. Changing team composition (B) disrupts rather than develops. Applying disciplinary techniques (D) escalates rather than resolves. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 여러 국가에서 온 팀원으로 구성된 프로젝트 팀이 협력에 어려움을 겪고 있다. 프로젝트 관리자는 팀 개발의 스토밍 단계에서 이러한 어려움을 수용했지만, 팀이 다음 단계로 이동하지 않았다. 프로젝트가 일정보다 뒤처지기 시작했다. 프로젝트 관리자는 팀을 노밍 단계로 이동시키기 위해 무엇을 할 수 있는가? | 팀에게 커뮤니케이션 문제의 일정 영향을 보여주고 차이점을 제쳐두도록 격려한다. | 팀 구성 변경에 대해 프로젝트 스폰서와 대화한다. | 더 강한 대인 관계를 촉진하고 공유 목표를 식별하기 위한 사회적 활동을 계획한다. | 문제의 원인이 누구인지 파악하고 점진적 징계 기법을 적용한다. |  | C | 다국적 팀이 스토밍 단계에 머물러 일정이 뒤처질 때, 프로젝트 관리자는 더 강한 대인 관계를 촉진하고 공유 목표를 식별하기 위한 사회적 활동을 계획해야 한다. 사회적 유대감은 팀 개발을 가속화한다. 일정 영향 보여주기(A)는 역학을 해결하지 않고 압박한다. 팀 구성 변경(B)은 개발하지 않고 혼란을 야기한다. 징계 기법 적용(D)은 해결이 아닌 에스컬레이션이다.
439 | A research and development department is planning to develop a product that will introduce a new line of business for the organization. What should the project manager do to increase the project's chances of success? | Conduct benchmarking to determine the business viability of the initiative | Start developing the project management plan based on a previous project template from the project management office (PMO). | Conduct an impact analysis of the new initiative to determine how the project should be rolled out | Plan a working session focusing on the scope, vision, and mission of the initiative |  | D | When a research and development department plans a product introducing a new line of business, the project manager should plan a working session focusing on scope, vision, and mission of the initiative. Collaborative visioning aligns stakeholders and defines strategic direction. Conducting benchmarking (A) assesses viability but does not define the project. Starting from a PMO template (B) applies a generic approach to a novel initiative. Conducting impact analysis (C) evaluates rollout but presupposes the scope is defined. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 연구개발 부서가 조직에 새로운 사업 라인을 도입할 제품을 개발하려 계획하고 있다. 프로젝트 관리자는 프로젝트의 성공 가능성을 높이기 위해 무엇을 해야 하는가? | 이니셔티브의 비즈니스 타당성을 결정하기 위해 벤치마킹을 수행한다. | 프로젝트 관리 오피스(PMO)의 이전 프로젝트 템플릿을 기반으로 프로젝트 관리 계획 개발을 시작한다. | 프로젝트가 어떻게 출시되어야 하는지 결정하기 위해 새로운 이니셔티브의 영향 분석을 수행한다. | 이니셔티브의 범위, 비전, 미션에 초점을 맞춘 워킹 세션을 계획한다. |  | D | 연구개발 부서가 새로운 사업 라인을 도입할 제품을 계획할 때, 프로젝트 관리자는 이니셔티브의 범위, 비전, 미션에 초점을 맞춘 워킹 세션을 계획해야 한다. 협업적 비전 수립은 이해관계자를 정렬하고 전략적 방향을 정의한다. 벤치마킹 수행(A)은 타당성을 평가하지만 프로젝트를 정의하지 않는다. PMO 템플릿으로 시작(B)은 새로운 이니셔티브에 일반적 접근을 적용한다. 영향 분석 수행(C)은 출시를 평가하지만 범위가 정의되어 있다고 전제한다.
440 | A project manager is asked to develop maintenance planning software for a power plant. A similar project was executed by another department in the organization that was later closed due to low performance. The project manager is concerned about the project's performance and wants to take action in advance to ensure the project succeeds. What should the project manager do? | Continue executing the project as planned and add more resources if they are required. | Review the lessons learned on similar projects so that they do not fall back into the same pattern. | Inform the project sponsor about the risk and try to convince them to withdraw from the project. | Evaluate the project risk and add external experts to address the potential risks. |  | B | When a similar project was previously closed for low performance, the project manager should review lessons learned from that project to avoid repeating mistakes. Learning from past failures is proactive risk management. Continuing as planned (A) ignores available knowledge. Informing the sponsor to withdraw (C) is defeatist. Evaluating risk and adding experts (D) acts without leveraging existing organizational knowledge. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 발전소용 유지보수 계획 소프트웨어를 개발하도록 요청받았다. 유사한 프로젝트가 조직의 다른 부서에서 수행되었다가 저조한 성과로 인해 종료되었다. 프로젝트 관리자는 프로젝트 성과가 우려되어 프로젝트 성공을 보장하기 위해 사전에 조치를 취하고자 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 계획대로 프로젝트를 계속 수행하고 필요하면 더 많은 자원을 추가한다. | 같은 패턴에 빠지지 않도록 유사한 프로젝트의 교훈을 검토한다. | 프로젝트 스폰서에게 리스크를 알리고 프로젝트에서 철수하도록 설득한다. | 프로젝트 리스크를 평가하고 잠재적 리스크를 처리하기 위해 외부 전문가를 추가한다. |  | B | 유사한 프로젝트가 저조한 성과로 이전에 종료되었을 때, 프로젝트 관리자는 실수를 반복하지 않기 위해 해당 프로젝트의 교훈을 검토해야 한다. 과거 실패로부터 배우는 것은 사전 예방적 리스크 관리이다. 계획대로 계속(A)은 이용 가능한 지식을 무시한다. 스폰서에게 철수 알림(C)은 패배주의적이다. 리스크 평가 및 전문가 추가(D)는 기존 조직 지식을 활용하지 않고 행동한다.
441 | An agile team is developing a new content management system. Some of the team members are struggling to deliver certain features since they have never worked on this type of solution. What should the project manager do? | Encourage the team to hold a knowledge-sharing session in each iteration. | Ask the team to read through all of the available system documents. | Encourage the team members to make changes directly in the system. | Replace the members with new members who understand the system. |  | A | When agile team members struggle with unfamiliar features of a new content management system, the project manager should encourage knowledge-sharing sessions in each iteration. This promotes continuous learning, collaborative problem-solving, and skill development aligned with agile principles. Asking the team to read all system documents (B) is passive and time-consuming. Encouraging direct system changes without guidance (C) risks errors. Replacing struggling members (D) is disruptive and wastes existing team knowledge. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 애자일 팀이 새로운 콘텐츠 관리 시스템을 개발하고 있다. 일부 팀원이 이 유형의 솔루션에서 작업한 적이 없어 특정 기능 전달에 어려움을 겪고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀이 각 이터레이션에서 지식 공유 세션을 개최하도록 격려한다. | 팀에게 이용 가능한 모든 시스템 문서를 읽도록 요청한다. | 팀원들이 시스템에서 직접 변경하도록 격려한다. | 시스템을 이해하는 새로운 멤버로 교체한다. |  | A | 애자일 팀원들이 새로운 콘텐츠 관리 시스템의 익숙하지 않은 기능에 어려움을 겪을 때, 프로젝트 관리자는 각 이터레이션에서 지식 공유 세션을 격려해야 한다. 이는 지속적 학습, 협력적 문제 해결, 애자일 원칙에 부합하는 기술 개발을 촉진한다. 모든 시스템 문서 읽기 요청(B)은 수동적이고 시간이 많이 걸린다. 안내 없이 직접 시스템 변경 격려(C)는 오류 위험이 있다. 어려움을 겪는 멤버 교체(D)는 파괴적이고 기존 팀 지식을 낭비한다.
442 | A project manager is assigned to a building construction project. The project manager has taken an agile course and wants to use agile practices in the project. What should the project manager do? | Review the stages of the project to allocate additional budget for agile resources. | Assign a scrum master to the project to implement agile practices in the project. | Choose the agile practices that can be implemented in this type of construction project and apply them. | Hire a consultant to provide a second opinion about whether agile can be applied to a construction project. |  | C | When a project manager with agile training wants to apply agile practices to a building construction project, they should choose the agile practices that can be implemented in this type of construction project and apply them. Selective adoption fits agile to the domain. Allocating additional budget for agile resources (A) is premature. Assigning a scrum master (B) imposes a framework. Hiring a consultant for a second opinion (D) delays action. | Process | Determine Appropriate PM Methodology | Development Approach & Life Cycle | Tailor Based on Context | Agile | Agile General Practices | Process | Develop Integrated PM Plan | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Hybrid/Tailoring | 프로젝트 관리자가 건물 건설 프로젝트에 배정되었다. 프로젝트 관리자는 애자일 과정을 수강했고 프로젝트에 애자일 실천법을 사용하고자 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 애자일 자원을 위한 추가 예산을 할당하기 위해 프로젝트 단계를 검토한다. | 프로젝트에 애자일 실천법을 구현하기 위해 스크럼 마스터를 배정한다. | 이 유형의 건설 프로젝트에 구현할 수 있는 애자일 실천법을 선택하여 적용한다. | 건설 프로젝트에 애자일을 적용할 수 있는지에 대한 제2의 의견을 위해 컨설턴트를 고용한다. |  | C | 애자일 교육을 받은 프로젝트 관리자가 건물 건설 프로젝트에 애자일 실천법을 적용하고자 할 때, 이 유형의 건설 프로젝트에 구현할 수 있는 애자일 실천법을 선택하여 적용해야 한다. 선택적 도입이 애자일을 해당 도메인에 맞춘다. 애자일 자원을 위한 추가 예산 할당(A)은 시기상조이다. 스크럼 마스터 배정(B)은 프레임워크를 강요한다. 제2의 의견을 위해 컨설턴트 고용(D)은 행동을 지연시킨다.
443 | During a status review meeting, a team member raises concerns about tasks that are not being completed due to an underperforming resource on the team. What should the project manager do first? | Ask the team to solve the issue internally and review the underperforming resource ' s situation | Discuss various options to improve the team member ' s performance with their functional managers | Meet with the team member privately to discuss the problem and work together to find a solution | Contact the functional manager and request to replace the team member with a better resource |  | C | When a team member raises concerns about tasks not being completed due to an underperforming resource, the project manager should first meet with the underperforming team member privately to discuss the problem and work together on a solution. Private dialogue identifies root causes. Asking the team to solve it internally (A) avoids PM responsibility. Discussing with functional managers (B) escalates prematurely. Requesting replacement (D) is drastic before understanding the issue. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 상태 검토 회의 중 팀원이 팀 내 저성과 자원으로 인해 완료되지 않는 작업에 대한 우려를 제기한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 팀에게 내부적으로 문제를 해결하고 저성과 자원의 상황을 검토하도록 요청한다. | 기능 관리자와 팀원의 성과 개선을 위한 다양한 옵션을 논의한다. | 팀원과 개인적으로 만나 문제를 논의하고 함께 해결책을 찾는다. | 기능 관리자에게 연락하여 더 나은 자원으로 팀원을 교체하도록 요청한다. |  | C | 팀원이 저성과 자원으로 인해 작업이 완료되지 않는다는 우려를 제기할 때, 프로젝트 관리자는 먼저 저성과 팀원과 개인적으로 만나 문제를 논의하고 함께 해결책을 찾아야 한다. 사적 대화는 근본 원인을 파악한다. 팀에게 내부적으로 해결하도록 요청(A)은 PM 책임을 회피한다. 기능 관리자와 논의(B)는 성급하게 에스컬레이션한다. 교체 요청(D)은 문제를 이해하기 전에 과격한 조치이다.
444 | A team member has very strong technical skills and is interested in a leadership role. A leadership position opens up outside of the team in the organization. The project manager has observed that the team member has a major gap in communicating in a professional manner. What should the project manager do? | Recommend the team member for effective communication training and support their career development interests. | Suggest the team member focus on positions with technical aspects and possible technical career opportunities. | Ask the team member to refrain from pursuing new opportunities as they are not a suitable fit for a leadership position. | Encourage the team member to stay in their current role as they are important to the project. |  | A | When a technically strong team member interested in leadership has a major communication gap, the project manager should recommend effective communication training and support their career development interests. Addressing the gap constructively supports growth. Suggesting they focus on technical positions (B) limits their aspirations. Asking them not to pursue opportunities (C) is discouraging. Encouraging them to stay in their current role (D) dismisses their goals. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 팀원이 매우 강한 기술 역량을 가지고 있으며 리더십 역할에 관심이 있다. 팀 외부의 조직에서 리더십 직위가 열렸다. 프로젝트 관리자는 팀원에게 전문적인 방식의 의사소통에 큰 격차가 있음을 관찰했다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원에게 효과적인 의사소통 교육을 추천하고 경력 개발 관심을 지원한다. | 팀원에게 기술적 측면이 있는 직위와 가능한 기술 경력 기회에 집중하도록 제안한다. | 팀원에게 리더십 직위에 적합하지 않으므로 새로운 기회를 추구하지 않도록 요청한다. | 팀원이 프로젝트에 중요하므로 현재 역할에 머무르도록 격려한다. |  | A | 기술적으로 강한 팀원이 리더십에 관심이 있지만 의사소통에 큰 격차가 있을 때, 프로젝트 관리자는 효과적인 의사소통 교육을 추천하고 경력 개발 관심을 지원해야 한다. 격차를 건설적으로 다루면 성장을 지원한다. 기술 직위에 집중하도록 제안(B)은 포부를 제한한다. 기회를 추구하지 않도록 요청(C)은 낙담시킨다. 현재 역할에 머무르도록 격려(D)는 목표를 무시한다.
445 | A company has decided to initiate a project to eliminate a sales channel that has been unprofitable for the past 3 years. Some members of the project team are pessimistic about the project. What should the project manager do in this situation? | Provide team members with specific and clear instructions on the project objectives and tasks. | Communicate the project ' s impact and plans to engage the project team throughout the project. | Engage the functional managers to describe the project ' s impact to the team members directly. | Escalate the team ' s concerns and ask the project sponsor to change the team ' s composition. |  | B | When team members are pessimistic about a project to eliminate an unprofitable sales channel, the project manager should communicate the project's impact and plans to engage the team throughout the project. Open communication about the rationale, benefits, and plans builds understanding and helps address concerns, fostering a collaborative environment. Providing specific instructions on tasks (A) addresses execution but not the underlying pessimism. Engaging functional managers to explain the impact (C) delegates the PM's responsibility. Escalating to the sponsor to change team composition (D) replaces team members rather than addressing their concerns. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 회사가 지난 3년간 수익성이 없었던 판매 채널을 제거하기 위한 프로젝트를 시작하기로 결정했다. 프로젝트 팀의 일부 구성원이 프로젝트에 대해 비관적이다. 프로젝트 관리자는 이 상황에서 무엇을 해야 하는가? | 팀원들에게 프로젝트 목표와 작업에 대한 구체적이고 명확한 지시를 제공한다. | 프로젝트의 영향과 계획을 전달하여 프로젝트 전반에 걸쳐 팀을 참여시킨다. | 기능 관리자를 참여시켜 팀원들에게 프로젝트의 영향을 직접 설명하도록 한다. | 팀의 우려를 에스컬레이션하고 프로젝트 스폰서에게 팀 구성을 변경하도록 요청한다. |  | B | 수익성 없는 판매 채널을 제거하는 프로젝트에 팀원들이 비관적일 때, 프로젝트 관리자는 프로젝트의 영향과 계획을 전달하여 프로젝트 전반에 걸쳐 팀을 참여시켜야 한다. 근거, 이점, 계획에 대한 개방적 소통은 이해를 구축하고 우려를 해결하며 협력적 환경을 조성한다. 작업에 대한 구체적 지시 제공(A)은 실행을 다루지만 근본적인 비관주의는 다루지 않는다. 기능 관리자를 참여시켜 영향 설명(C)은 PM의 책임을 위임한다. 팀 구성 변경을 위해 스폰서에게 에스컬레이션(D)은 우려를 해결하는 대신 팀원을 교체한다.
446 | A major public-transportation construction project is aimed at significantly reducing emissions. The project has been severely delayed due to noncompliance with environmental codes and bylaws. What should the project manager have done to prevent this? | Mapped environmental compliance requirements, identified risks to achieving them, and prepared mitigations. | Appointed a senior environmental compliance officer to report directly to the project manager. | Incorporated sufficient schedule reserves based on similar delays in past projects. | Approached the regulator for a partial waiver in light of the environmental importance of the project. |  | A | When a public-transportation project aimed at reducing emissions is severely delayed due to noncompliance with environmental codes, the project manager should have mapped environmental compliance requirements, identified risks to achieving them, and prepared mitigations. Proactive compliance planning prevents regulatory delays. Appointing a compliance officer (B) is one tactic but does not replace systematic planning. Incorporating schedule reserves (C) buffers time but does not prevent noncompliance. Approaching the regulator for a waiver (D) is reactive and unreliable. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 배출량을 크게 줄이는 것을 목표로 하는 대규모 대중교통 건설 프로젝트가 환경 법규 및 조례 미준수로 인해 심각하게 지연되었다. 프로젝트 관리자는 이를 방지하기 위해 무엇을 했어야 하는가? | 환경 준수 요구사항을 매핑하고, 달성 위험을 식별하며, 완화 조치를 준비했어야 한다. | 프로젝트 관리자에게 직접 보고하는 선임 환경 준수 담당자를 임명했어야 한다. | 유사 프로젝트의 과거 지연을 기반으로 충분한 일정 여유를 포함했어야 한다. | 프로젝트의 환경적 중요성을 고려하여 규제 기관에 부분적 면제를 요청했어야 한다. |  | A | 배출량 감소를 목표로 하는 대중교통 프로젝트가 환경 법규 미준수로 심각하게 지연될 때, 프로젝트 관리자는 환경 준수 요구사항을 매핑하고, 달성 위험을 식별하며, 완화 조치를 준비했어야 한다. 사전 예방적 준수 계획은 규제 지연을 방지한다. 준수 담당자 임명(B)은 한 가지 전술이지만 체계적 계획을 대체하지 않는다. 일정 여유 포함(C)은 시간을 완충하지만 미준수를 방지하지 않는다. 면제 요청(D)은 반응적이고 신뢰할 수 없다.
447 | A project manager assembled a team of 10 developers. Because the organization did not have a development team for this project, contractors were hired. In the kick-off meeting, one of the developers recommended the use of development standards. The project manager's previous team in another organization had good development guidelines. What should the project manager do? | Recommend that the team use industry-accepted guidelines. | Recommend that the team develop their own guidelines. | Contact the previous team and ask for a copy of their guidelines. | Contact the chief information officer (CIO) and request the enterprise development guidelines. |  | B | The PM should recommend that the team develop their own guidelines for quality and process standards. This approach empowers the team to take ownership of their work practices while ensuring alignment with project objectives. Proper procurement management involves selecting, managing, and controlling vendor relationships with appropriate oversight and established processes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Stakeholders | Initiating | Adopt a Holistic View | Identify Stakeholders | Traditional PM | 프로젝트 관리자가 10명의 개발자로 팀을 구성했다. 조직에 이 프로젝트를 위한 개발 팀이 없었기 때문에 계약자를 고용했다. 킥오프 회의에서 개발자 중 한 명이 개발 표준 사용을 권장했다. 프로젝트 관리자의 이전 팀은 다른 조직에서 좋은 개발 지침을 가지고 있었다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에게 업계에서 인정된 지침을 사용하도록 추천한다. | 팀에게 자체 지침을 개발하도록 추천한다. | 이전 팀에 연락하여 지침 사본을 요청한다. | 최고 정보 책임자(CIO)에게 연락하여 기업 개발 지침을 요청한다. |  | B | PM은 팀에게 품질 및 프로세스 표준을 위한 자체 지침을 개발하도록 추천해야 한다. 이 접근 방식은 팀이 작업 관행에 대한 주인의식을 갖도록 하면서 프로젝트 목표와의 정렬을 보장한다. 적절한 조달 관리는 적절한 감독과 확립된 프로세스로 벤더 관계를 선택, 관리, 통제하는 것을 포함한다.
448 | During a business review meeting, a key stakeholder raised a concern about the quality of deliverables and has now escalated the concern. What should the project manager do first? | Schedule a meeting with the stakeholder to clarify and plan next steps. | Schedule a meeting with all team members to clarify and plan next steps. | Discuss with the team and check all reports on the deliverables. | Discuss with the stakeholder and share a report on the deliverables. |  | A | When a key stakeholder escalates a concern about deliverable quality, the project manager should first schedule a meeting with the stakeholder to clarify the concern and plan next steps. Direct engagement ensures accurate understanding before action. Meeting with all team members (B) is premature without clarity on the concern. Discussing with the team and checking reports (C) assumes the issue is in reporting. Discussing with the stakeholder and sharing a report (D) is informational without planning. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 비즈니스 검토 회의 중 핵심 이해관계자가 산출물의 품질에 대한 우려를 제기하고 이를 에스컬레이션했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 이해관계자와 회의를 잡아 우려를 명확히 하고 다음 단계를 계획한다. | 모든 팀원과 회의를 잡아 우려를 명확히 하고 다음 단계를 계획한다. | 팀과 논의하고 산출물에 대한 모든 보고서를 확인한다. | 이해관계자와 논의하고 산출물에 대한 보고서를 공유한다. |  | A | 핵심 이해관계자가 산출물 품질에 대한 우려를 에스컬레이션할 때, 프로젝트 관리자는 먼저 이해관계자와 회의를 잡아 우려를 명확히 하고 다음 단계를 계획해야 한다. 직접적인 참여는 조치 전에 정확한 이해를 보장한다. 모든 팀원과 회의(B)는 우려에 대한 명확성 없이 시기상조이다. 팀과 논의하고 보고서 확인(C)은 문제가 보고에 있다고 가정한다. 이해관계자와 논의하고 보고서 공유(D)는 계획 없이 정보 제공만 한다.
449 | An agile project is in its ninth of 10 iterations. The team is delivering the work as expected. In the planning session, the team identifies a dependency with another project in the organization. What should the scrum master do in order to accomplish the iteration goal? | Ask the product owner to collaborate with the other team about the dependency. | Ask a team member to interact with the other team to complete the dependency. | Recommend that the product owner change the priority of the dependency. | Initiate collaboration with the other project team working on the dependency. |  | D | When a dependency with another project is identified in the ninth of 10 iterations, the scrum master should initiate collaboration with the other project team. Direct coordination resolves external dependencies that may block delivery. Asking the product owner to collaborate (A) shifts responsibility inappropriately. Recommending the product owner change priority (C) postpones rather than resolves. Asking a single team member to handle it (B) may lack authority for cross-team coordination. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트가 10회 반복 중 9번째에 있다. 팀은 예상대로 작업을 전달하고 있다. 계획 세션에서 팀이 조직 내 다른 프로젝트와의 의존성을 식별했다. 반복 목표를 달성하기 위해 스크럼 마스터는 무엇을 해야 하는가? | 제품 책임자에게 의존성에 대해 다른 팀과 협력하도록 요청한다. | 팀원에게 의존성을 완료하기 위해 다른 팀과 상호작용하도록 요청한다. | 제품 책임자에게 의존성의 우선순위를 변경하도록 권고한다. | 의존성을 작업하고 있는 다른 프로젝트 팀과 협력을 시작한다. |  | D | 10회 반복 중 9번째에서 다른 프로젝트와의 의존성이 식별될 때, 스크럼 마스터는 다른 프로젝트 팀과 협력을 시작해야 한다. 직접적인 조율은 전달을 차단할 수 있는 외부 의존성을 해결한다. 제품 책임자에게 협력 요청(A)은 책임을 부적절하게 전가한다. 제품 책임자에게 우선순위 변경 권고(C)는 해결하지 않고 연기한다. 단일 팀원에게 처리 요청(B)은 교차 팀 조율 권한이 부족할 수 있다.
450 | A project manager works for a large global company. The project manager is leading a project where the expected business value is to improve the company's image and reputation. During the project's closing phase, the project manager realizes that there is still a negative perception about the company's brand. What should the project manager have done to prevent this? | Asked for additional time to achieve the project goals and increase business value | Reviewed previous projects' lessons learned and applied them to this project | Monitored progress in achieving the business value throughout the project | Increased the number of project resources to ensure attainment of the business value |  | C | When the project's expected business value is to improve the company's image and reputation but negative perception persists at closing, the project manager should have monitored progress in achieving business value throughout the project. Continuous tracking of the project's impact on brand perception would have enabled early identification of issues and timely corrective action. Asking for additional time (A) does not address the monitoring gap. Reviewing past lessons learned (B) is helpful but insufficient without ongoing monitoring. Increasing resources (D) does not ensure business value alignment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 대규모 글로벌 회사에서 일하고 있다. 프로젝트의 예상 비즈니스 가치는 회사의 이미지와 명성을 개선하는 것이다. 프로젝트 종료 단계에서 프로젝트 관리자는 회사 브랜드에 대한 부정적 인식이 여전히 존재함을 인식한다. 프로젝트 관리자는 이를 방지하기 위해 무엇을 했어야 하는가? | 프로젝트 목표를 달성하고 비즈니스 가치를 높이기 위해 추가 시간을 요청했어야 한다. | 이전 프로젝트의 교훈을 검토하고 이 프로젝트에 적용했어야 한다. | 프로젝트 전반에 걸쳐 비즈니스 가치 달성 진행 상황을 모니터링했어야 한다. | 비즈니스 가치 달성을 보장하기 위해 프로젝트 자원 수를 늘렸어야 한다. |  | C | 프로젝트의 예상 비즈니스 가치가 회사 이미지와 명성 개선인데 종료 시 부정적 인식이 지속될 때, 프로젝트 관리자는 프로젝트 전반에 걸쳐 비즈니스 가치 달성 진행을 모니터링했어야 한다. 브랜드 인식에 대한 영향을 지속적으로 추적하면 문제를 조기에 식별하고 적시에 시정 조치를 취할 수 있다. 추가 시간 요청(A)은 모니터링 격차를 해결하지 않는다. 과거 교훈 검토(B)는 도움이 되지만 지속적인 모니터링 없이는 불충분하다. 자원 수 증가(D)는 비즈니스 가치 정렬을 보장하지 않는다.
451 | A project is approaching successful completion, and all stakeholders are really proud of the achieved results. The project management office (PMO) recommends the project manager to lead the next similar project. What should the project manager do next? | Engage key stakeholders to complete and deliver lessons learned. | Present the project achievements and delegate knowledge transfer to the steering committee. | Request the PMO to manage the lessons learned repository. | Select the same stakeholders for the next project to avoid doing knowledge transfer. |  | A | When a project approaches successful completion and the PMO recommends the PM lead the next similar project, the project manager should engage key stakeholders to complete and deliver lessons learned. Capturing insights while they are fresh ensures the organization benefits from this project's experience. Presenting achievements and delegating knowledge transfer (B) shifts responsibility. Requesting the PMO manage the repository (C) is administrative. Selecting the same stakeholders for the next project (D) avoids knowledge transfer. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트가 성공적으로 완료에 접근하고 있으며 모든 이해관계자가 달성된 결과에 매우 자랑스러워하고 있다. 프로젝트 관리 오피스(PMO)가 프로젝트 관리자에게 다음 유사 프로젝트를 이끌도록 추천한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 핵심 이해관계자를 참여시켜 교훈을 완료하고 전달한다. | 프로젝트 성과를 발표하고 지식 이전을 운영위원회에 위임한다. | PMO에 교훈 저장소를 관리하도록 요청한다. | 지식 이전을 피하기 위해 다음 프로젝트에 같은 이해관계자를 선정한다. |  | A | 프로젝트가 성공적으로 완료에 접근하고 PMO가 다음 유사 프로젝트를 이끌도록 추천할 때, 프로젝트 관리자는 핵심 이해관계자를 참여시켜 교훈을 완료하고 전달해야 한다. 통찰력이 신선할 때 포착하면 조직이 이 프로젝트의 경험으로부터 혜택을 받는다. 성과 발표 및 지식 이전 위임(B)은 책임을 전가한다. PMO에 저장소 관리 요청(C)은 행정적이다. 다음 프로젝트에 같은 이해관계자 선정(D)은 지식 이전을 회피한다.
452 | A new project manager is taking over a project to deliver a new payroll management system that is running behind schedule. In addition, costs are rising due to many late changes requested by the client. What should the project manager do first? | Discuss the situation with the sponsor and seek their guidance. | Arrange a time to meet with the team to understand the parameters. | Schedule a meeting with stakeholders and explain the situation. | Meet with the team to understand the areas of concern. |  | D | When taking over a troubled project, the first priority is understanding the operational reality. Meeting with the team provides direct insight into schedule slippage drivers, the nature of late changes, technical bottlenecks, and what has and hasn't worked. The team is closest to the work and can identify systemic issues such as unclear requirements, weak change control, or poor estimation. Communicating to stakeholders (A) without facts first risks misinformation. Seeking sponsor guidance (B) should be informed by a clear understanding of issues. A fact-based diagnosis enables a sound recovery plan. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 새로운 프로젝트 관리자가 일정이 지연되고 있는 새 급여 관리 시스템 전달 프로젝트를 인수하고 있다. 또한 고객이 요청한 많은 늦은 변경으로 인해 비용이 증가하고 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 스폰서와 상황을 논의하고 지침을 구한다. | 팀과 만나 매개변수를 이해할 시간을 잡는다. | 이해관계자와 회의를 잡고 상황을 설명한다. | 팀과 만나 우려 영역을 이해한다. |  | D | 문제가 있는 프로젝트를 인수할 때, 첫 번째 우선순위는 운영 현실을 이해하는 것이다. 팀과 만나면 일정 지연 원인, 늦은 변경의 성격, 기술적 병목 현상, 무엇이 효과가 있고 없는지에 대한 직접적인 통찰을 제공한다. 팀은 작업에 가장 가까우며 불명확한 요구사항, 약한 변경 통제, 잘못된 추정 등 체계적 문제를 식별할 수 있다. 사실 없이 이해관계자에게 소통(A)은 잘못된 정보를 위험에 빠뜨린다. 스폰서 지침 요청(B)은 문제에 대한 명확한 이해를 바탕으로 해야 한다. 사실 기반 진단은 건전한 회복 계획을 가능하게 한다.
453 | A laboratory is launching a new product, defined to be executed in eight iterations with a fixed release date. At the beginning of the second iteration, the project manager realizes that a significant regulatory feature is missing in the product backlog. What should the project manager do? | Estimate the related cost and ask for a project extension. | Invite stakeholders to discuss the impact of adding the regulatory feature. | Ask the product owner to add the missing feature in the backlog. | Increase the capacity of the team to include the missed feature. |  | B | When a significant regulatory feature is discovered missing from the product backlog, the PM must engage stakeholders to assess the impact of incorporating it. Continuous stakeholder engagement—understanding their needs, addressing issues as they surface, and involving them in project decisions—is fundamental to managing scope changes effectively. This is especially critical for regulatory requirements that could affect the product's compliance and viability. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 한 실험실이 8번의 반복으로 실행하고 고정된 출시일이 정해진 새 제품을 출시하고 있다. 두 번째 반복 시작 시 프로젝트 관리자가 제품 백로그에서 중요한 규제 기능이 누락되었음을 인식한다. 프로젝트 관리자는 무엇을 해야 하는가? | 관련 비용을 추정하고 프로젝트 연장을 요청한다. | 규제 기능 추가의 영향을 논의하기 위해 이해관계자를 초대한다. | 제품 책임자에게 백로그에 누락된 기능을 추가하도록 요청한다. | 누락된 기능을 포함하기 위해 팀의 역량을 증가시킨다. |  | B | 제품 백로그에서 중요한 규제 기능이 누락된 것을 발견했을 때, PM은 이해관계자를 참여시켜 해당 기능을 통합하는 영향을 평가해야 한다. 지속적인 이해관계자 참여—그들의 요구를 이해하고, 발생하는 이슈를 다루며, 프로젝트 결정에 참여시키는 것—은 범위 변경을 효과적으로 관리하는 데 근본적이다. 이는 특히 제품의 규정 준수와 실행 가능성에 영향을 미칠 수 있는 규제 요구사항에 매우 중요하다.
454 | One of the main deliverables of a project is delayed due to a problem with a key provider. What should the project manager do? | Discuss and create a project change request to replace the provider with a more responsible one from the provider list. | Discuss with the project sponsor and seek guidance to impose the penalty stipulated in the agreement. | Schedule a meeting with the provider to review any impacts to the project timeline and deliverables. | Schedule a meeting with all relevant stakeholders to determine the best approach to resolve the issue. |  | C | When a key provider delays a main deliverable, the project manager's first action should be to meet directly with the provider to review the impact on the project timeline and deliverables. This allows the PM to gather facts, understand the root cause, and develop corrective actions based on accurate information. Moving immediately to replace the provider (A) is premature without first assessing the situation. Seeking sponsor guidance to impose penalties (B) is also premature—contractual remedies should follow a recovery discussion, not precede it. Convening a broader stakeholder meeting (D) may be warranted later but is not the most immediate step; the PM should first engage the source of the delay directly. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트의 주요 산출물 중 하나가 핵심 공급업체의 문제로 지연되고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 공급업체 목록에서 더 책임감 있는 공급업체로 교체하기 위한 프로젝트 변경 요청을 논의하고 작성한다. | 프로젝트 스폰서와 논의하고 계약서에 명시된 위약금을 부과하기 위한 지침을 구한다. | 프로젝트 일정 및 산출물에 대한 영향을 검토하기 위해 공급업체와 회의를 예약한다. | 문제 해결을 위한 최선의 접근 방식을 결정하기 위해 모든 관련 이해관계자와 회의를 예약한다. |  | C | 핵심 공급업체가 주요 산출물을 지연시킬 때, 프로젝트 관리자의 첫 번째 조치는 공급업체와 직접 만나 프로젝트 일정 및 산출물에 대한 영향을 검토하는 것이어야 한다. 이를 통해 PM은 사실을 수집하고, 근본 원인을 이해하며, 정확한 정보에 기반한 시정 조치를 개발할 수 있다. 즉시 공급업체 교체(A)는 상황 평가 없이 시기상조이다. 위약금 부과를 위한 스폰서 지침(B)도 시기상조이다—계약상 구제 수단은 복구 논의 후에 와야 한다. 광범위한 이해관계자 회의 소집(D)은 나중에 필요할 수 있지만 가장 즉각적인 단계는 아니다.
455 | A company was awarded a project in a dangerous location that poses several high-level risks for employees. Help is needed to train the employees on major safety and health factors. The project is ongoing and uses a hybrid approach. The project will be conducted in multiple sites, with several development iterations running in parallel. How should the project manager handle this situation? | Hire only local resources who are aware of the terntory ' s hazards, providing employment to the local community | Allocate and use part of the project ' s contingency reserves for training purposes. | Perform a retrospective and update the risk register and resource management plan regarding the necessary budget for training | Negotiate a contract and form a partnership with a local authority for medical and security support services. |  | D | When a project in a dangerous location needs employee safety training using a hybrid approach with multiple parallel sites, the project manager should negotiate a contract and form a partnership with a local authority for medical and security support services. Professional safety partnerships provide comprehensive protection. Using contingency reserves for training (A) misuses reserves. Performing a retrospective for training budget (C) is reactive. Hiring only local resources (D) limits needed expertise. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Hybrid/Tailoring | 한 회사가 직원에게 여러 고위험을 야기하는 위험한 지역에서의 프로젝트를 수주했다. 직원들에게 주요 안전 및 보건 요소에 대한 교육이 필요하다. 프로젝트는 진행 중이며 하이브리드 접근 방식을 사용한다. 프로젝트는 여러 현장에서 수행되며, 여러 개발 반복이 병렬로 진행된다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 해당 지역의 위험을 알고 있는 현지 자원만 고용하여 지역 사회에 고용을 제공한다. | 교육 목적으로 프로젝트의 예비비 일부를 배정하고 사용한다. | 회고를 수행하고 교육에 필요한 예산에 대해 리스크 레지스터와 자원 관리 계획을 업데이트한다. | 의료 및 보안 지원 서비스를 위해 현지 기관과 계약을 협상하고 파트너십을 형성한다. |  | D | 여러 병렬 현장이 있는 위험한 지역의 프로젝트에서 직원 안전 교육이 필요할 때, 프로젝트 관리자는 의료 및 보안 지원 서비스를 위해 현지 기관과 계약을 협상하고 파트너십을 형성해야 한다. 전문적인 안전 파트너십은 포괄적인 보호를 제공한다. 교육을 위한 예비비 사용(A)은 예비비를 오용한다. 교육 예산을 위한 회고 수행(C)은 사후 대응적이다. 현지 자원만 고용(D)은 필요한 전문성을 제한한다.
456 | A project manager is leading a project that will be delivered using a Scrum framework. The organization has an innovative project management office (PMO) that fully supports agile and also has a very friendly procurement team. A new vendor needs to be engaged to provide more developers for a new reporting platform. What should the project manager do? | Use an agile approach and engage a vendor that delivered well in a previous organization. | Consult the development team and engage a vendor that is recommended by them. | Consult the product owner and engage a vendor that is recommended by them. | Use a formal approach using procurement policies, procedures, forms, and work instructions. |  | D | When engaging a new vendor for developers in a Scrum project with a supportive PMO and procurement team, the project manager should use a formal approach following procurement policies, procedures, forms, and work instructions. Formal procurement processes ensure consistency with organizational standards, mitigate vendor risks, and align with strategic goals—regardless of the agile delivery method. Using an agile approach with a previously known vendor (A) bypasses organizational procurement standards. Consulting only the development team (B) or product owner (C) for vendor recommendations ignores formal procurement governance. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 스크럼 프레임워크를 사용하여 전달될 프로젝트를 이끌고 있다. 조직에는 애자일을 완전히 지원하는 혁신적인 프로젝트 관리 오피스(PMO)가 있고 매우 협조적인 조달 팀도 있다. 새로운 보고 플랫폼을 위해 더 많은 개발자를 제공할 새 벤더를 참여시켜야 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 애자일 접근 방식을 사용하고 이전 조직에서 잘 전달한 벤더를 참여시킨다. | 개발 팀과 상의하고 그들이 추천하는 벤더를 참여시킨다. | 제품 책임자와 상의하고 그들이 추천하는 벤더를 참여시킨다. | 조달 정책, 절차, 양식 및 작업 지침을 사용하는 공식적인 접근 방식을 사용한다. |  | D | 지원적인 PMO와 조달 팀이 있는 스크럼 프로젝트에서 개발자를 위한 새 벤더를 참여시킬 때, 프로젝트 관리자는 조달 정책, 절차, 양식 및 작업 지침을 따르는 공식적인 접근 방식을 사용해야 한다. 공식적인 조달 프로세스는 조직 표준과의 일관성을 보장하고, 벤더 리스크를 완화하며, 전략적 목표에 정렬한다—전달 방법이 애자일이더라도. 이전에 알려진 벤더와 애자일 접근 방식 사용(A)은 조직의 조달 표준을 우회한다. 개발 팀(B)이나 제품 책임자(C)만의 추천에 의존하는 것은 공식적인 조달 거버넌스를 무시한다.
457 | A regulatory branch of an environmental government agency has recently placed a ban on the manufacturing of a specified thickness of plastic packaging products. This ban will take effect in 12 months. The project manager for a startup firm working in alternative packaging has been monitoring the progress of this law for a while and, as part of the risk management, has identified new products that can support a growing customer base. What should the project manager do next? | Continue production processes and plan to discuss changes at the next annual target review meeting. | Inform management of the new law as an opportunity to expand market share and share the proposed products 1232 | Organize a meeting with all stakeholders and review the stakeholder engagement plan | Begin a marketing campaign to sell alternative packaging after the 12-month period ends. |  | B | When a new law banning certain plastic packaging creates an opportunity for alternative products, the project manager should inform management of the new law as an opportunity to expand market share and share proposed products. Proactive stakeholder communication with strategic recommendations aligns the project with organizational goals. Continuing production and waiting for annual review (A) misses the window. Meeting all stakeholders to review engagement (C) is broad. Starting a marketing campaign after 12 months (D) is late. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 환경 정부 기관의 규제 부서가 최근 특정 두께의 플라스틱 포장 제품 제조를 금지했다. 이 금지는 12개월 후에 시행된다. 대안 포장 분야에서 일하는 스타트업 회사의 프로젝트 관리자는 이 법안의 진행을 한동안 모니터링해 왔으며, 리스크 관리의 일환으로 증가하는 고객 기반을 지원할 수 있는 새 제품을 식별했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 생산 공정을 계속하고 다음 연간 목표 검토 회의에서 변경 사항을 논의할 계획을 세운다. | 경영진에게 새 법률을 시장 점유율 확대 기회로 알리고 제안된 제품을 공유한다. | 모든 이해관계자와 회의를 조직하고 이해관계자 참여 계획을 검토한다. | 12개월 기간이 끝난 후 대안 포장을 판매하기 위한 마케팅 캠페인을 시작한다. |  | B | 특정 플라스틱 포장을 금지하는 새 법률이 대안 제품의 기회를 만들 때, 프로젝트 관리자는 경영진에게 새 법률을 시장 점유율 확대 기회로 알리고 제안된 제품을 공유해야 한다. 전략적 권고가 포함된 사전 예방적 이해관계자 커뮤니케이션은 프로젝트를 조직 목표에 정렬한다. 생산을 계속하고 연간 검토를 기다리는 것(A)은 기회를 놓친다. 모든 이해관계자와 참여 검토 회의(C)는 광범위하다. 12개월 후 마케팅 캠페인 시작(D)은 늦다.
458 | A project is approaching its project closure phase, and the project manager receives an email from a key stakeholder who complains that the project documentation and artifacts have not been updated. The project manager assigns a project specialist to support the project management office's (PMO) effort to update the project documentation and artifacts. Which three actions should the project manager ask the project specialist to take? (Choose three) | Create a quality assurance plan for the documentation. | Archive only the initial and draft versions of the documents. | Identify the components of the project documentation. | Ensure that the documents are in an easily retrievable form. | Collect the documents at the time of their creation. | A, C, D | When project documentation needs updating during the closure phase, the project specialist should take three actions: create a quality assurance plan for the documentation, identify the components of the project documentation, and ensure documents are in an easily retrievable form. These actions ensure completeness, quality, and accessibility. Archiving only initial and draft versions (B) is incomplete. Collecting documents at creation time (E) is a lifecycle activity, not a closure action. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Closing | Embed Quality | Close Project or Phase | Traditional PM | 프로젝트가 종료 단계에 접근하고 있을 때 프로젝트 관리자가 주요 이해관계자로부터 프로젝트 문서화 및 산출물이 업데이트되지 않았다는 불만 이메일을 받는다. 프로젝트 관리자는 프로젝트 관리 오피스(PMO)의 문서화 및 산출물 업데이트 노력을 지원하기 위해 프로젝트 전문가를 배정한다. 프로젝트 관리자는 프로젝트 전문가에게 어떤 세 가지 조치를 취하도록 요청해야 하는가? (3개 선택) | 문서화에 대한 품질 보증 계획을 작성한다. | 문서의 초기 및 초안 버전만 보관한다. | 프로젝트 문서화의 구성 요소를 식별한다. | 문서가 쉽게 검색 가능한 형태로 되어 있도록 보장한다. | 문서를 작성 시점에 수집한다. | A, C, D | 종료 단계에서 프로젝트 문서화를 업데이트해야 할 때, 프로젝트 전문가는 세 가지 조치를 취해야 한다: 문서화에 대한 품질 보증 계획 작성, 프로젝트 문서화의 구성 요소 식별, 문서가 쉽게 검색 가능한 형태로 되어 있도록 보장. 이 조치들은 완전성, 품질, 접근성을 보장한다. 초기 및 초안 버전만 보관(B)은 불완전하다. 작성 시점에 문서 수집(E)은 수명주기 활동이지 종료 조치가 아니다.
459 | A project manager is assigned to an agile project that has an aggressive timeline and a fixed budget. Currently, the majority of the items are in the backlog and only a few are in process or completed. What should the project manager do? | Assign an owner for each backlog activity and track progress. | Ask for more resources to clear the backlog activities. | Prioritize which backlog activities should be kept. | Work on the backlog activities with fewer story points. |  | C | When an agile project with an aggressive timeline and fixed budget has most items still in the backlog, the project manager should prioritize which backlog activities should be kept. Prioritization focuses effort on high-value items within constraints. Assigning owners and tracking (A) adds overhead without addressing prioritization. Asking for more resources (B) is not feasible with a fixed budget. Working on fewer story points (D) reduces throughput without strategic focus. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 관리자가 공격적인 일정과 고정된 예산이 있는 애자일 프로젝트에 배정되었다. 현재 대부분의 항목이 백로그에 있고 진행 중이거나 완료된 것은 소수에 불과하다. 프로젝트 관리자는 무엇을 해야 하는가? | 각 백로그 활동에 담당자를 배정하고 진행 상황을 추적한다. | 백로그 활동을 처리하기 위해 더 많은 자원을 요청한다. | 어떤 백로그 활동을 유지해야 하는지 우선순위를 정한다. | 스토리 포인트가 적은 백로그 활동부터 작업한다. |  | C | 공격적인 일정과 고정된 예산이 있는 애자일 프로젝트에서 대부분의 항목이 아직 백로그에 있을 때, 프로젝트 관리자는 어떤 백로그 활동을 유지할지 우선순위를 정해야 한다. 우선순위화는 제약 조건 내에서 높은 가치의 항목에 노력을 집중시킨다. 담당자 배정 및 추적(A)은 우선순위화 없이 오버헤드를 추가한다. 더 많은 자원 요청(B)은 고정된 예산에서 실현 불가능하다. 적은 스토리 포인트부터 작업(D)은 전략적 초점 없이 처리량을 줄인다.
460 | A project manager is working in a constantly changing business environment. In order to address this situation, the project manager has decided to use a collaborative leadership style. Which landscape describes the project environment? | Available resources, bad roadmaps | Enough authority, insufficient resources | High accountability, little authority | Good roadmaps, little accountability |  | C | The correct answer is C. High accountability, little authority. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Engage Stakeholders | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 끊임없이 변화하는 비즈니스 환경에서 일하고 있다. 이 상황에 대응하기 위해 프로젝트 관리자는 협력적 리더십 스타일을 사용하기로 결정했다. 어떤 환경이 프로젝트 환경을 설명하는가? | 가용 자원, 나쁜 로드맵 | 충분한 권한, 불충분한 자원 | 높은 책임, 적은 권한 | 좋은 로드맵, 적은 책임 |  | C | 정답은 C이다. 높은 책임, 적은 권한. 이 접근 방식은 상황을 효과적으로 다루고, 적절한 프로세스를 유지하며, 이해관계자 기대와 프로젝트 목표에 부합하도록 보장하는 프로젝트 관리 모범 사례를 따른다.
461 | An ongoing project is facing a challenging situation where the customer is not satisfied. The team is new to agile development and frequently communicates with the customer and provides regular status reports. What should the project lead do to satisfy the customer? | Reduce the frequent communication with the customer and improve the format of the status reports to include the team's progress. | Review the progress of the project with the customer and modify the frequency of sprint 502 reviews. | Schedule a meeting with the customer and let them know that the team is new to agile and the situation will improve. | Review the situation with the customer and make the required adjustments with the team. |  | D | When the customer remains unsatisfied despite frequent communication and status reports from a team new to agile, the project manager should review the situation with the customer and make the required adjustments with the team. The root issue is likely not communication volume but responsiveness to customer needs, requiring direct engagement and adaptive action. Explaining the team is new to agile (C) does not solve the customer's problem. Reducing communication and improving report format (A) misses the root issue. Modifying sprint review frequency (B) alone is less effective than understanding dissatisfaction and adapting. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 진행 중인 프로젝트에서 고객이 만족하지 않는 어려운 상황에 직면해 있다. 팀은 애자일 개발에 익숙하지 않으며 고객과 자주 소통하고 정기적인 상태 보고서를 제공한다. 프로젝트 리더는 고객을 만족시키기 위해 무엇을 해야 하는가? | 고객과의 빈번한 소통을 줄이고 팀의 진행 상황을 포함하도록 상태 보고서 형식을 개선한다. | 고객과 프로젝트 진행 상황을 검토하고 스프린트 리뷰의 빈도를 수정한다. | 고객과 회의를 예약하고 팀이 애자일에 익숙하지 않아 상황이 개선될 것이라고 알린다. | 고객과 상황을 검토하고 팀과 함께 필요한 조정을 한다. |  | D | 애자일에 익숙하지 않은 팀이 빈번한 소통과 상태 보고서에도 불구하고 고객이 여전히 불만족할 때, 프로젝트 관리자는 고객과 상황을 검토하고 팀과 함께 필요한 조정을 해야 한다. 근본적인 문제는 소통 양이 아니라 고객 요구에 대한 대응력이며, 직접적인 참여와 적응적 조치가 필요하다. 팀이 애자일에 익숙하지 않다고 설명(C)은 고객의 문제를 해결하지 않는다. 소통 줄이기 및 보고서 형식 개선(A)은 근본 원인을 놓친다. 스프린트 리뷰 빈도 수정(B)만으로는 불만족을 이해하고 적응하는 것보다 덜 효과적이다.
462 | A project manager is managing a project that will engage resources from multiple countries in different time zones. What should the project manager do to ensure that team members are effective? | Organize a daily meeting for all team members and extend it, if required. | Schedule meetings every 2 days at the same time with all team members. | Organize a standard meeting time to engage all of the team members. | Schedule meetings every 2 days that align with team members ' time zones. |  | D | The correct answer is D. Schedule meetings every 2 days that align with team members ' time zones. Effective resource management ensures team members have the necessary competencies and support. The PM should identify gaps and address them through training, coaching, or mentoring. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Cost & Resource Management | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 여러 국가의 다른 시간대에 있는 자원을 참여시킬 프로젝트를 관리하고 있다. 프로젝트 관리자는 팀원들이 효과적이도록 보장하기 위해 무엇을 해야 하는가? | 모든 팀원을 위한 일일 회의를 조직하고 필요하면 연장한다. | 모든 팀원과 동일한 시간에 2일마다 회의를 예약한다. | 모든 팀원을 참여시키기 위한 표준 회의 시간을 조직한다. | 팀원들의 시간대에 맞추어 2일마다 회의를 예약한다. |  | D | 정답은 D이다. 팀원들의 시간대에 맞추어 2일마다 회의를 예약한다. 효과적인 자원 관리는 팀원들이 필요한 역량과 지원을 갖추도록 보장한다. PM은 격차를 식별하고 교육, 코칭 또는 멘토링을 통해 이를 해결해야 한다.
463 | A project requires the procurement of a large amount of equipment that needs to be on-site before any other activity can begin. The procurement department has a lengthy approval process. What should the project manager do? | Use the existing equipment and replace it later with the new equipment | Ask the project sponsor to expedite the vendor selection process. | Work with the procurement team to find alternative options. | Contact the vendor that supplied similar equipment for a previous project. |  | C | When project activities depend on equipment procurement but the approval process is lengthy, the project manager should work with the procurement team to find alternative options. Collaborative exploration identifies faster paths such as expediting approvals or alternate vendors. Using existing equipment temporarily (A) may not meet specifications. Asking the sponsor to expedite vendor selection (B) bypasses procurement processes. Contacting a previous vendor (D) is one option within the broader alternatives. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트에 다른 활동이 시작되기 전에 현장에 있어야 하는 대량의 장비 조달이 필요하다. 조달 부서에는 긴 승인 프로세스가 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 기존 장비를 사용하고 나중에 새 장비로 교체한다. | 프로젝트 스폰서에게 벤더 선정 프로세스를 신속히 처리하도록 요청한다. | 조달 팀과 협력하여 대안 옵션을 찾는다. | 이전 프로젝트에서 유사한 장비를 공급한 벤더에 연락한다. |  | C | 프로젝트 활동이 장비 조달에 의존하지만 승인 프로세스가 길 때, 프로젝트 관리자는 조달 팀과 협력하여 대안 옵션을 찾아야 한다. 협력적 탐색은 승인 가속화나 대체 벤더 등 더 빠른 경로를 식별한다. 기존 장비 임시 사용(A)은 사양을 충족하지 못할 수 있다. 스폰서에게 벤더 선정 가속화 요청(B)은 조달 프로세스를 우회한다. 이전 벤더 연락(D)은 더 넓은 대안 내 하나의 옵션이다.
464 | During the course of a project, the project manager's immediate director is communicating directly with the client to approve changes without the project manager's knowledge. This is causing confusion in the project team where the scope is changing in the background, but only being mentioned in project meetings. How should the project manager handle this? | Review the stakeholder engagement plan and put in place any existing actionsaccordingly | Communicate directly with the client stating that any scope changes must go through the project manager | Communicate directly with the director and inform them of the communications management plan | Discuss the issues with the project team and let them know that the project manager will handle scope changes |  | C | When the PM's director communicates directly with the client to approve scope changes without the PM's knowledge, the project manager should communicate directly with the director and inform them of the communications management plan. This clarifies roles, responsibilities, and the change control process. Reviewing the stakeholder engagement plan (A) assesses the situation but does not address it. Communicating with the client about scope changes (B) bypasses the internal issue. Discussing with the project team (D) does not address the root cause. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Scope | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 진행 중 프로젝트 관리자의 직속 이사가 프로젝트 관리자의 인지 없이 고객과 직접 소통하여 변경을 승인하고 있다. 이로 인해 프로젝트 팀에 혼란이 발생하고 있으며 범위가 배경에서 변경되고 있지만 프로젝트 회의에서만 언급되고 있다. 프로젝트 관리자는 이를 어떻게 처리해야 하는가? | 이해관계자 참여 계획을 검토하고 기존 조치를 적절히 시행한다. | 고객에게 직접 연락하여 모든 범위 변경은 프로젝트 관리자를 통해야 한다고 알린다. | 이사에게 직접 연락하여 커뮤니케이션 관리 계획을 알린다. | 프로젝트 팀과 이슈를 논의하고 프로젝트 관리자가 범위 변경을 처리할 것이라고 알린다. |  | C | PM의 이사가 PM 인지 없이 고객과 직접 소통하여 범위 변경을 승인할 때, 프로젝트 관리자는 이사에게 직접 연락하여 커뮤니케이션 관리 계획을 알려야 한다. 이는 역할, 책임, 변경 통제 프로세스를 명확히 한다. 이해관계자 참여 계획 검토(A)는 상황을 평가하지만 해결하지 않는다. 고객에게 범위 변경 소통(B)은 내부 이슈를 우회한다. 팀과 논의(D)는 근본 원인을 해결하지 않는다.
465 | Toward the end of a project, the project manager did not receive approval from a key stakeholder because the necessary deliverables were not functioning as expected. What should the project manager do next? | Review the requirements traceability matrix | Review the stakeholder engagement plan | Review the work breakdown structure (WBS) | Review the quality management plan |  | D | When a key stakeholder withholds approval because deliverables are not functioning as expected, the project manager should review the quality management plan. The QMP defines quality standards, metrics, and control activities that identify root causes and corrective actions. Reviewing the requirements traceability matrix (A) checks scope alignment but not quality. Reviewing the stakeholder engagement plan (B) addresses engagement, not deliverable functionality. Reviewing the WBS (C) checks scope decomposition. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 종료에 가까워질 때, 프로젝트 관리자가 필요한 산출물이 예상대로 작동하지 않아 주요 이해관계자로부터 승인을 받지 못했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 요구사항 추적 매트릭스를 검토한다. | 이해관계자 참여 계획을 검토한다. | 작업 분류 체계(WBS)를 검토한다. | 품질 관리 계획을 검토한다. |  | D | 주요 이해관계자가 산출물이 예상대로 작동하지 않아 승인을 보류할 때, 프로젝트 관리자는 품질 관리 계획을 검토해야 한다. QMP는 근본 원인과 시정 조치를 식별하는 품질 기준, 메트릭, 통제 활동을 정의한다. 요구사항 추적 매트릭스 검토(A)는 범위 정렬을 확인하지만 품질은 아니다. 이해관계자 참여 계획 검토(B)는 참여를 다루지 산출물 기능은 아니다. WBS 검토(C)는 범위 분해를 확인한다.
466 | A project manager decided to incorporate the latest technological advancement with the client's devices at no additional cost to the project. Upon completion and submission of the project deliverables, the client rejected the devices, despite having the latest features. What should the project manager have done? | Documented the technical reviews with the new change | Reviewed the quality inspections | Complied with the customer specifications | Incorporated the change within the scope of the project |  | A | When the project manager incorporated a technological advancement at no cost but the client rejected the deliverables, the PM should have documented the technical reviews with the new change and obtained formal acceptance before delivery. Proper scope validation ensures customer agreement before implementation. Reviewing quality inspections (B) verifies quality but not scope acceptance. Complying with customer specifications (C) means not adding unapproved changes. Incorporating the change within scope (D) requires formal change control. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Focus on Value | Plan Scope Management | Traditional PM | 프로젝트 관리자가 프로젝트에 추가 비용 없이 고객 장치에 최신 기술 발전을 통합하기로 결정했다. 프로젝트 산출물을 완료하고 제출한 후 고객이 최신 기능이 있음에도 불구하고 장치를 거부했다. 프로젝트 관리자는 무엇을 했어야 하는가? | 새로운 변경에 대한 기술 검토를 문서화한다. | 품질 검사를 검토한다. | 고객 사양을 준수한다. | 프로젝트 범위 내에서 변경을 통합한다. |  | A | 프로젝트 관리자가 비용 없이 기술 발전을 통합했지만 고객이 산출물을 거부할 때, PM은 새로운 변경에 대한 기술 검토를 문서화하고 전달 전 공식 수락을 얻었어야 한다. 적절한 범위 확인은 구현 전 고객 동의를 보장한다. 품질 검사 검토(B)는 품질은 확인하지만 범위 수락은 아니다. 고객 사양 준수(C)는 승인되지 않은 변경을 추가하지 않는 것을 의미한다. 범위 내 변경 통합(D)은 공식 변경 통제가 필요하다.
467 | A functional team member often becomes disruptive during status meetings and attempts to derail progress with the key stakeholders. This team member often discusses why the project will not be successful. What should the project manager do? | Build trust and influence stakeholders. | Identify the root cause of the team member ' s misunderstanding. | Evaluate the engagement needs for stakeholders. | Investigate alternatives for team member needs. |  | B | The correct answer is B. Identify the root cause of the team member ' s misunderstanding. Stakeholder management requires understanding needs, maintaining engagement, and ensuring transparent communication. The PM should proactively address stakeholder concerns and maintain alignment with project goals. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 기능 팀원이 상태 회의에서 종종 방해를 하고 주요 이해관계자와의 진행을 탈선시키려 한다. 이 팀원은 프로젝트가 성공하지 못할 이유를 자주 논의한다. 프로젝트 관리자는 무엇을 해야 하는가? | 신뢰를 구축하고 이해관계자에게 영향을 미친다. | 팀원의 오해의 근본 원인을 파악한다. | 이해관계자의 참여 요구를 평가한다. | 팀원의 요구에 대한 대안을 조사한다. |  | B | 정답은 B이다. 팀원의 오해의 근본 원인을 파악한다. 이해관계자 관리는 요구를 이해하고 참여를 유지하며 투명한 커뮤니케이션을 보장해야 한다. PM은 이해관계자 우려를 사전 예방적으로 해결하고 프로젝트 목표와의 정렬을 유지해야 한다.
468 | The project sponsor requested technical specifications for a project-related component. The project sponsor does not have the authorization to see the specifications, but insists on seeing them. What should the project manager do first in this situation? | Provide the specifications to the project sponsor with some information removed | Update the issue log to make the project team aware and to develop a strategy | Create a stakeholder engagement plan to help the team formulate a response | Meet with the project sponsor as soon as possible to discuss the matter further |  | D | When the project sponsor requests unauthorized technical specifications and insists on seeing them, the project manager should first meet with the project sponsor to discuss the matter further. Direct conversation enables the PM to understand the reason behind the request and explain the confidentiality implications before deciding on next steps. Providing redacted specifications (A) bypasses authorization. Updating the issue log (B) is a follow-up, not the first action. Creating a stakeholder engagement plan (C) is too broad for this specific issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 프로젝트 스폰서가 프로젝트 관련 구성요소의 기술 사양을 요청했다. 프로젝트 스폰서는 사양을 볼 수 있는 권한이 없지만 보겠다고 고집한다. 프로젝트 관리자는 이 상황에서 먼저 무엇을 해야 하는가? | 일부 정보를 제거한 사양을 프로젝트 스폰서에게 제공한다. | 이슈 로그를 업데이트하여 프로젝트 팀이 인지하고 전략을 개발하도록 한다. | 팀이 대응을 수립하는 데 도움이 되는 이해관계자 참여 계획을 수립한다. | 가능한 빨리 프로젝트 스폰서와 만나 이 문제를 추가 논의한다. |  | D | 프로젝트 스폰서가 권한이 없는 기술 사양을 요청하고 보겠다고 고집할 때, 프로젝트 관리자는 먼저 프로젝트 스폰서와 만나 문제를 추가 논의해야 한다. 직접 대화를 통해 PM은 요청 이유를 이해하고 기밀 영향을 설명한 후 다음 단계를 결정할 수 있다. 편집된 사양 제공(A)은 권한을 우회한다. 이슈 로그 업데이트(B)는 후속 조치이지 첫 조치가 아니다. 이해관계자 참여 계획 수립(C)은 이 구체적 이슈에 비해 너무 광범위하다.
469 | A project manager is working on a project to modernize the information technology of a bank. The project manager is facing challenges with the project sponsor regarding how to proceed with implementation of a key piece of technology. How should the project manager resolve this conflict? | Identify the disagreement in the risk register and develop a contingency plan. | Meet with all project stakeholders to identify how to implement the technology. | Negotiate with the project sponsor to develop a mutually beneficial solution. | Update the project charter to align with the desires of the project sponsor. 1063 |  | C | When facing a conflict with the project sponsor over technology implementation, the project manager should negotiate to develop a mutually beneficial solution. Collaborative negotiation produces win-win outcomes. Identifying disagreement in the risk register (A) documents but does not resolve. Meeting all stakeholders (B) broadens the discussion unnecessarily. Updating the charter to align with the sponsor (D) surrenders the PM's professional judgment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 은행의 정보 기술을 현대화하는 프로젝트를 진행하고 있다. 프로젝트 관리자는 핵심 기술 구현 방법에 대해 프로젝트 스폰서와 갈등을 겪고 있다. 프로젝트 관리자는 이 갈등을 어떻게 해결해야 하는가? | 리스크 레지스터에 의견 불일치를 식별하고 비상 계획을 개발한다. | 모든 프로젝트 이해관계자와 만나 기술 구현 방법을 식별한다. | 프로젝트 스폰서와 협상하여 상호 유익한 해결책을 개발한다. | 프로젝트 스폰서의 요구에 맞추어 프로젝트 헌장을 업데이트한다. |  | C | 기술 구현에 대해 프로젝트 스폰서와 갈등이 있을 때, 프로젝트 관리자는 상호 유익한 해결책을 개발하기 위해 협상해야 한다. 협력적 협상은 윈윈 결과를 만든다. 리스크 레지스터에 의견 불일치 식별(A)은 문서화하지만 해결하지 않는다. 모든 이해관계자와 만남(B)은 논의를 불필요하게 확대한다. 스폰서에 맞추어 헌장 업데이트(D)는 PM의 전문적 판단을 포기한다.
470 | After completion of a project with specific users in various countries, the project manager's supervisor asks if the project users are satisfied with the way the project was run. What two actions should the project manager take? (Choose two) | Obtain official approval on the new process from the various countries | Send a questionnaire to the project participants and seek their feedback. | Prepare the lessons learned from the project phase. | Refer to the communications management plan | Deliver the project materials to the users and see if they have any comments | B, D | After project completion, to assess user satisfaction the project manager should take two actions: send a questionnaire to project participants to seek their feedback (B), and refer to the communications management plan to ensure appropriate follow-up channels are used (D). Questionnaires provide structured satisfaction data, while the communications management plan guides how and when to engage stakeholders for feedback. Obtaining official approval from various countries (A) is administrative and unrelated to satisfaction measurement. Preparing lessons learned (C) captures project insights but does not directly measure user satisfaction. Delivering project materials to users (E) is a handover activity, not a satisfaction assessment method. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 여러 국가의 특정 사용자가 참여한 프로젝트 완료 후, 프로젝트 관리자의 상사가 프로젝트 사용자들이 프로젝트 운영 방식에 만족하는지 묻는다. 프로젝트 관리자는 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 여러 국가로부터 새로운 프로세스에 대한 공식 승인을 받는다. | 프로젝트 참여자에게 설문지를 보내 피드백을 구한다. | 프로젝트 단계의 교훈을 준비한다. | 커뮤니케이션 관리 계획을 참조한다. | 사용자에게 프로젝트 자료를 전달하고 의견이 있는지 확인한다. | B, D | 프로젝트 완료 후 사용자 만족도를 평가하기 위해 프로젝트 관리자는 두 가지 조치를 취해야 한다: 프로젝트 참여자에게 설문지를 보내 피드백을 구하고(B), 커뮤니케이션 관리 계획을 참조하여 적절한 후속 채널이 사용되도록 한다(D). 설문지는 구조화된 만족도 데이터를 제공하고, 커뮤니케이션 관리 계획은 이해관계자 피드백을 위한 참여 방법과 시기를 안내한다. 여러 국가에서 공식 승인(A)은 행정적이며 만족도 측정과 무관하다. 교훈 준비(C)는 프로젝트 통찰을 포착하지만 사용자 만족도를 직접 측정하지 않는다. 사용자에게 프로젝트 자료 전달(E)은 인수인계 활동이지 만족도 평가 방법이 아니다.
471 | A project manager is part of a balanced matrix project organization. The project manager will receive all work performance updates directly from the new sourcing department head who has no time to spare to give the project manager the information. What should the project manager do? | Present the situation to the manager of the sourcing department head. | Work out a resolution in consultation with the sourcing department head. | Request information directly from the sourcing department team members. | Discuss the situation with the company project sponsor for advice. |  | B | When the sourcing department head has no time to provide work performance updates in a balanced matrix organization, the project manager should work out a resolution in consultation with the department head. Collaborative negotiation in a matrix respects shared authority. Presenting the situation to the department head's manager (A) escalates prematurely. Requesting information directly from team members (C) bypasses the reporting structure. Discussing with the sponsor (D) is unnecessary for an operational issue. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | 프로젝트 관리자가 균형 매트릭스 프로젝트 조직에 속해 있다. 프로젝트 관리자는 새로운 소싱 부서장으로부터 직접 모든 작업 성과 업데이트를 받게 되는데, 부서장은 프로젝트 관리자에게 정보를 줄 시간이 없다. 프로젝트 관리자는 무엇을 해야 하는가? | 소싱 부서장의 관리자에게 상황을 제시한다. | 소싱 부서장과 협의하여 해결책을 마련한다. | 소싱 부서 팀원에게 직접 정보를 요청한다. | 회사 프로젝트 스폰서와 상황을 논의하여 조언을 구한다. |  | B | 균형 매트릭스 조직에서 소싱 부서장이 작업 성과 업데이트를 제공할 시간이 없을 때, 프로젝트 관리자는 부서장과 협의하여 해결책을 마련해야 한다. 매트릭스에서의 협력적 협상은 공유 권한을 존중한다. 부서장의 관리자에게 상황 제시(A)는 성급한 에스컬레이션이다. 팀원에게 직접 정보 요청(C)은 보고 체계를 우회한다. 스폰서와 논의(D)는 운영적 이슈에 불필요하다.
472 | In a geographically distributed team, a developer continues to delay a coding activity. This activity is on the critical path. The project manager found out that the delay is due to the developer's lack of understanding of the customer requirements shared by the off-site team. What should the project manager do? | Perform a root cause analysis (RCA) with the team members. | Replace the developer with a skilled resource. | Facilitate communication to ensure clarification of the requirements. | Conduct frequent performance reviews. |  | C | When a developer on the critical path delays coding due to misunderstanding customer requirements from an off-site team, the project manager should facilitate communication to ensure requirements clarification. Bridging the communication gap resolves the root cause. Performing RCA (A) is analytical but does not immediately resolve the delay. Replacing the developer (B) is disproportionate. Conducting performance reviews (D) addresses symptoms, not the cause. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 지리적으로 분산된 팀에서 개발자가 코딩 활동을 계속 지연시키고 있다. 이 활동은 주요 공정 경로(Critical Path)에 있다. 프로젝트 관리자는 지연이 원격 팀이 공유한 고객 요구사항에 대한 개발자의 이해 부족 때문임을 알아냈다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원과 함께 근본 원인 분석(RCA)을 수행한다. | 숙련된 자원으로 개발자를 교체한다. | 요구사항 명확화를 보장하기 위해 커뮤니케이션을 촉진한다. | 빈번한 성과 검토를 실시한다. |  | C | 주요 공정 경로의 개발자가 원격 팀의 고객 요구사항 오해로 코딩을 지연할 때, 프로젝트 관리자는 요구사항 명확화를 보장하기 위해 커뮤니케이션을 촉진해야 한다. 커뮤니케이션 격차를 해소하면 근본 원인이 해결된다. RCA 수행(A)은 분석적이지만 즉각적인 지연을 해결하지 않는다. 개발자 교체(B)는 과도한 조치이다. 성과 검토 실시(D)는 증상을 다루지 원인을 다루지 않는다.
473 | A project is in the execution phase and there are disagreements between two key stakeholders about the project's scope. One stakeholder is adamant about expanding the scope and the other stakeholder is content with the current arrangement. What should the project manager do? | Suggest that the two stakeholders meet together to agree upon a project scope. | Schedule a one-on-one discussion with each stakeholder to understand their concerns. | Escalate the stakeholder ' s conflict to senior management so they can resolve the issue. | Schedule a meeting with both stakeholders to encourage dialogue and reach a decision. |  | D | When two key stakeholders disagree about project scope during execution, the project manager should schedule a meeting with both stakeholders to encourage dialogue and reach a decision. Facilitated joint discussion promotes collaborative resolution. Suggesting the stakeholders meet alone (A) lacks PM facilitation. One-on-one discussions (B) gather information but delay resolution. Escalating to senior management (C) should be a last resort. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트가 실행 단계에 있으며 두 명의 주요 이해관계자 간에 프로젝트 범위에 대한 의견 불일치가 있다. 한 이해관계자는 범위 확장을 강력히 주장하고 다른 이해관계자는 현재 구성에 만족한다. 프로젝트 관리자는 무엇을 해야 하는가? | 두 이해관계자가 프로젝트 범위에 동의하기 위해 함께 만나도록 제안한다. | 각 이해관계자와 1:1 논의를 일정에 잡아 그들의 우려를 이해한다. | 이해관계자의 갈등을 상급 경영진에게 에스컬레이션하여 그들이 해결하도록 한다. | 두 이해관계자와 회의를 일정에 잡아 대화를 장려하고 결정에 도달하도록 한다. |  | D | 실행 중 두 주요 이해관계자가 프로젝트 범위에 대해 의견이 불일치할 때, 프로젝트 관리자는 두 이해관계자와 회의를 일정에 잡아 대화를 장려하고 결정에 도달하도록 해야 한다. 촉진된 공동 논의가 협력적 해결을 촉진한다. 이해관계자끼리 단독으로 만나도록 제안(A)하면 PM의 촉진이 부족하다. 1:1 논의(B)는 정보를 수집하지만 해결을 지연시킨다. 상급 경영진에게 에스컬레이션(C)은 최후의 수단이어야 한다.
474 | A project manager is assigned to a yearlong project. Before the start of the design phase, a competitor announces that they will release a similar deliverable in 8 months, although with fewer features and functionality. Which two actions should the project manager take next? (Choose 2) | Evaluate the impact of incremental deliverables. | Modify the project management plan with an incremental approach. | Discuss and review this external risk with the project sponsor. | Reduce the scope items of the final deliverable. | Update the project artifacts to include this issue. | D, E | When a competitor announces a similar deliverable with fewer features in 8 months during a yearlong project, the project manager should take two actions: reduce the scope items of the final deliverable to focus on essentials (D), and update the project artifacts to include this issue (E). Scope reduction enables faster delivery of core features to compete, while updating artifacts ensures the competitive threat and its impact are formally documented for governance. Evaluating incremental deliverables (A) is useful but not the immediate priority. Modifying the plan with an incremental approach (B) changes methodology rather than directly responding to the threat. Discussing with the sponsor (C) is valuable but documenting and acting on the risk takes precedence. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 프로젝트 관리자가 1년간의 프로젝트에 배정되었다. 설계 단계 시작 전에 경쟁사가 8개월 후에 기능과 기능성이 적은 유사한 산출물을 출시할 것이라고 발표했다. 프로젝트 관리자는 다음에 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 점진적 산출물의 영향을 평가한다. | 점진적 접근 방식으로 프로젝트 관리 계획을 수정한다. | 프로젝트 스폰서와 이 외부 리스크를 논의하고 검토한다. | 최종 산출물의 범위 항목을 줄인다. | 이 이슈를 포함하도록 프로젝트 산출물을 업데이트한다. | D, E | 경쟁사가 1년간의 프로젝트 중 기능이 적은 유사 산출물을 8개월 후 발표할 때, 프로젝트 관리자는 두 가지 조치를 취해야 한다: 핵심에 집중하기 위해 최종 산출물의 범위 항목을 줄이고(D), 프로젝트 산출물을 업데이트하여 이 이슈를 포함한다(E). 범위 축소는 경쟁을 위한 핵심 기능의 빠른 전달을 가능하게 하고, 산출물 업데이트는 경쟁 위협과 그 영향이 거버넌스를 위해 공식적으로 문서화되도록 한다. 점진적 산출물 평가(A)는 유용하지만 즉각적 우선순위가 아니다. 점진적 접근 방식으로 계획 수정(B)은 위협에 직접 대응하기보다 방법론을 변경한다. 스폰서와 논의(C)는 가치 있지만 리스크 문서화와 조치가 우선이다.
475 | A project manager has been assigned to deliver a challenging project on time and within budget. The project manager needs to empower the team members by removing organizational impediments and facilitating collaboration. What should the project manager do to lead the project? | Assume the functional manager role. | Act as the project owner. | Use a servant leader approach. | Perform the project sponsor activities. |  | C | When the project manager needs to empower team members by removing organizational impediments and facilitating collaboration, they should use a servant leader approach. Servant leadership prioritizes team growth, removes barriers, and fosters high performance. Assuming the functional manager role (A) oversteps boundaries. Acting as project owner (B) confuses roles. Performing sponsor activities (D) is not the PM's responsibility. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 도전적인 프로젝트를 기한 내에 예산 범위 내에서 전달하도록 배정되었다. 프로젝트 관리자는 조직적 장애물을 제거하고 협업을 촉진하여 팀원들에게 권한을 부여해야 한다. 프로젝트 관리자는 프로젝트를 이끌기 위해 무엇을 해야 하는가? | 기능 관리자 역할을 맡는다. | 프로젝트 소유자로 활동한다. | 서번트 리더 접근 방식을 사용한다. | 프로젝트 스폰서 활동을 수행한다. |  | C | 프로젝트 관리자가 조직적 장애물을 제거하고 협업을 촉진하여 팀원들에게 권한을 부여해야 할 때, 서번트 리더 접근 방식을 사용해야 한다. 서번트 리더십은 팀 성장을 우선시하고 장벽을 제거하며 높은 성과를 촉진한다. 기능 관리자 역할 맡기(A)는 경계를 넘는다. 프로젝트 소유자로 활동(B)은 역할을 혼동시킨다. 스폰서 활동 수행(D)은 PM의 책임이 아니다.
476 | An IT team has reached out to the project manager for guidance on which communication method to use when system downtime will impact the resources working on the project. Which two communication methods should the project manager recommend? (Choose 2) | Communicate via the project team ' s document management site. | Communicate in the IT risk forum. | Communicate via instant messaging. | Communicate via email to the project ' s email distribution group. | Communicate verbally to the key project stakeholders. | D, E | When system downtime will impact project resources, the IT team should use two communication methods: communicate via email to the project's email distribution group (D) to ensure broad, documented notification to all affected parties, and communicate verbally to the key project stakeholders (E) to provide immediate, direct awareness to critical decision-makers. Email provides a formal record and reaches all team members, while verbal communication ensures urgency is conveyed to key stakeholders who may need to take immediate action. The document management site (A) is for document storage, not urgent notifications. The IT risk forum (B) is for risk discussions, not operational notifications. Instant messaging (C) may not reach all stakeholders and lacks formality. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | IT 팀이 시스템 다운타임이 프로젝트에 작업 중인 자원에 영향을 미칠 때 어떤 커뮤니케이션 방법을 사용해야 하는지 프로젝트 관리자에게 안내를 요청했다. 프로젝트 관리자는 어떤 두 가지 커뮤니케이션 방법을 권장해야 하는가? (2개 선택) | 프로젝트 팀의 문서 관리 사이트를 통해 커뮤니케이션한다. | IT 리스크 포럼에서 커뮤니케이션한다. | 인스턴트 메시징을 통해 커뮤니케이션한다. | 프로젝트의 이메일 배포 그룹으로 이메일을 통해 커뮤니케이션한다. | 주요 프로젝트 이해관계자에게 구두로 커뮤니케이션한다. | D, E | 시스템 다운타임이 프로젝트 자원에 영향을 미칠 때, IT 팀은 두 가지 커뮤니케이션 방법을 사용해야 한다: 프로젝트 이메일 배포 그룹으로 이메일 커뮤니케이션(D)하여 모든 영향을 받는 당사자에게 광범위하고 문서화된 알림을 보장하고, 주요 프로젝트 이해관계자에게 구두로 커뮤니케이션(E)하여 즉각적인 조치가 필요할 수 있는 핵심 의사결정자에게 즉시 직접적인 인식을 제공한다. 이메일은 공식 기록을 제공하고 모든 팀원에게 도달하며, 구두 커뮤니케이션은 긴급성을 전달한다. 문서 관리 사이트(A)는 문서 저장용이지 긴급 알림용이 아니다. IT 리스크 포럼(B)은 리스크 논의용이지 운영 알림용이 아니다. 인스턴트 메시징(C)은 모든 이해관계자에게 도달하지 못할 수 있고 공식성이 부족하다.
477 | In the planning phase, a project manager receives identified risks from the sponsors and subject matter experts (SMEs) and wants to develop a risk response strategy for them. What should the project manager do first? | Assign allocated budget to cover key risks. | Assign a risk responsibility to each team member. | Perform a risk reserve analysis. | Agree on the criteria to prioritize risks. |  | D | Before developing risk response strategies for identified risks from sponsors and SMEs, the project manager should first agree on the criteria to prioritize risks. Not all risks have equal impact or probability, so establishing prioritization criteria—such as expected monetary value, risk score, urgency, or stakeholder tolerance—enables focused resource allocation. Assigning budget to cover key risks (A) is premature without prioritization. Assigning risk responsibility to team members (B) distributes ownership without determining which risks matter most. Performing risk reserve analysis (C) addresses budget, not prioritization criteria. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 계획 단계에서 프로젝트 관리자가 스폰서와 주제 전문가(SME)로부터 식별된 리스크를 받고 이에 대한 리스크 대응 전략을 개발하고자 한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 주요 리스크를 커버하기 위해 할당된 예산을 배정한다. | 각 팀원에게 리스크 책임을 배정한다. | 리스크 예비비 분석을 수행한다. | 리스크 우선순위화 기준에 합의한다. |  | D | 스폰서와 SME로부터 식별된 리스크에 대한 리스크 대응 전략을 개발하기 전에, 프로젝트 관리자는 먼저 리스크 우선순위화 기준에 합의해야 한다. 모든 리스크가 동일한 영향이나 확률을 가지지 않으므로, 기대 화폐 가치, 리스크 점수, 긴급성, 이해관계자 허용 범위 등의 우선순위화 기준을 수립하면 집중적인 자원 배분이 가능해진다. 주요 리스크를 위한 예산 배정(A)은 우선순위화 없이 시기상조이다. 팀원에게 리스크 책임 배정(B)은 어떤 리스크가 가장 중요한지 결정하지 않고 소유권을 분배한다. 리스크 예비비 분석 수행(C)은 예산을 다루지 우선순위화 기준은 다루지 않는다.
478 | A company has been following a predictive approach and always waits for the preceding phase to be completed before evaluating the quality of their products. A new project manager with experience in hybrid approaches has been assigned to help increase the efficiency of the company's quality management process. What should the new project manager do to address the process improvements? | Discuss the process improvement with the project management office (PMO) lead to update the project delivery framework | Continue with the process as is. and wait until the next phase to suggest any improvements | Define a ground rule to comply with the quality standard and ask the team members to apply it. | Understand the context and interdependencies of the process from the team members and then define improvements |  | D | When assigned to improve a company's quality management process that currently uses a sequential, end-of-phase approach, the new project manager should understand the context and interdependencies of the process from team members and then define improvements. This leverages the team's frontline expertise and ensures improvements are grounded in actual process realities. Discussing with the PMO lead to update the framework (A) starts at the organizational level without first understanding the current process. Continuing as-is (B) ignores the improvement mandate. Defining a ground rule for quality compliance (C) imposes standards without understanding the underlying process challenges. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Hybrid/Tailoring | 회사가 예측적 접근 방식을 따르고 있으며 항상 선행 단계가 완료될 때까지 기다린 후에 제품 품질을 평가한다. 하이브리드 접근 방식에 경험이 있는 새로운 프로젝트 관리자가 회사의 품질 관리 프로세스 효율성을 높이기 위해 배정되었다. 새 프로젝트 관리자는 프로세스 개선을 해결하기 위해 무엇을 해야 하는가? | 프로젝트 관리 오피스(PMO) 리드와 프로세스 개선을 논의하여 프로젝트 전달 프레임워크를 업데이트한다. | 현재 프로세스를 그대로 유지하고 다음 단계까지 기다려 개선 사항을 제안한다. | 품질 기준을 준수하기 위한 기본 규칙을 정의하고 팀원들에게 적용하도록 요청한다. | 팀원들로부터 프로세스의 맥락과 상호의존성을 이해한 후 개선 사항을 정의한다. |  | D | 현재 순차적이고 단계 말 접근 방식을 사용하는 회사의 품질 관리 프로세스를 개선하도록 배정되었을 때, 새 프로젝트 관리자는 팀원들로부터 프로세스의 맥락과 상호의존성을 이해한 후 개선 사항을 정의해야 한다. 이는 팀의 현장 전문성을 활용하고 개선이 실제 프로세스 현실에 기반하도록 보장한다. PMO 리드와 프레임워크 업데이트 논의(A)는 현재 프로세스를 먼저 이해하지 않고 조직 수준에서 시작한다. 현재대로 유지(B)는 개선 의무를 무시한다. 품질 준수를 위한 기본 규칙 정의(C)는 근본적인 프로세스 도전을 이해하지 않고 기준을 부과한다.
479 | During the retrospective ceremony, the agile team is talking about the product owner's expectations not being met. What should the project manager have done at the beginning of the project? | Defined the expected agile team contribution in the creation of the backlog. | Defined the team ground rules and shared project vision. | Assessed the capabilities of the agile team and planned for the required training | Communicated project vision and sprint goals clearly to the team |  | B | When the retrospective reveals the product owner's expectations are not being met, the project manager should have defined the team ground rules and shared the project vision at the beginning. Clear vision and norms align expectations. Defining expected backlog contribution (A) is procedural. Assessing capabilities and planning training (C) addresses skills, not expectations. Communicating sprint goals (D) is ongoing but does not establish foundational alignment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 회고 의식에서 애자일 팀이 제품 책임자의 기대가 충족되지 않고 있다고 이야기하고 있다. 프로젝트 관리자는 프로젝트 초기에 무엇을 했어야 하는가? | 백로그 생성에 대한 애자일 팀의 예상 기여를 정의했어야 한다. | 팀 기본 규칙을 정의하고 프로젝트 비전을 공유했어야 한다. | 애자일 팀의 역량을 평가하고 필요한 교육을 계획했어야 한다. | 프로젝트 비전과 스프린트 목표를 팀에게 명확하게 전달했어야 한다. |  | B | 회고에서 제품 책임자의 기대가 충족되지 않고 있음이 밝혀졌을 때, 프로젝트 관리자는 초기에 팀 기본 규칙을 정의하고 프로젝트 비전을 공유했어야 한다. 명확한 비전과 규범이 기대를 정렬시킨다. 백로그 기여 정의(A)는 절차적이다. 역량 평가 및 교육 계획(C)은 기술을 다루지 기대는 다루지 않는다. 스프린트 목표 전달(D)은 지속적이지만 기초적인 정렬을 수립하지 않는다.
480 | A project manager is leading a project that needs to be launched quickly to the market. An influential stakeholder does not believe that the project management processes deliver business value. What can the project manager do to gain the stakeholder's support? | Ask the stakeholder for a meeting to review the project ' s charter and project management plan. | Clarify the project roles and responsibilities, and share the purpose to gain the stakeholder ' s buy-in. | Disregard the stakeholder ' s concerns and continue following the project management plan to execute the project. | Hold a training workshop to educate the stakeholder about project management best practices. |  | B | To win over an influential stakeholder who doubts the value of project management processes, the PM should clarify project roles, responsibilities, and the purpose behind each process. This direct approach aligns the stakeholder's understanding with project objectives and shows how structured processes contribute to project success. Engaging stakeholders through transparent communication and collaborative dialogue is more likely to secure their buy-in than bypassing their concerns or escalating the issue. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 관리자가 시장에 빠르게 출시해야 하는 프로젝트를 이끌고 있다. 영향력 있는 이해관계자가 프로젝트 관리 프로세스가 비즈니스 가치를 전달하지 못한다고 생각한다. 프로젝트 관리자는 이해관계자의 지지를 얻기 위해 무엇을 할 수 있는가? | 이해관계자에게 프로젝트 헌장과 프로젝트 관리 계획을 검토하기 위한 회의를 요청한다. | 프로젝트 역할과 책임을 명확히 하고, 이해관계자의 동의를 얻기 위해 목적을 공유한다. | 이해관계자의 우려를 무시하고 프로젝트 관리 계획에 따라 프로젝트를 실행한다. | 프로젝트 관리 모범 사례에 대해 이해관계자를 교육하기 위한 교육 워크숍을 개최한다. |  | B | 프로젝트 관리 프로세스의 가치를 의심하는 영향력 있는 이해관계자를 설득하기 위해, PM은 프로젝트 역할, 책임, 그리고 각 프로세스의 목적을 명확히 해야 한다. 이 직접적인 접근 방식은 이해관계자의 이해를 프로젝트 목표와 정렬시키고 구조화된 프로세스가 프로젝트 성공에 어떻게 기여하는지 보여준다. 투명한 커뮤니케이션과 협력적 대화를 통한 이해관계자 참여가 우려를 우회하거나 이슈를 에스컬레이션하는 것보다 동의를 확보할 가능성이 높다.
481 | A project manager has just been assigned a major, ongoing project. The project team is not working in harmony and their performance is decreasing. Some team members are autocratic in their approach whereas others are in avoidance mode. How should the project manager proceed? | Appeal for cooperation from all of the team members, emphasizing the benefit of the project outcome to the company. | Assess the various team behaviors through the use of personality indicators to appropriately deal with each personality type. | Emphasize their autonomy as project manager, implying that they will not allow team disunity. | Request for removal of the autocratic members who obviously are not interested in the project. |  | B | When the project team exhibits mixed dysfunctional behaviors—autocratic and avoidant—the project manager should assess team behaviors through personality indicators to appropriately deal with each personality type. Understanding behavioral styles enables tailored leadership and conflict resolution. Appealing for cooperation (A) is motivational but not diagnostic. Emphasizing authority (C) is authoritarian. Requesting removal of autocratic members (D) is extreme without first understanding and addressing the dynamics. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Hybrid/Tailoring | 프로젝트 관리자가 주요 진행 중인 프로젝트에 방금 배정되었다. 프로젝트 팀이 조화롭게 일하지 않고 성과가 저하되고 있다. 일부 팀원은 독재적인 접근 방식을 취하고 다른 팀원은 회피 모드에 있다. 프로젝트 관리자는 어떻게 진행해야 하는가? | 프로젝트 결과가 회사에 미치는 혜택을 강조하며 모든 팀원에게 협력을 호소한다. | 각 성격 유형에 적절히 대처하기 위해 성격 지표를 사용하여 다양한 팀 행동을 평가한다. | 프로젝트 관리자로서의 자율성을 강조하며, 팀 불화를 허용하지 않을 것임을 암시한다. | 프로젝트에 관심이 없는 것이 분명한 독재적 팀원의 제거를 요청한다. |  | B | 프로젝트 팀이 독재적 행동과 회피적 행동이 혼재된 기능 장애를 보일 때, 프로젝트 관리자는 각 성격 유형에 적절히 대처하기 위해 성격 지표를 통해 팀 행동을 평가해야 한다. 행동 스타일을 이해하면 맞춤화된 리더십과 갈등 해결이 가능해진다. 협력 호소(A)는 동기 부여적이지만 진단적이지 않다. 권한 강조(C)는 권위주의적이다. 독재적 팀원 제거 요청(D)은 역학을 먼저 이해하고 다루지 않고 극단적이다.
482 | In an agile project, some stakeholders are asking to have a meeting with the team every 2 weeks in order to understand project progress. What should the project lead do next? | Hold a meeting every 2 weeks with the stakeholders. | Negotiate by sending an informative email to stakeholders. | Invite the stakeholders to the sprint review meetings. | Invite the stakeholders to the retrospective meetings. |  | C | When stakeholders want biweekly meetings to understand project progress in an agile project, the project lead should invite them to the sprint review meetings. Sprint reviews demonstrate completed work and gather feedback, aligning with stakeholder needs. Holding separate biweekly meetings (A) duplicates effort. Sending informative emails (B) is one-way and lacks engagement. Inviting to retrospectives (D) exposes internal team processes, not progress. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 프로젝트에서 일부 이해관계자가 프로젝트 진행 상황을 이해하기 위해 2주마다 팀과 회의를 갖고 싶어 한다. 프로젝트 리더는 다음에 무엇을 해야 하는가? | 이해관계자와 2주마다 회의를 개최한다. | 이해관계자에게 정보성 이메일을 보내어 협상한다. | 이해관계자를 스프린트 리뷰 회의에 초대한다. | 이해관계자를 회고 회의에 초대한다. |  | C | 애자일 프로젝트에서 이해관계자가 프로젝트 진행 상황을 이해하기 위해 격주 회의를 원할 때, 프로젝트 리더는 이해관계자를 스프린트 리뷰 회의에 초대해야 한다. 스프린트 리뷰는 완료된 작업을 시연하고 피드백을 수집하여 이해관계자의 필요에 부합한다. 별도의 격주 회의 개최(A)는 노력을 중복시킨다. 정보성 이메일 발송(B)은 단방향이며 참여가 부족하다. 회고에 초대(D)는 내부 팀 프로세스를 노출시키지 진행 상황을 보여주지 않는다.
483 | A company is going through structural changes. A couple of people will leave the company as their positions were made redundant. The team members are unhappy as they do not understand why the changes are being made when the project is on track. What should the project manager do? | Organize a team meeting to discuss the changes and their importance for the company. | Advise the team to continue their work as planned because the schedule cannot be changed. | Inform the project sponsor about the team ' s unhappiness and ask for overtime pay. | Advise the team that the changes were decided by the CEO and must be implemented. |  | A | When the team is unhappy about structural changes making positions redundant while the project is on track, the project manager should organize a team meeting to discuss the changes and their importance. Transparent communication addresses concerns. Advising to continue as planned (B) ignores morale. Informing the sponsor about unhappiness and asking for overtime pay (C) is misdirected. Saying changes were decided by the CEO (D) is dismissive. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 회사가 구조적 변경을 진행 중이다. 몇 명의 직원이 직위가 불필요해져 회사를 떠나게 된다. 팀원들은 프로젝트가 순조롭게 진행되고 있는데 왜 변경이 이루어지는지 이해하지 못해 불만이다. 프로젝트 관리자는 무엇을 해야 하는가? | 변경 사항과 회사에 대한 중요성을 논의하기 위해 팀 회의를 조직한다. | 일정이 변경될 수 없으므로 계획대로 작업을 계속하도록 팀에 조언한다. | 프로젝트 스폰서에게 팀의 불만을 알리고 초과 근무 수당을 요청한다. | 변경 사항은 CEO가 결정한 것이며 반드시 실행되어야 한다고 팀에 조언한다. |  | A | 프로젝트가 순조롭게 진행 중인데 구조적 변경으로 직위가 불필요해져 팀이 불만일 때, 프로젝트 관리자는 변경 사항과 그 중요성을 논의하기 위해 팀 회의를 조직해야 한다. 투명한 커뮤니케이션이 우려를 해결한다. 계획대로 계속하도록 조언(B)은 사기를 무시한다. 스폰서에게 불만을 알리고 초과 근무 수당 요청(C)은 방향이 잘못되었다. CEO가 결정했다고 말하는 것(D)은 경시하는 것이다.
484 | A project manager is in the middle of a project when one of the key project team members needs to take an unexpected and prolonged leave of absence. The project is ahead of schedule and running under budget. Which two actions should the project manager take initially to resolve this problem? (Choose two) | Check the risk register for a prepared response to a resource being suddenly unavailable. | Reassign responsibilities across the remaining members using the available float for training. | Check the project ' s responsibility assignment matrix (RAM) to determine which activities will be affected | Check if the team member ' s activities are sufficiently documented to facilitate handover | Obtain the project sponsors support to replace the team member on leave | A, E | When a key team member takes unexpected prolonged leave while the project is ahead of schedule and under budget, the project manager should initially take two actions: check the risk register for a prepared response to sudden resource unavailability (A), and obtain the project sponsor's support to replace the team member on leave (E). The risk register provides a pre-planned contingency response, while sponsor support enables timely replacement of the critical resource. Reassigning responsibilities using available float (B) may work but lacks strategic risk response. Checking the RAM (C) clarifies responsibilities but does not solve the resource gap. Checking if activities are sufficiently documented (D) supports handover but is not an immediate priority compared to securing a replacement. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 프로젝트 중간에 핵심 프로젝트 팀원 중 한 명이 예상치 못한 장기 휴가를 가야 할 상황이다. 프로젝트는 일정보다 앞서 있고 예산 미만으로 진행 중이다. 프로젝트 관리자가 이 문제를 해결하기 위해 처음에 취해야 할 두 가지 조치는? (2개 선택) | 자원이 갑자기 사용 불가능해지는 상황에 대한 준비된 대응을 위해 리스크 레지스터를 확인한다. | 교육을 위한 가용 여유 시간을 활용하여 나머지 팀원들에게 책임을 재배정한다. | 어떤 활동이 영향을 받는지 확인하기 위해 프로젝트의 책임 배정 매트릭스(RAM)를 확인한다. | 인수인계를 용이하게 하기 위해 팀원의 활동이 충분히 문서화되어 있는지 확인한다. | 휴가 중인 팀원을 교체하기 위해 프로젝트 스폰서의 지원을 받는다. | A, E | 핵심 팀원이 프로젝트가 일정 및 예산보다 앞서는 상황에서 예기치 않게 장기 휴가를 갈 때, PM은 처음에 두 가지 조치를 취해야 한다: 갑작스러운 자원 부재에 대한 준비된 대응을 위해 리스크 레지스터를 확인하고(A), 휴가 중인 팀원을 대체하기 위해 프로젝트 스폰서의 지원을 받는다(E). 리스크 레지스터는 사전 계획된 비상 대응을 제공하고, 스폰서 지원은 핵심 자원의 적시 대체를 가능하게 한다. 가용 여유를 사용한 책임 재할당(B)은 가능하지만 전략적 리스크 대응이 부족하다. RAM 확인(C)은 책임을 명확히 하지만 자원 격차를 해결하지 않는다. 활동 문서화 확인(D)은 인수인계를 지원하지만 대체 확보보다 즉각적 우선순위가 아니다.
485 | A new team member is hired and the training is taking longer than expected. This impacts the overall project performance. What immediate action should the project manager take to improve the situation? | Update the issue log and define the mitigation strategy. | Increase team cohesiveness by sharing information and experiences openly. | Communicate this issue to the human resources department. | Provide additional training to the new hire. |  | A | When a new team member's training takes longer than expected and impacts project performance, the project manager should immediately update the issue log and define a mitigation strategy. Documenting and planning response enables structured resolution. Communicating to HR (C) is a follow-up, not the immediate action. Providing additional training (D) may be part of mitigation. Increasing team cohesiveness (B) does not directly address the training delay. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Traditional PM | 새 팀원이 고용되었고 교육이 예상보다 오래 걸리고 있다. 이는 전체 프로젝트 성과에 영향을 미친다. 프로젝트 관리자가 상황을 개선하기 위해 취해야 할 즉각적인 조치는? | 이슈 로그를 업데이트하고 완화 전략을 정의한다. | 정보와 경험을 공개적으로 공유하여 팀 결속력을 높인다. | 이 이슈를 인사부에 전달한다. | 새 직원에게 추가 교육을 제공한다. |  | A | 새 팀원의 교육이 예상보다 오래 걸리고 프로젝트 성과에 영향을 미칠 때, 프로젝트 관리자는 즉시 이슈 로그를 업데이트하고 완화 전략을 정의해야 한다. 문서화와 대응 계획 수립이 구조화된 해결을 가능하게 한다. 인사부에 전달(C)은 후속 조치이지 즉각적인 조치가 아니다. 추가 교육 제공(D)은 완화의 일부일 수 있다. 팀 결속력 향상(B)은 교육 지연을 직접 해결하지 않는다.
486 | A new facility project is being developed using a hybrid approach. After the third iteration, the project manager sees a decline in the team's productivity. What should the project manager do next? | Reduce the iteration backlog. | Review the iteration duration with the team. | Encourage the team to improve their performance. | Discuss the issue in the next retrospective. |  | D | When team productivity declines after the third iteration in a hybrid project, the project manager should discuss the issue in the next retrospective. Retrospectives enable the team to collectively identify causes and develop improvement solutions. Reducing the iteration backlog (A) treats the symptom. Reviewing iteration duration (B) may help but is more structural. Encouraging better performance (C) is vague and non-actionable. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Hybrid/Tailoring | 새로운 시설 프로젝트가 하이브리드 접근 방식을 사용하여 개발되고 있다. 세 번째 반복 후 프로젝트 관리자가 팀 생산성의 감소를 발견한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 반복 백로그를 줄인다. | 팀과 반복 기간을 검토한다. | 팀에게 성과를 개선하도록 격려한다. | 다음 회고에서 이슈를 논의한다. |  | D | 하이브리드 프로젝트에서 세 번째 반복 후 팀 생산성이 감소할 때, 프로젝트 관리자는 다음 회고에서 이슈를 논의해야 한다. 회고는 팀이 원인을 집단적으로 식별하고 개선 솔루션을 개발할 수 있게 한다. 반복 백로그 줄이기(A)는 증상을 치료한다. 반복 기간 검토(B)는 도움이 될 수 있지만 더 구조적이다. 더 나은 성과를 격려(C)는 모호하고 실행 불가능하다.
487 | At the end of planning a new project, the project manager needs to schedule the kick-off meeting but is having difficulty finding a common time slot when all necessary stakeholders can be available onsite. How should the project manager proceed to schedule the kick-off meeting? | Schedule a virtual meeting so onsite and remote stakeholders can attend at the same time. | Run separate meetings to accommodate everyone ' s schedule. | Wait for a date when all required attendees can be available onsite. | Email all stakeholders with the objectives of the project and ask for feedback. |  | A | When unable to find a common onsite time for all stakeholders for the kick-off meeting, the project manager should schedule a virtual meeting so onsite and remote stakeholders can attend simultaneously. Virtual meetings enable efficient, inclusive participation. Running separate meetings (B) creates inconsistencies. Waiting for full availability (C) causes unnecessary delays. Emailing objectives and requesting feedback (D) lacks interactive engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 새 프로젝트 계획 마무리 시 프로젝트 관리자가 킥오프 미팅을 예약해야 하지만, 모든 필요한 이해관계자가 현장에서 참석할 수 있는 공통 시간대를 찾기 어렵다. 프로젝트 관리자는 킥오프 미팅을 어떻게 예약해야 하는가? | 현장 및 원격 이해관계자가 동시에 참석할 수 있도록 가상 회의를 예약한다. | 모든 사람의 일정을 수용하기 위해 별도의 회의를 운영한다. | 모든 필수 참석자가 현장에서 참석할 수 있는 날짜를 기다린다. | 모든 이해관계자에게 프로젝트 목표를 이메일로 보내고 피드백을 요청한다. |  | A | 킥오프 미팅을 위해 모든 이해관계자의 현장 공통 시간을 찾을 수 없을 때, 프로젝트 관리자는 현장 및 원격 이해관계자가 동시에 참석할 수 있도록 가상 회의를 예약해야 한다. 가상 회의는 효율적이고 포용적인 참여를 가능하게 한다. 별도 회의 운영(B)은 불일치를 만든다. 전원 참석 가능일 대기(C)는 불필요한 지연을 초래한다. 목표를 이메일로 보내고 피드백 요청(D)은 상호작용적 참여가 부족하다.
488 | An information technology (IT) team is responsible for the validation and release of a product developed by the agile development team. Due to other priorities for the IT team, the releases are delayed. What action should the project manager take? | Escalate the issue from the IT team to management and get the validation prioritized | Work with the IT team to prioritize the validation and release of the new features | Deliver the features when the IT team is able to validate them | Request the IT team to immediately release the product and then validate the features |  | B | When the IT team's other priorities delay validation and release of agile team deliverables, the project manager should work with the IT team to prioritize the validation and release of new features. Collaborative prioritization promotes teamwork and addresses the bottleneck constructively. Escalating to management (A) may create tension before attempting collaboration. Delivering features when IT is available (C) accepts the delay passively. Requesting immediate release without validation (D) compromises quality. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Schedule | Planning | Build an Empowered Culture | Define Activities | Traditional PM | 정보 기술(IT) 팀이 애자일 개발 팀이 개발한 제품의 검증 및 릴리스를 담당하고 있다. IT 팀의 다른 우선순위로 인해 릴리스가 지연되고 있다. 프로젝트 관리자는 어떤 조치를 취해야 하는가? | IT 팀의 이슈를 경영진에 에스컬레이션하고 검증 우선순위를 높인다. | IT 팀과 협력하여 새로운 기능의 검증 및 릴리스 우선순위를 정한다. | IT 팀이 검증할 수 있을 때 기능을 전달한다. | IT 팀에 제품을 즉시 릴리스한 후 기능을 검증하도록 요청한다. |  | B | IT 팀의 다른 우선순위로 애자일 팀 산출물의 검증과 릴리스가 지연될 때, 프로젝트 관리자는 IT 팀과 협력하여 새 기능의 검증과 릴리스 우선순위를 정해야 한다. 협력적 우선순위화는 팀워크를 촉진하고 병목을 건설적으로 해결한다. 경영진에 에스컬레이션(A)은 협력 시도 전에 긴장을 만들 수 있다. IT가 가능할 때 기능 전달(C)은 지연을 수동적으로 수용한다. 검증 없이 즉시 릴리스 요청(D)은 품질을 저해한다.
489 | A company that is introducing a new product into the market by the end of the year requires a storage and distribution facility to be built. During the monthly stakeholder meeting, it is discovered that the location for implementation is a government-owned area. What should the project manager do first? | Issue a change request | Identify an alternative site. | Update the issue log | Update the risk register. |  | C | The PM should first identify and document the government land ownership issue in the issue log. An issue log captures matters requiring discussion or resolution and helps monitor their status. Documenting the issue enables proper tracking, stakeholder communication, and resolution planning. Alternative site identification, change requests, or risk register updates may follow depending on the issue's analysis, impact, and urgency—but formal documentation comes first. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 연말까지 새 제품을 시장에 출시해야 하는 회사가 보관 및 유통 시설을 건설해야 한다. 월간 이해관계자 회의에서 구현 예정 위치가 정부 소유 지역임이 발견되었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 변경 요청을 발행한다. | 대안 부지를 식별한다. | 이슈 로그를 업데이트한다. | 리스크 레지스터를 업데이트한다. |  | C | PM은 먼저 정부 토지 소유권 이슈를 이슈 로그에 식별하고 문서화해야 한다. 이슈 로그는 논의 또는 해결이 필요한 사안을 포착하고 상태를 모니터링하는 데 도움이 된다. 이슈를 문서화하면 적절한 추적, 이해관계자 소통, 해결 계획이 가능해진다. 대안 부지 식별, 변경 요청, 리스크 레지스터 업데이트는 이슈의 분석, 영향, 긴급성에 따라 후속될 수 있지만—공식 문서화가 먼저이다.
490 | A project manager is managing a hybrid project. During project execution, the project manager was informed that over half of the project budget was reallocated to a project that is handling an emergency that recently occurred. What should the project manager do? | Meet with the project team and reprioritize the backlog | Meet with the product owner to confirm the minimum viable product (MVP) option | Meet with the technical lead to review the sprint plan | Meet with the project sponsor to explain that the project cannot be completed as planned 1253 |  | B | When over half the budget is reallocated to an emergency project mid-execution of a hybrid project, the project manager should meet with the product owner to confirm the minimum viable product option. MVP focuses remaining budget on essential value. Meeting the team to reprioritize the backlog (A) is useful but needs PO alignment first. Reviewing the sprint plan with the tech lead (C) is too narrow. Explaining to the sponsor (D) without offering solutions is passive. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Scope | Planning | Focus on Value | Collect Requirements | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 프로젝트를 관리하고 있다. 프로젝트 실행 중 프로젝트 예산의 절반 이상이 최근 발생한 비상 상황을 처리하는 프로젝트에 재배정되었다고 통보받았다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 팀과 만나 백로그를 재우선순위화한다. | 제품 책임자와 만나 최소 기능 제품(MVP) 옵션을 확인한다. | 기술 리더와 만나 스프린트 계획을 검토한다. | 프로젝트 스폰서와 만나 프로젝트가 계획대로 완료될 수 없음을 설명한다. |  | B | 하이브리드 프로젝트 실행 중 예산의 절반 이상이 비상 프로젝트에 재배정될 때, 프로젝트 관리자는 제품 책임자와 만나 MVP 옵션을 확인해야 한다. MVP는 남은 예산을 핵심 가치에 집중시킨다. 팀과 백로그 재우선순위화(A)는 유용하지만 PO와의 정렬이 먼저 필요하다. 기술 리더와 스프린트 계획 검토(C)는 범위가 좁다. 스폰서에게 설명(D)은 해결책을 제시하지 않아 수동적이다.
491 | An iteration is almost finished, but the team is struggling to complete the stories that require more time. What should the project manager do first? | Request approval from the project sponsor to add more resources, | Update the project artifacts to reflect the new deadlines reported. 1026 | Meet with the project team to develop a proper resolution to the issue. | Prepare documentation to explain the issue and communicate accordingly. |  | C | When an iteration is almost finished but the team struggles to complete stories requiring more time, the project manager should first meet with the project team to develop a proper resolution. Collaborative problem-solving addresses root causes. Requesting more resources from the sponsor (A) may not address the real issue. Updating artifacts with new deadlines (B) accepts delay without resolution. Preparing documentation to explain (D) communicates but does not solve. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 반복이 거의 끝나가지만 팀이 더 많은 시간이 필요한 스토리를 완료하는 데 어려움을 겪고 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 더 많은 자원을 추가하기 위해 프로젝트 스폰서의 승인을 요청한다. | 보고된 새 마감일을 반영하도록 프로젝트 산출물을 업데이트한다. | 프로젝트 팀과 만나 이슈에 대한 적절한 해결책을 개발한다. | 이슈를 설명하고 적절히 소통하기 위한 문서를 준비한다. |  | C | 반복이 거의 끝나가지만 팀이 더 많은 시간이 필요한 스토리를 완료하는 데 어려움을 겪을 때, 프로젝트 관리자는 먼저 프로젝트 팀과 만나 적절한 해결책을 개발해야 한다. 협력적 문제 해결이 근본 원인을 다룬다. 스폰서에게 자원 추가 요청(A)은 실제 문제를 해결하지 못할 수 있다. 새 마감일로 산출물 업데이트(B)는 해결 없이 지연을 수용한다. 설명을 위한 문서 준비(D)는 소통하지만 해결하지 않는다.
492 | A project is almost complete when a key stakeholder raises a concern because the functionality of their preferred requirement was not showcased in the prototype. The prototype has already been approved, and the developers have started work on the final application. What should the project manager do next? | Document the stakeholder's requirements and validate those requirements by engaging stakeholders more often. | Inform the stakeholder that the requirement will be included in the next deliverable cycle. | Be firm with the stakeholder, since they would push through any unreasonable requirement. | Inform the stakeholder that little can be done at this time, since core development has begun and the project must be delivered on time. |  | B | When a key stakeholder raises a concern that their preferred requirement was not in the approved prototype and development has started, the project manager should inform the stakeholder that the requirement will be included in the next deliverable cycle. This balances stakeholder value with project stability. Documenting and validating requirements more often (A) is a future-oriented lesson. Being firm about unreasonable requirements (C) is confrontational. Informing them nothing can be done (D) damages the relationship. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트가 거의 완료될 때 핵심 이해관계자가 자신이 선호하는 요구사항의 기능이 프로토타입에서 보여지지 않았다고 우려를 제기한다. 프로토타입은 이미 승인되었고, 개발자들은 최종 애플리케이션 작업을 시작했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 이해관계자의 요구사항을 문서화하고 이해관계자를 더 자주 참여시켜 요구사항을 검증한다. | 이해관계자에게 해당 요구사항이 다음 전달 주기에 포함될 것임을 알린다. | 이해관계자에게 단호하게 대응한다. 비합리적인 요구사항을 밀어붙일 수 있기 때문이다. | 이해관계자에게 핵심 개발이 시작되었고 프로젝트가 제시간에 전달되어야 하므로 현재 시점에서 할 수 있는 것이 거의 없다고 알린다. |  | B | 핵심 이해관계자가 승인된 프로토타입에 자신이 선호하는 요구사항이 없었고 개발이 시작되었다고 우려를 제기할 때, 프로젝트 관리자는 이해관계자에게 해당 요구사항이 다음 전달 주기에 포함될 것임을 알려야 한다. 이는 이해관계자 가치와 프로젝트 안정성의 균형을 맞춘다. 요구사항을 더 자주 문서화하고 검증(A)은 미래 지향적 교훈이다. 비합리적 요구사항에 단호하게 대응(C)은 대립적이다. 할 수 있는 것이 없다고 알림(D)은 관계를 손상시킨다.
493 | A new solution is being deployed in countries A, B, and C. This solution will allow the countries to propose new services to their customers. Country A has asked for a change in the solution in order to comply with its own customer market. What should the project manager in charge of the deployment in country A do? | Accept the change request from country A and reschedule the deployment project for 151 country A. | Take the request into account and ask the sponsor to inform countries B and C about the change | Refuse country As request as there is no time for the change as deployment has already begun | Ask country A to submit a change request that will be analyzed along with countries B and C |  | D | When a stakeholder requests a change to a multi-country solution, the PM should ask them to submit a formal change request through the integrated change control process. This ensures proper documentation, evaluation, and approval or rejection by the CCB. It also allows assessment of impacts on the project's scope, time, and cost constraints across all affected countries. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Finance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 새로운 솔루션이 A, B, C 국가에 배치되고 있다. 이 솔루션은 국가들이 고객에게 새로운 서비스를 제안할 수 있게 해준다. A 국가가 자체 고객 시장을 준수하기 위해 솔루션 변경을 요청했다. A 국가 배치를 담당하는 프로젝트 관리자는 무엇을 해야 하는가? | A 국가의 변경 요청을 수락하고 A 국가의 배치 프로젝트 일정을 재조정한다. | 요청을 고려하고 스폰서에게 B, C 국가에 변경 사항을 알리도록 요청한다. | 배치가 이미 시작되었으므로 변경할 시간이 없다며 A 국가의 요청을 거부한다. | A 국가에게 B, C 국가와 함께 분석될 변경 요청을 제출하도록 요청한다. |  | D | 이해관계자가 다국가 솔루션에 변경을 요청할 때, PM은 통합 변경 통제 프로세스를 통해 공식 변경 요청을 제출하도록 요청해야 한다. 이는 적절한 문서화, 평가, CCB의 승인 또는 거부를 보장한다. 또한 영향을 받는 모든 국가에 걸쳐 프로젝트의 범위, 시간, 비용 제약에 대한 영향 평가를 가능하게 한다.
494 | Early in a project, a team member failed to effectively communicate the reason for their absence from three team meetings. How should the project manager handle this situation? | Assess the impact of the team member ' s absence on the task involved. | Ask the team member to explain the reason for the absences. | Reaffirm the required project obligations directly with the team member. oy | Send a formal letter to the team member stating that their absences are noted. |  | C | When a team member fails to communicate the reason for absences from team meetings, the project manager should reaffirm the required project obligations directly with the team member. This clarifies expectations, addresses the behavior constructively, and provides coaching to improve communication and accountability. Assessing the impact of the absence (A) is analytical but does not address the behavior. Asking for an explanation (B) is part of the conversation but is not sufficient on its own—the PM must also restate expectations. Sending a formal letter (D) is overly punitive at this stage and may damage the working relationship. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 프로젝트 초기에 팀원이 세 번의 팀 회의 결석 사유를 효과적으로 전달하지 못했다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 팀원의 결석이 관련 작업에 미치는 영향을 평가한다. | 팀원에게 결석 사유를 설명하도록 요청한다. | 팀원에게 필수 프로젝트 의무사항을 직접 재확인한다. | 팀원에게 결석이 기록되었다는 공식 서한을 보낸다. |  | C | 팀원이 팀 회의 결석 사유를 전달하지 못할 때, 프로젝트 관리자는 팀원에게 필수 프로젝트 의무사항을 직접 재확인해야 한다. 이는 기대를 명확히 하고, 행동을 건설적으로 다루며, 소통과 책임감 개선을 위한 코칭을 제공한다. 결석의 영향 평가(A)는 분석적이지만 행동을 다루지 않는다. 설명 요청(B)은 대화의 일부이지만 그것만으로는 충분하지 않다—PM은 기대도 재확인해야 한다. 공식 서한 발송(D)은 이 단계에서 지나치게 징벌적이며 업무 관계를 손상시킬 수 있다.
495 | After the merger of two large companies, a project manager is assigned to a project. The company hires a consultant to ensure best practices are being used in information security. During an iteration, the consultant requests changes to a software component, claiming that it is not meeting market requirements. What should the project manager do? | Continue the iteration and add the requested changes. | Cancel the iteration and meet with the product owner. | Cancel the iteration and add the requested changes. | Continue the iteration and review the change with the customer. |  | D | When a consultant requests changes to a software component during an iteration claiming it does not meet market requirements, the project manager should continue the iteration and review the change with the customer. This maintains progress while involving the decision-maker. Continuing and adding changes without review (A) skips governance. Canceling the iteration to meet the PO (B) is disruptive. Canceling and adding changes (C) halts work unnecessarily. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 두 대기업의 합병 후, 프로젝트 관리자가 프로젝트에 배정되었다. 회사는 정보 보안 모범 사례가 사용되고 있는지 확인하기 위해 컨설턴트를 고용했다. 반복 중에 컨설턴트가 소프트웨어 구성 요소가 시장 요구사항을 충족하지 못한다고 주장하며 변경을 요청한다. 프로젝트 관리자는 무엇을 해야 하는가? | 반복을 계속하고 요청된 변경 사항을 추가한다. | 반복을 취소하고 제품 책임자와 만난다. | 반복을 취소하고 요청된 변경 사항을 추가한다. | 반복을 계속하고 고객과 함께 변경 사항을 검토한다. |  | D | 컨설턴트가 반복 중에 시장 요구사항을 충족하지 못한다고 주장하며 소프트웨어 구성 요소 변경을 요청할 때, 프로젝트 관리자는 반복을 계속하고 고객과 함께 변경을 검토해야 한다. 이는 진행을 유지하면서 의사결정자를 참여시킨다. 검토 없이 계속하며 변경 추가(A)는 거버넌스를 건너뛴다. PO를 만나기 위해 반복 취소(B)는 파괴적이다. 취소하고 변경 추가(C)는 불필요하게 작업을 중단시킨다.
496 | A team is working on a hybrid project. Due to different interpretations of the project requirements, the deliverables are not aligned to the expectations. What steps should the project manager have taken to prevent this? | Submit a change request to adjust the project scope. | Update the project management plan in order to get back on track. | Ensure the team receives continuous feedback from customers users. | Ensure the team understands all additional project requirements. |  | C | When deliverables in a hybrid project are misaligned with expectations due to different requirement interpretations, the project manager should have ensured the team receives continuous feedback from customers and users. Ongoing feedback validates alignment throughout development. Submitting a change request (A) reacts after the problem occurs. Updating the project management plan (B) adjusts documents but does not prevent misalignment. Ensuring the team understands additional requirements (D) is one-time, not continuous. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Governance | Planning | Focus on Value | Develop Project Management Plan | Hybrid/Tailoring | 팀이 하이브리드 프로젝트에서 작업하고 있다. 프로젝트 요구사항의 서로 다른 해석으로 인해 산출물이 기대에 부합하지 않는다. 프로젝트 관리자는 이를 방지하기 위해 어떤 조치를 취했어야 하는가? | 프로젝트 범위를 조정하기 위해 변경 요청을 제출한다. | 정상 궤도로 복귀하기 위해 프로젝트 관리 계획을 업데이트한다. | 팀이 고객 사용자로부터 지속적인 피드백을 받도록 보장한다. | 팀이 모든 추가 프로젝트 요구사항을 이해하도록 보장한다. |  | C | 하이브리드 프로젝트에서 요구사항의 서로 다른 해석으로 산출물이 기대에 부합하지 않을 때, 프로젝트 관리자는 팀이 고객과 사용자로부터 지속적인 피드백을 받도록 보장했어야 한다. 지속적인 피드백은 개발 전반에 걸쳐 정렬을 검증한다. 변경 요청 제출(A)은 문제 발생 후 대응이다. 프로젝트 관리 계획 업데이트(B)는 문서를 조정하지만 불일치를 방지하지 않는다. 추가 요구사항 이해 보장(D)은 일회성이지 지속적이지 않다.
497 | A project manager is working with a customer's team on a new project. Some product definitions and requirements are still not clear, but the customer wants to start activities as soon as possible. The organization is also expecting product delivery for a specific date due to a regulatory requirement. Due to the nature of the project, the project manager has decided to use a hybrid approach. Why did the project manager choose a hybrid approach? | A hybrid approach will ensure the delivery date is accomplished and will eliminate product uncertainties. | A hybrid approach will allow for management of the requirement uncertainties as well as the date restriction. | A hybrid approach will allow the project manager to revise the product specifications. | A hybrid approach will enable project activities to start immediately and allow for a plan for the requirements definitions. |  | B | The project manager chose a hybrid approach because it allows management of requirement uncertainties as well as the date restriction. Hybrid combines predictive elements (fixed delivery date for regulatory compliance) with adaptive elements (iterative refinement of unclear requirements). Ensuring the delivery date is accomplished and eliminating uncertainties (A) overstates the approach—hybrid manages, not eliminates, uncertainty. Allowing revision of product specifications (C) is a feature but not the primary reason. Enabling immediate start with a requirements plan (D) describes an aspect but not the dual benefit of managing both uncertainty and fixed deadlines. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Hybrid/Tailoring | 프로젝트 관리자가 새 프로젝트에서 고객의 팀과 작업하고 있다. 일부 제품 정의와 요구사항이 아직 명확하지 않지만, 고객은 가능한 빨리 활동을 시작하고 싶어한다. 조직도 규제 요구사항으로 인해 특정 날짜까지 제품 전달을 기대하고 있다. 프로젝트의 특성상 프로젝트 관리자는 하이브리드 접근 방식을 사용하기로 결정했다. 프로젝트 관리자가 하이브리드 접근 방식을 선택한 이유는? | 하이브리드 접근 방식은 전달 날짜 달성을 보장하고 제품 불확실성을 제거한다. | 하이브리드 접근 방식은 요구사항 불확실성과 날짜 제한을 모두 관리할 수 있게 한다. | 하이브리드 접근 방식은 프로젝트 관리자가 제품 사양을 수정할 수 있게 한다. | 하이브리드 접근 방식은 프로젝트 활동을 즉시 시작하고 요구사항 정의 계획을 가능하게 한다. |  | B | 프로젝트 관리자가 하이브리드 접근 방식을 선택한 이유는 요구사항 불확실성과 날짜 제한을 모두 관리할 수 있기 때문이다. 하이브리드는 예측적 요소(규제 준수를 위한 고정 전달일)와 적응적 요소(불명확한 요구사항의 반복적 정제)를 결합한다. 전달 날짜 보장 및 불확실성 제거(A)는 과장이다—하이브리드는 불확실성을 관리하지 제거하지 않는다. 제품 사양 수정(C)은 기능이지만 주된 이유가 아니다. 즉시 시작 및 요구사항 계획(D)은 측면을 설명하지만 불확실성과 고정 기한의 이중 이점은 아니다.
498 | A Scrum team has committed to delivering a specific capability in their first release. Multiple operational issues have prevented the developer from delivering key capabilities. The technical lead has also given notice that they are resigning from the company. What should the project manager have the Scrum team do to recover from these issues? | Consult the resource management plan for an appropriate response | Continue with existing sprint plans to ensure some of the scope will be delivered | Stop the sprint and replan and prioritize the backlog to reduce resource levels | Review constraints in the ongoing sprint planning and evaluate options for the release plan |  | D | When a Scrum team faces multiple operational issues preventing key capability delivery and the tech lead is resigning, the team should review constraints in the ongoing sprint planning and evaluate options for the release plan. Adaptive replanning addresses the changed reality. Consulting the resource management plan (A) is bureaucratic. Continuing existing plans (B) ignores the changed situation. Stopping the sprint (C) is disruptive. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 스크럼 팀이 첫 번째 릴리스에서 특정 기능 전달을 약속했다. 여러 운영 문제로 인해 개발자가 핵심 기능을 전달하지 못했다. 기술 리드도 퇴사 통보를 했다. 프로젝트 관리자는 이러한 문제에서 회복하기 위해 스크럼 팀이 무엇을 하도록 해야 하는가? | 적절한 대응을 위해 자원 관리 계획을 참조한다. | 일부 범위라도 전달될 수 있도록 기존 스프린트 계획을 계속 진행한다. | 스프린트를 중단하고 자원 수준을 줄이기 위해 백로그를 재계획하고 우선순위를 조정한다. | 진행 중인 스프린트 계획에서 제약 조건을 검토하고 릴리스 계획의 옵션을 평가한다. |  | D | 스크럼 팀이 여러 운영 문제로 핵심 기능 전달이 불가능하고 기술 리드가 퇴사할 때, 팀은 진행 중인 스프린트 계획에서 제약 조건을 검토하고 릴리스 계획의 옵션을 평가해야 한다. 적응적 재계획이 변화된 현실을 다룬다. 자원 관리 계획 참조(A)는 관료적이다. 기존 계획 계속(B)은 변화된 상황을 무시한다. 스프린트 중단(C)은 파괴적이다.
499 | The Scrum team working with the quality department has been shifting away from the business unit due to unclear product requirements. It is now the third sprint and both teams have been at a standstill for a few days. What should the project leader do to solve this situation? | Demand that the business team stop wasting time and define final requirements for the product. | Tell the business team and Scrum team to continue following the initial plan. | Analyze the problem with both teams to figure out If pan of the work must be redone. | Select new team members in an effort to obtain fresh ideas to solve the impasse. |  | C | When the Scrum team and business unit have been at a standstill for days due to unclear product requirements, the project leader should analyze the problem with both teams to determine if part of the work must be redone. This collaborative approach addresses the root cause—unclear requirements—by facilitating communication and alignment between the teams. Demanding the business team define final requirements (A) creates conflict. Telling teams to follow the initial plan (B) ignores the feedback from previous sprints. Selecting new team members (D) disrupts existing dynamics and does not address the requirement clarity issue. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 품질 부서와 협력하는 스크럼 팀이 불명확한 제품 요구사항으로 인해 사업 부서와 멀어지고 있다. 현재 세 번째 스프린트이며 양 팀 모두 며칠간 교착 상태에 있다. 프로젝트 리더는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 사업 팀에게 시간 낭비를 중단하고 제품의 최종 요구사항을 정의하라고 요구한다. | 사업 팀과 스크럼 팀에게 초기 계획을 계속 따르라고 지시한다. | 양 팀과 함께 문제를 분석하여 작업의 일부를 재작업해야 하는지 파악한다. | 교착 상태를 해결하기 위해 새로운 아이디어를 얻고자 새 팀원을 선발한다. |  | C | 스크럼 팀과 사업 부서가 불명확한 제품 요구사항으로 며칠간 교착 상태에 있을 때, 프로젝트 리더는 양 팀과 함께 문제를 분석하여 작업의 일부를 재작업해야 하는지 판단해야 한다. 이 협력적 접근 방식은 근본 원인인 불명확한 요구사항을 팀 간 소통과 정렬을 촉진하여 해결한다. 최종 요구사항 정의 요구(A)는 갈등을 유발한다. 초기 계획 따르기 지시(B)는 이전 스프린트의 피드백을 무시한다. 새 팀원 선발(D)은 기존 역학을 방해하고 요구사항 명확성 문제를 해결하지 않는다.
500 | A customer is meeting with an agile team at regular intervals and keeps changing priorities for the team members. What should the project manager do to remove this impediment? | Ask the customer to discuss these changes with the product owner. | Ask the customer to discuss these changes with the management team. | Escalate the situation to the customer management team. | Request that the customer to meet with the team only at the weekly meeting. |  | A | The PM should direct the customer to discuss priority changes with the product owner, who represents customer interests and has authority to prioritize team work. The PO can assess the impact of changes on project goals and team workload, then appropriately adjust priorities. This maintains orderly backlog management and prevents the disruption caused by direct customer-to-team priority changes. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 고객이 정기적으로 애자일 팀과 만나면서 팀원들의 우선순위를 계속 변경하고 있다. 프로젝트 관리자는 이 장애물을 제거하기 위해 무엇을 해야 하는가? | 고객에게 이러한 변경 사항을 제품 책임자와 논의하도록 요청한다. | 고객에게 이러한 변경 사항을 경영 팀과 논의하도록 요청한다. | 상황을 고객 경영 팀에 에스컬레이션한다. | 고객에게 주간 회의에서만 팀과 만나도록 요청한다. |  | A | PM은 고객에게 우선순위 변경을 제품 책임자와 논의하도록 안내해야 한다. PO는 고객 이익을 대표하고 팀 작업의 우선순위를 결정할 권한을 가진다. PO는 변경이 프로젝트 목표와 팀 작업량에 미치는 영향을 평가한 후 적절히 우선순위를 조정할 수 있다. 이는 질서 있는 백로그 관리를 유지하고 고객이 팀에 직접 우선순위를 변경하여 발생하는 혼란을 방지한다.
501 | A new privacy law will go into effect at the beginning of the next calendar year. The project manager realizes the project needs to be compliant with the new law. What should the project manager do next? | Inform the project team and create a spike for the next Iteration. | Inform the legal department that the project scope will be updated. | Inform the project steering committee of this constraint. | Inform the product owner that the project will continue as planned. |  | A | When a new privacy law requires project compliance, the project manager should inform the project team and create a spike for the next iteration. A spike is a time-boxed investigation activity that allows the team to explore the compliance requirements, assess the impact on scope, schedule, cost, and quality, and plan accordingly. Informing the legal department about scope updates (B) assumes changes before investigation. Informing the steering committee (C) may be premature without understanding the impact. Informing the product owner that the project will continue as planned (D) ignores the compliance requirement. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 새로운 개인정보 보호법이 다음 역년 초에 시행된다. 프로젝트 관리자는 프로젝트가 새 법을 준수해야 한다는 것을 인식한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 팀에게 알리고 다음 반복을 위한 스파이크를 생성한다. | 법무 부서에 프로젝트 범위가 업데이트될 것임을 알린다. | 프로젝트 운영위원회에 이 제약 조건을 알린다. | 제품 책임자에게 프로젝트가 계획대로 계속될 것임을 알린다. |  | A | 새로운 개인정보 보호법이 프로젝트 준수를 요구할 때, 프로젝트 관리자는 프로젝트 팀에게 알리고 다음 반복을 위한 스파이크를 생성해야 한다. 스파이크는 팀이 준수 요구사항을 탐색하고, 범위·일정·비용·품질에 대한 영향을 평가하며, 적절히 계획할 수 있게 하는 시간 제한된 조사 활동이다. 범위 업데이트에 대해 법무 부서에 알리기(B)는 조사 전 변경을 가정한다. 운영위원회에 알리기(C)는 영향을 이해하기 전에는 시기상조일 수 있다. 계획대로 계속된다고 PO에게 알리기(D)는 준수 요구사항을 무시한다.
502 | A project manager has recently joined a small company. The company's chief operating officer (COO) asked the team to skip some steps in the process in order to work more quickly. The project manager wants to ensure that these steps are not skipped in the future. What should the project manager do? | Schedule a review of the process steps with the team and the COO. | Redesign the process so the team can move more quickly. | Notify all team members that all steps in the process must be completed. | Escalate the issue to the other executive leadership members. |  | C | The correct answer is C. Notify all team members that all steps in the process must be completed. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 최근 소규모 회사에 입사했다. 회사의 최고운영책임자(COO)가 더 빠르게 작업하기 위해 프로세스의 일부 단계를 건너뛰라고 팀에 요청했다. 프로젝트 관리자는 향후 이러한 단계가 건너뛰어지지 않도록 하고 싶다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀과 COO와 함께 프로세스 단계 검토 일정을 잡는다. | 팀이 더 빠르게 움직일 수 있도록 프로세스를 재설계한다. | 모든 팀원에게 프로세스의 모든 단계가 완료되어야 한다고 통보한다. | 다른 경영진에게 이슈를 에스컬레이션한다. |  | C | 정답은 C이다. 모든 팀원에게 프로세스의 모든 단계가 완료되어야 한다고 통보한다. 이 접근 방식은 적절한 프로세스와 이해관계자 정렬을 유지하면서 상황을 효과적으로 해결하는 프로젝트 관리 모범 사례를 따른다.
503 | A team member is hosting an event and invites several colleagues through their work calendars. Another team member, who was not invited to the event, is noticeably distracted during several standup meetings. What should the project manager do? | Add a social events section to the charter to handle these situations | Ask the individual who is hosting the event to use private communication methods. | Ask the individual who is hosting the event to mark it as private | Set up a meeting with the distracted team member to discuss any issues |  | D | When a team member is distracted during standups after not being invited to a colleague's event, the project manager should set up a meeting with the distracted team member to discuss any issues. Private, empathetic engagement identifies and addresses the concern. Adding social events to the charter (A) is structural overreach. Asking the host to use private communication (B) addresses the symptom, not the team member's distraction. Asking the host to mark events as private (C) is similar. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 팀원이 이벤트를 주최하면서 업무 캘린더를 통해 여러 동료를 초대했다. 이벤트에 초대받지 못한 다른 팀원이 여러 스탠드업 회의에서 눈에 띄게 산만해졌다. 프로젝트 관리자는 무엇을 해야 하는가? | 이러한 상황을 처리하기 위해 헌장에 사교 행사 섹션을 추가한다. | 이벤트를 주최하는 사람에게 비공개 커뮤니케이션 방법을 사용하도록 요청한다. | 이벤트를 주최하는 사람에게 비공개로 표시하도록 요청한다. | 산만해진 팀원과 미팅을 설정하여 이슈를 논의한다. |  | D | 동료의 이벤트에 초대받지 못한 후 스탠드업에서 팀원이 산만해질 때, 프로젝트 관리자는 산만해진 팀원과 미팅을 설정하여 이슈를 논의해야 한다. 비공개적이고 공감적인 참여가 우려를 식별하고 해결한다. 헌장에 사교 행사 추가(A)는 구조적으로 과도하다. 주최자에게 비공개 커뮤니케이션 요청(B)은 증상을 다루지 팀원의 산만함은 다루지 않는다. 비공개 표시 요청(C)도 유사하다.
504 | An operations manager continuously raises concerns about a project's benefits to the company. While some concerns are valid, most of the time these concerns have caused delays in project meetings. How should the project manager handle this? | Review the operations manager ' s concerns and ensure these concerns are addressed | Include the operations manager ' s concerns in the risk register and assign actions to mitigate the risks. | Discuss the meeting delays with the director of operations and ask for support with the concerns. | Escalate the concerns to the project sponsor and discuss options to address them |  | A | The PM should review the operations manager's concerns and ensure they are addressed as part of stakeholder engagement management. This involves communicating with stakeholders to meet their needs, address issues, and foster appropriate involvement. Reviewing and resolving concerns increases stakeholder satisfaction and project support while preventing conflicts and delays. Ignoring, escalating, or merely documenting concerns without resolution fails to address the stakeholder's needs effectively. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 운영 관리자가 프로젝트의 회사에 대한 혜택에 대해 지속적으로 우려를 제기한다. 일부 우려는 타당하지만, 대부분의 경우 이러한 우려가 프로젝트 회의에 지연을 초래했다. 프로젝트 관리자는 이를 어떻게 처리해야 하는가? | 운영 관리자의 우려를 검토하고 이러한 우려가 해결되도록 보장한다. | 운영 관리자의 우려를 리스크 레지스터에 포함하고 리스크를 완화하기 위한 조치를 배정한다. | 운영 이사와 회의 지연을 논의하고 우려에 대한 지원을 요청한다. | 프로젝트 스폰서에게 우려를 에스컬레이션하고 해결 옵션을 논의한다. |  | A | PM은 이해관계자 참여 관리의 일환으로 운영 관리자의 우려를 검토하고 해결되도록 보장해야 한다. 이는 요구를 충족하고 이슈를 해결하며 적절한 참여를 촉진하기 위해 이해관계자와 소통하는 것을 포함한다. 우려를 검토하고 해결하면 이해관계자 만족과 프로젝트 지원이 증가하고 갈등과 지연을 방지한다. 우려를 무시하거나, 에스컬레이션하거나, 해결 없이 단순히 문서화하는 것은 이해관계자의 요구를 효과적으로 해결하지 못한다.
505 | A food company is developing a new product using a predictive approach, and the product is currently in the testing phase. Given the nature of the feedback of the tests, the project manager has decided to use an iterative approach. At the end of one of the iterations, a new regulation related to the product is enacted. What should the project manager do next? | Conduct an iteration review to address the new regulation | Include an assessment to verfy compliance in the next iteration 289 | Make a change request regarding the project ' s scope to ensure compliance. | Start the tests over, adapting the trials to the new regulation |  | C | When a new regulation is enacted during an iterative testing phase, the project manager should make a change request regarding the project's scope to ensure compliance. A formal change request documents the regulatory requirement, communicates its impact on scope, schedule, and cost, and obtains necessary approvals from the change control board. Conducting an iteration review (A) may not be the appropriate forum for addressing regulatory changes that require formal approval. Including a compliance assessment in the next iteration (B) may be too late if the project is already in violation. Starting tests over (D) disregards completed work without following the change management process. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 식품 회사가 예측형 접근 방식을 사용하여 신제품을 개발 중이며, 제품은 현재 테스트 단계에 있다. 테스트 피드백의 특성을 고려하여 프로젝트 관리자는 반복적 접근 방식을 사용하기로 결정했다. 반복의 끝에 제품과 관련된 새로운 규정이 제정되었다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 새로운 규정을 다루기 위해 반복 검토를 수행한다. | 다음 반복에 규정 준수를 확인하기 위한 평가를 포함한다. | 규정 준수를 보장하기 위해 프로젝트 범위에 대한 변경 요청을 제출한다. | 새로운 규정에 맞추어 시험을 다시 시작하고 시험을 적응시킨다. |  | C | 반복적 테스트 단계에서 새로운 규정이 제정될 때, 프로젝트 관리자는 규정 준수를 보장하기 위해 프로젝트 범위에 대한 변경 요청을 제출해야 한다. 공식 변경 요청은 규제 요구사항을 문서화하고, 범위·일정·비용에 대한 영향을 전달하며, 변경 통제 위원회로부터 필요한 승인을 얻는다. 반복 검토 수행(A)은 공식 승인이 필요한 규제 변경을 다루기에 적절한 포럼이 아닐 수 있다. 다음 반복에 규정 준수 평가 포함(B)은 이미 위반 상태라면 너무 늦을 수 있다. 시험 재시작(D)은 변경 관리 프로세스를 따르지 않고 완료된 작업을 무시한다.
506 | A multinational company has a plan to expand their business into a new country where they currently have no presence. A project manager is assigned to initiate this project. After reviewing the business case, what should be considered first when developing an appropriate implementation strategy? | Ensure that project sponsors are in agreement on the project deliverables and timeline during the project | Evaluate the environmental and regulatory factors and identify high-level risks and assumptions | Acquire project resources from the new country to mitigate the risk of uncertainty | Identify and monitor the risks closely since the company does not have lessons learned for this country. |  | B | When expanding into a new country with no existing presence, the project manager should first evaluate the environmental and regulatory factors and identify high-level risks and assumptions. This foundational assessment—covering political, economic, social, technological, legal, and environmental aspects—informs all subsequent planning decisions. Ensuring sponsor agreement on deliverables (A) follows the initial assessment. Acquiring local resources (C) is premature without understanding the environment. Monitoring risks closely (D) is an execution activity, not a first planning step. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 다국적 회사가 현재 진출하지 않은 새로운 국가로 사업을 확장할 계획을 가지고 있다. 프로젝트 관리자가 이 프로젝트를 착수하도록 배정되었다. 비즈니스 케이스를 검토한 후, 적절한 실행 전략을 개발할 때 먼저 무엇을 고려해야 하는가? | 프로젝트 기간 동안 프로젝트 스폰서가 프로젝트 산출물과 일정에 합의하도록 보장한다. | 환경 및 규제 요인을 평가하고 상위 수준의 리스크와 가정을 식별한다. | 불확실성 리스크를 완화하기 위해 새로운 국가에서 프로젝트 자원을 확보한다. | 회사가 이 국가에 대한 교훈이 없으므로 리스크를 식별하고 면밀히 모니터링한다. |  | B | 기존 진출이 없는 새로운 국가로 확장할 때, 프로젝트 관리자는 먼저 환경 및 규제 요인을 평가하고 상위 수준의 리스크와 가정을 식별해야 한다. 이 기초 평가—정치, 경제, 사회, 기술, 법률, 환경적 측면을 포함—는 모든 후속 계획 결정에 정보를 제공한다. 스폰서 합의 보장(A)은 초기 평가 후에 온다. 현지 자원 확보(C)는 환경을 이해하지 않은 상태에서는 시기상조이다. 리스크 면밀 모니터링(D)은 실행 활동이지 첫 계획 단계가 아니다.
507 | A project in the execution phase is behind schedule and is missing some materials. The contractor submits an offer to supply the missing materials and reimburse the cost since the internal procurement process will cause more delay. The project manager does not agree with the costs submitted by the contractor for the missing materials. What should the project manager do next? | Ask the contractor to review the offer and reduce the costs. | Ask the project sponsor to allocate more budget to cover the costs | Update the procurement strategy and negotiate with the contractor | Update the procurement management plan and negotiate with the contractor. |  | D | When a contractor's costs for missing materials are unacceptable to the PM, the project manager should update the procurement management plan and negotiate with the contractor. Formal negotiation with an updated strategy protects project interests. Asking for cost reduction alone (A) lacks strategic backing. Asking the sponsor for more budget (B) accepts the costs. Updating procurement strategy without negotiation (C) is incomplete. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 실행 단계의 프로젝트가 일정에 뒤처져 있고 일부 자재가 부족하다. 계약자가 내부 조달 프로세스가 더 많은 지연을 초래할 것이므로 부족한 자재를 공급하고 비용을 환급하겠다는 제안을 제출했다. 프로젝트 관리자는 부족한 자재에 대해 계약자가 제출한 비용에 동의하지 않는다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 계약자에게 제안을 검토하고 비용을 줄이도록 요청한다. | 프로젝트 스폰서에게 비용을 충당할 추가 예산을 배정하도록 요청한다. | 조달 전략을 업데이트하고 계약자와 협상한다. | 조달 관리 계획을 업데이트하고 계약자와 협상한다. |  | D | 계약자의 부족 자재 비용이 PM에게 수용 불가능할 때, 프로젝트 관리자는 조달 관리 계획을 업데이트하고 계약자와 협상해야 한다. 업데이트된 전략을 갖춘 공식 협상이 프로젝트 이익을 보호한다. 비용 절감만 요청(A)은 전략적 뒷받침이 부족하다. 스폰서에게 추가 예산 요청(B)은 비용을 수용하는 것이다. 협상 없이 조달 전략만 업데이트(C)는 불완전하다.
508 | A company is undergoing a digital transformation and is changing its project portfolio to an agile approach. As a result, the leadership is looking to update the performance measuring system for the workforce. What should the project manager propose? | Propose an approach based on value measurement, such as the use of objectives and key results. | Keep the performance management as is and focus on the achievement of scope, cost, and schedule indicators. | Maintain the focus on schedule indicators, but remove scope and costs as they are flexible with an agile approach. | Maintain focus on cost indicators, but remove scope and schedule as they are flexible with an agile approach. |  | A | During a digital transformation to agile, the project manager should propose a value-based measurement approach such as objectives and key results (OKRs). This aligns performance measurement with agile principles of delivering value, flexibility, and adaptability—rather than traditional scope-cost-schedule metrics. Keeping the existing performance management system (B) does not align with agile. Focusing only on schedule indicators (C) is too narrow. Focusing only on cost indicators (D) is also too narrow and misrepresents agile flexibility. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Digital Transformation | 회사가 디지털 전환을 진행 중이며 프로젝트 포트폴리오를 애자일 접근 방식으로 변경하고 있다. 그 결과, 리더십이 인력의 성과 측정 시스템을 업데이트하려고 한다. 프로젝트 관리자는 무엇을 제안해야 하는가? | 목표와 핵심 결과(OKR) 사용과 같은 가치 측정 기반 접근 방식을 제안한다. | 성과 관리를 현재 상태로 유지하고 범위, 비용, 일정 지표 달성에 집중한다. | 일정 지표에 대한 집중을 유지하되, 애자일 접근 방식에서는 유연하므로 범위와 비용을 제거한다. | 비용 지표에 대한 집중을 유지하되, 애자일 접근 방식에서는 유연하므로 범위와 일정을 제거한다. |  | A | 애자일로의 디지털 전환 중, 프로젝트 관리자는 목표와 핵심 결과(OKR)와 같은 가치 기반 측정 접근 방식을 제안해야 한다. 이는 전통적인 범위-비용-일정 지표가 아닌 가치 전달, 유연성, 적응성이라는 애자일 원칙에 성과 측정을 맞춘다. 기존 성과 관리 시스템 유지(B)는 애자일에 맞지 않는다. 일정 지표에만 집중(C)은 너무 좁다. 비용 지표에만 집중(D)도 너무 좁고 애자일 유연성을 잘못 표현한다.
509 | A project manager finds an unexpected issue halfway through a customer's project. After analysis the project team determines that the issue will affect the timeline unless more resources are allocated to the project. What should the project manager do? | Absorb the additional cost for the additional resources internally so that the project completes within the timeline | Adjust the timeline since in the past the customer would not pay any additional costs then inform the customer of the change | Inform the customer of the issue and discuss the options so that they are able to make a decision on cost versus timeline | Meet with the project team to discuss internally whether they think cost is more important to the customer than the timeline |  | C | When an unexpected issue threatens the timeline unless more resources are added, the project manager should inform the customer of the issue and discuss options so they can make an informed decision on cost versus timeline. Transparency and active communication enable the customer to choose the preferred approach. Absorbing additional cost internally (A) may not be sustainable. Adjusting the timeline based on past customer behavior (B) assumes preferences without asking. Internal team discussion about customer priorities (D) speculates rather than engaging the customer directly. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 관리자가 고객 프로젝트 중간에 예상치 못한 이슈를 발견한다. 분석 후 프로젝트 팀은 더 많은 자원이 프로젝트에 배정되지 않으면 이슈가 일정에 영향을 줄 것이라고 판단한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트가 일정 내에 완료되도록 추가 자원에 대한 추가 비용을 내부적으로 흡수한다. | 과거에 고객이 추가 비용을 지불하지 않았으므로 일정을 조정한 후 고객에게 변경을 알린다. | 고객에게 이슈를 알리고 비용 대 일정에 대한 결정을 내릴 수 있도록 옵션을 논의한다. | 프로젝트 팀과 만나 고객에게 비용이 일정보다 중요한지 내부적으로 논의한다. |  | C | 예상치 못한 이슈가 추가 자원 없이는 일정을 위협할 때, 프로젝트 관리자는 고객에게 이슈를 알리고 비용 대 일정에 대한 정보에 기반한 결정을 내릴 수 있도록 옵션을 논의해야 한다. 투명성과 적극적인 커뮤니케이션이 고객이 선호하는 접근 방식을 선택할 수 있게 한다. 추가 비용 내부 흡수(A)는 지속 가능하지 않을 수 있다. 과거 고객 행동에 기반한 일정 조정(B)은 묻지 않고 선호도를 가정한다. 고객 우선순위에 대한 내부 팀 논의(D)는 고객과 직접 소통하는 대신 추측한다.
510 | During project execution, a project team member resigned and a new junior member joined the team. To smooth the transition, the project manager assigned a senior project team member to transfer knowledge and support the junior team member. The project manager subsequently received feedback from the senior team member saying that the junior member submitted a poor-quality deliverable and should be removed from the team. However, the project manager checked that deliverable and found it met quality requirements. Which technique should the project manager use to resolve this issue? | Compromise/reconcile | Collaborate/problem solve | Force/direct | Smooth/accommodate |  | B | When a senior team member claims a junior member's deliverable is poor quality but the PM verifies it meets requirements, the project manager should use the collaborate/problem-solve technique. This involves facilitating constructive dialogue between both team members to identify the root cause of the conflict and reach mutual understanding. Compromise/reconcile (A) seeks a middle ground but may not address the underlying issue. Force/direct (C) imposes a solution without buy-in. Smooth/accommodate (D) minimizes the conflict without resolving it. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 중 프로젝트 팀원이 사직하고 새로운 주니어 멤버가 팀에 합류했다. 전환을 원활하게 하기 위해 프로젝트 관리자는 시니어 프로젝트 팀원에게 지식 이전과 주니어 팀원 지원을 배정했다. 이후 프로젝트 관리자는 시니어 팀원으로부터 주니어 멤버가 품질이 낮은 산출물을 제출했으며 팀에서 제거해야 한다는 피드백을 받았다. 그러나 프로젝트 관리자가 해당 산출물을 확인한 결과 품질 요구사항을 충족했다. 프로젝트 관리자는 이 이슈를 해결하기 위해 어떤 기법을 사용해야 하는가? | 타협/화해 | 협력/문제 해결 | 강요/지시 | 완화/수용 |  | B | 시니어 팀원이 주니어 멤버의 산출물 품질이 낮다고 주장하지만 PM이 요구사항을 충족함을 확인했을 때, 프로젝트 관리자는 협력/문제 해결 기법을 사용해야 한다. 이는 두 팀원 간의 건설적인 대화를 촉진하여 갈등의 근본 원인을 식별하고 상호 이해에 도달하는 것을 포함한다. 타협/화해(A)는 중간 지점을 찾지만 근본 이슈를 다루지 못할 수 있다. 강요/지시(C)는 동의 없이 해결책을 강요한다. 완화/수용(D)은 갈등을 해결하지 않고 최소화한다.
511 | There are two interdependent projects: the first project is in execution, and the second one is about to be deployed. The first project has been delayed, which is now affecting the second project due to the sharing of resources. What should the project manager do in this situation? | Ask the procurement team to solicit offers from external providers in order to replace the internal resources for the deployment. | Ask for written commitment from the team manager assuring the deployment team can work on only one of the projects. | Assess the issue with the deployment resources ' availability and define a plan to deploy extra resources to the deployment team. | Organize a meeting with the deployment team and explain that, due to a resource shortage, the project will be delayed. |  | C | When interdependent projects are affected by resource sharing and a delay in the first project impacts the second, the project manager should assess the issue with deployment resource availability and define a plan to deploy extra resources. Impact assessment with a plan enables resolution. Soliciting external providers (A) is premature. Seeking written commitment for one project (B) does not solve the conflict. Organizing a meeting to explain delay (D) is passive. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 두 개의 상호 의존적인 프로젝트가 있다: 첫 번째 프로젝트는 실행 중이고, 두 번째 프로젝트는 배포를 앞두고 있다. 첫 번째 프로젝트가 지연되어 자원 공유로 인해 두 번째 프로젝트에 영향을 미치고 있다. 프로젝트 관리자는 이 상황에서 무엇을 해야 하는가? | 내부 자원을 배포용 외부 제공업체의 제안을 요청하기 위해 조달 팀에 요청한다. | 배포 팀이 하나의 프로젝트에만 작업할 수 있다는 팀 관리자의 서면 약속을 요청한다. | 배포 자원 가용성 이슈를 평가하고 배포 팀에 추가 자원을 투입할 계획을 수립한다. | 배포 팀과 회의를 조직하여 자원 부족으로 프로젝트가 지연될 것임을 설명한다. |  | C | 상호 의존적인 프로젝트가 자원 공유로 영향을 받고 첫 번째 프로젝트의 지연이 두 번째에 영향을 미칠 때, 프로젝트 관리자는 배포 자원 가용성 이슈를 평가하고 추가 자원을 투입할 계획을 수립해야 한다. 영향 평가와 계획이 해결을 가능하게 한다. 외부 제공업체 요청(A)은 시기상조이다. 하나의 프로젝트에 대한 서면 약속 요구(B)는 충돌을 해결하지 않는다. 지연 설명 회의 조직(D)은 수동적이다.
512 | A project manager is instructed by the project sponsor to draft the project charter. The project sponsor asks the project manager to involve a particular stakeholder in order to provide necessary resources. However, the stakeholder is refusing to get involved because the stakeholder believes there is no benefit in using the project deliverable. What should the project manager do to resolve this? | Escalate to the project sponsor due to the political nature of the issue. | Meet with the stakeholder to discuss the impact of the deliverable. | Consider the stakeholder as a risk and evaluate possible solutions with the project team. | Improve communication with the stakeholder to obtain their assistance in the future. |  | B | When a stakeholder refuses involvement in the charter because they see no benefit in the deliverable, the project manager should meet with the stakeholder to discuss the impact of the deliverable. Direct engagement addresses resistance at its root. Escalating to the sponsor (A) bypasses direct resolution. Treating as a risk (C) avoids direct engagement. Improving communication for future assistance (D) is vague and delayed. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 프로젝트 스폰서로부터 프로젝트 헌장 초안을 작성하라는 지시를 받았다. 프로젝트 스폰서는 필요한 자원을 제공하기 위해 특정 이해관계자를 참여시키도록 요청한다. 그러나 이해관계자는 프로젝트 산출물 사용에 혜택이 없다고 믿기 때문에 참여를 거부하고 있다. 프로젝트 관리자는 이를 해결하기 위해 무엇을 해야 하는가? | 이슈의 정치적 특성으로 인해 프로젝트 스폰서에게 에스컬레이션한다. | 이해관계자와 만나 산출물의 영향을 논의한다. | 이해관계자를 리스크로 간주하고 프로젝트 팀과 가능한 해결책을 평가한다. | 이해관계자와의 커뮤니케이션을 개선하여 향후 도움을 얻는다. |  | B | 이해관계자가 산출물에 혜택이 없다고 믿어 헌장 참여를 거부할 때, 프로젝트 관리자는 이해관계자와 만나 산출물의 영향을 논의해야 한다. 직접적인 참여가 저항의 근본 원인을 해결한다. 스폰서에게 에스컬레이션(A)은 직접 해결을 우회한다. 리스크로 간주(C)는 직접 참여를 회피한다. 향후 도움을 위한 커뮤니케이션 개선(D)은 모호하고 지연된다.
513 | A sales manager submitted a new feature request to the product owner, and the request was added to the product backlog. During the sprint planning meeting, the team struggles over which algorithm is the most efficient one to use. The team thinks that some development work is needed to decide. What should the project manager do? | Invite the sales manager to the next sprint meeting to clarify requirements. | Ask the scrum master to choose an algorithm based on the pros and cons of each option. | Create a new item in the sprint backlog to determine the appropriate algorithm. | Request a meeting with the product owner to help clarify the user story. |  | C | When a team cannot agree on the most efficient algorithm during sprint planning, creating a spike (research item) in the sprint backlog allows dedicated time for investigation and informed decision-making. This approach aligns with agile principles of iterative development and continuous improvement—ensuring technical decisions are based on adequate information rather than premature judgment. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Embed Quality | Determine Budget | Traditional PM | 영업 관리자가 제품 책임자에게 새로운 기능 요청을 제출했고, 요청이 제품 백로그에 추가되었다. 스프린트 계획 회의 중 팀이 가장 효율적인 알고리즘을 놓고 논쟁한다. 팀은 결정을 위해 일부 개발 작업이 필요하다고 생각한다. 프로젝트 관리자는 무엇을 해야 하는가? | 요구사항을 명확히 하기 위해 영업 관리자를 다음 스프린트 회의에 초대한다. | 스크럼 마스터에게 각 옵션의 장단점에 기반하여 알고리즘을 선택하도록 요청한다. | 적절한 알고리즘을 결정하기 위해 스프린트 백로그에 새 항목을 생성한다. | 사용자 스토리를 명확히 하기 위해 제품 책임자와 회의를 요청한다. |  | C | 스프린트 계획 중 팀이 가장 효율적인 알고리즘에 합의할 수 없을 때, 스프린트 백로그에 스파이크(연구 항목)를 생성하면 조사를 위한 전용 시간을 확보하여 정보에 기반한 의사결정을 가능하게 한다. 이 접근 방식은 반복적 개발과 지속적 개선의 애자일 원칙에 부합하며, 기술적 결정이 성급한 판단이 아닌 충분한 정보에 기반하도록 보장한다.
514 | A project manager holds meetings every Monday to review the team members' progress. The project sponsor is insisting on daily updates to ensure improved delivery on products developed by all of the teams, including this one. Some team members indicate they are on a very tight timeline and would attend the Monday meeting, but not the daily update meetings. What should the project manager do to ensure all team members participate in daily meetings? | Analyse the team members ' influence levels and schedule a training on the importance of daily standups and the time-bound feature of the meetings. | Inform the functional manager and replace (earn members who cannot join the daily progress meetings. | Review the influence of each team member, call the team members with the highest influence to a meeting, and convince them to join the daily standups. | Require all team members to attend the daily review meetings as they ate requested by the project sponsor. |  | A | When the sponsor insists on daily updates and some team members resist attending, the project manager should analyze influence levels and schedule training on the importance and time-bound nature of daily standups. Education drives understanding and buy-in. Replacing non-compliant members (B) is extreme. Convincing only high-influence members (C) ignores others. Requiring attendance per sponsor mandate (D) uses authority without building commitment. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 프로젝트 관리자가 매주 월요일 팀원들의 진행 상황을 검토하는 회의를 개최한다. 프로젝트 스폰서가 이 팀을 포함한 모든 팀의 제품 전달 개선을 위해 일일 업데이트를 요구하고 있다. 일부 팀원들은 일정이 매우 빡빡하여 월요일 회의에는 참석하겠지만 일일 업데이트 회의에는 참석하지 않겠다고 밝혔다. 프로젝트 관리자는 모든 팀원이 일일 회의에 참여하도록 무엇을 해야 하는가? | 팀원들의 영향력 수준을 분석하고 일일 스탠드업의 중요성과 시간 제한 특성에 대한 교육을 예약한다. | 기능 관리자에게 알리고 일일 진행 회의에 참석할 수 없는 팀원을 교체한다. | 각 팀원의 영향력을 검토하고, 가장 높은 영향력을 가진 팀원을 회의에 소집하여 일일 스탠드업에 참여하도록 설득한다. | 프로젝트 스폰서가 요청했으므로 모든 팀원이 일일 검토 회의에 참석하도록 요구한다. |  | A | 스폰서가 일일 업데이트를 요구하고 일부 팀원이 참석을 거부할 때, 프로젝트 관리자는 영향력 수준을 분석하고 일일 스탠드업의 중요성과 시간 제한 특성에 대한 교육을 예약해야 한다. 교육은 이해와 동의를 이끌어낸다. 비순응 팀원 교체(B)는 극단적이다. 높은 영향력 팀원만 설득(C)은 다른 사람들을 무시한다. 스폰서 지시에 따른 참석 요구(D)는 헌신을 구축하지 않고 권위를 사용한다.
515 | A project team is globally distributed with team members living and working in different time zones. The project manager is trying to get the team to collaborate effectively. Which three actions should the project manager take to accomplish this goal? (Choose three) | Send out a survey to review the preferred method, time frequency for communications. | Review the communications strategy with the team regularly with a view for continuous improvement. | Recommend the use of formal written documentation in all project communications. | Require the team to have daily mandatory meetings with the project management office (PMO). | Compile a communications management plan with input from all stakeholders and distribute for review and approval. | A, B, E | For effective collaboration across a globally distributed team in different time zones, the project manager should take three actions: review the communications strategy regularly for continuous improvement, send a survey to review preferred communication methods and timing, and compile a communications management plan with input from all stakeholders. Formal written documentation for all communications (C) is overly rigid. Mandatory daily PMO meetings (D) is impractical across time zones. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 다른 시간대에 거주하고 근무하는 팀원들로 전 세계에 분산되어 있다. 프로젝트 관리자가 팀의 효과적인 협업을 위해 노력하고 있다. 이 목표를 달성하기 위해 프로젝트 관리자가 취해야 할 세 가지 조치는? (3개 선택) | 커뮤니케이션의 선호 방법과 빈도를 검토하기 위해 설문조사를 발송한다. | 지속적 개선을 위해 정기적으로 팀과 커뮤니케이션 전략을 검토한다. | 모든 프로젝트 커뮤니케이션에서 공식 서면 문서 사용을 권장한다. | 프로젝트 관리 오피스(PMO)와의 일일 필수 회의를 팀에 요구한다. | 모든 이해관계자의 의견을 반영한 커뮤니케이션 관리 계획을 수립하고 검토 및 승인을 위해 배포한다. | A, B, E | 서로 다른 시간대에 있는 전 세계 분산 팀의 효과적 협업을 위해, 프로젝트 관리자는 세 가지 조치를 취해야 한다: 지속적 개선을 위해 정기적으로 커뮤니케이션 전략을 검토하고, 선호하는 커뮤니케이션 방법과 시기를 검토하기 위한 설문조사를 발송하며, 모든 이해관계자의 의견으로 커뮤니케이션 관리 계획을 수립한다. 모든 커뮤니케이션에 공식 서면 문서(C)는 지나치게 경직적이다. PMO와의 일일 필수 회의(D)는 시간대 차이로 비현실적이다.
516 | A project team member who was a top performer in the planning phase of a project was easily irritated during the fifth sprint of the software development phase. The team member's attitude and behavior made the other team members feel uncomfortable. What should the project manager do? | Reorganize the team to reduce the interactions causing the team discord. | Assess the workload of each team member and redistribute tasks. | Arrange an immediate agile training course for the team member. | Meet with the team member to offer any help that may be needed. |  | D | The correct answer is D. Meet with the team member to offer any help that may be needed. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 프로젝트 계획 단계에서 최고 성과자였던 팀원이 소프트웨어 개발 단계의 다섯 번째 스프린트 중 쉽게 짜증을 냈다. 팀원의 태도와 행동이 다른 팀원들을 불편하게 만들었다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀 불화를 일으키는 상호작용을 줄이기 위해 팀을 재편성한다. | 각 팀원의 업무량을 평가하고 작업을 재분배한다. | 팀원을 위한 즉각적인 애자일 교육 과정을 마련한다. | 팀원과 만나 필요한 도움을 제공한다. |  | D | 정답은 D이다. 팀원과 만나 필요한 도움을 제공한다. 애자일 환경에서 PM은 팀 협업을 촉진하고, 장애물을 제거하며, 애자일 원칙을 준수하면서 지속적인 가치 전달을 보장해야 한다.
517 | A project manager analyzes the cumulative flow chart and identifies a bottleneck in the testing activities from a self-organizing team. After discussing it with the team, a gap related to testing skills is identified. What should the project manager do to address the issue? | Provide training to the entire team so they all will be able to perform tests. | Onboard a new project team member who has testing skills. | Support the team to identify an approach to resolve the problem. | Ask the development team to slow down so the testers can catch up. |  | C | When a cumulative flow chart reveals a testing bottleneck caused by a skills gap in a self-organizing team, the project manager should support the team to identify an approach to resolve the problem. Empowering the team aligns with self-organization principles. Providing training to the entire team (A) may not be efficient. Onboarding a new tester (B) adds resources without team input. Asking developers to slow down (D) reduces throughput. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Kanban | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 자기 조직화 팀의 누적 흐름도를 분석하여 테스트 활동에서 병목 현상을 식별했다. 팀과 논의한 후 테스트 기술과 관련된 격차가 확인되었다. 프로젝트 관리자는 이 문제를 해결하기 위해 무엇을 해야 하는가? | 전체 팀에게 교육을 제공하여 모두 테스트를 수행할 수 있도록 한다. | 테스트 기술을 가진 새로운 프로젝트 팀원을 온보딩한다. | 팀이 문제를 해결할 접근 방식을 찾도록 지원한다. | 개발 팀에게 테스터가 따라잡을 수 있도록 속도를 늦추라고 요청한다. |  | C | 누적 흐름도에서 자기 조직화 팀의 기술 격차로 인한 테스트 병목 현상이 드러날 때, 프로젝트 관리자는 팀이 문제를 해결할 접근 방식을 찾도록 지원해야 한다. 팀에 권한을 부여하는 것은 자기 조직화 원칙에 부합한다. 전체 팀에 교육 제공(A)은 효율적이지 않을 수 있다. 새 테스터 온보딩(B)은 팀의 의견 없이 자원을 추가한다. 개발자에게 속도 감소 요청(D)은 처리량을 줄인다.
518 | A globally distributed project team is running behind schedule due to the lack of team commitment and low morale. In order to bring the schedule back on track, what should the project manager do first? | Permanently colocate the team for better performance. | Seek the sponsor ' s approval to extend the project schedule. 1273 | Set up a meeting to perform a root cause analysis. | Update the issue log and communicate it to the team. |  | C | When a globally distributed team is behind schedule due to low commitment and morale, the project manager should first set up a meeting to perform root cause analysis. Understanding the cause enables targeted solutions. Permanently colocating the team (A) may not be feasible for a global team. Seeking sponsor approval to extend the schedule (B) treats the symptom. Updating the issue log (D) documents but does not resolve. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | General | Schedule Management | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 전 세계에 분산된 프로젝트 팀이 팀 헌신 부족과 낮은 사기로 인해 일정에 뒤캘지고 있다. 일정을 다시 정상 궤도에 올리기 위해 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 더 나은 성과를 위해 팀을 영구적으로 함께 배치한다. | 프로젝트 일정을 연장하기 위해 스폰서의 승인을 구한다. | 근본 원인 분석을 수행하기 위한 회의를 설정한다. | 이슈 로그를 업데이트하고 팀에 전달한다. |  | C | 전 세계 분산 팀이 낮은 헌신과 사기로 일정에 뒤캘질 때, 프로젝트 관리자는 먼저 근본 원인 분석을 수행하기 위한 회의를 설정해야 한다. 원인을 이해해야 목표 지향적 해결책이 가능하다. 영구적 함께 배치(A)는 전 세계 팀에 비현실적일 수 있다. 스폰서에게 일정 연장 승인 요청(B)은 증상을 치료한다. 이슈 로그 업데이트(D)는 문서화하지만 해결하지 않는다.
519 | A project manager is leading an electrical project that spans five towns. The project manager is informed by the team that one of the towns is not allowing the team to work there even though the town was included in stakeholder engagements before the start of the project. What should the project manager do? | Retrieve all minutes of stakeholder engagements and send to the town as a reminder of their commitment to the project. | Instruct the team to move to the next town and continue the project to avoid further delays. | Change the project scope and seek approval to exclude this town from the overallproject. | Engage with the town ' s authorities to discuss the reason for the change in commitmentand agree on a solution. |  | D | When a town included in stakeholder engagements now refuses to allow the team to work there, the project manager should engage with the town's authorities to discuss the reason for the change in commitment and agree on a solution. Constructive dialogue identifies root causes and seeks mutually acceptable resolution. Sending meeting minutes as a reminder (A) is confrontational. Moving to the next town (B) ignores the commitment. Changing scope to exclude the town (C) is a major change without first attempting resolution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 5개 마을에 걸쳐 전기 프로젝트를 이끄고 있다. 프로젝트 시작 전 이해관계자 참여에 포함되었음에도 불구하고, 마을 중 한 곳이 팀의 작업을 허용하지 않는다는 것을 팀으로부터 듣게 된다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자 참여의 모든 회의록을 검색하여 프로젝트에 대한 약속을 상기시키기 위해 마을에 보낸다. | 팀에게 다음 마을로 이동하여 추가 지연을 피하며 프로젝트를 계속하도록 지시한다. | 프로젝트 범위를 변경하고 전체 프로젝트에서 이 마을을 제외하는 승인을 구한다. | 마을 당국과 대화하여 약속 변경의 이유를 논의하고 해결책에 합의한다. |  | D | 이해관계자 참여에 포함되었던 마을이 이제 팀의 작업을 거부할 때, 프로젝트 관리자는 마을 당국과 대화하여 약속 변경 이유를 논의하고 해결책에 합의해야 한다. 건설적 대화는 근본 원인을 파악하고 상호 수용 가능한 해결을 모색한다. 회의록을 상기 자료로 보내기(A)는 대립적이다. 다음 마을로 이동(B)은 약속을 무시한다. 마을을 제외하도록 범위 변경(C)은 먼저 해결을 시도하지 않는 중대한 변경이다.
520 | A team identifies a critical set of tasks that have not been included in the Kanban board, and there is not enough budget for the work hours needed to complete the activities. What solution should the agile project manager implement? | Involve stakeholders and ask them to descope some features. | Ask the sponsor for additional resources to hold the schedule. | Review alternatives with the product owner and agile team. | Increase productivity and modify the schedule as needed. |  | C | When critical tasks are discovered but budget is insufficient for the required work hours, the agile project manager should review alternatives with the product owner and agile team. Collaborative evaluation enables scope adjustment and value-focused trade-offs within constraints. Involving stakeholders to descope (A) may be needed later but should follow internal analysis. Asking for additional resources (B) may not be feasible. Increasing productivity and modifying the schedule (D) is vague and pressuring. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Kanban | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 팀이 칸반 보드에 포함되지 않은 중요한 작업 세트를 식별했으며, 활동을 완료하는 데 필요한 작업 시간에 충분한 예산이 없다. 애자일 프로젝트 관리자는 어떤 해결책을 구현해야 하는가? | 이해관계자를 참여시켜 일부 기능을 축소하도록 요청한다. | 일정을 유지하기 위해 스폰서에게 추가 자원을 요청한다. | 제품 책임자 및 애자일 팀과 대안을 검토한다. | 생산성을 높이고 필요에 따라 일정을 수정한다. |  | C | 중요 작업이 발견되었지만 필요한 작업 시간에 예산이 부족할 때, 애자일 프로젝트 관리자는 제품 책임자 및 애자일 팀과 대안을 검토해야 한다. 협력적 평가는 제약 내에서 범위 조정과 가치 중심의 트레이드오프를 가능하게 한다. 이해관계자를 참여시켜 기능 축소(A)는 나중에 필요할 수 있지만 내부 분석 후에 해야 한다. 추가 자원 요청(B)은 비현실적일 수 있다. 생산성 향상 및 일정 수정(D)은 모호하고 압박적이다.
521 | A project team member who has the expert knowledge necessary for the project is often absent from meetings. The team member sends a message to the project manager questioning them about the rationale behind some decisions made on the project. How should the project manager handle the situation? | Add the team member ' s concerns to the risk register and discuss them during the next regular meeting. | Inform the team member that decisions were already made and feedback should have been provided in the past. | Schedule a meeting to review the team member ' s concerns and revisit the decisions if required. | Explain to the team member that it is mandatory that they increase their participation in project meetings. |  | C | When an expert team member who is often absent questions decisions made without them, the project manager should schedule a meeting to review the concerns and revisit decisions if required. Collaborative engagement leverages expertise and resolves concerns. Adding concerns to the risk register (A) misclassifies the situation. Informing them decisions were already made (B) shuts down valuable feedback. Mandating increased meeting participation (D) addresses attendance, not the current concern. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트에 필요한 전문 지식을 가진 팀원이 회의에 자주 불참한다. 팀원이 프로젝트에서 내려진 몇 가지 결정의 근거에 대해 프로젝트 관리자에게 질문하는 메시지를 보냈다. 프로젝트 관리자는 상황을 어떻게 처리해야 하는가? | 팀원의 우려를 리스크 레지스터에 추가하고 다음 정기 회의에서 논의한다. | 팀원에게 결정은 이미 내려졌으며 피드백은 과거에 제공되었어야 한다고 알린다. | 팀원의 우려를 검토하고 필요시 결정을 재검토하기 위한 회의를 예약한다. | 팀원에게 프로젝트 회의 참여를 늘리는 것이 필수임을 설명한다. |  | C | 전문 팀원이 자주 불참하면서 자신 없이 내려진 결정에 의문을 제기할 때, 프로젝트 관리자는 우려를 검토하고 필요시 결정을 재검토하기 위한 회의를 예약해야 한다. 협력적 참여는 전문성을 활용하고 우려를 해소한다. 리스크 레지스터에 추가(A)는 상황을 잘못 분류한다. 결정이 이미 내려졌다고 알리기(B)는 가치 있는 피드백을 차단한다. 회의 참여 증가 요구(D)는 출석을 다루지 현재 우려는 다루지 않는다.
522 | During execution of a complex project, the project manager encounters numerous change requests from various teams. These changes may result in the project not meeting its objectives. How should the project manager ensure that these changes are managed effectively? | Record the changes using the risk register and continue monitoring. | Include the changes in the backlog and review priorities with the product owner. | Deny the change requests and keep delivering the project as planned. | Review the project and communications management plan with the main stakeholder. |  | A | When numerous change requests from various teams threaten project objectives, the project manager should record changes in the risk register and continue monitoring. This ensures structured assessment of each change's impact on scope, timeline, and finances, enabling informed decision-making. Including changes in the backlog and reviewing priorities with the product owner (B) may work in agile but does not address risk assessment. Denying all changes (C) is inflexible. Reviewing plans with the main stakeholder (D) is too narrow. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 복잡한 프로젝트 실행 중 프로젝트 관리자가 다양한 팀으로부터 수많은 변경 요청을 접수한다. 이러한 변경으로 인해 프로젝트가 목표를 달성하지 못할 수 있다. 프로젝트 관리자는 이러한 변경이 효과적으로 관리되도록 어떻게 해야 하는가? | 리스크 레지스터를 사용하여 변경을 기록하고 모니터링을 계속한다. | 변경을 백로그에 포함하고 제품 책임자와 우선순위를 검토한다. | 변경 요청을 거부하고 계획대로 프로젝트를 계속 전달한다. | 주요 이해관계자와 프로젝트 및 커뮤니케이션 관리 계획을 검토한다. |  | A | 다양한 팀으로부터 수많은 변경 요청이 프로젝트 목표를 위협할 때, 프로젝트 관리자는 리스크 레지스터에 변경을 기록하고 모니터링을 계속해야 한다. 이는 각 변경의 범위, 일정, 재무에 대한 영향을 구조적으로 평가하여 정보에 기반한 의사결정을 가능하게 한다. 백로그에 포함 및 제품 책임자와 우선순위 검토(B)는 애자일에서는 될 수 있지만 리스크 평가를 다루지 않는다. 모든 변경 거부(C)는 유연하지 않다. 주요 이해관계자와 계획 검토(D)는 범위가 좁다.
523 | A project manager has been assigned to an important project that will help set the future of the company. Meanwhile, the project management office (PMO) is implementing adaptive tools in a mostly predictive environment and has requested that the project manager follow this process as well. However, the functional manager has expressed concerns about the use of new tools on such an important project. What should the project manager do? | Follow the functional manager ' s recommendation to implement only predictive tools in the project. | Follow the project management office ' s (PMOs) request to implement the adaptive tools in the project. | Review the adaptive tools ' impact and obtain agreement from the functional manager. | Make the decision on which project approach to use that would best fit the project. |  | D | When the PMO requests adaptive tools on an important project but the functional manager has concerns, the project manager should make the decision on which project approach would best fit the project. The PM is responsible for tailoring the methodology based on project complexity, risk, stakeholder needs, and context. Following only the functional manager's recommendation (A) ignores the PMO. Following only the PMO's request (B) ignores legitimate concerns. Reviewing tools' impact and obtaining functional manager agreement (C) is close but does not capture the PM's authority to decide. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Tailored Approach | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Hybrid/Tailoring | 프로젝트 관리자가 회사의 미래를 결정하는 데 도움이 될 중요한 프로젝트에 배정되었다. 한편, 프로젝트 관리 오피스(PMO)가 대부분 예측형 환경에서 적응형 도구를 구현하기 시작했으며 프로젝트 관리자에게도 이 프로세스를 따르도록 요청했다. 그러나 기능 관리자가 이렇게 중요한 프로젝트에 새 도구를 사용하는 것에 대해 우려를 표명했다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트에 예측형 도구만 구현하라는 기능 관리자의 권고를 따른다. | 프로젝트에 적응형 도구를 구현하라는 프로젝트 관리 오피스(PMO)의 요청을 따른다. | 적응형 도구의 영향을 검토하고 기능 관리자로부터 합의를 얻는다. | 프로젝트에 가장 적합한 프로젝트 접근 방식을 결정한다. |  | D | PMO가 중요한 프로젝트에 적응형 도구를 요청하지만 기능 관리자가 우려할 때, 프로젝트 관리자는 프로젝트에 가장 적합한 프로젝트 접근 방식을 결정해야 한다. PM은 프로젝트 복잡성, 리스크, 이해관계자 요구, 맥락에 기반하여 방법론을 맞춤화할 책임이 있다. 기능 관리자의 권고만 따르기(A)는 PMO를 무시한다. PMO의 요청만 따르기(B)는 정당한 우려를 무시한다. 도구 영향 검토 및 기능 관리자 합의 획득(C)은 근접하지만 PM의 결정 권한을 포착하지 못한다.
524 | A project manager is managing a project which has a very complex and long execution period. Although the project is mostly predictive, the team was able to break the design and execution into smaller packages using a hybrid framework. The business wants to keep track of the value delivered by this framework application but there is no defined set of measurable items for the framework. What should the project manager do first? | Use the same benefits tracking process from the last predictive project and add this to the monthly status report | Create a report based on the work breakdown structure (WBS) and update it on a regular basis. | Research which templates of reports were used the most for this framework and incorporate them into the project | Work with the stakeholders to determine which measurable benefits can be tracked and assign an accountable person to monitor and report them |  | D | When a hybrid framework has no defined set of measurable items to track delivered value, the project manager should first work with stakeholders to determine which measurable benefits can be tracked and assign an accountable person to monitor and report them. This collaborative approach ensures KPIs align with business objectives and enables ongoing benefits realization tracking. Creating a WBS-based report (B) shows scope, not benefits. Using the last predictive project's tracking process (A) may not suit the hybrid framework. Researching existing templates (C) is passive and does not involve stakeholder input. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 매우 복잡하고 긴 실행 기간을 가진 프로젝트를 관리하고 있다. 프로젝트는 대부분 예측형이지만, 팀은 하이브리드 프레임워크를 사용하여 설계와 실행을 더 작은 패키지로 나눌 수 있었다. 비즈니스는 이 프레임워크 적용으로 전달된 가치를 추적하고 싶지만 프레임워크에 대한 정의된 측정 가능한 항목이 없다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 마지막 예측형 프로젝트의 동일한 혜택 추적 프로세스를 사용하고 이를 월간 상태 보고서에 추가한다. | 작업 분류 체계(WBS)를 기반으로 보고서를 작성하고 정기적으로 업데이트한다. | 이 프레임워크에 가장 많이 사용된 보고서 템플릿을 조사하고 프로젝트에 통합한다. | 이해관계자와 협력하여 추적할 수 있는 측정 가능한 혜택을 결정하고 모니터링 및 보고할 책임자를 배정한다. |  | D | 하이브리드 프레임워크에 전달된 가치를 추적할 정의된 측정 가능한 항목이 없을 때, 프로젝트 관리자는 먼저 이해관계자와 협력하여 추적할 수 있는 측정 가능한 혜택을 결정하고 모니터링 및 보고할 책임자를 배정해야 한다. 이 협력적 접근은 KPI가 비즈니스 목표에 정렬되고 지속적인 혜택 실현 추적을 가능하게 한다. WBS 기반 보고서 작성(B)은 범위를 보여주지 혜택은 보여주지 않는다. 마지막 예측형 프로젝트의 추적 프로세스 사용(A)은 하이브리드 프레임워크에 적합하지 않을 수 있다. 기존 템플릿 조사(C)는 수동적이며 이해관계자 입력을 포함하지 않는다.
525 | At the beginning of a project, a project manager is asked to provide human resources (HR) with an evaluation of every team member's performance. This evaluation will be delivered at the end of the project. How should the project manager approach this request? | Meet with HR at the end of the project and provide a confidential evaluation of every team member ' s performance. | Establish a set of objective and measurable performance indicators for evaluating team members and share it with the team. | Ask the project team how they would prefer to be evaluated and use those criteria to share results with HR. | Evaluate the project team members ' performance based on whether the completed project fulfills its intended objectives. |  | B | The project manager should establish a set of objective and measurable performance indicators early in the project and share them with the team. This approach ensures transparency, fairness, and alignment with HR evaluation expectations. Team members can then understand what is expected, track their own progress, and be assessed against consistent criteria. Meeting with HR only at the end (A) provides no opportunity for team members to improve during the project. Asking the team to define their own evaluation criteria (C) may lack consistency and alignment with organizational standards. Evaluating based solely on whether the completed project meets its objectives (D) measures project outcomes but not individual contributions. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Resources | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 초기에 프로젝트 관리자가 인사부(HR)에 모든 팀원의 성과 평가를 제공하도록 요청받았다. 이 평가는 프로젝트 종료 시 전달될 예정이다. 프로젝트 관리자는 이 요청에 어떻게 접근해야 하는가? | 프로젝트 종료 시 HR과 만나 모든 팀원의 성과에 대한 기밀 평가를 제공한다. | 팀원 평가를 위한 객관적이고 측정 가능한 성과 지표 세트를 수립하고 팀과 공유한다. | 프로젝트 팀에게 어떻게 평가받고 싶은지 물어보고 해당 기준을 사용하여 HR과 결과를 공유한다. | 완료된 프로젝트가 의도된 목표를 달성하는지 여부에 기반하여 프로젝트 팀원의 성과를 평가한다. |  | B | 프로젝트 관리자는 프로젝트 초기에 객관적이고 측정 가능한 성과 지표 세트를 수립하고 팀과 공유해야 한다. 이 접근 방식은 투명성, 공정성, HR 평가 기대와의 정렬을 보장한다. 팀원들은 무엇이 기대되는지 이해하고, 자신의 진행 상황을 추적하며, 일관된 기준에 따라 평가받을 수 있다. 프로젝트 종료 시에만 HR과 만나기(A)는 팀원이 프로젝트 중 개선할 기회를 제공하지 않는다. 팀이 자체 평가 기준을 정의하도록 요청(C)은 일관성과 조직 기준과의 정렬이 부족할 수 있다. 프로젝트 목표 달성 여부만으로 평가(D)는 프로젝트 결과를 측정하지 개인 기여는 측정하지 않는다.
526 | A project manager acquired information from the market that would reduce the business value being delivered by an ongoing project. Based on that information, the project manager believes the project should be stopped. How should the project manager handle the situation? | Have a discussion with the project sponsor and cancel the project | Continue working on the defined scope and review the risk matrix | Remove the items no longer applicable from the backlog and present the backlog to the project team | Have a discussion with the sponsor and recommend the project business value be reassessed |  | D | When market information indicates an ongoing project's business value will be significantly reduced, the project manager should discuss with the sponsor and recommend the project business value be reassessed. Sponsor involvement in value reassessment is proper governance. Canceling without analysis (A) is premature. Continuing with defined scope (B) ignores new information. Removing backlog items (C) acts without sponsor authorization. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Finance | Monitoring & Controlling | Be an Accountable Leader | Control Costs | Traditional PM | 프로젝트 관리자가 진행 중인 프로젝트의 비즈니스 가치를 감소시킬 시장 정보를 입수했다. 이 정보에 기반하여 프로젝트 관리자는 프로젝트를 중단해야 한다고 믿는다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 프로젝트 스폰서와 논의하고 프로젝트를 취소한다. | 정의된 범위에서 계속 작업하고 리스크 매트릭스를 검토한다. | 더 이상 적용되지 않는 항목을 백로그에서 제거하고 백로그를 프로젝트 팀에 제시한다. | 스폰서와 논의하고 프로젝트 비즈니스 가치를 재평가하도록 권고한다. |  | D | 시장 정보가 진행 중인 프로젝트의 비즈니스 가치가 크게 감소할 것을 나타낼 때, 프로젝트 관리자는 스폰서와 논의하고 프로젝트 비즈니스 가치를 재평가하도록 권고해야 한다. 가치 재평가에 대한 스폰서 참여는 적절한 거버넌스이다. 분석 없이 취소(A)는 시기상조이다. 정의된 범위로 계속(B)은 새로운 정보를 무시한다. 백로그 항목 제거(C)는 스폰서 승인 없이 행동한다.
527 | A telecommunications project consists of departments spread across several countries with different cultures. The project team rarely meets in person, and each team member works independently using online reporting tools. What should the project manager do to ensure team members are committed to project success? | Create a monthly report so everyone will be informed of the current status. | Meet in small groups and share information by email with the rest of the team | Control and follow the project ' s mam goals, budget, and schedule | Plan regular virtual meetings to motivate and support the team. |  | D | When a global telecommunications project has teams across countries working independently with rare in-person meetings, the project manager should plan regular virtual meetings to motivate and support the team. Regular communication fosters commitment and collaboration. Creating monthly reports (A) is one-directional. Meeting in small groups with email sharing (B) fragments communication. Controlling only goals, budget, and schedule (C) neglects team engagement. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 통신 프로젝트가 서로 다른 문화를 가진 여러 국가에 걸쳐 부서로 구성되어 있다. 프로젝트 팀은 거의 직접 만나지 않으며, 각 팀원은 온라인 보고 도구를 사용하여 독립적으로 작업한다. 프로젝트 관리자는 팀원들이 프로젝트 성공에 헌신하도록 보장하기 위해 무엇을 해야 하는가? | 모든 사람이 현재 상태를 알 수 있도록 월간 보고서를 작성한다. | 소그룹으로 만나고 나머지 팀에게 이메일로 정보를 공유한다. | 프로젝트의 주요 목표, 예산, 일정을 통제하고 추적한다. | 팀을 동기 부여하고 지원하기 위해 정기적인 가상 회의를 계획한다. |  | D | 글로벌 통신 프로젝트에서 여러 국가의 팀이 드물게 대면하며 독립적으로 작업할 때, 프로젝트 관리자는 팀을 동기 부여하고 지원하기 위해 정기적인 가상 회의를 계획해야 한다. 정기적인 소통은 헌신과 협력을 촉진한다. 월간 보고서 작성(A)은 일방향적이다. 소그룹 미팅과 이메일 공유(B)는 소통을 분산시킨다. 목표, 예산, 일정만 통제(C)는 팀 참여를 소홀히 한다.
528 | A project manager is working with an agile team. A key stakeholder who does not join the sprint planning session is very unhappy, as the delivery date for the final product has been pushed back three times. What should the project manager do? | Meet with the stakeholder to understand the concern and business impact, reprioritize as necessary, and invite them to join the sprint planning session. | Share the prioritized items that the team is working on with the stakeholder and invite them to join the sprint planning session. | Direct the product owner to drop other work in progress and work on this stakeholder's requirement as the top-priority item. | Secure some additional funding to recruit more resources to the project team to enable faster delivery. |  | A | When a key stakeholder who skips sprint planning is unhappy about three delivery date pushbacks, the project manager should meet with the stakeholder to understand concerns and business impact, reprioritize as necessary, and invite them to sprint planning. Direct engagement addresses root causes. Sharing prioritized items (B) informs but does not address the concern. Directing the PO to prioritize this stakeholder's work (C) disrupts flow. Recruiting more resources (D) adds complexity. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 애자일 팀과 작업하고 있다. 스프린트 계획 세션에 참여하지 않는 주요 이해관계자가 최종 제품의 납품 날짜가 세 번 연기되어 매우 불만이다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자와 만나 우려와 비즈니스 영향을 이해하고, 필요시 재우선순위화하며, 스프린트 계획 세션에 참여하도록 초대한다. | 팀이 작업 중인 우선순위 항목을 이해관계자와 공유하고 스프린트 계획 세션에 참여하도록 초대한다. | 제품 책임자에게 다른 진행 중인 작업을 중단하고 이 이해관계자의 요구사항을 최우선 항목으로 작업하도록 지시한다. | 더 빠른 전달을 가능하게 하기 위해 프로젝트 팀에 더 많은 자원을 충원하기 위한 추가 자금을 확보한다. |  | A | 스프린트 계획을 건너뛰는 주요 이해관계자가 세 번의 납품 날짜 연기로 불만일 때, 프로젝트 관리자는 이해관계자와 만나 우려와 비즈니스 영향을 이해하고, 필요시 재우선순위화하며, 스프린트 계획에 참여하도록 초대해야 한다. 직접적인 참여가 근본 원인을 다룬다. 우선순위 항목 공유(B)는 정보를 제공하지만 우려를 다루지 않는다. PO에게 이 이해관계자 작업 우선순위화 지시(C)는 흐름을 방해한다. 더 많은 자원 충원(D)은 복잡성을 추가한다.
529 | A project is in the start-up phase of the project life cycle. The project team consists of 20 people from five different countries. The project team is scheduled to have quarterly face-to-face meetings. However, due to unforeseen circumstances, no face-to-face meetings can occur. The project manager is concerned that the team may not be able to fulfill their individual roles without face-to-face meetings. What should the project manager do in this situation? | Review the risk register for this unforeseen circumstance. | Use the contingency reserve and subcontract the work. | Ask for an extension of time on the project deliverables. | Utilize virtual teams for meetings and deliverables. |  | D | When quarterly face-to-face meetings become impossible for a multinational team, the project manager should utilize virtual teams for meetings and deliverables. Virtual collaboration tools for communication, file sharing, and real-time interaction can maintain productivity and engagement across geographic locations. Reviewing the risk register (A) documents the issue but does not solve it. Using contingency reserves to subcontract work (B) is costly and excessive. Requesting a time extension (C) unnecessarily delays deliverables instead of adapting to the constraint. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트가 프로젝트 생애주기의 시작 단계에 있다. 프로젝트 팀은 5개국 20명으로 구성되어 있다. 프로젝트 팀은 분기별 대면 회의를 계획하고 있다. 그러나 예상치 못한 상황으로 인해 대면 회의가 열릴 수 없게 되었다. 프로젝트 관리자는 대면 회의 없이는 팀이 개별 역할을 수행할 수 없을까 우려한다. 프로젝트 관리자는 이 상황에서 무엇을 해야 하는가? | 이 예상치 못한 상황에 대해 리스크 레지스터를 검토한다. | 비상 예비비를 사용하여 작업을 하도급한다. | 프로젝트 산출물에 대한 일정 연장을 요청한다. | 회의와 산출물을 위해 가상 팀을 활용한다. |  | D | 다국적 팀의 분기별 대면 회의가 불가능해질 때, 프로젝트 관리자는 회의와 산출물을 위해 가상 팀을 활용해야 한다. 커뮤니케이션, 파일 공유, 실시간 상호작용을 위한 가상 협업 도구는 지리적 위치 전반에 걸쳐 생산성과 참여를 유지할 수 있다. 리스크 레지스터 검토(A)는 이슈를 문서화하지만 해결하지 않는다. 비상 예비비로 하도급(B)은 비용이 많고 과도하다. 일정 연장 요청(C)은 제약에 적응하는 대신 불필요하게 산출물을 지연시킨다.
530 | Due to scope changes, some of the risks identified during the initiation phase have materialized into issues. What should the project manager do next? | Ask the project sponsor to reject high-risk scope changes. | Submit a change request for additional resources and accept the changes. | Submit a request to access contingency reserves and accept the changes. | Closely monitor scope changes and implement corrective actions. |  | C | When risks identified during initiation have materialized into issues due to scope changes, the project manager should submit a request to access contingency reserves and accept the changes. Contingency reserves are specifically allocated for identified risks that materialize. Asking the sponsor to reject scope changes (A) is retrospective. Submitting a change request for additional resources (B) bypasses contingency reserves. Closely monitoring scope changes (D) is reactive, not responsive to current issues. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Risk & Issue Management | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 범위 변경으로 인해 초기화 단계에서 식별된 리스크 일부가 이슈로 현실화되었다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 스폰서에게 고위험 범위 변경을 거부하도록 요청한다. | 추가 자원을 위한 변경 요청을 제출하고 변경을 수락한다. | 비상 예비비에 접근하기 위한 요청을 제출하고 변경을 수락한다. | 범위 변경을 면밀히 모니터링하고 시정 조치를 구현한다. |  | C | 범위 변경으로 초기화 시 식별된 리스크가 이슈로 현실화되었을 때, 프로젝트 관리자는 비상 예비비에 접근하기 위한 요청을 제출하고 변경을 수락해야 한다. 비상 예비비는 현실화된 식별된 리스크를 위해 특별히 배정된다. 스폰서에게 범위 변경 거부 요청(A)은 회고적이다. 추가 자원을 위한 변경 요청 제출(B)은 비상 예비비를 우회한다. 범위 변경 모니터링(D)은 반응적이지 현재 이슈에 대응적이지 않다.
531 | A senior-level executive approached the project manager of a highly visible project that is currently in the execution phase. The executive indicated that they do not support the project and will be actively trying to prevent its success by reallocating key team members to another critical project. What should the project manager do? | Request help from human resources to keep the key team members on the project. | Discuss the incident with the key project team members. | Ask to meet privately with the senior-level executive to discuss the matter further. | Work with the project sponsor to determine an appropriate response. |  | D | When a senior executive actively opposes the project and threatens to reallocate key team members, the project manager should work with the project sponsor to determine an appropriate response. The sponsor has the organizational authority and influence to address executive-level resistance. Requesting HR help (A) addresses staffing but not the executive opposition. Discussing with key team members (B) may cause alarm. Meeting the executive privately (C) may be appropriate later but the sponsor should be engaged first. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 고위 임원이 현재 실행 단계인 매우 가시성 높은 프로젝트의 프로젝트 관리자에게 접근했다. 임원은 프로젝트를 지지하지 않으며 주요 팀원을 다른 중요 프로젝트로 재배치하여 성공을 적극적으로 방해할 것이라고 표명했다. 프로젝트 관리자는 무엇을 해야 하는가? | 주요 팀원을 프로젝트에 유지하기 위해 인사부에 도움을 요청한다. | 주요 프로젝트 팀원들과 사건을 논의한다. | 고위 임원과 비공개적으로 만나 사안을 더 논의하도록 요청한다. | 프로젝트 스폰서와 협력하여 적절한 대응을 결정한다. |  | D | 고위 임원이 프로젝트에 적극적으로 반대하고 주요 팀원 재배치를 위협할 때, 프로젝트 관리자는 프로젝트 스폰서와 협력하여 적절한 대응을 결정해야 한다. 스폰서는 임원급 저항을 해결할 조직적 권한과 영향력을 가지고 있다. HR에 도움 요청(A)은 인력 배치를 다루지만 임원 반대는 다루지 않는다. 주요 팀원과 논의(B)는 불안을 야기할 수 있다. 임원과 비공개 만남(C)은 나중에 적절할 수 있지만 먼저 스폰서를 참여시켜야 한다.
532 | During the implementation stage of a project, a newly appointed team leader approaches the project manager to verify the team's tasks and schedule. The work did not go as planned due to the team leader's lack of management experience. This could cause delays for the project. What should the project manager do? | Directly manage the project team to avoid project delays | Provide mentoring to the newly appointed team leader | Inform the project sponsor about the possible delay | Ask the human resources director to appoint a senior team leader |  | B | When a newly appointed team leader's lack of management experience causes unplanned work and potential delays, the project manager should provide mentoring. Mentoring develops leadership capability sustainably. Directly managing the team (A) undermines the team leader. Informing the sponsor (C) escalates without solution. Requesting a senior replacement from HR (D) may not be feasible. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 단계 중 새로 임명된 팀 리더가 프로젝트 관리자에게 팀의 작업과 일정을 확인하기 위해 접근했다. 팀 리더의 관리 경험 부족으로 인해 작업이 계획대로 진행되지 않았다. 이는 프로젝트에 지연을 야기할 수 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 지연을 피하기 위해 프로젝트 팀을 직접 관리한다. | 새로 임명된 팀 리더에게 멘토링을 제공한다. | 프로젝트 스폰서에게 가능한 지연에 대해 알린다. | 인사부 책임자에게 시니어 팀 리더를 임명하도록 요청한다. |  | B | 새로 임명된 팀 리더의 관리 경험 부족으로 계획되지 않은 작업과 잠재적 지연이 발생할 때, 프로젝트 관리자는 멘토링을 제공해야 한다. 멘토링은 리더십 역량을 지속 가능하게 개발한다. 팀을 직접 관리(A)는 팀 리더를 약화시킨다. 스폰서에게 알리기(C)는 해결성 없이 에스컬레이션한다. 시니어 교체 요청(D)은 실현 불가능할 수 있다.
533 | A company has made multiple staff and operational changes over the last several years, significantly improving the company culture. A project manager was recently assigned to report to a new project supervisor. The project manager notices the supervisor's style of leadership is about getting the job done in the shortest possible time regardless of operational and worker impacts. This is causing some complaints from workers. How should the project manager handle this situation? | Request that the new supervisor be assigned to another project. | Explain to the workers that they need to listen to the supervisor. | Review the overall organizational culture of the company again. | Discuss the company culture with the supervisor to clarify expectations. |  | D | The project manager should address this conflict by discussing the company's organizational culture and values with the new supervisor. Over the past several years, the company has invested in cultural improvements, and the supervisor's results-at-all-costs leadership style conflicts with those established norms. By clarifying expectations around how the organization operates, the PM can help align the supervisor's approach with the team's working environment. Requesting reassignment (A) is an overreaction and does not resolve the underlying issue. Telling workers to simply comply (B) ignores legitimate concerns and damages morale. Reviewing the organizational culture again (C) is passive and does not directly address the conflict between the supervisor's behavior and the team. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 한 회사가 지난 몇 년간 다수의 인사 및 운영 변경을 단행하여 회사 문화를 크게 개선했다. 프로젝트 관리자가 최근 새로운 프로젝트 감독관에게 보고하도록 배정되었다. 프로젝트 관리자는 감독관의 리더십 스타일이 운영 및 근로자 영향에 관계없이 가능한 한 빨리 업무를 완수하는 것임을 인지했다. 이로 인해 근로자들의 불만이 발생하고 있다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 새 감독관을 다른 프로젝트에 배정하도록 요청한다. | 근로자들에게 감독관의 말을 들어야 한다고 설명한다. | 회사의 전반적인 조직 문화를 다시 검토한다. | 감독관과 회사 문화에 대해 논의하여 기대치를 명확히 한다. |  | D | 프로젝트 관리자는 새 감독관과 회사의 조직 문화와 가치에 대해 논의하여 이 갈등을 해결해야 한다. 지난 몇 년간 회사가 문화 개선에 투자했으며, 감독관의 결과 중심 리더십 스타일은 확립된 규범과 충돌한다. 기대치를 명확히 하면 감독관의 접근 방식을 팀의 작업 환경에 맞출 수 있다. 재배정 요청(A)은 과잉 반응이며 근본 문제를 해결하지 않는다. 근로자에게 순응하라고 말하기(B)는 정당한 우려를 무시하고 사기를 저하시킨다. 조직 문화 재검토(C)는 수동적이며 감독관의 행동과 팀 간의 갈등을 직접 해결하지 않는다.
534 | A project is on its second iteration out of six. The team realizes that a key deliverable will depend on the acquisition of a new device. What should the project manager do? | Register a risk and escalate it to the project sponsor. | Invite the stakeholders to discuss prioritization of a new deliverable. | Include the responsibility for acquisition with the core team. | Detail the reason for the deliverable delay in the status report. |  | D | When the team realizes a key deliverable depends on acquiring a new device during the second iteration, the project manager should detail the reason for the deliverable delay in the status report. Transparent communication keeps stakeholders informed. Registering a risk and escalating (A) may be premature. Inviting stakeholders to prioritize (B) changes scope. Including acquisition with the core team (C) assigns responsibility without reporting. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트가 6개 반복 중 두 번째 반복을 진행 중이다. 팀은 핵심 산출물이 새 장비 획득에 의존한다는 것을 깨달았다. 프로젝트 관리자는 무엇을 해야 하는가? | 리스크를 등록하고 프로젝트 스폰서에게 에스컬레이션한다. | 이해관계자를 초대하여 새로운 산출물의 우선순위를 논의한다. | 핵심 팀에 획득 책임을 포함시킨다. | 산출물 지연 사유를 상태 보고서에 상세히 기술한다. |  | D | 팀이 두 번째 반복에서 핵심 산출물이 새 장비 획득에 의존한다는 것을 깨달을 때, 프로젝트 관리자는 산출물 지연 사유를 상태 보고서에 상세히 기술해야 한다. 투명한 커뮤니케이션이 이해관계자에게 정보를 제공한다. 리스크 등록 및 에스컬레이션(A)은 시기상조일 수 있다. 이해관계자 초대하여 우선순위 논의(B)는 범위를 변경한다. 핵심 팀에 획득 포함(C)은 보고 없이 책임을 배정한다.
535 | A bank is considering building another branch in one of three neighboring cities. The project manager has been tasked with demonstrating the benefits of building a new branch, renting an existing building, or not expanding at all. How should the project manager proceed? | Calculate the payback period (PBP) for building a new branch in each location versus renting an existing building. | Perform a Kano analysis on building a new branch versus renting in each of the locations. | Perform a gap analysis on renting in each of the locations. | Calculate the costs for each option in each location and compare the net present value (NPV) for each. |  | D | The PM should calculate costs for each option across the proposed locations and compare their net present value (NPV). NPV accounts for both the timing and magnitude of cash flows, providing a comprehensive view of profitability and financial feasibility. As a standard method for evaluating the time value of money in long-term projects, NPV comparison enables the PM to identify the most financially viable option among the alternatives. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 한 은행이 인접한 세 도시 중 한 곳에 지점을 추가 건설하는 것을 고려하고 있다. 프로젝트 관리자는 새 지점 건설, 기존 건물 임대, 또는 확장하지 않는 것의 이점을 입증하라는 과제를 받았다. 프로젝트 관리자는 어떻게 진행해야 하는가? | 각 위치에서 새 지점 건설 대 기존 건물 임대의 투자 회수 기간(PBP)을 계산한다. | 각 위치에서 새 지점 건설 대 임대에 대한 카노 분석을 수행한다. | 각 위치에서 임대에 대한 갭 분석을 수행한다. | 각 위치에서 각 옵션의 비용을 계산하고 각각의 순현재가치(NPV)를 비교한다. |  | D | PM은 제안된 위치에서 각 옵션의 비용을 계산하고 순현재가치(NPV)를 비교해야 한다. NPV는 현금 흐름의 시기와 규모를 모두 고려하여 수익성과 재무 실현 가능성에 대한 포괄적인 시각을 제공한다. 장기 프로젝트에서 화폐의 시간 가치를 평가하는 표준 방법으로서, NPV 비교는 대안 중 가장 재무적으로 실현 가능한 옵션을 식별할 수 있게 한다.
536 | A project is comprised of team members who are not engaged and committed to project success. What should the project manager do to address this situation? | Call each team member to gain their perspective on the problem, then bring the whole team together to discuss a solution. | Contact the project sponsor to request approval to release the current team and hire replacement personnel. | Send each team member a direct email indicating that disciplinary action is likely if they do 912 not change their attitude. | Accept the situation knowing there is schedule slack available to release on an incremental basis when necessary. |  | A | When team members are not engaged or committed to project success, the project manager should call each team member to gain their perspective on the problem, then bring the whole team together to discuss a solution. Individual engagement followed by collaborative problem-solving addresses root causes. Requesting approval to replace the team (B) is extreme. Sending disciplinary emails (C) is punitive. Accepting the situation (D) is passive. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 팀원들이 프로젝트 성공에 참여하지 않고 헌신하지 않는 팀으로 구성되어 있다. 프로젝트 관리자는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 각 팀원에게 전화하여 문제에 대한 관점을 파악한 다음, 전체 팀을 모아 해결책을 논의한다. | 프로젝트 스폰서에게 현재 팀을 해임하고 대체 인력을 고용할 승인을 요청한다. | 태도를 바꾸지 않으면 징계 조치가 있을 수 있다는 직접 이메일을 각 팀원에게 보낸다. | 필요할 때 점진적으로 릴리스할 수 있는 일정 여유가 있으므로 상황을 수용한다. |  | A | 팀원들이 프로젝트 성공에 참여하지 않거나 헌신하지 않을 때, 프로젝트 관리자는 각 팀원에게 전화하여 문제에 대한 관점을 파악한 다음, 전체 팀을 모아 해결책을 논의해야 한다. 개별 참여 후 협력적 문제 해결이 근본 원인을 다룬다. 팀 교체 승인 요청(B)은 극단적이다. 징계 이메일 발송(C)은 징벌적이다. 상황 수용(D)은 수동적이다.
537 | A project manager is working on a project to release a new version of a key product. The product strategy and marketing areas are still working on defining the final details for the product's appearance, but the team is clear about the main features. During the last sprint review, the project sponsor expressed concerns about the low quality of the product. What should the project manager, as a servant leader, do to address this situation? | Apply fast-track techniques to work on the missing details in parallel, | Create a new risk entry for the delay in the risk management plan. | Dedicate the next sprint to completing the missing details. | Continue iterating and monitoring quality aspects sprint by sprint. |  | D | As a servant leader, the PM should continue iterating and monitoring quality aspects sprint by sprint. This approach emphasizes communication, risk management, and proactive problem-solving while maintaining focus on value delivery rather than simply meeting predefined targets. Continuous quality monitoring across sprints enables early detection and correction of issues. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Develop a Common Vision | Schedule | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 핵심 제품의 새 버전을 출시하는 프로젝트를 진행 중이다. 제품 전략 및 마케팅 부서가 제품 외관의 최종 세부 사항을 아직 정의하고 있지만, 팀은 주요 기능에 대해 명확히 알고 있다. 마지막 스프린트 리뷰에서 프로젝트 스폰서가 제품의 낮은 품질에 대해 우려를 표명했다. 서번트 리더로서 프로젝트 관리자는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 누락된 세부 사항을 병행 작업하기 위해 빨리감기 기법을 적용한다. | 리스크 관리 계획에 지연에 대한 새로운 리스크 항목을 생성한다. | 다음 스프린트를 누락된 세부 사항 완성에 전념한다. | 스프린트별로 품질 측면을 계속 반복하고 모니터링한다. |  | D | 서번트 리더로서 PM은 스프린트별로 품질 측면을 계속 반복하고 모니터링해야 한다. 이 접근 방식은 커뮤니케이션, 리스크 관리, 사전 예방적 문제 해결을 강조하면서 사전 정의된 목표를 단순히 충족시키는 것보다 가치 전달에 집중을 유지한다. 스프린트 전반에 걸친 지속적인 품질 모니터링은 문제의 조기 발견과 수정을 가능하게 한다.
538 | An agile coach and technical writer for a globally distributed agile team are in a country with a 9-hour time zone difference from the agile team. The agile coach and project lead disagree on the timing for the daily standup. The project lead thinks the standup should be at 10:00 am local time, but the agile coach and technical writer feel that is an inconvenient time for them. How does the project lead ensure adherence to agile practices? | Escalate to management that the agile process is not going to work and ask them to speak to the agile coach, | Have two separate daily standups, one for the agile coach and technical writer and one for the agile development team. | Inform the agile coach that the daily standup will be at 10:00 am local time and ensure all parties can attend. | Have a discussion with the team on the approach and come to a decision on when the daily standups should be. |  | D | When team members in different time zones disagree on daily standup timing, the project lead should have a discussion with the team on the approach and come to a decision on when the standups should be. Agile principles value face-to-face conversation and team self-organization—the team should collectively agree on a time that respects everyone's constraints. Escalating to management (A) undermines team autonomy. Having two separate standups (B) fragments the team and reduces collaboration. Imposing a time without team input (C) contradicts agile self-organization principles. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 글로벌 분산 애자일 팀의 애자일 코치와 기술 작가가 애자일 팀과 9시간 시차가 있는 나라에 있다. 애자일 코치와 프로젝트 리드는 일일 스탠드업 시간에 대해 의견이 다르다. 프로젝트 리드는 스탠드업이 현지 시간 오전 10시에 해야 한다고 생각하지만, 애자일 코치와 기술 작가는 그 시간이 불편하다고 느낀다. 프로젝트 리드는 애자일 실천 준수를 어떻게 보장하는가? | 애자일 프로세스가 작동하지 않을 것이라고 경영진에게 에스컬레이션하고 애자일 코치와 대화하도록 요청한다. | 애자일 코치와 기술 작가를 위한 것과 애자일 개발팀을 위한 것, 두 개의 별도 일일 스탠드업을 진행한다. | 애자일 코치에게 일일 스탠드업은 현지 시간 오전 10시에 진행되며 모든 당사자가 참석할 수 있도록 한다고 알린다. | 팀과 접근 방식에 대해 토론하고 일일 스탠드업 시간에 대한 결정을 내린다. |  | D | 서로 다른 시간대의 팀원들이 일일 스탠드업 시간에 대해 의견이 다를 때, 프로젝트 리드는 팀과 접근 방식에 대해 토론하고 스탠드업 시간에 대한 결정을 내려야 한다. 애자일 원칙은 대면 대화와 팀 자기 조직화를 중시한다—팀이 모든 사람의 제약을 존중하는 시간에 공동으로 합의해야 한다. 경영진에게 에스컬레이션(A)은 팀 자율성을 약화시킨다. 두 개의 별도 스탠드업(B)은 팀을 분열시키고 협업을 줄인다. 팀 입력 없이 시간을 부과(C)하는 것은 애자일 자기 조직화 원칙에 반한다.
539 | The scope of a project is to replace the street signs within a 10-km radius. The client does not want to sign the project closure report if the radius is not extended by 1 km, to be aligned with the council's development plan. What should the project manager do? | Contact the council and ask for their approval to extend the scope of the project. | Initiate a new project and discuss the request because it came in too late. | Obtain formal acceptance for the completed work and submit a change request. | Delay the approval and ask the project sponsor for additional funding. |  | C | When a client requests a scope extension (adding 1 km to the project radius) as a condition for signing the closure report, the project manager should first obtain formal acceptance for the completed work within the original scope and then submit a change request for the additional requirement. This follows proper change management—separating acceptance of completed work from new scope requests. Contacting the council for approval (A) bypasses the project's change control process. Initiating a new project (B) is excessive for a scope extension. Delaying approval and requesting additional funding (D) does not follow the structured change management process. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Change Management | Process | Develop and Manage Scope | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 프로젝트의 범위는 10km 반경 내의 도로 표지판을 교체하는 것이다. 고객은 시의회의 개발 계획에 맞추기 위해 반경을 1km 연장하지 않으면 프로젝트 종료 보고서에 서명하지 않겠다고 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 시의회에 연락하여 프로젝트 범위 연장에 대한 승인을 요청한다. | 요청이 너무 늦게 들어왔으므로 새 프로젝트를 시작하고 요청을 논의한다. | 완료된 작업에 대한 공식 수락을 얻고 변경 요청을 제출한다. | 승인을 지연하고 프로젝트 스폰서에게 추가 자금을 요청한다. |  | C | 고객이 종료 보고서 서명 조건으로 범위 연장(프로젝트 반경에 1km 추가)을 요청할 때, 프로젝트 관리자는 먼저 원래 범위 내에서 완료된 작업에 대한 공식 수락을 얻은 다음 추가 요구사항에 대한 변경 요청을 제출해야 한다. 이는 적절한 변경 관리를 따르는 것으로—완료된 작업의 수락과 새로운 범위 요청을 분리한다. 시의회에 승인 요청(A)은 프로젝트의 변경 통제 프로세스를 우회한다. 새 프로젝트 시작(B)은 범위 연장에 대해 과도하다. 승인 지연 및 추가 자금 요청(D)은 구조화된 변경 관리 프로세스를 따르지 않는다.
540 | An agile project manager has just been given a sizeable software development project to implement. Early in the initiation stage, the project sponsor requests an indication of timelines for delivery of the initial release. What tools should the agile project manager use to do these estimates? | Resource management plan, retrospective notes, backlog grooming | Backlog grooming, product backlog, minimum viable product (MVP) | Product backlog, budget, resource management plan | Budget, minimum viable product (MVP), retrospective notes |  | B | For estimating initial release timelines on a sizeable agile project, the project manager should use backlog grooming, product backlog, and minimum viable product (MVP). Backlog grooming refines and estimates items; the product backlog provides the full scope of features; and the MVP defines the minimum first release scope—together enabling realistic timeline estimation. Resource management plan, retrospective notes, and backlog grooming (A) mix predictive and post-sprint tools. Budget-focused options (C, D) emphasize finances over agile estimation needs. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 애자일 프로젝트 관리자가 구현할 대규모 소프트웨어 개발 프로젝트를 막 받았다. 착수 단계 초기에 프로젝트 스폰서가 초기 릴리스 전달 일정의 개략적인 정보를 요청한다. 애자일 프로젝트 관리자는 이 추정을 위해 어떤 도구를 사용해야 하는가? | 자원 관리 계획, 회고 노트, 백로그 정제 | 백로그 정제, 제품 백로그, 최소 기능 제품(MVP) | 제품 백로그, 예산, 자원 관리 계획 | 예산, 최소 기능 제품(MVP), 회고 노트 |  | B | 대규모 애자일 프로젝트의 초기 릴리스 일정을 추정하기 위해, 프로젝트 관리자는 백로그 정제, 제품 백로그, 최소 기능 제품(MVP)을 사용해야 한다. 백로그 정제는 항목을 정련하고 추정하며, 제품 백로그는 전체 기능 범위를 제공하고, MVP는 최소 첫 릴리스 범위를 정의한다—이 세 가지가 합쳐져 현실적인 일정 추정이 가능해진다. 자원 관리 계획, 회고 노트, 백로그 정제(A)는 예측적 도구와 스프린트 후 도구를 혼합한다. 예산 중심 옵션(C, D)은 애자일 추정 요구보다 재무를 강조한다.
541 | The project is delayed due to the high amount of major changes requested by different stakeholders at different stages of the project. If the project continues on the same path, it will consume twice the time and budget planned. What two actions can the project manager take to be more cost effective? (Choose two) | Conduct a stakeholder analysis. | Update the project management plan with the new timeline | Adopt an incremental approach | Reinforce team communication. | Leverage work between team members | A, E | When a project faces excessive major changes from different stakeholders causing cost and schedule overruns, the project manager should conduct a stakeholder analysis (A) and leverage work between team members (E). Stakeholder analysis helps identify the source and motivation behind changes, enabling better expectation management. Leveraging work between team members optimizes resource utilization and reduces rework. Updating the project management plan with a new timeline (B) accepts the delays without addressing the root cause. Adopting an incremental approach (C) may help with delivery but does not address the change management problem. Reinforcing team communication (D) supports collaboration but does not directly control excessive stakeholder-driven changes. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트가 프로젝트의 다른 단계에서 다른 이해관계자가 요청한 대량의 주요 변경으로 인해 지연되고 있다. 프로젝트가 같은 경로로 계속되면 계획된 시간과 예산의 두 배를 소비할 것이다. 프로젝트 관리자가 더 비용 효율적이기 위해 취할 수 있는 두 가지 조치는 무엇인가? (2개 선택) | 이해관계자 분석을 수행한다. | 새로운 일정으로 프로젝트 관리 계획을 업데이트한다. | 점진적 접근 방식을 채택한다. | 팀 커뮤니케이션을 강화한다. | 팀원 간 작업을 활용한다. | A, E | 다른 이해관계자의 과도한 주요 변경으로 비용 및 일정 초과가 발생할 때, 프로젝트 관리자는 이해관계자 분석을 수행(A)하고 팀원 간 작업을 활용(E)해야 한다. 이해관계자 분석은 변경의 원인과 동기를 파악하여 기대 관리를 개선한다. 팀원 간 작업 활용은 자원 활용을 최적화하고 재작업을 줄인다. 새 일정으로 프로젝트 관리 계획 업데이트(B)는 근본 원인을 해결하지 않고 지연을 수용한다. 점진적 접근 방식 채택(C)은 전달에 도움이 될 수 있지만 변경 관리 문제를 해결하지 않는다. 팀 커뮤니케이션 강화(D)는 협업을 지원하지만 과도한 이해관계자 주도 변경을 직접 통제하지 않는다.
542 | A project management office (PMO) director finds that the project managers leading software development projects are not consistently seeking approval from other division leaders in cybersecurity and operations before deploying code into production. The PMO director asks the project manager to develop a solution for this issue. What should the project manager do to fix this problem? | Create a new policy requiring project managers to email division leaders before deploying code into production. | Launch an enterprise governance structure comprised of division leaders to establish policies for code releases. | Provide division leaders with a teleconference phone number to call if they have concerns after code is deployed into production. | Establish a daily scrum meeting and invite division leaders to attend so they can be aware of upcoming code releases. |  | B | When project managers are not consistently seeking division leader approval before deploying code, the solution should be structural and governance-focused. The project manager should launch an enterprise governance structure comprised of division leaders to establish policies for code releases. This creates a systematic framework with clear roles, responsibilities, and decision-making processes across the organization. Creating an email policy (A) is informal and easily bypassed. Providing a teleconference number for post-deployment concerns (C) is reactive, not preventive. Establishing a daily scrum with division leaders (D) is excessive and misuses agile ceremonies. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Compliance | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | 프로젝트 관리 오피스(PMO) 이사는 소프트웨어 개발 프로젝트를 이끄는 프로젝트 관리자들이 프로덕션에 코드를 배포하기 전에 사이버보안 및 운영 부서의 다른 부문 리더에게 일관되게 승인을 구하지 않는 것을 발견했다. PMO 이사는 프로젝트 관리자에게 이 문제에 대한 해결책을 개발하도록 요청한다. 프로젝트 관리자는 이 문제를 해결하기 위해 무엇을 해야 하는가? | 프로젝트 관리자가 프로덕션에 코드를 배포하기 전에 부문 리더에게 이메일을 보내도록 요구하는 새 정책을 만든다. | 코드 릴리스 정책을 수립하기 위해 부문 리더로 구성된 기업 거버넌스 구조를 출범시킨다. | 코드가 프로덕션에 배포된 후 우려 사항이 있으면 전화할 수 있도록 부문 리더에게 전화 회의 번호를 제공한다. | 일일 스크럼 회의를 설정하고 부문 리더를 초대하여 예정된 코드 릴리스를 인지할 수 있도록 한다. |  | B | 프로젝트 관리자들이 코드 배포 전 부문 리더 승인을 일관되게 구하지 않을 때, 해결책은 구조적이고 거버넌스 중심이어야 한다. 프로젝트 관리자는 코드 릴리스 정책을 수립하기 위해 부문 리더로 구성된 기업 거버넌스 구조를 출범시켜야 한다. 이는 조직 전반에 걸쳐 명확한 역할, 책임, 의사결정 프로세스를 갖춘 체계적 프레임워크를 만든다. 이메일 정책 생성(A)은 비공식적이고 쉽게 우회된다. 배포 후 우려를 위한 전화 회의 번호 제공(C)은 반응적이지 예방적이지 않다. 부문 리더와 일일 스크럼 설정(D)은 과도하며 애자일 의식을 오용한다.
543 | A customer requests additional changes 1 day before the planned change date. How should the project manager respond to the change request? | Review the additional changes and perform integrated change control. | Determine whether the project team is capable of making the changes. | Check if the changes are covered in the statement of work (SOW). | Reject the changes as the lead time is too short. |  | A | When receiving a change request close to the planned change date, the PM should review the changes and perform integrated change control. This assesses the feasibility and impact of the request and determines the appropriate approval path. Rejecting based on timing alone (A) may violate customer expectations. Assessing team capability (B) is insufficient without impact analysis. Checking the SOW (D) doesn't address the change request directly. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Resources | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 고객이 계획된 변경 날짜 1일 전에 추가 변경을 요청한다. 프로젝트 관리자는 변경 요청에 어떻게 대응해야 하는가? | 추가 변경을 검토하고 통합 변경 통제를 수행한다. | 프로젝트 팀이 변경을 수행할 수 있는 능력이 있는지 결정한다. | 변경 사항이 작업 기술서(SOW)에 포함되어 있는지 확인한다. | 리드 타임이 너무 짧으므로 변경을 거부한다. |  | A | 계획된 변경 날짜에 가까이 변경 요청을 받을 때, PM은 변경을 검토하고 통합 변경 통제를 수행해야 한다. 이는 요청의 실현 가능성과 영향을 평가하고 적절한 승인 경로를 결정한다. 타이밍만으로 거부(A)하면 고객 기대를 위반할 수 있다. 팀 역량 평가(B)는 영향 분석 없이 불충분하다. SOW 확인(D)은 변경 요청을 직접 다루지 않는다.
544 | One of the project manager's important assignments is to formally revise project compliance as it pertains to user data protection regulations. What should the project manager do to monitor compliance? | Perform retrospectives. | Assess the risk register. | Complete sprint reviews | Conduct project reviews. |  | D | To formally monitor compliance with user data protection regulations, the project manager should conduct project reviews. Regular project reviews assess progress, evaluate data handling practices, verify effectiveness of data protection measures, and identify areas for improvement. Performing retrospectives (A) focuses on process improvement, not formal compliance. Assessing the risk register (B) addresses risks but not systematic compliance monitoring. Completing sprint reviews (C) focuses on product increments, not compliance. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | Traditional Plan-Driven | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 프로젝트 관리자의 중요한 임무 중 하나는 사용자 데이터 보호 규정과 관련하여 프로젝트 준수를 공식적으로 검토하는 것이다. 프로젝트 관리자는 준수를 모니터링하기 위해 무엇을 해야 하는가? | 회고를 수행한다. | 리스크 레지스터를 평가한다. | 스프린트 리뷰를 완료한다. | 프로젝트 리뷰를 수행한다. |  | D | 사용자 데이터 보호 규정에 대한 준수를 공식적으로 모니터링하기 위해, 프로젝트 관리자는 프로젝트 리뷰를 수행해야 한다. 정기적인 프로젝트 리뷰는 진행 상황을 평가하고, 데이터 처리 관행을 평가하며, 데이터 보호 조치의 효과를 검증하고, 개선 영역을 식별한다. 회고(A)는 프로세스 개선에 초점을 맞추며 공식적 준수가 아니다. 리스크 레지스터 평가(B)는 리스크를 다루지만 체계적인 준수 모니터링은 아니다. 스프린트 리뷰(C)는 제품 증분에 초점을 맞추며 준수가 아니다.
545 | A project manager has just been assigned to a team that is developing a new design product. The work breakdown structure (WBS) has been created and the activities have been assigned to the team members. The project manager finds that there are activities that could be completed sooner by other team members. If the current assignments are left as is, the project could be delayed 2 weeks. What should the project manager do in this situation? | Review the work allocation and reassign some tasks to shorten the critical path. | Keep the task assignments unchanged since the project management plan has been 1141 approved. | Ask the team members to work overtime to finish the tasks on time according to the schedule. | Maintain the task assignments as planned and compress the other tasks to keep the project on schedule. |  | A | When certain tasks could be completed sooner by different team members, potentially avoiding a 2-week delay, the project manager should review work allocation and reassign tasks to shorten the critical path. Resource optimization prevents delays. Keeping assignments unchanged (B) accepts the delay. Asking for overtime (C) is unsustainable. Maintaining assignments and compressing other tasks (D) may not address the critical path. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 관리자가 새로운 디자인 제품을 개발하는 팀에 방금 배정되었다. 작업 분류 체계(WBS)가 작성되었고 활동이 팀원들에게 할당되었다. 프로젝트 관리자는 다른 팀원이 더 빨리 완료할 수 있는 활동이 있음을 발견했다. 현재 할당을 그대로 두면 프로젝트가 2주 지연될 수 있다. 프로젝트 관리자는 이 상황에서 무엇을 해야 하는가? | 작업 할당을 검토하고 일부 작업을 재배정하여 크리티컬 패스를 단축한다. | 프로젝트 관리 계획이 승인되었으므로 작업 할당을 변경하지 않는다. | 팀원에게 일정에 따라 제시간에 작업을 완료하기 위해 초과 근무를 요청한다. | 계획대로 작업 할당을 유지하고 프로젝트를 일정에 맞추기 위해 다른 작업을 압축한다. |  | A | 특정 작업을 다른 팀원이 더 빨리 완료할 수 있어 2주 지연을 방지할 수 있을 때, 프로젝트 관리자는 작업 할당을 검토하고 작업을 재배정하여 크리티컬 패스를 단축해야 한다. 자원 최적화가 지연을 방지한다. 할당 변경 없이 유지(B)는 지연을 수용한다. 초과 근무 요청(C)은 지속 가능하지 않다. 할당 유지 및 다른 작업 압축(D)은 크리티컬 패스를 해결하지 못할 수 있다.
546 | A project manager is appointed to manage an infrastructure project that spans across several countries, including different time zones within a subregion. It is likely that most of the project team members will never meet, but they will have to collaborate to ensure deliverables are met. What should the project manager do to ensure good collaboration between the remote project team members? | Plan a communication method and allow the project team members to virtually interact. | Create a social media group platform for the team to create a supportive environment. | Discuss the concerns with the project sponsor and modify the project charter to includemore budget for interactions. | Set the ground rules and identify a contingency plan in the risk register. |  | A | When an infrastructure project spans multiple countries and time zones where team members may never meet, the project manager should plan a communication method and allow team members to virtually interact. Structured virtual communication bridges geographic distances and enables collaboration. Creating a social media platform (B) is informal. Discussing with the sponsor for more budget (C) does not directly enable collaboration. Setting ground rules and contingency plans (D) addresses risk, not daily collaboration. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 관리자가 하위 지역 내 여러 시간대를 포함하여 여러 국가에 걸친 인프라 프로젝트를 관리하도록 임명되었다. 대부분의 프로젝트 팀원은 만날 일이 없겠지만 산출물이 충족되도록 협업해야 한다. 프로젝트 관리자는 원격 프로젝트 팀원 간의 좋은 협업을 보장하기 위해 무엇을 해야 하는가? | 커뮤니케이션 방법을 계획하고 프로젝트 팀원이 가상으로 상호 작용할 수 있도록 한다. | 팀이 지원적인 환경을 만들 수 있도록 소셜 미디어 그룹 플랫폼을 만든다. | 프로젝트 스폰서와 우려를 논의하고 상호 작용을 위한 더 많은 예산을 포함하도록 프로젝트 헌장을 수정한다. | 기본 규칙을 설정하고 리스크 레지스터에 비상 계획을 식별한다. |  | A | 인프라 프로젝트가 여러 국가와 시간대에 걸쳐 있고 팀원이 만날 수 없을 때, 프로젝트 관리자는 커뮤니케이션 방법을 계획하고 팀원이 가상으로 상호 작용할 수 있도록 해야 한다. 구조화된 가상 커뮤니케이션이 지리적 거리를 극복하고 협업을 가능하게 한다. 소셜 미디어 플랫폼 생성(B)은 비공식적이다. 스폰서와 추가 예산 논의(C)는 협업을 직접 가능하게 하지 않는다. 기본 규칙 및 비상 계획 설정(D)은 리스크를 다루지 일상적 협업은 다루지 않는다.
547 | A town wants to build a community center and has appointed a project manager. A site was found, and all of the necessary approvals and governance were completed. When the project kick-off was held, it was discovered that a local farmers' group was not consulted, and they use the site for a monthly market. What should the project manager do to move forward with the project? | Request that the project sponsor discuss compensation with the farmers ' group for the lost business. | Continue building the center as the farmers ' group does not need to be consulted. | Discuss the project objectives with all stakeholders, including the farmers ' group, and review their requirements. | Document a risk related to the impact that the farmers ' group could bring to the project. |  | C | When a local farmers' group that uses the project site was not consulted before the kick-off, the project manager should discuss the project objectives with all stakeholders, including the farmers' group, and review their requirements. Inclusive stakeholder engagement identifies concerns and enables collaborative solutions. Requesting sponsor compensation discussions (A) acts before understanding needs. Continuing without consultation (B) ignores a key stakeholder. Documenting a risk (D) is passive. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 한 도시가 커뮤니티 센터를 건설하려 하며 프로젝트 관리자를 임명했다. 부지가 발견되었고 모든 필요한 승인과 거버넌스가 완료되었다. 프로젝트 킥오프를 진행했을 때 지역 농민 단체가 자문을 받지 않았으며, 그들이 해당 부지를 월간 시장으로 사용하고 있음이 발견되었다. 프로젝트 관리자는 프로젝트를 진행하기 위해 무엇을 해야 하는가? | 프로젝트 스폰서에게 농민 단체와 사업 손실에 대한 보상을 논의하도록 요청한다. | 농민 단체는 자문을 받을 필요가 없으므로 센터 건설을 계속한다. | 농민 단체를 포함한 모든 이해관계자와 프로젝트 목표를 논의하고 그들의 요구사항을 검토한다. | 농민 단체가 프로젝트에 미칠 수 있는 영향에 대한 리스크를 문서화한다. |  | C | 프로젝트 부지를 사용하는 지역 농민 단체가 킥오프 전에 자문을 받지 않았을 때, 프로젝트 관리자는 농민 단체를 포함한 모든 이해관계자와 프로젝트 목표를 논의하고 그들의 요구사항을 검토해야 한다. 포용적인 이해관계자 참여가 우려를 식별하고 협력적 해결을 가능하게 한다. 스폰서 보상 논의 요청(A)은 요구를 이해하기 전에 행동한다. 자문 없이 계속(B)은 핵심 이해관계자를 무시한다. 리스크 문서화(D)는 수동적이다.
548 | A key stakeholder has recently started at a company and has been assigned to a hybrid project. Although very experienced in their domain, the stakeholder has only been exposed to predictive project approaches. What should the project manager do? | Allocate time to mentor the stakeholder in the selected project approach. | Inform the stakeholder that they must level their knowledge with other stakeholders. | Inform the project management office (PMO) that the team will use a predictive approach for this project. | Update the risk register with the potential impact and apprise the steering committee. |  | A | When a key stakeholder is experienced only in predictive approaches, the PM should invest time mentoring them on the hybrid project approach. This enables the stakeholder to understand the methodology, contribute effectively, and support project decisions. Without this foundational understanding, the stakeholder may resist or misinterpret agile elements of the hybrid approach. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Align Stakeholder Expectations | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 핵심 이해관계자가 최근 회사에 입사하여 하이브리드 프로젝트에 배정되었다. 해당 도메인에서 매우 경험이 풍부하지만, 이해관계자는 예측적 프로젝트 접근 방식만 경험했다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자에게 선택된 프로젝트 접근 방식에 대해 멘토링할 시간을 할당한다. | 이해관계자에게 다른 이해관계자와 지식 수준을 맞춰야 한다고 알린다. | 프로젝트 관리 오피스(PMO)에 이 프로젝트에 예측적 접근 방식을 사용할 것이라고 알린다. | 잠재적 영향을 리스크 레지스터에 업데이트하고 운영 위원회에 알린다. |  | A | 핵심 이해관계자가 예측적 접근 방식만 경험했을 때, PM은 하이브리드 프로젝트 접근 방식에 대해 멘토링하는 데 시간을 투자해야 한다. 이를 통해 이해관계자가 방법론을 이해하고 효과적으로 기여하며 프로젝트 의사결정을 지원할 수 있다. 이 기본적인 이해 없이는 이해관계자가 하이브리드 접근 방식의 애자일 요소에 저항하거나 오해할 수 있다.
549 | During a project audit, several risks are identified. The auditors realize that the team is having trouble quantifying and qualifying these risks. What should the project manager do? | Ask the sponsor to contribute to the risk management process. | Invite the project stakeholders to participate in the process. | Facilitate risk management training for the team. | Ask the subject matter expert (SME) to support the team. |  | C | When auditors identify that the team struggles to quantify and qualify risks, the project manager should facilitate risk management training for the team. Building the team's risk assessment competency addresses the root capability gap. Asking the sponsor to contribute (A) adds input but does not fix the team's skill deficiency. Inviting stakeholders to participate (B) broadens participation without building capability. Asking an SME to support (D) provides temporary help, not sustained improvement. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 감사 중 여러 리스크가 식별되었다. 감사원들은 팀이 이러한 리스크를 정량화하고 정성적으로 평가하는 데 어려움을 겪고 있음을 발견했다. 프로젝트 관리자는 무엇을 해야 하는가? | 스폰서에게 리스크 관리 프로세스에 기여하도록 요청한다. | 프로젝트 이해관계자를 초대하여 프로세스에 참여하도록 한다. | 팀을 위한 리스크 관리 교육을 촉진한다. | 주제 전문가(SME)에게 팀을 지원하도록 요청한다. |  | C | 감사원이 팀이 리스크를 정량화하고 정성적으로 평가하는 데 어려움을 겪고 있음을 식별할 때, 프로젝트 관리자는 팀을 위한 리스크 관리 교육을 촉진해야 한다. 팀의 리스크 평가 역량을 구축하면 근본적인 역량 격차를 해결한다. 스폰서에게 기여 요청(A)은 입력을 추가하지만 팀의 기술 부족을 해결하지 않는다. 이해관계자 참여 초대(B)는 참여를 확대하지만 역량을 구축하지 않는다. SME 지원 요청(D)은 임시적 도움을 제공하지만 지속적인 개선은 아니다.
550 | A key project stakeholder has started to escalate all issues and main requirements to the project sponsor. The project manager is concerned about the team not receiving direct communications from this stakeholder. Which two actions should the project manager take to improve the relationship with the stakeholder? (Choose two) | Submit performance reports and task assignments to keep the stakeholder informed. | Promote an adaptive and transparent environment where the team can easily communicate with the stakeholders. | Schedule regular meetings with the key stakeholder to provide updates and receive feedback, | Share weekly status reports with detailed information about the project and team performance. | Provide training to the team on emotional intelligence and status reporting techniques. | B, C | When a key stakeholder bypasses the team and escalates everything to the sponsor, the project manager should (C) schedule regular meetings with the stakeholder for updates and feedback, and (B) promote an adaptive and transparent environment for team-stakeholder communication. Regular engagement rebuilds the direct relationship. Submitting performance reports (A) is one-way. Weekly status reports (D) lack interaction. Training on emotional intelligence (E) addresses symptoms, not the relationship. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 핵심 프로젝트 이해관계자가 모든 이슈와 주요 요구사항을 프로젝트 스폰서에게 에스컬레이션하기 시작했다. 프로젝트 관리자는 팀이 이 이해관계자로부터 직접 커뮤니케이션을 받지 못하는 것에 대해 우려하고 있다. 프로젝트 관리자가 이해관계자와의 관계를 개선하기 위해 취해야 할 두 가지 조치는 무엇인가? (2개 선택) | 이해관계자에게 정보를 제공하기 위해 성과 보고서와 작업 할당을 제출한다. | 팀이 이해관계자와 쉽게 소통할 수 있는 적응적이고 투명한 환경을 촉진한다. | 핵심 이해관계자와 업데이트를 제공하고 피드백을 받기 위한 정기 회의를 예약한다. | 프로젝트와 팀 성과에 대한 상세한 정보가 포함된 주간 상태 보고서를 공유한다. | 감성 지능과 상태 보고 기법에 대한 팀 교육을 제공한다. | B, C | 핵심 이해관계자가 팀을 우회하고 모든 것을 스폰서에게 에스컬레이션할 때, 프로젝트 관리자는 (C) 이해관계자와 업데이트 및 피드백을 위한 정기 회의를 예약하고, (B) 팀-이해관계자 커뮤니케이션을 위한 적응적이고 투명한 환경을 촉진해야 한다. 정기적 참여가 직접적 관계를 재건한다. 성과 보고서 제출(A)은 일방적이다. 주간 상태 보고서(D)는 상호작용이 부족하다. 감성 지능 교육(E)은 증상을 다루지 관계를 다루지 않는다.
551 | A project manager is in the middle of handling a major upgrade to an existing product. The project manager learns that the resources initially promised as part of the project are being moved to another priority project. What should the project manager do? | Perform an impact analysis to see the effect on the project. | Retrieve the documentation that shows the resource allocation. | Examine ways of modifying the scope of the project. | Adopt a resource leveling procedure to level the resources. |  | A | When resources initially promised for the project are being moved to another priority project, the project manager should first perform an impact analysis. Understanding the effects on schedule, budget, scope, and quality enables informed decision-making about next steps. Retrieving resource allocation documentation (B) provides evidence but not analysis. Examining scope modification (C) is premature without impact assessment. Resource leveling (D) is a scheduling technique, not an immediate response to resource loss. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 기존 제품의 주요 업그레이드를 처리하는 중이다. 프로젝트 일부로 처음에 약속된 자원이 다른 우선순위 프로젝트로 이동되고 있음을 알게 되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트에 대한 영향을 파악하기 위해 영향 분석을 수행한다. | 자원 할당을 보여주는 문서를 검색한다. | 프로젝트 범위 수정 방법을 검토한다. | 자원 평활화 절차를 채택하여 자원을 평활화한다. |  | A | 프로젝트에 처음 약속된 자원이 다른 우선순위 프로젝트로 이동될 때, 프로젝트 관리자는 먼저 영향 분석을 수행해야 한다. 일정, 예산, 범위, 품질에 대한 영향을 이해하면 다음 단계에 대한 정보에 기반한 의사결정이 가능해진다. 자원 할당 문서 검색(B)은 증거를 제공하지만 분석은 아니다. 범위 수정 검토(C)는 영향 평가 없이 시기상조이다. 자원 평활화(D)는 일정 기법이지 자원 손실에 대한 즉각적 대응이 아니다.
552 | A project manager is assigned to a project that is in development. As the project manager reviews the project's progress, they find a few tasks that are behind schedule. After investigating, the project manager discovers that a few team members were pulled to work on other assignments, which impacted their ability to focus on the project manager's project. Which two actions can the project manager take to bring the team back on track? (Choose two) | Establish daily standups to review project progress and track the completion of deliverables | Allow the team members to catch up at their own pace | Alert the business stakeholders immediately of the schedule delay. | Discuss the risk of project delay and work priorities with the respective functional managers | Work with the team to identify options to accelerate project delivery. | A, E | When team members have been pulled to other assignments causing schedule delays, the project manager should take two actions: establish daily standups to review progress and track deliverables (A), and work with the team to identify options to accelerate delivery (E). Daily standups restore accountability and alignment, while identifying acceleration options—such as fast-tracking, crashing, or re-sequencing—helps recover the schedule. Allowing the team to catch up at their own pace (B) is passive. Alerting stakeholders immediately (C) creates unnecessary panic before internal resolution attempts. Discussing with functional managers (D) addresses the resource conflict but does not directly improve execution. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 개발 중인 프로젝트에 배정되었다. 프로젝트 관리자가 프로젝트 진행 상황을 검토하면서 일정보다 뒤캘진 작업이 몇 개 있음을 발견했다. 조사 결과 몇명의 팀원이 다른 작업에 차출되어 프로젝트에 집중하는 능력에 영향을 미쳤다. 프로젝트 관리자가 팀을 정상 궤도에 돌려놓기 위해 취할 수 있는 두 가지 조치는 무엇인가? (2개 선택) | 프로젝트 진행 상황을 검토하고 산출물 완료를 추적하기 위해 일일 스탠드업을 설정한다. | 팀원이 자체 속도로 따라잡도록 허용한다. | 비즈니스 이해관계자에게 일정 지연을 즉시 알린다. | 프로젝트 지연 리스크와 작업 우선순위를 각 기능 관리자와 논의한다. | 팀과 함께 프로젝트 전달을 가속화할 옵션을 식별한다. | A, E | 팀원들이 다른 작업에 차출되어 일정 지연이 발생할 때, 프로젝트 관리자는 두 가지 조치를 취해야 한다: 진행 상황을 검토하고 산출물을 추적하기 위한 일일 스탠드업 설정(A), 그리고 팀과 함께 전달을 가속화할 옵션 식별(E). 일일 스탠드업은 책임감과 정렬을 회복하고, 가속화 옵션 식별—빨리감기, 크래싱, 재순서화 등—은 일정 회복에 도움이 된다. 자체 속도로 따라잡도록 허용(B)은 수동적이다. 이해관계자에게 즉시 알림(C)은 내부 해결 시도 전에 불필요한 공황을 만든다. 기능 관리자와 논의(D)는 자원 충돌을 다루지만 실행을 직접 개선하지 않는다.
553 | At the closing phase of the project, the project manager sends the completion reports to the client as a formal written document, indicating that the contract has been completed. The client refuses to approve the document since the defect rate is 0.1%. The project manager insists that it is an acceptable rate as the standard defect rate of the industry is 0.15%. What should have been done to avoid this situation? | The client requirements should have been clearly defined in the contract | The Manage Quality process should have been appropriately conducted | The acceptance criteria should have been properly defined in the contract | The project manager should have reviewed the standard industry defect rate |  | C | When a client refuses to approve project completion due to a 0.1% defect rate despite the industry standard being 0.15%, the situation could have been avoided if acceptance criteria had been properly defined in the contract. Clearly documented, measurable acceptance criteria establish mutually agreed quality standards before execution, preventing disputes at closing. Defining client requirements clearly (A) addresses needs but not specific measurable thresholds. Conducting the Manage Quality process (B) ensures quality standards are followed but does not define the acceptance threshold. Reviewing industry defect rates (D) provides context but does not establish the contractual standard. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 프로젝트 종료 단계에서 프로젝트 관리자가 계약이 완료되었음을 나타내는 공식 서면 문서로 완료 보고서를 고객에게 보낸다. 고객은 결함률이 0.1%이므로 문서 승인을 거부한다. 프로젝트 관리자는 업계 표준 결함률이 0.15%이므로 수용 가능한 비율이라고 주장한다. 이 상황을 피하기 위해 무엇을 했어야 하는가? | 고객 요구사항이 계약에 명확히 정의되어야 했다. | 품질 관리 프로세스가 적절히 수행되어야 했다. | 수용 기준이 계약에 적절히 정의되어야 했다. | 프로젝트 관리자가 업계 표준 결함률을 검토했어야 했다. |  | C | 고객이 업계 표준이 0.15%임에도 0.1% 결함률로 인해 프로젝트 완료 승인을 거부할 때, 수용 기준이 계약에 적절히 정의되었다면 이 상황을 피할 수 있었다. 명확하고 측정 가능한 수용 기준은 실행 전에 상호 합의된 품질 표준을 설정하여 종료 시 분쟁을 방지한다. 고객 요구사항 명확한 정의(A)는 필요를 다루지만 구체적이고 측정 가능한 임계값은 다루지 않는다. 품질 관리 프로세스 수행(B)은 품질 표준 준수를 보장하지만 수용 임계값을 정의하지 않는다. 업계 결함률 검토(D)는 맥락을 제공하지만 계약적 기준을 설정하지 않는다.
554 | An IT company's office is closed abruptly due to a new government restriction. All employees are now working remotely. Project team A has a critical project delivery due in 2 weeks. The project manager, apprehensive about this sudden change, instantly emails the customer explaining that the project delivery will be delayed. The customer is unhappy with this and has escalated the issue to senior management. What should the project manager have done differently? | Spoken to the customer on the phone and explained the reason for the delay instead of writing an email | Communicated a new delivery date to the customer along with the news about the delay | Assessed the situation with the project stakeholders first and communicated the impact to the customer | Disclosed to senior management in confidence, then communicated the delay to the customer |  | C | When an abrupt office closure threatens project delivery, the project manager should have assessed the situation with project stakeholders first and then communicated the impact to the customer. Thorough assessment before communication ensures accurate and collaborative information sharing. Speaking on the phone instead of email (A) changes the medium but not the approach. Communicating a new date with the delay notice (B) acts without stakeholder input. Disclosing to senior management first (D) delays customer communication. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | IT 회사의 사무실이 새로운 정부 규제로 갑자기 폐쇄되었다. 모든 직원이 이제 원격으로 근무하고 있다. 프로젝트 팀 A는 2주 내에 중요한 프로젝트 전달이 예정되어 있다. 이 갑작스러운 변화에 불안한 프로젝트 관리자가 즉시 고객에게 프로젝트 전달이 지연될 것이라고 이메일을 보냈다. 고객은 이에 불만을 품고 상급 경영진에 이슈를 에스컬레이션했다. 프로젝트 관리자는 무엇을 다르게 했어야 하는가? | 이메일 대신 고객에게 전화하여 지연 사유를 설명했어야 한다. | 지연 소식과 함께 새로운 전달 날짜를 고객에게 전달했어야 한다. | 먼저 프로젝트 이해관계자와 상황을 평가한 후 고객에게 영향을 전달했어야 한다. | 상급 경영진에게 비밀리에 알린 후 고객에게 지연을 전달했어야 한다. |  | C | 갑작스러운 사무실 폐쇄로 프로젝트 전달이 위협받을 때, 프로젝트 관리자는 먼저 프로젝트 이해관계자와 상황을 평가한 후 고객에게 영향을 전달했어야 한다. 전달 전 철저한 평가는 정확하고 협력적인 정보 공유를 보장한다. 이메일 대신 전화(A)는 매체를 바꾸지만 접근 방식은 바꾸지 않는다. 지연과 함께 새 날짜 전달(B)은 이해관계자 입력 없이 행동한다. 상급 경영진에게 먼저 알리기(D)는 고객 커뮤니케이션을 지연시킨다.
555 | A project manager is managing a mobile application development project when one of the experienced team members starts missing deadlines. The delays will impact project implementation. What should the project manager do next? | Assign an additional resource to help the team member with the tasks. | Convene a team meeting to encourage and motivate the entire team. | Meet with the team member to understand their concerns and/or issues. | Ask the team member ' s functional manager if there are any known issues. |  | C | When an experienced team member starts missing deadlines impacting the project, the project manager should meet with the team member to understand their concerns and issues. Direct conversation identifies root causes. Assigning additional resources (A) treats symptoms. Convening a team meeting (B) is general, not targeted. Asking the functional manager (D) goes around the team member. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Risk | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 모바일 애플리케이션 개발 프로젝트를 관리하고 있는데 경험 있는 팀원 중 한 명이 마감일을 놓치기 시작했다. 지연이 프로젝트 구현에 영향을 미칠 것이다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 팀원의 작업을 돕기 위해 추가 자원을 배정한다. | 팀 전체를 격려하고 동기를 부여하기 위해 팀 회의를 소집한다. | 팀원과 만나 그들의 우려 사항 및/또는 이슈를 파악한다. | 팀원의 기능 관리자에게 알려진 이슈가 있는지 확인한다. |  | C | 경험 있는 팀원이 프로젝트에 영향을 미치는 마감일을 놓치기 시작할 때, 프로젝트 관리자는 팀원과 만나 그들의 우려와 이슈를 파악해야 한다. 직접적인 대화가 근본 원인을 식별한다. 추가 자원 배정(A)은 증상을 치료한다. 팀 회의 소집(B)은 일반적이지 대상화되지 않는다. 기능 관리자에게 확인(D)은 팀원을 우회한다.
556 | A project team member is having difficulty delivering assigned tasks for a project that is at risk of being delayed. The main issue is that the team member does not understand a new system that was recently implemented. What should the project manager do? | Issue a change request to extend the project schedule | Escalate the team members performance to the project sponsor | Assign an experienced resource to support the team member | Ask the team member to learn the new system as on-the-job training |  | C | When a team member struggles with a newly implemented system, putting the project at risk of delay, the project manager should assign an experienced resource to support the team member. Direct mentoring provides immediate, practical help to overcome the specific challenge. Issuing a change request for schedule extension (A) treats the symptom. Escalating performance to the sponsor (B) is punitive without first providing support. On-the-job training without support (D) is insufficient for a struggling team member. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀원이 지연 위험이 있는 프로젝트에서 배정된 작업을 전달하는 데 어려움을 겪고 있다. 주요 문제는 팀원이 최근 구현된 새 시스템을 이해하지 못하는 것이다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 일정을 연장하기 위한 변경 요청을 발행한다. | 팀원의 성과를 프로젝트 스폰서에게 에스컬레이션한다. | 팀원을 지원하기 위해 경험 있는 자원을 배정한다. | 팀원에게 새 시스템을 현장 교육(OJT)으로 학습하도록 요청한다. |  | C | 팀원이 새로 구현된 시스템에 어려움을 겪어 프로젝트 지연 위험이 있을 때, 프로젝트 관리자는 팀원을 지원하기 위해 경험 있는 자원을 배정해야 한다. 직접적인 멘토링은 특정 과제를 극복하기 위한 즉각적이고 실질적인 도움을 제공한다. 일정 연장 변경 요청(A)은 증상을 치료한다. 스폰서에게 성과 에스컬레이션(B)은 먼저 지원을 제공하지 않고 징벌적이다. 지원 없는 OJT(D)는 어려움을 겪는 팀원에게 불충분하다.
557 | An experienced project manager has recently joined a troubled project. The project is impacted by multiple delays caused by a vendor's late delivery of new servers. Due to budget restrictions, the project manager cannot switch vendors, and the project must be completed within a maximum of 90 days as agreed. What should the project manager do? | Reach out to the vendor to determine a plan to get the project back on track | Review lessons learned from previous projects and take action accordingly | Wait until the project deadline is reached in order to use contingency funds | Request the vendor to provide the servers on time as penalties may be applied |  | A | When facing multiple delays from a vendor's late server delivery with no option to switch vendors within a 90-day deadline, the project manager should reach out to the vendor to determine a plan to get the project back on track. Active supplier engagement enables collaborative recovery. Reviewing lessons learned (B) provides historical insight but does not directly resolve the current issue. Waiting for contingency funds (C) is reactive and risks the deadline. Requesting delivery with penalty threats (D) may damage collaboration. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 경험 있는 프로젝트 관리자가 최근 문제가 있는 프로젝트에 합류했다. 프로젝트는 벤더의 새 서버 납기 지연으로 인한 여러 지연의 영향을 받고 있다. 예산 제약으로 인해 프로젝트 관리자는 벤더를 교체할 수 없으며, 합의된 대로 최대 90일 이내에 프로젝트를 완료해야 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 벤더에게 연락하여 프로젝트를 정상 궤도에 올릴 계획을 수립한다. | 이전 프로젝트의 교훈을 검토하고 그에 따라 조치를 취한다. | 비상 자금을 사용하기 위해 프로젝트 마감일까지 기다린다. | 벤더에게 페널티가 적용될 수 있으므로 제시간에 서버를 제공하도록 요청한다. |  | A | 90일 기한 내에 벤더를 교체할 수 없는 상황에서 벤더의 서버 납기 지연으로 여러 지연이 발생할 때, 프로젝트 관리자는 벤더에게 연락하여 프로젝트를 정상 궤도에 올릴 계획을 수립해야 한다. 적극적인 공급자 참여가 협력적 회복을 가능하게 한다. 교훈 검토(B)는 역사적 통찰을 제공하지만 현재 이슈를 직접 해결하지 않는다. 비상 자금 대기(C)는 수동적이며 마감일을 위험에 빠뜨린다. 페널티 위협과 함께 납기 요청(D)은 협력을 손상시킬 수 있다.
558 | A project manager's customer is new to agile approaches. When the customer found out that the project was going to use an agile approach, the customer became concerned that the product quality will be sacrificed. What should the project manager do? | Invite the customer to join the daily standup meetings to better understand the product design and progress. 1217 | Invite the customer to join the regular sprint planning sessions to better understand the project ' s progress. | Ensure that the customer and the delivery team agree on the definition of done (DoD) in the beginning of the project. | Ensure the team demonstrates product features to this customer regularly to collect feedback and improve as needed. |  | D | When a customer new to agile is concerned about quality being sacrificed, the project manager should ensure the team demonstrates product features regularly to collect feedback and improve as needed. Regular demonstrations build confidence through transparency. Inviting to daily standups (A) may overwhelm the customer. Sprint planning sessions (B) are technical. Agreeing on definition of done (C) is important but demonstrations provide tangible evidence. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 관리자의 고객이 애자일 접근 방식에 익숙하지 않다. 고객이 프로젝트가 애자일 접근 방식을 사용할 것이라는 것을 알게 되자 제품 품질이 희생될 것이라고 우려했다. 프로젝트 관리자는 무엇을 해야 하는가? | 고객이 제품 설계와 진행 상황을 더 잘 이해할 수 있도록 일일 스탠드업 회의에 참여하도록 초대한다. | 고객이 프로젝트 진행 상황을 더 잘 이해할 수 있도록 정기 스프린트 계획 세션에 참여하도록 초대한다. | 프로젝트 초기에 고객과 전달 팀이 완료 정의(DoD)에 합의하도록 보장한다. | 팀이 이 고객에게 정기적으로 제품 기능을 시연하여 피드백을 수집하고 필요에 따라 개선하도록 보장한다. |  | D | 애자일에 익숙하지 않은 고객이 품질 희생을 우려할 때, 프로젝트 관리자는 팀이 정기적으로 제품 기능을 시연하여 피드백을 수집하고 필요에 따라 개선하도록 보장해야 한다. 정기 시연은 투명성을 통해 신뢰를 구축한다. 일일 스탠드업 초대(A)는 고객을 압도할 수 있다. 스프린트 계획 세션(B)은 기술적이다. 완료 정의 합의(C)는 중요하지만 시연이 실질적인 증거를 제공한다.
559 | A project manager is leading the construction of a high-rise mall for a customer in an emerging competitive market. Some customers want to move in as soon as the ground floor is completed. What should the project manager do to deliver business value to the client? | Use management reserve and crash the schedule | Explain the need to follow the quality assurance (QA) schedule to the customer | Adopt an incremental project delivery approach | Implement an agile project delivery approach |  | C | When customers want to move into the ground floor as soon as it is completed, the project manager should adopt an incremental project delivery approach. Incremental delivery allows usable portions of the mall to be handed over earlier, enabling tenants to begin operations and the client to generate revenue sooner. This directly supports business value realization while maintaining construction quality and sequencing requirements. Crashing the schedule with management reserve (A) increases cost and risk without addressing the value delivery strategy. Implementing agile delivery (D) is not the best fit for high-rise construction where scope and dependencies are largely deterministic. Explaining the QA schedule (B) is necessary for safety compliance but does not address the client's business need for early occupancy. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Schedule | Monitoring & Controlling | Focus on Value | Control Schedule | Traditional PM | 프로젝트 관리자가 경쟁이 치열한 신흥 시장에서 고객을 위한 고층 쇼핑몰 건설을 이끌고 있다. 일부 고객들이 1층이 완공되는 대로 입주하기를 원한다. 프로젝트 관리자는 고객에게 비즈니스 가치를 전달하기 위해 무엇을 해야 하는가? | 관리 예비비를 사용하고 일정을 크래싱한다. | 고객에게 품질 보증(QA) 일정을 따라야 할 필요성을 설명한다. | 점진적 프로젝트 전달 접근 방식을 채택한다. | 애자일 프로젝트 전달 접근 방식을 구현한다. |  | C | 고객들이 1층이 완공되는 대로 입주하기를 원할 때, 프로젝트 관리자는 점진적 프로젝트 전달 접근 방식을 채택해야 한다. 점진적 전달은 쇼핑몰의 사용 가능한 부분을 더 일찍 인도하여 세입자가 운영을 시작하고 고객이 더 빨리 수익을 창출할 수 있게 한다. 이는 건설 품질과 순서 요구사항을 유지하면서 비즈니스 가치 실현을 직접 지원한다. 관리 예비비로 일정 크래싱(A)은 가치 전달 전략을 다루지 않고 비용과 리스크를 증가시킨다. 애자일 전달 구현(D)은 범위와 의존성이 대부분 결정론적인 고층 건설에 가장 적합하지 않다. QA 일정 설명(B)은 안전 규정 준수에 필요하지만 조기 입주에 대한 고객의 비즈니스 요구를 다루지 않는다.
560 | During a project planning meeting, a product manager and team are finalizing the project deliverables and notice that a key feature has a dependency from another team. A team member suggests removing the feature from the scope. What should the project manager do? | Discuss the issue with the team so the product manager can understand the trade-offs. | Advise the team not to reduce the scope of the feature because the product manager originally included that requirement. | Suggest the team and product manager go with the faster approach, reducing the scope. | Prepare a presentation for the project sponsor with the team that includes both solutions and seek the sponsor ' s guidance. |  | A | The correct answer is A. Discuss the issue with the team so the product manager can understand the trade-offs. Resource management includes ensuring team members have the necessary skills and support. The PM should identify gaps and address them through training, mentoring, or other appropriate measures. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 계획 회의 중 제품 관리자와 팀이 프로젝트 산출물을 확정하고 있는데 핵심 기능이 다른 팀으로부터 의존성이 있음을 발견한다. 팀원이 범위에서 해당 기능을 제거하자고 제안한다. 프로젝트 관리자는 무엇을 해야 하는가? | 제품 관리자가 트레이드오프를 이해할 수 있도록 팀과 이슈를 논의한다. | 제품 관리자가 원래 해당 요구사항을 포함했으므로 기능 범위를 축소하지 않도록 팀에 조언한다. | 팀과 제품 관리자에게 범위를 축소하는 더 빠른 접근 방식으로 가도록 제안한다. | 두 가지 솔루션을 포함한 프레젠테이션을 팀과 함께 프로젝트 스폰서를 위해 준비하고 스폰서의 지침을 구한다. |  | A | 정답은 A이다. 제품 관리자가 트레이드오프를 이해할 수 있도록 팀과 이슈를 논의한다. 자원 관리에는 팀원들이 필요한 기술과 지원을 갖추도록 보장하는 것이 포함된다. PM은 격차를 식별하고 교육, 멘토링 또는 기타 적절한 조치를 통해 해결해야 한다.
561 | While managing a project using a hybrid approach, the project manager realizes that there is a high level of rework due to quality issues. Because of that, each feature is taking longer than initially estimated. What should the project manager do to address the issue? | Escalate the issue to the project sponsor. | Extend the dates for future project milestones. | Initiate a change request to extend the project end date. | Address the issue during the next sprint planning meeting. |  | D | When a hybrid project experiences high rework due to quality issues causing features to take longer than estimated, the project manager should address the issue during the next sprint planning meeting. This leverages the agile inspect-and-adapt cycle to discuss root causes and implement corrective actions collaboratively. Escalating to the sponsor (A) bypasses the team's problem-solving capability. Extending milestone dates (B) treats symptoms, not the root cause. Initiating a change request for a date extension (C) is premature without team-level corrective action. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Hybrid/Tailoring | 하이브리드 접근 방식을 사용하여 프로젝트를 관리하는 동안, 프로젝트 관리자가 품질 이슈로 인해 높은 수준의 재작업이 발생하고 있음을 인식한다. 이로 인해 각 기능이 초기 추정보다 더 오래 걸리고 있다. 프로젝트 관리자는 이 이슈를 해결하기 위해 무엇을 해야 하는가? | 이슈를 프로젝트 스폰서에게 에스컬레이션한다. | 향후 프로젝트 마일스톤의 날짜를 연장한다. | 프로젝트 종료일을 연장하기 위한 변경 요청을 개시한다. | 다음 스프린트 계획 회의에서 이슈를 다룬다. |  | D | 하이브리드 프로젝트에서 품질 이슈로 인한 높은 재작업으로 기능이 추정보다 더 오래 걸릴 때, 프로젝트 관리자는 다음 스프린트 계획 회의에서 이슈를 다루어야 한다. 이는 애자일의 검사-적응 주기를 활용하여 근본 원인을 논의하고 협력적으로 시정 조치를 구현한다. 스폰서에게 에스컬레이션(A)은 팀의 문제 해결 능력을 우회한다. 마일스톤 날짜 연장(B)은 근본 원인이 아닌 증상을 치료한다. 종료일 연장 변경 요청 개시(C)는 팀 수준의 시정 조치 없이 시기상조이다.
562 | A steering committee has asked the project manager to assist with the decision-making process between build versus buy delivery options. Which value metric should the project manager evaluate to respond to the steering committee's request? | Earned value (EV) | Expected monetary value (EMV) | Net present value (NPV) | Impact value |  | C | When the steering committee needs to decide between build versus buy options, the project manager should evaluate net present value (NPV). NPV compares long-term investments by discounting future costs and benefits to present value, enabling objective comparison. Earned value (A) measures execution performance. Expected monetary value (B) is for risk-based decisions. Impact value (D) is not a recognized PMI metric. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 운영 위원회가 프로젝트 관리자에게 자체 구축 대 구매 전달 옵션 간 의사결정 프로세스를 지원하도록 요청했다. 프로젝트 관리자는 운영 위원회의 요청에 응답하기 위해 어떤 가치 지표를 평가해야 하는가? | 획득 가치(EV) | 기대 화폐 가치(EMV) | 순현재가치(NPV) | 영향 가치 |  | C | 운영 위원회가 자체 구축 대 구매 옵션 간 결정이 필요할 때, 프로젝트 관리자는 순현재가치(NPV)를 평가해야 한다. NPV는 미래 비용과 혜택을 현재 가치로 할인하여 장기 투자를 비교하며 객관적인 비교를 가능하게 한다. 획득 가치(A)는 실행 성과를 측정한다. 기대 화폐 가치(B)는 리스크 기반 의사결정을 위한 것이다. 영향 가치(D)는 인정된 PMI 지표가 아니다.
563 | During the execution of a financial project, a project manager met with the project team weekly to evaluate the project's progress. However, the sponsor requests that project performance be checked daily. The key team members disagree with this requirement and argue that they do not have enough time to go to daily meetings because they are at an executive level. What should the project manager do first? | Evaluate the capacity of each team member to attend daily meetings in person or virtually and reduce the time of each meeting. | Review the communications management plan and submit a change request if required. | Recommend to the sponsor that performance of the project be reviewed once per week. | Negotiate with the key team members to send a daily report and let the sponsor know that the project cost will increase. ty |  | B | When the sponsor requests daily performance checks but key team members at executive level resist, the project manager should first review the communications management plan and submit a change request if required. The CMP defines communication agreements. Evaluating capacity and reducing meeting time (A) is a solution but should follow plan review. Recommending weekly reviews (C) may not satisfy the sponsor. Negotiating daily reports (D) bypasses governance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 금융 프로젝트 실행 중 프로젝트 관리자가 프로젝트 팀과 매주 만나 프로젝트 진행 상황을 평가했다. 그러나 스폰서가 프로젝트 성과를 매일 확인하도록 요청한다. 핵심 팀원들은 임원급이기 때문에 매일 회의에 참석할 시간이 없다고 반대한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 각 팀원이 대면 또는 가상으로 매일 회의에 참석할 수 있는 역량을 평가하고 각 회의 시간을 줄인다. | 커뮤니케이션 관리 계획을 검토하고 필요시 변경 요청을 제출한다. | 스폰서에게 프로젝트 성과를 주 1회 검토하도록 권고한다. | 핵심 팀원들과 일일 보고서를 보내도록 협상하고 스폰서에게 프로젝트 비용이 증가할 것이라고 알린다. |  | B | 스폰서가 매일 성과 확인을 요청하지만 임원급 핵심 팀원들이 반대할 때, 프로젝트 관리자는 먼저 커뮤니케이션 관리 계획을 검토하고 필요시 변경 요청을 제출해야 한다. 커뮤니케이션 관리 계획은 커뮤니케이션 합의를 정의한다. 역량 평가 및 회의 시간 단축(A)은 솔루션이지만 계획 검토 후에 해야 한다. 주간 검토 권고(C)는 스폰서를 만족시키지 못할 수 있다. 일일 보고서 협상(D)은 거버넌스를 우회한다.
564 | A new project manager was assigned to a project during implementation. The project manager realized that new tax policies are creating a risk for a cost overrun by 25%. The project manager updated the risk register and kept the project running as normal. The CEO has announced that the project could be cancelled since the acceptable cost overrun is only 20%. The project manager was quite surprised as this was new information. What should the project manager have done to avoid this? | Provided a proper risk response | Implemented the communications management plan properly | Ensured the risk tolerance of the company was property updated | Implemented the stakeholder engagement plan correctly. |  | B | When the CEO announces the project could be cancelled due to a cost overrun threshold the PM was unaware of, the project manager should have implemented the communications management plan properly. Effective stakeholder communication would have surfaced the CEO's risk tolerance earlier, enabling the PM to align risk responses accordingly. The communications plan defines how project information—including risks, their impacts, and proposed responses—is shared with stakeholders at appropriate frequency and detail. Providing a proper risk response (A) was done (updating the risk register), but without communicating the risk to the right stakeholders, it was insufficient. Updating risk tolerance (C) is the sponsor's responsibility. Implementing the stakeholder engagement plan (D) is related but the specific gap was in communicating risk information. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 새로운 프로젝트 관리자가 구현 중인 프로젝트에 배정되었다. 프로젝트 관리자는 새로운 세금 정책이 25% 비용 초과 리스크를 만들고 있음을 인식했다. 프로젝트 관리자는 리스크 레지스터를 업데이트하고 프로젝트를 정상적으로 운영했다. CEO가 허용 가능한 비용 초과가 20%에 불과하므로 프로젝트가 취소될 수 있다고 발표했다. 프로젝트 관리자는 이것이 새로운 정보여서 매우 놀랐다. 프로젝트 관리자는 이를 피하기 위해 무엇을 했어야 하는가? | 적절한 리스크 대응을 제공했어야 한다. | 커뮤니케이션 관리 계획을 적절히 이행했어야 한다. | 회사의 리스크 허용 범위가 적절히 업데이트되도록 보장했어야 한다. | 이해관계자 참여 계획을 올바르게 이행했어야 한다. |  | B | CEO가 PM이 몰랐던 비용 초과 임계값으로 인해 프로젝트가 취소될 수 있다고 발표할 때, 프로젝트 관리자는 커뮤니케이션 관리 계획을 적절히 이행했어야 한다. 효과적인 이해관계자 커뮤니케이션은 CEO의 리스크 허용 범위를 더 일찍 파악하여 PM이 리스크 대응을 그에 맞게 정렬할 수 있게 했을 것이다. 적절한 리스크 대응 제공(A)은 수행되었지만(리스크 레지스터 업데이트) 올바른 이해관계자에게 전달하지 않아 불충분했다. 리스크 허용 범위 업데이트(C)는 스폰서의 책임이다. 이해관계자 참여 계획 이행(D)은 관련이 있지만 구체적인 격차는 리스크 정보 전달에 있었다.
565 | A project manager has been assigned to a new agile project with rapidly changing knowledge areas. How should the project manager manage knowledge transfers on this project? | Work with QA to ensure domain knowledge is transferred properly among stakeholders | Mentor the team and stakeholders to ensure domain knowledge is exchanged during sprints | Require stakeholders to fully document all domain knowledge before starting | Ask the team to set up initial sprints for knowledge transfer before focusing on deliverables |  | B | For an agile project with rapidly changing knowledge areas, the project manager should mentor the team and stakeholders to ensure domain knowledge is exchanged during sprints. Embedding knowledge transfer into the delivery cadence through pairing, shared demos, and collaborative practices ensures continuous, sustainable learning. Requiring complete documentation before starting (C) delays value and becomes outdated quickly. Dedicating initial sprints to knowledge transfer (D) postpones delivery. Relying on QA for knowledge transfer (A) misaligns QA's role. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Lean | Business Environment | Plan and Manage Risk | Risk | Planning | Integrate Sustainability | Identify Risks | Sustainability | 프로젝트 관리자가 지식 영역이 빠르게 변화하는 새로운 애자일 프로젝트에 배정되었다. 프로젝트 관리자는 이 프로젝트에서 지식 이전을 어떻게 관리해야 하는가? | 도메인 지식이 이해관계자 간에 적절히 이전되도록 QA와 협력한다. | 스프린트 중 도메인 지식이 교환되도록 팀과 이해관계자를 멘토링한다. | 시작 전에 이해관계자에게 모든 도메인 지식을 완전히 문서화하도록 요구한다. | 팀에게 산출물에 집중하기 전에 지식 이전을 위한 초기 스프린트를 설정하도록 요청한다. |  | B | 지식 영역이 빠르게 변화하는 애자일 프로젝트에서 프로젝트 관리자는 스프린트 중 도메인 지식이 교환되도록 팀과 이해관계자를 멘토링해야 한다. 페어링, 공유 데모, 협력적 실천을 통해 전달 주기에 지식 이전을 내재화하면 지속적이고 지속 가능한 학습이 보장된다. 시작 전 완전한 문서화 요구(C)는 가치를 지연시키고 빠르게 구식이 된다. 지식 이전을 위한 초기 스프린트 할당(D)은 전달을 연기한다. 지식 이전을 QA에 의존(A)은 QA의 역할과 맞지 않는다.
566 | A project manager's team has been working very hard to meet a critical deadline. Some project team members are experiencing burnout due to the high workload. What should the project manager do first to manage the team's workload effectively? | Assign additional tasks to high-performing team members to decrease the burden on others. | Add additional temporary resources to the project to achieve the next milestone. | Encourage open communication and involve the team in task distribution decisions. | Renegotiate the scope of the next milestone with the stakeholders to align with the team ' s capacity. |  | C | The correct answer is C. Encourage open communication and involve the team in task distribution decisions. Effective leadership involves understanding team dynamics, addressing root causes, and creating a supportive environment. The PM should foster collaboration and well-being to maintain high performance. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자의 팀이 중요한 마감일을 맞추기 위해 매우 열심히 일하고 있다. 일부 프로젝트 팀원들이 높은 업무량으로 인해 번아웃을 경험하고 있다. 프로젝트 관리자는 팀의 업무량을 효과적으로 관리하기 위해 먼저 무엇을 해야 하는가? | 다른 사람들의 부담을 줄이기 위해 고성과 팀원에게 추가 작업을 배정한다. | 다음 마일스톤을 달성하기 위해 프로젝트에 추가 임시 자원을 투입한다. | 개방적 커뮤니케이션을 장려하고 팀을 작업 배분 결정에 참여시킨다. | 팀의 역량에 맞추기 위해 이해관계자와 다음 마일스톤의 범위를 재협상한다. |  | C | 정답은 C이다. 개방적 커뮤니케이션을 장려하고 팀을 작업 배분 결정에 참여시킨다. 효과적인 리더십은 팀 역학을 이해하고, 근본 원인을 다루며, 지원적 환경을 만드는 것을 포함한다. PM은 높은 성과를 유지하기 위해 협력과 웰빙을 촉진해야 한다.
567 | A project manager has recently joined an organization and notices that the engineering manager shouts at the project manager during project meetings. Also, the procurement manager will not return calls, and the accountant always insists the project manager clears approved budget line items with them personally before expensing. Which three corrective actions should the project manager perform? (Choose three) | Avoid the people causing stress and request a transfer as soon as possible | Discuss the possible actions with the project sponsor | Confront the people causing the stress directly with the aim of finding amicable solutions | Seek support from the project management office (PMO) on addressing issues affecting the project | Talk to the human resources (HR) manager about these concerns | C, D, E | When facing unprofessional behavior from colleagues, the PM should take three corrective actions: confront the people causing the stress directly with the aim of finding amicable solutions (C), seek support from the project management office (PMO) on addressing issues affecting the project (D), and talk to the human resources (HR) manager about these concerns (E). Direct confrontation with cooperative intent addresses root causes. PMO provides professional guidance and organizational resources. HR can intervene on behavioral issues with formal authority. Avoiding the people and requesting a transfer (A) does not resolve the underlying problem. Discussing with the project sponsor (B) is not the primary recourse for workplace behavioral issues. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Risk | Planning | Build an Empowered Culture | Plan Risk Management | Traditional PM | 프로젝트 관리자가 최근 한 조직에 합류했는데 엔지니어링 관리자가 프로젝트 회의 중 프로젝트 관리자에게 소리를 지른다. 또한 조달 관리자는 전화를 받지 않으며, 회계사는 항상 프로젝트 관리자가 승인된 예산 항목을 지출하기 전에 개인적으로 확인하도록 요구한다. 프로젝트 관리자가 수행해야 할 세 가지 시정 조치는? (3개 선택) | 스트레스를 유발하는 사람들을 피하고 가능한 빨리 전근을 요청한다. | 프로젝트 스폰서와 가능한 조치를 논의한다. | 우호적인 해결책을 찾기 위해 스트레스를 유발하는 사람들과 직접 대면한다. | 프로젝트에 영향을 미치는 이슈에 대해 프로젝트 관리 오피스(PMO)의 지원을 구한다. | 이러한 우려 사항에 대해 인사부(HR) 관리자와 대화한다. | C, D, E | 동료들의 비전문적 행동에 직면했을 때, PM은 세 가지 시정 조치를 취해야 한다: 우호적 해결을 목표로 스트레스를 유발하는 사람들에게 직접 대면하고(C), 프로젝트에 영향을 미치는 이슈 해결을 위해 PMO의 지원을 구하고(D), HR 관리자에게 이러한 우려를 논의한다(E). 협력적 의도의 직접 대면은 근본 원인을 해결한다. PMO는 전문적 지침과 조직 자원을 제공한다. HR은 공식 권한으로 행동 이슈에 개입할 수 있다. 회피하고 전근 요청(A)은 근본 문제를 해결하지 않는다. 프로젝트 스폰서와 논의(B)는 직장 행동 이슈의 주요 수단이 아니다.
568 | A project leader is assigned to a new project and is asked to assemble an effective five-member agile team. If the project leader has no restrictions, which team should they choose? | A team whose members work independently and are the best subject matter experts(SMES) | A team whose members have more general aptitudes and can collaborate on different tasks | A team whose members have more general aptitudes but like to work individually 1194 | A team whose members have different skill sets and are spread out geographically |  | B | When assembling a five-member agile team with no restrictions, the project leader should choose a team whose members have general aptitudes and can collaborate on different tasks. Agile teams need cross-functional, collaborative members. Independent SMEs (A) lack collaboration. General aptitudes with individual work preference (C) misses collaboration. Different skill sets spread geographically (D) introduces coordination challenges. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 리더가 새 프로젝트에 배정되어 효과적인 5인 애자일 팀을 구성하도록 요청받았다. 프로젝트 리더에게 제한이 없다면 어떤 팀을 선택해야 하는가? | 독립적으로 작업하며 최고의 주제 전문가(SME)인 팀원들로 구성된 팀 | 더 일반적인 적성을 가지고 다양한 작업에서 협업할 수 있는 팀원들로 구성된 팀 | 더 일반적인 적성을 가지지만 개인적으로 작업하는 것을 선호하는 팀원들로 구성된 팀 | 다양한 기술 세트를 가지고 지리적으로 분산된 팀원들로 구성된 팀 |  | B | 제한 없이 5인 애자일 팀을 구성할 때, 프로젝트 리더는 일반적인 적성을 가지고 다양한 작업에서 협업할 수 있는 팀원들로 구성된 팀을 선택해야 한다. 애자일 팀은 교차 기능적이고 협력적인 멤버가 필요하다. 독립적인 SME(A)는 협력이 부족하다. 일반적 적성이지만 개인 작업 선호(C)는 협력이 부족하다. 다양한 기술이지만 지리적으로 분산(D)된 팀은 조율 과제를 초래한다.
569 | The project management office (PMO) assigns a project manager who specializes in hybrid approaches to a predictive project that is off track from both the cost and schedule perspectives. The project runs into further delays as the project manager is ramping up on the project. The stakeholders ask senior management to replace the project manager. How should the project manager approach this situation? | Escalate the stakeholder issue to the management team and ask for help with resolving the conflict. | Continue to work on the project until the stakeholders and management come to a decision. | Meet with the stakeholders to understand their concerns and define an action plan to resolve issues. | Socialize with the stakeholders to better understand their needs and reset expectations. |  | C | When stakeholders request the PM's replacement due to further delays during ramp-up on a predictive project, the project manager should meet with the stakeholders to understand their concerns and define an action plan to resolve issues. Proactive stakeholder engagement addresses dissatisfaction directly. Escalating to management (A) asks others to solve the PM's problem. Continuing until management decides (B) is passive. Socializing without addressing root causes (D) avoids the real issue. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Hybrid/Tailoring | 프로젝트 관리 오피스(PMO)가 하이브리드 접근 방식을 전문으로 하는 프로젝트 관리자를 비용과 일정 면에서 궤도를 이탈한 예측형 프로젝트에 배정했다. 프로젝트 관리자가 프로젝트에 적응하는 동안 추가 지연이 발생한다. 이해관계자들이 상급 경영진에게 프로젝트 관리자를 교체하도록 요청한다. 프로젝트 관리자는 이 상황에 어떻게 접근해야 하는가? | 이해관계자 이슈를 경영 팀에 에스컬레이션하고 갈등 해결을 요청한다. | 이해관계자와 경영진이 결정을 내릴 때까지 프로젝트 작업을 계속한다. | 이해관계자와 만나 우려 사항을 이해하고 이슈 해결을 위한 실행 계획을 정의한다. | 이해관계자와 친교를 다져 그들의 요구를 더 잘 이해하고 기대치를 재설정한다. |  | C | 적응 기간 중 추가 지연으로 이해관계자가 PM 교체를 요청할 때, 프로젝트 관리자는 이해관계자와 만나 우려 사항을 이해하고 이슈 해결을 위한 실행 계획을 정의해야 한다. 사전 예방적 이해관계자 참여가 불만을 직접 다룬다. 경영진에 에스컬레이션(A)은 다른 사람에게 PM의 문제를 해결하도록 요청한다. 경영진이 결정할 때까지 계속(B)은 수동적이다. 근본 원인을 다루지 않는 친교(D)는 실질적 이슈를 회피한다.
570 | A project manager has been informed by a vendor that a shipment of supplies needed for the project will be delayed by 6 weeks. What should the project manager do first? | Find another vendor to deliver the required supplies on time. | Ask the procurement manager to resolve the issue with the vendor. | Document this as a risk and define a risk response plan. | Treat the risk as an issue and launch the risk response plan. |  | D | The vendor has already confirmed a 6-week delay, meaning this is no longer a risk—it has materialized into an issue. The project manager should treat it as an issue and execute the risk response plan that was previously defined for this scenario. Finding another vendor (A) might be part of a response strategy but should not be the first action—it bypasses established project controls. Asking the procurement manager to resolve it (B) delegates the problem without first applying the planned response. Documenting it as a new risk (C) is incorrect because the event has already occurred; it is an active issue requiring immediate management, not identification as a future uncertainty. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 벤더로부터 프로젝트에 필요한 물품 배송이 6주 지연될 것이라는 통보를 받았다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 필요한 물품을 제시간에 납품할 다른 벤더를 찾는다. | 조달 관리자에게 벤더와의 이슈를 해결하도록 요청한다. | 이것을 리스크로 문서화하고 리스크 대응 계획을 정의한다. | 리스크를 이슈로 취급하고 리스크 대응 계획을 실행한다. |  | D | 벤더가 이미 6주 지연을 확인했으므로 이는 더 이상 리스크가 아니라 이슈로 실현되었다. 프로젝트 관리자는 이를 이슈로 취급하고 이 시나리오에 대해 이전에 정의된 리스크 대응 계획을 실행해야 한다. 다른 벤더 찾기(A)는 대응 전략의 일부일 수 있지만 첫 번째 조치가 되어서는 안 된다—확립된 프로젝트 통제를 우회한다. 조달 관리자에게 요청(B)은 계획된 대응을 먼저 적용하지 않고 문제를 위임한다. 새로운 리스크로 문서화(C)는 이벤트가 이미 발생했으므로 부적절하다; 이는 미래 불확실성이 아니라 즉각적인 관리가 필요한 활성 이슈이다.
571 | A project manager is leading a global project with resources spread out in different locations. The stakeholders have different interpretations of the requirements. The project manager is concerned about scope creep. Which action should the project manager take to control the scope? | Ensure that all key stakeholders agree to the project deliverables and there will be no 604 need for changes. | Reject all changes that will increase the budget or increase the time line of the project. | Accept only those changes to requirements that provide additional value to the project. | Accept only those changes that are approved by the change control board (CCB) prior to being implemented. |  | D | When stakeholders have different interpretations of requirements and scope creep is a concern, the project manager should accept only those changes approved by the change control board (CCB) prior to implementation. Formal change control ensures all changes are evaluated, approved, and aligned with project objectives. Ensuring stakeholder agreement on no changes (A) is unrealistic. Rejecting all budget or timeline changes (B) is too rigid. Accepting only value-adding changes (C) lacks formal governance. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Finance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 프로젝트 관리자가 다양한 지역에 자원이 분산된 글로벌 프로젝트를 이끄고 있다. 이해관계자들이 요구사항에 대해 다른 해석을 가지고 있다. 프로젝트 관리자는 범위 크리프가 우려된다. 프로젝트 관리자는 범위를 통제하기 위해 어떤 조치를 취해야 하는가? | 모든 핵심 이해관계자가 프로젝트 산출물에 합의하고 변경이 필요하지 않도록 보장한다. | 예산이나 일정을 증가시키는 모든 변경을 거부한다. | 프로젝트에 추가 가치를 제공하는 요구사항 변경만 수락한다. | 변경 통제 위원회(CCB)가 구현 전에 승인한 변경만 수락한다. |  | D | 이해관계자들이 요구사항에 대해 다른 해석을 가지고 범위 크리프가 우려될 때, 프로젝트 관리자는 변경 통제 위원회(CCB)가 구현 전에 승인한 변경만 수락해야 한다. 공식적인 변경 통제는 모든 변경이 평가되고 승인되며 프로젝트 목표에 정렬되도록 보장한다. 변경 없음에 대한 이해관계자 합의 보장(A)은 비현실적이다. 모든 예산/일정 변경 거부(B)는 너무 경직하다. 가치 추가 변경만 수락(C)은 공식적인 거버넌스가 부족하다.
572 | After establishing a cost baseline and the appropriate cost management plan for a complex hybrid project, the project is still being challenged with cases of budgetary variations. What should the project manager do? | Approve budget variations upon request only when the cost performance index (CPI) is above 1. | Track budget variations and work with the key stakeholders to adjust as necessary. | Reject budget variations upon request to discourage the waste of money on the project. | Approve budget variations upon request to encourage rapid delivery of some components. |  | B | The correct answer is B. Track budget variations and work with the key stakeholders to adjust as necessary. A hybrid approach leverages the strengths of both predictive and agile methodologies. The PM should tailor the approach to the project's unique characteristics and organizational environment. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 복잡한 하이브리드 프로젝트에 대한 비용 기준선과 적절한 비용 관리 계획을 수립한 후에도 프로젝트는 여전히 예산 변동 사례로 어려움을 겪고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 비용 성과 지수(CPI)가 1 이상일 때만 요청 시 예산 변동을 승인한다. | 예산 변동을 추적하고 핵심 이해관계자와 협력하여 필요에 따라 조정한다. | 프로젝트에서 예산 낭비를 억제하기 위해 요청 시 예산 변동을 거부한다. | 일부 컴포넌트의 신속한 전달을 장려하기 위해 요청 시 예산 변동을 승인한다. |  | B | 정답은 B이다. 예산 변동을 추적하고 핵심 이해관계자와 협력하여 필요에 따라 조정한다. 하이브리드 접근 방식은 예측형과 애자일 방법론의 강점을 활용한다. PM은 프로젝트의 고유한 특성과 조직 환경에 맞게 접근 방식을 맞춤화해야 한다.
573 | A project manager receives a call from the customer's account manager requesting support for a critical operational issue. Although the issue is unrelated to the project, the customer believes that one of the project team members has the technical expertise to recommend a solution. What should the project manager do first? | Decline the request politely since the issue, although critical, is not the responsibility of the project team. | Organize a conference call with the internal expert and the client to estimate the amount of effort required to fix it. | Inform the customer that they should contact the sales manager and submit a formal request for a quote. | Allocate a task to the team member as a high priority and inform the customer that the issue will be resolved the next day. |  | A | When a customer requests project team support for an unrelated operational issue, the project manager should decline the request politely since the issue is not the responsibility of the project team. The PM must protect the team from external interference that could affect performance and availability, while respecting contractual scope boundaries. Organizing a call to estimate effort (B) implies commitment to out-of-scope work. Directing the customer to the sales manager (C) is appropriate as a follow-up suggestion but not the first action. Allocating a task as high priority (D) creates unauthorized scope creep. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 고객의 영업 관리자로부터 중요한 운영 문제에 대한 지원을 요청하는 전화를 받는다. 이 문제는 프로젝트와 관련이 없지만, 고객은 프로젝트 팀원 중 한 명이 솔루션을 추천할 기술 전문 지식을 가지고 있다고 생각한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 문제가 중요하지만 프로젝트 팀의 책임이 아니므로 요청을 정중히 거절한다. | 내부 전문가와 고객과의 컨퍼런스 콜을 조직하여 수정에 필요한 노력의 양을 추정한다. | 고객에게 영업 관리자에게 연락하여 공식 견적 요청서를 제출하라고 알린다. | 팀원에게 높은 우선순위로 작업을 배정하고 고객에게 다음 날 문제가 해결될 것이라고 알린다. |  | A | 고객이 프로젝트와 관련 없는 운영 문제에 대해 프로젝트 팀 지원을 요청할 때, 프로젝트 관리자는 문제가 프로젝트 팀의 책임이 아니므로 요청을 정중히 거절해야 한다. PM은 성과와 가용성에 영향을 줄 수 있는 외부 간섭으로부터 팀을 보호해야 하며, 계약적 범위 경계를 존중해야 한다. 노력 추정을 위한 통화 조직(B)은 범위 외 작업에 대한 약속을 암시한다. 영업 관리자에게 안내(C)는 후속 제안으로는 적절하지만 첫 번째 조치는 아니다. 높은 우선순위 작업 배정(D)은 승인되지 않은 범위 변경을 만든다.
574 | After a performance review, a team member approaches the project manager and asks for feedback. The project manager mentions anecdotal information about this team member being a positive team player and generally getting their work done on time, even though they have been late with work once or twice. The team member expresses frustration at not having better information included in the annual performance review. What should the project manager do to prevent this frustration going forward? | Set team performance goals and explain how the team receives the same performance scores. | Review the key performance indicators (KPIs) for this team member and remind the team member how they are determined. | Provide the team member with velocity tracking tools and explain how the team member can see and track performance. | Request the human resource (HR) department to provide the key performance indicators (KPls) that were defined for this project. |  | B | When a team member is frustrated about lacking objective performance data in their review, the project manager should review the KPIs for the team member and remind them how they are determined. Transparent metrics-based feedback prevents future frustrations. Setting team performance goals (A) focuses on team, not individual. Providing velocity tracking tools (C) is narrow. Requesting HR to provide KPIs (D) delegates the PM's responsibility. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 성과 검토 후 팀원이 프로젝트 관리자에게 피드백을 요청한다. 프로젝트 관리자는 이 팀원이 긍정적인 팀 플레이어이고 일반적으로 제시간에 작업을 완료하지만 한두 번 늦었다는 일화적 정보를 언급한다. 팀원은 연간 성과 검토에 더 나은 정보가 포함되지 않은 것에 좌절감을 표현한다. 프로젝트 관리자는 향후 이 좌절감을 방지하기 위해 무엇을 해야 하는가? | 팀 성과 목표를 설정하고 팀이 동일한 성과 점수를 받는 방법을 설명한다. | 이 팀원의 핵심 성과 지표(KPI)를 검토하고 팀원에게 어떻게 결정되는지 상기시킨다. | 팀원에게 속도 추적 도구를 제공하고 팀원이 성과를 확인하고 추적할 수 있는 방법을 설명한다. | 인사부(HR)에 이 프로젝트에 대해 정의된 핵심 성과 지표(KPI)를 제공하도록 요청한다. |  | B | 팀원이 성과 검토에서 객관적인 성과 데이터 부족에 좌절할 때, 프로젝트 관리자는 팀원의 KPI를 검토하고 어떻게 결정되는지 상기시켜야 한다. 투명한 지표 기반 피드백은 향후 좌절감을 방지한다. 팀 성과 목표 설정(A)은 개인이 아닌 팀에 초점을 맞춘다. 속도 추적 도구 제공(C)은 범위가 좁다. HR에 KPI 제공 요청(D)은 PM의 책임을 위임한다.
575 | In an agile project, the project manager notices that one team member rarely reports blockers during daily check-ins. Additionally, the team member is too shy to participate in team activities and prefers to provide status updates individually to the project manager. How should the project manager rectify this situation? | Create a safe space for status updates and encourage the team to approach the project manager. | Review team culture and the personality traits of the individual to address status update gaps. | Support team inclusion and change the format of status updates to email. | Review the team status updates more thoroughly to address the gaps. |  | B | When a team member rarely reports blockers, is too shy to participate in team activities, and prefers individual status updates, the project manager should review team culture and the personality traits of the individual to address the gaps. Understanding the root cause—whether it is personality, cultural factors, trust issues, or team dynamics—is essential before implementing solutions. Creating a safe space for updates (A) is a possible follow-up action but does not address the root cause first. Supporting inclusion and switching to email (C) accommodates the behavior without understanding it. Reviewing status updates more thoroughly (D) monitors symptoms but does not resolve the underlying issue. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scaled Agile | People | Engage Stakeholders | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트에서 프로젝트 관리자는 한 팀원이 일일 체크인에서 장애물을 거의 보고하지 않는 것을 발견한다. 또한 이 팀원은 팀 활동에 참여하기에 너무 수줍어하며 프로젝트 관리자에게 개별적으로 상태 업데이트를 제공하는 것을 선호한다. 프로젝트 관리자는 이 상황을 어떻게 시정해야 하는가? | 상태 업데이트를 위한 안전한 공간을 만들고 팀이 프로젝트 관리자에게 접근하도록 격려한다. | 팀 문화와 개인의 성격 특성을 검토하여 상태 업데이트 격차를 해결한다. | 팀 포용을 지원하고 상태 업데이트 형식을 이메일로 변경한다. | 팀 상태 업데이트를 더 철저히 검토하여 격차를 해결한다. |  | B | 팀원이 장애물을 거의 보고하지 않고, 팀 활동에 참여하기 수줍어하며, 개별 상태 업데이트를 선호할 때, 프로젝트 관리자는 팀 문화와 개인의 성격 특성을 검토하여 격차를 해결해야 한다. 근본 원인—성격, 문화적 요인, 신뢰 문제, 팀 역학—을 이해하는 것이 솔루션 구현 전에 필수적이다. 안전한 공간 만들기(A)는 가능한 후속 조치이지만 근본 원인을 먼저 다루지 않는다. 포용 지원 및 이메일 전환(C)은 행동을 수용하지만 이해하지 않는다. 상태 업데이트 철저 검토(D)는 증상을 모니터링하지만 근본 문제를 해결하지 않는다.
576 | A project team is performing extremely well when it comes to delivering the value-added features to the customer in each sprint. However, they are missing the documentation portion and the project manager must find a way to make sure the documentation is kept current. Which action should the project manager take? | Make documentation a standard part of the definition of done (DoD). | Focus on the documentation after the features are delivered. | Assign a dedicated resource to work on the documentation during the project. | Create a specific sprint to deliver the project documentation. |  | A | When an agile team delivers value-added features successfully but falls behind on documentation, the project manager should make documentation a standard part of the definition of done (DoD). This ensures documentation is treated with the same priority as development work and completed alongside each sprint's deliverables. Focusing on documentation after features (B) postpones a persistent problem. Assigning a dedicated documentation resource (C) separates documentation from the team's responsibility. Creating a specific documentation sprint (D) disrupts the delivery cadence. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 프로젝트 팀이 각 스프린트에서 고객에게 부가가치 기능을 전달하는 데 매우 잘 수행하고 있다. 그러나 문서화 부분을 놓치고 있으며 프로젝트 관리자는 문서화가 최신 상태로 유지되도록 방법을 찾아야 한다. 프로젝트 관리자는 어떤 조치를 취해야 하는가? | 문서화를 완료의 정의(DoD)의 표준 부분으로 만든다. | 기능이 전달된 후 문서화에 집중한다. | 프로젝트 기간 동안 문서화 작업을 위한 전담 자원을 배정한다. | 프로젝트 문서화를 전달하기 위한 특정 스프린트를 만든다. |  | A | 애자일 팀이 부가가치 기능을 성공적으로 전달하지만 문서화에 뒤처질 때, 프로젝트 관리자는 문서화를 완료의 정의(DoD)의 표준 부분으로 만들어야 한다. 이는 문서화가 개발 작업과 동일한 우선순위로 취급되고 각 스프린트의 산출물과 함께 완료되도록 보장한다. 기능 이후 문서화 집중(B)은 지속적인 문제를 미룬다. 전담 문서화 자원 배정(C)은 문서화를 팀의 책임에서 분리한다. 특정 문서화 스프린트 생성(D)은 전달 리듬을 방해한다.
577 | The execution stage of a construction project is beginning. There are many areas and phases to be built. The project team wants to review the relationships between the most important tasks to ensure that major items are executed properly during this stage. What project artifact should the project manager review with the team? | Project program evaluation review technique (PERT) | Project statement of work (SOW) | Project schedule management plan | Project milestone chart |  | A | When a construction project team wants to review relationships between the most important tasks at the start of execution, the project manager should review the PERT (Program Evaluation and Review Technique) diagram. A PERT-style network diagram visualizes logical relationships, dependencies, and sequencing among activities—essential for coordinating complex construction phases. The SOW (B) describes deliverables and contractual terms, not task relationships. The schedule management plan (C) explains how the schedule will be managed, not the dependencies themselves. A milestone chart (D) shows key dates but not detailed task relationships. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Schedule | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 건설 프로젝트의 실행 단계가 시작되고 있다. 건설할 많은 영역과 단계가 있다. 프로젝트 팀은 이 단계에서 주요 항목이 적절히 실행되도록 가장 중요한 작업 간의 관계를 검토하고자 한다. 프로젝트 관리자는 팀과 어떤 프로젝트 산출물을 검토해야 하는가? | 프로젝트 PERT(Program Evaluation Review Technique) | 프로젝트 작업 기술서(SOW) | 프로젝트 일정 관리 계획 | 프로젝트 마일스톤 차트 |  | A | 건설 프로젝트 팀이 실행 시작 시 가장 중요한 작업 간의 관계를 검토하고자 할 때, 프로젝트 관리자는 PERT(Program Evaluation and Review Technique) 다이어그램을 검토해야 한다. PERT 스타일 네트워크 다이어그램은 활동 간의 논리적 관계, 의존성, 순서를 시각화하여 복잡한 건설 단계를 조율하는 데 필수적이다. SOW(B)는 산출물과 계약 조건을 설명하지 작업 관계를 설명하지 않는다. 일정 관리 계획(C)은 일정 관리 방법을 설명하지 의존성 자체를 설명하지 않는다. 마일스톤 차트(D)는 주요 날짜를 보여주지만 상세한 작업 관계는 보여주지 않는다.
578 | A company is about to start a complex research project. Due to the level of uncertainty, the project manager recommends the use of a hybrid approach; however, the organization only has experience with predictive projects. How can the project manager strategize the use of a hybrid approach to the organization? | Create a project change request to execute the project using a hybrid approach. | Send a letter to the project management office (PMO) requesting to use a hybrid approach. | Submit a notification to the project team confirming they will be using a hybrid approach on the project. | Present the benefits of a hybrid approach to key stakeholders to get their support. |  | D | For a complex research project with high uncertainty, gaining organizational support is critical before implementing a hybrid approach. The project manager should present the benefits of a hybrid methodology to key stakeholders, explaining how it combines predictive structure with adaptive flexibility—particularly valuable when requirements are uncertain or likely to evolve. Creating a change request (A) is procedural but premature without stakeholder buy-in. Sending a letter to the PMO (B) lacks the persuasive engagement needed. Notifying the team that hybrid will be used (C) assumes the decision has already been made and bypasses organizational alignment. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Hybrid/Tailoring | 회사가 복잡한 연구 프로젝트를 시작하려 한다. 불확실성 수준으로 인해 프로젝트 관리자는 하이브리드 접근 방식의 사용을 권장하지만, 조직은 예측형 프로젝트에 대한 경험만 있다. 프로젝트 관리자는 어떻게 조직에 하이브리드 접근 방식의 사용을 전략화할 수 있는가? | 하이브리드 접근 방식으로 프로젝트를 실행하기 위한 프로젝트 변경 요청을 생성한다. | 프로젝트 관리 오피스(PMO)에 하이브리드 접근 방식 사용을 요청하는 서한을 보낸다. | 프로젝트 팀에 프로젝트에서 하이브리드 접근 방식을 사용할 것임을 확인하는 통지를 제출한다. | 주요 이해관계자에게 하이브리드 접근 방식의 이점을 제시하여 지지를 얻는다. |  | D | 불확실성이 높은 복잡한 연구 프로젝트에서 조직적 지지를 얻는 것이 하이브리드 접근 방식 구현 전에 중요하다. 프로젝트 관리자는 주요 이해관계자에게 하이브리드 방법론의 이점을 제시하여 예측형 구조와 적응형 유연성의 결합이 요구사항이 불확실하거나 진화할 가능성이 있을 때 특히 가치 있음을 설명해야 한다. 변경 요청 생성(A)은 절차적이지만 이해관계자 동의 없이는 시기상조이다. PMO에 서한 발송(B)은 필요한 설득적 참여가 부족하다. 팀에 하이브리드 사용 통지(C)는 결정이 이미 내려졌다고 가정하고 조직적 정렬을 우회한다.
579 | A project manager is a part of the project management office (PMO) and is tasked with finding a reputable vendor to provide on-site support for their project. The project sponsor stresses the urgency of the need and suggests using a vendor they know to provide the support. What should the project manager do given the urgency? | Source vendors with extensive experience. | Perform research on experienced vendors in the market. | Consult preferred vendors from the company. | Follow the company ' s standard vendor selection criteria process, |  | D | When the sponsor suggests using a vendor they know for urgent on-site support, the project manager should follow the company's standard vendor selection criteria process. Proper procurement process ensures fair selection and organizational compliance regardless of urgency. Sourcing vendors with extensive experience (A) is subjective. Performing market research (B) delays response. Consulting preferred vendors (C) may be part of the process but is incomplete. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 프로젝트 관리 오피스(PMO)의 일원이며 프로젝트를 위해 현장 지원을 제공할 신뢰할 수 있는 벤더를 찾는 업무를 맡고 있다. 프로젝트 스폰서는 필요의 긴급성을 강조하며 자신이 아는 벤더를 사용하여 지원을 제공하도록 제안한다. 긴급성을 고려할 때 프로젝트 관리자는 무엇을 해야 하는가? | 광범위한 경험을 가진 벤더를 소싱한다. | 시장에서 경험 있는 벤더에 대한 조사를 수행한다. | 회사의 선호 벤더를 참고한다. | 회사의 표준 벤더 선정 기준 프로세스를 따른다. |  | D | 스폰서가 긴급한 현장 지원을 위해 자신이 아는 벤더 사용을 제안할 때, 프로젝트 관리자는 회사의 표준 벤더 선정 기준 프로세스를 따라야 한다. 적절한 조달 프로세스는 긴급성과 관계없이 공정한 선정과 조직적 준수를 보장한다. 광범위한 경험을 가진 벤더 소싱(A)은 주관적이다. 시장 조사 수행(B)은 대응을 지연시킨다. 선호 벤더 참고(C)는 프로세스의 일부일 수 있지만 불완전하다.
580 | A project manager is assigned to lead a team comprised of business executives. After several roadmaps were denied by the sponsor, the project manager asks to be removed from the project. The sponsor urges the project manager to find a solution as the sponsoring organization requested their assignment. What should the project manager do? | Schedule deliverables solely based on priorities and must-have-by dates, and gauge responses | Emphasize to the executives that the project manager was specifically requested for this project | Hold a team meeting emphasizing existing governance policies and procedures | Adopt a project framework aligned to the executives' availabilities and then evaluate the risks |  | D | When leading executives and multiple roadmaps are denied by the sponsor, the project manager should adopt a project framework aligned to the executives' availabilities and then evaluate the risks. Adapting governance to stakeholder capacity enables progress. Emphasizing being specifically requested (A) does not solve the planning problem. Scheduling solely on must-have dates (B) ignores feasibility. Emphasizing existing governance policies (C) may be confrontational without adapting to executive realities. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 관리자가 비즈니스 임원들로 구성된 팀을 이끌도록 배정되었다. 여러 로드맵이 스폰서에 의해 거부된 후, 프로젝트 관리자가 프로젝트에서 제외해 달라고 요청한다. 스폰서는 스폰서 조직이 프로젝트 관리자의 배정을 요청했으므로 해결책을 찾으라고 촉구한다. 프로젝트 관리자는 무엇을 해야 하는가? | 우선순위와 반드시 필요한 날짜에만 기반하여 산출물 일정을 수립하고 반응을 평가한다. | 임원들에게 프로젝트 관리자가 이 프로젝트를 위해 특별히 요청되었음을 강조한다. | 기존 거버넌스 정책과 절차를 강조하는 팀 회의를 개최한다. | 임원들의 가용성에 맞춘 프로젝트 프레임워크를 채택한 후 리스크를 평가한다. |  | D | 임원들을 이끌면서 여러 로드맵이 스폰서에 의해 거부될 때, 프로젝트 관리자는 임원들의 가용성에 맞춘 프로젝트 프레임워크를 채택한 후 리스크를 평가해야 한다. 이해관계자 역량에 맞게 거버넌스를 조정하면 진전이 가능해진다. 특별히 요청되었음을 강조(A)는 계획 문제를 해결하지 않는다. 반드시 필요한 날짜에만 기반한 일정(B)은 실현 가능성을 무시한다. 기존 거버넌스 정책 강조(C)는 임원들의 현실에 적응하지 않으면 대립적일 수 있다.
581 | A team member in an agile project informs the project manager they might not be able to finish an assigned task on time, which could generate an obstacle for the rest of the team. What should the project manager do? | Ask the team member to bring up the concern in the next daily meeting. | Reassign the task to another team member. | Move the task to the next sprint. | Send an email explaining the issue to all team members. |  | A | When a team member anticipates being unable to finish an assigned task on time, which could obstruct the rest of the team, the project manager should ask the team member to bring up the concern in the next daily meeting. Transparency in standups enables team collaboration. Reassigning the task (B) may not address the underlying issue. Moving to the next sprint (C) delays value. Emailing all team members (D) is impersonal and less collaborative. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 프로젝트에서 팀원이 프로젝트 관리자에게 배정된 작업을 제시간에 완료하지 못할 수 있으며, 이는 나머지 팀에 장애가 될 수 있다고 알린다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원에게 다음 일일 회의에서 우려를 제기하도록 요청한다. | 작업을 다른 팀원에게 재배정한다. | 작업을 다음 스프린트로 이동한다. | 모든 팀원에게 이슈를 설명하는 이메일을 보낸다. |  | A | 팀원이 배정된 작업을 제시간에 완료하지 못하여 나머지 팀에 장애가 될 수 있음을 예상할 때, 프로젝트 관리자는 팀원에게 다음 일일 회의에서 우려를 제기하도록 요청해야 한다. 스탠드업에서의 투명성은 팀 협업을 가능하게 한다. 작업 재배정(B)은 근본 문제를 해결하지 못할 수 있다. 다음 스프린트로 이동(C)은 가치를 지연시킨다. 모든 팀원에게 이메일 발송(D)은 비인간적이고 덜 협력적이다.
582 | A project manager has expertise in the technical domain. The project manager frequently demonstrates unacceptable behavior toward other team members; however, when confronted, the project manager denies this behavior. What is the reason for the project manager's behavior? | The project manager lacks necessary empathy. | The project manager lacks emotional intelligence (El). | The project manager was not properly trained. | The project manager is in the wrong project role. |  | B | When a technically expert project manager frequently demonstrates unacceptable behavior toward team members but denies it when confronted, the underlying cause is a lack of emotional intelligence (EI). EI encompasses self-awareness, self-regulation, empathy, and social skills—deficiencies in which lead to poor behavioral control and inability to recognize one's impact on others. Lacking empathy (A) is a component of EI but not the complete picture. Lacking proper training (C) does not explain the denial of behavior. Being in the wrong role (D) does not address the behavioral pattern. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자가 기술 도메인에 전문성을 가지고 있다. 프로젝트 관리자는 다른 팀원들에게 자주 용납할 수 없는 행동을 보이지만, 직면하면 이 행동을 부인한다. 프로젝트 관리자의 행동 원인은 무엇인가? | 프로젝트 관리자에게 필요한 공감 능력이 부족하다. | 프로젝트 관리자에게 감성 지능(EI)이 부족하다. | 프로젝트 관리자가 적절한 교육을 받지 못했다. | 프로젝트 관리자가 잘못된 프로젝트 역할에 있다. |  | B | 기술적으로 전문적인 프로젝트 관리자가 팀원들에게 자주 용납할 수 없는 행동을 보이지만 직면하면 부인할 때, 근본 원인은 감성 지능(EI) 부족이다. EI는 자기 인식, 자기 조절, 공감, 사회적 기술을 포함하며, 이러한 결핍은 행동 통제 부족과 타인에 대한 자신의 영향을 인식하지 못하는 것으로 이어진다. 공감 부족(A)은 EI의 한 구성요소이지만 전체 그림이 아니다. 적절한 교육 부족(C)은 행동의 부인을 설명하지 못한다. 잘못된 역할(D)은 행동 패턴을 다루지 않는다.
583 | A project manager is managing a large project. During a review meeting, the project manager discovers that one of the team members who used to be a high performer was not able to complete their work on time. What should the project manager do? | Talk to the team member to determine why their performance changed. | Talk to the project lead and ask them to allocate less demanding tasks. | Talk to the team member and a human resources (HR) representative. | Talk to the team member ' s manager to provide more training. |  | A | When a formerly high-performing team member's performance declines, the project manager should talk directly to the team member to determine why their performance changed. Direct, empathetic conversation helps identify underlying personal or professional challenges and demonstrates the PM's engagement with team wellbeing. Talking to the project lead to assign less demanding tasks (B) assumes the reason without investigation. Talking to the team member with HR (C) may feel escalatory and formal before understanding the issue. Talking to the team member's manager about training (D) delegates responsibility without first understanding the problem. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 관리자가 대규모 프로젝트를 관리하고 있다. 검토 회의 중 이전에 고성과를 보였던 팀원 중 한 명이 제시간에 작업을 완료하지 못했음을 발견한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원과 대화하여 성과가 변한 이유를 파악한다. | 프로젝트 리드에게 덜 까다로운 작업을 배정하도록 요청한다. | 팀원과 인사부(HR) 담당자와 함께 대화한다. | 팀원의 관리자에게 추가 교육을 제공하도록 요청한다. |  | A | 이전에 고성과를 보였던 팀원의 성과가 저하될 때, 프로젝트 관리자는 팀원과 직접 대화하여 성과가 변한 이유를 파악해야 한다. 직접적이고 공감적인 대화는 근본적인 개인적 또는 전문적 문제를 식별하고 PM의 팀 복지에 대한 관심을 보여준다. 프로젝트 리드에게 덜 까다로운 작업 배정 요청(B)은 조사 없이 원인을 가정한다. HR과 함께 대화(C)는 문제를 이해하기 전에 에스컬레이션적이고 공식적으로 느껴질 수 있다. 관리자에게 교육 요청(D)은 먼저 문제를 이해하지 않고 책임을 위임한다.
584 | A project is starting its first iteration out of six. During one of the daily meetings, the project manager realized that one of the team members does not have experience working in agile environments. What should the project manager do? | Give the team member some time to learn agile practices. | Ask to increase the capacity of the team to finish on time. | Ask the sponsor for additional budget for training. | Assign an agile mentor and follow the training process. |  | D | The correct answer is D. Assign an agile mentor and follow the training process. Daily standups/scrums are key synchronization points in agile. They help the team identify impediments, coordinate work, and maintain transparency. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트가 6개 이터레이션 중 첫 번째 이터레이션을 시작하고 있다. 일일 회의 중 프로젝트 관리자는 팀원 중 한 명이 애자일 환경에서의 근무 경험이 없음을 깨달았다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원에게 애자일 실천법을 배울 시간을 준다. | 제시간에 완료하기 위해 팀 역량을 증가시키도록 요청한다. | 스폰서에게 교육을 위한 추가 예산을 요청한다. | 애자일 멘토를 배정하고 교육 프로세스를 따른다. |  | D | 정답은 D이다. 애자일 멘토를 배정하고 교육 프로세스를 따른다. 일일 스탠드업/스크럼은 애자일에서 핵심 동기화 지점이다. 이는 팀이 장애물을 식별하고 작업을 조율하며 투명성을 유지하는 데 도움이 된다.
585 | A project lead is managing an agile project. The project activities, which have been placed in a backlog, still need to be refined and prioritized. What should the project lead use for backlog refinement considering the sprints are 2 weeks long? | Sixty minutes every sprint going through stories with higher story points. | Ninety minutes every three sprints going through stories that are higher priority. | Sixty minutes every sprint going through stories that are higher priority. | Ninety minutes every three sprints going through stories with higher story points. |  | C | The correct answer is C. Sixty minutes every sprint going through stories that are higher priority. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 프로젝트 리더가 애자일 프로젝트를 관리하고 있다. 백로그에 배치된 프로젝트 활동은 여전히 정제와 우선순위 지정이 필요하다. 스프린트가 2주인 점을 고려하여 프로젝트 리더는 백로그 정제에 무엇을 사용해야 하는가? | 매 스프린트마다 높은 스토리 포인트의 스토리를 검토하는 60분. | 3 스프린트마다 높은 우선순위의 스토리를 검토하는 90분. | 매 스프린트마다 높은 우선순위의 스토리를 검토하는 60분. | 3 스프린트마다 높은 스토리 포인트의 스토리를 검토하는 90분. |  | C | 정답은 C이다. 매 스프린트마다 높은 우선순위의 스토리를 검토하는 60분. 애자일 환경에서 PM은 팀 협업을 촉진하고 장애물을 제거하며 애자일 원칙을 준수하면서 지속적인 가치 전달을 보장해야 한다.
586 | An organization is about to start a time-critical project and has decided to use an agile approach for the first time. However, stakeholders are worried they will not be able to verify project status because they believe their usual governance model will not work for an agile project. What should the project manager do? | Meet with stakeholders to discuss and review the governance structure | Review the governance structure to reflect scope changes | Recommend following the existing governance structure with the project team | Discuss using a hybrid governance structure with stakeholders |  | A | When stakeholders worry about governance in a first-time agile project, the project manager should meet with stakeholders to discuss and review the governance structure. Collaborative governance design builds confidence and adapts oversight to agile practices. Discussing a hybrid governance structure (A) presupposes the solution. Following existing governance unchanged (C) may not fit agile delivery. Reviewing governance only for scope changes (D) is too narrow. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Hybrid/Tailoring | 조직이 시간이 중요한 프로젝트를 시작하려 하며 처음으로 애자일 접근 방식을 사용하기로 결정했다. 그러나 이해관계자들은 기존 거버넌스 모델이 애자일 프로젝트에 적합하지 않다고 생각하여 프로젝트 상태를 확인할 수 없을 것이라 걱정한다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자와 만나 거버넌스 구조를 논의하고 검토한다. | 범위 변경을 반영하기 위해 거버넌스 구조를 검토한다. | 프로젝트 팀과 함께 기존 거버넌스 구조를 따르도록 권고한다. | 이해관계자와 하이브리드 거버넌스 구조 사용을 논의한다. |  | A | 처음으로 애자일 프로젝트에서 이해관계자가 거버넌스에 대해 걱정할 때, 프로젝트 관리자는 이해관계자와 만나 거버넌스 구조를 논의하고 검토해야 한다. 협력적 거버넌스 설계는 신뢰를 구축하고 애자일 실천에 맞게 감독을 조정한다. 하이브리드 거버넌스 구조 논의(D)는 솔루션을 전제한다. 기존 거버넌스를 변경 없이 따르기(C)는 애자일 전달에 적합하지 않을 수 있다. 범위 변경만을 위한 거버넌스 검토(B)는 너무 범위가 좁다.
587 | What is the correct way to put an organization on the proper path to changing their mindset to an agile approach? | Hire employees who specialize in agile approaches so they can better contribute toprojects. | Shift the way the company views, reviews, and assesses employees. | Train all employees in agile approaches. | Assign employees to agile projects so they can quickly adjust to the new approach. |  | B | The correct way to put an organization on the path to an agile mindset is to shift the way the company views, reviews, and assesses employees. Agile transformation requires cultural change in how people are evaluated and empowered, not just process changes. Hiring agile specialists (A) adds capability but does not change organizational culture. Training all employees (C) builds knowledge but not mindset. Assigning employees to agile projects (D) provides exposure but not cultural transformation. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Agile General Practices | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 조직을 애자일 접근 방식으로 마인드셋을 변경하는 올바른 경로에 올려놓는 정확한 방법은 무엇인가? | 애자일 접근 방식에 전문화된 직원을 고용하여 프로젝트에 더 잘 기여할 수 있게 한다. | 회사가 직원을 보고, 검토하고, 평가하는 방식을 전환한다. | 모든 직원에게 애자일 접근 방식을 교육한다. | 직원을 애자일 프로젝트에 배정하여 새로운 접근 방식에 빠르게 적응하도록 한다. |  | B | 조직을 애자일 마인드셋의 경로에 올려놓는 올바른 방법은 회사가 직원을 보고, 검토하고, 평가하는 방식을 전환하는 것이다. 애자일 전환은 프로세스 변경만이 아닌 사람들이 평가되고 권한을 부여받는 방식의 문화적 변화를 요구한다. 애자일 전문가 고용(A)은 역량을 추가하지만 조직 문화를 변경하지 않는다. 모든 직원 교육(C)은 지식을 쌓지만 마인드셋은 아니다. 애자일 프로젝트 배정(D)은 노출을 제공하지만 문화적 전환은 아니다.
588 | A project team is conducting sprint planning. Based on the estimated effort, only 95% of the items included in the sprint may be delivered. The product owner asks the project manager for advice on how to prioritize the backlog items. What should be used to prioritize the backlog items? | Business value | Estimation accuracy | Technical complexity | Risk to delivery |  | A | During sprint planning, when only 95% of items can be delivered, backlog items should be prioritized based on business value. This ensures the most valuable features are developed first, providing immediate benefits and enabling early stakeholder feedback. Business value aligns the team's efforts with organizational strategy and stakeholder needs. Estimation accuracy (B) relates to planning reliability, not prioritization. Technical complexity (C) may inform effort estimates but should not drive priority. Risk to delivery (D) is a consideration but secondary to the fundamental question of which items deliver the most business value. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 팀이 스프린트 계획을 진행하고 있다. 추정된 노력에 기반하여 스프린트에 포함된 항목의 95%만 전달될 수 있다. 제품 책임자가 프로젝트 관리자에게 백로그 항목의 우선순위 지정 방법에 대한 조언을 구한다. 백로그 항목의 우선순위를 지정하는 데 무엇을 사용해야 하는가? | 비즈니스 가치 | 추정 정확도 | 기술적 복잡성 | 전달 리스크 |  | A | 스프린트 계획 중 항목의 95%만 전달될 수 있을 때, 백로그 항목은 비즈니스 가치를 기준으로 우선순위를 지정해야 한다. 이는 가장 가치 있는 기능이 먼저 개발되어 즉각적인 혜택을 제공하고 조기 이해관계자 피드백을 가능하게 한다. 비즈니스 가치는 팀의 노력을 조직 전략 및 이해관계자 요구와 정렬시킨다. 추정 정확도(B)는 계획 신뢰성에 관련되지 우선순위 지정에는 관련되지 않는다. 기술적 복잡성(C)은 노력 추정을 알려주지만 우선순위를 주도해서는 안 된다. 전달 리스크(D)는 고려 사항이지만 가장 많은 비즈니스 가치를 전달하는 근본적 질문에 비해 부차적이다.
589 | A project needs to purchase a specific piece of equipment, as stated in the project documents and approved by the project sponsor. The procurement division is questioning the need to buy the specific brand of equipment and has suggested buying a cheaper alternative instead. What should the project manager have done earlier in the project to ensure the purchase of the specific equipment? | Included a procurement division member on the project team | Communicated the project management plan to the procurement division | Reminded the project sponsor about the procurement division ' s reputation | Communicated the project charter to the procurement division |  | B | When the procurement division questions a specific equipment purchase approved in project documents, the project manager should have communicated the project management plan to the procurement division earlier. The plan includes the procurement management plan detailing procurement strategy and requirements. Including a procurement member on the team (A) may not be necessary. Reminding the sponsor of procurement's reputation (C) is unprofessional. Communicating the charter (D) lacks procurement-specific detail. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Procurement | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트에서 프로젝트 문서에 명시되고 프로젝트 스폰서가 승인한 특정 장비를 구매해야 한다. 조달 부서가 특정 브랜드 장비 구매의 필요성에 의문을 제기하며 대신 더 저렴한 대안을 구매하자고 제안했다. 프로젝트 관리자는 특정 장비 구매를 보장하기 위해 프로젝트 초반에 무엇을 했어야 하는가? | 프로젝트 팀에 조달 부서 직원을 포함시쯄다. | 조달 부서에 프로젝트 관리 계획을 커뮤니케이션했다. | 프로젝트 스폰서에게 조달 부서의 평판을 상기시쯄다. | 조달 부서에 프로젝트 헌장을 커뮤니케이션했다. |  | B | 조달 부서가 프로젝트 문서에서 승인된 특정 장비 구매에 의문을 제기할 때, 프로젝트 관리자는 조기에 조달 부서에 프로젝트 관리 계획을 커뮤니케이션했어야 한다. 계획에는 조달 전략과 요구사항을 상세히 설명하는 조달 관리 계획이 포함된다. 팀에 조달 직원 포함(A)은 필요하지 않을 수 있다. 스폰서에게 조달부서 평판 상기(C)는 비전문적이다. 헌장 커뮤니케이션(D)은 조달 관련 세부 사항이 부족하다.
590 | A project started 12 months ago and is currently on iteration 12 of 14. The team has performed well and completed all deliverables on time. However, some team members are starting to complain about the length of the project, creating a risk for lack of performance at this critical stage. What should the project manager do as a servant leader to mitigate this risk? | Meet with the team to reinforce their responsibilities and the consequences if theproject deliverables are not completed on time. | Contact the functional manager to ensure that team motivation remains high untilthe end of the project. | Apply additional controls to the project deliverables to ensure that all milestonesare achieved on time. | Schedule a team event with the project sponsor to highlight the importance of theproject and recognize the work of the team. |  | D | When team members complain about project length near the end, risking performance decline, the project manager as servant leader should schedule a team event with the sponsor to highlight the project's importance and recognize the team. Recognition boosts morale. Reinforcing responsibilities and consequences (A) is authoritarian. Applying additional controls (C) is micromanaging. Contacting the functional manager (B) delegates the PM's leadership role. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트가 12개월 전에 시작되어 현재 14개 이터레이션 중 12번째를 진행 중이다. 팀은 잘 수행하여 모든 산출물을 제시간에 완료했다. 그러나 일부 팀원들이 프로젝트의 길이에 대해 불만을 제기하기 시작하여 이 중요한 단계에서 성과 부족 리스크를 만들고 있다. 서번트 리더로서 프로젝트 관리자는 이 리스크를 완화하기 위해 무엇을 해야 하는가? | 팀과 만나 책임과 산출물이 제시간에 완료되지 않을 경우의 결과를 강조한다. | 기능 관리자에게 연락하여 프로젝트 끝까지 팀 동기가 높게 유지되도록 보장한다. | 모든 마일스톤이 제시간에 달성되도록 프로젝트 산출물에 추가 통제를 적용한다. | 프로젝트 스폰서와 함께 프로젝트의 중요성을 강조하고 팀의 작업을 인정하는 팀 이벤트를 예약한다. |  | D | 팀원들이 프로젝트 마무리 근처에서 프로젝트 길이에 대해 불만을 제기하여 성과 저하 리스크가 있을 때, 서번트 리더로서 프로젝트 관리자는 스폰서와 함께 프로젝트의 중요성을 강조하고 팀의 작업을 인정하는 팀 이벤트를 예약해야 한다. 인정은 사기를 높인다. 책임과 결과 강조(A)는 권위적이다. 추가 통제 적용(C)은 마이크로매니징이다. 기능 관리자에게 연락(B)은 PM의 리더십 역할을 위임한다.
591 | A hybrid project manager has taken over a large-scale software development project in a highly regulated environment. During a handover session, the outgoing project manager explains that they devised their own status reports, which is different from the project management office's (PMO's) status report style. The project stakeholders are extremely particular about the information they receive in updates and do not believe the PMO's status reports have sufficient information. How should the new project manager proceed? | Explain to the PMO that the hybrid project team needs to keep an agile approach for reporting and will not be complying with the organizational standard | Meet with the project stakeholders to explain the need to comply with the PMO standards and update the status report format accordingly | Change the status reports according to the template supplied by the PMO and proceed with scheduled reporting | Continue using the outgoing project manager ' s status reports as well as their approach for schedule reporting |  | B | When stakeholders prefer customized status reports over PMO standard reports, the new project manager should meet with stakeholders, explain the need to comply with PMO standards, and update the report format accordingly. Balancing organizational requirements with stakeholder needs is appropriate. Refusing PMO compliance (A) violates organizational governance. Changing to PMO templates without stakeholder input (C) ignores their needs. Continuing the outgoing PM's approach (D) perpetuates non-compliance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 하이브리드 프로젝트 관리자가 고도로 규제된 환경에서 대규모 소프트웨어 개발 프로젝트를 인수했다. 인수 세션에서 전임 프로젝트 관리자는 PMO의 상태 보고서 스타일과 다른 자체적인 상태 보고서를 고안했다고 설명한다. 프로젝트 이해관계자들은 업데이트에서 받는 정보에 대해 매우 까다로우며 PMO의 상태 보고서에 충분한 정보가 없다고 믿는다. 새 프로젝트 관리자는 어떻게 진행해야 하는가? | PMO에 하이브리드 프로젝트 팀이 보고에 애자일 접근 방식을 유지해야 하며 조직 표준을 준수하지 않을 것임을 설명한다. | 프로젝트 이해관계자와 만나 PMO 표준 준수 필요성을 설명하고 상태 보고서 형식을 이에 맞게 업데이트한다. | PMO가 제공한 템플릿에 따라 상태 보고서를 변경하고 예정된 보고를 진행한다. | 전임 프로젝트 관리자의 상태 보고서와 일정 보고 접근 방식을 계속 사용한다. |  | B | 이해관계자가 PMO 표준 보고서보다 맞춤형 상태 보고서를 선호할 때, 새 프로젝트 관리자는 이해관계자와 만나 PMO 표준 준수 필요성을 설명하고 보고서 형식을 이에 맞게 업데이트해야 한다. 조직적 요구사항과 이해관계자 요구의 균형이 적절하다. PMO 준수 거부(A)는 조직 거버넌스를 위반한다. 이해관계자 입력 없이 PMO 템플릿으로 변경(C)은 이해관계자 요구를 무시한다. 전임 PM 접근 방식 유지(D)는 비준수를 영속화한다.
592 | A project manager is working on a unique project that is dissimilar to the project nature of the organization. The project manager is tailoring the artifacts for this new project. Who should determine which artifacts should be used in the project? | The project manager and the project management team should select the appropriate artifacts for use in the specific project. | The project stakeholders should meet and determine the project artifacts to be used by the project manager and the project management team. | The project manager and project management team should use the standard project artifacts from the database. | The project sponsor should select the project artifacts that the project manager and project management team should use in the project. |  | A | When tailoring artifacts for a unique project dissimilar to the organization's typical work, the project manager and project management team should select the appropriate artifacts. The PM team best understands project needs and delivery approach to determine relevant documentation. Stakeholders meeting to decide artifacts (B) may lack technical context. Using standard artifacts from the database (C) may not fit the unique project. The sponsor selecting artifacts (D) does not leverage PM expertise. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Hybrid/Tailoring | 프로젝트 관리자가 조직의 프로젝트 성격과 다른 독특한 프로젝트에서 작업하고 있다. 프로젝트 관리자는 이 새 프로젝트를 위해 산출물을 맞춤화하고 있다. 프로젝트에서 사용할 산출물을 누가 결정해야 하는가? | 프로젝트 관리자와 프로젝트 관리 팀이 특정 프로젝트에 사용할 적절한 산출물을 선택해야 한다. | 프로젝트 이해관계자가 만나 프로젝트 관리자와 프로젝트 관리 팀이 사용할 프로젝트 산출물을 결정해야 한다. | 프로젝트 관리자와 프로젝트 관리 팀이 데이터베이스의 표준 프로젝트 산출물을 사용해야 한다. | 프로젝트 스폰서가 프로젝트 관리자와 프로젝트 관리 팀이 프로젝트에서 사용할 프로젝트 산출물을 선택해야 한다. |  | A | 조직의 일반적인 작업과 다른 독특한 프로젝트를 위해 산출물을 맞춤화할 때, 프로젝트 관리자와 프로젝트 관리 팀이 적절한 산출물을 선택해야 한다. PM 팀이 프로젝트 요구와 전달 접근 방식을 가장 잘 이해하여 관련 문서화를 결정한다. 이해관계자가 산출물 결정 회의(B)는 기술적 맥락이 부족할 수 있다. 데이터베이스의 표준 산출물 사용(C)은 독특한 프로젝트에 적합하지 않을 수 있다. 스폰서가 산출물 선택(D)은 PM 전문성을 활용하지 못한다.
593 | An agile project is in its eighth iteration out of 16. After the last iteration review, the team members receive feedback from the security department about regulations with which the project must comply. Which two actions should the project manager take? (Choose two) | Ask the security department for details about regulations | Ask the team members to analyze the impact of including this regulation | Ask the stakeholders about the priority of this regulation | Ask the product owner to include the requirements in the product backlog | Ask the team members to include the requirements in the next iteration | B, D | When the security department provides new compliance regulations mid-project in an agile iteration, the project manager should (B) ask team members to analyze the impact of including the regulation, and (D) ask the product owner to include the requirements in the product backlog. Impact analysis informs planning while backlog inclusion ensures proper tracking. Asking about regulation priority (C) bypasses the PO's role. Requesting details from security (A) should have been done earlier. Including in the next iteration (E) skips analysis. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 애자일 프로젝트가 16개 반복 중 8번째 반복에 있다. 마지막 반복 검토 후 보안 부서로부터 프로젝트가 준수해야 하는 규정에 대한 피드백을 받았다. 프로젝트 관리자는 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 보안 부서에 규정에 대한 세부 사항을 요청한다. | 팀원들에게 이 규정을 포함하는 것의 영향을 분석하도록 요청한다. | 이해관계자에게 이 규정의 우선순위에 대해 질문한다. | 제품 책임자에게 요구사항을 제품 백로그에 포함하도록 요청한다. | 팀원들에게 다음 반복에 요구사항을 포함하도록 요청한다. | B, D | 보안 부서가 애자일 반복 중간에 새로운 준수 규정을 제공할 때, 프로젝트 관리자는 (B) 팀원들에게 규정 포함의 영향을 분석하도록 요청하고, (D) 제품 책임자에게 요구사항을 제품 백로그에 포함하도록 요청해야 한다. 영향 분석은 계획을 알리고 백로그 포함은 적절한 추적을 보장한다. 규정 우선순위 질문(C)은 PO의 역할을 우회한다. 보안에 세부 사항 요청(A)은 이미 했어야 한다. 다음 반복에 포함(E)은 분석을 건너뛴다.
594 | A project manager is asked to implement a hybrid approach that will replace a predictive approach on an upcoming project. How should the project manager adjust their responsibilities accordingly? | Become a servant leader by supporting team collaboration and removing impediments | Request a scrum master to focus on the collaboration while the project manager focuses on the coordination | introduce new communication tools to the project team members | Delegate coordination activities to the product owner so the project manager can locus on managing collaboration |  | A | When transitioning from a predictive to hybrid approach, the project manager should become a servant leader by supporting team collaboration and removing impediments. Servant leadership balances agile facilitation with coordination. Requesting a scrum master to handle collaboration (B) splits responsibilities unnecessarily. Introducing new communication tools (C) addresses tools, not leadership style. Delegating coordination to the product owner (D) misassigns the PM's role. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 예측형 접근 방식을 대체하는 하이브리드 접근 방식을 다가오는 프로젝트에 구현하도록 요청받았다. 프로젝트 관리자는 이에 따라 자신의 책임을 어떻게 조정해야 하는가? | 팀 협업을 지원하고 장애물을 제거하는 서번트 리더가 된다. | 프로젝트 관리자가 조율에 집중하는 동안 협업에 집중할 스크럼 마스터를 요청한다. | 프로젝트 팀원들에게 새로운 커뮤니케이션 도구를 도입한다. | 프로젝트 관리자가 협업 관리에 집중할 수 있도록 조율 활동을 제품 책임자에게 위임한다. |  | A | 예측형에서 하이브리드 접근 방식으로 전환할 때, 프로젝트 관리자는 팀 협업을 지원하고 장애물을 제거하는 서번트 리더가 되어야 한다. 서번트 리더십은 애자일 촉진과 조율의 균형을 맞춘다. 스크럼 마스터에게 협업 처리 요청(B)은 불필요하게 책임을 분리한다. 새 커뮤니케이션 도구 도입(C)은 도구를 다루지 리더십 스타일은 다루지 않는다. 제품 책임자에게 조율 위임(D)은 PM의 역할을 잘못 배정한다.
595 | An agile team is working on a project that will be launched in six countries. Each country has specific requirements in addition to the base offering. The estimates indicate it will take six months to develop the base offering and an additional month to finalize each country's unique requirements. The expected revenue for the product is the same for each country. Which release strategy should the project manager recommend? | An iterative-based strategy to maximize value by releasing the product to each country as it is finalized and ready for release in that country | A risk-based strategy to maximize the perceived value of the product by launching it to the countries with the lowest technical complexity | A quality-based strategy to maximize post-market adoption by releasing the product to the countries with the lowest probability of reporting field issues | A financial-based strategy to reduce the roll-out effort and costs by planning a single, bundled release to all countries at the same time |  | A | For a product launching in six countries with a common base offering and country-specific requirements, the project manager should recommend an iterative-based strategy—releasing the product to each country as it is finalized and ready. This maximizes value by delivering incrementally, enabling early feedback, and adapting to each country's specific needs. A risk-based strategy focused on lowest complexity (B) prioritizes ease over value. A quality-based strategy for lowest field issues (C) focuses on post-market adoption but may delay revenue. A single bundled release to all countries (D) delays value delivery until everything is complete. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 애자일 팀이 6개국에서 출시될 프로젝트를 진행 중이다. 각 국가에는 기본 제공 외에 특정 요구사항이 있다. 추정에 따르면 기본 제공을 개발하는 데 6개월이 걸리고 각 국가의 고유 요구사항을 완료하는 데 추가로 1개월이 걸린다. 제품의 예상 수익은 각 국가에서 동일하다. 프로젝트 관리자는 어떤 릴리스 전략을 권장해야 하는가? | 각 국가에서 완성되고 출시 준비가 되면 제품을 릴리스하여 가치를 극대화하는 반복 기반 전략 | 기술적 복잡성이 가장 낮은 국가에 먼저 출시하여 제품의 인지된 가치를 극대화하는 리스크 기반 전략 | 현장 문제 보고 가능성이 가장 낮은 국가에 먼저 출시하여 시장 후 채택을 극대화하는 품질 기반 전략 | 모든 국가에 동시에 단일 번들 릴리스를 계획하여 출시 노력과 비용을 줄이는 재무 기반 전략 |  | A | 공통 기본 제공과 국가별 요구사항이 있는 6개국 출시 제품의 경우, 프로젝트 관리자는 반복 기반 전략을 권장해야 한다—각 국가에서 완성되고 준비되면 제품을 릴리스한다. 이는 점진적으로 전달하여 가치를 극대화하고 조기 피드백을 가능하게 하며 각 국가의 특정 요구에 적응한다. 최저 복잡성에 초점을 맞춘 리스크 기반 전략(B)은 가치보다 용이성을 우선시한다. 최저 현장 문제를 위한 품질 기반 전략(C)은 시장 후 채택에 집중하지만 수익을 지연시킬 수 있다. 모든 국가에 단일 번들 릴리스(D)는 모든 것이 완료될 때까지 가치 전달을 지연시킨다.
596 | A local company is developing a new product and, for the first time, using a remote team for the programming tasks of features. The design for the product comes from the local team. During the third sprint review, the product owner has concerns about the project's outcomes. The remote development team is complaining that they do not clearly understand the requirements conveyed in the daily standup meetings. How should the project manager address this situation? | Determine the communication needs, environment, and tools to get the message across. | Review lessons learned from previous projects and organizational process assets (OPAs). | Evaluate and reassign the developing tasks to a local vendor who has worked on previous projects. | Document the risk in the risk management plan and use contingency reserves to hire a local vendor. |  | A | When a remote development team struggles to understand requirements conveyed during daily standups, the project manager should determine the communication needs, environment, and tools to get the message across effectively. This is part of planning communications management—identifying the most effective and efficient approach for cross-team communication. Reassigning tasks to a local vendor (C) disrupts the project and is disproportionate. Documenting the risk and hiring a local vendor (D) treats the symptom rather than fixing the communication issue. Reviewing lessons learned (B) provides historical insights but does not directly resolve the current communication breakdown. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 현지 회사가 새 제품을 개발하며 처음으로 기능의 프로그래밍 작업에 원격 팀을 사용하고 있다. 제품 디자인은 현지 팀에서 나온다. 세 번째 스프린트 검토에서 제품 책임자가 프로젝트 결과에 대한 우려를 제기한다. 원격 개발 팀은 일일 스탠드업 회의에서 전달되는 요구사항을 명확히 이해하지 못한다고 불만을 제기한다. 프로젝트 관리자는 이 상황을 어떻게 해결해야 하는가? | 메시지를 전달하기 위한 커뮤니케이션 요구, 환경 및 도구를 결정한다. | 이전 프로젝트의 교훈과 조직 프로세스 자산(OPA)을 검토한다. | 이전 프로젝트에서 작업한 현지 벤더에게 개발 작업을 평가하고 재배정한다. | 리스크 관리 계획에 리스크를 기록하고 예비비를 사용하여 현지 벤더를 고용한다. |  | A | 원격 개발 팀이 일일 스탠드업에서 전달되는 요구사항을 이해하는 데 어려움을 겪을 때, 프로젝트 관리자는 메시지를 효과적으로 전달하기 위한 커뮤니케이션 요구, 환경 및 도구를 결정해야 한다. 이는 커뮤니케이션 관리 계획의 일부로, 팀 간 커뮤니케이션을 위한 가장 효과적이고 효율적인 접근 방식을 식별한다. 현지 벤더에게 작업 재배정(C)은 프로젝트를 혼란시키고 불균형하다. 리스크 기록 및 현지 벤더 고용(D)은 커뮤니케이션 문제를 해결하지 않고 증상을 치료한다. 교훈 검토(B)는 역사적 통찰을 제공하지만 현재 커뮤니케이션 단절을 직접 해결하지 않는다.
597 | The steering committee has asked a project manager experienced in agile to provide an indication of the time remaining on a medium-sized project. What tools can be used to provide this information? | Surrogate measurements | A release burndown chart | Analysis of the business requirements document | Story points for the remaining user stories |  | B | When the steering committee asks for an indication of time remaining on a medium-sized agile project, a release burndown chart should be used. It shows remaining work over time based on velocity and progress, enabling completion projections. Surrogate measurements (A) are indirect proxies. Business requirements document analysis (C) is not a time-tracking tool. Story points for remaining stories (D) show effort but not a time-based view. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 운영위원회가 애자일에 경험이 있는 프로젝트 관리자에게 중간 규모 프로젝트의 남은 시간에 대한 지표를 제공하도록 요청했다. 이 정보를 제공하기 위해 어떤 도구를 사용할 수 있는가? | 대리 측정치 | 릴리스 번다운 차트 | 비즈니스 요구사항 문서 분석 | 남은 사용자 스토리의 스토리 포인트 |  | B | 운영위원회가 중간 규모 애자일 프로젝트의 남은 시간에 대한 지표를 요청할 때, 릴리스 번다운 차트를 사용해야 한다. 이는 속도와 진행 상황에 기반한 시간 경과에 따른 남은 작업을 보여주어 완료 예측을 가능하게 한다. 대리 측정치(A)는 간접적 대용치이다. 비즈니스 요구사항 문서 분석(C)은 시간 추적 도구가 아니다. 남은 스토리의 스토리 포인트(D)는 노력을 보여주지만 시간 기반 관점은 아니다.
598 | Having managed a similar project while working with previous stakeholders, a project team decided to use the same report format they used in the earlier project. However, stakeholders new to the project are not fully comprehending the status of the project based on the reports that are being circulated. How should the project manager address this concern moving forward? | Create a fishbone diagram to determine the root cause for the misunderstanding. | Share the communications management plan and remind all stakeholders of the agreed- upon reporting templates. | Employ Monitor Communications techniques, which may eventually trigger changes to the communications management plan. | Add the issue to the issue log and determine the corrective action. |  | C | When new stakeholders do not fully comprehend project status from existing report formats, the project manager should employ Monitor Communications techniques, which may trigger changes to the communications management plan. Systematic monitoring identifies communication gaps and drives targeted improvements. Adding to the issue log (D) documents but does not solve the problem. Creating a fishbone diagram (A) is overly analytical for a communication preference issue. Sharing the existing plan and reminding of templates (B) implies stakeholders are at fault. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 이전 이해관계자와 함께 유사한 프로젝트를 관리한 경험이 있는 프로젝트 팀이 이전 프로젝트에서 사용한 것과 동일한 보고서 형식을 사용하기로 결정했다. 그러나 프로젝트에 새로 합류한 이해관계자들은 배포되는 보고서를 기반으로 프로젝트 상태를 완전히 이해하지 못하고 있다. 프로젝트 관리자는 앞으로 이 우려를 어떻게 해결해야 하는가? | 오해의 근본 원인을 파악하기 위해 피시본 다이어그램을 작성한다. | 커뮤니케이션 관리 계획을 공유하고 모든 이해관계자에게 합의된 보고서 템플릿을 상기시킨다. | 커뮤니케이션 모니터링 기법을 사용하며, 이는 결국 커뮤니케이션 관리 계획의 변경을 촉발할 수 있다. | 이슈 로그에 이슈를 추가하고 시정 조치를 결정한다. |  | C | 새로운 이해관계자가 기존 보고서 형식에서 프로젝트 상태를 완전히 이해하지 못할 때, 프로젝트 관리자는 커뮤니케이션 모니터링 기법을 사용해야 하며, 이는 커뮤니케이션 관리 계획의 변경을 촉발할 수 있다. 체계적인 모니터링은 커뮤니케이션 격차를 식별하고 목표된 개선을 추진한다. 이슈 로그에 추가(D)는 기록하지만 문제를 해결하지 않는다. 피시본 다이어그램 작성(A)은 커뮤니케이션 선호도 이슈에 대해 과도하게 분석적이다. 기존 계획 공유 및 템플릿 상기(B)는 이해관계자에게 잘못이 있다고 암시한다.
599 | A project manager is managing a project that is halfway through its execution phase and the quality standards of the deliverables were formally accepted. However, a government agency has recently introduced new standards that may significantly impact the project. The deliverables must be changed to align with the new quality standards. What should the project manager do? | Set up a structured, independent processes to determine if project activities followed the standards. | Update the lessons learned register and inform senior management of the new standards | Evaluate the impact the new regulations will have on the project and submit a change request | Schedule training for the project team on the new regulations introduced by the 939 government agency |  | C | When new government quality standards are introduced midway through execution that require deliverable changes, the project manager should evaluate the impact the new regulations will have on the project and submit a change request. Integrated change control ensures proper assessment and approval. Setting up independent process audits (A) verifies compliance but does not implement the changes. Updating lessons learned (B) is retrospective. Scheduling training (D) addresses knowledge but not the change itself. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 실행 단계 중간에 있는 프로젝트를 관리하고 있으며 산출물의 품질 기준이 공식적으로 수락되었다. 그러나 정부 기관이 최근 프로젝트에 중대한 영향을 미칠 수 있는 새로운 기준을 도입했다. 새로운 품질 기준에 맞추기 위해 산출물을 변경해야 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 활동이 기준을 따랐는지 확인하기 위해 구조화되고 독립적인 프로세스를 설정한다. | 교훈 레지스터를 업데이트하고 상급 경영진에게 새 기준을 알린다. | 새 규정이 프로젝트에 미칠 영향을 평가하고 변경 요청을 제출한다. | 정부 기관이 도입한 새 규정에 대해 프로젝트 팀의 교육을 예약한다. |  | C | 실행 중간에 산출물 변경을 요구하는 새로운 정부 품질 기준이 도입될 때, 프로젝트 관리자는 새 규정이 프로젝트에 미칠 영향을 평가하고 변경 요청을 제출해야 한다. 통합 변경 통제는 적절한 평가와 승인을 보장한다. 독립적 프로세스 감사 설정(A)은 준수를 확인하지만 변경을 구현하지 않는다. 교훈 업데이트(B)는 회고적이다. 교육 예약(D)은 지식을 다루지만 변경 자체는 다루지 않는다.
600 | During project execution, one of the project tasks is to create an important document for a service vendor. The project manager assigns a senior engineer to clearly detail the service instructions to avoid any redo loops. Two days after the service information document was sent, the service vendor has doubts and needs more clarity on the task. This redo loop will probably cause a delay of one or more days. What should the project manager do next? | Escalate the issue to the engineer ' s functional manager. | Assign another engineer to the task due to the urgency. | Document the task on the kanban board and make it the highest priority. | Discuss the issue with the engineer and determine how to prevent another problem. |  | D | When a service vendor needs clarity on documentation prepared by a senior engineer, the project manager should discuss the issue with the engineer and determine how to prevent another problem. Direct engagement identifies gaps and establishes preventive measures. Escalating to the functional manager (A) is premature. Assigning another engineer (B) wastes resources. Documenting the task on a kanban board (C) addresses tracking, not the clarity issue. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 프로젝트 실행 중 프로젝트 작업 중 하나는 서비스 벤더를 위한 중요 문서를 작성하는 것이다. 프로젝트 관리자는 재작업 반복을 피하기 위해 시니어 엔지니어에게 서비스 지침을 명확히 상세하게 기술하도록 배정했다. 서비스 정보 문서가 발송된 지 2일 후, 서비스 벤더가 의문을 가지고 작업에 대한 더 많은 명확성이 필요하다. 이 재작업 반복은 1일 이상의 지연을 초래할 가능성이 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 엔지니어의 기능 관리자에게 이슈를 에스컬레이션한다. | 긴급성으로 인해 다른 엔지니어를 작업에 배정한다. | 칸반 보드에 작업을 기록하고 최우선순위로 만든다. | 엔지니어와 이슈를 논의하고 또 다른 문제를 방지하는 방법을 결정한다. |  | D | 서비스 벤더가 시니어 엔지니어가 작성한 문서에 대해 명확성이 필요할 때, 프로젝트 관리자는 엔지니어와 이슈를 논의하고 또 다른 문제를 방지하는 방법을 결정해야 한다. 직접적인 참여는 격차를 식별하고 예방 조치를 수립한다. 기능 관리자에게 에스컬레이션(A)은 시기상조이다. 다른 엔지니어 배정(B)은 자원을 낭비한다. 칸반 보드에 기록(C)은 추적을 다루지 명확성 이슈는 다루지 않는다.
601 | A project sponsor receives project information and updates in a timely manner, but the sponsor is concerned because key information is missing in the reports. What should the project manager do? | Confirm that the project information is understood and feedback is received. | Provide all project information to the stakeholder. | Determine communication methods, frequency, and level of detail. | Review the communication needs of key stakeholders. |  | D | When the project sponsor reports that key information is missing from reports, the project manager should review the communication needs of key stakeholders. This is the foundational step in developing effective communications—understanding what information each stakeholder requires, at what level of detail, and in what format. Confirming understanding and feedback (A) is good practice but does not address the root cause of missing information. Determining communication methods and frequency (C) is part of the communication plan but should follow the needs analysis. Providing all project information (B) may overwhelm the stakeholder with unnecessary data and does not target the specific gap. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 스폰서가 프로젝트 정보와 업데이트를 적시에 받고 있지만, 보고서에 주요 정보가 누락되어 우려하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 정보가 이해되고 피드백이 접수되었음을 확인한다. | 이해관계자에게 모든 프로젝트 정보를 제공한다. | 커뮤니케이션 방법, 빈도 및 세부 수준을 결정한다. | 주요 이해관계자의 커뮤니케이션 요구사항을 검토한다. |  | D | 프로젝트 스폰서가 보고서에 주요 정보가 누락되었다고 보고할 때, 프로젝트 관리자는 주요 이해관계자의 커뮤니케이션 요구사항을 검토해야 한다. 이는 효과적인 커뮤니케이션 개발의 기본 단계로—각 이해관계자가 어떤 정보를, 어떤 세부 수준으로, 어떤 형식으로 필요로 하는지를 이해하는 것이다. 이해 확인 및 피드백(A)은 좋은 관행이지만 누락된 정보의 근본 원인을 다루지 않는다. 커뮤니케이션 방법과 빈도 결정(C)은 커뮤니케이션 계획의 일부이지만 요구사항 분석 이후에 이루어져야 한다. 모든 프로젝트 정보 제공(B)은 불필요한 데이터로 이해관계자를 압도할 수 있으며 특정 격차를 겨냥하지 않는다.
602 | A project manager is leading an in-house company project in its very early stages. This current project is similar to another project that ended a year ago. What should the project manager do to analyze the involved stakeholders? | Use lessons learned from the previous project as a guide for the current project ' s stakeholder register | Lower the priority of stakeholder engagement as the stakeholders already have knowledge of this kind of project | Document in the risk register that the current project may have differentstakeholders than the previous project | Refer to the stakeholder register from the previous project as it was similar to the current project |  | A | For a project in its early stages that is similar to a recently completed project, the project manager should use lessons learned from the previous project as a guide for the current project's stakeholder register. Lessons learned provide valuable insights into stakeholder expectations, needs, influence, and potential impact, enabling a more accurate and comprehensive stakeholder identification. Lowering the priority of stakeholder engagement (B) is risky regardless of prior knowledge. Documenting a risk about different stakeholders (C) is reactive rather than proactive. Referring directly to the previous stakeholder register (D) assumes stakeholders are the same without validation. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 매우 초기 단계의 사내 회사 프로젝트를 이끌고 있다. 이 현재 프로젝트는 1년 전에 종료된 다른 프로젝트와 유사하다. 프로젝트 관리자는 관련 이해관계자를 분석하기 위해 무엇을 해야 하는가? | 이전 프로젝트의 교훈을 현재 프로젝트의 이해관계자 레지스터에 대한 가이드로 사용한다. | 이해관계자가 이미 이런 종류의 프로젝트에 대한 지식이 있으므로 이해관계자 참여의 우선순위를 낮춘다. | 현재 프로젝트가 이전 프로젝트와 다른 이해관계자를 가질 수 있다는 것을 리스크 레지스터에 기록한다. | 이전 프로젝트가 현재 프로젝트와 유사했으므로 이전 프로젝트의 이해관계자 레지스터를 참조한다. |  | A | 최근 완료된 프로젝트와 유사한 초기 단계 프로젝트의 경우, 프로젝트 관리자는 이전 프로젝트의 교훈을 현재 프로젝트의 이해관계자 레지스터에 대한 가이드로 사용해야 한다. 교훈은 이해관계자의 기대, 요구, 영향력 및 잠재적 영향에 대한 귀중한 통찰을 제공하여 보다 정확하고 포괄적인 이해관계자 식별을 가능하게 한다. 이해관계자 참여 우선순위 낮추기(B)는 이전 지식과 관계없이 위험하다. 다른 이해관계자에 대한 리스크 기록(C)은 사전 예방적이기보다 반응적이다. 이전 이해관계자 레지스터를 직접 참조(D)는 검증 없이 이해관계자가 동일하다고 가정한다.
603 | During a team meeting, the new agile project manager becomes aware that there are many complaints from the customer regarding project stability and other critical issues. A team member states that the deliverables were developed by experienced employees who confirmed that the project was stable. How should the new project manager address these concerns? | Hold a brainstorming session to identify the root cause of the complaints. | Allow the agile team to decide what they are able to deliver in each iteration | Ask the team for additional feedback and add tasks to the task board, | Document the customer ' s complaints and critical issues in the issue log. |  | A | When customers complain about project stability and critical issues while the team claims deliverables were validated by experienced employees, the project manager should hold a brainstorming session to identify the root cause of the complaints. Collaborative problem-solving engages the team in analyzing the disconnect between internal validation and customer experience. Allowing the team to decide what to deliver (B) does not address the existing quality complaints. Asking for additional feedback and adding tasks (C) is incremental. Documenting complaints in the issue log (D) records but does not actively resolve the issue. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀 회의에서 새로운 애자일 프로젝트 관리자가 프로젝트 안정성 및 기타 중요한 이슈에 대해 고객으로부터 많은 불만이 있다는 것을 알게 되었다. 팀원은 산출물이 프로젝트가 안정적임을 확인한 경험 많은 직원들에 의해 개발되었다고 말한다. 새로운 프로젝트 관리자는 이러한 우려를 어떻게 해결해야 하는가? | 불만의 근본 원인을 식별하기 위해 브레인스토밍 세션을 개최한다. | 애자일 팀이 각 이터레이션에서 무엇을 전달할 수 있는지 결정하도록 한다. | 팀에 추가 피드백을 요청하고 작업 보드에 작업을 추가한다. | 고객의 불만과 중요한 이슈를 이슈 로그에 문서화한다. |  | A | 고객이 프로젝트 안정성과 중요한 이슈에 대해 불만을 제기하는 반면 팀은 산출물이 경험 많은 직원에 의해 검증되었다고 주장할 때, 프로젝트 관리자는 불만의 근본 원인을 식별하기 위해 브레인스토밍 세션을 개최해야 한다. 협력적 문제 해결은 내부 검증과 고객 경험 간의 불일치를 분석하는 데 팀을 참여시킨다. 팀이 전달할 것을 결정하도록 허용(B)은 기존 품질 불만을 해결하지 않는다. 추가 피드백 요청 및 작업 추가(C)는 점진적이다. 이슈 로그에 문서화(D)는 기록하지만 적극적으로 해결하지 않는다.
604 | A project manager leads a regulatory initiative with strict, non-negotiable timelines. During a status meeting, a key stakeholder requests that a critical milestone related to the reporting functionality be moved up by 4 weeks. What should the project manager do first? | Gather additional information and ask the team to perform a root cause analysis. | Ask the team to work with the product owner to reprioritize the backlog. | Request additional information and discuss the feasibility options and impacts with the team. | Update the master schedule to reflect the reprioritized deliverables. |  | C | Faced with a request to accelerate a regulatory milestone, the PM's first action should be to request additional information and assess feasibility with the team. This means evaluating schedule impacts, resource constraints, regulatory implications, and potential scope trade-offs before making any commitments. A root cause analysis (A) is more suited to problem diagnosis, not acceleration requests. Reprioritizing the backlog (B) assumes the change is already approved. Updating the master schedule immediately (D) bypasses the required impact assessment. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Embed Quality | Develop Schedule | Traditional PM | 프로젝트 관리자가 엄격하고 협상 불가능한 일정의 규제 이니셔티브를 이끌고 있다. 상태 회의에서 주요 이해관계자가 보고 기능과 관련된 중요한 마일스톤을 4주 앞당기도록 요청한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 추가 정보를 수집하고 팀에게 근본 원인 분석을 수행하도록 요청한다. | 팀에게 제품 책임자와 함께 백로그를 재우선순위화하도록 요청한다. | 추가 정보를 요청하고 팀과 실현 가능성 옵션 및 영향을 논의한다. | 재우선순위화된 산출물을 반영하도록 마스터 일정을 업데이트한다. |  | C | 규제 마일스톤 가속 요청에 직면했을 때, PM의 첫 번째 조치는 추가 정보를 요청하고 팀과 실현 가능성을 평가하는 것이다. 이는 일정 영향, 자원 제약, 규제적 함의, 잠재적 범위 트레이드오프를 약속하기 전에 평가하는 것을 의미한다. 근본 원인 분석(A)은 가속 요청이 아닌 문제 진단에 더 적합하다. 백로그 재우선순위화(B)는 변경이 이미 승인되었다고 가정한다. 마스터 일정 즉시 업데이트(D)는 필요한 영향 평가를 우회한다.
605 | A project team is not motivated and is producing the bare minimum. The team has no interest in keeping pace with the aggressive project schedule. What should the project manager do first to get the team energized and performing efficiently? | Contact the functional manager to request a replacement for team members who are not able to meet the schedule. | Seek to understand the sentiments of each team member and then work with them to address their concerns. | Begin holding daily meetings and ask each team member to share their status and demand that they remain on schedule. | Bring the team together on a phone call to explain the criticality of the project and the 44 impact of schedule delays. |  | B | The PM should seek to understand each team member's sentiments and then work with them individually to address their concerns. Effective schedule management demands proactive monitoring and timely corrective actions. The PM should analyze schedule impacts, evaluate available options, and implement appropriate responses to keep the project on track. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 팀이 동기 부여가 되지 않고 최소한의 것만 산출하고 있다. 팀은 공격적인 프로젝트 일정에 맞추는 데 관심이 없다. 프로젝트 관리자는 팀에 활력을 불어넣고 효율적으로 성과를 내도록 먼저 무엇을 해야 하는가? | 일정을 충족할 수 없는 팀원의 교체를 요청하기 위해 기능 관리자에게 연락한다. | 각 팀원의 감정을 이해하고자 하고 그들의 우려를 해결하기 위해 함께 작업한다. | 매일 회의를 시작하고 각 팀원에게 상태를 공유하도록 요청하며 일정을 지키도록 요구한다. | 팀을 전화 통화로 모아 프로젝트의 중요성과 일정 지연의 영향을 설명한다. |  | B | PM은 각 팀원의 감정을 이해하고 개별적으로 그들의 우려를 해결하기 위해 함께 작업해야 한다. 효과적인 일정 관리는 사전 예방적 모니터링과 적시 시정 조치를 요구한다. PM은 일정 영향을 분석하고 가용 옵션을 평가하며 프로젝트를 정상 궤도에 유지하기 위해 적절한 대응을 구현해야 한다.
606 | An agile team is facing a challenge with the quality of its deliverables. Every time a feature is promoted to production, many defects arise, preventing the customers from properly using the solution. What should the project manager do to prevent this situation in the future? | Use the next retrospective to understand the root cause of the quality issues and have the team come up with an action plan. | Reduce the release cycle and invest more time on stabilizing the current features instead of releasing new ones. | Create a team incentive program with prizes, allowing the team members to work overtime to find defects. | Hire a quality assurance specialist and integrate a second phase of testing into the current project life cycle. |  | A | Retrospectives are fundamental to agile continuous improvement. They provide a structured opportunity to reflect on past iterations, identify what worked and what didn't, and create improvement plans. Addressing root causes of quality issues during retrospectives ensures the team develops effective solutions collaboratively, building buy-in and accountability for deliverable quality. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 애자일 팀이 산출물의 품질에 문제를 겪고 있다. 기능이 프로덕션에 배포될 때마다 많은 결함이 발생하여 고객이 솔루션을 제대로 사용하지 못한다. 프로젝트 관리자는 향후 이러한 상황을 방지하기 위해 무엇을 해야 하는가? | 다음 회고에서 품질 이슈의 근본 원인을 파악하고 팀이 실행 계획을 수립하도록 한다. | 릴리스 주기를 줄이고 새로운 기능 출시 대신 현재 기능 안정화에 더 많은 시간을 투자한다. | 팀원들이 결함을 찾기 위해 초과 근무를 하도록 상금이 있는 팀 인센티브 프로그램을 만든다. | 품질 보증 전문가를 고용하고 현재 프로젝트 생명주기에 두 번째 테스트 단계를 통합한다. |  | A | 회고는 애자일 지속적 개선의 기본이다. 회고는 과거 이터레이션을 반성하고, 무엇이 효과적이었고 무엇이 아니었는지 식별하며, 개선 계획을 만들 수 있는 구조화된 기회를 제공한다. 회고 중 품질 이슈의 근본 원인을 해결하면 팀이 협력적으로 효과적인 솔루션을 개발하여 산출물 품질에 대한 동의와 책임감을 구축한다.
607 | A critical project milestone was missed because one of the team members did not complete their tasks on time. This resulted in a heated discussion during a demonstration for the end users. What should the project manager do next? | Discuss the issue with the team member in a one-on-one meeting. | Ask the team member to justify the delay during a team meeting. | Review the human resources (HR) policies for relevant corrective actions. | Escalate the performance issue to the team member ' s functional manager. 1001 |  | A | When a missed milestone due to a team member's delayed tasks leads to a heated discussion at a demo, the project manager should discuss the issue with the team member in a one-on-one meeting. Private discussion enables understanding and corrective planning. Asking for justification in a team meeting (B) is confrontational. Reviewing HR policies (C) escalates prematurely. Escalating to the functional manager (D) bypasses direct engagement. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 팀원 중 한 명이 제시간에 작업을 완료하지 못해 중요한 프로젝트 마일스톤을 놓쳤다. 이로 인해 최종 사용자를 위한 시연 중 격렬한 논쟁이 발생했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 팀원과 1:1 미팅에서 이슈를 논의한다. | 팀 회의에서 팀원에게 지연을 정당화하도록 요청한다. | 관련 시정 조치를 위해 인사(HR) 정책을 검토한다. | 성과 이슈를 팀원의 기능 관리자에게 에스컬레이션한다. |  | A | 팀원의 작업 지연으로 마일스톤을 놓치고 시연에서 격렬한 논쟁이 발생했을 때, 프로젝트 관리자는 팀원과 1:1 미팅에서 이슈를 논의해야 한다. 비공개 논의는 이해와 시정 계획을 가능하게 한다. 팀 회의에서 정당화 요청(B)은 대립적이다. HR 정책 검토(C)는 성급하게 에스컬레이션한다. 기능 관리자에게 에스컬레이션(D)은 직접적 참여를 우회한다.
608 | Near the closing stage, a project is delayed due to staff shortages. In order to meet the mandatory deadline, additional resources are necessary, but there is no additional budget. What should the project manager do first to obtain the funding to hire the needed resources? | Update baselines to accommodate the delay. | Introduce a change request. | Ask the sponsor for additional financial resources. | Use management reserves. |  | D | When a project near closing is delayed due to staff shortages with no additional budget and a mandatory deadline, the project manager should first use management reserves. Management reserves address unforeseen needs within existing project funding. Updating baselines to accommodate delay (A) accepts the delay. Introducing a change request (B) formalizes but does not fund. Asking the sponsor for additional resources (C) is external funding that may not be available. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 종료 단계 근처에서 인력 부족으로 프로젝트가 지연되고 있다. 필수 마감일을 충족하기 위해 추가 자원이 필요하지만 추가 예산이 없다. 프로젝트 관리자는 필요한 자원을 고용하기 위한 자금을 확보하기 위해 먼저 무엇을 해야 하는가? | 지연을 수용하도록 기준선을 업데이트한다. | 변경 요청을 제출한다. | 스폰서에게 추가 재정 자원을 요청한다. | 관리 예비비를 사용한다. |  | D | 종료 근처에서 인력 부족으로 프로젝트가 지연되고 추가 예산 없이 필수 마감일이 있을 때, 프로젝트 관리자는 먼저 관리 예비비를 사용해야 한다. 관리 예비비는 기존 프로젝트 자금 내에서 예기치 않은 요구를 해결한다. 지연을 수용하도록 기준선 업데이트(A)는 지연을 수락한다. 변경 요청 제출(B)은 공식화하지만 자금을 확보하지 않는다. 스폰서에게 추가 자원 요청(C)은 사용 불가능할 수 있는 외부 자금이다.
609 | A project is delayed considerably from its original completion date for various reasons. The client attributes the delays to the contractor and is going to impose liquidated damages. The project manager of the contracting company reviews the schedule and observes that, though some activities were delayed by the contractor, the critical activity was delayed by the client. What should the project manager of the contracting company do? | Schedule a detailed analysis of the delays using cause and effect. | Check the contractual terms about liquidated damages and reject if not applicable. 1163 | Record that the delay is attributable to the client and request a meeting. | Meet with the sponsor to analyze the delays and the associated liquidated damages. |  | C | When the client attributes all delays to the contractor and threatens liquidated damages, but the PM identifies the critical activity was delayed by the client, the PM should record that the delay is attributable to the client and request a meeting. Documentation and dialogue protect interests transparently. Scheduling cause-and-effect analysis (A) is analytical but not immediate action. Checking contractual terms and rejecting (B) is adversarial. Meeting the sponsor to analyze (D) involves the wrong party. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Critical Path/Schedule Mgmt | Process | Plan and Manage Procurement | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | 프로젝트가 다양한 이유로 원래 완료일에서 상당히 지연되었다. 고객은 지연을 계약업체의 책임으로 돌리고 지체상금을 부과하려고 한다. 계약 회사의 프로젝트 관리자가 일정을 검토한 결과, 일부 활동은 계약업체에 의해 지연되었지만 주공정 활동은 고객에 의해 지연되었음을 관찰한다. 계약 회사의 프로젝트 관리자는 무엇을 해야 하는가? | 원인과 결과를 사용하여 지연에 대한 상세 분석을 예약한다. | 지체상금에 대한 계약 조건을 확인하고 해당되지 않으면 거부한다. | 지연이 고객에게 귀속됨을 기록하고 회의를 요청한다. | 스폰서와 만나 지연과 관련 지체상금을 분석한다. |  | C | 고객이 모든 지연을 계약업체에게 돌리고 지체상금을 위협하지만 PM이 주공정 활동이 고객에 의해 지연되었음을 식별할 때, PM은 지연이 고객에게 귀속됨을 기록하고 회의를 요청해야 한다. 문서화와 대화는 투명하게 이해를 보호한다. 원인-결과 분석 예약(A)은 분석적이지만 즉각적인 조치가 아니다. 계약 조건 확인 및 거부(B)는 적대적이다. 스폰서와 만나 분석(D)은 잘못된 당사자를 포함한다.
610 | A product owner is continuously adding requirements to a project that will significantly impact project delivery. How should the project manager address this? | Consult with senior managers on how to address this to ensure the product owner ' s expectations are fully met. | Reprioritize the work and add all new work to the product backlog. | Check with the project team about their availability to continue project work. | Ask the product owner to reprioritize and consider the project done when the highest priorities are delivered. |  | D | The correct answer is D. Ask the product owner to reprioritize and consider the project done when the highest priorities are delivered. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 제품 책임자가 프로젝트에 지속적으로 요구사항을 추가하여 프로젝트 전달에 큰 영향을 미칠 것이다. 프로젝트 관리자는 이를 어떻게 해결해야 하는가? | 제품 책임자의 기대가 완전히 충족되도록 이를 해결하는 방법에 대해 상급 경영진과 상의한다. | 작업을 재우선순위화하고 모든 새로운 작업을 제품 백로그에 추가한다. | 프로젝트 작업을 계속하기 위한 가용성에 대해 프로젝트 팀과 확인한다. | 제품 책임자에게 재우선순위화하고 가장 높은 우선순위가 전달될 때 프로젝트가 완료된 것으로 간주하도록 요청한다. |  | D | 정답은 D이다. 제품 책임자에게 재우선순위화하고 가장 높은 우선순위가 전달될 때 프로젝트가 완료된 것으로 간주하도록 요청한다. 이 접근 방식은 적절한 프로세스와 이해관계자 정렬을 유지하면서 상황을 효과적으로 해결하는 프로젝트 관리 모범 사례를 따른다.
611 | During a team meeting, the project manager asks the team to complete a personality assessment to help everyone understand themselves and one another better. The project manager analyzes the results and realizes that more than one-half of team members are introverts. What should the project manager do? | Present brainstorming topics a day before the session so the team can reflect and contribute more fully during the session | Ensure the team understands that their input needs to be fully articulated and explained to all team members during daily standups | Require everyone to share personal details at the start of each team meeting to allow learn members to get to know one another | Adjust the lighting and ambient sounds in the work and common areas to create a relaxing work atmosphere |  | A | When more than half the team members are introverts, the project manager should present brainstorming topics a day before the session so the team can reflect and contribute more fully during the discussion. Introverts typically prefer time to process information and formulate their thoughts before group interactions. This accommodation ensures all personality types can participate meaningfully. Requiring personal details at each meeting (C) may feel intrusive and uncomfortable, especially for introverts. Requiring fully articulated input during daily standups (B) creates pressure that disadvantages reflective team members. Adjusting lighting and ambient sounds (D) addresses the physical environment but does not solve the participation challenge. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 팀 회의에서 프로젝트 관리자가 팀에게 자신과 서로를 더 잘 이해하도록 돕기 위해 성격 평가를 완료하도록 요청한다. 프로젝트 관리자가 결과를 분석한 결과 팀원의 절반 이상이 내향적임을 알게 된다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀이 세션 중 더 충분히 반영하고 기여할 수 있도록 브레인스토밍 주제를 세션 하루 전에 제시한다. | 일일 스탠드업에서 모든 팀원에게 의견이 완전히 설명되고 설명되어야 함을 이해시킨다. | 팀원들이 서로를 알 수 있도록 각 팀 회의 시작 시 개인적인 세부 사항을 공유하도록 요구한다. | 편안한 작업 분위기를 조성하기 위해 작업 및 공용 공간의 조명과 주변 음향을 조정한다. |  | A | 팀원의 절반 이상이 내향적일 때, 프로젝트 관리자는 브레인스토밍 주제를 세션 하루 전에 제시하여 팀이 반영하고 더 충분히 기여할 수 있도록 해야 한다. 내향적인 사람들은 대그룹 상호작용 전에 정보를 처리하고 생각을 정리할 시간을 선호한다. 이 배려는 모든 성격 유형이 의미 있게 참여할 수 있도록 보장한다. 각 회의에서 개인적 세부 사항 공유 요구(C)는 특히 내향적인 사람들에게 불편할 수 있다. 일일 스탠드업에서 완전한 의견 설명 요구(B)는 성찰적인 팀원에게 압박을 준다. 조명 및 주변 음향 조정(D)은 물리적 환경을 다루지만 참여 문제를 해결하지 않는다.
612 | Negotiations are underway to secure an agreement with a critical supplier for the project. The negotiation situation has become contentious as it is becoming apparent that both parties will not receive everything they want and that a compromise might be necessary to avoid project delays, cost overruns, and damage to reputations. What should the project manager do to help ensure a successful outcome for the project? | Withhold from revealing the priorities and objectives until midway through negotiations. | Adjust priorities and objectives based on real-time developments during the negotiation process. | Collaborate with stakeholders to complete an analysis of priorities with ranked objectives. | Begin the negotiation process with predetermined objectives to guide the discussions. |  | C | When negotiations with a critical supplier become contentious and compromise is needed, the project manager should collaborate with stakeholders to complete an analysis of priorities with ranked objectives. Stakeholder-aligned prioritization enables strategic trade-offs during negotiation. Withholding priorities (A) is counterproductive. Beginning with predetermined objectives without stakeholder input (D) may misalign priorities. Adjusting priorities reactively mid-negotiation (B) lacks strategic preparation. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 중요한 공급업체와의 계약을 확보하기 위한 협상이 진행 중이다. 양쪽 모두 원하는 모든 것을 받을 수 없으며 프로젝트 지연, 비용 초과, 평판 손상을 피하기 위해 타협이 필요할 수 있음이 명백해지면서 논쟁이 되었다. 프로젝트 관리자는 프로젝트의 성공적인 결과를 보장하기 위해 무엇을 해야 하는가? | 협상 중반까지 우선순위와 목표를 공개하지 않는다. | 협상 과정 중 실시간 전개에 따라 우선순위와 목표를 조정한다. | 이해관계자와 협력하여 순위가 매겨진 목표로 우선순위 분석을 완료한다. | 논의를 안내하기 위해 사전 결정된 목표로 협상 과정을 시작한다. |  | C | 중요한 공급업체와의 협상이 논쟁이 되고 타협이 필요할 때, 프로젝트 관리자는 이해관계자와 협력하여 순위가 매겨진 목표로 우선순위 분석을 완료해야 한다. 이해관계자와 정렬된 우선순위화는 협상 중 전략적 트레이드오프를 가능하게 한다. 우선순위 비공개(A)는 비생산적이다. 이해관계자 입력 없이 사전 결정된 목표로 시작(D)은 우선순위가 잘못 정렬될 수 있다. 협상 중 실시간으로 우선순위 조정(B)은 전략적 준비가 부족하다.
613 | A project manager is working on a multinational project that has more than 100 stakeholders. The project manager is concerned about the appropriate stakeholder participation and involvement level required for successful project delivery. What should the project manager do? | Communicate with the stakeholders to find a solution. | Review the issue log with the project stakeholders. | Perform a stakeholder assumption and constraint analysis. | Evaluate the stakeholder engagement assessment matrix. |  | D | When managing a multinational project with 100+ stakeholders and concerns about participation levels, the project manager should evaluate the stakeholder engagement assessment matrix. This tool documents desired vs. current engagement levels and identifies gaps. Communicating with stakeholders (A) is ongoing but not analytical. Reviewing the issue log (B) is reactive. Performing assumption and constraint analysis (C) addresses project analysis, not engagement. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 100명 이상의 이해관계자가 있는 다국적 프로젝트에서 작업하고 있다. 프로젝트 관리자는 성공적인 프로젝트 전달에 필요한 적절한 이해관계자 참여 및 관여 수준에 대해 우려하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자와 소통하여 해결책을 찾는다. | 프로젝트 이해관계자와 이슈 로그를 검토한다. | 이해관계자 가정 및 제약 분석을 수행한다. | 이해관계자 참여 평가 매트릭스를 평가한다. |  | D | 100명 이상의 이해관계자가 있는 다국적 프로젝트에서 참여 수준에 대한 우려가 있을 때, 프로젝트 관리자는 이해관계자 참여 평가 매트릭스를 평가해야 한다. 이 도구는 원하는 참여 수준과 현재 참여 수준을 문서화하고 격차를 식별한다. 이해관계자와 소통(A)은 지속적이지만 분석적이지 않다. 이슈 로그 검토(B)는 사후 대응적이다. 가정 및 제약 분석 수행(C)은 프로젝트 분석을 다루지 참여는 다루지 않는다.
614 | A human resource (HR) acquisition process for a large project has recently changed. One major process change includes the approval of the financial manager and the recruitment manager. This change to the process implies longer processing. The project urgently needs new resources. What should the project manager do? | Adapt the resource management plan and ask for financial approval before sending it to the customer. | Ask the financial manager to delay implementation due to potential project delays and penalties. | Assess the impact of the change and review the project management plan for next steps. | Review the project schedule to determine which technique will reduce impact on project duration. |  | C | When HR acquisition process changes create longer processing times and the project urgently needs resources, the project manager should assess the impact of the change and review the project management plan for next steps. Impact assessment guides appropriate adjustments to schedule and strategy. Adapting the resource plan and requesting financial approval (A) acts before understanding impact. Asking the financial manager to delay implementation (B) is unrealistic. Reviewing the schedule for duration-reducing techniques (D) is narrowly focused. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Scope & Requirements Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 대규모 프로젝트의 인적 자원(HR) 확보 프로세스가 최근 변경되었다. 주요 프로세스 변경 사항에는 재무 관리자와 채용 관리자의 승인이 포함된다. 이 프로세스 변경은 더 긴 처리 시간을 의미한다. 프로젝트에 긴급하게 새 자원이 필요하다. 프로젝트 관리자는 무엇을 해야 하는가? | 자원 관리 계획을 조정하고 고객에게 보내기 전에 재무 승인을 요청한다. | 재무 관리자에게 잠재적 프로젝트 지연 및 페널티로 인해 시행을 연기하도록 요청한다. | 변경의 영향을 평가하고 다음 단계를 위해 프로젝트 관리 계획을 검토한다. | 프로젝트 기간에 대한 영향을 줄일 기법을 결정하기 위해 프로젝트 일정을 검토한다. |  | C | HR 확보 프로세스 변경으로 처리 시간이 길어지고 프로젝트에 긴급하게 자원이 필요할 때, 프로젝트 관리자는 변경의 영향을 평가하고 다음 단계를 위해 프로젝트 관리 계획을 검토해야 한다. 영향 평가가 일정 및 전략에 대한 적절한 조정을 안내한다. 자원 계획 조정 및 재무 승인 요청(A)은 영향을 이해하기 전에 행동하는 것이다. 재무 관리자에게 시행 연기 요청(B)은 비현실적이다. 기간 단축 기법을 위한 일정 검토(D)는 범위가 좁다.
615 | A project manager is managing a project that requires specialized architecture services. This project was identified as a high risk for the organization. The project manager works with an external architect who is highly specialized. However, the architect will soon resign because they accepted an offer from another firm. What should the project manager do next? | Escalate the issue to the procurement department and ask them to discuss this with the vendor firm. | Call the account manager and ask them to retain the expert by offering them an incentive. | Ask the architect for the contact details for their new employer and call their account manager. | Discuss this with the project team, assess the impact, and decide on the appropriate actions to follow. |  | D | When a highly specialized external architect on a high-risk project plans to resign, the project manager should discuss this with the project team, assess the impact, and decide on appropriate actions. Collaborative impact assessment enables informed decision-making about replacement, knowledge transfer, or risk mitigation. Escalating to procurement (A) is one possible action but not the first step. Calling the new employer (C) is inappropriate. Asking the account manager to retain the expert (B) may not be feasible. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자가 전문 건축 서비스가 필요한 프로젝트를 관리하고 있다. 이 프로젝트는 조직에 고위험으로 식별되었다. 프로젝트 관리자는 고도로 전문화된 외부 건축가와 협력하고 있다. 그러나 건축가가 다른 회사의 제안을 수락하여 곧 퇴직할 예정이다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 조달 부서에 이슈를 에스컬레이션하고 벤더 회사와 논의하도록 요청한다. | 계정 관리자에게 전화하여 인센티브를 제공하여 전문가를 유지하도록 요청한다. | 건축가에게 새 고용주의 연락처를 요청하고 계정 관리자에게 전화한다. | 프로젝트 팀과 논의하고 영향을 평가하며 따를 적절한 조치를 결정한다. |  | D | 고위험 프로젝트에서 고도로 전문화된 외부 건축가가 퇴직을 계획할 때, 프로젝트 관리자는 프로젝트 팀과 논의하고 영향을 평가하며 적절한 조치를 결정해야 한다. 협력적 영향 평가가 교체, 지식 이전 또는 리스크 완화에 대한 정보에 기반한 의사결정을 가능하게 한다. 조달에 에스컬레이션(A)은 가능한 조치 중 하나이지만 첫 번째 단계는 아니다. 새 고용주에게 전화(C)는 부적절하다. 계정 관리자에게 전문가 유지 요청(B)은 실현 불가능할 수 있다.
616 | In a newly formed project team, one experienced team member is overwhelmed by the complexity of the tasks and is not happy with the project team. What should the project manager do? | Explain that the tasks are unavoidable and ask the team member to find a solution to overcome the challenges | Actively listen to the team member and identify ways to support their needs in completing the tasks. | Ask the team member to enter this potential schedule delay in the risk register. | Set up team-building activities with the project team members to reduce tension |  | B | When an experienced team member is overwhelmed by task complexity and unhappy with the team, the project manager should actively listen and identify ways to support their needs. Active listening addresses root causes. Explaining tasks are unavoidable (A) dismisses concerns. Entering a risk in the register (C) is documentation, not support. Team-building activities (D) help group dynamics but do not address individual concerns. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 새로 구성된 프로젝트 팀에서 경험 있는 한 팀원이 작업의 복잡성에 압도당하고 프로젝트 팀에 만족하지 않는다. 프로젝트 관리자는 무엇을 해야 하는가? | 작업은 불가피하며 도전을 극복할 해결책을 찾도록 팀원에게 설명한다. | 팀원의 말을 적극적으로 경청하고 작업 완료에 필요한 지원 방법을 식별한다. | 팀원에게 이 잠재적 일정 지연을 리스크 레지스터에 입력하도록 요청한다. | 긴장을 줄이기 위해 프로젝트 팀원들과 팀 빌딩 활동을 설정한다. |  | B | 경험 있는 팀원이 작업 복잡성에 압도당하고 팀에 불만족할 때, 프로젝트 관리자는 적극적으로 경청하고 지원 방법을 식별해야 한다. 적극적 경청은 근본 원인을 해결한다. 작업이 불가피하다고 설명(A)은 우려를 무시한다. 리스크 레지스터에 입력(C)은 문서화이지 지원이 아니다. 팀 빌딩 활동(D)은 그룹 역학에 도움이 되지만 개인적 우려를 해결하지 않는다.
617 | A project manager is part of a distributed team. The project team is using a product backlog, but due to an excessive workload, the backlog items are not very detailed. In the retrospective, a couple of new team members are raising the issue of knowledge transfer inside the team. What should the project manager do? | Organize knowledge-sharing workshops and ask one of the senior team members to facilitate them. | Ask the team to outline their expectations and confirm with them the approach to use for knowledge transfer. | Hire a technical writer to document the work completed to date and develop a handover document. | Ensure that formal email communication is used when more information is needed to understand the work done. |  | A | In a distributed team where backlog items lack detail and new members raise knowledge transfer concerns, the project manager should organize knowledge-sharing workshops facilitated by a senior team member. This structured approach ensures knowledge is transferred comprehensively while fostering collaboration and shared understanding. Asking the team to outline expectations (B) gathers input but does not deliver the knowledge transfer. Hiring a technical writer (C) creates documentation but not interactive learning. Using formal email communication (D) is passive and inefficient for complex knowledge transfer. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트 관리자가 분산 팀의 일원이다. 프로젝트 팀은 제품 백로그를 사용하고 있지만, 과도한 업무량으로 백로그 항목이 매우 상세하지 않다. 회고에서 몇몇 신규 팀원들이 팀 내 지식 이전 문제를 제기하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 지식 공유 워크숍을 조직하고 시니어 팀원 중 한 명에게 진행을 요청한다. | 팀에게 기대치를 설명하고 지식 이전에 사용할 접근 방식을 확인하도록 요청한다. | 현재까지 완료된 작업을 문서화하고 인수인계 문서를 작성하기 위해 기술 작가를 고용한다. | 완료된 작업을 이해하기 위해 추가 정보가 필요할 때 공식 이메일 커뮤니케이션을 사용하도록 보장한다. |  | A | 분산 팀에서 백로그 항목이 상세하지 않고 신규 팀원들이 지식 이전 우려를 제기할 때, 프로젝트 관리자는 시니어 팀원이 진행하는 지식 공유 워크숍을 조직해야 한다. 이 구조적 접근은 지식이 포괄적으로 이전되도록 보장하면서 협력과 공유된 이해를 촉진한다. 팀에게 기대치 설명 요청(B)은 의견을 수집하지만 지식 이전을 전달하지 않는다. 기술 작가 고용(C)은 문서를 만들지만 상호작용적 학습은 아니다. 공식 이메일 사용(D)은 복잡한 지식 이전에 수동적이고 비효율적이다.
618 | A project manager is facilitating an iteration retrospective. The iteration did not go well and the committed functionality was not delivered to users. The project involves a vendor team for the build and an internal quality assurance (QA) team. In the past, there were tensions between the vendor and the internal team. What should the project manager do? | Schedule a preliminary meeting with the account manager from the vendor and the test manager. | Establish a clear agenda for the meeting and remind the vendor and internal teams that the scope is to improve the process. | Invite the procurement manager and a representative from the vendor to manage the current tense relationship. | Hold separate retrospective meetings for both the vendor team and the internal team. |  | B | During an iteration retrospective with tensions between a vendor team and the internal QA team, the project manager should establish a clear agenda and remind both teams that the scope of the meeting is to improve the process. A well-structured agenda keeps the discussion process-oriented and prevents blame—essential for constructive retrospectives. Scheduling a preliminary meeting with account and test managers (A) focuses only on leadership rather than the full team. Inviting the procurement manager (C) introduces unnecessary escalation and shifts focus from improvement to contract management. Holding separate retrospectives (D) prevents open communication and cross-team collaboration. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 이터레이션 회고를 촉진하고 있다. 이터레이션이 잘 되지 않았고 약속된 기능이 사용자에게 전달되지 않았다. 프로젝트에는 빌드를 위한 벤더 팀과 내부 품질 보증(QA) 팀이 참여하고 있다. 과거에 벤더와 내부 팀 간에 긴장이 있었다. 프로젝트 관리자는 무엇을 해야 하는가? | 벤더의 계정 관리자 및 테스트 관리자와 사전 회의를 예약한다. | 회의에 대한 명확한 안건을 수립하고 벤더 및 내부 팀에게 범위는 프로세스 개선임을 상기시킨다. | 현재의 긴장 관계를 관리하기 위해 조달 관리자와 벤더 대표를 초대한다. | 벤더 팀과 내부 팀 모두를 위해 별도의 회고 회의를 개최한다. |  | B | 벤더 팀과 내부 QA 팀 간 긴장이 있는 이터레이션 회고에서, 프로젝트 관리자는 명확한 안건을 수립하고 양 팀에게 회의의 범위가 프로세스 개선임을 상기시켜야 한다. 잘 구조화된 안건은 토론을 프로세스 중심으로 유지하고 비난을 방지한다—건설적인 회고에 필수적이다. 계정 관리자 및 테스트 관리자와 사전 회의 예약(A)은 전체 팀이 아닌 리더십에만 초점을 맞춘다. 조달 관리자 초대(C)는 불필요한 에스컬레이션을 도입하고 초점을 개선에서 계약 관리로 전환한다. 별도 회고 개최(D)는 개방적 소통과 팀 간 협력을 방해한다.
619 | A business improvement opportunity to reduce energy usage has been identified. The project manager has assembled a team that includes site engineers to deliver this project. However, due to production imperatives, the site engineers may not be fully focused on the project. How should the project manager manage the team? | Continue the project implementation without the site engineers to ensure the scheduleis maintained. | Commit each team member ' s time and deliverables and aim for overall projectcompletion. | Contract external resources to fulfill the role of the site engineers who cannot support the project. | Develop an approved responsibility assignment matrix (RAM) to confirm internal andexternal resource requirements. |  | D | When site engineers may not be fully focused on the project due to production demands, the project manager should develop an approved responsibility assignment matrix (RAM) to confirm internal and external resource requirements. A RAM clarifies roles, responsibilities, and expectations for all team members, enabling better coordination. Continuing without site engineers (A) loses critical expertise. Committing each member's time (B) is unrealistic without addressing competing priorities. Contracting external resources (C) adds cost and complexity before optimizing internal resources. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Integrate Sustainability | Direct and Manage Project Work | Sustainability | 에너지 사용량을 줄이기 위한 비즈니스 개선 기회가 식별되었다. 프로젝트 관리자가 이 프로젝트를 전달하기 위해 현장 엔지니어를 포함한 팀을 구성했다. 그러나 생산 우선사항으로 인해 현장 엔지니어가 프로젝트에 완전히 집중하지 못할 수 있다. 프로젝트 관리자는 팀을 어떻게 관리해야 하는가? | 일정 유지를 위해 현장 엔지니어 없이 프로젝트 실행을 계속한다. | 각 팀원의 시간과 산출물을 확약하고 전체 프로젝트 완료를 목표로 한다. | 프로젝트를 지원할 수 없는 현장 엔지니어의 역할을 수행할 외부 자원을 계약한다. | 내부 및 외부 자원 요구사항을 확인하기 위해 승인된 책임 배정 매트릭스(RAM)를 개발한다. |  | D | 생산 수요로 인해 현장 엔지니어가 프로젝트에 완전히 집중하지 못할 수 있을 때, 프로젝트 관리자는 내부 및 외부 자원 요구사항을 확인하기 위해 승인된 책임 배정 매트릭스(RAM)를 개발해야 한다. RAM은 모든 팀원의 역할, 책임, 기대를 명확히 하여 더 나은 조율을 가능하게 한다. 현장 엔지니어 없이 계속(A)은 핵심 전문성을 잃는다. 각 팀원 시간 확약(B)은 경쟁 우선순위를 해결하지 않으면 비현실적이다. 외부 자원 계약(C)은 내부 자원을 최적화하기 전에 비용과 복잡성을 추가한다.
620 | A project manager is part of a team that is launching a series of features to comply with a new regulation. The team has only 6 weeks to release the features to the legacy applications. During the standup meeting, a software engineer indicated that the development of an important feature is on hold until the assigned designer completes a specific task. This delay is a serious roadblock to meeting the release date. What should the project manager do? | Contact the design team manager and ask to reconsider the priority list based on the latest situation, | Ask the software engineer to move forward without completing the important feature. | Meet with the designer to share the current status and develop a solution to complete the 135 task. | Meet with the design team manager to inform them of the current status and request an additional designer. |  | C | The PM should meet with the designer to understand challenges and collaboratively find a solution. Active engagement with team members to identify and resolve issues promotes open communication, maintains project momentum, and demonstrates servant leadership. This approach is more effective than waiting for the problem to resolve itself or escalating prematurely. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 새로운 규정을 준수하기 위해 일련의 기능을 출시하는 팀의 일원이다. 팀은 레거시 애플리케이션에 기능을 릴리스하는 데 6주밖에 없다. 스탠드업 회의에서 소프트웨어 엔지니어가 배정된 디자이너가 특정 작업을 완료할 때까지 중요한 기능 개발이 보류 중이라고 알렸다. 이 지연은 릴리스 날짜를 맞추는 데 심각한 장애물이다. 프로젝트 관리자는 무엇을 해야 하는가? | 디자인 팀 관리자에게 연락하여 최신 상황에 기반하여 우선순위 목록을 재검토하도록 요청한다. | 소프트웨어 엔지니어에게 중요한 기능을 완료하지 않고 진행하도록 요청한다. | 디자이너와 만나 현재 상태를 공유하고 작업을 완료할 해결책을 개발한다. | 디자인 팀 관리자와 만나 현재 상태를 알리고 추가 디자이너를 요청한다. |  | C | PM은 디자이너와 만나 과제를 이해하고 협력적으로 해결책을 찾아야 한다. 팀원과의 적극적 참여를 통해 이슈를 식별하고 해결하면 개방적 소통을 촉진하고 프로젝트 추진력을 유지하며 서번트 리더십을 보여준다. 이 접근 방식은 문제가 자체적으로 해결되기를 기다리거나 성급하게 에스컬레이션하는 것보다 더 효과적이다.
621 | While preparing an earned value analysis (EVA) for the sponsor, the project manager provided this information in the latest project report: Approved Work Package Cost Estimates: US$9,500, Contingency reserves: $500, Management reserves: 10% of contingency reserves, Percent complete of the project: 50%, Planned percent of the project: 40%, Actual costs of the project: US$4,500. What is accurate about the project status? | The project cost is 10% lower than planned. | The actual work is 25% less than the planned work. | The project cost is 10% higher than planned. | The actual work is 25% more than the planned work. |  | A | Given BAC = $9,500 + $500 + $50 = $10,050, EV = 50% × $10,050 = $5,025, PV = 40% × $10,050 = $4,020, AC = $4,500. CPI = $5,025/$4,500 = 1.12 — the project is under budget. SPI = $5,025/$4,020 = 1.25 — the project is ahead of schedule. The project cost is approximately 10% lower than planned. The actual work is not 25% less (B) or more (D) than planned. The cost is not 10% higher (C). | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Earned Value Management | Business Environment | Plan and Manage Risk | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 스폰서를 위한 획득가치 분석(EVA)을 준비하면서 프로젝트 관리자가 최신 프로젝트 보고서에 다음 정보를 제공했다: 승인된 작업 패키지 비용 추정치: US$9,500, 우발사태 예비비: $500, 관리 예비비: 우발사태 예비비의 10%, 프로젝트 완료율: 50%, 계획된 프로젝트 비율: 40%, 프로젝트 실제 비용: US$4,500. 프로젝트 상태에 대해 정확한 것은? | 프로젝트 비용이 계획보다 10% 낮다. | 실제 작업이 계획된 작업보다 25% 적다. | 프로젝트 비용이 계획보다 10% 높다. | 실제 작업이 계획된 작업보다 25% 많다. |  | A | BAC = $9,500 + $500 + $50 = $10,050, EV = 50% × $10,050 = $5,025, PV = 40% × $10,050 = $4,020, AC = $4,500. CPI = $5,025/$4,500 = 1.12 — 프로젝트가 예산 이하이다. SPI = $5,025/$4,020 = 1.25 — 프로젝트가 일정보다 앞서 있다. 프로젝트 비용은 계획보다 약 10% 낮다. 실제 작업이 25% 적은(B) 것이나 많은(D) 것은 아니다. 비용이 10% 높은(C) 것도 아니다.
622 | A project manager just completed the planning phase when a new stakeholder was assigned to the project. The deliverables were discussed with the customer, but the new stakeholder is still concerned about the benefits of two of the deliverables. What should the project manager do next to address this stakeholder's concerns? | Add the stakeholder to the stakeholder engagement plan. | Review the prior analysis results with the stakeholder. | Review the benefits realization plan with the stakeholder. | Provide the stakeholder with regular updates on project progress. |  | C | When a new stakeholder is concerned about the benefits of two deliverables after the planning phase is complete, the project manager should review the benefits realization plan with the stakeholder. The benefits plan directly addresses benefit concerns. Adding to the engagement plan (A) is administrative. Reviewing prior analysis results (B) is one input but not benefit-focused. Providing regular progress updates (D) does not address specific benefit concerns. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 계획 단계를 막 완료했을 때 새로운 이해관계자가 프로젝트에 배정되었다. 산출물은 고객과 논의되었지만, 새 이해관계자는 여전히 두 산출물의 혜택에 대해 우려하고 있다. 이 이해관계자의 우려를 해결하기 위해 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 이해관계자를 이해관계자 참여 계획에 추가한다. | 이전 분석 결과를 이해관계자와 검토한다. | 이해관계자와 혜택 실현 계획을 검토한다. | 이해관계자에게 프로젝트 진행에 대한 정기적인 업데이트를 제공한다. |  | C | 계획 단계 완료 후 새 이해관계자가 두 산출물의 혜택에 대해 우려할 때, 프로젝트 관리자는 이해관계자와 혜택 실현 계획을 검토해야 한다. 혜택 계획은 혜택 우려를 직접 다룬다. 참여 계획에 추가(A)는 행정적이다. 이전 분석 결과 검토(B)는 하나의 입력이지만 혜택에 초점을 맞추지 않는다. 정기적 진행 업데이트 제공(D)은 특정 혜택 우려를 해결하지 않는다.
623 | A project manager has a team of shared resources from other projects who are working on a client project. Three days before the project is due, the team informs the project manager that the project will be delayed because a component was not delivered on time. Competing priorities of the shared resources are delaying delivery of the component. What should the project manager have done to prevent this delay from happening? | Updated the risk management plan and registered lessons learned for the project | Used the resource management plan to identify the impacts of the other projects | Maintained constant communication with the stakeholders of the other projects | Reorganized the team for the project based on the work breakdown structure (WBS) |  | B | When shared resources from other projects cause a component delay three days before the deadline due to competing priorities, the project manager should have used the resource management plan to identify the impacts of other projects. Proactive resource monitoring prevents conflicts. Updating the risk management plan and lessons learned (A) is retrospective. Maintaining stakeholder communication (C) is helpful but insufficient. Reorganizing based on the WBS (D) does not address cross-project resource conflicts. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | WBS/Decomposition | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트 관리자가 다른 프로젝트의 공유 자원으로 구성된 팀과 고객 프로젝트를 진행하고 있다. 프로젝트 마감 3일 전에 팀이 구성요소가 제시간에 전달되지 않아 프로젝트가 지연될 것이라고 알렸다. 공유 자원의 경쟁 우선순위가 구성요소 전달을 지연시키고 있다. 프로젝트 관리자는 이 지연을 방지하기 위해 무엇을 했어야 하는가? | 리스크 관리 계획을 업데이트하고 프로젝트에 대한 교훈을 등록했어야 한다. | 자원 관리 계획을 사용하여 다른 프로젝트의 영향을 식별했어야 한다. | 다른 프로젝트의 이해관계자와 지속적인 커뮤니케이션을 유지했어야 한다. | 작업 분류 체계(WBS)에 기반하여 프로젝트 팀을 재조직했어야 한다. |  | B | 다른 프로젝트의 공유 자원이 경쟁 우선순위로 인해 마감 3일 전에 구성요소 지연을 초래할 때, 프로젝트 관리자는 자원 관리 계획을 사용하여 다른 프로젝트의 영향을 식별했어야 한다. 사전 예방적 자원 모니터링이 충돌을 방지한다. 리스크 관리 계획 업데이트 및 교훈 등록(A)은 회고적이다. 이해관계자 커뮤니케이션 유지(C)는 도움이 되지만 불충분하다. WBS 기반 재조직(D)은 프로젝트 간 자원 충돌을 해결하지 않는다.
624 | A project manager is newly assigned to the second phase of an ongoing project. During the implementation, a defect occurred and no one knows how to fix it, as the former engineering team has moved to another project. The customer warns that previously, this defect negatively affected the project schedule. What should the project manager do first? | Update the risk management plan. | Acquire knowledgeable resources. | Check the organizational process assets (OPAs). | Extend the timeline of the project. |  | C | When a defect occurs and the original engineering team has moved on, the project manager should first check the organizational process assets (OPAs). OPAs include historical documentation, lessons learned, and knowledge bases that may contain solutions. Updating the risk management plan (A) addresses future risks, not the current defect. Acquiring knowledgeable resources (B) may be needed but not before checking existing knowledge. Extending the timeline (D) does not solve the defect. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트 관리자가 진행 중인 프로젝트의 2단계에 새로 배정되었다. 구현 중에 결함이 발생했으나 이전 엔지니어링 팀이 다른 프로젝트로 이동하여 아무도 수정 방법을 모른다. 고객은 이전에 이 결함이 프로젝트 일정에 부정적인 영향을 미쳤다고 경고한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 리스크 관리 계획을 업데이트한다. | 지식이 있는 자원을 확보한다. | 조직 프로세스 자산(OPA)을 확인한다. | 프로젝트 타임라인을 연장한다. |  | C | 결함이 발생하고 원래 엔지니어링 팀이 이동한 경우, 프로젝트 관리자는 먼저 조직 프로세스 자산(OPA)을 확인해야 한다. OPA에는 해결책을 포함할 수 있는 이력 문서, 교훈, 지식 기반이 포함되어 있다. 리스크 관리 계획 업데이트(A)는 미래 리스크를 다루지 현재 결함을 다루지 않는다. 지식이 있는 자원 확보(B)는 필요할 수 있지만 기존 지식을 확인하기 전에 해야 할 일이 아니다. 타임라인 연장(D)은 결함을 해결하지 않는다.
625 | An agile project team received an assignment to develop an industrial system that interfaces with robots. The project team does not have any prior experience performing this type of work. Team members are interested in acquiring such expertise but it may result in a project delay. How should this situation be handled? | Hire a consulting company to address the robotic interface questions, when necessary, and to help avoid delays and quality issues. | Use a robotics vendor company to develop the interfaces so the team will not be held back by a lack of expertise in this type of work, | Add an experienced professional to the team to reinforce knowledge sharing and help grow team expertise in the new product | Create a separate team with experienced members who understand the technology and split the product backlog according to team specialization. |  | C | Adding an experienced professional to the team bridges knowledge gaps while fostering learning and expertise development. This strategic approach leverages project team expertise to develop better solutions, facilitates knowledge sharing, and promotes effective use of specialist information—aligning with PMI guidance on team development and continuous capability improvement. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 애자일 프로젝트 팀이 로봇과 인터페이스하는 산업 시스템을 개발하는 과제를 받았다. 프로젝트 팀은 이 유형의 작업을 수행한 경험이 없다. 팀원들은 그러한 전문성을 습득하는 데 관심이 있지만 프로젝트 지연이 발생할 수 있다. 이 상황을 어떻게 처리해야 하는가? | 필요 시 로봇 인터페이스 질문을 처리하고 지연 및 품질 문제를 방지하기 위해 컨설팅 회사를 고용한다. | 팀이 이 유형의 작업에 대한 전문성 부족으로 지체되지 않도록 로봇 벤더 회사를 사용하여 인터페이스를 개발한다. | 경험이 있는 전문가를 팀에 추가하여 지식 공유를 강화하고 새로운 제품에 대한 팀 전문성 성장을 돕는다. | 기술을 이해하는 경험 있는 멤버로 별도의 팀을 구성하고 팀 전문성에 따라 제품 백로그를 분할한다. |  | C | 경험 있는 전문가를 팀에 추가하면 학습과 전문성 개발을 촉진하면서 지식 격차를 해소한다. 이 전략적 접근은 프로젝트 팀 전문성을 활용하여 더 나은 솔루션을 개발하고, 지식 공유를 촉진하며, 전문가 정보의 효과적 사용을 촉진한다—팀 개발 및 지속적 역량 개선에 대한 PMI 지침과 일치한다.
626 | A new project manager has been hired at a company that has suffered many project failures. The project manager has been tasked with delivering a software product for the company's biggest customer. The customer has not been able to articulate how a major piece of functionality should work. The project manager wants to deliver value immediately. How should the project manager approach the software development life cycle with this customer? | Raise a risk that scoping and estimating will be delayed if the customer cannot approve requirements | Explain that the team will build a production prototype model to help the customer visualize how the features should work | Assign a business analyst to build detailed requirements so the project manager can estimate the project duration | Add extra time and resources to the estimating phase to accommodate the lack of requirements |  | B | When a customer cannot clearly articulate how a major piece of functionality should work, the best approach is to build a production prototype model to help the customer visualize how the features should work. Prototyping makes requirements tangible, accelerates learning through rapid feedback, and reduces ambiguity by showing working behavior rather than relying on written specifications. This aligns with iterative delivery and progressive elaboration. Raising a scoping risk (A) documents uncertainty but does not solve the problem or create momentum. Assigning a business analyst for detailed requirements (C) still depends on the customer's ability to articulate needs. Adding extra time and resources to the estimating phase (D) delays value delivery without addressing the root cause. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 새로운 프로젝트 관리자가 많은 프로젝트 실패를 겪은 회사에 고용되었다. 프로젝트 관리자는 회사의 가장 큰 고객을 위한 소프트웨어 제품을 전달하는 임무를 맡았다. 고객이 주요 기능이 어떻게 작동해야 하는지 명확히 설명할 수 없었다. 프로젝트 관리자는 즉시 가치를 전달하고자 한다. 프로젝트 관리자는 이 고객과의 소프트웨어 개발 생명 주기에 어떻게 접근해야 하는가? | 고객이 요구사항을 승인할 수 없으면 범위 설정 및 추정이 지연될 리스크를 제기한다. | 팀이 고객이 기능이 어떻게 작동해야 하는지 시각화할 수 있도록 생산 프로토타입 모델을 구축할 것이라고 설명한다. | 프로젝트 관리자가 프로젝트 기간을 추정할 수 있도록 비즈니스 분석가를 배정하여 상세 요구사항을 작성한다. | 요구사항 부족을 수용하기 위해 추정 단계에 추가 시간과 자원을 투입한다. |  | B | 고객이 주요 기능이 어떻게 작동해야 하는지 명확히 설명할 수 없을 때, 가장 좋은 접근은 고객이 기능이 어떻게 작동해야 하는지 시각화할 수 있도록 생산 프로토타입 모델을 구축하는 것이다. 프로토타이핑은 요구사항을 실체화하고, 빠른 피드백을 통한 학습을 가속화하며, 서면 사양에 의존하는 대신 작동하는 동작을 보여줌으로써 모호성을 줄인다. 이는 반복적 전달 및 점진적 정교화와 일치한다. 범위 리스크 제기(A)는 불확실성을 문서화하지만 문제를 해결하거나 추진력을 만들지 않는다. 상세 요구사항을 위한 비즈니스 분석가 배정(C)은 여전히 고객의 요구 표현 능력에 의존한다. 추정 단계에 추가 시간과 자원 투입(D)은 근본 원인을 해결하지 않고 가치 전달을 지연시킨다.
627 | One of the main deliverables of a project is delayed due to a problem with a key provider. What should the project manager do? | Schedule a meeting with the provider to review impacts to the project timeline and deliverables | Create a change request to replace the provider with a more responsible one from the provider list | Schedule a meeting with all relevant stakeholders to determine the best approach to 355 resolve the issue | Discuss with the sponsor and seek guidance to impose the penalty stipulated in the agreement |  | A | When a key provider's problem delays a main deliverable, the project manager should first schedule a meeting with the provider to review impacts on the timeline and deliverables. Direct engagement enables fact-finding about root causes, negotiation on recovery options, and alignment on corrective actions. Immediately replacing the provider (B) is costly and contractually complex without first understanding the situation. Meeting all stakeholders (C) is broader than necessary before having concrete information from the provider. Seeking sponsor guidance on penalties (D) may be appropriate later but leading with penalties damages collaboration. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 프로젝트의 주요 산출물 중 하나가 핵심 공급업체의 문제로 지연되고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 공급업체와 회의를 예약하여 프로젝트 타임라인과 산출물에 대한 영향을 검토한다. | 공급업체 목록에서 더 책임감 있는 업체로 교체하기 위한 변경 요청을 작성한다. | 모든 관련 이해관계자와 회의를 예약하여 이슈를 해결할 최선의 접근 방식을 결정한다. | 스폰서와 논의하고 계약에 명시된 벌칙을 부과하기 위한 지침을 구한다. |  | A | 핵심 공급업체의 문제로 주요 산출물이 지연될 때, 프로젝트 관리자는 먼저 공급업체와 회의를 예약하여 타임라인과 산출물에 대한 영향을 검토해야 한다. 직접적 참여는 근본 원인에 대한 사실 확인, 회복 옵션 협상, 시정 조치 정렬을 가능하게 한다. 즉시 공급업체 교체(B)는 상황을 먼저 이해하지 않으면 비용이 많이 들고 계약상 복잡하다. 모든 이해관계자 회의(C)는 공급업체로부터 구체적 정보를 얻기 전에는 필요 이상으로 광범위하다. 스폰서에게 벌칙 지침 구하기(D)는 나중에 적절할 수 있지만 벌칙으로 시작하면 협력 관계를 손상시킨다.
628 | A project manager has been asked for performance feedback regarding one of the team members. The project manager would like to gather additional input from the project team because there are no metrics in place for evaluating employee performance. What should the project manager do next? | Determine the appropriate approach | Analyze team member influence | Identify levels of decision-making authority | Evaluate demonstrated task accountability |  | A | When asked for performance feedback with no metrics in place, the project manager should determine the appropriate approach for evaluation. Establishing a proper framework ensures fair and comprehensive assessment. Analyzing team member influence (B) is one metric, not a framework. Identifying decision-making authority levels (C) evaluates authority, not performance. Evaluating demonstrated task accountability (D) is one dimension of performance. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 팀원 중 한 명에 대한 성과 피드백을 요청받았다. 프로젝트 관리자는 직원 성과 평가를 위한 지표가 없기 때문에 프로젝트 팀으로부터 추가 입력을 수집하고자 한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 적절한 접근 방식을 결정한다. | 팀원의 영향력을 분석한다. | 의사결정 권한 수준을 식별한다. | 입증된 업무 책임을 평가한다. |  | A | 성과 피드백을 요청받았으나 지표가 없을 때, 프로젝트 관리자는 적절한 접근 방식을 결정해야 한다. 적절한 프레임워크를 수립하면 공정하고 포괄적인 평가가 보장된다. 팀원 영향력 분석(B)은 하나의 지표일 뿐 프레임워크가 아니다. 의사결정 권한 수준 식별(C)은 권한을 평가하지 성과를 평가하지 않는다. 입증된 업무 책임 평가(D)는 성과의 한 차원일 뿐이다.
629 | A multinational company is embarking on an ambitious organizational change project. The objectives of the project include the complete transformation of the organization's structure, role catalog, and global locations in which supporting services are to be delivered. What should the project manager advise as an essential component of the project? | A project stakeholder map to assist in understanding which senior executives need to be consulted on the communications management plan. | A project risk management plan to evaluate and mitigate the risks of change on the performing organization. | A communications management plan and a change management plan to convey the need for change and support the organization. | A panel of subject matter experts (SMEs) that can be consulted for their opinions on how to implement the change project. |  | C | The correct answer is C. A communications management plan and a change management plan to convey the need for change and support the organization. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Agile General Practices | Business Environment | Support Organizational Change | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 다국적 기업이 야심 찬 조직 변화 프로젝트에 착수하고 있다. 프로젝트의 목표는 조직의 구조, 역할 카탈로그, 지원 서비스가 전달되는 글로벌 위치의 완전한 변환을 포함한다. 프로젝트 관리자는 프로젝트의 필수 구성요소로 무엇을 조언해야 하는가? | 어떤 고위 경영진을 커뮤니케이션 관리 계획에 대해 상담해야 하는지 이해하기 위한 프로젝트 이해관계자 맵. | 변화가 수행 조직에 미치는 리스크를 평가하고 완화하기 위한 프로젝트 리스크 관리 계획. | 변화의 필요성을 전달하고 조직을 지원하기 위한 커뮤니케이션 관리 계획과 변경 관리 계획. | 변화 프로젝트를 어떻게 실행할지에 대한 의견을 상담할 수 있는 주제 전문가(SME) 패널. |  | C | 정답은 C이다. 변화의 필요성을 전달하고 조직을 지원하기 위한 커뮤니케이션 관리 계획과 변경 관리 계획. 이 접근은 상황을 효과적으로 해결하면서 적절한 프로세스와 이해관계자 정렬을 유지하는 프로젝트 관리 모범 사례를 따른다.
630 | A project manager is using a hybrid approach for a project. The project team created and reviewed the risk log with the stakeholders at the beginning of the project. However, midway through the project, the project team and stakeholders became misaligned with the risks and mitigation strategies. When should the risks be reviewed to ensure alignment between the project team and the stakeholders? | During the risk register update | During each iteration and review | During the retrospectives | During each steering committee meeting |  | B | In a hybrid project where the team and stakeholders became misaligned on risks and mitigation strategies midway through, risks should be reviewed during each iteration and review. Regular, frequent reviews ensure ongoing alignment, timely risk identification, and collaborative mitigation planning throughout the project. Reviewing during risk register updates (A) depends on when updates occur and may not be frequent enough. Reviewing during retrospectives (C) focuses on process improvement, not risk alignment with stakeholders. Reviewing during steering committee meetings (D) is too infrequent to maintain continuous alignment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Hybrid/Tailoring | 프로젝트 관리자가 프로젝트에 하이브리드 접근 방식을 사용하고 있다. 프로젝트 팀이 프로젝트 초기에 이해관계자와 함께 리스크 로그를 작성하고 검토했다. 그러나 프로젝트 중간에 프로젝트 팀과 이해관계자가 리스크와 완화 전략에 대해 정렬이 어긋나게 되었다. 리스크는 언제 검토해야 팀과 이해관계자 간의 정렬을 보장할 수 있는가? | 리스크 레지스터 업데이트 시 | 각 반복 및 검토 시 | 회고 시 | 각 운영 위원회 회의 시 |  | B | 하이브리드 프로젝트에서 팀과 이해관계자가 프로젝트 중간에 리스크와 완화 전략에 대해 정렬이 어긋나게 된 경우, 리스크는 각 반복 및 검토 시 검토해야 한다. 정기적이고 빈번한 검토는 지속적인 정렬, 적시 리스크 식별, 프로젝트 전반에 걸친 협력적 완화 계획을 보장한다. 리스크 레지스터 업데이트 시 검토(A)는 업데이트 시점에 따라 다르며 충분히 빈번하지 않을 수 있다. 회고 시 검토(C)는 프로세스 개선에 초점을 맞추지 이해관계자와의 리스크 정렬에는 초점을 맞추지 않는다. 운영 위원회 회의 시 검토(D)는 지속적 정렬을 유지하기에 너무 빈도가 낮다.
631 | A project manager is working on a software product that will be installed across all levels of the client's organization. The client's executive sponsor insists that only stakeholders at the highest level of the company will be involved in the planning phase. What should the project manager do? | Perform an independent analysis to determine the stakeholders from the client ' s organization. | Defer to the judgment of the client ' s executive sponsor since they will determine whether the project is a success. | Ask the client how the project will affect the client ' s organization and recommend that all impacted parties be involved. | involve an executive-level stakeholder at the project manager ' s own company to speak with the client ' s executive sponsor. |  | C | When the client's executive sponsor wants only the highest-level stakeholders in planning but the software affects all organizational levels, the project manager should ask the client how the project will affect the organization and recommend that all impacted parties be involved. This ensures comprehensive stakeholder engagement while respecting the client relationship. Performing an independent analysis (A) bypasses client engagement. Deferring entirely to the sponsor (B) risks missing critical stakeholder input. Involving an executive from the PM's company (D) escalates unnecessarily. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 고객 조직의 모든 수준에 설치될 소프트웨어 제품을 작업하고 있다. 고객의 임원 스폰서가 회사의 최고 수준 이해관계자만 기획 단계에 참여할 것이라고 주장한다. 프로젝트 관리자는 무엇을 해야 하는가? | 고객 조직의 이해관계자를 파악하기 위한 독립적 분석을 수행한다. | 고객의 임원 스폰서가 프로젝트 성공 여부를 결정하므로 그의 판단에 따른다. | 고객에게 프로젝트가 고객 조직에 어떤 영향을 미칠지 묻고 영향을 받는 모든 당사자가 참여하도록 권고한다. | 프로젝트 관리자의 회사에서 임원급 이해관계자를 참여시켜 고객의 임원 스폰서와 대화하도록 한다. |  | C | 고객의 임원 스폰서가 최고 수준 이해관계자만 기획에 참여하기를 원하지만 소프트웨어가 모든 조직 수준에 영향을 미칠 때, 프로젝트 관리자는 고객에게 프로젝트가 조직에 어떤 영향을 미칠지 묻고 영향을 받는 모든 당사자가 참여하도록 권고해야 한다. 이는 고객 관계를 존중하면서 포괄적인 이해관계자 참여를 보장한다. 독립적 분석 수행(A)은 고객 참여를 우회한다. 스폰서에게 전적으로 따르기(B)는 중요한 이해관계자 입력을 놓칠 위험이 있다. PM 회사의 임원 참여(D)는 불필요하게 에스컬레이션한다.
632 | A website application project is underway and the agile team has reached a stable velocity. After eight iterations, they complete 20 story points per sprint. The project lead and team plan to maintain the same velocity for the next 2 months. After this period, the team completed 100 story points. The project sponsor asks for the project status. How should the project lead respond? | The schedule performance index (SPI) is 25% less than expected. | The team ' s performance indicator is higher than expected. | The cost and schedule performance indicators are equivalent. | The cost performance index (CPI) is below average with a 25% reduction. |  | A | The team planned to maintain a velocity of 20 story points per sprint. Over 2 months, the expected output based on the planned velocity would have been higher than the 100 story points actually completed. This means the schedule performance index (SPI) is below the planned target, indicating a 25% shortfall in expected delivery performance. The cost performance index reference (D) is irrelevant since no cost data is provided. A higher-than-expected performance indicator (B) contradicts the actual results. Equivalent cost and schedule indicators (C) cannot be determined without cost information. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 웹사이트 애플리케이션 프로젝트가 진행 중이고 애자일 팀이 안정적인 벨로시티에 도달했다. 8번의 반복 후, 스프린트당 20 스토리 포인트를 완료한다. 프로젝트 리더와 팀은 다음 2개월 동안 동일한 벨로시티를 유지할 계획이다. 이 기간 후 팀은 100 스토리 포인트를 완료했다. 프로젝트 스폰서가 프로젝트 상태를 묻는다. 프로젝트 리더는 어떻게 응답해야 하는가? | 일정 성과 지수(SPI)가 예상보다 25% 낮다. | 팀의 성과 지표가 예상보다 높다. | 비용 및 일정 성과 지표가 동등하다. | 비용 성과 지수(CPI)가 25% 감소로 평균 이하이다. |  | A | 팀은 스프린트당 20 스토리 포인트의 벨로시티를 유지할 계획이었다. 2개월에 걸쳐 계획된 벨로시티를 기반으로 한 예상 산출량은 실제 완료된 100 스토리 포인트보다 높았을 것이다. 이는 일정 성과 지수(SPI)가 계획된 목표보다 낮음을 의미하며, 예상 전달 성과에서 25% 부족을 나타낸다. 비용 성과 지수 언급(D)은 비용 데이터가 제공되지 않아 관련이 없다. 예상보다 높은 성과 지표(B)는 실제 결과와 모순된다. 동등한 비용 및 일정 지표(C)는 비용 정보 없이는 판단할 수 없다.
633 | At the end of a project, the project manager was asked to provide a performance rating of the project team members. What should the project manager mainly make reference to? | Agreed-upon key performance indicators (KPIs) | Competencies of team members | Input from project stakeholders | Feedback from the project sponsor |  | A | Performance ratings should primarily reference the agreed-upon key performance indicators (KPIs). KPIs are quantifiable measures established at the beginning of the project to evaluate each team member's contribution toward achieving project objectives. This ensures assessments are objective and based on predefined criteria. Competencies of team members (B) describe capabilities, not performance outcomes. Input from stakeholders (C) provides perspective but may be subjective. Feedback from the sponsor (D) reflects one stakeholder's view and may not cover all aspects of individual performance. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 종료 시, 프로젝트 관리자가 프로젝트 팀원들의 성과 평가를 제공하도록 요청받았다. 프로젝트 관리자는 주로 무엇을 참고해야 하는가? | 합의된 핵심 성과 지표(KPI) | 팀원들의 역량 | 프로젝트 이해관계자의 의견 | 프로젝트 스폰서의 피드백 |  | A | 성과 평가는 주로 합의된 핵심 성과 지표(KPI)를 참고해야 한다. KPI는 프로젝트 초기에 수립된 정량적 측정 기준으로, 프로젝트 목표 달성에 대한 각 팀원의 기여를 평가한다. 이를 통해 객관적이고 사전 정의된 기준에 기반한 평가가 보장된다. 팀원 역량(B)은 능력을 설명하지 성과 결과를 설명하지 않는다. 이해관계자 의견(C)은 관점을 제공하지만 주관적일 수 있다. 스폰서 피드백(D)은 한 이해관계자의 견해를 반영하며 개인 성과의 모든 측면을 다루지 못할 수 있다.
634 | After a project review meeting, a key stakeholder tells another stakeholder they do not trust the project status report. The second stakeholder approaches the project manager and mentions the conversation. What should the project manager do? | Email the status report to all stakeholders and ask them to review and provide feedback | Request the sponsor ask the key stakeholder to be attentive during the project review meeting | Present the status report in a chart and assume everyone understands the report | Schedule a meeting with the key stakeholder to address the issue and obtain direct feedback |  | D | When a key stakeholder expresses distrust in the project status report, the project manager should schedule a meeting with that stakeholder to address the issue and obtain direct feedback. Understanding the specific concerns—whether about data accuracy, reporting format, metrics clarity, or perceived bias—enables the PM to make targeted improvements and restore credibility. Requesting the sponsor to intervene (A) escalates unnecessarily. Emailing the report for broad feedback (C) dilutes the issue without addressing the root concern. Presenting a chart and assuming understanding (B) ignores the trust gap entirely. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 검토 회의 후, 주요 이해관계자가 다른 이해관계자에게 프로젝트 상태 보고서를 신뢰하지 않는다고 말했다. 두 번째 이해관계자가 프로젝트 관리자에게 접근하여 대화를 언급했다. 프로젝트 관리자는 무엇을 해야 하는가? | 모든 이해관계자에게 상태 보고서를 이메일로 보내고 검토 및 피드백을 요청한다. | 스폰서에게 주요 이해관계자가 프로젝트 검토 회의에서 주의를 기울이도록 요청한다. | 상태 보고서를 차트로 제시하고 모든 사람이 보고서를 이해한다고 가정한다. | 주요 이해관계자와 회의를 예약하여 이슈를 다루고 직접적인 피드백을 얻는다. |  | D | 주요 이해관계자가 프로젝트 상태 보고서에 불신을 표현할 때, 프로젝트 관리자는 해당 이해관계자와 회의를 예약하여 이슈를 다루고 직접적인 피드백을 얻어야 한다. 데이터 정확성, 보고 형식, 지표 명확성, 인식된 편향 등 구체적 우려를 이해하면 PM이 목표 지향적 개선을 하고 신뢰를 회복할 수 있다. 스폰서에게 개입 요청(A)은 불필요하게 에스컬레이션한다. 광범위한 피드백을 위해 보고서 이메일 발송(C)은 근본 우려를 다루지 않고 이슈를 희석시킨다. 차트로 제시하고 이해를 가정(B)은 신뢰 격차를 완전히 무시한다.
635 | A project sponsor is concerned that the scope is not being met correctly and has questioned several team members about this individually. When the project sponsor approached the project manager, the project manager realized that the issue was that the project sponsor understood the scope in a different manner than the project team. What should the project manager do to address this issue? | Ask the project team to compile a project scope document and obtain approval from the project sponsor. | Set up a daily standup and request that the project sponsor attend to understand the project ' s tasks and deliverables. | Facilitate a stakeholder alignment session so that the team and project sponsor are in agreement with the deliverables. | Request that the project team change their task deliverables to reflect the project sponsor ' s requirements. |  | C | When the project sponsor understands scope differently than the project team, the project manager should facilitate a stakeholder alignment session so team and sponsor agree on deliverables. Joint alignment resolves misunderstandings collaboratively. Asking the team to compile a new scope document (A) may not resolve the different understanding. Setting up daily standups for the sponsor (B) is excessive. Changing deliverables to match the sponsor's view (D) may misalign with actual requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 스폰서가 범위가 올바르게 충족되지 않고 있다고 우려하며 여러 팀원에게 개별적으로 질문했다. 프로젝트 스폰서가 프로젝트 관리자에게 접근했을 때, 프로젝트 관리자는 프로젝트 스폰서가 프로젝트 팀과 다른 방식으로 범위를 이해하고 있다는 것을 깨달았다. 프로젝트 관리자는 이 이슈를 해결하기 위해 무엇을 해야 하는가? | 프로젝트 팀에게 프로젝트 범위 문서를 작성하고 프로젝트 스폰서의 승인을 받도록 요청한다. | 일일 스탠드업을 설정하고 프로젝트 스폰서에게 참석하여 프로젝트의 작업과 산출물을 이해하도록 요청한다. | 팀과 프로젝트 스폰서가 산출물에 대해 합의할 수 있도록 이해관계자 정렬 세션을 촉진한다. | 프로젝트 팀에게 프로젝트 스폰서의 요구사항을 반영하도록 작업 산출물을 변경하도록 요청한다. |  | C | 프로젝트 스폰서가 프로젝트 팀과 다르게 범위를 이해할 때, 프로젝트 관리자는 팀과 스폰서가 산출물에 합의할 수 있도록 이해관계자 정렬 세션을 촉진해야 한다. 공동 정렬은 오해를 협력적으로 해결한다. 새 범위 문서 작성 요청(A)은 다른 이해를 해결하지 못할 수 있다. 스폰서를 위한 일일 스탠드업 설정(B)은 과도하다. 스폰서 견해에 맞게 산출물 변경(D)은 실제 요구사항과 불일치할 수 있다.
636 | During the project quality control process, the project manager realizes that the quality management plan does not include how the final user will perceive the benefits of the new product compared with the actual product. What should the project manager do first? | Submit a change request to analyze a new set of quality tests | Let the product go to market and wait for customer feedback regarding quality | Ask the quality manager to include the final user tests in the quality management plan. | Ask the product manager to include the final user tests in the quality management plan |  | A | When the quality management plan does not address how the final user will perceive product benefits compared to the existing product, the project manager should first submit a change request to analyze a new set of quality tests. Formal change control is needed to update the quality plan. Letting the product go to market and waiting for feedback (B) is too risky. Asking the quality manager (C) or product manager (D) to include tests bypasses change control. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 품질 관리 프로세스 중, 프로젝트 관리자는 품질 관리 계획에 최종 사용자가 기존 제품과 비교하여 새 제품의 혜택을 어떻게 인식할지가 포함되어 있지 않음을 깨달았다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 새로운 품질 테스트 세트를 분석하기 위한 변경 요청을 제출한다. | 제품을 시장에 출시하고 품질에 대한 고객 피드백을 기다린다. | 품질 관리자에게 품질 관리 계획에 최종 사용자 테스트를 포함하도록 요청한다. | 제품 관리자에게 품질 관리 계획에 최종 사용자 테스트를 포함하도록 요청한다. |  | A | 품질 관리 계획에 최종 사용자가 제품 혜택을 어떻게 인식할지가 다뤄지지 않을 때, 프로젝트 관리자는 먼저 새로운 품질 테스트 세트를 분석하기 위한 변경 요청을 제출해야 한다. 품질 계획을 업데이트하려면 공식적인 변경 통제가 필요하다. 시장에 출시하고 피드백 대기(B)는 너무 위험하다. 품질 관리자(C) 또는 제품 관리자(D)에게 테스트 포함 요청은 변경 통제를 우회한다.
637 | An agile team is funded for a fixed 6-month period. The sponsor's request will take at least 12 months to complete. What should the project manager do? | Have the team work on the list of requests from the sponsor without modification until the 6-month period ends. | Inform the sponsor that the team is unable to complete the requests due to a lack of funding, and defer the project. | Request the team complete all scope items, with the assumption of securing additional funding within 6 months. | Prioritize the scope items to determine the duration needed for a minimal viable product (MVP) and adjust the funding request. |  | D | The correct answer is D. Prioritize the scope items to determine the duration needed for a minimal viable product (MVP) and adjust the funding request. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Agile General Practices | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 애자일 팀이 고정 6개월 기간으로 자금을 받았다. 스폰서의 요청은 완료하는 데 최소 12개월이 필요하다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀이 6개월 기간이 끝날 때까지 수정 없이 스폰서의 요청 목록에 대해 작업하도록 한다. | 자금 부족으로 팀이 요청을 완료할 수 없다고 스폰서에게 알리고 프로젝트를 연기한다. | 6개월 이내에 추가 자금 확보를 가정하고 팀에게 모든 범위 항목을 완료하도록 요청한다. | 최소 기능 제품(MVP)에 필요한 기간을 결정하기 위해 범위 항목의 우선순위를 정하고 자금 요청을 조정한다. |  | D | 정답은 D이다. 최소 기능 제품(MVP)에 필요한 기간을 결정하기 위해 범위 항목의 우선순위를 정하고 자금 요청을 조정한다. 애자일 환경에서 PM은 팀 협업을 촉진하고, 장애물을 제거하며, 애자일 원칙을 준수하면서 지속적인 가치 전달을 보장해야 한다.
638 | A project manager submits several requests to purchase required hardware and knows from previous experience that this kind of procurement usually results in disputes between the company and its suppliers. How can the project manager mitigate this risk in the request for proposal (RFP) with suppliers? | Request approval of the RFP from the project sponsor. | Ask the legal team to review the RFP. | Request approval of the RFP from management. | Ask the project team to submit the RFP. |  | B | When past procurement experience indicates likely disputes with suppliers, the project manager should ask the legal team to review the RFP. Legal review ensures contractual clarity and reduces dispute risk. Requesting sponsor approval (A) does not mitigate legal risks. Requesting management approval (C) adds bureaucracy without legal expertise. Asking the project team to submit (D) lacks legal or procurement expertise. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 프로젝트 관리자가 필수 하드웨어를 구매하기 위한 여러 요청을 제출했으며, 이전 경험상 이런 종류의 조달은 보통 회사와 공급업체 간 분쟁을 초래한다는 것을 알고 있다. 프로젝트 관리자는 공급업체와의 제안요청서(RFP)에서 이 리스크를 어떻게 완화할 수 있는가? | 프로젝트 스폰서에게 RFP 승인을 요청한다. | 법무팀에 RFP 검토를 요청한다. | 경영진에게 RFP 승인을 요청한다. | 프로젝트 팀에게 RFP를 제출하도록 요청한다. |  | B | 과거 조달 경험상 공급업체와의 분쟁이 발생할 가능성이 있을 때, 프로젝트 관리자는 법무팀에 RFP 검토를 요청해야 한다. 법률 검토는 계약의 명확성을 보장하고 분쟁 리스크를 줄인다. 스폰서 승인 요청(A)은 법적 리스크를 완화하지 않는다. 경영진 승인 요청(C)은 법률 전문성 없이 관료주의를 추가한다. 프로젝트 팀에게 제출 요청(D)은 법률 또는 조달 전문성이 부족하다.
639 | A new project manager is assigned to lead an agile project. The project manager wants to use motivation to encourage the team to perform well throughout the project. What should the project manager do? | Find another method to increase the team ' s performance | Use the management reserves to fund some team-building activities | Inflate project estimates to provide a financial buffer for team activities. | Implement a reward system aimed to keep the team engaged and motivated |  | D | When an agile project manager wants to motivate the team, they should implement a reward system aimed at keeping the team engaged and motivated. Recognition and rewards aligned with agile values reinforce desired behaviors and achievements. Finding another method (A) is vague. Using management reserves for team-building (B) misuses project funds. Inflating estimates for a financial buffer (C) is dishonest and unethical. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새로운 프로젝트 관리자가 애자일 프로젝트를 이끌도록 배정되었다. 프로젝트 관리자는 프로젝트 전반에 걸쳐 팀이 좋은 성과를 내도록 동기 부여를 활용하고 싶다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀의 성과를 높이기 위한 다른 방법을 찾는다. | 팀 빌딩 활동에 자금을 지원하기 위해 관리 예비비를 사용한다. | 팀 활동을 위한 재정적 여유를 제공하기 위해 프로젝트 추정치를 부풀린다. | 팀의 참여와 동기를 유지하기 위한 보상 시스템을 구현한다. |  | D | 애자일 프로젝트 관리자가 팀에 동기를 부여하고 싶을 때, 팀의 참여와 동기를 유지하기 위한 보상 시스템을 구현해야 한다. 애자일 가치에 맞춘 인정과 보상은 바람직한 행동과 성취를 강화한다. 다른 방법 찾기(A)는 모호하다. 팀 빌딩에 관리 예비비 사용(B)은 프로젝트 자금을 오용한다. 재정적 여유를 위해 추정치 부풀리기(C)는 부정직하고 비윤리적이다.
640 | A team is ready to start working on a project with a customer who was very difficult to work with in the past because the customer was unable to describe exactly what they wanted. What approach should the project manager take to remove this impediment? | Work with the product owner to define the minimum viable product(s) | Develop and monitor a plan with due dates to reduce the time of completing the product | Reinforce the negotiation and soft skills of the team through training | Follow a predictive approach in order to obtain formal acceptance of each deliverable |  | A | When working with a customer who cannot describe exactly what they want, the project manager should work with the product owner to define the minimum viable product(s). MVPs enable early and frequent feedback, validating requirements iteratively—removing the impediment of unclear requirements through collaboration. Developing a plan with due dates (B) manages schedule but does not address unclear requirements. Reinforcing negotiation skills (C) improves communication but does not validate product requirements. Following a predictive approach (D) may deliver a product that does not meet evolving customer needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 팀이 과거에 원하는 것을 정확히 설명할 수 없었던 매우 까다로운 고객과 함께 프로젝트 작업을 시작할 준비가 되었다. 프로젝트 관리자는 이 장애물을 제거하기 위해 어떤 접근 방식을 취해야 하는가? | 제품 책임자와 함께 최소 기능 제품(MVP)을 정의한다. | 제품 완료 시간을 줄이기 위해 마감일이 포함된 계획을 개발하고 모니터링한다. | 교육을 통해 팀의 협상 및 소프트 스킬을 강화한다. | 각 산출물의 공식 수락을 얻기 위해 예측형 접근 방식을 따른다. |  | A | 원하는 것을 정확히 설명할 수 없는 고객과 작업할 때, 프로젝트 관리자는 제품 책임자와 함께 최소 기능 제품(MVP)을 정의해야 한다. MVP는 조기에 빈번한 피드백을 가능하게 하여 협력을 통해 불명확한 요구사항이라는 장애물을 반복적으로 검증하며 제거한다. 마감일 포함 계획 개발(B)은 일정을 관리하지만 불명확한 요구사항을 해결하지 않는다. 협상 스킬 강화(C)는 의사소통을 개선하지만 제품 요구사항을 검증하지 않는다. 예측형 접근 방식(D)은 변화하는 고객 요구를 충족하지 못하는 제품을 전달할 수 있다.
641 | A project manager is working on a project with multiple workstreams. One of the workstreams missed its deadline multiple times. Who should the project manager speak to about this situation to ensure it does not happen again? | Workstream leader alone | Workstream leader and functional manager | Workstream leader and project sponsor | Workstream leader and project management office (PMO) |  | B | When a workstream repeatedly misses deadlines, the project manager should speak to the workstream leader and functional manager. Both have responsibility for resource allocation and execution. Speaking to the workstream leader alone (A) may not address resource constraints. Involving the project sponsor (C) escalates before involving the direct manager. Involving the PMO (D) adds governance but not direct operational authority. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 여러 작업 흐름이 있는 프로젝트를 진행 중이다. 작업 흐름 중 하나가 여러 번 마감일을 놓쳤다. 프로젝트 관리자는 이것이 다시 발생하지 않도록 누구와 이야기해야 하는가? | 작업 흐름 리더 단독 | 작업 흐름 리더 및 기능 관리자 | 작업 흐름 리더 및 프로젝트 스폰서 | 작업 흐름 리더 및 프로젝트 관리 오피스(PMO) |  | B | 작업 흐름이 반복적으로 마감일을 놓칠 때, 프로젝트 관리자는 작업 흐름 리더와 기능 관리자에게 이야기해야 한다. 둘 다 자원 배정과 실행에 대한 책임이 있다. 작업 흐름 리더 단독(A)은 자원 제약을 해결하지 못할 수 있다. 프로젝트 스폰서 참여(C)는 직접 관리자를 참여시키기 전에 에스컬레이션한다. PMO 참여(D)는 거버넌스를 추가하지만 직접적인 운영 권한은 없다.
642 | After a couple of iterations, the project manager decides to present the product to a key stakeholder. The stakeholder's feedback is that the team missed the mark on many features. What should the project manager do to avoid this in the future? | Schedule adequate sprint demos to gather early feedback from the stakeholders and adapt the plan accordingly | Set up requirements-gathering sessions with all key stakeholders to evaluate the scope once again and reprioritize the backlog based on the sessions. | Incorporate design thinking practices into the project life cycle to better understand the product ' s personas and be more effective to match their needs. | Evaluate the team ' s skills to look for someone with experience in product design and assign that person the task of rebuilding the product interface |  | C | When stakeholder feedback reveals the team missed the mark on many features, the project manager should incorporate design thinking practices into the project lifecycle. Design thinking—including empathy mapping, persona creation, user journey mapping, and prototyping—helps teams deeply understand user needs and create solutions that match their expectations. Scheduling sprint demos (A) gathers feedback but does not improve the design approach. Setting up requirements-gathering sessions (B) revisits scope but may not improve user understanding. Evaluating team skills for product design (D) addresses capability but not methodology. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 몇 번의 이터레이션 후, 프로젝트 관리자가 주요 이해관계자에게 제품을 발표하기로 결정했다. 이해관계자의 피드백은 팀이 많은 기능에서 목표를 놓쳤다는 것이다. 프로젝트 관리자는 향후 이를 방지하기 위해 무엇을 해야 하는가? | 이해관계자로부터 조기 피드백을 수집하고 그에 따라 계획을 조정하기 위해 적절한 스프린트 데모를 예약한다. | 범위를 다시 평가하기 위해 모든 주요 이해관계자와 요구사항 수집 세션을 설정하고 세션에 기반하여 백로그를 재우선순위화한다. | 제품의 페르소나를 더 잘 이해하고 그들의 요구를 더 효과적으로 충족시키기 위해 프로젝트 생애주기에 디자인 씽킹 실천을 통합한다. | 제품 디자인 경험이 있는 팀원을 찾기 위해 팀의 역량을 평가하고 해당 인원에게 제품 인터페이스 재구축 작업을 배정한다. |  | C | 이해관계자 피드백에서 팀이 많은 기능에서 목표를 놓쳤다는 것이 드러날 때, 프로젝트 관리자는 프로젝트 생애주기에 디자인 씽킹 실천을 통합해야 한다. 공감 매핑, 페르소나 생성, 사용자 여정 매핑, 프로토타이핑을 포함한 디자인 씽킹은 팀이 사용자 요구를 깊이 이해하고 기대에 부합하는 솔루션을 만들도록 돕는다. 스프린트 데모 예약(A)은 피드백을 수집하지만 디자인 접근 방식을 개선하지 않는다. 요구사항 수집 세션 설정(B)은 범위를 재검토하지만 사용자 이해를 개선하지 못할 수 있다. 제품 디자인 역량 평가(D)는 역량을 다루지만 방법론을 다루지 않는다.
643 | A project manager has been assigned a project to build a new solar farm that will provide clean energy to a new housing complex. The government has decided to reduce the tax on renewable energy products starting 1 January. The supplier has reached out and stated that the order placed for solar panels to be delivered on 20 December might be delayed until early January. On the other hand, the project will face similar constraints due to the December holidays. What should the project manager do about this risk? | Accept the risk and update the risk register. | Review the supplier ' s contract to understand the terms of sale. | Insist that the supplier deliver the goods on the agreed date. | Update the risk register and take advantage of the opportunity. |  | D | When a supplier may delay delivery past a date after which tax reductions take effect, the project manager should update the risk register and take advantage of the opportunity. The delay creates a cost-saving opportunity through the tax reduction. Accepting the risk passively (A) does not capture the benefit. Reviewing contract terms (B) is secondary to recognizing the opportunity. Insisting on the original delivery date (C) forgoes potential savings. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Focus on Value | Plan Risk Management | Traditional PM | 프로젝트 관리자가 새로운 주택 단지에 청정 에너지를 공급할 새로운 태양광 발전소를 건설하는 프로젝트에 배정되었다. 정부가 1월 1일부터 재생 에너지 제품에 대한 세금을 인하하기로 결정했다. 공급업체가 12월 20일에 납품 예정인 태양광 패널 주문이 1월 초까지 지연될 수 있다고 연락해왔다. 한편, 프로젝트도 12월 휴가로 인해 유사한 제약에 직면할 것이다. 프로젝트 관리자는 이 리스크에 대해 무엇을 해야 하는가? | 리스크를 수용하고 리스크 레지스터를 업데이트한다. | 판매 조건을 이해하기 위해 공급업체의 계약을 검토한다. | 공급업체에게 합의된 날짜에 물품을 납품하도록 요구한다. | 리스크 레지스터를 업데이트하고 기회를 활용한다. |  | D | 공급업체가 세금 인하가 발효되는 날짜 이후로 납품을 지연할 수 있을 때, 프로젝트 관리자는 리스크 레지스터를 업데이트하고 기회를 활용해야 한다. 지연은 세금 인하를 통한 비용 절감 기회를 만든다. 리스크를 수동적으로 수용(A)하면 혜택을 포착하지 못한다. 계약 조건 검토(B)는 기회 인식에 비해 부차적이다. 원래 납품일 고수(C)는 잠재적 절감을 포기한다.
644 | A company plans to initiate a project involving a new technology. Approval for the project is required. What should the project manager do? | Analyze the cost and identify the project benefits. | Define change management for the new technology. | Review the cost and schedule baselines for execution. | Identify the risks in implementing the new technology. |  | D | Before initiating a project involving new technology that requires approval, the project manager should identify the risks in implementing the new technology. Risk identification is critical for new technology projects because unknown technical challenges, integration issues, and cost uncertainties must be assessed before the project can be properly evaluated for approval. Analyzing cost and identifying benefits (A) is important but secondary to understanding the risks that could invalidate those projections. Defining change management (B) is a later planning activity. Reviewing cost and schedule baselines (C) assumes baselines already exist, which is premature at the initiation stage. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 회사가 새로운 기술을 포함하는 프로젝트를 시작할 계획이다. 프로젝트 승인이 필요하다. 프로젝트 관리자는 무엇을 해야 하는가? | 비용을 분석하고 프로젝트 혜택을 식별한다. | 새로운 기술에 대한 변경 관리를 정의한다. | 실행을 위한 비용 및 일정 기준선을 검토한다. | 새로운 기술 구현의 리스크를 식별한다. |  | D | 승인이 필요한 새 기술 프로젝트를 시작하기 전에, 프로젝트 관리자는 새로운 기술 구현의 리스크를 식별해야 한다. 리스크 식별은 새 기술 프로젝트에서 중요한데, 알려지지 않은 기술적 과제, 통합 이슈, 비용 불확실성을 승인 전에 평가해야 하기 때문이다. 비용 분석 및 혜택 식별(A)은 중요하지만 예측을 무효화할 수 있는 리스크 이해에 비해 부차적이다. 변경 관리 정의(B)는 이후 계획 활동이다. 비용 및 일정 기준선 검토(C)는 기준선이 이미 존재한다고 가정하며 착수 단계에서는 시기상조이다.
645 | A project with multiple teams recently transitioned from a predictive approach to agile as requested by the product owner. Midway through implementation, a team member noticed there was no technical capability to support the current business requirement; therefore, the project will need to be reworked and the issue needs to be communicated to all stakeholders. What should the agile project lead have done to avoid this situation? | Assessed the technical and organizational readiness for the project and identified risksat the beginning of the first iteration | Requested the product owner ' s approval to add an external expert to define theacceptance criteria | Defined a clear acceptance criteria at the initiation phase and continued with theproject | Increased the communications between the team member and the product owner |  | A | When a team member discovers midway through implementation that no technical capability exists to support the current business requirement, the agile project lead should have assessed technical and organizational readiness and identified risks at the beginning of the first iteration. Early readiness assessment prevents mid-project surprises. Requesting product owner approval for an external expert (B) acts after the gap is discovered. Defining acceptance criteria at initiation (C) addresses what, not technical feasibility. Increasing communications (D) does not address technical assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Traditional PM | 여러 팀이 있는 프로젝트가 최근 제품 책임자의 요청에 따라 예측형 접근 방식에서 애자일로 전환했다. 구현 중반에 팀원이 현재 비즈니스 요구사항을 지원할 기술적 역량이 없음을 발견하여 프로젝트를 재작업해야 하며 모든 이해관계자에게 이슈를 전달해야 한다. 애자일 프로젝트 리더는 이 상황을 피하기 위해 무엇을 했어야 하는가? | 첫 번째 반복의 시작에서 프로젝트의 기술적 및 조직적 준비 상태를 평가하고 리스크를 식별했어야 한다. | 수락 기준을 정의하기 위해 외부 전문가를 추가하도록 제품 책임자의 승인을 요청했어야 한다. | 착수 단계에서 명확한 수락 기준을 정의하고 프로젝트를 계속 진행했어야 한다. | 팀원과 제품 책임자 간의 커뮤니케이션을 증가시켰어야 한다. |  | A | 팀원이 구현 중반에 현재 비즈니스 요구사항을 지원할 기술적 역량이 없음을 발견할 때, 애자일 프로젝트 리더는 첫 번째 반복의 시작에서 기술적 및 조직적 준비 상태를 평가하고 리스크를 식별했어야 한다. 조기 준비 상태 평가는 프로젝트 중간의 놀라움을 방지한다. 외부 전문가에 대한 제품 책임자 승인 요청(B)은 격차가 발견된 후의 조치이다. 착수 시 수락 기준 정의(C)는 '무엇'을 다루지 기술적 실현 가능성은 다루지 않는다. 커뮤니케이션 증가(D)는 기술적 평가를 다루지 않는다.
646 | A project lead is working on an agile project to build the team's vision, including the decision-making process. It was decided that the team will vote on items, and if 90% of the team agrees on a decision, then it will be carried forward. At the very first technical design meeting, the team makes a decision that the project lead strongly disagrees with. How should the project lead proceed? | Refuse to let the team proceed with the work based on their decision. | Take the technical team lead aside and try to persuade them to change their vote. | Note the reasons for the disagreement and let the team proceed. | Set up a meeting with the project champion and ask them to intervene. |  | C | In agile teams, when a decision is reached through the agreed-upon voting process, the project lead should respect that outcome even if they personally disagree. The lead should document their disagreement and rationale but allow the team to proceed. This respects team autonomy, collaboration, and empowerment—core agile principles. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 리더가 의사결정 프로세스를 포함한 팀의 비전을 구축하기 위해 애자일 프로젝트에서 작업 중이다. 팀이 항목에 대해 투표하기로 결정했으며, 팀의 90%가 결정에 동의하면 추진하기로 했다. 첫 번째 기술 설계 회의에서 팀이 프로젝트 리더가 강하게 반대하는 결정을 내렸다. 프로젝트 리더는 어떻게 진행해야 하는가? | 그들의 결정에 기반한 작업 진행을 팀에게 거부한다. | 기술 팀 리더를 따로 불러 투표를 변경하도록 설득한다. | 불일치 이유를 기록하고 팀이 진행하도록 한다. | 프로젝트 챔피언과 회의를 설정하고 개입을 요청한다. |  | C | 애자일 팀에서 합의된 투표 프로세스를 통해 결정이 이루어지면, 프로젝트 리더는 개인적으로 동의하지 않더라도 그 결과를 존중해야 한다. 리더는 불일치와 근거를 문서화하되 팀이 진행하도록 해야 한다. 이는 팀 자율성, 협업, 권한 부여라는 핵심 애자일 원칙을 존중한다.
647 | A project manager is assigned to a time-bound internal project on quality improvement. During project execution, the project manager observes that a specific team member is being isolated by other team members. Which three actions should the project manager take? (Choose three) | Obtain feedback from the isolated team member to understand the situation | Arrange and conduct team-building sessions to improve team effectiveness | Allow team members to resolve personal issues without involving the project manager | Get feedback from other team members to understand what led to this situation | Identify the isolated team member as a risk and document the situation in the risk register. | A, B, D | When a team member is being isolated, the PM must take proactive steps to address the situation. Arranging team-building exercises improves dynamics and integration(B). Obtaining feedback from both the isolated member and other team members provides insights into root causes(A,D). These combined actions help the PM understand the situation comprehensively and implement effective solutions to restore a positive, productive team environment. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Engage Stakeholders | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 품질 개선에 관한 시한이 정해진 내부 프로젝트에 배정되었다. 프로젝트 실행 중 프로젝트 관리자는 특정 팀원이 다른 팀원들로부터 고립되고 있음을 관찰한다. 프로젝트 관리자는 어떤 세 가지 조치를 취해야 하는가? (3개 선택) | 고립된 팀원으로부터 상황을 이해하기 위한 피드백을 얻는다. | 팀 효과성을 개선하기 위한 팀 빌딩 세션을 준비하고 진행한다. | 프로젝트 관리자가 관여하지 않고 팀원들이 개인적 문제를 스스로 해결하도록 한다. | 이 상황을 초래한 원인을 이해하기 위해 다른 팀원들로부터 피드백을 얻는다. | 고립된 팀원을 리스크로 식별하고 리스크 레지스터에 상황을 문서화한다. | A, B, D | 팀원이 고립당할 때, PM은 상황을 해결하기 위해 사전 예방적 조치를 취해야 한다. 팀 빌딩 활동을 준비하면 역학과 통합을 개선한다(B). 고립된 팀원과 다른 팀원 모두로부터 피드백을 얻으면 근본 원인에 대한 통찰을 제공한다(A, D). 이러한 결합된 조치는 PM이 상황을 포괄적으로 이해하고 긍정적이고 생산적인 팀 환경을 회복하기 위한 효과적인 솔루션을 구현하는 데 도움이 된다.
648 | A project manager notices a product owner has been unresponsive over the last few weeks. During one-on-one sessions, the product owner is unable to provide complete information, leading to rework of the project stories. What should the project manager do first? | Conduct a root cause analysis before addressing the issue | Increase the sprint duration to accommodate the additional work | Escalate the issue to the stakeholder ' s functional manager | Cancel the one-on-one sessions and obtain the information via email |  | A | When a product owner is unresponsive and causing story rework, the project manager should first conduct a root cause analysis to understand why the issue is occurring. The cause could be capacity constraints, competing priorities, lack of decision authority, unclear expectations, or organizational impediments. Without diagnosis, other actions may worsen the situation. Increasing sprint duration (B) masks dysfunction rather than addressing it and delays value delivery. Escalating to a functional manager (C) may become necessary but is more effective after the PM has evidence and a clear articulation of the problem. Cancelling one-on-ones and switching to email (D) reduces collaboration and increases misinterpretation, fueling more rework. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트 관리자가 제품 책임자가 지난 몇 주 동안 응답이 없었음을 알아챘다. 1:1 세션에서 제품 책임자가 완전한 정보를 제공하지 못해 프로젝트 스토리의 재작업이 발생하고 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 이슈를 해결하기 전에 근본 원인 분석을 수행한다. | 추가 작업을 수용하기 위해 스프린트 기간을 연장한다. | 이슈를 이해관계자의 기능 관리자에게 에스컬레이션한다. | 1:1 세션을 취소하고 이메일로 정보를 얻는다. |  | A | 제품 책임자가 응답이 없고 스토리 재작업이 발생할 때, 프로젝트 관리자는 먼저 근본 원인 분석을 수행하여 문제가 발생하는 이유를 이해해야 한다. 원인은 업무 과다, 경쟁하는 우선순위, 의사결정 권한 부족, 불명확한 기대, 또는 조직적 장애물일 수 있다. 진단 없이 다른 조치는 상황을 악화시킬 수 있다. 스프린트 기간 연장(B)은 기능 장애를 은폐하고 가치 전달을 지연시킨다. 기능 관리자에게 에스컬레이션(C)은 필요할 수 있지만 PM이 증거와 문제의 명확한 설명을 가진 후에 더 효과적이다. 1:1 취소 및 이메일 전환(D)은 협업을 줄이고 오해를 증가시켜 더 많은 재작업을 초래한다.
649 | A project manager is leading an innovation project that is facing a lot of risks due to a high level of uncertainty. What strategy should the project manager use to manage these risks using an agile approach? | Evaluate the risks constantly and reprioritize work as the project progresses. | Implement a scrum risk retrospective to analyze the risks at the end of the project. | Assign an agile risk manager to better understand and track the project risks. | Develop an agile risk matrix to track, assess, and evaluate the uncertainty of the project. |  | A | In an agile project facing high uncertainty and numerous risks, the project manager should evaluate risks constantly and reprioritize work as the project progresses. This continuous, iterative risk management approach aligns with agile principles of responding to change and adapting priorities based on evolving project conditions. Implementing a risk retrospective only at the end (B) is too late for an ongoing project with active risks. Assigning a dedicated risk manager (C) adds overhead without leveraging the team's collective awareness. Developing a risk matrix (D) is a one-time assessment tool that does not support the continuous evaluation agile requires. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 프로젝트 관리자가 높은 불확실성으로 인해 많은 리스크에 직면한 혁신 프로젝트를 이끌고 있다. 프로젝트 관리자는 애자일 접근 방식으로 이러한 리스크를 관리하기 위해 어떤 전략을 사용해야 하는가? | 프로젝트가 진행됨에 따라 리스크를 지속적으로 평가하고 작업의 우선순위를 재조정한다. | 프로젝트 종료 시 리스크를 분석하기 위한 스크럼 리스크 회고를 구현한다. | 프로젝트 리스크를 더 잘 이해하고 추적하기 위해 애자일 리스크 관리자를 배정한다. | 프로젝트의 불확실성을 추적, 평가, 검토하기 위한 애자일 리스크 매트릭스를 개발한다. |  | A | 높은 불확실성과 많은 리스크에 직면한 애자일 프로젝트에서, 프로젝트 관리자는 리스크를 지속적으로 평가하고 프로젝트가 진행됨에 따라 작업의 우선순위를 재조정해야 한다. 이 지속적이고 반복적인 리스크 관리 접근 방식은 변화에 대응하고 진화하는 프로젝트 조건에 기반하여 우선순위를 조정하는 애자일 원칙과 일치한다. 프로젝트 종료 시에만 리스크 회고 구현(B)은 활성 리스크가 있는 진행 중인 프로젝트에는 너무 늦다. 전담 리스크 관리자 배정(C)은 팀의 집단적 인식을 활용하지 않으면서 오버헤드를 추가한다. 리스크 매트릭스 개발(D)은 일회성 평가 도구로 애자일이 요구하는 지속적 평가를 지원하지 않는다.
650 | A project manager has heard about the large volume of emails the team receives each day which prevents them from doing project work. One team member has stated that they would like to be able to access project-related information when needed. To what type of communication is the team member referring? | Mass communication | Interactive communication | Pull communication | Push communication |  | C | When a team member overwhelmed by daily email volume wants to access project information on their own schedule, they are referring to pull communication. Pull communication allows recipients to access information at their discretion from repositories, intranets, or databases. Mass communication (A) broadcasts to large audiences. Interactive communication (B) involves real-time exchange. Push communication (D) sends information directly to recipients. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 팀이 매일 받는 대량의 이메일로 인해 프로젝트 작업을 수행하지 못한다는 것을 들었다. 한 팀원이 필요할 때 프로젝트 관련 정보에 접근할 수 있기를 원한다고 말했다. 이 팀원이 언급하는 커뮤니케이션 유형은 무엇인가? | 대중 커뮤니케이션 | 상호작용 커뮤니케이션 | 풀(Pull) 커뮤니케이션 | 푸시(Push) 커뮤니케이션 |  | C | 매일 이메일 과부하에 시달리는 팀원이 자신의 일정에 맞춰 프로젝트 정보에 접근하고 싶어할 때, 풀(Pull) 커뮤니케이션을 언급하는 것이다. 풀 커뮤니케이션은 수신자가 저장소, 인트라넷 또는 데이터베이스에서 자신의 재량에 따라 정보에 접근할 수 있게 한다. 대중 커뮤니케이션(A)은 대규모 청중에게 전달한다. 상호작용 커뮤니케이션(B)은 실시간 교환을 포함한다. 푸시 커뮤니케이션(D)은 정보를 수신자에게 직접 전송한다.
651 | A project manager leads a software development project in a hybrid environment. During project planning, the project manager identified a risk where a technical resource for a critical path item may not be available when needed. One week before the resource is needed, the technical engineer had a personal emergency and had to take a leave. What should the project manager do next? | Consult the risk register for an appropriate planned risk response and implement. | Update the lessons learned report and the risk log to reflect that this risk has materialized. | Revise the project management plan and move the task to a time when the technical resource will be available. | Review the business requirement with stakeholders and exclude the task assigned to the technical resource. |  | A | When a previously identified risk materializes — a critical technical resource becomes unavailable one week before needed — the project manager should consult the risk register for the planned risk response and implement it. Pre-planned responses enable rapid action. Updating lessons learned (B) documents after the fact. Revising the plan to reschedule the task (C) delays delivery. Reviewing requirements to exclude the task (D) removes functionality. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 환경에서 소프트웨어 개발 프로젝트를 이끌고 있다. 프로젝트 계획 중 프로젝트 관리자는 크리티컬 패스 항목의 기술 자원이 필요할 때 사용 가능하지 않을 수 있는 리스크를 식별했다. 자원이 필요한 1주일 전에 기술 엔지니어가 개인적 긴급 상황으로 휴가를 떠나야 했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 적절한 계획된 리스크 대응을 위해 리스크 레지스터를 참조하고 구현한다. | 이 리스크가 실현되었음을 반영하기 위해 교훈 보고서와 리스크 로그를 업데이트한다. | 프로젝트 관리 계획을 수정하고 기술 자원이 사용 가능할 때로 작업을 이동한다. | 이해관계자와 비즈니스 요구사항을 검토하고 기술 자원에 배정된 작업을 제외한다. |  | A | 이전에 식별된 리스크가 실현될 때 — 중요한 기술 자원이 필요 1주일 전에 사용 불가능해질 때 — 프로젝트 관리자는 계획된 리스크 대응을 위해 리스크 레지스터를 참조하고 구현해야 한다. 사전 계획된 대응은 신속한 조치를 가능하게 한다. 교훈 업데이트(B)는 사후 문서화이다. 작업 재일정(C)은 전달을 지연시킨다. 작업 제외를 위한 요구사항 검토(D)는 기능을 제거한다.
652 | A project is behind schedule and over budget, resulting in a problem for the next deliverable. The project manager informs the stakeholders, who are very concerned about the project. What should the project manager do to alleviate the stakeholders' concerns? | Speak with the sponsor and explain the situation so that the sponsor can explain it to the stakeholders | Demonstrate the performance indexes and recommend corrective actions to the stakeholders | Schedule a kick-off session to explain the problems of the project and gain approval and support | Send communications for clarification so there is a full understanding about the situation. |  | C | The PM should schedule a kick-off session to explain project challenges, gain stakeholder approval and support, and align expectations. This helps clarify objectives and address concerns proactively. Follow-up communications, performance metric presentations, and sponsor conversations are all important but should come after the kick-off session establishes a shared understanding among stakeholders. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트가 일정에 뒤처지고 예산을 초과하여 다음 산출물에 문제가 발생했다. 프로젝트 관리자가 이해관계자들에게 알리자 프로젝트에 대해 매우 우려하고 있다. 프로젝트 관리자는 이해관계자들의 우려를 완화하기 위해 무엇을 해야 하는가? | 스폰서에게 상황을 설명하고 스폰서가 이해관계자들에게 설명하도록 한다. | 성과 지표를 보여주고 이해관계자들에게 시정 조치를 권고한다. | 프로젝트 문제를 설명하고 승인과 지원을 얻기 위한 킥오프 세션을 예약한다. | 상황에 대한 완전한 이해를 위해 명확화를 위한 커뮤니케이션을 발송한다. |  | C | PM은 프로젝트 과제를 설명하고, 이해관계자의 승인과 지원을 얻으며, 기대치를 정렬하기 위한 킥오프 세션을 예약해야 한다. 이는 목표를 명확히 하고 우려를 사전 예방적으로 해결하는 데 도움이 된다. 후속 커뮤니케이션, 성과 지표 프레젠테이션, 스폰서 대화는 모두 중요하지만 킥오프 세션이 이해관계자 간 공유된 이해를 확립한 후에 이루어져야 한다.
653 | During the development of a product, multiple identified risks have now become issues, which is hindering the team's velocity. What should the project manager do in this situation? | Convene the steering committee and inform them of the impact to the project. | Prioritize the user stories with issues and have the team resolve them | Update the project management plan and risk management plan. | Document the issues and extend the project delivery timeline. |  | B | When multiple identified risks have become issues hindering team velocity, the project manager should prioritize the user stories with issues and have the team resolve them. Addressing the most critical issues first minimizes impact on delivery and restores velocity. Convening the steering committee (A) escalates before attempting team-level resolution. Updating plans (C) documents the situation but does not resolve it. Documenting and extending the timeline (D) accepts delay without addressing root causes. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 제품 개발 중 여러 식별된 리스크가 이슈로 전환되어 팀의 속도를 저해하고 있다. 이 상황에서 프로젝트 관리자는 무엇을 해야 하는가? | 운영위원회를 소집하여 프로젝트에 대한 영향을 알린다. | 이슈가 있는 사용자 스토리의 우선순위를 정하고 팀이 해결하도록 한다. | 프로젝트 관리 계획과 리스크 관리 계획을 업데이트한다. | 이슈를 문서화하고 프로젝트 전달 일정을 연장한다. |  | B | 여러 식별된 리스크가 이슈로 전환되어 팀 속도를 저해할 때, 프로젝트 관리자는 이슈가 있는 사용자 스토리의 우선순위를 정하고 팀이 해결하도록 해야 한다. 가장 중요한 이슈를 먼저 해결하면 전달 영향을 최소화하고 속도를 회복한다. 운영위원회 소집(A)은 팀 수준의 해결을 시도하기 전에 에스컬레이션한다. 계획 업데이트(C)는 상황을 문서화하지만 해결하지 않는다. 문서화 및 일정 연장(D)은 근본 원인을 해결하지 않고 지연을 수용한다.
654 | During the execution of a project, a company decides that everybody will need to take vacation time before the end of the year. This may cause a change in the project timeline. How should the project manager address the situation? | Discuss the vacation plan and include scheduling changes in the change log database. | Push out the project timeline according to the vacation plan in place based on the recent company policy. | Submit a formal request to senior management asking them not to proceed with this decision based on the impact it will have on the project. | Agree with functional management and team members on a vacation schedule that would minimally impact the project schedule. |  | D | When a company-wide mandatory vacation may impact the project timeline, the project manager should agree with functional management and team members on a vacation schedule that would minimally impact the project schedule. Collaborative scheduling balances organizational policy with project needs. Discussing and logging changes (A) does not optimize the schedule. Pushing out the timeline (B) accepts maximum impact. Requesting management to reverse the decision (C) challenges corporate authority. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Schedule Management | Process | Plan and Manage Schedule | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 프로젝트 실행 중 회사가 연말 전에 모든 직원이 휴가를 사용해야 한다고 결정했다. 이는 프로젝트 일정에 변경을 초래할 수 있다. 프로젝트 관리자는 이 상황을 어떻게 해결해야 하는가? | 휴가 계획을 논의하고 변경 로그 데이터베이스에 일정 변경을 포함한다. | 최근 회사 정책에 기반한 휴가 계획에 따라 프로젝트 일정을 연장한다. | 프로젝트에 미칠 영향을 근거로 이 결정을 진행하지 말 것을 요청하는 공식 요청서를 상급 경영진에 제출한다. | 기능 관리자 및 팀원들과 프로젝트 일정에 최소한의 영향을 미치는 휴가 일정에 합의한다. |  | D | 회사 전체 의무 휴가가 프로젝트 일정에 영향을 미칠 수 있을 때, 프로젝트 관리자는 기능 관리자 및 팀원들과 프로젝트 일정에 최소한의 영향을 미치는 휴가 일정에 합의해야 한다. 협력적 일정 수립은 조직 정책과 프로젝트 요구를 균형 있게 조정한다. 변경 논의 및 로깅(A)은 일정을 최적화하지 않는다. 일정 연장(B)은 최대 영향을 수용한다. 경영진에 결정 취소 요청(C)은 기업 권위에 도전한다.
655 | Shipping problems are impacting the supply chain worldwide, and the project's primary vendor has indicated potential delays in supplying certain equipment that will be ordered later in the project. What should the project manager do with this information? | Update the risk and continue to monitor developments by keeping in touch with the vendor. | Request the procurement team to find another vendor that has available stock of this equipment. | Note the information but refrain from recording it as an issue because the project has not yet placed the order. | Request the vendor to provide specific information about the delivery delays before taking any action. |  | A | When the primary vendor indicates potential delays for equipment not yet ordered, the project manager should update the risk register and continue monitoring developments with the vendor. Proactive risk management preserves options. Switching vendors immediately (B) is premature. Noting but not recording (C) loses visibility. Requesting details before any action (D) delays risk documentation. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 배송 문제가 전 세계 공급망에 영향을 미치고 있으며, 프로젝트의 주요 공급업체가 프로젝트 후반에 주문할 특정 장비의 공급 지연 가능성을 알려왔다. 프로젝트 관리자는 이 정보를 어떻게 처리해야 하는가? | 리스크를 업데이트하고 공급업체와 연락을 유지하며 상황을 계속 모니터링한다. | 조달 팀에 이 장비의 재고가 있는 다른 공급업체를 찾도록 요청한다. | 프로젝트가 아직 주문을 하지 않았으므로 정보를 기록하되 이슈로 기록하지 않는다. | 공급업체에 조치를 취하기 전에 배송 지연에 대한 구체적인 정보를 제공하도록 요청한다. |  | A | 주요 공급업체가 아직 주문하지 않은 장비에 대한 잠재적 지연을 알릴 때, 프로젝트 관리자는 리스크 레지스터를 업데이트하고 공급업체와 함께 상황을 계속 모니터링해야 한다. 사전 예방적 리스크 관리는 옵션을 보존한다. 즉시 공급업체 변경(B)은 시기상조이다. 기록하되 등록하지 않는 것(C)은 가시성을 잃는다. 조치 전 세부사항 요청(D)은 리스크 문서화를 지연시킨다.
656 | A project manager receives information in preparation for reporting the project's monthly performance to the project steering committee: Actual progress = 2 units, Planned progress = 3 units, Actual cost (AC) = 2 units, Budgeted cost = 3 units. What statement should the project manager make to the project steering committee? | The project is currently behind schedule but is under the planned expenditure, and the project manager is pleased to declare a project cost savings, | The project is currently behind schedule with a corresponding cost savings, and no further actions should be taken. | The project is currently behind schedule with a corresponding lower cost, and every effort is being made to expedite the delayed activities. | The project is currently behind schedule but at a lower cost, and an application for a time and budget extension will be submitted. |  | C | With actual progress of 2 units versus planned progress of 3 units, the project is behind schedule. With actual cost of 2 units versus budgeted cost of 3 units, the project is under budget. The project manager should inform the steering committee that the project is behind schedule with a corresponding lower cost, and that every effort is being made to expedite delayed activities. Declaring cost savings (A) mischaracterizes the underspend, which results from incomplete work. Stating no further action is needed (B) ignores the schedule issue. Requesting a time and budget extension (D) is premature before expediting efforts. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 프로젝트 관리자가 프로젝트 운영위원회에 월간 성과를 보고하기 위한 정보를 받았다: 실제 진행 = 2 단위, 계획 진행 = 3 단위, 실제 비용(AC) = 2 단위, 예산 비용 = 3 단위. 프로젝트 관리자는 프로젝트 운영위원회에 어떤 진술을 해야 하는가? | 프로젝트는 현재 일정보다 지연되었지만 계획된 지출 이하이며, 프로젝트 관리자는 프로젝트 비용 절감을 선언하게 되어 기쁘다. | 프로젝트는 현재 일정보다 지연되었으며 이에 상응하는 비용 절감이 있고, 추가 조치가 필요하지 않다. | 프로젝트는 현재 일정보다 지연되었으며 이에 상응하는 낮은 비용이 발생하고 있고, 지연된 활동을 빨리 진행하기 위해 모든 노력을 기울이고 있다. | 프로젝트는 현재 일정보다 지연되었지만 낮은 비용이며, 시간 및 예산 연장 신청서를 제출할 것이다. |  | C | 실제 진행 2단위 대 계획 진행 3단위로 프로젝트는 일정보다 지연되었다. 실제 비용 2단위 대 예산 비용 3단위로 프로젝트는 예산 이하이다. 프로젝트 관리자는 운영위원회에 프로젝트가 일정보다 지연되었으며 이에 상응하는 낮은 비용이 발생하고 있고, 지연된 활동을 빨리 진행하기 위해 모든 노력을 기울이고 있다고 알려야 한다. 비용 절감 선언(A)은 미완성 작업으로 인한 미지출을 잘못 표현한다. 추가 조치 불필요 진술(B)은 일정 문제를 무시한다. 시간 및 예산 연장 요청(D)은 빨리 진행 노력 전에 시기상조이다.
657 | During the execution phase of a project, a project manager notices that the project team is not motivated and performance is decreasing. The decision is made to invest in financial rewards for all of the key team members. After the rewards are distributed, the team is still underperforming. What should the project manager have done to avoid this situation? | Conducted frequent monitoring on key team members' performance during project execution | Determined the appropriate type of incentive for key team members | Distributed the monetary incentive according to the team members' individual performance | identified the underperforming team members and asked the human resources (HR) department to replace them |  | B | When financial rewards fail to motivate an underperforming team, the project manager should have first determined the appropriate type of incentive for each key team member. Not all team members are motivated by monetary rewards—some value recognition, growth opportunities, or other non-monetary incentives. Understanding individual motivations enables targeted, effective incentive strategies. Conducting frequent performance monitoring (A) is surveillance, not motivation. Distributing incentives based on individual performance (C) still assumes monetary rewards work for everyone. Identifying underperformers and requesting replacements (D) is punitive and does not address motivation. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Help Ensure Knowledge Transfer | Resources | Executing | Focus on Value | Acquire Resources | Hybrid/Tailoring | 프로젝트 실행 단계에서 프로젝트 관리자가 프로젝트 팀의 동기가 부족하고 성과가 하락하고 있음을 인지했다. 모든 핵심 팀원에게 재정적 보상에 투자하기로 결정했다. 보상이 지급된 후에도 팀은 여전히 저성과이다. 이 상황을 피하기 위해 프로젝트 관리자는 무엇을 했어야 하는가? | 프로젝트 실행 중 핵심 팀원의 성과를 자주 모니터링한다. | 핵심 팀원에게 적절한 인센티브 유형을 결정한다. | 팀원의 개별 성과에 따라 금전적 인센티브를 배분한다. | 저성과 팀원을 식별하고 인사부(HR)에 교체를 요청한다. |  | B | 재정적 보상이 저성과 팀에 동기를 부여하지 못할 때, 프로젝트 관리자는 먼저 각 핵심 팀원에게 적절한 인센티브 유형을 결정했어야 한다. 모든 팀원이 금전적 보상에 동기 부여되는 것은 아니며, 일부는 인정, 성장 기회 또는 기타 비금전적 인센티브를 중시한다. 개인의 동기를 이해하면 표적화되고 효과적인 인센티브 전략이 가능해진다. 빈번한 성과 모니터링(A)은 감시이지 동기 부여가 아니다. 개별 성과에 따른 인센티브 배분(C)은 여전히 금전적 보상이 모두에게 효과적이라고 가정한다. 저성과자 식별 및 교체 요청(D)은 징벌적이며 동기 부여를 해결하지 않는다.
658 | A project manager is managing the opening of a new office overseas. At the beginning of the project, possible delays due to legal permits are raised by one stakeholder. Subject matter experts (SMEs) reassessed the concern and suggested assigning more time for this permit, and the change control board (CCB) agrees. Which document should the project manager update first to document this change? | Schedule baseline | Scope baseline | Risk register | Cost baseline |  | C | When a stakeholder raises concerns about delays due to legal permits and SMEs recommend assigning more time—approved by the CCB—the project manager should first update the risk register. The risk register documents identified risks, their assessments, and response plans. Since the concern about permit delays is a project risk that has been reassessed with a new mitigation strategy (allocating more time), this change should be formally captured in the risk register. Updating the schedule baseline (A) or cost baseline (D) may follow, but the risk documentation comes first. Updating the scope baseline (B) is unnecessary since the project scope has not changed. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 해외 신규 사무실 개설을 관리하고 있다. 프로젝트 초기에 한 이해관계자가 법적 허가로 인한 지연 가능성을 제기했다. 주제 전문가(SME)들이 우려를 재평가하고 이 허가에 더 많은 시간을 배정할 것을 제안했으며, 변경 통제 위원회(CCB)가 동의했다. 이 변경을 문서화하기 위해 프로젝트 관리자가 먼저 업데이트해야 할 문서는? | 일정 기준선 | 범위 기준선 | 리스크 레지스터 | 비용 기준선 |  | C | 이해관계자가 법적 허가 지연 우려를 제기하고 SME가 더 많은 시간 배정을 권장하며 CCB가 승인할 때, 프로젝트 관리자는 먼저 리스크 레지스터를 업데이트해야 한다. 리스크 레지스터는 식별된 리스크, 평가, 대응 계획을 문서화한다. 허가 지연에 대한 우려는 새로운 완화 전략(더 많은 시간 배정)으로 재평가된 프로젝트 리스크이므로 리스크 레지스터에 공식적으로 기록되어야 한다. 일정 기준선(A) 또는 비용 기준선(D) 업데이트는 뒤따를 수 있지만 리스크 문서화가 먼저이다. 범위 기준선(B) 업데이트는 프로젝트 범위가 변경되지 않았으므로 불필요하다.
659 | A servant leader is about to start a confidential agile research project. A high risk has been identified related to a team member disclosing details of the project with external people. What should the servant leader do to address this risk? | Forecast the cost of the risk to calculate the required contingency reserve that needs to be allocated if the risk materializes. | Ask the functional manager to educate the team about this risk and ensure that disciplinary actions will be taken. | Include this restriction as a ground rule and ensure all team members are familiar with it by reviewing the ground rules at the end of everyiteration. | Contact the human resources (HR) department to ensure that disciplinary actions will be taken if the employees disclose any confidentialinformation. |  | C | To address the risk of confidential information disclosure in an agile research project, the servant leader should include this restriction as a ground rule and ensure all team members are familiar with it by reviewing the ground rules at the end of every iteration. This proactive approach integrates confidentiality into the team's working norms and reinforces awareness regularly. Forecasting the risk cost for contingency reserves (A) addresses financial impact but not prevention. Asking the functional manager to enforce disciplinary actions (B) is reactive and fear-based rather than proactive. Contacting HR for disciplinary consequences (D) focuses on punishment rather than prevention and culture-building. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 서번트 리더가 기밀 애자일 연구 프로젝트를 시작하려 한다. 팀원이 외부인에게 프로젝트 세부 사항을 공개할 관련 높은 리스크가 식별되었다. 서번트 리더는 이 리스크를 해결하기 위해 무엇을 해야 하는가? | 리스크가 실현될 경우 배정해야 할 비상 예비비를 계산하기 위해 리스크 비용을 예측한다. | 기능 관리자에게 이 리스크에 대해 팀을 교육하고 징계 조치가 취해질 것을 보장하도록 요청한다. | 이 제한을 기본 규칙에 포함시키고 매 이터레이션 종료 시 기본 규칙을 검토하여 모든 팀원이 숙지하도록 보장한다. | 직원이 기밀 정보를 공개할 경우 징계 조치가 취해지도록 인사부(HR)에 연락한다. |  | C | 애자일 연구 프로젝트에서 기밀 정보 공개 리스크를 해결하기 위해, 서번트 리더는 이 제한을 기본 규칙에 포함시키고 매 이터레이션 종료 시 기본 규칙을 검토하여 모든 팀원이 숙지하도록 해야 한다. 이 사전 예방적 접근은 기밀 유지를 팀의 작업 규범에 통합하고 인식을 정기적으로 강화한다. 비상 예비비를 위한 리스크 비용 예측(A)은 재정적 영향을 다루지만 예방은 아니다. 기능 관리자에게 징계 조치 시행 요청(B)은 사전 예방적이기보다 반응적이고 두려움 기반이다. HR에 징계 결과 연락(D)은 예방과 문화 구축보다 처벌에 초점을 맞춘다.
660 | A project manager is assigned to a new project. Many of the project deliverables need to be outsourced. What should the project manager use to document the project deliverables? | Statement of work (SOW) | Memorandum of understanding (MOU) | Scope management plan | Service level agreement (SLA) |  | A | When project deliverables need to be outsourced, the project manager should use a statement of work (SOW) to document them. A SOW is a formal document that outlines specific tasks, deliverables, requirements, schedule, quality standards, and payment terms—serving as a contractual agreement between vendor and client. A memorandum of understanding (B) is less formal and typically non-binding. The scope management plan (C) describes how scope will be managed, not specific deliverables for outsourcing. A service level agreement (D) defines service performance standards, not project deliverables. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | WBS/Decomposition | Process | Plan and Manage Procurement | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 관리자가 새 프로젝트에 배정되었다. 프로젝트 산출물의 많은 부분을 외주해야 한다. 프로젝트 관리자는 프로젝트 산출물을 문서화하기 위해 무엇을 사용해야 하는가? | 작업 기술서(SOW) | 양해각서(MOU) | 범위 관리 계획 | 서비스 수준 협약(SLA) |  | A | 프로젝트 산출물을 외주해야 할 때, 프로젝트 관리자는 작업 기술서(SOW)를 사용하여 문서화해야 한다. SOW는 특정 작업, 산출물, 요구사항, 일정, 품질 기준, 지불 조건을 개요하는 공식 문서로, 공급업체와 고객 간의 계약적 합의 역할을 한다. 양해각서(B)는 덜 공식적이며 일반적으로 구속력이 없다. 범위 관리 계획(C)은 범위 관리 방법을 설명하지 외주를 위한 특정 산출물을 기술하지 않는다. 서비스 수준 협약(D)은 서비스 성능 기준을 정의하지 프로젝트 산출물을 정의하지 않는다.
661 | An ongoing project is facing a challenging situation where the customer is not satisfied. The team is new to agile development and frequently communicates with the customer and gives regular status reports. What should the project lead do to satisfy the customer? | Reduce frequent communication and improve the status report format to include team 1142 progress | Review the situation with the customer and make the required adjustments with the team | Review project progress with the customer and modify the frequency of sprint review | Schedule a meeting with the customer and explain the team is new to agile and the situation will improve |  | B | When the customer is dissatisfied despite frequent communication and status reports from a team new to agile, the project lead should review the situation with the customer and make required adjustments with the team. Collaborative review identifies real gaps. Reducing communication (A) worsens alignment. Explaining the team is new to agile (D) is not a solution. Modifying sprint review frequency (C) treats a symptom. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 진행 중인 프로젝트에서 고객이 만족하지 않는 어려운 상황에 직면하고 있다. 팀은 애자일 개발에 처음이며 고객과 자주 소통하고 정기적인 상태 보고를 한다. 고객을 만족시키기 위해 프로젝트 리더는 무엇을 해야 하는가? | 빈번한 소통을 줄이고 팀 진행 상황을 포함하도록 상태 보고서 형식을 개선한다. | 고객과 상황을 검토하고 팀과 필요한 조정을 한다. | 고객과 프로젝트 진행 상황을 검토하고 스프린트 리뷰 빈도를 수정한다. | 고객과 미팅을 예약하고 팀이 애자일에 처음이며 상황이 개선될 것이라고 설명한다. |  | B | 애자일에 처음인 팀이 빈번한 소통과 상태 보고에도 불구하고 고객이 불만족할 때, 프로젝트 리더는 고객과 상황을 검토하고 팀과 필요한 조정을 해야 한다. 협력적 검토가 실질적인 격차를 식별한다. 소통 줄이기(A)는 정렬을 악화시킨다. 팀이 애자일에 처음이라고 설명(D)은 해결책이 아니다. 스프린트 리뷰 빈도 수정(C)은 증상을 치료한다.
662 | During a network upgrade for a company, the client informs the project manager that a government representative notified the client about a separate project that will affect the network upgrade. Any change in the upgrade will impact the project's cost and schedule. What should the project manager do first? | Perform an impact analysis with subject matter experts (SMEs). | Implement a change request to increase the budget and schedule. | Inform the government representative about the impact of the separate project. | Consult and update the risk register with the project stakeholders. |  | A | When the project manager learns of a separate government project that may affect the network upgrade, the first step should be to perform an impact analysis with subject matter experts (SMEs). This assessment determines the magnitude and probability of the risks, as well as possible responses and contingency plans. Implementing a change request (B) is premature without understanding the impact. Informing the government representative (C) may be appropriate later but is not the first action. Consulting and updating the risk register (D) is a useful follow-up after the impact analysis provides the necessary data. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 회사의 네트워크 업그레이드 중 고객이 프로젝트 관리자에게 정부 대표가 네트워크 업그레이드에 영향을 미칠 별도 프로젝트에 대해 고객에게 통보했다고 알렸다. 업그레이드의 어떤 변경도 프로젝트의 비용과 일정에 영향을 미칠 것이다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 주제 전문가(SME)와 영향 분석을 수행한다. | 예산과 일정을 증가시키는 변경 요청을 실행한다. | 정부 대표에게 별도 프로젝트의 영향을 알린다. | 프로젝트 이해관계자와 리스크 레지스터를 협의하고 업데이트한다. |  | A | 프로젝트 관리자가 네트워크 업그레이드에 영향을 미칠 수 있는 별도의 정부 프로젝트를 알게 되었을 때, 첫 번째 단계는 주제 전문가(SME)와 영향 분석을 수행하는 것이다. 이 평가는 리스크의 크기와 확률, 그리고 가능한 대응과 비상 계획을 결정한다. 변경 요청 실행(B)은 영향을 이해하지 못한 채 시기상조이다. 정부 대표에게 알리기(C)는 나중에 적절할 수 있지만 첫 번째 조치는 아니다. 리스크 레지스터 협의 및 업데이트(D)는 영향 분석이 필요한 데이터를 제공한 후의 유용한 후속 조치이다.
663 | A facility extension project is in the execution stage. There is a project activity to connect the power of all new equipment to an existing facility, Point A, which requires a significant cable length. The construction team found that the power could be connected to Point B and save money. What should the project manager do next? | Seek a decision from the construction team after explaining the project budget and schedule constraint. | Use the Point B option because it will save the project cost and time. | Add the issue to the change log and request additional budget through the change control board (CCB). | Perform a cost-benefit analysis to evaluate using the Point B option. |  | D | When the construction team finds a cheaper power connection option (Point B) versus the specified Point A, the project manager should perform a cost-benefit analysis to evaluate the Point B option. Systematic evaluation ensures informed decision-making. Seeking the construction team's decision (A) delegates PM authority. Using Point B without analysis (B) bypasses evaluation. Adding to the change log and requesting budget through the CCB (C) acts before analyzing the merit. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Finance | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 시설 확장 프로젝트가 실행 단계에 있다. 모든 새 장비의 전력을 기존 시설의 A 지점에 연결하는 프로젝트 활동이 있으며, 이는 상당한 케이블 길이가 필요하다. 건설 팀이 B 지점에 전력을 연결하면 비용을 절감할 수 있다는 것을 발견했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 예산 및 일정 제약을 설명한 후 건설 팀에 결정을 구한다. | 프로젝트 비용과 시간을 절감할 수 있으므로 B 지점 옵션을 사용한다. | 변경 로그에 이슈를 추가하고 변경 통제 위원회(CCB)를 통해 추가 예산을 요청한다. | B 지점 옵션 사용을 평가하기 위해 비용-편익 분석을 수행한다. |  | D | 건설 팀이 지정된 A 지점 대비 더 저렴한 전력 연결 옵션(B 지점)을 발견할 때, 프로젝트 관리자는 B 지점 옵션을 평가하기 위해 비용-편익 분석을 수행해야 한다. 체계적인 평가가 정보에 기반한 의사결정을 보장한다. 건설 팀에 결정을 구하는 것(A)은 PM 권한을 위임한다. 분석 없이 B 지점을 사용하는 것(B)은 평가를 우회한다. 변경 로그에 추가하고 CCB를 통해 예산을 요청하는 것(C)은 장점을 분석하기 전에 행동한다.
664 | A project manager is assigned to an organizational transformation project. The company typically defines individual performance plans at the beginning of the year, and functional managers conduct feedback reviews at the end of the year. The transformation project team members are concerned that the work they are doing for this project is not aligned with the work included in their individual performance plan for the year. What should the project manager do? | Request to be made responsible for the performance plans of those on this project team | Provide performance feedback to the learn members ' functional managers at the end of the year. | Meet with the functional managers to align the expected frequency and results reporting for the team members. | Assure team members that this project is a high priority for the company and they will be evaluated accordingly. |  | C | When team members are concerned that project work does not align with their individual performance plans, the project manager should meet with functional managers to align expected frequency and results reporting. Collaboration between PM and functional managers ensures project contributions are recognized. Requesting control of performance plans (A) oversteps the PM's authority. Providing year-end feedback (B) delays resolution. Assuring team members of the project's priority (D) does not address the performance plan misalignment. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Develop a Common Vision | Finance | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 관리자가 조직 변환 프로젝트에 배정되었다. 회사는 일반적으로 연초에 개인 성과 계획을 정의하고, 기능 관리자가 연말에 피드백 리뷰를 수행한다. 변환 프로젝트 팀원들은 이 프로젝트를 위해 수행하는 작업이 연간 개인 성과 계획에 포함된 작업과 일치하지 않는다고 우려하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 이 프로젝트 팀의 성과 계획에 대한 책임을 맡겠다고 요청한다. | 연말에 팀원들의 기능 관리자에게 성과 피드백을 제공한다. | 기능 관리자와 만나 팀원들의 예상 빈도와 결과 보고를 정렬한다. | 팀원들에게 이 프로젝트가 회사의 높은 우선순위이며 그에 따라 평가받을 것이라고 안심시킨다. |  | C | 팀원들이 프로젝트 작업이 개인 성과 계획과 일치하지 않는다고 우려할 때, 프로젝트 관리자는 기능 관리자와 만나 예상 빈도와 결과 보고를 정렬해야 한다. PM과 기능 관리자 간의 협력은 프로젝트 기여가 인정되도록 보장한다. 성과 계획 통제를 요청하는 것(A)은 PM의 권한을 초과한다. 연말 피드백 제공(B)은 해결을 지연시킨다. 프로젝트의 우선순위를 안심시키는 것(D)은 성과 계획 불일치를 해결하지 않는다.
665 | A project manager accepts a delivery at the project site but the items are of a poor quality. The project manager gets the local vendor to fix the items but more deliveries from this vendor are expected. What should the project manager do going forward? | Review the contract requirements and ask for the applicable evidence for quality assurance | Have the vendor issue the quality documentation prior to the next delivery. | Call the vendor and have them verbally guarantee the quality of the next site delivery | Allocate extra time to inspect deliveries for quality assurance upon arrival at the site |  | B | When a vendor delivered poor-quality items and more deliveries are expected, the project manager should have the vendor issue quality documentation prior to the next delivery. Upfront quality evidence prevents recurrence. Reviewing contract requirements (A) is important but does not change the vendor's process. Calling for a verbal guarantee (C) is unenforceable. Allocating extra inspection time (D) adds cost without preventing the root cause. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 프로젝트 관리자가 프로젝트 현장에서 납품을 수령했지만 품목의 품질이 좋지 않다. 프로젝트 관리자는 현지 공급업체에 품목을 수리하도록 했지만, 이 공급업체로부터 더 많은 납품이 예상된다. 프로젝트 관리자는 앞으로 무엇을 해야 하는가? | 계약 요구사항을 검토하고 품질 보증에 대한 해당 증거를 요청한다. | 공급업체가 다음 납품 전에 품질 문서를 발행하도록 한다. | 공급업체에 전화하여 다음 현장 납품의 품질을 구두로 보증하도록 한다. | 현장 도착 시 품질 보증을 위해 납품물을 검사할 추가 시간을 배정한다. |  | B | 공급업체가 품질이 좋지 않은 품목을 납품하고 더 많은 납품이 예상될 때, 프로젝트 관리자는 공급업체가 다음 납품 전에 품질 문서를 발행하도록 해야 한다. 사전 품질 증거가 재발을 방지한다. 계약 요구사항 검토(A)는 중요하지만 공급업체의 프로세스를 변경하지 않는다. 구두 보증 요청(C)은 강제할 수 없다. 추가 검사 시간 배정(D)은 근본 원인을 방지하지 않고 비용을 추가한다.
666 | It is taking several additional iterations for a project team to complete planned backlog items. The project manager notices that some features are not meeting the iteration-level definition and must be placed back into the backlog. What should the project manager do? | Address the required changes in the next release | Extend the iterations to complete the items | Review and update the acceptance criteria | Put more emphasis on the definition of done (DoD) |  | D | When features repeatedly fail iteration expectations and return to the backlog, the root cause is typically weak adherence to the Definition of Done. Reinforcing the DoD establishes clear, shared quality and completeness standards, reducing rework and ensuring increments are potentially shippable. Updating acceptance criteria alone (B) doesn't ensure internal quality activities are completed. Deferring fixes (A) normalizes technical debt. Extending iterations (D) masks the problem without improving quality discipline. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 팀이 계획된 백로그 항목을 완료하는 데 여러 추가 이터레이션이 소요되고 있다. 프로젝트 관리자는 일부 기능이 이터레이션 수준의 정의를 충족하지 못하고 백로그에 다시 배치되어야 함을 인지했다. 프로젝트 관리자는 무엇을 해야 하는가? | 다음 릴리스에서 필요한 변경 사항을 해결한다. | 항목을 완료하기 위해 이터레이션을 연장한다. | 수락 기준을 검토하고 업데이트한다. | 완료의 정의(DoD)에 더 많은 강조를 둔다. |  | D | 기능이 반복적으로 이터레이션 기대를 충족하지 못하고 백로그로 돌아갈 때, 근본 원인은 일반적으로 완료의 정의에 대한 약한 준수이다. DoD를 강화하면 명확하고 공유된 품질 및 완전성 기준이 확립되어 재작업이 줄고 증분이 잠재적으로 출시 가능해진다. 수락 기준만 업데이트(B)하는 것은 내부 품질 활동 완료를 보장하지 않는다. 수정을 연기(A)하면 기술 부채가 정상화된다. 이터레이션 연장(D)은 품질 규율을 개선하지 않고 문제를 가린다.
667 | A project manager for a defense software application has a culturally and gender-diverse team with a short project timeline. Considering the project will be stressful, what skill should the project manager use to monitor the team's performance? | Conflict resolution | Emotional intelligence | Coercion | Negotiating |  | B | For monitoring a culturally and gender-diverse team's performance under stressful conditions in a defense project, the project manager should use emotional intelligence. EQ enables understanding of individual and team emotions, building trust and managing stress. Conflict resolution (A) addresses disputes but not ongoing performance monitoring. Coercion (C) is authoritarian and counterproductive. Negotiating (D) addresses agreements, not team emotional dynamics. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 국방 소프트웨어 애플리케이션의 프로젝트 관리자가 짧은 프로젝트 일정으로 문화적, 성별 다양성이 있는 팀을 이끌고 있다. 프로젝트가 스트레스가 될 것을 고려하여, 프로젝트 관리자는 팀의 성과를 모니터링하기 위해 어떤 기술을 사용해야 하는가? | 갈등 해결 | 감성 지능 | 강압 | 협상 |  | B | 국방 프로젝트에서 스트레스 상황 하에 문화적, 성별 다양성이 있는 팀의 성과를 모니터링하기 위해 프로젝트 관리자는 감성 지능을 사용해야 한다. EQ는 개인 및 팀의 감정을 이해하고 신뢰를 구축하며 스트레스를 관리할 수 있게 한다. 갈등 해결(A)은 분쟁을 다루지만 지속적인 성과 모니터링은 아니다. 강압(C)은 권위적이고 비생산적이다. 협상(D)은 합의를 다루지 팀의 감정 역학은 다루지 않는다.
668 | A project manager works in a hierarchical organization. The project team members are used to being told what to do, and the performance reviews include the percentage of completion of the allocated tasks. After a conversation with the sponsor, the project manager realizes that they need to reassign a couple of tasks to meet the next milestone. This change can be perceived as poor performance by the current assignees. What should the project manager do? | Organize a team meeting and inform the team members that, as the person accountable for delivery, they decided to change the task allocation. | Organize a team meeting to inform team members about a change in direction and work with them to change the task allocation. | Ask the less experienced team member privately to stop working on the task and inform another team member that the work has been reassigned. | Ask the more experienced team member privately to take the task and inform the other team members that work has been reassigned. |  | B | When task reassignment may be perceived as poor performance in a hierarchical organization, the project manager should organize a team meeting to inform about the change in direction and work with the team to adjust task allocation. Transparent, collaborative communication prevents misunderstandings. Unilaterally announcing the decision (A) ignores team input. Privately reassigning one team member (C) lacks transparency. Privately asking experienced members to take over (D) creates confusion. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 위계적 조직에서 근무한다. 프로젝트 팀원들은 지시받는 것에 익숙하며, 성과 리뷰에는 배정된 작업의 완료 비율이 포함된다. 스폰서와의 대화 후, 프로젝트 관리자는 다음 마일스톤을 충족시키기 위해 몇 가지 작업을 재배정해야 한다는 것을 인식했다. 이 변경은 현재 담당자들에게 저조한 성과로 인식될 수 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀 회의를 조직하여 팀원들에게 전달 책임자로서 작업 배정을 변경하기로 결정했다고 알린다. | 팀 회의를 조직하여 팀원들에게 방향 변경을 알리고 함께 작업 배정을 변경한다. | 경험이 적은 팀원에게 개인적으로 작업을 중단하라고 요청하고 다른 팀원에게 작업이 재배정되었다고 알린다. | 경험이 많은 팀원에게 개인적으로 작업을 맡으라고 요청하고 다른 팀원들에게 작업이 재배정되었다고 알린다. |  | B | 위계적 조직에서 작업 재배정이 저조한 성과로 인식될 수 있을 때, 프로젝트 관리자는 팀 회의를 조직하여 방향 변경을 알리고 팀과 함께 작업 배정을 조정해야 한다. 투명하고 협력적인 의사소통이 오해를 방지한다. 일방적으로 결정을 발표하는 것(A)은 팀의 의견을 무시한다. 한 팀원에게 개인적으로 재배정(C)은 투명성이 부족하다. 경험 많은 팀원에게 개인적으로 인수를 요청(D)은 혼란을 야기한다.
669 | An organization is producing a product using a hybrid approach with several phases. Some of the phases are planned to be executed in predictive and some in agile. During the agile phase, the project manager notices that the team members sometimes unknowingly work on the same task. What should the project manager do? | Verify that the product owner has made the task assignments clear. | Communicate the task assignments to the team members in a clear manner. | Verify that the team members have made the task assignments clear. | Confirm that the agile coach has made the task assignments clear. |  | B | In agile environments, the PM facilitates collaboration and ensures the team has the resources needed to deliver value. A fundamental agile practice is decomposing large efforts into smaller, manageable tasks tracked through tools like task boards or backlogs. This reduces duplication, minimizes dependencies, and increases transparency and accountability. When team members unknowingly work on identical tasks, it signals a communication or visibility gap. The PM should clarify task assignments using appropriate tools and encourage regular status updates among team members. The product owner (B) defines the backlog but not task assignments. The agile coach (C) supports process improvement but does not assign tasks. Verifying team assignments (D) alone is insufficient—the PM must actively communicate and coordinate to prevent overlap. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 조직이 여러 단계를 가진 하이브리드 접근 방식으로 제품을 생산하고 있다. 일부 단계는 예측형으로, 일부는 애자일로 실행될 예정이다. 애자일 단계 중 프로젝트 관리자는 팀원들이 때때로 모르는 사이에 같은 작업을 하고 있음을 인지했다. 프로젝트 관리자는 무엇을 해야 하는가? | 제품 책임자가 작업 배정을 명확히 했는지 확인한다. | 팀원들에게 작업 배정을 명확하게 전달한다. | 팀원들이 작업 배정을 명확히 했는지 확인한다. | 애자일 코치가 작업 배정을 명확히 했는지 확인한다. |  | B | 애자일 환경에서 PM은 협업을 촉진하고 팀이 가치를 전달하는 데 필요한 자원을 확보하도록 한다. 기본적인 애자일 실천은 큰 작업을 작업 보드나 백로그와 같은 도구로 추적되는 더 작고 관리 가능한 작업으로 분해하는 것이다. 이는 중복을 줄이고 의존성을 최소화하며 투명성과 책임감을 높인다. 팀원들이 모르는 사이에 동일한 작업을 할 때, 이는 의사소통 또는 가시성 격차를 나타낸다. PM은 적절한 도구를 사용하여 작업 배정을 명확히 하고 팀원들 간의 정기적인 상태 업데이트를 권장해야 한다. 제품 책임자(B)는 백로그를 정의하지만 작업 배정은 아니다. 애자일 코치(C)는 프로세스 개선을 지원하지만 작업을 배정하지 않는다. 팀 배정 확인(D)만으로는 불충분하다—PM이 적극적으로 소통하고 조율하여 중복을 방지해야 한다.
670 | A project manager was recently assigned to rescue a high-priority project for an Olympic facility. The project is behind schedule, with a heavy contractual penalty. The former project manager had numerous conflicts with the project team members and a few stakeholders. What should the project manager do first? | Review the project schedule and ask for the contingency reserve to crash the project. | Meet the project team and stakeholders to identify the root cause of the issue and develop a solution. | Meet the project team to assert authority and reassign the project tasks for a timely 512 delivery. | Review the lessons learned register with the former project manager in a private meeting. |  | B | When taking over a troubled, schedule-delayed project with contractual penalties and prior team conflicts, the new project manager should first meet with the project team and stakeholders to identify the root cause of the issue and develop a solution. Understanding the current situation comprehensively before taking corrective action is essential. Reviewing the schedule and requesting reserves to crash (A) acts before understanding root causes. Asserting authority and reassigning tasks (C) is autocratic. Reviewing lessons learned with the former PM (D) may provide context but does not address current stakeholder relationships. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Procurement & Contract Mgmt | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 최근 올림픽 시설의 우선순위 높은 프로젝트를 구출하도록 배정되었다. 프로젝트는 일정이 지연되었으며, 상당한 계약상 위약금이 있다. 이전 프로젝트 관리자는 프로젝트 팀원 및 일부 이해관계자와 수많은 갈등이 있었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트 일정을 검토하고 프로젝트를 크래싱하기 위한 예비비를 요청한다. | 프로젝트 팀 및 이해관계자와 만나 이슈의 근본 원인을 식별하고 해결책을 개발한다. | 프로젝트 팀과 만나 권위를 주장하고 적시 전달을 위해 프로젝트 작업을 재배정한다. | 이전 프로젝트 관리자와 개인 회의에서 교훈 레지스터를 검토한다. |  | B | 일정이 지연되고 계약상 위약금이 있으며 이전 팀 갈등이 있는 문제 프로젝트를 인수할 때, 새 프로젝트 관리자는 먼저 프로젝트 팀 및 이해관계자와 만나 이슈의 근본 원인을 식별하고 해결책을 개발해야 한다. 시정 조치를 취하기 전에 현재 상황을 포괄적으로 이해하는 것이 필수적이다. 일정 검토 및 크래싱을 위한 예비비 요청(A)은 근본 원인을 이해하기 전에 행동한다. 권위를 주장하고 작업을 재배정(C)은 독단적이다. 이전 PM과 교훈 검토(D)는 맥락을 제공할 수 있지만 현재 이해관계자 관계를 다루지 않는다.
671 | A project team member is struggling to deliver an assigned task. In a team meeting, the project manager determines that there are other members on the team who have more experience with similar tasks. What should the project manager do? | Ask one of the more experienced team members to support the team member with the task. | Ask the experienced team members to produce a manual on how to complete the task. | Inform the project management office (PMO) of the issue and request a replacement for the less experienced team member. | Reassign the task to one of the more experienced project team members for a faster completion of the assigned task. |  | A | When a team member struggles with an assigned task and more experienced members are available, the project manager should ask one of the experienced team members to support the struggling member. Peer support enables task completion while developing the less experienced member's skills through knowledge sharing. Producing a manual (B) is indirect and slow. Informing the PMO for a replacement (C) is disproportionate. Reassigning the task entirely (D) does not develop the struggling member. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 팀원이 배정된 작업을 전달하는 데 어려움을 겪고 있다. 팀 회의에서 프로젝트 관리자는 유사한 작업에 더 많은 경험이 있는 다른 팀원이 있음을 확인했다. 프로젝트 관리자는 무엇을 해야 하는가? | 경험이 많은 팀원 중 한 명에게 해당 팀원의 작업을 지원하도록 요청한다. | 경험이 많은 팀원들에게 작업 완료 방법에 대한 매뉴얼을 작성하도록 요청한다. | 프로젝트 관리 오피스(PMO)에 이슈를 알리고 경험이 적은 팀원의 교체를 요청한다. | 배정된 작업의 더 빠른 완료를 위해 경험이 많은 프로젝트 팀원 중 한 명에게 작업을 재배정한다. |  | A | 팀원이 배정된 작업에 어려움을 겪고 경험이 많은 팀원이 있을 때, 프로젝트 관리자는 경험이 많은 팀원 중 한 명에게 어려움을 겪는 팀원을 지원하도록 요청해야 한다. 동료 지원은 지식 공유를 통해 경험이 적은 팀원의 기술을 개발하면서 작업 완료를 가능하게 한다. 매뉴얼 작성(B)은 간접적이고 느리다. PMO에 교체를 요청(C)은 과도한 대응이다. 작업을 완전히 재배정(D)은 어려움을 겪는 팀원을 개발하지 않는다.
672 | A project team has recently finished a sprint for developing two features for a fleet management system. Although the team delivered the required features, they encountered several issues and conflicts during the sprint. Team members were upset about this experience and are now showing a lack of motivation due to what has occurred. What can the project manager do to help increase the team's motivation and engagement with the project? | Review sprint progress with the project team members | Review sprint planning procedures with the project team members | Set up one-on-one meetings with the project team members | Perform a sprint retrospective with the project team members |  | D | Sprint retrospectives provide a structured space for the team to reflect on the past sprint, identify improvement areas, and commit to action items for the next sprint. They support open, honest communication about issues and conflicts while maintaining a constructive, collaborative atmosphere. Retrospectives are not performance evaluations or blame sessions—they are continuous improvement mechanisms that boost team motivation and engagement. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 팀이 최근 차량 관리 시스템의 두 가지 기능 개발을 위한 스프린트를 완료했다. 팀이 필요한 기능을 전달했지만, 스프린트 중 여러 이슈와 갈등을 겪었다. 팀원들은 이 경험에 대해 불만이 있으며 발생한 일로 인해 동기 부족을 보이고 있다. 프로젝트 관리자는 팀의 동기 부여와 프로젝트 참여를 높이기 위해 무엇을 할 수 있는가? | 프로젝트 팀원들과 스프린트 진행 상황을 검토한다. | 프로젝트 팀원들과 스프린트 계획 절차를 검토한다. | 프로젝트 팀원들과 1:1 미팅을 설정한다. | 프로젝트 팀원들과 스프린트 회고를 수행한다. |  | D | 스프린트 회고는 팀이 지난 스프린트를 되돌아보고, 개선 영역을 식별하며, 다음 스프린트를 위한 실행 항목에 합의하는 구조화된 공간을 제공한다. 건설적이고 협력적인 분위기를 유지하면서 이슈와 갈등에 대한 개방적이고 솔직한 의사소통을 지원한다. 회고는 성과 평가나 비난 세션이 아니라 팀의 동기 부여와 참여를 높이는 지속적 개선 메커니즘이다.
673 | A project manager is responsible for building a bridge. The high-level elements of the project are handled using a predictive approach. The software responsible for retracting the bridge has been developed based on agile principles. During software development, the workflow is often interrupted by various delays or impediments due to lack of information. How should the project manager handle this situation? | Incorporate small batches of work into the project | Apply lean manufacturing to limit the team's work | Make work visible using kanban boards. | Increase retrospectives to deliver results fast |  | C | When agile software development within a hybrid bridge construction project is frequently interrupted by delays due to lack of information, the project manager should make work visible using kanban boards. Kanban boards surface bottlenecks and flow issues. Incorporating small batches (A) is good practice but does not address information gaps. Applying lean to limit work (B) constrains without identifying causes. Increasing retrospectives (D) does not directly address workflow interruptions. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Kanban | Process | Plan and Optimize Quality | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 프로젝트 관리자가 교량 건설을 담당하고 있다. 프로젝트의 상위 수준 요소는 예측형 접근 방식으로 관리된다. 교량 개폐를 담당하는 소프트웨어는 애자일 원칙에 기반하여 개발되었다. 소프트웨어 개발 중 정보 부족으로 인해 다양한 지연이나 장애물로 워크플로가 자주 중단된다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 소규모 작업 배치를 프로젝트에 통합한다. | 팀의 작업을 제한하기 위해 린 제조를 적용한다. | 칸반 보드를 사용하여 작업을 가시화한다. | 결과를 빠르게 전달하기 위해 회고를 늘린다. |  | C | 하이브리드 교량 건설 프로젝트 내 애자일 소프트웨어 개발이 정보 부족으로 자주 중단될 때, 프로젝트 관리자는 칸반 보드를 사용하여 작업을 가시화해야 한다. 칸반 보드는 병목 현상과 흐름 문제를 표면화한다. 소규모 배치 통합(A)은 좋은 관행이지만 정보 격차를 해결하지 않는다. 린으로 작업 제한(B)은 원인 파악 없이 제약한다. 회고 증가(D)는 워크플로 중단을 직접 해결하지 않는다.
674 | A project team identified a low-cost software product available for purchase that would drastically reduce the scope of development. The development manager has confirmed that this tool would fulfill the business need. What should the project manager do? | Discuss the Option in the next daily standup meeting to finalize the decision. | Recommend the option to the product owner for consideration. | Remind the team that their primary responsibility is software development. | Add a user story to the product backlog to test the software product. |  | B | When the team identifies a low-cost software product that could reduce development scope and fulfill the business need, the project manager should recommend the option to the product owner for consideration. The product owner decides on backlog priorities and product direction. Discussing in the daily standup (A) is not the forum for this decision. Reminding the team of their development responsibility (C) dismisses a valid option. Adding a user story to test it (D) acts before product owner approval. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 팀이 개발 범위를 크게 줄일 수 있는 저비용 소프트웨어 제품을 발견했다. 개발 관리자가 이 도구가 비즈니스 요구를 충족할 것이라고 확인했다. 프로젝트 관리자는 무엇을 해야 하는가? | 결정을 확정하기 위해 다음 일일 스탠드업 회의에서 옵션을 논의한다. | 제품 책임자에게 검토를 위해 옵션을 추천한다. | 팀에게 주요 책임이 소프트웨어 개발임을 상기시킨다. | 소프트웨어 제품을 테스트하기 위해 제품 백로그에 사용자 스토리를 추가한다. |  | B | 팀이 개발 범위를 줄이고 비즈니스 요구를 충족할 수 있는 저비용 소프트웨어 제품을 발견할 때, 프로젝트 관리자는 제품 책임자에게 검토를 위해 옵션을 추천해야 한다. 제품 책임자가 백로그 우선순위와 제품 방향을 결정한다. 일일 스탠드업에서 논의(A)는 이 결정에 적합한 포럼이 아니다. 개발 책임 상기(C)는 유효한 옵션을 무시한다. 테스트를 위한 사용자 스토리 추가(D)는 제품 책임자 승인 전에 행동한다.
675 | A project manager is working on a project that will transform the organization's operating model. The project manager reviewed the budget allocation for various phases and was informed that upper management will not approve any additional funds. Knowing that there are no additional funds available, how should the project manager proceed? | Decide to work on the small deliveries, leaving the big deliveries until the end of the project, and track critical expenses. 1170 | Allocate the budget to the phases of the project and meet with upper management to consolidate the final funds. | Allocate the budget to the deliveries that have higher business value for the organization than those with lower business value. | Ensure that the budget is enough to cover the internal resources, since external supplies can be covered by procurement. |  | C | When there is a fixed budget with no additional funds, the project manager should allocate the budget to deliveries with higher business value. Value-driven prioritization maximizes benefit within constraints. Working on small deliveries first and deferring big ones (A) does not consider value. Allocating by phase and meeting management (B) adds overhead. Ensuring budget covers internal resources only (D) is incomplete planning. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 관리자가 조직의 운영 모델을 변환할 프로젝트에서 작업하고 있다. 프로젝트 관리자가 다양한 단계의 예산 배정을 검토했으며 상급 경영진이 추가 자금을 승인하지 않을 것이라는 통보를 받았다. 추가 자금이 없다는 것을 알고 프로젝트 관리자는 어떻게 진행해야 하는가? | 소규모 전달물에 먼저 작업하고 대규모 전달물은 프로젝트 말미까지 남겨두며 중요 비용을 추적한다. | 프로젝트 단계에 예산을 배정하고 상급 경영진과 만나 최종 자금을 확정한다. | 비즈니스 가치가 높은 전달물에 낮은 것보다 예산을 우선 배정한다. | 외부 공급은 조달로 충당할 수 있으므로 내부 자원을 충당하기에 충분한 예산인지 확인한다. |  | C | 추가 자금 없이 고정 예산일 때, 프로젝트 관리자는 비즈니스 가치가 높은 전달물에 예산을 배정해야 한다. 가치 중심 우선순위화는 제약 내에서 혜택을 극대화한다. 소규모 먼저 작업하고 대규모 연기(A)는 가치를 고려하지 않는다. 단계별 배정 및 경영진 회의(B)는 오버헤드를 추가한다. 내부 자원만 충당 확인(D)은 불완전한 계획이다.
676 | A company recently adopted agile to develop innovation projects. The project manager is experiencing problems with some team members who consider some agile ceremonies to be unnecessary. What should the project manager have done before the beginning of the project? | Discussed with the product owner and requested assistance by requiring the adoption of agile ceremonies. | Prepared an inception deck and clearly explained the purpose of agile ceremonies and their benefits to the project. | Discussed with the project sponsor about convincing the team to adopt the agile ceremonies as part of their routine. | Conducted a survey to determine if the team was willing to adopt agile ceremonies on the current project. |  | B | Before starting an agile project, the PM should ensure all team members understand the value and purpose of agile ceremonies. Preparing an inception deck and explaining ceremony benefits aligns team expectations and secures buy-in. Agile ceremonies foster collaboration, transparency, and continuous improvement—essential for innovation project success. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Governance | Executing | Embed Quality | Direct and Manage Project Work | Hybrid/Tailoring | 최근 회사가 혁신 프로젝트를 개발하기 위해 애자일을 도입했다. 프로젝트 관리자가 일부 팀원들이 일부 애자일 의식을 불필요하다고 여기는 문제를 겪고 있다. 프로젝트 관리자는 프로젝트 시작 전에 무엇을 했어야 하는가? | 제품 책임자와 논의하고 애자일 의식 도입을 요구하여 지원을 요청했어야 한다. | 인셉션 덱을 준비하고 애자일 의식의 목적과 프로젝트에 대한 이점을 명확히 설명했어야 한다. | 프로젝트 스폰서와 논의하여 팀이 일상의 일부로 애자일 의식을 도입하도록 설득했어야 한다. | 팀이 현재 프로젝트에서 애자일 의식을 도입할 의향이 있는지 설문조사를 실시했어야 한다. |  | B | 애자일 프로젝트를 시작하기 전, PM은 모든 팀원이 애자일 의식의 가치와 목적을 이해하도록 해야 한다. 인셉션 덱을 준비하고 의식의 이점을 설명하면 팀의 기대치를 정렬하고 동의를 확보한다. 애자일 의식은 협업, 투명성, 지속적 개선을 촉진하며—혁신 프로젝트 성공에 필수적이다.
677 | A company is changing their current business model. The change requires implementing a complex project using multiple agile teams. What three options should the project manager have the testing team adopt as testing mechanisms? (Choose three) | Security and performance testing | Story testing | Independent personal testing | An experimental approach to cover all possible choices | Tests based on behavior and test-driven development | A, B, E | For a complex project using multiple agile teams implementing a business model change, the testing team should adopt three mechanisms: security and performance testing for nonfunctional quality assurance, story testing for user story acceptance verification, and tests based on behavior and test-driven development for quality-driven coding practices. Independent personal testing (C) is not a collaborative agile approach. An experimental approach (D) is too broad and unstructured. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | XP (Extreme Programming) | Process | Plan and Optimize Quality | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 회사가 현재 비즈니스 모델을 변경하고 있다. 변경에는 여러 애자일 팀을 사용하는 복잡한 프로젝트 구현이 필요하다. 프로젝트 관리자는 테스팅 팀이 테스팅 메커니즘으로 채택해야 할 세 가지 옵션은? (3개 선택) | 보안 및 성능 테스팅 | 스토리 테스팅 | 독립적 개인 테스팅 | 모든 가능한 선택을 커버하기 위한 실험적 접근 | 행동 기반 테스트 및 테스트 주도 개발 | A, B, E | 비즈니스 모델 변경을 구현하는 여러 애자일 팀의 복잡한 프로젝트에서 테스팅 팀은 세 가지 메커니즘을 도입해야 한다: 비기능적 품질 보증을 위한 보안 및 성능 테스팅, 사용자 스토리 수락 검증을 위한 스토리 테스팅, 품질 주도 코딩 관행을 위한 행동 기반 테스트 및 테스트 주도 개발. 독립적 개인 테스팅(C)은 협력적 애자일 접근이 아니다. 실험적 접근(D)은 너무 광범위하고 비구조적이다.
678 | A project manager is assigned to a dental equipment development project that is in the middle of its design phase. After reviewing the project prototype, it is identified that a couple of requirements specifications are missing. Which action should the project manager take next? | Prepare a change request for the change control board (CCB) to remove the missing requirements specifications. | Discuss with the team and build a workaround plan to immediately deliver the pending requirements specifications. | Meet with the development team to review and assess the requirements specifications. | Ask the team to wait until they are able to update the requirements specifications. |  | C | When missing requirement specifications are discovered during the design phase, the PM should meet with the development team to review and assess the gaps. This collaborative approach ensures all team members are aware of discrepancies and can contribute to solutions. Maintaining open communication and stakeholder engagement throughout the project lifecycle keeps the project aligned with its objectives while addressing specification gaps. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 설계 단계 중간에 있는 치과 장비 개발 프로젝트에 배정되었다. 프로젝트 프로토타입을 검토한 후 몇 가지 요구사항 명세가 누락되었음을 발견했다. 프로젝트 관리자가 다음에 취해야 할 조치는? | 누락된 요구사항 명세를 제거하기 위해 변경 통제 위원회(CCB)에 변경 요청을 준비한다. | 팀과 논의하고 보류 중인 요구사항 명세를 즉시 전달하기 위한 우회 계획을 수립한다. | 개발 팀과 만나 요구사항 명세를 검토하고 평가한다. | 요구사항 명세를 업데이트할 수 있을 때까지 기다리도록 팀에게 요청한다. |  | C | 설계 단계에서 요구사항 명세 누락이 발견될 때, PM은 개발 팀과 만나 격차를 검토하고 평가해야 한다. 이 협력적 접근 방식은 모든 팀원이 불일치를 인지하고 해결책에 기여할 수 있도록 한다. 프로젝트 수명주기 전반에 걸쳐 열린 소통과 이해관계자 참여를 유지하면 명세 격차를 해결하면서 프로젝트 목표와의 정렬을 유지한다.
679 | A project is delayed. The project manager added extra resources to some activities and approved overtime for several team members. What technique is the project manager applying? | Schedule crashing | Fast tracking | Critical chain method | Resource leveling |  | A | When a project is delayed and the PM adds extra resources to activities and approves overtime, the technique being applied is schedule crashing. Crashing shortens the schedule by adding resources to critical path activities at increased cost. Fast tracking (B) involves performing activities in parallel. The critical chain method (C) manages buffers. Resource leveling (D) adjusts schedules to resolve resource conflicts. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트가 지연되었다. 프로젝트 관리자가 일부 활동에 추가 자원을 투입하고 여러 팀원의 초과근무를 승인했다. 프로젝트 관리자가 적용하고 있는 기법은? | 일정 크래싱 | 빠른 추적 | 크리티컬 체인 방법 | 자원 평준화 |  | A | 프로젝트가 지연되고 PM이 활동에 추가 자원을 투입하고 초과근무를 승인할 때, 적용되는 기법은 일정 크래싱이다. 크래싱은 비용 증가를 감수하며 크리티컬 패스 활동에 자원을 추가하여 일정을 단축한다. 빠른 추적(B)은 활동을 병렬로 수행하는 것이다. 크리티컬 체인 방법(C)은 버퍼를 관리한다. 자원 평준화(D)는 자원 충돌을 해결하기 위해 일정을 조정한다.
680 | After the second iteration of a component development project, the project team conducts a retrospective. It shows that in the initial phase the project has failed to comply with a product functionality. The planning for this product has a predominantly predictive approach. Which technique will help the project manager to accelerate the deliverable? | Collective code ownership | Rolling wave planning | Impact mapping | Scrum of Scrums |  | B | When a component development project with a predominantly predictive approach fails to comply with a product functionality after two iterations, rolling wave planning will help accelerate the deliverable. It enables detailed planning for near-term work while keeping future work at a high level, accommodating changes as information emerges. Collective code ownership (A) improves software quality but does not address planning. Impact mapping (C) aligns deliverables with goals but does not accelerate delivery. Scrum of Scrums (D) coordinates multiple teams but does not address single-project planning. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Tailored Approach | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Hybrid/Tailoring | 컴포넌트 개발 프로젝트의 두 번째 반복 후, 프로젝트 팀이 회고를 실시한다. 초기 단계에서 프로젝트가 제품 기능을 준수하지 못했음이 나타났다. 이 제품의 계획은 주로 예측형 접근 방식이다. 프로젝트 관리자가 전달물을 가속화하는 데 도움이 되는 기법은? | 집단 코드 소유권 | 롤링 웨이브 계획 | 임팩트 매핑 | Scrum of Scrums |  | B | 주로 예측형 접근 방식의 컴포넌트 개발 프로젝트가 두 반복 후 제품 기능을 준수하지 못할 때, 롤링 웨이브 계획이 전달물을 가속화하는 데 도움이 된다. 근기 작업은 상세하게 계획하고 미래 작업은 상위 수준으로 유지하여 정보가 나타남에 따라 변경을 수용한다. 집단 코드 소유권(A)은 소프트웨어 품질을 개선하지만 계획은 다루지 않는다. 임팩트 매핑(C)은 전달물을 목표에 정렬하지만 전달을 가속화하지 않는다. Scrum of Scrums(D)는 여러 팀을 조율하지만 단일 프로젝트 계획은 다루지 않는다.
681 | During the implementation phase of a project, a new regulation affects the project, and a critical status meeting discussing the scope changes is required. The project manager discovers that a key stakeholder cannot attend the scheduled meeting. What should the project manager do? | Meet with the project sponsor to discuss how to address the situation. | Call for a change control board (CCB) meeting, and inform the stakeholder about the outcome | Update the communications management plan and implement the change | Meet with the stakeholder prior to the meeting to obtain their opinion |  | D | When a key stakeholder cannot attend a critical meeting about regulation-driven scope changes, the project manager should meet with the stakeholder prior to the meeting to obtain their opinion. This ensures the stakeholder's input is captured and represented in decision-making. Meeting with the sponsor to discuss (A) does not directly include the stakeholder. Calling a CCB meeting and informing the stakeholder afterward (B) excludes them from input. Updating the communications plan (C) is process-focused, not stakeholder-focused. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 프로젝트 실행 단계 중 새로운 규정이 프로젝트에 영향을 미치며 범위 변경을 논의하는 중요한 상태 회의가 필요하다. 프로젝트 관리자가 핵심 이해관계자가 예정된 회의에 참석할 수 없음을 발견한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서와 만나 상황 대응 방법을 논의한다. | 변경 통제 위원회(CCB) 회의를 소집하고 이해관계자에게 결과를 알린다. | 커뮤니케이션 관리 계획을 업데이트하고 변경을 구현한다. | 회의 전에 이해관계자와 만나 의견을 수집한다. |  | D | 핵심 이해관계자가 규정 변경에 따른 범위 변경에 대한 중요한 회의에 참석할 수 없을 때, 프로젝트 관리자는 회의 전에 이해관계자와 만나 의견을 수집해야 한다. 이를 통해 이해관계자의 의견이 의사결정에 반영된다. 스폰서와 상황 논의(A)는 이해관계자를 직접 포함하지 않는다. CCB 회의 소집 후 알림(B)은 의견 수렴에서 배제한다. 커뮤니케이션 계획 업데이트(C)는 프로세스 중심이지 이해관계자 중심이 아니다.
682 | A project team completed sprint planning, but at the end of the session the project lead receives a message from a stakeholder about a legislative change that requires a new validation rule in one backlog item committed for the sprint. What should the project lead do? | Remove the current backlog item from the sprint and replace it with defect fixing | Update the backlog and advise the team to add this to the acceptance criteria | Update the product backlog and include the change as a high priority for the next iteration | Remove the current backlog item from the sprint and replace it with a similar item |  | C | When a legislative change after sprint planning requires a new validation rule in a committed backlog item, the project lead should update the product backlog and include the change as a high priority for the next iteration. This respects agile cadence while ensuring compliance through proper prioritization. Removing the backlog item and replacing with defect fixing (A) disrupts the sprint without adding the needed change. Adding to acceptance criteria mid-sprint (B) changes committed scope without re-estimation. Replacing with a similar item (D) does not address the legislative requirement. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 팀이 스프린트 계획을 완료했으나, 세션 종료 시 프로젝트 리더가 이해관계자로부터 스프린트에 커밋된 한 백로그 항목에 새로운 검증 규칙을 요구하는 법률 변경에 대한 메시지를 받았다. 프로젝트 리더는 무엇을 해야 하는가? | 현재 백로그 항목을 스프린트에서 제거하고 결함 수정으로 대체한다. | 백로그를 업데이트하고 팀에게 이를 수락 기준에 추가하도록 조언한다. | 제품 백로그를 업데이트하고 다음 반복에서 높은 우선순위로 변경을 포함한다. | 현재 백로그 항목을 스프린트에서 제거하고 유사한 항목으로 대체한다. |  | C | 스프린트 계획 후 법률 변경이 커밋된 백로그 항목에 새로운 검증 규칙을 요구할 때, 프로젝트 리더는 제품 백로그를 업데이트하고 다음 반복에서 높은 우선순위로 변경을 포함해야 한다. 이는 적절한 우선순위화를 통해 준수를 보장하면서 애자일 케이던스를 존중한다. 백로그 항목 제거 후 결함 수정 대체(A)는 필요한 변경을 추가하지 않고 스프린트를 혼란시킨다. 수락 기준에 추가(B)는 재추정 없이 커밋된 범위를 변경한다. 유사 항목 대체(D)는 법률 요구사항을 해결하지 않는다.
683 | A new product is designed for a certain market. This product needs to adhere to the health and safety regulations for that region. What should the project manager do to ensure that the product complies with the regulations? | Inform the design team to ensure compliance during the product design phase | Meet with the team and remind them of the compliance requirements | Inform the quality team that they need to ensure that the product is in compliance | Ensure that compliance is explicitly mentioned in the relevant requirements |  | D | To ensure a new product complies with regional health and safety regulations, the project manager should ensure that compliance requirements are explicitly stated in the relevant project requirements documentation. This makes the regulatory obligations visible to all teams from the outset and integrates them into the project's scope and deliverables. Informing the design team (A) or quality team (C) individually is important but insufficient—compliance must be embedded in the documented requirements, not just communicated verbally. Holding meetings to remind the team (B) is helpful as a reinforcement but does not substitute for having requirements formally captured in project documentation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | 특정 시장을 위해 새로운 제품이 설계되었다. 이 제품은 해당 지역의 보건 및 안전 규정을 준수해야 한다. 프로젝트 관리자는 제품이 규정을 준수하도록 하기 위해 무엇을 해야 하는가? | 제품 설계 단계에서 준수를 보장하도록 설계 팀에 알린다. | 팀과 만나 준수 요구사항을 상기시킨다. | 제품이 준수하도록 보장해야 한다고 품질 팀에 알린다. | 관련 요구사항에 준수가 명시적으로 언급되도록 보장한다. |  | D | 새로운 제품이 지역 보건 및 안전 규정을 준수하도록 하기 위해, 프로젝트 관리자는 준수 요구사항이 관련 프로젝트 요구사항 문서에 명시적으로 기술되도록 보장해야 한다. 이는 규제 의무를 처음부터 모든 팀에게 가시적으로 만들고 프로젝트 범위와 산출물에 통합한다. 설계 팀(A)이나 품질 팀(C)에 개별적으로 알리는 것은 중요하지만 불충분하다—준수는 구두 전달이 아닌 문서화된 요구사항에 내장되어야 한다. 팀에게 상기시키기 위한 회의 개최(B)는 강화에 도움이 되지만 프로젝트 문서에 요구사항을 공식적으로 포착하는 것을 대체하지 않는다.
684 | An agile project has a documented list of requirements prioritized in high, medium, and low categories. The project team has expressed that it is difficult to know what to work on next as so many items are listed as high priority. What should the project manager recommend? | Discard the current categorization of requirements as high, medium, and low and prioritize numerically. | Ask the team to prioritize the high-priority items based on what they feel is a logical sequence to build. | Ask the team to prioritize the high-priority Items based on the release plan and what allows tor testing most effectively. | Ensure the product owner determines the priority based on a product roadmap. release 645 plan, and iteration plan. |  | A | When many items are categorized as high priority and the team does not know what to work on next, the project manager should recommend discarding the vague high/medium/low categorization and prioritizing numerically. Numerical ranking eliminates ambiguity and creates clear sequencing. Having the team prioritize by logical build sequence (B) may not align with business value. Prioritizing by release plan and testing (C) is more structured but less direct. Having the product owner determine priority (D) is appropriate but the question focuses on the categorization problem. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 애자일 프로젝트에 높음, 중간, 낮음 범주로 우선순위화된 요구사항 목록이 문서화되어 있다. 프로젝트 팀은 너무 많은 항목이 높은 우선순위로 나열되어 있어 다음에 무엇을 작업해야 할지 알기 어렵다고 표현했다. 프로젝트 관리자는 무엇을 권고해야 하는가? | 현재의 높음, 중간, 낮음 요구사항 분류를 폐기하고 숫자로 우선순위를 매긴다. | 팀에게 논리적인 구축 순서라고 느끼는 것에 기반하여 높은 우선순위 항목을 우선순위화하도록 요청한다. | 팀에게 릴리스 계획과 가장 효과적인 테스트를 가능하게 하는 것에 기반하여 높은 우선순위 항목을 우선순위화하도록 요청한다. | 제품 책임자가 제품 로드맵, 릴리스 계획 및 반복 계획에 기반하여 우선순위를 결정하도록 보장한다. |  | A | 많은 항목이 높은 우선순위로 분류되어 팀이 다음에 무엇을 작업할지 모를 때, 프로젝트 관리자는 모호한 높음/중간/낮음 분류를 폐기하고 숫자로 우선순위를 매기도록 권고해야 한다. 숫자 순위는 모호성을 제거하고 명확한 순서를 만든다. 팀이 논리적 구축 순서로 우선순위화(B)하는 것은 비즈니스 가치와 정렬되지 않을 수 있다. 릴리스 계획과 테스트로 우선순위화(C)는 더 구조화되지만 덜 직접적이다. 제품 책임자가 우선순위를 결정(D)하는 것은 적절하지만 질문은 분류 문제에 초점을 맞추고 있다.
685 | The key stakeholder of an agile project has low visibility of the project's progress. The stakeholder expresses a concern to the project manager about whether or not the scope is moving in the right direction. What should the project manager do? | Review the scope with the stakeholder, request their feedback, and create an action plan. | Prioritize all of the requirements that are critical to the stakeholder in the next planning session. | Determine alternative solutions to provide improved stakeholder visibility and engagement . | Invite the stakeholder to the demo session and request their feedback about which direction to follow. |  | C | The correct answer is C. Determine alternative solutions to provide improved stakeholder visibility and engagement . In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 애자일 프로젝트의 핵심 이해관계자가 프로젝트 진행에 대한 가시성이 낮다. 이해관계자가 범위가 올바른 방향으로 이동하고 있는지에 대해 프로젝트 관리자에게 우려를 표명한다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자와 범위를 검토하고, 피드백을 요청하며, 실행 계획을 작성한다. | 다음 계획 세션에서 이해관계자에게 중요한 모든 요구사항을 우선순위화한다. | 개선된 이해관계자 가시성과 참여를 제공하기 위한 대안적 솔루션을 결정한다. | 이해관계자를 데모 세션에 초대하고 어떤 방향을 따를지에 대한 피드백을 요청한다. |  | C | 정답은 C이다. 개선된 이해관계자 가시성과 참여를 제공하기 위한 대안적 솔루션을 결정한다. 애자일 환경에서 PM은 팀 협업을 촉진하고 장애물을 제거하며 애자일 원칙을 준수하면서 지속적인 가치 전달을 보장해야 한다.
686 | A virtual project team is working on a multinational project with a risk management strategy. An unexpected situation occurs in one of the project countries, creating the possibility that project operations will shut down for at least two months. What should the project manager do to address this risk? | Evaluate the possibility of having another country complete the task. | Relocate the project to another country that is not shutting down. | Identify additional team members who are able to complete the task. | Determine if the project has built-in slack to remain on schedule. |  | A | The PM should evaluate the possibility of having another country complete the task. Proper risk management requires identifying, documenting, and responding to risks using established processes and plans. The risk register and risk management plan are the primary tools for tracking and managing project risks, and alternative execution locations may represent a viable mitigation strategy. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 가상 프로젝트 팀이 리스크 관리 전략이 있는 다국적 프로젝트에서 작업하고 있다. 프로젝트 국가 중 하나에서 예상치 못한 상황이 발생하여 최소 2개월 동안 프로젝트 운영이 중단될 가능성이 생겼다. 프로젝트 관리자는 이 리스크를 해결하기 위해 무엇을 해야 하는가? | 다른 국가가 작업을 완료할 수 있는 가능성을 평가한다. | 중단되지 않는 다른 국가로 프로젝트를 이전한다. | 작업을 완료할 수 있는 추가 팀원을 식별한다. | 프로젝트에 일정을 유지할 수 있는 내장된 여유가 있는지 확인한다. |  | A | PM은 다른 국가가 작업을 완료할 수 있는 가능성을 평가해야 한다. 적절한 리스크 관리는 확립된 프로세스와 계획을 사용하여 리스크를 식별, 문서화, 대응하는 것을 요구한다. 리스크 레지스터와 리스크 관리 계획은 프로젝트 리스크를 추적하고 관리하기 위한 주요 도구이며, 대안적 실행 장소는 실행 가능한 완화 전략을 나타낼 수 있다.
687 | A construction project to build a fish hatchery is in execution. The operations group notified the project manager about a concern that might turn into a potential issue; however, the concern could not be addressed. In which project document should the project manager record the concern? | Risk register | Issue log | Request for information | Scope statement |  | B | When the operations group notifies the project manager about a concern that might turn into a potential issue but cannot currently be addressed, the project manager should record the concern in the issue log. The issue log documents and monitors unresolved concerns. The risk register (A) tracks uncertain future events, not current concerns. A request for information (C) is a procurement document. The scope statement (D) defines project boundaries. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 양식장 건설 프로젝트가 실행 중이다. 운영 그룹이 잠재적 이슈가 될 수 있는 우려를 프로젝트 관리자에게 알렸지만, 해당 우려는 해결할 수 없었다. 프로젝트 관리자는 어떤 프로젝트 문서에 우려를 기록해야 하는가? | 리스크 레지스터 | 이슈 로그 | 정보 요청서 | 범위 기술서 |  | B | 운영 그룹이 잠재적 이슈가 될 수 있지만 현재 해결할 수 없는 우려를 프로젝트 관리자에게 알릴 때, 프로젝트 관리자는 이슈 로그에 우려를 기록해야 한다. 이슈 로그는 미해결 우려를 문서화하고 모니터링한다. 리스크 레지스터(A)는 불확실한 미래 사건을 추적하며 현재 우려는 아니다. 정보 요청서(C)는 조달 문서이다. 범위 기술서(D)는 프로젝트 경계를 정의한다.
688 | A project is being delayed due to a large amount of rework caused by a quality problem that is impacting the critical path. What should the project manager do? | Notify the project steering committee about the cause of the delay. | Report the delay with rectifying actions to the project management office (PMO). | Rebaseline the project schedule to absorb the delay. | Report the delay with rectifying actions to the change control board (CCB) for review, |  | D | When a project is delayed due to rework from a quality problem impacting the critical path, the project manager should report the delay with rectifying actions to the change control board (CCB) for review. The CCB can assess impact and approve corrective measures. Notifying the steering committee (A) informs but does not initiate formal change control. Reporting to the PMO (B) is informational. Rebaselining the schedule (C) accepts the delay without proper approval. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Critical Path/Schedule Mgmt | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 크리티컬 패스에 영향을 미치는 품질 문제로 인한 대량 재작업으로 프로젝트가 지연되고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 운영 위원회에 지연 원인을 알린다. | 프로젝트 관리 오피스(PMO)에 시정 조치와 함께 지연을 보고한다. | 지연을 흡수하기 위해 프로젝트 일정을 재기준선화한다. | 변경 통제 위원회(CCB)에 시정 조치와 함께 지연을 보고하여 검토를 받는다. |  | D | 크리티컬 패스에 영향을 미치는 품질 문제로 인한 재작업으로 프로젝트가 지연될 때, 프로젝트 관리자는 변경 통제 위원회(CCB)에 시정 조치와 함께 지연을 보고하여 검토를 받아야 한다. CCB는 영향을 평가하고 시정 조치를 승인할 수 있다. 운영 위원회 통보(A)는 정보 제공이지만 공식 변경 통제를 시작하지 않는다. PMO 보고(B)는 정보 제공이다. 일정 재기준선화(C)는 적절한 승인 없이 지연을 수용한다.
689 | A project manager is managing a hybrid project. There is software in place to access the repository of project artifacts. However, a few stakeholders are reporting that they are unable to find the latest project schedule. What should the project manager do? | Advise the project management office (PMO) that there is a resource gap for sharing project artifacts effectively | Escalate the issue to the steering committee and ask them to deal with the stakeholders ' lack of training | Make sure all stakeholders have access to the system and know where to find project artifacts | Send the project schedule via email to the stakeholders who need that information |  | C | When stakeholders in a hybrid project cannot find the latest project schedule in the repository, the project manager should ensure all stakeholders have access and know where to find project artifacts. Addressing access and awareness resolves the issue. Advising the PMO of a resource gap (A) deflects responsibility. Escalating to the steering committee (B) is excessive. Emailing the schedule (D) is a workaround, not a fix. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Tailored Approach | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 프로젝트를 관리하고 있다. 프로젝트 산출물 저장소에 접근할 수 있는 소프트웨어가 있지만, 일부 이해관계자가 최신 프로젝트 일정을 찾을 수 없다고 보고하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 관리 오피스(PMO)에 프로젝트 산출물을 효과적으로 공유하기 위한 자원 격차가 있다고 조언한다. | 운영 위원회에 이슈를 에스컬레이션하고 이해관계자들의 교육 부족을 처리하도록 요청한다. | 모든 이해관계자가 시스템에 접근할 수 있고 프로젝트 산출물을 어디에서 찾을 수 있는지 알도록 보장한다. | 해당 정보가 필요한 이해관계자들에게 이메일로 프로젝트 일정을 보낸다. |  | C | 하이브리드 프로젝트에서 이해관계자가 저장소에서 최신 프로젝트 일정을 찾을 수 없을 때, 프로젝트 관리자는 모든 이해관계자가 접근할 수 있고 산출물을 어디에서 찾을 수 있는지 알도록 보장해야 한다. 접근과 인식 해결이 문제를 해결한다. PMO에 자원 격차 조언(A)은 책임을 전가한다. 운영 위원회 에스컬레이션(B)은 과도하다. 일정을 이메일로 보내기(D)는 임시방편이지 해결책이 아니다.
690 | A project manager has been asked by the human resources (HR) review team to share information about how the project team members interact, communicate, and conduct themselves to reduce the risk of conflicts and improve overall team performance. What should the project manager do next? | Direct the HR review team to the communications management plan. | Invite the HR review team to attend one of the daily standup meetings. | Discuss the resource management plan with the HR review team. | Provide the HR review team with the team norms document. |  | D | The team norms document (often part of the team charter) outlines behavioral expectations, communication styles, and collaboration rules. It is the most appropriate document to share with HR for insights into how the team interacts and conducts themselves. Performance reports (B) show transparency but lack structured behavioral insight. The project management plan (C) is broader and not behavior-focused. The communications plan (D) covers logistics rather than interpersonal norms. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 인사(HR) 검토 팀으로부터 프로젝트 팀원들이 어떻게 상호작용하고, 의사소통하며, 행동하는지에 대한 정보를 공유하여 갈등 위험을 줄이고 전체 팀 성과를 개선하도록 요청받았다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | HR 검토 팀에게 커뮤니케이션 관리 계획을 안내한다. | HR 검토 팀을 일일 스탠드업 회의 중 하나에 참석하도록 초대한다. | HR 검토 팀과 자원 관리 계획을 논의한다. | HR 검토 팀에게 팀 규범 문서를 제공한다. |  | D | 팀 규범 문서(종종 팀 헌장의 일부)는 행동 기대, 의사소통 스타일, 협업 규칙을 개략적으로 설명한다. HR에게 팀이 어떻게 상호작용하고 행동하는지에 대한 통찰을 공유하기에 가장 적절한 문서이다. 성과 보고서(B)는 투명성을 보여주지만 구조화된 행동적 통찰이 부족하다. 프로젝트 관리 계획(C)은 더 광범위하고 행동에 초점을 맞추지 않는다. 커뮤니케이션 계획(A)은 대인 관계 규범이 아닌 물류를 다룬다.
691 | A project manager became aware of misunderstandings between a key stakeholder and a team member regarding some of the features defined in the project scope. What should the project manager do? | Reconcile the key stakeholder to the team member ' s recommendation. | Escalate the communication concerns to the project management office (PMO) andrequest that they take action | Work with both the team member and the key stakeholder to reach a consensus. | Reconcile the team member to the key stakeholder ' s recommendation. |  | C | The PM's role includes facilitating communication and resolving conflicts among stakeholders. When disagreements arise between a team member and a key stakeholder, the PM should work with both parties to reach a consensus. This collaborative approach ensures all perspectives are heard and the optimal solution for the project is identified. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 핵심 이해관계자와 팀원 사이에 프로젝트 범위에 정의된 일부 기능에 대한 오해가 있음을 인식했다. 프로젝트 관리자는 무엇을 해야 하는가? | 핵심 이해관계자를 팀원의 권고에 동의하도록 조정한다. | 프로젝트 관리 오피스(PMO)에 커뮤니케이션 우려를 에스컬레이션하고 조치를 취하도록 요청한다. | 팀원과 핵심 이해관계자 모두와 협력하여 합의에 도달한다. | 팀원을 핵심 이해관계자의 권고에 동의하도록 조정한다. |  | C | PM의 역할에는 의사소통 촉진과 이해관계자 간 갈등 해결이 포함된다. 팀원과 핵심 이해관계자 사이에 의견 불일치가 발생할 때, PM은 양측과 협력하여 합의에 도달해야 한다. 이러한 협력적 접근 방식은 모든 관점이 청취되고 프로젝트를 위한 최적의 솔루션이 도출되도록 보장한다.
692 | A team member increased the estimated completion time for their activities on the critical path. This action, however, has caused friction among the team members. The project manager reviewed the key performance indicators (KPIs) that show the issue. What should the project manager do first? | Apply crashing to the strategic tasks to recover any time that was lost to bring the project on track. | Train the team member in the methodology to get the sufficient knowledge to meet the estimated activity time. | Allocate another resource to help the team member to complete the tasks and meet the estimated activity time. | Conduct a root cause analysis (RCA) and plan the correct actions to ensure completion of the tasks on time. |  | D | When a team member increases the estimated completion time for critical path activities, causing friction among team members, the project manager should first conduct a root cause analysis (RCA) and plan corrective actions. Understanding why the estimate increased—whether due to skill gaps, scope uncertainty, workload issues, or other factors—ensures the right mitigation strategy is implemented. Applying crashing (A) is a corrective technique that should follow root cause understanding. Training the team member (B) assumes skill gaps without verification. Allocating another resource (C) adds cost without addressing the underlying issue. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 팀원이 크리티컬 패스에 있는 활동의 예상 완료 시간을 늘렸다. 그러나 이 조치가 팀원들 사이에 마찰을 일으켰다. 프로젝트 관리자가 이슈를 보여주는 핵심 성과 지표(KPI)를 검토했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 손실된 시간을 복구하여 프로젝트를 정상 궤도에 올리기 위해 전략적 작업에 크래싱을 적용한다. | 팀원에게 방법론 교육을 실시하여 예상 활동 시간을 충족할 충분한 지식을 습득하도록 한다. | 팀원이 작업을 완료하고 예상 활동 시간을 충족하도록 다른 자원을 배정한다. | 근본 원인 분석(RCA)을 수행하고 작업을 제시간에 완료하기 위한 올바른 조치를 계획한다. |  | D | 팀원이 크리티컬 패스 활동의 예상 완료 시간을 늘려 팀원들 사이에 마찰이 발생할 때, 프로젝트 관리자는 먼저 근본 원인 분석(RCA)을 수행하고 시정 조치를 계획해야 한다. 추정치가 증가한 이유—역량 격차, 범위 불확실성, 작업량 문제 또는 기타 요인—를 이해하면 올바른 완화 전략이 구현된다. 크래싱 적용(A)은 근본 원인 이해 후에 따라야 할 시정 기법이다. 팀원 교육(B)은 검증 없이 역량 격차를 가정한다. 다른 자원 배정(C)은 근본 이슈를 해결하지 않고 비용을 추가한다.
693 | A project is starting its first iteration out of eight. The team realizes that a key deliverable will depend on the acquisition of a new device. What should the project manager do? | Update the status report with information about this dependency. | Assign a resource from the core team to handle the acquisition. | Register a risk and monitor its exposure variation. | Register a risk and escalate it to the project sponsor. |  | C | The correct answer is C. Register a risk and monitor its exposure variation. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Scrum | Process | Manage Project Closure | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 프로젝트가 8개 반복 중 첫 번째 반복을 시작하고 있다. 팀이 핵심 산출물이 새 장비 획득에 의존한다는 것을 인식했다. 프로젝트 관리자는 무엇을 해야 하는가? | 이 의존성에 대한 정보로 상태 보고서를 업데이트한다. | 핵심 팀에서 자원을 배정하여 획득을 처리하도록 한다. | 리스크를 등록하고 노출 변동을 모니터링한다. | 리스크를 등록하고 프로젝트 스폰서에게 에스컬레이션한다. |  | C | 정답은 C이다. 리스크를 등록하고 노출 변동을 모니터링한다. 애자일 환경에서 PM은 팀 협업을 촉진하고, 장애물을 제거하며, 애자일 원칙을 준수하면서 지속적인 가치 전달을 보장해야 한다.
694 | For the purposes of quality assurance, a quality audit was conducted on the processes being used in the project execution plan. One of the nonconformance issues raised by the auditor was that attendance lists for the project risk review meetings were not available. Why is an attendance list important? | It is standard practice on projects to conduct risk review meetings which should have records on meeting attendance | It is a document that is registered within the lessons learned register | It is a record that shows the number of attendees in the meeting | The attendance list is evidence that risk review meetings were held with the appropriate project team members |  | D | The attendance list for risk review meetings is important because it is evidence that risk review meetings were held with the appropriate project team members. Attendance records demonstrate compliance with the risk management plan and accountability. Being standard practice (A) does not explain why it is important. Being part of lessons learned (B) mischaracterizes its purpose. Showing the number of attendees (C) is a fact but not the reason for its importance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 품질 보증 목적으로 프로젝트 실행 계획에서 사용되는 프로세스에 대한 품질 감사가 수행되었다. 감사자가 제기한 부적합 이슈 중 하나는 프로젝트 리스크 검토 회의의 참석자 명단이 없다는 것이었다. 참석자 명단이 왜 중요한가? | 프로젝트에서 리스크 검토 회의를 실시하는 것은 표준 관행이며, 회의 참석에 대한 기록이 있어야 한다. | 교훈 레지스터 내에 등록되는 문서이다. | 회의 참석자 수를 보여주는 기록이다. | 참석자 명단은 적절한 프로젝트 팀원과 함께 리스크 검토 회의가 개최되었다는 증거이다. |  | D | 리스크 검토 회의의 참석자 명단이 중요한 이유는 적절한 프로젝트 팀원과 함께 리스크 검토 회의가 개최되었다는 증거이기 때문이다. 참석 기록은 리스크 관리 계획 준수와 책임성을 입증한다. 표준 관행(A)은 중요한 이유를 설명하지 않는다. 교훈의 일부(B)는 목적을 잘못 설명한다. 참석자 수 표시(C)는 사실이지만 중요한 이유는 아니다.
695 | A project is in its sixth iteration out of seven. During the daily meeting, a team member reports that a key function will take longer to finish than originally expected. What should the project manager do? | Ask for a project extension to deliver the committed scope. | Update the issue log and escalate the problem to the project sponsor. | Review the options and possible solutions with the project team. | Ask for help to increase the team capacity to deliver on time. |  | C | When a key function is at risk of taking longer than expected late in the project, the PM should collaborate with the team to review available options and possible solutions. This approach aligns with agile principles of team engagement, collaborative problem-solving, and adaptive planning. Requesting a project extension (A), escalating to the sponsor (B), or requesting additional capacity (D) may be considered as part of the solution, but the first step should always be exploring options with the team. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트가 7개 반복 중 6번째 반복에 있다. 일일 회의에서 팀원이 핵심 기능이 원래 예상보다 완료하는 데 더 오래 걸릴 것이라고 보고한다. 프로젝트 관리자는 무엇을 해야 하는가? | 약속된 범위를 전달하기 위해 프로젝트 연장을 요청한다. | 이슈 로그를 업데이트하고 문제를 프로젝트 스폰서에게 에스컬레이션한다. | 프로젝트 팀과 함께 옵션과 가능한 해결책을 검토한다. | 제시간에 전달하기 위해 팀 역량을 증가시킬 도움을 요청한다. |  | C | 프로젝트 후반에 핵심 기능이 예상보다 오래 걸릴 위험이 있을 때, PM은 팀과 협력하여 사용 가능한 옵션과 가능한 해결책을 검토해야 한다. 이 접근 방식은 팀 참여, 협력적 문제 해결, 적응적 계획의 애자일 원칙에 부합한다. 프로젝트 연장 요청(A), 스폰서에게 에스컬레이션(B), 추가 역량 요청(D)은 해결책의 일부로 고려될 수 있지만, 첫 번째 단계는 항상 팀과 옵션을 탐색하는 것이어야 한다.
696 | A retail chain is evaluating a project to replace payment systems across all its stores in multiple locations. The project does not pass the financial threshold but is also expected to increase market share, improve customer services, and retain more customers. The project is planned as a phased implementation building on learning from the retrospectives during each phase. How should the business increase the value of the project? | Use a fishbone diagram to find the root cause of the lower financial benefits with the benefits owner | Ask the benefits owner to reassess the identified risks that are impacting the outcomes of the financial benefits. | Quantify the expected tangible and intangible benefits in the benefits management plan for each phase | Consult with experts on methods to reduce costs and increase the financial value of the project |  | C | When a project does not pass the financial threshold but offers strategic benefits like market share and customer retention, the business should quantify the expected tangible and intangible benefits in the benefits management plan for each phase. Documenting all benefits demonstrates total value beyond financial metrics. Using a fishbone diagram for financial root causes (A) is diagnostic, not value-building. Reassessing risks impacting financial benefits (B) is narrow. Consulting experts on cost reduction (D) focuses only on the financial gap. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 소매 체인이 여러 지역의 모든 매장에서 결제 시스템을 교체하는 프로젝트를 평가하고 있다. 프로젝트가 재무 기준을 통과하지 못하지만 시장 점유율 증가, 고객 서비스 개선, 더 많은 고객 유지도 기대된다. 프로젝트는 각 단계의 회고에서 얻은 학습을 바탕으로 단계적 구현으로 계획되었다. 비즈니스는 프로젝트의 가치를 어떻게 높여야 하는가? | 혜택 소유자와 함께 피시본 다이어그램을 사용하여 낮은 재무 혜택의 근본 원인을 찾는다. | 혜택 소유자에게 재무 혜택의 결과에 영향을 미치는 식별된 리스크를 재평가하도록 요청한다. | 각 단계에 대한 혜택 관리 계획에서 예상되는 유형 및 무형 혜택을 정량화한다. | 비용을 줄이고 프로젝트의 재무 가치를 높이는 방법에 대해 전문가와 상담한다. |  | C | 프로젝트가 재무 기준을 통과하지 못하지만 시장 점유율, 고객 유지 등 전략적 혜택을 제공할 때, 비즈니스는 각 단계에 대한 혜택 관리 계획에서 예상되는 유형 및 무형 혜택을 정량화해야 한다. 모든 혜택을 문서화하면 재무 지표를 넘어선 총 가치를 입증한다. 재무 근본 원인에 피시본 다이어그램 사용(A)은 진단적이지 가치 구축이 아니다. 재무 혜택 영향 리스크 재평가(B)는 범위가 좁다. 비용 절감에 대한 전문가 상담(D)은 재무 격차에만 집중한다.
697 | A project manager is leading a project when a key stakeholder requests additional work that is not in the scope. The stakeholder is also concerned that the project sponsors may not approve and fund the additional change in scope. What should the project manager do first? | Evaluate the cost of the additional requested work. | Evaluate the impact and submit a change request. 1162 | Discuss the requested change with the sponsor. | Discuss the requested change with the team. |  | B | When a key stakeholder requests additional out-of-scope work and is concerned about sponsor approval and funding, the project manager should first evaluate the impact and submit a change request. Impact assessment and formal change control ensure proper governance. Evaluating cost alone (A) is incomplete. Discussing with the sponsor (C) bypasses formal process. Discussing with the team (D) does not address the governance requirement. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 프로젝트를 이끌고 있는데 핵심 이해관계자가 범위에 없는 추가 작업을 요청한다. 이해관계자는 프로젝트 스폰서가 추가 범위 변경을 승인하고 자금을 지원하지 않을 수 있다는 우려도 있다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 추가 요청 작업의 비용을 평가한다. | 영향을 평가하고 변경 요청을 제출한다. | 요청된 변경을 스폰서와 논의한다. | 요청된 변경을 팀과 논의한다. |  | B | 핵심 이해관계자가 범위 외 추가 작업을 요청하고 스폰서 승인 및 자금에 대한 우려가 있을 때, 프로젝트 관리자는 먼저 영향을 평가하고 변경 요청을 제출해야 한다. 영향 평가와 공식적인 변경 통제가 적절한 거버넌스를 보장한다. 비용만 평가(A)는 불완전하다. 스폰서와 논의(C)는 공식 프로세스를 우회한다. 팀과 논의(D)는 거버넌스 요구사항을 해결하지 않는다.
698 | A building management system (BMS) project is in its commissioning phase and handover to the operations team will commence soon. However, the project manager noted that both the project and operation teams are not able to properly operate the BMS. As a result, there is an increased risk of the project schedule being delayed. What should the project manager have done to avoid this situation? | Allocated a dedicated handover team at early phases of the project | Allocated proper resources for training on BMS in the project plan | Brought both teams together in a joint meeting to resolve the issue | Made some adjustments to BMS to be more suitable for the teams |  | B | To avoid the risk of schedule delays caused by the project and operations teams' inability to operate the BMS, the project manager should have allocated proper resources for training on BMS in the project plan. Proactive training ensures both teams are adequately prepared to operate the system upon handover, minimizing operational disruptions. Allocating a dedicated handover team early (A) supports transition management but does not address the competency gap. Bringing both teams together in a joint meeting (C) may help communication but is reactive rather than preventive. Making adjustments to the BMS (D) changes the system to fit the teams' limitations rather than building the teams' capabilities. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 건물 관리 시스템(BMS) 프로젝트가 시운전 단계에 있으며 곧 운영 팀에 인수인계가 시작될 예정이다. 그러나 프로젝트 관리자는 프로젝트 팀과 운영 팀 모두 BMS를 제대로 운영할 수 없다는 것을 확인했다. 그 결과 프로젝트 일정이 지연될 위험이 증가했다. 프로젝트 관리자는 이 상황을 피하기 위해 무엇을 했어야 하는가? | 프로젝트 초기 단계에 전담 인수인계 팀을 배정한다. | 프로젝트 계획에 BMS 교육을 위한 적절한 자원을 배정한다. | 문제를 해결하기 위해 양 팀을 공동 회의에 모은다. | 팀에 더 적합하도록 BMS를 일부 조정한다. |  | B | 프로젝트 팀과 운영 팀이 BMS를 운영할 수 없어 일정 지연 위험이 있을 때, 프로젝트 관리자는 프로젝트 계획에 BMS 교육을 위한 적절한 자원을 배정했어야 한다. 사전 예방적 교육은 양 팀이 인수인계 시 시스템을 적절히 운영할 수 있도록 준비시켜 운영 중단을 최소화한다. 초기 전담 인수인계 팀 배정(A)은 전환 관리를 지원하지만 역량 격차를 해결하지 않는다. 공동 회의(C)는 의사소통에 도움이 되지만 예방적이라기보다 반응적이다. BMS 조정(D)은 팀의 역량을 키우는 대신 시스템을 팀의 한계에 맞추는 것이다.
699 | A company strictly uses an agile approach, and the backlogs are continuously updated. A new project lead is hired and feels uncomfortable sharing some of the product's vital information with the team and the product owner. What does the project lead need to do to prevent a risky situation in the next iterations? | Keep the project focused and executed in silos for better outcomes. | Report the concern to the agile project management office (PMO), | Open up to the team to work collaboratively to achieve the outcomes. | Inform the product owner of the concern so that i can be addressed. |  | C | When a new project lead is uncomfortable sharing vital product information with the team and PO in an agile environment, they need to open up and work collaboratively. Transparency is fundamental to agile. Working in silos (A) violates agile principles. Reporting to the PMO (B) escalates unnecessarily. Informing the PO of the concern (D) is partial but does not address the behavior. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 회사가 엄격하게 애자일 접근 방식을 사용하고 있으며, 백로그는 지속적으로 업데이트된다. 새로운 프로젝트 리더가 고용되었으며 제품의 중요한 정보를 팀과 제품 책임자에게 공유하는 것이 불편하다고 느낀다. 프로젝트 리더는 다음 반복에서 위험한 상황을 방지하기 위해 무엇을 해야 하는가? | 더 나은 결과를 위해 프로젝트를 사일로에서 집중하고 실행한다. | 애자일 프로젝트 관리 오피스(PMO)에 우려를 보고한다. | 결과를 달성하기 위해 팀과 협력적으로 작업하도록 개방한다. | 제품 책임자에게 우려를 알려 해결할 수 있도록 한다. |  | C | 애자일 환경에서 새 프로젝트 리더가 팀과 제품 책임자에게 중요한 제품 정보를 공유하는 것이 불편할 때, 개방적으로 협력해야 한다. 투명성은 애자일의 기본이다. 사일로에서 작업(A)은 애자일 원칙에 위배된다. PMO에 보고(B)는 불필요하게 에스컬레이션한다. 제품 책임자에게 우려 알림(D)은 부분적이지만 행동을 해결하지 않는다.
700 | A member of the project team always extends discussion topics, taking more time than necessary during project team meetings. Other team members feel this member is not being considerate of their time. What should the project manager do? | Ask this member to only discuss the current topic to achieve team efficiency. | Allow the self-organized team to discuss the situation among themselves and come to a resolution. | Explain to the team that open discussions are needed but remind the team to follow the ground rules. | Ask the team to accept the input from this particular member as their input may be useful. |  | C | When a team member consistently extends discussions beyond their allotted time, the project manager should explain to the team that open discussions are encouraged but remind everyone to follow the ground rules. This balanced approach values the team member's input while enforcing agreed-upon meeting protocols for efficiency and mutual respect. Asking the member to limit their contributions (A) may feel dismissive and stifle valuable input. Letting the team self-organize a resolution (B) may not work when ground rules already exist but are not being enforced. Asking the team to accept the member's input because it may be useful (D) ignores the legitimate time concerns of other team members. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 프로젝트 팀원 중 한 명이 프로젝트 팀 회의에서 토론 주제를 항상 확장하여 필요 이상으로 시간을 사용한다. 다른 팀원들은 이 팀원이 자신들의 시간을 배려하지 않는다고 느낀다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀 효율성을 달성하기 위해 이 팀원에게 현재 주제만 논의하도록 요청한다. | 자기 조직화된 팀이 스스로 상황을 논의하고 해결책을 찾도록 허용한다. | 팀에게 열린 토론이 필요하지만 기본 규칙을 따르도록 상기시킨다. | 팀에게 이 특정 팀원의 의견이 유용할 수 있으므로 수용하도록 요청한다. |  | C | 팀원이 지속적으로 토론을 할당된 시간 이상으로 연장할 때, 프로젝트 관리자는 팀에게 열린 토론이 권장되지만 모두가 기본 규칙을 따르도록 상기시켜야 한다. 이 균형 잡힌 접근 방식은 팀원의 의견을 존중하면서 효율성과 상호 존중을 위해 합의된 회의 프로토콜을 시행한다. 팀원에게 기여를 제한하도록 요청(A)은 거부감을 줄 수 있다. 팀이 스스로 해결하도록 허용(B)은 기본 규칙이 존재하지만 시행되지 않을 때 효과적이지 않을 수 있다. 팀에게 유용할 수 있으므로 수용하도록 요청(D)은 다른 팀원의 정당한 시간 우려를 무시한다.
701 | A project manager was just assigned to an ongoing project. According to the project's status, all the increments produced passed the acceptance criteria. During the last meeting with the project sponsor, the prototype is far from the sponsor's original expectations. What should the project manager do first? | Invite the sponsor to the retrospective meeting so they can clarify expectations. | Cancel the ongoing project and start a new one. | Complete the project and start a new one for the updated scope. | Add additional sprints to modify the deliverables with the new information. |  | D | When all increments passed acceptance criteria but the prototype does not meet the sponsor's expectations, the project manager should first add additional sprints to modify deliverables with new information. Iterative refinement addresses expectation gaps. Inviting the sponsor to a retrospective (A) mixes roles. Canceling and restarting (B) is wasteful. Completing and starting a new project (C) delays correction. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 관리자가 진행 중인 프로젝트에 방금 배정되었다. 프로젝트 상태에 따르면, 생산된 모든 증분이 수락 기준을 통과했다. 프로젝트 스폰서와의 마지막 회의에서 프로토타입이 스폰서의 원래 기대와 크게 다르다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 스폰서를 회고 회의에 초대하여 기대를 명확히 하도록 한다. | 진행 중인 프로젝트를 취소하고 새로운 것을 시작한다. | 프로젝트를 완료하고 업데이트된 범위로 새로운 것을 시작한다. | 새 정보로 산출물을 수정하기 위한 추가 스프린트를 추가한다. |  | D | 모든 증분이 수락 기준을 통과했지만 프로토타입이 스폰서의 기대를 충족하지 못할 때, 프로젝트 관리자는 먼저 새 정보로 산출물을 수정하기 위한 추가 스프린트를 추가해야 한다. 반복적 개선이 기대 격차를 해결한다. 스폰서를 회고에 초대(A)는 역할을 혼합한다. 취소하고 재시작(B)은 낭비적이다. 완료하고 새 프로젝트 시작(C)은 수정을 지연시킨다.
702 | A project manager is developing a project baseline schedule and has started to assign team members to the project activities according to their function. What should the project manager do in this phase? | Ensure that a kick-off meeting is planned and invite relevant stakeholders toparticipate. | Develop project onboarding guidelines for the team members assigned to the project. | Confirm that no conflicts exist in resource calendars with assigned activities on otherprojects. | Ensure that lessons learned are considered as part of the project scheduledecomposition. |  | A | When developing a baseline schedule and assigning team members to activities, the project manager should ensure a kick-off meeting is planned and invite relevant stakeholders to participate. The kick-off meeting formally starts the project, communicates objectives, scope, schedule, roles, and expectations to the team and stakeholders. Developing onboarding guidelines (B) supports new members but is not the primary action. Confirming no resource calendar conflicts (C) is important but operational. Incorporating lessons learned (D) enhances planning but is a secondary concern. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 관리자가 프로젝트 기준선 일정을 개발하고 기능에 따라 팀원을 프로젝트 활동에 배정하기 시작했다. 프로젝트 관리자는 이 단계에서 무엇을 해야 하는가? | 킥오프 미팅이 계획되어 있고 관련 이해관계자를 참여하도록 초대하는지 확인한다. | 프로젝트에 배정된 팀원을 위한 프로젝트 온보딩 가이드라인을 개발한다. | 다른 프로젝트의 배정된 활동과 자원 캘린더에 충돌이 없는지 확인한다. | 프로젝트 일정 분해의 일부로 교훈이 고려되도록 보장한다. |  | A | 기준선 일정을 개발하고 팀원을 활동에 배정할 때, 프로젝트 관리자는 킥오프 미팅이 계획되어 있고 관련 이해관계자를 참여하도록 초대해야 한다. 킥오프 미팅은 프로젝트를 공식적으로 시작하고, 팀과 이해관계자에게 목표, 범위, 일정, 역할, 기대를 전달한다. 온보딩 가이드라인 개발(B)은 신규 멤버를 지원하지만 주요 조치는 아니다. 자원 캘린더 충돌 확인(C)은 중요하지만 운영적이다. 교훈 반영(D)은 계획을 강화하지만 부차적 관심사이다.
703 | A project manager has just been assigned to a project to build new software for a client. All the requirements have been gathered. What should the project manager tell the team members to focus on? | Reducing cost for the customer | Finishing the project on schedule | Working together as a team | Delivering value to the customer |  | D | When a project manager is assigned to build new software with all requirements gathered, the team should focus on delivering value to the customer. Value delivery is the primary objective of any project. Reducing cost (A) may compromise quality or scope. Working as a team (C) is important but not the ultimate goal. Finishing on schedule (B) may not ensure value if deliverables do not meet requirements. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 관리자가 고객을 위한 새로운 소프트웨어를 구축하는 프로젝트에 배정되었다. 모든 요구사항이 수집되었다. 프로젝트 관리자는 팀원들에게 무엇에 집중하라고 해야 하는가? | 고객을 위한 비용 절감 | 일정에 맞춰 프로젝트 완료 | 팀으로서 함께 일하기 | 고객에게 가치 전달 |  | D | 모든 요구사항이 수집된 새 소프트웨어 구축 프로젝트에 배정될 때, 팀은 고객에게 가치를 전달하는 데 집중해야 한다. 가치 전달은 모든 프로젝트의 주요 목표이다. 비용 절감(A)은 품질이나 범위를 손상시킬 수 있다. 팀으로 일하기(C)는 중요하지만 궁극적 목표는 아니다. 일정에 맞춰 완료(B)는 산출물이 요구사항을 충족하지 못하면 가치를 보장하지 않을 수 있다.
704 | A project manager has established daily standup meetings with the team during the execution phase of the project. The project manager has been successful in removing 75% of the obstacles reported, but the timeline continues to deviate further each day with no signs of improvement. What should the project manager have done to avoid this issue? | Distributed the daily standup meeting agenda beforehand | Prioritized blockers on the critical path | Developed the team members' competences | Followed the quality control measurements |  | B | The project manager should have prioritized blockers on the critical path. The critical path represents the longest sequence of dependent activities that determines the project's minimum duration—any delay on this path directly impacts the overall timeline. While removing 75% of obstacles is commendable, if the remaining 25% are on the critical path, the schedule will continue to deviate. Distributing the standup agenda beforehand (A) improves meeting efficiency but does not address blocker prioritization. Developing team competences (C) is a long-term improvement but does not resolve immediate schedule deviations. Following quality control measurements (D) addresses quality, not schedule performance. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 프로젝트 관리자가 프로젝트 실행 단계에서 팀과 일일 스탠드업 회의를 수립했다. 프로젝트 관리자는 보고된 장애물의 75%를 성공적으로 제거했지만, 타임라인은 매일 더 벗어나며 개선의 징후가 없다. 프로젝트 관리자는 이 문제를 방지하기 위해 무엇을 했어야 하는가? | 일일 스탠드업 회의 안건을 사전에 배포한다. | 크리티컬 패스상의 차단 요소를 우선순위화한다. | 팀원들의 역량을 개발한다. | 품질 관리 측정을 따른다. |  | B | 프로젝트 관리자는 크리티컬 패스상의 차단 요소를 우선순위화했어야 한다. 크리티컬 패스는 프로젝트의 최소 기간을 결정하는 가장 긴 종속 활동 시퀀스를 나타내며, 이 경로상의 지연은 전체 타임라인에 직접 영향을 미친다. 장애물의 75%를 제거한 것은 훌륭하지만, 나머지 25%가 크리티컬 패스에 있다면 일정은 계속 벗어날 것이다. 스탠드업 안건 사전 배포(A)는 회의 효율성을 개선하지만 차단 요소 우선순위화를 다루지 않는다. 팀 역량 개발(C)은 장기적 개선이지만 즉각적인 일정 이탈을 해결하지 않는다. 품질 관리 측정 준수(D)는 품질을 다루지 일정 성과는 아니다.
705 | In order to increase a project's profit margin, the project manager and subject matter experts (SMEs) agreed to select the oldest model of a specific machine available in the market. When the machine reached its destination country, it was blocked by customs authorities who restricted the import of this machine model. What should the project manager have done to prevent this from happening? | Ensured the project sponsor provided enough funding to purchase the latest version of the machine. | Ensured that regulatory compliance was considered in the quality management plan. | Ensured that the SMEs correctly defined the project scope and the machine model. 1254 | Ensured that the technical team researched and selected the latest model of the machine. |  | B | When an imported machine is blocked by customs due to model restrictions, the project manager should have ensured regulatory compliance was considered in the quality management plan. Regulatory compliance prevents import issues. Ensuring sponsor funding for the latest model (A) does not address regulations. Ensuring SMEs defined scope correctly (C) focuses on scope, not compliance. Selecting the latest model (D) may not address regulatory requirements. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트의 수익 마진을 높이기 위해 프로젝트 관리자와 주제 전문가(SME)가 시장에서 구할 수 있는 특정 기계의 가장 오래된 모델을 선택하기로 합의했다. 기계가 목적지 국가에 도착했을 때 이 기계 모델의 수입을 제한하는 세관 당국에 의해 차단되었다. 프로젝트 관리자는 이를 방지하기 위해 무엇을 했어야 하는가? | 최신 버전의 기계를 구매할 수 있도록 프로젝트 스폰서가 충분한 자금을 제공하도록 보장한다. | 품질 관리 계획에서 규제 준수가 고려되도록 보장한다. | SME가 프로젝트 범위와 기계 모델을 올바르게 정의하도록 보장한다. | 기술 팀이 최신 모델의 기계를 조사하고 선택하도록 보장한다. |  | B | 수입된 기계가 모델 제한으로 세관에 의해 차단될 때, 프로젝트 관리자는 품질 관리 계획에서 규제 준수가 고려되도록 보장했어야 한다. 규제 준수는 수입 문제를 방지한다. 최신 모델을 위한 스폰서 자금 보장(A)은 규정을 다루지 않는다. SME가 범위를 올바르게 정의하도록 보장(C)은 범위에 집중하지 준수는 아니다. 최신 모델 선택(D)은 규제 요구사항을 다루지 않을 수 있다.
706 | An agile project team is working on a large project involving multiple cross-functional teams in different geographical locations. Some team members are not clear on the next tasks. Which strategy should the project lead implement to help the team? | Review the work scope with the functional managers and their teams. | Review the action items with the respective project team members. | Review the prioritized backlog with the project team. | Review the project objectives at the next team meeting. |  | C | When team members across multiple cross-functional teams in different locations are unclear on next tasks, the project lead should review the prioritized backlog with the project team. The backlog provides shared visibility into upcoming work. Reviewing scope with functional managers (A) is hierarchical, not agile. Reviewing action items with individuals (B) is narrow. Reviewing project objectives at the next meeting (D) addresses the "why" but not the immediate "what next." | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scaled Agile | People | Manage Conflicts | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 다양한 지리적 위치에 있는 여러 교차 기능 팀이 참여하는 대규모 프로젝트에서 애자일 프로젝트 팀이 작업하고 있다. 일부 팀원들이 다음 작업에 대해 명확하지 않다. 프로젝트 리더는 팀을 돕기 위해 어떤 전략을 구현해야 하는가? | 기능 관리자 및 해당 팀과 작업 범위를 검토한다. | 해당 프로젝트 팀원들과 실행 항목을 검토한다. | 프로젝트 팀과 우선순위화된 백로그를 검토한다. | 다음 팀 회의에서 프로젝트 목표를 검토한다. |  | C | 다양한 위치의 여러 교차 기능 팀에서 팀원들이 다음 작업에 대해 불명확할 때, 프로젝트 리더는 프로젝트 팀과 우선순위화된 백로그를 검토해야 한다. 백로그는 예정된 작업에 대한 공유 가시성을 제공한다. 기능 관리자와 범위 검토(A)는 계층적이며 애자일적이지 않다. 개인과 실행 항목 검토(B)는 좁다. 다음 회의에서 프로젝트 목표 검토(D)는 '왜'를 다루지만 즉각적인 '다음은 무엇'은 다루지 않는다.
707 | A project manager and project team developing a new product are discussing which work methods and tools to use to build the deliverable. What should the result of this discussion be? | A detailed mitigation plan on the risks for each work method and the tools used | A technology roadmap for creating similar deliverables in the future with the same tools | An agreed-upon work method and tools that should fit the business need and project constraints | A consensus that everything will run as anticipated once the tools and work methods are identified |  | C | When a project manager and team discuss which work methods and tools to use for building the deliverable, the result should be an agreed-upon work method and tools that fit the business need and project constraints. Alignment with needs and constraints ensures practical applicability. A risk mitigation plan (A) is a subset outcome. A technology roadmap (B) is forward-looking, not project-specific. Consensus that everything will run as anticipated (D) is overly optimistic. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 새로운 제품을 개발하는 프로젝트 관리자와 프로젝트 팀이 산출물을 구축하기 위해 어떤 작업 방법과 도구를 사용할지 논의하고 있다. 이 논의의 결과는 무엇이어야 하는가? | 각 작업 방법과 사용되는 도구에 대한 리스크의 상세한 완화 계획 | 동일한 도구로 향후 유사한 산출물을 만들기 위한 기술 로드맵 | 비즈니스 요구와 프로젝트 제약에 맞는 합의된 작업 방법과 도구 | 도구와 작업 방법이 식별되면 모든 것이 예상대로 진행될 것이라는 합의 |  | C | 프로젝트 관리자와 팀이 산출물 구축을 위한 작업 방법과 도구를 논의할 때, 결과는 비즈니스 요구와 프로젝트 제약에 맞는 합의된 작업 방법과 도구여야 한다. 요구와 제약과의 정렬이 실용적 적용을 보장한다. 리스크 완화 계획(A)은 하위 결과물이다. 기술 로드맵(B)은 미래 지향적이며 프로젝트에 특화되지 않는다. 모든 것이 예상대로 진행될 것이라는 합의(D)는 지나치게 낙관적이다.
708 | A project team is transitioning to agile. During the sprint retrospective, a new member of the team proposed a more structured approach for capturing requirements that would improve clarity and reduce rework. Although the team members are happy to use it, changing the way business requirements are described requires agreement from an influential business manager. What should the project manager do? | Ask the team member to wait until the business is ready for the new approach. | Contact the project management office (PMO) and ask them to endorse the new approach. | Contact the business manager and discuss the benefits of the new approach. | Ask the team to describe the requirements using the more structured approach. |  | C | When a new team member proposes a structured requirements approach that needs an influential business manager's agreement, the project manager should contact the business manager and discuss the benefits of the new approach. Direct stakeholder engagement secures buy-in. Asking the team to wait (A) delays improvement. Contacting the PMO (B) adds unnecessary layers. Asking the team to just use it (D) ignores the need for business alignment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 팀이 애자일로 전환하고 있다. 스프린트 회고 중 새 팀원이 명확성을 개선하고 재작업을 줄일 수 있는 더 구조화된 요구사항 수집 접근 방식을 제안했다. 팀원들은 기꺼이 사용하지만, 비즈니스 요구사항 기술 방식을 변경하려면 영향력 있는 비즈니스 관리자의 동의가 필요하다. 프로젝트 관리자는 무엇을 해야 하는가? | 비즈니스가 새 접근 방식에 준비될 때까지 기다리라고 팀원에게 요청한다. | 프로젝트 관리 오피스(PMO)에 연락하여 새 접근 방식을 승인하도록 요청한다. | 비즈니스 관리자에게 연락하여 새 접근 방식의 이점을 논의한다. | 팀에게 더 구조화된 접근 방식으로 요구사항을 기술하도록 요청한다. |  | C | 새 팀원이 영향력 있는 비즈니스 관리자의 동의가 필요한 구조화된 요구사항 접근 방식을 제안할 때, 프로젝트 관리자는 비즈니스 관리자에게 연락하여 새 접근 방식의 이점을 논의해야 한다. 직접적인 이해관계자 참여가 동의를 확보한다. 기다리라고 요청(A)은 개선을 지연시킨다. PMO에 연락(B)은 불필요한 계층을 추가한다. 팀에게 그냥 사용하라고 요청(D)은 비즈니스 정렬 필요성을 무시한다.
709 | A customer's technical lead discussed a new feature with the project manager. The project manager believes the new feature will boost performance significantly and adds it as a high-priority item in the sprint backlog. At the end of the sprint, all of the planned stories were not completed because the new feature took more time. What should the project manager do next? | Agree with the project team to modify and delete some of the stories in the current sprint backlog | Obtain approval from the project team and add the new story to the product backlog | Negotiate with the scrum master before adding the new story to the sprint backlog | Receive an agreement from the product owner and add the new story to the product backlog |  | D | When a PM unilaterally added a new feature to the sprint backlog causing planned stories to remain incomplete, the project manager should receive agreement from the product owner and add the new story to the product backlog. The product owner owns backlog prioritization. Modifying and deleting current sprint stories (A) disrupts commitments. Obtaining team approval to add to the backlog (B) bypasses the product owner. Negotiating with the scrum master (C) misassigns backlog authority. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 고객의 기술 리드가 프로젝트 관리자와 새 기능을 논의했다. 프로젝트 관리자는 새 기능이 성능을 크게 향상시킬 것이라 믿고 스프린트 백로그에 높은 우선순위 항목으로 추가했다. 스프린트 종료 시 새 기능이 더 많은 시간이 소요되어 계획된 모든 스토리가 완료되지 않았다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 현재 스프린트 백로그의 일부 스토리를 수정 및 삭제하기로 프로젝트 팀과 합의한다. | 프로젝트 팀의 승인을 받아 새 스토리를 제품 백로그에 추가한다. | 새 스토리를 스프린트 백로그에 추가하기 전에 스크럼 마스터와 협상한다. | 제품 책임자의 동의를 받아 새 스토리를 제품 백로그에 추가한다. |  | D | PM이 일방적으로 새 기능을 스프린트 백로그에 추가하여 계획된 스토리가 미완료될 때, 프로젝트 관리자는 제품 책임자의 동의를 받아 새 스토리를 제품 백로그에 추가해야 한다. 제품 책임자가 백로그 우선순위를 소유한다. 현재 스프린트 스토리 수정 및 삭제(A)는 약속을 깨뜨린다. 팀 승인으로 백로그 추가(B)는 제품 책임자를 우회한다. 스크럼 마스터와 협상(C)은 백로그 권한을 잘못 부여한다.
710 | A project manager is leading an agile team. The daily standups and iteration meetings are currently facilitated by the product owner. A team member contacts the project manager and mentions that they are looking to improve their facilitation skills. How should the project manager respond to this request? | Add new elements to the project backlog to account for the training needs of the team member. | Suggest that the team member facilitate an upcoming iteration and review the outcomes in the iteration retrospective. | Engage their functional manager to determine if there is alignment to their development plan before agreeing. | Ask the team member to review the lessons learned on facilitation from previous projects. |  | B | When a team member wants to improve their facilitation skills, the project manager should suggest the team member facilitate an upcoming iteration and review the outcomes in the retrospective. Hands-on experience with feedback develops practical skills. Adding training to the backlog (A) formalizes unnecessarily. Engaging the functional manager (C) adds bureaucracy. Reviewing lessons learned (D) provides theory without practice. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Embed Quality | Manage Team | Traditional PM | 프로젝트 관리자가 애자일 팀을 이끌고 있다. 일일 스탠드업과 이터레이션 회의는 현재 제품 책임자가 진행하고 있다. 팀원이 프로젝트 관리자에게 연락하여 퍼실리테이션 기술을 향상시키고 싶다고 언급한다. 프로젝트 관리자는 이 요청에 어떻게 대응해야 하는가? | 팀원의 교육 요구를 반영하기 위해 프로젝트 백로그에 새 요소를 추가한다. | 팀원에게 다가오는 이터레이션을 진행하고 이터레이션 회고에서 결과를 검토하도록 제안한다. | 개발 계획과의 정렬을 확인하기 위해 기능 관리자를 참여시킨다. | 팀원에게 이전 프로젝트의 퍼실리테이션에 대한 교훈을 검토하도록 요청한다. |  | B | 팀원이 퍼실리테이션 기술을 향상시키고 싶을 때, 프로젝트 관리자는 팀원에게 다가오는 이터레이션을 진행하고 회고에서 결과를 검토하도록 제안해야 한다. 피드백이 수반되는 실습 경험이 실용적 기술을 개발한다. 백로그에 교육 추가(A)는 불필요하게 공식화한다. 기능 관리자 참여(C)는 관료주의를 추가한다. 교훈 검토(D)는 실습 없이 이론을 제공한다.
711 | During a meeting with a customer, it was determined that participants of the meeting had different draft versions of an important design document. What should the project manager do first to ensure that this does not happen again? | Investigate how draft versions were shared. | Ensure only the latest version is shared. | Ensure only the approved version is shared. | Revisit the communication process control. |  | D | When meeting participants had different draft versions of an important design document, the project manager should first revisit the communication process control. Reviewing the communication governance identifies and fixes the root cause of version confusion. Investigating how drafts were shared (A) is one step within process review. Sharing only the latest version (B) is a tactic, not a systemic fix. Sharing only the approved version (C) is a corrective action but does not address the underlying process. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 고객과의 회의에서 참가자들이 중요한 설계 문서의 서로 다른 초안 버전을 가지고 있는 것으로 확인되었다. 이러한 일이 다시 발생하지 않도록 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 초안 버전이 어떻게 공유되었는지 조사한다. | 최신 버전만 공유되도록 보장한다. | 승인된 버전만 공유되도록 보장한다. | 커뮤니케이션 프로세스 통제를 재검토한다. |  | D | 회의 참가자들이 중요한 설계 문서의 서로 다른 초안 버전을 가지고 있을 때, 프로젝트 관리자는 먼저 커뮤니케이션 프로세스 통제를 재검토해야 한다. 커뮤니케이션 거버넌스를 검토하면 버전 혼동의 근본 원인을 식별하고 수정할 수 있다. 초안 공유 방법 조사(A)는 프로세스 검토 내의 한 단계이다. 최신 버전만 공유(B)는 전술이지 시스템적 수정이 아니다. 승인된 버전만 공유(C)는 시정 조치이지만 근본적인 프로세스를 다루지 않는다.
712 | A project manager is leading a cross-departmental project that involves many stakeholders. During the project, the project manager observes that the stakeholders are diverse and have different expectations about how the project should be handled. This leads to frequent confusion and misunderstandings among the stakeholders. What should the project manager do to integrate the diverse stakeholder groups? | Develop a joint quality policy for the project and seek a commitment by all of the departments. | Advise the team members to focus on project work and avoid getting distracted by the stakeholders' disagreements. | Hold separate meetings with the individual stakeholders and escalate their concerns to the project sponsor. | Analyze the probability and impact of the risks linked with the situation and implement the proper response plan. |  | D | When diverse stakeholders have conflicting expectations causing confusion and misunderstandings, the project manager should analyze the probability and impact of the associated risks and implement a proper response plan. Treating stakeholder conflicts as risks enables structured identification, assessment, and mitigation of their impacts on the project. Developing a joint quality policy (A) addresses one narrow aspect. Advising team members to avoid stakeholder disagreements (B) ignores the problem. Holding separate meetings and escalating to the sponsor (C) fragments communication. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 많은 이해관계자가 참여하는 부서 간 프로젝트를 이끌고 있다. 프로젝트 중 이해관계자들이 다양하며 프로젝트 처리 방법에 대해 서로 다른 기대를 가지고 있음을 관찰한다. 이로 인해 이해관계자들 사이에 빈번한 혼란과 오해가 발생한다. 프로젝트 관리자는 다양한 이해관계자 그룹을 통합하기 위해 무엇을 해야 하는가? | 프로젝트를 위한 공동 품질 정책을 개발하고 모든 부서의 동의를 구한다. | 팀원들에게 프로젝트 작업에 집중하고 이해관계자의 의견 불일치에 방해받지 않도록 조언한다. | 개별 이해관계자와 별도 회의를 개최하고 그들의 우려를 프로젝트 스폰서에게 에스컬레이션한다. | 상황과 관련된 리스크의 확률과 영향을 분석하고 적절한 대응 계획을 구현한다. |  | D | 다양한 이해관계자가 상충하는 기대를 가지고 혼란과 오해를 야기할 때, 프로젝트 관리자는 관련 리스크의 확률과 영향을 분석하고 적절한 대응 계획을 구현해야 한다. 이해관계자 갈등을 리스크로 취급하면 프로젝트에 미치는 영향을 구조적으로 식별, 평가, 완화할 수 있다. 공동 품질 정책 개발(A)은 한 가지 좁은 측면을 다룬다. 팀에게 의견 불일치를 피하라고 조언(B)은 문제를 무시한다. 별도 회의 개최 및 스폰서에게 에스컬레이션(C)은 커뮤니케이션을 분절시킨다.
713 | A project manager is assigned to a project team midway through execution. Several dependencies are impacting the project, and the project manager feels the team is not adequately informed of the impacting changes. What should the project manager do first? | Convene an impact analysis meeting. | Consult the communications management plan. | Review the stakeholder register. | Escalate the issue to the product owner. |  | B | When joining a project midway and finding the team is inadequately informed of dependency changes, the project manager should first consult the communications management plan. This plan defines how project communications are structured and implemented, revealing gaps in the current approach. Convening an impact analysis meeting (A) addresses one issue but not the systemic communication problem. Reviewing the stakeholder register (C) identifies who but not how. Escalating to the product owner (D) is premature. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Scope | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 실행 중간에 프로젝트 팀에 배정되었다. 여러 의존성이 프로젝트에 영향을 미치고 있으며, 프로젝트 관리자는 팀이 영향을 미치는 변경 사항에 대해 적절히 통보받지 못하고 있다고 느낀다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 영향 분석 회의를 소집한다. | 커뮤니케이션 관리 계획을 참조한다. | 이해관계자 레지스터를 검토한다. | 이슈를 제품 책임자에게 에스컬레이션한다. |  | B | 프로젝트 중간에 합류하여 팀이 의존성 변경에 대해 적절히 통보받지 못하고 있음을 발견할 때, 프로젝트 관리자는 먼저 커뮤니케이션 관리 계획을 참조해야 한다. 이 계획은 프로젝트 커뮤니케이션이 어떻게 구조화되고 실행되는지를 정의하며, 현재 접근 방식의 격차를 드러낸다. 영향 분석 회의 소집(A)은 하나의 이슈를 다루지만 시스템적 커뮤니케이션 문제는 다루지 않는다. 이해관계자 레지스터 검토(C)는 '누구'를 식별하지만 '어떻게'는 아니다. 제품 책임자에게 에스컬레이션(D)은 시기상조이다.
714 | A project manager for a maintenance project has a contract that is renewed annually. The project started 6 years ago. After contract renewal this year, the auditors reported that this version of the contract violates a new law that was passed last year. What has happened in this situation? | The legal department has not disseminated the law correctly to all staff. | The stakeholder engagement plan has not been correctly implemented | The contract has not been appropriately reviewed by the project team | The project manager does not have enough knowledge on this legal matter |  | C | When an annually renewed contract violates a new law passed the previous year, the situation indicates the contract has not been appropriately reviewed by the project team. Contract reviews should include legal compliance checks. The legal department not disseminating correctly (A) shifts blame. The stakeholder engagement plan not being implemented (B) is unrelated. The PM lacking legal knowledge (D) does not excuse the failure to review. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 유지보수 프로젝트의 프로젝트 관리자가 매년 갱신되는 계약을 가지고 있다. 프로젝트는 6년 전에 시작되었다. 올해 계약 갱신 후 감사관이 이 버전의 계약이 작년에 통과된 새 법률을 위반한다고 보고했다. 이 상황에서 무엇이 발생한 것인가? | 법무 부서가 모든 직원에게 법률을 올바르게 배포하지 않았다. | 이해관계자 참여 계획이 올바르게 실행되지 않았다. | 계약이 프로젝트 팀에 의해 적절하게 검토되지 않았다. | 프로젝트 관리자가 이 법적 사안에 대해 충분한 지식이 없다. |  | C | 매년 갱신되는 계약이 전년에 통과된 새 법률을 위반할 때, 이 상황은 계약이 프로젝트 팀에 의해 적절하게 검토되지 않았음을 나타낸다. 계약 검토에는 법적 준수 확인이 포함되어야 한다. 법무 부서의 부적절한 배포(A)는 책임을 전가한다. 이해관계자 참여 계획 미실행(B)은 관련이 없다. PM의 법적 지식 부족(D)은 검토 실패를 면제하지 않는다.
715 | Early on during a sprint in an agile project, the project team begins deliberating two different approaches to implement a feature. The project manager is concerned that the team is spending too much time discussing this feature, because the team needs to cover other features in the sprint as well. How should the project manager approach the situation? | Intervene in the deliberation process and weigh in on which approach would be better to use. | Stop the deliberation process and ask the team to take a vote using the nominal group technique. | Deliberate with the team moving the item to the product backlog and taking up the next item in the list. | Allow the team to continue deliberating until the team reaches a consensus on the desired approach. |  | C | The correct answer is C. Deliberate with the team moving the item to the product backlog and taking up the next item in the list. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Scrum | Process | Manage Project Closure | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 애자일 프로젝트의 스프린트 초기에 프로젝트 팀이 기능 구현을 위한 두 가지 다른 접근 방식을 논의하기 시작한다. 프로젝트 관리자는 팀이 이 기능에 너무 많은 시간을 소비하고 있다고 우려하는데, 스프린트에서 다른 기능도 다루어야 하기 때문이다. 프로젝트 관리자는 이 상황에 어떻게 접근해야 하는가? | 논의 과정에 개입하여 어떤 접근 방식이 더 나은지 의견을 제시한다. | 논의 과정을 중단하고 팀에게 명목 집단 기법을 사용하여 투표하도록 요청한다. | 항목을 제품 백로그로 이동하고 목록의 다음 항목을 진행하는 것에 대해 팀과 논의한다. | 팀이 원하는 접근 방식에 대한 합의에 도달할 때까지 계속 논의하도록 허용한다. |  | C | 정답은 C이다. 항목을 제품 백로그로 이동하고 목록의 다음 항목을 진행하는 것에 대해 팀과 논의한다. 애자일 실천은 반복적 전달, 팀 권한 부여, 지속적 개선을 강조한다. PM은 협업을 촉진하고 장애물을 제거하며 팀이 효과적으로 가치를 전달할 수 있도록 보장해야 한다.
716 | A company has assigned a project manager to the initial task of determining the resources required for a new project. What should the project manager consult? | Company ' s project responsibility assignment matrix (RAM) | Company ' s resource calendars | Company ' s historical organizational project artifacts | Company ' s resource management plan |  | B | When determining resources required for a new project, the project manager should consult the company's resource calendars. Resource calendars specify the availability, capability, and skills of human resources and the availability of equipment and materials—essential information for resource planning. The responsibility assignment matrix (A) shows roles and responsibilities but not availability. Historical project artifacts (C) may not reflect current resource availability. The resource management plan (D) describes policies and procedures but not individual resource details. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Traditional PM | 회사가 새 프로젝트에 필요한 자원을 결정하는 초기 작업에 프로젝트 관리자를 배정했다. 프로젝트 관리자는 무엇을 참조해야 하는가? | 회사의 프로젝트 책임 배정 매트릭스(RAM) | 회사의 자원 캘린더 | 회사의 과거 조직 프로젝트 산출물 | 회사의 자원 관리 계획 |  | B | 새 프로젝트에 필요한 자원을 결정할 때, 프로젝트 관리자는 회사의 자원 캘린더를 참조해야 한다. 자원 캘린더는 인적 자원의 가용성, 역량, 기술과 장비 및 자재의 가용성을 명시한다—자원 계획에 필수적인 정보이다. 책임 배정 매트릭스(A)는 역할과 책임을 보여주지만 가용성은 아니다. 과거 프로젝트 산출물(C)은 현재 자원 가용성을 반영하지 않을 수 있다. 자원 관리 계획(D)은 정책과 절차를 기술하지만 개별 자원 세부 사항은 아니다.
717 | A project manager is finalizing the project charter and has invited the project sponsor and key stakeholders to confirm the project estimates. The project manager suggests adding a budget reserve to meet unforeseen risks, but the project sponsor disagrees. What should the project manager do? | Seek key stakeholders ' approval and finalize the budget with the reserve. | Explain to the project sponsor and key stakeholders the need to add the reserve and get their buy-in. | Agree with the project sponsor and finalize the budget without the reserve. | Demonstrate that risky projects are subject to change so adding reserves to the budget is a necessity. |  | B | When the project sponsor disagrees with adding a budget reserve for unforeseen risks, the project manager should explain the need and get their buy-in. Open communication and justification based on risk management principles builds shared understanding. Seeking key stakeholders' approval and bypassing the sponsor (A) is inappropriate. Agreeing without the reserve (C) ignores risk. Demonstrating that reserves are a necessity (D) is confrontational. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 프로젝트 헌장을 확정하고 있으며 프로젝트 스폰서와 주요 이해관계자를 초대하여 프로젝트 추정치를 확인하려 한다. 프로젝트 관리자가 예상치 못한 리스크를 충족하기 위해 예산 예비비를 추가할 것을 제안하지만 프로젝트 스폰서가 동의하지 않는다. 프로젝트 관리자는 무엇을 해야 하는가? | 주요 이해관계자의 승인을 받아 예비비를 포함한 예산을 확정한다. | 프로젝트 스폰서와 주요 이해관계자에게 예비비 추가 필요성을 설명하고 동의를 구한다. | 프로젝트 스폰서에 동의하고 예비비 없이 예산을 확정한다. | 위험한 프로젝트는 변경 대상이므로 예산에 예비비를 추가하는 것이 필수적임을 입증한다. |  | B | 프로젝트 스폰서가 예상치 못한 리스크를 위한 예산 예비비 추가에 동의하지 않을 때, 프로젝트 관리자는 필요성을 설명하고 동의를 구해야 한다. 리스크 관리 원칙에 기반한 공개적 소통과 정당화가 공유된 이해를 구축한다. 주요 이해관계자 승인을 구하고 스폰서를 우회(A)하는 것은 부적절하다. 예비비 없이 동의(C)하는 것은 리스크를 무시한다. 예비비가 필수적임을 입증(D)하는 것은 대립적이다.
718 | A project manager is working on the initial phases of a highly technical project that employs first-of-its-kind technology. Many of the key project stakeholders are unaware of the project objectives and their participation levels are poor. At every meeting, there are a lot of objections and queries raised that are taking the discussions to a different level, and a great deal of time is wasted. What should the project manager do? | Include the issue in the Issue log and escalate to senior management. | Request stakeholders who understand the technology. | Plan to conduct informal sessions with the stakeholders. | Recommend a change in technology to senior management. |  | C | When key stakeholders are unaware of project objectives, participate poorly, and raise objections that waste time, the project manager should plan informal sessions with stakeholders. Informal education builds understanding and buy-in. Logging and escalating (A) does not address awareness. Requesting tech-savvy stakeholders (B) avoids engagement. Recommending a technology change (D) compromises the project vision. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 최초 기술을 사용하는 고도로 기술적인 프로젝트의 초기 단계에서 작업하고 있다. 많은 주요 프로젝트 이해관계자가 프로젝트 목표를 인지하지 못하고 참여 수준이 저조하다. 매 회의마다 많은 반대 의견과 질의가 제기되어 토론이 다른 수준으로 이동하며 많은 시간이 낭비된다. 프로젝트 관리자는 무엇을 해야 하는가? | 이슈 로그에 이슈를 포함시키고 상급 경영진에게 에스컬레이션한다. | 기술을 이해하는 이해관계자를 요청한다. | 이해관계자와 비공식 세션을 계획하여 실시한다. | 상급 경영진에게 기술 변경을 권고한다. |  | C | 주요 이해관계자가 프로젝트 목표를 인지하지 못하고, 참여가 저조하며, 시간을 낭비하는 반대 의견을 제기할 때, 프로젝트 관리자는 이해관계자와 비공식 세션을 계획해야 한다. 비공식 교육은 이해와 동의를 구축한다. 이슈 로깅 및 에스컬레이션(A)은 인식을 다루지 않는다. 기술에 정통한 이해관계자 요청(B)은 참여를 회피한다. 기술 변경 권고(D)는 프로젝트 비전을 손상시킨다.
719 | A project team is working on a company restructure that involves team member rotation. There is a concern about how to execute the project within the schedule based on all of the new team members. What should the project manager do? | Ask the team to analyze the impact and develop a new schedule for a project change request. | Advise the new team that the schedule cannot be changed and encourage them to complete the project. | Discuss the issue with the project sponsor and advise that the project will probably be delayed. | Set up a team alignment session to discuss the remaining work and contract with the team. |  | D | When team member rotation due to company restructuring raises schedule concerns, the project manager should set up a team alignment session to discuss the remaining work and contract with the team. Alignment resets expectations, builds cohesion, and establishes shared understanding. Asking the team to develop a change request (A) is premature without alignment. Advising that the schedule cannot change (B) is rigid. Discussing delays with the sponsor (C) should follow team engagement. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 팀이 팀원 교체를 수반하는 회사 구조조정 작업을 하고 있다. 새로운 팀원들을 기반으로 일정 내에서 프로젝트를 실행하는 방법에 대한 우려가 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에게 영향을 분석하고 프로젝트 변경 요청을 위한 새 일정을 개발하도록 요청한다. | 새 팀에게 일정은 변경할 수 없으므로 프로젝트를 완료하도록 격려한다. | 프로젝트 스폰서와 이슈를 논의하고 프로젝트가 아마도 지연될 것이라고 조언한다. | 팀 정렬 세션을 설정하여 남은 작업을 논의하고 팀과 계약한다. |  | D | 회사 구조조정으로 인한 팀원 교체가 일정 우려를 야기할 때, 프로젝트 관리자는 팀 정렬 세션을 설정하여 남은 작업을 논의하고 팀과 계약해야 한다. 정렬은 기대를 재설정하고 결속력을 구축하며 공유된 이해를 확립한다. 팀에게 변경 요청을 개발하도록 요청(A)은 정렬 없이는 시기상조이다. 일정 변경이 불가능하다고 조언(B)은 경직적이다. 스폰서와 지연을 논의(C)는 팀 참여 후에 해야 한다.
720 | A project manager has recently taken over a project and notices that a client team member often halts progress due to a lack of understanding of some project elements. The former project manager gave the new project manager a complete list of people to communicate with, and this client team member is not on it. What should the project manager do? | Increase the project meeting frequency and duration to allow for the extra work required. | Speak with the client team member about the continuous delays during project meetings. | Submit a change request to cover extra hours associated with project meetings. | Update the communications matrix to ensure that client team member is included. |  | D | When a client team member frequently halts progress due to misunderstanding project elements and is not on the communications list, the project manager should update the communications matrix to ensure the client team member is included. Addressing the communication gap directly resolves the root cause of the delays. Increasing meeting frequency (A) adds overhead without targeting the issue. Speaking about delays during meetings (B) is confrontational. Submitting a change request for extra hours (C) does not address the underlying communication problem. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 최근 프로젝트를 인수했으며 고객 팀원이 일부 프로젝트 요소에 대한 이해 부족으로 자주 진행을 중단시키는 것을 발견했다. 이전 프로젝트 관리자가 새 프로젝트 관리자에게 소통할 사람들의 전체 목록을 제공했으나, 이 고객 팀원은 그 목록에 없다. 프로젝트 관리자는 무엇을 해야 하는가? | 추가 작업에 필요한 시간을 허용하기 위해 프로젝트 회의 빈도와 기간을 늘린다. | 프로젝트 회의 중 지속적인 지연에 대해 고객 팀원과 대화한다. | 프로젝트 회의와 관련된 추가 시간을 충당하기 위해 변경 요청을 제출한다. | 고객 팀원이 포함되도록 커뮤니케이션 매트릭스를 업데이트한다. |  | D | 고객 팀원이 프로젝트 요소에 대한 오해로 자주 진행을 중단시키고 커뮤니케이션 목록에 없을 때, 프로젝트 관리자는 해당 고객 팀원이 포함되도록 커뮤니케이션 매트릭스를 업데이트해야 한다. 커뮤니케이션 격차를 직접 해결하면 지연의 근본 원인을 해소한다. 회의 빈도 증가(A)는 이슈를 겨냥하지 않고 부담을 추가한다. 회의 중 지연에 대해 대화(B)는 대립적이다. 추가 시간을 위한 변경 요청 제출(C)은 근본적인 커뮤니케이션 문제를 다루지 않는다.
721 | In a multinational project, stakeholders are in different time zones. The project manager has regular project update meetings with the stakeholders. However, a group of stakeholders who has never attended project update meetings is complaining to the project sponsor that they know very little about the project. What should the project manager do? | Change the meeting time to the working time zones of the stakeholders who are complaining. | Record the regular project update meeting and share it with all stakeholders after the meeting is completed. | Discuss the issue with all stakeholders and work on a communications management plan to meet all stakeholder requirements. | Ensure that the stakeholders who are complaining are present for the next project update meetings. |  | C | When stakeholders who never attend meetings complain about lack of project knowledge, the project manager should discuss the issue with all stakeholders and work on a communications management plan to meet all requirements. A comprehensive plan addresses root causes by defining communication methods, formats, and frequency for each stakeholder group. Changing meeting times (A) may inconvenience other stakeholders. Recording and sharing meetings (B) is a good practice but does not address the root cause. Ensuring attendance at the next meeting (D) is short-term. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 다국적 프로젝트에서 이해관계자가 다른 시간대에 있다. 프로젝트 관리자는 이해관계자와 정기적인 프로젝트 업데이트 회의를 진행하고 있다. 그러나 프로젝트 업데이트 회의에 한 번도 참석하지 않은 이해관계자 그룹이 프로젝트 스폰서에게 프로젝트에 대해 거의 아는 것이 없다고 불만을 제기하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 불만을 제기하는 이해관계자의 근무 시간대에 맞게 회의 시간을 변경한다. | 정기 프로젝트 업데이트 회의를 녹화하고 회의 완료 후 모든 이해관계자와 공유한다. | 모든 이해관계자와 이슈를 논의하고 모든 이해관계자 요구사항을 충족하는 커뮤니케이션 관리 계획을 수립한다. | 불만을 제기하는 이해관계자가 다음 프로젝트 업데이트 회의에 참석하도록 보장한다. |  | C | 회의에 참석하지 않는 이해관계자가 프로젝트 지식 부족에 대해 불만을 제기할 때, 프로젝트 관리자는 모든 이해관계자와 이슈를 논의하고 모든 요구사항을 충족하는 커뮤니케이션 관리 계획을 수립해야 한다. 포괄적인 계획은 각 이해관계자 그룹에 대한 커뮤니케이션 방법, 형식, 빈도를 정의하여 근본 원인을 해결한다. 회의 시간 변경(A)은 다른 이해관계자에게 불편을 줄 수 있다. 회의 녹화 및 공유(B)는 좋은 실천이지만 근본 원인을 다루지 않는다. 다음 회의 참석 보장(D)은 단기적이다.
722 | A project manager is working on an agile project that is within the scope of a recently announced corporate audit. The project manager was appointed to attend the first meeting with the auditors scheduled for the following week. What should the project manager do to prepare for the audit? | Ask the development team to provide compliance information. | Review the project information. | Reserve story points for the next iteration if needed. | Ask for a waiver during the audit. |  | B | When an agile project falls under a corporate audit, the project manager should review the project information to prepare. Thorough review of plans, user stories, sprint reports, and documentation ensures readiness. Asking the development team for compliance information (A) shifts responsibility. Reserving story points for the next iteration (C) is unrelated to audit preparation. Asking for a waiver (D) avoids the audit obligation. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 최근 발표된 기업 감사 범위 내에 있는 애자일 프로젝트를 수행하고 있다. 프로젝트 관리자는 다음 주에 예정된 감사관과의 첫 회의에 참석하도록 지정되었다. 프로젝트 관리자는 감사를 준비하기 위해 무엇을 해야 하는가? | 개발 팀에게 규정 준수 정보를 제공하도록 요청한다. | 프로젝트 정보를 검토한다. | 필요한 경우 다음 이터레이션을 위한 스토리 포인트를 예약한다. | 감사 중 면제를 요청한다. |  | B | 애자일 프로젝트가 기업 감사 대상이 될 때, 프로젝트 관리자는 프로젝트 정보를 검토하여 준비해야 한다. 계획, 사용자 스토리, 스프린트 보고서, 문서의 철저한 검토가 준비를 보장한다. 개발 팀에게 규정 준수 정보를 요청(A)은 책임을 전가한다. 다음 이터레이션을 위한 스토리 포인트 예약(C)은 감사 준비와 무관하다. 면제 요청(D)은 감사 의무를 회피한다.
723 | During the third iteration of a project, the main sponsor retired from the company, and a new sponsor was appointed. The new sponsor is not familiar with the agile approach for project delivery, which leads them to request more control over the project team. What should the project manager do? | Review the sponsor ' s request with the project team during the next daily review meeting in order to provide the requested control. | Schedule a meeting with the new sponsor in order to explain the agile approach and how teams are supposed to be self-organized. | Review the sponsor ' s request with the project team during the next iteration review meeting in order to obtain a team decision. | Schedule an emergency meeting with the project team so they fulfill every request that comes from the sponsor. |  | B | When a new sponsor unfamiliar with agile requests more control over the team, the project manager should schedule a meeting to explain the agile approach and how teams are self-organized. Education builds understanding and trust. Reviewing the request at daily review (A) is inappropriate venue. Reviewing at iteration review (C) defers action. Scheduling an emergency meeting to comply with every request (D) undermines team autonomy. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 프로젝트의 세 번째 반복 중에 주요 스폰서가 회사를 퇴직하고 새로운 스폰서가 임명되었다. 새 스폰서는 프로젝트 전달을 위한 애자일 접근 방식에 익숙하지 않아 프로젝트 팀에 대한 더 많은 통제를 요청한다. 프로젝트 관리자는 무엇을 해야 하는가? | 요청된 통제를 제공하기 위해 다음 일일 검토 회의에서 프로젝트 팀과 스폰서의 요청을 검토한다. | 새 스폰서와 회의를 예약하여 애자일 접근 방식과 팀이 자기 조직화되어야 하는 방식을 설명한다. | 팀 결정을 얻기 위해 다음 반복 검토 회의에서 프로젝트 팀과 스폰서의 요청을 검토한다. | 스폰서로부터 오는 모든 요청을 충족시키기 위해 프로젝트 팀과 긴급 회의를 예약한다. |  | B | 애자일에 익숙하지 않은 새 스폰서가 팀에 대한 더 많은 통제를 요청할 때, 프로젝트 관리자는 애자일 접근 방식과 팀의 자기 조직화 방식을 설명하기 위해 회의를 예약해야 한다. 교육은 이해와 신뢰를 구축한다. 일일 검토에서 요청 검토(A)는 부적절한 장소이다. 반복 검토에서 검토(C)는 조치를 지연시킨다. 모든 요청을 준수하기 위한 긴급 회의 예약(D)은 팀 자율성을 약화시킨다.
724 | An agile team is brainstorming and prioritizing all of the risks according to severity. What should the team do about the identified risks? | Mitigate the risks that are applicable to the current and following iterations. | Acknowledge that the risks will be handled in the corresponding iteration. | Focus on the project deliverables rather than the documented risks. | Agree that any issue can be handled when it becomes a problem. |  | B | After brainstorming and prioritizing risks by severity, the agile team should acknowledge that risks will be handled in the corresponding iteration. Agile risk management is continuous and iterative—risks are incorporated into iteration planning and addressed as they become relevant, allowing for timely and proportionate responses. Mitigating all applicable risks immediately (A) may divert effort from current delivery priorities. Focusing only on deliverables and ignoring documented risks (C) is negligent. Agreeing to handle issues only when they become problems (D) is reactive and contradicts proactive risk management principles. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Develop a Common Vision | Finance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 애자일 팀이 심각도에 따라 모든 리스크를 브레인스토밍하고 우선순위를 매기고 있다. 팀은 식별된 리스크에 대해 무엇을 해야 하는가? | 현재 및 다음 반복에 해당하는 리스크를 완화한다. | 리스크가 해당 반복에서 처리될 것임을 인지한다. | 문서화된 리스크보다 프로젝트 산출물에 집중한다. | 모든 이슈가 문제가 될 때 처리할 수 있다는 데 동의한다. |  | B | 심각도별로 리스크를 브레인스토밍하고 우선순위를 매긴 후, 애자일 팀은 리스크가 해당 반복에서 처리될 것임을 인지해야 한다. 애자일 리스크 관리는 지속적이고 반복적이다—리스크는 반복 계획에 통합되고 관련성이 있을 때 처리되어 적시에 비례적인 대응이 가능하다. 해당하는 모든 리스크를 즉시 완화(A)하면 현재 전달 우선순위에서 노력이 분산될 수 있다. 산출물에만 집중하고 문서화된 리스크를 무시(C)하는 것은 태만하다. 이슈가 문제가 될 때만 처리하기로 동의(D)하는 것은 반응적이며 사전 예방적 리스크 관리 원칙에 반한다.
725 | A project team has completed many iterations without proper sizing of the stories. In some iterations the team sized some stories and completed them ahead of time. In other iterations the team sized the stories but was unable to complete the planned activities. What should the team do differently during planning for the next iteration? | Request the product owner and team facilitator to provide the size of the story | Collaborate with different teams and arrive at the size of the story | Continue multiple rounds of planning poker and arrive at the size of the story | Average the story points provided by each team member for a story |  | C | When story sizing has been inconsistent across iterations, the team should continue multiple rounds of planning poker to arrive at story sizes. Planning poker encourages discussion, reduces bias, and builds consensus through iterative estimation. Requesting the product owner and facilitator to provide sizes (A) bypasses team ownership. Collaborating with different teams (B) may introduce external inconsistency. Averaging story points (D) masks disagreements and ignores discussion value. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 팀이 스토리의 적절한 크기 산정 없이 많은 반복을 완료했다. 일부 반복에서는 스토리 크기를 산정하고 예정보다 일찍 완료했다. 다른 반복에서는 스토리 크기를 산정했지만 계획된 활동을 완료하지 못했다. 팀은 다음 반복 계획 중 무엇을 다르게 해야 하는가? | 제품 책임자와 팀 퍼실리테이터에게 스토리 크기를 제공하도록 요청한다. | 다른 팀과 협력하여 스토리 크기를 도출한다. | 여러 라운드의 플래닝 포커를 계속하여 스토리 크기를 도출한다. | 각 팀원이 제공한 스토리 포인트의 평균을 낸다. |  | C | 스토리 크기 산정이 반복 간 일관되지 않을 때, 팀은 여러 라운드의 플래닝 포커를 계속하여 스토리 크기를 도출해야 한다. 플래닝 포커는 토론을 장려하고, 편향을 줄이며, 반복적 추정을 통해 합의를 구축한다. 제품 책임자와 퍼실리테이터에게 크기 제공 요청(A)은 팀 소유권을 우회한다. 다른 팀과 협력(B)은 외부 불일치를 초래할 수 있다. 스토리 포인트 평균(D)은 의견 불일치를 감추고 토론의 가치를 무시한다.
726 | While finalizing project management plans, a customer provides the project manager with a new set of quality standards to which the final product must adhere. What should the project manager do to ensure a smooth delivery of the product? | Agree with the client on acceptance criteria. | Involve the client in risk identification. | Involve the client in a performance gap analysis. | Agree with the client on a new project charter. |  | A | When a customer provides new quality standards while project management plans are being finalized, the project manager should agree with the client on acceptance criteria. Clear acceptance criteria align deliverables with new standards. Involving the client in risk identification (B) is good but does not address quality standards directly. Performance gap analysis (C) is premature before defining criteria. Agreeing on a new charter (D) is excessive for a quality standards update. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Quality Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리 계획을 마무리하는 중에 고객이 프로젝트 관리자에게 최종 제품이 준수해야 할 새로운 품질 표준을 제공한다. 프로젝트 관리자는 제품의 원활한 전달을 보장하기 위해 무엇을 해야 하는가? | 고객과 인수 기준에 합의한다. | 고객을 리스크 식별에 참여시킨다. | 고객을 성과 격차 분석에 참여시킨다. | 고객과 새로운 프로젝트 헌장에 합의한다. |  | A | 프로젝트 관리 계획 마무리 중 고객이 새로운 품질 표준을 제공할 때, 프로젝트 관리자는 고객과 인수 기준에 합의해야 한다. 명확한 인수 기준은 산출물을 새 표준에 정렬시킨다. 리스크 식별에 고객 참여(B)는 좋지만 품질 표준을 직접 다루지 않는다. 성과 격차 분석(C)은 기준 정의 전에는 시기상조이다. 새 헌장 합의(D)는 품질 표준 업데이트에 대해 과도하다.
727 | A project manager joins a startup and finds that the chief technology officer (CTO) encourages the team to skip some procedures in the interest of speed. What should the project manager do to ensure that all the procedures are followed going forward? | Initiate a review of the procedures with the CTO and the team. | Develop new procedures that are easy for the team to follow. | Instruct the team that the procedures should always be followed. | Escalate the issue to the CEO and the board members. |  | A | When a CTO encourages the team to bypass procedures for speed, the PM should work to ensure proper adherence going forward by collaborating with the CTO to establish a shared understanding of why the processes exist and negotiating a balanced approach. The PM should advocate for necessary governance while being pragmatic about which processes add genuine value versus those that may be streamlined without compromising quality or compliance. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 스타트업에 합류하여 최고기술책임자(CTO)가 속도를 위해 일부 절차를 건너뛰도록 팀을 독려하는 것을 발견한다. 프로젝트 관리자는 앞으로 모든 절차가 준수되도록 무엇을 해야 하는가? | CTO 및 팀과 절차 검토를 시작한다. | 팀이 쉽게 따를 수 있는 새로운 절차를 개발한다. | 팀에게 절차를 항상 준수해야 한다고 지시한다. | 이슈를 CEO와 이사회에 에스컬레이션한다. |  | A | CTO가 속도를 위해 절차를 우회하도록 독려할 때, PM은 CTO와 협력하여 프로세스가 존재하는 이유에 대한 공유된 이해를 구축하고, 균형 잡힌 접근 방식을 협상하여 적절한 준수를 보장해야 한다. PM은 필요한 거버넌스를 옹호하면서 품질이나 준수를 저해하지 않고 간소화할 수 있는 프로세스에 대해 실용적이어야 한다.
728 | A project manager has been assigned to a new project. There is one team member who never says anything during meetings. After meetings, however, the team member sends detailed emails with very good suggestions that help with project execution. How should the project manager guide the team members? | Motivate the team members to speak freely in the meeting. | Review the communications management plan with the team members. | Remind the team members to follow the team charter. | Arrange a team-building activity to involve all team members. |  | A | The correct answer is A. Motivate the team members to speak freely in the meeting. Resource management includes ensuring team members have the necessary skills and support. The PM should identify gaps and address them through training, mentoring, or other appropriate measures. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 새로운 프로젝트에 배정되었다. 회의에서 절대 발언하지 않는 팀원이 한 명 있다. 그러나 회의 후에 이 팀원은 프로젝트 실행에 도움이 되는 매우 좋은 제안이 담긴 상세한 이메일을 보낸다. 프로젝트 관리자는 팀원들을 어떻게 안내해야 하는가? | 팀원들이 회의에서 자유롭게 발언하도록 동기를 부여한다. | 팀원들과 커뮤니케이션 관리 계획을 검토한다. | 팀원들에게 팀 헌장을 따르도록 상기시킨다. | 모든 팀원을 참여시키기 위해 팀 빌딩 활동을 준비한다. |  | A | 정답은 A이다. 팀원들이 회의에서 자유롭게 발언하도록 동기를 부여한다. 자원 관리는 팀원들이 필요한 기술과 지원을 갖추도록 보장하는 것을 포함한다. PM은 격차를 식별하고 교육, 멘토링 또는 기타 적절한 조치를 통해 해결해야 한다.
729 | A project sponsor has approved the project charter and business case. The project manager has reviewed the artifacts to initiate the project and is unclear if the intended benefits of the project align with the strategic objectives of the business. What should the project manager do first? | Start executing the project since leadership is responsible for the business strategy. | Meet with the project sponsor to better understand the strategic benefits of the project. | Conduct qualitative and quantitative risk analysis and record the results in the risk register. | Propose an updated business case and project charter that are more aligned with the business strategy. |  | B | When the project manager is unclear whether the intended benefits align with business strategy, the first action should be to meet with the project sponsor to better understand the strategic benefits of the project. The sponsor provides the authoritative perspective on how the project supports organizational objectives. Proceeding with execution (A) without this understanding risks delivering a project that does not serve the business. Conducting risk analysis (C) addresses uncertainty but does not resolve the strategic alignment question. Proposing an updated business case and charter (D) is premature before first understanding the current strategic intent from the sponsor. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Integration & General PM | Business Environment | Define and Establish Governance | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 스폰서가 프로젝트 헌장과 비즈니스 케이스를 승인했다. 프로젝트 관리자가 프로젝트를 착수하기 위해 산출물을 검토했으며, 프로젝트의 의도된 혜택이 비즈니스의 전략적 목표와 정렬되는지 불명확하다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 리더십이 비즈니스 전략에 책임이 있으므로 프로젝트 실행을 시작한다. | 프로젝트의 전략적 혜택을 더 잘 이해하기 위해 프로젝트 스폰서와 만난다. | 정성적 및 정량적 리스크 분석을 수행하고 결과를 리스크 레지스터에 기록한다. | 비즈니스 전략에 더 정렬된 업데이트된 비즈니스 케이스와 프로젝트 헌장을 제안한다. |  | B | 프로젝트 관리자가 의도된 혜택이 비즈니스 전략과 정렬되는지 불명확할 때, 첫 번째 조치는 프로젝트의 전략적 혜택을 더 잘 이해하기 위해 프로젝트 스폰서와 만나는 것이다. 스폰서는 프로젝트가 조직 목표를 어떻게 지원하는지에 대한 권위 있는 관점을 제공한다. 이해 없이 실행 진행(A)은 비즈니스에 도움이 되지 않는 프로젝트를 전달할 위험이 있다. 리스크 분석 수행(C)은 불확실성을 다루지만 전략적 정렬 질문을 해결하지 않는다. 업데이트된 비즈니스 케이스와 헌장 제안(D)은 먼저 스폰서로부터 현재 전략적 의도를 이해하기 전에는 시기상조이다.
730 | A project manager leads a project that implements a new process throughout the organization. The rollout is done in stages and the project manager planned a demonstration for the pilot business units. A manager from a business unit that is scheduled for a later date asks to be invited to the sprint review. What should the project manager do? | Organize a special demonstration for the manager only. | Ask the manager to get an approval from the product owner. | Invite the manager to the scheduled sprint review. | Refer the sprint review request to the project sponsor. |  | C | When a manager from a later-phase business unit asks to attend the sprint review, the project manager should invite them. Sprint reviews promote transparency and early feedback from stakeholders. Organizing a special demonstration (A) adds unnecessary overhead. Asking for PO approval (B) adds gatekeeping. Referring to the sponsor (D) escalates unnecessarily. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 조직 전체에 새로운 프로세스를 구현하는 프로젝트를 이끌고 있다. 롤아웃은 단계적으로 수행되며 프로젝트 관리자는 파일럿 비즈니스 유닛을 위한 시연을 계획했다. 나중 날짜로 예정된 비즈니스 유닛의 관리자가 스프린트 리뷰에 초대받기를 요청한다. 프로젝트 관리자는 무엇을 해야 하는가? | 관리자만을 위한 특별 시연을 조직한다. | 관리자에게 제품 책임자의 승인을 받도록 요청한다. | 관리자를 예정된 스프린트 리뷰에 초대한다. | 스프린트 리뷰 요청을 프로젝트 스폰서에게 전달한다. |  | C | 나중 단계의 비즈니스 유닛 관리자가 스프린트 리뷰 참석을 요청할 때, 프로젝트 관리자는 초대해야 한다. 스프린트 리뷰는 이해관계자의 투명성과 조기 피드백을 촉진한다. 특별 시연 조직(A)은 불필요한 부담을 추가한다. PO 승인 요청(B)은 게이트키핑을 추가한다. 스폰서에게 전달(D)은 불필요하게 에스컬레이션한다.
731 | A project team is implementing a hosted system for a third party. Just before going live, the customer asks the project team to include additional functionality. The project team identified risks to the delivery date and informed the project manager that some of the requested functions are in conflict with the agreed scope. What should the project manager do? | Discuss with the customer the risks identified and team ' s concerns. | Ask the team to deliver the functionality on the agreed go-live date. | Ask the customer to go live and add the new functionality in the backlog. | Discuss with the team, estimate the effort, and raise a change request. |  | D | When a customer requests additional functionality just before go-live that conflicts with the agreed scope and introduces delivery risks, the project manager should discuss with the team, estimate the effort, and raise a change request. This structured approach ensures changes are assessed for impact on scope, schedule, and cost before being approved through the change control board. Discussing risks with the customer (A) is important but incomplete without a formal change request. Asking the team to deliver on the original go-live date (B) ignores the scope conflict. Asking the customer to go live and adding functionality to the backlog (C) defers the issue without proper change evaluation. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Risk & Issue Management | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 제3자를 위해 호스팅 시스템을 구현하고 있다. 라이브 직전에 고객이 프로젝트 팀에게 추가 기능을 포함해 달라고 요청한다. 프로젝트 팀은 납기 일정에 대한 리스크를 식별하고 요청된 기능 중 일부가 합의된 범위와 충돌한다고 프로젝트 관리자에게 알렸다. 프로젝트 관리자는 무엇을 해야 하는가? | 고객에게 식별된 리스크와 팀의 우려를 논의한다. | 팀에게 합의된 라이브 일정에 맞춰 기능을 전달하도록 요청한다. | 고객에게 라이브하고 새 기능을 백로그에 추가하도록 요청한다. | 팀과 논의하고 노력을 추정하며 변경 요청을 제기한다. |  | D | 라이브 직전에 고객이 합의된 범위와 충돌하는 추가 기능을 요청하고 납기 리스크가 있을 때, 프로젝트 관리자는 팀과 논의하고 노력을 추정하며 변경 요청을 제기해야 한다. 이 구조화된 접근 방식은 변경 통제 위원회를 통해 승인되기 전에 범위, 일정, 비용에 대한 영향을 평가하도록 보장한다. 고객에게 리스크 논의(A)는 중요하지만 공식 변경 요청 없이는 불완전하다. 원래 라이브 일정에 맞춰 전달 요청(B)은 범위 충돌을 무시한다. 라이브하고 백로그에 추가 요청(C)은 적절한 변경 평가 없이 이슈를 미룬다.
732 | A project manager is managing a government project that targets the development of small businesses in remote towns. The project team is having difficulty conducting entrepreneurship training in some of the targeted towns because the local municipal governments will not authorize the training. As a result of the delay, project implementation is at risk. What is a probable reason for this? | The project did not fully engage the project sponsor. | The project should have representatives in all the remote towns. | The project did not identify and engage the correct stakeholders. | The project should have constructed training centers in the remote towns. |  | C | The probable reason the project is facing difficulty with municipal authorization is that the project did not identify and engage the correct stakeholders. Local municipal governments hold the authority to approve or reject training activities in their towns, making them key stakeholders whose support is essential. The project manager should have identified them early and engaged them to obtain their cooperation. Failing to engage the sponsor (A) is less directly related to the local authorization issue. Having representatives in remote towns (B) is logistically useful but does not address the governance and authorization gap. Constructing training centers (D) is a resource-intensive solution that does not resolve the stakeholder engagement failure. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | 프로젝트 관리자가 외진 마을의 소기업 발전을 목표로 하는 정부 프로젝트를 관리하고 있다. 프로젝트 팀이 일부 대상 마을에서 기업가 교육을 실시하는 데 어려움을 겪고 있는데, 지방 자치 정부가 교육을 허가하지 않기 때문이다. 지연의 결과로 프로젝트 구현이 위험에 처해 있다. 이에 대한 가능한 이유는 무엇인가? | 프로젝트가 프로젝트 스폰서를 충분히 참여시키지 못했다. | 프로젝트가 모든 외진 마을에 대표자를 두어야 한다. | 프로젝트가 올바른 이해관계자를 식별하고 참여시키지 못했다. | 프로젝트가 외진 마을에 교육 센터를 건설했어야 한다. |  | C | 프로젝트가 지방 자치 정부 허가에 어려움을 겪는 가능한 이유는 올바른 이해관계자를 식별하고 참여시키지 못했기 때문이다. 지방 자치 정부는 마을에서 교육 활동을 승인하거나 거부할 권한을 가지고 있어 협력이 필수적인 핵심 이해관계자이다. 프로젝트 관리자는 조기에 이들을 식별하고 참여시켜 협조를 얻었어야 한다. 스폰서 참여 실패(A)는 지역 허가 이슈와 직접 관련이 적다. 외진 마을에 대표자 두기(B)는 물류적으로 유용하지만 거버넌스와 허가 격차를 해결하지 않는다. 교육 센터 건설(D)은 이해관계자 참여 실패를 해결하지 못하는 자원 집약적 해결책이다.
733 | During a project's execution phase, the team faced a setback in one of the deliveries and was asked to come up with a new plan. All team members joined a meeting to address the issue and, after a while, the project manager observed that two members of the team were just agreeing with anything that was proposed even though they were opposed to the outcome. What conflict resolution style were the team members adopting? | Combative style | Accommodative style | Collaborative style | Avoidant style |  | B | When team members agree with proposals despite internally opposing the outcome, they are adopting the accommodative (smoothing/yielding) conflict resolution style. Accommodating means giving in to maintain harmony at the cost of one's own interests. Combative (A) involves pursuing one's concerns aggressively. Collaborative (C) seeks win-win solutions. Avoidant (D) involves withdrawing from conflict entirely. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 실행 단계에서 팀이 산출물 중 하나에 차질이 생겨 새로운 계획을 수립하도록 요청받았다. 모든 팀원이 회의에 참석하여 이슈를 논의했고, 잠시 후 프로젝트 관리자는 두 명의 팀원이 결과에 반대함에도 불구하고 제안된 모든 것에 동의하고 있음을 관찰했다. 팀원들이 채택하고 있는 갈등 해결 방식은 무엇인가? | 공격적 방식 | 수용적 방식 | 협력적 방식 | 회피적 방식 |  | B | 팀원들이 내부적으로 결과에 반대하면서도 제안에 동의할 때, 이는 수용적(원활화/양보) 갈등 해결 방식을 채택하고 있는 것이다. 수용은 자신의 이익을 희생하며 조화를 유지하기 위해 양보하는 것을 의미한다. 공격적(A)은 자신의 관심사를 공격적으로 추구한다. 협력적(C)은 상생 해결책을 모색한다. 회피적(D)은 갈등에서 완전히 철수하는 것이다.
734 | Phase 1 of a project has been implemented and moved into post-production support, while phase 2 development has started. During phase 1 closeout, team members are asked by the product manager to work on the phase 1 backlog items that are not in the approved requirements document. The team members complain that no one is in charge of production issues. What two actions should the project manager take? (Choose 2) | Discuss the backlog items with the product manager to determine what should be included as part of phase 2, and communicate the findings to the team. | Set up time to review the approved production support plan and associated processes with the business and team members. | Reopen phase 1 to allow time for team members to wrap up issue resolutions for phase 1, and submit a change request to add backlog items to phase 2. | Review production support processes with the team, and request that the product manager take control over support issues going forward. | Work with the business and product manager to determine any backlog items that should be reprioritized for inclusion in the next phase. | B, D | During a phase transition where team members are asked to work on unapproved backlog items and production support ownership is unclear, the project manager should take two actions: set up time to review the approved production support plan and associated processes with the business and team members (B), and review production support processes with the team and request that the product manager take control over support issues going forward (D). Reviewing the approved plan clarifies roles and responsibilities, while having the product manager take control establishes clear ownership for support. Discussing backlog items with the product manager alone (A) does not address the support ownership gap. Reprioritizing backlog items (E) is useful but secondary to establishing governance. Reopening phase 1 (C) is excessive and disruptive. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Scope | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트 1단계가 구현되어 사후 프로덕션 지원으로 전환되었고, 2단계 개발이 시작되었다. 1단계 종료 중에 제품 관리자가 팀원들에게 승인된 요구사항 문서에 없는 1단계 백로그 항목 작업을 요청했다. 팀원들은 프로덕션 이슈를 담당하는 사람이 없다고 불만을 제기한다. 프로젝트 관리자는 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 제품 관리자와 백로그 항목을 논의하여 2단계에 포함될 사항을 결정하고 결과를 팀에 전달한다. | 비즈니스 및 팀원들과 승인된 프로덕션 지원 계획 및 관련 프로세스를 검토할 시간을 설정한다. | 팀원들이 1단계 이슈 해결을 마무리할 시간을 확보하기 위해 1단계를 재개하고, 백로그 항목을 2단계에 추가하는 변경 요청을 제출한다. | 팀과 프로덕션 지원 프로세스를 검토하고, 향후 제품 관리자가 지원 이슈를 통제하도록 요청한다. | 비즈니스 및 제품 관리자와 협력하여 다음 단계에 포함하기 위해 재우선순위화해야 할 백로그 항목을 결정한다. | B, D | 단계 전환 중 팀원들이 미승인 백로그 항목 작업을 요청받고 프로덕션 지원 소유권이 불명확할 때, PM은 두 가지 조치를 취해야 한다: 비즈니스 및 팀원과 승인된 프로덕션 지원 계획 및 관련 프로세스를 검토하고(B), 팀과 프로덕션 지원 프로세스를 검토하고 제품 관리자에게 향후 지원 이슈에 대한 통제를 요청한다(D). 승인된 계획 검토는 역할과 책임을 명확히 하고, 제품 관리자에게 통제를 맡기는 것은 지원에 대한 명확한 소유권을 수립한다. 제품 관리자에게만 백로그 항목 논의(A)는 지원 소유권 격차를 해결하지 않는다. 백로그 항목 재우선순위화(E)는 유용하지만 거버넌스 수립보다 부차적이다. 1단계 재개(C)는 과도하고 파괴적이다.
735 | A project manager is working on an agile project. The organization does not have experience with agile delivery. During business case development, the new product owner asks when project deliverables are considered complete. How should the project manager respond? | At the end of each sprint, the outcome is considered ready for production | The scrum master will approve the user stories that are complete | Items are considered complete when they satisfy the definition of done (DoD) | Backlog items are considered complete when the product owner approves the demo |  | C | In agile, deliverables are considered complete when they satisfy the definition of done (DoD). The DoD is an explicit checklist of quality and completeness criteria ensuring increments are potentially shippable and objectively verifiable. Being ready for production (A) depends on release policies and may not always apply. Scrum master approval (B) is not the scrum master's role. Product owner demo approval (D) is important for acceptance but insufficient without the DoD's internal quality checks. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 애자일 프로젝트에 참여하고 있다. 조직은 애자일 전달 경험이 없다. 비즈니스 케이스 개발 중 새로운 제품 책임자가 프로젝트 산출물이 언제 완료된 것으로 간주되는지 묻는다. 프로젝트 관리자는 어떻게 응답해야 하는가? | 각 스프린트 끝에 결과물이 프로덕션 준비 완료로 간주된다. | 스크럼 마스터가 완료된 사용자 스토리를 승인한다. | 항목은 완료 정의(DoD)를 충족할 때 완료된 것으로 간주된다. | 백로그 항목은 제품 책임자가 데모를 승인할 때 완료된 것으로 간주된다. |  | C | 애자일에서 산출물은 완료 정의(DoD)를 충족할 때 완료된 것으로 간주된다. DoD는 증분이 잠재적으로 출하 가능하고 객관적으로 검증 가능하도록 보장하는 품질 및 완전성 기준의 명시적 체크리스트이다. 프로덕션 준비 완료(A)는 릴리스 정책에 따라 다르며 항상 적용되지 않을 수 있다. 스크럼 마스터 승인(B)은 스크럼 마스터의 역할이 아니다. 제품 책임자 데모 승인(D)은 수락에 중요하지만 DoD의 내부 품질 검사 없이는 불충분하다.
736 | Eight people have been working on a project for an extended period of time. The scope has changed significantly and the product owner has been replaced multiple times. The team members are feeling disassociated from the project. What should the project manager do to ensure team alignment with the goals? | Facilitate a discussion of the vision for the project. | Email the team a detailed outline of the business requirements. | Review the project charter with the team. | Ask the new product owner to explain the importance of the project. |  | A | When eight team members feel disassociated after significant scope changes and multiple product owner replacements, the project manager should facilitate a discussion of the vision for the project. Collaborative vision alignment re-engages the team. Emailing business requirements (B) is one-directional. Reviewing the project charter (C) provides structure but not engagement. Asking the new PO to explain importance (D) puts the burden on one person. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Scope | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 8명이 장기간 프로젝트에 참여해 왔다. 범위가 크게 변경되었고 제품 책임자가 여러 번 교체되었다. 팀원들이 프로젝트와의 연결감이 떨어지고 있다. 프로젝트 관리자는 팀의 목표 정렬을 보장하기 위해 무엇을 해야 하는가? | 프로젝트 비전에 대한 토론을 촉진한다. | 팀에게 비즈니스 요구사항의 상세 개요를 이메일로 보낸다. | 팀과 프로젝트 헌장을 검토한다. | 새 제품 책임자에게 프로젝트의 중요성을 설명하도록 요청한다. |  | A | 8명의 팀원이 상당한 범위 변경과 여러 차례의 제품 책임자 교체 후 연결감이 떨어질 때, PM은 프로젝트 비전에 대한 토론을 촉진해야 한다. 협력적 비전 정렬이 팀을 다시 참여시킨다. 비즈니스 요구사항 이메일 발송(B)은 일방적이다. 프로젝트 헌장 검토(C)는 구조를 제공하지만 참여를 이끌어내지 못한다. 새 PO에게 중요성 설명 요청(D)은 한 사람에게 부담을 지운다.
737 | A project manager has just taken over a project that is halfway through its schedule. In a brief meeting with the client's key project team, the project manager receives several requests from a specific client team member who was not at the project team meeting. The requests for information seem to be for trivial information that was previously submitted in project documents. What should the project manager do first? | Inform the client project manager that they are sending too many trivial requests. | Update the project risk register to include potential delays in answering these requests. | Send an email to the client team member explaining that they have the information already. | Review the stakeholder register to gain insight into the expectations of that team member. |  | D | When a client team member who was absent from the project meeting makes trivial information requests for data already in project documents, the project manager should first review the stakeholder register. The register contains information about stakeholder expectations, interests, and influence, helping the PM understand the underlying reasons for the behavior—such as low engagement, lack of trust, or a hidden agenda—and plan appropriate management strategies. Informing the client PM about trivial requests (A) may create conflict. Updating the risk register (B) treats this as a risk rather than a stakeholder management issue. Sending an email explaining the information is available (C) is dismissive and may damage the relationship. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 일정의 절반이 지난 프로젝트를 인수했다. 고객의 핵심 프로젝트 팀과의 간단한 미팅에서, 프로젝트 팀 미팅에 참석하지 않았던 특정 고객 팀원으로부터 여러 요청을 받는다. 정보 요청은 이전에 프로젝트 문서로 제출된 사소한 정보에 대한 것이다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 고객 프로젝트 관리자에게 너무 많은 사소한 요청을 보내고 있다고 알린다. | 이러한 요청에 대한 답변 지연의 잠재적 위험을 프로젝트 리스크 레지스터에 업데이트한다. | 고객 팀원에게 이미 해당 정보가 있다고 설명하는 이메일을 보낸다. | 해당 팀원의 기대를 파악하기 위해 이해관계자 레지스터를 검토한다. |  | D | 프로젝트 미팅에 불참한 고객 팀원이 이미 프로젝트 문서에 있는 사소한 정보를 요청할 때, PM은 먼저 이해관계자 레지스터를 검토해야 한다. 레지스터에는 이해관계자의 기대, 관심사, 영향력에 대한 정보가 포함되어 있어 PM이 행동의 근본적 이유를 이해하고 적절한 관리 전략을 계획하는 데 도움이 된다. 고객 PM에게 사소한 요청에 대해 알리기(A)는 갈등을 야기할 수 있다. 리스크 레지스터 업데이트(B)는 이해관계자 관리 이슈가 아닌 리스크로 취급한다. 정보가 이미 있다는 이메일 발송(C)은 무시하는 태도로 관계를 손상시킬 수 있다.
738 | An events company is planning their annual event for a retirement fund. The organization has run the event planning using agile approaches for the last 3 years. During the initiation phase, while assessing possible risks and improvements for the event, the project manager uses previous event feedback to assist in developing the risk register. Which ceremony should be used in developing this register? | Sprint report | Project status report | Retrospective results | Sprint plans |  | C | When using agile event planning and developing a risk register from previous event feedback, the ceremony to use is retrospective results. Retrospectives reflect on what went well, what could improve, and what actions to take—directly providing inputs for risk identification and opportunity assessment. Sprint reports (A) summarize delivery metrics but not reflective lessons. Project status reports (B) provide current state but not improvement insights. Sprint plans (D) outline upcoming work, not historical reflection. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 이벤트 회사가 퇴직 기금을 위한 연례 이벤트를 계획하고 있다. 조직은 지난 3년간 이벤트 기획에 애자일 접근 방식을 사용해 왔다. 착수 단계에서 이벤트의 가능한 리스크와 개선 사항을 평가하는 동안, 프로젝트 관리자는 리스크 레지스터 개발을 돕기 위해 이전 이벤트 피드백을 사용한다. 이 레지스터 개발에 어떤 세레모니를 사용해야 하는가? | 스프린트 보고서 | 프로젝트 상태 보고서 | 회고(레트로스펙티브) 결과 | 스프린트 계획 |  | C | 애자일 이벤트 기획에서 이전 피드백으로 리스크 레지스터를 개발할 때 사용할 세레모니는 회고(레트로스펙티브) 결과이다. 회고는 잘된 점, 개선할 점, 취해야 할 조치를 돌아보며 리스크 식별과 기회 평가에 직접적인 입력을 제공한다. 스프린트 보고서(A)는 전달 지표를 요약하지만 반성적 교훈은 아니다. 프로젝트 상태 보고서(B)는 현재 상태를 제공하지만 개선 통찰력은 아니다. 스프린트 계획(D)은 향후 작업을 개요하지 과거 반성은 아니다.
739 | A project manager has received an updated earned value analysis report. The following are the key findings from the report: Budget at completion = US$1 million, Earned value = US$0.7 million, Actual cost = US$0.75 million, Cost performance index = 0.933. Based on this information, what should the project manager conclude about project performance? | The project will be easier to complete than planned | The project will not be completed as planned | The project will be difficult to complete as planned. | The project will be completed exactly as planned |  | C | With a CPI of 0.933, the project is spending more than planned per unit of work delivered, indicating it is over budget. The project will be difficult to complete as planned unless corrective actions improve cost performance. Being easier to complete (A) is incorrect since CPI < 1. Not being completed as planned (B) is too strong a conclusion without further analysis. Being completed exactly as planned (D) contradicts the CPI data. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 관리자가 업데이트된 획득가치 분석 보고서를 받았다. 보고서의 주요 결과는 다음과 같다: 완료 시 예산(BAC) = 100만 달러, 획득가치(EV) = 70만 달러, 실제 비용(AC) = 75만 달러, 비용 성과 지수(CPI) = 0.933. 이 정보에 기반하여 프로젝트 관리자는 프로젝트 성과에 대해 어떤 결론을 내려야 하는가? | 프로젝트는 계획보다 쉽게 완료될 것이다. | 프로젝트는 계획대로 완료되지 않을 것이다. | 프로젝트는 계획대로 완료하기 어려울 것이다. | 프로젝트는 정확히 계획대로 완료될 것이다. |  | C | CPI가 0.933이면, 프로젝트는 작업 단위당 계획보다 더 많이 지출하고 있으며 예산을 초과하고 있음을 나타낸다. 시정 조치가 비용 성과를 개선하지 않으면 계획대로 완료하기 어려울 것이다. 더 쉽게 완료(A)는 CPI < 1이므로 틀리다. 계획대로 완료되지 않음(B)은 추가 분석 없이 너무 강한 결론이다. 정확히 계획대로 완료(D)는 CPI 데이터와 모순된다.
740 | A project manager is working on a construction project. The company owner asks the project manager to provide cost estimates for the new decoration project within 4 hours. How will the project manager be able to complete this task? | Contact a subject matter expert (SME) for advice and consultation. | Tell the owner that a rough order of magnitude will be provided. | Tell the owner that the task requires more time and expertise | Call a meeting with the project team to identify the most appropriate approach. |  | A | When asked to provide cost estimates for a new decoration project within 4 hours, the project manager should contact a subject matter expert (SME) for advice and consultation. Expert input enables quick, reliable estimates. Telling the owner a rough order of magnitude will be provided (B) manages expectations but may not leverage available expertise. Telling the owner the task requires more time (C) does not attempt to meet the deadline. Calling a team meeting (D) may take more time than available. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 관리자가 건설 프로젝트에 참여하고 있다. 회사 소유주가 4시간 이내에 새로운 인테리어 프로젝트의 비용 추정치를 제공해 달라고 요청한다. 프로젝트 관리자는 이 작업을 어떻게 완료할 수 있는가? | 주제 전문가(SME)에게 조언과 상담을 요청한다. | 소유주에게 개략적 규모 추정치를 제공할 것이라고 말한다. | 소유주에게 이 작업에 더 많은 시간과 전문성이 필요하다고 말한다. | 프로젝트 팀과 회의를 소집하여 가장 적절한 접근 방식을 식별한다. |  | A | 4시간 이내에 새 인테리어 프로젝트의 비용 추정치를 요청받을 때, PM은 SME에게 조언과 상담을 요청해야 한다. 전문가 의견은 빠르고 신뢰할 수 있는 추정을 가능하게 한다. 개략적 규모 추정치 제공(B)은 기대를 관리하지만 가용 전문성을 활용하지 않을 수 있다. 더 많은 시간 필요(C)는 기한을 맞추려는 시도를 하지 않는다. 팀 회의 소집(D)은 가용 시간보다 더 걸릴 수 있다.
741 | The rollout of a new finance system is in the execution phase. A number of issues have surfaced in the last month that are slowing the project down. A new project sponsor has recently started with the company but has not had time to meet the project manager. The project is at the point where the issues are significantly impacting delivery of the project. How should the project manager alert the new project sponsor about these concerns? | Complete a risk analysis outlining the delays and impacts, and email a copy of the risk register, urging the project sponsor to respond | Send an email to the project sponsor summarizing the project status and key concerns, and request an immediate face-to-face meeting to discuss them | Continue emailing updated project status reports highlighting the key risks andissues, and wait for the project sponsor to request a meeting | Send an email invitation to the project sponsor to attend all of the project team ' s weekly meetings, and hope the sponsor will find time to attend |  | B | When project issues are significantly impacting delivery and the new project sponsor has not yet met the PM, the project manager should send an email summarizing the project status and key concerns and request an immediate face-to-face meeting. This proactive approach communicates urgency, provides essential context, and establishes a direct connection with the sponsor. Inviting the sponsor to weekly team meetings (D) is passive and hopes the sponsor finds time. Continuing to email status reports and waiting (C) is ineffective and does not convey the severity of the situation. Completing a risk analysis and emailing the risk register (A) provides data but lacks the personal engagement needed to establish the relationship and discuss solutions. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 새로운 재무 시스템의 롤아웃이 실행 단계에 있다. 지난 한 달간 프로젝트를 지연시키는 여러 이슈가 발생했다. 새로운 프로젝트 스폰서가 최근 회사에 합류했지만 아직 프로젝트 관리자를 만날 시간이 없었다. 프로젝트는 이슈가 전달에 심각한 영향을 미치는 지점에 있다. 프로젝트 관리자는 이러한 우려에 대해 새 프로젝트 스폰서에게 어떻게 알려야 하는가? | 지연과 영향을 설명하는 리스크 분석을 완료하고 리스크 레지스터 사본을 이메일로 보내며 프로젝트 스폰서에게 응답을 촉구한다. | 프로젝트 상태와 주요 우려 사항을 요약한 이메일을 스폰서에게 보내고, 이를 논의하기 위한 즉각적인 대면 미팅을 요청한다. | 핵심 리스크와 이슈를 강조하는 업데이트된 프로젝트 상태 보고서를 계속 이메일로 보내고 스폰서가 미팅을 요청할 때까지 기다린다. | 프로젝트 팀의 주간 회의에 참석하도록 스폰서에게 이메일 초대를 보내고 스폰서가 시간을 내기를 바란다. |  | B | 프로젝트 이슈가 전달에 심각한 영향을 미치고 새 스폰서가 아직 PM을 만나지 않았을 때, PM은 상태와 주요 우려를 요약한 이메일을 보내고 즉각적인 대면 미팅을 요청해야 한다. 이 사전 예방적 접근은 긴급성을 전달하고 필수 맥락을 제공하며 스폰서와 직접적인 연결을 구축한다. 주간 팀 미팅 초대(D)는 수동적이다. 상태 보고서를 계속 보내며 기다리기(C)는 비효과적이다. 리스크 분석 완료 후 이메일(A)은 데이터를 제공하지만 관계 구축과 해결책 논의에 필요한 개인적 참여가 부족하다.
742 | In a fixed time and budget project, the customer wants development of a core component to be based on agile practices because the final scope has not yet been fully developed. The project manager is participating in contract development with the sales team and wants to ensure that development costs do not impact project profitability. Which two controls should the project manager incorporate into the contract to address development of the core component? (Choose two) | Tier the contract for fixed and agile components | Require that only internal resources be utilized for this project | Establish a governance committee to review contract delivery | Provide alternatives to scope change at specific project phases within the contract | Limit the number of iterations for development in the contract | A, D | For a fixed time and budget project with an agile core component whose scope is not fully developed, the PM should take two actions: tier the contract for fixed and agile components (A) to separate pricing models, and provide alternatives to scope change at specific project phases within the contract (D) to give the customer structured options for managing scope evolution. Tiering addresses the hybrid nature, while scope change alternatives ensure flexibility within governance. Requiring only internal resources (B) restricts flexibility. Establishing a governance committee (C) adds oversight but not cost control. Limiting the number of iterations (E) constrains agile delivery without addressing scope uncertainty. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scaled Agile | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 고정된 시간과 예산의 프로젝트에서 최종 범위가 아직 완전히 개발되지 않았기 때문에 고객이 핵심 구성요소의 개발을 애자일 관행에 기반하기를 원한다. 프로젝트 관리자는 영업팀과 계약 개발에 참여하고 있으며 개발 비용이 프로젝트 수익성에 영향을 미치지 않도록 보장하고자 한다. 핵심 구성요소 개발을 다루기 위해 프로젝트 관리자가 계약에 포함해야 할 두 가지 통제는 무엇인가? (2개 선택) | 고정 구성요소와 애자일 구성요소에 대해 계약을 계층화한다. | 이 프로젝트에 내부 자원만 활용하도록 요구한다. | 계약 전달을 검토하기 위한 거버넌스 위원회를 설립한다. | 계약 내 특정 프로젝트 단계에서 범위 변경에 대한 대안을 제공한다. | 계약에서 개발 반복 횟수를 제한한다. | A, D | 고정 시간과 예산의 프로젝트에서 범위가 완전히 개발되지 않은 애자일 핵심 구성요소가 있을 때, PM은 두 가지 조치를 취해야 한다: 고정 및 애자일 구성요소에 대해 계약을 계층화하고(A), 계약 내 특정 프로젝트 단계에서 범위 변경에 대한 대안을 제공한다(D). 계층화는 하이브리드 특성을 다루고, 범위 변경 대안은 거버넌스 내 유연성을 보장한다. 내부 자원만 요구(B)는 유연성을 제한한다. 거버넌스 위원회 설치(C)는 감독을 추가하지만 비용 통제는 아니다. 반복 횟수 제한(E)은 범위 불확실성을 해결하지 않고 애자일 전달을 제약한다.
743 | A project manager is assigned to a project with a long timeline and complex scope. The client requires a high-level, long-term plan as well as something that will work immediately, adding features to the product as the project progresses. How should the project manager plan and deliver this project? | Plan the project with a predictive approach and a work breakdown structure (WBS) following the plan and deliver value at the end of theproject. | Select an agile approach and manage the project according to best practices to ensure value is delivered to the client. | Agree on a minimum viable product (MVP) first to be delivered immediately with the client and then release the rest of the scope at the endof the project. | Plan the project with a predictive approach with a work breakdown structure (WBS) and then execute it using an agile approach to delivervalue incrementally. |  | D | When a project has a long timeline and complex scope where the client needs a high-level plan and immediate feature delivery, the project manager should plan with a predictive approach using a WBS and execute with an agile approach to deliver value incrementally. A hybrid method leverages both predictive structure and agile flexibility. Pure predictive (A) delays value delivery. Pure agile (B) may lack the long-term planning the client requires. MVP-then-end delivery (C) does not provide continuous incremental value. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Tailored Approach | Process | Plan and Manage Schedule | Scope | Planning | Embed Quality | Collect Requirements | Hybrid/Tailoring | 프로젝트 관리자가 긴 타임라인과 복잡한 범위를 가진 프로젝트에 배정되었다. 고객은 고수준의 장기 계획과 프로젝트가 진행됨에 따라 제품에 기능을 추가하면서 즉시 작동하는 것을 요구한다. 프로젝트 관리자는 이 프로젝트를 어떻게 계획하고 전달해야 하는가? | 예측형 접근 방식과 작업 분류 체계(WBS)로 프로젝트를 계획하고 계획을 따라 프로젝트 종료 시 가치를 전달한다. | 애자일 접근 방식을 선택하고 모범 사례에 따라 프로젝트를 관리하여 고객에게 가치가 전달되도록 한다. | 고객과 즉시 전달할 최소 기능 제품(MVP)에 먼저 합의한 후 프로젝트 종료 시 나머지 범위를 릴리스한다. | 예측형 접근 방식과 작업 분류 체계(WBS)로 프로젝트를 계획한 후 애자일 접근 방식으로 실행하여 점진적으로 가치를 전달한다. |  | D | 프로젝트가 긴 타임라인과 복잡한 범위를 가지며 고객이 고수준 계획과 즉각적인 기능 전달을 필요로 할 때, 프로젝트 관리자는 WBS를 사용한 예측형 접근 방식으로 계획하고 애자일 접근 방식으로 실행하여 점진적으로 가치를 전달해야 한다. 하이브리드 방법은 예측형 구조와 애자일 유연성을 모두 활용한다. 순수 예측형(A)은 가치 전달을 지연시킨다. 순수 애자일(B)은 고객이 요구하는 장기 계획이 부족할 수 있다. MVP 후 종료 시 전달(C)은 지속적인 점진적 가치를 제공하지 않는다.
744 | A project manager is in the beginning stages of delivering a project and is assessing and prioritizing identified risks. What should the project manager do next? | Plan the risk responses and assign risk response owners. | Start monitoring and controlling the identified risks. | Spend the contingency budget on the identified risks. | Proceed with executing the risk management plan. |  | A | After assessing and prioritizing identified risks in the early project stages, the project manager should next plan risk responses and assign risk response owners. Response planning converts analysis into actionable mitigation. Monitoring and controlling (B) follows response planning. Executing the risk management plan (C) is too generic. Spending contingency (D) is premature — contingency is used when triggers occur. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 관리자가 프로젝트 전달 초기 단계에 있으며 식별된 리스크를 평가하고 우선순위를 정하고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 리스크 대응을 계획하고 리스크 대응 소유자를 배정한다. | 식별된 리스크의 모니터링 및 통제를 시작한다. | 식별된 리스크에 예비비를 지출한다. | 리스크 관리 계획의 실행을 진행한다. |  | A | 초기 프로젝트 단계에서 식별된 리스크를 평가하고 우선순위를 정한 후, 프로젝트 관리자는 다음으로 리스크 대응을 계획하고 리스크 대응 소유자를 배정해야 한다. 대응 계획은 분석을 실행 가능한 완화 조치로 전환한다. 모니터링 및 통제(B)는 대응 계획 이후에 온다. 리스크 관리 계획 실행(C)은 너무 일반적이다. 예비비 지출(D)은 시기상조이다—예비비는 트리거가 발생할 때 사용된다.
745 | A project manager is working with a team that is new to agile. One of the more influential stakeholders struggles with the nature of agile. The project manager knows that this stakeholder is needed as an advocate and wants to do everything possible to make the stakeholder comfortable with the project. What should the project manager include in the status report to illustrate the project's performance? | Results of the MoSCoW assessment | Return on investment (ROI) analysis | Cost-benefit analysis | Earned value analysis (EVA) |  | D | When an influential stakeholder struggles with agile and the PM needs them as an advocate, earned value analysis (EVA) should be included in the status report. EVA provides familiar quantitative performance metrics that bridge traditional and agile perspectives. MoSCoW assessment results (A) show prioritization, not performance. ROI analysis (B) measures profitability, not ongoing progress. Cost-benefit analysis (C) evaluates feasibility, not sprint performance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 프로젝트 관리자가 애자일에 익숙하지 않은 팀과 작업하고 있다. 영향력 있는 이해관계자 중 한 명이 애자일의 특성에 어려움을 겪고 있다. 프로젝트 관리자는 이 이해관계자가 옹호자로 필요하며 이해관계자가 프로젝트에 편안함을 느끼도록 가능한 모든 것을 하고 싶다. 프로젝트 성과를 보여주기 위해 상태 보고서에 무엇을 포함해야 하는가? | MoSCoW 평가 결과 | 투자 수익률(ROI) 분석 | 비용-편익 분석 | 획득 가치 분석(EVA) |  | D | 영향력 있는 이해관계자가 애자일에 어려움을 겪고 PM이 그를 옹호자로 필요로 할 때, 상태 보고서에 획득 가치 분석(EVA)을 포함해야 한다. EVA는 전통적 관점과 애자일 관점을 연결하는 친숙한 정량적 성과 지표를 제공한다. MoSCoW 평가 결과(A)는 우선순위를 보여주지 성과를 보여주지 않는다. ROI 분석(B)은 수익성을 측정하지 진행 중인 진척을 측정하지 않는다. 비용-편익 분석(C)은 타당성을 평가하지 스프린트 성과를 평가하지 않는다.
746 | A project manager has been assigned to a new agile project with a lot of rapidly changing knowledge areas. How should the project manager manage knowledge transfers on this project? | Request the stakeholders to completely document all the domain knowledge before starting the project. | Mentor the team and stakeholders to ensure domain knowledge is being exchanged properly among them during sprints. | Ask the project team to set up the initial sprints to transfer domain knowledge before focusing on the deliverables. | Work with the quality assurance (QA) team to make sure all domain knowledge is being transferred properly among stakeholders. |  | B | For an agile project with rapidly changing knowledge areas, the project manager should mentor the team and stakeholders to ensure domain knowledge is exchanged during sprints. Continuous, embedded knowledge sharing through collaboration practices supports learning while maintaining delivery momentum. Requiring complete documentation before starting (A) delays value and becomes quickly outdated. Setting up initial sprints for knowledge transfer (C) separates learning from delivery. Relying on QA for knowledge transfer (D) misaligns roles. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Align Stakeholder Expectations | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 빠르게 변화하는 지식 영역이 많은 새로운 애자일 프로젝트에 배정되었다. 프로젝트 관리자는 이 프로젝트에서 지식 이전을 어떻게 관리해야 하는가? | 프로젝트 시작 전에 이해관계자에게 모든 도메인 지식을 완전히 문서화하도록 요청한다. | 스프린트 중 팀과 이해관계자 간에 도메인 지식이 적절히 교환되도록 멘토링한다. | 프로젝트 팀에게 산출물에 집중하기 전에 도메인 지식을 이전하기 위한 초기 스프린트를 설정하도록 요청한다. | 품질 보증(QA) 팀과 협력하여 모든 도메인 지식이 이해관계자 간에 적절히 이전되고 있는지 확인한다. |  | B | 빠르게 변화하는 지식 영역이 있는 애자일 프로젝트에서, 프로젝트 관리자는 스프린트 중 팀과 이해관계자 간에 도메인 지식이 교환되도록 멘토링해야 한다. 협업 실천을 통한 지속적이고 내재된 지식 공유는 전달 모멘텀을 유지하면서 학습을 지원한다. 시작 전 완전한 문서화 요구(A)는 가치를 지연시키고 빠르게 구식이 된다. 지식 이전을 위한 초기 스프린트 설정(C)은 학습과 전달을 분리한다. 지식 이전을 QA에 의존(D)은 역할을 잘못 정렬한다.
747 | A project manager for a strategic initiative realizes a new stakeholder is interested in the project and wants to ensure the stakeholder is fully aware of the goals, objectives, benefits, and risks of the project. What should the project manager do to enhance the success of the project? | Share the project status reports with the new stakeholder. | Add the new stakeholder to the communications management plan | Update the stakeholder engagement plan | Schedule a meeting with the new stakeholder |  | C | When a new stakeholder is identified and needs to understand the project's goals, objectives, benefits, and risks, the project manager should update the stakeholder engagement plan. The engagement plan captures strategies for stakeholder involvement. Sharing status reports (A) provides information but not strategic engagement. Adding to the communications plan (B) addresses channels, not engagement strategy. Scheduling a meeting (D) is tactical, not strategic. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 전략적 이니셔티브의 프로젝트 관리자가 새로운 이해관계자가 프로젝트에 관심이 있음을 인식하고 이해관계자가 프로젝트의 목표, 목적, 혜택 및 리스크를 완전히 인식하도록 하고 싶다. 프로젝트의 성공을 높이기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 새로운 이해관계자에게 프로젝트 상태 보고서를 공유한다. | 새로운 이해관계자를 커뮤니케이션 관리 계획에 추가한다. | 이해관계자 참여 계획을 업데이트한다. | 새로운 이해관계자와 회의를 예약한다. |  | C | 새로운 이해관계자가 식별되어 프로젝트의 목표, 목적, 혜택 및 리스크를 이해해야 할 때, 프로젝트 관리자는 이해관계자 참여 계획을 업데이트해야 한다. 참여 계획은 이해관계자 참여 전략을 포착한다. 상태 보고서 공유(A)는 정보를 제공하지만 전략적 참여는 아니다. 커뮤니케이션 계획에 추가(B)는 채널을 다루지 참여 전략을 다루지 않는다. 회의 예약(D)은 전술적이지 전략적이지 않다.
748 | A company is using an agile approach to launch a new product. In the second sprint, the team encounters a technical problem they have never faced before. What should the project manager do? | Facilitate a problem-solving session with the team to analyze the problem. | Inform the project sponsor about the problem faced by the team. | Ask the product owner to write the specifications for the related user story. | Organize an early retrospective with the team to analyze the problem. |  | A | When an agile team in its second sprint encounters a never-before-seen technical problem, the project manager should facilitate a problem-solving session with the team to analyze the problem. Collaborative problem-solving leverages team expertise. Informing the sponsor (B) escalates without attempting resolution. Asking the PO to write specifications (C) addresses requirements, not technical problems. Organizing a retrospective (D) is for after the sprint. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 회사가 새로운 제품을 출시하기 위해 애자일 접근 방식을 사용하고 있다. 두 번째 스프린트에서 팀이 이전에 직면한 적 없는 기술적 문제를 만난다. 프로젝트 관리자는 무엇을 해야 하는가? | 문제를 분석하기 위해 팀과 문제 해결 세션을 촉진한다. | 팀이 직면한 문제에 대해 프로젝트 스폰서에게 알린다. | 제품 책임자에게 관련 사용자 스토리의 사양을 작성하도록 요청한다. | 문제를 분석하기 위해 팀과 조기 회고를 조직한다. |  | A | 두 번째 스프린트에서 애자일 팀이 이전에 직면한 적 없는 기술적 문제를 만날 때, 프로젝트 관리자는 팀과 문제 해결 세션을 촉진하여 문제를 분석해야 한다. 협력적 문제 해결은 팀의 전문성을 활용한다. 스폰서에게 알림(B)은 해결을 시도하지 않고 에스컬레이션한다. PO에게 사양 작성 요청(C)은 기술적 문제가 아닌 요구사항을 다룬다. 회고 조직(D)은 스프린트 이후에 하는 것이다.
749 | A project manager notices that the team lacks a subject matter expert (SME) in a specific area. This expertise will be required for many future projects. What should the project manager do? | Provide an opportunity to one of the existing team members to become an SME. | Hire a contractor from outside of the organization to continue with the project. | Ask team members to document the issue and address it in the next project meeting. | Seek help from the project sponsor to get an SME from another team in the organization. |  | A | The project manager should provide an opportunity to an existing team member to become an SME in the specific area. This develops the team's long-term capabilities, increases motivation and engagement, and addresses both current and future project needs. Seeking an SME from another team through the sponsor (D) creates dependencies and does not build internal capacity. Hiring an external contractor (B) incurs additional costs and risks without fostering team development. Documenting the issue for the next project meeting (C) delays action and does not address the immediate or long-term expertise gap. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 팀에 특정 분야의 주제 전문가(SME)가 부족한 것을 발견한다. 이 전문 지식은 향후 많은 프로젝트에 필요할 것이다. 프로젝트 관리자는 무엇을 해야 하는가? | 기존 팀원 중 한 명에게 SME가 될 수 있는 기회를 제공한다. | 프로젝트를 계속 진행하기 위해 조직 외부에서 계약자를 고용한다. | 팀원에게 이슈를 문서화하고 다음 프로젝트 회의에서 다루도록 요청한다. | 프로젝트 스폰서에게 조직 내 다른 팀에서 SME를 구하도록 도움을 요청한다. |  | A | 프로젝트 관리자는 기존 팀원에게 특정 분야의 SME가 될 기회를 제공해야 한다. 이는 팀의 장기적 역량을 개발하고 동기와 참여를 높이며 현재 및 향후 프로젝트 요구를 모두 해결한다. 스폰서를 통해 다른 팀에서 SME 구하기(D)는 의존성을 생성하고 내부 역량을 구축하지 않는다. 외부 계약자 고용(B)은 추가 비용과 리스크를 발생시키며 팀 개발을 촉진하지 않는다. 다음 회의를 위한 이슈 문서화(C)는 조치를 지연시키고 즉각적 또는 장기적 전문성 격차를 해결하지 않는다.
750 | Experienced team members assigned to a critical project are also supporting several other projects and this is delaying the critical project. If this critical project is not delivered, the company could receive a fine from the government. What should the project manager do? | Review and update the risk management plan. | Review the resources required for the tasks on the critical path. | Allocate resources to develop the competencies of the other team members | Discuss the issue with the project sponsor. |  | B | When experienced team members on a critical project are also supporting other projects and causing delays, the project manager should review the resources required for tasks on the critical path. These tasks determine project duration and have the highest delay risk. By reviewing resource allocation, the PM can identify shortages, conflicts, or overallocation and take corrective actions. Reviewing the risk management plan (A) addresses potential risks but not current resource issues. Allocating resources for training others (C) helps long-term but not the immediate deadline. Discussing with the sponsor (D) escalates without identifying the root cause first. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 핵심 프로젝트에 배정된 경험 있는 팀원들이 다른 여러 프로젝트도 지원하고 있어 핵심 프로젝트가 지연되고 있다. 이 핵심 프로젝트가 전달되지 않으면 회사가 정부로부터 벌금을 받을 수 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 리스크 관리 계획을 검토하고 업데이트한다. | 크리티컬 패스의 작업에 필요한 자원을 검토한다. | 다른 팀원들의 역량을 개발하기 위해 자원을 할당한다. | 프로젝트 스폰서와 이슈를 논의한다. |  | B | 핵심 프로젝트의 경험 있는 팀원들이 다른 프로젝트도 지원하여 지연을 초래할 때, 프로젝트 관리자는 크리티컬 패스의 작업에 필요한 자원을 검토해야 한다. 이 작업들이 프로젝트 기간을 결정하며 지연 리스크가 가장 높다. 자원 할당을 검토하면 부족, 충돌 또는 과할당을 식별하고 시정 조치를 취할 수 있다. 리스크 관리 계획 검토(A)는 잠재적 리스크를 다루지만 현재 자원 문제를 다루지 않는다. 다른 사람 교육을 위한 자원 할당(C)은 장기적으로 도움이 되지만 즉각적인 마감에는 아니다. 스폰서와 논의(D)는 근본 원인을 먼저 식별하지 않고 에스컬레이션한다.
751 | A project team has expressed concern that certain remote team members are not able to collaborate with the larger project team due to their work schedule. The project manager is confused since the entire team is located in the same time zone and believes there are other factors at play. What should the project manager do next? | Examine the team ' s virtual needs. | Review performance formally. | Rectify ground rule violations. | Implement new options. |  | A | When remote team members in the same time zone cannot collaborate due to their work schedule, the project manager should examine the team's virtual needs. Investigating beyond scheduling reveals gaps in tools, technology, or processes. Reviewing performance formally (B) is punitive without understanding causes. Rectifying ground rule violations (C) assumes violations exist. Implementing new options (D) is premature without understanding needs. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 특정 원격 팀원들이 업무 일정으로 인해 더 큰 프로젝트 팀과 협업할 수 없다는 우려를 표명했다. 프로젝트 관리자는 전체 팀이 같은 시간대에 있어 혼란스러우며 다른 요인이 작용한다고 생각한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 팀의 가상 요구 사항을 검토한다. | 공식적으로 성과를 검토한다. | 기본 규칙 위반을 시정한다. | 새로운 옵션을 구현한다. |  | A | 같은 시간대의 원격 팀원들이 업무 일정으로 협업할 수 없을 때, 프로젝트 관리자는 팀의 가상 요구 사항을 검토해야 한다. 일정 너머의 조사는 도구, 기술 또는 프로세스의 격차를 밝힌다. 공식적인 성과 검토(B)는 원인을 이해하지 않고 징벌적이다. 기본 규칙 위반 시정(C)은 위반이 존재한다고 가정한다. 새로운 옵션 구현(D)은 요구 사항을 이해하지 않고 시기상조이다.
752 | A team is focusing on quickly developing and shipping new product features due to very aggressive market demands. The team is setting aside long-term work not directly related to the current business objective, which affects product performance and generates more customer support requests. How can the team minimize the impact of the reduced focus on quality? | Consider implementing test-driven methodology. | Adapt the management plan to reduce the quality constraints. | Work on the technical debt at a later stage in the project. | Reduce complexity to focus on the minimum viable product (MVP). |  | A | When a team is shipping features quickly due to aggressive market demands while setting aside long-term quality work, generating more support requests, the team should consider implementing test-driven methodology. TDD embeds quality early in development. Reducing quality constraints (B) worsens the problem. Working on technical debt later (C) defers the issue. Reducing to MVP (D) limits scope but does not address quality. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | XP (Extreme Programming) | Process | Plan and Optimize Quality | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 팀이 매우 공격적인 시장 요구로 인해 새로운 제품 기능을 빠르게 개발하고 출시하는 데 집중하고 있다. 팀은 현재 비즈니스 목표와 직접 관련이 없는 장기 작업을 보류하고 있으며, 이는 제품 성능에 영향을 미치고 더 많은 고객 지원 요청을 발생시킨다. 팀은 품질에 대한 집중 감소의 영향을 어떻게 최소화할 수 있는가? | 테스트 주도 방법론 구현을 고려한다. | 품질 제약을 줄이기 위해 관리 계획을 조정한다. | 프로젝트의 후속 단계에서 기술 부채를 처리한다. | 최소 기능 제품(MVP)에 집중하기 위해 복잡성을 줄인다. |  | A | 공격적인 시장 요구로 기능을 빠르게 출시하면서 장기적 품질 작업을 보류하여 더 많은 지원 요청이 발생할 때, 팀은 테스트 주도 방법론 구현을 고려해야 한다. TDD는 개발 초기에 품질을 내재화한다. 품질 제약 줄이기(B)는 문제를 악화시킨다. 기술 부채를 나중에 처리(C)는 이슈를 미룬다. MVP로 축소(D)는 범위를 제한하지만 품질을 다루지 않는다.
753 | A project manager in a matrix organization has been assigned to a system solution project with tight timelines. There are two resources assigned as part of the solution team: one who is experienced and one who is new. During development, the project manager notices that the resources disagree on the solution approach. What should the project manager do next to deliver a reliable solution? | Meet with the entire project team and decide on a further course of action based on team consensus. | Meet with each resource ' s functional manager and arrive at a common approach that is appropriate for the project ' s constraints. | Meet with the resources together and find common ground on viewpoints to compromise on an approach. | Meet with the resources and agree that the more experienced resource ' s approach has proven to be effective in the past. |  | C | In a matrix organization with team members of varying experience levels, the PM should facilitate collaboration and find a compromise that incorporates the strengths of both perspectives. This approach encourages mutual respect, leverages diverse expertise, and produces a more robust solution. It aligns with PMI principles of conflict resolution and team management. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 매트릭스 조직의 프로젝트 관리자가 빠듯한 일정의 시스템 솔루션 프로젝트에 배정되었다. 솔루션 팀의 일부로 경험이 많은 자원 1명과 신입 자원 1명이 배정되었다. 개발 중 프로젝트 관리자는 두 자원이 솔루션 접근 방식에 대해 의견이 다르다는 것을 알게 되었다. 프로젝트 관리자는 신뢰할 수 있는 솔루션을 전달하기 위해 다음에 무엇을 해야 하는가? | 전체 프로젝트 팀과 만나 팀 합의에 기반하여 추가 조치 방향을 결정한다. | 각 자원의 기능 관리자와 만나 프로젝트의 제약에 적합한 공통 접근 방식에 도달한다. | 두 자원과 함께 만나 관점의 공통점을 찾아 접근 방식에 대한 절충안을 마련한다. | 두 자원과 만나 경험이 더 많은 자원의 접근 방식이 과거에 효과적이었음에 동의한다. |  | C | 매트릭스 조직에서 경험 수준이 다른 팀원들이 있을 때, PM은 협업을 촉진하고 양쪽 관점의 강점을 통합하는 절충안을 찾아야 한다. 이 접근 방식은 상호 존중을 장려하고 다양한 전문성을 활용하며 더 견고한 솔루션을 만든다. 이는 PMI의 갈등 해결 및 팀 관리 원칙에 부합한다.
754 | A project has been running for 2 months and now requires approval for a supplier to begin some execution tasks. The project team has evaluated several suppliers and selected their top two preferred suppliers. The project sponsor requested that another supplier who has lower costs be added to the list. However, the project manager is aware that this supplier does not always fulfill the project requirements. What should the project manager do? | Choose the sponsor ' s preferred supplier for the project to avoid conflict between theteam and sponsor. | Set up a requirements review session and obtain agreement for selection criteria. | Recommend to the sponsor to review the results of the team ' s supplier evaluation. | Recommend to the team to add the sponsor ' s preferred supplier to the list. |  | C | The PM should recommend the sponsor review the team's supplier evaluation results. The source selection criteria—including cost, quality, technical capability, schedule, and risk—form the basis for an objective evaluation. The PM should communicate the rationale behind preferred suppliers and highlight risks of choosing a lower-cost supplier that may not meet project requirements. Seeking sponsor approval through a transparent evaluation process prevents conflicts and ensures alignment between the team and sponsor. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트가 2개월 동안 진행되었으며 이제 공급업체가 일부 실행 작업을 시작하기 위한 승인이 필요하다. 프로젝트 팀은 여러 공급업체를 평가하고 상위 2개의 선호 공급업체를 선정했다. 프로젝트 스폰서가 비용이 더 낮은 다른 공급업체를 목록에 추가하도록 요청했다. 그러나 프로젝트 관리자는 이 공급업체가 항상 프로젝트 요구사항을 충족시키지 못한다는 것을 알고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀과 스폰서 간의 갈등을 피하기 위해 스폰서가 선호하는 공급업체를 프로젝트에 선택한다. | 요구사항 검토 세션을 설정하고 선정 기준에 대한 합의를 얻는다. | 스폰서에게 팀의 공급업체 평가 결과를 검토하도록 권고한다. | 팀에게 스폰서가 선호하는 공급업체를 목록에 추가하도록 권고한다. |  | C | PM은 스폰서에게 팀의 공급업체 평가 결과를 검토하도록 권고해야 한다. 비용, 품질, 기술 역량, 일정, 리스크를 포함한 소스 선정 기준은 객관적 평가의 기반을 형성한다. PM은 선호 공급업체의 근거를 전달하고 프로젝트 요구사항을 충족하지 못할 수 있는 저비용 공급업체의 리스크를 강조해야 한다. 투명한 평가 프로세스를 통해 스폰서 승인을 구하면 갈등을 방지하고 팀과 스폰서 간의 정렬을 보장한다.
755 | A project manager is assigned to a major system integration project that is currently in the execution phase. The project relies heavily on the presence and availability of certain products and services, which are provided at various periods throughout the project phases by selected third-party vendors. What should the project manager do to ensure the successful execution of the project? | Ask the procurement department to select the vendor using established processes | Oversee the selection process for the vendor to procure the needed products and services | Activate the mitigation plan for the procurement risks | Perform procurement control checks throughout the project |  | D | Procurement management involves selecting, managing, and controlling external vendor relationships throughout the project lifecycle. The PM should implement procurement control checks to ensure proper oversight, monitor deliverables, and address performance issues through established procurement processes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 현재 실행 단계에 있는 주요 시스템 통합 프로젝트에 배정되었다. 프로젝트는 선정된 제3자 공급업체가 프로젝트 단계 전반에 걸쳐 다양한 시기에 제공하는 특정 제품 및 서비스의 존재와 가용성에 크게 의존한다. 프로젝트의 성공적인 실행을 보장하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 조달 부서에 확립된 프로세스를 사용하여 공급업체를 선정하도록 요청한다. | 필요한 제품 및 서비스를 조달하기 위한 공급업체 선정 프로세스를 감독한다. | 조달 리스크에 대한 완화 계획을 활성화한다. | 프로젝트 전반에 걸쳐 조달 통제 점검을 수행한다. |  | D | 조달 관리는 프로젝트 수명 주기 전반에 걸쳐 외부 공급업체 관계를 선정, 관리, 통제하는 것을 포함한다. PM은 조달 통제 점검을 구현하여 적절한 감독을 보장하고, 산출물을 모니터링하며, 확립된 조달 프로세스를 통해 성과 문제를 해결해야 한다.
756 | A project's customer is furious. When the customer arrived at the project site, they discovered that one of their requirements was not met. What should the project manager do? | Discuss and agree with the customer to implement the missing requirement. | Refer to the requirements traceability matrix and analyze the requirement. | Consult the scope management plan with the customer to understand the gap. | Analyze the benefits management plan and implement the needed change. |  | B | When a customer discovers an unmet requirement at the project site, the project manager should refer to the requirements traceability matrix (RTM) and analyze the requirement. The RTM traces requirements to deliverables and identifies where the gap occurred. Discussing implementation with the customer (A) acts before understanding the gap. Consulting the scope management plan (C) provides process context but not requirement-level detail. Analyzing the benefits management plan (D) addresses value, not requirement fulfillment. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 프로젝트의 고객이 분노하고 있다. 고객이 프로젝트 현장에 도착했을 때 자신의 요구사항 중 하나가 충족되지 않았음을 발견했다. 프로젝트 관리자는 무엇을 해야 하는가? | 고객과 누락된 요구사항을 구현하는 것에 대해 논의하고 합의한다. | 요구사항 추적 매트릭스를 참조하고 해당 요구사항을 분석한다. | 격차를 이해하기 위해 고객과 범위 관리 계획을 확인한다. | 혜택 관리 계획을 분석하고 필요한 변경을 구현한다. |  | B | 고객이 프로젝트 현장에서 충족되지 않은 요구사항을 발견할 때, 프로젝트 관리자는 요구사항 추적 매트릭스(RTM)를 참조하고 해당 요구사항을 분석해야 한다. RTM은 요구사항을 산출물까지 추적하고 격차가 발생한 지점을 식별한다. 고객과 구현을 논의(A)하는 것은 격차를 이해하기 전에 행동하는 것이다. 범위 관리 계획 확인(C)은 프로세스 맥락을 제공하지만 요구사항 수준의 세부 사항은 제공하지 않는다. 혜택 관리 계획 분석(D)은 가치를 다루지 요구사항 충족을 다루지 않는다.
757 | A project manager has identified the key stakeholders for the project. The project manager wants to use their expertise to help the stakeholders understand and support the project objectives and benefits. What should the project manager do? | Provide the stakeholders with regular updates and reports on the project status, progress, and issues. | Educate the stakeholders on the project scope, quality, and risks, and how their expectations will be affected. | Update the stakeholders during project meetings, workshops, and reviews to solicit their input and feedback. | Provide customized reports to each stakeholder regarding the project progress, upcoming risks, and issues. |  | B | When a project manager wants to help stakeholders understand and support project objectives and benefits, they should educate stakeholders on scope, quality, and risks and how their expectations will be affected. Proactive education builds understanding and alignment. Providing regular status updates (A) informs but does not educate. Providing customized reports (D) communicates information without building understanding. Updating during meetings (C) is valuable but is not focused on education. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 프로젝트의 핵심 이해관계자를 식별했다. 프로젝트 관리자는 자신의 전문성을 활용하여 이해관계자가 프로젝트 목표와 혜택을 이해하고 지원하도록 돕고 싶다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자에게 프로젝트 상태, 진행 상황, 이슈에 대한 정기적인 업데이트와 보고서를 제공한다. | 이해관계자에게 프로젝트 범위, 품질, 리스크 및 그들의 기대에 미치는 영향을 교육한다. | 프로젝트 회의, 워크숍, 검토 중에 이해관계자를 업데이트하여 의견과 피드백을 구한다. | 각 이해관계자에게 프로젝트 진행 상황, 다가오는 리스크, 이슈에 대한 맞춤형 보고서를 제공한다. |  | B | 프로젝트 관리자가 이해관계자가 프로젝트 목표와 혜택을 이해하고 지원하도록 돕고 싶을 때, 이해관계자에게 범위, 품질, 리스크 및 기대에 미치는 영향을 교육해야 한다. 사전 예방적 교육은 이해와 정렬을 구축한다. 정기적 상태 업데이트 제공(A)은 정보를 전달하지만 교육하지 않는다. 맞춤형 보고서 제공(D)은 이해를 구축하지 않고 정보를 전달한다. 회의 중 업데이트(C)는 가치 있지만 교육에 초점을 맞추지 않는다.
758 | A credit collection company is implementing new software to assist customer service agents when calling clients for payments. The software will benefit the company by freeing up staff to work on other projects. Several business areas want to take advantage of this benefit. What should the project manager do? | Request all of the business areas to plan for a portion of the benefit equally and include it in their staffing plans. | Ask the project sponsor to make a decision on who will own the benefit and document the decision. | Set up a stakeholder session with all teams to agree and document the benefits and establish ownership. | Ask the project sponsor for approval to distribute the project benefits equally to the business areas. |  | C | When multiple business areas want to benefit from new software that frees up staff, the project manager should set up a stakeholder session with all teams to agree and document the benefits and establish ownership. Collaborative benefit planning ensures clear accountability and shared understanding. Requesting equal distribution (A) is arbitrary. Asking the sponsor to decide ownership (B) excludes stakeholder input. Asking the sponsor for equal distribution approval (D) imposes a decision without stakeholder agreement. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Risk | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 신용 추심 회사가 고객 서비스 사원이 고객에게 결제 전화를 할 때 도움을 주는 새로운 소프트웨어를 구현하고 있다. 소프트웨어는 직원이 다른 프로젝트에 작업할 수 있도록 해주어 회사에 도움이 된다. 여러 사업 부서가 이 혜택을 활용하고 싶어한다. 프로젝트 관리자는 무엇을 해야 하는가? | 모든 사업 부서에 혜택의 일부를 동등하게 계획하고 인력 계획에 포함하도록 요청한다. | 프로젝트 스폰서에게 혜택의 소유권을 결정하고 문서화하도록 요청한다. | 모든 팀과 이해관계자 세션을 설정하여 혜택을 합의하고 문서화하며 소유권을 확립한다. | 프로젝트 스폰서에게 프로젝트 혜택을 사업 부서에 동등하게 배분하는 승인을 요청한다. |  | C | 여러 사업 부서가 직원을 해방하는 새 소프트웨어의 혜택을 원할 때, 프로젝트 관리자는 모든 팀과 이해관계자 세션을 설정하여 혜택을 합의하고 문서화하며 소유권을 확립해야 한다. 협력적 혜택 계획은 명확한 책임과 공유된 이해를 보장한다. 동등 배분 요청(A)은 임의적이다. 스폰서에게 소유권 결정 요청(B)은 이해관계자 입력을 배제한다. 스폰서에게 동등 배분 승인 요청(D)은 이해관계자 합의 없이 결정을 강요한다.
759 | A software development project was recently initiated. One of the project team members is regularly questioning the project's risk response strategy. The team member vocalizes their doubts during the daily standup meeting to share concerns regarding how the project should handle risks. What should the project manager do first? | Meet with the individual to understand their concerns. | Assign each concern to the appropriate team member. | Escalate the team member's concerns to the project sponsor. | Utilize the daily meetings to respond to the concerns. |  | A | When a team member regularly questions the risk response strategy during daily standups, the project manager should first meet with the individual to understand their concerns. Private discussion enables deeper understanding. Assigning concerns to team members (B) distributes without diagnosing. Escalating to the sponsor (C) is premature. Utilizing daily meetings to respond (D) turns standups into extended discussions. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 소프트웨어 개발 프로젝트가 최근 시작되었다. 프로젝트 팀원 중 한 명이 일일 스탠드업 회의에서 프로젝트의 리스크 대응 전략에 정기적으로 의문을 제기하고 있다. 팀원이 프로젝트가 리스크를 어떻게 처리해야 하는지에 대한 우려를 공유하기 위해 의심을 아무런 거리낂 없이 이야기한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 개인과 만나 우려를 이해한다. | 각 우려를 적절한 팀원에게 배정한다. | 팀원의 우려를 프로젝트 스폰서에게 에스컬레이션한다. | 일일 회의를 활용하여 우려에 대응한다. |  | A | 팀원이 일일 스탠드업에서 리스크 대응 전략에 정기적으로 의문을 제기할 때, 프로젝트 관리자는 먼저 개인과 만나 우려를 이해해야 한다. 비공개 논의는 더 깊은 이해를 가능하게 한다. 우려를 팀원에게 배정(B)하는 것은 진단 없이 분배하는 것이다. 스폰서에게 에스컬레이션(C)은 시기상조이다. 일일 회의에서 대응(D)은 스탠드업을 확장된 토론으로 전환시킨다.
760 | During the design phase, a project manager realizes that the project will benefit from using adaptive tools. The effectiveness of this approach has been proven in past projects inside the organization. What should the project manager do first? | Confirm team capabilities before introducing adaptive tools and artifacts to the project | Update project documents to include adaptive tools and artifacts and plan the first iterative session | Freeze the design phase and look for an external resource to run iterative design at extra cost | Contact the project sponsor and request new team members who are familiar with adaptive projects |  | B | When a project manager realizes the project will benefit from adaptive tools proven in past organizational projects, the first step should be to update project documents to include adaptive tools and artifacts and plan the first iterative session. This formally integrates the new approach into the project framework. Confirming team capabilities first (A) is good practice but not the first required step. Contacting the sponsor for new team members (D) is premature. Freezing the design and hiring externally (C) is costly and unnecessary. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Hybrid/Tailoring | 설계 단계에서 프로젝트 관리자가 프로젝트가 적응형 도구를 사용하면 혜택을 얻을 수 있음을 인식한다. 이 접근 방식의 효과는 조직 내 과거 프로젝트에서 입증되었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 적응형 도구와 산출물을 포함하도록 프로젝트에 도입하기 전에 팀 역량을 확인한다. | 적응형 도구와 산출물을 포함하도록 프로젝트 문서를 업데이트하고 첫 번째 반복 세션을 계획한다. | 설계 단계를 동결하고 추가 비용으로 반복적 설계를 수행할 외부 자원을 찾는다. | 프로젝트 스폰서에게 연락하여 적응형 프로젝트에 익숙한 새 팀원을 요청한다. |  | B | 프로젝트 관리자가 조직 내 과거 프로젝트에서 입증된 적응형 도구가 프로젝트에 도움이 될 것이라고 인식할 때, 첫 단계는 적응형 도구와 산출물을 포함하도록 프로젝트 문서를 업데이트하고 첫 번째 반복 세션을 계획하는 것이다. 이는 새로운 접근 방식을 프로젝트 프레임워크에 공식적으로 통합한다. 팀 역량 확인(A)은 좋은 실천이지만 첫 단계는 아니다. 스폰서에게 새 팀원 요청(D)은 시기상조이다. 설계 동결 및 외부 고용(C)은 비용이 많고 불필요하다.
761 | Two functional managers disagree on key features of one deliverable during the planning of a project. The project manager discovers that each manager included requirements that contradict each other. The functional managers do not want to meet with each other to find a solution. This situation has been escalated to the sponsor who requests a meeting with them. What strategy should the project manager use to resolve this conflict in the meeting? | Ensure that both managers understand the requirements and search for a solution that best satisfies this deliverable | Request that the managers explain why each requirement must be implemented and decide by considering the cost and benefits | Explain to the managers that only one of the two requirements can be implemented, and submit a change request, | Explain to the managers that the contradicting requirements are being considered for implementation in the project |  | A | When two functional managers have contradicting requirements and will not meet to resolve the issue, the project manager should ensure both managers understand the requirements and search for a solution that best satisfies the deliverable. Collaborative problem-solving seeks a win-win outcome. Requesting cost-benefit justification (B) creates competition. Stating only one can be implemented (C) forces a win-lose outcome. Stating both are being considered (D) avoids resolution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 두 기능 관리자가 프로젝트 계획 중 하나의 산출물의 핵심 기능에 대해 의견이 다르다. 프로젝트 관리자는 각 관리자가 서로 모순되는 요구사항을 포함한 것을 발견했다. 기능 관리자들은 해결책을 찾기 위해 서로 만나고 싶어하지 않는다. 이 상황이 스폰서에게 에스컬레이션되었고 스폰서가 그들과의 회의를 요청한다. 프로젝트 관리자는 이 회의에서 이 갈등을 해결하기 위해 어떤 전략을 사용해야 하는가? | 두 관리자가 요구사항을 이해하고 이 산출물을 가장 잘 충족시키는 솔루션을 찾도록 보장한다. | 관리자들에게 각 요구사항이 왜 구현되어야 하는지 설명하도록 요청하고 비용과 혜택을 고려하여 결정한다. | 관리자들에게 두 요구사항 중 하나만 구현할 수 있음을 설명하고 변경 요청을 제출한다. | 관리자들에게 모순되는 요구사항이 프로젝트에서 구현을 고려 중이라고 설명한다. |  | A | 두 기능 관리자가 모순되는 요구사항을 가지고 있고 해결을 위해 만나지 않으려 할 때, 프로젝트 관리자는 두 관리자가 요구사항을 이해하고 산출물을 가장 잘 충족시키는 솔루션을 찾도록 보장해야 한다. 협력적 문제 해결은 윈-윈 결과를 추구한다. 비용-혜택 정당화 요청(B)은 경쟁을 만든다. 하나만 구현 가능하다고 명시(C)하면 승-패 결과를 강요한다. 둘 다 고려 중이라고 명시(D)하면 해결을 회피한다.
762 | A company is experiencing a high rate of rejected project deliverables. The project manager is requested to suggest a solution to improve quality. What should the project manager suggest? | Break down the project into several iterations and incorporate a quality check by a quality auditor in each iteration. | Request that all team members receive the newest quality standards training and review one another ' s work. | Break down the project into several iterations and incorporate automatic testing and quality improvement sessions. | Request that a quality specialist be assigned to the project to check the final product at the end of the project. |  | C | To improve the rate of deliverable acceptance, the project manager should suggest breaking the project into iterations and incorporating automatic testing and quality improvement sessions. This approach embeds continuous feedback and inspection throughout the process, using automated testing early and often while leveraging retrospectives for continuous improvement. Providing quality standards training and peer review (B) addresses knowledge but lacks systematic quality integration. Breaking into iterations with a quality auditor (A) relies on external inspection rather than built-in quality. Assigning a quality specialist for end-of-project checks (D) is reactive and catches issues too late. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | XP (Extreme Programming) | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 회사가 높은 프로젝트 산출물 거부율을 경험하고 있다. 프로젝트 관리자가 품질을 개선할 솔루션을 제안하도록 요청받았다. 프로젝트 관리자는 무엇을 제안해야 하는가? | 프로젝트를 여러 반복으로 나누고 각 반복에 품질 감사자의 품질 점검을 포함한다. | 모든 팀원이 최신 품질 기준 교육을 받고 서로의 작업을 검토하도록 요청한다. | 프로젝트를 여러 반복으로 나누고 자동 테스트와 품질 개선 세션을 포함한다. | 프로젝트 끝에 최종 제품을 점검하도록 품질 전문가를 프로젝트에 배정하도록 요청한다. |  | C | 산출물 수락률을 개선하기 위해 프로젝트 관리자는 프로젝트를 반복으로 나누고 자동 테스트와 품질 개선 세션을 포함할 것을 제안해야 한다. 이 접근 방식은 자동 테스트를 조기에 자주 사용하면서 회고를 활용한 지속적 개선으로 프로세스 전반에 지속적인 피드백과 검사를 내장한다. 품질 기준 교육 및 동료 검토 제공(B)은 지식을 다루지만 체계적 품질 통합이 부족하다. 품질 감사자와 반복으로 나누기(A)는 내장 품질이 아닌 외부 검사에 의존한다. 프로젝트 끝 품질 전문가 배정(D)은 반응적이며 너무 늦게 문제를 발견한다.
763 | A project is nearing finalization and just released the final product to the customer. The assigned project manager left the company without notice and without sharing any information or documents for the remaining activities. A new project manager has just been assigned to the project. What should the new project manager do next? | Document the project manager ' s departure and the missing documents in the risk log. | Prepare a transition plan to hand over the operations and other closing documentation. | Schedule a lessons learned meeting with the project team and close out the project. | Use the contingency fund to extend the timeline and conduct a detailed review of past deliverables. |  | B | When the previous PM left without sharing information and the final product is already delivered, the new project manager should prepare a transition plan to hand over operations and other closing documentation. Formal closure activities ensure proper knowledge transfer and administrative completion. Documenting the departure in the risk log (A) tracks the incident but does not advance closure. Scheduling a lessons learned meeting and closing out (C) skips transition planning. Using contingency funds for a detailed review (D) is unnecessary if the product is already delivered. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Evaluate Project Status | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 프로젝트가 최종 마무리 단계에 근접해 있으며 최종 제품을 고객에게 릴리스했다. 배정된 프로젝트 관리자가 남은 활동에 대한 정보나 문서를 공유하지 않고 예고 없이 퇴사했다. 새로운 프로젝트 관리자가 프로젝트에 배정되었다. 새 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 관리자의 퇴사와 누락된 문서를 리스크 로그에 기록한다. | 운영 및 기타 종료 문서를 인계하기 위한 전환 계획을 준비한다. | 프로젝트 팀과 교훈 회의를 예약하고 프로젝트를 종료한다. | 예비비를 사용하여 일정을 연장하고 과거 산출물에 대한 상세 검토를 수행한다. |  | B | 이전 PM이 정보를 공유하지 않고 떠나고 최종 제품이 이미 전달되었을 때, 새 프로젝트 관리자는 운영 및 기타 종료 문서를 인계하기 위한 전환 계획을 준비해야 한다. 공식적인 종료 활동은 적절한 지식 이전과 행정적 완료를 보장한다. 퇴사를 리스크 로그에 기록(A)하는 것은 사건을 추적하지만 종료를 진행하지 않는다. 교훈 회의 예약 및 종료(C)는 전환 계획을 건너뛴다. 상세 검토를 위해 예비비 사용(D)은 제품이 이미 전달되었으므로 불필요하다.
764 | A project manager at a plant with continuous operations needs to deliver a project urgently to meet a market opportunity. What should the project manager do to meet the time-to-market need? | Conduct serial activities on tasks | Add resources to activities | Perform tasks in parallel | Increase the number of standup meetings |  | C | When a plant with continuous operations needs to deliver a project urgently to meet a market opportunity, the project manager should perform tasks in parallel (fast-tracking). This schedule compression technique overlaps activities originally planned sequentially, accelerating delivery without changing scope. Conducting serial activities (A) maintains the original sequence without compression. Adding resources (B) is crashing, which increases cost. Increasing standup meetings (D) improves communication but does not compress the schedule. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Traditional PM | 연속 운영 중인 공장의 프로젝트 관리자가 시장 기회를 충족시키기 위해 프로젝트를 긴급하게 전달해야 한다. 프로젝트 관리자는 시장 출시 시기 요구를 충족시키기 위해 무엇을 해야 하는가? | 작업을 순차적으로 수행한다. | 활동에 자원을 추가한다. | 작업을 병렬로 수행한다. | 스탠드업 회의 횟수를 늘린다. |  | C | 연속 운영 중인 공장에서 시장 기회를 위해 긴급 전달이 필요할 때, 프로젝트 관리자는 작업을 병렬로 수행(빨리 진행)해야 한다. 이 일정 압축 기법은 원래 순차적으로 계획된 활동을 중첩시켜 범위 변경 없이 전달을 가속화한다. 순차적 활동 수행(A)은 압축 없이 원래 순서를 유지한다. 자원 추가(B)는 크래싱으로 비용을 증가시킨다. 스탠드업 회의 증가(D)는 커뮤니케이션을 개선하지만 일정을 압축하지 않는다.
765 | A recently concluded quality audit failed and came back with multiple action items. A newly appointed project manager is reviewing the project status with the team. New stakeholders have been identified, and new audit resources may have to be added to the project. What should the project manager do next? | Perform integrated change control. | Update the risk management plan. | Perform stakeholder engagement. | Update the quality management plan. |  | A | After a failed quality audit with multiple action items, new stakeholders identified, and potential new audit resources needed, the project manager should perform integrated change control. This process evaluates the impact of the audit findings, determines necessary corrective actions, assesses whether additional resources are required, and ensures all changes are formally reviewed and approved before implementation. Performing stakeholder engagement (C) is ongoing but not the immediate priority. Updating the quality management plan (D) or risk management plan (B) are specific responses that should follow the integrated change control assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 최근 완료된 품질 감사가 실패하고 여러 조치 항목이 도출되었다. 새로 임명된 프로젝트 관리자가 팀과 프로젝트 상태를 검토하고 있다. 새로운 이해관계자가 식별되었고 새로운 감사 자원을 프로젝트에 추가해야 할 수 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 통합 변경 통제를 수행한다. | 리스크 관리 계획을 업데이트한다. | 이해관계자 참여를 수행한다. | 품질 관리 계획을 업데이트한다. |  | A | 실패한 품질 감사에 여러 조치 항목이 있고, 새로운 이해관계자가 식별되었으며, 추가 감사 자원이 필요할 수 있을 때, 프로젝트 관리자는 통합 변경 통제를 수행해야 한다. 이 프로세스는 감사 결과의 영향을 평가하고, 필요한 시정 조치를 결정하며, 추가 자원이 필요한지 평가하고, 구현 전에 모든 변경이 공식적으로 검토되고 승인되도록 보장한다. 이해관계자 참여 수행(C)은 지속적이지만 즉각적인 우선순위가 아니다. 품질 관리 계획(D) 또는 리스크 관리 계획(B) 업데이트는 통합 변경 통제 평가 후에 따라야 할 구체적인 대응이다.
766 | During the project planning phase, a project manager called a meeting to discuss the product backlog with multiple stakeholders who represent the end users in various capacities. Only one executive manager attended the meeting. What should the project manager do? | Proceed with prioritization of the product backlog based on previous lessons learnedand complete the project planning phase. | Proceed with the meeting in order to keep the project on track and start prioritizing the product backlog. | Meet with each stakeholder individually to gather input to the product backlog andbegin project planning. | Reschedule the meeting to ensure the majority of stakeholders are present for theproduct backlog discussions. |  | D | When only one executive attended a product backlog meeting with multiple stakeholders, the project manager should reschedule the meeting to ensure the majority of stakeholders are present. Adequate stakeholder participation ensures comprehensive input for backlog prioritization. Proceeding based on lessons learned (A) bypasses stakeholder input. Proceeding with those present (B) risks incomplete prioritization. Meeting stakeholders individually (C) fragments the collaborative discussion. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 계획 단계에서 프로젝트 관리자가 다양한 역할로 최종 사용자를 대표하는 여러 이해관계자와 제품 백로그를 논의하기 위한 회의를 소집했다. 한 명의 임원 관리자만 회의에 참석했다. 프로젝트 관리자는 무엇을 해야 하는가? | 이전 교훈에 기반하여 제품 백로그의 우선순위를 진행하고 프로젝트 계획 단계를 완료한다. | 프로젝트를 궤도에 유지하기 위해 회의를 진행하고 제품 백로그 우선순위화를 시작한다. | 각 이해관계자를 개별적으로 만나 제품 백로그에 대한 입력을 수집하고 프로젝트 계획을 시작한다. | 대다수의 이해관계자가 제품 백로그 논의에 참석하도록 회의를 재예약한다. |  | D | 여러 이해관계자와의 제품 백로그 회의에 한 명의 임원만 참석했을 때, 프로젝트 관리자는 대다수의 이해관계자가 참석하도록 회의를 재예약해야 한다. 충분한 이해관계자 참여는 백로그 우선순위화에 대한 포괄적인 입력을 보장한다. 교훈에 기반한 진행(A)은 이해관계자 입력을 우회한다. 참석자만으로 진행(B)은 불완전한 우선순위화를 위험에 빠뜨린다. 개별 만남(C)은 협력적 논의를 분산시킨다.
767 | A company's board of directors announced that a major layoff will occur at the end of the month. When evaluating the impact, the project manager found that 25% of the project team members are part of the layoff. What should the project manager do first? | Request a meeting with the project sponsor to discuss the viability of the project and determine the next actions | Request a meeting with the finance department to increase the budget of the project to hire temporary personnel to perform the affected activities | Request a meeting with the customer and discuss trade-offs to reduce the scope and product quality as a result of the lack of personnel | Request a meeting with the human resources (HR) department and demand they find a 579 solution to retain the project team members |  | A | When 25% of the project team is part of an announced layoff, the project manager should first request a meeting with the project sponsor to discuss project viability and determine next actions. The sponsor authorizes resources and approves changes to the project plan. Discussing trade-offs with the customer (B) bypasses the sponsor. Requesting a budget increase from finance (C) needs sponsor approval first. Demanding HR retain team members (D) is neither realistic nor respectful. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 회사 이사회가 월말에 대규모 정리해고가 있을 것이라고 발표했다. 영향을 평가할 때 프로젝트 관리자는 프로젝트 팀원의 25%가 정리해고 대상임을 발견했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트 스폰서와 만나 프로젝트의 실행 가능성을 논의하고 다음 조치를 결정한다. | 재무부와 만나 영향받는 활동을 수행할 임시 인력 고용을 위해 프로젝트 예산 증액을 요청한다. | 고객과 만나 인력 부족으로 인한 범위 및 제품 품질 축소에 대한 절충안을 논의한다. | 인사부(HR)와 만나 프로젝트 팀원을 유지할 방안을 찾도록 요구한다. |  | A | 프로젝트 팀의 25%가 정리해고 대상일 때, 프로젝트 관리자는 먼저 프로젝트 스폰서와 만나 프로젝트 실행 가능성을 논의하고 다음 조치를 결정해야 한다. 스폰서는 자원을 승인하고 프로젝트 계획 변경을 승인한다. 고객과 절충안 논의(B)는 스폰서를 우회한다. 재무부에 예산 증액 요청(C)은 먼저 스폰서 승인이 필요하다. HR에 팀원 유지 요구(D)는 현실적이지도 존중적이지도 않다.
768 | One team member is not as active as the rest of the team during a brainstorming session. The project manager has a separate conversation with the team member and learns that the team member is slightly hearing impaired. The team member appreciates the project manager's concern. The project manager then decides to change the time and room for the meeting to ensure everyone can participate. What interpersonal skill did the project manager use? | Networking | Conflict management | Emotional intelligence | Influencing |  | C | The PM demonstrated emotional intelligence—the ability to identify, assess, and manage personal emotions of oneself and others, as well as collective group emotions. By recognizing the team member's hearing impairment, showing empathy, and taking action to accommodate their needs by changing the meeting venue and time, the PM applied emotional intelligence effectively. While networking, conflict management, and influencing are also interpersonal skills, they are not applicable to this specific scenario. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 브레인스토밍 세션에서 한 팀원이 나머지 팀만큼 적극적이지 않다. 프로젝트 관리자가 팀원과 별도로 대화하여 팀원이 약간의 청각 장애가 있음을 알게 되었다. 팀원은 프로젝트 관리자의 관심에 감사를 표했다. 프로젝트 관리자는 모든 사람이 참여할 수 있도록 회의 시간과 장소를 변경하기로 결정했다. 프로젝트 관리자가 사용한 대인관계 기술은 무엇인가? | 네트워킹 | 갈등 관리 | 감성 지능 | 영향력 행사 |  | C | PM은 감성 지능을 보여주었다—자신과 타인의 개인적 감정 및 집단 감정을 식별, 평가, 관리하는 능력이다. 팀원의 청각 장애를 인식하고 공감을 보이며 회의 장소와 시간을 변경하여 그들의 필요를 수용하는 조치를 취함으로써 PM은 감성 지능을 효과적으로 적용했다. 네트워킹, 갈등 관리, 영향력 행사도 대인관계 기술이지만 이 특정 시나리오에는 적용되지 않는다.
769 | A project manager has developed a communications management plan. A junior team member asks why they are duplicating efforts by producing different versions of the same newsletter. How should the project manager respond? | Explain that each stakeholder expects a different customized newsletter, ensuring it complies to all of their requirements. | Explain that customized newsletters are part of the organizational culture and that following this step- by-step process is of utmost importance. | Explain that to prepare for all situations and as part of risk mitigation, many different newsletters are created just in case they are needed. | Explain that each individual newsletter is based on specific categories of communication for the intended audience. |  | D | When a junior team member questions why different newsletter versions are produced, the project manager should explain that each individual newsletter is based on specific categories of communication for the intended audience. Audience-tailored communication is a core communications management principle. Explaining stakeholder customization requirements (A) is close but less precise. Describing organizational culture (B) cites norms, not best practices. Explaining risk mitigation (C) mischaracterizes the purpose. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 커뮤니케이션 관리 계획을 개발했다. 주니어 팀원이 왜 동일한 뉴스레터의 다른 버전을 만들어 노력을 중복하는지 질문한다. 프로젝트 관리자는 어떻게 대응해야 하는가? | 각 이해관계자가 모든 요구사항에 부합하도록 맞춤화된 다른 뉴스레터를 기대한다고 설명한다. | 맞춤화된 뉴스레터는 조직 문화의 일부이며 이 단계별 프로세스를 따르는 것이 가장 중요하다고 설명한다. | 모든 상황에 대비하고 리스크 완화의 일환으로 필요할 경우를 대비하여 많은 다른 뉴스레터를 작성한다고 설명한다. | 각 개별 뉴스레터는 의도된 수신자를 위한 특정 커뮤니케이션 범주에 기반한다고 설명한다. |  | D | 주니어 팀원이 왜 다른 버전의 뉴스레터를 만드는지 질문할 때, 프로젝트 관리자는 각 개별 뉴스레터가 의도된 수신자를 위한 특정 커뮤니케이션 범주에 기반한다고 설명해야 한다. 수신자 맞춤형 커뮤니케이션은 핵심 커뮤니케이션 관리 원칙이다. 이해관계자 맞춤화 요구사항 설명(A)은 유사하지만 덜 정확하다. 조직 문화 설명(B)은 규범을 인용하지 모범 사례를 인용하지 않는다. 리스크 완화 설명(C)은 목적을 잘못 특성화한다.
770 | A project manager is leading an agile software development project with strict deadlines. The client complained that the last deployment did not meet the acceptance criteria. The development team lead is arguing that the deployment met all specifications and has provided evidence of the client's specifications. What should the project manager do? | Schedule a meeting with all stakeholders to understand what went wrong and who should be held responsible | Seek approval for more time for rework and resolve the issue | Meet with the client and discuss the project deadlines | Review the requirements traceability matrix with the team lead and the client to adequately resolve the issue |  | D | When the client claims a deployment did not meet acceptance criteria but the development team argues it met specifications, the project manager should review the requirements traceability matrix with the team lead and the client. This matrix links requirements through the validation process, helping identify discrepancies between the client's expectations and the team's understanding. Scheduling a meeting to assign blame (A) is counterproductive. Seeking approval for rework time (B) accepts the issue without understanding it. Meeting only with the client to discuss deadlines (C) does not address the root cause of the disagreement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 엄격한 마감일이 있는 애자일 소프트웨어 개발 프로젝트를 이끌고 있다. 고객이 마지막 배포가 수락 기준을 충족하지 못했다고 불만을 제기했다. 개발팀 리더는 배포가 모든 사양을 충족했다고 주장하며 고객의 사양에 대한 증거를 제시했다. 프로젝트 관리자는 무엇을 해야 하는가? | 모든 이해관계자와 회의를 예약하여 무엇이 잘못되었는지, 누가 책임져야 하는지 파악한다. | 재작업을 위한 추가 시간 승인을 구하고 이슈를 해결한다. | 고객과 만나 프로젝트 마감일을 논의한다. | 팀 리더와 고객과 함께 요구사항 추적성 매트릭스를 검토하여 이슈를 적절히 해결한다. |  | D | 고객이 배포가 수락 기준을 충족하지 못했다고 주장하지만 개발팀이 사양을 충족했다고 주장할 때, 프로젝트 관리자는 팀 리더와 고객과 함께 요구사항 추적성 매트릭스를 검토해야 한다. 이 매트릭스는 요구사항을 검증 프로세스를 통해 연결하여 고객의 기대와 팀의 이해 사이의 차이를 식별하는 데 도움이 된다. 책임 추궁을 위한 회의 예약(A)은 비생산적이다. 재작업 시간 승인 요청(B)은 이슈를 이해하지 않고 수용한다. 마감일 논의를 위해 고객만 만나는 것(C)은 불일치의 근본 원인을 다루지 않는다.
771 | A project is delayed due to multiple problems discovered during the quality review. Every time the team addresses one problem, additional problems are encountered. This is frustrating for both the project team and the project sponsor, who are driven to meet the dates and results expected by the organization. What should the project manager do? | Ask the team to commit to a new date to fix all the problems and proceed with a change request to adjust the baseline. | Request that the team identifies, documents, and registers the issues to locate the source of the problems. | Evaluate the cost and schedule variance in order to determine how much the project is off track. | Request that a senior subject matter expert (SME) be hired to analyze and solve the problems. |  | B | When a project faces cascading quality problems where fixing one reveals others, the project manager should request that the team identifies, documents, and registers the issues to locate the source of the problems. Systematic problem documentation enables root cause analysis and prevents recurrence. Asking the team to commit to a new date with a change request (A) does not address the root cause. Evaluating cost and schedule variance (C) measures impact but not cause. Hiring a senior SME (D) adds expertise but does not systematize the problem-solving process. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트가 품질 검토 중 발견된 여러 문제로 지연되고 있다. 팀이 한 문제를 해결할 때마다 추가 문제가 발생한다. 이는 프로젝트 팀과 프로젝트 스폰서 모두에게 좌절감을 주고 있으며, 그들은 조직이 기대하는 날짜와 결과를 충족하려 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에게 모든 문제를 수정할 새 날짜에 커밋하도록 요청하고 기준선을 조정하기 위한 변경 요청을 진행한다. | 팀에게 문제의 원인을 파악하기 위해 이슈를 식별, 문서화, 등록하도록 요청한다. | 프로젝트가 얼마나 벗어났는지 판단하기 위해 비용 및 일정 차이를 평가한다. | 문제를 분석하고 해결하기 위해 시니어 주제 전문가(SME)를 고용하도록 요청한다. |  | B | 하나를 수정하면 다른 문제가 드러나는 연쇄적 품질 문제에 직면할 때, 프로젝트 관리자는 팀에게 문제의 원인을 파악하기 위해 이슈를 식별, 문서화, 등록하도록 요청해야 한다. 체계적인 문제 문서화는 근본 원인 분석을 가능하게 하고 재발을 방지한다. 새 날짜 커밋과 변경 요청(A)은 근본 원인을 다루지 않는다. 비용 및 일정 차이 평가(C)는 영향을 측정하지 원인은 측정하지 않는다. 시니어 SME 고용(D)은 전문성을 추가하지만 문제 해결 프로세스를 체계화하지 않는다.
772 | Stakeholders in some industries prefer to deal with programmers and system analysts directly, bypassing project managers. This complicates managing resources on projects. How should a project manager address this issue? | Request a meeting with senior management to escalate the situation | Propose implementing a new project management information system (PMIS). | Promote adoption of the communications management plan with the project team. | Host a team-building event to develop team cohesion and improve communication |  | C | The PM should manage stakeholder expectations and communication based on the project management plan and stakeholder engagement plan. These documents define how information is shared, at what frequency, and through which channels, ensuring consistent and appropriate communication with all stakeholders. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 일부 산업의 이해관계자들은 프로젝트 관리자를 우회하여 프로그래머 및 시스템 분석가와 직접 거래하는 것을 선호한다. 이는 프로젝트의 자원 관리를 복잡하게 만든다. 프로젝트 관리자는 이 이슈를 어떻게 해결해야 하는가? | 상황을 에스컬레이션하기 위해 상급 경영진과 회의를 요청한다. | 새로운 프로젝트 관리 정보 시스템(PMIS) 구현을 제안한다. | 프로젝트 팀과 함께 커뮤니케이션 관리 계획의 채택을 촉진한다. | 팀 결속력을 개발하고 커뮤니케이션을 개선하기 위해 팀 빌딩 이벤트를 주최한다. |  | C | PM은 프로젝트 관리 계획과 이해관계자 참여 계획에 기반하여 이해관계자 기대와 커뮤니케이션을 관리해야 한다. 이러한 문서는 정보가 공유되는 방법, 빈도, 채널을 정의하여 모든 이해관계자와 일관되고 적절한 커뮤니케이션을 보장한다.
773 | A project manager presented the project schedule to the main stakeholders. They have requested that the project be completed two months earlier than the scheduled date. What should the project manager do? | Reduce the scope of the project by removing activities and shortening the timeline | Update the cost management plan to allocate more resources to the project to finish the scope earlier. | Crash the schedule to shorten the timeline while keeping the scope unchanged | Hold a stakeholder meeting to align timelines and scope expectations. |  | D | When stakeholders request the project be completed two months early, the project manager should hold a stakeholder meeting to align timelines and scope expectations. Collaborative discussion explores feasible options. Reducing scope (A) may not meet requirements. Allocating more resources (B) increases cost without stakeholder alignment. Crashing the schedule (C) increases cost and risk without discussion. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 관리자가 주요 이해관계자에게 프로젝트 일정을 제시했다. 그들은 프로젝트를 예정된 날짜보다 2개월 일찍 완료해 달라고 요청했다. 프로젝트 관리자는 무엇을 해야 하는가? | 활동을 제거하고 일정을 단축하여 프로젝트 범위를 줄인다. | 범위를 더 일찍 완료하기 위해 프로젝트에 더 많은 자원을 할당하도록 비용 관리 계획을 업데이트한다. | 범위를 변경하지 않고 일정을 단축하기 위해 크래싱을 수행한다. | 이해관계자 회의를 개최하여 일정과 범위 기대치를 정렬한다. |  | D | 이해관계자가 프로젝트를 2개월 일찍 완료하도록 요청할 때, 프로젝트 관리자는 이해관계자 회의를 개최하여 일정과 범위 기대치를 정렬해야 한다. 협력적 논의가 실현 가능한 옵션을 탐색한다. 범위 축소(A)는 요구사항을 충족하지 못할 수 있다. 자원 추가 할당(B)은 이해관계자 정렬 없이 비용을 증가시킨다. 크래싱(C)은 논의 없이 비용과 리스크를 증가시킨다.
774 | A project manager is working on a large project with a very difficult client. During the course of the project, the project manager realizes that if the project team had a little more time and funding to make some minor changes, the client could realize the benefits of 25% of the project outcomes early. How should the project manager approach this? | Develop a business case and submit it to the client. | Make all the changes and then show the client the results. | Concentrate on the current project milestones. | Update the project management plan for this new work. |  | A | The PM should develop a business case documenting the estimated costs, benefits, and risks of the proposed changes, then submit it to the client. This communicates the value proposition clearly and seeks client approval. Focusing only on current milestones (A) misses the opportunity for early value delivery. Updating the project plan unilaterally (B) may violate scope baselines. Making changes without approval (D) creates scope creep and damages trust. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Risk | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 관리자가 매우 까다로운 고객과 함께 대규모 프로젝트를 수행하고 있다. 프로젝트 과정에서 프로젝트 관리자는 팀에게 약간의 추가 시간과 자금을 주어 일부 사소한 변경을 하면 고객이 프로젝트 성과의 25%에 대한 혜택을 조기에 실현할 수 있음을 깨달았다. 프로젝트 관리자는 이를 어떻게 접근해야 하는가? | 비즈니스 케이스를 개발하여 고객에게 제출한다. | 모든 변경을 수행한 다음 고객에게 결과를 보여준다. | 현재 프로젝트 마일스톤에 집중한다. | 이 새로운 작업을 위해 프로젝트 관리 계획을 업데이트한다. |  | A | PM은 제안된 변경의 예상 비용, 혜택, 리스크를 문서화한 비즈니스 케이스를 개발하여 고객에게 제출해야 한다. 이는 가치 제안을 명확히 전달하고 고객 승인을 구한다. 현재 마일스톤에만 집중(A)하는 것은 조기 가치 전달 기회를 놓친다. 일방적인 프로젝트 계획 업데이트(B)는 범위 기준선을 위반할 수 있다. 승인 없이 변경(D)하는 것은 범위 변경을 초래하고 신뢰를 손상시킨다.
775 | A project manager regularly sends out project progress reports. However, there have been a few complaints from stakeholders who expressed that the communication does not meet their needs. What should the project manager do? | Communicate progress more frequently to the stakeholders. | Introduce a separate stakeholder engagement meeting. | Analyze the communication needs of the stakeholders. | Communicate the project details to the stakeholders. |  | C | Effective stakeholder management starts with analyzing communication needs. The PM should assess what information each stakeholder requires, in what format, at what frequency, and through which channels. This proactive approach ensures transparent communication and alignment with project objectives, addressing stakeholder concerns before they become obstacles. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 관리자가 정기적으로 프로젝트 진행 보고서를 발송하고 있다. 그러나 커뮤니케이션이 자신의 요구를 충족하지 못한다고 불만을 표한 이해관계자가 여럿 있었다. 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자에게 더 자주 진행 상황을 전달한다. | 별도의 이해관계자 참여 회의를 도입한다. | 이해관계자의 커뮤니케이션 요구를 분석한다. | 이해관계자에게 프로젝트 세부 사항을 전달한다. |  | C | 효과적인 이해관계자 관리는 커뮤니케이션 요구 분석에서 시작된다. PM은 각 이해관계자가 어떤 정보를, 어떤 형식으로, 어떤 빈도로, 어떤 채널을 통해 필요로 하는지 평가해야 한다. 이러한 사전 예방적 접근은 투명한 커뮤니케이션과 프로젝트 목표와의 정렬을 보장하여 이해관계자의 우려가 장애물이 되기 전에 해결한다.
776 | Two days before the end of a sprint, a team member updates the team lead that they will not be able to complete their tasks for the sprint due to a technical difficulty. What should the agile team lead do? | Raise this issue during the daily meeting to determine a possible solution with the team. | Suggest the team member get more technical training in the next quarter. 1283 | Inform the product owner of the issue and request that they reprioritize the delayed task. | Update the risk register to reflect the possible risk of a schedule delay. |  | A | When a team member cannot complete sprint tasks due to a technical difficulty two days before sprint end, the agile team lead should raise the issue during the daily meeting to determine a solution with the team. Team collaboration enables swarming. Suggesting training (B) does not address the current sprint. Informing the PO to reprioritize (C) may follow but team problem-solving comes first. Updating the risk register (D) is a predictive practice. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 스프린트 종료 이틀 전, 팀원이 팀 리더에게 기술적 어려움으로 인해 스프린트 작업을 완료할 수 없다고 업데이트했다. 애자일 팀 리더는 무엇을 해야 하는가? | 일일 회의에서 이 이슈를 제기하여 팀과 함께 가능한 해결책을 결정한다. | 팀원에게 다음 분기에 더 많은 기술 교육을 받도록 제안한다. | 제품 책임자에게 이슈를 알리고 지연된 작업의 재우선순위화를 요청한다. | 일정 지연의 가능한 리스크를 반영하여 리스크 레지스터를 업데이트한다. |  | A | 스프린트 종료 이틀 전 팀원이 기술적 어려움으로 스프린트 작업을 완료할 수 없을 때, 애자일 팀 리더는 일일 회의에서 이슈를 제기하여 팀과 함께 해결책을 결정해야 한다. 팀 협업은 스워밍을 가능하게 한다. 교육 제안(B)은 현재 스프린트를 해결하지 않는다. PO에게 재우선순위화 요청(C)은 후속 조치일 수 있지만 팀 문제 해결이 먼저다. 리스크 레지스터 업데이트(D)는 예측적 실천이다.
777 | A company is moving its headquarters to another city. The project manager responsible for the assignment has been using a predictive approach during the transition. However, the information systems will be migrated using an agile approach. The project manager needs to decide which kind of contract to sign with the vendor responsible for migrating the systems. How should the project manager address this situation? | Confirm payment after each project retrospective | Use fixed-price increments as user stories are completed. | Negotiate payment after all project migration is completed | Sign a single agreement for the whole project |  | B | When migrating information systems using an agile approach within a larger predictive project, the project manager should use fixed-price increments as user stories are completed. This contract type aligns payment with value delivery while providing the flexibility agile requires. Confirming payment after retrospectives (A) does not link payment to delivered value. Negotiating payment after all migration is complete (C) lacks agile flexibility. Signing a single agreement for the whole project (D) does not accommodate iterative delivery. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 회사가 본사를 다른 도시로 이전하고 있다. 전환을 담당하는 프로젝트 관리자는 예측적 접근 방식을 사용해 왔다. 그러나 정보 시스템은 애자일 접근 방식으로 마이그레이션될 예정이다. 프로젝트 관리자는 시스템 마이그레이션을 담당하는 벤더와 어떤 종류의 계약을 체결할지 결정해야 한다. 프로젝트 관리자는 이 상황을 어떻게 해결해야 하는가? | 각 프로젝트 회고 후 대금을 확인한다. | 사용자 스토리가 완료될 때마다 고정가 증분을 사용한다. | 모든 프로젝트 마이그레이션이 완료된 후 대금을 협상한다. | 전체 프로젝트에 대해 단일 계약을 체결한다. |  | B | 더 큰 예측적 프로젝트 내에서 애자일 접근 방식으로 정보 시스템을 마이그레이션할 때, 프로젝트 관리자는 사용자 스토리가 완료될 때마다 고정가 증분을 사용해야 한다. 이 계약 유형은 대금을 가치 전달에 맞추면서 애자일에 필요한 유연성을 제공한다. 회고 후 대금 확인(A)은 대금을 전달된 가치에 연결하지 않는다. 모든 마이그레이션 완료 후 대금 협상(C)은 애자일 유연성이 부족하다. 전체 프로젝트에 대한 단일 계약(D)은 반복적 전달을 수용하지 않는다.
778 | A project manager for an iterative project received feedback from an on-site team member that the virtual team was not meeting the deliverables on time. The project manager gathered details on what the status report should contain in order to track deliverables. What is the remedial action the project manager should take? | Add status report creation as a product backlog item | Add status reports to the communications management plan | Convene an on-site meeting for both of the teams | Perform stakeholder engagement with the virtual team |  | D | When on-site team members report that the virtual team is not meeting deliverables, the project manager should perform stakeholder engagement with the virtual team. Proactive engagement addresses the root cause by improving communication, visibility, and collaboration with remote members. Adding status reports to the backlog (A) treats reporting as a feature. Adding to the communications plan (B) is process-focused. Convening an on-site meeting (C) may not be feasible for virtual teams. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 반복적 프로젝트의 프로젝트 관리자가 현장 팀원으로부터 가상 팀이 산출물을 제때에 충족하지 못하고 있다는 피드백을 받았다. 프로젝트 관리자는 상태 보고서에 포함되어야 할 내용에 대한 세부 사항을 수집하여 산출물을 추적했다. 프로젝트 관리자가 취해야 할 시정 조치는 무엇인가? | 상태 보고서 작성을 제품 백로그 항목으로 추가한다. | 커뮤니케이션 관리 계획에 상태 보고서를 추가한다. | 두 팀 모두를 위한 현장 회의를 소집한다. | 가상 팀과 이해관계자 참여를 수행한다. |  | D | 현장 팀원이 가상 팀이 산출물을 충족하지 못한다고 보고할 때, 프로젝트 관리자는 가상 팀과 이해관계자 참여를 수행해야 한다. 사전 예방적 참여는 원격 구성원과의 커뮤니케이션, 가시성, 협업을 개선하여 근본 원인을 해결한다. 상태 보고서를 백로그에 추가(A)하는 것은 보고를 기능으로 취급한다. 커뮤니케이션 계획에 추가(B)는 프로세스 중심적이다. 현장 회의 소집(C)은 가상 팀에는 실현 불가능할 수 있다.
779 | A project manager has been approached by the project sponsor about adding to the project scope. How should the project manager accommodate this request? | Disregard the request since the project scope is finalized | Update the project team about the change request | Create a change request lor the change control board (CCB) to review | Adjust the project schedule to accommodate the new project scope requests |  | C | When a project sponsor requests additions to the project scope, the project manager must follow the formal change management process. The correct action is to create a change request for the change control board (CCB) to review. The CCB evaluates proposed changes against the project's objectives, constraints, timeline, and resource availability before making an informed decision. Disregarding the request (A) is inappropriate—even if scope is finalized, changes may still be valid and must go through the proper process. Simply updating the team (B) skips the evaluation and approval step. Adjusting the schedule to accommodate the new scope (D) assumes approval before the change has been formally assessed and authorized. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Change Management | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 스폰서가 프로젝트 범위에 추가하는 것에 대해 프로젝트 관리자에게 접근했다. 프로젝트 관리자는 이 요청을 어떻게 수용해야 하는가? | 프로젝트 범위가 확정되었으므로 요청을 무시한다. | 프로젝트 팀에게 변경 요청에 대해 업데이트한다. | 변경 통제 위원회(CCB)가 검토하도록 변경 요청을 작성한다. | 새로운 프로젝트 범위 요청을 수용하기 위해 프로젝트 일정을 조정한다. |  | C | 프로젝트 스폰서가 프로젝트 범위 추가를 요청할 때, 프로젝트 관리자는 공식적인 변경 관리 프로세스를 따라야 한다. 올바른 조치는 변경 통제 위원회(CCB)가 검토하도록 변경 요청을 작성하는 것이다. CCB는 프로젝트의 목표, 제약, 일정, 자원 가용성에 대해 제안된 변경을 평가한 후 정보에 입각한 결정을 내린다. 요청 무시(A)는 부적절하다—범위가 확정되었더라도 변경은 여전히 유효할 수 있으며 적절한 프로세스를 거쳐야 한다. 단순히 팀에 업데이트(B)하는 것은 평가와 승인 단계를 건너뛴다. 새 범위를 수용하기 위해 일정 조정(D)은 변경이 공식적으로 평가되고 승인되기 전에 승인을 가정한다.
780 | A project manager is working on a project to build a manufacturing complex. The project will run in three different phases: engineering, procurement, and construction. The procurement phase is in the initiation stage. The project sponsor wants to pursue the project phases as they have been planned, but also wants to accommodate and adjust to new data, input from the customer, and changes during the various phases as the project progresses. How should the project manager approach this project? | Apply a predictive project management approach. | Evaluate and decide on a phased project management approach. | Implement an adaptive project management approach. | Use a hybrid model to combine predictive and adaptive life cycles. |  | D | When the sponsor wants to pursue planned project phases but also accommodate new data, customer input, and changes, the project manager should use a hybrid model combining predictive and adaptive life cycles. Hybrid balances structured phasing with adaptive flexibility. A purely predictive approach (A) cannot accommodate changes. A phased approach alone (B) does not ensure adaptability. A purely adaptive approach (C) may not preserve the structured phases the sponsor wants. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Scope | Planning | Be an Accountable Leader | Collect Requirements | Hybrid/Tailoring | 프로젝트 관리자가 제조 단지를 건설하는 프로젝트를 수행하고 있다. 프로젝트는 세 가지 다른 단계로 진행된다: 설계, 조달, 시공. 조달 단계는 착수 단계에 있다. 프로젝트 스폰서는 계획된 대로 프로젝트 단계를 추진하되 프로젝트가 진행됨에 따라 새로운 데이터, 고객 입력, 변경을 수용하고 조정하길 원한다. 프로젝트 관리자는 이 프로젝트를 어떻게 접근해야 하는가? | 예측적 프로젝트 관리 접근 방식을 적용한다. | 단계별 프로젝트 관리 접근 방식을 평가하고 결정한다. | 적응형 프로젝트 관리 접근 방식을 구현한다. | 예측적 및 적응형 생명주기를 결합한 하이브리드 모델을 사용한다. |  | D | 스폰서가 계획된 프로젝트 단계를 추진하되 새로운 데이터, 고객 입력, 변경도 수용하길 원할 때, 프로젝트 관리자는 예측적 및 적응형 생명주기를 결합한 하이브리드 모델을 사용해야 한다. 하이브리드는 구조화된 단계와 적응적 유연성을 균형 있게 제공한다. 순수 예측적 접근(A)은 변경을 수용할 수 없다. 단계별 접근만(B)으로는 적응성을 보장하지 않는다. 순수 적응형 접근(C)은 스폰서가 원하는 구조화된 단계를 보존하지 못할 수 있다.
781 | A construction company is executing a building contract that includes firm milestones for replacing certain components of the building. During execution, the client complains that the new components do not meet the requirements. What should the project manager have done to prevent this from happening? | Defined acceptance criteria in a quality checklist agreed upon before starting the build phase | Approved a detailed change management process before starting the build phase | Continuously communicated the changes in the work plan and the agreement to the client | Provided compensation for issues due to the variance in the agreed-upon requirements |  | A | When a client complains that replaced building components do not meet requirements, the project manager should have defined acceptance criteria in a quality checklist agreed upon before starting the build phase. Clear, pre-agreed criteria ensure shared understanding of expected standards. Approving a detailed change management process (B) addresses change but not acceptance criteria. Continuously communicating work plan changes (C) is informative but not preventive. Providing compensation for variances (D) is reactive. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 건설회사가 건물의 특정 구성요소를 교체하는 확정 마일스톤을 포함하는 건물 계약을 실행하고 있다. 실행 중 고객이 새 구성요소가 요구사항을 충족하지 않는다고 불만을 제기한다. 프로젝트 관리자는 이를 방지하기 위해 무엇을 했어야 하는가? | 건설 단계 시작 전에 합의된 품질 체크리스트에 수락 기준을 정의했어야 한다. | 건설 단계 시작 전에 상세한 변경 관리 프로세스를 승인했어야 한다. | 작업 계획과 합의의 변경 사항을 고객에게 지속적으로 전달했어야 한다. | 합의된 요구사항의 차이로 인한 문제에 대해 보상을 제공했어야 한다. |  | A | 고객이 교체된 건물 구성요소가 요구사항을 충족하지 않는다고 불만을 제기할 때, 프로젝트 관리자는 건설 단계 시작 전에 합의된 품질 체크리스트에 수락 기준을 정의했어야 한다. 명확하고 사전 합의된 기준은 기대 기준에 대한 공유된 이해를 보장한다. 상세한 변경 관리 프로세스 승인(B)은 변경을 다루지 수락 기준은 다루지 않는다. 작업 계획 변경 지속적 전달(C)은 정보제공이지만 예방적이지 않다. 차이에 대한 보상 제공(D)은 반응적이다.
782 | A company is transitioning from a predictive to an agile approach. During the last two sprint reviews, the product owner complained about the development team, indicating that the increments do not meet the acceptance criteria defined in the user stories. The development team complained about the product owner, who is defining sprint backlog items, because the backlog items cannot be delivered during the 2-week sprints agreed to at the beginning of the project. How should the project manager resolve this situation in their new role as servant leader? | Review the organizational process assets (OPAs) to find similar situations and review the resolution actions taken, | Extend the sprints to 3 weeks to allow the work requested by the product owner to be completed. | Request that the team use the next sprint to complete all technical debt remaining from the previous sprints. | Encourage the whole team to be empowered and accountable for the decisions made according to their roles, |  | D | In agile, the team is self-organizing and empowered to make decisions within their roles. The servant leader should encourage the whole team to be empowered and accountable—the product owner prioritizes the product backlog, and the development team determines how much work can be committed to each sprint. Reviewing OPAs (A) may provide historical context but does not directly address the current team dynamics. Extending sprints to 3 weeks (B) treats the symptom rather than the cause and undermines the agreed sprint cadence. Requesting the team complete all technical debt in one sprint (C) diverts focus from the core issue of role clarity and collaboration between the product owner and development team. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 회사가 예측적에서 애자일 접근 방식으로 전환 중이다. 지난 두 번의 스프린트 리뷰에서 제품 책임자가 개발팀에 대해 불만을 제기하며 증분이 사용자 스토리에 정의된 수락 기준을 충족하지 못한다고 했다. 개발팀은 제품 책임자가 스프린트 백로그 항목을 정의하는 것에 대해 불만을 제기하며 프로젝트 초기에 합의된 2주 스프린트 내에 전달할 수 없다고 했다. 프로젝트 관리자는 서번트 리더로서의 새로운 역할에서 이 상황을 어떻게 해결해야 하는가? | 유사한 상황을 찾고 취한 해결 조치를 검토하기 위해 조직 프로세스 자산(OPA)을 검토한다. | 제품 책임자가 요청한 작업을 완료할 수 있도록 스프린트를 3주로 연장한다. | 팀에게 다음 스프린트를 사용하여 이전 스프린트에서 남은 모든 기술 부채를 완료하도록 요청한다. | 전체 팀이 역할에 따른 의사결정에 권한을 부여받고 책임을 지도록 격려한다. |  | D | 애자일에서 팀은 자기 조직화되고 역할 내에서 의사결정 권한을 부여받는다. 서번트 리더는 전체 팀이 권한을 부여받고 책임을 지도록 격려해야 한다—제품 책임자는 제품 백로그를 우선순위화하고, 개발팀은 각 스프린트에 얼마나 많은 작업을 수행할 수 있는지 결정한다. OPA 검토(A)는 역사적 맥락을 제공하지만 현재 팀 역학을 직접 해결하지 않는다. 스프린트 3주 연장(B)은 원인이 아닌 증상을 치료하며 합의된 스프린트 주기를 약화시킨다. 다음 스프린트에 모든 기술 부채 완료 요청(C)은 역할 명확성과 제품 책임자-개발팀 협업의 핵심 문제에서 초점을 볬어나게 한다.
783 | A project manager works in a startup company and is in charge of a key project that has critical and time-sensitive delivery objectives. One of the project team members missed completing an assigned deliverable on time, despite repeated assurances from the team member that it would be completed on time. What should the project manager do next? | Hold a team meeting to discuss team member commitments and communications | Record the issue then refocus the team ' s efforts on delivering the next set of deliverables | Give the team member a formal warning for the negative impact due to failure to delrver and not meet deadlines | Meet with the team member and work on a development plan for them to avoid missed deliverables in the future |  | D | When a team member in a startup project repeatedly fails to deliver on time despite assurances, the project manager should meet with the team member and work on a development plan to avoid future missed deliverables. Coaching addresses the root cause. Holding a team meeting about commitments (A) is general. Recording the issue and moving on (B) does not address the individual. Issuing a formal warning (C) is punitive without understanding. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Resources | Executing | Adopt a Holistic View | Acquire Resources | Traditional PM | PM이 스타트업 회사에서 핵심 프로젝트를 담당하고 있다. 팀원 한 명이 반복적으로 납기를 놓치면서도 다음에는 맞추겠다고 약속한다. PM은 무엇을 해야 하는가? | 팀 회의를 열어 팀원 약속과 커뮤니케이션을 논의한다 | 이슈를 기록하고 팀이 다음 인도물에 집중하도록 재정비한다 | 납품 실패와 기한 미준수의 부정적 영향에 대해 팀원에게 공식 경고를 한다 | 팀원과 만나 향후 인도물 누락을 방지하기 위한 개발 계획을 수립한다 |  | D | 스타트업 프로젝트에서 팀원이 반복적으로 납기를 놓칠 때, PM은 팀원과 만나 향후 인도물 누락을 방지하기 위한 개발 계획을 수립해야 한다. 코칭이 근본 원인을 해결한다. 팀 회의(A)는 개인 문제를 공개한다. 이슈 기록(B)은 능동적 해결이 아니다. 공식 경고(C)는 징벌적이다.
784 | After a meeting with the customer, the project manager receives special recognition because the project is always on schedule. Later that day, the project manager attends a regular project team meeting to follow up on the status of the deliverables. What should the project manager do in the project team meeting? | Document this feedback in the meeting minutes. | Share the customer feedback with the project team | Follow the meeting agenda and make a list of the next deliverables | Start planning how to improve the dates of next deliverables |  | B | When the project manager receives special recognition from the customer for on-time delivery, they should share the customer feedback with the project team during the team meeting. Sharing positive feedback motivates and acknowledges team efforts. Documenting in meeting minutes (A) records but does not acknowledge. Following the agenda and listing deliverables (C) ignores the recognition opportunity. Planning to improve dates (D) is unrelated and may undermine the positive feedback. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | Scope & Requirements Mgmt | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 고객 회의 후 PM이 프로젝트가 항상 일정에 맞다는 특별한 인정을 받았다. 같은 날 팀 회의에서 PM은 무엇을 해야 하는가? | 이 피드백을 회의록에 문서화한다 | 고객 피드백을 프로젝트 팀과 공유한다 | 회의 안건을 따르고 다음 인도물 목록을 만든다 | 다음 인도물의 일정을 개선하는 방법을 계획한다 |  | B | PM이 고객으로부터 일정 준수에 대한 인정을 받으면, 팀 회의에서 고객 피드백을 프로젝트 팀과 공유해야 한다. 긍정적 피드백 공유가 팀에 동기를 부여하고 노력을 인정한다. 회의록 문서화(A)는 팀에 전달되지 않는다. 안건 진행(C)은 인정 기회를 놓친다. 일정 개선 계획(D)은 현재 성과 인정이 아니다.
785 | An agile team wants to maximize the work delivered for the upcoming project that involves considerable product complexity. What should the project manager do to help improve the team's collaboration approach? | Meet with the human resources (HR) department to ask for team support. | Compare the team ' s velocity with other teams in the organization. | Follow the process of the most successful team in the organization. | Focus on the team ' s engagement during the next retrospective meeting. |  | D | To help an agile team maximize work delivery on a complex product, the project manager should focus on the team's engagement during the next retrospective meeting. Retrospectives are dedicated to reflecting on processes, discussing what worked and what did not, and identifying collaborative improvements. This drives continuous improvement and strengthens team collaboration. Meeting with HR for team support (A) escalates externally. Comparing velocity with other teams (B) creates unhelpful competition. Following another team's process (C) ignores the current team's unique context and dynamics. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 애자일 팀이 상당한 제품 복잡성을 가진 프로젝트의 작업 납품을 극대화하고자 한다. PM은 무엇을 해야 하는가? | 인사부(HR)에 팀 지원을 요청한다 | 팀 속도를 조직 내 다른 팀과 비교한다 | 조직에서 가장 성공적인 팀의 프로세스를 따른다 | 다음 회고 회의에서 팀의 참여도에 집중한다 |  | D | 복잡한 제품에서 작업 납품을 극대화하려면, PM은 다음 회고 회의에서 팀의 참여도에 집중해야 한다. 회고는 프로세스를 반성하고 개선점을 논의하는 전용 시간이다. HR 지원(A)은 간접적이다. 속도 비교(B)는 비생산적이다. 다른 팀 프로세스(C)는 팀 고유 상황에 맞지 않을 수 있다.
786 | During a daily standup meeting, a roadblock was raised that is preventing one of the team members from proceeding with work. The project manager figures out that it is due to a technical issue. What should the project manager do to prioritize this critical impediment? | Solve the issue for the team member. | Escalate the issue to the software vendor for technical resolution | Coach the team to come up with their own solution and add it to the next sprint | Perform a brainstorming session to address the issue and add the solution to the sprint. |  | D | When a technical roadblock prevents a team member from proceeding, the project manager should perform a brainstorming session to address the issue and add the solution to the sprint. Collaborative problem-solving leverages the team's collective expertise while keeping the solution within the current sprint. Solving the issue for the team member (A) does not empower the team. Escalating to the software vendor (B) may be slow. Coaching the team and adding to the next sprint (C) delays resolution unnecessarily. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 데일리 스탠드업 회의에서 팀원의 작업 진행을 방해하는 장애물이 제기되었다. PM이 이를 파악했다. PM은 무엇을 해야 하는가? | 팀원을 위해 이슈를 직접 해결한다 | 기술적 해결을 위해 소프트웨어 벤더에 이슈를 에스컬레이션한다 | 팀이 자체적으로 해결책을 도출하도록 코칭하고 다음 스프린트에 추가한다 | 이슈를 해결하기 위한 브레인스토밍 세션을 수행하고 해결책을 스프린트에 추가한다 |  | D | 기술적 장애물이 팀원의 진행을 방해할 때, PM은 브레인스토밍 세션을 수행하여 이슈를 해결하고 해결책을 스프린트에 추가해야 한다. 협력적 문제 해결이 팀의 집단 전문성을 활용한다. 직접 해결(A)은 팀 역량을 무시한다. 벤더 에스컬레이션(B)은 팀 참여가 없다. 코칭 후 다음 스프린트(C)는 즉각성이 부족하다.
787 | In a standup meeting, a team member has been providing the same update for five consecutive days. The task, which is on the critical path, is now at risk for delaying the schedule. What should the project manager do? | Keep the project sponsor informed about the delay | Ask the team member if there is an impediment and help to remove the blockers | Support the team member by providing one more resource to complete the task immediately | Reassign the task to another member of the team |  | B | When a team member provides the same update for consecutive days on a critical-path task, the PM should investigate whether an impediment exists. In agile practice, daily standups surface blockers that need to be resolved. The PM should proactively ask about impediments and facilitate their removal to keep the project on track and prevent schedule delays. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 스탠드업 회의에서 팀원이 5일 연속 같은 업데이트를 하고 있다. 주공정선(CP) 작업이 리스크에 처해 있다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 지연을 알린다 | 팀원에게 장애물이 있는지 물어보고 방해 요소를 제거하도록 돕는다 | 작업을 즉시 완료하기 위해 추가 자원을 제공하여 팀원을 지원한다 | 작업을 팀의 다른 팀원에게 재할당한다 |  | B | 팀원이 주공정선 작업에서 연속 같은 업데이트를 할 때, PM은 장애물이 있는지 조사해야 한다. 애자일에서 데일리 스탠드업은 해결해야 할 방해 요소를 표면화한다. PM이 능동적으로 장애물을 파악하고 제거해야 한다. 스폰서 알림(A)은 해결이 아니다. 추가 자원(C)은 근본 원인을 모른다. 재할당(D)은 성급하다.
788 | A state-of-the-art product was delivered at the end of a project life cycle. However, the customer claims the product was not designed to specifications. What should the project manager have done to avoid this issue? | The iteration review planning meeting should have been planned accordingly. | The sprint retrospective meeting should have included necessary stakeholders. | The customer ' s requirements should have been captured in order to meet the customer ' s standards. | The customer ' s requirements should have been captured and modified to meet the supplier's standards. |  | C | When a customer claims the delivered product was not designed to specifications, the project manager should have ensured customer requirements were properly captured to meet customer standards. Requirements elicitation is foundational. Planning iteration review meetings (A) addresses feedback cadence, not requirement capture. Including stakeholders in retrospectives (B) is internal-focused. Modifying requirements to meet supplier standards (D) reverses the priority — customer needs come first. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 프로젝트 수명주기 종료 시 최첨단 제품이 납품되었다. 그러나 고객이 제품이 사양에 맞게 설계되지 않았다고 주장한다. 무엇을 했어야 하는가? | 이터레이션 검토 계획 회의가 적절히 계획되었어야 했다 | 스프린트 회고 회의에 필요한 이해관계자가 포함되었어야 했다 | 고객의 기준을 충족하기 위해 고객 요구사항이 제대로 수집되었어야 했다 | 공급자 기준을 충족하도록 고객 요구사항이 수집되고 수정되었어야 했다 |  | C | 고객이 납품된 제품이 사양에 맞지 않다고 주장할 때, 고객 기준을 충족하기 위해 고객 요구사항이 제대로 수집되었어야 했다. 요구사항 도출이 기본이다. 이터레이션 검토(A)는 부분적이다. 회고 참여(B)는 요구사항 수집이 아니다. 공급자 기준 수정(D)은 고객 중심이 아니다.
789 | During the initial phase of a construction project, the team is confused about the safety requirements it needs to consider during implementation. The project manager recently met with the client to define the project scope. How should the project manager share this information? | Meet with the team and present the scope of the safety requirements. | Send an email to the team with the details of the safety requirements. | Modify the project charter by including the safety requirements. | Distribute the security requirements during the project execution phase. |  | A | When the team is confused about safety requirements after the PM defined scope with the client, the project manager should meet with the team and present the scope of the safety requirements. Direct presentation ensures clarity. Sending an email (B) is impersonal for important safety information. Modifying the charter (C) is a document change, not communication. Distributing during execution (D) is too late. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Stakeholders | Initiating | Adopt a Holistic View | Identify Stakeholders | Traditional PM | 건설 프로젝트 초기 단계에서 팀이 구현 시 고려해야 할 안전 요구사항에 대해 혼란스러워한다. PM은 무엇을 해야 하는가? | 팀과 만나 안전 요구사항의 범위를 발표한다 | 팀에게 안전 요구사항의 세부 사항을 이메일로 보낸다 | 안전 요구사항을 포함하여 프로젝트 헌장을 수정한다 | 프로젝트 실행 단계에서 보안 요구사항을 배포한다 |  | A | PM이 고객과 범위를 정의한 후 팀이 안전 요구사항에 혼란스러울 때, PM은 팀과 만나 안전 요구사항의 범위를 발표해야 한다. 직접적인 발표가 명확성을 보장한다. 이메일(B)은 일방적이며 질문 기회가 없다. 헌장 수정(C)은 과도하다. 실행 단계 배포(D)는 너무 늦다.
790 | In the middle of the execution phase for a big project, a new stakeholder who was unfamiliar with the project joined the board of directors and is influencing the decisions made in the project. This change is impacting the project's progress. What should the project manager do first? | Update the risk register with a new risk | Inform the client about the change | Revise the project schedule | Present the project to the stakeholder |  | D | When a new, unfamiliar stakeholder joins the board of directors and influences project decisions negatively, the project manager should first present the project to the stakeholder. Providing a clear understanding of objectives, scope, and constraints aligns the stakeholder's expectations with project goals. Updating the risk register (A) documents but does not engage the stakeholder. Informing the client (B) is indirect. Revising the schedule (C) accepts the impact without addressing the cause. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 대형 프로젝트 실행 중반에 프로젝트에 익숙하지 않은 새 이해관계자가 이사회에 합류하여 프로젝트 결정에 부정적 영향을 미친다. PM은 무엇을 먼저 해야 하는가? | 새 리스크로 리스크 등록부를 업데이트한다 | 고객에게 변경을 알린다 | 프로젝트 일정을 수정한다 | 이해관계자에게 프로젝트를 발표한다 |  | D | 프로젝트에 익숙하지 않은 새 이해관계자가 이사회에 합류하여 부정적 영향을 미칠 때, PM은 먼저 이해관계자에게 프로젝트를 발표해야 한다. 목적, 범위, 제약에 대한 명확한 이해를 제공하면 부정적 영향이 줄어든다. 리스크 등록부(A)는 대응이지 해결이 아니다. 고객 알림(B)은 불필요하다. 일정 수정(C)은 시기상조이다.
791 | A project manager is assigned to a multiyear enterprise resource planning (ERP) solution project. During planning, the business sponsor emphasizes the importance of demonstrating value along the way, while maintaining the integrity of the final product. How should the project manager establish the delivery model for this project? | Schedule routine demos on features completed and deliver a single product once all features are completed. | Reestablish the project as a program with multiple small projects, as each project will be delivered as a product of its own. | Communicate the latest status to the steering committee and provide a demo of the features completed. | Organize the project into multiple subsets based on business functions and deliver each subset as a component of the final product. |  | D | When a multiyear ERP project sponsor emphasizes demonstrating value throughout while maintaining final product integrity, the project manager should organize the project into multiple subsets based on business functions and deliver each as a component. Incremental delivery by business function demonstrates value progressively. Routine demos with single delivery (A) delays value realization. Reestablishing as a program (B) adds overhead. Communicating status and demos (C) provides visibility but not incremental value delivery. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | PM이 다년간의 ERP 솔루션 프로젝트에 배정되었다. 스폰서가 최종 제품의 무결성을 유지하면서 가치를 지속적으로 보여줄 것을 강조한다. PM은 무엇을 해야 하는가? | 완료된 기능에 대한 정기적 데모를 일정에 잡고 모든 기능 완료 후 단일 제품으로 납품한다 | 각 프로젝트가 제품으로 납품되도록 여러 소규모 프로젝트가 있는 프로그램으로 재설정한다 | 운영위원회에 최신 상태를 전달하고 완료된 기능의 데모를 제공한다 | 비즈니스 기능별로 프로젝트를 여러 하위 집합으로 구성하고 각 하위 집합을 최종 제품의 구성 요소로 납품한다 |  | D | 다년간의 ERP 프로젝트에서 스폰서가 가치 시연과 제품 무결성을 모두 강조할 때, PM은 비즈니스 기능별로 프로젝트를 하위 집합으로 구성하고 각각을 최종 제품의 구성 요소로 납품해야 한다. 점진적 납품이 가치를 보여주면서 통합성을 유지한다. 데모만(A)은 실제 가치 전달이 아니다. 프로그램 재설정(B)은 과도하다. 상태 전달(C)은 가치 전달이 아니다.
792 | A new project manager is assigned to a project midway through its implementation. During the first risk review meeting, the project manager notices that the version of the risk register used by the project team members is different from the one the project manager is using. What should the project manager have done to avoid this issue? | Referred to the communications management plan | Performed expert judgment | Validated the issue log | Validated the project artifacts |  | D | When the project team uses a different version of the risk register than the project manager, the project manager should have validated the project artifacts. Proper validation through configuration management and version control ensures all stakeholders use current, approved documents. Referring to the communications management plan (A) addresses distribution but not version control. Performing expert judgment (B) provides advice but not artifact validation. Validating the issue log (C) addresses only one document. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 새 PM이 구현 중간에 프로젝트에 배정되었다. 첫 리스크 검토 회의에서 팀이 PM과 다른 버전의 리스크 등록부를 사용하고 있음을 발견했다. PM이 이전에 무엇을 했어야 하는가? | 커뮤니케이션 관리 계획을 참조했다 | 전문가 판단을 수행했다 | 이슈 로그를 검증했다 | 프로젝트 산출물을 검증했다 |  | D | 프로젝트 팀이 PM과 다른 버전의 리스크 등록부를 사용할 때, PM은 프로젝트 산출물을 검증했어야 한다. 구성 관리와 버전 관리를 통한 적절한 검증이 모든 이해관계자가 같은 최신 문서를 사용하도록 보장한다. 커뮤니케이션 계획(A)은 문서 버전이 아닌 소통 방법을 다룬다. 전문가 판단(B)은 문서 검증이 아니다. 이슈 로그(C)는 관련이 없다.
793 | A project manager has been assigned to take over an existing software project. The project manager inherited a lean team comprised of key stakeholders, subject matter experts (SMEs), and senior developers. While reviewing the project status with the team, the project manager observes that the team seems to lack direction and enthusiasm. What should the new project manager do? | Organize frequent team building sessions and update the risk register. | Meet with the project sponsor and propose a corrective action for the project. | Encourage participation in decision making and empower the team. | Ensure everyone performs their assigned tasks as planned. |  | C | When inheriting a lean team of key stakeholders, SMEs, and senior developers who lack direction and enthusiasm, the new project manager should encourage participation in decision-making and empower the team. This builds trust, collaboration, and ownership—addressing the root causes of low morale. Ensuring tasks are performed as planned (D) implies micromanagement. Organizing team-building sessions and updating the risk register (A) are supplementary but insufficient alone. Meeting with the sponsor to propose corrective action (B) escalates without first addressing the team directly. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 관리자가 기존 소프트웨어 프로젝트를 인수하도록 배정되었다. 프로젝트 관리자는 핵심 이해관계자, 주제 전문가(SME), 시니어 개발자로 구성된 소규모 팀을 인수했다. 팀과 프로젝트 상태를 검토하면서 프로젝트 관리자는 팀이 방향성과 열정이 부족한 것으로 관찰했다. 새 프로젝트 관리자는 무엇을 해야 하는가? | 빈번한 팀 빌딩 세션을 조직하고 리스크 레지스터를 업데이트한다. | 프로젝트 스폰서와 만나 프로젝트에 대한 시정 조치를 제안한다. | 의사결정 참여를 장려하고 팀에 권한을 부여한다. | 모든 사람이 계획대로 배정된 작업을 수행하도록 보장한다. |  | C | 핵심 이해관계자, SME, 시니어 개발자로 구성된 소규모 팀이 방향성과 열정이 부족할 때, 새 프로젝트 관리자는 의사결정 참여를 장려하고 팀에 권한을 부여해야 한다. 이는 신뢰, 협력, 주인의식을 구축하여 사기 저하의 근본 원인을 해결한다. 계획대로 작업 수행 보장(D)은 마이크로매니지먼트를 암시한다. 팀 빌딩 세션 조직 및 리스크 레지스터 업데이트(A)는 보조적이지만 단독으로는 불충분하다. 스폰서에게 시정 조치 제안(B)은 팀을 직접 다루지 않고 에스컬레이션한다.
794 | A project stakeholder complained that they did not receive an important delivery that was stated in the schedule. The team member responsible for this deliverable explained that they sent an email to the stakeholder, advising them that the deliverable would not be delivered on time. What should the project manager have done to avoid this situation? | Ensured that the team member did not communicate directly with the project stakeholder. | Confirmed that the stakeholder was made aware of the delivery delay. | Told the team member to send the unfinished deliverable to the stakeholder and finalize it later. | Communicated with the stakeholder directly regarding the delivery delay. |  | D | When a team member emailed a stakeholder about a delivery delay but the stakeholder missed it, the project manager should have communicated with the stakeholder directly regarding the delivery delay. Direct communication ensures important information is received and expectations are managed effectively. Preventing team members from communicating with stakeholders (A) is overly restrictive. Confirming stakeholder awareness (B) is follow-up, not prevention. Sending the unfinished deliverable (C) compromises quality. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 이해관계자가 일정에 명시된 중요한 산출물을 받지 못했다고 불만을 제기했다. 이 산출물을 담당하는 팀원은 이해관계자에게 산출물이 제시간에 전달되지 않을 것이라고 알리는 이메일을 보냈다고 설명했다. 프로젝트 관리자는 이 상황을 방지하기 위해 무엇을 했어야 하는가? | 팀원이 프로젝트 이해관계자와 직접 소통하지 않도록 보장했어야 한다. | 이해관계자가 전달 지연을 인지했는지 확인했어야 한다. | 팀원에게 미완성 산출물을 이해관계자에게 보내고 나중에 마무리하도록 지시했어야 한다. | 전달 지연에 관해 이해관계자와 직접 소통했어야 한다. |  | D | 팀원이 이해관계자에게 전달 지연에 대해 이메일을 보냈지만 이해관계자가 놓쳤을 때, 프로젝트 관리자는 전달 지연에 관해 이해관계자와 직접 소통했어야 한다. 직접 소통은 중요한 정보가 수신되고 기대가 효과적으로 관리되도록 보장한다. 팀원의 소통 방지(A)는 지나치게 제한적이다. 이해관계자 인지 확인(B)은 후속 조치이지 예방이 아니다. 미완성 산출물 전송(C)은 품질을 손상시킨다.
795 | A project manager has just finished initiating a project. While planning, the project manager notes that several essential team members do not have the required skills for key tasks later in the project. What should the project manager do first? | Replace the current project team members | Update the issue log to account for the lack of team member qualifications | Develop the resource management plan and ensure adequate training | Outsource the task to be completed by a specialized vendor. |  | C | When several essential team members lack required skills for key tasks later in the project, the project manager should first develop the resource management plan and ensure adequate training. Proactive planning addresses skill gaps before they impact delivery. Replacing team members (A) is disruptive. Updating the issue log (B) documents the problem without solving it. Outsourcing (D) may not be necessary if training is feasible. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Cost & Resource Management | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 프로젝트 착수를 막 완료했다. 계획 중에 프로젝트 관리자는 여러 필수 팀원이 프로젝트 후반의 핵심 작업에 필요한 기술을 갖추지 못했음을 발견했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 현재 프로젝트 팀원을 교체한다. | 팀원 자격 부족을 반영하여 이슈 로그를 업데이트한다. | 자원 관리 계획을 개발하고 적절한 교육을 보장한다. | 전문 벤더에게 작업을 아웃소싱한다. |  | C | 여러 필수 팀원이 프로젝트 후반의 핵심 작업에 필요한 기술이 부족할 때, 프로젝트 관리자는 먼저 자원 관리 계획을 개발하고 적절한 교육을 보장해야 한다. 사전 예방적 계획은 기술 격차가 전달에 영향을 미치기 전에 해결한다. 팀원 교체(A)는 파괴적이다. 이슈 로그 업데이트(B)는 문제를 문서화하지만 해결하지 않는다. 아웃소싱(D)은 교육이 가능하다면 불필요할 수 있다.
796 | A project manager was recently appointed to an agile project. The project will have a lot of visibility and impact for the company, so the project management office (PMO) manager wants to ensure that the project manager manages the risks correctly. What should the project manager do? | Implement the role of an agile risk manager to take care of the risk management process. | Follow the risk management process while ensuring that risks are identified, analyzed, and managed during each iteration. | Ask the product owner to act as a risk manager to assist with the remediation of risks. | Implement the agile risk manifesto to ensure the proper tracking, analysis, and remediation of the project risks. |  | B | When the PMO wants to ensure correct risk management on a high-visibility agile project, the project manager should follow the risk management process while ensuring risks are identified, analyzed, and managed during each iteration. Iterative risk management aligns with agile practices. Implementing an agile risk manager role (A) adds unnecessary overhead. Asking the PO to act as risk manager (C) conflates roles. Implementing an agile risk manifesto (D) is not a standard practice. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트 관리자가 최근 애자일 프로젝트에 임명되었다. 이 프로젝트는 회사에 높은 가시성과 영향을 미칠 것이므로 프로젝트 관리 오피스(PMO) 관리자는 프로젝트 관리자가 리스크를 올바르게 관리하도록 보장하고자 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 리스크 관리 프로세스를 담당할 애자일 리스크 관리자 역할을 구현한다. | 리스크 관리 프로세스를 따르면서 각 반복에서 리스크가 식별, 분석, 관리되도록 보장한다. | 제품 책임자에게 리스크 관리자 역할을 하여 리스크 시정을 지원하도록 요청한다. | 프로젝트 리스크의 적절한 추적, 분석, 시정을 보장하기 위해 애자일 리스크 매니페스토를 구현한다. |  | B | PMO가 고가시성 애자일 프로젝트에서 올바른 리스크 관리를 보장하고자 할 때, 프로젝트 관리자는 리스크 관리 프로세스를 따르면서 각 반복에서 리스크가 식별, 분석, 관리되도록 보장해야 한다. 반복적 리스크 관리는 애자일 관행에 부합한다. 애자일 리스크 관리자 역할 구현(A)은 불필요한 오버헤드를 추가한다. 제품 책임자에게 리스크 관리자 역할 요청(C)은 역할을 혼합한다. 애자일 리스크 매니페스토 구현(D)은 표준 관행이 아니다.
797 | A supplier informs the project manager that producing the quantity of a key component for the project will require an additional month. The project manager has to meet an important milestone in a week. What should the project manager do next? | Involve the legal department, as the vendor is breaching the contract by not delivering the full amount in time. | Perform market research to find out if there are other vendors that can produce similar kinds of materials. | Ask the vendor if the minimally sufficient materials can be produced in time to meet the deadline. | Submit a change request to the change control board (CCB) asking to extend the deadline in order to reflect the late delivery. |  | C | When a vendor needs an additional month to produce a key component but a milestone is due in a week, the project manager should ask the vendor if minimally sufficient materials can be produced in time to meet the deadline. Exploring partial delivery maintains momentum. Involving legal (A) is adversarial. Market research for alternatives (B) may help long-term but not within a week. Submitting a change request to extend (D) accepts the delay without exploring options. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 공급업체가 프로젝트의 핵심 부품을 필요한 수량만큼 생산하려면 추가 1개월이 필요하다고 프로젝트 관리자에게 알렸다. 프로젝트 관리자는 1주일 내에 중요한 마일스톤을 달성해야 한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 벤더가 전체 수량을 제시간에 전달하지 않아 계약을 위반하고 있으므로 법무부를 참여시킨다. | 유사한 자재를 생산할 수 있는 다른 벤더가 있는지 시장 조사를 수행한다. | 마감일을 맞추기 위해 최소한으로 충분한 자재를 제시간에 생산할 수 있는지 벤더에게 문의한다. | 늦은 납품을 반영하여 마감일을 연장하도록 변경 통제 위원회(CCB)에 변경 요청을 제출한다. |  | C | 벤더가 핵심 부품에 추가 1개월이 필요하지만 마일스톤이 1주일 내인 경우, 프로젝트 관리자는 마감일을 맞추기 위해 최소한으로 충분한 자재를 제시간에 생산할 수 있는지 벤더에게 문의해야 한다. 부분 납품 탐색은 추진력을 유지한다. 법무부 참여(A)는 적대적이다. 대안 시장 조사(B)는 장기적으로 도움이 되지만 1주일 내에는 어렵다. 마감일 연장 변경 요청 제출(D)은 옵션을 탐색하지 않고 지연을 수용한다.
798 | A project manager is leading a project with a risk management plan detailing strategy and actions if any of the identified risks become an issue. One of the identified risks becomes an issue, but the project manager acknowledges that the response considered in the risk management plan may not be the best. What should the project manager do? | Adopt the action prescribed in the risk management plan since it was agreed to beforehand. | Submit a change request to perform a different issue response than what is registered in the risk management plan. | Escalate the issue to the project sponsor and register the new risk response in the project documents. | Meet with the project team and sponsor to reevaluate all issue responses registered in the risk management plan. |  | B | When an identified risk becomes an issue but the planned response may not be the best option, the project manager should submit a change request to perform a different issue response. Formal change control ensures the revised approach is documented, reviewed, and approved. Adopting the prescribed action rigidly (A) ignores professional judgment. Escalating to the sponsor (C) skips the formal process. Reevaluating all responses (D) is excessive when only one response needs revision. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 관리자가 리스크 관리 계획에 식별된 리스크가 이슈가 될 경우의 전략과 조치를 상세히 설명한 프로젝트를 이끌고 있다. 식별된 리스크 중 하나가 이슈가 되었지만, 프로젝트 관리자는 리스크 관리 계획에서 고려한 대응이 최선이 아닐 수 있다고 인정한다. 프로젝트 관리자는 무엇을 해야 하는가? | 사전에 합의된 것이므로 리스크 관리 계획에 처방된 조치를 채택한다. | 리스크 관리 계획에 등록된 것과 다른 이슈 대응을 수행하기 위한 변경 요청을 제출한다. | 이슈를 프로젝트 스폰서에게 에스컬레이션하고 프로젝트 문서에 새로운 리스크 대응을 등록한다. | 프로젝트 팀과 스폰서와 만나 리스크 관리 계획에 등록된 모든 이슈 대응을 재평가한다. |  | B | 식별된 리스크가 이슈가 되었지만 계획된 대응이 최선이 아닐 수 있을 때, 프로젝트 관리자는 다른 이슈 대응을 수행하기 위한 변경 요청을 제출해야 한다. 공식적인 변경 통제는 수정된 접근 방식이 문서화되고, 검토되고, 승인되도록 보장한다. 처방된 조치를 경직되게 채택(A)하는 것은 전문적 판단을 무시한다. 스폰서에게 에스컬레이션(C)은 공식 프로세스를 건너뛴다. 모든 대응 재평가(D)는 하나의 대응만 수정이 필요한 데 과도하다.
799 | A vice president has asked a project manager to support a new urgent project and has informed team members that the project will start soon. The CEO of the company has not yet approved the project to start. The vice president is concerned that the project will not be approved by the CEO on time. What should the project manager do next? | Start working on the project immediately and determine the scope later | Ask the vice president to define who will be the product owner for the project | Investigate if the value and benefits of the project are identified | Ask the vice president to approve the project charter to kick off the project |  | C | The correct answer is C. Investigate if the value and benefits of the project are identified. Resource management includes ensuring team members have the necessary skills and support. The PM should identify gaps and address them through training, mentoring, or other appropriate measures. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 부사장이 프로젝트 관리자에게 새로운 긴급 프로젝트를 지원하도록 요청했고 팀원들에게 프로젝트가 곧 시작될 것이라고 알렸다. 회사 CEO는 아직 프로젝트 시작을 승인하지 않았다. 부사장은 CEO가 제시간에 프로젝트를 승인하지 않을까 우려한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 즉시 프로젝트 작업을 시작하고 범위는 나중에 결정한다. | 부사장에게 프로젝트의 제품 책임자를 정의하도록 요청한다. | 프로젝트의 가치와 혜택이 식별되었는지 조사한다. | 부사장에게 프로젝트를 시작하기 위해 프로젝트 헌장을 승인하도록 요청한다. |  | C | 정답은 C이다. 프로젝트의 가치와 혜택이 식별되었는지 조사한다. 자원 관리는 팀원이 필요한 기술과 지원을 받도록 보장하는 것을 포함한다. PM은 격차를 식별하고 교육, 멘토링 또는 기타 적절한 조치를 통해 해결해야 한다.
800 | A project manager is acting as a scrum master in a hybrid project and is dealing with a conflict between team members. What strategy should be used to handle this conflict? | Review conflicts during daily Scrum so they are handled in a timely manner | Sort conflicts into two groups: positive and negative | Place conflicts into categories: structural and interpersonal. | Place conflicts on a shared conflict list and ensure it is visible |  | A | In hybrid projects, daily standup meetings provide a forum where team members communicate progress, issues, and impediments. The PM or scrum master facilitates these meetings and helps resolve conflicts among team members or stakeholders in a timely manner, preventing escalation and minimizing performance impact. This agile practice addresses conflict at its source rather than allowing it to persist. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 하이브리드 프로젝트에서 스크럼 마스터 역할을 하고 있으며 팀원 간 갈등을 다루고 있다. 이 갈등을 처리하기 위해 어떤 전략을 사용해야 하는가? | 갈등이 적시에 처리되도록 일일 스크럼 중에 갈등을 검토한다. | 갈등을 긍정적과 부정적 두 그룹으로 분류한다. | 갈등을 구조적과 대인관계적 범주로 분류한다. | 갈등을 공유 갈등 목록에 놓고 가시성을 보장한다. |  | A | 하이브리드 프로젝트에서 일일 스탠드업 회의는 팀원이 진행 상황, 이슈, 장애물을 소통하는 포럼을 제공한다. PM 또는 스크럼 마스터는 이러한 회의를 촉진하고 팀원 또는 이해관계자 간 갈등을 적시에 해결하여 에스컬레이션과 성과 영향을 최소화한다.
801 | A project is in the knowledge transfer phase, and a few subject matter experts (SMEs) went to the client site for knowledge transfer. The SMEs captured various process deviations without sharing with the project team. How can the project manager ensure knowledge transfer across the team? | Ask the project management office (PMO) to provide team members with real-time visibility for deviations and facilitate team members to resolve issues | Ask the project team to facilitate a lessons learned session during the projectclosure phase to incorporate this issue | Ask the project team to run a deviation log review meeting with the client, highlighting that the project may not be able to go live as scheduled | Ask the SMEs to share the knowledge transfer documents with all other members by placing the documents in the project management information system (PMIS) |  | D | When SMEs captured process deviations during knowledge transfer at the client site without sharing them with the project team, the project manager should ask the SMEs to share the knowledge transfer documents with all team members by placing them in the project management information system (PMIS). The PMIS collects, organizes, and distributes project information, ensuring all team members have access to current and accurate documentation. Asking the PMO to provide real-time visibility (A) adds overhead without addressing the immediate documentation gap. Facilitating lessons learned during closure (B) is too late to help the current team. Running a deviation log review meeting with the client (C) escalates the issue without first ensuring internal knowledge sharing. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트가 지식 이전 단계에 있으며, 몇 명의 주제 전문가(SME)가 지식 이전을 위해 고객 사이트에 갔다. SME들이 프로젝트 팀과 공유하지 않고 다양한 프로세스 편차를 포착했다. 프로젝트 관리자는 팀 전체에 지식 이전을 어떻게 보장할 수 있는가? | PMO에 팀원들에게 편차에 대한 실시간 가시성을 제공하고 이슈 해결을 촉진하라고 요청한다. | 프로젝트 종료 단계에서 교훈 세션을 촉진하여 이 이슈를 포함하도록 요청한다. | 고객과 편차 로그 검토 회의를 진행하여 예정대로 운영 개시하지 못할 수 있음을 강조하도록 요청한다. | SME들에게 지식 이전 문서를 PMIS에 배치하여 모든 팀원과 공유하도록 요청한다. |  | D | SME들이 지식 이전 중 프로세스 편차를 포착했지만 팀과 공유하지 않았을 때, PM은 SME들에게 지식 이전 문서를 PMIS에 배치하여 모든 팀원과 공유하도록 요청해야 한다. PMIS는 프로젝트 정보를 수집, 조직, 배포하여 모든 팀원이 최신 문서에 접근할 수 있도록 보장한다.
802 | The project manager started a new project and must ensure that the team members and stakeholders are adequately trained. After an interview with the team, the project manager discovers that all resources have experience in different agile methodologies. What should the project manager do? | Teach one agile methodology fully and completely | Skip the training because the team already understands agile | Ensure the team has a common understanding of agile | Make sure the project team is aware of all agile techniques |  | C | When all team resources have experience in different agile methodologies, the project manager should ensure the team has a common understanding of agile. Shared understanding of values, principles, and practices enables effective collaboration. Teaching one methodology fully (A) ignores team diversity. Skipping training (B) assumes alignment without verification. Making the team aware of all techniques (D) is broad without building shared understanding. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 관리자가 새 프로젝트를 시작하며 팀원과 이해관계자가 적절히 교육을 받도록 보장해야 한다. 팀과 인터뷰 후 모든 자원이 다양한 애자일 방법론에 경험이 있음을 발견했다. 프로젝트 관리자는 무엇을 해야 하는가? | 하나의 애자일 방법론을 완전하고 철저하게 가르친다. | 팀이 이미 애자일을 이해하므로 교육을 건너뛴다. | 팀이 애자일에 대한 공통된 이해를 가지도록 보장한다. | 프로젝트 팀이 모든 애자일 기법을 인지하도록 보장한다. |  | C | 모든 팀 자원이 다양한 애자일 방법론에 경험이 있을 때, PM은 팀이 애자일에 대한 공통된 이해를 가지도록 보장해야 한다. 공유된 이해는 효과적인 협업을 가능하게 한다. 하나의 방법론 교육(A)은 팀의 다양성을 무시한다. 교육 건너뛰기(B)는 정렬을 가정한다. 모든 기법 인지 보장(D)은 공유된 이해를 구축하지 않는다.
803 | A project team is using an iterative and incremental delivery approach. The sprint's duration is 1 month with a production release every 3 months. In the last sprint review, the users communicated that they want the functionality presented and deployed in 5 weeks. The project lead is working on the next release plan. When should the project lead have their team deploy the functionality? | In 5 weeks | In 12 weeks | In 2 months 928 | In 1 month |  | A | The correct answer is A. In 5 weeks. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 반복적이고 점진적인 전달 접근 방식을 사용하고 있다. 스프린트 기간은 1개월이며 3개월마다 프로덕션 릴리스가 있다. 마지막 스프린트 리뷰에서 사용자들이 5주 내에 제시된 기능을 배포해 달라고 요청했다. 프로젝트 리더가 다음 릴리스 계획을 작업 중이다. 프로젝트 리더는 팀에게 언제 기능을 배포하도록 해야 하는가? | 5주 후 | 12주 후 | 2개월 후 | 1개월 후 |  | A | 정답은 A이다. 5주 후. 애자일 실천법은 반복적 전달, 팀 권한 부여, 지속적 개선을 강조한다. PM은 협업을 촉진하고 장애물을 제거하며 팀이 효과적으로 가치를 전달할 수 있도록 보장해야 한다.
804 | During the project planning phase, the customer explained the importance of delivering the project results proposed in the scope as soon as possible. What should the project manager do first to address this? | Assess the opportunities to deliver project value incrementally | Gather all the requirements' details and schedule a refinement meeting | Prepare a project management plan for the full scope using an agile approach | Approve a change request to change the project approach to agile |  | A | When a customer wants project results delivered as soon as possible, the project manager should first assess opportunities to deliver project value incrementally. Evaluating incremental delivery options identifies which deliverables can be released earlier for early value realization. Gathering all requirements and scheduling refinement (B) may delay delivery. Preparing a full agile plan (C) is premature. Approving a change request to switch to agile (D) should follow feasibility analysis. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 계획 단계에서 고객이 범위에 제안된 프로젝트 결과를 가능한 빨리 전달하는 것의 중요성을 설명했다. 프로젝트 관리자는 이를 해결하기 위해 먼저 무엇을 해야 하는가? | 프로젝트 가치를 점진적으로 전달할 기회를 평가한다. | 모든 요구사항 세부 사항을 수집하고 정제 회의를 예약한다. | 애자일 접근 방식을 사용하여 전체 범위에 대한 프로젝트 관리 계획을 준비한다. | 프로젝트 접근 방식을 애자일로 변경하는 변경 요청을 승인한다. |  | A | 고객이 프로젝트 결과를 가능한 빨리 전달받기를 원할 때, 프로젝트 관리자는 먼저 프로젝트 가치를 점진적으로 전달할 기회를 평가해야 한다. 점진적 전달 옵션을 평가하면 어떤 산출물을 더 일찍 릴리스하여 조기 가치 실현을 할 수 있는지 식별된다. 모든 요구사항 수집 및 정제 예약(B)은 전달을 지연시킬 수 있다. 전체 애자일 계획 준비(C)는 시기상조이다. 애자일로 변경하는 변경 요청 승인(D)은 타당성 분석 후에 이루어져야 한다.
805 | A project team is having difficulties understanding technical details regarding requirements. The information was not initially provided by the customer, but the information is critical in the current iteration for clarification on how tasks need to be accomplished. How should the project manager approach this situation? | Schedule weekly meetings and product reviews with the customer to clarify requirements | Educate the customer and have them participate in daily standup meetings. | Request that the customer reviews and clarifies feature definitions for the current sprint | Send a burndown chart of the current sprint to the customer and seek clarifications. |  | C | When the team needs critical technical details from the customer for the current iteration, the project manager should request that the customer reviews and clarifies feature definitions for the current sprint. Direct customer engagement addresses the immediate information gap. Scheduling weekly meetings (A) delays clarification beyond the current sprint's needs. Educating the customer to attend standups (B) is time-consuming and potentially impractical. Sending a burndown chart (D) shows progress but does not elicit technical details. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 팀이 요구사항에 관한 기술적 세부 사항을 이해하는 데 어려움을 겪고 있다. 이 정보는 처음에 고객이 제공하지 않았지만, 작업 수행 방법에 대한 명확화를 위해 현재 이터레이션에서 중요한 정보이다. 프로젝트 관리자는 이 상황에 어떻게 접근해야 하는가? | 요구사항을 명확히 하기 위해 고객과 주간 회의 및 제품 리뷰를 예약한다. | 고객을 교육하고 일일 스탠드업 회의에 참여하도록 한다. | 고객에게 현재 스프린트의 기능 정의를 검토하고 명확히 해달라고 요청한다. | 현재 스프린트의 번다운 차트를 고객에게 보내고 명확화를 요청한다. |  | C | 팀이 현재 이터레이션에 대한 중요한 기술적 세부 사항을 고객으로부터 필요로 할 때, 프로젝트 관리자는 고객에게 현재 스프린트의 기능 정의를 검토하고 명확히 해달라고 요청해야 한다. 직접적인 고객 참여가 즉각적인 정보 격차를 해결한다. 주간 회의 예약(A)은 현재 스프린트의 필요를 넘어 명확화를 지연시킨다. 고객을 교육하여 스탠드업에 참석(B)시키는 것은 시간이 많이 걸리고 비현실적일 수 있다. 번다운 차트 전송(D)은 진행 상황을 보여주지만 기술적 세부 사항을 이끌어내지 못한다.
806 | Two teams are engaged on a global project which uses a follow-the-sun approach in order to speed up delivery. After the first release, many issues were identified on the product, which could easily have been avoided with better communication. What should the project manager do? | Move working windows so that team members can have increased overlap for the handover of status and issues to their counterparts. | Improve the videoconferencing system to provide better availability and quality in order to increase communication. | Facilitate a meeting with both teams so that they can agree on the issues and propose solutions that work for both teams. | Have team ambassadors from each location travel to the other in order to facilitate communication and minimize issues. |  | A | When a follow-the-sun global project has quality issues after the first release due to poor communication, the project manager should move working windows to increase overlap for handover of status and issues. Overlapping hours enable real-time communication. Improving videoconferencing (B) enhances tools but not process. Facilitating a meeting (C) is a one-time action. Having ambassadors travel (D) is costly and not sustainable. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 글로벌 프로젝트에서 두 팀이 전달을 가속화하기 위해 '해를 따르는(follow-the-sun)' 접근 방식을 사용하고 있다. 첫 번째 릴리스 후 제품에서 많은 이슈가 식별되었으며, 더 나은 커뮤니케이션으로 쉽게 피할 수 있었다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원들이 상대방에게 상태 및 이슈 인수인계를 위한 중복 시간을 늘릴 수 있도록 근무 시간대를 조정한다. | 커뮤니케이션을 증가시키기 위해 화상회의 시스템의 가용성과 품질을 개선한다. | 두 팀이 이슈에 합의하고 양쪽에 적합한 솔루션을 제안할 수 있도록 회의를 촉진한다. | 각 위치의 팀 대사를 상대 위치로 출장 보내어 커뮤니케이션을 촉진하고 이슈를 최소화한다. |  | A | 해를 따르는' 글로벌 프로젝트에서 첫 릴리스 후 부족한 커뮤니케이션으로 품질 이슈가 발생했을 때, 프로젝트 관리자는 상태 및 이슈 인수인계를 위한 중복 시간을 늘리도록 근무 시간대를 조정해야 한다. 중복 시간은 실시간 커뮤니케이션을 가능하게 한다. 화상회의 개선(B)은 도구를 향상시키지만 프로세스는 아니다. 회의 촉진(C)은 일회성 조치이다. 대사 출장(D)은 비용이 많이 들고 지속 가능하지 않다.
807 | A project manager noticed that the functional manager is not cooperating with staff assignment schedules and is always finding excuses not to release the requested staff. What should the project manager do first? | Have a direct talk with the functional manager to understand the reasons behind their attitude. | Check with human resources (HR) regarding the availability of staff. | Ask the leadership team for help obtaining the needed staff. | Evaluate the impact caused by the delay of forming the team and confront the functional manager. |  | A | When a functional manager is not cooperating with staff assignment schedules, the project manager should first have a direct talk with the functional manager to understand the reasons behind their attitude. Understanding the root cause through direct communication is the first step in conflict resolution. Checking with HR about availability (B) bypasses the relationship. Asking leadership for help (C) escalates prematurely. Evaluating the impact and confronting the manager (D) is aggressive without first understanding their perspective. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Cost & Resource Management | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 기능 관리자가 인력 배정 일정에 협조하지 않고 요청된 인력을 방출하지 않으려는 핑계를 항상 찾고 있음을 발견했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 기능 관리자와 직접 대화하여 그들의 태도 뒤에 있는 이유를 이해한다. | 인사부(HR)에 인력 가용성을 확인한다. | 리더십 팀에 필요한 인력 확보를 위한 도움을 요청한다. | 팀 구성 지연으로 인한 영향을 평가하고 기능 관리자와 대면한다. |  | A | 기능 관리자가 인력 배정 일정에 협조하지 않을 때, 프로젝트 관리자는 먼저 기능 관리자와 직접 대화하여 그들의 태도 뒤에 있는 이유를 이해해야 한다. 직접 커뮤니케이션을 통한 근본 원인 이해가 갈등 해결의 첫 단계이다. HR에 가용성 확인(B)은 관계를 우회한다. 리더십에 도움 요청(C)은 성급하게 에스컬레이션한다. 영향 평가 후 대면(D)은 먼저 그들의 관점을 이해하지 않고 공격적이다.
808 | Which two actions should a project manager consider while launching a new virtual team? (Choose two) | Evaluate the project manager's own strengths and weaknesses as a virtual team leader to identify avoidable pitfalls | Recruit the best resources within the organization to be part of the virtual team | Identify the types and quantities of resources required for each work package or activity | Establish in the beginning, how progress will be monitored and the best means for communicating progress | Verify if team members are on more than one team and cannot devote enough time to this team | A, D | When launching a new virtual team, the project manager should consider two key actions: evaluating the PM's own strengths and weaknesses as a virtual team leader to identify avoidable pitfalls, and establishing how progress will be monitored and the best means for communicating progress from the beginning. Self-assessment and clear communication protocols set the foundation for virtual team success. Recruiting the best resources (B) is a planning activity. Identifying resource quantities per work package (C) is resource management. Verifying if team members are on multiple teams (E) is performance management. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 새로운 가상 팀을 출범시킬 때 프로젝트 관리자가 고려해야 할 두 가지 조치는 무엇인가? (2개 선택) | 피할 수 있는 함정을 식별하기 위해 가상 팀 리더로서의 자신의 강점과 약점을 평가한다. | 가상 팀의 일원이 될 최고의 자원을 조직 내에서 모집한다. | 각 작업 패키지 또는 활동에 필요한 자원의 유형과 수량을 식별한다. | 처음부터 진행 상황이 어떻게 모니터링되고 진행 상황을 전달하는 최선의 수단을 수립한다. | 팀원이 둘 이상의 팀에 속해 있어 이 팀에 충분한 시간을 할애할 수 없는지 확인한다. | A, D | 새로운 가상 팀을 출범시킬 때, 프로젝트 관리자는 두 가지 핵심 조치를 고려해야 한다: 피할 수 있는 함정을 식별하기 위해 가상 팀 리더로서의 자신의 강점과 약점을 평가하고, 처음부터 진행 상황 모니터링 방법과 진행 상황 전달을 위한 최선의 커뮤니케이션 수단을 수립한다. 자기 평가와 명확한 커뮤니케이션 프로토콜이 가상 팀 성공의 기반을 마련한다. 최고 자원 모집(B)은 계획 활동이다. 작업 패키지별 자원 수량 식별(C)은 자원 관리이다. 팀원 다중 팀 여부 확인(E)은 성과 관리이다.
809 | A project manager is assigned to a new project. The project is for a new product that the company wants to launch as soon as possible to test market readiness. The project is part of a large business transformation, and the objective is to open delivery channels for the new product. Which delivery approach should the project manager recommend? | A predictive approach with an experienced project team. | An adaptive approach with clearly defined user stories. | A predictive approach with clear acceptance criteria. | An adaptive approach with loosely defined large epics. |  | B | For a new product launch aimed at testing market readiness as part of a business transformation, the project manager should recommend an adaptive approach with clearly defined user stories. An adaptive approach provides the flexibility to respond to market feedback and adjust the product iteratively, while clearly defined user stories ensure the team delivers the most valuable features to customers. A predictive approach with an experienced team (A) or clear acceptance criteria (C) lacks the flexibility needed for market testing. An adaptive approach with loosely defined large epics (D) lacks the specificity needed for the team to deliver focused, valuable increments. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 새 프로젝트에 배정되었다. 프로젝트는 회사가 시장 준비를 테스트하기 위해 가능한 빨리 출시하고자 하는 새로운 제품을 위한 것이다. 프로젝트는 대규모 비즈니스 전환의 일부이며, 목표는 새 제품의 전달 채널을 여는 것이다. 프로젝트 관리자는 어떤 전달 접근 방식을 권장해야 하는가? | 경험 있는 프로젝트 팀과 함께 예측형 접근 방식 | 명확하게 정의된 사용자 스토리와 함께 적응형 접근 방식 | 명확한 수락 기준과 함께 예측형 접근 방식 | 느슨하게 정의된 대규모 에픽과 함께 적응형 접근 방식 |  | B | 시장 준비를 테스트하기 위한 새 제품 출시와 비즈니스 전환의 일부인 경우, 프로젝트 관리자는 명확하게 정의된 사용자 스토리와 함께 적응형 접근 방식을 권장해야 한다. 적응형 접근 방식은 시장 피드백에 대응하고 제품을 반복적으로 조정할 수 있는 유연성을 제공하며, 명확하게 정의된 사용자 스토리는 팀이 고객에게 가장 가치 있는 기능을 전달하도록 보장한다. 경험 있는 팀과 예측형(A) 또는 명확한 수락 기준과 예측형(C)은 시장 테스트에 필요한 유연성이 부족하다. 느슨하게 정의된 대규모 에픽과 적응형(D)은 팀이 집중적이고 가치 있는 증분을 전달하는 데 필요한 구체성이 부족하다.
810 | After months of careful planning and discussions with subject matter experts (SMEs), a new law is announced that may significantly affect the project budget. What should the project manager do first? | Create a baseline impact assessment | Initiate a project change request. | Discuss with the project sponsor. | Consult the risk and issue logs. |  | D | When new legislation may significantly affect the project budget, the PM should first consult the risk and issue logs to determine whether this scenario was anticipated and what mitigation strategies were planned. Simultaneously, the PM should discuss the potential impact with the project sponsor, who has decision-making authority, to determine the best course of action for addressing the budgetary implications. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | 수개월의 신중한 계획과 주제 전문가(SME)와의 논의 후, 프로젝트 예산에 상당한 영향을 미칠 수 있는 새로운 법률이 발표되었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 기준선 영향 평가를 작성한다. | 프로젝트 변경 요청을 개시한다. | 프로젝트 스폰서와 논의한다. | 리스크 및 이슈 로그를 확인한다. |  | D | 새로운 법률이 프로젝트 예산에 상당한 영향을 미칠 수 있을 때, PM은 먼저 리스크 및 이슈 로그를 확인하여 이 시나리오가 예상되었는지와 어떤 완화 전략이 계획되었는지 확인해야 한다. 동시에 PM은 예산적 영향을 다루기 위한 최선의 조치를 결정하기 위해 의사결정 권한이 있는 프로젝트 스폰서와 잠재적 영향을 논의해야 한다.
811 | An agile leader is working on a complex project that is entering the final phase where solutions from different vendors are being integrated. This is the most critical delivery stage for the project. How should the agile leader ensure successful delivery? | Ensure participation from all team members | Ensure cross-departmental teams are colocated | Ask the client to attend all daily calls. | Request additional project resources |  | A | When an agile project enters the critical integration phase with multiple vendors, the agile leader should ensure participation from all team members. Full participation fosters collaboration, identifies integration issues, and promotes shared accountability. Ensuring cross-departmental colocation (B) may not be feasible. Asking the client to attend all daily calls (C) may not be practical. Requesting additional resources (D) introduces coordination complexity. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 리더가 다양한 벤더의 솔루션이 통합되는 최종 단계에 진입하는 복잡한 프로젝트를 작업 중이다. 이것은 프로젝트의 가장 중요한 전달 단계이다. 애자일 리더는 성공적인 전달을 어떻게 보장해야 하는가? | 모든 팀원의 참여를 보장한다. | 부서 간 팀이 함께 위치하도록 보장한다. | 고객에게 모든 일일 콜에 참석하도록 요청한다. | 추가 프로젝트 자원을 요청한다. |  | A | 애자일 프로젝트가 여러 벤더와의 중요한 통합 단계에 진입할 때, 애자일 리더는 모든 팀원의 참여를 보장해야 한다. 전원 참여는 협업을 촉진하고 통합 이슈를 식별하며 공동 책임의식을 촉진한다. 부서 간 함께 위치(B)는 현실적으로 불가능할 수 있다. 고객에게 모든 일일 콜 참석 요청(C)은 실용적이지 않을 수 있다. 추가 자원 요청(D)은 조정 복잡성을 도입한다.
812 | A project manager is working on an agile project. The organization does not have experience with agile delivery. During business case development, the new product owner asks when the project deliverables are considered complete. How should the project manager respond? | The scrum master will approve the user stories that are complete. | Items are considered complete when they satisfy the definition of done (DoD). | Backlog items are considered complete when the product owner approves the demo. | At the end of each sprint, the outcome is considered ready for production. |  | B | The Definition of Done (DoD) defines the criteria for accepting a feature or story as finished. Work that doesn't meet the team's DoD is considered unfinished and doesn't count as delivered value. The scrum master doesn't formally approve completed scope (B). Demos provide feedback but completion is determined by meeting the DoD, not just demonstration approval (C). Sprint outcomes aren't automatically production-ready unless they meet the established DoD and release criteria (D). | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 애자일 프로젝트를 작업 중이다. 조직이 애자일 전달 경험이 없다. 비즈니스 케이스 개발 중 새로운 제품 책임자가 프로젝트 산출물이 언제 완료된 것으로 간주되는지 질문한다. 프로젝트 관리자는 어떻게 대응해야 하는가? | 스크럼 마스터가 완료된 사용자 스토리를 승인한다. | 항목은 완료의 정의(DoD)를 충족할 때 완료된 것으로 간주된다. | 백로그 항목은 제품 책임자가 데모를 승인할 때 완료된 것으로 간주된다. | 각 스프린트 마지막에 결과물은 프로덕션 준비가 된 것으로 간주된다. |  | B | 완료의 정의(DoD)는 기능이나 스토리를 완료된 것으로 수락하기 위한 기준을 정의한다. 팀의 DoD를 충족하지 못하는 작업은 미완료로 간주되며 전달된 가치로 계산되지 않는다. 스크럼 마스터는 완료된 범위를 공식적으로 승인하지 않는다(A). 데모는 피드백을 제공하지만 완료는 데모 승인이 아니라 DoD 충족에 의해 결정된다(C). 스프린트 결과물은 확립된 DoD와 릴리스 기준을 충족하지 않으면 자동으로 프로덕션 준비가 되지 않는다(D).
813 | In the execution phase of a project, the development team is informed by the IT security department that one of the external platforms that the team is using will be uninstalled for the whole organization. What should the project manager do first? | Ask the project team to analyze the impact. | Register the risk and document the contingency plan. | Escalate the issue to the change control board (CCB). | Have the project team brainstorm alternatives. |  | A | When an external platform used by the development team will be uninstalled organization-wide, the project manager should first ask the project team to analyze the impact. Understanding the scope of the disruption guides all subsequent decisions about alternatives, risk responses, or escalation. Registering the risk and documenting contingency (B) is premature without impact analysis. Escalating to the CCB (C) requires impact data. Having the team brainstorm alternatives (D) should follow impact assessment. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 프로젝트 실행 단계에서 IT 보안 부서가 외부 플랫폼 중 하나가 조직 전체에서 제거될 것이라고 알렸다. PM은 무엇을 해야 하는가? | 프로젝트 팀에 영향을 분석하도록 요청한다 | 리스크를 등록하고 비상 계획을 문서화한다 | 변경통제위원회(CCB)에 이슈를 에스컬레이션한다 | 프로젝트 팀에 대안을 브레인스토밍하도록 한다 |  | A | 개발팀이 사용하는 외부 플랫폼이 조직 전체에서 제거될 때, PM은 먼저 프로젝트 팀에 영향을 분석하도록 요청해야 한다. 영향 범위 이해가 올바른 대응의 기초이다. 리스크 등록(B)은 분석 후에 한다. CCB 에스컬레이션(C)은 영향 파악 후에 한다. 대안 브레인스토밍(D)은 영향 분석 후에 한다.
814 | A team decides to adopt an agile approach for their new project. During a sprint, the project manager realizes that there is a need to show progress and optimize the collaboration among teams. Which tool should the project manager use? | Daily meetings | Kanban board | Gantt chart | Retrospective meetings |  | B | When needing to show progress and optimize collaboration among agile teams during a sprint, the project manager should use a Kanban board. Kanban boards provide real-time visual workflow management that enhances transparency and collaboration. Daily meetings (A) support communication but do not visualize progress. Gantt charts (C) are predictive tools not suited for agile collaboration. Retrospective meetings (D) improve future performance but do not show real-time progress. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀이 새 프로젝트에 애자일 접근법을 채택했다. 스프린트 중 PM이 진행 상황을 보여주고 협업을 최적화해야 한다. 어떤 도구를 사용해야 하는가? | 데일리 미팅 | 칸반 보드 | 간트 차트 | 회고 미팅 |  | B | 애자일 팀의 스프린트 중 진행 상황을 보여주고 협업을 최적화하려면 칸반 보드를 사용해야 한다. 칸반 보드는 실시간 시각적 워크플로 관리를 제공한다. 데일리 미팅(A)은 소통 도구이지 시각화 도구가 아니다. 간트 차트(C)는 예측형 도구이다. 회고(D)는 스프린트 종료 후 활동이다.
815 | An updated schedule for work delivered by a subcontractor is a condition for a milestone payment. The subcontractor completed the work but does not have a schedule, claiming that work was already agreed upon with the client. What should the project manager do? | Tell the subcontractor to submit a draft schedule. | Negotiate a contract change with the subcontractor. | Meet with the client to discuss the issue with the subcontractor. | Inform the subcontractor that they must send the schedule. |  | D | When an updated schedule is a contractual condition for milestone payment and the subcontractor has not provided one, the project manager should inform the subcontractor that the schedule must be submitted to comply with the contract and process payment. Contractual obligations must be enforced regardless of verbal agreements with the client. Telling the subcontractor to submit a draft (A) is weaker than requiring the contractual deliverable. Negotiating a contract change (B) is unnecessary since the requirement is already established. Meeting with the client to discuss the issue (C) bypasses the contractual relationship between the PM and the subcontractor. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 하도급업체의 업데이트된 일정이 마일스톤 지급 조건이다. 하도급업체가 작업은 완료했지만 일정을 제출하지 않았다. PM은 무엇을 해야 하는가? | 하도급업체에게 초안 일정을 제출하라고 말한다 | 하도급업체와 계약 변경을 협상한다 | 고객과 만나 하도급업체 이슈를 논의한다 | 하도급업체에게 일정을 보내야 한다고 알린다 |  | D | 업데이트된 일정이 마일스톤 지급의 계약 조건이고 하도급업체가 제출하지 않았을 때, PM은 하도급업체에게 일정을 보내야 한다고 알려야 한다. 계약 의무를 명확히 전달하는 것이 적절하다. 초안 제출(A)은 기준을 낮춘다. 계약 변경(B)은 불필요하다. 고객 논의(C)는 하도급업체와 먼저 해결해야 한다.
816 | Two weeks after the approval of the project management plan for a global project, the project manager noticed that it was approved based on a different level of understanding by international stakeholders and is not what the project manager presented for approval. What should the project manager have done to prevent this from happening? | Reviewed all the approvals immediately after the kick-off meeting was over | Validated each stakeholder ' s understanding during the kick-off meeting | Ran separate kick-off meetings for each culture and time zone | Sent the meeting minutes to the stakeholders after the kick-off meeting |  | B | When a global project's management plan was approved based on different levels of understanding by international stakeholders, the project manager should have validated each stakeholder's understanding during the kick-off meeting. Active validation ensures shared comprehension before approval, preventing misalignment. Reviewing approvals after the meeting (A) catches issues too late. Running separate meetings per culture and time zone (C) may create inconsistencies. Sending meeting minutes afterward (D) is passive and does not confirm understanding. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 글로벌 프로젝트 관리 계획 승인 2주 후, PM이 서로 다른 이해 수준으로 승인되었음을 발견했다. PM이 이전에 무엇을 했어야 하는가? | 킥오프 미팅 후 즉시 모든 승인을 검토했다 | 킥오프 미팅 중 각 이해관계자의 이해를 검증했다 | 각 문화와 시간대별로 별도 킥오프 미팅을 진행했다 | 킥오프 미팅 후 이해관계자에게 회의록을 보냈다 |  | B | 글로벌 프로젝트에서 국제 이해관계자가 서로 다른 이해 수준으로 승인했을 때, PM은 킥오프 미팅 중 각 이해관계자의 이해를 검증했어야 한다. 이해 검증이 향후 불일치를 방지한다. 승인 검토(A)는 이해를 확인하지 않는다. 별도 미팅(C)은 과도하다. 회의록 발송(D)은 일방적이다.
817 | A project manager is leading a software development project with agile practices and has outsourced work to three well-qualified subcontractors. Over time, problems arise related to supply-chain management, and the project manager considers replacing the subcontractors with new suppliers. What should the project manager have done to avoid this problem? | Engaged the suppliers by category and validated the strategy with stakeholders. | Escalated the issue to the product owner to seek possible solutions. | Hired more Scrum Masters so every Scrum Master manages one supplier. | Created user stories for the suppliers and saved their qualification records to the backlog. |  | A | To avoid supply-chain management problems with outsourced subcontractors, the project manager should have engaged suppliers by category and validated the strategy with stakeholders. Early, structured supplier engagement—segmented by capability and criticality—establishes clear expectations, communication channels, and risk responsibilities before issues escalate. Validating the strategy with stakeholders ensures alignment on governance and trade-offs. Escalating to the product owner (B) is reactive. Hiring more Scrum Masters per supplier (C) misunderstands the Scrum Master role. Creating user stories for supplier qualification (D) misapplies agile artifacts to procurement management. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | PM이 애자일 실천법으로 소프트웨어 개발 프로젝트를 이끌고 있다. 3개 하도급업체에 작업을 외주했다. 공급망 문제를 피하기 위해 PM이 이전에 무엇을 했어야 하는가? | 공급업체를 카테고리별로 참여시키고 이해관계자와 전략을 검증했다 | 제품 책임자에게 이슈를 에스컬레이션하여 가능한 해결책을 찾았다 | 모든 스크럼 마스터가 한 공급업체를 관리하도록 더 많은 스크럼 마스터를 고용했다 | 공급업체를 위한 사용자 스토리를 생성하고 자격 기록을 백로그에 저장했다 |  | A | 외주 하도급업체와의 공급망 문제를 피하기 위해, PM은 공급업체를 카테고리별로 참여시키고 이해관계자와 전략을 검증했어야 한다. 조기 구조화된 참여가 공급망 리스크를 줄인다. 에스컬레이션(B)은 사후 대응이다. 추가 고용(C)은 비용 과다이다. 스토리 생성(D)은 공급망 관리가 아니다.
818 | A project manager is assigned to a new project that will launch the digital version of a current product. Even though the product is well known, the vision for its digital version is not clear to the stakeholders. What should the project manager do to increase value delivery? | Gather the team to create a comprehensive product roadmap but only commit to requirements for the next quarter. | Work with the team on the definition of a minimum viable product (MVP) and present it to the stakeholders. | Use spikes to dig deeper into the technical challenges of the new product, thus reducing the technical risk. | Create a visual task board with all of the relevant stakeholders to support backlog prioritization. |  | B | When the digital version of a product lacks a clear vision among stakeholders, the project manager should work with the team on defining a minimum viable product (MVP) and present it to stakeholders. MVP clarifies vision through tangible features. Creating a comprehensive roadmap (A) may be premature without clear vision. Using spikes (C) addresses technical risk only. Creating a visual task board (D) supports tracking, not vision. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | PM이 현재 제품의 디지털 버전을 출시하는 새 프로젝트에 배정되었다. 이해관계자 사이에 명확한 비전이 없다. PM은 무엇을 해야 하는가? | 팀과 포괄적 제품 로드맵을 만들되 다음 반복 요구사항에만 커밋한다 | 팀과 최소 기능 제품(MVP)을 정의하고 이해관계자에게 제시한다 | 스파이크를 사용하여 새 제품의 기술적 도전을 깊이 파고든다 | 모든 관련 이해관계자와 시각적 작업 보드를 만들어 백로그 우선순위를 지원한다 |  | B | 디지털 제품에 이해관계자 사이 명확한 비전이 없을 때, PM은 팀과 MVP를 정의하고 이해관계자에게 제시해야 한다. MVP 정의가 공통 이해와 비전 정렬을 촉진한다. 로드맵(A)은 비전 없이 방향을 제시하지 못한다. 스파이크(C)는 기술적이지 비전 정렬이 아니다. 작업 보드(D)는 실행 도구이다.
819 | In the middle of an iteration, a team member suggests a new method of doing things. The method provides no value to the end customer, however it may help the team to work more efficiently. The change may require several days of work to implement. How should the project manager respond to the suggestion? | The change should be considered because it will help the team work more efficiently | The change should be considered and presented to the project sponsor for approval | The change should not be considered because it adds no value to the end customer | The change should be considered and immediately added to the product backlog. |  | A | When a team member suggests a new method that provides no customer value but may improve team efficiency, requiring several days of work, the project manager should consider the change because it will help the team work more efficiently. Internal process improvements are valid and should be evaluated for cost-benefit. Presenting to the sponsor (B) is unnecessary for internal efficiency changes. Rejecting because it adds no customer value (C) ignores team efficiency gains. Immediately adding to the backlog (D) skips evaluation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | 이터레이션 중 팀원이 고객에게 가치를 제공하지 않지만 팀 효율성을 개선할 수 있는 새 방법을 제안했다. 며칠의 작업이 필요하다. 어떻게 해야 하는가? | 팀이 더 효율적으로 일하는 데 도움이 되므로 변경을 고려해야 한다 | 변경을 고려하고 프로젝트 스폰서에게 승인을 위해 제시해야 한다 | 최종 고객에게 가치를 추가하지 않으므로 변경을 고려해서는 안 된다 | 변경을 고려하고 즉시 제품 백로그에 추가해야 한다 |  | A | 고객 가치는 없지만 팀 효율성을 개선할 수 있는 변경은 고려해야 한다. 팀 효율성 향상은 장기적으로 고객에게 더 많은 가치를 전달하게 한다. 스폰서 승인(B)은 과도하다. 고려 안 함(C)은 팀 개선 기회를 무시한다. 즉시 추가(D)는 평가 없이 성급하다.
820 | In the beginning of project execution, the project manager finds out that a key resource will be unavailable for two weeks, which could cause a delay to the schedule. What should the project manager do first? | Ask human resources (HR) for a replacement, and update the nsk register | Update the schedule to reflect the project ' s changes in duration 1193 | Update the resource management plan and resource allocation chart accordingly | Assign the tasks to another resource, and ask the resource to work double shifts |  | C | When a key resource will be unavailable for two weeks early in execution, potentially delaying the schedule, the project manager should first update the resource management plan and resource allocation chart. Documentation of the change enables planning alternatives. Asking HR for a replacement (A) may not address the immediate gap. Updating the schedule (B) reflects impact but not the resource response. Assigning double shifts (D) is unsustainable. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 실행 초기에 PM이 핵심 자원이 2주간 사용 불가능하여 일정이 지연될 수 있음을 알게 되었다. PM은 무엇을 해야 하는가? | HR에 대체 자원을 요청하고 리스크 등록부를 업데이트한다 | 프로젝트의 기간 변경을 반영하도록 일정을 업데이트한다 | 자원 관리 계획과 자원 배정 차트를 적절히 업데이트한다 | 다른 자원에 작업을 배정하고 이중 교대 근무를 요청한다 |  | C | 핵심 자원이 실행 초기 2주간 사용 불가능할 때, PM은 먼저 자원 관리 계획과 자원 배정 차트를 업데이트해야 한다. 체계적 계획 업데이트가 올바른 대응의 기초이다. HR 요청(A)은 계획 업데이트 후에 한다. 일정 업데이트(B)는 자원 계획 후에 한다. 이중 교대(D)는 지속 불가능하다.
821 | An agile team is working on a product deliverable in an organization that is transforming itself to quickly respond to change. The finance team is requesting a project budget for the new product. What should the team do to address this request? | Request the finance team to allocate a budget based on historical data. | Extrapolate the budget based on the current cost performance index (CPI). | Provide the budget to the finance team for only the planned increments. | Work with the finance team to transition to incremental budgeting. |  | D | When the finance team requests a project budget for a new product being developed by an agile team in a transforming organization, the team should work with the finance team to transition to incremental budgeting. Incremental budgeting aligns with agile delivery. Requesting budget based on historical data (A) may not reflect current needs. Providing budget for only planned increments (C) is too narrow. Extrapolating from CPI (B) may be unreliable for new products. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 애자일 팀이 변화에 빠르게 대응하도록 전환 중인 조직에서 제품을 개발 중이다. 재무팀이 새 제품의 프로젝트 예산을 요청한다. 팀은 무엇을 해야 하는가? | 재무팀에 역사적 데이터를 기반으로 예산을 배정하도록 요청한다 | 현재 비용성과지수(CPI)를 기반으로 예산을 추정한다 | 계획된 인크리먼트에 대해서만 재무팀에 예산을 제공한다 | 재무팀과 협력하여 점진적 예산 편성으로 전환한다 |  | D | 전환 중인 조직의 애자일 팀이 예산을 요청받으면, 재무팀과 협력하여 점진적 예산 편성으로 전환해야 한다. 점진적 예산이 애자일의 적응적 특성에 맞다. 역사적 데이터(A)는 새 제품에 부적합하다. CPI 추정(B)은 아직 데이터가 없다. 인크리먼트만(C)은 협력이 부족하다.
822 | An agile project team is looking to develop quality standards for a project. How should the project manager coach the team? | Ensure that the definition of done (DoD) is provided when the product owner agrees that all acceptance criteria have been met for the user story | Inform the team that user acceptance testing is required to ensure that the product owner accepts the solution | Insist that test-driven development is implemented along with the automated testing | Determine the tools and techniques suitable for the project and ensure that testing is done early and continuously. |  | D | When an agile team is developing quality standards, the project manager should coach them to determine suitable tools and techniques and ensure testing is done early and continuously. Early testing validates value and catches defects. Defining DoD only when PO accepts (A) is too narrow. Requiring user acceptance testing (B) is one element, not the full coaching. Insisting on test-driven development (C) is prescriptive rather than coaching. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 애자일 프로젝트 팀이 품질 표준을 개발하려 한다. PM은 팀을 어떻게 코칭해야 하는가? | 제품 책임자가 모든 인수 기준에 동의할 때 완료 정의(DoD)가 제공되도록 한다 | 팀에 제품 책임자가 인도물을 수락하려면 사용자 인수 테스트가 필요하다고 알린다 | 자동화된 테스트와 함께 테스트 주도 개발 구현을 주장한다 | 프로젝트에 적합한 도구와 기법을 결정하고 테스트가 조기에 지속적으로 수행되도록 한다 |  | D | 애자일 팀이 품질 표준을 개발할 때, PM은 적합한 도구와 기법을 결정하고 테스트가 조기에 지속적으로 수행되도록 코칭해야 한다. 조기 테스트가 지속적 품질 검증을 보장한다. DoD 제공(A)은 일방적이다. UAT만(B)은 늦은 테스트이다. TDD 주장(C)은 하나의 방법에 제한적이다.
823 | In a geographically distributed project team, the project team members continue to email status reports and update schedules after their weekly meeting discussions. However, the team is having difficulty tracking the changes and progress made. What should the project manager do? | Facilitate training on version control and project artifacts, | Maintain a central repository of artifacts with a version control system. | Develop a document management software for version control. | Maintain separate document control via regions to avoid discrepancies. |  | B | When a geographically distributed team has difficulty tracking changes despite emailing updates after meetings, the project manager should maintain a central repository of artifacts with a version control system. Centralized version control ensures consistency. Facilitating training on version control (A) addresses skills but not the tool gap. Developing custom software (C) is overkill. Maintaining separate regional control (D) increases fragmentation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 지리적으로 분산된 프로젝트 팀에서 팀원들이 회의 후 이메일로 상태 보고서를 보내고 일정을 업데이트하지만 변경 추적이 어렵다. PM은 무엇을 해야 하는가? | 버전 관리 및 프로젝트 산출물에 대한 교육을 촉진한다 | 버전 관리 시스템이 있는 중앙 산출물 저장소를 유지한다 | 버전 관리를 위한 문서 관리 소프트웨어를 개발한다 | 불일치를 피하기 위해 지역별 별도 문서 관리를 유지한다 |  | B | 분산된 팀이 이메일 업데이트 후에도 변경 추적이 어려울 때, PM은 버전 관리 시스템이 있는 중앙 산출물 저장소를 유지해야 한다. 중앙 저장소가 단일 진실 소스를 제공한다. 교육(A)은 시스템 없이 부족하다. 소프트웨어 개발(C)은 과도하다. 지역별 분리(D)는 불일치를 악화시킨다.
824 | A highly skilled team resource received a job offer and is leaving the project soon. What should the project manager do to maintain project performance while a new team member is being onboarded? | Offer cross-training and mentoring to the new team member | Motivate the new team member to perform. | Log a risk in the risk register and work with the new team member to mitigate it | Share project documents with the new team member. |  | A | Cross-training and mentoring are effective team development techniques for managing key resource transitions. Cross-training enables team members to acquire new skills from colleagues, while mentoring provides guidance from experienced members. These approaches help maintain project performance during personnel changes by distributing critical knowledge across the team rather than concentrating it in a single resource. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Adopt a Holistic View | Acquire Resources | Traditional PM | 고급 기술을 가진 팀 자원이 이직 제안을 받고 곧 프로젝트를 떠난다. PM은 프로젝트 지식 유지를 위해 무엇을 해야 하는가? | 새 팀원에게 교차 교육과 멘토링을 제공한다 | 새 팀원에게 성과를 내도록 동기를 부여한다 | 리스크 등록부에 리스크를 기록하고 새 팀원과 완화 작업을 한다 | 새 팀원에게 프로젝트 문서를 공유한다 |  | A | 핵심 자원의 이직 시 프로젝트 지식을 유지하려면, 새 팀원에게 교차 교육과 멘토링을 제공해야 한다. 교차 교육과 멘토링이 효과적인 지식 이전 기법이다. 동기 부여(B)는 지식 이전이 아니다. 리스크 기록(C)은 관리적이다. 문서 공유(D)는 부분적이다.
825 | An innovation project with a budget of over US$30 million is expected to have a large impact on the technology industry. The business area is concerned if the project will meet stakeholder expectations and raised this concern with the project manager. What should the project manager do to manage business concerns and expectations before starting the project? | Ask the product owner to prioritize the backlog items based on the return on investment (ROI). | Direct the project team to estimate user stories in greater detail. | Request that the project team develop a release plan and roadmap for the project. | Meet with the project finance team to measure market variations and product impact. |  | C | Before starting a high-impact innovation project, the project manager should request the project team to develop a release plan and roadmap. This provides stakeholders with a clear visual representation of the project's trajectory, milestones, deliverables, and timelines—setting realistic expectations and aligning business concerns with project goals. Asking the product owner to prioritize by ROI (A) is a backlog activity, not expectation management. Directing detailed story estimation (B) is too granular for pre-project planning. Meeting with the finance team (D) addresses financial aspects but not overall stakeholder expectations. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 3천만 달러 이상의 예산을 가진 혁신 프로젝트가 기술 산업에 큰 영향을 미칠 것으로 예상된다. 비즈니스 케이스 준비가 끝났다. PM은 무엇을 해야 하는가? | 제품 책임자에게 ROI 기반으로 백로그 항목의 우선순위를 지정하도록 요청한다 | 프로젝트 팀에게 사용자 스토리를 더 세부적으로 추정하도록 지시한다 | 프로젝트 팀에게 릴리스 계획과 로드맵을 개발하도록 요청한다 | 프로젝트 재무팀과 만나 시장 변동과 제품 영향을 측정한다 |  | C | 고영향 혁신 프로젝트 시작 전, PM은 프로젝트 팀에게 릴리스 계획과 로드맵을 개발하도록 요청해야 한다. 이는 이해관계자에게 명확한 시각적 표현을 제공한다. ROI 우선순위(A)는 부분적이다. 세부 추정(B)은 로드맵 전에 시기상조이다. 시장 변동(D)은 계획 전에 측정이 어렵다.
826 | In a hybrid project, a stakeholder requests some feature modifications directly to one of the team members. When investigating further, the project manager finds this to be a common practice in the business, which is different from what is stated in the project management plan. What should the project manager do? | Make sure that all stakeholders are aware and in agreement with the project governance structure m place | Advise the team not to engage in modifications unless it follows the proper change approval process | Update the risk register including noncompliance with the change process as a probable cause for scope creep | Escalate to the project management office (PMO) and request that the team member who accepted the request be replaced |  | B | When stakeholders request feature modifications directly to team members outside the formal change process, the project manager should advise the team not to engage in modifications unless it follows the proper change approval process. This ensures scope is controlled and aligned with the project management plan. Making stakeholders aware of governance (A) is informational but does not directly address the team's behavior. Updating the risk register (C) documents the concern but does not prevent recurrence. Escalating to the PMO and requesting team member replacement (D) is excessive and punitive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 하이브리드 프로젝트에서 이해관계자가 팀원에게 직접 기능 수정을 요청한다. PM은 무엇을 해야 하는가? | 모든 이해관계자가 프로젝트 거버넌스 구조를 인식하고 동의하도록 한다 | 적절한 변경 승인 절차를 따르지 않으면 수정에 참여하지 않도록 팀에 조언한다 | 변경 프로세스 미준수를 범위 확대의 가능한 원인으로 리스크 등록부에 업데이트한다 | PMO에 에스컬레이션하고 요청을 수락한 팀원에 대한 조치를 요청한다 |  | B | 이해관계자가 공식 변경 프로세스 밖에서 팀원에게 직접 수정을 요청할 때, PM은 적절한 변경 승인 절차를 따르지 않으면 수정에 참여하지 않도록 팀에 조언해야 한다. 프로세스 준수가 범위 통제를 보장한다. 거버넌스 인식(A)은 예방적이지만 즉각 대응이 아니다. 리스크 등록(C)은 보조적이다. PMO 에스컬레이션(D)은 과도하다.
827 | A project manager notices that an extroverted project team member appears to be increasingly controlling the direction of the entire team. The other team members are not complaining but seem to be more passive. What should the project manager do? | Meet with the extroverted team member and ask them to be more sensitive to others. | Observe the team dynamics closely and step in if a team member complains. | Meet with each team member to better understand the situation. | Address the situation in a team meeting and ask everyone to be more active. |  | C | The correct answer is C. Meet with each team member to better understand the situation. Effective resource management ensures team members have the necessary competencies and support. The PM should identify gaps and address them through training, coaching, or mentoring. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 외향적인 팀원이 전체 프로젝트의 방향을 점점 통제하는 것을 발견했다. PM은 무엇을 해야 하는가? | 외향적인 팀원과 만나 다른 사람에게 더 민감해지도록 요청한다 | 팀 역학을 면밀히 관찰하고 팀원이 불만을 표시하면 개입한다 | 각 팀원과 만나 상황을 더 잘 이해한다 | 팀 회의에서 상황을 다루고 모두에게 더 적극적으로 참여하도록 요청한다 |  | C | 정답은 C이다. 각 팀원과 만나 상황을 더 잘 이해한다. 효과적인 자원 관리는 팀원들이 필요한 역량과 지원을 갖추도록 한다. PM은 개별 면담을 통해 근본 원인을 파악해야 한다. 외향적 팀원에게만(A)은 한쪽만 다룬다. 관찰만(B)은 수동적이다. 팀 회의(D)는 개인을 당황하게 할 수 있다.
828 | A project team is struggling to meet the project deadline due to a recurring conflict between two team members. What should the project manager do? | Schedule team-building activities as required. | Hold the team collectively responsible for their actions. | Explore the possibility of reshuffling the team. | Introduce training sessions to improve the team ' s performance. |  | A | The correct answer is A. Schedule team-building activities as required. The PM should address team issues proactively by understanding root causes, building trust, and creating an environment that fosters collaboration and high performance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 두 팀원 간의 반복적 갈등으로 프로젝트 기한을 맞추기 어려워하고 있다. PM은 무엇을 해야 하는가? | 필요에 따라 팀빌딩 활동을 일정에 잡는다 | 팀에 행동에 대한 공동 책임을 묻는다 | 팀 재편성 가능성을 탐색한다 | 팀 성과 향상을 위한 교육 세션을 도입한다 |  | A | 정답은 A이다. 필요에 따라 팀빌딩 활동을 일정에 잡는다. PM은 근본 원인을 이해하고, 신뢰를 구축하며, 협력을 촉진하는 환경을 만들어 팀 이슈를 사전적으로 해결해야 한다. 공동 책임(B)은 갈등을 해결하지 않는다. 재편성(C)은 과도한 조치이다. 교육(D)은 대인관계 갈등을 다루지 않는다.
829 | A project manager working on a software development project asked the software developer about the status of a task. The developer responded that the task was delivered 1 week ago and mentioned that the delivery was reported via a specific project management software. What should the project manager do next? | Review the stakeholder engagement plan and communicate which technology is available to develop, transmit, and store project artifacts. | Review the communications management plan and communicate which technology is to be used to develop, transmit, and store project artifacts, | Research the project management software to understand how it works, and establish it as the acceptable software to hold the project artifacts. | Engage the software developer, let them work with this project management software, and then conduct a train-the-trainer activity to ensure everyone can use it. |  | B | When a developer reports task delivery via a project management tool the PM was unaware of, the project manager should review the communications management plan and communicate which technology is to be used for project artifacts. Aligning on communication tools prevents future gaps. Reviewing the stakeholder engagement plan (A) is broader than needed. Researching and establishing the software (C) acts before reviewing the plan. Training the developer (D) assumes the tool is correct. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 소프트웨어 개발 프로젝트에서 PM이 개발자에게 작업 상태를 물었더니 PM이 모르는 PM 도구를 통해 인도했다고 보고했다. PM은 무엇을 해야 하는가? | 이해관계자 참여 계획을 검토하고 사용 가능한 기술을 커뮤니케이션한다 | 커뮤니케이션 관리 계획을 검토하고 사용할 기술을 커뮤니케이션한다 | PM 소프트웨어를 연구하여 작동 방식을 이해하고 수용 가능한 도구로 설정한다 | 소프트웨어 개발자를 참여시켜 이 PM 소프트웨어로 작업하게 한 후 검토를 실시한다 |  | B | 개발자가 PM이 모르는 도구를 통해 작업을 보고했을 때, PM은 커뮤니케이션 관리 계획을 검토하고 사용할 기술을 커뮤니케이션해야 한다. 공식 커뮤니케이션 채널을 명확히 하는 것이 중요하다. 이해관계자 계획(A)은 커뮤니케이션 도구를 다루지 않는다. 소프트웨어 연구(C)는 비공식 도구를 공식화한다. 참여(D)는 과도하다.
830 | A team has been working on a project for several months, but the completion date is unclear because the scope is changing frequently as new knowledge is gained. Some deliverables have already been completed, but when new stakeholders join the team, they complain that project outcomes are not meeting business goals. How can the project manager prevent this situation from happening in the future? | Create a prioritized backlog and define iteration review sessions with stakeholders | Schedule a kick-off meeting for every project phase to share the project management plan with all stakeholders | Schedule a daily meeting to review team performance and impediments | Create a detailed work breakdown structure (WBS) and milestone schedule approved by all stakeholders |  | A | When project scope changes frequently and new stakeholders complain outcomes do not meet business goals, the project manager can prevent this by creating a prioritized backlog and defining iteration review sessions with stakeholders. Prioritization ensures alignment with business goals while iteration reviews validate deliverables. Scheduling kick-off meetings per phase (B) is too infrequent. Daily meetings for performance (C) is excessive. A detailed WBS and milestone schedule (D) is predictive and may not accommodate changing scope. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Embed Quality | Define Scope | Traditional PM | 팀이 수개월간 프로젝트를 진행했지만 범위가 자주 변경되어 완료 날짜가 불분명하다. 새 이해관계자가 결과가 비즈니스 목표를 충족하지 않는다고 불만이다. PM은 무엇으로 이를 방지할 수 있었는가? | 우선순위가 지정된 백로그를 만들고 이해관계자와 이터레이션 검토 세션을 정의한다 | 모든 이해관계자와 프로젝트 관리 계획을 공유하기 위해 각 단계마다 킥오프 미팅을 일정한다 | 팀 성과와 장애물을 검토하기 위한 일일 미팅을 일정한다 | 모든 이해관계자가 승인하는 상세한 WBS와 마일스톤 일정을 만든다 |  | A | 범위가 자주 변경되고 결과가 비즈니스 목표를 충족하지 않을 때, PM은 우선순위 백로그를 만들고 이터레이션 검토 세션을 정의하여 방지할 수 있었다. 정기적 검토가 지속적 정렬을 보장한다. 킥오프 미팅(B)은 일회성이다. 일일 미팅(C)은 전략 정렬이 아닌 전술 관리이다. WBS(D)는 변경이 잦은 환경에 경직적이다.
831 | A project has been running successfully for 2 months. At a regular project meeting, the team raises several potential obstacles to future progress. The obstacles include vendor delivery performance, technical performance of a subsystem, and conflict with another division of the organization. What should the project manager do next? | Determine a change response to identify and resolve the obstacles to move the projectforward. | Escalate the obstacles to the project sponsor for assistance with resolution. | Engage with the external stakeholders and the other division of the organization toresolve the issues. | Work with the team and others in the network to assess and prioritize the obstacles. |  | D | When the team raises potential obstacles including vendor performance, technical subsystem issues, and organizational conflict, the project manager should work with the team and others in the network to assess and prioritize the obstacles. This collaborative assessment determines impact and probability, enabling informed decisions about response strategies. Determining a change response (A) is premature without first assessing and prioritizing. Escalating to the sponsor (B) delegates the PM's responsibility. Engaging external stakeholders directly (C) addresses one obstacle without prioritizing all three. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 프로젝트가 2개월간 성공적으로 진행 중이다. 정기 회의에서 팀이 벤더 성과, 기술 하위시스템 문제, 조직 갈등 등 여러 잠재적 장애물을 제기했다. PM은 무엇을 해야 하는가? | 장애물을 식별하고 해결하기 위한 변경 대응을 결정한다 | 해결 지원을 위해 프로젝트 스폰서에게 장애물을 에스컬레이션한다 | 외부 이해관계자 및 조직의 다른 부서와 이슈를 해결하기 위해 참여한다 | 팀 및 네트워크의 다른 사람들과 협력하여 장애물을 평가하고 우선순위를 지정한다 |  | D | 팀이 벤더 성과, 기술 문제, 조직 갈등 등 다양한 장애물을 제기할 때, PM은 팀 및 네트워크와 협력하여 평가하고 우선순위를 지정해야 한다. 협력적 평가가 효과적 대응의 기초이다. 변경 대응(A)은 평가 후에 한다. 에스컬레이션(B)은 직접 해결 전에 시기상조이다. 외부 참여(C)는 내부 평가 후에 한다.
832 | Important projects in the portfolio backlog need to be delivered. Budget estimates are needed to prioritize the projects. How should the project budgets be estimated? | The product owner obtains all project details and based on the team ' s experience and velocity provides a budget estimate | The project is decomposed into features and based on the feature value and the velocity of the team, the team provides the estimate | Budget estimates are provided based on the experience of the sponsor, product owner and team facilitator | The team facilitator uses historical data and arrives at an estimate based on the nature of the project. |  | B | For portfolio projects needing budget estimates for prioritization, the project should be decomposed into features and based on feature value and team velocity, the team provides the estimate. Feature-based estimation with velocity data enables realistic agile budgeting. Product owner providing estimates alone (A) lacks team input. Sponsor and facilitator experience-based estimates (C) are subjective. Historical data from the facilitator alone (D) may not reflect current team capacity. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 포트폴리오 백로그의 중요 프로젝트가 전달되어야 한다. 프로젝트 우선순위 지정을 위해 예산 추정이 필요하다. 어떻게 추정해야 하는가? | 제품 책임자가 모든 프로젝트 세부사항을 얻고 팀 경험과 속도를 기반으로 추정을 제공한다 | 프로젝트를 기능으로 분해하고 기능 가치와 팀 속도를 기반으로 팀이 추정을 제공한다 | 스폰서, 제품 책임자, 팀 퍼실리테이터의 경험을 기반으로 예산 추정을 제공한다 | 팀 퍼실리테이터가 역사적 데이터를 사용하고 프로젝트 특성에 기반하여 추정한다 |  | B | 포트폴리오 프로젝트의 예산 추정을 위해, 프로젝트를 기능으로 분해하고 기능 가치와 팀 속도를 기반으로 팀이 추정을 제공해야 한다. 기능 기반 분해와 속도 기반 추정이 애자일에서 가장 정확하다. 제품 책임자만(A)은 팀 참여가 부족하다. 경험 기반(C)은 주관적이다. 퍼실리테이터만(D)은 팀 입력이 부족하다.
833 | A business analyst on the project meets the customer in the elevator and says that due to constant changes in requirements, the development of the product will take more time than expected. What should the project manager do? | Point out to the project team and the customer that all information concerning the timeline of the project should be communicated by the project manager. | Explain that distribution of important news can only be done using traceable communication methods | Refer to the resource management plan to find out if more business analysts may be assigned to process the requirements changes | Submit a change request to the change control board (CCB) in order to reflect the new requirements and longer timeline of the project |  | A | When a business analyst informally tells the customer about timeline impacts from requirement changes, the project manager should point out that all timeline information should be communicated by the project manager. Controlled communication prevents confusion and maintains project governance. Referring to the resource management plan (B) addresses staffing, not communication. Explaining traceable communication methods (C) is good practice but does not address the authority issue. Submitting a change request (D) acts before establishing communication protocols. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 비즈니스 분석가가 엘리베이터에서 고객을 만나 요구사항 변경으로 인해 납기가 지연될 수 있다고 말했다. PM은 무엇을 해야 하는가? | 프로젝트 팀과 고객에게 프로젝트 일정에 관한 모든 정보는 PM이 전달해야 한다고 지적한다 | 중요한 뉴스의 배포는 추적 가능한 커뮤니케이션 방법으로만 가능하다고 설명한다 | 자원 관리 계획을 참조하여 더 많은 비즈니스 분석가를 배정할 수 있는지 확인한다 | 새로운 요구사항과 일정을 반영하기 위해 변경통제위원회(CCB)에 변경 요청을 제출한다 |  | A | 비즈니스 분석가가 비공식적으로 고객에게 일정 영향을 알릴 때, PM은 모든 일정 정보는 PM이 커뮤니케이션해야 한다고 지적해야 한다. 통제된 커뮤니케이션이 오해를 방지한다. 추적 가능한 방법(B)은 부분적으로 맞지만 핵심은 PM의 역할이다. 자원 추가(C)는 커뮤니케이션 문제를 다루지 않는다. CCB 제출(D)은 변경이 확정된 후의 단계이다.
834 | A new team member has joined an agile project, replacing a team member who recently left. The project team needs the new team member to speed up their ability to contribute effectively to the project. What should the project manager do to help in this situation? | Assign the new team member the same tasks that were assigned to the previous team member who they replaced | Send technical documentation to the new team member and schedule training for the next iteration. | Have the new team member complete all of the company's mandatory training | Schedule knowledge transfer sessions and assign less complex tasks to the new team member |  | D | When a new team member replaces someone on an agile project and needs to contribute quickly, the project manager should schedule knowledge transfer sessions and assign less complex tasks to the new member. This combination provides context through interactive learning and builds confidence through manageable work. Assigning the same tasks as the predecessor (A) may overwhelm the new member. Sending documentation and scheduling future training (B) delays contribution. Completing mandatory company training (C) is not project-specific. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scaled Agile | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Hybrid/Tailoring | 새 팀원이 최근 떠난 팀원을 대체하여 애자일 프로젝트에 합류했다. 팀은 새 팀원이 빠르게 기여하도록 해야 한다. PM은 무엇을 해야 하는가? | 이전 팀원에게 배정되었던 동일한 작업을 새 팀원에게 할당한다 | 새 팀원에게 기술 문서를 보내고 다음 이터레이션에 대한 교육을 예약한다 | 새 팀원에게 회사의 모든 필수 교육을 완료하게 한다 | 지식 이전 세션을 예약하고 덜 복잡한 작업을 새 팀원에게 할당한다 |  | D | 새 팀원이 빠르게 기여해야 할 때, 지식 이전 세션과 덜 복잡한 작업 할당을 결합해야 한다. 맥락을 제공하면서 점진적으로 역량을 구축한다. 동일 작업 할당(A)은 준비 없이 과부하를 줄 수 있다. 문서 전달(B)은 수동적이다. 필수 교육(C)은 프로젝트 기여와 직접 관련 없을 수 있다.
835 | A project sponsor has asked for a trend analysis of all risks the project has tracked over the last 12 months. What should the agile project manager do? | Organize a stakeholder meeting to brainstorm on general project risks. | Extract this from the project risk register tracking tool and issues log. | Refer the sponsor to the contract document. | Share the annual report with the sponsor. |  | B | Trend analysis leverages past performance data to forecast future project outcomes and serves as a quality control mechanism for tracking cost and schedule variances. Within agile projects, this technique is particularly useful for monitoring delivery velocity, quality metrics, and scope progress. The project risk register and issues log provide the historical data foundation needed for this analysis—the risk register captures identified risks along with their probability, impact, and planned responses, while the issues log documents occurred issues, their current status, and how they were resolved. Using these two data sources, the agile PM can compile a comprehensive trend analysis covering all monitored risks over the prior 12 months and deliver meaningful insights to the sponsor. The remaining options fall short: an annual report lacks sufficient risk-level detail, a brainstorming meeting may not accurately represent actual project data, and the contract document does not fulfill a trend analysis request. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 프로젝트 스폰서가 지난 12개월간 추적한 모든 리스크의 추세 분석을 요청했다. 애자일 PM은 무엇을 해야 하는가? | 일반 프로젝트 리스크에 대해 이해관계자 회의를 조직하여 브레인스토밍한다 | 프로젝트 리스크 등록부 추적 도구와 이슈 로그에서 추출한다 | 스폰서에게 계약 문서를 참조하도록 한다 | 스폰서에게 연간 보고서를 공유한다 |  | B | 리스크 추세 분석은 과거 성과 데이터를 활용하여 미래 프로젝트 결과를 예측한다. 리스크 등록부와 이슈 로그에서 데이터를 추출하는 것이 적절하다. 브레인스토밍(A)은 새 리스크 식별이지 추세 분석이 아니다. 계약 문서(C)는 리스크 추세와 무관하다. 연간 보고서(D)는 일반적이다.
836 | A project manager is leading a project that is on time and under budget. In the weekly meeting with the team, the project manager finds out that one of the tasks due next week does not have an assigned resource available for it. The resource is currently assigned to another project. What should the project manager do to manage the situation? | Ask the procurement department to supply a different resource. | Ask the sponsor to obtain the resource as originally planned. | Contact the other project manager to request the resource. | Change the schedule according to the availability of the resource. |  | C | When a required resource is currently assigned to another project, the project manager should contact the other project manager to request the resource. Negotiation and collaboration between project managers is the preferred approach to resolve resource conflicts, seeking a mutually acceptable agreement that balances both projects' needs. Asking procurement for a different resource (A) may introduce additional costs and delays. Asking the sponsor to obtain the resource (B) escalates unnecessarily when the PM should first try direct negotiation. Changing the schedule to accommodate availability (D) affects scope and stakeholder expectations without attempting to resolve the conflict. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 프로젝트가 일정에 맞고 예산 미만이다. PM이 필요한 자원이 다른 프로젝트에 배정되어 있음을 발견했다. PM은 무엇을 해야 하는가? | 조달 부서에 다른 자원을 공급하도록 요청한다 | 스폰서에게 원래 계획대로 자원을 확보하도록 요청한다 | 다른 프로젝트 관리자에게 연락하여 자원을 요청한다 | 자원 가용성에 따라 일정을 변경한다 |  | C | 필요한 자원이 다른 프로젝트에 배정되어 있을 때, PM은 다른 프로젝트 관리자에게 연락하여 자원을 요청해야 한다. PM 간 협상과 협업이 자원 충돌 해결의 선호 접근법이다. 조달 부서(A)는 외부 자원이다. 스폰서 요청(B)은 직접 해결 시도 전에 성급하다. 일정 변경(D)은 자원 확보 노력 전에 수동적이다.
837 | After the demo on a software project, one of the key stakeholders contacted the scrum master and complained that they were unaware of changes made to the project. After checking, the scrum master learned that the stakeholder's details were incorrectly entered into the register. What should the scrum master do? | Ask the product owner to update the stakeholders ' contact information at every meeting to address any changes. | Update the stakeholder ' s information and inform them that they must make the team aware of any changes. | Check the stakeholder register and ensure that every stakeholder ' s information is correct and current. | Consider it a loss since the stakeholder should have ensured the contact information was up to date. |  | C | When a stakeholder's details were incorrectly entered in the register causing them to miss project updates, the scrum master should check the stakeholder register and ensure every stakeholder's information is correct and current. Proactive verification prevents recurrence. Asking the product owner to update contacts at every meeting (A) is inefficient. Updating the stakeholder and shifting responsibility to them (B) is inappropriate. Considering it a loss (D) demonstrates poor accountability. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 소프트웨어 프로젝트 데모 후 주요 이해관계자가 연락처가 잘못 입력되어 업데이트를 받지 못했다고 불만했다. 스크럼 마스터는 무엇을 해야 하는가? | 제품 책임자에게 매 회의 시 이해관계자 연락처 정보를 업데이트하도록 요청한다 | 이해관계자의 정보를 업데이트하고 연락처 변경 시 팀에 알려야 한다고 알린다 | 이해관계자 등록부를 확인하고 모든 이해관계자의 정보가 정확하고 최신인지 확인한다 | 이해관계자가 연락처 정보가 최신인지 확인했어야 하므로 손실로 간주한다 |  | C | 이해관계자의 연락처가 잘못 입력되어 업데이트를 받지 못했을 때, 스크럼 마스터는 이해관계자 등록부를 확인하고 모든 정보가 정확하고 최신인지 확인해야 한다. 사전적 검증이 재발을 방지한다. 매 회의 업데이트(A)는 과도하다. 이해관계자에게 알림(B)은 책임을 전가한다. 손실 간주(D)는 무책임하다.
838 | A new regulation has been approved that will impact the deliverables in the fourth phase of the project. The delivery is following an iterative approach and is currently completing the second phase. What should the project manager do next? | Consult with the project sponsor to discuss a cost increase | Meet with subject matter experts (SMEs) to assess the impact to objectives | Acquire approval for an exception to the implementation of the new regulation. | Get approval for the additional budget from the steering committee |  | B | When a new regulation will impact fourth-phase deliverables while completing the second phase using an iterative approach, the project manager should meet with SMEs to assess the impact on objectives. Expert assessment provides informed understanding. Consulting the sponsor about cost increase (A) is premature. Seeking an exception (C) may not be feasible. Getting budget approval from the steering committee (D) assumes cost impact before assessment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 새 규제가 프로젝트 4단계 인도물에 영향을 줄 것이다. 현재 반복적 접근으로 2단계를 완료 중이다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 스폰서와 비용 증가를 논의한다 | 주제 전문가(SME)와 만나 목표에 대한 영향을 평가한다 | 새 규제 시행에 대한 예외 승인을 얻는다 | 운영위원회에서 추가 예산 승인을 받는다 |  | B | 새 규제가 4단계 인도물에 영향을 줄 때, PM은 먼저 SME와 만나 목표에 대한 영향을 평가해야 한다. 전문가 평가가 정보에 기반한 이해를 제공한다. 비용 증가 논의(A)는 영향 평가 후에 한다. 예외 승인(C)은 규정 준수를 위험에 빠뜨린다. 추가 예산(D)은 영향 평가 후의 단계이다.
839 | A project manager is working with several junior engineers on a project. The project manager noticed that when the junior engineers are asked questions, they defer to more senior team members on the team for answers. Having worked with the junior engineers on another project, the project manager knows they are capable of making these minor decisions correctly. This uncertainty from the junior engineers is now slowing progress. What should the project manager do? | Update the risk register to reflect the possible impact of the projects slower progress, | Ensure the junior engineers make decisions within a certain responsibility level and commit to it, | Remove the junior engineers from any decision-making activity until further trained. | Pair senior engineers to shadow the junior engineers and correct them throughout. 1249 |  | B | When capable junior engineers defer to seniors on minor decisions, slowing progress, the project manager should ensure the junior engineers make decisions within a defined responsibility level and commit to them. Empowerment within boundaries builds confidence. Updating the risk register (A) is documentation, not development. Removing them from decisions (C) worsens the problem. Pairing with seniors for shadowing (D) may reinforce dependency. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Align Stakeholder Expectations | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 여러 주니어 엔지니어와 프로젝트를 진행 중이다. 주니어 엔지니어들이 사소한 결정도 시니어에게 미루어 진행이 느려진다. PM은 무엇을 해야 하는가? | 프로젝트 진행 속도 저하의 가능한 영향을 반영하도록 리스크 등록부를 업데이트한다 | 주니어 엔지니어가 일정 책임 수준 내에서 결정을 내리고 이를 이행하도록 한다 | 추가 교육을 받을 때까지 주니어 엔지니어를 모든 의사결정 활동에서 제외한다 | 시니어 엔지니어를 배치하여 주니어 엔지니어를 따라다니며 전체적으로 교정한다 |  | B | 역량 있는 주니어 엔지니어가 사소한 결정을 시니어에게 미룰 때, PM은 정의된 책임 수준 내에서 결정을 내리고 이행하도록 해야 한다. 경계 내 권한 부여가 자신감을 구축한다. 리스크 등록부(A)는 근본 원인을 해결하지 않는다. 활동 제외(C)는 성장을 방해한다. 쉐도잉(D)은 의존성을 만든다.
840 | A project manager is using a hybrid approach for project delivery. The development team was sized, but is not yet fully resourced. The project manager is working on defining the project schedule. What should the project manager do to address the issue of developer availability? | Use expert judgment to estimate all of the tasks and complete the schedule in the allocated time. 1245 | Ask the sponsor to provide the desired completion date for project activities and complete the schedule. | Organize a planning session with the development team and use their estimations to complete the schedule. | Ask the resource manager when the new contractor is available to start and change the delivery date for the project schedule. |  | C | When the development team is not fully resourced but the schedule must be defined, the project manager should organize a planning session with the team and use their estimations to complete the schedule. Team-based estimation is most accurate. Using expert judgment alone (A) misses team input. Asking the sponsor for dates (B) imposes external deadlines. Waiting for a contractor (D) delays planning. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Schedule | Planning | Be an Accountable Leader | Define Activities | Hybrid/Tailoring | PM이 하이브리드 접근법으로 프로젝트를 관리 중이다. 개발 팀이 규모는 정해졌으나 아직 완전히 자원이 확보되지 않았다. 일정을 정의해야 한다. PM은 무엇을 해야 하는가? | 전문가 판단을 사용하여 모든 작업을 추정하고 할당된 시간 내에 일정을 완성한다 | 스폰서에게 프로젝트 활동의 원하는 완료 날짜를 제공하도록 요청하고 일정을 완성한다 | 개발 팀과 계획 세션을 조직하고 팀의 추정을 사용하여 일정을 완성한다 | 자원 관리자에게 새 계약자의 가용 시점을 물어보고 그에 따라 납기일을 변경한다 |  | C | 개발 팀이 완전히 자원 확보되지 않았지만 일정을 정의해야 할 때, PM은 팀과 계획 세션을 조직하고 팀의 추정을 사용해야 한다. 팀 기반 추정이 가장 정확하다. 전문가 판단(A)은 팀 참여가 없다. 스폰서 날짜(B)는 하향식이다. 자원 가용성 대기(D)는 일정을 지연시킨다.
841 | As part of its growth strategy, management is providing all of its ongoing projects with junior employees and is requesting experienced team members to mentor them. The experienced employees argue that the mentoring program will not add value to their projects and will limit their ability to deliver. How should the project manager handle this situation? | Recommend to management that the junior employees should receive formal training and courses. | Allocate specific time for experienced team members to mentor the junior employees. | Assign an instructor to mentor the junior employees so that the experienced team members can focus on project tasks. | Schedule time with all of the project team members since it is the role of the project manager to mentor the team. |  | B | When management directs experienced staff to mentor junior employees and experienced members argue it limits delivery, the project manager should allocate specific time for mentoring. Structured time balances delivery and development. Recommending formal training (A) removes experiential learning. Scheduling PM-led mentoring (C) misinterprets the mentoring structure. Assigning an external instructor (D) reduces team cohesion. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Resources | Executing | Focus on Value | Acquire Resources | Traditional PM | 경영진이 모든 진행 중인 프로젝트에 주니어 직원을 배치하고 경험 있는 팀원에게 멘토링을 요청한다. 경험 있는 팀원은 납품이 제한된다고 주장한다. PM은 무엇을 해야 하는가? | 경영진에게 주니어 직원이 공식 교육과 과정을 받아야 한다고 추천한다 | 경험 있는 팀원이 주니어 직원을 멘토링할 특정 시간을 할당한다 | 경험 있는 팀원이 납품에 집중할 수 있도록 강사를 배정하여 주니어 직원을 멘토링한다 | PM의 역할이므로 모든 프로젝트 팀원과 시간을 예약한다 |  | B | 경영진이 경험자에게 멘토링을 지시하고 경험자가 납품 제한을 주장할 때, PM은 멘토링을 위한 특정 시간을 할당해야 한다. 구조화된 시간이 납품과 개발의 균형을 맞춘다. 공식 교육(A)은 현장 멘토링과 다르다. 강사 배정(C)은 경영진 지시를 우회한다. PM이 직접 멘토링(D)은 역할 혼동이다.
842 | At the end of a workshop to review project deliverables, a number of follow-up action items were generated. What should the project manager do next? | Prioritize the actions with the team, assign individuals who will be responsible for completion, and monitor progress. | Follow up on each item as soon as possible to ensure timely completion and report the status to management. | Defer all actions until the next workshop to keep the team focused on other higher priorities | Review the critical path and update the project schedule with the newly identified tasks. |  | A | After a workshop generates follow-up action items, the project manager should prioritize the actions with the team, assign individuals responsible for completion, and monitor progress. Clear ownership and deadlines ensure accountability and momentum. Following up individually as soon as possible (B) lacks prioritization and team coordination. Deferring all actions until the next workshop (C) loses momentum. Reviewing the critical path and updating the schedule (D) may not apply to all workshop action items. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 인도물 검토 워크숍 종료 시 다수의 후속 조치 항목이 생성되었다. PM은 무엇을 해야 하는가? | 팀과 함께 조치를 우선순위화하고, 완료 책임자를 지정하며, 진행 상황을 모니터링한다 | 적시 완료를 보장하기 위해 각 항목을 가능한 빨리 후속 조치하고 경영진에게 상태를 보고한다 | 팀이 다른 우선순위에 집중하도록 모든 조치를 다음 워크숍까지 연기한다 | 주공정선을 검토하고 새로 식별된 작업으로 프로젝트 일정을 업데이트한다 |  | A | 워크숍에서 후속 조치 항목이 생성된 후, PM은 팀과 함께 우선순위화하고 책임자를 지정하며 진행을 모니터링해야 한다. 명확한 책임과 기한이 책임감과 추진력을 보장한다. 즉시 후속 조치(B)는 우선순위화 없이 비효율적이다. 연기(C)는 모멘텀을 잃는다. 일정 업데이트(D)는 부분적이다.
843 | An external project manager is managing the construction of new corporate offices for a large company. The project management plan states that it is necessary to contract a highly trained external resource to review and validate an important project component. The client has rejected hiring the external resource because of the high cost even though it is within the project budget. What should the project manager do to resolve this issue? | Try to accomplish the task internally by leveling resources from other projects | Evaluate the consequences and meet with the client to explain the possible scenarios. | Hire the resource in order to achieve the project objectives. | Ask the client for a meeting and explain that the task will not be performed |  | B | The PM should evaluate the consequences of the situation and meet with the client to present possible scenarios. Hiring the resource without client approval would violate contractual terms and trust. Simply declining to perform the task would compromise project objectives. Leveling resources from other projects would create cross-project risks and dependencies. Instead, the PM should assess the impact of not engaging the external resource, identify alternative solutions (negotiation, alternative resources, plan modifications), and collaborate with the client to reach a mutually acceptable resolution. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 외부 프로젝트 매니저가 대기업의 신규 사옥 건설을 관리하고 있습니다. Project Management Plan에는 중요한 프로젝트 구성 요소를 검토하고 검증하기 위해 고도로 훈련된 외부 리소스를 계약해야 한다고 명시되어 있습니다. 고객은 해당 비용이 프로젝트 예산 내에 있음에도 불구하고 높은 비용을 이유로 외부 리소스 고용을 거부했습니다. 프로젝트 매니저는 이 문제를 해결하기 위해 무엇을 해야 합니까? | 다른 프로젝트의 리소스를 평준화하여 내부적으로 작업을 수행하도록 노력한다. | 결과를 평가하고 고객과 만나 가능한 시나리오에 대해 설명한다. | 프로젝트 목표 달성을 위해 리소스를 고용한다. | 고객에게 회의를 요청하고 해당 작업이 수행되지 않을 것임을 설명한다. |  | B | PM은 상황의 결과를 평가하고 고객과 만나 가능한 시나리오를 제시해야 합니다. 고객의 승인 없이 리소스를 고용하는 것은 계약 조건과 신뢰를 위반하는 것입니다. 단순히 작업 수행을 거부하는 것은 프로젝트 목표를 훼손할 수 있습니다. 타 프로젝트의 리소스를 평준화하는 것은 프로젝트 간 리스크와 의존성을 생성합니다. 대신 PM은 외부 리소스를 사용하지 않을 때의 영향을 평가하고, 대안(협상, 대체 리소스, 계획 수정 등)을 식별하여 고객과 상호 수용 가능한 해결책에 도달하도록 협력해야 합니다.
844 | A project manager is managing an agile project that is part of a program with many interconnected projects. Dependency management is fundamental because there will be many milestones for different projects that are dependent upon each other during the program duration. What should the project manager do? | Assign a development team member to have the responsibility of managing dependencies. | Continue the project with 2-week iterations as dependencies will be managed individually | Suggest that each project develops a high-level plan to monitor the dependencies | Recommend switching to a predictive approach to have detailed plans to manage the dependencies |  | C | When managing an agile project within a program with many interconnected project dependencies, the project manager should suggest that each project develops a high-level plan to monitor dependencies. High-level planning ensures cross-project visibility. Assigning one team member to manage dependencies (A) creates a bottleneck. Continuing with 2-week iterations (B) ignores program-level coordination. Switching to predictive (D) contradicts the agile approach. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 매니저가 상호 연결된 프로젝트가 많은 프로그램의 일부인 Agile 프로젝트를 관리하고 있습니다. 프로그램 기간 동안 서로 의존하는 여러 프로젝트의 Milestones이 많기 때문에 의존성 관리(Dependency management)가 필수적입니다. 프로젝트 매니저는 무엇을 해야 합니까? | 개발 팀원 중 한 명에게 의존성 관리 책임을 할당한다. | 의존성은 개별적으로 관리될 것이므로 2주 간격의 Iteration으로 프로젝트를 계속 진행한다. | 각 프로젝트가 의존성을 모니터링하기 위한 상위 수준의 계획을 개발하도록 제안한다. | 의존성 관리를 위한 세부 계획을 갖출 수 있도록 예측형(Predictive) 접근 방식으로 전환할 것을 권장한다. |  | C | 상호 연결된 프로젝트 의존성이 많은 프로그램 내에서 Agile 프로젝트를 관리할 때, 프로젝트 매니저는 각 프로젝트가 의존성을 모니터링하기 위한 상위 수준의 계획을 개발하도록 제안해야 합니다. 상위 수준의 계획은 프로젝트 간 가시성을 보장합니다. 한 팀원에게 의존성 관리를 할당하는 것(A)은 병목 현상을 만듭니다. 2주 간격의 이터레이션을 계속하는 것(B)은 프로그램 수준의 조정을 무시하는 것입니다. 예측형으로 전환하는 것(D)은 Agile 접근 방식과 상충됩니다.
845 | As the project progresses, the team is not performing at acceptable levels and in accordance with the key performance indicators (KPIs) that were set at the beginning of the project. How should the project manager resolve this? | Escalate a schedule risk to the sponsor. | Make sure that the team has a full understanding of the scope. | Stop the project and perform a team skill assessment. | Conduct team-building exercises. |  | B | When the team is not performing to KPIs set at the beginning, the project manager should make sure the team has a full understanding of the scope. Clarity on expectations enables performance improvement. Escalating a schedule risk (A) does not address team performance. Stopping the project for skill assessment (C) is extreme. Team-building exercises (D) improve dynamics but do not address scope understanding. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트가 진행됨에 따라, 팀의 성과가 프로젝트 시작 시 설정된 Key Performance Indicators (KPIs)에 따른 허용 가능한 수준에 미치지 못하고 있습니다. 프로젝트 매니저는 이를 어떻게 해결해야 합니까? | 일정 리스크를 Sponsor에게 보고(Escalate)한다. | 팀이 범위(Scope)를 완전히 이해하고 있는지 확인한다. | 프로젝트를 중단하고 팀 기술 평가를 실시한다. | 팀 빌딩 활동을 수행한다. |  | B | 팀이 처음에 설정된 KPI를 달성하지 못할 때, 프로젝트 매니저는 팀이 범위(Scope)를 완전히 이해하고 있는지 확인해야 합니다. 기대치에 대한 명확성은 성과 개선을 가능하게 합니다. 일정 리스크를 에스컬레이션하는 것(A)은 팀 성과 문제를 해결하지 못합니다. 기술 평가를 위해 프로젝트를 중단하는 것(C)은 극단적입니다. 팀 빌딩 활동(D)은 역동성을 개선하지만 범위 이해 문제를 해결하지는 못합니다.
846 | A project manager collects various pieces of information and consolidates metrics in an agile project. The project manager finds that there is slack in the team in terms of productivity. The number of items sent to development per person has decreased by 10%, and the project manager used a root cause analysis (RCA) and discovered the reason is a lack of knowledge in one of the frameworks used for modeling. What should the project manager do next? | Arrange for external training amid the tight project schedules. | Add new members for the underperforming team. | Seek an external expert to review the framework. | Foster knowledge sharing and coaching among team members. |  | D | When root cause analysis reveals decreased productivity due to lack of knowledge in a modeling framework, the project manager should foster knowledge sharing and coaching among team members. Internal collaboration addresses the knowledge gap efficiently without disrupting team dynamics. Arranging external training during tight schedules (A) is disruptive. Adding new members (B) does not leverage existing team knowledge. Seeking an external expert review (C) provides assessment but not sustained capability building. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 매니저가 Agile 프로젝트에서 다양한 정보를 수집하고 메트릭을 통합합니다. 프로젝트 매니저는 팀의 생산성 측면에서 Slack(여유)이 있음을 발견했습니다. 인당 개발로 넘어가는 항목의 수가 10% 감소했으며, 프로젝트 매니저는 Root Cause Analysis (RCA)를 사용하여 그 원인이 모델링에 사용되는 프레임워크 중 하나에 대한 지식 부족임을 발견했습니다. 프로젝트 매니저는 다음에 무엇을 해야 합니까? | 촉박한 프로젝트 일정 속에서도 외부 교육을 마련한다. | 성과가 저조한 팀에 신규 팀원을 추가한다. | 프레임워크를 검토할 외부 전문가를 찾는다. | 팀원들 간의 지식 공유와 코칭을 장려한다. |  | D | 근본 원인 분석(RCA)을 통해 모델링 프레임워크에 대한 지식 부족으로 생산성이 저하된 것이 밝혀지면, 프로젝트 매니저는 팀원 간의 지식 공유와 코칭을 장려해야 합니다. 내부 협업은 팀의 역동성을 해치지 않으면서 지식 격차를 효율적으로 해결합니다. 촉박한 일정 중 외부 교육을 마련하는 것(A)은 방해가 됩니다. 새 멤버를 추가하는 것(B)은 기존 팀 지식을 활용하지 못합니다. 외부 전문가 검토를 요청하는 것(C)은 평가는 제공하지만 지속적인 역량 구축은 되지 않습니다.
847 | A project manager is managing a project which is approaching the end of the execution phase. A high-level stakeholder informs the project manager that a very important requirement was not included in the scope of the project, and that without that requirement the project will deliver no value. What is the first thing the project manager should do? | Inform the project sponsor about the situation and request assistance | Include the requirement into the project and schedule it as soon as possible | Evaluate the impact that the inclusion of this new requirement will have on project performance | Inform the stakeholder that it is impossible to add new requirements to an approved project scope |  | C | When a high-level stakeholder identifies a missing critical requirement near execution's end, the project manager should first evaluate the impact of including the new requirement on project performance. Impact analysis enables informed decision-making. Informing the sponsor (A) is reactive without data. Including it immediately (B) bypasses change control. Informing the stakeholder it is impossible (D) dismisses a potentially valid need. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 매니저가 실행 단계의 끝에 가까워진 프로젝트를 관리하고 있습니다. 고위 관계자(High-level stakeholder)가 매우 중요한 요구사항이 프로젝트 범위에 포함되지 않았으며, 그 요구사항 없이는 프로젝트가 아무런 가치를 제공하지 못할 것이라고 프로젝트 매니저에게 알립니다. 프로젝트 매니저가 가장 먼저 해야 할 일은 무엇입니까? | 프로젝트 Sponsor에게 상황을 알리고 지원을 요청한다. | 요구사항을 프로젝트에 포함시키고 가능한 한 빨리 일정을 잡는다. | 이 새로운 요구사항의 포함이 프로젝트 성과에 미칠 영향을 평가한다. | 이해관계자에게 승인된 프로젝트 범위에 새로운 요구사항을 추가하는 것이 불가능하다고 알린다. |  | C | 실행 단계 종료 직전에 고위 이해관계자가 누락된 중요한 요구사항을 발견하면, 프로젝트 매니저는 먼저 이 새로운 요구사항이 프로젝트 성과에 미칠 영향을 평가해야 합니다. 영향 분석은 정보에 입각한 의사결정을 가능하게 합니다. 스폰서에게 알리는 것(A)은 데이터 없는 사후 반응일 뿐입니다. 즉시 포함하는 것(B)은 변경 통제를 무시하는 것입니다. 불가능하다고 알리는 것(D)은 잠재적으로 유효한 요구를 묵살하는 것입니다.
848 | A project manager is managing a hybrid project. After attending an iteration review, a stakeholder tells the project manager that they are very busy and asks why these reviews are held so frequently. How should the project manager respond? | Discuss with the stakeholder the benefits of the hybrid project and how frequent reviews lead to greater value and less rework | Record the issue in the issue log and escalate the conflict to the project sponsor for assistance | Negotiate a reduced review attendance with the stakeholder and update the stakeholder engagement plan to reflect this reduced attendance | Explain to the stakeholder that the stakeholder engagement plan requires theirattendance at all reviews |  | A | When a stakeholder questions why iteration reviews are held so frequently, the project manager should discuss the benefits of the hybrid approach and explain how frequent reviews lead to greater value delivery and less rework. Educating the stakeholder on the value of their participation helps maintain engagement and project quality. Recording the issue in the log and escalating to the sponsor (B) treats a legitimate question as a conflict. Negotiating reduced attendance (C) undermines the review process. Stating that the engagement plan requires attendance (D) is authoritarian and does not address the stakeholder's concern. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Hybrid/Tailoring | 프로젝트 매니저가 Hybrid 프로젝트를 관리하고 있습니다. Iteration review에 참석한 후, 한 이해관계자가 자신이 매우 바쁘다고 말하며 왜 이러한 리뷰를 그렇게 자주 여는지 묻습니다. 프로젝트 매니저는 어떻게 답변해야 합니까? | 이해관계자와 함께 Hybrid 프로젝트의 이점과 빈번한 리뷰가 어떻게 더 큰 가치를 창출하고 재작업을 줄이는지 논의한다. | 이슈 로그(Issue log)에 기록하고 해결을 위해 프로젝트 Sponsor에게 보고(Escalate)한다. | 이해관계자와 협의하여 리뷰 참석 횟수를 줄이고 이해관계자 참여 계획(Stakeholder engagement plan)을 업데이트한다. | 이해관계자에게 Stakeholder engagement plan에 따라 모든 리뷰에 참여해야 함을 설명한다. |  | A | 이해관계자가 이터레이션 리뷰를 왜 그렇게 자주 하는지 의문을 제기하면, PM은 하이브리드 접근 방식의 이점을 논의하고 빈번한 리뷰가 어떻게 더 큰 가치 전달과 재작업 감소로 이어지는지 설명해야 합니다. 참여의 가치에 대해 이해관계자를 교육하는 것은 참여도와 프로젝트 품질을 유지하는 데 도움이 됩니다. 이슈 로그 기록 및 에스컬레이션(B)은 정당한 질문을 갈등으로 취급하는 것입니다. 참석 횟수 협의(C)는 리뷰 프로세스를 약화시킵니다. 참여 계획에 따라 참석해야 한다고 명시하는 것(D)은 권위적이며 이해관계자의 우려를 해결하지 못합니다.
849 | At a meeting, the project manager for an agile project indicates that the sprint goals were not met. The product owner leaves the meeting early, and the team discusses how the meeting went. Team members are confused as there were no defects for the new user stories and no new requirements were discussed. What should the project manager do in the future to avoid this situation? | Review the definition of done (DoD) with the product owner. | Create better plans to test the functionality in more detail. | Get approval from the product owner on the user stories. | Include previous sprint defects and close them in the actual sprint. |  | A | When sprint goals are not met despite no defects or new requirements, it likely indicates a misalignment between the team's understanding and the product owner's expectations of what constitutes completed work. The project manager should review the definition of done (DoD) with the product owner to ensure everyone shares the same understanding. Creating better test plans (B) addresses quality but not the expectation gap. Getting product owner approval on user stories (C) is already part of the agile process and does not address DoD misalignment. Including previous sprint defects in the current sprint (D) is a separate backlog management concern. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 회의에서 Agile 프로젝트의 프로젝트 매니저가 Sprint 목표를 달성하지 못했다고 언급합니다. Product Owner는 회의를 일찍 떠나고, 팀은 회의가 어떻게 진행되었는지 논의합니다. 팀원들은 새로운 User stories에 결함이 없었고 새로운 요구사항도 논의되지 않았기 때문에 혼란스러워합니다. 프로젝트 매니저는 향후 이러한 상황을 피하기 위해 무엇을 해야 합니까? | Product Owner와 함께 완료 정의(DoD)를 검토한다. | 기능을 더 자세히 테스트하기 위한 더 나은 계획을 수립한다. | User stories에 대해 Product Owner로부터 승인을 받는다. | 이전 Sprint의 결함을 포함시키고 실제 Sprint에서 종료한다. |  | A | 결함이나 새로운 요구사항이 없음에도 스프린트 목표를 달성하지 못했다면, 이는 팀의 이해와 제품 책임자(PO)가 생각하는 '완료된 작업'에 대한 기대치가 일치하지 않음을 나타낼 가능성이 높습니다. 프로젝트 매니저는 모두가 동일한 이해를 공유할 수 있도록 PO와 함께 완료 정의(DoD)를 검토해야 합니다. 더 나은 테스트 계획 수립(B)은 품질은 다루지만 기대치 격차는 해결하지 못합니다. 사용자 스토리 승인(C)은 이미 Agile 프로세스의 일부이며 DoD 불일치를 해결하지 않습니다. 이전 결함 포함(D)은 별개의 백로그 관리 문제입니다.
850 | A project manager is managing a national rollout for an innovative product in a regulated environment that is expected to change. The project management office (PMO) needs visibility of the regulatory constraints while maintaining a degree of flexibility. Which tool can the project manager use? | Use a burndown chart to provide transparency. | Use a product backlog to manage changes. | Use a burnup chart to provide transparency. | Use a kanban board to increase accountability. |  | B | When a PMO needs visibility of regulatory constraints while maintaining flexibility for a national rollout in a changing regulated environment, the project manager should use a product backlog to manage changes. The backlog provides transparent, prioritized requirements management. A burndown chart (A) shows progress, not constraints. A burnup chart (C) tracks scope completion. A kanban board (D) manages workflow, not regulatory visibility. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 프로젝트 매니저가 변화가 예상되는 규제 환경에서 혁신적인 제품의 전국적인 출시를 관리하고 있습니다. Project Management Office (PMO)는 유연성을 유지하면서 규제 제약 조건에 대한 가시성을 필요로 합니다. 프로젝트 매니저는 어떤 도구를 사용할 수 있습니까? | 투명성을 제공하기 위해 Burndown chart를 사용한다. | 변경 사항을 관리하기 위해 Product backlog를 사용한다. | 투명성을 제공하기 위해 Burnup chart를 사용한다. | 책임성을 높이기 위해 Kanban board를 사용한다. |  | B | 변화하는 규제 환경에서 국가적 출시를 위해 규제 제약 조건의 가시성과 유연성이 모두 필요할 때, 프로젝트 매니저는 변경 사항 관리를 위해 제품 백로그(Product Backlog)를 사용해야 합니다. 백로그는 투명하고 우선순위가 정해진 요구사항 관리를 제공합니다. 번다운 차트(A)는 제약이 아닌 진행 상황을 보여줍니다. 번업 차트(C)는 범위 완료를 추적합니다. 칸반 보드(D)는 규제 가시성이 아닌 워크플로우를 관리합니다.
851 | At the end of a project's initiation phase, the budget was developed and submitted to the approval board. During the approval meeting, one of the key stakeholders asked how the budget was developed for future uncertainties. How should the project manager respond? | Feedback from stakeholders will be addressed at each board meeting to adapt the budget. | Probabilistic analysis was used to develop the budget to address future uncertainties. | The budget was developed by using the lessons learned from previous project data. | Recurrent team meetings are planned to control the budget against future uncertainties. |  | B | Probabilistic analysis examines multiple possible scenarios and their associated likelihoods to develop a budget that accounts for future uncertainties. This technique is widely used in project management to address inherent budgetary risks, providing a more comprehensive and realistic financial plan—particularly when significant unknowns exist about future conditions. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 프로젝트의 개시(Initiation) 단계 끝에 예산이 수립되어 승인 위원회에 제출되었습니다. 승인 회의 중에 주요 이해관계자 중 한 명이 미래의 불확실성에 대비해 예산이 어떻게 수립되었는지 물었습니다. 프로젝트 매니저는 어떻게 답변해야 합니까? | 각 이사회 회의에서의 이해관계자 피드백을 통해 예산을 조정할 것이다. | 미래의 불확실성에 대비하기 위해 확률적 분석(Probabilistic analysis)을 사용하여 예산을 수립했다. | 이전 프로젝트 데이터의 교훈(Lessons learned)을 활용하여 예산을 수립했다. | 미래의 불확실성에 대비해 예산을 통제하기 위해 반복적인 팀 회의가 계획되어 있다. |  | B | 확률적 분석(Probabilistic analysis)은 여러 가능한 시나리오와 그에 따른 확률을 조사하여 미래의 불확실성을 고려한 예산을 수립합니다. 이 기법은 프로젝트 관리에서 내재된 예산 리스크를 해결하기 위해 널리 사용되며, 특히 미래 조건에 대한 불확실성이 큰 경우 더욱 포괄적이고 현실적인 재무 계획을 제공합니다.
852 | A project manager is working on a software development project. Software development will be carried out through a partnership with a vendor based on a list of initial requirements not yet completely defined. What type of contract and project approach should the project manager consider? | Cost reimbursable contract with a predictive approach | Memorandum of understanding (MOU) with an agile approach | Time and materials (T & M) with an agile approach | Fixed-price contract with a predictive approach |  | C | When software development involves a vendor partnership with incompletely defined requirements, the project manager should consider a time and materials (T&M) contract with an agile approach. T&M provides payment flexibility while agile supports iterative development with evolving requirements. Cost reimbursable with predictive (A) lacks iterative flexibility. An MOU with agile (B) is not a formal enforceable contract. Fixed-price with predictive (D) assumes fixed scope, which does not fit undefined requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 프로젝트 매니저가 소프트웨어 개발 프로젝트를 진행하고 있습니다. 소프트웨어 개발은 아직 완전히 정의되지 않은 초기 요구사항 목록을 기반으로 벤더와 파트너십을 통해 수행될 예정입니다. 프로젝트 매니저는 어떤 유형의 계약과 프로젝트 접근 방식을 고려해야 합니까? | 예측형(Predictive) 접근 방식과 실비 정산 계약(Cost reimbursable contract) | Agile 접근 방식과 양해각서(MOU) | Agile 접근 방식과 시간 및 자재 투입 계약(T & M) | 예측형(Predictive) 접근 방식과 확정 고정가 계약(Fixed-price contract) |  | C | 요구사항이 불완전하게 정의된 벤더 파트너십의 경우, 프로젝트 매니저는 Agile 접근 방식과 시간 및 자재 투입(T&M) 계약을 고려해야 합니다. T&M은 지불 유연성을 제공하고, Agile은 진화하는 요구사항에 따른 반복적 개발을 지원합니다. 예측형과 실비 정산(A)은 반복적 유연성이 부족합니다. Agile과 MOU(B)는 정식 계약이 아닙니다. 예측형과 고정가 계약(D)은 확정된 범위를 가정하므로 미확정된 요구사항에는 적합하지 않습니다.
853 | A newly assigned project manager is reviewing the project management plan and realizes that the project is running behind schedule. What should the new project manager do to address this situation? | Negotiate with the project sponsor immediately and establish a new project charter. | Modify the project management plan and get approval from relevant stakeholders | Add more resources to recover the schedule without making changes to the baseline. | Issue a change order to the change control board (CCB) and rebaseline the schedule. |  | D | When a new project manager discovers the project is running behind schedule, they should issue a change order to the change control board (CCB) and rebaseline the schedule. Formal change management ensures authorized and documented modifications. Negotiating a new charter with the sponsor (A) is excessive. Modifying the plan and getting approval (B) bypasses formal change control. Adding resources without baseline changes (C) may not address the root cause. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 새로 배정된 프로젝트 관리자가 프로젝트 관리 계획을 검토하다가 프로젝트가 일정보다 뒤처지고 있음을 발견한다. 새 프로젝트 관리자는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 프로젝트 스폰서와 즉시 협상하고 새로운 프로젝트 헌장을 수립한다. | 프로젝트 관리 계획을 수정하고 관련 이해관계자의 승인을 받는다. | 기준선을 변경하지 않고 일정을 회복하기 위해 더 많은 자원을 추가한다. | 변경 통제 위원회(CCB)에 변경 명령을 발행하고 일정을 재기준선화한다. |  | D | 새 프로젝트 관리자가 프로젝트가 일정보다 뒤처지고 있음을 발견할 때, 변경 통제 위원회(CCB)에 변경 명령을 발행하고 일정을 재기준선화해야 한다. 공식적인 변경 관리는 승인되고 문서화된 수정을 보장한다. 스폰서와 새 헌장 협상(A)은 과도하다. 계획 수정 및 승인(B)은 공식적인 변경 통제를 우회한다. 기준선 변경 없이 자원 추가(C)는 근본 원인을 해결하지 못할 수 있다.
854 | A transformation project that is composed of agile streams has come to an end. How should the project manager collect the experience gained during this project? | Organize a lessons learned session with the team. | Ask for feedback during the next standup meeting. | Create a document with the information from the last sprint retrospective. | Conduct a session with the members of the project steering committee. |  | A | When a transformation project composed of agile streams concludes, the project manager should organize a lessons learned session with the team. A comprehensive retrospective captures what went well, what did not, and improvements for future projects. Asking for feedback at the next standup (B) is too limited. Creating a document from the last sprint retrospective (C) only covers the final sprint. Conducting a session with the steering committee (D) provides leadership insights but misses team-level experience. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Scrum | Process | Evaluate Project Status | Governance | Closing | Embed Quality | Close Project or Phase | Traditional PM | 애자일 스트림으로 구성된 전환 프로젝트가 종료되었다. 프로젝트 관리자는 이 프로젝트에서 얻은 경험을 어떻게 수집해야 하는가? | 팀과 함께 교훈 세션을 조직한다. | 다음 스탠드업 회의에서 피드백을 요청한다. | 마지막 스프린트 회고의 정보로 문서를 작성한다. | 프로젝트 운영 위원회 구성원들과 세션을 수행한다. |  | A | 애자일 스트림으로 구성된 전환 프로젝트가 종료될 때, 프로젝트 관리자는 팀과 함께 교훈 세션을 조직해야 한다. 포괄적인 회고는 잘된 점, 잘못된 점, 향후 프로젝트를 위한 개선 사항을 포착한다. 스탠드업에서 피드백 요청(B)은 너무 제한적이다. 마지막 스프린트 회고 문서 작성(C)은 최종 스프린트만 다룬다. 운영 위원회와 세션 수행(D)은 리더십 통찰을 제공하지만 팀 수준의 경험을 놓친다.
855 | A project manager receives a voicemail from a business analyst on the project team. The business analyst indicates that an internal stakeholder is upset that they were not included before the project began. The stakeholder is asking for an addition to the requirements traceability matrix. What should the project manager do to improve the stakeholder relationship? | Consult the project scope document to make sure the addition is in scope. | Update the stakeholder engagement plan to ensure the stakeholder is included in the project stakeholder list | Engage the stakeholder to solicit more information before responding to the request | Initiate a project change request so the change control board (CCB) can decide if it is in scope. |  | C | When an internal stakeholder missed from the project requests an addition to the requirements traceability matrix, the project manager should engage the stakeholder to solicit more information before responding to the request. Understanding their needs and concerns builds the relationship and provides context for the request. Consulting the scope document (A) checks scope but does not engage the stakeholder. Updating the stakeholder engagement plan (B) is procedural without engagement. Initiating a change request immediately (D) is premature before understanding the requirement. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 관리자가 프로젝트 팀의 비즈니스 분석가로부터 음성 메시지를 받는다. 비즈니스 분석가는 내부 이해관계자가 프로젝트 시작 전에 포함되지 않아 화가 났다고 알린다. 이해관계자가 요구사항 추적 매트릭스에 추가를 요청하고 있다. 프로젝트 관리자는 이해관계자 관계를 개선하기 위해 무엇을 해야 하는가? | 추가 사항이 범위 내에 있는지 확인하기 위해 프로젝트 범위 문서를 참조한다. | 이해관계자가 프로젝트 이해관계자 목록에 포함되도록 이해관계자 참여 계획을 업데이트한다. | 요청에 응답하기 전에 이해관계자와 소통하여 더 많은 정보를 수집한다. | 변경 통제 위원회(CCB)가 범위 내인지 결정할 수 있도록 프로젝트 변경 요청을 시작한다. |  | C | 프로젝트에서 누락된 내부 이해관계자가 요구사항 추적 매트릭스에 추가를 요청할 때, 프로젝트 관리자는 요청에 응답하기 전에 이해관계자와 소통하여 더 많은 정보를 수집해야 한다. 그들의 요구와 우려를 이해하면 관계를 구축하고 요청에 대한 맥락을 제공한다. 범위 문서 참조(A)는 범위를 확인하지만 이해관계자와 소통하지 않는다. 이해관계자 참여 계획 업데이트(B)는 참여 없는 절차적 작업이다. 즉시 변경 요청 시작(D)은 요구사항을 이해하기 전에 시기상조이다.
856 | A project manager is leading the construction of a branch office building for a national bank. The project manager is informed that the regulatory authority has closed the bank. In closing this project midway, which activities should the project manager execute first? | Perform contract, financial, and administrative tasks. | Execute financial and administrative tasks. | Finalize the in-progress administrative tasks. | Evaluate contract and administrative tasks. |  | D | The correct answer is D. Evaluate contract and administrative tasks. Regulatory compliance is non-negotiable and must be addressed proactively. The PM should evaluate impacts, engage appropriate experts, and follow change management processes to ensure compliance. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Integration & General PM | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 관리자가 국립 은행의 지점 사무실 건물 건설을 이끌고 있다. 규제 당국이 은행을 폐쇄했다는 통보를 받는다. 프로젝트를 중간에 종료할 때, 프로젝트 관리자가 먼저 수행해야 할 활동은 무엇인가? | 계약, 재무 및 행정 업무를 수행한다. | 재무 및 행정 업무를 실행한다. | 진행 중인 행정 업무를 완료한다. | 계약 및 행정 업무를 평가한다. |  | D | 정답은 D이다. 계약 및 행정 업무를 평가한다. 규제 준수는 협상 불가하며 사전 예방적으로 처리해야 한다. PM은 영향을 평가하고 적절한 전문가를 참여시키며 준수를 보장하기 위해 변경 관리 프로세스를 따라야 한다.
857 | A company's leadership team has decided to invest in a new product using an agile approach. The commercial and product teams have started the planning activity for this new venture. Which three key factors does the project manager need in order to deliver this product? (Choose 3) | Key performance indicators (KPls) | Schedule performance indexes (SPIs) | High-level product backlog | Product vision | Product roadmap | C, D, E | In agile delivery, the PM needs a clear understanding of the product vision, product roadmap, and product backlog. The product vision describes the desired outcome and value to be delivered. The roadmap provides a high-level overview of features with planned timelines. The backlog contains prioritized requirements and user stories for iterative execution. These three elements help align objectives with customer needs and deliver value incrementally. KPIs and SPI, while useful for tracking, focus on plan adherence rather than value delivery and are more suited to predictive approaches. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 회사의 리더십 팀이 애자일 접근 방식을 사용하여 새 제품에 투자하기로 결정했다. 상업 및 제품 팀이 이 새로운 사업을 위한 계획 활동을 시작했다. 이 제품을 전달하기 위해 프로젝트 관리자에게 필요한 세 가지 핵심 요소는 무엇인가? (3개 선택) | 핵심 성과 지표(KPI) | 일정 성과 지수(SPI) | 상위 수준 제품 백로그 | 제품 비전 | 제품 로드맵 | C, D, E | 애자일 전달에서 PM은 제품 비전, 제품 로드맵, 제품 백로그에 대한 명확한 이해가 필요하다. 제품 비전은 원하는 결과와 전달할 가치를 설명한다. 로드맵은 계획된 일정과 함께 기능의 상위 수준 개요를 제공한다. 백로그는 반복적 실행을 위한 우선순위화된 요구사항과 사용자 스토리를 포함한다. 이 세 가지 요소는 목표를 고객 요구와 정렬하고 점진적으로 가치를 전달하는 데 도움이 된다. KPI와 SPI는 추적에 유용하지만 가치 전달보다는 계획 준수에 초점을 맞추며 예측적 접근 방식에 더 적합하다.
858 | On a project with multiple international locations, a trend for delays has been flagged. When looking into the issue, the project manager realized that some of the key activities were scheduled over the holiday periods in the overseas offices. What should the project manager do next? | Hire additional personnel on a temporary basis to cover the extra workload during theholiday seasons. | Update the schedule to reflect the holidays and share the workload among offices tomitigate schedule slippage. | Update the schedule to reflect the holidays and notify the project sponsor of thedelayed completion. | Request that the offices in overseas locations work overtime to mitigate scheduleslippages. |  | B | When key activities were scheduled over holiday periods in overseas offices causing delays, the project manager should update the schedule to reflect the holidays and share the workload among offices to mitigate schedule slippage. This adjusts the schedule based on actual resource availability and balances allocation across locations. Hiring temporary personnel (A) incurs additional cost. Updating the schedule and merely notifying the sponsor of delays (C) accepts the delay without mitigating it. Requesting overtime for overseas offices (D) may create conflicts and does not address the root scheduling issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 여러 국제 지사가 있는 프로젝트에서 지연 추세가 플래그되었다. 문제를 조사하던 중 프로젝트 관리자는 일부 핵심 활동이 해외 사무소의 휴일 기간에 예정되어 있었음을 발견했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 휴일 시즌에 추가 업무량을 커버하기 위해 임시 인력을 추가로 고용한다. | 휴일을 반영하여 일정을 업데이트하고 일정 지연을 완화하기 위해 사무소 간 업무를 분담한다. | 휴일을 반영하여 일정을 업데이트하고 프로젝트 스폰서에게 완료 지연을 통보한다. | 일정 지연을 완화하기 위해 해외 사무소에 초과 근무를 요청한다. |  | B | 핵심 활동이 해외 사무소 휴일 기간에 예정되어 지연이 발생할 때, 프로젝트 관리자는 휴일을 반영하여 일정을 업데이트하고 사무소 간 업무를 분담하여 일정 지연을 완화해야 한다. 이는 실제 자원 가용성에 맞춰 일정을 조정하고 지역 간 배분을 균형 잡는다. 임시 인력 고용(A)은 추가 비용이 발생한다. 일정 업데이트 및 스폰서 지연 통보(C)는 완화 없이 지연을 수용한다. 해외 사무소 초과 근무 요청(D)은 갈등을 유발하며 근본적인 일정 뤨 문제를 해결하지 못한다.
859 | When a project is in its final stage, the project manager will request from the team to prepare a delivery acceptance document. What is the importance of this document to the project manager? | Needed to share it with the stakeholders. | Needed to close the work breakdown structure (WBS). | Needed to release the team at the end of the project. | Needed to close out the project or a phase. |  | D | The delivery acceptance document is essential for formally closing the project or a phase. It signifies official recognition of project completion by the sponsor or customer, confirming all deliverables are accepted and objectives met. This is a key component of the project closing process. Sharing with stakeholders (A) is a related activity but not the document's primary purpose. Closing the WBS (B) is a structural activity. Releasing the team (C) follows project closure but is not the document's primary function. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | WBS/Decomposition | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트가 최종 단계에 있을 때, 프로젝트 관리자는 팀에게 전달 수락 문서를 준비하도록 요청한다. 이 문서가 프로젝트 관리자에게 중요한 이유는 무엇인가? | 이해관계자와 공유하기 위해 필요하다. | 작업 분류 체계(WBS)를 종료하기 위해 필요하다. | 프로젝트 종료 시 팀을 해산하기 위해 필요하다. | 프로젝트 또는 단계를 종료하기 위해 필요하다. |  | D | 전달 수락 문서는 프로젝트 또는 단계를 공식적으로 종료하는 데 필수적이다. 이는 스폰서 또는 고객이 프로젝트 완료를 공식적으로 인정하며 모든 산출물이 수락되고 목표가 충족되었음을 확인한다. 이는 프로젝트 종료 프로세스의 핵심 구성 요소이다. 이해관계자와 공유(A)는 관련 활동이지만 문서의 주요 목적이 아니다. WBS 종료(B)는 구조적 활동이다. 팀 해산(C)은 프로젝트 종료 후에 따르지만 문서의 주요 기능이 아니다.
860 | During the execution of a hybrid project, one developer had to be replaced. The new resource is extremely competent in quality assurance tasks, but does not have much experience in development. What should the project manager do? | Allow the team to reevaluate the tasks and determine how they should be allocated. | Request that all quality assurance tasks be allocated to the new resource. | Move the developer to another team and look for a replacement developer. | Maintain the same task allocation structure to avoid any disruption in the project team. |  | A | When a replacement developer is highly competent in QA but lacks development experience on a hybrid project, the project manager should allow the team to reevaluate tasks and determine allocation. Collaborative task redistribution leverages the new resource's strengths. Requesting all QA tasks go to the new resource (B) is one-dimensional. Moving the developer to another team (C) loses the resource. Maintaining the same allocation (D) ignores the skill mismatch. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Help Ensure Knowledge Transfer | Governance | Executing | Embed Quality | Manage Project Knowledge | Hybrid/Tailoring | 하이브리드 프로젝트 실행 중에 개발자 한 명을 교체해야 했다. 새 자원은 품질 보증 업무에 매우 능숙하지만 개발 경험은 많지 않다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀이 작업을 재평가하고 어떻게 배분할지 결정하도록 허용한다. | 모든 품질 보증 작업을 새 자원에게 배정하도록 요청한다. | 개발자를 다른 팀으로 이동시키고 대체 개발자를 찾는다. | 프로젝트 팀의 혼란을 피하기 위해 동일한 작업 배분 구조를 유지한다. |  | A | 하이브리드 프로젝트에서 대체 개발자가 QA에는 능숙하지만 개발 경험이 부족할 때, 프로젝트 관리자는 팀이 작업을 재평가하고 배분을 결정하도록 허용해야 한다. 협업적 작업 재배분은 새 자원의 강점을 활용한다. 모든 QA 작업 배정 요청(B)은 일차원적이다. 다른 팀으로 이동(C)은 자원을 잃는다. 동일한 배분 유지(D)는 기술 불일치를 무시한다.
861 | During the execution of a maintenance project, the contractor submits an offer for additional work. The project manager realizes that the activities billed are included in the initial scope of work. What should the project manager do next in this situation? | Review the project costs and communicate this to the project sponsor | Submit a change request to approve the offer | Refuse the offer as it is included in the initial project scope | Review the project scope and negotiate with the contractor |  | C | When a contractor submits an offer for additional work that is already included in the initial scope, the project manager should refuse the offer as it is included in the initial project scope. Work already within the agreed scope does not constitute a valid change request. Reviewing project costs and communicating to the sponsor (A) is informative but does not resolve the issue. Submitting a change request (B) is inappropriate for in-scope work. Reviewing scope and negotiating (D) implies the scope is unclear. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 유지보수 프로젝트 실행 중에 계약자가 추가 작업에 대한 제안을 제출한다. 프로젝트 관리자는 청구된 활동이 초기 작업 범위에 포함되어 있음을 인식한다. 이 상황에서 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 비용을 검토하고 프로젝트 스폰서에게 전달한다. | 제안을 승인하기 위해 변경 요청을 제출한다. | 초기 프로젝트 범위에 포함되어 있으므로 제안을 거부한다. | 프로젝트 범위를 검토하고 계약자와 협상한다. |  | C | 계약자가 이미 초기 범위에 포함된 추가 작업에 대한 제안을 제출할 때, 프로젝트 관리자는 초기 프로젝트 범위에 포함되어 있으므로 제안을 거부해야 한다. 합의된 범위 내의 작업은 유효한 변경 요청이 되지 않는다. 프로젝트 비용 검토 및 스폰서 전달(A)은 정보 제공이지만 문제를 해결하지 않는다. 변경 요청 제출(B)은 범위 내 작업에 적절하지 않다. 범위 검토 및 협상(D)은 범위가 불명확함을 암시한다.
862 | A project manager is planning a project to build a research center with the installation of scientific equipment. Since the research topic is new and unfamiliar, the equipment required might change during project execution. How should the project manager plan this project? | Separate the tender into two parts, one for the building and one for the equipment, with careful selection of contractors. | Put a fixed price contract out to tender for the research building and issue a cost- reimbursable contract for installing the equipment. | Use a different project life cycle approach for the different parts of this project by adopting a hybrid approach. | Lock down the requirements for the equipment early and avoid any changes during further phases of the project. |  | C | A hybrid approach enables the PM to apply predictive methods for the building construction (well-defined, stable scope) and adaptive methods for the scientific equipment (uncertain, evolving requirements). This balances control with flexibility. Contracting approaches (B, D) address procurement but not the planning methodology needed for changing requirements. A fully defined scope (C) contradicts the evolving nature of equipment needs. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Scope | Planning | Adopt a Holistic View | Collect Requirements | Hybrid/Tailoring | 프로젝트 관리자가 과학 장비 설치를 포함한 연구 센터 건설 프로젝트를 계획하고 있다. 연구 주제가 새롭고 익숙하지 않아 프로젝트 실행 중 필요한 장비가 변경될 수 있다. 프로젝트 관리자는 이 프로젝트를 어떻게 계획해야 하는가? | 입찰을 건물과 장비 두 부분으로 분리하고 계약자를 신중하게 선정한다. | 연구 건물에 대해 고정 가격 계약을 입찰에 붙이고 장비 설치에 대해 비용 상환 계약을 발행한다. | 하이브리드 접근 방식을 채택하여 프로젝트의 다른 부분에 다른 프로젝트 생명주기 접근 방식을 사용한다. | 장비 요구사항을 조기에 확정하고 이후 단계에서 변경을 피한다. |  | C | 하이브리드 접근 방식은 PM이 건물 건설(잘 정의된 안정적 범위)에는 예측적 방법을, 과학 장비(불확실하고 진화하는 요구사항)에는 적응적 방법을 적용할 수 있게 한다. 이는 통제와 유연성의 균형을 맞춘다. 계약 접근 방식(B, D)은 조달을 다루지만 변화하는 요구사항에 필요한 계획 방법론을 다루지 않는다. 완전히 정의된 범위(C)는 장비 요구의 진화하는 특성과 모순된다.
863 | A project to add metro stations is being executed, with seven out of eight stations currently in place. Suddenly, a notification from the local community is received demanding the project be stopped. What should the project manager do first? | Meet with project stakeholders to define a mitigation plan | Register the issue and escalate it to the project sponsor | Estimate the cost of changing the project location | Execute the contingency plan defined in the risk management plan |  | B | When the local community demands a near-complete metro project be stopped, the project manager should first register the issue and escalate it to the project sponsor. This high-impact issue with potential legal, political, and reputational implications exceeds the PM's authority and requires executive response. Meeting stakeholders for a mitigation plan (A) may follow but escalation should come first. Estimating relocation costs (C) is premature. Executing a contingency plan (D) assumes a pre-approved plan exists for this scenario. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 지하철역 추가 프로젝트가 실행 중이며, 8개 역 중 7개가 현재 설치되었다. 갑자기 지역 사회로부터 프로젝트 중단을 요구하는 통보가 접수되었다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트 이해관계자와 만나 완화 계획을 수립한다. | 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션한다. | 프로젝트 위치 변경 비용을 추정한다. | 리스크 관리 계획에 정의된 비상 대응 계획을 실행한다. |  | B | 지역 사회가 거의 완료된 지하철 프로젝트의 중단을 요구할 때, 프로젝트 관리자는 먼저 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션해야 한다. 법적, 정치적, 평판 영향이 있는 이 고영향 이슈는 PM의 권한을 초과하며 경영진 대응이 필요하다. 이해관계자와 완화 계획 회의(A)는 후속 조치일 수 있지만 에스컬레이션이 먼저다. 이전 비용 추정(C)은 시기상조다. 비상 대응 계획 실행(D)은 이 시나리오에 대한 사전 승인된 계획이 있다고 가정한다.
864 | During an iteration of a project, a planned activity becomes more complex. The work should be delivered in the shortest time possible. What approach should be used in this situation? | The team members bring in a specialist to help them | The product owner moves it to the product backlog. | The cross-functional team member work together to complete the activity | The team facilitator gets support from external team members. |  | C | When a planned activity becomes more complex and must be delivered quickly, the cross-functional team members should work together to complete the activity. This leverages the team's diverse skills and expertise, enabling collaborative problem-solving and faster delivery. Bringing in a specialist (A) creates dependency. Moving the activity to the product backlog (B) delays delivery. Getting external team support (D) introduces coordination overhead and unfamiliarity with the project context. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트의 반복 중에 계획된 활동이 더 복잡해졌다. 작업은 가능한 한 최단 시간 내에 전달되어야 한다. 이 상황에서 어떤 접근 방식을 사용해야 하는가? | 팀원들이 전문가를 데려와 도움을 받는다. | 제품 책임자가 제품 백로그로 이동시킨다. | 교차 기능 팀원들이 함께 작업하여 활동을 완료한다. | 팀 퍼실리테이터가 외부 팀원의 지원을 받는다. |  | C | 계획된 활동이 더 복잡해지고 빠르게 전달해야 할 때, 교차 기능 팀원들이 함께 작업하여 활동을 완료해야 한다. 이는 팀의 다양한 기술과 전문성을 활용하여 협력적 문제 해결과 더 빠른 전달을 가능하게 한다. 전문가 투입(A)은 의존성을 만든다. 제품 백로그로 이동(B)은 전달을 지연시킨다. 외부 팀 지원(D)은 조율 부담과 프로젝트 맥락에 대한 생소함을 야기한다.
865 | The team's velocity is inconsistent, leading the product owner to believe the team is creating too many points in their user stories. What should the scrum master do first? | Invite the product owner to planning poker meetings and get their approval after each story is sized. | Meet with the product owner for planning and to resize the stories in the backlog. | Raise this concern with the team and review the performance of the past three sprints. | Remind the product owner that their role is to determine what the team should work on during the iteration. |  | C | When the team's velocity is inconsistent and the product owner suspects over-estimation, the scrum master should first raise this concern with the team and review the past three sprints' performance. Team-led reflection identifies patterns and root causes for velocity fluctuation. Inviting the product owner to planning poker (A) inserts them into team-owned estimation. Meeting with the product owner to resize stories (B) bypasses team ownership. Reminding the product owner of their role (D) deflects the concern. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 팀의 속도(velocity)가 일관되지 않아 제품 책임자가 팀이 사용자 스토리에 너무 많은 포인트를 부여하고 있다고 생각한다. 스크럼 마스터는 먼저 무엇을 해야 하는가? | 제품 책임자를 플래닝 포커 회의에 초대하고 각 스토리 크기 결정 후 승인을 받는다. | 제품 책임자와 만나 백로그의 스토리를 계획하고 크기를 재조정한다. | 팀에게 이 우려를 제기하고 지난 3개 스프린트의 성과를 검토한다. | 제품 책임자에게 반복 중 팀이 작업해야 할 것을 결정하는 것이 그들의 역할임을 상기시킨다. |  | C | 팀의 속도가 일관되지 않고 제품 책임자가 과대 추정을 의심할 때, 스크럼 마스터는 먼저 팀에게 이 우려를 제기하고 지난 3개 스프린트의 성과를 검토해야 한다. 팀 주도의 회고는 속도 변동의 패턴과 근본 원인을 식별한다. 제품 책임자를 플래닝 포커에 초대(A)는 팀 소유의 추정에 개입시킨다. 제품 책임자와 스토리 재조정(B)은 팀 주인의식을 우회한다. 역할 상기(D)는 우려를 회피한다.
866 | A project sponsor indicates that the time frame for a project needs to be shortened. The project network diagram cannot be modified, but there are extra resources available in the company. What action should the project manager take? | Conduct earned value management (EVM) analysis. | Perform Monte Carlo analysis. | Crash the project schedule. | Fast track the project. |  | C | When the project timeline must be shortened and extra resources are available, the PM should crash the project schedule by adding resources to critical-path activities. This approach reduces duration without changing the project scope, leveraging available organizational capacity to meet the compressed timeline. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Cost & Resource Management | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 스폰서가 프로젝트의 기간을 단축해야 한다고 말한다. 프로젝트 네트워크 다이어그램은 수정할 수 없지만 회사에 추가 자원이 있다. 프로젝트 관리자는 어떤 조치를 취해야 하는가? | 획득 가치 관리(EVM) 분석을 수행한다. | 몬테카를로 분석을 수행한다. | 프로젝트 일정을 크래싱한다. | 프로젝트를 빨리 진행(Fast tracking)한다. |  | C | 프로젝트 기간을 단축해야 하고 추가 자원이 가용할 때, PM은 주공정(Critical Path) 활동에 자원을 추가하여 프로젝트 일정을 크래싱해야 한다. 이 접근법은 프로젝트 범위를 변경하지 않으면서 기간을 줄이고, 가용한 조직 역량을 활용하여 압축된 일정을 충족한다.
867 | During the early phases of a project, mitigation actions were not executed in a timely manner; therefore, the project schedule was impacted. Several project stakeholders are now frustrated with the delays. What should the project manager have done to manage the issue? | Monitored and controlled the issue | Communicated any identified action to impacted stakeholders | Identified the appropriate response and had it implemented | Identified and reported the issue |  | C | When mitigation actions were not executed in a timely manner causing schedule impacts and stakeholder frustration, the project manager should have identified the appropriate response and had it implemented. Proactive response execution prevents issues from escalating. Monitoring and controlling alone (A) tracks without resolving. Communicating actions to stakeholders (B) informs but does not ensure implementation. Identifying and reporting the issue (D) documents without acting. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 초기 단계에서 완화 조치가 적시에 실행되지 않아 프로젝트 일정에 영향을 미쳤다. 여러 프로젝트 이해관계자가 지연에 불만을 느끼고 있다. 프로젝트 관리자는 이 이슈를 관리하기 위해 무엇을 했어야 하는가? | 이슈를 모니터링하고 통제했어야 한다. | 식별된 조치를 영향받는 이해관계자에게 전달했어야 한다. | 적절한 대응을 식별하고 이를 실행했어야 한다. | 이슈를 식별하고 보고했어야 한다. |  | C | 완화 조치가 적시에 실행되지 않아 일정 영향과 이해관계자 불만이 발생했을 때, 프로젝트 관리자는 적절한 대응을 식별하고 이를 실행했어야 한다. 사전 예방적 대응 실행이 이슈 확대를 방지한다. 모니터링 및 통제만(A)으로는 해결 없이 추적만 한다. 이해관계자에게 조치 전달(B)은 알리지만 실행을 보장하지 않는다. 이슈 식별 및 보고(D)는 조치 없이 문서화만 한다.
868 | An agile project is starting its seventh out of eight iterations. In a planning meeting, the team realizes that an unidentified risk became an issue and the contingency reserve has to be used. What should the project manager do? | Ask the sponsor for money to implement the contingency plan. | Ask the sponsor to approve inclusion of an additional iteration to the project | Ask the team to include the contingency plan in the iteration backlog | Help the team review the project approach to initiate the corrective actions |  | D | In agile projects, when an unidentified risk becomes an issue, the PM should help the team review the project approach and initiate corrective actions to address the issue and prevent recurrence. Requesting additional iterations or budget contradicts agile principles of flexibility and adaptation within fixed time-boxes. The contingency plan should have been developed proactively and executed immediately upon risk occurrence, not added to the iteration backlog after the fact. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 애자일 프로젝트가 8개 반복 중 7번째를 시작하고 있다. 계획 회의에서 팀이 미식별 리스크가 이슈가 되었으며 비상 예비비를 사용해야 한다고 인식한다. 프로젝트 관리자는 무엇을 해야 하는가? | 비상 대응 계획을 실행하기 위해 스폰서에게 자금을 요청한다. | 프로젝트에 추가 반복을 포함하도록 스폰서의 승인을 요청한다. | 팀에게 비상 대응 계획을 반복 백로그에 포함하도록 요청한다. | 팀이 프로젝트 접근 방식을 검토하여 시정 조치를 개시하도록 지원한다. |  | D | 애자일 프로젝트에서 미식별 리스크가 이슈가 될 때, PM은 팀이 프로젝트 접근 방식을 검토하고 시정 조치를 개시하여 이슈를 해결하고 재발을 방지하도록 지원해야 한다. 추가 반복이나 예산을 요청하는 것은 고정된 타임박스 내 유연성과 적응의 애자일 원칙에 반한다. 비상 대응 계획은 사전 예방적으로 개발되어 리스크 발생 시 즉시 실행되어야 하며, 사후에 반복 백로그에 추가되어서는 안 된다.
869 | A new major project is starting that consists of two interconnected subprojects. One of the subprojects was assigned to a contractor who commits to submitting biweekly status reports and attending weekly integration meetings. Halfway through the project, the contractor stops participating in the meetings and does not submit the reports. Their excuse is that these activities are consuming too much time. How should the project manager handle this situation? | File a claim for not fulfilling the contract terms in accordance with alternative dispute resolution. | Assess the situation as a risk and reach out to the contractor to check the origin of this resistance. | Remind the contractor to join the meetings and submit their report as this is their commitment. | Compromise with the contractor to only attend the weekly meetings without submitting the reports. |  | B | When a contractor stops attending meetings and submitting reports mid-project citing time consumption, the project manager should assess the situation as a risk and reach out to understand the resistance. Diagnosis before action is prudent. Filing a claim (A) is adversarial without first engaging. Reminding them of commitments (C) may not address underlying issues. Compromising to drop reports (D) weakens project controls. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 새로운 대규모 프로젝트가 시작되며 상호 연결된 두 개의 하위 프로젝트로 구성된다. 하위 프로젝트 중 하나가 격주 상태 보고서 제출과 주간 통합 회의 참석을 약속한 계약업체에 배정되었다. 프로젝트 중반에 계약업체가 회의 참여를 중단하고 보고서를 제출하지 않는다. 변명은 이러한 활동이 너무 많은 시간을 소모한다는 것이다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 대안적 분쟁 해결(ADR)에 따라 계약 조건 불이행에 대한 클레임을 제기한다. | 상황을 리스크로 평가하고 계약업체에게 연락하여 이 저항의 원인을 확인한다. | 계약업체에게 회의 참여와 보고서 제출이 그들의 약속임을 상기시킨다. | 계약업체와 타협하여 보고서 제출 없이 주간 회의만 참석하도록 한다. |  | B | 계약업체가 시간 소모를 이유로 회의 참여와 보고서 제출을 중단할 때, 프로젝트 관리자는 상황을 리스크로 평가하고 연락하여 저항의 원인을 이해해야 한다. 조치 전 진단이 신중하다. 클레임 제기(A)는 먼저 대화 없이 적대적이다. 약속 상기(C)는 근본적 문제를 해결하지 못할 수 있다. 보고서 없이 타협(D)은 프로젝트 통제를 약화시킨다.
870 | A technology project is delivering new functionality on a new platform. Several team resources are starting to train their teams, but they are asking questions about the training that the project will provide. What should the project manager's first action be? | Review the project charter to determine if the training is in scope and, if not, put in a change request. | Indicate that on the new technology is the functional manager ' s responsibility. | Consult with the organizational change management specialist as to what the training plan includes. | Document the skill requirements for the product to determine what training is needed. |  | A | When team resources ask questions about training for new technology, the project manager should first review the project charter to determine if training is in scope and, if not, submit a change request. The charter defines scope boundaries and guides governance. Indicating training is the functional manager's responsibility (B) deflects accountability. Consulting the change management specialist (C) is helpful but secondary. Documenting skill requirements (D) is useful but not the first action. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Finance | Scope | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 기술 프로젝트가 새로운 플랫폼에서 새로운 기능을 전달하고 있다. 여러 팀 자원들이 팀 교육을 시작하고 있지만, 프로젝트가 제공할 교육에 대해 질문하고 있다. 프로젝트 관리자의 첫 번째 조치는 무엇인가? | 프로젝트 헌장을 검토하여 교육이 범위에 포함되는지 확인하고, 그렇지 않으면 변경 요청을 제출한다. | 새로운 기술은 기능 관리자의 책임이라고 알린다. | 조직 변경 관리 전문가와 상담하여 교육 계획에 포함된 내용을 확인한다. | 제품에 필요한 기술 요구사항을 문서화하여 필요한 교육을 결정한다. |  | A | 팀 자원들이 새로운 기술에 대한 교육에 대해 질문할 때, 프로젝트 관리자는 먼저 프로젝트 헌장을 검토하여 교육이 범위에 포함되는지 확인하고, 그렇지 않으면 변경 요청을 제출해야 한다. 헌장은 범위 경계를 정의하고 거버넌스를 안내한다. 기능 관리자 책임 통보(B)는 책임을 전가한다. 변경 관리 전문가 상담(C)은 도움이 되지만 부차적이다. 기술 요구사항 문서화(D)는 유용하지만 첫 번째 조치는 아니다.
871 | A project manager is working on a major construction project. Part of the agreed-upon plan was to use a cloud-based system with a server that runs on high-speed internet service since most of the team members work virtually. The company needs to reduce operating costs as much as possible and management insists that the project will now use a system running on a conventional dial-up service. What should the project manager do next? | Replace some of the team members that work virtually to help the company save money. | Meet with management about their decision and ask them to get another project manager. | Agree with management and continue working the project management plan. | Evaluate the impact of this decision and communicate with management. |  | D | When management insists on switching from a cloud-based high-speed system to conventional dial-up service to reduce costs, the project manager should evaluate the impact of this decision and communicate with management. Impact analysis ensures informed decision-making about the trade-offs. Replacing virtual team members (A) addresses the wrong problem. Asking management to reassign the PM (B) is unprofessional. Agreeing without analysis (C) risks project performance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 관리자가 대규모 건설 프로젝트에서 작업 중이다. 합의된 계획의 일부로 대부분의 팀원이 가상으로 작업하기 때문에 고속 인터넷 서비스가 작동하는 서버를 가진 클라우드 기반 시스템을 사용하기로 했다. 회사는 운영 비용을 최대한 줄여야 하며, 경영진이 프로젝트가 이제 기존 다이얼업 서비스로 작동하는 시스템을 사용하도록 요구한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 비용 절감을 위해 가상으로 작업하는 일부 팀원을 교체한다. | 경영진에게 그들의 결정에 대해 만나고 다른 프로젝트 관리자를 배정하도록 요청한다. | 경영진에 동의하고 프로젝트 관리 계획을 계속 작업한다. | 이 결정의 영향을 평가하고 경영진과 소통한다. |  | D | 경영진이 클라우드 기반 고속 시스템에서 기존 다이얼업 서비스로 전환하여 비용을 줄이도록 요구할 때, 프로젝트 관리자는 이 결정의 영향을 평가하고 경영진과 소통해야 한다. 영향 분석이 절충안에 대한 정보에 입각한 의사결정을 보장한다. 가상 팀원 교체(A)는 잘못된 문제를 해결한다. PM 재배정 요청(B)은 비전문적이다. 분석 없이 동의(C)는 프로젝트 성과를 위험에 빠트린다.
872 | A project manager has been assigned to an education project with the objective of training a workforce in application development. One of the deliverables is to provide internships to the best students in the customer's active projects. However, the customer does not have enough projects in progress right now. The project manager decides to create several internal projects in order to ensure the internships. Which three actions should the project manager take to fulfill this scenario without adding costs for the customer? (Choose three) | Influence the client to initiate a new project. | Use the project ' s contingency budget | Create a change request with the scope of the new internal projects. | Create a work breakdown structure (WBS) of the new scope with the internal projects | Manage the quality of the delivery | C, D, E | To provide internships through internal projects without adding customer costs, the project manager should take three actions: create a change request with the scope of the new internal projects, create a WBS of the new scope with the internal projects, and manage the quality of the delivery. Formal change management, structured planning, and quality control ensure successful execution. Influencing the client to initiate a new project (A) adds external cost. Using the contingency budget (B) misuses reserves. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 관리자가 애플리케이션 개발 인력 교육을 목표로 하는 교육 프로젝트에 배정되었다. 산출물 중 하나는 우수 학생에게 고객의 활성 프로젝트에서 인턴십을 제공하는 것이다. 그러나 고객이 현재 진행 중인 프로젝트가 충분하지 않다. 프로젝트 관리자는 인턴십을 보장하기 위해 여러 내부 프로젝트를 만들기로 결정했다. 프로젝트 관리자가 고객에게 비용을 추가하지 않고 이 시나리오를 달성하기 위해 취해야 할 세 가지 조치는? (3개 선택) | 고객에게 새로운 프로젝트를 시작하도록 영향력을 행사한다. | 프로젝트의 예비비 예산을 사용한다. | 새로운 내부 프로젝트의 범위를 포함한 변경 요청을 작성한다. | 내부 프로젝트를 포함한 새로운 범위의 작업분류체계(WBS)를 작성한다. | 전달의 품질을 관리한다. | C, D, E | 고객 비용 추가 없이 내부 프로젝트를 통해 인턴십을 제공하려면, 프로젝트 관리자는 세 가지 조치를 취해야 한다: 새로운 내부 프로젝트 범위를 포함한 변경 요청 작성, 내부 프로젝트를 포함한 새로운 범위의 WBS 작성, 전달 품질 관리. 공식적인 변경 관리, 구조화된 계획, 품질 통제가 성공적 실행을 보장한다. 고객에게 새 프로젝트 시작 영향력 행사(A)는 외부 비용을 추가한다. 예비비 예산 사용(B)은 예비비를 오용한다.
873 | A project manager is leading a hybrid project in which one technical team executes tasks using an agile approach, while a second team executes other tasks using a predictive framework. These teams are struggling to cooperate effectively, and several delays have occurred in transmitting information and coordinating activities. What should the project manager do? | Meet with senior team members of both project teams to establish the working rules for the project. | Ask the agile team to establish the working rules for both project teams. | Meet with the project sponsor to establish the working rules for the project and inform both project teams. | Ask the predictive team to establish the working rules for both project teams. |  | A | When agile and predictive teams in a hybrid project struggle to cooperate, the project manager should meet with senior team members of both project teams to establish joint working rules. This collaborative approach creates shared understanding of communication channels, handoff expectations, and coordination mechanisms. Asking the agile team to establish rules for both (B) is unbalanced. Asking the predictive team to set rules (D) has the same problem. Having the sponsor establish rules (C) is top-down and reduces team buy-in. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Hybrid/Tailoring | 프로젝트 관리자가 한 기술 팀은 애자일 접근 방식으로, 다른 팀은 예측형 프레임워크로 작업을 수행하는 하이브리드 프로젝트를 이끌고 있다. 이 팀들이 효과적으로 협력하지 못하고, 정보 전달 및 활동 조율에 여러 지연이 발생했다. 프로젝트 관리자는 무엇을 해야 하는가? | 양 프로젝트 팀의 시니어 팀원과 만나 프로젝트의 작업 규칙을 수립한다. | 애자일 팀에게 양 프로젝트 팀의 작업 규칙을 수립하도록 요청한다. | 프로젝트 스폰서와 만나 프로젝트의 작업 규칙을 수립하고 양 프로젝트 팀에 알린다. | 예측형 팀에게 양 프로젝트 팀의 작업 규칙을 수립하도록 요청한다. |  | A | 하이브리드 프로젝트에서 애자일 팀과 예측형 팀이 협력에 어려움을 겪을 때, 프로젝트 관리자는 양 팀의 시니어 팀원과 만나 공동 작업 규칙을 수립해야 한다. 이 협력적 접근은 커뮤니케이션 채널, 인수인계 기대치, 조율 메커니즘에 대한 공유된 이해를 만든다. 애자일 팀에게 양 팀의 규칙 수립 요청(B)은 불균형적이다. 예측형 팀에게 규칙 설정 요청(D)도 같은 문제가 있다. 스폰서가 규칙을 수립하는 것(C)은 하향식이며 팀 동의를 감소시킨다.
874 | A company has rolled out the latest retail management system, and the project has been handed over to operations. The operations team finds that many of the day-to-day requirements are not covered in the system, and support for the project has limited hours. The project team has dissolved and the contract resources are no longer working on the project. As a result, the operations team has been facing numerous customer issues. What should the project lead have done initially to avoid this situation? | Increased support hours for the hours of operation | Reviewed the project management plan | Created a detailed operations manual | Involved operations stakeholders during planning |  | D | When a retail management system is handed to operations but day-to-day requirements are missing and support is limited, the project lead should have involved operations stakeholders during planning. Early operations engagement ensures requirements completeness. Increasing support hours (A) addresses post-handover symptoms. Reviewing the project management plan (B) is general. Creating a detailed operations manual (C) helps but does not prevent missing requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Scope | Planning | Adopt a Holistic View | Collect Requirements | Traditional PM | 회사가 최신 소매 관리 시스템을 출시했고 프로젝트가 운영팀에 인계되었다. 운영팀은 시스템에 일상적인 요구사항이 많이 포함되지 않았으며 프로젝트 지원 시간이 제한적임을 발견했다. 프로젝트 팀은 해산되었고 계약 자원은 더 이상 프로젝트에 참여하지 않는다. 결과적으로 운영팀은 수많은 고객 이슈에 직면하고 있다. 프로젝트 리더는 이 상황을 방지하기 위해 초기에 무엇을 했어야 하는가? | 운영 시간에 대한 지원 시간을 늘린다. | 프로젝트 관리 계획을 검토한다. | 상세한 운영 매뉴얼을 작성한다. | 계획 단계에서 운영 이해관계자를 참여시킨다. |  | D | 소매 관리 시스템이 운영팀에 인계되었지만 일상 요구사항이 누락되고 지원이 제한적일 때, 프로젝트 리더는 계획 단계에서 운영 이해관계자를 참여시켰어야 한다. 조기 운영 참여가 요구사항 완전성을 보장한다. 지원 시간 증가(A)는 인계 후 증상을 다룬다. 프로젝트 관리 계획 검토(B)는 일반적이다. 상세 운영 매뉴얼 작성(C)은 도움이 되지만 누락된 요구사항을 방지하지 못한다.
875 | A project manager had to schedule additional planning sessions to add requirements from an international stakeholder. The stakeholder expressed concern about the product not meeting the client's needs. Which factor should the project manager have considered when developing the product? | Stakeholder ' s needs | Responsibility matrix | Stakeholder ' s location | Availability of resources |  | A | When an international stakeholder raises concern about the product not meeting client needs, the factor the project manager should have considered during development is the stakeholder's needs. Understanding and integrating stakeholder requirements prevents misalignment. A responsibility matrix (B) defines roles, not product requirements. Stakeholder location (C) is logistical. Resource availability (D) affects execution, not product design. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자는 국제 이해관계자의 요구사항을 추가하기 위해 추가 계획 세션을 일정에 넣어야 했다. 이해관계자는 제품이 고객의 요구를 충족하지 못할 것에 대한 우려를 표명했다. 프로젝트 관리자가 제품 개발 시 고려했어야 할 요소는? | 이해관계자의 요구 | 책임 매트릭스 | 이해관계자의 위치 | 자원의 가용성 |  | A | 국제 이해관계자가 제품이 고객 요구를 충족하지 못할 것에 대한 우려를 제기할 때, 프로젝트 관리자가 개발 시 고려했어야 할 요소는 이해관계자의 요구이다. 이해관계자 요구사항을 이해하고 통합하면 불일치를 방지한다. 책임 매트릭스(B)는 역할을 정의하지 제품 요구사항은 아니다. 이해관계자 위치(C)는 물류적이다. 자원 가용성(D)은 실행에 영향을 미치지 제품 설계에는 아니다.
876 | A project manager and project team are developing a strategic approach to engage the internal and external stakeholders. Which approach should be followed? | Involve only the internal stakeholders, as the external stakeholders should not have access to confidential information. | Schedule status meetings with all stakeholders to allow their participation in all project discussions and reports. | Analyze both internal and external stakeholders and develop a customized engagement strategy for each stakeholder. | Classify all high-risk stakeholders and request that the project sponsor communicate directly with them. |  | C | When developing a strategic approach to engage internal and external stakeholders, the project manager should analyze both internal and external stakeholders and develop a customized engagement strategy for each. Stakeholders have varying levels of interest, influence, and impact, requiring tailored approaches. Involving only internal stakeholders (A) excludes important external perspectives. Scheduling status meetings with all stakeholders (B) applies a one-size-fits-all approach. Classifying high-risk stakeholders for sponsor communication (D) delegates engagement rather than managing it strategically. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Hybrid/Tailoring | 프로젝트 관리자와 프로젝트 팀이 내부 및 외부 이해관계자를 참여시키기 위한 전략적 접근 방식을 개발하고 있다. 어떤 접근 방식을 따라야 하는가? | 외부 이해관계자는 기밀 정보에 접근해서는 안 되므로 내부 이해관계자만 참여시킨다. | 모든 이해관계자와 상태 회의를 예약하여 모든 프로젝트 토론 및 보고서에 참여할 수 있도록 한다. | 내부 및 외부 이해관계자를 모두 분석하고 각 이해관계자에 대한 맞춤형 참여 전략을 개발한다. | 모든 고위험 이해관계자를 분류하고 프로젝트 스폰서가 직접 그들과 소통하도록 요청한다. |  | C | 내부 및 외부 이해관계자를 참여시키기 위한 전략적 접근 방식을 개발할 때, 프로젝트 관리자는 양쪽 이해관계자를 모두 분석하고 각각에 대한 맞춤형 참여 전략을 개발해야 한다. 이해관계자는 관심, 영향력, 영향의 수준이 다양하여 맞춤형 접근이 필요하다. 내부 이해관계자만 참여(A)는 중요한 외부 관점을 배제한다. 모든 이해관계자와 상태 회의 예약(B)은 획일적 접근이다. 고위험 이해관계자를 스폰서 소통으로 분류(D)는 전략적 관리가 아닌 참여를 위임한다.
877 | A project manager is in the process of authoring the communications management plan for a new project. One of the project's stakeholders has a habit of posting work updates on social media, which may include confidential project status updates. What should the project manager do? | Ensure that social media posts related to the project are removed. | Review the protocols and security measures to ensure confidentiality. | Ensure that sensitive information is not included in stakeholder updates. | Review social media access and restrict it to ensure confidentiality. |  | C | The correct answer is C. Ensure that sensitive information is not included in stakeholder updates. Effective stakeholder management requires proactive engagement, transparent communication, and alignment with project objectives. Understanding stakeholder needs and addressing their concerns is essential for project success. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 새 프로젝트를 위한 커뮤니케이션 관리 계획을 작성하는 과정에 있다. 프로젝트의 이해관계자 중 한 명이 소셜 미디어에 업무 업데이트를 게시하는 습관이 있으며, 여기에 기밀 프로젝트 상태 업데이트가 포함될 수 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트와 관련된 소셜 미디어 게시물이 삭제되도록 한다. | 기밀성을 보장하기 위해 프로토콜과 보안 조치를 검토한다. | 이해관계자 업데이트에 민감한 정보가 포함되지 않도록 한다. | 기밀성을 보장하기 위해 소셜 미디어 접근을 검토하고 제한한다. |  | C | 정답은 C이다. 이해관계자 업데이트에 민감한 정보가 포함되지 않도록 한다. 효과적인 이해관계자 관리는 사전 예방적 참여, 투명한 커뮤니케이션, 프로젝트 목표와의 정렬을 요구한다. 이해관계자의 요구를 이해하고 우려를 해결하는 것이 프로젝트 성공에 필수적이다.
878 | A project is being planned with two hardware deliverables and one software deliverable that will be used to monitor the operation of the two hardware deliverables. When preparing the consolidated project schedule, what should be the top priority for the project manager? | The user stories and story points | The stakeholder engagement plan | The interdependencies between the deliverables | The business continuity plan of the deliverables |  | C | When preparing a consolidated schedule with two hardware and one software deliverable, the project manager's top priority should be managing interdependencies between deliverables. Dependencies drive sequencing, integration testing, and critical path. User stories and story points (A) are agile artifacts, not the primary scheduling concern. The stakeholder engagement plan (B) supports communication, not sequencing. The business continuity plan (D) is operational, not scheduling. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트가 두 개의 하드웨어 산출물과 두 하드웨어 산출물의 운영을 모니터링하는 데 사용될 하나의 소프트웨어 산출물로 계획되고 있다. 통합 프로젝트 일정을 준비할 때 프로젝트 관리자의 최우선 순위는 무엇이어야 하는가? | 사용자 스토리와 스토리 포인트 | 이해관계자 참여 계획 | 산출물 간 상호의존성 | 산출물의 비즈니스 연속성 계획 |  | C | 두 개의 하드웨어와 하나의 소프트웨어 산출물로 통합 일정을 준비할 때, 프로젝트 관리자의 최우선 순위는 산출물 간 상호의존성을 관리하는 것이어야 한다. 의존성이 순서, 통합 테스트, 크리티컬 패스를 결정한다. 사용자 스토리와 스토리 포인트(A)는 애자일 아티팩트로 주요 일정 관심사가 아니다. 이해관계자 참여 계획(B)은 커뮤니케이션을 지원하지 순서를 정하지 않는다. 비즈니스 연속성 계획(D)은 운영적이지 일정 관련이 아니다.
879 | A project manager is leading a project to modernize the information technology of a bank. The project manager needs to determine how the project stakeholders should communicate, and has discussed the various options with the project team. What should the project manager do to communicate with the stakeholders? | Use a variety of communication methods that respect cultural, practical, and personal preferences. | Send frequent updates via email to each stakeholder because this is an information technology project. | Use a single communication medium such as video teleconferencing to limit confusion. 1219 | Provide updates to the project sponsor to review and distribute to each stakeholder. |  | A | When determining how stakeholders should communicate on a bank IT modernization project, the project manager should use a variety of communication methods that respect cultural, practical, and personal preferences. Diverse methods ensure effective reach. Frequent emails only (B) ignores preferences. A single medium like video (C) limits accessibility. Providing updates via the sponsor (D) adds a bottleneck. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 은행의 정보 기술 현대화 프로젝트를 이끌고 있다. 프로젝트 관리자는 프로젝트 이해관계자들이 어떻게 커뮤니케이션해야 하는지 결정해야 하며, 프로젝트 팀과 다양한 옵션을 논의했다. 프로젝트 관리자는 이해관계자와 커뮤니케이션하기 위해 무엇을 해야 하는가? | 문화적, 실용적, 개인적 선호를 존중하는 다양한 커뮤니케이션 방법을 사용한다. | 이것은 정보 기술 프로젝트이므로 각 이해관계자에게 이메일로 빈번한 업데이트를 보낸다. | 혼란을 줄이기 위해 화상 회의와 같은 단일 커뮤니케이션 매체를 사용한다. | 프로젝트 스폰서에게 업데이트를 제공하여 검토하고 각 이해관계자에게 배포하도록 한다. |  | A | 은행 IT 현대화 프로젝트에서 이해관계자 커뮤니케이션 방법을 결정할 때, 프로젝트 관리자는 문화적, 실용적, 개인적 선호를 존중하는 다양한 커뮤니케이션 방법을 사용해야 한다. 다양한 방법이 효과적인 도달을 보장한다. 이메일만 빈번히 보내기(B)는 선호를 무시한다. 화상과 같은 단일 매체(C)는 접근성을 제한한다. 스폰서를 통한 업데이트 제공(D)은 병목현상을 추가한다.
880 | A team member shares with their functional manager some negative details about the performance of another team member that was discussed during the retrospective. The project manager finds out about this discussion. What two actions should the project manager take? (Choose two) | Meet with the entire team to review the ground rules about safe environments | Meet with the product owner to talk about the situation. | Contact the team member to explain what information can be shared outside the team | Contact the team member ' s functional manager and invite them to the next retrospective | Meet with the sponsor to review the situation. | A, D | The PM should take two actions: meet with the entire team to review the ground rules about safe environments and confidentiality (A), and contact the team member's functional manager and invite them to the next retrospective (D). Reviewing ground rules reinforces the importance of psychological safety and confidentiality expectations. Involving the functional manager creates visibility and accountability, and their participation in the retrospective helps bridge communication between the team and functional management. Meeting with the product owner (B) is not relevant to this interpersonal issue. Contacting the team member individually (C) addresses one person but does not reinforce team-wide norms. Meeting with the sponsor (E) is unnecessary at this stage. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scaled Agile | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀원이 회고에서 논의된 다른 팀원의 성과에 대한 부정적인 세부 사항을 기능 관리자와 공유한다. 프로젝트 관리자가 이 논의에 대해 알게 된다. 프로젝트 관리자는 어떤 두 가지 조치를 취해야 하는가? (2개 선택) | 안전한 환경에 대한 기본 규칙을 검토하기 위해 전체 팀과 회의한다. | 상황에 대해 제품 책임자와 만난다. | 팀원에게 연락하여 팀 외부에 공유할 수 있는 정보를 설명한다. | 팀원의 기능 관리자에게 연락하여 다음 회고에 초대한다. | 스폰서와 만나 상황을 검토한다. | A, D | PM은 두 가지 조치를 취해야 한다: 안전한 환경과 기밀성에 대한 기본 규칙을 검토하기 위해 전체 팀과 회의하고(A), 해당 팀원의 기능 관리자에게 연락하여 다음 회고에 초대한다(D). 기본 규칙 검토는 심리적 안전과 기밀성 기대의 중요성을 강화한다. 기능 관리자를 참여시키면 가시성과 책임감이 생기고, 회고 참여는 팀과 기능 관리 간의 소통을 연결하는 데 도움이 된다. 제품 책임자와 회의(B)는 이 대인관계 이슈와 관련이 없다. 해당 팀원에게만 개별 연락(C)은 한 사람만 다루고 팀 전체 규범을 강화하지 않는다. 스폰서와 회의(E)는 이 단계에서 불필요하다.
881 | A labor union contract negotiation is delaying the completion of a project to build a new manufacturing plant. Because the labor contract was due for renewal this year, the project manager documented the negotiation process as a risk to the project. The project was about to start the first phase of equipment installation at the plant when the negotiation began. How should the project manager address the situation? | Meet with the project team to determine options for risk mitigation. | Log the issue and follow the planned actions in the risk response plan. | Escalate the issue to the steering committee to ask for mitigation support. | Acquire contract resources and submit a change request for the cost impact. |  | B | When a documented risk — labor union contract negotiation — materializes and delays equipment installation, the project manager should log the issue and follow the planned actions in the risk response plan. Executing pre-planned responses is proper risk management. Meeting the team for new options (A) bypasses the existing plan. Escalating to the steering committee (C) is premature. Acquiring contract resources (D) introduces scope and cost changes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 노동조합 계약 협상이 새로운 제조 공장 건설 프로젝트의 완료를 지연시키고 있다. 올해 노동 계약이 갱신 예정이었기 때문에 프로젝트 관리자는 협상 과정을 프로젝트의 리스크로 문서화했다. 프로젝트는 협상이 시작되었을 때 공장의 첫 번째 장비 설치 단계를 시작하려던 참이었다. 프로젝트 관리자는 이 상황을 어떻게 해결해야 하는가? | 리스크 완화 옵션을 결정하기 위해 프로젝트 팀과 만난다. | 이슈를 기록하고 리스크 대응 계획의 계획된 조치를 따른다. | 완화 지원을 요청하기 위해 운영위원회에 이슈를 에스컬레이션한다. | 계약 자원을 확보하고 비용 영향에 대한 변경 요청을 제출한다. |  | B | 문서화된 리스크인 노동조합 계약 협상이 실현되어 장비 설치를 지연시킬 때, 프로젝트 관리자는 이슈를 기록하고 리스크 대응 계획의 계획된 조치를 따라야 한다. 사전 계획된 대응을 실행하는 것이 적절한 리스크 관리이다. 새로운 옵션을 위해 팀과 만나기(A)는 기존 계획을 우회한다. 운영위원회에 에스컬레이션(C)은 시기상조이다. 계약 자원 확보(D)는 범위와 비용 변경을 도입한다.
882 | A team is preparing the closing phase and building a plan for the next phase. One of the project sponsors is complaining that the last phase had some quality deliverable issues. However, the quality acceptance document was signed. What should the project manager do? | Review best practices and lessons learned and apply them to the project plan. 1052 | Postpone the next project phase until the impact of the quality issues is assessed. | Reopen the quality acceptance documentation to add the sponsor ' s complaints. | Schedule a quality review meeting and include the sponsor ' s complaints. |  | D | When a project sponsor complains about quality issues from the last phase despite having signed the quality acceptance document, the project manager should schedule a quality review meeting and include the sponsor's complaints. Addressing concerns constructively improves future phases. Reviewing best practices and lessons learned (A) is general. Postponing the next phase (B) delays without assessing. Reopening quality acceptance documentation (C) undermines the signed agreement. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 팀이 종료 단계를 준비하고 다음 단계 계획을 수립 중이다. 프로젝트 스폰서 중 한 명이 지난 단계에 일부 품질 산출물 이슈가 있었다고 불만을 제기하고 있다. 그러나 품질 수락 문서는 서명되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 모범 사례와 교훈을 검토하고 프로젝트 계획에 적용한다. | 품질 이슈의 영향이 평가될 때까지 다음 프로젝트 단계를 연기한다. | 스폰서의 불만을 추가하기 위해 품질 수락 문서를 다시 연다. | 품질 검토 회의를 예약하고 스폰서의 불만을 포함한다. |  | D | 프로젝트 스폰서가 품질 수락 문서에 서명했음에도 지난 단계의 품질 이슈에 대해 불만을 제기할 때, 프로젝트 관리자는 품질 검토 회의를 예약하고 스폰서의 불만을 포함해야 한다. 우려 사항을 건설적으로 다루면 향후 단계가 개선된다. 모범 사례 및 교훈 검토(A)는 일반적이다. 다음 단계 연기(B)는 평가 없이 지연시킨다. 품질 수락 문서 재개(C)는 서명된 합의를 훼손한다.
883 | The project manager of a globally dispersed team evaluates the organization's current virtual engagement tools and strategies. A couple of the remote team members are not participating effectively in virtual meetings. Which action should the project manager take to improve remote engagement? | Implement a new suite of collaboration tools to provide various communication options for the team. | Schedule one-on-one meetings with the team members to understand their specific needs and challenges. | Survey all team members to identify common issues with virtual engagement and address them systematically. | Organize an in-person, team-building event to improve team engagement and communication. |  | B | When specific remote team members are not participating effectively in virtual meetings, the project manager should schedule one-on-one meetings to understand their specific needs and challenges. Personalized engagement identifies root causes and builds trust. Implementing new collaboration tools (A) adds complexity without addressing individual issues. Surveying all team members (C) is broad when specific members are affected. Organizing an in-person event (D) may not be feasible for global teams. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 글로벌 분산 팀의 프로젝트 관리자가 조직의 현재 가상 참여 도구와 전략을 평가하고 있다. 원격 팀원 몇 명이 가상 회의에 효과적으로 참여하지 않고 있다. 프로젝트 관리자는 원격 참여를 개선하기 위해 어떤 조치를 취해야 하는가? | 팀에 다양한 커뮤니케이션 옵션을 제공하기 위해 새로운 협업 도구 세트를 도입한다. | 해당 팀원들과 1:1 미팅을 예약하여 그들의 구체적인 요구와 과제를 이해한다. | 모든 팀원을 대상으로 설문조사를 실시하여 가상 참여의 공통 이슈를 파악하고 체계적으로 해결한다. | 팀 참여와 소통을 개선하기 위해 대면 팀빌딩 이벤트를 조직한다. |  | B | 특정 원격 팀원이 가상 회의에 효과적으로 참여하지 않을 때, 프로젝트 관리자는 1:1 미팅을 예약하여 그들의 구체적인 요구와 과제를 이해해야 한다. 개인화된 참여가 근본 원인을 파악하고 신뢰를 구축한다. 새 협업 도구 도입(A)은 개인적 이슈를 해결하지 않고 복잡성을 추가한다. 전체 팀원 설문조사(C)는 특정 팀원이 영향받을 때 너무 광범위하다. 대면 이벤트 조직(D)은 글로벌 팀에서 실현 불가능할 수 있다.
884 | In a project, one team member has been asking for directions and what actions to take on many tasks. As a result, the team member has performed slowly in project delivery. What should the project manager do to help this team member? | Address the team member ' s performance accordingly. | Mentor the team member on a regular basis. | Assign another senior team member to coach the team member. | Empower the team member to make decisions. |  | B | The project manager should mentor the team member on a regular basis. When a team member frequently asks for direction and guidance on tasks, it typically indicates a lack of confidence, competence, or clarity in their role. Mentoring provides personalized support—helping the team member develop skills, understand project objectives and processes, and build the confidence needed to work more independently. Addressing performance (A) is evaluative rather than developmental and does not address the root cause. Assigning another senior team member to coach (C) may help but shifts the responsibility away from the PM's leadership role. Empowering the team member to make decisions (D) is premature when the individual lacks the foundational understanding to do so effectively. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트에서 한 팀원이 많은 작업에 대해 지시와 취해야 할 조치를 계속 물어보고 있다. 그 결과, 이 팀원은 프로젝트 전달에서 느린 성과를 보이고 있다. 프로젝트 관리자는 이 팀원을 돕기 위해 무엇을 해야 하는가? | 팀원의 성과를 적절히 다룬다. | 정기적으로 팀원을 멘토링한다. | 팀원을 코칭하기 위해 다른 시니어 팀원을 배정한다. | 팀원이 스스로 결정을 내릴 수 있도록 권한을 부여한다. |  | B | 프로젝트 관리자는 정기적으로 팀원을 멘토링해야 한다. 팀원이 작업에 대해 자주 지시와 안내를 구할 때, 이는 일반적으로 자신감, 역량 또는 역할에 대한 명확성이 부족함을 나타낸다. 멘토링은 개인화된 지원을 제공하여 팀원이 기술을 개발하고, 프로젝트 목표와 프로세스를 이해하며, 더 독립적으로 작업하는 데 필요한 자신감을 구축하도록 돕는다. 성과 다루기(A)는 개발적이 아닌 평가적이며 근본 원인을 해결하지 않는다. 시니어 팀원 코칭 배정(C)은 도움이 되지만 PM의 리더십 역할에서 책임을 전가한다. 의사결정 권한 부여(D)는 개인이 효과적으로 수행할 기초적 이해가 부족할 때 시기상조이다.
885 | A large construction project is progressing well as per the project objectives. The project manager would like to report the project's value to the project sponsor and seek the next phase of funding closure. What should the project manager do? | Ensure a measurement system is in place like earned value analysis (EVA) to track project value for the project sponsor. | Submit a detailed report on the cost budget vs. the cost actuals as the project sponsor will want to know more about finances. | Create a detailed project report on successes and challenges for the project sponsor. | Arrange a site visit to show the project sponsor the construction progress in person. |  | A | When reporting project value to the sponsor for next-phase funding, the project manager should ensure a measurement system like earned value analysis is in place to track project value. EVA integrates scope, schedule, and cost performance. Submitting cost budget vs. actuals (B) is partial. Creating a successes/challenges report (C) is narrative, not quantitative. Arranging a site visit (D) is subjective. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Earned Value Management | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 대규모 건설 프로젝트가 프로젝트 목표에 따라 잘 진행되고 있다. 프로젝트 관리자는 프로젝트 스폰서에게 프로젝트의 가치를 보고하고 다음 단계 자금 종결을 추진하고자 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서를 위해 프로젝트 가치를 추적하기 위한 획득가치 분석(EVA)과 같은 측정 시스템이 마련되어 있는지 확인한다. | 프로젝트 스폰서가 재무에 대해 더 알고 싶어할 것이므로 비용 예산 대 실제 비용에 대한 상세 보고서를 제출한다. | 프로젝트 스폰서를 위해 성공과 과제에 대한 상세 프로젝트 보고서를 작성한다. | 프로젝트 스폰서에게 건설 진행 상황을 직접 보여주기 위해 현장 방문을 준비한다. |  | A | 스폰서에게 다음 단계 자금을 위해 프로젝트 가치를 보고할 때, 프로젝트 관리자는 획득가치 분석과 같은 측정 시스템이 마련되어 있는지 확인해야 한다. EVA는 범위, 일정, 비용 성과를 통합한다. 비용 예산 대 실제 비용 제출(B)은 부분적이다. 성공/과제 보고서 작성(C)은 서술적이지 정량적이지 않다. 현장 방문 준비(D)는 주관적이다.
886 | A project manager is about to start a large-scale project with unclear requirements, a fixed deadline, and a fixed budget. The client is unable to provide a product owner, as they do not have enough capacity and they want to be involved only a few times during the project. How should the project manager plan and manage the project? | Convince the client that a product owner is needed, as the project manager is not able to run an agile project without all the relevant roles in place, | Refuse to manage the project as there is too much risk in developing this kind of project without a product owner. | Agree up front on a minimum viable product (MVP), establish deadlines for review, and run the project with a backlog and weekly sprints. | Define the project ' s requirements, prepare a long-term detailed plan, and manage the project according to it. |  | C | When facing unclear requirements, fixed deadline and budget, and limited client availability as product owner, the project manager should agree up front on a minimum viable product (MVP), establish review deadlines, and run the project with a backlog and weekly sprints. This approach provides structure, incremental delivery, and scheduled client checkpoints. Convincing the client a product owner is needed (A) may not be feasible. Refusing to manage the project (B) is unprofessional. Creating a detailed long-term plan (D) does not accommodate unclear requirements. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 관리자가 불명확한 요구사항, 고정된 마감일, 고정된 예산으로 대규모 프로젝트를 시작하려 한다. 고객은 역량이 부족하여 제품 책임자를 제공할 수 없으며, 프로젝트 중 몇 번만 참여하고 싶어한다. 프로젝트 관리자는 프로젝트를 어떻게 계획하고 관리해야 하는가? | 고객에게 제품 책임자가 필요하다고 설득한다. 프로젝트 관리자는 모든 관련 역할이 갖추어지지 않으면 애자일 프로젝트를 수행할 수 없다. | 제품 책임자 없이 이러한 종류의 프로젝트를 개발하는 데 리스크가 너무 크므로 프로젝트 관리를 거부한다. | 최소 기능 제품(MVP)에 사전 합의하고, 검토 마감일을 설정하며, 백로그와 주간 스프린트로 프로젝트를 운영한다. | 프로젝트의 요구사항을 정의하고, 장기 상세 계획을 준비하며, 그에 따라 프로젝트를 관리한다. |  | C | 불명확한 요구사항, 고정된 마감일과 예산, 제품 책임자로서의 제한적인 고객 가용성에 직면할 때, 프로젝트 관리자는 MVP에 사전 합의하고, 검토 마감일을 설정하며, 백로그와 주간 스프린트로 프로젝트를 운영해야 한다. 이 접근 방식은 구조, 점진적 전달, 예약된 고객 체크포인트를 제공한다. 제품 책임자 필요성 설득(A)은 실현 불가능할 수 있다. 프로젝트 관리 거부(B)는 비전문적이다. 상세 장기 계획 수립(D)은 불명확한 요구사항에 적합하지 않다.
887 | A project manager is leading a technically complex project. The project is part of a strategic program of work and the first to use an agile approach. One of the board members is interested in attending a meeting to see how the delivery of the project scope is progressing. What should the project lead do? | Invite the board member to the next daily standup. | Invite the board member to a separate demo. | Invite the board member to the next sprint review. | Invite the board member to the next sprint retrospective. |  | C | When a board member wants to see how project scope delivery is progressing in an agile project, the project lead should invite the board member to the next sprint review. Sprint reviews are the appropriate forum for stakeholders to inspect the increment and provide feedback. Inviting to the daily standup (A) is inappropriate for stakeholders. A separate demo (B) creates extra work outside the standard process. The sprint retrospective (D) is an internal team meeting. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 기술적으로 복잡한 프로젝트를 이끄고 있다. 이 프로젝트는 전략 프로그램의 일부이며 애자일 접근 방식을 처음 사용하는 프로젝트이다. 이사회 멤버 중 한 명이 프로젝트 범위 전달의 진행 상황을 보기 위해 회의에 참석하고자 한다. 프로젝트 리더는 무엇을 해야 하는가? | 이사회 멤버를 다음 일일 스탠드업에 초대한다. | 이사회 멤버를 별도 데모에 초대한다. | 이사회 멤버를 다음 스프린트 리뷰에 초대한다. | 이사회 멤버를 다음 스프린트 회고에 초대한다. |  | C | 이사회 멤버가 애자일 프로젝트에서 범위 전달 진행 상황을 보고 싶을 때, 프로젝트 리더는 이사회 멤버를 다음 스프린트 리뷰에 초대해야 한다. 스프린트 리뷰는 이해관계자가 증분을 검사하고 피드백을 제공하는 적절한 포럼이다. 일일 스탠드업 초대(A)는 이해관계자에게 부적절하다. 별도 데모(B)는 표준 프로세스 외에 추가 작업을 만든다. 스프린트 회고(D)는 내부 팀 회의이다.
888 | A project manager and a stakeholder have different opinions on the budget estimates for a project that is being initiated based on a new consumer privacy law. What would be a reason for this difference in opinion? | The use of the Monte Carlo method can result in different estimations. | Relative estimation by the team resulted in two estimates. | Organizational assets were not available to back the rationale. | The communications management plan was not used by all stakeholders. |  | A | When the project manager and a stakeholder disagree on budget estimates for a project based on a new privacy law, the reason may be that the Monte Carlo method can result in different estimations. Different inputs, assumptions, or scenarios produce varying results. Relative estimation producing two estimates (B) is team-level, not PM-vs-stakeholder. Unavailable organizational assets (C) is a process gap, not an estimation method. The communications plan not being used (D) relates to information sharing, not budget methodology. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 프로젝트 관리자와 이해관계자가 새로운 소비자 개인정보보호법에 기반하여 시작되는 프로젝트의 예산 추정치에 대해 의견이 다르다. 이러한 의견 차이의 이유는 무엇인가? | 몸테카를로 방법의 사용으로 다른 추정치가 나올 수 있다. | 팀의 상대적 추정이 두 가지 추정치를 만들었다. | 근거를 뒷받침할 조직 자산이 사용 불가능했다. | 커뮤니케이션 관리 계획이 모든 이해관계자에 의해 사용되지 않았다. |  | A | 프로젝트 관리자와 이해관계자가 새로운 개인정보보호법 기반 프로젝트의 예산 추정치에 대해 의견이 다를 때, 몸테카를로 방법이 다른 추정치를 만들 수 있기 때문이다. 다른 입력, 가정 또는 시나리오는 다양한 결과를 생성한다. 팀의 상대적 추정이 두 가지 추정치를 만듬(B)은 팀 수준이지 PM 대 이해관계자가 아니다. 조직 자산 사용 불가(C)는 프로세스 격차이지 추정 방법이 아니다. 커뮤니케이션 계획 미사용(D)은 정보 공유와 관련되지 예산 방법론과는 관련없다.
889 | Throughout the project, the project manager consistently checks the work performance data and finds that two stakeholders are not engaged in the project as expected. In addition, another stakeholder always complains that they are often involved in irrelevant meetings. What should the project manager do first? | Perform a root cause analysis using the Ishikawa method. | Communicate regularly with stakeholders and address issues. | Remove those stakeholders from unwanted meetings. | Review and update the stakeholder engagement plan. |  | D | When two stakeholders are underengaged and another is over-involved in irrelevant meetings, the project manager should first review and update the stakeholder engagement plan. Recalibrating engagement levels—defining communication frequency, meeting invitations, and decision roles based on stakeholder influence and interest—addresses all three issues systematically. Performing root cause analysis with Ishikawa (A) is suited for technical issues, not engagement misfit. Communicating regularly (B) does not fix the strategic alignment. Removing stakeholders from meetings (C) may create governance gaps without a plan update. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 프로젝트 전반에 걸쳐 프로젝트 관리자가 작업 성과 데이터를 지속적으로 확인한 결과, 두 이해관계자가 예상대로 프로젝트에 참여하지 않고 있음을 발견했다. 또한 다른 이해관계자는 관련 없는 회의에 자주 참여한다고 항상 불만을 제기한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 이시카와 방법을 사용하여 근본 원인 분석을 수행한다. | 이해관계자와 정기적으로 소통하고 이슈를 해결한다. | 해당 이해관계자를 불필요한 회의에서 제외한다. | 이해관계자 참여 계획을 검토하고 업데이트한다. |  | D | 두 이해관계자가 참여 부족하고 다른 이해관계자가 불필요한 회의에 과다하게 참여할 때, 프로젝트 관리자는 먼저 이해관계자 참여 계획을 검토하고 업데이트해야 한다. 참여 수준을 재조정하면 세 가지 이슈를 체계적으로 해결한다. 이시카와로 근본 원인 분석(A)은 기술적 이슈에 적합하지 참여 부조화에는 적합하지 않다. 정기적 소통(B)은 전략적 정렬을 해결하지 않는다. 회의에서 이해관계자 제외(C)는 계획 업데이트 없이 거버넌스 격차를 만들 수 있다.
890 | A large company is transitioning its projects to an agile approach. After the transition, executive management requests the information that was previously available in old reports and dashboards. Many of the old reports and dashboards are no longer relevant after the shift to agile practices. What should the project manager do in this situation? | Remind the management team that an agile approach empowers teams to be self-directed and therefore there is no need for reporting | Explain to the management team that reporting and management dashboards are not effective agile practices | Help the management team understand how the change to an agile approach impacts the relevance of certain reports and key performance indicators (KPls) | Ask the management team to review the endorsed agile concepts to prove that the old information s not relevant |  | C | When executive management requests previously available reports after transitioning to agile but many old reports are no longer relevant, the project manager should help management understand how the agile approach impacts report relevance and KPIs. Collaborative education aligns expectations. Stating no need for reporting (A) is dismissive. Explaining reports are not effective in agile (B) is inaccurate. Asking management to review agile concepts (D) is confrontational. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 대기업이 프로젝트를 애자일 접근 방식으로 전환하고 있다. 전환 후 임원진이 이전 보고서와 대시보드에서 사용 가능했던 정보를 요청한다. 많은 이전 보고서와 대시보드는 애자일 실천으로 전환한 후 더 이상 관련이 없다. 이 상황에서 프로젝트 관리자는 무엇을 해야 하는가? | 경영진에게 애자일 접근 방식은 팀이 자기 주도적이도록 권한을 부여하므로 보고가 필요 없다고 상기시킨다. | 경영진에게 보고와 경영 대시보드는 효과적인 애자일 실천이 아니라고 설명한다. | 경영진이 애자일 접근 방식으로의 변화가 특정 보고서의 관련성과 핵심 성과 지표(KPI)에 어떻게 영향을 미치는지 이해하도록 돕는다. | 경영진에게 이전 정보가 관련 없음을 증명하기 위해 승인된 애자일 개념을 검토하도록 요청한다. |  | C | 애자일로 전환 후 임원진이 이전에 사용 가능했던 보고서를 요청하지만 많은 이전 보고서가 더 이상 관련이 없을 때, 프로젝트 관리자는 경영진이 애자일 접근 방식이 보고서 관련성과 KPI에 어떻게 영향을 미치는지 이해하도록 도와야 한다. 협력적 교육이 기대치를 정렬한다. 보고가 필요 없다고 상기(A)는 무시적이다. 보고서가 효과적이지 않다고 설명(B)은 부정확하다. 경영진에게 애자일 개념 검토 요청(D)은 대립적이다.
891 | A company is going through a large cost-cutting initiative. Senior management requests a report on the work remaining for outstanding projects. Which tool should the project manager use for this purpose? | Forecast estimation | Burndown chart | Cumulative flow diagram | Earned value (EV) |  | B | The correct answer is B. Burndown chart. Cost management requires careful budgeting, monitoring, and control throughout the project lifecycle. The PM should track variances and work with stakeholders to address financial issues proactively. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 회사가 대규모 비용 절감 이니셔티브를 진행 중이다. 상급 경영진이 미결 프로젝트의 잔여 작업에 대한 보고서를 요청한다. 프로젝트 관리자는 이 목적으로 어떤 도구를 사용해야 하는가? | 예측 추정 | 번다운 차트 | 누적 흐름 다이어그램 | 획득가치(EV) |  | B | 정답은 B이다. 번다운 차트. 비용 관리는 프로젝트 생애주기 전반에 걸쳐 신중한 예산 수립, 모니터링, 통제를 요구한다. PM은 차이를 추적하고 이해관계자와 협력하여 재무적 이슈를 사전 예방적으로 해결해야 한다.
892 | A project leader is preparing to facilitate a sprint retrospective. The sales manager sends the project leader an email asking how a feature planned for the next shipment is being implemented. What should the project leader do next? | Invite the sales manager to the sprint retrospective. | Organize a demo for the sales manager with the development team. | Organize a meeting between the product owner and the sales manager. | Invite the sales manager to the next sprint review. |  | D | The correct answer is D. Invite the sales manager to the next sprint review. Retrospectives are essential for continuous improvement in agile. They provide a structured way for the team to reflect on their process and identify actionable improvements. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 리더가 스프린트 회고를 촉진할 준비를 하고 있다. 영업 관리자가 다음 출하에 계획된 기능이 어떻게 구현되고 있는지 묻는 이메일을 프로젝트 리더에게 보낸다. 프로젝트 리더는 다음에 무엇을 해야 하는가? | 영업 관리자를 스프린트 회고에 초대한다. | 개발 팀과 함께 영업 관리자를 위한 데모를 조직한다. | 제품 책임자와 영업 관리자 간의 회의를 조직한다. | 영업 관리자를 다음 스프린트 리뷰에 초대한다. |  | D | 정답은 D이다. 영업 관리자를 다음 스프린트 리뷰에 초대한다. 회고는 애자일에서 지속적 개선에 필수적이다. 팀이 프로세스를 되돌아보고 실행 가능한 개선 사항을 식별하는 구조화된 방법을 제공한다.
893 | A key customer stakeholder asks the project team to include new tasks in the backlog and begin analyzing new requests. The customer expects results as soon as possible and pressures the team to attend noncritical meetings. The team is frustrated by this situation. How should the project manager approach this situation? | Ask the customer to work with the product owner to prioritize all requests. | Call for an internal team retrospective and create an improvement action plan. | Work with the team to receive customer directions and improve the process. | Understand the customer ' s perspective and provide mentoring on agile mindsets. |  | A | When a key customer stakeholder pressures for new tasks and quick results while the team is frustrated, the project manager should ask the customer to work with the product owner to prioritize all requests. Product owner-mediated prioritization channels demands through proper governance. Calling an internal retrospective (B) addresses team frustration but not the customer behavior. Working with the team to receive directions (C) does not manage expectations. Understanding the customer's perspective and mentoring (D) is helpful but secondary. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Traditional PM | 핵심 고객 이해관계자가 프로젝트 팀에게 백로그에 새 작업을 포함하고 새 요청 분석을 시작하도록 요청한다. 고객은 가능한 한 빨리 결과를 기대하며 팀에게 비핵심 회의에 참석하도록 압력을 가한다. 팀은 이 상황에 불만이다. 프로젝트 관리자는 이 상황에 어떻게 접근해야 하는가? | 고객에게 모든 요청의 우선순위를 정하기 위해 제품 책임자와 협력하도록 요청한다. | 내부 팀 회고를 소집하고 개선 실행 계획을 수립한다. | 팀과 협력하여 고객의 방향을 수용하고 프로세스를 개선한다. | 고객의 관점을 이해하고 애자일 마인드셋에 대한 멘토링을 제공한다. |  | A | 핵심 고객 이해관계자가 새 작업과 빠른 결과를 압박하고 팀이 불만일 때, 프로젝트 관리자는 고객에게 모든 요청의 우선순위를 정하기 위해 제품 책임자와 협력하도록 요청해야 한다. 제품 책임자를 통한 우선순위화는 적절한 거버넌스를 통해 요구를 채널링한다. 내부 회고 소집(B)은 팀 불만을 다루지만 고객 행동은 다루지 않는다. 팀과 협력하여 방향 수용(C)은 기대를 관리하지 않는다. 고객 관점 이해 및 멘토링(D)은 도움이 되지만 부차적이다.
894 | A project development team is located in different areas around the world. Last week, a very important release was delayed because one of the developers did not respond on time to an email that was sent to everyone. The developer seems to have missed reading the email. What should the project manager do to avoid these situations? | Review the stakeholder engagement plan. | Review the risk management plan. | Review the communications management plan. | Review the resource management plan. |  | C | When a developer in a globally distributed team missed a critical email causing a release delay, the project manager should review the communications management plan. Evaluating and updating communication processes ensures robust channels for distributed teams. Reviewing the stakeholder engagement plan (A) addresses engagement, not communication mechanics. Reviewing the risk management plan (B) is unrelated. Reviewing the resource management plan (D) addresses resources, not communication. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 개발 팀이 전 세계 여러 지역에 분산되어 있다. 지난주 모든 사람에게 보낸 이메일에 개발자 한 명이 제때 응답하지 않아 매우 중요한 릴리스가 지연되었다. 개발자가 이메일을 읽지 못한 것으로 보인다. 프로젝트 관리자는 이러한 상황을 방지하기 위해 무엇을 해야 하는가? | 이해관계자 참여 계획을 검토한다. | 리스크 관리 계획을 검토한다. | 커뮤니케이션 관리 계획을 검토한다. | 자원 관리 계획을 검토한다. |  | C | 전 세계에 분산된 팀에서 개발자가 중요한 이메일을 놓쳐 릴리스가 지연될 때, 프로젝트 관리자는 커뮤니케이션 관리 계획을 검토해야 한다. 커뮤니케이션 프로세스를 평가하고 업데이트하면 분산 팀을 위한 강력한 채널이 보장된다. 이해관계자 참여 계획 검토(A)는 참여를 다루지 커뮤니케이션 메커니즘은 다루지 않는다. 리스크 관리 계획 검토(B)는 관련이 없다. 자원 관리 계획 검토(D)는 자원을 다루지 커뮤니케이션은 다루지 않는다.
895 | A project manager is leading the first agile project for the organization. During the kick-off meeting, the project manager notices that the team does not have the same understanding about agile approaches. The project manager is concerned about the impact of that confusion. What should the project manager do to address this situation? | Mentor the team to explain agile principles and create a shared understanding. | Submit a change request for a new team that has agile experience. | Hire a functional manager who is familiar with agile methodologies. | Evaluate the possibility of managing this project using a predictive approach. |  | A | When the team lacks shared understanding of agile approaches on the organization's first agile project, the project manager should mentor the team to explain agile principles and create a shared understanding. This builds agile competencies through coaching and support, addressing the confusion at its root. Submitting a change request for a new agile-experienced team (B) is disruptive and unnecessary. Hiring an agile-experienced functional manager (C) does not develop the existing team. Evaluating a predictive approach (D) abandons the agile initiative without addressing the knowledge gap. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Align Stakeholder Expectations | Risk | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 관리자가 조직의 첫 번째 애자일 프로젝트를 이끌고 있다. 킥오프 회의에서 프로젝트 관리자는 팀이 애자일 접근 방식에 대해 동일한 이해를 가지고 있지 않음을 알아챈다. 프로젝트 관리자는 그 혼란의 영향에 대해 우려한다. 프로젝트 관리자는 이 상황을 해결하기 위해 무엇을 해야 하는가? | 팀에게 애자일 원칙을 설명하고 공유된 이해를 만들기 위해 멘토링한다. | 애자일 경험이 있는 새 팀으로의 변경 요청을 제출한다. | 애자일 방법론에 익숙한 기능 관리자를 고용한다. | 예측형 접근 방식으로 이 프로젝트를 관리할 가능성을 평가한다. |  | A | 조직의 첫 번째 애자일 프로젝트에서 팀이 애자일 접근 방식에 대한 공유된 이해가 부족할 때, 프로젝트 관리자는 팀에게 애자일 원칙을 설명하고 공유된 이해를 만들기 위해 멘토링해야 한다. 이는 코칭과 지원을 통해 애자일 역량을 구축하며 근본적인 혼란을 해결한다. 애자일 경험 팀으로 변경 요청 제출(B)은 파괴적이고 불필요하다. 애자일 경험 기능 관리자 고용(C)은 기존 팀을 발전시키지 않는다. 예측형 접근 방식 평가(D)는 지식 격차를 해결하지 않고 애자일 이니셔티브를 포기한다.
896 | A project manager is struggling to obtain participation from key stakeholders who do not usually attend project meetings. What should the project manager do? | Escalate the issue to senior management | Set clear meeting expectations by sharing agendas in advance | Distribute the communications management plan | Reschedule meetings lo align with the stakeholders ' availability |  | B | When key stakeholders do not attend project meetings, the project manager should set clear meeting expectations by sharing agendas in advance. Clear agendas communicate meeting value and set expectations. Escalating to senior management (A) is premature. Distributing the communications plan (C) is informational. Rescheduling meetings (D) accommodates availability but does not address engagement. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 프로젝트 회의에 보통 참석하지 않는 핵심 이해관계자의 참여를 확보하는 데 어려움을 겪고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 이슈를 상급 경영진에게 에스컬레이션한다. | 사전에 안건을 공유하여 명확한 회의 기대치를 설정한다. | 커뮤니케이션 관리 계획을 배포한다. | 이해관계자의 가용성에 맞게 회의를 재조정한다. |  | B | 핵심 이해관계자가 프로젝트 회의에 참석하지 않을 때, 프로젝트 관리자는 사전에 안건을 공유하여 명확한 회의 기대치를 설정해야 한다. 명확한 안건은 회의 가치를 전달하고 기대치를 설정한다. 상급 경영진에게 에스컬레이션(A)은 시기상조이다. 커뮤니케이션 계획 배포(C)는 정보 제공에 그친다. 회의 재조정(D)은 가용성은 수용하지만 참여는 해결하지 않는다.
897 | A project manager is leading a strategic and competitive advantage project for a healthcare organization that is in its testing phase. The team has been working on this project for 6 months, and the morale of the team is low due to the schedule. What can the project manager do to motivate the team? | Continue to perform the last phase of the project with the project team as this will benefit the organization and provide a competitive edge. | Talk to the business team about the project phase and the team ' s commitment, and request a monetary reward for the team. | Meet with the horizontal team managers to recognize the team members and give rewards and promotions upon completion of the project. | Speak with the project management office (PMO) and request a 2-week extension of the schedule so the team can have rotational time off. |  | D | When team morale is low due to a demanding 6-month schedule during the testing phase, the project manager should speak with the PMO and request a 2-week schedule extension so the team can have rotational time off. Addressing the team's immediate need for rest aligns with motivational theories—basic needs like rest and stress relief must be met before team members can be motivated by higher-level factors. Continuing without intervention (A) ignores the morale problem. Requesting monetary rewards from the business team (B) addresses extrinsic motivation but not the fundamental need for rest. Meeting with horizontal managers for rewards and promotions (C) is a longer-term recognition effort that does not address the immediate burnout risk. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 테스트 단계에 있는 의료 기관의 전략적이고 경쟁 우위 프로젝트를 이끌고 있다. 팀은 6개월 동안 이 프로젝트에 작업해 왔으며, 일정으로 인해 팀의 사기가 낮다. 프로젝트 관리자는 팀에 동기를 부여하기 위해 무엇을 할 수 있는가? | 프로젝트의 마지막 단계를 계속 수행한다. 이것은 조직에 이익이 되고 경쟁 우위를 제공할 것이다. | 비즈니스 팀에게 프로젝트 단계와 팀의 헌신에 대해 이야기하고 팀에 대한 금전적 보상을 요청한다. | 수평적 팀 관리자와 만나 팀원을 인정하고 프로젝트 완료 시 보상과 승진을 제공한다. | 프로젝트 관리 오피스(PMO)에 문의하여 팀이 교대로 휴가를 가질 수 있도록 2주 일정 연장을 요청한다. |  | D | 테스트 단계에서 6개월간의 힘든 일정으로 팀 사기가 낮을 때, 프로젝트 관리자는 PMO에 문의하여 팀이 교대로 휴가를 가질 수 있도록 2주 일정 연장을 요청해야 한다. 팀의 즉각적인 휴식 필요를 해결하는 것은 동기부여 이론에 부합한다—휴식과 스트레스 해소 같은 기본 욕구가 충족되어야 더 높은 수준의 요인으로 동기를 부여할 수 있다. 개입 없이 계속하기(A)는 사기 문제를 무시한다. 비즈니스 팀에 금전적 보상 요청(B)은 외적 동기를 다루지만 근본적인 휴식 필요는 다루지 않는다. 수평적 관리자와 만나 보상 및 승진(C)은 장기적 인정 노력이지만 즉각적인 번아웃 위험을 해결하지 않는다.
898 | A project manager has been assigned to manage multiple agile project teams. The project manager wants to empower the teams and encourage them to become self-organizing. What should the project manager do to foster a positive environment? | Establish the team ground rules and share them with the team for strict adherence. | Extract the organization ' s policies and processes, customize them, and give them to the teams to adhere to. | Copy the ground rules established by another project and provide them to the teams. | Help the teams in establishing and adhering to their ground rules and revisit after regular intervals. |  | D | Empowering agile teams to become self-organizing requires the PM to help them establish their own ground rules rather than imposing pre-defined ones. The PM should facilitate the creation of team agreements and revisit them at regular intervals to support continuous improvement. This approach builds collaboration, shared understanding, and strong internal leadership. Dictating ground rules (A), extracting and customizing organizational policies (B), or copying another project's rules (C) all undermine the team's autonomy and self-organizing capability. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 프로젝트 관리자가 여러 애자일 프로젝트 팀을 관리하도록 배정되었다. 프로젝트 관리자는 팀에 권한을 부여하고 자기 조직화를 장려하고자 한다. 프로젝트 관리자는 긍정적인 환경을 조성하기 위해 무엇을 해야 하는가? | 팀 기본 규칙을 수립하고 엄격한 준수를 위해 팀과 공유한다. | 조직의 정책과 프로세스를 추출하여 맞춤화하고 팀에게 준수하도록 제공한다. | 다른 프로젝트에서 수립한 기본 규칙을 복사하여 팀에 제공한다. | 팀이 자체 기본 규칙을 수립하고 준수하도록 돕고 정기적인 간격으로 재검토한다. |  | D | 애자일 팀의 자기 조직화를 위한 권한 부여는 PM이 사전 정의된 규칙을 강요하는 대신 팀이 자체 기본 규칙을 수립하도록 돕는 것을 요구한다. PM은 팀 합의 생성을 촉진하고 지속적 개선을 지원하기 위해 정기적 간격으로 재검토해야 한다. 이 접근 방식은 협력, 공유된 이해, 강력한 내부 리더십을 구축한다. 기본 규칙 지시(A), 조직 정책 추출 및 맞춤화(B), 다른 프로젝트 규칙 복사(C)는 모두 팀의 자율성과 자기 조직화 능력을 약화시킨다.
899 | A project to build a new energy plant was just completed. However, a few days before operation of the plant, the local community protested and closed access to the plant. They argue that an important natural reserve was impacted and prior consultation was not done by the project team. What should the project manager verify first? | Stakeholder engagement plan | Cost-benefit analysis | Business case | Risk management plan |  | A | When a completed energy plant faces community protests about impacted natural reserves and lack of prior consultation, the project manager should first verify the stakeholder engagement plan. This confirms whether all required consultations were planned and executed, identifying what went wrong. Checking the cost-benefit analysis (B) evaluates financial viability, not stakeholder engagement. Reviewing the business case (C) assesses justification. Reviewing the risk management plan (D) addresses risks but not the engagement oversight. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 새로운 에너지 발전소를 건설하는 프로젝트가 막 완료되었다. 그러나 발전소 가동 며칠 전에 지역 주민이 항의하고 발전소 접근을 차단했다. 그들은 중요한 자연 보호구역이 영향을 받았으며 프로젝트 팀이 사전 협의를 하지 않았다고 주장한다. 프로젝트 관리자는 먼저 무엇을 확인해야 하는가? | 이해관계자 참여 계획 | 비용-편익 분석 | 비즈니스 케이스 | 리스크 관리 계획 |  | A | 완료된 에너지 발전소가 영향받은 자연 보호구역과 사전 협의 부족에 대한 지역 주민 항의에 직면할 때, 프로젝트 관리자는 먼저 이해관계자 참여 계획을 확인해야 한다. 이는 모든 필수 협의가 계획되고 실행되었는지 확인하여 무엇이 잘못되었는지 식별한다. 비용-편익 분석 확인(B)은 재정적 타당성을 평가하지 이해관계자 참여는 아니다. 비즈니스 케이스 검토(C)는 정당성을 평가한다. 리스크 관리 계획 검토(D)는 리스크를 다루지만 참여 누락은 다루지 않는다.
900 | A project sponsor insists that the project scope for a new product launch should include two geographical locations. However, after the project scoping session was done, a project charter was completed and approved with one location only. What should the project manager do? | Discuss with the sponsor that the project scope is approved and it is not possible to include two locations as it will affect the budget. | Assess the impact to the scope and submit a change request for approval of the two locations before including them in the scope of the project. | Ask the sponsor to increase the budget and schedule of the project to accommodate the additional scope. | Encourage the sponsor to start another project for the additional location so that the current project is not impacted. |  | B | When the project sponsor insists on including two geographical locations but the approved charter covers only one, the project manager should assess the impact and submit a change request for approval. This follows the integrated change control process, ensuring scope changes are formally documented, evaluated, and approved before implementation. Discussing that changes are impossible (A) is not solution-oriented. Asking to increase budget and schedule (C) assumes approval before assessment. Encouraging a separate project (D) may not be practical or aligned with the sponsor's needs. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Finance | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 스폰서가 신제품 출시의 프로젝트 범위에 두 개의 지리적 위치를 포함해야 한다고 주장한다. 그러나 프로젝트 범위 설정 세션 후 프로젝트 헌장은 한 곳만으로 완성되어 승인되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 스폰서에게 프로젝트 범위가 승인되었으며 예산에 영향을 미치므로 두 곳을 포함하는 것이 불가능하다고 논의한다. | 범위에 대한 영향을 평가하고 두 곳을 프로젝트 범위에 포함하기 전에 승인을 위한 변경 요청을 제출한다. | 스폰서에게 추가 범위를 수용하기 위해 프로젝트 예산과 일정을 늘리도록 요청한다. | 현재 프로젝트가 영향을 받지 않도록 추가 위치를 위한 별도 프로젝트를 시작하도록 스폰서를 격려한다. |  | B | 프로젝트 스폰서가 두 개의 지리적 위치를 주장하지만 승인된 헌장이 한 곳만 포함할 때, 프로젝트 관리자는 영향을 평가하고 승인을 위한 변경 요청을 제출해야 한다. 이는 통합 변경 통제 프로세스를 따르며, 범위 변경이 구현 전에 공식적으로 문서화, 평가, 승인되도록 보장한다. 변경이 불가능하다고 논의(A)는 솔루션 지향적이지 않다. 예산과 일정 증가 요청(C)은 평가 전에 승인을 가정한다. 별도 프로젝트 격려(D)는 실용적이지 않거나 스폰서의 요구에 부합하지 않을 수 있다.
901 | A project team consists of several consultants from an external vendor. These consultants often change from month to month. What should the project manager do to communicate the organizational values? | Host a question and answer (Q & A) session with the new team members. | Distribute the team charter to new team members. | Review communications options with the vendor. | Schedule a collaborative team outing to strengthen team relationships. |  | B | The correct answer is B. Distribute the team charter to new team members. Effective communication considers cultural differences, stakeholder preferences, and the appropriate format for information exchange. The PM should tailor communication approaches to the audience. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 외부 벤더의 여러 컨설턴트로 구성되어 있다. 이 컨설턴트는 매달 자주 바뀐다. 프로젝트 관리자는 조직의 가치를 전달하기 위해 무엇을 해야 하는가? | 새 팀원과 질의응답(Q&A) 세션을 개최한다. | 새 팀원에게 팀 헌장을 배포한다. | 벤더와 커뮤니케이션 옵션을 검토한다. | 팀 관계를 강화하기 위해 협력적 팀 외출을 예약한다. |  | B | 정답은 B이다. 새 팀원에게 팀 헌장을 배포한다. 효과적인 커뮤니케이션은 문화적 차이, 이해관계자 선호도, 정보 교환에 적절한 형식을 고려한다. PM은 대상에 맞게 커뮤니케이션 접근 방식을 맞춤화해야 한다.
902 | When reviewing the project team's performance, the project manager realizes that the team velocity is not fast enough to meet the next review gate goal. What should the project manager do? | Increase the sprint duration to allow the team more time | Prioritize the contents of the backlog and remove some stories | Create a change request to modify the gate review goals | Use the standup meeting to assess impediments and problems |  | D | When team velocity is insufficient to meet the next review gate goal, the project manager should use the standup meeting to assess impediments and problems. Daily standups enable identification, tracking, and resolution of obstacles affecting velocity—including resource issues, unclear requirements, technical debt, and communication gaps. Increasing sprint duration (A) violates agile principles of frequent delivery. Removing backlog stories (B) reduces scope without addressing root causes. Creating a change request to modify gate goals (C) delays delivery and avoids solving the underlying performance issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 팀의 성과를 검토할 때, 프로젝트 관리자는 팀 속도가 다음 검토 게이트 목표를 충족하기에 충분히 빠르지 않다는 것을 인식한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에게 더 많은 시간을 허용하기 위해 스프린트 기간을 늘린다. | 백로그의 내용에 우선순위를 매기고 일부 스토리를 제거한다. | 게이트 검토 목표를 수정하기 위한 변경 요청을 생성한다. | 스탠드업 회의를 사용하여 장애물과 문제를 평가한다. |  | D | 팀 속도가 다음 검토 게이트 목표를 충족하기에 부족할 때, 프로젝트 관리자는 스탠드업 회의를 사용하여 장애물과 문제를 평가해야 한다. 일일 스탠드업은 자원 이슈, 불명확한 요구사항, 기술 부채, 커뮤니케이션 격차 등 속도에 영향을 미치는 장애물의 식별, 추적, 해결을 가능하게 한다. 스프린트 기간 증가(A)는 빈번한 전달의 애자일 원칙을 위반한다. 백로그 스토리 제거(B)는 근본 원인을 해결하지 않고 범위를 축소한다. 게이트 목표 수정 변경 요청(C)은 전달을 지연시키고 근본적인 성과 이슈 해결을 회피한다.
903 | A project manager is consolidating information for all the workstreams within a data center and IT service transition project. To ensure the project delivers value quickly, the project manager will assess a large number of consolidated project schedules. Which two actions should the project manager take with regard to schedule analysis? (Choose two) | Evaluate the master schedule and perform fast tracking and task crashing | Review the project schedules to ensure that all tasks end with milestones | Look (or gaps in the different schedules to determine which major risks might evolve over time | Review with subject matter experts (SMEs) to ensure they have contributed to the schedule development | Evaluate the schedules for interdependencies to establish the critical path | D, E | The PM should ensure all relevant stakeholders, including subject matter experts, contribute to schedule development. This produces a realistic schedule accounting for all necessary tasks and dependencies. Evaluating interdependencies to establish the critical path is equally crucial—the critical path method identifies the longest sequence of dependent activities, determining the minimum project duration and highlighting activities where delays directly impact the completion date. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 프로젝트 관리자가 데이터 센터 및 IT 서비스 전환 프로젝트 내 모든 워크스트림의 정보를 통합하고 있다. 프로젝트가 빠르게 가치를 전달하도록 보장하기 위해, 프로젝트 관리자는 많은 수의 통합된 프로젝트 일정을 평가할 것이다. 일정 분석과 관련하여 프로젝트 관리자가 취해야 할 두 가지 조치는? (2개 선택) | 마스터 일정을 평가하고 빠른 추적 및 작업 크래싱을 수행한다. | 모든 작업이 마일스톤으로 종료되도록 프로젝트 일정을 검토한다. | 시간이 지남에 따라 어떤 주요 리스크가 발생할 수 있는지 판단하기 위해 다양한 일정의 격차를 찾는다. | 주제 전문가(SME)가 일정 개발에 기여했는지 확인하기 위해 검토한다. | 상호 의존성을 평가하여 크리티컬 패스를 수립한다. | D, E | PM은 주제 전문가를 포함한 모든 관련 이해관계자가 일정 개발에 기여하도록 보장해야 한다. 이는 필요한 모든 작업과 의존성을 고려한 현실적인 일정을 산출한다. 상호 의존성을 평가하여 크리티컬 패스를 수립하는 것도 동일하게 중요하다—크리티컬 패스 방법은 의존 활동의 가장 긴 순서를 식별하여 최소 프로젝트 기간을 결정하고 지연이 완료일에 직접 영향을 미치는 활동을 강조한다.
904 | A project team has recently completed the initial sprint for developing an automated payroll system for a company. The project manager has scheduled a sprint planning meeting with the product owner and team members to discuss which features should be worked on next. Which two pieces of information does the project manager need in order to make this meeting productive and effective? (Choose two) | Product backlog | Company mission and vision | Burndown chart | Sprint charter | Sprint goal | A, B | For an effective sprint planning meeting, the project manager needs two key pieces of information: the product backlog (A)—the source of work items the team will select—and the company mission and vision (B)—the strategic context that ensures sprint work aligns with organizational goals. Together, these enable the team to select items that deliver both immediate sprint value and long-term strategic alignment. The burndown chart (C) tracks progress during a sprint but is not needed as input for planning. A sprint charter (D) is not a standard Scrum artifact. The sprint goal (E) is an output of sprint planning, not an input—it is defined during the meeting itself. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 회사의 자동화된 급여 시스템 개발을 위한 초기 스프린트를 최근 완료했다. 프로젝트 관리자는 제품 책임자 및 팀원들과 다음에 어떤 기능을 작업할지 논의하기 위한 스프린트 계획 회의를 예약했다. 이 회의를 생산적이고 효과적으로 만들기 위해 프로젝트 관리자에게 필요한 두 가지 정보는? (2개 선택) | 제품 백로그 | 회사 미션 및 비전 | 번다운 차트 | 스프린트 헌장 | 스프린트 목표 | A, B | 효과적인 스프린트 계획 회의를 위해 프로젝트 관리자는 두 가지 핵심 정보가 필요하다: 제품 백로그(A)—팀이 선택할 작업 항목의 출처—와 회사 미션과 비전(B)—스프린트 작업이 조직 목표와 일치하도록 하는 전략적 맥락. 이 둘이 함께 있어야 팀이 즉각적 스프린트 가치와 장기적 전략 정렬을 모두 제공하는 항목을 선택할 수 있다. 번다운 차트(C)는 스프린트 중 진행 상황을 추적하지만 계획 입력으로는 필요하지 않다. 스프린트 헌장(D)은 표준 스크럼 산출물이 아니다. 스프린트 목표(E)는 스프린트 계획의 출력이지 입력이 아니며—회의 중에 정의된다.
905 | During the execution phase of a project, a new department has been created in the company. The manager of this department has requested to be involved in the regular project communications and reporting cycles. What should the project manager do? | Inform the manager that only stakeholders identified in the communications management plan should be involved. | Suggest the manager contact the steering committee and project management office (PMO) to be included. | Ask the project team members to include the manager in all of their communications regarding this project. | Perform a stakeholder analysis and update the communications management plan to reflect the new situation. |  | D | When a new department manager requests inclusion in project communications, the project manager should perform a stakeholder analysis and update the communications management plan to reflect the new situation. Formal assessment ensures appropriate inclusion. Informing the manager only identified stakeholders are included (A) is exclusionary without assessment. Suggesting the manager contact the steering committee (B) deflects responsibility. Asking team members to include the manager (C) is ad hoc. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 실행 단계 중 회사에 새로운 부서가 생성되었다. 이 부서의 관리자가 정기적인 프로젝트 커뮤니케이션 및 보고 주기에 참여하기를 요청했다. 프로젝트 관리자는 무엇을 해야 하는가? | 커뮤니케이션 관리 계획에 식별된 이해관계자만 참여해야 한다고 관리자에게 알린다. | 관리자에게 포함되기 위해 운영위원회 및 프로젝트 관리 오피스(PMO)에 연락하도록 제안한다. | 프로젝트 팀원들에게 이 프로젝트에 관한 모든 커뮤니케이션에 관리자를 포함하도록 요청한다. | 이해관계자 분석을 수행하고 새로운 상황을 반영하여 커뮤니케이션 관리 계획을 업데이트한다. |  | D | 새로운 부서 관리자가 프로젝트 커뮤니케이션에 포함을 요청할 때, 프로젝트 관리자는 이해관계자 분석을 수행하고 새로운 상황을 반영하여 커뮤니케이션 관리 계획을 업데이트해야 한다. 공식적인 평가가 적절한 포함을 보장한다. 식별된 이해관계자만 포함된다고 알리기(A)는 평가 없이 배타적이다. 운영위원회에 연락하도록 제안(B)은 책임을 전가한다. 팀원들에게 포함 요청(C)은 임시방편적이다.
906 | A stressful situation has presented some challenges for the team. The project manager notices stress behavior in some of the team members, and it is beginning to spread across the group. The project manager needs to coach the team to change their mindset in order to be more efficient. What should the project manager do? | Establish a productive environment where all team members can assist one another with the workload. | Meet with the team to discuss the correct, expected behavior in stressful situations and start practicing it. | Ensure that people care about each other and work effectively together through effective team management. | Create an environment of respect and fairness so the team can increase their project performance in stressful situations. |  | A | When stress is spreading across the team, the project manager should establish a productive environment where all team members can assist one another with the workload. Supportive environments reduce stress collectively. Meeting to discuss expected behavior (B) is prescriptive. Ensuring people care about each other (C) is aspirational but vague. Creating an environment of respect and fairness (D) is broader and less actionable. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Align Stakeholder Expectations | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 스트레스 상황이 팀에 몇 가지 도전을 제시했다. 프로젝트 관리자는 일부 팀원들에게서 스트레스 행동을 발견했으며, 그룹 전체로 퍼지기 시작하고 있다. 프로젝트 관리자는 더 효율적이 되기 위해 팀의 사고방식을 변화시키도록 코칭해야 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 모든 팀원이 업무량에 대해 서로 도울 수 있는 생산적인 환경을 구축한다. | 팀과 만나 스트레스 상황에서의 올바른 예상 행동을 논의하고 실천을 시작한다. | 효과적인 팀 관리를 통해 사람들이 서로를 돌보고 효과적으로 함께 일하도록 보장한다. | 팀이 스트레스 상황에서 프로젝트 성과를 높일 수 있도록 존중과 공정의 환경을 만든다. |  | A | 스트레스가 팀 전체로 퍼질 때, 프로젝트 관리자는 모든 팀원이 업무량에 대해 서로 도울 수 있는 생산적인 환경을 구축해야 한다. 지원적인 환경은 스트레스를 집단적으로 줄인다. 예상 행동을 논의하기 위한 회의(B)는 규범적이다. 서로 돌보도록 보장(C)은 열망적이지만 모호하다. 존중과 공정의 환경 만들기(D)는 더 넓고 덜 실행 가능하다.
907 | A project team with a tight schedule has succeeded in maintaining a schedule performance index (SPI) of 1.0 through regular daily standups and overtime, when required. After a few months, the project manager notices that some of the team members' performance has decreased but that the overall project team performance is still ahead of schedule by a few days. What should the project manager do first to maintain the project team's performance level? | Invite the team to a team-building event to alleviate their stress while strengthening teamwork | Remind the team frequently that the project must be delivered on time and within budget | Provide routine mentoring and coaching to the team members to identify any demotivating issues | Initiate a performance-based bonus for the team members to provide them with a monetary incentive |  | C | When some team members' performance decreases despite the project being ahead of schedule, the project manager should first provide routine mentoring and coaching to identify any demotivating issues. Mentoring and coaching allow the PM to uncover root causes—such as stress, burnout, conflict, or lack of recognition—and address them before they worsen. Organizing a team-building event (A) addresses team morale broadly but may not identify individual issues. Reminding the team about deadlines (B) is demotivating and does not address the root cause. Offering performance-based bonuses (D) provides extrinsic motivation but does not uncover or resolve underlying problems. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 빠듯한 일정의 프로젝트 팀이 정기적인 일일 스탠드업과 필요 시 초과 근무를 통해 일정 성과 지수(SPI) 1.0을 유지하는 데 성공했다. 몇 개월 후, 프로젝트 관리자는 일부 팀원의 성과가 감소했지만 전체 프로젝트 팀 성과는 여전히 며칠 일정보다 앞서고 있음을 발견한다. 프로젝트 관리자는 팀의 성과 수준을 유지하기 위해 먼저 무엇을 해야 하는가? | 팀의 스트레스를 완화하면서 팀워크를 강화하기 위해 팀 빌딩 이벤트에 초대한다. | 프로젝트가 일정과 예산 내에 전달되어야 한다고 팀에게 자주 상기시킨다. | 동기 저하 요인을 파악하기 위해 팀원들에게 일상적인 멘토링과 코칭을 제공한다. | 팀원들에게 금전적 인센티브를 제공하기 위한 성과 기반 보너스를 도입한다. |  | C | 일부 팀원의 성과가 감소하고 프로젝트가 일정보다 앞서 있을 때, 프로젝트 관리자는 먼저 일상적인 멘토링과 코칭을 제공하여 동기 저하 요인을 파악해야 한다. 멘토링과 코칭은 PM이 스트레스, 번아웃, 갈등, 인정 부족 등 근본 원인을 밝혀내고 악화되기 전에 해결할 수 있게 한다. 팀 빌딩 이벤트 조직(A)은 팀 사기를 광범위하게 다루지만 개인 이슈를 파악하지 못할 수 있다. 마감일 상기(B)는 동기를 저하시키며 근본 원인을 해결하지 않는다. 성과 기반 보너스 제공(D)은 외적 동기를 제공하지만 근본적인 문제를 밝혀내거나 해결하지 않는다.
908 | A CEO of a general contracting company urgently asks the project manager to sign up two project team members to participate in a specific training course. Halfway through the training, both team members complain that the training is too difficult, above their experience level, and that the material does not align with their tasks. What should the project manager have done to prevent this situation? | Sent an immediate request to the human resources (HR) department to replace the current team members with higher skilled candidates | Planned a training to follow the specific course to bring the two team members to the required experience level | Communicated with the two team members that the purpose of the training is to provide material that might be useful to them in the future | Observed and assessed the competencies and skills of the team members and analyzed the training material beforehand |  | D | When team members complain training is too difficult and misaligned with their tasks, the project manager should have observed and assessed competencies and skills and analyzed the training material beforehand. Pre-assessment ensures training appropriateness. Requesting HR replacements (A) is disproportionate. Planning prerequisite training (B) adds cost without ensuring alignment. Communicating future usefulness (C) does not address the immediate mismatch. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 종합 건설 회사의 CEO가 프로젝트 관리자에게 두 명의 프로젝트 팀원을 특정 교육 과정에 참여시키도록 긴급하게 요청한다. 교육 중간에 두 팀원이 교육이 너무 어렵고, 자신들의 경험 수준 이상이며, 자료가 자신들의 업무와 맞지 않는다고 불만을 제기한다. 이전 프로젝트 관리자는 이 상황을 방지하기 위해 무엇을 했어야 하는가? | 현재 팀원을 더 높은 기술을 가진 후보자로 교체하기 위해 인사부(HR)에 즉각 요청을 보낸다. | 두 팀원을 필요한 경험 수준으로 올리기 위해 특정 과정 전에 교육을 계획한다. | 두 팀원에게 교육의 목적이 향후 유용할 수 있는 자료를 제공하는 것이라고 소통한다. | 팀원들의 역량과 기술을 관찰 및 평가하고 사전에 교육 자료를 분석한다. |  | D | 팀원들이 교육이 너무 어렵고 업무와 맞지 않다고 불만을 제기할 때, 프로젝트 관리자는 사전에 역량과 기술을 관찰 및 평가하고 교육 자료를 분석했어야 한다. 사전 평가가 교육의 적절성을 보장한다. HR에 교체 요청(A)은 비례하지 않는다. 사전 교육 계획(B)은 정렬을 보장하지 않고 비용을 추가한다. 향후 유용성 소통(C)은 즉각적인 불일치를 해결하지 않는다.
909 | A company's CEO has just returned from a conference on the use of artificial intelligence (AI) and would like the project manager to implement this technology in the organization. What should the project manager do first? | Start developing a business case. | Engage stakeholders and allocate resources | Start a strengths, weaknesses, opportunities and threats (SWOT). | Gather requirements from stakeholders |  | D | When the CEO wants to implement AI technology in the organization, the project manager should first gather requirements from stakeholders. Understanding stakeholder needs and expectations before planning ensures the right scope and objectives. Developing a business case (A) requires stakeholder input first. Starting a SWOT analysis (B) is a planning technique, not an initiating step. Engaging stakeholders and allocating resources (C) is part of planning and executing, not the first step. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | AI | 회사의 CEO가 인공지능(AI) 사용에 관한 컨퍼런스에서 돌아와 프로젝트 관리자에게 이 기술을 조직에 구현하고 싶다고 한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 비즈니스 케이스 개발을 시작한다. | 이해관계자를 참여시키고 자원을 배정한다. | 강점, 약점, 기회, 위협(SWOT) 분석을 시작한다. | 이해관계자로부터 요구사항을 수집한다. |  | D | CEO가 조직에 AI 기술을 구현하고자 할 때, 프로젝트 관리자는 먼저 이해관계자로부터 요구사항을 수집해야 한다. 계획 전에 이해관계자의 요구와 기대를 이해하면 올바른 범위와 목표를 보장한다. 비즈니스 케이스 개발(A)은 먼저 이해관계자 입력이 필요하다. SWOT 분석 시작(B)은 계획 기법이지 착수 단계가 아니다. 이해관계자 참여 및 자원 배정(C)은 계획 및 실행의 일부이지 첫 번째 단계가 아니다.
910 | An organization is introducing agile to its projects. During an informal discussion, the project manager learned that team members who are currently working on different teams are discussing how they would like to be together on the same team. What should the project manager do? | The project manager should not allow resources to choose on which team they would like to work because they will always choose their favorite team | The project manager should indicate that the team members have already been assigned to a team through workforce optimization | The project manager should allow the resources to periodically choose on which team they would like to work. | The project manager should not allow resources to choose teams because the project manager assigns the resources based upon project needs |  | C | When team members across different teams express desire to work together on the same team during an agile transition, the project manager should allow resources to periodically choose which team they would like to work on. Self-organization fosters empowerment and motivation. Not allowing choice because of favoritism (A) is presumptive. Citing workforce optimization (B) implies fixed assignments. Not allowing based on PM authority (D) undermines agile self-organization. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 조직이 프로젝트에 애자일을 도입하고 있다. 비공식 대화에서 프로젝트 관리자는 현재 다른 팀에서 일하는 팀원들이 같은 팀에 함께하고 싶다고 논의하고 있음을 알게 되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 관리자는 자원이 항상 선호하는 팀을 선택할 것이므로 원하는 팀을 선택하도록 허용해서는 안 된다. | 프로젝트 관리자는 인력 최적화를 통해 팀원들이 이미 팀에 배정되었다고 알려야 한다. | 프로젝트 관리자는 자원이 주기적으로 원하는 팀을 선택할 수 있도록 허용해야 한다. | 프로젝트 관리자는 프로젝트 필요에 따라 자원을 배정하므로 팀 선택을 허용해서는 안 된다. |  | C | 여러 팀의 팀원들이 애자일 전환 중 같은 팀에서 함께 일하고 싶다고 표현할 때, 프로젝트 관리자는 자원이 주기적으로 원하는 팀을 선택할 수 있도록 허용해야 한다. 자기 조직화는 권한 부여와 동기를 촉진한다. 편애 때문에 선택 불허(A)는 추정적이다. 인력 최적화 언급(B)은 고정 배정을 암시한다. PM 권한에 기반한 불허(D)는 애자일 자기 조직화를 약화시킨다.
911 | An experienced project manager is managing a multi-million dollar agile project. The project manager communicates the ground rules to the team but after 12 iterations, the project manager starts noticing that some team members are not following the ground rules. What should the project manager do first to ensure team adherence to the ground rules? | Notify the project sponsor about this behavior and ask the sponsor to take disciplinary action | Contact human resources to request a written warning letter be sent to team members not following the ground rules. | Schedule a meeting with the project team to reinforce the ground rules. | Ask the functional manager to replace team members not following the ground rules |  | C | When team members stop following ground rules after 12 iterations, the project manager should first schedule a meeting with the project team to reinforce the ground rules. This collaborative approach allows listening to feedback, addressing concerns, and making adjustments while maintaining team cohesion. Notifying the sponsor for disciplinary action (A) escalates externally before internal resolution. Contacting HR for written warnings (B) is punitive. Asking the functional manager to replace team members (D) is extreme without first attempting direct resolution. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 경험 많은 프로젝트 관리자가 수백만 달러 규모의 애자일 프로젝트를 관리하고 있다. 프로젝트 관리자가 팀에 기본 규칙을 전달했지만 12번의 이터레이션 후 일부 팀원이 기본 규칙을 따르지 않고 있음을 발견한다. 팀의 기본 규칙 준수를 보장하기 위해 프로젝트 관리자가 먼저 해야 할 일은? | 프로젝트 스폰서에게 이 행동을 알리고 징계 조치를 요청한다. | 기본 규칙을 따르지 않는 팀원에게 서면 경고서를 보내도록 인사부에 요청한다. | 프로젝트 팀과 회의를 예약하여 기본 규칙을 재강조한다. | 기본 규칙을 따르지 않는 팀원을 교체하도록 기능 관리자에게 요청한다. |  | C | 12번의 이터레이션 후 팀원들이 기본 규칙을 따르지 않을 때, 프로젝트 관리자는 먼저 프로젝트 팀과 회의를 예약하여 기본 규칙을 재강조해야 한다. 이 협력적 접근 방식은 피드백을 듣고, 우려를 해결하며, 팀 결속력을 유지하면서 조정할 수 있게 한다. 징계 조치를 위해 스폰서에게 알리기(A)는 내부 해결 전에 외부로 에스컬레이션한다. 서면 경고를 위해 HR에 연락(B)은 징벌적이다. 팀원 교체를 기능 관리자에게 요청(D)은 먼저 직접 해결을 시도하지 않은 극단적 조치이다.
912 | A project manager has been assigned to complete a worksite project that was started by a different project manager. The project is now in the execution stage. Upon careful review, the project manager realizes that the local community was not included in the stakeholder register, which has resulted in extreme opposition from the community. How should the project manager handle this issue? | Update the stakeholder register and revise the stakeholder engagement plan. | Explain to the community members why they were not included as stakeholders for the 496 project. | Disregard these stakeholders since the relevant documents have been secured to execute this project. | Update the stakeholder register and risk management plan. |  | A | When the local community was omitted from the stakeholder register, causing extreme opposition, the project manager should update the stakeholder register and revise the stakeholder engagement plan. This acknowledges the community as stakeholders, assesses their interests and influence, and develops appropriate engagement strategies. Explaining why they were excluded (B) does not address their concerns. Disregarding them (C) violates stakeholder engagement principles. Updating only the stakeholder register and risk plan (D) omits the engagement strategy needed to manage the relationship. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 관리자가 다른 프로젝트 관리자가 시작한 현장 프로젝트를 완료하도록 배정되었다. 프로젝트는 현재 실행 단계에 있다. 신중한 검토 후, 프로젝트 관리자는 지역 사회가 이해관계자 레지스터에 포함되지 않았음을 발견했으며, 이로 인해 지역 사회의 극심한 반대가 발생했다. 프로젝트 관리자는 이 이슈를 어떻게 처리해야 하는가? | 이해관계자 레지스터를 업데이트하고 이해관계자 참여 계획을 수정한다. | 지역 사회 구성원들에게 왜 이해관계자로 포함되지 않았는지 설명한다. | 이 프로젝트를 실행하기 위한 관련 문서가 확보되었으므로 이 이해관계자들을 무시한다. | 이해관계자 레지스터와 리스크 관리 계획을 업데이트한다. |  | A | 지역 사회가 이해관계자 레지스터에서 누락되어 극심한 반대가 발생할 때, 프로젝트 관리자는 이해관계자 레지스터를 업데이트하고 이해관계자 참여 계획을 수정해야 한다. 이는 지역 사회를 이해관계자로 인정하고, 그들의 이해와 영향력을 평가하며, 적절한 참여 전략을 개발한다. 왜 제외되었는지 설명(B)은 그들의 우려를 해결하지 않는다. 무시(C)는 이해관계자 참여 원칙을 위반한다. 레지스터와 리스크 계획만 업데이트(D)는 관계 관리에 필요한 참여 전략을 누락한다.
913 | A project team is experiencing conflict between two team members. Team member A feels that team member B is always talking over team member A and does not listen to any advice. Team member B is not willing to listen to feedback. What should the project manager do to resolve the issue? | Report the performance issue to both of the team members ' supervisors | Move one of the team members to a different protect team | Modify the communications management plan and resend it to the team | Review the ground rules for collaboration within the team |  | D | When team member A feels talked over and team member B will not listen to feedback, the project manager should review the ground rules for collaboration within the team. Reinforcing norms addresses behavioral expectations. Reporting to supervisors (A) escalates unnecessarily. Moving a team member (B) avoids resolution. Modifying the communications plan (C) addresses documents, not interpersonal behavior. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 두 팀원 간의 갈등을 겪고 있다. 팀원 A는 팀원 B가 항상 팀원 A의 말을 끊고 어떤 조언도 듣지 않는다고 느낀다. 팀원 B는 피드백을 들으려 하지 않는다. 프로젝트 관리자는 이 이슈를 해결하기 위해 무엇을 해야 하는가? | 두 팀원의 상사에게 성과 이슈를 보고한다. | 팀원 중 한 명을 다른 프로젝트 팀으로 이동시킨다. | 커뮤니케이션 관리 계획을 수정하고 팀에게 재배포한다. | 팀 내 협업을 위한 기본 규칙을 검토한다. |  | D | 팀원 A가 말을 끊긴다고 느끼고 팀원 B가 피드백을 듣지 않을 때, 프로젝트 관리자는 팀 내 협업을 위한 기본 규칙을 검토해야 한다. 규범을 강화하면 행동 기대치를 다룬다. 상사에게 보고(A)는 불필요하게 에스컬레이션한다. 팀원 이동(B)은 해결을 회피한다. 커뮤니케이션 계획 수정(C)은 문서를 다루지 대인 관계 행동은 다루지 않는다.
914 | A human resources (HR) cost report was disclosed, by error, to all members of the project team. This situation generated a conflict between the team members about differences in their salaries. What should the project manager have done to avoid this situation? | Included noncompliance punishment measures in the communications management plan | Validated the information and the appropriate recipients per the communications management plan | Ensured reports with significant information were not included in the communications management plan | Defined the appropriate recipients for the report in the communications management plan |  | D | When an HR cost report is accidentally disclosed to the entire team causing salary conflict, the project manager should have defined the appropriate recipients for the report in the communications management plan. Proper recipient controls prevent sensitive information from reaching unauthorized recipients. Including noncompliance punishment measures (A) is punitive, not preventive. Excluding significant reports from the plan (C) leaves gaps. The plan should control distribution, not restrict content. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Scope & Requirements Mgmt | People | Manage Conflicts | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 인사(HR) 비용 보고서가 실수로 프로젝트 팀의 모든 구성원에게 공개되었다. 이 상황은 팀원들 사이에 급여 차이에 대한 갈등을 발생시켰다. 프로젝트 관리자는 이 상황을 피하기 위해 무엇을 했어야 하는가? | 커뮤니케이션 관리 계획에 비준수 처벌 조치를 포함시킨다. | 커뮤니케이션 관리 계획에 따라 정보와 적절한 수신자를 검증한다. | 중요한 정보가 포함된 보고서가 커뮤니케이션 관리 계획에 포함되지 않도록 보장한다. | 커뮤니케이션 관리 계획에서 보고서의 적절한 수신자를 정의한다. |  | D | HR 비용 보고서가 실수로 전체 팀에 공개되어 급여 갈등이 발생했을 때, 프로젝트 관리자는 커뮤니케이션 관리 계획에서 보고서의 적절한 수신자를 정의했어야 한다. 적절한 수신자 통제는 민감한 정보가 비인가 수신자에게 전달되는 것을 방지한다. 비준수 처벌 조치 포함(A)은 징벌적이지 예방적이지 않다. 중요 보고서를 계획에서 제외(C)는 공백을 남긴다. 계획은 배포를 통제해야지 내용을 제한해서는 안 된다.
915 | An agile project is 25% complete when the product owner changes. The new product owner does not show interest in the project's success, and one of the sprints got delayed as the deliverable was not approved on time. What should the project manager have done to prevent this delay? | Updated the communications management plan to reflect a change in the communication needs | Updated the stakeholder engagement plan to reflect a change in the product owner | Communicated the status of the project more frequently with the product owner | Reevaluated the new product owner ' s needs for better engagement |  | D | To prevent delays caused by an unengaged product owner, the PM should have proactively ensured the new PO was properly onboarded and committed from the outset. This includes conducting a thorough handover from the departing PO, establishing clear expectations for PO responsibilities (such as timely deliverable reviews), and building a strong working relationship early. Stakeholder engagement planning should have identified the PO transition as a risk and established mitigation measures. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트가 25% 완료되었을 때 제품 책임자가 변경되었다. 새 제품 책임자가 프로젝트 성공에 관심을 보이지 않으며, 산출물이 제시간에 승인되지 않아 스프린트 중 하나가 지연되었다. 프로젝트 관리자는 이 지연을 방지하기 위해 무엇을 했어야 하는가? | 커뮤니케이션 요구 변경을 반영하여 커뮤니케이션 관리 계획을 업데이트한다. | 제품 책임자 변경을 반영하여 이해관계자 참여 계획을 업데이트한다. | 제품 책임자와 프로젝트 상태를 더 자주 커뮤니케이션한다. | 더 나은 참여를 위해 새 제품 책임자의 요구를 재평가한다. |  | D | 참여하지 않는 제품 책임자로 인한 지연을 방지하기 위해, PM은 새 PO가 처음부터 적절히 온보딩되고 헌신하도록 사전 예방적으로 보장했어야 한다. 이는 이전 PO로부터의 철저한 인수인계, PO 책임에 대한 명확한 기대 설정(적시 산출물 검토 등), 초기에 강력한 업무 관계 구축을 포함한다. 이해관계자 참여 계획은 PO 전환을 리스크로 식별하고 완화 조치를 수립했어야 한다.
916 | A project manager is working on a large event and developing budgets for sign-off. The stakeholders and project sponsor are all working remotely using various tools to ensure that all documentation is tracked and handled discretely and appropriately. The primary stakeholder has missed several deadlines for the milestone sign-offs, resulting in the project manager being forced to find alternative suppliers for items, now at higher costs. When questioned regarding the delays, the stakeholder says the notifications hadn't appeared in their email inbox. How should the project manager proceed? | Request human resources (HR) intervene and send the stakeholder to appropriate technical training. | Escalate the issue to the IT department and request they check the software on the stakeholder ' s computer. | Assess whether the communications channels are appropriate for the primary stakeholder and amend accordingly. | Request the primary stakeholder be replaced to avoid any more delays and budget issues. |  | C | When a primary stakeholder misses sign-off deadlines claiming email notifications did not appear, the project manager should assess whether the communication channels are appropriate for that stakeholder and amend accordingly. Fixing the communication method addresses the root cause of missed approvals. Requesting HR training (A) is disproportionate. Escalating to IT (B) addresses a symptom, not the process. Requesting stakeholder replacement (D) is extreme and typically outside the PM's authority. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 대규모 이벤트를 작업하며 서명 승인을 위한 예산을 개발하고 있다. 이해관계자와 프로젝트 스폰서 모두 원격으로 다양한 도구를 사용하여 모든 문서가 신중하고 적절하게 추적되고 처리되도록 하고 있다. 주요 이해관계자가 마일스톤 서명 승인에 대한 여러 마감일을 놓쳤고, 이로 인해 프로젝트 관리자가 더 높은 비용으로 대안 공급업체를 찾아야 했다. 지연에 대해 질문했을 때, 이해관계자는 알림이 이메일 수신함에 나타나지 않았다고 말했다. 프로젝트 관리자는 어떻게 진행해야 하는가? | 인사부(HR)에 개입하여 이해관계자를 적절한 기술 교육에 보내도록 요청한다. | IT 부서에 이슈를 에스컬레이션하고 이해관계자의 컴퓨터 소프트웨어를 확인하도록 요청한다. | 커뮤니케이션 채널이 주요 이해관계자에게 적절한지 평가하고 그에 따라 수정한다. | 더 이상의 지연과 예산 문제를 피하기 위해 주요 이해관계자를 교체하도록 요청한다. |  | C | 주요 이해관계자가 이메일 알림이 나타나지 않았다며 서명 승인 마감일을 놓칠 때, 프로젝트 관리자는 커뮤니케이션 채널이 해당 이해관계자에게 적절한지 평가하고 그에 따라 수정해야 한다. 커뮤니케이션 방법을 수정하면 놓친 승인의 근본 원인을 해결한다. HR 교육 요청(A)은 과도한 대응이다. IT에 에스컬레이션(B)은 프로세스가 아닌 증상을 다룬다. 이해관계자 교체 요청(D)은 극단적이며 일반적으로 PM의 권한 밖이다.
917 | A project manager has considered a detailed and expensive training plan for a new technology for all team members. The training is needed several months into the execution phase of a project. Surprisingly, many problems still appear that are related to the team members' lack of competence and the training costs are now negatively impacting the budget baseline. What should the project manager do next? | Perform a root-cause analysis to measure how the new training will address the issue | Select resources who are more experienced with the new technology | Include in the risk register a risk of unskilled resources for the new technology | Elaborate and socialize the team charter as per the resource management plan |  | D | When training for new technology produces problems due to continued lack of competence and negatively impacts the budget, the project manager should elaborate and socialize the team charter as per the resource management plan. The team charter aligns team members with roles, responsibilities, expectations, and project objectives—addressing competence gaps holistically. Root cause analysis of new training (A) evaluates training but not team alignment. Selecting more experienced resources (B) changes the team without addressing existing members. Adding risk of unskilled resources to the register (C) documents but does not resolve the problem. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 프로젝트 관리자가 모든 팀원을 위한 새 기술에 대한 상세하고 비용이 많이 드는 교육 계획을 고려했다. 교육은 프로젝트 실행 단계 수개월 후에 필요하다. 놀랍게도, 팀원들의 역량 부족과 관련된 많은 문제가 여전히 발생하고 있으며 교육 비용이 이제 예산 기준선에 부정적 영향을 미치고 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 새 교육이 이슈를 어떻게 해결할지 측정하기 위해 근본 원인 분석을 수행한다. | 새 기술에 더 경험이 있는 자원을 선발한다. | 새 기술에 대한 미숙련 자원의 리스크를 리스크 레지스터에 포함시킨다. | 자원 관리 계획에 따라 팀 헌장을 정교화하고 사회화한다. |  | D | 새 기술 교육이 역량 부족 문제를 해결하지 못하고 예산에 부정적 영향을 미칠 때, 프로젝트 관리자는 자원 관리 계획에 따라 팀 헌장을 정교화하고 사회화해야 한다. 팀 헌장은 팀원들을 역할, 책임, 기대, 프로젝트 목표에 정렬시켜 역량 격차를 총체적으로 해결한다. 새 교육의 근본 원인 분석(A)은 교육을 평가하지만 팀 정렬은 다루지 않는다. 더 경험 있는 자원 선발(B)은 기존 구성원을 다루지 않고 팀을 변경한다. 미숙련 자원 리스크를 레지스터에 추가(C)는 문서화하지만 해결하지 않는다.
918 | A project lead was recently appointed to complete the execution of a legacy project for a water filtration plant due to the project director's reassignment. The project lead has been on five similar projects in the recent past. The client has challenged the completion status due to a lack of construction evidence. The client has also indicated their intention to apply performance-associated penalties that are detailed in the contract. What should the project lead do? | Accept the client ' s observations and pay the penalties as per the project contract details. | Investigate the client ' s project reports and proceed to negotiate the levying of any penalties. | Inform the project director of the change and complete the project so as to not incur any penalties. | Request for the recall of the project director to investigate the situation and negotiate potential penalties. 1125 |  | B | When a client challenges completion status due to lack of construction evidence and threatens contract penalties, the project lead should investigate the client's project reports and proceed to negotiate potential penalties. Fact-finding before action is essential. Accepting and paying penalties (A) is premature. Informing the project director and completing to avoid penalties (C) bypasses due diligence. Requesting the director's recall (D) deflects responsibility. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 프로젝트 리더가 프로젝트 책임자의 재배치로 인해 정수 처리 시설을 위한 레거시 프로젝트의 실행을 완료하도록 최근 임명되었다. 프로젝트 리더는 최근 5건의 유사 프로젝트 경험이 있다. 고객이 공사 증거 부족으로 완료 상태에 이의를 제기했다. 고객은 또한 계약에 명시된 성과 관련 벌금을 적용할 의향을 표시했다. 프로젝트 리더는 무엇을 해야 하는가? | 고객의 관찰을 수락하고 프로젝트 계약 세부사항에 따라 벌금을 지불한다. | 고객의 프로젝트 보고서를 조사하고 벌금 부과를 협상한다. | 프로젝트 책임자에게 변경 사항을 알리고 벌금이 발생하지 않도록 프로젝트를 완료한다. | 상황을 조사하고 잠재적 벌금을 협상하기 위해 프로젝트 책임자의 복귀를 요청한다. |  | B | 고객이 공사 증거 부족으로 완료 상태에 이의를 제기하고 계약 벌금을 위협할 때, 프로젝트 리더는 고객의 프로젝트 보고서를 조사하고 잠재적 벌금을 협상해야 한다. 조치 전 사실 확인이 필수적이다. 벌금을 수락하고 지불(A)은 시기상조이다. 프로젝트 책임자에게 알리고 완료(C)는 실사를 우회한다. 책임자의 복귀 요청(D)은 책임을 전가한다.
919 | A project manager is newly appointed to an ongoing project that will develop a new solution using an affiliate of the company. The deploying resources will come from another entity of the company. When asked to confirm the availability of the deploying team, the deploying manager declined. What should the project manager do first? | Create a change request to be validated by the project sponsor. | Ask the project sponsor for external resources. | Refer to the project ' s resource management plan. | Reschedule the project taking this new information into account. |  | C | When the deploying manager declines to confirm resource availability for an ongoing project, the project manager should first refer to the project's resource management plan. The plan outlines how resources are identified, acquired, and managed. Creating a change request (A) is premature. Asking the sponsor for external resources (B) skips internal resolution. Rescheduling the project (D) concedes before exploring options. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 회사의 계열사를 사용하여 새로운 솔루션을 개발하는 진행 중인 프로젝트에 새로 임명되었다. 배포 자원은 회사의 다른 법인에서 나올 예정이다. 배포 팀의 가용성을 확인해 달라는 요청에 배포 관리자가 거부했다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 프로젝트 스폰서가 검증할 변경 요청을 생성한다. | 프로젝트 스폰서에게 외부 자원을 요청한다. | 프로젝트의 자원 관리 계획을 참조한다. | 이 새로운 정보를 고려하여 프로젝트 일정을 재조정한다. |  | C | 배포 관리자가 진행 중인 프로젝트에 대한 자원 가용성 확인을 거부할 때, 프로젝트 관리자는 먼저 프로젝트의 자원 관리 계획을 참조해야 한다. 계획은 자원이 어떻게 식별, 확보, 관리되는지를 설명한다. 변경 요청 생성(A)은 시기상조이다. 스폰서에게 외부 자원 요청(B)은 내부 해결을 건너뛴다. 프로젝트 재조정(D)은 옵션을 탐색하기 전에 양보한다.
920 | A company is transitioning its projects from a predictive to an iterative approach. The project team is complaining because they are unsure of what needs to be done due to all of the changes requested by the product owner for features already developed since the beginning of the project. How should the project manager handle this situation? | Make sure that the product and sprint backlogs have the required level of documentation and both are visible to the team | Review the backlogs from similar projects and understand how change requests were implemented | Ask the product owner to follow the change request process to formalize new requirements | Ask the product owner to create a new entry in the risk management plan regarding likelihood and imped |  | A | When transitioning from predictive to iterative approaches, clear and transparent communication about requirements and changes is essential. Product and sprint backlogs should be well-documented and visible to all team members. If the team is uncertain about their work due to frequent changes, it indicates that the backlogs are not adequately maintained or accessible. The PM should ensure proper documentation and visibility of all backlog items to eliminate confusion and enable effective delivery. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Scope | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 회사가 프로젝트를 예측형에서 반복형 접근 방식으로 전환하고 있다. 프로젝트 팀이 프로젝트 초기부터 이미 개발된 기능에 대해 제품 책임자가 요청한 모든 변경 사항으로 인해 무엇을 해야 하는지 확실하지 않아 불만을 제기하고 있다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 제품 및 스프린트 백로그가 필요한 수준의 문서화를 갖추고 둘 다 팀에 가시적이도록 보장한다. | 유사 프로젝트의 백로그를 검토하고 변경 요청이 어떻게 구현되었는지 이해한다. | 제품 책임자에게 새로운 요구사항을 공식화하기 위한 변경 요청 프로세스를 따르도록 요청한다. | 제품 책임자에게 새 기술에 대한 가능성과 영향에 관한 리스크 관리 계획에 새 항목을 생성하도록 요청한다. |  | A | 예측형에서 반복형 접근 방식으로 전환할 때 요구사항과 변경에 대한 명확하고 투명한 커뮤니케이션이 필수적이다. 제품 및 스프린트 백로그는 잘 문서화되고 모든 팀원에게 가시적이어야 한다. 팀이 빈번한 변경으로 인해 작업에 확신이 없다면 백로그가 적절히 유지되거나 접근 가능하지 않음을 나타낸다. PM은 모든 백로그 항목의 적절한 문서화와 가시성을 보장하여 혼란을 제거하고 효과적인 전달을 가능하게 해야 한다.
921 | A project manager is developing the stakeholder register and is having trouble understanding the motivation of some of the stakeholders. What should the project manager do to get this information? | Identify each stakeholder ' s motivations from the business case. | Email project objectives to all stakeholders and ask for endorsement. | Request stakeholders articulate their motivations at the kick-off meeting. | Organize a one-on-one conversation with each stakeholder. |  | D | When having trouble understanding stakeholder motivations while developing the stakeholder register, the project manager should organize one-on-one conversations with each stakeholder. Direct personal engagement reveals motivations, concerns, and interests that group settings may not uncover. Identifying motivations from the business case (A) provides context but not individual perspectives. Emailing project objectives for endorsement (B) is impersonal. Requesting articulation at the kickoff meeting (C) may not allow for candid discussion. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 이해관계자 레지스터를 개발하고 있으며 일부 이해관계자의 동기를 이해하는 데 어려움을 겪고 있다. 프로젝트 관리자는 이 정보를 얻기 위해 무엇을 해야 하는가? | 비즈니스 케이스에서 각 이해관계자의 동기를 식별한다. | 모든 이해관계자에게 프로젝트 목표를 이메일로 보내고 승인을 요청한다. | 이해관계자들에게 킥오프 회의에서 동기를 표명하도록 요청한다. | 각 이해관계자와 1:1 대화를 진행한다. |  | D | 이해관계자 레지스터를 개발하면서 이해관계자 동기를 이해하는 데 어려움이 있을 때, 프로젝트 관리자는 각 이해관계자와 1:1 대화를 진행해야 한다. 직접적인 개인 참여는 그룹 환경에서 발견되지 않을 수 있는 동기, 우려, 관심사를 드러낸다. 비즈니스 케이스에서 동기 식별(A)은 맥락을 제공하지만 개별 관점은 아니다. 프로젝트 목표 이메일(B)은 비인격적이다. 킥오프 회의에서 표명 요청(C)은 솔직한 논의를 허용하지 않을 수 있다.
922 | At the start of a project, the sponsor declares that demonstrating benefits from the product will be extremely important. The project sponsor calls a meeting with the project manager and the project leadership team to discuss the best approach because the project has a high degree of uncertainty and many changes are expected. What should the project manager propose? | Recommend an agile approach so the project can be delivered iteratively. | Outsource development of the product to a third party with more experience. | Develop requirements and designs to support a faster product release. | Emphasize the adoption of a predictive approach to minimize ambiguity. |  | A | An agile approach suits projects with high uncertainty and change, enabling frequent feedback, adaptation, and value delivery through working increments or prototypes. This demonstrates product benefits to the sponsor and stakeholders directly. Rushing requirements development (A) may compromise quality. Adopting a predictive approach (B) requires detailed upfront planning incompatible with high uncertainty. Outsourcing (D) introduces additional risks and reduces stakeholder visibility into progress. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | AI | 프로젝트 시작 시 스폰서가 제품의 혜택을 입증하는 것이 매우 중요하다고 선언한다. 프로젝트 스폰서가 프로젝트 관리자 및 프로젝트 리더십 팀과 회의를 소집하여 최선의 접근 방식을 논의한다. 프로젝트의 불확실성이 높고 많은 변경이 예상되기 때문이다. 프로젝트 관리자는 무엇을 제안해야 하는가? | 프로젝트를 반복적으로 전달할 수 있도록 애자일 접근 방식을 권장한다. | 더 많은 경험을 가진 제3자에게 제품 개발을 아웃소싱한다. | 더 빠른 제품 출시를 지원하기 위해 요구사항과 설계를 개발한다. | 모호성을 최소화하기 위해 예측적 접근 방식 채택을 강조한다. |  | A | 애자일 접근 방식은 높은 불확실성과 변경이 있는 프로젝트에 적합하며, 작동하는 증분 또는 프로토타입을 통해 빈번한 피드백, 적응, 가치 전달을 가능하게 한다. 이는 스폰서와 이해관계자에게 제품 혜택을 직접 입증한다. 요구사항 개발 서두르기(A)는 품질을 저하시킬 수 있다. 예측적 접근 방식 채택(B)은 높은 불확실성과 양립할 수 없는 상세한 사전 계획을 요구한다. 아웃소싱(D)은 추가 리스크를 도입하고 이해관계자의 진행 가시성을 줄인다.
923 | During the course of a project, the project manager wants to ensure that the work carried out and the product being created do not deviate from the prescribed business value. What should the project manager pay special attention to in order to achieve this goal? | Carrying out quality audits and failure analyses | Monitoring and updating the benefits realization plan | Reviewing and updating the requirements management plan | Monitoring the work breakdown structure (WBS) |  | B | When ensuring that work and the product do not deviate from prescribed business value, the project manager should pay special attention to monitoring and updating the benefits realization plan. This plan tracks value delivery alignment. Carrying out quality audits (A) addresses product quality, not business value. Reviewing the requirements management plan (C) focuses on requirements, not benefits. Monitoring the WBS (D) tracks scope decomposition, not value. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Stakeholder & Communication Mgmt | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Traditional PM | 프로젝트 진행 중 프로젝트 관리자는 수행된 작업과 생성되는 제품이 규정된 비즈니스 가치에서 벗어나지 않도록 보장하고자 한다. 이 목표를 달성하기 위해 프로젝트 관리자는 무엇에 특별히 주의를 기울여야 하는가? | 품질 감사 및 실패 분석 수행 | 혜택 실현 계획 모니터링 및 업데이트 | 요구사항 관리 계획 검토 및 업데이트 | 작업 분류 체계(WBS) 모니터링 |  | B | 작업과 제품이 규정된 비즈니스 가치에서 벗어나지 않도록 보장할 때, 프로젝트 관리자는 혜택 실현 계획 모니터링 및 업데이트에 특별히 주의를 기울여야 한다. 이 계획은 가치 전달 정렬을 추적한다. 품질 감사 수행(A)은 제품 품질을 다루지 비즈니스 가치를 다루지 않는다. 요구사항 관리 계획 검토(C)는 요구사항에 초점을 맞추지 혜택에는 초점을 맞추지 않는다. WBS 모니터링(D)은 범위 분해를 추적하지 가치를 추적하지 않는다.
924 | A project manager works in an organization that embraces using different project approaches. The project manager's current project uses a predictive approach with clear requirements. A few months following the kickoff, the project manager notices that the virtual development teams are not communicating enough, and coordination is becoming an issue. The teams are not aligned on the tasks being done or the current impediments. What should the project manager do? | Review the issue with the project sponsor and ask for support. | Plan a monthly virtual meeting to align and to review the plans. | Ask the members to be more proactive and share ideas with each other. | Set up a daily virtual meeting with the development team. |  | D | When virtual development teams in a predictive project are not communicating enough and coordination is becoming an issue, the project manager should set up daily virtual meetings with the development team. Regular cadence fosters alignment and addresses impediments. Reviewing the issue with the sponsor (A) escalates prematurely. Planning monthly meetings (B) is too infrequent for coordination needs. Asking members to be more proactive (C) is vague and non-actionable. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 다양한 프로젝트 접근 방식 사용을 수용하는 조직에서 프로젝트 관리자가 일하고 있다. 현재 프로젝트는 명확한 요구사항을 가진 예측적 접근 방식을 사용한다. 킥오프 후 몇 달이 지나 프로젝트 관리자는 가상 개발 팀이 충분히 소통하지 않으며 조율이 문제가 되고 있음을 발견한다. 팀들은 수행 중인 작업이나 현재 장애물에 대해 정렬되지 않았다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서와 이슈를 검토하고 지원을 요청한다. | 정렬하고 계획을 검토하기 위해 월간 가상 회의를 계획한다. | 멤버들에게 더 적극적이 되고 서로 아이디어를 공유하도록 요청한다. | 개발 팀과 매일 가상 회의를 설정한다. |  | D | 예측적 프로젝트에서 가상 개발 팀이 충분히 소통하지 않고 조율이 문제가 될 때, 프로젝트 관리자는 개발 팀과 매일 가상 회의를 설정해야 한다. 정기적인 케이던스는 정렬을 촉진하고 장애물을 해결한다. 스폰서와 이슈 검토(A)는 성급한 에스컬레이션이다. 월간 회의 계획(B)은 조율 필요에 비해 너무 빈도가 낮다. 멤버들에게 적극적이 되라고 요청(C)은 모호하고 실행 불가능하다.
925 | A new relevant project stakeholder suggested a change to some of the project parameters midway through execution. What should the project manager do next? | Transfer the change to the steering committee for them to evaluate and decide the appropriate next steps | Evaluate the proposed change with integrated change controls and discuss the change with the project sponsor | Accept the change and use contingency funds to implement this change with minimal schedule impacts | Reject the change because it is contrary to what was agreed to during earlier phases of the project |  | B | When a new stakeholder suggests changes to project parameters midway through execution, the project manager should evaluate the proposed change with integrated change controls and discuss it with the project sponsor. Formal evaluation ensures informed decision-making. Transferring to the steering committee (A) abdicates PM responsibility. Accepting and using contingency funds (C) bypasses change control. Rejecting outright (D) dismisses the proposal without evaluation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 새로운 관련 프로젝트 이해관계자가 실행 중간에 일부 프로젝트 매개변수 변경을 제안했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 적절한 다음 단계를 평가하고 결정하도록 변경을 운영위원회에 이관한다. | 통합 변경 통제로 제안된 변경을 평가하고 프로젝트 스폰서와 변경을 논의한다. | 변경을 수락하고 일정 영향을 최소화하며 이 변경을 구현하기 위해 예비비를 사용한다. | 프로젝트 초기 단계에서 합의된 것과 상반되므로 변경을 거부한다. |  | B | 새 이해관계자가 실행 중간에 프로젝트 매개변수 변경을 제안할 때, 프로젝트 관리자는 통합 변경 통제로 제안된 변경을 평가하고 프로젝트 스폰서와 논의해야 한다. 공식적 평가는 정보에 기반한 의사결정을 보장한다. 운영위원회에 이관(A)은 PM의 책임을 포기한다. 수락하고 예비비 사용(C)은 변경 통제를 우회한다. 즉시 거부(D)는 평가 없이 제안을 무시한다.
926 | At the end of a meeting, a functional manager takes the project manager aside to raise some concerns on behalf of a project team member who is unclear about their role and responsibilities for the project. What should the project manager do in this situation? | Ask the functional manager to create a specific responsible, accountable, consult, and inform (RACI) chart for the team member | Develop a work plan for the project team member with the help of the resource manager | Tell the functional manager and the project team member to review the projectcharter | Advise the functional manager and the project team member to review the resource management plan |  | A | When a functional manager raises concerns about a team member unclear on their role and responsibilities, the project manager should ask the functional manager to create a specific RACI chart for the team member. A RACI chart clarifies involvement levels for each activity. Developing a work plan with the resource manager (B) addresses tasks, not role clarity. Reviewing the project charter (C) is too high-level. Reviewing the resource management plan (D) may not provide activity-level role definition. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Cost & Resource Management | People | Lead the Project Team | Resources | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 회의 종료 시 기능 관리자가 프로젝트 관리자를 따로 불러 프로젝트에서의 역할과 책임이 불분명한 프로젝트 팀원을 대신하여 우려를 제기한다. 이 상황에서 프로젝트 관리자는 무엇을 해야 하는가? | 기능 관리자에게 팀원을 위한 구체적인 RACI(책임, 승인, 자문, 통보) 차트를 작성하도록 요청한다. | 자원 관리자의 도움을 받아 프로젝트 팀원을 위한 작업 계획을 개발한다. | 기능 관리자와 프로젝트 팀원에게 프로젝트 헌장을 검토하도록 말한다. | 기능 관리자와 프로젝트 팀원에게 자원 관리 계획을 검토하도록 조언한다. |  | A | 기능 관리자가 역할과 책임이 불분명한 팀원에 대한 우려를 제기할 때, 프로젝트 관리자는 기능 관리자에게 팀원을 위한 구체적인 RACI 차트를 작성하도록 요청해야 한다. RACI 차트는 각 활동에 대한 참여 수준을 명확히 한다. 자원 관리자와 작업 계획 개발(B)은 역할 명확성이 아닌 작업을 다룬다. 프로젝트 헌장 검토(C)는 너무 상위 수준이다. 자원 관리 계획 검토(D)는 활동 수준의 역할 정의를 제공하지 못할 수 있다.
927 | A complex project is being developed in phases as per the original plan. Half of the systems have been handed over to the customer for operational use. There is no delay in the schedule. However, the customer is still not happy because some of the systems handed over are no longer useful due to changes in the environment. What should the project manager have done to avoid this? | Informed the project team to closely monitor the deliverables and keep the customer informed | Asked the customer to participate in project status meetings to better understand the progress | Reviewed benefits realization with the customer regularly and constantly aligned expectations | Explained to the customer that the project is in good shape as the system is operational |  | C | When phased deliveries stay on schedule but become obsolete due to environmental changes, the project manager should have reviewed benefits realization with the customer regularly and constantly aligned expectations. Ongoing benefits validation ensures deliverables remain valuable. Monitoring deliverables and informing the customer (A) is delivery-centric, not value-focused. Inviting the customer to status meetings (B) discusses progress, not value alignment. Explaining operational readiness (D) ignores business context changes. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 복잡한 프로젝트가 원래 계획대로 단계별로 개발되고 있다. 시스템의 절반이 운영 사용을 위해 고객에게 인계되었다. 일정 지연은 없다. 그러나 인계된 시스템 일부가 환경 변화로 인해 더 이상 유용하지 않아 고객이 여전히 만족하지 않는다. 프로젝트 관리자는 이를 방지하기 위해 무엇을 했어야 하는가? | 프로젝트 팀에게 산출물을 면밀히 모니터링하고 고객에게 정보를 제공하도록 지시했어야 한다. | 고객에게 프로젝트 상태 회의에 참석하여 진행 상황을 더 잘 이해하도록 요청했어야 한다. | 고객과 정기적으로 혜택 실현을 검토하고 지속적으로 기대를 정렬했어야 한다. | 시스템이 운영 중이므로 프로젝트가 양호한 상태임을 고객에게 설명했어야 한다. |  | C | 단계별 인도가 일정대로 진행되지만 환경 변화로 인해 구식이 될 때, 프로젝트 관리자는 고객과 정기적으로 혜택 실현을 검토하고 지속적으로 기대를 정렬했어야 한다. 지속적인 혜택 검증은 산출물이 가치를 유지하도록 보장한다. 산출물 모니터링 및 고객 정보 제공(A)은 전달 중심이지 가치 중심이 아니다. 고객을 상태 회의에 초대(B)는 진행 상황을 논의하지 가치 정렬은 논의하지 않는다. 운영 준비 상태 설명(D)은 비즈니스 맥락 변화를 무시한다.
928 | A project manager has been assigned to a project after the charter has been approved. While reviewing the charter with the team, the project manager finds that some major budget items, necessary for achieving the project outcome, have been missed. What should the project manager do next? | Reduce the quality and cost of other deliverables to allow additional budget for the items that were missed. | Add the missing budget items to the risk log and present them in the next project steering committee. | Immediately discuss this with the project sponsor and request to revisit the budget to ensure its accuracy. | Start the project and deal with these budget issues as they arise throughout the project life cycle. |  | C | When reviewing the approved charter reveals major budget items were missed for achieving the project outcome, the project manager should immediately discuss this with the project sponsor and request to revisit the budget for accuracy. Early escalation of budget gaps prevents downstream failures. Reducing quality of other deliverables (A) compromises the project. Adding to the risk log for the steering committee (B) delays resolution. Starting the project and dealing with issues as they arise (D) is reactive. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 프로젝트 관리자가 헌장 승인 후 프로젝트에 배정되었다. 팀과 헌장을 검토하면서 프로젝트 관리자는 프로젝트 결과 달성에 필요한 일부 주요 예산 항목이 누락되었음을 발견한다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 누락된 항목에 대한 추가 예산을 확보하기 위해 다른 산출물의 품질과 비용을 줄인다. | 누락된 예산 항목을 리스크 로그에 추가하고 다음 프로젝트 운영위원회에 제시한다. | 프로젝트 스폰서와 즉시 논의하고 정확성을 보장하기 위해 예산을 재검토하도록 요청한다. | 프로젝트를 시작하고 프로젝트 생애주기 전반에 걸쳐 이러한 예산 이슈가 발생할 때 처리한다. |  | C | 승인된 헌장 검토 시 프로젝트 결과 달성에 필요한 주요 예산 항목이 누락된 것을 발견할 때, 프로젝트 관리자는 스폰서와 즉시 논의하고 정확성을 위해 예산 재검토를 요청해야 한다. 예산 격차의 조기 에스컬레이션은 하류 실패를 방지한다. 다른 산출물의 품질 축소(A)는 프로젝트를 훼손한다. 리스크 로그에 추가하고 운영위원회에 제시(B)는 해결을 지연시킨다. 프로젝트를 시작하고 발생 시 처리(D)는 반응적이다.
929 | A transportation company is transforming its operational processes and the main system this company uses to move freight. The scope statement is in place. An iterative delivery approach has been agreed by all stakeholders. What does the project manager need to do next to help the team understand the work that needs to be done? | Start working on the project management plan with work packages, a detailed schedule, and work assignments for team members | Create the requirements management plan to outline how project requirements will be collected analyzed and documented and then assign requirements to team members | Work directly with stakeholders on the work breakdown structure (WBS) and assign tasks with a required timeline for each team member to start the work. | Work with the team to decompose the scope into a WBS and work packages in order to create required deliverables and timelines. |  | D | When a transportation company has agreed on an iterative delivery approach and the scope statement is in place, the project manager should work with the team to decompose the scope into a WBS and work packages to create required deliverables and timelines. WBS decomposition clarifies work for iterative delivery. Starting the full project management plan with detailed schedules (A) is too prescriptive for iterative delivery. Creating the requirements management plan (B) is one component, not the primary next step. Working directly with stakeholders on WBS without the team (C) excludes team involvement. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Build an Empowered Culture | Plan Scope Management | Traditional PM | 운송 회사가 운영 프로세스와 화물 이동에 사용하는 주요 시스템을 전환하고 있다. 범위 기술서가 마련되어 있다. 반복적 전달 접근 방식이 모든 이해관계자에 의해 합의되었다. 팀이 수행해야 할 작업을 이해하도록 돕기 위해 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 작업 패키지, 상세 일정, 팀원별 작업 배정이 포함된 프로젝트 관리 계획 작업을 시작한다. | 프로젝트 요구사항의 수집, 분석, 문서화 방법을 설명하는 요구사항 관리 계획을 작성한 후 팀원에게 요구사항을 배정한다. | 이해관계자와 직접 작업 분류 체계(WBS)를 작업하고 각 팀원이 작업을 시작할 수 있도록 필요한 타임라인과 함께 작업을 배정한다. | 팀과 함께 범위를 WBS와 작업 패키지로 분해하여 필요한 산출물과 타임라인을 생성한다. |  | D | 운송 회사가 반복적 전달 접근 방식에 합의하고 범위 기술서가 마련되었을 때, 프로젝트 관리자는 팀과 함께 범위를 WBS와 작업 패키지로 분해하여 필요한 산출물과 타임라인을 생성해야 한다. WBS 분해는 반복적 전달을 위한 작업을 명확히 한다. 상세 일정이 포함된 전체 프로젝트 관리 계획 시작(A)은 반복적 전달에 너무 규범적이다. 요구사항 관리 계획 작성(B)은 하나의 구성요소이지 주요 다음 단계가 아니다. 팀 없이 이해관계자와 직접 WBS 작업(C)은 팀 참여를 배제한다.
930 | A team member is always late to work. The project manager is concerned that this may affect the motivation of other team members. The project manager tells the new team member to align with the team's principles and arrive on time. What kind of conflict resolution did the project manager apply in this situation? | Collaborate/problem solve | Force/direct | Smooth/accommodate | Compromise/reconcile |  | B | The project manager applied the force/direct conflict resolution technique. In this approach, one party imposes their solution on the other without considering the other party's views or interests. The PM simply told the team member what to do and expected compliance, without engaging in discussion about the reasons or consequences of the behavior. Collaborate/problem solve (A) would involve a two-way discussion. Smooth/accommodate (C) would prioritize harmony over the issue. Compromise/reconcile (D) would involve both parties making concessions. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀원이 항상 늦게 출근한다. 프로젝트 관리자는 이것이 다른 팀원들의 동기에 영향을 미칠 수 있다고 우려한다. 프로젝트 관리자는 새 팀원에게 팀의 원칙에 맞추어 제시간에 출근하라고 말한다. 이 상황에서 프로젝트 관리자는 어떤 갈등 해결 방식을 적용했는가? | 협력/문제 해결 | 강제/지시 | 완화/수용 | 타협/조정 |  | B | 프로젝트 관리자는 강제/지시 갈등 해결 기법을 적용했다. 이 접근 방식에서는 한쪽이 상대방의 관점이나 이해를 고려하지 않고 자신의 해결책을 부과한다. PM은 단순히 팀원에게 무엇을 해야 하는지 말하고 행동의 이유나 결과에 대한 논의 없이 준수를 기대했다. 협력/문제 해결(A)은 양방향 논의를 포함한다. 완화/수용(C)은 이슈보다 조화를 우선시한다. 타협/조정(D)은 양측이 양보하는 것을 포함한다.
931 | An organization is transitioning to an agile environment. The project manager finds that most of the team members are not familiar with an agile environment. What should the project manager do to address this concern? | Analyze the level of the team ' s agile maturity. | Change the approach with the team. | Support the team members ' growth and development. | Meet with an agile coach to handle this issue. |  | C | When most team members are unfamiliar with agile during an organizational transition, the project manager should support the team members' growth and development. This involves providing training, guidance, and resources to build agile competencies. Analyzing agile maturity (A) assesses but does not address the gap. Changing the approach (B) abandons the transition. Meeting with an agile coach (D) is helpful but less direct than actively supporting team development. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 조직이 애자일 환경으로 전환하고 있다. 프로젝트 관리자는 대부분의 팀원이 애자일 환경에 익숙하지 않음을 발견한다. 프로젝트 관리자는 이 우려를 해결하기 위해 무엇을 해야 하는가? | 팀의 애자일 성숙도 수준을 분석한다. | 팀과 함께 접근 방식을 변경한다. | 팀원들의 성장과 발전을 지원한다. | 이 이슈를 처리하기 위해 애자일 코치와 만난다. |  | C | 조직의 애자일 전환 중 대부분의 팀원이 애자일에 익숙하지 않을 때, 프로젝트 관리자는 팀원들의 성장과 발전을 지원해야 한다. 이는 교육, 지도, 자원을 제공하여 애자일 역량을 구축하는 것을 포함한다. 애자일 성숙도 분석(A)은 평가하지만 격차를 해결하지 않는다. 접근 방식 변경(B)은 전환을 포기한다. 애자일 코치와 만나기(D)는 도움이 되지만 적극적으로 팀 발전을 지원하는 것보다 덜 직접적이다.
932 | A project manager is assigned to a new marketing campaign. The sponsor gives the project manager an approved project management plan for review and explains the scope, business requirements, deliverables, and stakeholders. The project manager asks to see the project charter to gain a better understanding of the project. The sponsor says the project is small and simple so there is no need for a project charter. What should the project manager do? | Explain that a project charter is necessary to ensure agreement on scope and deliverables 1176 and to define the project manager ' s responsibilities | Agree that the project does not require a project charter, especially since the deliverables and milestones are included in the project management plan | Speak with peers about the need for a project charter | Develop the project charter and send it for approval |  | A | When the sponsor says no project charter is needed because the project is small and simple, the project manager should explain that a charter is necessary to ensure agreement on scope and deliverables and to define the PM's responsibilities. The charter authorizes the project formally. Agreeing no charter is needed (B) accepts risk. Speaking with peers (C) is indirect. Developing the charter and sending for approval (D) acts without stakeholder alignment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 관리자가 새로운 마케팅 캠페인에 배정되었다. 스폰서가 프로젝트 관리자에게 검토를 위한 승인된 프로젝트 관리 계획을 제공하고 범위, 비즈니스 요구사항, 산출물, 이해관계자를 설명한다. 프로젝트 관리자는 프로젝트를 더 잘 이해하기 위해 프로젝트 헌장을 보여달라고 요청한다. 스폰서는 프로젝트가 작고 단순하므로 프로젝트 헌장이 필요 없다고 말한다. 프로젝트 관리자는 무엇을 해야 하는가? | 범위와 산출물에 대한 합의를 보장하고 프로젝트 관리자의 책임을 정의하기 위해 프로젝트 헌장이 필요하다고 설명한다. | 특히 산출물과 마일스톤이 프로젝트 관리 계획에 포함되어 있으므로 프로젝트에 프로젝트 헌장이 필요하지 않다는 데 동의한다. | 프로젝트 헌장의 필요성에 대해 동료들과 이야기한다. | 프로젝트 헌장을 개발하고 승인을 위해 제출한다. |  | A | 스폰서가 프로젝트가 작고 단순하므로 헌장이 필요 없다고 말할 때, 프로젝트 관리자는 범위와 산출물에 대한 합의를 보장하고 PM의 책임을 정의하기 위해 헌장이 필요하다고 설명해야 한다. 헌장은 프로젝트를 공식적으로 승인한다. 헌장이 필요 없다는 데 동의(B)는 리스크를 수용한다. 동료와 이야기(C)는 간접적이다. 헌장을 개발하여 승인 요청(D)은 이해관계자 정렬 없이 행동한다.
933 | A project manager is leading a project that is implementing an assembly line. During the quality review meeting, a team member reports an issue stating that the product being developed has discrepancies with the one requested by the customer. What should the project manager do? | Make a proposal of new specifications and submit it to the customer for approval. | Check that the product meets the requirements established by the customer. | Ensure the current solution is in place to enable future usability. | Run a root cause analysis to identify the quality breach and update the qualitymanagement plan. |  | D | When a team member reports that the product being developed has discrepancies with customer requirements, the project manager should run a root cause analysis to identify the quality breach and update the quality management plan. Root cause analysis determines why the deviation occurred and enables corrective actions to prevent recurrence. Proposing new specifications to the customer (A) assumes the original requirements were wrong without investigation. Checking that the product meets requirements (B) confirms the problem but does not address why it occurred. Ensuring the current solution enables future usability (C) sidesteps the immediate quality issue entirely. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 관리자가 조립 라인을 구현하는 프로젝트를 이끌고 있다. 품질 검토 회의 중 팀원이 개발 중인 제품이 고객이 요청한 것과 불일치한다는 이슈를 보고한다. 프로젝트 관리자는 무엇을 해야 하는가? | 새로운 사양을 제안하고 고객에게 승인을 위해 제출한다. | 제품이 고객이 수립한 요구사항을 충족하는지 확인한다. | 향후 사용성을 가능하게 하기 위해 현재 솔루션이 적절히 작동하는지 확인한다. | 근본 원인 분석을 수행하여 품질 위반을 식별하고 품질 관리 계획을 업데이트한다. |  | D | 팀원이 개발 중인 제품이 고객 요구사항과 불일치한다고 보고할 때, 프로젝트 관리자는 근본 원인 분석을 수행하여 품질 위반을 식별하고 품질 관리 계획을 업데이트해야 한다. 근본 원인 분석은 편차가 발생한 이유를 파악하고 재발 방지를 위한 시정 조치를 가능하게 한다. 고객에게 새 사양 제안(A)은 조사 없이 원래 요구사항이 잘못되었다고 가정한다. 제품이 요구사항을 충족하는지 확인(B)은 문제를 확인하지만 원인을 다루지 않는다. 현재 솔루션의 향후 사용성 확인(C)은 즉각적인 품질 이슈를 완전히 회피한다.
934 | A project manager is nearing completion of an automation project. One of the key stakeholders requests a meeting to discuss some new ideas that would make the project even more appealing to end users. As a result, the stakeholder suggests that the project manager does not close the project. What should the project manager do first? | Add it to the issue log as an ongoing issue. | Add a risk to the risk register. | Update the project charter with the new requirement. | Review and validate the scope management plan. |  | D | When a stakeholder requests new ideas near project completion and suggests not closing the project, the project manager should first review and validate the scope management plan. The scope management plan defines how scope changes are managed. Adding to the issue log (A) does not address scope governance. Adding a risk to the register (B) is not the primary concern. Updating the project charter (C) is inappropriate for scope changes late in the project. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Change Management | Process | Plan and Optimize Quality | Scope | Closing | Embed Quality | Close Project or Phase | Traditional PM | 프로젝트 관리자가 자동화 프로젝트 완료에 가까워지고 있다. 주요 이해관계자 중 한 명이 최종 사용자에게 프로젝트를 더 매력적으로 만들 새로운 아이디어를 논의하기 위한 회의를 요청한다. 그 결과, 이해관계자는 프로젝트 관리자에게 프로젝트를 종료하지 말 것을 제안한다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 진행 중인 이슈로 이슈 로그에 추가한다. | 리스크 레지스터에 리스크를 추가한다. | 새로운 요구사항으로 프로젝트 헌장을 업데이트한다. | 범위 관리 계획을 검토하고 검증한다. |  | D | 이해관계자가 프로젝트 완료 근처에서 새로운 아이디어를 요청하고 프로젝트를 종료하지 말 것을 제안할 때, 프로젝트 관리자는 먼저 범위 관리 계획을 검토하고 검증해야 한다. 범위 관리 계획은 범위 변경이 어떻게 관리되는지를 정의한다. 이슈 로그에 추가(A)는 범위 거버넌스를 다루지 않는다. 리스크 레지스터에 추가(B)는 주요 관심사가 아니다. 프로젝트 헌장 업데이트(C)는 프로젝트 후반의 범위 변경에 부적절하다.
935 | During the design phase of a project, the project manager notices that the schedule performance index (SPI) is 1.8 and the cost performance index (CPI) is 0.1. In a weekly meeting with top management, the project manager reports concerns about these indicators. However, the most concerned person was the project sponsor who said that if the trend continues, they will be forced to prematurely close the project. What should the project manager do? | Monitor the project sponsor but understand that it is normal to spend more money in the design phase of a project. | Manage the project sponsor closely and revise the project ' s resource management plan to improve indicators | Use a resource-levelling technique | Stop crashing the schedule |  | B | With an SPI of 1.8 (significantly ahead of schedule) and CPI of 0.1 (massively over budget), the project is spending resources far faster than planned. The project manager should manage the sponsor closely and revise the project's resource management plan to improve indicators. This involves transparent communication about cost overruns, identifying cost reduction strategies, and optimizing resource allocation. Assuming higher design-phase spending is normal (A) ignores the severity of CPI = 0.1. Using resource leveling (C) may delay the project. Stopping schedule crashing (D) may help costs but should be part of a comprehensive resource management review. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Finance | Closing | Embed Quality | Close Project or Phase | Traditional PM | 프로젝트 설계 단계에서 프로젝트 관리자가 일정 성과 지수(SPI)가 1.8이고 비용 성과 지수(CPI)가 0.1임을 발견한다. 최고 경영진과의 주간 회의에서 프로젝트 관리자가 이러한 지표에 대한 우려를 보고한다. 그러나 가장 우려한 사람은 프로젝트 스폰서로, 추세가 계속되면 프로젝트를 조기 종료할 수밖에 없다고 말했다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서를 모니터링하되 설계 단계에서 더 많은 비용을 지출하는 것은 정상이라고 이해한다. | 프로젝트 스폰서를 면밀히 관리하고 지표를 개선하기 위해 프로젝트의 자원 관리 계획을 수정한다. | 자원 평준화 기법을 사용한다. | 일정 크래싱을 중단한다. |  | B | SPI가 1.8(일정보다 크게 앞서는)이고 CPI가 0.1(예산을 대폭 초과하는) 상태에서, 프로젝트는 계획보다 훨씬 빠르게 자원을 소비하고 있다. 프로젝트 관리자는 스폰서를 면밀히 관리하고 지표를 개선하기 위해 자원 관리 계획을 수정해야 한다. 이는 비용 초과에 대한 투명한 소통, 비용 절감 전략 식별, 자원 배분 최적화를 포함한다. 설계 단계에서 더 높은 지출이 정상이라고 가정(A)은 CPI 0.1의 심각성을 무시한다. 자원 평준화(C)는 프로젝트를 지연시킬 수 있다. 크래싱 중단(D)은 비용에 도움이 될 수 있지만 포괄적인 자원 관리 검토의 일부여야 한다.
936 | A project team is executing a megaproject, and several contract requirements have been identified. In the planning phase, the project team agreed that a contract would be required 3 months prior to the project's finish date. During project execution, it was determined that the contract was required immediately. What should the project manager do? | Challenge the project team to identify the reasons for early contract execution. | Request the team to initiate a change request to execute the contract. | Support the team ' s request and allow for early contract execution. | Seek management ' s approval for executing the contract earlier than planned. |  | B | When a contract planned for 3 months before the finish date is suddenly needed immediately, the project manager should request the team to initiate a change request. Formal change control ensures proper documentation and stakeholder awareness. Challenging the team to identify reasons (A) delays action. Supporting early execution without a change request (C) bypasses governance. Seeking management approval (D) does not follow the integrated change control process. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 메가프로젝트를 실행 중이며, 여러 계약 요구사항이 식별되었다. 계획 단계에서 프로젝트 팀은 프로젝트 완료 3개월 전에 계약이 필요할 것이라고 합의했다. 프로젝트 실행 중 계약이 즉시 필요하다고 판단되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 팀에게 조기 계약 실행의 이유를 식별하도록 도전한다. | 팀에게 계약을 실행하기 위한 변경 요청을 개시하도록 요청한다. | 팀의 요청을 지원하고 조기 계약 실행을 허용한다. | 계획보다 일찍 계약을 실행하기 위해 경영진의 승인을 구한다. |  | B | 완료 3개월 전으로 계획된 계약이 갑자기 즉시 필요할 때, 프로젝트 관리자는 팀에게 변경 요청을 개시하도록 요청해야 한다. 공식적인 변경 통제는 적절한 문서화와 이해관계자 인식을 보장한다. 팀에게 이유 식별 도전(A)은 조치를 지연시킨다. 변경 요청 없이 조기 실행 지원(C)은 거버넌스를 우회한다. 경영진 승인 요청(D)은 통합 변경 통제 프로세스를 따르지 않는다.
937 | A project team wants to change a delivery approach for a project. Team members explain the need for a review of the information-sharing approach to ensure efficient information exchange during the project. What should the project manager do? | Ask the project sponsor to approve funding for a collaboration tool. | Review the communications management plan with the project team. | Review the stakeholder engagement plan with the project team. | Ask the project sponsor to decide on the best communication strategy. |  | B | The correct answer is B. Review the communications management plan with the project team. Resource management includes ensuring team members have the necessary skills and support. The PM should identify gaps and address them through training, mentoring, or other appropriate measures. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 프로젝트의 전달 접근 방식을 변경하고자 한다. 팀원들이 프로젝트 중 효율적인 정보 교환을 보장하기 위해 정보 공유 접근 방식의 검토가 필요하다고 설명한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서에게 협업 도구에 대한 자금 승인을 요청한다. | 프로젝트 팀과 커뮤니케이션 관리 계획을 검토한다. | 프로젝트 팀과 이해관계자 참여 계획을 검토한다. | 프로젝트 스폰서에게 최적의 커뮤니케이션 전략을 결정하도록 요청한다. |  | B | 정답은 B이다. 프로젝트 팀과 커뮤니케이션 관리 계획을 검토한다. 자원 관리에는 팀원들이 필요한 기술과 지원을 갖추도록 보장하는 것이 포함된다. PM은 격차를 식별하고 교육, 멘토링 또는 기타 적절한 조치를 통해 해결해야 한다.
938 | A project team is executing a large regulatory project comprised of a multitude of internal and external stakeholders. An initial impact analysis revealed several systems, including an enhancement to existing modules as well as new builds. After completion of the initial design workshop, the team conducted a brainstorming session to better understand the types of likely users. Which technique will best serve this purpose? | Salience model | Personas | Power influence grid | Power user grid |  | B | When a team needs to understand the types of likely users for a regulatory project after an initial design workshop, the personas technique best serves this purpose. Personas create fictional user profiles based on real behaviors and motivations, enabling user-centered design. The salience model (A) classifies stakeholders by power, urgency, and legitimacy. The power influence grid (C) maps stakeholder influence. The power user grid (D) is not a standard technique. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 팀이 다수의 내부 및 외부 이해관계자로 구성된 대규모 규제 프로젝트를 실행하고 있다. 초기 영향 분석에서 기존 모듈의 개선과 신규 구축을 포함하여 여러 시스템이 밝혀졌다. 초기 설계 워크숍 완료 후 팀이 예상 사용자 유형을 더 잘 이해하기 위해 브레인스토밍 세션을 수행했다. 이 목적에 가장 적합한 기법은? | 현저성 모델(Salience model) | 페르소나(Personas) | 권력 영향력 그리드(Power influence grid) | 파워 유저 그리드(Power user grid) |  | B | 초기 설계 워크숍 후 규제 프로젝트의 예상 사용자 유형을 이해해야 할 때, 페르소나(Personas) 기법이 가장 적합하다. 페르소나는 실제 행동과 동기에 기반한 가상의 사용자 프로필을 생성하여 사용자 중심 설계를 가능하게 한다. 현저성 모델(A)은 권력, 긴급성, 정당성으로 이해관계자를 분류한다. 권력 영향력 그리드(C)는 이해관계자 영향력을 매핑한다. 파워 유저 그리드(D)는 표준 기법이 아니다.
939 | A team is having a hard time completing work due to unclear requirements. They have not been able to complete an iteration successfully in several months. In order to help the team, what should the project leader do? | Recommend a review of the team members' individual performances. | Recommend that the product owner reviews the backlog refinement processes. | Recommend limiting the work in progress to improve the team's focus. | Recommend that the team reviews the length of the iteration with the stakeholders. |  | B | When a team has not completed an iteration successfully in months due to unclear requirements, the project leader should recommend that the product owner reviews the backlog refinement processes. Better backlog refinement produces clearer requirements. Reviewing individual performances (A) blames team members rather than the process. Limiting work in progress (C) improves focus but does not clarify requirements. Reviewing iteration length with stakeholders (D) changes timing, not clarity. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 팀이 불명확한 요구사항으로 인해 작업 완료에 어려움을 겪고 있다. 수개월 동안 이터레이션을 성공적으로 완료하지 못했다. 팀을 돕기 위해 프로젝트 리더는 무엇을 해야 하는가? | 팀원들의 개인 성과를 검토하도록 권장한다. | 제품 책임자에게 백로그 정제 프로세스를 검토하도록 권장한다. | 팀의 집중력을 향상시키기 위해 진행 중인 작업(WIP)을 제한하도록 권장한다. | 팀이 이해관계자와 함께 이터레이션 기간을 검토하도록 권장한다. |  | B | 불명확한 요구사항으로 인해 팀이 수개월간 이터레이션을 성공적으로 완료하지 못할 때, 프로젝트 리더는 제품 책임자에게 백로그 정제 프로세스를 검토하도록 권장해야 한다. 더 나은 백로그 정제는 더 명확한 요구사항을 생성한다. 개인 성과 검토(A)는 프로세스가 아닌 팀원을 탓한다. WIP 제한(C)은 집중력을 향상시키지만 요구사항을 명확히 하지는 않는다. 이터레이션 기간 검토(D)는 시간을 변경하지 명확성은 변경하지 않는다.
940 | A project manager encounters a governance issue during the project execution phase. One of the team members complains about receiving assignments from multiple people and states they are not able to work effectively. What should the project manager establish first in the project governance structure? | Risk management and issues resolution plan | Resource management and conflict resolution plan | Clear project work breakdown structure (WBS) and timeline | Clear responsible, accountable, consult, and inform (RACI) matrix |  | D | When a team member receives assignments from multiple people and cannot work effectively, the project manager should first establish a clear RACI matrix. The RACI matrix defines who is responsible, accountable, consulted, and informed for each task, eliminating role confusion. A risk management plan (A) addresses project risks, not role clarity. A resource management plan (B) covers staffing but not task accountability. A WBS and timeline (C) define work structure, not reporting lines. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 프로젝트 관리자가 프로젝트 실행 단계에서 거버넌스 이슈를 발견한다. 팀원 중 한 명이 여러 사람으로부터 업무를 받고 있어 효과적으로 일할 수 없다고 불만을 제기한다. 프로젝트 관리자는 프로젝트 거버넌스 구조에서 먼저 무엇을 수립해야 하는가? | 리스크 관리 및 이슈 해결 계획 | 자원 관리 및 갈등 해결 계획 | 명확한 프로젝트 작업 분류 체계(WBS) 및 일정 | 명확한 책임 배정 매트릭스(RACI) |  | D | 팀원이 여러 사람으로부터 업무를 받아 효과적으로 일할 수 없을 때, 프로젝트 관리자는 먼저 명확한 RACI 매트릭스를 수립해야 한다. RACI 매트릭스는 각 작업에 대해 누가 책임지고, 승인하고, 자문하고, 통보받는지를 정의하여 역할 혼란을 제거한다. 리스크 관리 계획(A)은 프로젝트 리스크를 다루지 역할 명확성은 다루지 않는다. 자원 관리 계획(B)은 인력 배치를 다루지만 작업 책임은 다루지 않는다. WBS와 일정(C)은 작업 구조를 정의하지 보고 체계는 정의하지 않는다.
941 | A project manager has just been hired by a company without a project management governance structure. During the kick-off meeting, a key stakeholder emphasizes the importance of the project meeting the company's strategy, investment, and compliance requirements. What should the project manager do? | Create an organizational project management governance. | Put into place a project governance model in line with the requirements. | Ask the organization to create a project portfolio governance. | Replicate the organizational governance to the project governance. |  | B | The PM should establish a project governance model aligned with the company's strategic, investment, and compliance requirements. This includes creating oversight structures, decision-making processes, and performance measurement frameworks tailored to the specific project while supporting the organization's broader governance needs. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Compliance | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 관리자가 프로젝트 관리 거버넌스 구조가 없는 회사에 채용되었다. 킥오프 미팅에서 주요 이해관계자가 프로젝트가 회사의 전략, 투자, 컴플라이언스 요구사항을 충족하는 것의 중요성을 강조한다. 프로젝트 관리자는 무엇을 해야 하는가? | 조직 프로젝트 관리 거버넌스를 생성한다. | 요구사항에 맞는 프로젝트 거버넌스 모델을 수립한다. | 조직에 프로젝트 포트폴리오 거버넌스를 생성하도록 요청한다. | 조직 거버넌스를 프로젝트 거버넌스에 복제한다. |  | B | PM은 회사의 전략, 투자, 컴플라이언스 요구사항에 맞는 프로젝트 거버넌스 모델을 수립해야 한다. 이는 특정 프로젝트에 맞춤화되면서 조직의 광범위한 거버넌스 요구를 지원하는 감독 구조, 의사결정 프로세스, 성과 측정 프레임워크를 만드는 것을 포함한다.
942 | A project manager is reviewing several potential changes to the contract with third-party vendors. Which two changes could trigger a modification to the vendor contractual obligations? (Choose 2) | Introducing additional requirements based on new regulations | Modifying a supplier ' s name due to a vendor acquisition | Adding vendors to increase flexibility and availability of work crews | Adding new resources to the change control team | Replacing a material type based on product availability | A, E | Changes that could trigger modifications to vendor contractual obligations include (A) introducing additional requirements based on new regulations and (E) replacing a material type based on product availability. Both alter the scope, specifications, or deliverables under the contract. Adding vendors (C) affects resource planning, not existing obligations. Modifying a supplier's name due to acquisition (B) is administrative. Adding resources to the change control team (D) is an internal governance change. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Change Management | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 관리자가 제3자 벤더와의 계약에 대한 여러 잠재적 변경을 검토하고 있다. 벤더의 계약 의무 변경을 촉발할 수 있는 두 가지 변경은 무엇인가? (2개 선택) | 새로운 규정에 기반한 추가 요구사항 도입 | 벤더 인수로 인한 공급업체 명칭 변경 | 작업 인력의 유연성과 가용성을 높이기 위한 벤더 추가 | 변경 통제 팀에 새로운 자원 추가 | 제품 가용성에 기반한 자재 유형 교체 | A, E | 벤더 계약 의무 변경을 촉발할 수 있는 변경은 (A) 새로운 규정에 기반한 추가 요구사항 도입과 (E) 제품 가용성에 기반한 자재 유형 교체이다. 둘 다 계약 범위, 사양 또는 산출물을 변경한다. 벤더 추가(C)는 자원 계획에 영향을 미치지 기존 의무는 아니다. 인수로 인한 공급업체 명칭 변경(B)은 행정적이다. 변경 통제 팀에 자원 추가(D)는 내부 거버넌스 변경이다.
943 | A major issue about conflicting priorities has been highlighted by the project team with regard to a few stakeholder requirements. What should the project manager do? | Prioritize other items for the team and deal with the conflicting requirements later. | Escalate to the project management office (PMO) and request a solution for the requirements. | Allow the project team to decide what is the most appropriate requirement to follow. | Negotiate a common agreement with the involved stakeholders regarding the requirements. |  | D | When conflicting stakeholder requirements create a major priority issue, the project manager should negotiate a common agreement with the involved stakeholders regarding the requirements. Collaborative negotiation ensures all stakeholder needs are understood and a solution aligned with project objectives is reached. Prioritizing other items and deferring the conflict (A) avoids the issue. Escalating to the PMO (B) delegates resolution externally. Allowing the team to decide (C) puts the team in a stakeholder management role they may not be equipped for. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 몇몇 이해관계자 요구사항에 관해 상충하는 우선순위에 대한 주요 이슈가 프로젝트 팀에 의해 강조되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀을 위해 다른 항목의 우선순위를 정하고 상충하는 요구사항은 나중에 처리한다. | 프로젝트 관리 오피스(PMO)에 에스컬레이션하고 요구사항에 대한 해결책을 요청한다. | 프로젝트 팀이 가장 적절한 요구사항을 결정하도록 허용한다. | 관련 이해관계자와 요구사항에 대한 공통 합의를 협상한다. |  | D | 상충하는 이해관계자 요구사항이 주요 우선순위 이슈를 야기할 때, 프로젝트 관리자는 관련 이해관계자와 요구사항에 대한 공통 합의를 협상해야 한다. 협력적 협상은 모든 이해관계자의 요구를 이해하고 프로젝트 목표에 정렬된 해결책을 보장한다. 다른 항목 우선순위 지정 및 갈등 연기(A)는 이슈를 회피한다. PMO에 에스컬레이션(B)은 해결을 외부에 위임한다. 팀이 결정하도록 허용(C)은 팀을 이해관계자 관리 역할에 놓으며 적합하지 않을 수 있다.
944 | A project requires testing of the final product to be done at another department's testing facility, which is known for having low availability. This situation could potentially impact the project schedule. What should the project manager do next? | Update the project schedule. | Update the lessons learned register. | Update the issue log. | Update the risk register. |  | D | When the final product testing requires a facility with known low availability that could impact the schedule, the project manager should update the risk register. Documenting the potential schedule impact as a risk enables planned responses. Updating the project schedule (A) is premature without risk assessment. Updating the lessons learned register (B) is not applicable for a current risk. Updating the issue log (C) is inappropriate since the low availability has not yet materialized as an issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트에서 최종 제품의 테스트를 가용성이 낮은 것으로 알려진 다른 부서의 테스트 시설에서 수행해야 한다. 이 상황은 잠재적으로 프로젝트 일정에 영향을 미칠 수 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 프로젝트 일정을 업데이트한다. | 교훈 레지스터를 업데이트한다. | 이슈 로그를 업데이트한다. | 리스크 레지스터를 업데이트한다. |  | D | 최종 제품 테스트가 가용성이 낮아 일정에 영향을 줄 수 있는 시설을 요구할 때, 프로젝트 관리자는 리스크 레지스터를 업데이트해야 한다. 잠재적 일정 영향을 리스크로 문서화하면 계획된 대응이 가능해진다. 프로젝트 일정 업데이트(A)는 리스크 평가 없이 시기상조이다. 교훈 레지스터 업데이트(B)는 현재 리스크에 적용되지 않는다. 이슈 로그 업데이트(C)는 낮은 가용성이 아직 이슈로 실현되지 않았으므로 부적절하다.
945 | Midway into a project, the project manager is concerned with the lack of responsiveness from a vendor. What should the project manager do to ensure the project is delivered successfully? | Invite the vendor to a meeting to discuss the concerns. | Escalate the vendor ' s lack of responsiveness to the project sponsor. | Ask the vendor to communicate via the established channels. | Proceed with other tasks while awaiting a response from the vendor. |  | A | When a vendor is unresponsive midway through a project, the project manager should invite the vendor to a meeting to discuss the concerns. Direct, proactive communication addresses the issue collaboratively and identifies root causes of unresponsiveness. Escalating to the project sponsor (B) bypasses direct engagement. Asking the vendor to use established channels (C) addresses communication method but not the responsiveness issue. Proceeding with other tasks (D) avoids the problem. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 중간에 프로젝트 관리자가 벤더의 응답 부족에 우려하고 있다. 프로젝트가 성공적으로 전달되도록 프로젝트 관리자는 무엇을 해야 하는가? | 벤더를 회의에 초대하여 우려를 논의한다. | 벤더의 응답 부족을 프로젝트 스폰서에게 에스컬레이션한다. | 벤더에게 확립된 채널을 통해 커뮤니케이션하도록 요청한다. | 벤더의 응답을 기다리며 다른 작업을 진행한다. |  | A | 벤더가 프로젝트 중간에 응답하지 않을 때, 프로젝트 관리자는 벤더를 회의에 초대하여 우려를 논의해야 한다. 직접적이고 사전 예방적인 커뮤니케이션이 협력적으로 이슈를 해결하고 응답 부족의 근본 원인을 파악한다. 프로젝트 스폰서에게 에스컬레이션(B)은 직접적 참여를 우회한다. 확립된 채널 사용 요청(C)은 커뮤니케이션 방법을 다루지만 응답성 문제는 다루지 않는다. 다른 작업 진행(D)은 문제를 회피한다.
946 | Some of the more experienced members of a project team have complained about the project manager. The senior project team members feel that the project manager is micromanaging them and preventing them from completing their work. What should the project manager do when made aware of these issues? | Meet daily with each senior team member to monitor project status. | Ask for advice on how to be a better mentor to these team members. | Adjust the project manager ' s management style to better fit senior team members. | Set up a team building event to bring synergy back to the project team. |  | C | When experienced senior team members complain about being micromanaged, the project manager should adjust their management style to better fit senior team members. Adapting leadership to team maturity improves collaboration. Meeting daily with each member (A) reinforces micromanagement. Asking for mentoring advice (B) does not address the issue. Team-building events (D) improve morale but do not change management style. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Resources | Executing | Embed Quality | Develop Team | Traditional PM | 프로젝트 팀의 경험 많은 선임 멤버 일부가 프로젝트 관리자에 대해 불만을 제기했다. 선임 프로젝트 팀원들은 프로젝트 관리자가 그들을 마이크로매니징하여 업무 완수를 방해한다고 느낀다. 프로젝트 관리자는 이러한 문제를 인지했을 때 무엇을 해야 하는가? | 프로젝트 상태를 모니터링하기 위해 매일 각 선임 팀원과 만난다. | 이 팀원들에게 더 나은 멘토가 되는 방법에 대한 조언을 구한다. | 선임 팀원에게 더 적합하도록 프로젝트 관리자의 관리 스타일을 조정한다. | 프로젝트에 시너지를 되찾기 위해 팀 빌딩 이벤트를 설정한다. |  | C | 경험 많은 선임 팀원들이 마이크로매니징에 대해 불만을 제기할 때, 프로젝트 관리자는 선임 팀원에게 더 적합하도록 관리 스타일을 조정해야 한다. 팀 성숙도에 맞게 리더십을 적응시키면 협업이 개선된다. 매일 각 멤버와 만남(A)은 마이크로매니징을 강화한다. 멘토링 조언 요청(B)은 이슈를 해결하지 않는다. 팀 빌딩 이벤트(D)는 사기를 개선하지만 관리 스타일을 변경하지 않는다.
947 | A new project manager is assigned to a project that will deliver a new and optimized credit system. The project manager is allowed to use a hybrid approach, which is new to the organization, to manage the project and new tools. In order to deliver the project successfully, what should the project manager focus on as part of the plan? | Align with the organization ' s project management office (PMO) to inform and make them aware of the new approach | Communicate with other project managers to see how they manage hybrid projects | Develop a detailed schedule for the entire project m the planning phase and communicate that to the stakeholders | Explain and communicate the new approach to the project sponsor and key stakeholders |  | D | When introducing a new approach—particularly in hybrid environments—it is essential to ensure all key stakeholders, including the project sponsor, understand and support it. Explaining and communicating the approach proactively prevents misunderstandings and conflicts later. This aligns with PMI's emphasis on effective communication as a critical success factor in project management. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Hybrid/Tailoring | 새로운 프로젝트 관리자가 새롭고 최적화된 신용 시스템을 전달할 프로젝트에 배정되었다. 프로젝트 관리자는 조직에 새로운 하이브리드 접근 방식과 새로운 도구를 사용하여 프로젝트를 관리할 수 있다. 프로젝트를 성공적으로 전달하기 위해, 프로젝트 관리자는 계획의 일부로 무엇에 집중해야 하는가? | 조직의 프로젝트 관리 오피스(PMO)와 정렬하여 새로운 접근 방식을 알리고 인식시킨다. | 다른 프로젝트 관리자와 소통하여 그들이 하이브리드 프로젝트를 어떻게 관리하는지 확인한다. | 기획 단계에서 전체 프로젝트에 대한 상세 일정을 개발하고 이해관계자에게 전달한다. | 프로젝트 스폰서 및 주요 이해관계자에게 새로운 접근 방식을 설명하고 전달한다. |  | D | 특히 하이브리드 환경에서 새로운 접근 방식을 도입할 때, 프로젝트 스폰서를 포함한 모든 주요 이해관계자가 이를 이해하고 지원하도록 하는 것이 필수적이다. 접근 방식을 사전에 설명하고 전달하면 나중에 오해와 갈등을 방지한다. 이는 PMI가 프로젝트 관리에서 효과적인 커뮤니케이션을 핵심 성공 요인으로 강조하는 것과 일치한다.
948 | A project manager is assigned to lead a design for a new version of an existing product with the technology and operations teams. The project manager organizes a joint requirements session to determine the most practical ideas. The project manager was advised that the session may become chaotic. What should the project manager do to ensure the session is interactive, productive, and efficient? | Distribute a questionnaire on the key features of the product and encourage the teamsto respond with their design recommendations. | Hold multiple sessions of manageable sizes with participants from both teams todiscuss their ideas. | Pick the senior and experienced staff members from both teams and arrange face-toface interviews. | Organize a formal session led by a skilled facilitator with defined rules for howparticipants will interact with one another. |  | D | When organizing a joint requirements session between technology and operations teams that may become chaotic, the project manager should organize a formal session led by a skilled facilitator with defined interaction rules. Structured facilitation ensures productive outcomes. Distributing a questionnaire (A) lacks interaction. Holding multiple smaller sessions (B) may miss cross-team discussions. Picking senior staff for interviews (C) excludes broader input. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 기술 및 운영 팀과 함께 기존 제품의 새 버전 설계를 이끌도록 배정되었다. 프로젝트 관리자는 가장 실용적인 아이디어를 도출하기 위해 공동 요구사항 세션을 조직한다. 프로젝트 관리자는 세션이 혼란스러워질 수 있다는 조언을 받았다. 세션이 상호작용적이고 생산적이며 효율적이 되도록 프로젝트 관리자는 무엇을 해야 하는가? | 제품의 핵심 기능에 대한 설문지를 배포하고 팀에게 설계 권장 사항으로 응답하도록 독려한다. | 양 팀의 참가자와 함께 관리 가능한 규모의 여러 세션을 개최하여 아이디어를 논의한다. | 양 팀의 선임 및 경험 있는 직원을 선별하여 대면 인터뷰를 준비한다. | 참가자 간 상호작용 규칙이 정의된 숙련된 퍼실리테이터가 이끄는 공식 세션을 조직한다. |  | D | 기술 및 운영 팀 간 공동 요구사항 세션이 혼란스러워질 수 있을 때, 프로젝트 관리자는 상호작용 규칙이 정의된 숙련된 퍼실리테이터가 이끄는 공식 세션을 조직해야 한다. 구조화된 퍼실리테이션이 생산적인 결과를 보장한다. 설문지 배포(A)는 상호작용이 부족하다. 여러 소규모 세션 개최(B)는 팀 간 논의를 놓칠 수 있다. 선임 직원 인터뷰 선별(C)은 더 넓은 입력을 배제한다.
949 | A key resource is newly assigned to a project. The project manager and the resource did not get along well in a previous project. This resource is needed to ensure the completion of a major component for the project. What should the project manager do? | Monitor the key resource closely throughout the project, but do not let the projectsponsor know about the conflict. | Discuss this with the project sponsor and request that this key resource be replaced onthe project. | Work on resolving the differences with the key resource and building a good workingrelationship to ensure project success. | Request that the key resource ' s functional manager work directly with the resourceduring the project. |  | C | The PM should use conflict management skills to resolve differences with the key resource and build a working relationship based on trust and respect. The manage team process includes tracking performance, providing feedback, and resolving issues. Monitoring without transparency (B) creates distrust. Involving the functional manager directly (C) may undermine PM authority. Requesting replacement (D) causes project disruption when the resource is essential. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 핵심 자원이 프로젝트에 새로 배정되었다. 프로젝트 관리자와 이 자원은 이전 프로젝트에서 잘 지내지 못했다. 이 자원은 프로젝트의 주요 구성요소 완료를 보장하기 위해 필요하다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 전반에 걸쳐 핵심 자원을 면밀히 모니터링하되, 프로젝트 스폰서에게 갈등에 대해 알리지 않는다. | 프로젝트 스폰서와 논의하고 이 핵심 자원을 프로젝트에서 교체하도록 요청한다. | 핵심 자원과의 차이를 해결하고 프로젝트 성공을 보장하기 위해 좋은 업무 관계를 구축한다. | 핵심 자원의 기능 관리자에게 프로젝트 기간 동안 자원과 직접 작업하도록 요청한다. |  | C | PM은 갈등 관리 기술을 사용하여 핵심 자원과의 차이를 해결하고 신뢰와 존중에 기반한 업무 관계를 구축해야 한다. 팀 관리 프로세스는 성과 추적, 피드백 제공, 이슈 해결을 포함한다. 투명성 없는 모니터링(B)은 불신을 만든다. 기능 관리자를 직접 참여시키기(C)는 PM 권한을 약화시킬 수 있다. 교체 요청(D)은 자원이 필수적일 때 프로젝트 혼란을 초래한다.
950 | In an agile environment, a project is running iteration four out of six. A team member leaves the company with no replacement. What should the project manager do? | Reduce the scope of the project and inform stakeholders. | Ask the sponsor for an experienced team member in the company to help the project team. | Ask the team for extra work to fulfill the project commitment. | Update the issue log and refer to the resource management plan to address the situation. |  | D | When a team member leaves an agile project with no replacement during iteration four of six, the project manager should update the issue log and refer to the resource management plan to address the situation. Documenting the issue and following the resource plan provides structured response. Reducing scope (A) is premature. Asking for extra work (C) may burn out the team. Asking the sponsor for a replacement (B) may follow but issue logging comes first. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 애자일 환경에서 프로젝트가 6번 중 4번째 이터레이션을 진행 중이다. 팀원이 대체 없이 회사를 떠난다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 범위를 축소하고 이해관계자에게 알린다. | 스폰서에게 프로젝트 팀을 도울 회사 내 경험 있는 팀원을 요청한다. | 팀에게 프로젝트 약속을 이행하기 위해 추가 작업을 요청한다. | 이슈 로그를 업데이트하고 상황을 해결하기 위해 자원 관리 계획을 참조한다. |  | D | 애자일 프로젝트에서 6번 중 4번째 이터레이션 중 대체 없이 팀원이 떠날 때, 프로젝트 관리자는 이슈 로그를 업데이트하고 상황을 해결하기 위해 자원 관리 계획을 참조해야 한다. 이슈를 문서화하고 자원 계획을 따르면 구조화된 대응이 가능하다. 범위 축소(A)는 시기상조이다. 추가 작업 요청(C)은 팀을 소진시킬 수 있다. 스폰서에게 대체 요청(B)은 이어질 수 있지만 이슈 기록이 먼저다.
951 | During a retrospective review, many project team members say they are not completing tasks during the iterations because of interruptions and requests for help from other teams. As a team facilitator, what should the project manager do to avoid this? | Hire a coach to help all project teams to improve their abilities to solve problems ontheir own. | Identify the problem ' s root causes and define the ground rules with all project team members to minimize interferences | Recommend to the project team members that they should improve their planningand make their stones smaller | Reunite with the project team members affected and tell them not to reduce the team ' s capacity |  | B | When team members cannot complete iteration tasks due to interruptions from other teams, the project manager should identify root causes and define ground rules with all team members to minimize interferences. Systemic solutions address the problem sustainably. Hiring a coach (A) is indirect and expensive. Recommending smaller stories (C) does not address external interruptions. Telling members not to reduce capacity (D) pressures without solving. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 회고 검토 중 많은 프로젝트 팀원들이 다른 팀의 방해와 도움 요청으로 인해 이터레이션 중 작업을 완료하지 못하고 있다고 말한다. 팀 퍼실리테이터로서, 프로젝트 관리자는 이를 방지하기 위해 무엇을 해야 하는가? | 모든 프로젝트 팀이 스스로 문제를 해결하는 능력을 향상시키도록 코치를 고용한다. | 문제의 근본 원인을 파악하고 방해를 최소화하기 위해 모든 프로젝트 팀원과 기본 규칙을 정의한다. | 프로젝트 팀원에게 계획을 개선하고 스토리를 더 작게 만들도록 권장한다. | 영향받는 프로젝트 팀원과 만나 팀의 역량을 축소하지 말라고 말한다. |  | B | 팀원들이 다른 팀의 방해로 이터레이션 작업을 완료하지 못할 때, 프로젝트 관리자는 근본 원인을 파악하고 모든 팀원과 기본 규칙을 정의하여 방해를 최소화해야 한다. 체계적 해결책이 문제를 지속 가능하게 해결한다. 코치 고용(A)은 간접적이고 비용이 많이 든다. 더 작은 스토리 권장(C)은 외부 방해를 해결하지 않는다. 역량 축소하지 말라고 말하기(D)는 해결 없이 압박한다.
952 | A hybrid project has just started, which will result in a new technology that could disrupt the market if well accepted by the public. The product requires health and safety approvals from the government. As this is an innovative solution, the sponsor and product owner are unsure if it will be accepted by the public. What is the appropriate flow for product development? | Complete development with all functionalities in perfect condition prior to demonstrating to stakeholders to ensure a great first impression. | Complete development for the must-have functionalities only prior to demonstration in order to fail fast and get early feedback. | Complete development for each sprint and demonstrate the product increment to internal stakeholders and the government, without engaging other externalstakeholders. | Complete development for must-have functionalities only and demonstrate it to a focus group, but wait until all development is complete to demonstrate it to thegovernment. |  | B | For innovative technology requiring government approval with uncertain public acceptance, the PM should prioritize developing must-have functionalities first. This enables early testing of core capabilities, faster feedback collection, and necessary adjustments before further investment. This approach aligns with hybrid and agile principles of early, continuous delivery of valuable increments. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Hybrid/Tailoring | 하이브리드 프로젝트가 막 시작되었으며, 대중에게 잘 수용되면 시장을 교란할 수 있는 새로운 기술을 결과물로 낳게 된다. 제품은 정부의 보건 및 안전 승인이 필요하다. 혁신적인 솔루션이므로 스폰서와 제품 책임자는 대중에게 수용될지 확신하지 못한다. 제품 개발에 적합한 흐름은 무엇인가? | 모든 기능이 완벽한 상태로 개발을 완료한 후 이해관계자에게 시연하여 훌륭한 첫인상을 보장한다. | 필수 기능만 개발을 완료한 후 시연하여 빠르게 실패하고 조기 피드백을 받는다. | 각 스프린트의 개발을 완료하고 내부 이해관계자와 정부에 제품 증분을 시연하되, 다른 외부 이해관계자는 참여시키지 않는다. | 필수 기능만 개발을 완료하고 포커스 그룹에 시연하되, 모든 개발이 완료될 때까지 정부에 시연하는 것은 기다린다. |  | B | 정부 승인이 필요하고 대중 수용이 불확실한 혁신 기술의 경우, PM은 필수 기능만 먼저 개발하는 것을 우선시해야 한다. 이를 통해 핵심 역량의 조기 테스트, 더 빠른 피드백 수집, 추가 투자 전 필요한 조정이 가능하다. 이 접근 방식은 가치 있는 증분의 조기 지속적 전달이라는 하이브리드 및 애자일 원칙에 부합한다.
953 | A project manager has received a new request to integrate more features to a product. The team is fully allocated, and there is no budget to acquire new resources. What strategy should the project manager implement to deal with this situation? | Verify team performance and ask for improvement during daily standup meetings. | Discuss the problem with the team and decide how to do the work together. | Recommend that the project sponsor increases the budget to bring new resources. | Ask the team.to accelerate the iterations and avoid interruptions. |  | B | When a new feature integration request comes with a fully allocated team and no budget for new resources, the project manager should discuss the problem with the team and decide how to do the work together. Collaborative problem-solving leverages existing capacity. Verifying performance in standups (A) is indirect. Recommending budget increases (C) contradicts the constraint. Accelerating iterations (D) risks quality and burnout. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Integrate Sustainability | Plan Scope Management | Sustainability | 프로젝트 관리자가 제품에 더 많은 기능을 통합하라는 새로운 요청을 받았다. 팀은 완전히 배정되어 있으며 새 자원을 확보할 예산이 없다. 프로젝트 관리자는 이 상황에 대처하기 위해 어떤 전략을 구현해야 하는가? | 팀 성과를 확인하고 일일 스탠드업 회의에서 개선을 요청한다. | 팀과 문제를 논의하고 함께 작업을 수행하는 방법을 결정한다. | 프로젝트 스폰서에게 새 자원을 확보하기 위해 예산을 늘리도록 권고한다. | 팀에게 반복을 가속화하고 중단을 피하도록 요청한다. |  | B | 새로운 기능 통합 요청이 완전히 배정된 팀과 새 자원 예산 없이 들어올 때, 프로젝트 관리자는 팀과 문제를 논의하고 함께 작업 방법을 결정해야 한다. 협력적 문제 해결은 기존 역량을 활용한다. 스탠드업에서 성과 확인(A)은 간접적이다. 예산 증가 권고(C)는 제약 조건에 반한다. 반복 가속화(D)는 품질과 번아웃을 위험에 빠뜨린다.
954 | A project is almost complete when a key stakeholder raises a concern because the functionality of their preferred requirement was not showcased in the prototype. The prototype has already been approved and developers have started work on the final application. What should the project manager do next? | Document the stakeholder ' s requirements and validate those requirements by engaging stakeholders more often | Be firm with the stakeholder, since they would push through any unreasonable requirement | Inform the stakeholder that the requirement will be included in the next deliverable cycle | Inform the stakeholder that little can be done at this time, since core development has begun and the project must be delivered on time |  | C | When a key stakeholder raises a late concern about a requirement not showcased in the approved prototype while development has begun, the project manager should inform the stakeholder that the requirement will be included in the next deliverable cycle. This respects current commitments while providing a structured path for the requirement. Documenting and engaging more often (A) is good practice but not the immediate decision. Being firm and dismissive (B) damages the relationship. Saying nothing can be done (D) undermines collaboration. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트가 거의 완료되었을 때 주요 이해관계자가 자신이 선호하는 요구사항의 기능이 프로토타입에서 시연되지 않았다는 우려를 제기한다. 프로토타입은 이미 승인되었고 개발자들이 최종 애플리케이션 작업을 시작했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 이해관계자의 요구사항을 문서화하고 이해관계자를 더 자주 참여시켜 해당 요구사항을 검증한다. | 이해관계자에게 단호하게 대하며, 어떤 불합리한 요구사항이든 밀어붙일 것이므로 | 이해관계자에게 해당 요구사항이 다음 전달 주기에 포함될 것임을 알린다. | 이해관계자에게 핵심 개발이 시작되었고 프로젝트가 제시간에 전달되어야 하므로 현재로서는 할 수 있는 것이 거의 없다고 알린다. |  | C | 주요 이해관계자가 개발이 시작된 상태에서 승인된 프로토타입에 시연되지 않은 요구사항에 대한 늦은 우려를 제기할 때, 프로젝트 관리자는 해당 요구사항이 다음 전달 주기에 포함될 것임을 알려야 한다. 이는 현재 약속을 존중하면서 요구사항에 대한 구조화된 경로를 제공한다. 문서화 및 더 자주 참여(A)는 좋은 실천이지만 즉각적인 결정은 아니다. 단호하고 무시하는 태도(B)는 관계를 손상시킨다. 할 수 있는 것이 없다(D)는 협업을 훼손한다.
955 | A project with a geographically distributed team is ending its first iteration out of eight. During the daily meetings, the project manager realizes that some team members are not engaging in the discussion. What should the project manager do? | Ask the team members to speak during the meetings. | Speak with the team to find a better time to hold the meeting. | Update the risk log and follow the team members ' performance. | Conduct a team activity to determine the reasons for this situation. |  | D | When some team members in a geographically distributed team are not engaging during daily meetings at the end of the first iteration, the project manager should conduct a team activity to determine the reasons. Understanding root causes enables targeted solutions. Asking members to speak (A) is directive. Finding a better meeting time (B) assumes scheduling is the issue. Updating the risk log (C) treats a symptom. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Scaled Agile | People | Lead the Project Team | Resources | Executing | Embed Quality | Develop Team | Traditional PM | 지리적으로 분산된 팀의 프로젝트가 8개 반복 중 첫 번째를 마무리하고 있다. 일일 회의 중 프로젝트 관리자가 일부 팀원이 토론에 참여하지 않고 있음을 인식한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원들에게 회의 중 발언하도록 요청한다. | 팀과 대화하여 회의를 개최하기 더 좋은 시간을 찾는다. | 리스크 로그를 업데이트하고 팀원들의 성과를 추적한다. | 이 상황의 이유를 파악하기 위해 팀 활동을 수행한다. |  | D | 지리적으로 분산된 팀에서 첫 번째 반복이 끝날 때 일부 팀원이 일일 회의에 참여하지 않을 때, 프로젝트 관리자는 이유를 파악하기 위해 팀 활동을 수행해야 한다. 근본 원인을 이해하면 맞춤형 해결이 가능하다. 발언 요청(A)은 지시적이다. 더 좋은 회의 시간 찾기(B)는 일정이 문제라고 가정한다. 리스크 로그 업데이트(C)는 증상을 다룬다.
956 | An organization has recently decided to switch from a predictive to an agile delivery approach. The one ongoing project will still be led by a project manager. The agile teams for that project have not produced any documentation. What should the project manager of the ongoing project do? | Introduce a document management tool to support the agile teams in preparing the documentation. | Submit new user stories to the product owner in order to put documentation in the product backlog. | Add an additional team member to take up the role of scribe for the required documentation. | Check with the agile teams to see if the project manager ' s understanding of the Agile Manifesto is correct. |  | D | When agile teams on a project transitioning from predictive to agile have not produced any documentation, the project manager should check with the agile teams to see if their understanding of the Agile Manifesto is correct. The Manifesto values working software over comprehensive documentation but does not eliminate all documentation. Introducing a document management tool (A) imposes structure without understanding needs. Submitting user stories for documentation (B) creates unnecessary backlog items. Adding a scribe (C) treats the symptom without verifying root cause. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 조직이 최근 예측형에서 애자일 전달 접근 방식으로 전환하기로 결정했다. 진행 중인 하나의 프로젝트는 여전히 프로젝트 관리자가 이끈다. 해당 프로젝트의 애자일 팀들이 어떤 문서도 작성하지 않았다. 진행 중인 프로젝트의 프로젝트 관리자는 무엇을 해야 하는가? | 문서 관리 도구를 도입하여 애자일 팀이 문서를 준비하도록 지원한다. | 제품 백로그에 문서화를 넣기 위해 제품 책임자에게 새 사용자 스토리를 제출한다. | 필요한 문서를 위한 기록 담당자 역할을 맡을 추가 팀원을 추가한다. | 애자일 팀과 확인하여 프로젝트 관리자의 Agile Manifesto 이해가 올바른지 확인한다. |  | D | 예측형에서 애자일로 전환하는 프로젝트의 애자일 팀이 문서를 작성하지 않았을 때, 프로젝트 관리자는 애자일 팀과 확인하여 Agile Manifesto에 대한 이해가 올바른지 확인해야 한다. Manifesto는 포괄적인 문서보다 작동하는 소프트웨어를 가치 있게 여기지만 모든 문서를 제거하지는 않는다. 문서 관리 도구 도입(A)은 필요를 이해하지 않고 구조를 부과한다. 문서를 위한 사용자 스토리 제출(B)은 불필요한 백로그 항목을 만든다. 기록 담당자 추가(C)는 근본 원인 확인 없이 증상을 다룬다.
957 | An experienced project manager has recently joined a jeopardized project. The project is being impacted by multiple delays caused by a vendor's late delivery of new servers. Due to budget restrictions, the project manager cannot add a new vendor, and the project must be completed within a maximum of 90 days as agreed. What should the project manager do? | Request that the vendor provide the servers on time, as penalties may be applied. | Review lessons learned from previous projects and take action accordingly. | Wait until the project deadline is reached in order to use the contingency funds. | Reach out to the vendor to determine a plan to get the project back on track. |  | D | When a vendor's late server delivery causes multiple delays on a jeopardized project with budget restrictions and a 90-day deadline, the project manager should reach out to the vendor to determine a plan to get back on track. Direct vendor collaboration addresses the root cause. Requesting on-time delivery with penalty threats (A) is adversarial. Reviewing lessons learned (B) is informative but not immediately actionable. Waiting for contingency funds (C) wastes time. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 경험 많은 프로젝트 관리자가 최근 위기에 처한 프로젝트에 합류했다. 프로젝트는 벤더의 새 서버 납품 지연으로 인한 다수의 지연에 영향을 받고 있다. 예산 제한으로 인해 프로젝트 관리자는 새 벤더를 추가할 수 없으며, 합의된 대로 최대 90일 이내에 프로젝트를 완료해야 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 벤더에게 제시간에 서버를 제공하도록 요청하며, 위약금이 적용될 수 있다고 알린다. | 이전 프로젝트의 교훈을 검토하고 그에 따라 조치를 취한다. | 프로젝트 기한에 도달할 때까지 기다려 비상 예비비를 사용한다. | 벤더에게 연락하여 프로젝트를 정상 궤도에 올리기 위한 계획을 수립한다. |  | D | 벤더의 서버 납품 지연이 예산 제한과 90일 기한이 있는 위기 프로젝트에서 다수의 지연을 야기할 때, 프로젝트 관리자는 벤더에게 연락하여 정상 궤도 복귀 계획을 수립해야 한다. 직접적인 벤더 협업이 근본 원인을 해결한다. 위약금 위협과 함께 제시간 납품 요청(A)은 적대적이다. 교훈 검토(B)는 유익하지만 즉시 실행 가능하지 않다. 비상 예비비를 위해 기다리기(C)는 시간을 낭비한다.
958 | An important email from a project sponsor states that a backlog item should be immediately prioritized. What should the project manager do with many tasks still open on the Kanban board? | Finish the small tasks in progress before decomposing the item. | Communicate the impact with the project sponsor. | Discuss the impact of starting the item with the team. | Decompose the item immediately and begin work. |  | C | When a project sponsor emails to prioritize a new backlog item while many tasks remain on the Kanban board, the project manager should discuss the impact of starting the item with the team. This enables a collaborative assessment of how the new item affects current work, team capacity, and flow before committing to changes. Finishing small tasks first (A) delays addressing the sponsor's request. Communicating impact with the sponsor only (B) does not involve the team. Decomposing and starting work immediately (D) disrupts current flow without assessing impact. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Kanban | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 스폰서로부터 온 중요한 이메일에 백로그 항목을 즉시 우선순위에 놓아야 한다고 되어 있다. 칸반 보드에 아직 많은 작업이 열려 있는 상태에서 프로젝트 관리자는 무엇을 해야 하는가? | 항목을 분해하기 전에 진행 중인 작은 작업을 마무리한다. | 프로젝트 스폰서에게 영향을 전달한다. | 팀과 함께 항목을 시작하는 것의 영향을 논의한다. | 항목을 즉시 분해하고 작업을 시작한다. |  | C | 프로젝트 스폰서가 새 백로그 항목의 우선순위를 지정하라고 이메일을 보내고 칸반 보드에 많은 작업이 남아 있을 때, 프로젝트 관리자는 팀과 항목 시작의 영향을 논의해야 한다. 이를 통해 새 항목이 현재 작업, 팀 역량, 흐름에 미치는 영향을 협력적으로 평가할 수 있다. 작은 작업 먼저 마무리(A)는 스폰서의 요청 대응을 지연시킨다. 스폰서에게만 영향 전달(B)은 팀을 참여시키지 않는다. 즉시 분해하고 작업 시작(D)은 영향 평가 없이 현재 흐름을 방해한다.
959 | A project lead conducted coordination meetings to estimate the budget and confirm the timeframe for a new project. Due to internal resource challenges, outsourcing some activities could be implemented during execution. What should the project lead ensure before submitting the project for a stage gate review to receive the needed investment? | Add a percentage for management reserve | Align with relevant stakeholders on the procurement strategy | Conduct a retrospective with all involved stakeholders | Initiate a recruitment plan to explore the market situation |  | B | Before submitting a project with potential outsourcing needs for a stage gate review, the project lead should align with relevant stakeholders on the procurement strategy. A clear sourcing strategy strengthens the business case. Adding management reserve (A) is important but does not replace procurement planning. Conducting a retrospective (C) is a continuous improvement ceremony, not a gate preparation. Initiating recruitment (D) explores one option but does not address outsourcing strategy. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 리더가 새 프로젝트의 예산을 추정하고 일정을 확인하기 위해 조율 회의를 수행했다. 내부 자원 문제로 인해 실행 중 일부 활동을 아웃소싱할 수 있다. 프로젝트 리더가 필요한 투자를 받기 위해 단계 관문 검토에 프로젝트를 제출하기 전에 보장해야 할 것은? | 관리 예비비에 대한 백분율을 추가한다. | 관련 이해관계자와 조달 전략을 정렬한다. | 모든 관련 이해관계자와 회고를 수행한다. | 시장 상황을 탐색하기 위한 채용 계획을 시작한다. |  | B | 잠재적 아웃소싱 필요가 있는 프로젝트를 단계 관문 검토에 제출하기 전에, 프로젝트 리더는 관련 이해관계자와 조달 전략을 정렬해야 한다. 명확한 소싱 전략이 비즈니스 케이스를 강화한다. 관리 예비비 추가(A)는 중요하지만 조달 계획을 대체하지 않는다. 회고 수행(C)은 지속적 개선 의식이지 관문 준비가 아니다. 채용 계획 시작(D)은 하나의 옵션을 탐색하지만 아웃소싱 전략을 다루지 않는다.
960 | A project manager is tracking a project, but a key stakeholder will not accept the project's key performance indicator (KPI) results. Which tool or technique should the project manager use? | Context diagram | Change control tools | Autocratic decision making | Expert judgment |  | A | When a key stakeholder will not accept the project's KPI results, the project manager should use a context diagram. Context diagrams show the system boundary and external interactions, helping stakeholders understand what is measured. Change control tools (B) manage changes, not stakeholder understanding. Autocratic decision making (C) overrides the stakeholder. Expert judgment (D) is general and does not specifically address KPI disputes. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 관리자가 프로젝트를 추적하고 있지만, 주요 이해관계자가 프로젝트의 핵심성과지표(KPI) 결과를 수용하지 않는다. 프로젝트 관리자는 어떤 도구 또는 기법을 사용해야 하는가? | 컨텍스트 다이어그램 | 변경 통제 도구 | 독재적 의사결정 | 전문가 판단 |  | A | 주요 이해관계자가 프로젝트의 KPI 결과를 수용하지 않을 때, 프로젝트 관리자는 컨텍스트 다이어그램을 사용해야 한다. 컨텍스트 다이어그램은 시스템 경계와 외부 상호작용을 보여주어 이해관계자가 무엇이 측정되는지 이해하도록 돕는다. 변경 통제 도구(B)는 변경을 관리하지 이해관계자 이해를 관리하지 않는다. 독재적 의사결정(C)은 이해관계자를 무시한다. 전문가 판단(D)은 일반적이며 KPI 분쟁을 구체적으로 다루지 않는다.
961 | A project team has been together for a long time and has been led by three different project managers. Lately, the performance of one of the team members has been declining and has affected the project delivery. What should the current project manager do to ensure that team performance is improved and sustained? | Liaise with the functional managers to replace the team member. | Organize quarterly team-building events. | Engage with the team member and draw up a development plan. | Request that a new team member be added to the team |  | C | The correct answer is C. Engage with the team member and draw up a development plan. Effective leadership involves understanding team dynamics, addressing root causes, and creating a supportive environment. The PM should foster collaboration and well-being to maintain high performance. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Finance | Planning | Build an Empowered Culture | Plan Finance Management | AI | 프로젝트 팀이 오랫동안 함께 해왔고 세 명의 다른 프로젝트 관리자가 이끌어 왔다. 최근 팀원 중 한 명의 성과가 하락하여 프로젝트 전달에 영향을 미치고 있다. 현재 프로젝트 관리자는 팀 성과를 개선하고 유지하기 위해 무엇을 해야 하는가? | 팀원을 교체하기 위해 기능 관리자와 연락한다. | 분기별 팀 빌딩 이벤트를 조직한다. | 팀원과 소통하고 개발 계획을 수립한다. | 팀에 새 팀원을 추가하도록 요청한다. |  | C | 정답은 C이다. 팀원과 소통하고 개발 계획을 수립한다. 효과적인 리더십은 팀 역학을 이해하고, 근본 원인을 해결하며, 지원적인 환경을 조성하는 것을 포함한다. PM은 높은 성과를 유지하기 위해 협업과 웰빙을 촉진해야 한다.
962 | A team needs to implement a mandatory compliance regulation in a product, which is required for its release. While nearing the product release, when completeness was being verified, it was found that the compliance part was not implemented in the project. What should the project manager do next? | Obtain approval from management and release. | Get an exception approval from the legal team. | Ask the stakeholder to descope the compliance. | Request the team to implement the compliance. |  | D | When a mandatory compliance regulation was not implemented and is required for product release, the project manager should request the team to implement the compliance. Compliance is non-negotiable and must be completed before release. Obtaining management approval to release without it (A) risks legal consequences. Getting a legal exception (B) may not be possible for mandatory regulations. Asking the stakeholder to descope compliance (C) is inappropriate for mandatory requirements. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 팀이 제품 출시에 필요한 필수 규정 준수 사항을 제품에 구현해야 한다. 제품 출시가 가까워져 완전성을 검증하던 중 프로젝트에서 규정 준수 부분이 구현되지 않았음이 발견되었다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 경영진의 승인을 받고 출시한다. | 법무팀으로부터 예외 승인을 받는다. | 이해관계자에게 규정 준수를 범위에서 제외하도록 요청한다. | 팀에게 규정 준수를 구현하도록 요청한다. |  | D | 필수 규정 준수 사항이 구현되지 않았고 제품 출시에 필요할 때, 프로젝트 관리자는 팀에게 규정 준수를 구현하도록 요청해야 한다. 규정 준수는 협상할 수 없으며 출시 전에 완료되어야 한다. 규정 준수 없이 출시하기 위한 경영진 승인(A)은 법적 결과를 초래할 위험이 있다. 법적 예외 승인(B)은 필수 규정에 대해 불가능할 수 있다. 규정 준수 범위 제외 요청(C)은 필수 요구사항에 부적절하다.
963 | An engineer working on a project team has tasks that require an additional skill that the engineer does not have. A designer on the team is experienced with this skill from previous jobs and is willing to teach this skill even though it is not part of the current work. What should the project manager do? | Escalate the situation to the engineer ' s manager | Request external training for the engineer | Allow the engineer and designer to cross-train with each other 1118 | Request external training for the engineer and designer |  | C | When an engineer lacks a skill that a willing designer on the team can teach, the project manager should allow them to cross-train with each other. Cross-training leverages internal expertise and builds team flexibility. Escalating to the engineer's manager (A) is unnecessary. Requesting external training for the engineer (B) or for both (D) wastes resources when internal expertise is available. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트 팀에서 일하는 엔지니어가 보유하지 않은 추가 기술이 필요한 작업이 있다. 팀의 디자이너가 이전 직장에서 이 기술에 경험이 있으며 현재 업무의 일부가 아님에도 이 기술을 가르칠 의향이 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 엔지니어의 관리자에게 상황을 에스컬레이션한다. | 엔지니어를 위한 외부 교육을 요청한다. | 엔지니어와 디자이너가 서로 교차 교육하도록 허용한다. | 엔지니어와 디자이너를 위한 외부 교육을 요청한다. |  | C | 엔지니어에게 부족한 기술을 팀의 디자이너가 가르칠 의향이 있을 때, 프로젝트 관리자는 서로 교차 교육하도록 허용해야 한다. 교차 교육은 내부 전문성을 활용하고 팀 유연성을 구축한다. 관리자에게 에스컬레이션(A)은 불필요하다. 엔지니어를 위한 외부 교육 요청(B) 또는 둘 다를 위한 외부 교육(D)은 내부 전문성이 있을 때 자원 낭비이다.
964 | A project manager coordinates several projects in one program. Each project concerns a different country, has a different sponsor, and has specific business priorities. The resources are shared among the projects. The project manager anticipates this could result in delays and/or conflicts that will affect the program outcomes. What should the project manager do to prevent such a situation? | Organize regular meetings to identify risks related to the projects and program, assess them, and define action plans when needed to mitigate the risks. | Ask the project managers to work on their own schedules independently of one another and aggregate these schedules to present at the monthly steering committee meeting. | Review all project schedules and add a 3-month time period to each to cover such a risk and ensure there will be no delay that could affect the program. | Ask each project manager to write a detailed weekly report listing all the activities, what was achieved, what needs to be done, and the identified risks. |  | A | The correct answer is A. Organize regular meetings to identify risks related to the projects and program, assess them, and define action plans when needed to mitigate the risks. The PM should address team issues proactively by understanding root causes, building trust, and creating an environment that fosters collaboration and high performance. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 관리자가 하나의 프로그램에서 여러 프로젝트를 조율하고 있다. 각 프로젝트는 서로 다른 국가와 다른 스폰서를 가지며 특정 비즈니스 우선순위가 있다. 자원은 프로젝트 간에 공유된다. 프로젝트 관리자는 이것이 프로그램 결과에 영향을 미치는 지연 및/또는 충돌을 초래할 수 있다고 예상한다. 프로젝트 관리자는 이러한 상황을 방지하기 위해 무엇을 해야 하는가? | 프로젝트 및 프로그램과 관련된 리스크를 식별하고 평가하며 필요시 리스크를 완화하기 위한 실행 계획을 정의하기 위해 정기 회의를 조직한다. | 프로젝트 관리자들에게 서로 독립적으로 자체 일정을 수립하고 이를 취합하여 월간 운영위원회에 제시하도록 요청한다. | 모든 프로젝트 일정을 검토하고 이러한 리스크를 커버하기 위해 각각 3개월의 기간을 추가하여 프로그램에 영향을 줄 수 있는 지연이 없도록 보장한다. | 각 프로젝트 관리자에게 모든 활동, 달성된 것, 해야 할 것, 식별된 리스크를 나열하는 상세한 주간 보고서를 작성하도록 요청한다. |  | A | 정답은 A이다. 프로젝트 및 프로그램 관련 리스크를 식별하고 평가하며 필요시 완화 실행 계획을 정의하기 위해 정기 회의를 조직한다. PM은 근본 원인을 이해하고, 신뢰를 구축하며, 협업과 높은 성과를 촉진하는 환경을 조성하여 팀 이슈를 사전 예방적으로 해결해야 한다.
965 | An agile leader notices that one team member consistently fails to complete the deliverables on time. The agile leader suspects that this team member does not have the proper training. What should the agile leader do? | Review the definition of done (DoD) with the team so that everyone understands what the team must deliver in this sprint. | Reassign the task to another team member and require the team member to complete training | Speak directly with the team member about improvements and commit to an agreed-upon time frame. | Use the retrospective meeting to remind the entire team that they must complete all deliverables in each sprint |  | C | The agile leader should speak directly with the underperforming team member, provide constructive feedback, and agree on a realistic improvement timeline. This demonstrates respect, empathy, and commitment to helping the team member grow. Direct conversation enables understanding of root causes and development of an achievable improvement plan. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Be an Accountable Leader | Develop Team | Traditional PM | 애자일 리더가 한 팀원이 지속적으로 제시간에 산출물을 완료하지 못하는 것을 발견한다. 애자일 리더는 이 팀원이 적절한 교육을 받지 못했다고 의심한다. 애자일 리더는 무엇을 해야 하는가? | 팀이 이번 스프린트에서 전달해야 할 것을 모두가 이해하도록 완료 정의(DoD)를 팀과 검토한다. | 작업을 다른 팀원에게 재배정하고 해당 팀원에게 교육을 완료하도록 요구한다. | 팀원과 직접 대화하여 개선 사항을 논의하고 합의된 기간을 약속한다. | 회고 회의를 활용하여 전체 팀에게 각 스프린트에서 모든 산출물을 완료해야 한다는 것을 상기시킨다. |  | C | 애자일 리더는 성과가 부진한 팀원과 직접 대화하고 건설적인 피드백을 제공하며 현실적인 개선 기한에 합의해야 한다. 이는 존중, 공감, 팀원의 성장을 돕겠다는 헌신을 보여준다. 직접 대화는 근본 원인을 이해하고 달성 가능한 개선 계획을 수립할 수 있게 한다.
966 | A typically high-performing team member has started to demonstrate a performance drop as well as some aggressive behaviors toward other team members in meetings. The project manager has worked with this individual for many months on this project and has not seen this type of behavior before. What should the project manager do? | Discuss their performance with the team member ' s functional manager as well as human resources (HR) and discuss next steps. | Attend more team meetings to observe the team more closely to determine the root cause. | Discuss the individual ' s behavior with the other team members to determine if they have noticed and know what is going on. | Discuss the project manager ' s observations with the individual to determine why they are behaving this way. |  | D | When a typically high-performing team member shows performance decline and aggressive behavior for the first time, the project manager should discuss observations with the individual to determine why they are behaving this way. A private, empathetic conversation allows the team member to share personal or professional issues affecting their performance without assumptions. Discussing with the functional manager and HR (A) escalates before understanding the cause. Attending more meetings to observe (B) is passive surveillance. Discussing with other team members (C) may breach the individual's privacy. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Embed Quality | Develop Team | Traditional PM | 일반적으로 높은 성과를 보이던 팀원이 성과 저하와 함께 회의에서 다른 팀원들에 대한 공격적인 행동을 보이기 시작했다. 프로젝트 관리자는 이 개인과 여러 달 동안 이 프로젝트에서 함께 일했으며 이전에는 이런 유형의 행동을 본 적이 없다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀원의 기능 관리자 및 인사부(HR)와 성과를 논의하고 다음 단계를 논의한다. | 근본 원인을 파악하기 위해 팀을 더 면밀히 관찰하도록 더 많은 팀 회의에 참석한다. | 다른 팀원들과 해당 개인의 행동을 논의하여 그들이 알아챘는지, 무슨 일인지 아는지 확인한다. | 프로젝트 관리자의 관찰을 개인과 논의하여 왜 이런 행동을 하는지 파악한다. |  | D | 일반적으로 높은 성과를 보이던 팀원이 처음으로 성과 저하와 공격적 행동을 보일 때, 프로젝트 관리자는 개인과 관찰 사항을 논의하여 왜 이런 행동을 하는지 파악해야 한다. 사적이고 공감적인 대화는 가정 없이 개인적 또는 직업적 문제를 공유할 수 있게 한다. 기능 관리자 및 HR과 논의(A)는 원인을 이해하기 전에 에스컬레이션한다. 더 많은 회의 참석 관찰(B)은 수동적 감시이다. 다른 팀원과 논의(C)는 개인의 프라이버시를 침해할 수 있다.
967 | A project manager is working on an ongoing construction project. The designer notifies the project manager about materials that were not included in the budget due to a technical mistake. What should the project manager have done to avoid this situation? | Used past projects as a reference during budget estimations | Updated the budget before moving to another stage of the project | Added enough budget to cover all uncertainties | Asked the project sponsor to review the budget |  | A | When materials are excluded from a construction budget due to a technical mistake, the project manager should have used past projects as a reference during budget estimations. Analogous estimating with historical data helps identify overlooked items and improves cost accuracy. Updating the budget before moving stages (B) is a governance step but does not improve initial estimation. Adding budget for all uncertainties (C) is padding, not best practice. Asking the sponsor to review (D) adds oversight but does not improve the estimation process. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 관리자가 진행 중인 건설 프로젝트에서 작업하고 있다. 설계자가 기술적 실수로 예산에 포함되지 않은 자재에 대해 프로젝트 관리자에게 통보한다. 프로젝트 관리자는 이 상황을 방지하기 위해 무엇을 했어야 하는가? | 예산 추정 시 과거 프로젝트를 참조로 사용했어야 한다. | 프로젝트의 다른 단계로 넘어가기 전에 예산을 업데이트했어야 한다. | 모든 불확실성을 커버할 충분한 예산을 추가했어야 한다. | 프로젝트 스폰서에게 예산을 검토하도록 요청했어야 한다. |  | A | 기술적 실수로 건설 예산에서 자재가 누락되었을 때, 프로젝트 관리자는 예산 추정 시 과거 프로젝트를 참조로 사용했어야 한다. 유사 추정을 통한 과거 데이터 활용은 누락된 항목을 식별하고 비용 정확성을 개선한다. 단계 이동 전 예산 업데이트(B)는 거버넌스 단계이지만 초기 추정을 개선하지 않는다. 모든 불확실성을 위한 예산 추가(C)는 패딩이며 모범 사례가 아니다. 스폰서 검토 요청(D)은 감독을 추가하지만 추정 프로세스를 개선하지 않는다.
968 | A project lead accepted an assignment for a project that is still in the feasibility study phase. There are many uncertainties about project specifications, including poor alignment among the project sponsors on the final targets of the project. Which approach should the project lead choose to deliver business value? | Identify and communicate clear risk mitigation plans. | Ensure commitment from sponsors on executing the project until it ends. | Recommend predictive project management to the sponsors. | Subdivide project tasks to find the minimum viable product (MVP). |  | D | When a project is in feasibility with many uncertainties and poor sponsor alignment on targets, the project lead should subdivide project tasks to find the minimum viable product. MVP identifies core value under uncertainty. Identifying risk mitigation plans (A) is reactive. Ensuring sponsor commitment to the end (B) ignores the need for alignment on targets. Recommending predictive management (C) is unsuitable for high uncertainty. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Hybrid | Tailored Approach | Business Environment | Define and Establish Governance | Risk | Initiating | Be an Accountable Leader | Develop Project Charter | Hybrid/Tailoring | 프로젝트 리더가 아직 타당성 조사 단계에 있는 프로젝트에 배정되었다. 프로젝트 사양에 대한 많은 불확실성이 있으며, 프로젝트 스폰서 간 최종 목표에 대한 정렬이 부족하다. 프로젝트 리더는 비즈니스 가치를 전달하기 위해 어떤 접근 방식을 선택해야 하는가? | 명확한 리스크 완화 계획을 식별하고 커뮤니케이션한다. | 프로젝트를 끝까지 실행하겠다는 스폰서의 약속을 확보한다. | 스폰서에게 예측형 프로젝트 관리를 권장한다. | 프로젝트 작업을 세분화하여 최소 기능 제품(MVP)을 찾는다. |  | D | 프로젝트가 타당성 조사 단계에 있고 많은 불확실성과 스폰서 간 목표 정렬 부족이 있을 때, 프로젝트 리더는 프로젝트 작업을 세분화하여 MVP를 찾아야 한다. MVP는 불확실성 하에서 핵심 가치를 식별한다. 리스크 완화 계획 식별(A)은 반응적이다. 끝까지 스폰서 약속 확보(B)는 목표 정렬의 필요성을 무시한다. 예측형 관리 권장(C)은 높은 불확실성에 부적합하다.
969 | An experienced project manager is leading an enthusiastic team but realizes the team lacks the experience to complete the job successfully. What should the project manager do to reduce the risk of project failure? | Approve the appropriate training program for team members. | Ask the sponsor to add experienced professionals to the team. | Provide team members with the necessary coaching and mentoring. | Assign a dedicated resource to check the quality of each deliverable. |  | C | When leading an enthusiastic but inexperienced team, the project manager should provide team members with necessary coaching and mentoring. Developing team capabilities bridges the experience gap and reduces project failure risk. Approving a training program (A) is more formal and may take longer. Asking the sponsor to add experienced professionals (B) adds resources but does not develop the existing team. Assigning a dedicated quality resource (D) checks output but does not build capability. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 경험 많은 프로젝트 관리자가 열정적인 팀을 이끌고 있지만 팀이 업무를 성공적으로 완수할 경험이 부족하다는 것을 인식한다. 프로젝트 관리자는 프로젝트 실패 위험을 줄이기 위해 무엇을 해야 하는가? | 팀원을 위한 적절한 교육 프로그램을 승인한다. | 스폰서에게 경험 많은 전문가를 팀에 추가하도록 요청한다. | 팀원에게 필요한 코칭과 멘토링을 제공한다. | 각 산출물의 품질을 확인할 전담 자원을 배정한다. |  | C | 열정적이지만 경험이 부족한 팀을 이끌 때, 프로젝트 관리자는 팀원에게 필요한 코칭과 멘토링을 제공해야 한다. 팀 역량을 개발하면 경험 격차를 해소하고 프로젝트 실패 위험을 줄인다. 교육 프로그램 승인(A)은 더 공식적이며 시간이 더 걸릴 수 있다. 경험 많은 전문가 추가 요청(B)은 자원을 추가하지만 기존 팀을 개발하지 않는다. 전담 품질 자원 배정(D)은 산출물을 확인하지만 역량을 구축하지 않는다.
970 | An integrated project involves the interaction of both hardware and software and the sponsor has approved the schedule management plan. The project team evaluated the product's feasibility of functionality and accelerated testing. What should the project manager do as a servant leader? | Amend the project budget to include MVP testing | Submit a change request to the project sponsor for accelerated testing. | Develop the product as per the schedule to perform integration and testing | Support the team as necessary to find the minimum viable product (MVP). |  | D | When the project team has evaluated product feasibility and accelerated testing on an integrated hardware-software project, the project manager as servant leader should support the team as necessary to find the minimum viable product (MVP). Servant leadership removes impediments and empowers the team. Amending the budget for MVP testing (A) is a financial action, not leadership. Submitting a change request (B) is procedural. Developing per schedule (C) ignores the team's findings. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 통합 프로젝트가 하드웨어와 소프트웨어의 상호작용을 포함하며 스폰서가 일정 관리 계획을 승인했다. 프로젝트 팀이 제품의 기능 타당성을 평가하고 테스트를 가속화했다. 프로젝트 관리자는 서번트 리더로서 무엇을 해야 하는가? | MVP 테스트를 포함하도록 프로젝트 예산을 수정한다. | 가속화된 테스트를 위해 프로젝트 스폰서에게 변경 요청을 제출한다. | 통합 및 테스트를 수행하기 위해 일정에 따라 제품을 개발한다. | 최소 기능 제품(MVP)을 찾기 위해 필요에 따라 팀을 지원한다. |  | D | 프로젝트 팀이 통합 하드웨어-소프트웨어 프로젝트에서 제품 타당성을 평가하고 테스트를 가속화했을 때, 서번트 리더로서 프로젝트 관리자는 MVP를 찾기 위해 필요에 따라 팀을 지원해야 한다. 서번트 리더십은 장애물을 제거하고 팀에 권한을 부여한다. MVP 테스트를 위한 예산 수정(A)은 재무적 조치이지 리더십이 아니다. 변경 요청 제출(B)은 절차적이다. 일정에 따른 개발(C)은 팀의 발견을 무시한다.
971 | A project manager for a software technology project works in a matrixed organization with virtual teams. Unfortunately, the functional manager informs the project manager that there may not be any resources available to test the software. What should the project manager do next? | Engage with the functional manager to discuss details to obtain the required support. | Send an email to the procurement specialist to negotiate with a company that specializes in software testing. | Discuss testing requirements at the weekly project meeting to negotiate the best approach to test software. 1259 | Request a teleconference meeting with the sponsor to submit a change request to allow the development team to conduct testing. |  | A | When the functional manager in a matrixed organization indicates no resources may be available for software testing, the project manager should engage with the functional manager to discuss details and obtain required support. Direct negotiation addresses resource constraints. Emailing procurement for outsourcing (B) bypasses the functional manager. Discussing at the weekly meeting (C) delays action. Requesting a teleconference with the sponsor for a change request (D) escalates prematurely. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Cost & Resource Management | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 소프트웨어 기술 프로젝트의 프로젝트 관리자가 가상 팀이 있는 매트릭스 조직에서 근무하고 있다. 불행히도 기능 관리자가 프로젝트 관리자에게 소프트웨어를 테스트할 자원이 없을 수 있다고 알렸다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 기능 관리자와 만나 필요한 지원을 얻기 위한 세부 사항을 논의한다. | 소프트웨어 테스트 전문 회사와 협상하기 위해 조달 전문가에게 이메일을 보낸다. | 주간 프로젝트 회의에서 테스트 요구사항을 논의하여 소프트웨어 테스트에 대한 최선의 접근 방식을 협상한다. | 스폰서와 화상 회의를 요청하여 개발 팀이 테스트를 수행할 수 있도록 변경 요청을 제출한다. |  | A | 매트릭스 조직에서 기능 관리자가 소프트웨어 테스트에 자원이 없을 수 있다고 할 때, 프로젝트 관리자는 기능 관리자와 만나 세부 사항을 논의하고 필요한 지원을 얻어야 한다. 직접 협상이 자원 제약을 해결한다. 아웃소싱을 위해 조달에 이메일(B)은 기능 관리자를 우회한다. 주간 회의에서 논의(C)는 조치를 지연시킨다. 스폰서에게 변경 요청 화상 회의 요청(D)은 시기상조로 에스컬레이션한다.
972 | In an organization with good work-life balance, one team was continuously overloaded, thereby delivering the product at lower quality. What should the project manager do? | Request management for a high-performing team. | Request the team to focus on doing better planning. | Request the replacement of certain team members. | Request the team to work more for on-time delivery. |  | A | When one team is continuously overloaded and delivering lower-quality work in an organization that otherwise values work-life balance, the project manager should request management for a high-performing team to address the resource constraint. This advocates for a sustainable work environment while ensuring quality deliverables. Requesting the team to plan better (B) implies the overload is their fault. Requesting replacement of certain members (C) disrupts the team without addressing the resource imbalance. Requesting the team to work more (D) worsens the overload and contradicts work-life balance principles. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Resources | Planning | Integrate Sustainability | Plan Resource Management | Sustainability | 일과 삶의 균형이 좋은 조직에서 한 팀이 지속적으로 과부하가 걸려 낮은 품질로 제품을 전달하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 경영진에게 고성과 팀을 요청한다. | 팀에게 더 나은 계획 수립에 집중하도록 요청한다. | 특정 팀원의 교체를 요청한다. | 정시 전달을 위해 팀에게 더 많이 일하도록 요청한다. |  | A | 일과 삶의 균형을 중시하는 조직에서 한 팀이 지속적으로 과부하가 걸리고 낮은 품질의 작업을 전달할 때, 프로젝트 관리자는 자원 제약을 해결하기 위해 경영진에게 고성과 팀을 요청해야 한다. 이는 품질 산출물을 보장하면서 지속 가능한 작업 환경을 옹호한다. 더 나은 계획 요청(B)은 과부하가 팀 탓이라고 암시한다. 특정 멤버 교체 요청(C)은 자원 불균형을 해결하지 않고 팀을 혼란시킨다. 더 많이 일하도록 요청(D)은 과부하를 악화시키고 일과 삶의 균형 원칙에 모순된다.
973 | A project manager who is experienced in predictive and adaptive approaches has been assigned to a new project. Most of the project stakeholders have only worked on predictive projects, and only a few have been exposed to adaptive projects. What should the project manager do? | Use an adaptive approach, engage the stakeholders who have been exposed to adaptive projects, and train those who have not. | Follow a predictive approach to reduce the training effort, even though there are incremental deliveries in the project. | Propose a hybrid approach and determine which stakeholders will be engaged in each phase of the project. | Understand the scope complexity and project magnitude prior to determining which approach to use. |  | D | When most stakeholders have only predictive experience and a few have adaptive exposure, the project manager should understand the scope complexity and project magnitude prior to determining which approach to use. Project characteristics should drive methodology selection. Using adaptive and training everyone (A) ignores project fit. Following predictive to reduce training (B) limits flexibility. Proposing hybrid and assigning stakeholders to phases (C) decides the approach prematurely. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Hybrid/Tailoring | 예측형과 적응형 접근 방식에 경험이 있는 프로젝트 관리자가 새 프로젝트에 배정되었다. 대부분의 프로젝트 이해관계자는 예측형 프로젝트에서만 근무했으며, 소수만 적응형 프로젝트를 경험했다. 프로젝트 관리자는 무엇을 해야 하는가? | 적응형 접근 방식을 사용하고, 적응형 프로젝트를 경험한 이해관계자를 참여시키며, 경험이 없는 이해관계자를 교육한다. | 프로젝트에 점진적 전달이 있더라도 교육 노력을 줄이기 위해 예측형 접근 방식을 따른다. | 하이브리드 접근 방식을 제안하고 프로젝트의 각 단계에 어떤 이해관계자를 참여시킬지 결정한다. | 어떤 접근 방식을 사용할지 결정하기 전에 범위 복잡성과 프로젝트 규모를 파악한다. |  | D | 대부분의 이해관계자가 예측형 경험만 있고 소수가 적응형 노출이 있을 때, 프로젝트 관리자는 어떤 접근 방식을 사용할지 결정하기 전에 범위 복잡성과 프로젝트 규모를 파악해야 한다. 프로젝트 특성이 방법론 선택을 주도해야 한다. 적응형을 사용하고 모두를 교육(A)은 프로젝트 적합성을 무시한다. 교육 감소를 위해 예측형(B)은 유연성을 제한한다. 하이브리드를 제안하고 이해관계자를 단계에 배정(C)은 접근 방식을 시기상조로 결정한다.
974 | A project manager is managing a complex research project with a high level of uncertainty. A request is made to implement a mechanism to measure the quality of the deliverables. Using a hybrid approach, what techniques can be used to achieve this goal? | Time-boxed iterations and standup review meetings | Scrum master reviews and the quality Kanban method | Paired work and the customer role method. | Daily Scrum and product owner quality assessments. |  | C | Paired work—where two team members collaborate on the same task—improves quality through shared feedback, error reduction, and enhanced creativity. The customer role technique assigns a team member to represent the end user, providing input, validation, and acceptance criteria. Both are hybrid approaches that combine agile and traditional elements, well-suited for projects with high uncertainty and complexity. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Hybrid/Tailoring | 프로젝트 관리자가 불확실성이 높은 복잡한 연구 프로젝트를 관리하고 있다. 산출물의 품질을 측정하는 메커니즘을 구현하라는 요청이 있었다. 하이브리드 접근 방식을 사용하여 이 목표를 달성하기 위해 어떤 기법을 사용할 수 있는가? | 타임박스 반복과 스탠드업 검토 회의 | 스크럼 마스터 검토와 품질 칸반 방법 | 페어 작업과 고객 역할 방법 | 일일 스크럼과 제품 책임자 품질 평가 |  | C | 페어 작업—두 팀원이 동일한 작업에 협력하는 것—은 공유 피드백, 오류 감소, 향상된 창의성을 통해 품질을 개선한다. 고객 역할 기법은 팀원에게 최종 사용자를 대표하도록 배정하여 입력, 검증, 인수 기준을 제공한다. 둘 다 애자일과 전통적 요소를 결합한 하이브리드 접근 방식으로, 높은 불확실성과 복잡성이 있는 프로젝트에 적합하다.
975 | A flagship project is sponsored by the CEO and has a critical go-live date. The project's product requires a regulatory review and approval before it can go live. The CEO instructed to allow only 2 weeks for regulatory approval in the schedule; however, the director for the regulatory liaison indicated 6 weeks was a more realistic timeline. What should the project manager do? | Schedule final testing activities in parallel with the regulatory approval activities to compensate for lost time. | Meet with the CEO and the director to discuss and register it as a major risk if agreement cannot be made. | Proceed with the direction given by the director for the regulatory liaison, as they are the subject matter expert (SME). | Follow the CEO ' s directive, as they are the highest authority in the company and are the ultimate decision maker. |  | B | When the CEO's directive of 2 weeks for regulatory approval conflicts with the regulatory liaison director's realistic estimate of 6 weeks, the project manager should meet with both parties to discuss and attempt alignment. If agreement cannot be reached, the discrepancy should be registered as a major risk. Stakeholder collaboration on realistic constraints supports both risk mitigation and informed decision-making. Scheduling testing in parallel with approval (A) may introduce unnecessary risk. Proceeding solely with the director's timeline (C) bypasses the CEO's authority. Following only the CEO's directive (D) ignores the SME's expertise and creates an unrealistic schedule. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | CEO가 후원하고 중요한 운영 개시일이 있는 대표 프로젝트가 있다. 프로젝트의 제품은 운영 개시 전에 규제 검토 및 승인이 필요하다. CEO는 일정에서 규제 승인에 2주만 허용하도록 지시했지만, 규제 연락 담당 이사는 6주가 더 현실적인 일정이라고 제시했다. 프로젝트 관리자는 무엇을 해야 하는가? | 시간 손실을 보상하기 위해 규제 승인 활동과 병행하여 최종 테스트 활동을 일정에 편성한다. | CEO와 이사를 만나 논의하고 합의가 이루어지지 않으면 주요 리스크로 등록한다. | 규제 연락 담당 이사가 해당 분야의 전문가(SME)이므로 이사의 지시에 따라 진행한다. | CEO가 회사의 최고 권한이며 최종 의사결정자이므로 CEO의 지시를 따른다. |  | B | CEO의 규제 승인 2주 지시가 규제 연락 담당 이사의 현실적 추정치 6주와 충돌할 때, 프로젝트 관리자는 양측을 만나 논의하고 정렬을 시도해야 한다. 합의에 도달하지 못하면 그 차이를 주요 리스크로 등록해야 한다. 현실적 제약에 대한 이해관계자 협력이 리스크 완화와 정보에 입각한 의사결정을 모두 지원한다. 승인과 병행하여 테스트 일정 편성(A)은 불필요한 리스크를 도입할 수 있다. 이사의 일정으로만 진행(C)은 CEO의 권한을 우회한다. CEO의 지시만 따르는 것(D)은 SME의 전문성을 무시하고 비현실적 일정을 만든다.
976 | An unforeseen event has shut down public works projects for 4 weeks. Activities on the critical path will fall behind based on the project schedule. What should the project manager do? | Add 4 additional weeks to the schedule and request additional resources. | Review the project management plan to see the impact of the possible delay. | Ask the sponsor to obtain a special work permit to continue work. | Crash the resource management plan to keep the schedule on track. |  | B | When an unforeseen event shuts down work for 4 weeks and critical path activities will fall behind, the project manager should review the project management plan to understand the full impact of the delay on project objectives. This review informs the PM's assessment and subsequent decisions, which may include re-sequencing activities, schedule compression, or negotiating scope changes. Adding 4 weeks and requesting resources (A) assumes a specific solution without first assessing the full impact. Asking the sponsor for a special work permit (C) may not be feasible depending on the nature of the shutdown. Crashing the resource management plan (D) is a specific compression technique that should only be considered after understanding the overall impact. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Critical Path/Schedule Mgmt | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 예상치 못한 사건으로 공공사업 프로젝트가 4주 동안 중단되었다. 크리티컬 패스의 활동이 프로젝트 일정에 따라 지연될 것이다. 프로젝트 관리자는 무엇을 해야 하는가? | 일정에 4주를 추가하고 추가 자원을 요청한다. | 가능한 지연의 영향을 확인하기 위해 프로젝트 관리 계획을 검토한다. | 스폰서에게 작업을 계속하기 위한 특별 작업 허가를 받도록 요청한다. | 일정을 궤도에 유지하기 위해 자원 관리 계획을 크래싱한다. |  | B | 예상치 못한 사건으로 4주 동안 작업이 중단되고 크리티컬 패스 활동이 지연될 때, 프로젝트 관리자는 프로젝트 목표에 대한 지연의 전체 영향을 파악하기 위해 프로젝트 관리 계획을 검토해야 한다. 이 검토는 PM의 평가와 후속 결정을 알려주며, 활동 재순서화, 일정 압축 또는 범위 변경 협상을 포함할 수 있다. 4주 추가 및 자원 요청(A)은 전체 영향을 먼저 평가하지 않고 특정 해결책을 가정한다. 스폰서에게 특별 허가 요청(C)은 중단의 성격에 따라 실현 가능하지 않을 수 있다. 자원 관리 계획 크래싱(D)은 전체 영향을 이해한 후에만 고려해야 하는 특정 압축 기법이다.
977 | A project manager is leading a diverse project team that includes new and experienced team members. A conflict has occurred between two team members. One team member prefers using digital tools for project communication. The other team member prefers in-person meetings and phone calls for communication. What should the project manager do to manage this conflict? | Initiate a conversation with the team members individually to understand their situations regarding communication. | Arrange a team-building activity to foster understanding and open communication among the team members. | Allow the team members to continue using their preferred communication tools and methods. | Instruct the team members to adapt to the project ' s communication tools and methods. |  | A | When two team members conflict over communication preferences—digital tools versus in-person meetings—the project manager should initiate a conversation with each team member individually to understand their situations. Understanding each perspective first enables mediation and a balanced resolution. Team-building activities (B) are general and do not address the specific issue. Allowing different tools (C) risks inconsistent communication. Instructing members to adapt (D) is prescriptive and may create resistance. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 관리자가 새로운 팀원과 경험 많은 팀원을 포함하는 다양한 프로젝트 팀을 이끌고 있다. 두 팀원 사이에 갈등이 발생했다. 한 팀원은 프로젝트 커뮤니케이션에 디지털 도구를 선호하고, 다른 팀원은 대면 회의와 전화 통화를 선호한다. 프로젝트 관리자는 이 갈등을 관리하기 위해 무엇을 해야 하는가? | 각 팀원과 개별적으로 대화를 시작하여 커뮤니케이션에 관한 상황을 파악한다. | 팀원 간 이해와 열린 소통을 촉진하기 위한 팀 빌딩 활동을 준비한다. | 팀원들이 선호하는 커뮤니케이션 도구와 방법을 계속 사용하도록 허용한다. | 팀원들에게 프로젝트의 커뮤니케이션 도구와 방법에 적응하도록 지시한다. |  | A | 두 팀원이 커뮤니케이션 선호도—디지털 도구 대 대면 회의—로 갈등할 때, 프로젝트 관리자는 각 팀원과 개별적으로 대화를 시작하여 상황을 파악해야 한다. 각 관점을 먼저 이해하면 중재와 균형 잡힌 해결이 가능해진다. 팀 빌딩 활동(B)은 일반적이며 특정 이슈를 다루지 않는다. 다른 도구 허용(C)은 일관성 없는 커뮤니케이션을 초래할 위험이 있다. 적응하도록 지시(D)는 규범적이며 저항을 유발할 수 있다.
978 | After gathering all the requirements for a project with dependencies on external stakeholders, the project team is finishing the second iteration. At this point, the project manager learns about a possible change in regulations that would prevent the product launch. What should the project manager do to realize benefits? | Review target benefits. | Improve the team ' s velocity | Add an entry in the risk log | Implement the changes |  | A | When learning about a possible regulation change that could prevent the product launch during the second iteration, the project manager should review target benefits. Assessing whether benefits remain valid and achievable is the priority. Improving velocity (B) addresses speed, not viability. Adding a risk log entry (C) is documentation but not benefit-focused. Implementing changes (D) is premature without benefit review. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 외부 이해관계자에 대한 의존성이 있는 프로젝트의 모든 요구사항을 수집한 후, 프로젝트 팀이 두 번째 반복을 마무리하고 있다. 이 시점에서 프로젝트 관리자가 제품 출시를 방해할 수 있는 규정 변경 가능성에 대해 알게 되었다. 프로젝트 관리자는 혜택을 실현하기 위해 무엇을 해야 하는가? | 목표 혜택을 검토한다. | 팀의 속도를 개선한다. | 리스크 로그에 항목을 추가한다. | 변경을 구현한다. |  | A | 두 번째 반복 중 제품 출시를 방해할 수 있는 규정 변경 가능성에 대해 알게 될 때, 프로젝트 관리자는 목표 혜택을 검토해야 한다. 혜택이 여전히 유효하고 달성 가능한지 평가하는 것이 우선이다. 속도 개선(B)은 속도를 다루지 실현 가능성은 다루지 않는다. 리스크 로그에 항목 추가(C)는 문서화이지 혜택 중심이 아니다. 변경 구현(D)은 혜택 검토 없이 시기상조이다.
979 | A project manager is planning the fifth sprint of a project when the sponsor requests a report on the business value gained to date. What should the project manager show to the sponsor? | The fifth sprint retrospective report | The metrics plan to track benefits | The cumulative flow diagram | The data of the metrics defined to track benefits |  | D | The correct answer is D. The data of the metrics defined to track benefits. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 프로젝트의 다섯 번째 스프린트를 계획하고 있을 때 스폰서가 현재까지 얻은 비즈니스 가치에 대한 보고서를 요청한다. 프로젝트 관리자는 스폰서에게 무엇을 보여주어야 하는가? | 다섯 번째 스프린트 회고 보고서 | 혜택을 추적하기 위한 메트릭스 계획 | 누적 흐름 다이어그램 | 혜택을 추적하기 위해 정의된 메트릭스의 데이터 |  | D | 정답은 D이다. 혜택을 추적하기 위해 정의된 메트릭스의 데이터. 애자일 환경에서 PM은 팀 협업을 촉진하고 장애물을 제거하며 애자일 원칙과 의식을 존중하면서 지속적인 가치 전달을 보장하는 데 집중해야 한다.
980 | A team is entering into a forming stage after kickoff, with project objectives identified and team members assigned with roles and responsibilities. However, during the team meetings, a team member does not agree on project documents and makes comments that could affect the performance of other team members. What should the project manager do? | Observe to ensure this typical forming stage behavior does not escalate beyond what is acceptable. | Collaborate with the team to arrive at team ground rules and publish the rules to the team. | Escalate the team member ' s disruptive behavior to their functional manager. | Request team members document their decisions independently and share with each other. |  | B | During the forming stage of team development, establishing team ground rules is a proactive measure to prevent conflicts and ensure alignment. Collaboratively creating ground rules enables the team to address disagreements in a structured way and supports a positive team environment—crucial for progressing through subsequent development stages. This approach emphasizes collaboration and team engagement as key project management components. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 킥오프 후 형성(Forming) 단계에 진입한 팀이 있으며, 프로젝트 목표가 식별되고 팀원에게 역할과 책임이 배정되었다. 그러나 팀 회의 중 한 팀원이 프로젝트 문서에 동의하지 않고 다른 팀원의 성과에 영향을 줄 수 있는 발언을 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 이 전형적인 형성 단계 행동이 허용 가능한 수준을 넘어 확대되지 않도록 관찰한다. | 팀과 협력하여 팀 기본 규칙을 수립하고 팀에 규칙을 공유한다. | 팀원의 방해 행동을 기능 관리자에게 에스컬레이션한다. | 팀원들에게 독립적으로 결정 사항을 문서화하고 서로 공유하도록 요청한다. |  | B | 팀 개발의 형성 단계에서 팀 기본 규칙을 수립하는 것은 갈등을 예방하고 정렬을 보장하는 사전 예방적 조치이다. 기본 규칙을 협력적으로 만들면 팀이 구조화된 방식으로 의견 불일치를 다룰 수 있으며, 후속 개발 단계로 진행하는 데 중요한 긍정적인 팀 환경을 지원한다. 이 접근 방식은 협업과 팀 참여를 핵심 프로젝트 관리 구성 요소로 강조한다.
981 | An agile team has released the second version of its product, but the feedback is that the software has many bugs that compromise the user experience. What should the project manager do? | Hire an external consultancy firm to focus on testing and quality control to avoid the issue in the future. | Propose an internal program that offers incentives for the team members who find and fix bugs. | Closely evaluate the skill set of the team, looking for technical gaps that need to be filed in order to improve quality. | Facilitate the next retrospective meeting, focusing the team on analyzing root causes and proposing solutions. |  | D | When the second product release has many bugs compromising user experience, the project manager should facilitate the next retrospective meeting, focusing on root cause analysis and solutions. Retrospectives enable team-driven quality improvement. Hiring an external consultancy (A) is costly and external. Offering bug-fix incentives (B) treats symptoms. Evaluating team skill gaps (C) addresses capability but not process. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 애자일 팀이 제품의 두 번째 버전을 출시했지만, 소프트웨어에 사용자 경험을 저해하는 많은 버그가 있다는 피드백을 받았다. 프로젝트 관리자는 무엇을 해야 하는가? | 향후 이 문제를 방지하기 위해 테스트와 품질 관리에 집중할 외부 컨설팅 회사를 고용한다. | 버그를 찾아 수정한 팀원에게 인센티브를 제공하는 내부 프로그램을 제안한다. | 품질 향상을 위해 채워야 할 기술적 격차를 찾아 팀의 역량을 면밀히 평가한다. | 다음 회고 회의를 촉진하여 팀이 근본 원인을 분석하고 해결책을 제안하는 데 집중하도록 한다. |  | D | 두 번째 제품 출시에 사용자 경험을 저해하는 많은 버그가 있을 때, 프로젝트 관리자는 다음 회고 회의를 촉진하여 근본 원인 분석과 해결책에 집중해야 한다. 회고는 팀 주도의 품질 개선을 가능하게 한다. 외부 컨설팅 고용(A)은 비용이 많이 들고 외부적이다. 버그 수정 인센티브 제공(B)은 증상만 치료한다. 팀 역량 격차 평가(C)는 역량을 다루지만 프로세스는 다루지 않는다.
982 | A project manager submits a version of the software that the project team created. During the review meeting, a team member informs the project manager of a recent regulation that requires a dual verification process in the software. However, the product sponsor strongly insists there should be no updates to the software. What should the project manager do? | Inform the team that the sponsor decided to reject any changes and release the software as is. | Include the new requirement in the next iteration of the software without informing the sponsor. | Release the software as is and start a new project to deliver the new requirements. | Collect the requirements of the regulation and follow the change control process. |  | D | When a team member reports a new regulation requiring dual verification in the software but the sponsor insists on no updates, the project manager should collect the requirements of the regulation and follow the change control process. This ensures proper impact analysis and stakeholder approval while maintaining regulatory compliance. Informing the team of the sponsor's rejection (A) ignores regulatory requirements. Including the requirement without informing the sponsor (B) bypasses governance. Releasing as-is and starting a new project (C) creates unnecessary rework and risk. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 관리자가 프로젝트 팀이 만든 소프트웨어 버전을 제출한다. 검토 회의 중 팀원이 프로젝트 관리자에게 소프트웨어에 이중 검증 프로세스를 요구하는 최근 규정을 알린다. 그러나 제품 스폰서는 소프트웨어에 대한 업데이트가 없어야 한다고 강력히 주장한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에게 스폰서가 모든 변경을 거부하기로 결정했으며 소프트웨어를 현재 상태로 출시한다고 알린다. | 스폰서에게 알리지 않고 소프트웨어의 다음 반복에 새로운 요구사항을 포함한다. | 소프트웨어를 현재 상태로 출시하고 새로운 요구사항을 전달하기 위한 새 프로젝트를 시작한다. | 규정의 요구사항을 수집하고 변경 통제 프로세스를 따른다. |  | D | 팀원이 소프트웨어에 이중 검증을 요구하는 새 규정을 보고하지만 스폰서가 업데이트를 거부할 때, 프로젝트 관리자는 규정의 요구사항을 수집하고 변경 통제 프로세스를 따라야 한다. 이는 규정 준수를 유지하면서 적절한 영향 분석과 이해관계자 승인을 보장한다. 스폰서의 거부를 팀에 알림(A)은 규제 요구사항을 무시한다. 스폰서에게 알리지 않고 포함(B)은 거버넌스를 우회한다. 현재 상태로 출시하고 새 프로젝트 시작(C)은 불필요한 재작업과 리스크를 만든다.
983 | A new offshore call center project is vital for a company's branch offices. The project is at the end of the planning phase when the project manager is informed by the sponsor that the project will be delayed due to reprioritization. What should the project manager do? | Create a messaging group chat with the branch office stakeholders to inform them about the project delay. | Schedule a video conference to inform the branch office stakeholders about the project delay. | Send an official project memo to inform the branch office stakeholders about the project delay. | Include the project delay in the monthly progress report for the branch office stakeholders. |  | B | When a vital project is delayed due to reprioritization at the end of planning, the project manager should schedule a video conference to inform branch office stakeholders. Video conferencing enables two-way communication, clarity, and immediate response to concerns. A messaging group chat (A) is too informal. Sending an official memo (C) is one-way communication. Including it in the monthly report (D) delays the message unnecessarily. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 새로운 해외 콜센터 프로젝트가 회사의 지사에 중요하다. 프로젝트가 계획 단계 끝에 있을 때 프로젝트 관리자가 스폰서로부터 우선순위 재조정으로 인해 프로젝트가 지연될 것이라고 통보받는다. 프로젝트 관리자는 무엇을 해야 하는가? | 지사 이해관계자에게 프로젝트 지연을 알리기 위해 메시징 그룹 채팅을 만든다. | 지사 이해관계자에게 프로젝트 지연을 알리기 위해 화상 회의를 예약한다. | 지사 이해관계자에게 프로젝트 지연을 알리기 위해 공식 프로젝트 메모를 보낸다. | 지사 이해관계자를 위한 월간 진행 보고서에 프로젝트 지연을 포함한다. |  | B | 중요한 프로젝트가 계획 단계 끝에서 우선순위 재조정으로 지연될 때, 프로젝트 관리자는 지사 이해관계자에게 알리기 위해 화상 회의를 예약해야 한다. 화상 회의는 양방향 커뮤니케이션, 명확성, 우려에 대한 즉각적인 대응을 가능하게 한다. 메시징 그룹 채팅(A)은 너무 비공식적이다. 공식 메모 발송(C)은 일방적 커뮤니케이션이다. 월간 보고서에 포함(D)은 메시지를 불필요하게 지연시킨다.
984 | An organization started the process of a digital transformation and is trying to change its culture from a predictive to a more agile approach. The project manager leading the change management process identified some knowledge gaps of key team members, which could prevent the transformation from happening as planned. What should the project manager do? | Provide mentoring for the key team members on agile practices and support the teamwith training and encouragement. | Create an agile conduct guideline and ensure that all team members follow the rulesstated in the document. | Provide directions to the team members on how to accelerate the company ' stransformation, bringing the project back on track. | Replace the key team members with new resources who are already aware of the agilemindset. |  | A | When key team members have knowledge gaps that could prevent a digital transformation from predictive to agile, the project manager should provide mentoring on agile practices and support the team with training and encouragement. This develops existing team capabilities while fostering a positive culture of agility and collaboration. Creating a conduct guideline (B) provides rules but does not address the underlying knowledge gaps. Providing directions to accelerate transformation (C) is top-down and does not build genuine understanding. Replacing key team members (D) is disruptive, costly, and may not be necessary. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Digital Transformation | 조직이 디지털 전환 프로세스를 시작했으며 문화를 예측형에서 더 애자일한 접근 방식으로 변경하려 하고 있다. 변경 관리 프로세스를 이끄는 프로젝트 관리자가 주요 팀원들의 지식 격차를 식별했으며, 이것이 계획대로 전환이 이루어지는 것을 방해할 수 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 주요 팀원들에게 애자일 실무에 대한 멘토링을 제공하고 교육과 격려로 팀을 지원한다. | 애자일 행동 지침을 작성하고 모든 팀원이 문서에 명시된 규칙을 따르도록 보장한다. | 팀원들에게 회사의 전환을 가속화하는 방법에 대한 지시를 제공하여 프로젝트를 정상 궤도에 올린다. | 주요 팀원들을 이미 애자일 마인드셋을 알고 있는 새로운 자원으로 교체한다. |  | A | 주요 팀원들에게 예측형에서 애자일로의 디지털 전환을 방해할 수 있는 지식 격차가 있을 때, 프로젝트 관리자는 애자일 실무에 대한 멘토링을 제공하고 교육과 격려로 팀을 지원해야 한다. 이는 민첩성과 협업의 긍정적 문화를 육성하면서 기존 팀 역량을 개발한다. 행동 지침 작성(B)은 규칙을 제공하지만 근본적인 지식 격차를 해결하지 않는다. 전환 가속화 지시(C)는 하향식이며 진정한 이해를 구축하지 않는다. 주요 팀원 교체(D)는 파괴적이고 비용이 많이 들며 불필요할 수 있다.
985 | An organization's human resources (HR) department wants to create a high-performing team and implement a project that includes job grading, organizational restructuring, and soft skills training. To ensure the quality of the project deliverable, which three actions should the project manager take? (Choose 3) | Collect feedback and conduct surveys and questionnaires. | Develop a proper quality management plan with measurable metrics. | Document quality gaps and analyze them for continuous improvement. | Hire a certified expert to lead the project quality process. | Apply an existing external framework for performance improvement. | A, B, C | For an HR project including job grading, restructuring, and soft skills training, the project manager should take three quality actions: collect feedback through surveys and questionnaires for direct stakeholder input, document quality gaps and analyze them for continuous improvement, and develop a proper quality management plan with measurable metrics. Hiring a certified expert (D) is not mandatory. Applying an external framework (E) can support but is insufficient alone. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 조직의 인사(HR) 부서가 고성과 팀을 만들고 직무 등급화, 조직 구조조정, 소프트 스킬 교육을 포함하는 프로젝트를 구현하고자 한다. 프로젝트 산출물의 품질을 보장하기 위해 프로젝트 관리자는 어떤 세 가지 조치를 취해야 하는가? (3개 선택) | 피드백을 수집하고 설문조사와 질문지를 실시한다. | 측정 가능한 지표가 포함된 적절한 품질 관리 계획을 개발한다. | 품질 격차를 문서화하고 지속적 개선을 위해 분석한다. | 프로젝트 품질 프로세스를 이끌 공인 전문가를 고용한다. | 성과 개선을 위한 기존 외부 프레임워크를 적용한다. | A, B, C | 직무 등급화, 구조조정, 소프트 스킬 교육을 포함하는 HR 프로젝트에서 프로젝트 관리자는 세 가지 품질 조치를 취해야 한다: 직접적인 이해관계자 입력을 위해 설문조사와 질문지를 통해 피드백을 수집하고, 지속적 개선을 위해 품질 격차를 문서화하고 분석하며, 측정 가능한 지표가 포함된 적절한 품질 관리 계획을 개발한다. 공인 전문가 고용(D)은 필수가 아니다. 외부 프레임워크 적용(E)은 지원할 수 있지만 단독으로는 불충분하다.
986 | A project manager is struggling to figure out the performance of the project teams in an agile environment. For the same scope of work, team A has calculated 100 story points and team B has calculated 125 story points. Which team is performing better? | The team that completes the most stories selected from the sprint backlog | Team B as they have calculated more story points than team A | Team A as they have calculated fewer story points than team B. | The team with the least amount of defects in their deliverables |  | D | When comparing team performance across two teams with different story point calculations for the same scope, the team with the least amount of defects in their deliverables is performing better. Story points are relative estimates that vary by team, making cross-team comparison invalid. Team A with fewer points (C) does not mean better performance. Team B with more points (B) does not mean better performance. Completing the most stories (A) ignores quality. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 프로젝트 관리자가 애자일 환경에서 프로젝트 팀의 성과를 파악하는 데 어려움을 겪고 있다. 동일한 범위의 작업에 대해 팀 A는 100 스토리 포인트를 계산했고 팀 B는 125 스토리 포인트를 계산했다. 어느 팀이 더 잘 수행하고 있는가? | 스프린트 백로그에서 선택한 스토리를 가장 많이 완료하는 팀 | 팀 A보다 더 많은 스토리 포인트를 계산한 팀 B | 팀 B보다 더 적은 스토리 포인트를 계산한 팀 A | 산출물의 결함이 가장 적은 팀 |  | D | 동일한 범위에 대해 서로 다른 스토리 포인트 계산을 가진 두 팀의 성과를 비교할 때, 산출물의 결함이 가장 적은 팀이 더 잘 수행하고 있다. 스토리 포인트는 팀마다 다른 상대적 추정치이므로 팀 간 비교가 유효하지 않다. 더 적은 포인트의 팀 A(C)가 더 나은 성과를 의미하지 않는다. 더 많은 포인트의 팀 B(B)가 더 나은 성과를 의미하지 않는다. 가장 많은 스토리 완료(A)는 품질을 무시한다.
987 | A new agile team is having trouble completing tasks. There are many disputes occurring in the team. What should the agile leader do in this situation? | Remove some of the team members. | Escalate the issue to the team ' s manager. | Review the roles and responsibilities document. | Develop working agreements with the team. |  | D | When a new agile team has trouble completing tasks and many disputes arise, the agile leader should develop working agreements with the team. Collaborative norms establish shared expectations and resolve conflicts. Removing team members (A) disrupts dynamics. Escalating to the manager (B) undermines team autonomy. Reviewing roles and responsibilities (C) is useful but insufficient to address behavioral disputes. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 새로운 애자일 팀이 작업을 완료하는 데 어려움을 겪고 있다. 팀 내에서 많은 분쟁이 발생하고 있다. 애자일 리더는 이 상황에서 무엇을 해야 하는가? | 일부 팀원을 제거한다. | 이슈를 팀의 관리자에게 에스컬레이션한다. | 역할과 책임 문서를 검토한다. | 팀과 함께 작업 합의를 개발한다. |  | D | 새로운 애자일 팀이 작업 완료에 어려움을 겪고 많은 분쟁이 발생할 때, 애자일 리더는 팀과 함께 작업 합의를 개발해야 한다. 협력적 규범은 공유된 기대를 수립하고 갈등을 해결한다. 팀원 제거(A)는 역학을 방해한다. 관리자에게 에스컬레이션(B)은 팀 자율성을 약화시킨다. 역할과 책임 검토(C)는 유용하지만 행동적 분쟁을 해결하기에 불충분하다.
988 | A newly formed team has become accustomed to agile practices. The project lead has noticed that while they are performing according to expectations, there is boredom with daily team practices among many of the team members. What should the project lead do in this situation? | Speak with individual team members to determine what they would like to do to improve the situation in the team 595 | Challenge the team to find new ways to achieve higher levels of performance to improve the situation. | Have the team inform senior management of the situation and ask for recommendations. | Allow the team to self-organize and have them analyze the situation in their retrospective session and self correct |  | D | When an agile team performs well but shows boredom with daily practices, the project lead should allow the team to self-organize and have them analyze the situation in their retrospective session and self-correct. Agile teams are expected to inspect and adapt their own processes. Speaking with individuals (A) bypasses team self-organization. Challenging the team to higher performance (B) does not address the boredom. Asking senior management for recommendations (C) undermines team autonomy. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scaled Agile | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 새로 구성된 팀이 애자일 실무에 익숙해졌다. 프로젝트 리드는 기대에 따라 수행하고 있지만, 많은 팀원들 사이에 일일 팀 실무에 대한 권태가 있음을 발견했다. 프로젝트 리드는 이 상황에서 무엇을 해야 하는가? | 개별 팀원들과 대화하여 팀 상황을 개선하기 위해 무엇을 하고 싶은지 파악한다. | 상황을 개선하기 위해 더 높은 수준의 성과를 달성할 새로운 방법을 찾도록 팀에 도전한다. | 팀이 상급 경영진에게 상황을 알리고 권고를 요청하도록 한다. | 팀이 자기 조직화하여 회고 세션에서 상황을 분석하고 스스로 수정하도록 허용한다. |  | D | 애자일 팀이 잘 수행하지만 일일 실무에 대한 권태를 보일 때, 프로젝트 리드는 팀이 자기 조직화하여 회고 세션에서 상황을 분석하고 스스로 수정하도록 허용해야 한다. 애자일 팀은 자체 프로세스를 검사하고 적응할 것으로 기대된다. 개인과 대화(A)는 팀 자기 조직화를 우회한다. 더 높은 성과에 도전(B)은 권태를 해결하지 않는다. 상급 경영진에게 권고 요청(C)은 팀 자율성을 약화시킨다.
989 | A newly commissioned project has had trouble recruiting team members because the turnover rate is high. The human resource (HR) manager has conducted several exit interviews. Many team members have expressed that the project manager has inadequate relationship management competencies. The project manager explains that the exiting team members were lazy. What should the project manager do to prevent this high turnover rate from continuing? | Be more involved in the team member recruitment process to ensure qualified team members are chosen. | Develop relationship skills as a leader and also develop the teams' emotional intelligence skills. | Explain to the recruiting manager that a project is temporary in nature, making it different than an operational environment. | Avoid micromanaging the team, enforce stricter rules, and monitor employees. |  | B | When team members leave citing inadequate relationship management and the PM blames them, the project manager should develop relationship skills as a leader and develop the team's emotional intelligence skills. Improved interpersonal competencies create a positive environment that reduces turnover. Being more involved in recruiting (A) does not address the root cause. Explaining the temporary nature of projects (C) dismisses the feedback. Enforcing stricter rules (D) worsens the relationship problem. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 새로 위임된 프로젝트가 높은 이직률로 인해 팀원 모집에 어려움을 겪고 있다. 인사(HR) 관리자가 여러 퇴직 인터뷰를 실시했다. 많은 팀원들이 프로젝트 관리자의 관계 관리 역량이 부적절하다고 표현했다. 프로젝트 관리자는 퇴직하는 팀원들이 게으르다고 설명한다. 이 높은 이직률이 계속되는 것을 방지하기 위해 프로젝트 관리자는 무엇을 해야 하는가? | 자격을 갖춘 팀원이 선택되도록 팀원 모집 프로세스에 더 많이 관여한다. | 리더로서 관계 기술을 개발하고 팀의 감성 지능 기술도 개발한다. | 채용 관리자에게 프로젝트는 본질적으로 일시적이므로 운영 환경과 다르다고 설명한다. | 팀에 대한 마이크로매니징을 피하고, 더 엄격한 규칙을 시행하며, 직원을 모니터링한다. |  | B | 팀원들이 부적절한 관계 관리를 언급하며 떠나고 PM이 그들을 비난할 때, 프로젝트 관리자는 리더로서 관계 기술을 개발하고 팀의 감성 지능 기술을 개발해야 한다. 향상된 대인 역량은 이직률을 줄이는 긍정적인 환경을 만든다. 모집에 더 많이 관여(A)는 근본 원인을 해결하지 않는다. 프로젝트의 일시적 본질 설명(C)은 피드백을 무시한다. 더 엄격한 규칙 시행(D)은 관계 문제를 악화시킨다.
990 | A feature has been added to the iteration backlog that has been prioritized by the project sponsor over other critical security patches. What should the project manager do? | Give all the work packages parallel priority and continue activities. | Meet with the project sponsor to discuss the feature with the product owner. | Push back on the feature because it is not an immediate priority. | Perform a risk analysis and then meet with the project sponsor to discuss it. |  | C | When the project sponsor prioritizes a feature over critical security patches, the project manager should perform a risk analysis and then meet with the project sponsor to discuss it. Security patches address vulnerabilities that could have serious consequences if delayed. A risk analysis provides objective data on the potential impact of deferring security work, enabling an informed discussion with the sponsor about priorities. Giving all work packages parallel priority (A) ignores the trade-off decision. Pushing back without analysis (C) lacks supporting evidence. Meeting with the sponsor without risk analysis (B) may not provide the compelling data needed to influence the prioritization. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 스폰서가 다른 중요한 보안 패치보다 우선순위를 매긴 기능이 반복 백로그에 추가되었다. 프로젝트 관리자는 무엇을 해야 하는가? | 모든 작업 패키지에 병렬 우선순위를 부여하고 활동을 계속한다. | 프로젝트 스폰서와 만나 제품 책임자와 해당 기능을 논의한다. | 즉각적인 우선순위가 아니므로 해당 기능에 반대한다. | 리스크 분석을 수행한 후 프로젝트 스폰서와 만나 논의한다. |  | C | 프로젝트 스폰서가 중요한 보안 패치보다 기능을 우선시할 때, 프로젝트 관리자는 리스크 분석을 수행한 후 프로젝트 스폰서와 만나 논의해야 한다. 보안 패치는 지연 시 심각한 결과를 초래할 수 있는 취약점을 해결한다. 리스크 분석은 보안 작업 연기의 잠재적 영향에 대한 객관적 데이터를 제공하여 스폰서와 정보에 기반한 우선순위 논의를 가능하게 한다. 모든 작업 패키지에 병렬 우선순위 부여(A)는 절충 결정을 무시한다. 분석 없이 반대(C)는 뒷받침하는 증거가 부족하다. 리스크 분석 없이 스폰서와 만남(B)은 우선순위 변경에 필요한 설득력 있는 데이터를 제공하지 못할 수 있다.
991 | A project manager is implementing a project similar to a previous one that required strict adherence to occupational health and safety (OHS). Both projects are for the same client whose business environment is highly regulated. However, this time the client does not appear to be concerned about OHS requirements. What should the project manager do first? | Discuss the OHS requirements with the client. | Relax the OHS requirements as the client is not concerned. | Discuss the OHS requirements with the regulatory organization. | Apply the same OHS requirements as the previous project. |  | A | Even though the client does not appear concerned about occupational health and safety requirements, the project manager should first discuss the OHS requirements with the client. In a highly regulated business environment, compliance is mandatory regardless of the client's expressed level of concern. Open communication ensures alignment on safety obligations and prevents regulatory breaches. Relaxing OHS requirements (B) is inappropriate and exposes both parties to legal and safety risks. Discussing with the regulatory organization (C) may cause unnecessary complexity without first clarifying the client's position. Applying the same OHS requirements as the previous project (D) assumes identical conditions without confirming current client expectations and regulatory context. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 직업 건강 및 안전(OHS)을 엄격하게 준수해야 했던 이전 프로젝트와 유사한 프로젝트를 실행하고 있다. 두 프로젝트 모두 비즈니스 환경이 고도로 규제되는 동일한 고객을 위한 것이다. 그러나 이번에는 고객이 OHS 요구사항에 관심이 없는 것으로 보인다. 프로젝트 관리자는 먼저 무엇을 해야 하는가? | 고객과 OHS 요구사항을 논의한다. | 고객이 관심이 없으므로 OHS 요구사항을 완화한다. | 규제 기관과 OHS 요구사항을 논의한다. | 이전 프로젝트와 동일한 OHS 요구사항을 적용한다. |  | A | 고객이 직업 건강 및 안전 요구사항에 관심이 없어 보이더라도, 프로젝트 관리자는 먼저 고객과 OHS 요구사항을 논의해야 한다. 고도로 규제된 비즈니스 환경에서 규정 준수는 고객의 표현된 관심 수준과 관계없이 필수적이다. 개방적 소통은 안전 의무에 대한 정렬을 보장하고 규제 위반을 방지한다. OHS 요구사항 완화(B)는 부적절하며 양측을 법적 및 안전 위험에 노출시킨다. 규제 기관과 논의(C)는 먼저 고객의 입장을 확인하지 않고 불필요한 복잡성을 초래할 수 있다. 이전 프로젝트와 동일한 OHS 요구사항 적용(D)은 현재 고객 기대와 규제 맥락을 확인하지 않고 동일한 조건을 가정한다.
992 | A project team has established contracts for purchasing vehicles and construction services. In the middle of project execution, the team learns that the vehicle supplier cannot deliver the vehicles. There is not enough time to find a new supplier without delaying the project. Which action should the project manager take to procure the vehicles? | Arrange a meeting with the client to request additional time to find a new supplier. | Procure the vehicles from another supplier and report the change to the change control board (CCB) later. | Ask the technical team to revise the requirements, even if it requires extra budget. | Review the existing service contracts to find an option to help procure the vehicles. |  | D | When the original vehicle supplier cannot deliver and there is insufficient time to find a new supplier, the project manager should review existing service contracts for clauses or options that could facilitate vehicle procurement. Exploring contractual avenues and existing relationships is a procurement management best practice before seeking external solutions. Requesting additional time from the client (A) delays the project without exploring available options. Procuring from another supplier and reporting to the CCB afterward (B) bypasses proper change control. Revising technical requirements with extra budget (C) changes the project scope rather than addressing the procurement problem. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 차량 구매와 건설 서비스를 위한 계약을 체결했다. 프로젝트 실행 중간에 팀은 차량 공급업체가 차량을 납품할 수 없다는 것을 알게 되었다. 프로젝트를 지연시키지 않고 새 공급업체를 찾을 시간이 충분하지 않다. 프로젝트 관리자는 차량을 조달하기 위해 어떤 조치를 취해야 하는가? | 고객과 회의를 준비하여 새 공급업체를 찾기 위한 추가 시간을 요청한다. | 다른 공급업체에서 차량을 조달하고 나중에 변경 통제 위원회(CCB)에 변경을 보고한다. | 추가 예산이 필요하더라도 기술 팀에 요구사항을 수정하도록 요청한다. | 기존 서비스 계약을 검토하여 차량 조달을 도울 수 있는 옵션을 찾는다. |  | D | 원래 차량 공급업체가 납품할 수 없고 새 공급업체를 찾을 시간이 부족할 때, 프로젝트 관리자는 기존 서비스 계약에서 차량 조달을 촉진할 수 있는 조항이나 옵션을 검토해야 한다. 계약 경로와 기존 관계를 탐색하는 것은 외부 솔루션을 찾기 전에 조달 관리 모범 사례이다. 고객에게 추가 시간 요청(A)은 가용 옵션을 탐색하지 않고 프로젝트를 지연시킨다. 다른 공급업체에서 조달 후 CCB에 보고(B)는 적절한 변경 통제를 우회한다. 추가 예산으로 기술 요구사항 수정(C)은 조달 문제를 해결하지 않고 프로젝트 범위를 변경한다.
993 | During project execution, the risk owner is monitoring the critical speed rate of a power engine to eventually trigger the defined risk-response strategy. During the risk assessment and management process phase, it was defined that the power engine has the following characteristics: 1,600 rpm (rate-per-minute) -> stops working and crashes the system, 1,500 rpm (rate-per-minute) -> warns of max rate allowed, 1,400 rpm (rate-per-minute) -> reduces the power and brakes the engine. Which of the following statements is correct? | 1600 rpm is a project issue; 1,500 rpm is a project risk; and1,400 rpm is an event that triggers a response strategy | 0 1,600 rpm is a project risk,1,500 rpm is an event that triggers a response strategy and 1,400 rpm is a project issue. | 1.600 rpm is an event that triggers a response strategy.1,500 rpm is a project issue and 1,400 rpm is a project risk. | 1,600 rpm is a project issue,1,500 rpm is an event that triggers a response strategy and 1,400 rpm is a project risk |  | A | In this risk monitoring scenario: 1,600 rpm is a project issue because it causes the system to stop working and crash—it represents an event that has already materialized into a problem. 1,500 rpm is a project risk because it warns of maximum rate allowed—it represents an uncertain condition that could lead to negative consequences. 1,400 rpm is an event that triggers a response strategy because it activates the defined action of reducing power and braking the engine to prevent escalation. The other options incorrectly categorize these thresholds. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 실행 중 리스크 소유자가 정의된 리스크 대응 전략을 궁극적으로 발동하기 위해 동력 엔진의 임계 속도율을 모니터링하고 있다. 리스크 평가 및 관리 프로세스 단계에서 동력 엔진이 다음과 같은 특성을 가지는 것으로 정의되었다: 1,600 rpm(분당 회전수) → 작동 중지 및 시스템 충돌, 1,500 rpm(분당 회전수) → 허용 최대 속도 경고, 1,400 rpm(분당 회전수) → 출력 감소 및 엔진 제동. 다음 중 올바른 설명은? | 1,600 rpm은 프로젝트 이슈이고, 1,500 rpm은 프로젝트 리스크이며, 1,400 rpm은 대응 전략을 발동하는 이벤트이다. | 1,600 rpm은 프로젝트 리스크이고, 1,500 rpm은 대응 전략을 발동하는 이벤트이며, 1,400 rpm은 프로젝트 이슈이다. | 1,600 rpm은 대응 전략을 발동하는 이벤트이고, 1,500 rpm은 프로젝트 이슈이며, 1,400 rpm은 프로젝트 리스크이다. | 1,600 rpm은 프로젝트 이슈이고, 1,500 rpm은 대응 전략을 발동하는 이벤트이며, 1,400 rpm은 프로젝트 리스크이다. |  | A | 이 리스크 모니터링 시나리오에서: 1,600 rpm은 시스템이 작동을 멈추고 충돌하므로 프로젝트 이슈이다—이미 문제로 현실화된 이벤트를 나타낸다. 1,500 rpm은 최대 허용 속도를 경고하므로 프로젝트 리스크이다—부정적 결과를 초래할 수 있는 불확실한 조건을 나타낸다. 1,400 rpm은 출력 감소 및 엔진 제동이라는 정의된 조치를 활성화하므로 대응 전략을 발동하는 이벤트이다. 다른 옵션들은 이러한 임계값을 잘못 분류한다.
994 | A project team is working on the design of a solution for a complex project. Due to a lack of clarity of the customer's requirements, daily meetings were agreed upon between the team and the customer. There are a few external contractors in the project who do not agree with this idea as they feel it is a waste of time. What should the project manager do? | Warn and penalize the contractors who do not attend the meeting. | Ask the contractors to meet with the customer independently. | Welcome and involve the contractors as part of the project team. | Ask the customer to develop a document with the requirements. |  | C | When external contractors disagree with daily customer meetings on a complex project with unclear requirements, the project manager should welcome and involve the contractors as part of the project team. Full inclusion fosters collaboration, ensures all team members understand the project objectives, and reduces resistance through engagement. Warning and penalizing contractors (A) creates an adversarial environment. Asking contractors to meet customers independently (B) fragments communication. Asking the customer to document requirements (D) reduces interaction rather than building collaborative understanding. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | 프로젝트 팀이 복잡한 프로젝트의 솔루션 설계 작업을 하고 있다. 고객의 요구사항이 명확하지 않아 팀과 고객 간의 일일 회의가 합의되었다. 프로젝트에 이 아이디어에 동의하지 않는 외부 계약자 몇 명이 있으며, 시간 낭비라고 느끼고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 회의에 참석하지 않는 계약자에게 경고하고 벌칙을 부과한다. | 계약자에게 고객과 별도로 만나도록 요청한다. | 계약자를 프로젝트 팀의 일원으로 환영하고 참여시킨다. | 고객에게 요구사항을 담은 문서를 작성하도록 요청한다. |  | C | 불명확한 요구사항이 있는 복잡한 프로젝트에서 외부 계약자가 일일 고객 회의에 동의하지 않을 때, 프로젝트 관리자는 계약자를 프로젝트 팀의 일원으로 환영하고 참여시켜야 한다. 완전한 포용은 협력을 촉진하고, 모든 팀원이 프로젝트 목표를 이해하도록 보장하며, 참여를 통해 저항을 줄인다. 계약자에게 경고 및 벌칙(A)은 적대적 환경을 만든다. 계약자에게 별도 만남 요청(B)은 소통을 분산시킨다. 고객에게 요구사항 문서화 요청(D)은 협력적 이해를 구축하지 않고 상호작용을 줄인다.
995 | A project team is experiencing communication issues during project execution. The project manager realizes that the communications management plan needs to be reviewed. Which are three fundamental actions the project manager should take? (Choose 3) | Decide on the frequency of communications. | Identify the level of detail needed by different stakeholders. | Determine the appropriate methods of communication. | Define key performance indicators (KPIs) to measure and report. | Obtain executive approval on the communications management plan. | A, B, C | When reviewing the communications management plan due to communication issues, three fundamental actions are: decide on the frequency of communications (A) to establish regular cadence, identify the level of detail needed by different stakeholders (B) to tailor information appropriately, and determine the appropriate methods of communication (C) to match channel to audience and message type. These three elements—frequency, detail level, and method—form the foundation of effective communication planning. Defining KPIs to measure and report (D) is a monitoring activity, not a fundamental communication planning action. Obtaining executive approval (E) is a governance step that follows plan development. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 프로젝트 실행 중 커뮤니케이션 문제를 겪고 있다. 프로젝트 관리자는 커뮤니케이션 관리 계획을 검토해야 함을 인식했다. 프로젝트 관리자가 취해야 할 세 가지 기본 조치는? (3개 선택) | 커뮤니케이션 빈도를 결정한다. | 다양한 이해관계자가 필요로 하는 세부 수준을 식별한다. | 적절한 커뮤니케이션 방법을 결정한다. | 측정 및 보고를 위한 핵심 성과 지표(KPI)를 정의한다. | 커뮤니케이션 관리 계획에 대한 경영진 승인을 받는다. | A, B, C | 커뮤니케이션 문제로 인해 커뮤니케이션 관리 계획을 검토할 때, 세 가지 기본 조치는: 정기적 주기를 설정하기 위한 커뮤니케이션 빈도 결정(A), 정보를 적절히 맞춤화하기 위해 다양한 이해관계자에게 필요한 세부 수준 식별(B), 채널을 대상과 메시지 유형에 맞추기 위한 적절한 커뮤니케이션 방법 결정(C). 이 세 가지 요소—빈도, 세부 수준, 방법—가 효과적인 커뮤니케이션 계획의 기초를 형성한다. 측정 및 보고를 위한 KPI 정의(D)는 모니터링 활동이지 기본적인 커뮤니케이션 계획 조치가 아니다. 경영진 승인 획득(E)은 계획 개발 후의 거버넌스 단계이다.
996 | A company just started managing a project using an agile approach. Due to this change, the general manager is worried about the scope definition process for upcoming projects. What should the project manager do to ensure the project scope is completely defined? | Ask the general manager to review every requirement to ensure all projects will deliver the requested products | Help sponsors and stakeholders craft the product vision, and bring the team and product owner together to clarify expectations | Meet with the general manager and convince them to return to using predictive approaches to avoid any risk. | Ask for a budget increase to implement a double-check process to ensure every business need is included in the requirements |  | B | When the general manager is worried about scope definition for agile projects, the project manager should help sponsors and stakeholders craft the product vision, and bring the team and product owner together to clarify expectations. Product vision and collaborative refinement ensure iterative scope definition. Asking the GM to review every requirement (A) is micromanagement. Convincing a return to predictive (C) undermines the agile adoption. Requesting a budget increase for double-checking (D) adds unnecessary overhead. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Build an Empowered Culture | Plan Scope Management | Traditional PM | 회사가 애자일 전달 접근 방식을 사용하여 프로젝트를 관리하기 시작했다. 이 변경으로 인해 총괄 관리자가 향후 프로젝트의 범위 정의 프로세스에 대해 우려하고 있다. 프로젝트 관리자는 프로젝트 범위가 완전히 정의되도록 보장하기 위해 무엇을 해야 하는가? | 총괄 관리자에게 모든 프로젝트가 요청된 제품을 전달하도록 모든 요구사항을 검토하도록 요청한다. | 스폰서와 이해관계자가 제품 비전을 수립하도록 돕고, 팀과 제품 책임자를 함께 모아 기대치를 명확히 한다. | 총괄 관리자와 만나 리스크를 피하기 위해 예측형 접근 방식으로 돌아가도록 설득한다. | 모든 비즈니스 요구가 요구사항에 포함되도록 이중 확인 프로세스를 구현하기 위한 예산 증액을 요청한다. |  | B | 총괄 관리자가 애자일 프로젝트의 범위 정의에 대해 우려할 때, 프로젝트 관리자는 스폰서와 이해관계자가 제품 비전을 수립하도록 돕고, 팀과 제품 책임자를 함께 모아 기대치를 명확히 해야 한다. 제품 비전과 협력적 정제가 반복적 범위 정의를 보장한다. 총괄 관리자에게 모든 요구사항 검토 요청(A)은 마이크로매니지먼트이다. 예측형으로 돌아가도록 설득(C)은 애자일 도입을 약화시킨다. 이중 확인을 위한 예산 증액 요청(D)은 불필요한 오버헤드를 추가한다.
997 | A project for Company A was successfully delivered within scope, schedule, and budget by the end of the last iteration. However, during the project celebration ceremony, one of the business stakeholders says they perceive the project as a failure as it did not add any business value. What should the project manager have done to avoid this perception? | Defined product backlog priorities with the sponsor and key stakeholders to deliver 1185 business benefits | Confirmed that there is a communications management plan in place to make business stakeholders aware of the success | Involved the business stakeholders in the sprint review | Implemented a closing survey for key stakeholders |  | A | When a stakeholder perceives a successfully delivered project as a failure because it did not add business value, the project manager should have defined product backlog priorities with the sponsor and key stakeholders to deliver business benefits. Value-driven prioritization ensures stakeholder expectations align with delivery. Having a communications plan (B) addresses awareness, not value alignment. Sprint review involvement (C) provides feedback but does not set priorities. A closing survey (D) is too late. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Risk | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | A사의 프로젝트가 마지막 이터레이션 종료 시점에 범위, 일정, 예산 내에서 성공적으로 전달되었다. 그러나 프로젝트 축하 행사에서 비즈니스 이해관계자 중 한 명이 비즈니스 가치를 추가하지 못했으므로 프로젝트가 실패라고 인식한다고 말했다. 프로젝트 관리자는 이 인식을 피하기 위해 무엇을 했어야 하는가? | 비즈니스 혜택을 전달하기 위해 스폰서 및 주요 이해관계자와 함께 제품 백로그 우선순위를 정의했어야 한다. | 비즈니스 이해관계자가 성공을 인식하도록 커뮤니케이션 관리 계획이 마련되어 있는지 확인했어야 한다. | 비즈니스 이해관계자를 스프린트 리뷰에 참여시켰어야 한다. | 주요 이해관계자를 위한 종료 설문조사를 실시했어야 한다. |  | A | 이해관계자가 성공적으로 전달된 프로젝트를 비즈니스 가치를 추가하지 못했다고 실패로 인식할 때, 프로젝트 관리자는 비즈니스 혜택을 전달하기 위해 스폰서 및 주요 이해관계자와 함께 제품 백로그 우선순위를 정의했어야 한다. 가치 중심 우선순위화는 이해관계자 기대치와 전달을 정렬시킨다. 커뮤니케이션 계획(B)은 인식을 다루지 가치 정렬을 다루지 않는다. 스프린트 리뷰 참여(C)는 피드백을 제공하지만 우선순위를 설정하지 않는다. 종료 설문조사(D)는 너무 늦다.
998 | A project manager is leading a new project that is in the initiation phase. The project will build a new type of software technology service that has never existed at the organization before and will reengineer the business process for several operations teams. The project manager needs to determine the project management approach to be used, and there are many team members and stakeholders who have contradictory opinions. What should the project manager do? | Meet with the stakeholders to determine the approach using the project goals and desired outcomes. | Leverage hybrid methods as the project has a blend of work that needs to bring in both agile and predictive methods, | Leverage agile methods only as the project pertains to software implementation, which can be broken into increments. | Determine what methods the team has been trained on and utilize those methods for the project. |  | B | When determining the approach for a new project with contradictory opinions among team members and stakeholders, the project manager should leverage hybrid methods since the project blends software development and business process reengineering. Hybrid combines agile and predictive for different work types. Meeting stakeholders to determine approach (A) is valuable but does not specify a methodology. Using only agile (C) ignores predictive needs. Using only trained methods (D) limits flexibility. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Resources | Executing | Focus on Value | Acquire Resources | Hybrid/Tailoring | 프로젝트 관리자가 착수 단계에 있는 새 프로젝트를 이끌고 있다. 이 프로젝트는 조직에서 이전에 존재하지 않았던 새로운 유형의 소프트웨어 기술 서비스를 구축하고 여러 운영 팀의 비즈니스 프로세스를 재설계할 것이다. 프로젝트 관리자는 사용할 프로젝트 관리 접근 방식을 결정해야 하며, 상반된 의견을 가진 많은 팀원과 이해관계자가 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 목표와 원하는 결과를 사용하여 접근 방식을 결정하기 위해 이해관계자와 만난다. | 프로젝트가 애자일과 예측형 방법 모두를 필요로 하는 작업이 혼합되어 있으므로 하이브리드 방법을 활용한다. | 프로젝트가 증분으로 나눌 수 있는 소프트웨어 구현에 관련되므로 애자일 방법만 활용한다. | 팀이 교육받은 방법을 파악하고 프로젝트에 해당 방법을 활용한다. |  | B | 팀원과 이해관계자 간에 상반된 의견이 있는 새 프로젝트의 접근 방식을 결정할 때, 프로젝트 관리자는 소프트웨어 개발과 비즈니스 프로세스 재설계가 혼합된 프로젝트이므로 하이브리드 방법을 활용해야 한다. 하이브리드는 다양한 작업 유형에 대해 애자일과 예측형을 결합한다. 이해관계자와 만나 접근 방식 결정(A)은 가치 있지만 방법론을 특정하지 않는다. 애자일만 사용(C)은 예측형 필요를 무시한다. 교육받은 방법만 사용(D)은 유연성을 제한한다.
999 | A project manager works at an organization that intends to use an agile delivery approach. The product owner asks the project manager what the benefit of agile delivery is from a project evaluation perspective. How should the project manager reply to the product owner? | The cost is reduced: therefore, the total value delivered is higher. | The functionality is delivered early; therefore, more value is delivered. | The team productivity is higher; therefore, more value is delivered, | The risk is significantly reduced; therefore, more value Is delivered. |  | B | From a project evaluation perspective, the benefit of agile delivery is that functionality is delivered early, therefore more value is delivered. Early incremental delivery provides faster ROI. Cost reduction (A) is not the primary benefit. Higher team productivity (C) may result but is not the evaluation benefit. Risk reduction (D) is a benefit but not the primary project evaluation advantage. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 관리자가 애자일 전달 접근 방식을 사용하려는 조직에서 근무하고 있다. 제품 책임자가 프로젝트 관리자에게 프로젝트 평가 관점에서 애자일 전달의 이점이 무엇인지 묻는다. 프로젝트 관리자는 제품 책임자에게 어떻게 답변해야 하는가? | 비용이 절감되어 전달되는 총 가치가 더 높다. | 기능이 조기에 전달되어 더 많은 가치가 전달된다. | 팀 생산성이 더 높아 더 많은 가치가 전달된다. | 리스크가 크게 감소하여 더 많은 가치가 전달된다. |  | B | 프로젝트 평가 관점에서 애자일 전달의 이점은 기능이 조기에 전달되어 더 많은 가치가 전달된다는 것이다. 조기 증분 전달은 더 빠른 ROI를 제공한다. 비용 절감(A)은 주요 이점이 아니다. 높은 팀 생산성(C)은 결과일 수 있지만 평가 이점이 아니다. 리스크 감소(D)는 이점이지만 주요 프로젝트 평가 장점이 아니다.
1000 | A sales team working on an IT deployment project approached the project manager on several occasions and complained about nonpayment of their overtime pay. The project manager realized that other team members are receiving their overtime pay. What should the project manager do next? | Escalate the issue to the functional manager | Have a discussion with the sales team to find a solution to the issue | Validate the reason and add it as an issue in the issue log | Direct the sales team to speak with accounting to resolve the issue |  | C | When the sales team complains about nonpayment of overtime while other teams receive theirs, the project manager should validate the reason and add it as an issue in the issue log. Verification and documentation enable structured resolution. Escalating to the functional manager (A) acts before investigation. Having a discussion with the sales team (B) is informal. Directing the team to accounting (D) deflects responsibility. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Risk & Issue Management | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | IT 배포 프로젝트에서 일하는 영업 팀이 여러 차례 프로젝트 관리자에게 접근하여 초과 근무 수당 미지급에 대해 불만을 제기했다. 프로젝트 관리자는 다른 팀원들은 초과 근무 수당을 받고 있음을 인식했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 기능 관리자에게 이슈를 에스컬레이션한다. | 영업 팀과 논의하여 이슈에 대한 해결책을 찾는다. | 이유를 검증하고 이슈 로그에 이슈로 추가한다. | 영업 팀에게 회계부서와 대화하여 이슈를 해결하도록 지시한다. |  | C | 영업 팀이 초과 근무 수당 미지급에 대해 불만을 제기하고 다른 팀은 수당을 받고 있을 때, 프로젝트 관리자는 이유를 검증하고 이슈 로그에 이슈로 추가해야 한다. 확인과 문서화는 구조화된 해결을 가능하게 한다. 기능 관리자에게 에스컬레이션(A)은 조사 전에 행동하는 것이다. 영업 팀과 논의(B)는 비공식적이다. 팀에게 회계부서로 지시(D)는 책임을 전가한다.
1001 | A project team has not been meeting its deliverables because they are not receiving adequate resources to do their job. What should the project manager do for the team to meet the upcoming deliverables? | Ask the team to adapt based on their current resources. | Replan the upcoming deliverables based on the available tools. | Plan a meeting with the stakeholders to get more resources. | Ask the project sponsor to provide the needed resources. |  | D | The PM should request the project sponsor to provide needed resources. Effective resource management ensures team members have the necessary skills, tools, and support. When resource gaps are identified, the PM should escalate to the appropriate authority for resolution rather than attempting workarounds that compromise project quality or team performance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 프로젝트 팀이 업무를 수행하기 위한 적절한 자원을 받지 못해 산출물을 충족시키지 못하고 있다. 프로젝트 관리자는 팀이 다가오는 산출물을 충족시키기 위해 무엇을 해야 하는가? | 팀에게 현재 자원에 기반하여 적응하도록 요청한다. | 사용 가능한 도구에 기반하여 다가오는 산출물을 재계획한다. | 더 많은 자원을 확보하기 위해 이해관계자와 회의를 계획한다. | 프로젝트 스폰서에게 필요한 자원을 제공하도록 요청한다. |  | D | PM은 프로젝트 스폰서에게 필요한 자원을 제공하도록 요청해야 한다. 효과적인 자원 관리는 팀원들이 필요한 기술, 도구, 지원을 갖추도록 보장한다. 자원 격차가 식별되면 PM은 품질이나 팀 성과를 저해하는 우회 방법을 시도하기보다 적절한 권한에 에스컬레이션해야 한다.
1002 | A company is initiating a project to decommission inefficient sales channels. Several stakeholders argue that one channel that indicates a downturn in generating value is still more efficient than some of the channels that are planned to remain. What should the project manager do? | Escalate the objection to the steering committee and human resources (HR) as a personal intimidation incident. | Review and update the success criteria to ensure that the channel is not decommissioned. 1038 | Inform the stakeholders that the list of channels to be decommissioned was approved by the CEO. | Plan for incremental and iterative delivery based on feedback from the marketing and sales team. |  | D | When stakeholders argue a sales channel flagged for decommissioning still generates more value than some channels being retained, the project manager should plan for incremental and iterative delivery based on feedback from marketing and sales teams. Data-driven iterative assessment validates assumptions. Escalating as intimidation (A) is inappropriate. Updating success criteria (B) changes criteria without evidence. Informing that the CEO approved (C) dismisses valid concerns. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 회사가 비효율적인 영업 채널을 폐쇄하는 프로젝트를 시작하고 있다. 여러 이해관계자가 가치 창출이 하락 추세를 보이는 한 채널이 유지될 예정인 일부 채널보다 여전히 더 효율적이라고 주장한다. 프로젝트 관리자는 무엇을 해야 하는가? | 운영위원회와 인사부(HR)에 개인 위협 사건으로 이의를 에스컬레이션한다. | 해당 채널이 폐쇄되지 않도록 성공 기준을 검토하고 업데이트한다. | 폐쇄 대상 채널 목록이 CEO에 의해 승인되었음을 이해관계자에게 알린다. | 마케팅 및 영업 팀의 피드백에 기반하여 점진적이고 반복적인 전달을 계획한다. |  | D | 이해관계자가 폐쇄 대상 영업 채널이 유지되는 일부 채널보다 더 많은 가치를 창출한다고 주장할 때, 프로젝트 관리자는 마케팅 및 영업 팀의 피드백에 기반하여 점진적이고 반복적인 전달을 계획해야 한다. 데이터 기반 반복적 평가가 가정을 검증한다. 위협으로 에스컬레이션(A)은 부적절하다. 성공 기준 업데이트(B)는 근거 없이 기준을 변경한다. CEO가 승인했다고 알리기(C)는 유효한 우려를 무시한다.
1003 | During a scope validation exercise toward the end of a project, a project manager realizes that some operational project requirements were not captured in the project scope of work. Although completing these items will have an impact on the project's completion date, it will increase the likelihood of customer acceptance. What should the project manager do to address the issue? | Issue a change request to remove items from the scope of work and keep the project on schedule. | Issue a change request to include the additional scope, and track the completion of the work items. | Document the issue in the lessons learned document, and discuss this with the project sponsor. | Arrange to pass the cost to the operational area since the customer will benefit. |  | B | When scope validation reveals uncaptured operational requirements near project end that would increase customer acceptance but impact the completion date, the project manager should issue a change request to include the additional scope and track completion. Formal change control manages the trade-off. Removing items to keep schedule (A) compromises deliverables. Documenting in lessons learned (C) does not resolve the gap. Passing costs to operations (D) creates stakeholder conflict. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 프로젝트 종료 무렵의 범위 검증 활동 중, 프로젝트 관리자가 일부 운영 프로젝트 요구사항이 프로젝트 작업 범위에 포함되지 않았음을 발견했다. 이 항목들을 완료하면 프로젝트 완료일에 영향을 미치지만, 고객 수락 가능성을 높일 것이다. 프로젝트 관리자는 이 이슈를 해결하기 위해 무엇을 해야 하는가? | 작업 범위에서 항목을 제거하고 프로젝트를 일정대로 유지하는 변경 요청을 발행한다. | 추가 범위를 포함하는 변경 요청을 발행하고 작업 항목의 완료를 추적한다. | 교훈 문서에 이슈를 기록하고 프로젝트 스폰서와 논의한다. | 고객이 혜택을 받으므로 비용을 운영 부서에 전가하도록 준비한다. |  | B | 범위 검증 시 프로젝트 종료 무렵에 미포착된 운영 요구사항이 발견되어 고객 수락을 높이지만 완료일에 영향을 미칠 때, 프로젝트 관리자는 추가 범위를 포함하는 변경 요청을 발행하고 완료를 추적해야 한다. 공식적인 변경 통제가 트레이드오프를 관리한다. 일정 유지를 위해 항목 제거(A)는 산출물을 손상시킨다. 교훈에 기록(C)은 격차를 해결하지 않는다. 운영 부서에 비용 전가(D)는 이해관계자 갈등을 초래한다.
1004 | A project manager is leading a project with several stakeholders in other functional areas of the company. One of these stakeholders has just been promoted to lead another functional area, and remains a stakeholder for this project. What should the project manager have the project team update to ensure proper communications to stakeholders? | Stakeholder engagement plan | Project management plan | Communications management plan | Stakeholder register |  | D | When a stakeholder is promoted to lead another functional area and remains on the project, the project team should update the stakeholder register. The register captures roles, influence, and contact information. Updating the project management plan (B) is unnecessary for a role change. The stakeholder engagement plan (A) may need updates later. The communications management plan (C) addresses channels, not stakeholder profiles. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 회사의 다른 기능 부서에 여러 이해관계자가 있는 프로젝트를 이끌고 있다. 이 이해관계자 중 한 명이 다른 기능 부서를 이끌도록 승진했으며, 이 프로젝트의 이해관계자로 남아 있다. 프로젝트 관리자는 이해관계자에 대한 적절한 커뮤니케이션을 보장하기 위해 프로젝트 팀이 무엇을 업데이트하도록 해야 하는가? | 이해관계자 참여 계획 | 프로젝트 관리 계획 | 커뮤니케이션 관리 계획 | 이해관계자 레지스터 |  | D | 이해관계자가 다른 기능 부서를 이끌도록 승진하고 프로젝트에 남아 있을 때, 프로젝트 팀은 이해관계자 레지스터를 업데이트해야 한다. 레지스터는 역할, 영향력, 연락처 정보를 포착한다. 프로젝트 관리 계획 업데이트(B)는 역할 변경에 불필요하다. 이해관계자 참여 계획(A)은 나중에 업데이트가 필요할 수 있다. 커뮤니케이션 관리 계획(C)은 채널을 다루지 이해관계자 프로필은 다루지 않는다.
1005 | A project manager is managing a project that has a new sponsor who is cutting the budget. As a servant leader, how should the project manager handle the budget cuts with the team? | Notify the project sponsor that the budget reduction will require a schedule slip and scope reduction. | Meet with the schedule coordinator and financial analyst to tell them which budget lines to reduce and where to release slack | Inform each team member that they must release a portion of their budget but must remain on schedule with no change to the scope | Collaborate with the team to assess the impact of the change on the project and recommend an updated project plan |  | D | When the project budget is cut, the PM should collaborate with the team to assess the change's impact on scope, schedule, and quality. Together, they should develop an updated project plan reflecting the reduced budget. This collaborative approach aligns with servant leadership principles—emphasizing team empowerment, shared decision-making, and transparent communication about constraints. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 프로젝트 관리자가 예산을 삭감하는 새 스폰서가 있는 프로젝트를 관리하고 있다. 서번트 리더로서 프로젝트 관리자는 팀과 예산 삭감을 어떻게 처리해야 하는가? | 프로젝트 스폰서에게 예산 감소로 일정 지연과 범위 축소가 필요하다고 알린다. | 일정 조정관과 재무 분석가를 만나 어떤 예산 항목을 줄이고 어디에서 여유를 해제할지 알린다. | 각 팀원에게 예산의 일부를 해제해야 하지만 범위 변경 없이 일정을 유지해야 한다고 알린다. | 팀과 협력하여 변경이 프로젝트에 미치는 영향을 평가하고 업데이트된 프로젝트 계획을 권고한다. |  | D | 프로젝트 예산이 삭감될 때, PM은 팀과 협력하여 범위, 일정, 품질에 대한 변경의 영향을 평가해야 한다. 함께 감소된 예산을 반영한 업데이트된 프로젝트 계획을 개발해야 한다. 이 협력적 접근 방식은 서번트 리더십 원칙—팀 권한 부여, 공유된 의사결정, 제약 조건에 대한 투명한 커뮤니케이션—과 일치한다.
1006 | A project lead was asked to support the team by subdividing the project tasks as necessary to help define the minimum viable product (MVP). Which two steps should the project lead take to define the MVP? (Choose 2) | Conduct an information gathering session to determine the project value. | Create a responsible, accountable, consulted, informed (RACI) chart. | Develop a project management plan, including subtasks, to meet the requirements. | Hold a team meeting to generate a work breakdown structure (WBS). | Refer to the stakeholder register to determine who should be consulted. | A, C | To define the MVP for the project, the project manager should take two actions: conduct an information gathering session to determine the project value (A) to understand stakeholder needs and priorities, and develop a project management plan, including subtasks, to meet the requirements (C) to create a structured approach for delivering the minimum viable scope. Information gathering identifies what matters most, while the project plan translates those priorities into actionable work. Creating a RACI chart (B) clarifies roles but does not define product scope. Generating a WBS (D) follows a predictive approach that may be premature before the MVP is defined. Referring to the stakeholder register (E) identifies who to consult but does not itself define the product. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Schedule | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 리더가 최소 기능 제품(MVP)을 정의하는 데 도움을 주기 위해 필요에 따라 프로젝트 작업을 세분화하여 팀을 지원하도록 요청받았다. 프로젝트 리더가 MVP를 정의하기 위해 취해야 할 두 가지 단계는 무엇인가? (2개 선택) | 프로젝트 가치를 결정하기 위한 정보 수집 세션을 수행한다. | 책임 배정 매트릭스(RACI) 차트를 작성한다. | 요구사항을 충족시키기 위한 하위 작업을 포함한 프로젝트 관리 계획을 개발한다. | 작업 분류 체계(WBS)를 생성하기 위한 팀 회의를 개최한다. | 누구에게 자문을 구해야 하는지 결정하기 위해 이해관계자 레지스터를 참조한다. | A, C | MVP를 정의하기 위해 PM은 두 가지 조치를 취해야 한다: 프로젝트 가치를 결정하기 위한 정보 수집 세션을 실시하고(A) 이해관계자 요구와 우선순위를 파악하며, 요구사항을 충족하기 위한 하위 작업을 포함한 프로젝트 관리 계획을 개발한다(C). 정보 수집은 가장 중요한 것을 식별하고, 프로젝트 계획은 그 우선순위를 실행 가능한 작업으로 전환한다. RACI 차트 작성(B)은 역할을 명확히 하지만 제품 범위를 정의하지 않는다. WBS 생성(D)은 MVP 정의 전에는 시기상조일 수 있는 예측적 접근을 따른다. 이해관계자 레지스터 참조(E)는 상담 대상을 식별하지만 제품 자체를 정의하지 않는다.
1007 | A company's project management office (PMO) is incorporating more adaptive technologies and has hired a new project manager with hybrid project management experience. The team is slow in adopting the new methodology and has not been updating project artifacts in a timely manner. Which action should the project manager take to improve the team's performance? | Set up a training session for all project team members | Speak individually with each project team member about making the needed updates | Send an email asking all project team members to complete updates at the end of the day | Reach out to the functional managers for support |  | A | When a PMO is incorporating adaptive technologies and the team is slow to adopt the new methodology, the project manager should set up a training session for all team members. Training addresses the root cause—lack of understanding—and builds capability for the new approach. Speaking individually with each member (B) is time-consuming and less effective. Sending an email about updates (C) is passive. Reaching out to functional managers (D) does not build team capability. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Hybrid/Tailoring | 회사의 프로젝트 관리 오피스(PMO)가 더 많은 적응형 기술을 도입하고 있으며 하이브리드 프로젝트 관리 경험이 있는 새 프로젝트 관리자를 고용했다. 팀이 새로운 방법론 채택이 느리고 프로젝트 산출물을 적시에 업데이트하지 않고 있다. 프로젝트 관리자는 팀의 성과를 개선하기 위해 어떤 조치를 취해야 하는가? | 모든 프로젝트 팀원을 위한 교육 세션을 설정한다. | 각 프로젝트 팀원과 개별적으로 필요한 업데이트에 대해 이야기한다. | 모든 프로젝트 팀원에게 하루 종료 시 업데이트를 완료하라는 이메일을 보낸다. | 지원을 위해 기능 관리자에게 연락한다. |  | A | PMO가 적응형 기술을 도입하고 팀이 새로운 방법론 채택이 느릴 때, 프로젝트 관리자는 모든 팀원을 위한 교육 세션을 설정해야 한다. 교육은 근본 원인인 이해 부족을 해결하고 새로운 접근 방식에 대한 역량을 구축한다. 각 팀원과 개별적으로 이야기(B)는 시간이 많이 걸리고 효과가 떨어진다. 업데이트에 대한 이메일 전송(C)은 수동적이다. 기능 관리자에게 연락(D)은 팀 역량을 구축하지 않는다.
1008 | A project manager is building a team that will be comprised of subject matter experts (SMEs) from two different divisions of the same company. The project team will be virtual and will include members from different countries around the world. What should the project manager do to ensure effective team building occurs? | Explain to the team that since they are all SMEs and know one another, they are expected to immediately collaborate and deliver effectively. | Coordinate with team members to define and communicate ways of working, roles and responsibilities, scheduling, time zone, and culturalobservance information. | Colocate the team members at the beginning of the project to explain the expectations for team interaction, meeting schedules, and overallproject governance. | Update the communications management plan and determine an issue resolution process for when furture conflicts arise. |  | B | When building a virtual team of SMEs from different divisions and countries, the project manager should coordinate with team members to define and communicate ways of working, roles, responsibilities, scheduling, time zones, and cultural observances. Clear protocols enable effective cross-cultural collaboration. Expecting immediate collaboration from SMEs (A) ignores team formation needs. Colocating at the start (C) may not be feasible for global teams. Updating the communications plan and defining issue resolution (D) is helpful but secondary to establishing working agreements. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 관리자가 같은 회사의 두 다른 부서의 주제 전문가(SME)로 구성될 팀을 구성하고 있다. 프로젝트 팀은 가상이며 전 세계 여러 국가의 팀원을 포함할 것이다. 프로젝트 관리자는 효과적인 팀 빌딩이 이루어지도록 무엇을 해야 하는가? | 팀에게 모두 SME이고 서로 알고 있으므로 즉시 협력하고 효과적으로 전달할 것이 기대된다고 설명한다. | 팀원들과 조율하여 작업 방식, 역할과 책임, 일정, 시간대, 문화적 관례 정보를 정의하고 커뮤니케이션한다. | 프로젝트 시작 시 팀원들을 한 곳에 모아 팀 상호작용, 회의 일정, 전반적인 프로젝트 거버넌스에 대한 기대를 설명한다. | 커뮤니케이션 관리 계획을 업데이트하고 향후 갈등 발생 시 이슈 해결 프로세스를 결정한다. |  | B | 다른 부서와 국가의 SME로 구성된 가상 팀을 구성할 때, 프로젝트 관리자는 팀원들과 조율하여 작업 방식, 역할, 책임, 일정, 시간대, 문화적 관례를 정의하고 커뮤니케이션해야 한다. 명확한 프로토콜이 효과적인 다문화 협력을 가능하게 한다. SME에게 즉각적인 협력 기대(A)는 팀 형성 요구를 무시한다. 시작 시 한 곳에 모으기(C)는 글로벌 팀에 실현 불가능할 수 있다. 커뮤니케이션 계획 업데이트 및 이슈 해결 정의(D)는 도움이 되지만 작업 합의 수립에 부차적이다.
1009 | A complex project is in the execution phase. A key stakeholder who is new to the project has not been approving project deliverables, which could impact the overall progress. What should the project manager do next? | Discuss the need to influence this stakeholder with the sponsor. | Meet with the stakeholder to understand what is causing the delays. | Capture this in the issue log and escalate it to the project sponsor. | Facilitate a brainstorming session to find potential workarounds. |  | B | When a new key stakeholder is not approving project deliverables and impacting progress, the project manager should first meet with the stakeholder to understand what is causing the delays. Direct communication identifies the root cause—whether unclear expectations, insufficient information, or quality concerns—before taking further action. Discussing influence with the sponsor (A) escalates before understanding the issue. Capturing in the issue log and escalating (C) is premature. Facilitating brainstorming for workarounds (D) addresses symptoms, not the cause. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 복잡한 프로젝트가 실행 단계에 있다. 프로젝트에 새로 합류한 핵심 이해관계자가 프로젝트 산출물을 승인하지 않아 전체 진행에 영향을 미칠 수 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | 스폰서와 이 이해관계자에게 영향을 미칠 필요성을 논의한다. | 이해관계자와 만나 지연을 일으키는 원인을 파악한다. | 이슈 로그에 기록하고 프로젝트 스폰서에게 에스컬레이션한다. | 잠재적 우회 방법을 찾기 위한 브레인스토밍 세션을 촉진한다. |  | B | 새로운 핵심 이해관계자가 프로젝트 산출물을 승인하지 않아 진행에 영향을 미칠 때, 프로젝트 관리자는 먼저 이해관계자와 만나 지연의 원인을 파악해야 한다. 직접적인 커뮤니케이션이 근본 원인을 식별한다—불명확한 기대, 불충분한 정보, 품질 우려 등—추가 조치 전에. 스폰서와 영향 논의(A)는 이슈를 이해하기 전에 에스컬레이션한다. 이슈 로그에 기록하고 에스컬레이션(C)은 시기상조이다. 우회 방법을 위한 브레인스토밍(D)은 원인이 아닌 증상을 다룬다.
1010 | A team has had issues with behavior on an ongoing project, which is causing conflicts. As a result, the team is losing momentum and falling behind in its sprints. How should the project manager handle this situation? | Control backlog assignments and reduce direct communications between team members. | Engage a counselor to reconcile the situation between the team members affected. | Revisit the ground rules and team communication protocols, and discuss what is happening. | Require team members experiencing the conflicts to take a day off from work. |  | C | When behavioral issues cause conflicts that slow the team's sprint progress, the project manager should revisit the ground rules and team communication protocols and facilitate a discussion about what is happening. This approach addresses the root cause by reinforcing established norms, encouraging transparency, and allowing team members to collaboratively resolve their differences. Controlling backlog assignments and reducing direct communication (A) is authoritarian and stifles collaboration. Engaging a counselor (B) may be appropriate for severe cases but is premature as a first response. Requiring team members to take a day off (D) is avoidant and does not resolve the conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀이 진행 중인 프로젝트에서 행동 문제로 갈등이 발생하고 있다. 결과적으로 팀이 추진력을 잃고 스프린트에서 뒤처지고 있다. 프로젝트 관리자는 이 상황을 어떻게 처리해야 하는가? | 백로그 배정을 통제하고 팀원 간 직접 커뮤니케이션을 줄인다. | 팀원 간 상황을 화해시키기 위해 상담사를 참여시킨다. | 기본 규칙과 팀 커뮤니케이션 프로토콜을 재검토하고 무슨 일이 일어나고 있는지 논의한다. | 갈등을 겪고 있는 팀원에게 하루 휴가를 취하도록 요구한다. |  | C | 행동 문제로 갈등이 팀의 스프린트 진행을 늦출 때, 프로젝트 관리자는 기본 규칙과 팀 커뮤니케이션 프로토콜을 재검토하고 무슨 일이 일어나고 있는지에 대한 논의를 촉진해야 한다. 이 접근 방식은 확립된 규범을 강화하고, 투명성을 장려하며, 팀원들이 협력적으로 차이를 해결할 수 있도록 한다. 백로그 배정 통제 및 직접 커뮤니케이션 감소(A)는 권위적이며 협력을 억제한다. 상담사 참여(B)는 심각한 경우에 적절할 수 있지만 첫 대응으로는 시기상조이다. 팀원에게 휴가 요구(D)는 회피적이며 갈등을 해결하지 않는다.
1011 | An agile project is running its second of six iterations. One new team member who does not have agile experience has just joined the team. In the daily meetings, the project manager observes that the team is having problems meeting their goals. What should the project manager do? | Provide feedback to the team and coach the new team member in agile methodology. | Provide feedback to the team and request agile training for the new member. | Provide feedback to the team and conduct a meeting to review the team rules. | Provide feedback to the team and conduct a retrospective meeting to find a root cause. |  | C | When an agile team struggles to meet goals in the second iteration after a new inexperienced member joins, the project manager should provide feedback to the team and conduct a meeting to review team rules. Reviewing working agreements helps the entire team—including the new member—realign on expectations and collaboration norms. Coaching the new member in agile (A) assumes they are the sole problem. Requesting agile training (B) delays resolution. Conducting a retrospective to find root causes (D) is typically done at iteration end, not mid-iteration. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Align Stakeholder Expectations | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트가 6회 반복 중 두 번째를 진행 중이다. 애자일 경험이 없는 새 팀원이 팀에 합류했다. 일일 회의에서 프로젝트 관리자는 팀이 목표 달성에 문제가 있음을 관찰한다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에 피드백을 제공하고 새 팀원에게 애자일 방법론을 코칭한다. | 팀에 피드백을 제공하고 새 팀원을 위한 애자일 교육을 요청한다. | 팀에 피드백을 제공하고 팀 규칙을 검토하는 회의를 진행한다. | 팀에 피드백을 제공하고 근본 원인을 찾기 위한 회고 회의를 진행한다. |  | C | 새 경험 없는 팀원이 합류한 후 두 번째 반복에서 애자일 팀이 목표 달성에 어려움을 겪을 때, 프로젝트 관리자는 팀에 피드백을 제공하고 팀 규칙을 검토하는 회의를 진행해야 한다. 작업 합의 검토는 새 팀원을 포함한 전체 팀이 기대치와 협업 규범에 재정렬하도록 돕는다. 새 팀원에게 애자일 코칭(A)은 문제가 그들에게만 있다고 가정한다. 애자일 교육 요청(B)은 해결을 지연시킨다. 근본 원인을 찾기 위한 회고(D)는 일반적으로 반복 종료 시 수행되며 반복 중간에는 아니다.
1012 | A project team member wants to select specific challenging tasks in the subsequent iteration. How can the project lead help the team member in the next iteration? | Coach the team member to pick up the challenging tasks. | Assign the challenging tasks to the team member. | Reprioritize the challenging tasks to future sprints. | Ask the product owner to assign the challenging tasks. |  | A | When a team member wants to select specific challenging tasks in the next iteration, the project lead should coach the team member to pick up the challenging tasks. Coaching empowers through guidance and skill development. Assigning the tasks directly (B) removes team member agency. Reprioritizing to future sprints (C) delays development. Asking the product owner to assign (D) misuses the product owner's role. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 프로젝트 팀원이 다음 반복에서 특정 도전적인 작업을 선택하고 싶어한다. 프로젝트 리더는 다음 반복에서 팀원을 어떻게 도울 수 있는가? | 팀원이 도전적인 작업을 선택하도록 코칭한다. | 팀원에게 도전적인 작업을 배정한다. | 도전적인 작업을 향후 스프린트로 재우선순위화한다. | 제품 책임자에게 도전적인 작업을 배정하도록 요청한다. |  | A | 팀원이 다음 반복에서 특정 도전적인 작업을 선택하고 싶을 때, 프로젝트 리더는 팀원이 도전적인 작업을 선택하도록 코칭해야 한다. 코칭은 안내와 기술 개발을 통해 권한을 부여한다. 직접 작업 배정(B)은 팀원의 자율성을 제거한다. 향후 스프린트로 재우선순위화(C)는 개발을 지연시킨다. 제품 책임자에게 배정 요청(D)은 제품 책임자의 역할을 오용한다.
1013 | An adaptive project is in the planning phase. The project manager is developing a communications management plan to distribute critical, project-related information and updates. Which approach should the project manager take? | Employ verbal techniques to share project-related information and updates. | Install push communication to share project-related information and updates. | Apply information radiators to share project-related information and updates. | Implement pull communication to share project-related information and updates. |  | C | In agile and adaptive settings, information radiators serve as essential communication mechanisms. These are continuously updated visual displays—such as task boards and burn-down charts—that remain accessible to all stakeholders at all times. They foster transparency, provide real-time status visibility, and support self-organizing team dynamics. The Agile Practice Guide endorses information radiators as a recommended practice for enabling fast, highly visible communication. Pull communication (A) puts the burden on stakeholders to actively seek updates, which limits transparency. Push communication (B) has value but falls short of the real-time visibility that agile environments demand. Verbal techniques (D) tend to be informal and have limited reach across the team. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 적응형 프로젝트가 계획 단계에 있다. 프로젝트 관리자가 중요한 프로젝트 관련 정보와 업데이트를 배포하기 위한 커뮤니케이션 관리 계획을 개발하고 있다. 프로젝트 관리자는 어떤 접근 방식을 취해야 하는가? | 프로젝트 관련 정보와 업데이트를 공유하기 위해 구두 기법을 사용한다. | 프로젝트 관련 정보와 업데이트를 공유하기 위해 푸시 커뮤니케이션을 설치한다. | 프로젝트 관련 정보와 업데이트를 공유하기 위해 정보 라디에이터를 적용한다. | 프로젝트 관련 정보와 업데이트를 공유하기 위해 풀 커뮤니케이션을 구현한다. |  | C | 애자일 및 적응형 환경에서 정보 라디에이터는 필수적인 커뮤니케이션 메커니즘이다. 이는 작업 보드 및 번다운 차트와 같이 지속적으로 업데이트되는 시각적 표시로, 모든 이해관계자가 항상 접근할 수 있다. 투명성을 촉진하고 실시간 상태 가시성을 제공하며 자기 조직화 팀 역학을 지원한다. 풀 커뮤니케이션(A)은 이해관계자에게 적극적으로 업데이트를 찾도록 부담을 주어 투명성을 제한한다. 푸시 커뮤니케이션(B)은 가치가 있지만 애자일 환경이 요구하는 실시간 가시성에는 미치지 못한다. 구두 기법(D)은 비공식적이며 팀 전체에 대한 도달 범위가 제한적이다.
1014 | To estimate the costs of a new project that is similar to a project that was implemented last year, the project manager meets with a group of experts from the previous project. The group uses a three-point estimating technique. The project manager submits the estimated budget to the project sponsor for approval. The project sponsor, who is new to the company, is concerned because the budget exceeded their expectations. What should the project manager do? | Review the historical information and lessons learned from last year's project to justify the new budget estimate | Change the budgeting technique to a more accurate, bottom-up cost estimation. | Review the organizational process assessment to determine if a contingency reserve was considered in the budget estimate | Use soft skills to convince the project sponsor to approve the new budget estimate |  | A | When a new project sponsor questions a budget estimate derived from three-point estimating based on a similar prior project, the project manager should review historical information and lessons learned from last year's project to justify the estimate. Documented data supports the rationale. Changing to bottom-up estimation (B) is more costly and may not be necessary. Reviewing for contingency reserves (C) addresses one component but does not justify the overall estimate. Using soft skills to convince the sponsor (D) lacks analytical substance. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 작년에 수행된 프로젝트와 유사한 새 프로젝트의 비용을 추정하기 위해 프로젝트 관리자가 이전 프로젝트의 전문가 그룹과 만난다. 그룹은 3점 추정 기법을 사용한다. 프로젝트 관리자는 추정된 예산을 승인을 위해 프로젝트 스폰서에게 제출한다. 회사에 새로 온 프로젝트 스폰서는 예산이 기대를 초과했기 때문에 우려한다. 프로젝트 관리자는 무엇을 해야 하는가? | 새 예산 추정을 정당화하기 위해 작년 프로젝트의 이력 정보와 교훈을 검토한다. | 더 정확한 상향식 비용 추정으로 예산 기법을 변경한다. | 예산 추정에 예비비가 고려되었는지 확인하기 위해 조직 프로세스 평가를 검토한다. | 새 예산 추정을 승인하도록 프로젝트 스폰서를 설득하기 위해 소프트 스킬을 사용한다. |  | A | 새 프로젝트 스폰서가 유사한 이전 프로젝트에 기반한 3점 추정 예산에 의문을 제기할 때, 프로젝트 관리자는 추정을 정당화하기 위해 작년 프로젝트의 이력 정보와 교훈을 검토해야 한다. 문서화된 데이터가 근거를 뒷받침한다. 상향식 추정으로 변경(B)은 더 비용이 들며 필요하지 않을 수 있다. 예비비에 대한 검토(C)는 한 구성요소를 다루지만 전체 추정을 정당화하지 않는다. 소프트 스킬로 스폰서 설득(D)은 분석적 근거가 부족하다.
1015 | The project team is planning a schedule with limited information. The team is having issues identifying the detailed tasks and estimating task durations. Which three techniques should the project manager use? (Choose three) | Bottom-up estimating based on a work breakdown structure (WBS) | Relative estimation to determine the task or deliverable sizes | Iterations and reviews to continuously keep adapting the plan | Rolling wave planning and an adaptive approach | Gantt chart that includes milestones and deadlines https://www.projectmanager.com/blog/project- management/planning-techniques-for-projects | B, C, D | When planning a schedule with limited information and difficulty identifying detailed tasks, the project manager should use (D) rolling wave planning and an adaptive approach, (B) relative estimation for task sizing, and (C) iterations and reviews to continuously adapt. Bottom-up estimating (A) requires detailed WBS that is not yet available. A Gantt chart with milestones (E) is an output, not an estimation technique. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 팀이 제한된 정보로 일정을 계획하고 있다. 팀은 상세 작업 식별과 작업 기간 추정에 문제가 있다. 프로젝트 관리자가 사용해야 할 세 가지 기법은? (3개 선택) | 작업분류체계(WBS)에 기반한 상향식 추정 | 작업 또는 산출물 크기를 결정하기 위한 상대적 추정 | 계획을 지속적으로 적응시키기 위한 반복과 검토 | 롤링 웨이브 계획과 적응형 접근 방식 | 마일스톤과 마감일을 포함하는 간트 차트 | B,C,D | 제한된 정보로 일정을 계획하고 상세 작업 식별이 어려울 때, 프로젝트 관리자는 (D) 롤링 웨이브 계획과 적응형 접근 방식, (B) 작업 크기를 위한 상대적 추정, (C) 지속적으로 적응하기 위한 반복과 검토를 사용해야 한다. 상향식 추정(A)은 아직 사용할 수 없는 상세 WBS가 필요하다. 마일스톤이 있는 간트 차트(E)는 산출물이지 추정 기법이 아니다.
1016 | Due to a company merger and acquisition process, the main stakeholder of a critical project has been changed. This new stakeholder complains that they were unaware of a delay on the project of which the rest of the stakeholders were aware. All the communications about the project are shared via email at the start of every week. How should the project manager address this situation? | Suggest that the new stakeholder review the project status before the next board meeting | Share the communications management plan with the new stakeholder | Discuss project requirements with the new stakeholder, and update the communications management plan. | Send evidence to the new stakeholder that the project ' s status was sent according to the schedule |  | C | When a new stakeholder from a merger is unaware of a project delay that others know about, the project manager should discuss project requirements with the new stakeholder and update the communications management plan. Understanding needs and updating the plan addresses the gap. Suggesting a pre-meeting review (A) is informal. Sharing the existing plan (B) does not adapt to new needs. Sending evidence of past communications (D) is defensive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 회사 합병 및 인수 과정으로 인해 중요한 프로젝트의 주요 이해관계자가 변경되었다. 새 이해관계자는 나머지 이해관계자들이 알고 있었던 프로젝트 지연을 몰랐다고 불만을 제기한다. 프로젝트에 대한 모든 커뮤니케이션은 매주 초에 이메일로 공유된다. 프로젝트 관리자는 이 상황을 어떻게 해결해야 하는가? | 새 이해관계자에게 다음 이사회 전에 프로젝트 상태를 검토하도록 제안한다. | 새 이해관계자에게 커뮤니케이션 관리 계획을 공유한다. | 새 이해관계자와 프로젝트 요구사항을 논의하고 커뮤니케이션 관리 계획을 업데이트한다. | 새 이해관계자에게 일정에 따라 프로젝트 상태가 발송되었다는 증거를 보낸다. |  | C | 합병으로 인한 새 이해관계자가 다른 사람들이 알고 있었던 프로젝트 지연을 몰랐을 때, 프로젝트 관리자는 새 이해관계자와 프로젝트 요구사항을 논의하고 커뮤니케이션 관리 계획을 업데이트해야 한다. 요구를 이해하고 계획을 업데이트하면 격차를 해소한다. 이사회 전 검토 제안(A)은 비공식적이다. 기존 계획 공유(B)는 새로운 요구에 적응하지 않는다. 과거 커뮤니케이션 증거 발송(D)은 방어적이다.
1017 | A project lead with a strong technical background oversees a project using agile delivery. The product owner asked the project lead to assist with ensuring the benefits of functionality that are built in the sprint are tracked. What should the project lead advise? | During the daily standup, ensure that each item meets the definition of done (DoD) before accepting it. | During the sprint review, ensure that the completed items deliver business benefits. | Review in detail the criteria for the definition of done (DoD) for each item during the sprint planning. | Present in detail the business benefits delivered in the sprint during the sprint retrospective. |  | B | The correct answer is B. During the sprint review, ensure that the completed items deliver business benefits. 800. The product owner manages backlog priorities and defines requirements. The PM should support the product owner's role while facilitating team collaboration and maintaining agile practices. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 강한 기술적 배경을 가진 프로젝트 리더가 애자일 전달을 사용하는 프로젝트를 감독하고 있다. 제품 책임자가 스프린트에서 구축된 기능의 혜택이 추적되도록 프로젝트 리더에게 지원을 요청했다. 프로젝트 리더는 무엇을 조언해야 하는가? | 일일 스탠드업에서 각 항목이 완료 기준(DoD)을 충족하는지 수락하기 전에 확인한다. | 스프린트 리뷰에서 완료된 항목이 비즈니스 혜택을 전달하는지 확인한다. | 스프린트 계획 중 각 항목의 완료 기준(DoD) 기준을 상세히 검토한다. | 스프린트 회고에서 전달된 비즈니스 혜택을 상세히 발표한다. |  | B | 정답은 B이다. 스프린트 리뷰에서 완료된 항목이 비즈니스 혜택을 전달하는지 확인한다. 제품 책임자는 백로그 우선순위를 관리하고 요구사항을 정의한다. PM은 제품 책임자의 역할을 지원하면서 팀 협업을 촉진하고 애자일 관행을 유지해야 한다.
1018 | A team is performing above expectations, and the sponsor wants to expand the project scope to benefit the organization. However, there are only a few team members with the needed leadership experience. What should the project manager do? | Communicate the risks and propose hiring members with leadership experience before continuing with the request. | Recognize each team member for their contributions and recommend them to the leadership development program. | Implement the scope expansion and suggest the team members get a mentor due to their lack of leadership experience. | Decline the scope expansion until the team members get appropriate leadership opportunities within the project. |  | A | The correct answer is A. Communicate the risks and propose hiring members with leadership experience before continuing with the request. Effective resource management ensures team members have the necessary competencies and support. The PM should identify gaps and address them through training, coaching, or mentoring. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Be an Accountable Leader | Develop Team | Traditional PM | 팀이 기대 이상의 성과를 내고 있으며 스폰서가 조직에 이익이 되도록 프로젝트 범위를 확장하려 한다. 그러나 필요한 리더십 경험을 가진 팀원은 소수에 불과하다. 프로젝트 관리자는 무엇을 해야 하는가? | 리스크를 전달하고 요청을 계속하기 전에 리더십 경험이 있는 멤버를 고용할 것을 제안한다. | 각 팀원의 기여를 인정하고 리더십 개발 프로그램에 추천한다. | 범위 확장을 실행하고 팀원들에게 리더십 경험 부족으로 인해 멘토를 구하도록 제안한다. | 팀원들이 프로젝트 내에서 적절한 리더십 기회를 얻을 때까지 범위 확장을 거부한다. |  | A | 정답은 A이다. 리스크를 전달하고 요청을 계속하기 전에 리더십 경험이 있는 멤버를 고용할 것을 제안한다. 효과적인 자원 관리는 팀원들이 필요한 역량과 지원을 갖추도록 보장한다. PM은 격차를 식별하고 교육, 코칭 또는 멘토링을 통해 해결해야 한다.
1019 | A member of the board of directors is the sponsor of a project that is important to the organization. This stakeholder has many other priorities and is not currently engaged in the project activities. How should the stakeholder be engaged in the project? | The stakeholder needs to be made aware of the project progress | Keep the stakeholder informed and consult with them based on their needs | Involve the stakeholder in governance and decision making | Consult with the stakeholder and increase their level of interest |  | B | When a board member sponsor has many priorities and is not engaged in project activities, the stakeholder should be kept informed and consulted with based on their needs. This respects their time constraints while ensuring they remain aligned and can provide support when needed. Making them aware of progress (A) is one-directional. Involving them in governance (C) may overcommit their time. Consulting and increasing their interest level (D) may not match their availability. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 이사회 멤버가 조직에 중요한 프로젝트의 스폰서이다. 이 이해관계자는 다른 우선순위가 많아 현재 프로젝트 활동에 참여하지 않고 있다. 이해관계자는 프로젝트에 어떻게 참여시켜야 하는가? | 이해관계자에게 프로젝트 진행 상황을 알려야 한다. | 이해관계자에게 정보를 제공하고 그들의 필요에 따라 상담한다. | 이해관계자를 거버넌스와 의사결정에 참여시킨다. | 이해관계자와 상담하고 관심도를 높인다. |  | B | 이사회 멤버 스폰서가 우선순위가 많아 프로젝트 활동에 참여하지 않을 때, 이해관계자에게 정보를 제공하고 필요에 따라 상담해야 한다. 이는 시간 제약을 존중하면서 정렬 상태를 유지하고 필요할 때 지원을 제공할 수 있도록 보장한다. 진행 상황만 알리기(A)는 단방향적이다. 거버넌스에 참여(C)는 시간을 과도하게 투입시킬 수 있다. 상담 및 관심도 증가(D)는 가용성에 맞지 않을 수 있다.
1020 | A project manager is assigned to a project related to taxes, which will be managed using an agile approach. By reviewing lessons learned from a previous project, the project manager discovers that a key stakeholder is an expert on taxes and is willing to help. How should the project manager leverage this information? | Request the functional manager to assign the team from the lessons learned project tothe current project to avoid a learning curve. | Ask the project team to review the lessons learned and have the team contact thestakeholder directly if there are any questions. | Send a request to the project sponsor to hire the stakeholder and have them becomepart of the project team. | Recognize the stakeholder ' s skills are important for the project and evaluate thepossibility of the stakeholder supporting the project team. |  | D | The PM should recognize the stakeholder's tax expertise and evaluate how they might support the project team. Leveraging the stakeholder's knowledge and experience increases both project capability and stakeholder engagement. Direct collaboration between the stakeholder and team should be established through clear communication. Creating unnecessary dependencies through functional managers, team requests, or sponsor escalation may introduce delays or conflicts. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 프로젝트 관리자가 애자일 접근 방식으로 관리될 세금 관련 프로젝트에 배정되었다. 이전 프로젝트의 교훈을 검토하면서 프로젝트 관리자는 핵심 이해관계자가 세금 전문가이며 도움을 줄 의향이 있음을 발견한다. 프로젝트 관리자는 이 정보를 어떻게 활용해야 하는가? | 학습 곡선을 피하기 위해 교훈 프로젝트의 팀을 현재 프로젝트에 배정하도록 기능 관리자에게 요청한다. | 프로젝트 팀에게 교훈을 검토하도록 요청하고 질문이 있으면 이해관계자에게 직접 연락하도록 한다. | 프로젝트 스폰서에게 이해관계자를 고용하여 프로젝트 팀의 일원이 되도록 요청을 보낸다. | 이해관계자의 기술이 프로젝트에 중요함을 인식하고 이해관계자가 프로젝트 팀을 지원할 가능성을 평가한다. |  | D | PM은 이해관계자의 세금 전문성을 인식하고 프로젝트 팀을 지원할 수 있는 방법을 평가해야 한다. 이해관계자의 지식과 경험을 활용하면 프로젝트 역량과 이해관계자 참여가 모두 증가한다. 이해관계자와 팀 간의 직접적인 협력은 명확한 커뮤니케이션을 통해 구축되어야 한다. 기능 관리자, 팀 요청 또는 스폰서 에스컬레이션을 통한 불필요한 의존성 생성은 지연이나 갈등을 초래할 수 있다.
1021 | A project manager is assigned to a new project. The project management office (PMO) and the project manager agree that this is the right opportunity to include daily standup meetings. The project team has never used such tools, and a few members are challenging the decision. What should the project manager do in this situation? | Define the ground rules, responsibilities, and conflict management strategies. | Engage an external vendor to perform the design phase under an iterative approach. | Update the project schedule to consider a daily standup as part of the project design phase. | Request that new team members familiar with iterative approaches be assigned to this project. |  | A | When introducing daily standup meetings to a team unfamiliar with the practice, the project manager should define the ground rules, responsibilities, and conflict management strategies. This establishes clear expectations, explains the purpose and benefits of standups, and assigns roles such as facilitator and timekeeper. It also creates a framework for addressing resistance constructively. Engaging an external vendor for the design phase (B) is unrelated to the team adoption issue. Requesting new team members familiar with iterative approaches (D) replaces the team rather than developing them. Updating the project schedule (C) is a procedural step that does not address the team's concerns. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Risk | Planning | Build an Empowered Culture | Plan Risk Management | Hybrid/Tailoring | 프로젝트 관리자가 새 프로젝트에 배정되었다. 프로젝트 관리 오피스(PMO)와 프로젝트 관리자는 이것이 일일 스탠드업 회의를 포함할 적절한 기회라고 합의했다. 프로젝트 팀은 이러한 도구를 사용한 적이 없으며, 일부 구성원이 결정에 이의를 제기하고 있다. 프로젝트 관리자는 이 상황에서 무엇을 해야 하는가? | 기본 규칙, 책임, 갈등 관리 전략을 정의한다. | 반복적 접근 방식으로 설계 단계를 수행하기 위해 외부 벤더를 참여시킨다. | 프로젝트 설계 단계의 일부로 일일 스탠드업을 고려하여 프로젝트 일정을 업데이트한다. | 반복적 접근 방식에 익숙한 새 팀원을 이 프로젝트에 배정하도록 요청한다. |  | A | 팀이 익숙하지 않은 일일 스탠드업 회의를 도입할 때, 프로젝트 관리자는 기본 규칙, 책임, 갈등 관리 전략을 정의해야 한다. 이는 명확한 기대를 설정하고, 스탠드업의 목적과 이점을 설명하며, 촉진자와 시간 관리자 같은 역할을 배정한다. 외부 벤더 참여(B)는 팀 채택 문제와 무관하다. 반복적 접근에 익숙한 새 팀원 요청(D)은 팀을 개발하기보다 교체한다. 일정 업데이트(C)는 팀의 우려를 해결하지 않는다.
1022 | A project manager working on a large-scale network implementation is frustrated with the hardware supplier. Their deliveries have been consistently late and frequently do not have vital components. The project manager's company has decided to cancel the contract and move to a new supplier, but the only other option is an overseas company. What should the project manager do first to proceed with this change? | Check social media to determine if there are any common connections that use the new supplier. | Request assistance from the procurement department on the next steps. | Become aware of any cultural characteristics of the new supplier that could impactnegotiation. | Engage the services of an interpreter who understands the project domain. |  | C | When switching to an overseas hardware supplier, the project manager should first become aware of cultural characteristics that could impact negotiation. Cultural awareness prevents misunderstandings. Checking social media (A) is informal. Requesting procurement assistance (B) is procedural but premature. Engaging an interpreter (D) is helpful but secondary to cultural understanding. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 대규모 네트워크 구현 작업을 수행하는 프로젝트 관리자가 하드웨어 공급업체에 불만을 느끼고 있다. 납품이 지속적으로 늦고 자주 중요한 구성요소가 누락된다. 프로젝트 관리자의 회사가 계약을 취소하고 새 공급업체로 전환하기로 결정했지만, 유일한 다른 옵션은 해외 회사이다. 프로젝트 관리자는 이 변경을 진행하기 위해 먼저 무엇을 해야 하는가? | 소셜 미디어를 확인하여 새 공급업체를 사용하는 공통 연결이 있는지 확인한다. | 조달 부서에 다음 단계에 대한 지원을 요청한다. | 협상에 영향을 줄 수 있는 새 공급업체의 문화적 특성을 파악한다. | 프로젝트 도메인을 이해하는 통역사의 서비스를 참여시킨다. |  | C | 해외 하드웨어 공급업체로 전환할 때, 프로젝트 관리자는 먼저 협상에 영향을 줄 수 있는 문화적 특성을 파악해야 한다. 문화적 인식은 오해를 방지한다. 소셜 미디어 확인(A)은 비공식적이다. 조달 지원 요청(B)은 절차적이지만 시기상조이다. 통역사 참여(D)는 도움이 되지만 문화적 이해에 부차적이다.
1023 | A project manager is responsible for providing a budget estimate for a long-term project that will be executed over several years. Which essential task should the project manager carry out at this phase? | Perform an analogous estimate. | Include projected inflation rates. | Include key risks in the cost baseline. | Perform a bottom-up estimate. |  | B | For long-term projects spanning multiple years, the PM should incorporate projected inflation rates into the budget estimate. Inflation affects the purchasing power of project funds and the cost of resources over time. By accounting for projected inflation, the PM can adjust the budget to reflect changes in the value of money and the cost of goods and services—an essential consideration within the Estimate Costs process for developing realistic monetary approximations. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 관리자가 수년에 걸쳐 실행될 장기 프로젝트의 예산 추정치를 제공할 책임이 있다. 이 단계에서 프로젝트 관리자가 수행해야 할 필수 작업은 무엇인가? | 유사 추정을 수행한다. | 예상 인플레이션율을 포함한다. | 비용 기준선에 주요 리스크를 포함한다. | 상향식 추정을 수행한다. |  | B | 수년에 걸친 장기 프로젝트의 경우, PM은 예산 추정치에 예상 인플레이션율을 반영해야 한다. 인플레이션은 프로젝트 자금의 구매력과 시간 경과에 따른 자원 비용에 영향을 미친다. 예상 인플레이션을 반영함으로써 PM은 화폐 가치와 상품 및 서비스 비용의 변화를 반영하여 예산을 조정할 수 있다.
1024 | A new sales software development project is underway. The customer is still finalizing the requirements for the system when a new CEO is introduced. The new CEO is expected to make changes to the organization, which most likely will impact development. However, the most important criterion for the project is that the software must provide correct sales results. No intermediate results are required. Which project approach should the project manager take? | iterative | Predictive | Hybrid | Incremental |  | C | When a new CEO is expected to make changes impacting development while the most important criterion is correct sales results with no intermediate results required, the project manager should take a hybrid approach. Hybrid combines predictive certainty for final delivery with adaptive flexibility for changing requirements. Iterative (A) may not suit the no-intermediate-results requirement. Predictive (B) cannot accommodate expected changes. Incremental (D) delivers in parts, which may not meet the no-intermediate-results criterion. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Build an Empowered Culture | Plan Scope Management | Hybrid/Tailoring | 새로운 영업 소프트웨어 개발 프로젝트가 진행 중이다. 고객이 시스템 요구사항을 최종 확정하고 있을 때 새 CEO가 취임했다. 새 CEO는 조직에 변경을 가할 것으로 예상되며, 이는 개발에 영향을 미칠 가능성이 높다. 그러나 프로젝트에서 가장 중요한 기준은 소프트웨어가 정확한 영업 결과를 제공해야 한다는 것이다. 중간 결과는 필요하지 않다. 프로젝트 관리자는 어떤 프로젝트 접근 방식을 취해야 하는가? | 반복적 | 예측형 | 하이브리드 | 점진적 |  | C | 새 CEO가 개발에 영향을 미치는 변경을 가할 것으로 예상되고, 가장 중요한 기준이 정확한 영업 결과이며 중간 결과가 필요하지 않을 때, 프로젝트 관리자는 하이브리드 접근 방식을 취해야 한다. 하이브리드는 최종 전달의 예측적 확실성과 변화하는 요구사항에 대한 적응적 유연성을 결합한다. 반복적(A)은 중간 결과 불필요 요구에 적합하지 않을 수 있다. 예측형(B)은 예상되는 변경을 수용할 수 없다. 점진적(D)은 부분별로 전달하므로 중간 결과 불필요 기준에 맞지 않을 수 있다.
1025 | During the development of a product, the project manager observes conflicts between project stakeholders, resulting in deliverable and output approval delays. On which area should the project manager focus? | Revisiting the project management plan to ensure deliverables are on time | Increasing the frequency of project update meetings to keep stakeholders informed | Revisiting the stakeholder engagement plan, focusing on specific overlooked stakeholders | Reviewing the business case and identifying gaps within scope |  | C | When stakeholder conflicts cause deliverable and output approval delays, the project manager should focus on revisiting the stakeholder engagement plan with attention to specific overlooked stakeholders. Identifying root causes of conflict and developing targeted engagement strategies resolves the approval bottleneck. Revisiting the project management plan for timeliness (A) does not address stakeholder conflicts. Increasing meeting frequency (B) adds overhead without resolving conflicts. Reviewing the business case (D) is too strategic. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 제품 개발 중 프로젝트 관리자가 프로젝트 이해관계자 간의 갈등을 관찰하여 산출물 및 출력 승인이 지연되고 있다. 프로젝트 관리자는 어떤 영역에 초점을 맞춰야 하는가? | 산출물이 제시간에 완료되도록 프로젝트 관리 계획을 재검토한다. | 이해관계자에게 정보를 제공하기 위해 프로젝트 업데이트 회의 빈도를 늘린다. | 특정 간과된 이해관계자에 초점을 맞춰 이해관계자 참여 계획을 재검토한다. | 비즈니스 케이스를 검토하고 범위 내 격차를 식별한다. |  | C | 이해관계자 갈등이 산출물 및 출력 승인 지연을 야기할 때, 프로젝트 관리자는 특정 간과된 이해관계자에 초점을 맞춰 이해관계자 참여 계획을 재검토해야 한다. 갈등의 근본 원인을 식별하고 맞춤형 참여 전략을 개발하면 승인 병목을 해결할 수 있다. 적시성을 위한 프로젝트 관리 계획 재검토(A)는 이해관계자 갈등을 해결하지 않는다. 회의 빈도 증가(B)는 갈등을 해결하지 않고 오버헤드를 추가한다. 비즈니스 케이스 검토(D)는 너무 전략적이다.
1026 | A project manager just finished a meeting to identify the main stakeholders of the project. What should the project manager do next? | Monitor all stakeholders. | Analyze the stakeholders. | Keep all stakeholders informed. | Engage the stakeholders. |  | B | After identifying the main stakeholders, the project manager should next analyze the stakeholders. Stakeholder analysis determines interest, influence, and potential impact to guide engagement strategy. Monitoring all stakeholders (A) comes later. Keeping all informed (C) is ongoing. Engaging stakeholders (D) follows analysis. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 프로젝트 관리자가 프로젝트의 주요 이해관계자를 식별하기 위한 회의를 마쳤다. 프로젝트 관리자가 다음으로 해야 할 일은 무엇인가? | 모든 이해관계자를 모니터링한다. | 이해관계자를 분석한다. | 모든 이해관계자에게 정보를 제공한다. | 이해관계자를 참여시킨다. |  | B | 주요 이해관계자를 식별한 후, 프로젝트 관리자는 다음으로 이해관계자를 분석해야 한다. 이해관계자 분석은 관심도, 영향력, 잠재적 영향을 파악하여 참여 전략을 수립하는 데 활용된다. 모든 이해관계자 모니터링(A)은 이후 단계이다. 모든 이해관계자에게 정보 제공(C)은 지속적 활동이다. 이해관계자 참여(D)는 분석 이후에 이루어진다.
1027 | During a meeting with the customer, it was observed that the features delivered during the last few iterations were not meeting the planned expectations. What should the project manager do? | Review the requirements and instruct the team to develop the deliverables according to the documentation. | Mentor the team members and ensure they perform peer reviews of their work before implementation. | Utilize the retrospectives to identify issues in the development phase that may cause deliverables to not be accepted. | Ensure a continuous feedback environment is leveraged to improve the quality and overall satisfaction. |  | D | When features delivered during iterations are not meeting customer expectations, the root cause is typically a breakdown in feedback loops. The project manager should ensure a continuous feedback environment is leveraged to improve quality and overall satisfaction. Continuous feedback allows stakeholder input to be captured early and often, enabling course corrections before features are finalized. Reviewing requirements and instructing the team (A) is a top-down approach that does not address the underlying communication gap. Mentoring and peer reviews (B) improve internal quality but do not directly address customer expectation alignment. Retrospectives (C) are valuable but occur after the sprint; continuous feedback is more proactive and prevents dissatisfaction before it grows. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 고객과의 회의에서 최근 몇 차례 이터레이션에서 전달된 기능이 계획된 기대치를 충족하지 못하고 있음이 관찰되었다. 프로젝트 관리자는 어떻게 해야 하는가? | 요구사항을 검토하고 팀에게 문서에 따라 산출물을 개발하도록 지시한다. | 팀원들을 멘토링하고 구현 전에 동료 검토를 수행하도록 한다. | 회고를 활용하여 산출물이 수락되지 않는 원인이 될 수 있는 개발 단계의 문제를 식별한다. | 품질과 전반적 만족도를 개선하기 위해 지속적인 피드백 환경을 활용하도록 한다. |  | D | 이터레이션에서 전달된 기능이 고객 기대치를 충족하지 못할 때, 근본 원인은 일반적으로 피드백 루프의 단절이다. 프로젝트 관리자는 품질과 전반적 만족도를 개선하기 위해 지속적인 피드백 환경을 활용해야 한다. 지속적 피드백은 이해관계자 입력을 조기에 자주 포착하여 기능이 확정되기 전에 방향 수정을 가능하게 한다. 요구사항 검토 및 문서 기반 개발 지시(A)는 지시적이며 애자일 원칙에 반한다. 동료 검토 멘토링(B)은 유용하지만 근본적인 피드백 격차를 해결하지 않는다. 회고 활용(C)은 프로세스 개선에 좋지만 고객과의 지속적 피드백만큼 즉각적이지 않다.
1028 | An organization that embraced agile a couple of years ago is looking for a more efficient way to ensure that the increments produced in each sprint meet the end users' quality requirements. What should the project lead recommend? | Organize more frequent sprint reviews with a broader audience. | Establish a quality assurance (QA) team separate from the development team. | Increase the percentage allocated for testing each backlog item. | Develop a more comprehensive template for the definition of done (DoD). |  | A | Organizing more frequent sprint reviews with a broader audience ensures product increments meet end-user quality requirements. This approach enables continuous feedback and collaboration—allowing the team to present work to stakeholders, receive immediate input, and incorporate feedback into subsequent sprints. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 몇 년 전 애자일을 도입한 조직이 각 스프린트에서 생산되는 증분이 최종 사용자의 품질 요구사항을 충족하는지 더 효율적으로 확인하는 방법을 찾고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 더 넓은 참석자와 함께 스프린트 리뷰를 더 자주 조직한다. | 개발팀과 별도의 품질 보증(QA) 팀을 구성한다. | 각 백로그 항목의 테스트에 할당되는 비율을 늘린다. | 완료 정의(DoD)를 위한 더 포괄적인 템플릿을 개발한다. |  | A | 더 넓은 참석자와 함께 스프린트 리뷰를 더 자주 조직하면 제품 증분이 최종 사용자 품질 요구사항을 충족하는지 확인할 수 있다. 이 접근 방식은 지속적 피드백과 협업을 가능하게 하여 팀이 이해관계자에게 작업을 제시하고, 즉각적인 입력을 받고, 후속 스프린트에 피드백을 반영할 수 있게 한다. 별도 QA 팀 구성(B)은 사일로를 만들 수 있다. 테스트 비율 증가(C)는 비용을 늘리지만 사용자 피드백을 개선하지 않는다. 포괄적 DoD 템플릿(D)은 유용하지만 직접적인 사용자 피드백을 대체하지 않는다.
1029 | An agile project to provide a material information system has started. During the kick-off meeting, the team realizes that the stakeholders require a solution in 2 months, but it will take at least 4 months to deliver the entire project. Who should the project manager contact to help the team accelerate the delivery? | The product owner and the stakeholders-to prioritize the requirements in the product backlog. | The team-to have them increase their velocity to accomplish the stakeholders requirements. | The human resources (HR) department-to ask for more resources to add to the project team. | The stakeholders-to have them prioritize the requirements in the product backlog. |  | A | When stakeholders need a solution in 2 months but the full project requires 4 months, the project manager should contact the product owner and the stakeholders to prioritize the requirements in the product backlog. By identifying and prioritizing the most critical features, the team can deliver the highest-value functionality first within the 2-month timeframe while continuing development on the remaining scope. Asking the team to increase velocity (B) is unrealistic and risks burnout. Requesting more resources from HR (C) may help but does not address the fundamental need to prioritize what gets delivered first. Asking stakeholders to prioritize the backlog without the product owner (D) bypasses the product owner's authority over backlog management. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 자재 정보 시스템을 제공하는 애자일 프로젝트가 시작되었다. 킥오프 회의에서 팀은 이해관계자들이 2개월 내 솔루션을 필요로 하지만 최소 4개월이 걸린다는 것을 알게 되었다. 프로젝트 관리자는 누구에게 연락해야 하는가? | 제품 소유자와 이해관계자—제품 백로그의 요구사항 우선순위를 정하기 위해. | 팀—이해관계자 요구사항을 달성하기 위해 벨로시티를 높이도록. | 인사(HR) 부서—프로젝트 팀에 더 많은 자원을 추가하기 위해. | 이해관계자—제품 백로그의 요구사항 우선순위를 정하도록. |  | A | 이해관계자가 2개월 내 솔루션을 필요로 하지만 전체 프로젝트에 4개월이 걸릴 때, PM은 제품 소유자와 이해관계자에게 연락하여 제품 백로그의 요구사항 우선순위를 정해야 한다. 가장 중요한 기능을 식별하고 우선순위를 정하여 2개월 안에 가장 높은 가치의 기능을 먼저 전달할 수 있다. 벨로시티를 높이도록 요청(B)은 비현실적이며 번아웃을 야기한다. HR에 더 많은 자원 요청(C)은 복잡성을 추가하고 시기가 맞지 않을 수 있다. 이해관계자만으로 우선순위 정하기(D)는 제품 소유자의 전문성이 빠진다.
1030 | A project manager is managing a project to develop a new tool. Because of the nature of the project, the project manager decides to use an agile approach. One of the identified risks becomes an issue when the project manager finds out that another company patented a very similar tool. What should the project manager do to address this issue? | Inform the product owner and log the issue in the risk register to monitor closely for next steps. | Put the project on hold and release the resources until the issue is resolved | Contact the company that owns the patent of the similar tool to compare the similarities and differences with the current project. | Schedule a meeting with critical stakeholders to review the issue and decide on the next steps |  | D | When an identified risk becomes an issue because another company patented a very similar tool, the project manager should schedule a meeting with critical stakeholders to review the issue and decide on next steps. Collaborative decision-making with relevant parties is essential. Informing the PO and logging in the risk register (A) documents but does not decide. Putting the project on hold (B) is premature. Contacting the patent holder (C) acts without stakeholder input. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 새로운 도구를 개발하는 프로젝트를 관리하고 있다. 프로젝트 특성상 애자일 접근 방식을 사용하기로 결정했다. 식별된 리스크 중 하나가 이슈가 되었는데, 다른 회사가 매우 유사한 도구에 대한 특허를 보유하고 있었다. PM은 어떻게 해야 하는가? | 제품 소유자에게 알리고 리스크 레지스터에 이슈를 기록하여 다음 단계를 면밀히 모니터링한다. | 이슈가 해결될 때까지 프로젝트를 보류하고 자원을 해제한다. | 유사 도구의 특허를 보유한 회사에 연락하여 현재 프로젝트와의 유사점과 차이점을 비교한다. | 핵심 이해관계자와 회의를 잡아 이슈를 검토하고 다음 단계를 결정한다. |  | D | 다른 회사가 매우 유사한 도구에 대한 특허를 보유하여 식별된 리스크가 이슈가 되었을 때, PM은 핵심 이해관계자와 회의를 잡아 이슈를 검토하고 다음 단계를 결정해야 한다. 관련 당사자와의 협력적 의사결정이 필수적이다. 제품 소유자에게 알리고 리스크 레지스터에 기록(A)은 문서화하지만 결정하지 않는다. 프로젝트 보류(B)는 과도한 반응이다. 특허 회사에 연락(C)은 법적 함의가 있으며 이해관계자 협의 없이 진행하면 안 된다.
1031 | A project is impacting several business units with different expectations and priorities. The project manager leading this project is meeting every month with each of these groups individually. During these meetings, each group has expressed dissatisfaction with the project and uses every opportunity to replace other groups' priorities with their own. What should the project manager do to address these challenges? | Develop a project schedule that accommodates all requirements from all groups. | Establish consensus on project priorities by meeting with all the groups together. | Meet with each group separately to avoid confrontation and send meeting notes at the end of each meeting. | Escalate the priorities of all the groups to the project sponsor and ask them to facilitate the process. |  | B | The correct answer is B. Establish consensus on project priorities by meeting with all the groups together. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트가 서로 다른 기대와 우선순위를 가진 여러 사업부에 영향을 미치고 있다. 프로젝트 관리자는 매월 각 그룹과 개별적으로 만나고 있다. 진행 중에 우선순위에 대한 갈등이 발생했다. PM은 어떻게 해야 하는가? | 모든 그룹의 모든 요구사항을 수용하는 프로젝트 일정을 개발한다. | 모든 그룹이 함께 참석하는 회의를 통해 프로젝트 우선순위에 대한 합의를 도출한다. | 대립을 피하기 위해 각 그룹과 별도로 만나고 각 회의 후 회의록을 보낸다. | 모든 그룹의 우선순위를 프로젝트 스폰서에게 에스컬레이션하고 프로세스를 촉진하도록 요청한다. |  | B | 정답은 B이다. 모든 그룹이 함께 참석하는 회의를 통해 프로젝트 우선순위에 대한 합의를 도출한다. 이 접근 방식은 상황을 효과적으로 다루면서 적절한 프로세스와 이해관계자 정렬을 유지하는 프로젝트 관리 모범 사례를 따른다.
1032 | A project is coming to a close, and the experienced project team members will be moving on to the next project. Who is responsible for ensuring that the appropriate knowledge transfer is done prior to project closure? | The project manager must ensure that the knowledge transfer occurred and that this is also included in the organizational process assets (OPAs), | The project sponsor must ensure all knowledge transfer is completed before project closure. | The stakeholders need to ensure they have received sufficient knowledge transfer for ongoing support after the project handover. | The project team members need to ensure they have supplied sufficient knowledge transfer. |  | A | The project manager is responsible for ensuring that appropriate knowledge transfer occurs prior to project closure. This includes facilitating the capture of lessons learned, documenting project experiences, and updating organizational process assets (OPAs) so that knowledge gained is preserved for future projects. The project sponsor (B) oversees governance but is not responsible for executing knowledge transfer activities. Stakeholders (C) are recipients of knowledge transfer, not its drivers. Individual team members (D) contribute to the process but the PM bears the overall accountability for ensuring it is completed. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트가 종료에 가까워지고 있으며, 경험 많은 프로젝트 팀원들이 다음 프로젝트로 이동할 예정이다. 프로젝트 종료 전 적절한 지식 이전이 이루어지도록 하는 책임은 누구에게 있는가? | 프로젝트 관리자가 지식 이전이 이루어졌는지 확인하고 이를 조직 프로세스 자산에 포함해야 한다. | 프로젝트 스폰서가 프로젝트 종료 전 모든 지식 이전이 완료되었는지 확인해야 한다. | 이해관계자가 프로젝트 종료 후 지속적 지원을 위해 충분한 지식 이전을 받았는지 확인해야 한다. | 프로젝트 팀원들이 충분한 지식 이전을 제공했는지 확인해야 한다. |  | A | 프로젝트 관리자는 프로젝트 종료 전 적절한 지식 이전이 이루어지도록 하는 책임이 있다. 이에는 교훈 포착 촉진, 프로젝트 경험 문서화, 조직 프로세스 자산(OPA) 업데이트가 포함되어 획득된 지식이 미래 프로젝트를 위해 보존된다. 프로젝트 스폰서(B)는 거버넌스를 감독하지만 지식 이전 실행 책임은 없다. 이해관계자(C)는 수신자이지 지식 이전 과정의 관리자가 아니다. 팀원(D)은 지식에 기여하지만 전체 이전 프로세스를 보장하는 것은 PM의 역할이다.
1033 | An organization imports many of the materials for a product build. Due to global shipping delays, some of the essential materials have yet to arrive, resulting in the inability to finish building the product for the upcoming release. The project manager is meeting with stakeholders to discuss options. What should the project manager recommend? | Update the project management plan, factoring in furloughs of the assembly team to reduce expenses. | Request marketing to launch an advertising campaign for the product that is currently in stock. | Explore if the materials could be supplied locally and obtained on time. | Meet with the engineering team to manufacture the materials in-house. |  | C | When global shipping delays prevent essential materials from arriving for an upcoming release, the project manager should explore if the materials could be supplied locally and obtained on time. Local sourcing mitigates the external dependency risk while maintaining the release schedule. Updating the plan with furloughs (A) reduces the team rather than solving the supply issue. Launching an advertising campaign for existing stock (B) does not address the supply problem. Manufacturing in-house (D) may not be feasible without proper capability. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 조직이 제품 제작을 위해 많은 자재를 수입하고 있다. 글로벌 배송 지연으로 일부 필수 자재가 아직 도착하지 않아 제품 완성이 불가능하다. 프로젝트 관리자는 어떻게 해야 하는가? | 조립팀의 일시 해고를 반영하여 비용을 줄이도록 프로젝트 관리 계획을 업데이트한다. | 마케팅에 현재 재고 중인 제품에 대한 광고 캠페인을 시작하도록 요청한다. | 자재를 현지에서 공급받아 제때 조달할 수 있는지 탐색한다. | 엔지니어링 팀과 만나 자재를 자체 제조할 수 있는지 논의한다. |  | C | 글로벌 배송 지연으로 필수 자재가 도착하지 않을 때, PM은 자재를 현지에서 공급받아 제때 조달할 수 있는지 탐색해야 한다. 현지 조달은 외부 의존성 리스크를 완화하면서 출시 일정을 유지한다. 일시 해고를 반영한 계획 업데이트(A)는 공급 문제를 해결하지 않고 팀을 줄인다. 광고 캠페인 시작(B)은 관련이 없다. 자체 제조(D)는 비현실적이고 비용이 많이 들 수 있다.
1034 | A project is about to close and the project manager is preparing a draft of the project closure report. The project sponsor has approached the project manager to stay on longer to ensure the benefits in the charter are tracked as completed. However, some of the benefits will not be realized until 1 year after project implementation. What should the project manager do? | Document who will be tracking benefits realization what will be tracked and when it will be tracked in the project closure report | Explain to the project sponsor that the project manager is only accountable for managing the project scope budget quality and schedule | Explain to the project sponsor that they are accountable for tracking benefits realization after project completion | Discuss extending the project manager ' s allocation to the project until all benefits are realized with the project management office (PMO) |  | A | The project closure report should include benefits realization information—identifying who will track and report benefits, which metrics and indicators will be used, and when benefits are expected to materialize. This documentation ensures the project sponsor and stakeholders understand the post-project benefits tracking plan, particularly when some benefits won't be realized until after project completion. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트가 종료되려 하고 있으며 프로젝트 관리자가 프로젝트 종료 보고서 초안을 준비하고 있다. 프로젝트 스폰서가 일부 혜택이 완료 후에야 실현될 것이므로 혜택 추적을 위해 더 오래 머물 것을 요청했다. PM은 어떻게 해야 하는가? | 혜택 실현을 누가 추적할 것인지, 무엇을 추적할 것인지, 언제 추적할 것인지를 프로젝트 종료 보고서에 문서화한다. | 프로젝트 관리자는 프로젝트 범위, 예산, 품질, 일정 관리에만 책임이 있음을 스폰서에게 설명한다. | 프로젝트 완료 후 혜택 실현 추적은 스폰서의 책임임을 설명한다. | 모든 혜택이 실현될 때까지 프로젝트 관리자의 배정을 연장하는 것을 프로젝트 관리 사무소와 논의한다. |  | A | 프로젝트 종료 보고서에는 혜택 실현 정보를 포함해야 한다—누가 혜택을 추적하고 보고할 것인지, 어떤 지표와 지표를 사용할 것인지, 혜택이 언제 실현될 것으로 예상되는지를 식별한다. 이 문서화는 특히 일부 혜택이 프로젝트 종료 후에야 실현될 때 스폰서와 이해관계자가 사후 혜택 추적 계획을 이해하도록 보장한다. 범위/예산/일정 관리만 책임이라는 설명(B)은 소극적이다. 스폰서 책임이라는 설명(C)은 정확하지만 문서화를 다루지 않는다. 배정 연장(D)은 프로젝트 범위를 넘어선다.
1035 | A company wants to show the commercial advantages of a product in a competitive market. They commissioned a project team to create a prototype. The team is building the prototype incrementally. What should the project manager set as a priority? | Implement the plan-do-check-action (PDCA) cycle. | Deliver business value as soon as possible. | Emphasize the use of Kanban methods. | Ensure that the project sponsor knows the schedule. |  | B | When a team is building a prototype incrementally to show commercial advantages in a competitive market, the project manager should prioritize delivering business value as soon as possible. Early value delivery enables market feedback. Implementing PDCA (A) is for continuous improvement, not prioritization. Emphasizing Kanban (C) addresses workflow visualization. Ensuring the sponsor knows the schedule (D) is communication, not prioritization. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 회사가 경쟁 시장에서 제품의 상업적 이점을 보여주려 한다. 프로젝트 팀에 프로토타입 제작을 의뢰했다. 팀은 점진적으로 프로토타입을 구축하고 있다. PM은 무엇에 집중해야 하는가? | 계획-실행-점검-조치(PDCA) 사이클을 실행한다. | 가능한 한 빨리 비즈니스 가치를 전달한다. | 칸반 방법의 사용을 강조한다. | 프로젝트 스폰서가 일정을 알도록 한다. |  | B | 팀이 경쟁 시장에서 상업적 이점을 보여주기 위해 점진적으로 프로토타입을 구축할 때, PM은 가능한 한 빨리 비즈니스 가치를 전달하는 데 집중해야 한다. 조기 가치 전달은 시장 피드백을 가능하게 한다. PDCA 실행(A)은 지속적 개선을 위한 것이지 우선순위 결정이 아니다. 칸반 강조(C)는 워크플로 시각화를 다룬다. 스폰서에게 일정 알리기(D)는 유용하지만 가치 전달보다 부차적이다.
1036 | A project team member identified a defect in the initial solution design for a project. The stakeholders are not sure whether to deploy the system or not. What should the project manager do? | Propose a solution redesign for the project | Revise the project ' s quality control measurements | Perform risk analysis against the issue. | Develop a mitigation based on the solution design |  | C | When a defect is found in the initial solution design and stakeholders are unsure whether to deploy, the project manager should perform risk analysis against the issue. Evaluating the potential impact informs the deploy-or-not decision. Proposing a redesign (A) acts before analysis. Revising quality control measurements (B) does not address the deployment decision. Developing a mitigation plan (D) should follow risk analysis. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 팀원이 프로젝트의 초기 솔루션 설계에서 결함을 식별했다. 이해관계자들은 시스템을 배포할지 확신하지 못하고 있다. PM은 어떻게 해야 하는가? | 프로젝트의 솔루션 재설계를 제안한다. | 프로젝트의 품질 통제 측정을 수정한다. | 이슈에 대한 리스크 분석을 수행한다. | 솔루션 설계를 기반으로 완화 조치를 개발한다. |  | C | 초기 솔루션 설계에서 결함이 발견되고 이해관계자가 배포 여부를 확신하지 못할 때, PM은 이슈에 대한 리스크 분석을 수행해야 한다. 잠재적 영향 평가는 배포 여부 결정에 정보를 제공한다. 재설계 제안(A)은 분석 전에 조치한다. 품질 통제 측정 수정(B)은 배포 결정을 다루지 않는다. 완화 계획 개발(D)은 리스크를 이해하기 전에는 시기상조이다.
1037 | A member of a testing team in an agile project works well with the project team. However, in the previous two iterations, this team member's performance was poor, and the team had difficulty meeting the iteration goals. How should the project manager handle this situation? | Allow the project team to discuss the problem with this team member. | Speak to the team member regarding the need to improve performance. | Discuss the issue with the team member ' s functional manager. | Inform the human resource (HR) department about the issue. |  | A | When a well-integrated agile team member has poor performance over two iterations affecting iteration goals, the project manager should allow the team to discuss the problem with the team member. Self-organizing agile teams are empowered to address internal performance issues collaboratively. Speaking to the member about improvement (B) is PM-directed rather than team-driven. Discussing with the functional manager (C) escalates before team engagement. Informing HR (D) is premature. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 프로젝트 테스트 팀의 한 맴버가 프로젝트 팀과 잘 협력한다. 그러나 지난 두 번의 이터레이션에서 이 팀원의 성과가 저조했고, 팀은 이터레이션 목표를 달성하는 데 어려움을 겪었다. PM은 어떻게 해야 하는가? | 프로젝트 팀이 해당 팀원과 문제를 논의하도록 한다. | 팀원에게 성과 개선의 필요성에 대해 말한다. | 팀원의 기능 관리자와 이슈를 논의한다. | 인사(HR) 부서에 이슈를 알린다. |  | A | 잘 통합된 애자일 팀원의 성과가 두 번의 이터레이션에 걸쳐 저조하여 목표에 영향을 미칠 때, PM은 팀이 해당 팀원과 문제를 논의하도록 해야 한다. 자기 조직화된 애자일 팀은 내부 성과 문제를 협력적으로 해결할 권한이 있다. 개선에 대해 말하기(B)는 PM 주도적이며 팀 주도적이지 않다. 기능 관리자와 논의(C)는 팀 외부로 에스컬레이션하는 것이다. HR에 알리기(D)는 직접 해결 시도 전에는 시기상조이다.
1038 | A project is in the execution phase. The client was actively involved in the early stages but has been less engaged lately. A number of changes to the requirements have recently been requested. What should the project manager do next? | Review the risk register to see if mitigations have already been outlined for this scenario. | Review the changes and make the decision based on the project team ' s recommendations. | Discuss the changes with the client and jointly make the decision on how to proceed. | Reject the changes and stay the original course as initially agreed with the client. |  | C | When a client's engagement changes during project execution, maintaining open communication and collaboration is crucial. Discussing requested changes with the client ensures their needs are understood and considered. This collaborative approach aligns with PMI's emphasis on stakeholder engagement—jointly assessing impact on objectives, timeline, and budget to make informed decisions. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트가 실행 단계에 있다. 고객은 초기 단계에서 적극적으로 참여했지만 최근 참여가 줄었다. 요구사항에 대한 여러 변경이 요청되었다. PM은 어떻게 해야 하는가? | 리스크 레지스터를 검토하여 이 시나리오에 대한 완화 조치가 이미 설명되어 있는지 확인한다. | 변경 사항을 검토하고 프로젝트 팀의 권고를 바탕으로 결정한다. | 고객과 변경 사항을 논의하고 진행 방법을 공동으로 결정한다. | 변경 사항을 거부하고 고객과 초기에 합의한 대로 원래 경로를 유지한다. |  | C | 프로젝트 실행 중 고객의 참여가 변할 때, 개방적 소통과 협업 유지가 중요하다. 요청된 변경 사항을 고객과 논의하면 그들의 요구가 이해되고 고려된다. 이 협력적 접근은 PMI의 이해관계자 참여 강조와 일치하며—목표, 일정, 예산에 대한 영향을 공동으로 평가하여 정보에 입각한 결정을 내린다. 리스크 레지스터 검토(A)는 완화 조치를 확인하지만 고객과의 협력이 부족하다. 팀 권고 기반 결정(B)은 고객 입력을 배제한다. 변경 거부(D)는 고객 관계를 손상시킨다.
1039 | During an agile project, a project manager lost one of the resources, and at the same time, uncovered new requirements, which were added to the backlog. What should the project manager do next? | Reevaluate the velocity as the iteration duration will be impacted by new requirements | Reevaluate the project schedule as the velocity will be impacted by the loss of resources | Reevaluate the scope of the current iteration to keep the same velocity and timeline | Reevaluate the backlog priority with the product owner since the velocity has been impacted |  | D | When an agile team loses a resource while new requirements are added to the backlog, the project manager should reevaluate the backlog priority with the product owner since velocity has been impacted. Reduced team capacity requires reassessing which items deliver the most value given current constraints. Reevaluating velocity alone (A) assesses impact but does not adjust priorities. Reevaluating the project schedule (B) applies a predictive approach. Reevaluating current iteration scope (C) is narrow and does not address the broader backlog. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | 애자일 프로젝트에서 PM이 자원 한 명을 잃었고, 동시에 새로운 요구사항이 발견되어 백로그에 추가되었다. PM이 다음으로 해야 할 일은? | 이터레이션 기간이 새로운 요구사항으로 인해 영향을 받으므로 벨로시티를 재평가한다. | 자원 손실로 벨로시티가 영향을 받으므로 프로젝트 일정을 재평가한다. | 동일한 벨로시티와 일정을 유지하기 위해 현재 이터레이션의 범위를 재평가한다. | 벨로시티가 영향을 받았으므로 제품 소유자와 백로그 우선순위를 재평가한다. |  | D | 애자일 팀이 자원을 잃고 새로운 요구사항이 백로그에 추가될 때, PM은 벨로시티가 영향을 받았으므로 제품 소유자와 백로그 우선순위를 재평가해야 한다. 감소된 팀 역량은 현재 제약 조건에서 가장 많은 가치를 전달하는 항목을 재평가해야 한다. 벨로시티만 재평가(A)는 영향을 평가하지만 우선순위를 조정하지 않는다. 일정 재평가(B)는 우선순위가 아닌 일정에 초점을 맞춤다. 이터레이션 범위 재평가(C)는 좨 더 넓은 백로그 우선순위 재평가가 필요하다.
1040 | A project manager who has been working on an ongoing volatile project is retiring. A new project manager is collaborating with the retiring project manager to ensure a smooth transition. What should the new project manager first discuss, review, and clarify during the transition meetings? | Lessons learned log | Resource management plan | Risk register | Change management plan |  | C | The correct answer is C. Risk register. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | General | General PM Principles | Business Environment | Support Organizational Change | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 변동성이 큰 프로젝트를 담당하던 PM이 퇴직한다. 새 PM이 퇴직하는 PM과 협력하여 원활한 전환을 보장하고 있다. 새 PM이 검토해야 하는 가장 중요한 문서는? | 교훈 로그 | 자원 관리 계획 | 리스크 레지스터 | 변경 관리 계획 |  | C | 변동성이 큰 프로젝트의 전환 시 새 PM이 검토해야 하는 가장 중요한 문서는 리스크 레지스터이다. 변동성이 큰 프로젝트에서는 리스크가 프로젝트 결과에 직접 영향을 미친다. 교훈 로그(A)는 가치 있지만 미래 개선을 위한 것이다. 자원 관리 계획(B)은 중요하지만 리스크보다 덮 위험하지 않다. 변경 관리 계획(D)은 프로세스를 다루지만 현재의 위험 요소는 다루지 않는다.
1041 | A project manager is working on a project. A few months after the project has launched, the project manager starts receiving complaints from the business unit managers about the lack of updated project information. What should the project manager do? | Check the organizational responsibility of functional managers in the project. | Run Monte Carlo simulation to identify any flaws in the communication matrix. | Review the communications management plan and stakeholder register. | Request that the business unit managers attend weekly review meetings. |  | C | When business unit managers complain about lacking updated project information months after launch, the project manager should review the communications management plan and stakeholder register. These artifacts define information needs and channels. Checking organizational responsibility (A) addresses roles, not information flow. Running Monte Carlo simulation (B) is a risk analysis tool, not communication-related. Requesting managers attend meetings (D) assumes meetings are the right solution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Hybrid/Tailoring | PM이 프로젝트를 진행 중이다. 프로젝트 시작 몇 개월 후 사업부 관리자들로부터 프로젝트 정보 업데이트 부족에 대한 불만을 받기 시작했다. PM은 어떻게 해야 하는가? | 프로젝트에서 기능 관리자의 조직적 책임을 확인한다. | 커뮤니케이션 매트릭스의 결함을 식별하기 위해 본테카를로 시뮬레이션을 실행한다. | 커뮤니케이션 관리 계획과 이해관계자 레지스터를 검토한다. | 사업부 관리자에게 주간 검토 회의에 참석하도록 요청한다. |  | C | 사업부 관리자가 프로젝트 정보 업데이트 부족을 불만스러워할 때, PM은 커뮤니케이션 관리 계획과 이해관계자 레지스터를 검토해야 한다. 이러한 산출물은 정보 요구와 채널을 정의한다. 조직적 책임 확인(A)은 역할을 다루지만 정보 흐름은 다루지 않는다. 본테카를로 시뮬레이션(B)은 리스크 분석 도구이지 커뮤니케이션 도구가 아니다. 회의 참석 요청(D)은 일방향적이며 근본 원인을 해결하지 않는다.
1042 | A project manager is reviewing the requirements of a large program. Which requirements should the project team prioritize to avoid getting fines? | Establishing company processes | Complying with new regulations | Developing new product lines | Certifying sustainable products |  | B | When reviewing requirements for a large program, the project team should prioritize complying with new regulations to avoid fines. Regulatory compliance is mandatory and non-negotiable. Establishing company processes (A) is internal improvement. Developing new product lines (C) is strategic growth. Certifying sustainable products (D) may be important but is secondary to mandatory compliance. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Business Environment | Plan and Manage Compliance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | PM이 대규모 프로그램의 요구사항을 검토하고 있다. 벌금을 피하기 위해 프로젝트 팀이 우선시해야 할 요구사항은? | 회사 프로세스 수립 | 새로운 규정 준수 | 새로운 제품 라인 개발 | 지속가능한 제품 인증 |  | B | 대규모 프로그램의 요구사항을 검토할 때, 벌금을 피하기 위해 새로운 규정 준수를 우선시해야 한다. 규제 준수는 필수적이고 협상의 여지가 없다. 회사 프로세스 수립(A)은 내부 개선이다. 새로운 제품 라인 개발(C)은 전략적 성장이다. 지속가능 제품 인증(D)은 중요하지만 필수 준수보다 부차적이다.
1043 | A new major road project is starting, and the contractor has contractually committed to submitting regular status reports and participating in integration meetings. Halfway through the project life cycle, the contractor stops participating in meetings and submitting reports, stating these items consume too much time. What should the project manager do first? | Assess the risk of the contractor not attending meetings and submitting reports for the rest of the project and escalate it to the project sponsor. | Remind the contractor that they committed to attending meetings and submitting reports per the contract. | Speak with the company's lawyer and request that they demand the contractor fulfill their contractual commitments. | Submit a claim for not fulfilling the contract terms and handle the claim in accordance with the alternative dispute resolution. |  | B | When a contractor stops participating in meetings and submitting reports despite contractual commitments, the project manager should first remind the contractor of their obligations. Direct communication to address the compliance gap is the appropriate initial step—it seeks to understand the contractor's perspective and work toward resolution before escalating. Assessing and escalating the risk to the sponsor (A) is premature before direct engagement. Speaking with the company's lawyer (C) escalates to legal action too quickly. Submitting a formal claim (D) is the most aggressive response and should be a last resort. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 새로운 주요 도로 프로젝트가 시작되었고, 계약업체가 정기적인 상태 보고서 제출과 통합 회의 참여를 계약적으로 약속했다. 프로젝트 수명주기 중반에 계약업체가 회의 불참과 보고서 미제출을 시작했다. PM은 어떻게 해야 하는가? | 계약업체의 회의 불참과 보고서 미제출의 리스크를 평가하고 에스컬레이션한다. | 계약업체에게 계약에 따른 회의 참석과 보고서 제출 의무를 상기시킨다. | 회사 변호사에게 계약업체가 계약 의무를 이행하도록 요구하도록 요청한다. | 계약 조건 불이행에 대한 청구를 제출하고 대안적 분쟁 해결 절차에 따라 처리한다. |  | B | 계약업체가 계약상 약속에도 불구하고 회의 참여와 보고서 제출을 중단할 때, PM은 먼저 계약업체에게 의무를 상기시켜야 한다. 준수 격차를 해결하기 위한 직접 소통이 적절한 초기 단계이다—계약업체의 관점을 이해하고 에스컬레이션 전에 해결을 모색한다. 리스크 평가 및 에스컬레이션(A)은 직접 소통 전에는 시기상조이다. 변호사 개입(C)은 과도한 에스컬레이션이다. 청구 제출(D)은 상호 합의 시도 없이 법적 조치를 취하는 것이다.
1044 | A project manager is working on a project to transform the service delivery model in the organization. As part of the scope, this project includes diverse elements that have been well defined by the product owner. The team has expressed that the scope is not clearly defined. How should the project manager address this situation? | Meet with the product owner to validate the backlog prioritization. | Ask the team members to focus only on their assignments. | Ask the product owner to clarify the project ' s vision with the team. | Distribute the release plan among the team members. |  | C | When a team expresses the scope is unclear despite the product owner defining diverse elements, the project manager should ask the product owner to clarify the project's vision with the team. Vision clarity resolves scope confusion. Distributing the release plan (A) addresses schedule, not understanding. Asking members to focus on assignments (B) is directive. Validating backlog prioritization with the PO (D) focuses on ordering, not clarity. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | PM이 조직의 서비스 전달 모델을 변환하는 프로젝트를 진행 중이다. 범위에는 제품 소유자가 잘 정의한 다양한 요소가 포함되어 있지만, 팀은 범위가 불명확하다고 표현했다. PM은 어떻게 해야 하는가? | 제품 소유자와 만나 백로그 우선순위를 검증한다. | 팀원들에게 자신의 업무에만 집중하도록 요청한다. | 제품 소유자에게 팀과 함께 프로젝트 비전을 명확히 하도록 요청한다. | 팀원들에게 릴리스 계획을 배포한다. |  | C | 제품 소유자가 다양한 요소를 정의했음에도 팀이 범위가 불명확하다고 표현할 때, PM은 제품 소유자에게 팀과 함께 프로젝트 비전을 명확히 하도록 요청해야 한다. 비전의 명확성이 범위 혼란을 해결한다. 릴리스 계획 배포(A)는 일정을 다루지 이해를 다루지 않는다. 업무 집중 요청(B)은 지시적이다. 백로그 우선순위 검증(D)은 유용하지만 근본적인 비전 불명확성을 해결하지 않는다.
1045 | A project team strongly encourages the project manager to purchase an application that will significantly reduce work time. Without the application, the deadline might be missed. However, the purchase will impact the project cost. The sponsor would like to explore a less expensive application that will save the team's time. What should the project manager do? | Analyze assumptions and constraints. | Create a decision tree. | Purchase the application. | Raise a change request. |  | B | When the team wants an expensive application to meet the deadline while the sponsor prefers a cheaper alternative, the project manager should create a decision tree. A decision tree visualizes outcomes, costs, and probabilities for objective comparison of options. Analyzing assumptions and constraints (A) is general. Purchasing the application (C) ignores the sponsor's input. Raising a change request (D) is premature before analysis. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트 팀이 PM에게 작업 시간을 크게 줄여줄 애플리케이션 구매를 강력히 권고한다. 애플리케이션 없이는 마감일을 놓칠 수 있다. 그러나 구매 비용이 예산을 초과하며, 스폰서는 더 저렴한 대안을 선호한다. PM은 어떻게 해야 하는가? | 가정과 제약 조건을 분석한다. | 의사결정 트리를 만든다. | 애플리케이션을 구매한다. | 변경 요청을 제기한다. |  | B | 팀이 마감일을 맞추기 위해 값비싼 애플리케이션을 원하고 스폰서는 더 저렴한 대안을 선호할 때, PM은 의사결정 트리를 만들어야 한다. 의사결정 트리는 결과, 비용, 확률을 시각화하여 옵션의 객관적 비교를 가능하게 한다. 가정과 제약 조건 분석(A)은 일반적이다. 애플리케이션 구매(C)는 스폰서 입력을 무시한다. 변경 요청 제기(D)는 의사결정 분석을 대체하지 않는다.
1046 | A project manager joins an existing project. One project stakeholder is unhappy with the frequency and types of project updates received and has made a request for more information to be shared. What should the project manager do next? | Consult the scope baseline document to track project updates | Inform the stakeholder to wait for the annual stakeholder review meeting | Update the project communications management plan immediately | Schedule a meeting with the stakeholder to better understand their request |  | D | The correct answer is D. Schedule a meeting with the stakeholder to better understand their request. Effective stakeholder management requires proactive engagement, transparent communication, and alignment with project objectives. Understanding stakeholder needs and addressing their concerns is essential for project success. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자가 기존 프로젝트에 합류했다. 한 프로젝트 이해관계자가 프로젝트 업데이트 빈도에 불만을 가지고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 업데이트를 추적하기 위해 범위 기준선 문서를 참조한다. | 연례 이해관계자 검토까지 기다리라고 이해관계자에게 알린다. | 프로젝트 커뮤니케이션 관리 계획을 즉시 업데이트한다. | 이해관계자와 미팅을 예약하여 그들의 요청을 더 잘 이해한다. |  | D | 정답은 D이다. 이해관계자와 미팅을 예약하여 그들의 요청을 더 잘 이해해야 한다. 효과적인 이해관계자 관리는 능동적 참여, 투명한 소통, 이해관계자 요구와 프로젝트 목표의 정렬을 필요로 한다.
1047 | A project is on its third iteration out of nine. During the daily meetings, the project team realizes that some deliverable approvals are delayed because a key stakeholder is out of the office. | Remove the deliverables from the iteration backlog. | Meet with the stakeholders and request a solution. | Update the issue log and escalate it to the project sponsor. | Ask the team to work on the unblocked deliverables. |  | D | The correct answer is D. Ask the team to work on the unblocked deliverables. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 프로젝트가 9회 반복 중 3번째 반복에 있다. 일일 회의 중 팀이 일부 산출물이 차단되었다고 보고했다. 프로젝트 관리자는 어떻게 해야 하는가? | 반복 백로그에서 산출물을 제거한다. | 이해관계자와 만나 해결책을 요청한다. | 이슈 로그를 업데이트하고 프로젝트 스폰서에게 에스컬레이션한다. | 팀에게 차단되지 않은 산출물에 대해 작업하도록 요청한다. |  | D | 정답은 D이다. 팀에게 차단되지 않은 산출물에 대해 작업하도록 요청해야 한다. 애자일 환경에서 PM은 팀 협업을 촉진하고, 장애물을 제거하며, 지속적인 가치 전달을 보장해야 한다.
1048 | A key team member shared confidential information about another team member with management, a practice that is against ethical standards. During a team meeting, some of the team members requested that the key team member be removed from the team. What should the project manager do next? | Speak with the key team member to clarify the situation. | Suspend the team member until further notice. | Conduct a meeting with the team to deliberate on a decision. | Contact the human resource (HR) department for a solution. |  | A | When a team member breaches ethical standards by sharing confidential information, the PM should address the issue directly through a private conversation. This allows the PM to clarify the situation, understand the reasons behind the breach, explain consequences and expectations, and work toward resolution. Direct communication restores trust and prevents escalation. Escalating to a sponsor (A) is too passive, a group discussion (C) may increase tension, and immediate removal (D) may violate due process or contractual obligations. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 핵심 팀원이 다른 팀원에 대한 기밀 정보를 프로젝트 스폰서에게 공유했다. 프로젝트 관리자는 어떻게 해야 하는가? | 핵심 팀원과 대화하여 상황을 명확히 한다. | 추후 통지가 있을 때까지 해당 팀원을 정직시킨다. | 팀과 회의를 진행하여 결정을 심의한다. | 인사(HR) 부서에 연락하여 해결책을 구한다. |  | A | 팀원이 기밀 정보를 공유하여 윤리 기준을 위반했을 때, PM은 비공개 대화를 통해 문제를 직접 해결해야 한다. 이를 통해 상황을 명확히 하고, 기밀 유지 기대치를 강화하며, 에스컬레이션 전에 시정 조치를 적용할 수 있다.
1049 | During the early phase of a project, the requirements documentation was not approved. It was identified that the leader of a user party was not included in any of the requirements collection communications. Which of the documents was likely missed or outdated? | Project Charter | Risk Register | Stakeholder Register | Business Documentation |  | C | When a user party leader was excluded from requirements collection communications during the early project phase, the document likely missed or outdated was the Stakeholder Register. This critical document lists all project stakeholders, their roles, requirements, expectations, and influence. An up-to-date Stakeholder Register ensures all relevant parties are included in communications and requirements gathering. The Project Charter (A) defines high-level scope, not individual stakeholder details. The Risk Register (B) tracks risks, not stakeholder information. Business Documentation (D) provides business justification, not stakeholder identification. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 초기 단계에서 요구사항 문서가 모든 주요 당사자의 승인을 받지 못했다. 이후 사용자측 리더가 요구사항 수집 커뮤니케이션에서 누락되었음이 밝혀졌다. 어떤 문서가 누락되었거나 오래되었을 가능성이 가장 높은가? | 프로젝트 헌장 | 리스크 레지스터 | 이해관계자 레지스터 | 비즈니스 문서 |  | C | 사용자측 리더가 프로젝트 초기 단계에서 요구사항 수집 커뮤니케이션에서 제외되었을 때, 누락 또는 오래되었을 가능성이 가장 높은 문서는 이해관계자 레지스터이다. 이 핵심 문서는 모든 이해관계자와 그들의 역할, 관심사, 커뮤니케이션 요구사항을 식별한다.
1050 | During a meeting for product review, a key stakeholder announces that because they are receiving adequate information about the project they will not attend any further meetings. What should the project manager do? | Ignore the stakeholder as the product is almost complete. | Log this as an issue in the issue log and address it with the project sponsor. | Inform the stakeholder that changes can happen in this project. | Explain that the needs will be updated in the stakeholder engagement plan. |  | D | When a key stakeholder says they receive adequate information and will not attend further meetings, the project manager should explain that their needs will be updated in the stakeholder engagement plan. This dynamic document should reflect changing stakeholder requirements and continued engagement is important for project success. Ignoring the stakeholder (A) risks losing valuable input. Logging it as an issue and escalating to the sponsor (B) over-escalates a manageable situation. Informing the stakeholder about potential changes (C) is vague and does not address the engagement strategy. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 제품 검토 미팅 중 핵심 이해관계자가 충분한 정보를 받고 있으므로 향후 미팅에 참석하지 않겠다고 발표했다. 프로젝트 관리자는 어떻게 해야 하는가? | 제품이 거의 완성되었으므로 이해관계자를 무시한다. | 이슈 로그에 이슈로 기록하고 팀과 함께 해결한다. | 이해관계자에게 이 프로젝트에서는 변경이 발생할 수 있다고 알린다. | 이해관계자 참여 계획에서 그들의 요구가 업데이트될 것이라고 설명한다. |  | D | 핵심 이해관계자가 충분한 정보를 받고 있으므로 향후 미팅에 참석하지 않겠다고 할 때, PM은 이해관계자 참여 계획에서 그들의 요구가 업데이트될 것이라고 설명해야 한다. 이는 지속적 참여를 보장하고 프로젝트 변경에 대한 정보를 유지하게 한다.
1051 | In the middle of an iteration, the product owner tells the agile team that the government has updated legal requirements. This will result in some changes in the product definition. How should the project manager handle this situation? | Continue work and ask the product owner to assess the changes and add/remove thestories as needed in the backlog. | Ask a business analyst to assess the changes and then add/remove the stories in thebacklog and prioritize them by business value. | Review the iteration backlog because the product definition has changed and needs tobe reassessed before continuing the project. | Ask the product owner to add new changes to the bottom of the backlog in order tohandle the modifications as a change request. |  | A | When the product owner informs the agile team of updated legal requirements mid-iteration, the project manager should continue work and ask the product owner to assess the changes and add or remove stories as needed in the backlog. The product owner is responsible for managing the backlog and incorporating requirement changes while the team maintains focus on current iteration work. Asking a business analyst to assess and prioritize changes (B) bypasses the product owner's authority. Reviewing the iteration backlog to reassess before continuing (C) may be disruptive if the changes can be incorporated into future iterations. Adding changes to the bottom of the backlog as a change request (D) may not reflect the urgency of legal compliance. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 반복 중간에 제품 소유자가 애자일 팀에게 정부가 법적 요구사항을 업데이트했다고 알렸다. 프로젝트 관리자는 어떻게 해야 하는가? | 작업을 계속하고 제품 소유자에게 변경 사항을 평가하여 백로그에서 스토리를 추가/제거하도록 요청한다. | 비즈니스 분석가에게 변경 사항을 평가한 후 스토리를 추가/제거하도록 요청한다. | 제품 정의가 변경되었으므로 반복 백로그를 검토한다. | 제품 소유자에게 제품 백로그 하단에 새 변경 사항을 추가하도록 요청한다. |  | A | 제품 소유자가 반복 중간에 법적 요구사항 업데이트를 알렸을 때, PM은 작업을 계속하고 제품 소유자에게 변경 사항을 평가하여 백로그에서 스토리를 추가/제거하도록 요청해야 한다. 이는 애자일의 적응적 특성을 유지하면서 적절한 변경 관리를 보장한다.
1052 | A project manager has noticed that a critical team member is consistently arguing with a client. This has started to have a negative effect on the meetings. How should the project manager address this? | Explain the impact of the scenario to the project team member. | Remove the project team member from all future meetings. | Recommend a performance improvement plan to the project team member. | Talk to the client privately to highlight the situation. |  | A | When a critical team member is consistently arguing with a client and negatively affecting meetings, the project manager should explain the impact of the scenario to the team member. Direct feedback raises awareness of the consequences. Removing the team member from meetings (B) eliminates their contribution. Recommending a performance improvement plan (C) is a formal escalation, not a first step. Talking to the client privately (D) addresses only one side. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 핵심 팀원이 지속적으로 고객과 논쟁하여 미팅에 부정적 영향을 미치고 있음을 발견했다. 프로젝트 관리자는 어떻게 해야 하는가? | 해당 팀원에게 상황의 영향을 설명한다. | 해당 팀원을 향후 모든 미팅에서 제외한다. | 해당 팀원에게 성과 개선 계획을 권고한다. | 고객에게 비공개로 상황을 알린다. |  | A | 핵심 팀원이 지속적으로 고객과 논쟁하여 미팅에 부정적 영향을 미칠 때, PM은 해당 팀원에게 상황의 영향을 설명해야 한다. 직접적 피드백은 전문적 성장을 촉진하고 문제를 비공개로 해결한다.
1053 | During a blueprint review meeting, the finance department representative is not comfortable with a proposed solution that favors another department. As a result, document approval is delayed and impacts the project schedule. What should the project manager do? | Schedule a meeting with the project sponsor to seek advice on the approach of both departments | Work with the project team to find a compromise solution that suits both departments | Assess the risk of postponing this specific solution and advise both departments of the delay | Arrange a meeting with the two departments to understand their differences and address their needs |  | D | When a finance department representative blocks document approval due to discomfort with a solution favoring another department, the project manager should arrange a meeting with both departments to understand their differences and address their needs. Direct facilitation enables collaborative resolution. Finding a compromise (A) may be premature without understanding concerns. Seeking sponsor advice (B) escalates before attempting resolution. Assessing risk and advising of delay (C) is passive. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 설계 검토 미팅에서 재무 부서 대표가 다른 부서에 유리한 솔루션에 불만을 표시하며 문서 승인을 거부하고 있다. 프로젝트 관리자는 어떻게 해야 하는가? | 프로젝트 스폰서와 미팅을 예약하여 해결 방법에 대한 조언을 구한다. | 프로젝트 팀과 협력하여 양쪽 부서를 만족시키는 절충안을 찾는다. | 이 특정 솔루션 연기의 리스크를 평가하고 그에 따라 조언한다. | 두 부서와 미팅을 주선하여 이견을 이해하고 합의점을 찾는다. |  | D | 재무 부서 대표가 다른 부서에 유리한 솔루션에 불만으로 문서 승인을 거부할 때, PM은 두 부서와 미팅을 주선하여 이견을 이해하고 합의점을 찾아야 한다. 직접적 대화가 가장 효과적인 갈등 해결 방법이다.
1054 | A project team member is providing updates to assigned work and reports a task as complete. As the project progresses, it is observed that the task is not fully complete. What should the project manager do moving forward? | Provide templates for the product owner to use in the future. | Review the task list with the team on a regular basis, | Review the task with the sponsor to see if they are satisfied. | Provide clear expectations around task requirements. |  | D | When a team member reports a task as complete but it is later found incomplete, the project manager should provide clear expectations around task requirements moving forward. Establishing explicit definition of done criteria and task completion standards prevents future misunderstandings. Providing templates for the product owner (A) shifts responsibility. Reviewing with the sponsor (B) escalates unnecessarily. Reviewing the task list regularly (C) monitors progress but does not address the root cause of unclear expectations. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀원이 배정된 작업에 대해 업데이트를 제공하고 작업이 완료되었다고 보고했으나, 이후 불완전한 것으로 확인되었다. 프로젝트 관리자는 어떻게 해야 하는가? | 제품 소유자가 향후 사용할 템플릿을 제공한다. | 팀과 정기적으로 작업 목록을 검토한다. | 스폰서와 작업을 검토하여 만족하는지 확인한다. | 작업 요구사항에 대한 명확한 기대치를 제공한다. |  | D | 팀원이 작업을 완료했다고 보고했으나 이후 불완전한 것으로 확인되었을 때, PM은 향후 작업 요구사항에 대한 명확한 기대치를 제공해야 한다. 명시적인 완료 정의를 수립하면 이해를 맞추고 재발을 방지한다.
1055 | During a status meeting, a project manager reported that a project is on track. However, the project sponsor thinks the project is behind schedule because a few tasks have already passed their planned finish dates but are still in progress. How should the project manager revise the report and demonstrate the project is on schedule? | Use a network diagram to show the task duration and dependencies among tasks. | Use a Gantt chart to compare the actual schedule with the planned project schedule. | Use a resource histogram to show that the resources are adequate to complete all tasks on time. | Use a network diagram to show that the delayed tasks are not on the critical path. |  | D | When the sponsor believes the project is behind schedule because some tasks have passed their planned dates, the project manager should use a network diagram to show that the delayed tasks are not on the critical path. Demonstrating that slipped tasks have float and do not affect the overall completion date directly addresses the sponsor's concern. Using a network diagram for task duration (A) does not clarify critical path impact. A Gantt chart (B) shows variance but not float clearly. A resource histogram (C) addresses capacity, not schedule logic. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 상태 미팅에서 프로젝트 관리자가 프로젝트가 순조롭다고 보고했다. 그러나 스폰서는 일부 작업이 계획된 날짜를 지났기 때문에 프로젝트가 지연되고 있다고 생각한다. 프로젝트 관리자는 어떻게 해야 하는가? | 네트워크 다이어그램을 사용하여 작업 기간과 종속성을 보여준다. | 간트 차트를 사용하여 실제 일정과 계획된 일정을 비교한다. | 자원 히스토그램을 사용하여 자원이 적절함을 보여준다. | 네트워크 다이어그램을 사용하여 지연된 작업이 주공정선에 없음을 보여준다. |  | D | 스폰서가 일부 작업이 계획된 날짜를 지났기 때문에 프로젝트가 지연된다고 생각할 때, PM은 네트워크 다이어그램을 사용하여 지연된 작업이 주공정선에 없음을 보여주어야 한다. 이는 전체 일정에 영향을 미치지 않음을 시각적으로 입증한다.
1056 | A project manager needs the team to define the steps and identify the risks of migrating data to a new system. What type of leadership should the project manager use to accomplish this? | Laissez-faire | Transformational | Dynamic | Servant |  | D | When the project manager needs the team to define migration steps and identify risks, servant leadership is the appropriate style. Servant leaders focus on team growth, empowerment, and removing obstacles so the team can perform effectively. Laissez-faire (A) provides too little guidance. Transformational (B) inspires vision but may not prioritize team needs in this context. Dynamic (C) is not a recognized leadership style in PMI frameworks. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 팀에게 마이그레이션 단계를 정의하고 리스크를 식별하도록 요청해야 한다. 어떤 리더십 스타일이 적절한가? | 방임형(Laissez-faire) | 변혁적(Transformational) | 동적(Dynamic) | 서번트(Servant) |  | D | PM이 팀에게 마이그레이션 단계를 정의하고 리스크를 식별하도록 할 때, 서번트 리더십이 적절한 스타일이다. 서번트 리더는 팀 성장, 권한 부여, 장애물 제거에 집중하여 팀이 스스로 문제를 해결할 수 있도록 한다.
1057 | A team needs to follow defined cybersecurity compliance that is mandatory for a customer project. What should the project manager do to monitor compliance in the project? | Confer with team members. | Discuss with the customer. | Schedule regular project audits. | Review with security experts. |  | C | To monitor mandatory cybersecurity compliance on a customer project, the project manager should schedule regular project audits. Audits provide structured assessment, monitoring, and documentation of compliance status—identifying gaps and ensuring adherence to required standards. Conferring with team members (A) is informal. Discussing with the customer (B) addresses external expectations but not internal monitoring. Reviewing with security experts (D) provides expertise but not systematic, recurring compliance checks. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | 팀이 고객 프로젝트에 필수적인 정해진 사이버 보안 컴플라이언스를 준수해야 한다. 프로젝트 관리자는 컴플라이언스를 어떻게 모니터링해야 하는가? | 팀원들과 협의한다. | 고객과 논의한다. | 정기적인 프로젝트 감사를 예약한다. | 보안 전문가와 검토한다. |  | C | 고객 프로젝트에서 필수 사이버 보안 컴플라이언스를 모니터링하기 위해 PM은 정기적인 프로젝트 감사를 예약해야 한다. 감사는 컴플라이언스 요구사항에 대한 구조화된 평가, 모니터링 및 문서화를 제공한다.
1058 | An agile team has completed five sprints. The final product is expected to be delivered in another three sprints. The project manager receives a call from the technical resource manager that one of the developers must take leave for the next 4 weeks, with no temporary replacement available. This is going to significantly impact the deliverable. What should the project manager do? | Perform an impact analysis, readjust the schedule as needed, and communicate the changes to the customer. | Request additional funding from the sponsor to obtain a new resource to fill in the gap. | Ask the product owner to stretch the delivery team further to complete the final product in the original timeline. | Inform the customer of the impact immediately and prepare for escalation. |  | A | When a key developer must take unexpected leave with no replacement available and the impact on deliverables is significant, the project manager should perform an impact analysis, readjust the schedule as needed, and communicate changes to the customer. Systematic assessment and transparent communication maintain trust and realistic expectations. Requesting additional funding for a new resource (B) may not be feasible. Asking the team to stretch further (C) risks burnout. Informing the customer and preparing for escalation (D) is premature before assessment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 애자일 팀이 5개 스프린트를 완료했다. 핵심 개발자가 예상치 못한 휴가를 가야 하고 대체 인력이 없어 산출물에 상당한 영향이 예상된다. 프로젝트 관리자는 어떻게 해야 하는가? | 영향 분석을 수행하고 필요에 따라 일정을 조정하며 이해관계자에게 알린다. | 스폰서에게 새 테스터를 확보하기 위한 추가 자금을 요청한다. | 제품 소유자에게 배달 팀을 더 늘리도록 요청한다. | 고객에게 즉시 영향을 알리고 범위 변경을 준비한다. |  | A | 핵심 개발자가 예상치 못한 휴가를 가야 하고 대체 인력이 없어 산출물에 상당한 영향이 예상될 때, PM은 영향 분석을 수행하고 필요에 따라 일정을 조정하며 이해관계자에게 알려야 한다. 이는 투명성과 적절한 기대치 관리를 보장한다.
1059 | A project is 20% complete. The client has accepted a project order amendment that involves a major change. Without this major change, the project result will be useless for the client organization. What should the project manager do? | Update the project status from " active " to " on hold " until there is more clarity on the scope of the change. | Consult the project sponsor to understand if the change must be processed for project execution. | Initiate planning for the project with the modified scope as laid out in the client ' s purchase order. | Set up a meeting with the client and the project team to identify ways to safeguard the project from the change. |  | C | When a project is 20% complete and the client has accepted an order amendment involving a major change without which the result is useless, the project manager should consult the project sponsor to understand if the change must be processed for execution. Sponsor guidance is needed for major scope changes. Putting the project on hold (A) delays unnecessarily. Initiating replanning directly (C) skips governance. Meeting to safeguard from the change (D) resists a necessary change. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Adopt a Holistic View | Collect Requirements | Traditional PM | 프로젝트가 20% 완료되었다. 고객이 주요 변경을 포함하는 프로젝트 주문 수정을 수락했으며, 이 변경 없이는 결과가 쓸모없다. 프로젝트 관리자는 어떻게 해야 하는가? | 스폰서가 결정할 때까지 프로젝트 상태를 '활성'에서 '보류'로 업데이트한다. | 변경을 반드시 수용해야 하는지 프로젝트 스폰서와 상담한다. | 수정된 범위로 프로젝트 계획을 시작한다. | 고객 및 프로젝트 팀과 미팅을 설정하여 영향을 파악한다. |  | C | 프로젝트가 20% 완료되었고 고객이 주요 변경을 포함한 주문 수정을 수락했을 때(변경 없이는 결과가 쓸모없음), PM은 프로젝트 스폰서와 상담하여 변경을 반드시 수용해야 하는지 이해해야 한다. 스폰서의 의견을 수렴한 후 적절한 조치를 취하는 것이 중요하다.
1060 | The project manager has initiated the project and the team's roles and responsibilities have been assigned. In preparation for the development of the project management plan, the project manager reviews lessons learned from previous projects and discovers that the same team has been missing delivery dates. What should the project manager do to ensure timely delivery? | Update the issue log. | Ask the team leader to assign other resources. | Include this in the risk register. | Escalate the issue to the functional manager. |  | C | When lessons learned reveal the same team has been missing delivery dates on previous projects, the project manager should include this in the risk register. Documenting the pattern as a risk enables monitoring and proactive response. Updating the issue log (A) treats it as a current issue, not a future risk. Asking the team leader to assign other resources (B) acts without analysis. Escalating to the functional manager (D) is premature without documented risk assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 관리자가 프로젝트를 시작했다. 교훈에서 동일 팀이 이전 프로젝트에서 납기를 놓치고 있었음이 밝혀졌다. 프로젝트 관리자는 어떻게 해야 하는가? | 이슈 로그를 업데이트한다. | 팀 리더에게 다른 자원을 배정하도록 요청한다. | 리스크 레지스터에 포함한다. | 기능 관리자에게 이슈를 에스컬레이션한다. |  | C | 교훈에서 동일 팀이 이전 프로젝트에서 납기를 놓치고 있었음이 밝혀졌을 때, PM은 리스크 레지스터에 포함해야 한다. 패턴을 리스크로 문서화하면 능동적 모니터링과 완화 전략을 수립할 수 있다.
1061 | During the implementation phase of a project, functional managers are adding new requirements, which may impact cost and schedule baselines. The project manager notices that some of the team members are communicating with their managers directly to fulfill their requests. This will lead the project to go beyond the agreed baselines. How should the project manager handle this situation? | Ask the functional managers to communicate with their peers and emphasize the impact of their requirements. | Set up a proper governance structure to ensure functional managers' requests are processed correctly. | Follow the project constraints and move forward with the agreed schedule baseline and the cost baseline. | Modify the communications management plan to enable functional managers to add changes to the project. |  | B | When functional managers add new requirements during implementation and team members fulfill requests directly without change control, the project manager should set up a proper governance structure to ensure requests are processed correctly. Governance prevents uncontrolled scope creep. Asking managers to communicate impacts among themselves (A) lacks authority. Following existing baselines without addressing the behavior (C) ignores the problem. Modifying the communications plan to enable direct changes (D) worsens the situation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | Baseline & Change Control | People | Plan and Manage Communication | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 구현 단계에서 기능 관리자들이 새로운 요구사항을 추가하고 팀원들이 변경 통제 없이 직접 요청을 이행한다. 프로젝트 관리자는 어떻게 해야 하는가? | 기능 관리자에게 동료와 소통하도록 요청한다. | 적절한 거버넌스 구조를 수립하여 기능 관리자가 공식 채널을 통해 소통하도록 한다. | 프로젝트 제약 조건을 따르고 합의된 범위로 진행한다. | 커뮤니케이션 관리 계획을 수정하여 기능 관리자가 프로젝트에 변경을 제출할 수 있도록 한다. |  | B | 기능 관리자들이 구현 중 새 요구사항을 추가하고 팀원들이 변경 통제 없이 직접 이행할 때, PM은 적절한 거버넌스 구조를 수립해야 한다. 이를 통해 기능 관리자가 공식 채널을 통해 소통하고 변경 통제 프로세스를 준수하도록 보장한다.
1062 | A project manager is leading a project that is in the execution phase. During a team meeting, the project manager realizes that there are two team members who lack the technical skills required for some of the upcoming tasks. What should the servant leader project manager do next? | Discuss with the human resource (HR) manager about the possibility of changing teammembers. | Inform the sponsor about a possible delay due to the lack of skills in the team. | Explore a training program that is within the project budget for the team members. | Recommend to the team members to upskill themselves on the requirements for theproject. |  | C | When two team members lack technical skills for upcoming tasks, the servant leader project manager should explore a training program within the project budget. This demonstrates commitment to team development while addressing project needs. Discussing with HR about changing team members (A) is not supportive. Informing the sponsor about possible delay (B) is premature before exploring solutions. Recommending self-upskilling (D) does not provide adequate support. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 실행 단계의 프로젝트를 이끄고 있다. 팀 회의에서 두 명의 팀원이 다가오는 작업에 기술적 능력이 부족함을 알게 되었다. 프로젝트 관리자는 어떻게 해야 하는가? | 인사(HR) 관리자와 교체 가능성을 논의한다. | 기술 부족으로 인한 지연 가능성을 스폰서에게 알린다. | 프로젝트 예산 내의 교육 프로그램을 탐색한다. | 팀원들에게 필요한 기술을 스스로 업스킬하도록 권고한다. |  | C | 두 팀원이 다가오는 작업에 기술적 능력이 부족할 때, 서번트 리더 PM은 프로젝트 예산 내의 교육 프로그램을 탐색해야 한다. 이는 팀 개발과 역량 강화에 대한 헌신을 보여준다.
1063 | A new systems project requires feedback from the accounting manager at the beginning of solution discussions and before meeting with other functional managers. The project manager knows the accounting manager will not be available until a few days before the deadline for the solution document. What should the project manager do to avoid a delay in the project? | Wait for the accounting manager to be available while identifying subsequent tasks that 1073 can be compressed, | Begin discussions with other functional managers and meet with the accounting manager later. | Ask the accounting manager to delegate a team member who can support the project. | Request that the sponsor direct the accounting manager ' s supervisor to provide a replacement resource, |  | B | When the accounting manager needed first for solution discussions is unavailable until near the deadline, the project manager should begin discussions with other functional managers and meet with the accounting manager later. Maintaining project momentum prevents delays. Waiting while compressing other tasks (A) accepts delay. Asking for delegation (C) may not ensure the right expertise. Requesting sponsor intervention (D) escalates unnecessarily. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 새로운 시스템 프로젝트에서 초기에 회계 관리자의 피드백이 필요하다. 그러나 회계 관리자가 마감일 근처까지 부재중이다. 프로젝트 관리자는 어떻게 해야 하는가? | 회계 관리자가 가용할 때까지 기다리며 리스크를 식별한다. | 다른 기능 관리자와 논의를 시작하고 회계 관리자가 가용하면 만난다. | 회계 관리자에게 대리인을 지명하도록 요청한다. | 스폰서에게 회계 관리자의 지원을 지시하도록 요청한다. |  | B | 초기에 필요한 회계 관리자가 마감일 근처까지 부재중일 때, PM은 다른 기능 관리자와 논의를 시작하고 회계 관리자가 가용하면 만나야 한다. 이는 진행을 유지하면서 모든 필요한 입력을 수집한다.
1064 | A project team is completing a design, while another team in a different country is performing implementation. How should the project manager communicate the design to the implementation team? | Upload the design documents into the project repository. | Send a detailed email with the completed design document. | Conduct a workshop with all of the stakeholders. | Conduct a workshop with both of the teams. |  | D | When a design team in one country needs to communicate completed designs to an implementation team in another country, the project manager should conduct a workshop with both teams. Interactive workshops enable two-way communication, immediate feedback, and shared understanding across geographic boundaries. Uploading documents to a repository (A) is passive. Sending a detailed email (B) lacks interaction. Conducting a workshop with all stakeholders (C) is broader than needed for this specific handoff. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 팀이 설계를 완료하고 있으며, 다른 나라의 팀이 설계를 기반으로 구현할 예정이다. 프로젝트 관리자는 어떻게 해야 하는가? | 설계 문서를 프로젝트 리포지토리에 업로드한다. | 완성된 설계 문서와 함께 상세 이메일을 보난다. | 모든 이해관계자와 워크샵을 진행한다. | 두 팀과 함께 워크샵을 진행한다. |  | D | 한 나라의 설계 팀이 완성된 설계를 다른 나라의 구현 팀에 전달해야 할 때, PM은 두 팀과 워크샵을 진행해야 한다. 대화형 워크샵은 질문, 설명, 실시간 피드백을 가능하게 하여 정확한 지식 전달을 보장한다.
1065 | The customer is reviewing the new reporting system and informs the project manager that one of the components in the printing module is not complete. The project manager reviews the work breakdown structure (WBS) and confirms that the component is included. What does the project manager need to do first? | Raise a change request to immediately implement the printing module component. | Escalate this issue to the project sponsor immediately | Ask the project team to conduct a quality audit of the printing module components. | Meet with the project team to understand the issue and define actions. |  | D | When the customer reports an incomplete printing module component that is confirmed in the WBS, the project manager should first meet with the project team to understand the issue and define actions. Root cause analysis identifies why the component is incomplete and determines the best corrective action. Raising a change request immediately (A) is premature without understanding the issue. Escalating to the sponsor (B) bypasses team-level problem-solving. Conducting a quality audit (C) is broader than needed for a specific component issue. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | WBS/Decomposition | Process | Plan and Optimize Quality | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 고객이 새 보고 시스템을 검토하던 중 인쇄 모듈 구성 요소가 불완전하다고 PM에게 알렸다. WBS에서 확인되었다. 프로젝트 관리자는 어떻게 해야 하는가? | 인쇄 기능을 즉시 구현하기 위해 변경 요청을 제기한다. | 이 이슈를 프로젝트 스폰서에게 즉시 에스컬레이션한다. | 프로젝트 팀에게 인쇄 기능의 품질 감사를 수행하도록 요청한다. | 프로젝트 팀과 미팅하여 이슈를 이해하고 조치를 정의한다. |  | D | 고객이 WBS에서 확인된 불완전한 인쇄 모듈 구성 요소를 보고할 때, PM은 먼저 프로젝트 팀과 미팅하여 이슈를 이해하고 조치를 정의해야 한다. 영향을 이해한 후 적절한 대응을 결정하는 것이 중요하다.
1066 | A project manager is working with the same project team as in the last two construction projects. The project manager managed this team on a micro level for the last two projects. However, now the project manager would like to use a different leadership style to allow the team to make their own decisions. What kind of leadership style should the project manager utilize for the current project? | Interactional | Transformational | Laissez-faire | Charismatic |  | C | When a project manager who previously micromanaged wants to allow the team to make their own decisions, they should adopt a laissez-faire leadership style. Laissez-faire gives the team autonomy and decision-making authority. Interactional (A) focuses on exchanges. Transformational (B) inspires change but maintains leader involvement. Charismatic (D) relies on personality, not delegation. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 이전 두 건설 프로젝트와 동일한 팀과 작업하고 있다. 이전에는 마이크로매니징을 했으나 이번에는 팀이 스스로 결정하도록 하고 싶다. 어떤 리더십 스타일이 필요한가? | 상호작용형(Interactional) | 변혁적(Transformational) | 방임형(Laissez-faire) | 카리스마형(Charismatic) |  | C | 이전에 마이크로매니징했던 PM이 팀이 스스로 결정하도록 하려면 방임형(Laissez-faire) 리더십을 채택해야 한다. 방임형은 팀에게 자율성과 의사결정 권한을 부여하여 최소한의 간섭으로 운영하게 한다.
1067 | During the last sprint review, the main stakeholder complained that the product was missing many features they had been expecting. The project team argued that every increment met the acceptance criteria and was approved by the main stakeholder. The cost performance index (CPI) of the project is 1.15 and the schedule performance index (SPI) is 1.43. What should the project manager do? | Explain to the stakeholder that since the acceptance criteria for every increment were met the project can be closed. | Ask the project team to perform the modifications since the project budget and schedule can support them. | Analyze the reason for the gap in understanding with both sides and negotiate a solution | Ask the stakeholder to submit a change request to increase the budget and time for the modifications requested |  | C | When the main stakeholder complains about missing features despite all increments meeting acceptance criteria and being approved, with CPI of 1.15 and SPI of 1.43, the project manager should analyze the reason for the gap in understanding with both sides and negotiate a solution. The disconnect between approval and satisfaction suggests miscommunication or unclear requirements that need root cause analysis. Explaining that the project can be closed since criteria were met (A) ignores the stakeholder's dissatisfaction. Asking the team to perform modifications (B) may not address the underlying issue. Asking for a change request (D) is procedural without first understanding the gap. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 마지막 스프린트 리뷰에서 주요 이해관계자가 제품에 예상했던 기능이 누락되었다고 불만을 표했다. 모든 증분이 인수 기준을 충족했고 이해관계자가 승인했다. CPI=1.15, SPI=1.43이다. PM은 어떻게 해야 하는가? | 이해관계자에게 인수 기준이 충족되었고 모든 증분이 승인되었으므로 차이를 좁힐 필요가 없다고 설명한다. | 이해관계자가 고객이므로 프로젝트 팀에게 수정을 수행하도록 요청한다. | 양측과 함께 이해 차이의 원인을 분석하고 백로그에 필요한 기능을 추가한다. | 이해관계자에게 프로젝트 범위를 늘리기 위한 변경 요청을 제출하도록 요청한다. |  | C | 주요 이해관계자가 인수 기준을 충족하고 승인된 증분에도 불구하고 누락된 기능에 대해 불만을 제기할 때, PM은 양측과 함께 이해 차이의 원인을 분석해야 한다. 이는 근본 원인을 파악하고 향후 오해를 방지한다.
1068 | A project for a financial organization is in the proposal phase for the selection of a software tool. There have been conflicting opinions on the software that was ranked in the selection. After analyzing the issue, the project manager realizes that two out of the eight teams have concerns about the tool's scalability to support their business needs. How should the project manager resolve this conflict and reach a consensus? | Escalate this to senior management and ensure that the team ' s acceptance is achieved. | Communicate to the two teams that the tool has won per the selection process and they need to accept the outcome. | Discuss the outcome of the proposal process and the ranking, then influence the team for acceptance. | Ignore the conflict as the tool is selected per the proposal guidelines and the project is complete. |  | C | When two of eight teams have concerns about a selected software tool's scalability in a financial organization, the project manager should discuss the outcome of the proposal process and ranking, then influence the teams toward acceptance. Transparent rationale and data-driven influence build consensus. Escalating to senior management (A) is premature. Communicating they must accept (B) is authoritarian. Ignoring the conflict (D) neglects stakeholder engagement. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 금융 기관의 소프트웨어 도구 선정 제안 단계에서 8개 팀 중 2개 팀이 선정된 도구의 확장성에 우려를 표명한다. PM은 어떻게 해야 하는가? | 고위 경영진에게 에스컬레이션하여 팀이 결정을 따르도록 한다. | 두 팀에게 도구가 선정 기준에 따라 선정되었다고 알린다. | 제안 프로세스의 결과와 순위를 논의하고, 두 팀에게 확장성 테스트를 진행시킨다. | 도구가 선정 기준에 따라 선정되었으므로 갈등을 무시한다. |  | C | 8개 팀 중 2개 팀이 선정된 소프트웨어 도구의 확장성에 우려를 표명할 때, PM은 제안 프로세스의 결과와 순위를 논의하고 확장성 테스트를 진행하도록 해야 한다. 투명한 소통과 검증을 통해 우려를 해소한다.
1069 | A project manager is assigned to a research project. The project team has been selected and has worked together on other projects. Based on the project documentation, team members seem to be working at their own pace and have had little interaction with the project manager. What should the project manager do to have a high-performing team? | Invite team members to an informal meeting to get to know one another. | Encourage the team to define the ground rules for performance. | Set up individual calls to follow up on each team member ' s progress. | Set up regular project status meetings and invite all team members. |  | B | The PM should encourage the team to define their own performance ground rules collaboratively. This empowers the team to take ownership of their work practices and ensures alignment with project objectives, reflecting effective resource management principles. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 연구 프로젝트에 배정된 PM이다. 팀은 그룹으로서 함께 일한 적이 없으며 프로젝트는 다양한 시간대에 걸쳐 가상으로 운영된다. PM이 먼저 해야 할 일은? | 비공식 미팅에 팀원들을 초대하여 서로 알아가게 한다. | 팀이 성과를 위한 기본 규칙을 정의하도록 장려한다. | 각 팀원의 역할과 책임을 후속 확인하기 위한 개별 통화를 설정한다. | 정기 프로젝트 상태 회의를 설정하고 모든 팀원을 초대한다. |  | B | 함께 일한 적 없는 가상 팀의 경우, PM은 팀이 성과를 위한 기본 규칙을 직접 정의하도록 장려해야 한다. 이는 팀에게 작업 관행의 주인의식을 부여하고 프로젝트 목표와의 정렬을 보장한다.
1070 | A project manager who recently joined the company has been assigned to manage a software project for a major recurring customer. What should the project manager do to enhance the budget estimations for the project? | Review budget-related lessons learned from similar projects. | Implement an agile approach to avoid using a fixed budget, | Invite the client to the kick-off meeting and create the project budget during the meeting, | Discuss the budget with the team during the daily standups to ensure the budget is under control. |  | A | When a new project manager is assigned to a software project for a recurring customer, they should review budget-related lessons learned from similar projects to enhance budget estimations. Historical data and past experiences inform realistic budget planning and help avoid previous pitfalls. Implementing agile to avoid fixed budgets (B) changes methodology rather than improving estimation. Inviting the client to create the budget at a kick-off (C) is impractical. Discussing budget during daily standups (D) is not the appropriate forum for budget estimation. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 최근 입사한 PM이 반복 고객의 소프트웨어 프로젝트를 관리하게 되었다. 예산 초과 이력이 있다. PM이 먼저 해야 할 일은? | 유사 프로젝트의 예산 관련 교훈을 검토한다. | 고정 예산 사용을 피하기 위해 애자일 접근법을 구현한다. | 고객을 킥오프 미팅에 초대하고 함께 프로젝트 예산을 만든다. | 일일 스탠드업에서 팀과 예산을 논의하여 준수를 보장한다. |  | A | 반복 고객의 예산 초과 이력이 있는 프로젝트를 맡았을 때, PM은 유사 프로젝트의 예산 관련 교훈을 검토해야 한다. 과거 데이터는 예산 추정을 향상시키고 반복적인 실수를 방지한다.
1071 | A project manager is leading a highly visible project initiative. A few weeks after the kickoff, the project manager starts to receive requests for updates from various stakeholders. What should the project manager do? | Explain to the stakeholders that they must request project updates from the project sponsor. | Remove those stakeholders from the project since they may negatively affect the goals of the project. | Invite all project stakeholders to join the daily standup meeting to ensure they are informed. | Schedule a meeting with relevant stakeholders to review the project communications plan. |  | D | When multiple stakeholders request project updates shortly after kickoff, it signals that the current communication approach does not meet their information needs. The project manager should schedule a meeting with relevant stakeholders to review the project communications plan, clarifying update frequency, format, reporting channels, and expectations. Directing stakeholders to request updates from the sponsor (A) is dismissive and weakens engagement. Removing requesting stakeholders from the project (B) is inappropriate. Inviting all stakeholders to daily standups (C) misuses the standup format, which is for team synchronization, not stakeholder reporting. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Hybrid/Tailoring | 높은 가시성의 프로젝트를 이끌고 있다. 킥오프 후 몇 주 만에 여러 이해관계자가 프로젝트 업데이트를 요청한다. PM은 어떻게 해야 하는가? | 이해관계자에게 공식 채널을 통해 업데이트를 요청해야 한다고 설명한다. | 프로젝트에 부정적 영향을 줄 수 있으므로 해당 이해관계자를 제거한다. | 모든 이해관계자를 일일 스탠드업에 참여하도록 초대한다. | 관련 이해관계자와 미팅을 예약하여 커뮤니케이션 관리 계획을 검토한다. |  | D | 킥오프 직후 여러 이해관계자가 업데이트를 요청할 때, 현재 커뮤니케이션 접근 방식이 정보 요구를 충족하지 못한다는 신호이다. PM은 관련 이해관계자와 미팅을 예약하여 커뮤니케이션 관리 계획을 검토해야 한다.
1072 | A client wants to create an innovative software for the travel industry using an agile approach. A project manager from the company was assigned to work on the details and estimates as requested by the client. What should the project manager do before sending the information to the client? | Sequence the tasks with estimates and add standard risk reserves to use for software development. | Put the tasks with estimates in the backlog and clarify that the project will not need any reserves. | Analyze the tasks, provide estimates, include a prototype demo, and send to the client directly. | Work with the team to understand their views and add the appropriate dependencies and risks. |  | D | Before sending project details and estimates to the client for an innovative agile software project, the project manager should work with the team to understand their views and add the appropriate dependencies and risks. Team collaboration ensures realistic estimates and identifies technical challenges early. Sequencing tasks with standard risk reserves (A) follows a predictive approach. Putting tasks in the backlog without reserves (B) ignores risk. Analyzing tasks and sending directly to the client (C) bypasses team input. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 고객이 애자일 접근법을 사용한 여행 산업용 혁신 소프트웨어를 원한다. 프로젝트 상세 및 견적을 보내기 전에 PM이 먼저 해야 할 일은? | 작업 순서를 정하고 견적에 표준 리스크 준비금을 추가한다. | 작업과 견적을 백로그에 넣고 예상되는 조정을 명확히 한다. | 작업을 분석하고 견적을 제공하며 프로토타입 전달을 포함한다. | 팀과 협력하여 의견을 이해하고 적절한 의존성 수준을 추가한다. |  | D | 혁신적인 애자일 소프트웨어 프로젝트의 상세 및 견적을 고객에게 보내기 전에, PM은 팀과 협력하여 의견을 이해하고 적절한 의존성 수준을 추가해야 한다. 팀 입력은 정확하고 현실적인 견적을 보장한다.
1073 | As part of a temporary assignment, a project manager is leading a business project. During a daily status meeting, it is discovered that the project manager's former department has not completed a task. This is delaying the current iteration. What should the project manager do? | Invite the project team to a swarming session to define a solution | Leverage the network of the former department and ask for help | Escalate the issue to the product owner to define the next steps | Create an entry in the impediment board and assign it. |  | D | When a task from the project manager's former department is delaying the current iteration, the project manager should create an entry in the impediment board and assign it. Visual tracking ensures transparency and accountability. Inviting the team to swarm (A) is for team-level problems. Leveraging the former department network (B) is informal. Escalating to the product owner (C) is not the PO's responsibility. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 임시 배정의 일환으로 비즈니스 프로젝트를 이끌고 있다. 이전 부서의 작업이 현재 반복을 지연시키고 있다. PM은 어떻게 해야 하는가? | 팀을 스워밍 세션에 초대하여 솔루션을 정의한다. | 이전 부서의 네트워크를 활용하여 도움을 요청한다. | 제품 소유자에게 이슈를 에스컬레이션하여 다음 단계를 정의한다. | 장애물 보드에 항목을 생성하고 할당한다. |  | D | 이전 부서의 작업이 현재 반복을 지연시킬 때, PM은 장애물 보드에 항목을 생성하고 할당해야 한다. 시각적 추적은 투명성을 보장하고 장애물의 공식적 추적을 가능하게 한다.
1074 | A project team has transitioned to full-time remote working. The project manager started noticing that some team members have not been completing their assigned tasks by the planned dates despite reminders during weekly team meetings. This has the potential for delaying the project delivery. How should the project manager resolve this situation? | Talk to the resource managers regarding the delay and request additional resources | Mentor the team members to work in a remote work environment to ensureproductivity. | Set up review sessions with each of the team members to identify the root cause ofdelays. | Communicate the delivery dates twice a week to the team members to ensure timelydelivery. |  | C | The PM should conduct root cause analysis to understand why remote team members are missing deadlines. This data-driven approach identifies specific underlying factors—whether technical obstacles, communication gaps, workload issues, or personal challenges—enabling targeted corrective actions such as coaching, training, or process adjustments. Simply communicating deadlines more frequently (A) doesn't address root causes. Mentoring for remote work (C) may help but isn't targeted. Requesting additional resources (D) adds cost and complexity without solving the underlying problem. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 팀이 완전 원격 근무로 전환했다. PM이 일부 팀원들이 납기를 놓치고 있음을 발견했다. PM은 어떻게 해야 하는가? | 자원 관리자에게 지연에 대해 논의하고 추가 지원을 요청한다. | 팀원들을 원격 근무 환경에서 일하도록 멘토링한다. | 각 팀원과 리뷰 세션을 설정하여 지연의 근본 원인을 파악한다. | 팀원들에게 주 2회 납기일을 전달한다. |  | C | 원격 근무 전환 후 팀원들이 납기를 놓칠 때, PM은 각 팀원과 리뷰 세션을 설정하여 근본 원인을 파악해야 한다. 데이터 기반 접근은 기술적 장애물, 커뮤니케이션 문제, 업무량 등 구체적인 원인을 식별한다.
1075 | A new project manager has been hired at a company that has suffered many project failures. The project manager has been tasked with delivering a software product for the company's biggest customer. The customer has not been able to articulate how a major piece of functionality should work. The project manager wants to deliver value immediately. How should the project manager approach the software development life cycle with this customer? | Assign a business analyst to build a detailed set of requirements with the customer so the project manager can properly estimate the project duration. | Explain to the customer that the team will build a production prototyping model to help the customer visualize how the additional features should work. | Raise a risk that the scoping and estimating phase of the project will be delayed if the customer cannot deliver an approved set of requirements. | Add extra time to the estimating phase of the project as well as additional resources to accommodate the lack of requirements. |  | B | When the customer cannot articulate how major functionality should work and the PM wants to deliver value immediately, the project manager should explain that the team will build a production prototyping model to help the customer visualize the features. Prototyping clarifies requirements through feedback. Assigning a BA for detailed requirements (A) assumes requirements can be elicited traditionally. Raising a risk about delays (C) documents without solving. Adding time and resources (D) increases cost without improving understanding. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | 새 PM이 많은 프로젝트 실패를 겪은 회사에 채용되었다. 고객이 주요 기능의 작동 방식을 명확히 할 수 없다. PM이 즉시 가치를 전달하려면 어떻게 해야 하는가? | 비즈니스 분석가를 배정하여 상세한 요구사항 세트를 구축한다. | 고객에게 팀이 프로덕션 프로토타입을 구축하여 피드백을 받을 것이라고 설명한다. | 스코핑 및 추정 단계가 지연될 수 있다는 리스크를 제기한다. | 추정 단계에 추가 시간과 비상 예비비를 추가한다. |  | B | 고객이 주요 기능의 작동 방식을 명확히 할 수 없고 PM이 즉시 가치를 전달하려 할 때, 팀이 프로덕션 프로토타입을 구축하여 피드백을 받을 것이라고 설명해야 한다. 프로토타입은 조기 피드백과 반복적 개선을 가능하게 한다.
1076 | Eight highly qualified experts have been assembled to work for a 6-month period on a specific aspect of an organization's product development process. How should the project manager support this team to succeed? | Bring in a senior colleague who is also an expert to ensure the team is on track to achieve the goals and objectives. | Hand over control of specific aspects of their roles as experts and let them agree on their own timelines and targets. | Define roles and targets for all team members and regularly follow up with one-to-one meetings to review progress. | Work with the team members to define the overall objective and support them to engage around the goal. |  | D | When eight highly qualified experts are assembled for a six-month specialized assignment, the project manager should work with the team to define the overall objective and support them to engage around the goal. Collaborative goal-setting leverages expertise and fosters ownership. Bringing in a senior colleague to oversee (A) undermines the experts' autonomy. Handing over control entirely (B) provides no PM support. Defining roles, targets, and regular one-on-ones (C) is micromanagement for a team of experts. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 8명의 고도로 자격을 갖춘 전문가가 6개월간 전문 과제를 수행하기 위해 구성되었다. PM이 이 팀을 관리하는 가장 좋은 방법은? | 고급 동료를 데려와 일이 제대로 수행되도록 한다. | 전문가로서의 역할의 특정 측면에 대한 통제를 인계한다. | 모든 팀원의 역할과 목표를 정의하고 정기적으로 모니터링한다. | 팀과 함께 전반적인 목표를 정의하고 목표 달성을 위해 지원한다. |  | D | 8명의 고도로 자격을 갖춘 전문가가 6개월간 특수 과제를 수행할 때, PM은 팀과 함께 전반적인 목표를 정의하고 목표 달성을 위해 지원해야 한다. 이는 자율성과 공유 목적 의식을 바탕으로 한 협업을 촉진한다.
1077 | A few developers have identified a list of impediments at the daily standup and are asking for the project lead's assistance in prioritizing them. There are a few complex backlog items, and a new junior tester has identified a few compliance defects. The product owner and a couple of developers will be leaving the project team, and the contract with the test and production support partner will not be renewed. Which issue should the project lead focus on first? | Regulatory compliance issues discussed in the meeting. | Developing a new contract for production support. | Recruiting, onboarding, and training new developers. | Finding a new product owner to prioritize the product backlog. |  | A | When multiple impediments surface at the daily standup — complex backlog items, compliance defects from a junior tester, departing team members, and expiring contracts — the project lead should focus first on regulatory compliance issues. Compliance has legal and financial implications. Developing a new contract (B) is procurement. Recruiting and onboarding (C) addresses resourcing. Finding a new PO (D) is also important but secondary to compliance. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 일일 스탠드업에서 여러 개발자가 장애물 목록을 식별했다. 복잡한 백로그 항목, 주니어 테스터의 컴플라이언스 결함, 팀원 퇴직, 계약 만료 등이 있다. 프로젝트 리더가 먼저 집중해야 할 장애물은? | 회의에서 논의된 규제 컴플라이언스 이슈 | 프로덕션 지원을 위한 새 계약 개발 | 새 개발자 채용, 온보딩, 교육 | 제품 백로그를 우선순위화할 새 제품 소유자 찾기 |  | A | 여러 장애물이 발생했을 때(복잡한 백로그 항목, 컴플라이언스 결함, 팀원 퇴직, 계약 만료), 프로젝트 리더는 규제 컴플라이언스 이슈에 먼저 집중해야 한다. 컴플라이언스 위반은 법적/재정적 결과를 초래하며 가장 높은 우선순위를 가진다.
1078 | A consultancy firm is finally selected and contracted for a project following an extensive and competitive procurement process. A few months into project execution, the client asks the project manager why the consultant is contracted for only 18 months instead of the full 32-month-long project. The project manager will need to carry out an unplanned second bidding process to ensure services are in place until the end of the project. What should the project manager have done to prevent this? | Prepared and negotiated a second contract with the consultancy firm for the remaining 14 months after the first contract signature. | Included the client in all negotiation phases with the consultancy to obtain their advanced approval before signing the contract. 1195 | Developed a detailed, phased procurement management plan including all activities required and had the client approve it. | Agreed beforehand with the client on the frequency of reporting on the status of the procurement activities within the project. |  | C | When a consultant was contracted for only 18 months of a 32-month project, requiring an unplanned second bidding process, the project manager should have developed a detailed, phased procurement management plan including all required activities and had the client approve it. Comprehensive procurement planning prevents gaps. Preparing a second contract after the first (A) is reactive. Including the client in negotiations (B) adds oversight but does not prevent the gap. Agreeing on procurement reporting frequency (D) is monitoring, not planning. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 입찰 후 컨설팅 회사가 선정되어 계약되었다. 32개월 프로젝트에서 컨설턴트 계약이 18개월만 적용되어 계획에 없던 2차 입찰이 필요했다. PM이 다르게 했어야 할 점은? | 컨설턴트와 2차 계약을 준비하고 협상했어야 한다. | 모든 협상 단계에 고객을 포함시켰어야 한다. | 조달 전략을 포함한 상세한 단계별 조달 관리 계획을 개발했어야 한다. | 고객과 보고 빈도를 사전에 합의했어야 한다. |  | C | 32개월 프로젝트에서 컨설턴트가 18개월만 계약되어 계획에 없던 2차 입찰이 필요했을 때, PM은 조달 전략을 포함한 상세한 단계별 조달 관리 계획을 개발했어야 한다. 적절한 조달 계획은 계약 갱신을 예측하고 중단을 방지한다.
1079 | A new project team has formed and the project manager notices that some of the team members do not feel comfortable being part of the project team. As a result, members of the team are working individually and not as a team. What should the project manager do to resolve this? | Directly guide the team members on how to perform their tasks | Facilitate a team-building meeting to help this issue | Allow the team members to remain in their former individual roles | Wait until some iterations are completed to intervene |  | B | When new team members feel uncomfortable and work individually rather than as a team, the project manager should facilitate a team-building meeting. Team building fosters trust, open communication, and a sense of belonging—encouraging collaboration. Directly guiding task performance (A) is micromanagement. Allowing individual roles to continue (C) accepts the dysfunction. Waiting until iterations are completed (D) delays necessary intervention. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 프로젝트 팀이 구성되었고 PM이 일부 팀원들이 이전 개인 업무 스타일에 머물러 있음을 발견했다. PM은 어떻게 해야 하는가? | 팀원들에게 업무 수행 방법을 직접 안내한다. | 팀 빌딩 미팅을 진행하여 이 문제를 해결한다. | 팀원들이 이전 개인 업무 스타일을 유지하도록 허용한다. | 몇 차례 반복이 완료될 때까지 개입을 기다린다. |  | B | 새 팀원들이 불편해하며 팀이 아닌 개인으로 일할 때, PM은 팀 빌딩 미팅을 진행해야 한다. 팀 빌딩은 신뢰, 개방적 커뮤니케이션, 협력을 촉진하여 팀 응집력을 구축한다.
1080 | There are several dependent work streams in a project. Some of the project stakeholders feel that coordination among project team members and progress visibility are lacking. What should the project manager do? | Discuss the concerns with the project sponsor. | Escalate the concerns to the project steering committee. | Organize a team meeting to review the project status. | Review and update the communications management plan. |  | D | When stakeholders report poor coordination and limited progress visibility across dependent work streams, the project manager should review and update the communications management plan. Structural improvements to communication governance address the root cause systematically. Discussing with the sponsor (A) escalates prematurely. Escalating to the steering committee (B) is unnecessary as a first step. Organizing a team meeting (C) is a one-time tactic, not a systemic fix. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Integrate Sustainability | Manage Communications | Sustainability | 프로젝트에 여러 종속적 작업 스트림이 있다. 일부 이해관계자가 조정 부족과 제한된 진행 가시성을 보고한다. PM은 어떻게 해야 하는가? | 프로젝트 스폰서와 우려사항을 논의한다. | 프로젝트 운영 위원회에 우려사항을 에스컬레이션한다. | 팀 미팅을 조직하여 프로젝트 상태를 검토한다. | 커뮤니케이션 관리 계획을 검토하고 업데이트한다. |  | D | 이해관계자가 종속적 작업 스트림 간 조정 부족과 제한된 진행 가시성을 보고할 때, PM은 커뮤니케이션 관리 계획을 검토하고 업데이트해야 한다. 구조적 커뮤니케이션 개선이 조정 및 가시성 문제의 근본 원인을 해결한다.
1081 | A project team's performance has declined for the last three iterations. Some of the team members are disappointed and raise their concerns during the retrospective meeting. What should the project manager do? | Compare the team ' s performance against other project teams | Motivate the team to perform better | Identify potential failure points based on the iteration workload | Focus on remediation not merely on correcting symptoms |  | D | When a team's performance has declined for three iterations and members raise concerns in the retrospective, the project manager should identify potential failure points based on the iteration workload. Root cause identification through workload analysis enables targeted improvement. Comparing against other teams (A) is not actionable. Motivating the team (B) does not address specific issues. Focusing on remediation (C) requires identifying failure points first. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀의 성과가 지난 3회 반복에서 하락했다. 일부 팀원이 회고에서 우려를 제기한다. PM은 어떻게 해야 하는가? | 다른 프로젝트 팀과 성과를 비교한다. | 팀을 동기부여하여 더 나은 성과를 내도록 한다. | 반복 작업량을 기반으로 잠재적 실패 지점을 식별한다. | 증상만 수정하는 것이 아니라 근본 원인 해결에 집중한다. |  | D | 팀의 성과가 3회 반복에서 하락하고 팀원들이 회고에서 우려를 제기할 때, PM은 반복 작업량을 기반으로 잠재적 실패 지점을 식별해야 한다. 근본 원인 해결에 집중하면 증상만 수정하는 것이 아닌 지속적인 개선이 가능하다.
1082 | A project manager for a large multiyear industrial project has a project with diversified stakeholders from various geographical areas. Recently, the project manager encountered an issue with stakeholder engagement. Which two tools should the project manager use to determine the underlying reason for why engagement is not having the planned effect? (Choose two) | Issue log | Communications management plan | Ishikawa diagrams | Five whys | Open-space meetings | D, E | To understand the root cause of decreasing stakeholder engagement, the project manager should use two tools: five whys (D) to systematically drill down through layers of causation until the fundamental issue is identified, and open-space meetings (E) to create an inclusive forum where stakeholders can freely express their concerns and ideas. Five whys is a structured root cause analysis technique, while open-space meetings encourage open dialogue and surface hidden issues. The issue log (A) records issues but does not analyze their causes. The communications management plan (B) describes communication methods but does not diagnose engagement root causes. Ishikawa diagrams (C) are useful for manufacturing or process issues but are less suited to stakeholder engagement analysis. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Traditional PM | 대규모 다년간 산업 프로젝트의 PM이 이해관계자 참여 감소의 근본 원인을 이해하기 위해 사용해야 할 두 가지 도구는? | 이슈 로그 | 커뮤니케이션 관리 계획 | 이시카와 다이어그램 | 5 Why | 오픈스페이스 미팅 | D, E | 이해관계자 참여 감소의 근본 원인을 이해하기 위해 PM은 두 가지 도구를 사용해야 한다: 5 Why(D)를 통해 원인의 계층을 체계적으로 탐색하고, 오픈스페이스 미팅(E)을 통해 이해관계자가 우려와 아이디어를 자유롭게 표현할 수 있는 포럼을 만든다.
1083 | A project team member is struggling to understand a specific requirement. How should a servant leader address this issue? | Assist by connecting the product owner with the team member to discuss what problem is to be solved | Reassign the requirement to another team member who may have ideas on how to meet the requirement | Deprioritize the requirement and assign a task tor it to be restated to provide the necessary clarity | Assess and evaluate the team member ' s skills to ensure alignment to the particular requirement and solution |  | A | When a team member struggles to understand a specific requirement, a servant leader should assist by connecting the product owner with the team member to discuss the problem. Facilitating direct communication with the requirement source addresses the root cause. Reassigning the requirement (B) avoids the issue. Deprioritizing it (C) delays resolution. Assessing the team member's skills (D) questions competence rather than clarifying the requirement. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트 팀원이 특정 요구사항을 이해하는 데 어려움을 겠고 있다. 서번트 리더로서 PM은 어떻게 해야 하는가? | 제품 소유자와 팀원을 연결하여 문제를 논의하도록 돕는다. | 더 나은 이해력을 가진 다른 팀원에게 요구사항을 재배정한다. | 요구사항의 우선순위를 낮추고 후속 조치 작업을 할당한다. | 팀원의 역량을 평가하여 정렬을 보장한다. |  | A | 팀원이 특정 요구사항을 이해하는 데 어려움을 겠을 때, 서번트 리더 PM은 제품 소유자와 팀원을 연결하여 문제를 논의하도록 돕는다. 직접적인 커뮤니케이션 촉진은 이해를 가속화하고 제품 소유자의 의도가 정확히 전달되도록 한다.
1084 | A project manager is working with a colocated agile project team that has worked together long enough to be in the performing phase of team development. An unforeseen event has caused the team to be dispersed and they are now unable to colocate. What should the project manager do to keep the team performing as effectively as possible? | Evaluate project performance and step in if performance decreases to. an unacceptable level, | Transition the team from an agile approach to a predictive approach for better performance cantral. | Ask the project sponsor and executive stakeholders to encourage the team to maintain their performance, | Provide the team with virtual collaboration software and training on the software to minimize disruption, |  | D | When a performing agile team is suddenly dispersed and unable to colocate due to an unforeseen event, the project manager should provide the team with virtual collaboration software and training to minimize disruption. Technology enablement preserves team dynamics and communication patterns. Evaluating performance and stepping in if needed (A) is reactive. Transitioning to predictive approach (B) disrupts established team practices. Asking stakeholders to encourage the team (C) does not provide practical support. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 함께 일해온 코로케이티드 애자일 팀이 예상치 못한 사건으로 분산되어 코로케이티드할 수 없게 되었다. PM은 어떻게 해야 하는가? | 프로젝트 성과를 평가하고 성과가 떨어지면 개입한다. | 애자일 접근법에서 예측적 접근법으로 전환한다. | 프로젝트 스폰서와 경영진 이해관계자에게 팀을 격려하도록 요청한다. | 팀에게 가상 협업 소프트웨어와 교육을 제공한다. |  | D | 성과를 내던 애자일 팀이 예상치 못한 사건으로 분산되어 코로케이티드할 수 없을 때, PM은 가상 협업 소프트웨어와 교육을 제공해야 한다. 이는 원격 환경에서도 팀의 협업 역량을 유지한다.
1085 | An agile team is struggling to successfully deliver what they have committed. During the daily status meetings, the project manager notices that the most senior engineer is doing all of the talking, leaving little time for the other members to share their status. The team's performance is not good, and some team members want to leave the team. How should the project manager approach this situation? | Rotate the team ' s daily meeting roles frequently. | Reschedule the team ' s retrospective meeting. | Coach the team to be more inclusive. | Measure the team ' s psychological safety. |  | C | When one team member dominates and others feel excluded, the PM should coach the team on inclusive behavior and reinforce agile values such as shared responsibility and open communication. Coaching is the primary tool for correcting team dynamics and fostering psychological safety. Observation alone (A) isn't action-oriented. Reassigning work (B) doesn't address the root behavioral issue. Restructuring (D) may help but doesn't correct the underlying dynamic. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Align Stakeholder Expectations | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 팀이 커밋한 작업을 성공적으로 전달하는 데 어려움을 겠고 있다. 일일 스탠드업에서 한 팀원이 지배적이고 다른 팀원들은 배제된다고 느낌. PM은 어떻게 해야 하는가? | 팀의 일일 회의 역할을 자주 로테이션한다. | 팀의 회고 회의를 재일정한다. | 팀을 더 포용적으로 코칭한다. | 팀의 심리적 안전을 측정한다. |  | C | 한 팀원이 지배적이고 다른 팀원들이 배제된다고 느낄 때, PM은 팀을 포용적 행동에 대해 코칭해야 한다. 코칭은 공유 책임과 개방적 커뮤니케이션 같은 애자일 가치를 강화한다.
1086 | A project steering committee meeting was arranged to approve a milestone of a project within two weeks. The project manager is informed that a new project executive will take over the project. What should the project manager do first? | Brief the new stakeholders on the current project status. | Assess the risks with the team members. | Evaluate the project impact and seek additional funding if necessary. | Submit a change request to the change control board (CCB). |  | A | The correct answer is A. Brief the new stakeholders on the current project status. This approach best addresses the situation described by following project management best practices. The other options either fail to address the root cause, bypass proper processes, or may create additional problems. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Schedule Management | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 운영 위원회 회의가 2주 이내에 프로젝트 마일스톤을 승인하기 위해 예정되었다. 프로젝트 관리자는 새로운 프로젝트 임원이 프로젝트를 인수할 것이라는 통보를 받았다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 새로운 이해관계자에게 현재 프로젝트 상태를 브리핑한다. | B. 팀원들과 리스크를 평가한다. | C. 프로젝트 영향을 평가하고 필요 시 추가 자금을 요청한다. | D. 변경통제위원회(CCB)에 변경 요청을 제출한다. |  | A | 정답은 A이다. 새로운 이해관계자에게 현재 프로젝트 상태를 브리핑한다. 새로운 프로젝트 임원이 인수할 때, 현재 상태에 대한 포괄적 브리핑이 원활한 전환을 보장한다. 리스크 평가(B)는 중요하지만 즉각적 우선사항이 아니다. 추가 자금 요청(C)은 시기상조이다. 변경 요청 제출(D)은 리더십 변경에 적절하지 않다.
1087 | In an attempt to streamline project communications, a project manager established a shared portal for all stakeholders to get project information. The sponsor complained about this system and says that it is ineffective. What should the project manager have done to prevent this situation from occurring? | Confirmed that the portal is providing adequate information. | Analyzed the sponsor ' s communication requirements. | Ensured the sponsor had the necessary skills to use the portal. | Verified that the project team is following the communications management plan. |  | B | When a sponsor complains that a shared portal is ineffective for project communications, the project manager should have analyzed the sponsor's communication requirements. Understanding stakeholder needs before implementing tools ensures satisfaction. Confirming portal adequacy (A) is reactive. Ensuring the sponsor can use the portal (C) addresses skills, not needs. Verifying the team follows the plan (D) checks compliance, not stakeholder fit. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 커뮤니케이션을 효율화하기 위해 프로젝트 관리자가 모든 이해관계자를 위한 공유 포털을 구축했다. 스폰서가 이 시스템에 불만을 표하며 효과적이지 않다고 말한다. 프로젝트 관리자가 먼저 했어야 할 것은? | A. 포털이 적절한 정보를 제공하고 있는지 확인한다. | B. 스폰서의 커뮤니케이션 요구사항을 분석한다. | C. 스폰서가 포털을 사용할 필요한 기술이 있는지 확인한다. | D. 프로젝트 팀이 커뮤니케이션 관리 계획을 따르고 있는지 확인한다. |  | B | 스폰서가 공유 포털이 효과적이지 않다고 불만을 표할 때, 프로젝트 관리자는 스폰서의 커뮤니케이션 요구사항을 분석했어야 한다. 도구 구현 전 이해관계자 요구 파악이 만족을 보장한다. 포털 적절성 확인(A)은 반응적이다. 기술 확인(C)은 스폰서를 책망하는 것이다. 계획 준수 확인(D)은 요구사항 격차를 해결하지 않는다.
1088 | A project manager decided to use a highly adaptive approach to manage a large-scale project. In this project, there are many iterative tasks that utilize highly specialized experts. The project manager would like to create practical plans with high levels of buy-in from the team members. What should the project manager do next? | Review lessons learned from similar projects with the team. | Explain the higher-level objectives to be assigned to the team. | Review the budget with the team for the needed resources. | Assign critical tasks to the most experienced team members. |  | A | When using a highly adaptive approach with specialized experts and seeking practical plans with high team buy-in, the project manager should review lessons learned from similar projects with the team. Collaborative review of past experience builds shared understanding and informed planning. Explaining higher-level objectives (B) provides direction but not practical planning insight. Reviewing the budget (C) addresses resources, not planning approach. Assigning critical tasks to experienced members (D) is execution, not planning. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 대규모 프로젝트를 관리하기 위해 고도의 적응적 접근법을 사용하기로 했다. 이 프로젝트에는 고도로 전문화된 전문가를 활용하는 많은 반복 작업이 있다. 프로젝트 관리자가 높은 팀 동의를 가진 실용적 계획을 얻으려면 무엇을 해야 하는가? | A. 팀과 함께 유사 프로젝트의 교훈을 검토한다. | B. 팀에게 할당할 상위 수준 목표를 설명한다. | C. 필요한 자원에 대해 팀과 예산을 검토한다. | D. 가장 경험 많은 팀원에게 핵심 작업을 할당한다. |  | A | 고도의 적응적 접근법에서 전문가들과 높은 팀 동의를 가진 실용적 계획을 얻으려면, 팀과 함께 유사 프로젝트의 교훈을 검토해야 한다. 과거 경험의 협력적 검토는 공유된 이해와 정보에 기반한 계획을 구축한다. 상위 수준 목표 설명(B)은 하향식이다. 예산 검토(C)는 계획이 아닌 자원에 초점을 맞춘다. 경험자에게 할당(D)은 팀 동의를 구축하지 않는다.
1089 | Companies A and B are codeveloping a cutting-edge technology product. Based on customer feedback, the marketing department urgently requests a new feature in 2 weeks. Company A's front end is ready, but company B requires 4 weeks to deliver the complete back end and is busy with the current release. What should the project manager do to obtain agreement from both companies and acceptance from marketing? | Create a special release 4 weeks after the current release to deliver the new feature in its 85 entirety. | Add the new feature to the list for the next release and continue working on the current release. | Plan the delivery of a minimum viable feature in 2 weeks to enable early showcasing of business value. | Stop the current release work for 4 weeks in order to work and deliver the new feature completely. |  | C | When customer feedback creates urgent demand for a new feature, delivering a minimum viable feature (MVF) provides immediate value while full development continues. This approach aligns with agile principles of rapid, incremental value delivery. An MVF demonstrates responsiveness to customer needs and delivers a tangible product increment within a short timeframe without disrupting ongoing work by other teams. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 회사 A와 B가 최첨단 기술 제품을 공동 개발하고 있다. 고객 피드백을 기반으로 마케팅 부서가 2주 내에 새로운 기능을 긴급 요청한다. 회사 A의 프론트엔드는 준비되었으나, 회사 B의 백엔드는 약 4주가 소요된다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 현재 릴리스 4주 후에 특별 릴리스를 만들어 새 기능을 전체적으로 전달한다. | B. 새 기능을 다음 릴리스 목록에 추가하고 현재 릴리스 작업을 계속한다. | C. 2주 내에 최소 실행 가능 기능을 전달하여 비즈니스 가치의 조기 시연을 가능하게 한다. | D. 새 기능을 완전히 작업하고 전달하기 위해 4주 동안 현재 릴리스 작업을 중단한다. |  | C | 고객 피드백이 새 기능에 대한 긴급 수요를 만들 때, 최소 실행 가능 기능(MVF) 전달이 전체 개발이 계속되는 동안 즉각적 가치를 제공한다. 이는 신속하고 점진적인 가치 전달의 애자일 원칙에 부합한다. 특별 릴리스(A)는 4주를 지연시킨다. 다음 릴리스로 연기(B)는 긴급성을 무시한다. 현재 작업 중단(D)은 진행 중인 작업을 방해한다.
1090 | A project manager notices that a project participant seems frustrated and expresses themselves loudly at status meetings and later discovers that the participant is hearing impaired. Which process should the project manager have used at the start of the project that would have identified this situation? | Accommodations assessment | Team member assessment | Stakeholder analysis | Resource needs analysis |  | B | The project manager should have used a team member assessment at the start of the project to identify the hearing-impaired participant's needs. Team member assessments evaluate skills, knowledge, abilities, preferences, and potential accommodation needs of project team members, enabling the PM to plan appropriate adjustments—such as written materials, visual aids, adequate meeting room arrangements, and assistive technologies. An accommodations assessment (A) sounds relevant but is not a standard project management process. Stakeholder analysis (C) identifies influence and interest, not individual accommodation needs. Resource needs analysis (D) focuses on staffing levels, not individual team member requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자가 프로젝트 참여자가 상태 회의에서 좌절감을 표현하며 큰 소리로 말하는 것을 발견하고, 이후 그 참여자가 청각 장애가 있다는 것을 알게 되었다. 프로젝트 시작 시 어떤 프로세스를 수행했어야 하는가? | A. 편의 시설 평가 | B. 팀원 평가 | C. 이해관계자 분석 | D. 자원 필요 분석 |  | B | 프로젝트 관리자는 프로젝트 시작 시 팀원 평가를 수행했어야 한다. 팀원 평가는 기술, 지식, 능력, 선호도 및 잠재적 편의 필요를 평가하여 PM이 적절한 환경을 계획할 수 있게 한다. 편의 시설 평가(A)는 필요가 식별된 후에 온다. 이해관계자 분석(C)은 외부 이해관계자에 초점을 맞춘다. 자원 필요 분석(D)은 역할과 기술에 초점을 맞추지 개인 필요에는 맞추지 않는다.
1091 | A project team delivered a critical deliverable to the customer. The customer complained that the maintenance manual was not included. What should the project manager do next? | Submit a change request to include the manual. | Review the terms and conditions of the contract. | Review the stakeholder engagement plan. 1042 | Add the needed manual and update the risk log. |  | B | When a customer complains that the maintenance manual was not included with a critical deliverable, the project manager should review the terms and conditions of the contract. Contract review determines if the manual was part of agreed scope. Submitting a change request (A) assumes it was not in scope. Reviewing the stakeholder engagement plan (C) does not address the contractual issue. Adding the manual and updating the risk log (D) acts before verifying obligations. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 프로젝트 팀이 고객에게 핵심 산출물을 전달했다. 고객이 유지보수 매뉴얼이 포함되지 않았다고 불만을 제기했다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | A. 매뉴얼을 포함하기 위한 변경 요청을 제출한다. | B. 계약의 조건을 검토한다. | C. 이해관계자 참여 계획을 검토한다. | D. 필요한 매뉴얼을 추가하고 리스크 로그를 업데이트한다. |  | B | 고객이 핵심 산출물에 유지보수 매뉴얼이 포함되지 않았다고 불만을 제기할 때, 프로젝트 관리자는 계약의 조건을 검토해야 한다. 계약 검토는 매뉴얼이 합의된 범위의 일부인지 결정한다. 변경 요청 제출(A)은 범위에 없다고 가정한다. 이해관계자 참여 계획 검토(C)는 범위 문제를 해결하지 않는다. 매뉴얼 추가(D)는 범위 확인 없이 진행하는 것이다.
1092 | In an advanced stage of a project, a stakeholder who is not receiving the project status report communicates this to the project manager. After checking, the project manager determines that the person is registered as a stakeholder but was not included in the communications management plan. What should the project manager do next? | Inform the project sponsor that there are stakeholders who are not included in the communications management plan | Update the communications management plan to include the missed stakeholder, and send the current project status documentation to this stakeholder | Inform the stakeholder that the project team cannot provide information to anyone who is not registered in the project ' s communications management plan | Ask the stakeholder to get the project status report from another stakeholder listed in the communications management plan. |  | B | When a registered stakeholder was omitted from the communications management plan and is not receiving status reports, the project manager should update the communications management plan to include the missed stakeholder and send the current project status documentation to them. This corrects the gap and ensures immediate engagement. Informing the sponsor (A) escalates before fixing the issue. Informing the stakeholder they are not in the plan (C) is unhelpful. Asking them to get reports from another stakeholder (D) is dismissive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 진행 단계에서 프로젝트 상태 보고서를 받지 못하는 이해관계자가 프로젝트 관리자에게 이를 알렸다. 확인 결과 그 사람은 프로젝트에 등록되어 있으나 커뮤니케이션 관리 계획에서 누락되었다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 프로젝트 스폰서에게 커뮤니케이션 관리 계획에 포함되지 않은 이해관계자가 있다고 알린다. | B. 커뮤니케이션 관리 계획을 업데이트하여 누락된 이해관계자를 포함하고, 현재 프로젝트 상태 문서를 보낸다. | C. 이해관계자에게 프로젝트에 등록되지 않은 사람에게는 정보를 제공할 수 없다고 알린다. | D. 이해관계자에게 커뮤니케이션 관리 계획에 등록된 다른 이해관계자로부터 프로젝트 상태 보고서를 받으라고 요청한다. |  | B | 등록된 이해관계자가 커뮤니케이션 관리 계획에서 누락되어 상태 보고서를 받지 못할 때, 프로젝트 관리자는 계획을 업데이트하여 누락된 이해관계자를 포함하고 현재 상태 문서를 보내야 한다. 이는 격차를 시정하고 즉시 정보를 제공한다. 스폰서에게 알리기(A)는 직접 해결을 지연시킨다. 정보 거부(C)는 부적절하다. 다른 이해관계자에게 요청(D)은 책임을 전가한다.
1093 | During a sprint planning meeting, a stakeholder is told that their requirement is in progress and on track for the final product to be ready in the next two sprints. The stakeholder is very satisfied with the timeline and gives their full support to the agile team. After the meeting, the project sponsor calls the project manager about a large requirement they want the team to work on right away as it has significant business value. What should the project manager do? | Call the stakeholder to tell them that the final product schedule must be extended due to this last minute, urgent request. | Perform an impact analysis and share the overall schedule impact before deciding on a new priority. | Ask the product owner to prioritize the new request from the sponsor and ask the team to work on it immediately. | Reject the new requirement from the sponsor as this is going to impact the delivery of the stakeholder ' s final product. |  | B | When a sponsor requests an urgent, high-value requirement be worked on immediately while another stakeholder's requirement is on track, the project manager should perform an impact analysis and share the overall schedule impact before deciding on a new priority. Impact analysis ensures informed decision-making about trade-offs between competing priorities. Calling the stakeholder about schedule extension (A) communicates a decision before analysis. Asking the product owner to prioritize and start immediately (C) bypasses analysis. Rejecting the sponsor's requirement outright (D) dismisses a potentially valuable change. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 스프린트 계획 회의에서 이해관계자가 자신의 요구사항이 진행 중이며 다음 두 스프린트에서 최종 제품이 준비될 예정이라는 말을 듣는다. 이해관계자는 매우 만족한다. 그때 스폰서가 긴급하고 높은 가치의 요구사항을 즉시 작업해달라고 요청한다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 이해관계자에게 마지막 순간의 긴급 요청으로 인해 최종 제품 일정이 연장되어야 한다고 전화한다. | B. 영향 분석을 수행하고 새로운 우선순위를 결정하기 전에 전체 일정 영향을 공유한다. | C. 제품 책임자에게 스폰서의 새 요청을 우선순위로 지정하고 팀에게 즉시 작업하도록 요청한다. | D. 이해관계자의 최종 제품 전달에 영향을 미칠 것이므로 스폰서의 새 요구사항을 거부한다. |  | B | 스폰서가 다른 이해관계자의 요구사항이 진행 중인 상황에서 긴급한 고가치 요구사항을 즉시 작업하도록 요청할 때, 프로젝트 관리자는 영향 분석을 수행하고 새 우선순위를 결정하기 전에 전체 일정 영향을 공유해야 한다. 영향 분석은 정보에 기반한 의사결정을 보장한다. 일정 연장 통보(A)는 분석 없이 성급하다. 즉시 우선순위 변경(C)은 영향 평가를 건너뛴다. 요구사항 거부(D)는 비즈니스 가치를 무시한다.
1094 | An ongoing project with company A is impacted by the recent acquisition of company B. This could affect the current suppliers for the ongoing project. What should the project manager do next? | Retain company A ' s supplier based on the long-term relationship with them. | Evaluate the project suppliers of company B for future use. | Engage the suppliers of company B to validate the current list of suppliers. | Consolidate the list of suppliers for companies A and B. |  | C | The correct answer is C. Engage the suppliers of company B to validate the current list of suppliers. Procurement and vendor management involves proper planning, oversight, and control. The PM should ensure contract compliance, evaluate performance, and address issues appropriately. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 회사 A와 진행 중인 프로젝트가 최근 회사 B의 인수로 영향을 받았다. 이는 진행 중인 프로젝트의 현재 공급업체에 영향을 미칠 수 있다. 프로젝트 관리자는 다음에 무엇을 해야 하는가? | A. 장기적 관계를 기반으로 회사 A의 공급업체를 유지한다. | B. 향후 사용을 위해 회사 B의 프로젝트 공급업체를 평가한다. | C. 회사 B의 공급업체를 참여시켜 현재 공급업체 목록을 검증한다. | D. 회사 A와 B의 공급업체 목록을 통합한다. |  | C | 정답은 C이다. 회사 B의 공급업체를 참여시켜 현재 공급업체 목록을 검증한다. 인수 후 조달 및 벤더 관리는 적절한 계획, 감독 및 통제를 포함한다. PM은 계약 준수를 보장하고 성과를 평가하며 이슈를 적절히 해결해야 한다. 장기 관계만으로 유지(A)는 객관적이지 않다. 향후 사용 평가(B)는 현재 영향을 해결하지 않는다. 목록 통합(D)은 성급하다.
1095 | An agile project manager has team members from different continents on the project team. During the daily scrum meetings, the project manager notices that there are gaps in understanding about the project goals and objectives. What should the project manager do? | Coach the team members to resolve the gaps in understanding | Conduct a kick-off meeting and communicate the goals and objectives of the project | Continue the meetings and communicate the goals and objectives to resolve the gaps | Schedule team-building activities to encourage collaboration among the team |  | B | When team members from different continents show gaps in understanding project goals during daily scrums, the project manager should conduct a kick-off meeting to communicate the project's goals and objectives clearly. A kick-off meeting establishes a common understanding of the project vision, scope, deliverables, and roles—especially critical for distributed teams. Coaching team members (A) addresses individual gaps but not the foundational alignment issue. Continuing meetings and communicating goals incrementally (C) is too gradual. Scheduling team-building activities (D) builds relationships but does not directly address the knowledge gaps. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 애자일 프로젝트 관리자가 다른 대륙의 팀원들로 구성된 프로젝트 팀을 보유하고 있다. 일일 스크럼 회의에서 프로젝트 목표와 목적에 대한 이해 격차가 있음을 발견한다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 팀원들이 이해 격차를 해결하도록 코칭한다. | B. 킥오프 회의를 실시하고 프로젝트 목표와 목적을 전달한다. | C. 회의를 계속하면서 격차를 해결하기 위해 목표와 목적을 전달한다. | D. 팀 간 협력을 장려하기 위해 팀 빌딩 활동을 예약한다. |  | B | 다른 대륙의 팀원들이 일일 스크럼에서 프로젝트 목표 이해 격차를 보일 때, 프로젝트 관리자는 킥오프 회의를 실시하여 프로젝트 목표와 목적을 명확히 전달해야 한다. 킥오프 회의는 프로젝트 비전, 범위 및 기대에 대한 공통 이해를 수립한다. 코칭(A)은 개별적이며 근본적 정렬 격차를 해결하지 않는다. 회의 계속(C)은 비효율적이다. 팀 빌딩(D)은 지식 격차가 아닌 관계에 초점을 맞춘다.
1096 | A project team member just informed the project manager that the license for the software that the team uses to perform calculations has just expired. As a result, the team cannot continue with their project tasks. What should the project manager do first? | Ask the team members to find an alternative way to perform calculations. | Issue a formal complaint to the project sponsor claiming a lack of proper tools. | Meet with the IT team to evaluate how fast the software license can be renewed. | Ask the team to fast-track the project and perform tasks that do not require calculations. |  | C | When the team's software license has expired and they cannot continue project tasks, the project manager should first meet with the IT team to evaluate how fast the software license can be renewed. This addresses the root cause directly and aims for the quickest resolution. Asking team members to find alternatives (A) is ad hoc and may not produce reliable solutions. Issuing a formal complaint to the sponsor (B) escalates without attempting resolution. Fast-tracking tasks without calculations (D) compromises work quality. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 프로젝트 팀원이 계산을 수행하는 데 사용하는 소프트웨어 라이선스가 만료되었다고 프로젝트 관리자에게 알렸다. 그 결과 팀은 작업을 계속할 수 없다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 팀원들에게 계산을 수행할 대안적 방법을 찾으라고 요청한다. | B. 프로젝트 스폰서에게 적절한 도구 부족에 대한 공식 불만을 제기한다. | C. IT 팀과 만나 소프트웨어 라이선스를 얼마나 빨리 갱신할 수 있는지 평가한다. | D. 팀에게 프로젝트를 패스트트랙하고 계산이 필요하지 않은 작업을 수행하라고 요청한다. |  | C | 팀의 소프트웨어 라이선스가 만료되어 프로젝트 작업을 계속할 수 없을 때, 프로젝트 관리자는 먼저 IT 팀과 만나 라이선스를 얼마나 빨리 갱신할 수 있는지 평가해야 한다. 이는 근본 원인을 직접 해결하고 가장 빠른 해결을 목표로 한다. 대안적 방법 찾기(A)는 해결책이 아닌 우회이다. 공식 불만(B)은 불필요하게 확대한다. 패스트트랙(D)은 핵심 작업을 무시한다.
1097 | A project manager has been tasked with developing a project schedule with fully detailed requirements. The project manager reaches out to subject matter experts (SMEs) for their initial thoughts on task duration. The project manager is concerned when these estimates appear to differ significantly. What should the project manager do to help with the estimate development? | Ask the SMEs to hold up cards that show their estimate, discuss the highest and lowest estimates, and then estimate again. | Escalate to the project sponsor and explain the differences in the estimations coming from the SMEs. | Recommend using an iterative approach, with a focus on estimates, that the SMEs agree with. | Use historical information to help guide the estimates that were proposed by the SMEs. |  | A | When SME estimates differ significantly, the project manager should use a structured consensus-building technique—having SMEs show estimates simultaneously, discuss the highest and lowest, and re-estimate. This approach (similar to Planning Poker or Delphi) reduces anchoring bias, surfaces hidden assumptions, and aligns understanding of work complexity. Using historical information (D) is complementary but may not resolve differences if the work is novel. Recommending an iterative approach (C) is too vague. Escalating to the sponsor (B) is inappropriate for a normal planning activity best resolved through facilitation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트 관리자가 완전히 상세한 요구사항으로 프로젝트 일정을 개발하는 임무를 받았다. 주제 전문가(SME)에게 작업 기간에 대한 초기 생각을 요청했으나, SME들의 추정치가 크게 다르다. 프로젝트 관리자는 무엇을 해야 하는가? | A. SME에게 추정치를 보여주는 카드를 들게 하고, 가장 높은 것과 낮은 것을 논의한 후 다시 추정한다. | B. 프로젝트 스폰서에게 SME들의 추정 차이를 설명하고 에스컬레이션한다. | C. SME들이 동의하는 추정치에 초점을 맞춘 반복적 접근법을 권장한다. | D. SME들이 제안한 추정치를 안내하기 위해 역사적 정보를 사용한다. |  | A | SME 추정치가 크게 다를 때, 프로젝트 관리자는 구조화된 합의 구축 기법을 사용해야 한다—SME에게 동시에 추정치를 보여주고, 가장 높고 낮은 것을 논의하고, 다시 추정한다. 이 접근법(플래닝 포커 또는 델파이와 유사)은 고정 편향을 줄이고 숨겨진 가정을 표면화한다. 에스컬레이션(B)은 불필요하다. 반복적 접근(C)은 추정 불일치를 해결하지 않는다. 역사적 정보(D)는 보완적이지만 합의를 구축하지 않는다.
1098 | A key project team member has exhibited high interest in a project. The input from this person has been very useful, and the project is steadily progressing. Suddenly, this individual's participation decreases, and activities that they were responsible for are not being completed within the planned period. What should the project manager do? | Reallocate tasks for the team member of concern so that work is handled by another team member. | Schedule a meeting to discuss recent observations with the team member. | Consult the resource allocation matrix to see if the team member is still required for theproject. | Organize a team-building session with all of the team members. |  | B | When a previously high-performing team member shows a sudden decline in participation and task completion, the project manager should schedule a meeting to discuss the recent observations directly with that team member. This demonstrates effective communication, empathy, and a desire to understand the root cause before taking action. Reallocating tasks to another team member (A) ignores the underlying issue and may demoralize the individual. Organizing a general team-building session (D) does not address the specific individual's concerns. Consulting the resource allocation matrix (C) is an administrative check that does not resolve the behavioral change. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Embed Quality | Develop Team | Traditional PM | 핵심 프로젝트 팀원이 프로젝트에 높은 관심을 보여왔다. 이 사람의 기여는 매우 유용했고 프로젝트가 꾸준히 진행되고 있었다. 갑자기 이 개인의 참여도와 작업 완료가 크게 감소했다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 해당 팀원의 작업을 다른 팀원이 처리하도록 재할당한다. | B. 최근 관찰 사항을 논의하기 위해 팀원과 회의를 예약한다. | C. 자원 할당 매트릭스를 확인하여 팀원이 여전히 프로젝트에 필요한지 확인한다. | D. 모든 팀원과 함께 팀 빌딩 세션을 조직한다. |  | B | 이전에 높은 성과를 보이던 팀원의 참여도와 작업 완료가 갑자기 감소할 때, 프로젝트 관리자는 해당 팀원과 직접 최근 관찰 사항을 논의하기 위한 회의를 예약해야 한다. 이는 효과적인 커뮤니케이션, 공감, 이해 의지를 보여준다. 작업 재할당(A)은 근본 원인을 해결하지 않는다. 자원 매트릭스 확인(C)은 비인간적이다. 팀 빌딩(D)은 개인적 이슈를 해결하지 않는다.
1099 | A project team is working on a product that is planned for multiple iterations. They are delivering incremental value. When should the value be demonstrated? | When the sponsor approves the increment | When a major feature is completed | After full development is completed | At the end of each and every iteration |  | D | When a product is planned for multiple iterations delivering incremental value, the value should be demonstrated at the end of each and every iteration. Regular demonstrations ensure continuous feedback. Waiting for sponsor approval (A) delays feedback. Waiting for a major feature (B) misses incremental value. After full development (C) eliminates iterative benefits. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 팀이 여러 이터레이션을 계획한 제품을 작업하고 있다. 점진적 가치를 전달하고 있다. 가치는 언제 시연되어야 하는가? | A. 스폰서가 증분을 승인할 때 | B. 주요 기능이 완료될 때 | C. 전체 개발이 완료된 후 | D. 각 이터레이션이 끝날 때마다 |  | D | 여러 이터레이션으로 계획된 제품이 점진적 가치를 전달할 때, 가치는 각 이터레이션이 끝날 때마다 시연되어야 한다. 정기적 시연은 지속적 피드백을 보장한다. 스폰서 승인 대기(A)는 피드백을 지연시킨다. 주요 기능 완료 대기(B)는 점진적 피드백 기회를 놓친다. 전체 개발 완료 후(C)는 폭포수 접근법이다.
1100 | During the initiating phase of a project, a key stakeholder requests frequent changes to the project scope. What should the project manager do to improve the stakeholder's engagement? | Discuss the work breakdown structure (WBS) with the key stakeholder and refine the requirements | Update the project backlog and discuss it with the key stakeholder | Discuss the project scope statement with the key stakeholder and build prototypes | Update the project charter and discuss it with the key stakeholder. |  | C | When a key stakeholder requests frequent scope changes during the initiating phase, the project manager should discuss the project scope statement with the stakeholder and build prototypes. Prototypes elicit concrete feedback and reduce changes. Discussing the WBS (A) focuses on structure, not requirements validation. Updating the backlog (B) captures changes but does not improve engagement. Updating the charter (D) is too high-level. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 프로젝트 착수 단계에서 핵심 이해관계자가 프로젝트 범위에 빈번한 변경을 요청한다. 프로젝트 관리자는 이해관계자의 참여를 개선하기 위해 무엇을 해야 하는가? | A. 핵심 이해관계자와 작업 분류 체계(WBS)를 논의하고 요구사항을 정제한다. | B. 프로젝트 백로그를 업데이트하고 핵심 이해관계자와 논의한다. | C. 핵심 이해관계자와 프로젝트 범위 기술서를 논의하고 프로토타입을 구축한다. | D. 프로젝트 헌장을 업데이트하고 핵심 이해관계자와 논의한다. |  | C | 핵심 이해관계자가 착수 단계에서 빈번한 범위 변경을 요청할 때, 프로젝트 관리자는 이해관계자와 프로젝트 범위 기술서를 논의하고 프로토타입을 구축해야 한다. 프로토타입은 구체적 피드백을 도출하고 변경을 줄인다. WBS 논의(A)는 구조에 초점을 맞추지 요구사항 명확화에는 맞추지 않는다. 백로그 업데이트(B)는 애자일 도구이며 착수 단계에 부적절하다. 헌장 업데이트(D)는 범위 세부사항이 아닌 상위 수준 문서이다.
1101 | In a highly politicized organizational environment, the stakeholders are driven by their own operational or business goals, which results in conflicting interests regarding the project. What should the project manager do to steer the stakeholders toward the collective project goal? | Anticipate, alert, and follow the risk management process. | Detect, track, and follow the issue management process. | Discuss, educate, and follow the communications management process. | Promote, inspire, and follow the stakeholder engagement process. |  | D | In a highly politicized environment with conflicting stakeholder interests, the project manager should promote, inspire, and follow the stakeholder engagement process. Active engagement aligns stakeholders around the collective project goal through collaboration and shared objectives. Anticipating risks (A) addresses threats but not stakeholder alignment. Detecting and tracking issues (B) is reactive. Discussing and educating on communications (C) improves information flow but does not drive alignment. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 고도로 정치화된 조직 환경에서 이해관계자들이 자신의 운영 또는 비즈니스 목표에 의해 움직이며, 프로젝트에 대해 상충되는 이해관계를 가져온다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 리스크 관리 프로세스를 예상하고, 경고하고, 따른다. | B. 이슈 관리 프로세스를 탐지하고, 추적하고, 따른다. | C. 커뮤니케이션 관리 프로세스를 논의하고, 교육하고, 따른다. | D. 이해관계자 참여 프로세스를 촉진하고, 영감을 주고, 따른다. |  | D | 고도로 정치화된 환경에서 상충되는 이해관계자 이해관계가 있을 때, 프로젝트 관리자는 이해관계자 참여 프로세스를 촉진하고, 영감을 주고, 따라야 한다. 적극적 참여는 협력과 공유된 목표를 통해 이해관계자를 집단적 프로젝트 목표 주위에 정렬시킨다. 리스크 예상(A)은 관계를 구축하지 않는다. 이슈 추적(B)은 반응적이다. 커뮤니케이션 교육(C)은 정보에 초점을 맞추지 정렬에는 맞추지 않는다.
1102 | Two team members are arguing about which technology they should use when implementing iteration tasks. The predictive approach was broken into several iterations that need to be completed on time so as not to jeopardize the project's timely completion. What should the project manager do to resolve this issue and help the team move on to the next iteration? | Allow the team to decide since the teams should be autonomous | Suggest their own approach to solve the issue and ask the team to follow it | Postpone the selection of the technology used until more information is gathered | Call for an open dialogue which the team will arrive at through consensus |  | D | When team members disagree on technology choices in a predictive project, the PM should facilitate open dialogue where everyone voices their opinions and concerns. Through collaborative discussion, the team can reach consensus, ensuring alignment and commitment. This approach resolves the immediate disagreement while fostering an inclusive, collaborative team environment essential for project success. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 두 팀원이 이터레이션 작업 구현 시 어떤 기술을 사용할지에 대해 논쟁하고 있다. 예측적 접근법은 제시간에 완료해야 하는 여러 이터레이션으로 나뉘었다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 팀이 자율적이어야 하므로 팀이 결정하도록 허용한다. | B. 자신의 접근법을 제안하고 팀에게 따르라고 요청한다. | C. 더 많은 정보가 수집될 때까지 기술 선택을 연기한다. | D. 팀이 합의에 도달할 수 있는 열린 대화를 요청한다. |  | D | 예측적 프로젝트에서 팀원들이 기술 선택에 대해 의견이 다를 때, PM은 모든 사람이 의견과 우려를 표명하는 열린 대화를 촉진해야 한다. 협력적 논의를 통해 팀이 합의에 도달하여 정렬과 몰입을 보장한다. 팀 자율성 허용(A)은 의견 불일치를 해결하지 않는다. 자신의 접근법 제안(B)은 독단적이다. 선택 연기(C)는 진행을 지연시킨다.
1103 | An organization with a new project management office (PMO) team is now undergoing a restructuring. Additionally, there is a lack of communication from the PMO to the team members. How should the project manager handle this situation? | Meet the PMO team and explain the importance of communicating with the team members for project success. | Request the PMO team share updates on the restructuring with the team members on an immediate basis. | Set up a meeting with the PMO and project team to discuss and clarify questions related to restructuring. | Inform the team that despite the new PMO and restructuring, the team will not change. |  | C | When an organization's new PMO is restructuring with inadequate communication to team members, the project manager should set up a meeting with the PMO and project team to discuss and clarify questions. Joint dialogue ensures alignment and reduces uncertainty. Meeting only the PMO team (A) excludes the project team. Requesting the PMO share updates immediately (B) is directive without facilitation. Informing the team nothing will change (D) may be inaccurate. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | General | Stakeholder & Communication Mgmt | Business Environment | Support Organizational Change | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새로운 프로젝트 관리 사무소(PMO) 팀이 있는 조직이 구조조정을 진행하고 있다. 또한 PMO에서 팀원들에 대한 커뮤니케이션이 부족하다. 프로젝트 관리자는 어떻게 해야 하는가? | A. PMO 팀을 만나 프로젝트 성공을 위한 팀원과의 커뮤니케이션 중요성을 설명한다. | B. PMO 팀에게 구조조정에 대한 업데이트를 팀원에게 즉시 공유하도록 요청한다. | C. PMO와 프로젝트 팀의 회의를 설정하여 구조조정 관련 질문을 논의하고 명확히 한다. | D. 새로운 PMO와 구조조정에도 불구하고 팀은 변경되지 않을 것이라고 팀에게 알린다. |  | C | 조직의 새로운 PMO가 팀원에게 부적절한 커뮤니케이션으로 구조조정하고 있을 때, 프로젝트 관리자는 PMO와 프로젝트 팀의 회의를 설정하여 질문을 논의하고 명확히 해야 한다. 공동 대화가 정렬을 보장하고 불확실성을 줄인다. PMO만 만나기(A)는 팀원을 배제한다. 즉시 공유 요청(B)은 맥락 없는 것이다. 변화 없다고 알리기(D)는 오해의 소지가 있다.
1104 | Two members of a new project team disagree on the best approach to solve a problem. The conflict has been going on for 1 week. The two members are tense around each other and are taking everything personally. What should the project manager do? | Help the team members to resolve the conflict in a way that results in the best team performance. | Understand each team member ' s argument and select the one that results in less risk to the project. | Offer a compromise that is acceptable to both team members, even if it may not be the best solution. | Send both team members to the human resources (HR) department for an acceptable resolution. |  | A | When two team members disagree on a problem-solving approach for a week and the conflict has become personal, the project manager should help them resolve the conflict in a way that results in the best team performance. Facilitated collaborative resolution produces win-win outcomes. Understanding each argument and selecting one (B) is authoritative. Offering a compromise (C) may not yield the best solution. Sending both to HR (D) escalates unnecessarily. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 프로젝트 팀의 두 팀원이 문제 해결 최선의 접근법에 대해 의견이 다르다. 갈등이 1주일간 지속되었다. 두 팀원은 서로 긴장되어 있으며 모든 것을 개인적으로 받아들이고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 최고의 팀 성과를 가져오는 방식으로 갈등을 해결하도록 팀원을 돕는다. | B. 각 팀원의 논점을 이해하고 프로젝트에 리스크가 적은 것을 선택한다. | C. 최선의 해결책이 아닐 수 있더라도 양쪽 팀원에게 수용 가능한 타협을 제안한다. | D. 두 팀원을 인사부(HR)에 보내 수용 가능한 해결을 위해 보낸다. |  | A | 두 팀원이 1주일간 문제 해결 접근법에 대해 의견이 다르고 갈등이 개인적으로 된 경우, 프로젝트 관리자는 최고의 팀 성과를 가져오는 방식으로 갈등을 해결하도록 도와야 한다. 촉진된 협력적 해결은 윈-윈 결과를 만든다. 각자 논점 이해 후 선택(B)은 권위적이다. 타협 제안(C)은 차선책을 수용한다. HR로 보내기(D)는 관리 책임을 회피한다.
1105 | A project manager is leading a project that is in the execution phase. Due to a company reorganization, some key project team members are likely to leave the project. What should the project manager do next? | Discuss this issue with the affected team members and support them during the transition. | Start looking for replacements as soon as possible to help prevent any schedule slippage. | Determine the impact to the project and implement mitigations per the project management plan. | Engage with the project sponsor to ensure that this change does not affect the project execution. |  | C | When key team members are likely to leave due to a company reorganization, the project manager should determine the impact to the project and implement mitigations per the project management plan. Systematic impact assessment and planned responses maintain project continuity. Discussing with affected members and supporting them (A) is empathetic but does not address project impact. Looking for replacements immediately (B) is reactive. Engaging the sponsor about execution impact (D) is helpful but secondary to following the risk plan. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 실행 단계에 있는 프로젝트를 이끌고 있다. 회사 구조조정으로 인해 일부 핵심 프로젝트 팀원이 프로젝트를 떠날 가능성이 있다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 영향을 받는 팀원들과 이 문제를 논의하고 전환 기간 동안 지원한다. | B. 일정 지연을 방지하기 위해 가능한 한 빨리 대체 인력을 찾기 시작한다. | C. 프로젝트에 대한 영향을 결정하고 프로젝트 관리 계획에 따라 완화 조치를 실행한다. | D. 이 변경이 프로젝트 실행에 영향을 미치지 않도록 프로젝트 스폰서와 협의한다. |  | C | 회사 구조조정으로 핵심 팀원이 떠날 가능성이 있을 때, 프로젝트 관리자는 프로젝트에 대한 영향을 결정하고 프로젝트 관리 계획에 따라 완화 조치를 실행해야 한다. 체계적 영향 평가와 계획된 대응이 프로젝트 연속성을 유지한다. 팀원과 논의(A)는 지지적이지만 즉각적 관리 조치가 아니다. 대체 인력 찾기(B)는 영향 평가 전에 성급하다. 스폰서 협의(D)는 보조적이지만 일차적 조치는 아니다.
1106 | A company is interested in reducing production costs in one of its production lines. When the project charter was about to be approved, one of the key stakeholders questioned the project's value and caused a delay in the approval. What should the project manager have done to avoid this setback? | Analyzed stakeholders | Assessed feasibility and impacts | Detailed the project charter | Developed benchmarking |  | A | When a key stakeholder questioned the project's value before charter approval, the project manager should have analyzed stakeholders earlier. Stakeholder analysis identifies concerns and influence before approvals. Assessing feasibility and impacts (B) is project analysis, not stakeholder engagement. Detailing the charter (C) does not address stakeholder alignment. Developing benchmarking (D) is a quality technique unrelated to stakeholder management. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Integration & General PM | People | Engage Stakeholders | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 회사가 생산 라인 중 하나의 생산 비용을 줄이는 데 관심이 있다. 프로젝트 헌장이 승인되려 할 때, 핵심 이해관계자가 프로젝트의 가치와 이점에 의문을 제기했다. 프로젝트 관리자가 먼저 했어야 할 것은? | A. 이해관계자를 분석했어야 한다. | B. 타당성과 영향을 평가했어야 한다. | C. 프로젝트 헌장을 상세화했어야 한다. | D. 벤치마킹을 개발했어야 한다. |  | A | 핵심 이해관계자가 헌장 승인 전에 프로젝트 가치에 의문을 제기했을 때, PM은 이해관계자를 더 일찍 분석했어야 한다. 이해관계자 분석은 승인 전 우려사항과 영향력을 식별한다. 타당성 평가(B)는 프로젝트 분석이지 이해관계자 참여가 아니다. 헌장 상세화(C)는 이해관계자 우려를 해결하지 않는다. 벤치마킹(D)은 비교 도구이지 참여 도구가 아니다.
1107 | Project stakeholders are engaged in a discussion on how to achieve the best user experience in the design of a new application. The agile team is divided on the approach. The conflict is more of a collective disagreement than an outright conflict. What should the project manager do next? | Call a team meeting to have a formal discussion of the issue. | Allow the team to work through it on their own unless help is needed. | Engage in individual conversation with each team member. | Apply appropriate conflict resolution techniques to solve the issue. |  | B | When stakeholders disagree on user experience design and the agile team has a collective disagreement rather than outright conflict, the project manager should allow the team to work through it on their own unless help is needed. Self-organization empowers teams. Calling a formal meeting (A) may escalate unnecessarily. Individual conversations (C) fragment the discussion. Applying formal conflict resolution techniques (D) treats a disagreement as a conflict. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 이해관계자들이 새 애플리케이션 설계에서 최고의 사용자 경험을 달성하는 방법에 대해 논의하고 있다. 애자일 팀은 접근법에 대해 의견이 갈린다. 갈등은 전면적 충돌이라기보다 집단적 의견 불일치에 가깝다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 팀 회의를 소집하여 이슈에 대한 공식적 논의를 한다. | B. 도움이 필요하지 않는 한 팀이 스스로 해결하도록 한다. | C. 각 팀원과 개별 대화에 참여한다. | D. 적절한 갈등 해결 기법을 적용하여 이슈를 해결한다. |  | B | 이해관계자들이 UX 설계에 대해 의견이 다르고 애자일 팀이 전면 충돌이 아닌 집단적 의견 불일치를 가질 때, PM은 도움이 필요하지 않는 한 팀이 스스로 해결하도록 해야 한다. 자기 조직화가 팀에 권한을 부여한다. 공식 회의(A)는 상황을 확대할 수 있다. 개별 대화(C)는 집단 역학을 분리한다. 갈등 해결 기법(D)은 전면 충돌에 적합하다.
1108 | A project stakeholder has left the company. The new stakeholder is a family member of one of the team members. This stakeholder does not attend meetings. The project manager finds out that the stakeholder has been asking the family member for project updates. What should the project manager do? | Escalate this to the project sponsor. | Forward the project status reports. | Request a meeting with the stakeholder. | Design an updated status report. |  | C | When a stakeholder avoids meetings and gets updates through a family member on the team, the project manager should request a meeting with the stakeholder. Direct engagement establishes proper communication. Escalating to the sponsor (A) is premature. Forwarding status reports (B) does not address the communication gap. Designing an updated report (D) does not fix stakeholder engagement. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 프로젝트 이해관계자가 회사를 떠났다. 새 이해관계자는 팀원 중 한 명의 가족이다. 이 이해관계자는 회의에 참석하지 않는다. PM은 이해관계자가 팀에 있는 가족을 통해 업데이트를 받고 있음을 알게 되었다. PM은 무엇을 해야 하는가? | A. 프로젝트 스폰서에게 에스컬레이션한다. | B. 프로젝트 상태 보고서를 전달한다. | C. 이해관계자와 회의를 요청한다. | D. 업데이트된 상태 보고서를 설계한다. |  | C | 이해관계자가 회의를 피하고 팀 내 가족을 통해 업데이트를 받을 때, PM은 이해관계자와 직접 회의를 요청해야 한다. 직접 참여가 적절한 커뮤니케이션을 수립한다. 스폰서에게 에스컬레이션(A)은 시기상조이다. 보고서 전달(B)은 참여 부족을 해결하지 않는다. 보고서 재설계(D)는 핵심 이슈를 놓친다.
1109 | A project manager is reviewing the lessons learned for a historical project. The review identifies that the client's engineer was adamant that they review all changes, even those not identified in the contract. How should the project manager deal with this when planning the project? | Ensure the change management plan highlights this requirement to prevent future issues. | Update the project charter with this information regarding change management. | Update the project risk register to identify this risk and describe how to mitigate the issue. | Talk with the client to ensure they are aware of the change management procedure. |  | A | The PM should ensure the change management plan addresses the client engineer's requirement to review all changes—including those not specified in the contract. A comprehensive change management plan that reflects actual stakeholder expectations prevents misunderstandings and conflicts related to change approvals. This proactive approach aligns with best practices in change management and stakeholder engagement. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 과거 프로젝트의 교훈을 검토하고 있다. 검토 결과 고객 엔지니어가 계약에 명시되지 않은 변경사항도 포함하여 모든 변경을 검토해야 한다고 고집했던 것이 확인되었다. PM은 무엇을 해야 하는가? | A. 변경 관리 계획이 향후 이슈를 방지하기 위해 이 요구사항을 강조하도록 한다. | B. 변경 관리에 관한 이 정보로 프로젝트 헌장을 업데이트한다. | C. 프로젝트 리스크 레지스터를 업데이트하여 이 리스크를 식별하고 완화 방법을 기술한다. | D. 고객과 대화하여 변경 관리 절차를 인지하고 있는지 확인한다. |  | A | PM은 변경 관리 계획이 고객 엔지니어의 모든 변경 검토 요구사항을 반영하도록 해야 한다. 실제 이해관계자 기대를 반영하는 포괄적 변경 관리 계획이 오해와 갈등을 방지한다. 헌장 업데이트(B)는 상위 수준이며 변경 관리 세부사항에 적합하지 않다. 리스크 레지스터(C)는 리스크를 기록하지만 프로세스를 설정하지 않는다. 고객 대화(D)는 반응적이며 향후 프로젝트를 방지하지 않는다.
1110 | The project manager has finished all the tasks of the project and immediately starts on a new project. A few months after beginning the new project, the accounting manager asks for confirmation of previous projects because the budget is still open with no further cash flows. What should the project manager have done? | Completed the transition process | Performed administrative closure of the project | Conveyed task completion information to accounting | Closed the procurement process properly |  | B | When the project manager moved to a new project without properly closing the previous one and accounting later finds the budget still open, the project manager should have performed administrative closure of the project. Formal closure finalizes budgets, releases resources, and updates records. Completing the transition process (A) transfers deliverables but does not close the project. Conveying task completion to accounting (C) is one step but insufficient. Closing the procurement process (D) is specific to contracts, not overall project closure. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Finance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트 관리자가 프로젝트의 모든 작업을 마치고 즉시 새 프로젝트를 시작했다. 새 프로젝트 시작 몇 달 후, 회계 관리자가 이전 프로젝트 예산이 여전히 열려 있다며 확인을 요청한다. PM이 하지 않은 것은? | A. 전환 프로세스를 완료했어야 한다. | B. 프로젝트의 행정적 종료를 수행했어야 한다. | C. 작업 완료 정보를 회계에 전달했어야 한다. | D. 조달 프로세스를 적절히 종료했어야 한다. |  | B | 프로젝트 관리자가 이전 프로젝트를 적절히 종료하지 않고 새 프로젝트로 이동했고 이후 회계에서 예산이 여전히 열려 있음을 발견했을 때, PM은 프로젝트의 행정적 종료를 수행했어야 한다. 공식 종료가 예산을 확정하고, 자원을 해제하고, 기록을 업데이트한다. 전환 완료(A)는 운영 전환이지 프로젝트 종료가 아니다. 회계에 전달(C)은 부분적이다. 조달 종료(D)는 한 구성요소이지 전체 종료가 아니다.
1111 | A project manager is working on a project to develop a new watch at a matrix organization. Which two key items should the project manager include in their feedback to external stakeholders? (Choose two) | Schedule performance index (SPI) for the portfolio | Earned value in terms of schedule | Expected return on investment (ROI) for portfolio projects | Earned value in terms of resources | Earned value in terms of cost | B, C | When providing feedback to external stakeholders, the project manager should include (B) earned value in terms of schedule and (C) earned value in terms of cost. Schedule and cost performance are key external metrics. SPI for the portfolio (A) is too broad. Expected ROI (D) is strategic, not project-level. Earned value in terms of resources (E) is not a standard earned value metric. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Earned Value Management | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 프로젝트 관리자가 매트릭스 조직에서 새 시계를 개발하는 프로젝트를 진행하고 있다. 외부 이해관계자에 대한 피드백에 포함해야 할 두 가지 핵심 항목은? (2개 선택) | A. 포트폴리오의 일정 성과 지수(SPI) | B. 일정 측면의 획득 가치 | C. 포트폴리오 프로젝트의 예상 투자 수익률(ROI) | D. 자원 측면의 획득 가치 | E. 비용 측면의 획득 가치 | B, C | 외부 이해관계자에게 피드백을 제공할 때, PM은 일정 측면의 획득 가치(B)와 비용 측면의 획득 가치(E)를 포함해야 한다. 일정과 비용 성과가 핵심 외부 지표이다. 포트폴리오 SPI(A)는 너무 광범위하다. 예상 ROI(C)는 전략적이지 프로젝트 수준이 아니다. 자원 측면 획득 가치(D)는 일반적으로 외부에 보고하지 않는다.
1112 | The team's work assignments have been generically distributed. A new team member is performing slower than expected. What should the project manager do? | Have all of the other team members retrain the new team member to improve team performance. | Extend the project timeline to allow the new team member to work at their own pace. | Assess the new team member ' s skills in order to determine additional training needs. | Change the way the work assignments are distributed to facilitate new team member development. |  | C | When a new team member with generic work assignments performs slower than expected, the project manager should assess the new member's skills to determine additional training needs. Skills assessment identifies the gap. Retraining by all other members (A) is disruptive. Extending the timeline (B) accepts inefficiency. Changing work distribution (D) may help but should follow assessment. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 팀의 업무 배정이 일반적으로 분배되었다. 새 팀원이 예상보다 느리게 수행하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | A. 다른 모든 팀원이 새 팀원을 재교육하여 팀 성과를 개선한다. | B. 새 팀원이 자신의 속도로 작업할 수 있도록 프로젝트 일정을 연장한다. | C. 새 팀원의 기술을 평가하여 추가 교육 필요를 결정한다. | D. 새 팀원 개발을 촉진하기 위해 업무 배정 분배 방식을 변경한다. |  | C | 일반적 업무 배정을 받은 새 팀원이 예상보다 느리게 수행할 때, PM은 새 팀원의 기술을 평가하여 추가 교육 필요를 결정해야 한다. 기술 평가가 격차를 식별한다. 모든 팀원에 의한 재교육(A)은 방해적이다. 일정 연장(B)은 저성과를 수용한다. 배정 방식 변경(D)은 시기상조이다.
1113 | A project team member is sick and will not be able to return to the project for a few weeks. During the daily meeting, the team shares their concerns as the sick team member was the only one skilled in the component they were developing. What should the project manager have done to prevent this? | Requested robust documentation for the component ' s build. | Outsourced development of the specific component to another team. | Acquired more than one resource skilled in each component. | Facilitated cross-functional knowledge transfer during the project. |  | D | When a sick team member was the only one skilled in their component, the project manager should have facilitated cross-functional knowledge transfer during the project. Knowledge sharing prevents single points of failure. Requesting robust documentation (A) is partial. Outsourcing the component (B) does not build internal capability. Acquiring multiple skilled resources (C) is helpful but knowledge transfer is the more sustainable prevention. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 팀원이 아파서 몇 주 동안 프로젝트에 복귀할 수 없다. 일일 회의에서 팀이 그 팀원만이 해당 구성요소에 대한 기술을 가지고 있었다며 우려를 공유한다. PM이 했어야 할 것은? | A. 구성요소 빌드에 대한 견고한 문서화를 요청했어야 한다. | B. 특정 구성요소 개발을 다른 팀에 아웃소싱했어야 한다. | C. 각 구성요소에 숙련된 자원을 둘 이상 확보했어야 한다. | D. 프로젝트 중 교차 기능 지식 이전을 촉진했어야 한다. |  | D | 아픈 팀원이 해당 구성요소에 대한 유일한 기술자였을 때, PM은 프로젝트 중 교차 기능 지식 이전을 촉진했어야 한다. 지식 공유는 단일 장애점을 방지한다. 견고한 문서화 요청(A)은 부분적이다. 아웃소싱(B)은 비용이 많이 들고 비효율적이다. 다중 자원 확보(C)는 이상적이나 현실적이지 않을 수 있다.
1114 | An information technology project manager works at an insurance company and is assigned to an infrastructure upgrade project. During the execution phase, a stakeholder approaches the project manager and informs them that a deliverable is not meeting the quality requirements. What should the project manager do first? | Ask the project sponsor for additional funding for improved quality outcomes. | Acknowledge the stakeholder ' s concerns and work to correct the deliverable. | Update the risk register with information on the noncompliant deliverable. | Compare the stakeholder ' s assertion to the metrics in the quality report. |  | D | When a stakeholder reports a deliverable is not meeting quality requirements during execution, the project manager should first compare the stakeholder's assertion to the metrics in the quality report. Evidence-based verification ensures accurate assessment. Asking for additional funding (A) assumes a problem without verification. Acknowledging and correcting (B) acts before confirming. Updating the risk register (C) treats it as a risk rather than a quality check. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | IT 프로젝트 관리자가 보험 회사에서 인프라 업그레이드 프로젝트에 배정되었다. 실행 단계에서 이해관계자가 산출물이 품질 요구사항을 충족하지 못한다고 접근한다. PM은 무엇을 해야 하는가? | A. 프로젝트 스폰서에게 품질 개선을 위한 추가 자금을 요청한다. | B. 이해관계자의 우려를 인정하고 산출물을 수정하기 위해 작업한다. | C. 비준수 산출물에 대한 정보로 리스크 레지스터를 업데이트한다. | D. 이해관계자의 주장을 품질 보고서의 메트릭과 비교한다. |  | D | 이해관계자가 실행 중 산출물이 품질 요구사항을 충족하지 못한다고 보고할 때, PM은 먼저 이해관계자의 주장을 품질 보고서의 메트릭과 비교해야 한다. 증거 기반 검증이 정확한 평가를 보장한다. 추가 자금 요청(A)은 결함이 있다고 가정한다. 즉시 수정(B)은 검증 없이 진행한다. 리스크 레지스터 업데이트(C)는 이슈를 확인한 후에 한다.
1115 | A client from the travel and hospitality industry is building software for an ongoing project. The project sponsor and key project stakeholders ask to add four new functionalities to the upcoming sprint. What should the product owner do next? | Request a change control to expand the scope with the new tasks. | Ask the team to start implementing the new tasks. | Prioritize the new tasks in the planning of the upcoming sprint. | Add the new tasks to the current sprint backlog. |  | C | When the sponsor and key stakeholders want four new functionalities added to the upcoming sprint, the product owner should prioritize the new tasks in the planning of the upcoming sprint. New work should enter through backlog prioritization, not mid-sprint. Requesting change control (A) uses a predictive approach. Asking the team to start implementing (B) bypasses sprint planning. Adding to the current sprint backlog (D) disrupts the ongoing sprint. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 여행 및 숙박 산업의 고객이 진행 중인 프로젝트를 위한 소프트웨어를 구축하고 있다. 스폰서와 핵심 이해관계자가 다가오는 스프린트에 네 가지 새로운 기능을 추가하도록 요청한다. PM은 무엇을 해야 하는가? | A. 새 작업으로 범위를 확장하기 위한 변경 통제를 요청한다. | B. 팀에게 새 작업 구현을 시작하라고 요청한다. | C. 다가오는 스프린트 계획에서 새 작업의 우선순위를 정한다. | D. 현재 스프린트 백로그에 새 작업을 추가한다. |  | C | 스폰서와 핵심 이해관계자가 다가오는 스프린트에 네 가지 새 기능을 추가하길 원할 때, 제품 책임자가 다가오는 스프린트 계획에서 새 작업의 우선순위를 정해야 한다. 새 작업은 백로그 우선순위화를 통해 들어와야 하며 스프린트 중간에 넣지 않는다. 변경 통제 요청(A)은 예측적 접근법이다. 즉시 구현(B)은 우선순위를 건너뛴다. 현재 백로그에 추가(D)는 진행 중인 스프린트를 방해한다.
1116 | A project manager agreed to a team member's request to have an alternative working schedule whereby they begin working at 12:00 p.m. each day. This arrangement has worked well for the project, but has recently been scrutinized by members from other project teams because the company's core working hours begin at 9:00 a.m. What should the project manager have done to prevent this situation? | Managed and rectified the ground rule violations | Analyzed the boundaries of the negotiations for agreement | Broken down the situation to identify the root cause | Determined communication methods and channels |  | B | When an alternative working schedule arrangement is scrutinized by other teams because it deviates from core hours policy, the project manager should have analyzed the boundaries of the negotiations for agreement. Understanding organizational constraints before agreeing prevents conflicts. Managing ground rule violations (A) applies rules after the fact. Breaking down the root cause (C) is retrospective. Determining communication methods (D) does not address the scheduling issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 관리자가 팀원의 요청에 따라 매일 오후 12시에 시작하는 대체 근무 일정에 동의했다. 이 배치는 프로젝트에 잘 작동했으나, 핵심 업무 시간 정책에서 벗어나 다른 팀의 조사를 받았다. PM이 했어야 할 것은? | A. 기본 규칙 위반을 관리하고 시정했어야 한다. | B. 합의를 위한 협상의 경계를 분석했어야 한다. | C. 상황을 분해하여 근본 원인을 식별했어야 한다. | D. 커뮤니케이션 방법과 채널을 결정했어야 한다. |  | B | 대체 근무 일정이 핵심 업무 시간 정책에서 벗어나 다른 팀의 조사를 받을 때, PM은 합의를 위한 협상의 경계를 분석했어야 한다. 동의 전 조직적 제약을 이해하면 갈등을 방지한다. 기본 규칙 위반 관리(A)는 반응적이다. 근본 원인 식별(C)은 이미 원인이 알려져 있다. 커뮤니케이션 방법 결정(D)은 관련이 없다.
1117 | A project manager is hired by a global company. The project manager is an agile specialist and is tasked with supporting the project team to reduce rework and dissatisfaction. How should the project manager address these objectives? | Deliver a schedule with the portfolio timeline and delivery to the customer. | Decrease the scope of the portfolio and send new solutions to the customer. | Prepare deliveries with more details to satisfy the customer. | Adopt an incremental cycle of delivering value to the customer. |  | D | When tasked with reducing rework and customer dissatisfaction as an agile specialist in a global company, the project manager should adopt an incremental cycle of delivering value to the customer. Incremental delivery enables continuous feedback and adaptation. Delivering a schedule with portfolio timelines (A) follows a predictive approach. Decreasing scope (B) is reactive. Preparing deliveries with more detail (C) focuses on documentation over working products. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 프로젝트 관리자가 글로벌 회사에 고용되었다. PM은 애자일 전문가이며 재작업과 불만족을 줄이기 위해 프로젝트 팀을 지원하는 임무를 받았다. PM은 어떻게 해야 하는가? | A. 포트폴리오 일정과 고객 전달 일정을 제공한다. | B. 포트폴리오 범위를 줄이고 고객에게 새 솔루션을 보낸다. | C. 고객을 만족시키기 위해 더 상세한 전달물을 준비한다. | D. 고객에게 가치를 전달하는 점진적 사이클을 채택한다. |  | D | 애자일 전문가로서 재작업과 고객 불만족을 줄이는 임무를 받았을 때, PM은 고객에게 가치를 전달하는 점진적 사이클을 채택해야 한다. 점진적 전달은 지속적 피드백과 적응을 가능하게 한다. 포트폴리오 일정 제공(A)은 전략적이지 전술적이 아니다. 범위 축소(B)는 가치를 줄인다. 더 상세한 전달물(C)은 재작업의 근본 원인을 해결하지 않는다.
1118 | During the daily meetings with the team, the project manager notices that a new team member is not making the expected progress on an assigned task. What should the project manager do? | Ask an experienced team member to coach the new team member | Ask the new team member to follow the team ground rules. | Ask the new team member to reassess their own capabilities | Ask an experienced team member to identify a replacement |  | A | When a new team member is not making expected progress on an assigned task, the project manager should ask an experienced team member to coach them. Coaching leverages existing team expertise, fosters collaboration, and develops the new member's skills in context. Asking them to follow ground rules (B) does not address the specific task challenge. Asking them to reassess capabilities (C) provides no support. Asking someone to identify a replacement (D) is premature and demoralizing. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 일일 회의에서 프로젝트 관리자가 새 팀원이 배정된 작업에서 예상된 진행을 하지 못하고 있음을 발견한다. PM은 무엇을 해야 하는가? | A. 경험 많은 팀원에게 새 팀원을 코칭하도록 요청한다. | B. 새 팀원에게 팀 기본 규칙을 따르라고 요청한다. | C. 새 팀원에게 자신의 역량을 재평가하라고 요청한다. | D. 경험 많은 팀원에게 대체자를 식별하라고 요청한다. |  | A | 새 팀원이 배정된 작업에서 예상된 진행을 하지 못할 때, PM은 경험 많은 팀원에게 코칭을 요청해야 한다. 코칭은 기존 팀 전문성을 활용하고 협력을 촉진하며 맥락에서 새 팀원의 기술을 개발한다. 기본 규칙 따르기(B)는 성과 문제를 해결하지 않는다. 역량 재평가(C)는 사기를 저하시킨다. 대체자 식별(D)은 과도하다.
1119 | A project manager is assigned to develop a wire bending machine midway through the design phase. The project manager discovered that the team did not have any test cases or acceptance criteria for the equipment. The project manager started communication with the team to move the project forward. What should the project manager do first at this point? | Meet with the quality planning manager to identify the reason why the quality plan was not created yet | Meet with the hardware design engineers to identify the minimum performance required to establish a market for the machine | Meet with the key stakeholders to identify the proper product concept for the development team | Meet with the sales and marketing teams to identify the requirements that were collected during the interview sessions with potential customers |  | D | When a project manager discovers the team has no test cases or acceptance criteria mid-design phase, they should first meet with the sales and marketing teams to identify requirements collected during customer interview sessions. Understanding customer needs provides the foundation for developing test cases and acceptance criteria. Meeting with the quality planning manager (A) investigates the gap but does not gather requirements. Meeting with hardware engineers for minimum performance (B) is premature without customer requirements. Meeting with key stakeholders for the product concept (C) is higher-level than needed. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | 프로젝트 관리자가 설계 단계 중간에 와이어 벤딩 머신 개발 프로젝트에 배정되었다. 팀에게 테스트 케이스나 인수 기준이 없음을 발견했다. PM은 무엇을 해야 하는가? | A. 품질 계획 관리자와 만나 품질 계획이 아직 만들어지지 않은 이유를 확인한다. | B. 하드웨어 설계 엔지니어와 만나 시장 확보를 위한 최소 성능을 식별한다. | C. 핵심 이해관계자와 만나 개발팀을 위한 적절한 제품 개념을 식별한다. | D. 영업 및 마케팅 팀과 만나 고객 인터뷰 세션에서 수집된 요구사항을 식별한다. |  | D | PM이 설계 단계 중간에 팀에게 테스트 케이스나 인수 기준이 없음을 발견했을 때, 영업 및 마케팅 팀과 만나 고객 인터뷰에서 수집된 요구사항을 식별해야 한다. 고객 요구 이해가 테스트 케이스와 인수 기준 개발의 기초를 제공한다. 품질 관리자 회의(A)는 책임 추궁이지 해결이 아니다. 최소 성능(B)은 부분적이다. 제품 개념(C)은 상위 수준이며 구체적 기준을 제공하지 않는다.
1120 | During the execution phase of a large project, there is an extremely high number of change requests. Because of this, the project manager realizes that there is a greater risk for rejection of the deliverables. How should the project manager mitigate this risk without compromising the completion date? | Review the integrated change control process to restrict the number of changes | Restart the stakeholder engagement process by collecting user requirements again | Focus on delivering incremental value through multiple smaller deliveries | Request sponsor support to get buy-in from the users and stakeholders |  | C | When an extremely high number of change requests during execution creates risk of deliverable rejection, the project manager should focus on delivering incremental value through multiple smaller deliveries. Frequent delivery enables continuous feedback and reduces rejection risk. Reviewing integrated change control to restrict changes (A) may miss valid needs. Restarting stakeholder engagement (B) delays progress. Requesting sponsor support for buy-in (D) does not address the delivery approach. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 대규모 프로젝트의 실행 단계에서 변경 요청이 극히 많다. 이로 인해 PM은 산출물 거부의 리스크가 더 크다는 것을 인식한다. PM은 무엇을 해야 하는가? | A. 통합 변경 통제 프로세스를 검토하여 변경 수를 제한한다. | B. 사용자 요구사항을 다시 수집하여 이해관계자 참여 프로세스를 재시작한다. | C. 여러 번의 작은 전달을 통해 점진적 가치 제공에 집중한다. | D. 사용자와 이해관계자의 동의를 얻기 위해 스폰서 지원을 요청한다. |  | C | 실행 중 극히 많은 변경 요청이 산출물 거부 리스크를 만들 때, PM은 여러 번의 작은 전달을 통해 점진적 가치 제공에 집중해야 한다. 빈번한 전달이 지속적 피드백을 가능하게 하고 거부 리스크를 줄인다. 변경 통제 검토(A)는 변경을 제한하지만 근본 원인을 해결하지 않는다. 요구사항 재수집(B)은 시간이 많이 들고 비효율적이다. 스폰서 지원(D)은 보조적이다.
1121 | After a project has been approved, a key stakeholder tells the project manager that the current project management strategy is not well defined. The project manager is also informed that the key stakeholder does not want to hold a working session. What should the project manager do first? | Ask the project sponsor to exert authority on the key stakeholder in order to maintain the approved timeline | Invite the key stakeholder to the project ' s change control board (CCB) to discuss adjustment of the project strategy | Proceed with a working session for teams that do not belong to that key stakeholder | Share the project documents and invite the key stakeholder to discuss any concerns |  | D | When a key stakeholder says the project strategy is not well defined but refuses a working session, the project manager should share project documents and invite the stakeholder to discuss any concerns. Open communication addresses dissatisfaction collaboratively. Asking the sponsor to exert authority (A) is confrontational. Proceeding with a session excluding the stakeholder (C) ignores their input. Inviting them to the CCB (B) is premature without understanding their concerns. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Focus on Value | Identify Stakeholders | Traditional PM | 프로젝트가 승인된 후, 핵심 이해관계자가 현재 프로젝트 관리 전략이 잘 정의되지 않았다고 말한다. PM은 또한 핵심 이해관계자가 작업 세션을 거부했다는 통보를 받는다. PM은 무엇을 해야 하는가? | A. 프로젝트 스폰서에게 승인된 일정을 유지하기 위해 핵심 이해관계자에 대한 권한을 행사하도록 요청한다. | B. 핵심 이해관계자를 프로젝트 변경통제위원회(CCB)에 초대하여 프로젝트 전략 조정을 논의한다. | C. 핵심 이해관계자에게 속하지 않는 팀들과 작업 세션을 진행한다. | D. 프로젝트 문서를 공유하고 핵심 이해관계자를 초대하여 우려사항을 논의한다. |  | D | 핵심 이해관계자가 프로젝트 전략이 잘 정의되지 않았다고 하면서 작업 세션을 거부할 때, PM은 프로젝트 문서를 공유하고 이해관계자를 초대하여 우려사항을 논의해야 한다. 개방적 커뮤니케이션이 불만을 협력적으로 해결한다. 스폰서 권한 행사(A)는 관계를 손상시킨다. CCB 초대(B)는 변경 통제용이지 전략 논의용이 아니다. 해당 팀 없이 진행(C)은 이해관계자를 무시한다.
1122 | An increment was delivered to the customer at the end of a sprint. The customer complains that the product does not meet the expected quality and will require some rework. What should the project manager do next? | Review the evidence of the quality assurance (QA) activities performed. | Include time in the next increment for quality assurance (QA) inspections. | Perform an analysis of the impact caused by the required rework. | Confirm with the customer the expected quality in the next increment. |  | A | When a customer complains that a delivered increment does not meet expected quality, the project manager should first review the evidence of QA activities performed. This determines whether the team followed agreed quality practices, met the Definition of Done, and executed required tests—identifying the root cause of the quality failure. Including time for QA inspections next increment (B) assumes more inspection is the solution without understanding the cause. Performing impact analysis (C) is important but premature without understanding why quality failed. Confirming expected quality with the customer (D) may be needed later but the immediate action is internal QA review. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 스프린트 말에 증분이 고객에게 전달되었다. 고객이 제품이 예상 품질을 충족하지 못하며 재작업이 필요하다고 불만을 제기한다. PM은 무엇을 해야 하는가? | A. 수행된 품질 보증(QA) 활동의 증거를 검토한다. | B. 다음 증분에 QA 검사를 위한 시간을 포함한다. | C. 필요한 재작업으로 인한 영향 분석을 수행한다. | D. 고객에게 다음 증분에서 예상되는 품질을 확인한다. |  | A | 고객이 전달된 증분이 예상 품질을 충족하지 못한다고 불만을 제기할 때, PM은 먼저 수행된 QA 활동의 증거를 검토해야 한다. 이는 팀이 합의된 품질 관행을 따랐는지, 완료 정의를 충족했는지, 필요한 테스트를 수행했는지 결정한다. QA 시간 포함(B)은 다음 증분에 대한 것이지 현재 이슈를 해결하지 않는다. 영향 분석(C)은 두 번째 단계이다. 품질 확인(D)은 현재 문제를 먼저 해결하지 않는다.
1123 | Vendor A submitted a bid for US$500,000. There is a 65% probability that the vendor will deliver behind schedule with a cost overrun of US$100,000. The vendor will come in ahead of schedule for a savings of US$50,000. What should the project manager determine as the value of the vendor's bid? | 547500 | 650000 | 452500 | 582500 |  | A | The vendor bid value is calculated using expected monetary value (EMV). EMV = (0.65 × $100,000 overrun) − (0.35 × $50,000 savings) = $65,000 − $17,500 = $47,500 risk cost. Value = $500,000 + $47,500 = $547,500. Option B ($650,000) and D ($582,500) use incorrect calculations. Option C ($452,500) subtracts incorrectly. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 벤더 A가 US$500,000 입찰을 제출했다. 일정 지연으로 US$100,000 비용 초과가 발생할 확률이 65%이다. 일정보다 앞서 US$50,000 절감을 가져올 확률이 35%이다. 벤더의 입찰 가치는? | A. 547,500 | B. 650,000 | C. 452,500 | D. 582,500 |  | A | 벤더 입찰 가치는 기대 화폐 가치(EMV)를 사용하여 계산된다. EMV = (0.65 × $100,000 초과) − (0.35 × $50,000 절감) = $65,000 − $17,500 = $47,500 리스크 비용. 가치 = $500,000 + $47,500 = $547,500. B($650,000)와 D($582,500)는 잘못된 계산을 사용한다. C($452,500)는 리스크 비용을 더하지 않고 뺀다.
1124 | A project manager is in the middle of an agile project comprised of 100 user stories broken down into five iterations. Each user story is worth US$50. The actual expenditure is US$2,000 and 50 user stories have been delivered. Which statement is true? | The project is on budget and on schedule. | The project is under budget and on schedule. | The project is under budget and behind schedule. | The project is over budget and behind schedule |  | B | With 100 user stories at $50 each, the BAC is $5,000. At the current point: PV = ($5,000 ÷ 100) × 40 planned stories = $2,000; EV = ($5,000 ÷ 100) × 50 delivered stories = $2,500; AC = $2,000. Cost variance = EV − AC = $500 (under budget); CPI = $2,500 ÷ $2,000 = 1.25. Schedule variance = EV − PV = $500 (ahead of schedule); SPI = $2,500 ÷ $2,000 = 1.25. The project is under budget and on schedule (actually ahead of schedule). On budget and on schedule (A) understates performance. Under budget and behind schedule (C) is incorrect. Over budget and behind schedule (D) is incorrect. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 프로젝트 관리자가 100개 사용자 스토리로 구성된 애자일 프로젝트를 진행 중이며 5개 이터레이션으로 나뉜다. 각 사용자 스토리의 가치는 US$50이다. 실제 지출은 US$2,000이고 50개 사용자 스토리가 전달되었다. 40개 사용자 스토리가 완료 예정이었다. 프로젝트 상태는? | A. 프로젝트가 예산에 맞고 일정에 맞다. | B. 프로젝트가 예산 이하이고 일정에 맞다. | C. 프로젝트가 예산 이하이고 일정이 지연되었다. | D. 프로젝트가 예산 초과이고 일정이 지연되었다. |  | B | 100개 사용자 스토리 × $50 = BAC $5,000. 현 시점: PV = ($5,000 ÷ 100) × 40 계획 스토리 = $2,000; EV = ($5,000 ÷ 100) × 50 전달 스토리 = $2,500; AC = $2,000. 비용 차이 = EV − AC = $500 (예산 이하); CPI = 1.25. 일정 차이 = EV − PV = $500 (일정 앞서감); SPI = 1.25. 프로젝트는 예산 이하이고 일정보다 앞서 있다(B).
1125 | In the middle of an iteration, an agile team working on the development of a new product was notified that an important team member will leave the project for a few weeks due to some urgent personal issues. What should the project manager do regarding the activities that were the responsibility of this team member? | Allow senior management to decide how to proceed with the project. | Convince the team member not to leave until the project is completed. | Reach out to the procurement team to hire a substitute for the team member. | Reach an agreement with the team on how to handle the situation. |  | D | When an important agile team member must leave for a few weeks due to personal issues during an iteration, the project manager should reach an agreement with the team on how to handle the situation. Collaborative team decision-making aligns with agile self-organization. Allowing senior management to decide (A) bypasses the team. Convincing the member to stay (B) is insensitive. Hiring a substitute through procurement (C) may not be necessary or timely. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 이터레이션 중간에 새 제품을 개발하는 애자일 팀이 중요한 팀원이 긴급 개인 사유로 몇 주 동안 프로젝트를 떠날 것이라는 통보를 받았다. PM은 무엇을 해야 하는가? | A. 고위 경영진이 프로젝트 진행 방법을 결정하도록 한다. | B. 프로젝트가 완료될 때까지 떠나지 않도록 팀원을 설득한다. | C. 조달 팀에 연락하여 팀원 대체자를 고용한다. | D. 팀과 상황을 처리하는 방법에 대해 합의에 도달한다. |  | D | 중요한 애자일 팀원이 이터레이션 중 개인 사유로 떠나야 할 때, PM은 팀과 상황 처리 방법에 대해 합의에 도달해야 한다. 협력적 팀 의사결정이 애자일 자기 조직화에 부합한다. 고위 경영진 결정(A)은 팀 자율성을 무시한다. 설득(B)은 비윤리적이며 개인을 존중하지 않는다. 대체자 고용(C)은 몇 주의 부재에 과도하다.
1126 | An organization is transitioning to agile delivery, and a new team has been assembled. A project is not going well because the variation of the team velocity is very high and every sprint delivers less than committed. A new project lead with a strong technical background has been assigned to the project. What should the project lead do? | Recommend a different estimation method in the retrospective. | Ask that estimations be provided only by senior developers. | Allocate more time for estimation in the sprint planning. | Review and update the estimations in the daily standup. |  | A | When an agile team has high velocity variation and consistently delivers less than committed, the new project lead should recommend a different estimation method in the retrospective. The retrospective is the ideal setting for the team to reflect on estimation accuracy, analyze root causes of high variation, and collaboratively adopt improved estimation practices. Asking only senior developers to estimate (B) excludes the team and undermines agile collaboration. Allocating more estimation time in sprint planning (C) does not address the method's accuracy. Reviewing estimations in daily standups (D) is not the appropriate ceremony for estimation process changes. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scaled Agile | Process | Plan and Manage Schedule | Schedule | Planning | Embed Quality | Develop Schedule | Traditional PM | 조직이 애자일 전달로 전환 중이며 새 팀이 구성되었다. 팀 속도의 변동이 매우 높고 매 스프린트마다 약속한 것보다 적게 전달하여 프로젝트가 잘 진행되지 않는다. 새로운 프로젝트 리더는 무엇을 해야 하는가? | A. 회고에서 다른 추정 방법을 권장한다. | B. 시니어 개발자만 추정을 제공하도록 요청한다. | C. 스프린트 계획에서 추정에 더 많은 시간을 할당한다. | D. 일일 스탠드업에서 추정을 검토하고 업데이트한다. |  | A | 애자일 팀의 속도 변동이 높고 지속적으로 약속보다 적게 전달할 때, 회고에서 다른 추정 방법을 권장해야 한다. 회고는 팀이 추정 정확도를 반영하고 높은 변동의 근본 원인을 분석하는 이상적인 장소이다. 시니어만 추정(B)은 팀 참여를 배제한다. 추정 시간 증가(C)는 방법 자체를 개선하지 않는다. 스탠드업에서 업데이트(D)는 스탠드업의 목적에 맞지 않는다.
1127 | During the execution of a construction project, one of the neighboring businesses is complaining that the current building height does not agree with the initial project plans. What should the project manager do first? | Ask the neighbor to leave the site immediately because the site is on private property. | Ask the neighbor to submit a formal complaint about their concerns. | Inform the neighbor that all of the project documentation has been approved. | Inform the neighbor that the complaint will be escalated to the project sponsor. |  | C | When a neighboring business complains that building height does not match initial project plans, the project manager should first inform the neighbor that all project documentation has been approved. Providing factual clarification addresses the concern transparently. Asking the neighbor to leave (A) is confrontational. Requesting a formal complaint (B) adds bureaucracy. Escalating to the sponsor (D) is premature before clarifying the situation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 건설 프로젝트 실행 중 인접 사업체가 현재 건물 높이가 초기 프로젝트 계획과 일치하지 않는다고 불만을 제기한다. PM은 무엇을 해야 하는가? | A. 이웃에게 사유지이므로 즉시 현장을 떠나라고 요청한다. | B. 이웃에게 우려사항에 대한 공식 불만을 제출하라고 요청한다. | C. 이웃에게 모든 프로젝트 문서가 승인되었음을 알린다. | D. 이웃에게 불만이 프로젝트 스폰서에게 에스컬레이션될 것임을 알린다. |  | C | 인접 사업체가 건물 높이가 초기 계획과 맞지 않다고 불만을 제기할 때, PM은 모든 프로젝트 문서가 승인되었음을 알려야 한다. 사실에 기반한 명확한 설명이 우려를 투명하게 해결한다. 떠나라고 요청(A)은 적대적이다. 공식 불만 요청(B)은 불필요하게 확대한다. 스폰서에게 에스컬레이션(D)은 PM이 직접 해결할 수 있는 것을 넘긴다.
1128 | A project manager is leading a highly visible project initiative. A few weeks after kickoff, the project manager starts receiving requests for updates from various stakeholders. What should the project manager do? | Remove those stakeholders from the project since they may negatively affect project goal s | Invite all project stakeholders to join the daily standup meeting to ensure they are informed | Explain to the stakeholders that they must request project updates from the project sponsor | Schedule a meeting with relevant stakeholders to review the project communications plan |  | D | When receiving ad-hoc update requests from various stakeholders shortly after kickoff on a highly visible project, the project manager should schedule a meeting with relevant stakeholders to review the project communications plan. Aligning expectations prevents recurring requests. Removing stakeholders (A) is inappropriate. Inviting all to daily standups (B) disrupts team meetings. Directing stakeholders to the sponsor (C) creates bottlenecks. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 매우 가시적인 프로젝트를 이끌고 있다. 킥오프 몇 주 후 다양한 이해관계자로부터 업데이트 요청을 받기 시작한다. PM은 무엇을 해야 하는가? | A. 프로젝트 목표에 부정적 영향을 미칠 수 있으므로 해당 이해관계자를 제거한다. | B. 모든 프로젝트 이해관계자를 일일 스탠드업 회의에 초대하여 정보를 제공한다. | C. 이해관계자에게 프로젝트 스폰서에게 업데이트를 요청해야 한다고 설명한다. | D. 관련 이해관계자와 회의를 예약하여 프로젝트 커뮤니케이션 계획을 검토한다. |  | D | 가시적 프로젝트에서 킥오프 직후 다양한 이해관계자로부터 임시 업데이트 요청을 받을 때, PM은 관련 이해관계자와 회의를 예약하여 커뮤니케이션 계획을 검토해야 한다. 기대 정렬이 반복적 요청을 방지한다. 이해관계자 제거(A)는 부적절하다. 전원 스탠드업 초대(B)는 비효율적이다. 스폰서에게 돌리기(C)는 책임을 전가한다.
1129 | A newly hired team member just joined the project team and reports directly to the project manager. In the first week, this new member tells the project manager that there is a task priority conflict with hard, dependent tasks on the critical path. What should the project manager do to handle the conflict? | Perform crashing and/or fast tracking of the schedule. | Analyze the project schedule and look for alternatives. | Meet the team member and try to plan a course of action together. | Guide the team member on how to resolve the conflict. |  | C | When a new team member faces a task priority conflict with dependent tasks on the critical path, the project manager should meet the team member and try to plan a course of action together. Collaborative problem-solving fosters trust, considers the member's perspective, and produces better solutions. Crashing or fast tracking (A) may introduce new risks. Analyzing the schedule for alternatives (B) excludes the team member's input. Guiding the member on conflict resolution (D) is directive rather than collaborative. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | Critical Path/Schedule Mgmt | People | Plan and Manage Communication | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새로 고용된 팀원이 프로젝트 팀에 합류하여 PM에게 직접 보고한다. 첫 주에 새 팀원이 PM에게 종속 작업이 주공정선에 있어 작업 우선순위 충돌이 있다고 말한다. PM은 무엇을 해야 하는가? | A. 일정의 공정 압축 및/또는 패스트 트래킹을 수행한다. | B. 프로젝트 일정을 분석하고 대안을 찾는다. | C. 팀원을 만나 함께 행동 방안을 계획한다. | D. 팀원에게 갈등 해결 방법을 안내한다. |  | C | 새 팀원이 주공정선의 종속 작업과 우선순위 충돌에 직면할 때, PM은 팀원을 만나 함께 행동 방안을 계획해야 한다. 협력적 문제 해결이 신뢰를 구축하고 더 나은 솔루션을 만든다. 공정 압축(A)은 과도한 반응이다. 일정 분석(B)은 팀원을 배제한다. 갈등 해결 안내(D)는 이 상황에서 일방적이다.
1130 | At the end of the last iteration, the customer rejects the deliverables since they did not meet the customer's expectations. What should the project manager have done to prevent this situation? | Provided the customer with the backlog and the specified user stories at the beginning of the iteration. | Developed the DoD in close cooperation with all stakeholders to ensure their expectations were included. | Included all relevant criteria in the agreed upon definition of done (DoD), and crafted a shared product vision. | Involved the customer more in the planning process for the project, and ensuredagreement on the proceedings. |  | C | When the customer rejects deliverables at the end of the last iteration for not meeting expectations, the project manager should have included all relevant criteria in the agreed-upon definition of done (DoD) and crafted a shared product vision. Clear DoD and shared vision ensure alignment. Providing the backlog and user stories (A) is informational without quality criteria. Developing the DoD with all stakeholders (B) dilutes customer focus. Involving the customer more in planning (D) is helpful but not as specific as defining clear DoD. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 마지막 이터레이션 말에 고객이 기대를 충족하지 못해 산출물을 거부했다. PM이 이 상황을 방지하기 위해 했어야 할 것은? | A. 이터레이션 시작 시 고객에게 백로그와 명시된 사용자 스토리를 제공했어야 한다. | B. 모든 이해관계자와 긴밀히 협력하여 DoD를 개발하여 기대가 포함되도록 했어야 한다. | C. 합의된 완료 정의(DoD)에 모든 관련 기준을 포함하고 공유된 제품 비전을 수립했어야 한다. | D. 고객을 프로젝트 계획 프로세스에 더 많이 참여시키고 절차에 대한 합의를 확보했어야 한다. |  | C | 고객이 마지막 이터레이션 말에 기대 미충족으로 산출물을 거부했을 때, PM은 합의된 DoD에 모든 관련 기준을 포함하고 공유된 제품 비전을 수립했어야 한다. 명확한 DoD와 공유 비전이 정렬을 보장한다. 백로그 제공(A)은 정렬을 보장하지 않는다. 이해관계자와 DoD 개발(B)은 좋지만 공유 비전이 없다. 계획 참여(D)는 기준이 아닌 프로세스에 초점을 맞춘다.
1131 | A project manager is preparing a project closure report. The project sponsor is confident about the success of the project, but the client is not sure that the project outputs will achieve their business needs. Which aspect should the project manager highlight in the closure report to address the stakeholder's concern? | How the quality was managed | How the acceptance criteria were met | How the stakeholders were managed | How the scope was managed |  | B | When the client doubts whether project outputs will achieve business needs, the project manager should highlight in the closure report how the acceptance criteria were met. Acceptance criteria directly measure whether deliverables satisfy stakeholder requirements. How quality was managed (A) addresses process, not outcome verification. How stakeholders were managed (C) covers engagement. How scope was managed (D) covers control but not business value confirmation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | PM이 프로젝트 종료 보고서를 준비하고 있다. 스폰서는 프로젝트 성공을 확신하지만, 고객은 프로젝트 산출물이 비즈니스 요구를 달성할지 확신하지 못한다. 종료 보고서에서 강조해야 할 것은? | A. 품질이 어떻게 관리되었는지 | B. 인수 기준이 어떻게 충족되었는지 | C. 이해관계자가 어떻게 관리되었는지 | D. 범위가 어떻게 관리되었는지 |  | B | 고객이 프로젝트 산출물이 비즈니스 요구를 달성할지 의구심을 가질 때, PM은 종료 보고서에서 인수 기준이 어떻게 충족되었는지 강조해야 한다. 인수 기준이 산출물이 이해관계자 요구사항을 충족하는지 직접 측정한다. 품질 관리 방법(A)은 프로세스를 다루지 결과를 다루지 않는다. 이해관계자 관리(C)는 참여를 다루지 산출물을 다루지 않는다. 범위 관리(D)는 전달을 다루지 가치를 다루지 않는다.
1132 | During a project review meeting, several project team members expressed that they did not have an understanding of the benefits of certain features for the project. What should the project manager do next? | Confirm ownership for ongoing value realization | Appraise the stakeholders of value gain progress | Review the project scope statement | Escalate the issue to the project sponsor |  | A | When project team members do not understand the benefits of certain features, the project manager should confirm ownership for ongoing value realization. This ensures the team understands not only what they are building but why—how each feature contributes to the project's business value and how benefits will be measured and sustained after delivery. Appraising stakeholders of value progress (B) communicates externally but does not address the team's internal understanding gap. Reviewing the project scope statement (C) provides scope details but may not explain benefits clearly. Escalating to the project sponsor (D) delegates a responsibility the PM should handle directly. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Agile General Practices | Process | Manage Project Closure | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트 검토 회의에서 여러 팀원이 프로젝트의 특정 기능의 이점을 이해하지 못한다고 표현했다. PM은 무엇을 해야 하는가? | A. 지속적 가치 실현을 위한 소유권을 확인한다. | B. 이해관계자에게 가치 획득 진행 상황을 평가한다. | C. 프로젝트 범위 기술서를 검토한다. | D. 이슈를 프로젝트 스폰서에게 에스컬레이션한다. |  | A | 팀원들이 특정 기능의 이점을 이해하지 못할 때, PM은 지속적 가치 실현을 위한 소유권을 확인해야 한다. 이는 팀이 무엇을 만드는지뿐만 아니라 왜 만드는지—각 기능이 비즈니스 가치에 어떻게 기여하는지 이해하도록 한다. 가치 진행 평가(B)는 이해관계자용이지 팀 이해용이 아니다. 범위 기술서(C)는 무엇을 만드는지는 다루지만 왜 만드는지는 다루지 않는다. 에스컬레이션(D)은 불필요하다.
1133 | A project manager must manage a virtual application control software team that is culturally and geographically diverse. The project manager wants to promote open collaboration in a real-time manner. What should the project manager do? | Document all information on the team wiki. | Facilitate regular conference calls. | Promote the use of remote site syndication. 1216 | Provide a software for instant messaging. |  | D | When managing a culturally and geographically diverse virtual team and wanting to promote real-time open collaboration, the project manager should provide instant messaging software. IM enables real-time, informal communication across time zones. Documenting on a team wiki (A) is asynchronous. Regular conference calls (B) are scheduled, not always real-time. Remote site syndication (C) is a content distribution method, not collaboration. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 문화적·지리적으로 다양한 가상 소프트웨어 통제 팀을 관리해야 한다. PM은 실시간으로 개방적 협업을 촉진하고 싶다. 어떤 도구를 사용해야 하는가? | A. 팀 위키에 모든 정보를 문서화한다. | B. 정기적 전화 회의를 촉진한다. | C. 원격 사이트 신디케이션 사용을 촉진한다. | D. 인스턴트 메시징 소프트웨어를 제공한다. |  | D | 문화적·지리적으로 다양한 가상 팀을 관리하며 실시간 개방적 협업을 촉진하고 싶을 때, PM은 인스턴트 메시징 소프트웨어를 제공해야 한다. IM은 시간대를 넘어 실시간, 비공식적 커뮤니케이션을 가능하게 한다. 위키 문서화(A)는 비동기적이다. 정기 전화(B)는 시간대 차이로 어렵다. 원격 사이트 신디케이션(C)은 정보 배포이지 상호작용이 아니다.
1134 | A global petroleum crisis has affected the distribution of crude oil in the region where the construction project is underway. Materials are not being delivered on time and this phase of construction is already behind what was initially planned. What should the project manager do first to prevent the project from going further off track? | Establish new partnerships with other suppliers in anticipation of any delays. | Propose a pause in this phase to save labor costs and asset depreciation. | Perform a risk assessment and define a risk response action plan. | Proceed with the project using management reserves to cover any delays or losses. |  | C | When a global petroleum crisis delays material delivery and the construction phase is behind schedule, the project manager should first perform a risk assessment and define a risk response action plan. Systematic risk evaluation identifies impacts and enables targeted responses. Establishing new supplier partnerships (A) is a response without assessment. Proposing a pause (B) may not be justified. Using management reserves (D) is premature before understanding the risk scope. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 글로벌 석유 위기가 건설 프로젝트가 진행 중인 지역의 원유 배급에 영향을 미쳤다. 자재가 제때 배달되지 않으며 이 건설 단계가 일정보다 지연되었다. PM은 무엇을 해야 하는가? | A. 지연에 대비하여 다른 공급업체와 새로운 파트너십을 구축한다. | B. 노동 비용과 자산 감가상각을 절감하기 위해 이 단계의 일시 중단을 제안한다. | C. 리스크 평가를 수행하고 리스크 대응 행동 계획을 정의한다. | D. 관리 예비비를 사용하여 지연이나 손실을 충당하며 프로젝트를 진행한다. |  | C | 글로벌 석유 위기로 자재 배달이 지연되고 건설 단계가 뒤처질 때, PM은 먼저 리스크 평가를 수행하고 리스크 대응 행동 계획을 정의해야 한다. 체계적 리스크 평가가 영향을 식별하고 목표 대응을 가능하게 한다. 새 파트너십(A)은 평가 전 성급하다. 일시 중단(B)은 극단적이다. 관리 예비비 사용(D)은 적절한 평가 없이 진행하는 것이다.
1135 | A project manager is establishing a project management office (PMO) for a company-wide program to implement a software based on artificial intelligence (AI). As part of the PMO tasks, some stakeholders need help understanding how to deal with difficult situations. Which activity should the project manager use to help train the stakeholders? | Mentoring and coaching | Team assessment | On-the-job training | Contract negotiation |  | A | When establishing a PMO and stakeholders need help dealing with difficult situations, the project manager should use mentoring and coaching. These techniques provide personalized guidance, feedback, and support to help stakeholders improve skills and overcome challenges. Team assessment (B) evaluates performance but does not train. On-the-job training (C) develops operational skills but is not specific to difficult situation management. Contract negotiation (D) is a procurement activity, not a training tool. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PM이 AI 기반 소프트웨어를 구현하는 회사 전체 프로그램을 위한 PMO를 설립하고 있다. PMO 업무의 일환으로 일부 이해관계자가 어려운 상황 대처에 도움이 필요하다. PM이 사용해야 할 것은? | A. 멘토링과 코칭 | B. 팀 평가 | C. 현장 실습(OJT) | D. 계약 협상 |  | A | PMO를 설립하고 이해관계자가 어려운 상황 대처에 도움이 필요할 때, PM은 멘토링과 코칭을 사용해야 한다. 이 기법은 이해관계자가 기술을 개선하고 도전을 극복하도록 개인화된 지침, 피드백, 지원을 제공한다. 팀 평가(B)는 기술을 평가하지 지원하지 않는다. OJT(C)는 기술 교육이지 상황 대처가 아니다. 계약 협상(D)은 무관하다.
1136 | During project execution, the project manager notices that the work performance reports have deteriorated drastically in less than two weeks. The project team in country A is complaining about delays resulting from holidays occurring in country B that have impacted their project team. How should the project manager handle this situation? | Implement crashing to compress the schedule and improve the schedule performance index (SRI). | Review the risk management plan to evaluate the probability and impact of these delays | Perform conflict management using the project ' s resource management plan. | Implement fast-tracking to compress the schedule and improve the SPI |  | B | The project manager should review the risk management plan to evaluate the probability and impact of delays caused by holidays in country B. The risk management plan provides the framework for identifying, analyzing, and responding to project risks—including cross-cultural and scheduling factors inherent in multinational projects. By reviewing it, the PM can assess how these delays affect project objectives and select appropriate response strategies such as avoidance, mitigation, or acceptance. Implementing crashing (A) or fast-tracking (D) are schedule compression techniques that may increase costs, risks, or rework and do not address the root cause of the delays. Conflict management (C) is relevant for interpersonal disagreements but is not effective when the delays are caused by external factors like national holidays beyond the team's control. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 프로젝트 실행 중 PM이 업무 성과 보고서가 2주 이내에 급격히 악화된 것을 발견한다. 국가 A의 팀이 국가 B의 팀이 현지 공휴일로 일정보다 뒤처져 있어 지연에 대해 불만을 제기한다. PM은 무엇을 해야 하는가? | A. 일정을 압축하고 SPI를 개선하기 위해 공정 압축을 실행한다. | B. 리스크 관리 계획을 검토하여 이러한 지연의 확률과 영향을 평가한다. | C. 프로젝트 자원 관리 계획을 사용하여 갈등 관리를 수행한다. | D. 일정을 압축하고 SPI를 개선하기 위해 패스트 트래킹을 실행한다. |  | B | 국가 B의 공휴일로 인한 지연이 성과 보고서를 악화시킬 때, PM은 리스크 관리 계획을 검토하여 지연의 확률과 영향을 평가해야 한다. 리스크 관리 계획은 문화적·일정적 요인을 포함한 리스크를 식별, 분석, 대응하는 프레임워크를 제공한다. 공정 압축(A)은 비용이 증가한다. 갈등 관리(C)는 팀 간 갈등이지 일정 리스크가 아니다. 패스트 트래킹(D)은 리스크를 증가시킨다.
1137 | During the execution of a project within an operations function, the project manager encounters scope changes and a delay in the delivery of critical tasks. How should the project manager address this situation? | Initiate the change request to modify the scope and adjust the timelines | Call for a team meeting to decide if the changes should be included | Conduct an impact analysis and present the results to the steering committee for approval | Communicate the concerns to the project management office (PMO) during the weekly project reports |  | A | When encountering scope changes and delivery delays during execution within an operations function, the project manager should initiate a change request to modify scope and adjust timelines. Formal change control ensures governed approval. Calling a team meeting to decide (B) bypasses change management authority. Conducting impact analysis for the steering committee (C) is a step within the change request process. Communicating to the PMO in weekly reports (D) is passive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | Baseline & Change Control | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 운영 기능 내 프로젝트 실행 중 PM이 범위 변경과 핵심 작업 전달 지연에 직면한다. PM은 이를 어떻게 해결해야 하는가? | A. 범위를 수정하고 일정을 조정하기 위한 변경 요청을 시작한다. | B. 변경 포함 여부를 결정하기 위해 팀 회의를 소집한다. | C. 영향 분석을 수행하고 결과를 운영 위원회에 승인을 위해 제출한다. | D. 주간 프로젝트 보고서에서 PMO에 우려사항을 전달한다. |  | A | 운영 기능 내 실행 중 범위 변경과 전달 지연에 직면할 때, PM은 범위를 수정하고 일정을 조정하기 위한 변경 요청을 시작해야 한다. 공식 변경 통제가 거버넌스 승인을 보장한다. 팀 회의 소집(B)은 변경 관리 프로세스를 우회한다. 운영 위원회에 제출(C)은 공식 변경 요청 없이 적절하지 않다. PMO에 전달(D)은 수동적이다.
1138 | A company has decided to create a new product to prepare itself for the changing economy. The technology required for the new product is not well understood yet, and the requirements are still being debated. Which approach should the project manager advise for this project? | Hybrid | Lean | Agile | Predictive |  | C | The correct answer is C. Agile. Selecting the appropriate delivery approach requires evaluating project characteristics, team capabilities, and organizational context. The PM should tailor the methodology to best serve the project's needs. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 회사가 변화하는 경제에 대비하여 새 제품을 만들기로 했다. 새 제품에 필요한 기술이 아직 잘 이해되지 않았고, 요구사항이 아직 정의 중이다. 가장 적합한 전달 접근법은? | A. 하이브리드 | B. 린 | C. 애자일 | D. 예측적 |  | C | 정답은 C이다. 애자일. 기술이 잘 이해되지 않고 요구사항이 아직 정의 중일 때, 애자일 접근법이 가장 적합하다. 애자일은 불확실성과 변화에 대한 적응력을 제공한다. 하이브리드(A)는 일부 예측적 요소를 포함하여 높은 불확실성에 덜 적합하다. 린(B)은 낭비 제거에 초점이지 제품 개발 방법론이 아니다. 예측적(D)은 명확한 요구사항이 필요하다.
1139 | A project manager realizes that the team members are new to the hybrid approach and do not value standup meetings. Team members often arrive late, digress into solutioning, or skip the meetings altogether. How should the project manager improve this situation with the project team? | Engage the project team In implementing and Improving key aspects of the standup meetings. | Ask the product owner to remove team members who do not comply with standup meeting rules. 1250 | Send a daily retrospective report to all team members instead of holding standup meetings. | Include a daily brainstorming session In the standup meetings to resolve pending Issues. |  | A | When team members do not value standup meetings, arrive late, digress, or skip them, the project manager should engage the team in implementing and improving key aspects of standups. Participatory improvement builds buy-in. Removing non-compliant members (B) is extreme. Sending retrospective reports instead (C) eliminates the standup's purpose. Adding brainstorming sessions (D) increases meeting scope. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | PM이 팀원들이 하이브리드 접근법에 익숙하지 않고 스탠드업 회의를 가치 있게 여기지 않음을 인식한다. 팀원들은 종종 늦게 도착하거나, 해결 방안 논의로 빠지거나, 회의를 건너뛴다. PM은 무엇을 해야 하는가? | A. 프로젝트 팀이 스탠드업 회의의 핵심 측면을 구현하고 개선하는 데 참여시킨다. | B. 제품 책임자에게 스탠드업 회의 규칙을 준수하지 않는 팀원을 제거하라고 요청한다. | C. 스탠드업 회의 대신 모든 팀원에게 일일 회고 보고서를 보낸다. | D. 스탠드업 회의에 미해결 이슈를 해결하기 위한 일일 브레인스토밍 세션을 포함한다. |  | A | 팀원들이 스탠드업 회의를 가치 있게 여기지 않고, 늦게 오거나, 주제에서 벗어나거나, 건너뛸 때, PM은 팀이 스탠드업의 핵심 측면을 구현하고 개선하는 데 참여시켜야 한다. 참여적 개선이 동의를 구축한다. 비준수 팀원 제거(B)는 극단적이다. 회고 보고서 전송(C)은 상호작용을 제거한다. 브레인스토밍 포함(D)은 스탠드업의 목적을 벗어난다.
1140 | An organization is transitioning to agile and a project has been chosen as a pilot. The assigned project manager only has experience using predictive approaches but the project manager is now required to use agile approaches with the help of an agile coach. During the retrospective of the fifth sprint, the project team complains that many obstacles exist with the organization that are creating project delays and rework. What should the project manager do in this situation? | Create a dedicated sprint to solve the obstacles with the team | Promote collaboration to help remove the obstacles for the team | Include impediment resolutions during daily standup meetings | Perform a root cause analysis during the standup meetings |  | B | When an organization transitioning to agile faces organizational obstacles creating delays and rework for the pilot project team, the project manager should promote collaboration to help remove the obstacles. Collaborative impediment removal aligns with agile values. Creating a dedicated sprint for obstacles (A) delays value delivery. Including resolutions in standups (C) is too brief for complex impediments. Root cause analysis during standups (D) is inappropriate for that ceremony's purpose. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 조직이 애자일로 전환 중이며 파일럿으로 프로젝트가 선정되었다. 배정된 PM은 예측적 접근법만 경험이 있지만, 이제 조직적 장애물이 팀에 지연과 재작업을 초래하고 있다. PM은 무엇을 해야 하는가? | A. 팀과 함께 장애물을 해결하기 위한 전용 스프린트를 만든다. | B. 팀을 위한 장애물 제거를 돕기 위해 협업을 촉진한다. | C. 일일 스탠드업 회의에서 장애물 해결을 포함한다. | D. 스탠드업 회의에서 근본 원인 분석을 수행한다. |  | B | 애자일로 전환하는 조직에서 장애물이 파일럿 팀에 지연과 재작업을 초래할 때, PM은 장애물 제거를 위한 협업을 촉진해야 한다. 협력적 장애물 제거가 애자일 가치에 부합한다. 전용 스프린트(A)는 전달에서 벗어난다. 스탠드업에서 해결(C)은 스탠드업 시간을 초과한다. 스탠드업에서 RCA(D)는 부적절하다.
1141 | A project manager prepared a project benefits management plan. Which of the following should be included in this document? | Target benefits, benefits owner, lessons learned | Strategic alignment, benefits owner, risk register | Target benefits, strategic alignment, time frame for realizing benefits | Project requirements, target benefits, issue log, metrics |  | C | A project benefits management plan should include target benefits (expected tangible and intangible outcomes providing stakeholder value), strategic alignment (how the project supports organizational objectives), and time frame for realizing benefits (when and how benefits will be delivered). Options containing lessons learned (A), risk register (B), or issue log and project requirements (D) mix operational documents with benefits planning components. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Traditional PM | PM이 프로젝트 편익 관리 계획을 준비했다. 이 문서에 포함되어야 하는 것은? | A. 목표 편익, 편익 소유자, 교훈 | B. 전략적 정렬, 편익 소유자, 리스크 레지스터 | C. 목표 편익, 전략적 정렬, 편익 실현 기간 | D. 프로젝트 요구사항, 목표 편익, 이슈 로그, 메트릭 |  | C | 프로젝트 편익 관리 계획에는 목표 편익(이해관계자 가치를 제공하는 기대 유무형 성과), 전략적 정렬(프로젝트가 조직 목표를 어떻게 지원하는지), 편익 실현 기간(편익이 언제 어떻게 전달되는지)이 포함되어야 한다. A는 교훈이 별도 문서이다. B는 리스크 레지스터가 별도이다. D는 이슈 로그와 프로젝트 요구사항이 별도 문서이다.
1142 | A project has recently kicked off. The project manager observes that there are different expectations among the project team members. These growing misunderstandings are affecting team productivity. Which document should the project manager review? | Project charter | Team charter | Stakeholder register | Project organization charts |  | B | When different expectations among team members cause growing misunderstandings and affect productivity, the project manager should review the team charter. A team charter defines purpose, objectives, roles, and behavioral norms that align expectations and foster collaboration. The project charter (A) authorizes the project, not team behavior. The stakeholder register (C) identifies stakeholders, not team norms. Project organization charts (D) show reporting relationships, not team expectations. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 프로젝트가 최근 킥오프되었다. PM이 팀원들 사이에 다른 기대가 있음을 관찰한다. 이 증가하는 오해가 팀 생산성에 영향을 미치고 있다. PM이 검토해야 할 것은? | A. 프로젝트 헌장 | B. 팀 헌장 | C. 이해관계자 레지스터 | D. 프로젝트 조직도 |  | B | 팀원들 간의 다른 기대가 오해를 일으키고 생산성에 영향을 미칠 때, PM은 팀 헌장을 검토해야 한다. 팀 헌장은 목적, 목표, 역할, 행동 규범을 정의하여 기대를 정렬하고 협업을 촉진한다. 프로젝트 헌장(A)은 상위 수준 목표를 다루지 팀 행동을 다루지 않는다. 이해관계자 레지스터(C)는 외부 이해관계자에 초점을 맞춘다. 조직도(D)는 구조를 보여주지 기대를 정렬하지 않는다.
1143 | A software delivery project is in the execution phase. The project team has identified a need for an additional server as the software requires more data storage space than planned for. Without the additional server, the project delivery cannot continue. What should the project manager do? | Raise a change request and obtain approval from the project owner. | Request that the requirement is funded with the business operational expenses. | Use the project budget and procure a new server before raising a change request. | Apply contingency reserves to procure a server that fits the requirement. |  | A | When the team identifies a need for an additional server not in the original plan, the project manager should raise a change request and obtain approval from the project owner. Formal change control ensures governance and proper authorization before procurement. Using the project budget without approval (C) bypasses change control. Requesting operational expense funding (B) shifts costs improperly. Applying contingency reserves (D) assumes coverage without verification. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 소프트웨어 전달 프로젝트가 실행 단계에 있다. 팀이 소프트웨어가 계획보다 더 많은 데이터 저장 공간이 필요하여 추가 서버가 필요하다고 식별했다. 추가 서버 없이는 프로젝트 산출물의 품질이 영향을 받을 것이다. PM은 무엇을 해야 하는가? | A. 변경 요청을 제기하고 프로젝트 소유자의 승인을 받는다. | B. 비즈니스 운영 비용으로 요구사항 자금을 요청한다. | C. 변경 요청 전에 프로젝트 예산을 사용하여 새 서버를 조달한다. | D. 요구사항에 맞는 서버를 조달하기 위해 예비비를 적용한다. |  | A | 팀이 원래 계획에 없는 추가 서버 필요를 식별했을 때, PM은 변경 요청을 제기하고 프로젝트 소유자의 승인을 받아야 한다. 공식 변경 통제가 거버넌스와 적절한 승인을 보장한다. 승인 없이 예산 사용(C)은 거버넌스를 우회한다. 운영 비용 요청(B)은 프로젝트 범위에 맞지 않는다. 예비비 적용(D)은 승인된 리스크에만 사용한다.
1144 | In a review session held halfway through the project's development, several important stakeholders voice extreme dissatisfaction with the solution's current development versus what they had agreed were the goals and outputs of the project. One of the more prominent individuals threatens to close the project immediately. With no dissatisfaction having been voiced at prior sessions, the project manager is surprised. How should the project manager respond during the session? | Agree with the individual that they have every right to close the project and remind them of the resources already consumed. | Reprise past responses, especially positive ones, that the dissenters presented in previous sessions to defend the team ' s work. | Emphasize that this is the first occurrence of voiced dissatisfaction and then proceed to reconcile their concerns. | Engage with the individuals about their dissatisfactions and determine what they view as possible resolutions. |  | D | When important stakeholders voice extreme dissatisfaction mid-project and threaten to close it, the project manager should engage with the individuals about their dissatisfactions and determine what they view as possible resolutions. This demonstrates emotional intelligence and focuses on constructive problem-solving. Agreeing they have the right to close the project (A) is passive. Reprising past positive responses (B) is confrontational and defensive. Emphasizing this is the first occurrence (C) downplays their concerns. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Risk | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트 개발 중간 검토 세션에서 여러 중요 이해관계자가 합의된 프로젝트 기준 대비 현재 개발에 극도의 불만을 표현한다. 한 사람이 프로젝트 종료를 위협한다. PM은 무엇을 해야 하는가? | A. 개인에게 프로젝트를 종료할 권리가 있다는 데 동의하고 이미 소비된 자원을 상기시킨다. | B. 반대자들이 이전 세션에서 제시한 과거의 긍정적 응답을 되풀이하여 팀 작업을 방어한다. | C. 이것이 불만을 표명한 첫 번째 사례임을 강조하고 우려 해결을 진행한다. | D. 개인들의 불만에 참여하고 가능한 해결책으로 무엇을 보는지 파악한다. |  | D | 중요 이해관계자가 중간 검토에서 극도의 불만을 표현하고 프로젝트 종료를 위협할 때, PM은 개인들의 불만에 참여하고 가능한 해결책으로 무엇을 보는지 파악해야 한다. 이는 감성 지능을 보여주고 건설적 해결에 집중한다. 종료 권리 동의(A)는 수동적이다. 과거 긍정 응답 인용(B)은 방어적이다. 첫 불만 강조(C)는 우려를 경시한다.
1145 | A new project team consists of team members from different departments who have varying levels of experience and different areas of expertise. Which three approaches should the project manager take in order to facilitate knowledge sharing? (Choose 3) | Assess the gaps and assign an expert resource for respective areas of knowledge. | Arrange a daily learning session for project team members during lunch to facilitate knowledge transfer. | Identify external subject matter experts (SMEs) and plan training sessions to conduct knowledge transfer. | Allow each team member time in the retrospective sessions to share a little bit about their role and areas of knowledge. | Schedule shadowing sessions among team members to facilitate team learning. | B, D, E | To facilitate knowledge sharing in a cross-functional team with varying expertise, the project manager should take three approaches: arrange daily learning sessions during lunch for knowledge transfer, allow time in retrospectives for team members to share about their roles and knowledge, and schedule shadowing sessions among team members. Assigning expert resources for gaps (A) focuses on filling gaps, not sharing. Identifying external SMEs for training (C) relies on external rather than internal collaboration. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 새 프로젝트 팀이 다양한 경험 수준과 전문 분야를 가진 다른 부서의 팀원으로 구성되어 있다. PM이 지식 공유를 촉진하기 위해 취해야 할 세 가지 접근법은? (3개 선택) | A. 격차를 평가하고 해당 지식 분야에 전문 자원을 배정한다. | B. 프로젝트 팀원을 위한 점심시간 일일 학습 세션을 마련하여 지식 이전을 촉진한다. | C. 외부 주제 전문가(SME)를 식별하고 지식 이전을 위한 교육 세션을 계획한다. | D. 회고 세션에서 각 팀원이 자신의 역할과 지식 분야를 공유할 시간을 허용한다. | E. 팀원 간 섀도잉 세션을 예약하여 팀 학습을 촉진한다. | B, D, E | 교차 기능 팀에서 지식 공유를 촉진하기 위해 PM은 세 가지 접근법을 취해야 한다: 점심시간 일일 학습 세션을 마련하여 지식 이전(B), 회고에서 역할과 지식 공유 시간 허용(D), 팀원 간 섀도잉 세션 예약(E). 이 방법들은 일상 업무에 통합된 유기적 학습을 촉진한다. 전문 자원 배정(A)은 팀 학습이 아닌 격차 보완이다. 외부 SME(C)는 내부 지식 공유가 아닌 외부 교육이다.
1146 | An important project to build a new airport was suddenly stopped because of complaints from residents in the surrounding communities. The residents stated they were not consulted and that the project would cause ecological and pollution damage. What should the project manager have done first to avoid this situation? | Added these requests to the project scope statement | Presented the project to the community | Identified the stakeholders and their expectations | Added this situation to the risk register |  | C | The correct answer is C. Identified the stakeholders and their expectations. This approach best addresses the situation described by following project management best practices. The other options either fail to address the root cause, bypass proper processes, or may create additional problems. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | General PM Principles | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 새 공항 건설을 위한 중요한 프로젝트가 주변 주민들의 불만으로 갑자기 중단되었다. 프로젝트 관리자가 이 상황을 방지하기 위해 이전에 무엇을 했어야 하는가? | 이러한 요청을 프로젝트 범위 기술서에 추가했다 | 프로젝트를 커뮤니티에 발표했다 | 이해관계자와 그들의 기대를 식별했다 | 이 상황을 리스크 등록부에 추가했다 |  | C | 정답은 C이다. 이해관계자와 그들의 기대를 식별한다. 이 접근법은 프로젝트 관리 모범 사례를 따라 설명된 상황을 가장 잘 해결한다. 이해관계자 식별과 기대 분석은 프로젝트 초기에 수행해야 하는 핵심 활동이다. 범위 기술서에 추가(A)는 적절한 분석 없이 이루어진다. 커뮤니티 발표(B)는 이해관계자 식별 후에 해야 한다. 리스크 등록부 추가(D)는 반응적이며 예방적이지 않다.
1147 | A team is holding the first demonstration of the software built to date on a medium-sized project. The product owner has uncovered a number of issues they would like to be addressed before providing approval. How should the project manager approach this problem? | Refer the product owner to the change management plan, then escalate to the steering committee | Refer the product owner to the signed business requirement document and explain that the current plan cannot facilitate these changes | Tell the product owner the issues will be addressed in the second version of the software | Plan to address the issues through backlog grooming and incorporate them into the next sprint |  | D | When the product owner identifies issues during the first software demonstration that need to be addressed before approval, the project manager should plan to address the issues through backlog grooming and incorporate them into the next sprint. This ensures issues are properly documented, analyzed, prioritized, and addressed in the next iteration—maintaining agile principles of delivering value and responding to change. Referring to the change management plan and escalating (A) is too rigid for agile. Citing the business requirements document as immutable (B) conflicts with agile responsiveness. Deferring to the second version (C) delays value and risks losing stakeholder trust. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 팀이 중간 규모 프로젝트에서 지금까지 구축된 소프트웨어의 첫 번째 시연을 진행하고 있다. 제품 책임자가 승인 전에 해결해야 할 문제를 식별했다. 프로젝트 관리자는 무엇을 해야 하는가? | 제품 책임자에게 변경 관리 계획을 참조시킨 후 운영위원회에 에스컬레이션한다 | 제품 책임자에게 서명된 비즈니스 요구사항 문서를 참조시키고 현재 계획을 설명한다 | 제품 책임자에게 소프트웨어 두 번째 버전에서 문제를 해결하겠다고 말한다 | 백로그 정리를 통해 문제를 해결하고 다음 스프린트에 통합할 계획을 수립한다 |  | D | 제품 책임자가 첫 소프트웨어 시연 중 승인 전 해결이 필요한 문제를 식별하면, PM은 백로그 정리를 통해 문제를 해결하고 다음 스프린트에 통합해야 한다. 이는 애자일 원칙에 부합하며 지속적 개선을 가능하게 한다. 변경 관리 계획 참조(A)는 애자일 환경에서 과도하게 공식적이다. 서명된 문서 참조(B)는 유연성을 제한한다. 다음 버전으로 연기(C)는 즉각적 피드백 반영을 무시한다.
1148 | A project manager faces a major conflict within their project team that should be resolved as soon as possible. Which form of communication should the project manager use to deal with the conflict? | Distribute the progress report and risk register. | Send email communications to all members. | Schedule a conference call with the project team. | Schedule meetings with individual members. |  | C | Major team conflicts require fast, interactive, two-way communication. A conference call allows immediate clarification, tone management, and collaborative problem-solving. The project manager can set ground rules, keep discussion focused on issues rather than personalities, and drive toward agreement. Distributing progress reports and risk registers (A) provides information but does not resolve interpersonal conflict. Email communications (B) are easily misinterpreted, can escalate emotions, and delay resolution. Individual meetings (D) may be useful for sensitive one-on-one coaching but are less effective for resolving a conflict that affects the full team. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 가능한 빨리 해결해야 할 프로젝트 팀 내 주요 갈등에 직면하고 있다. 다음 중 어떤 형태의 의사소통이 가장 효과적인가? | 진행 보고서와 리스크 등록부를 배포한다 | 모든 구성원에게 이메일 의사소통을 보낸다 | 프로젝트 팀과 전화 회의를 예약한다 | 개별 구성원과 회의를 예약한다 |  | C | 주요 팀 갈등은 빠르고 상호작용적인 양방향 의사소통이 필요하다. 전화 회의는 즉각적인 설명, 톤 관리, 협력적 문제 해결을 가능하게 한다. PM이 분위기를 설정하고 모든 당사자가 동시에 참여할 수 있다. 진행 보고서 배포(A)는 단방향이다. 이메일(B)은 톤과 뉘앙스가 부족하다. 개별 회의(D)는 팀 전체 논의가 필요한 상황에서 비효율적이다.
1149 | A new team member has joined a project team. During the first sprint, the new team member approached the project manager and requested to implement a new way of testing. The team has been resistant to the proposed change. What should the project manager do? | Coach the new team member to conduct the testing the way it has always been done for this project. | Ask the new team member to focus only on development and not do the testing. | Request that the new team member do the testing the way it has always been done for this project. | Schedule a meeting with the new team member to learn about the new method of testing. |  | D | When a new team member proposes a new testing method and the team resists, the project manager should schedule a meeting with the new team member to learn about the new method. Understanding the proposal enables informed evaluation and team discussion. Coaching the member to follow existing methods (A) dismisses innovation. Asking them to focus only on development (B) suppresses their expertise. Requesting they follow existing methods (C) is also dismissive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 새 팀원이 프로젝트 팀에 합류했다. 첫 스프린트에서 새 팀원이 PM에게 새로운 테스트 방법을 제안했지만 팀이 저항했다. PM은 무엇을 해야 하는가? | 새 팀원에게 이 프로젝트에서 항상 해왔던 방식으로 테스트하도록 코칭한다 | 새 팀원에게 개발에만 집중하고 테스트는 하지 않도록 요청한다 | 새 팀원에게 이 프로젝트에서 항상 해왔던 방식으로 테스트하도록 요청한다 | 새 팀원과 회의를 예약하여 새로운 테스트 방법에 대해 배운다 |  | D | 새 팀원이 새로운 테스트 방법을 제안하고 팀이 저항할 때, PM은 새 팀원과 회의를 예약하여 새로운 방법에 대해 배워야 한다. 제안된 방법을 이해하면 정보에 기반한 결정이 가능하다. 기존 방식 코칭(A)은 혁신을 억제한다. 테스트 배제(B)는 팀원의 기여를 제한한다. 기존 방식 요청(C)은 지시적이며 개방성이 부족하다.
1150 | A project manager has been asked to participate in the procurement process for a software application that allows customers to buy online e-learning courses. The project manager will take over the project once the supplier has been sourced. What should the project manager do before the project starts? | Ask the project sponsor to involve the legal department in the negotiation for the project agreement. | Notify the project sponsor that the project manager cannot be involved in theagreement negotiation process. | Ensure that the requirements for the project are understood and that the objectivesare verified before approval of an agreement. | Inform the project sponsor that once the agreement has been signed, there cannotbe any changes to the scope of the project. |  | C | The PM should be actively involved in the procurement process to ensure project requirements are clearly defined and communicated to potential suppliers. Before approving any agreement, the PM must verify that project objectives align with business needs and stakeholder expectations. Restricting scope changes (B) is unrealistic for managing uncertainty. Declining involvement in negotiations (C) is neither proactive nor collaborative. Involving the legal department (D) is not the PM's responsibility and may not address the procurement participation issue. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | PM이 고객이 주문을 온라인으로 할 수 있는 소프트웨어 애플리케이션 조달 프로세스에 참여하도록 요청받았다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 법무부를 협상에 참여시키도록 요청한다 | 프로젝트 스폰서에게 PM이 계약 협상에 참여할 수 없다고 통보한다 | 프로젝트 요구사항이 이해되고 목표가 검증되었는지 확인한 후 계약을 승인한다 | 프로젝트 스폰서에게 계약이 서명되면 변경할 수 없다고 알린다 |  | C | PM은 잠재 공급업체에게 프로젝트 요구사항이 명확히 정의되고 전달되도록 조달 프로세스에 적극적으로 참여해야 한다. 계약 승인 전에 요구사항을 이해하고 목표를 검증해야 한다. 법무부 참여(A)는 PM의 역할을 회피한다. 참여 불가 통보(B)는 책임을 포기한다. 변경 불가 통보(D)는 부정확하고 비유연적이다.
1151 | A project manager brings in a new team member from an agile environment to work in a predictive environment. The project manager expects to leverage the new team member's agile experience with the existing team members. What should the project manager do to integrate the new team member effectively? | Set expectations with the new team member and explain what is needed | Train the new team member in the predictive project management approach. | Acknowledge that hiring this new employee is a risk to the existing team | Meet with all team members and explain the new employee ' s position. |  | A | The PM should set clear expectations with the new team member, explaining differences between agile and predictive approaches and the benefits and challenges of hybrid environments. The PM should also encourage the new member to share their agile experience with existing team members, fostering a collaborative learning culture. Training only in the predictive approach (A) is insufficient. Labeling the hire as a risk (B) undermines trust. A general introduction meeting (D) doesn't clarify roles or leverage the member's expertise. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Hybrid/Tailoring | PM이 애자일 환경 출신의 새 팀원을 예측형 환경에서 일하게 한다. PM은 무엇을 해야 하는가? | 새 팀원과 기대치를 설정하고 필요한 것을 설명한다 | 새 팀원에게 예측형 프로젝트 관리 접근법을 교육한다 | 이 신규 직원 고용이 기존 팀에 대한 리스크임을 인정한다 | 모든 팀원과 만나 신규 직원의 포지션을 설명한다 |  | A | PM은 새 팀원과 명확한 기대치를 설정하고, 애자일과 예측형 접근법의 차이점과 하이브리드 환경의 장단점을 설명해야 한다. 교육(B)은 유용하지만 먼저 기대치 설정이 필요하다. 리스크 인정(C)은 부정적이고 팀 사기를 저하시킨다. 전체 팀 회의(D)는 먼저 개별적으로 기대치를 설정한 후 고려해야 한다.
1152 | A project manager is quantifying risk for their project. The project manager needs an expert opinion in this process, but experts are spread over different geographic locations and time zones. What should the project manager do? | Utilize story point estimating. | Apply the critical path method (CPM). | Use the Delphi Technique. | Use the Monte Carlo analysis online. |  | D | The correct answer is D. Use the Monte Carlo analysis online. Risk and compliance management require proactive identification and assessment. The PM should evaluate impacts, follow proper processes, and implement appropriate response strategies. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | PM이 프로젝트의 리스크를 정량화하고 있다. 전문가 의견이 필요하지만 예산이 부족하다. PM은 무엇을 해야 하는가? | 스토리 포인트 추정을 활용한다 | 주공정선(CPM)을 적용한다 | 델파이 기법을 사용한다 | 몬테카를로 분석을 온라인으로 사용한다 |  | D | 정답은 D이다. 몬테카를로 분석을 온라인으로 사용한다. 예산 제약으로 전문가를 고용할 수 없을 때, 온라인 몬테카를로 분석은 비용 효율적인 정량적 리스크 분석을 제공한다. 스토리 포인트 추정(A)은 리스크 정량화가 아닌 작업 추정 기법이다. CPM(B)은 일정 관리 도구이다. 델파이 기법(C)은 전문가 참여가 필요하므로 예산 제약에 부합하지 않는다.
1153 | A project manager is leading a hybrid project. A project team member has not been delivering on time; as a result, the project is about to be delayed. What should the project manager do? | Negotiate revised timelines with the project sponsor. | Schedule a meeting with the project team to address timelines. | Revise the project schedule with the customer. | Discuss the situation with the project team member. |  | D | When a team member on a hybrid project is not delivering on time and the project faces delay, the project manager should discuss the situation directly with the team member. Direct communication identifies whether the cause is skill-related, workload-related, or caused by blockers, enabling targeted corrective action. Negotiating revised timelines with the sponsor (A) escalates before understanding the problem. Revising the schedule with the customer (C) changes commitments prematurely. Scheduling a team meeting to address timelines (B) involves the entire team unnecessarily for an individual performance issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | PM이 하이브리드 프로젝트를 이끌고 있다. 팀원 한 명이 제시간에 납품하지 못하여 프로젝트가 지연되고 있다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서와 수정된 일정을 협상한다 | 프로젝트 팀과 일정 문제를 논의하기 위한 회의를 예약한다 | 고객과 프로젝트 일정을 수정한다 | 해당 팀원과 상황을 논의한다 |  | D | 하이브리드 프로젝트에서 팀원이 제시간에 납품하지 못하고 프로젝트가 지연될 때, PM은 해당 팀원과 직접 상황을 논의해야 한다. 직접 대화는 근본 원인을 파악하고 해결책을 도출한다. 스폰서와 일정 협상(A)은 근본 원인 해결 전에 시기상조이다. 팀 회의(B)는 개인 문제를 팀 앞에서 다루는 것이다. 고객과 일정 수정(C)은 내부 해결 전에 외부에 영향을 미친다.
1154 | A complex, high-value agile project includes sprint demonstrations with the customer every four weeks. Executive management is concerned about the project's progress and wants more frequent updates on the project status. What should the project manager do? | Prepare a weekly status report and share it with executive management every week. | Inform executive management that the customer is made aware of the status duringthe sprint demo. | Inform executive management about agile principles and processes that are followedin the project. | Ask the team to prepare and share the status report with executive management everyweek. |  | A | When executive management wants more frequent updates on an agile project beyond the four-week sprint demos, the project manager should prepare a weekly status report and share it with executive management. This addresses their information needs with key metrics on schedule, cost, scope, quality, risks, and issues without disrupting the agile process. Informing executives about agile principles (B) is educational but does not satisfy their immediate information needs. Asking the team to prepare reports (C) adds burden to the team. Simply informing executives about the sprint demo process (D) does not address their request for more frequent updates. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 복잡한 고가치 애자일 프로젝트에서 4주마다 고객과 스프린트 시연을 진행한다. 경영진이 더 자주 업데이트를 원한다. PM은 무엇을 해야 하는가? | 주간 상태 보고서를 작성하여 경영진과 매주 공유한다 | 경영진에게 스프린트 시연 시 고객이 상태를 파악한다고 알린다 | 경영진에게 프로젝트에서 따르는 애자일 원칙과 프로세스를 알린다 | 팀에게 상태 보고서를 준비하여 경영진과 매주 공유하도록 요청한다 |  | A | 경영진이 4주 스프린트 시연 외에 더 자주 업데이트를 원할 때, PM은 주간 상태 보고서를 작성하여 경영진과 공유해야 한다. 이는 이해관계자 요구에 맞춰 의사소통을 조정하는 것이다. 스프린트 시연으로 충분하다고 알리기(B)는 이해관계자 요구를 무시한다. 애자일 원칙 교육(C)은 경영진의 정보 요구를 해결하지 않는다. 팀에게 보고서 준비 요청(D)은 팀의 개발 시간을 빼앗는다.
1155 | A project manager is managing the transition to operations. The project sponsor wants to ensure that good support is provided to the end users. What should the project manager do? | Ensure that the user guide is detailed and has clear instructions. | Ask the project team to provide operational support for 1 year. | Ensure that knowledge is transferred to the operations team. | Ensure that comprehensive documentation is handed over. |  | C | During the transition to operations, the project manager should ensure that knowledge is transferred to the operations team. This equips the operations team to support end users effectively through training sessions, documentation, and hands-on support during the initial phase. A detailed user guide (A) is helpful but insufficient without interactive knowledge transfer. Asking the project team to provide operational support for a year (B) delays the transition. Comprehensive documentation handover (D) is one component but does not replace interactive knowledge transfer. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Scope & Requirements Mgmt | People | Help Ensure Knowledge Transfer | Resources | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | PM이 운영 전환을 관리하고 있다. 프로젝트 스폰서가 최종 사용자에게 좋은 지원이 제공되기를 원한다. PM은 무엇을 해야 하는가? | 사용자 가이드가 상세하고 명확한 지침을 갖추도록 한다 | 프로젝트 팀에게 1년간 운영 지원을 제공하도록 요청한다 | 운영 팀에게 지식이 전달되도록 한다 | 포괄적인 문서가 인계되도록 한다 |  | C | 운영 전환 시, PM은 운영 팀에게 지식이 전달되도록 해야 한다. 이는 운영 팀이 교육, 세션, 실습을 통해 최종 사용자를 효과적으로 지원할 수 있게 한다. 상세한 사용자 가이드(A)는 유용하지만 지식 전달을 대체하지 않는다. 1년 운영 지원(B)은 프로젝트 팀의 범위를 벗어난다. 포괄적 문서 인계(D)는 중요하지만 지식 전달이 더 효과적이다.
1156 | The sponsor approaches the project manager with new features they want added to the project. The project is 95% complete, but the sponsor insists that continued support for the project relies on the addition of the new features. What should the project manager do? | Implement the new features after assessing the impact. | Assess the impact of the features and refer it to the change control board (CCB). | Reject the new features since it amounts to gold plating. | Add the new features to avoid losing the sponsor ' s support for the project. |  | B | When the sponsor insists on adding features to a 95% complete project and ties continued support to them, the project manager should assess the impact and refer it to the change control board. Formal change control ensures governance. Implementing without assessment (A) skips governance. Rejecting as gold plating (C) risks sponsor relationship. Adding features just to please the sponsor (D) enables scope creep. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 스폰서가 PM에게 프로젝트에 새로운 기능을 추가하고 싶다고 접근한다. 프로젝트는 95% 완료되었다. PM은 무엇을 해야 하는가? | 영향 평가 후 새 기능을 구현한다 | 기능의 영향을 평가하고 변경통제위원회(CCB)에 회부한다 | 골드 플레이팅에 해당하므로 새 기능을 거부한다 | 스폰서의 지원을 잃지 않기 위해 새 기능을 추가한다 |  | B | 스폰서가 95% 완료된 프로젝트에 기능 추가를 요구하고 지원 지속을 조건으로 걸 때, PM은 영향을 평가하고 변경통제위원회에 회부해야 한다. 공식 변경 통제 프로세스는 적절한 거버넌스를 보장한다. 영향 평가 후 바로 구현(A)은 CCB 승인을 건너뛴다. 골드 플레이팅으로 거부(C)는 스폰서 요청을 무시한다. 무조건 추가(D)는 변경 통제를 우회한다.
1157 | A supplier, who was tasked with providing an important component for a project, is unable to deliver the materials due to a large-scale labor problem. What document should the project manager use to update the details and communicate to relevant stakeholders? | Project schedule | Change request | Issue log | Risk register |  | C | When a supplier cannot deliver materials due to a large-scale labor problem, the project manager should use the issue log to update the details and communicate to relevant stakeholders. The issue log records and tracks current problems that can impact the project, making it the appropriate document for this situation. The project schedule (A) reflects timelines but is not the communication vehicle for issue tracking. A change request (B) may follow but documents proposed changes, not current issues. The risk register (D) tracks potential future events, whereas this is an issue that has already occurred. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트의 중요한 구성 요소를 제공하도록 한 공급업체가 대규모 노동 문제로 자재를 납품할 수 없다. PM은 어떤 문서를 업데이트해야 하는가? | 프로젝트 일정 | 변경 요청 | 이슈 로그 | 리스크 등록부 |  | C | 공급업체가 대규모 노동 문제로 자재를 납품할 수 없을 때, PM은 이슈 로그를 사용하여 세부 사항을 업데이트하고 관련 이해관계자에게 전달해야 한다. 이슈 로그는 발생한 문제를 추적하고 해결을 관리한다. 프로젝트 일정(A)은 이슈 문서화가 아닌 일정 관리 도구이다. 변경 요청(B)은 이슈 문서화 후 필요할 수 있다. 리스크 등록부(D)는 잠재적 리스크용이며 이미 발생한 이슈는 이슈 로그에 기록한다.
1158 | A project management office (PMO) is currently stretched for project control resources. Specifically, the cost control resources are short of the staff required for this activity level. A new project is about to start soon. What should the project lead do to obtain the needed resources? | Inform the project sponsor and initiate a recruitment exercise outside of the PMO. | Evaluate running the project without the required resources and depend on the lessons learned from similar past projects. | Meet with the PMO team and review the resource management plan ahead of the project kickoff to ensure resource availability. | Prepare to perform the duties of the cost controller for the duration of the project. |  | C | When the PMO is short on cost control resources for a new project, the project lead should meet with the PMO team and review the resource management plan ahead of kickoff to ensure resource availability. This aligns on constraints and enables negotiation or reprioritization before the project starts. Informing the sponsor and recruiting externally (A) bypasses internal governance. Evaluating running without resources (B) is risky. Performing cost controller duties personally (D) creates role confusion and inefficiency. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Finance | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Traditional PM | PMO가 프로젝트 통제 자원이 부족하다. 특히 비용 통제 자원이 새 프로젝트에 배정되지 않았다. 프로젝트 리더는 무엇을 해야 하는가? | 프로젝트 스폰서에게 알리고 PMO 외부에서 채용을 시작한다 | 필요한 자원 없이 프로젝트를 운영하고 유사 프로젝트의 교훈에 의존한다 | PMO 팀과 만나 프로젝트 착수 전에 자원 관리 계획을 검토하여 자원 가용성을 확보한다 | 프로젝트 기간 동안 비용 통제자의 역할을 수행할 준비를 한다 |  | C | PMO가 비용 통제 자원이 부족할 때, 프로젝트 리더는 PMO 팀과 만나 착수 전에 자원 관리 계획을 검토하여 자원 가용성을 확보해야 한다. 사전 계획이 자원 격차를 해결한다. 외부 채용(A)은 PMO 구조를 우회한다. 자원 없이 운영(B)은 리스크가 높다. PM이 비용 통제 수행(D)은 역할 과부하를 초래한다.
1159 | A construction services company has influence within the local community with the potential to derail a project site establishment. Their bid was unsuccessful but they continue to communicate with the hope that their influence will persuade the project manager to reconsider their offer. What is the appropriate course of action for the project manager to pursue? | Reassess the bid to establish areas for improvement with the intention to assign work to this contractor | Meet with the unsuccessful bidder to review their submission and the areas that led to the bid being unsuccessful | Report the unsuccessful bidder to the local community leadership who have been supportive of the project | Do not communicate with the unsuccessful bidder as they do not have any further influence on the project |  | B | When an unsuccessful bidder continues to communicate hoping to influence the project manager, the appropriate action is to meet with them to review their submission and areas that led to the bid being unsuccessful. Transparent feedback maintains professional relationships and may benefit future projects. Reassessing the bid to assign work (A) undermines the procurement process. Reporting them to community leadership (C) is adversarial. Refusing all communication (D) damages relationships unnecessarily. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 건설 서비스 회사가 지역 커뮤니티에 영향력이 있어 프로젝트 현장 설립을 방해할 가능성이 있다. 입찰에 실패한 후에도 PM에게 계속 연락한다. PM은 무엇을 해야 하는가? | 입찰을 재평가하여 이 계약자에게 일부 작업을 배정할 개선 영역을 찾는다 | 낙찰되지 않은 입찰자를 만나 제출물과 탈락 이유를 검토한다 | 프로젝트를 지지한 지역 커뮤니티 리더십에 낙찰되지 않은 입찰자를 보고한다 | 낙찰되지 않은 입찰자는 더 이상 영향력이 없으므로 연락하지 않는다 |  | B | 낙찰되지 않은 입찰자가 지역 커뮤니티에 영향력이 있고 계속 연락할 때, PM은 그들을 만나 제출물과 탈락 이유를 검토해야 한다. 이는 투명성을 보여주고 관계를 관리하며 잠재적 방해를 완화한다. 입찰 재평가(A)는 프로세스 무결성을 손상시킨다. 커뮤니티에 보고(C)는 적대적이다. 연락 차단(D)은 이해관계자 관리를 무시한다.
1160 | A project manager is leading a project that is in an advanced stage. All high-level risks identified in the risk management plan have been resolved or are no longer a risk for the project. Only low-level risks remain. What should the project manager do now? | Reclassify low-level risks as high-level risks | Notify stakeholders that all high-level risks have been resolved | Reduce the priority of project risks as all remaining risks are low-level | Reevaluate identified risks and update the risk register |  | D | Even when all high-level risks have been resolved and only low-level risks remain, the project manager should reevaluate identified risks and update the risk register. Risk management is continuous throughout the project lifecycle—low-level risks can escalate, new risks can emerge, and previously resolved risks can recur. Reclassifying low-level risks as high-level (A) is arbitrary without analysis. Notifying stakeholders that all high-level risks are resolved (B) creates a false sense of security. Reducing the priority of all project risks (C) is negligent and ignores the dynamic nature of risk. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 진행된 단계의 프로젝트를 이끌고 있다. 리스크 관리 계획에서 식별된 모든 고수준 리스크가 해결되었다. PM은 무엇을 해야 하는가? | 저수준 리스크를 고수준 리스크로 재분류한다 | 이해관계자에게 모든 고수준 리스크가 해결되었음을 통보한다 | 남은 리스크가 모두 저수준이므로 프로젝트 리스크의 우선순위를 낮춘다 | 식별된 리스크를 재평가하고 리스크 등록부를 업데이트한다 |  | D | 모든 고수준 리스크가 해결되고 저수준 리스크만 남아도, PM은 식별된 리스크를 재평가하고 리스크 등록부를 업데이트해야 한다. 리스크 관리는 프로젝트 전체에 걸쳐 지속적이다. 재분류(A)는 근거 없이 리스크를 과장한다. 해결 통보(B)는 지속적 모니터링을 중단한다. 우선순위 하향(C)은 새로운 리스크 출현 가능성을 무시한다.
1161 | Customers are concerned about the quality of an interim software system for a project. The quality control team has approved the software, but the customers are complaining that some functions do not comply with the requirements. What should the project manager do to prevent this from happening again? | Review the communications management plan. | Revise the quality management plan. | Review the risk impact of quality nonconformance. | Revise the product acceptance specifications. |  | D | The correct answer is D. Revise the product acceptance specifications. Quality management ensures deliverables meet established standards and acceptance criteria. The PM should implement appropriate quality controls and take corrective action when issues are identified. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 고객이 프로젝트의 중간 소프트웨어 시스템 품질에 우려를 표명한다. 품질 관리 팀은 인도물을 승인했다. PM은 무엇을 해야 하는가? | 커뮤니케이션 관리 계획을 검토한다 | 품질 관리 계획을 수정한다 | 품질 부적합의 리스크 영향을 검토한다 | 제품 인수 사양을 수정한다 |  | D | 정답은 D이다. 제품 인수 사양을 수정한다. 품질 관리 팀이 승인했지만 고객이 우려를 표명할 때, 인수 사양이 고객 기대에 부합하지 않을 수 있다. 인수 기준을 수정하여 고객 요구사항에 맞추어야 한다. 커뮤니케이션 계획 검토(A)는 품질 문제를 해결하지 않는다. 품질 관리 계획 수정(B)은 프로세스 변경이지 기준 변경이 아니다. 리스크 영향 검토(C)는 분석적이지만 즉각적 해결이 아니다.
1162 | A prefeasibility study for a new renewable energy project is nearing approval. To ensure that the project timelines are maintained, activities associated with the feasibility study must continue while the prefeasibility study is being approved. How should the project manager proceed? | Proceed with both the prefeasibility and feasibility studies in parallel while waiting for (he final approvals | Obtain approval to proceed with the feasibility study as a parallel activity while the prefeasibility study is approved | Secure approval of the prefeasibility study before proceeding with the feasibility activities. | Include the feasibility activities in the prefeasibility study and apply for a change of scope and budget. |  | B | When feasibility study activities must continue while the prefeasibility study is being approved to maintain timelines, the project manager should obtain approval to proceed with the feasibility study as a parallel activity. Formal authorization enables concurrent work. Proceeding without approval (A) bypasses governance. Waiting for prefeasibility approval (C) delays timelines. Including feasibility in the prefeasibility study (D) changes scope inappropriately. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 신규 재생 에너지 프로젝트의 사전타당성 조사가 승인에 가까워졌다. 프로젝트 일정을 유지하기 위해 PM은 무엇을 해야 하는가? | 사전타당성 조사와 타당성 조사를 최종 승인을 기다리며 병행 진행한다 | 사전타당성 조사가 검토되는 동안 타당성 조사를 병행 활동으로 진행하기 위한 승인을 받는다 | 타당성 활동을 진행하기 전에 사전타당성 조사의 승인을 확보한다 | 타당성 활동을 사전타당성 조사에 포함시키고 범위 및 예산 변경을 신청한다 |  | B | 타당성 조사 활동이 사전타당성 조사 승인 중에도 계속되어야 일정을 유지할 수 있을 때, PM은 타당성 조사를 병행 활동으로 진행하기 위한 승인을 받아야 한다. 이는 적절한 거버넌스와 승인을 유지하면서 일정을 보호한다. 승인 없이 병행(A)은 거버넌스를 우회한다. 완전 승인 대기(C)는 일정 지연을 초래한다. 범위 변경(D)은 불필요한 복잡성을 추가한다.
1163 | A project manager recognizes that a key stakeholder is not engaged in the project and does not seem interested in the project status. The project manager is concerned that the project may go off track if the stakeholder expectations are not met. How should the project manager approach the stakeholder? | Post regular updates to the project teams board and email the stakeholder when they are posted so the stakeholder can review at their convenience | Continue to send status reports by email and schedule one-on-one sessions with the stakeholder so they are regularly debriefed on the project status | Schedule regular review sessions with the stakeholder and the project team so the 1064 stakeholder can understand the status and engage with team members | Analyze the stakeholder ' s expectations and emphasize the topics of interest that may influence the project ' s success |  | D | When a key stakeholder is disengaged and the PM is concerned about unmet expectations affecting the project, the project manager should analyze the stakeholder's expectations and emphasize topics of interest that may influence success. Understanding motivations enables targeted engagement. Posting updates to a board (A) is passive. Sending reports and scheduling one-on-ones (B) is routine, not strategic. Scheduling review sessions with the team (C) is good but does not analyze stakeholder expectations first. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 핵심 이해관계자가 프로젝트에 참여하지 않고 관심이 없는 것을 인식한다. PM은 무엇을 해야 하는가? | 프로젝트 팀 보드에 정기 업데이트를 게시하고 이해관계자에게 이메일로 알린다 | 이메일로 상태 보고서를 계속 보내고 이해관계자와 일대일 세션을 예약한다 | 이해관계자와 프로젝트 팀이 참여하는 정기 검토 세션을 예약한다 | 이해관계자의 기대를 분석하고 프로젝트에 영향을 미칠 수 있는 관심 주제를 강조한다 |  | D | 핵심 이해관계자가 참여하지 않고 미충족 기대가 프로젝트에 영향을 미칠 우려가 있을 때, PM은 이해관계자의 기대를 분석하고 관심을 끌 수 있는 주제를 강조해야 한다. 맞춤형 참여가 관계를 재구축한다. 보드 업데이트(A)는 수동적이다. 이메일 보고서(B)는 일방적이다. 정기 검토 세션(C)은 이해관계자의 관심 없이는 효과적이지 않다.
1164 | During the execution of a project, an experienced team member informs the project manager that they cannot take part in all of the scheduled project activities due to a conflicting operational schedule. What should the project manager do? | Replace the team member with another available resource on the team. | Encourage the team member to prioritize scheduled project activities. | Discuss the situation with the team member ' s functional manager to see if the schedule can be adjusted. | Check with the project management office (PMO) on the available resources to complete the activities. |  | C | When an experienced team member cannot participate in all scheduled activities due to a conflicting operational schedule, the project manager should discuss the situation with the team member's functional manager to see if the schedule can be adjusted. Collaborative negotiation optimizes resource allocation. Replacing the team member (A) loses valuable expertise. Encouraging them to prioritize project activities (B) does not resolve the operational conflict. Checking with the PMO for available resources (D) is a fallback, not the first step. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 실행 중 경험 많은 팀원이 PM에게 운영 일정 충돌로 모든 예정 활동에 참여할 수 없다고 알린다. PM은 무엇을 해야 하는가? | 팀의 다른 가용 자원으로 해당 팀원을 교체한다 | 팀원에게 예정된 프로젝트 활동을 우선시하도록 권장한다 | 팀원의 기능 관리자와 일정 조정 가능 여부를 논의한다 | PMO에 활동 완료를 위한 가용 자원을 확인한다 |  | C | 경험 많은 팀원이 운영 일정 충돌로 모든 예정 활동에 참여할 수 없을 때, PM은 팀원의 기능 관리자와 일정 조정 가능 여부를 논의해야 한다. 기능 관리자가 자원 배분 권한을 가지며 일정 조정이 가능하다. 자원 교체(A)는 경험과 지식 손실을 초래한다. 우선시 권장(B)은 운영 의무를 무시한다. PMO 확인(D)은 기능 관리자와의 논의 후 고려해야 한다.
1165 | A project manager is leading a project that has a dependency on the client's vendor management system for critical requirements. The vendor management team will not derive any benefits from the project. However, the project requires support from the vendor management head. What should the project manager do next? | Work with the sponsor on a communications management plan to obtain support from the vendor management head. | Get support from the sponsor to hire a subject matter expert (SME) from the vendor management team to work on the project. | Review the terms of reference of the steering committee to include the vendor management head. | Obtain help from the sponsor to highlight any nonfinancial benefits for the vendor management team. |  | A | When the project depends on a client's vendor management system but the vendor management team will not benefit from the project, the project manager should work with the sponsor on a communications management plan to obtain support. Structured communication builds alignment. Getting sponsor support to hire a vendor SME (B) bypasses the team's cooperation. Reviewing steering committee terms (C) is administrative. Highlighting nonfinancial benefits (D) may help but is not the first structured approach. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | PM이 고객의 벤더 관리 시스템에 의존하는 프로젝트를 이끌고 있다. 벤더 관리 팀은 이 프로젝트로부터 혜택을 받지 않는다. PM은 무엇을 해야 하는가? | 스폰서와 커뮤니케이션 관리 계획을 수립하여 벤더 관리 팀의 지원을 확보한다 | 스폰서의 지원을 받아 벤더 관리 팀에서 SME를 고용한다 | 운영위원회의 위임사항을 검토하여 벤더 관리 책임자를 포함시킨다 | 스폰서의 도움을 받아 벤더 관리 팀에 비재무적 혜택을 강조한다 |  | A | 프로젝트가 고객의 벤더 관리 시스템에 의존하지만 벤더 관리 팀이 혜택을 받지 않을 때, PM은 스폰서와 커뮤니케이션 관리 계획을 수립하여 벤더 관리 팀의 지원을 확보해야 한다. 공식적인 의사소통 채널과 스폰서 지원이 협력을 촉진한다. SME 고용(B)은 비용이 많이 들고 근본 문제를 해결하지 않는다. 운영위원회 포함(C)은 거버넌스 변경이 필요하다. 비재무적 혜택 강조(D)는 공식적 지원 확보를 대체하지 않는다.
1166 | A project is about to start. The project manager has found that the client does not have an appropriate knowledge management system and does not have a requirement for it. What should the project manager do? | Ask the team to collect the knowledge locally and share it at the end of the project. | Provide just-in-time knowledge to the client, upon request. | Coordinate with the team and the project stakeholders to collect the knowledge. | Utilize the cloud wiki to collect the necessary knowledge. |  | C | When a client lacks a knowledge management system and has no requirement for one, the project manager should coordinate with the team and project stakeholders to collect the knowledge. Collaborative knowledge gathering ensures relevant information is captured and available for project needs. Asking the team to collect locally and share at project end (A) risks losing knowledge. Providing just-in-time knowledge upon request (B) is reactive. Using a cloud wiki (D) implements a system the client has not requested. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Stakeholder & Communication Mgmt | Process | Develop and Manage Scope | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 프로젝트가 시작되려 한다. PM이 고객에게 적절한 지식 관리 시스템이 없고 요구사항도 없음을 발견했다. PM은 무엇을 해야 하는가? | 팀에게 지식을 로컬로 수집하고 프로젝트 종료 시 공유하도록 요청한다 | 요청 시 고객에게 적시 지식을 제공한다 | 팀과 프로젝트 이해관계자와 협력하여 지식을 수집한다 | 클라우드 위키를 활용하여 필요한 지식을 수집한다 |  | C | 고객에게 지식 관리 시스템이 없고 요구사항도 없을 때, PM은 팀과 이해관계자와 협력하여 지식을 수집해야 한다. 협력적 지식 수집은 포괄적이고 접근 가능한 정보를 보장한다. 로컬 수집 후 공유(A)는 시기적절한 활용을 방해한다. 적시 제공(B)은 체계적이지 않다. 클라우드 위키(D)는 고객에게 시스템이 없는 상황에서 적합하지 않을 수 있다.
1167 | A project manager is leading a fast-moving project with strict deadlines and minimal time to deliver each milestone. The project manager discovers that one of the remote team members, who puts a lot of effort into delivering the project, has confided in an on-site team member. The remote team member feels they are not being adequately rewarded and recognized for their job. What should the project manager do? | Make arrangements with the resource ' s functional manager to relocate the team member to another existing project. | Inform the human resource (HR) manager of this situation and ensure this news does not spread. | Send a copy of the engagement contract to the remote team member and indicate that the team member is entitled to what is included in thecontract. | Engage the remote team member, empathize with them, and let them know their contribution is appreciated regardless of their remote work status. |  | D | When a remote team member confides feeling inadequately recognized despite high effort, the project manager should engage with them, empathize, and let them know their contribution is appreciated regardless of remote status. Direct recognition addresses the core concern. Relocating to another project (A) removes a contributor. Informing HR (B) escalates unnecessarily. Sending the engagement contract (C) is impersonal and legalistic. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | PM이 엄격한 기한과 최소한의 마일스톤 납기 시간이 있는 빠른 프로젝트를 이끌고 있다. 원격 팀원이 높은 노력에도 불구하고 충분히 인정받지 못한다고 느낀다. PM은 무엇을 해야 하는가? | 자원의 기능 관리자와 협의하여 팀원을 다른 프로젝트로 이동시킨다 | 인사(HR) 관리자에게 상황을 알리고 소문이 퍼지지 않도록 한다 | 원격 팀원에게 참여 계약서 사본을 보내고 위반 사항을 알린다 | 원격 팀원과 소통하고 공감하며 기여가 인정됨을 알린다 |  | D | 원격 팀원이 충분히 인정받지 못한다고 느낄 때, PM은 그들과 소통하고 공감하며 기여가 인정됨을 알려야 한다. 이는 팀원의 동기와 참여를 회복시킨다. 다른 프로젝트 이동(A)은 문제를 해결하지 않고 자원을 잃는다. HR 통보(B)는 과도한 대응이다. 계약서 사본 발송(C)은 위협적이고 비공감적이다.
1168 | A product owner asks a project manager for details about products that were added during the last iteration. What should the project manager do to gather this information and send it to the product owner? | Evaluate the product development cycle | Evaluate the sprint backlog | Evaluate the sprint increment | Evaluate the product backlog |  | C | When the product owner asks for details about products added during the last iteration, the project manager should evaluate the sprint increment. The increment is the definitive record of completed work. The sprint backlog (B) shows planned work, not completed. The product backlog (D) shows future work. The product development cycle (A) is too broad. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 제품 책임자가 PM에게 마지막 이터레이션에서 추가된 제품에 대한 세부 정보를 요청한다. PM은 무엇을 평가해야 하는가? | 제품 개발 주기를 평가한다 | 스프린트 백로그를 평가한다 | 스프린트 증분을 평가한다 | 제품 백로그를 평가한다 |  | C | 제품 책임자가 마지막 이터레이션에서 추가된 제품 세부 정보를 요청할 때, PM은 스프린트 증분을 평가해야 한다. 증분은 완료된 작업의 확정적 기록이며 이전 증분에 추가된 것을 보여준다. 제품 개발 주기(A)는 전체적 관점이다. 스프린트 백로그(B)는 계획된 작업이지 완료된 작업이 아니다. 제품 백로그(D)는 향후 작업 항목이다.
1169 | A large organization decided to adopt an agile methodology based on the trends seen in the industry. The organization invested a large amount of money in adopting it, but after a few months, the implementation failed. What should the project manager have done differently to avoid the implementation failure? | Assessed the organization ' s culture, performed a suitability analysis, and determinedthe future state. | Hired a third-party agile delivery team to do the implementation. | Conducted agile training for all employees ranging from the project teams throughmid- level to upper- level management. | Conducted a postmortem and captured the learning in organizational process assets(OPAs) for future use. |  | A | When a large organization's agile adoption fails despite significant investment, the project manager should have assessed the organization's culture, performed a suitability analysis, and determined the future state before adoption. Understanding readiness, gaps, and risks enables planned transformation. Hiring a third-party agile team (B) creates dependency. Conducting agile training alone (C) is insufficient without cultural assessment. Conducting a postmortem (D) is reactive, occurring after failure. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 대규모 조직이 업계 트렌드를 기반으로 애자일 방법론을 채택하기로 결정했다. 상당한 투자에도 불구하고 구현에 실패했다. PM이 이전에 무엇을 했어야 하는가? | 조직 문화를 평가하고 적합성 분석을 수행하며 미래 상태를 결정했다 | 타사 애자일 전달 팀을 고용하여 구현했다 | 프로젝트 팀부터 중간 관리자, 상위 관리자까지 모든 직원에게 애자일 교육을 실시했다 | 사후 분석을 수행하고 학습 내용을 조직 프로세스 자산(OPA)에 기록했다 |  | A | 대규모 조직의 애자일 채택이 상당한 투자에도 실패했을 때, PM은 조직 문화를 평가하고 적합성 분석을 수행하며 미래 상태를 결정했어야 한다. 문화적 준비도 평가가 성공적 전환의 기초이다. 타사 팀 고용(B)은 내부 역량을 구축하지 않는다. 전체 교육(C)은 문화 평가 없이는 효과적이지 않다. 사후 분석(D)은 실패 후 활동이다.
1170 | While working on a poorly defined internal project, a project manager receives multiple change requests from senior management. What should the project manager do first? | Assess the schedule delay and begin implementation to avoid additional lags | Identify how the proposed changes will benefit the project in relation to the businesscase. | Ask for a temporary budget increase to avoid cost overruns. | Keep the team motivated and incentivized to avoid exhaustion from working on alengthy project. |  | B | When receiving multiple change requests from senior management on a poorly defined internal project, the project manager should first identify how the proposed changes will benefit the project in relation to the business case. Evaluating changes against value ensures alignment. Assessing schedule delay (A) acts before analysis. Requesting a budget increase (C) is premature. Keeping the team motivated (D) does not address the change requests. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 잘 정의되지 않은 내부 프로젝트에서 고위 관리자로부터 여러 변경 요청을 받았다. PM은 무엇을 먼저 해야 하는가? | 일정 지연을 평가하고 추가 지연을 피하기 위해 구현을 시작한다 | 제안된 변경이 비즈니스 케이스와 관련하여 프로젝트에 어떻게 혜택을 줄지 식별한다 | 비용 초과를 피하기 위해 임시 예산 증가를 요청한다 | 긴 프로젝트 작업으로 인한 피로를 방지하기 위해 팀의 동기와 인센티브를 유지한다 |  | B | 잘 정의되지 않은 프로젝트에서 고위 관리자의 여러 변경 요청을 받을 때, PM은 먼저 제안된 변경이 비즈니스 케이스에 비추어 프로젝트에 어떻게 혜택을 주는지 식별해야 한다. 비즈니스 가치 평가가 우선이다. 즉시 구현(A)은 영향 분석을 건너뛴다. 예산 증가(C)는 가치 평가 전에 시기상조이다. 팀 동기 유지(D)는 중요하지만 즉각적 조치가 아니다.
1171 | A project manager is leading a project with a negative risk that has just become an issue. The risk was recorded and a response plan was set. However, a project team member proposes a response that differs from the response recorded in the risk management plan and believes it will be cheaper and equally effective. What should the project manager do? | Adhere to the issue response in the risk management plan as it is the agreed-on solution | Implement the new proposal as soon as possible since it is cheaper and equally effective | Ask the team member to write a formal email explaining the proposal and send it to the change control board (CCB) | Evaluate the new proposal with the project team to determine if it is a more beneficial 1302 alternative |  | D | When a risk becomes an issue and a team member proposes a cheaper, equally effective alternative to the planned response, the project manager should evaluate the new proposal with the team to determine if it is a more beneficial alternative. Structured evaluation ensures the best response is selected. Adhering to the original plan (A) ignores improvement. Implementing immediately (B) skips validation. Sending to the CCB via email (C) is premature before evaluation. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 방금 이슈가 된 부정적 리스크가 있는 프로젝트를 이끌고 있다. 리스크는 기록되었고 대응이 합의되었으나, 팀원이 더 저렴하고 동등하게 효과적인 대안을 제안한다. PM은 무엇을 해야 하는가? | 리스크 관리 계획의 이슈 대응을 합의된 솔루션으로 준수한다 | 새 제안이 더 저렴하고 동등하게 효과적이므로 가능한 빨리 구현한다 | 팀원에게 제안을 설명하는 공식 이메일을 작성하여 CCB에 보내도록 요청한다 | 새 제안을 프로젝트 팀과 평가하여 더 유익한 대안인지 결정한다 |  | D | 리스크가 이슈가 되고 팀원이 더 저렴하고 동등하게 효과적인 대안을 제안할 때, PM은 새 제안을 팀과 평가하여 더 유익한 대안인지 결정해야 한다. 팀 평가는 정보에 기반한 결정을 가능하게 한다. 기존 대응 고수(A)는 더 나은 옵션을 무시한다. 즉시 구현(B)은 평가를 건너뛴다. 공식 이메일(C)은 불필요한 관료주의를 추가한다.
1172 | The project manager of a large construction project discovers that the blueprints received from the client appear incomplete. What should the project manager do first? | Escalate this issue to the project sponsor | Consult with the client to determine if project execution should be continued. | Continue project execution using the current blueprints from the client. | Reschedule the project execution date. |  | B | When the PM discovers client-provided blueprints appear incomplete, the first action is to consult with the client to determine if project execution should continue. The client owns the requirements. Escalating to the sponsor (A) bypasses the source. Continuing with current blueprints (C) risks rework. Rescheduling the execution date (D) acts before confirming the issue. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Risk & Issue Management | Process | Develop and Manage Scope | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 대규모 건설 프로젝트의 PM이 고객으로부터 받은 청사진이 불완전해 보인다. PM은 무엇을 해야 하는가? | 이 이슈를 프로젝트 스폰서에게 에스컬레이션한다 | 고객과 상의하여 프로젝트 실행을 계속해야 하는지 결정한다 | 고객의 현재 청사진을 사용하여 프로젝트 실행을 계속한다 | 프로젝트 실행 날짜를 재조정한다 |  | B | PM이 고객 제공 청사진이 불완전해 보인다고 발견하면, 첫 번째 조치는 고객과 상의하여 프로젝트 실행을 계속해야 하는지 결정하는 것이다. 고객이 요구사항의 소유자이다. 스폰서 에스컬레이션(A)은 고객과의 직접 소통 전에 시기상조이다. 현재 청사진으로 계속(C)은 결함을 무시한다. 날짜 재조정(D)은 근본 문제를 해결하지 않는다.
1173 | A primary stakeholder is unable to join the project status meetings consistently. The project manager has been communicating with this stakeholder informally and regularly to ensure that the stakeholder is up to date on the project. However, the project manager has recently resigned and will not be meeting with the new project manager prior to departure. How should the project manager ensure that the new project manager continues to update this particular stakeholder? | Update the communications management plan with specific information on stakeholder engagement. | Update the stakeholder engagement plan with the specific communication needs for the stakeholder. | Ensure that the project team has been provided guidance on the specific needs of this stakeholder. | Ensure that the project documents contain specific instructions regarding the stakeholder. |  | B | To ensure continuity of communication with a stakeholder who cannot consistently attend status meetings, the departing project manager should update the stakeholder engagement plan with the specific communication needs for that stakeholder. This plan is part of the project management plan and outlines strategies for productive stakeholder involvement, ensuring the new PM can continue the established communication approach. Updating the communications management plan (A) is broader and less specific to this individual's needs. Providing guidance to the project team (C) is informal and may not persist. Including instructions in project documents (D) may not be reviewed by the new PM in a timely manner. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 주요 이해관계자가 프로젝트 상태 회의에 일관되게 참석할 수 없다. PM이 이해관계자에게 정보를 전달해왔지만 곧 프로젝트를 떠날 예정이다. PM은 무엇을 해야 하는가? | 이해관계자 참여에 대한 구체적 정보로 커뮤니케이션 관리 계획을 업데이트한다 | 이해관계자의 구체적 커뮤니케이션 요구사항으로 이해관계자 참여 계획을 업데이트한다 | 프로젝트 팀에게 이 이해관계자의 구체적 요구에 대한 지침을 제공한다 | 프로젝트 문서에 이해관계자에 관한 구체적 지침을 포함시킨다 |  | B | 일관되게 참석할 수 없는 이해관계자와의 소통 연속성을 보장하기 위해, 떠나는 PM은 이해관계자의 구체적 커뮤니케이션 요구사항으로 이해관계자 참여 계획을 업데이트해야 한다. 이는 후임 PM이 맞춤형 참여를 계속할 수 있게 한다. 커뮤니케이션 관리 계획 업데이트(A)는 일반적 커뮤니케이션이지 이해관계자 특화가 아니다. 팀 지침(C)은 PM 전환을 다루지 않는다. 문서 지침(D)은 특정 계획보다 덜 체계적이다.
1174 | In a hybrid project, the project manager has identified a few stakeholders. According to the stakeholder matrix, the head of development has a high rating of power/influence and a high likelihood of conflict. Which action should the project manager avoid? | Giving special attention to this stakeholder | Escalating a conflict within the project | Dismissing the stakeholder ' s opinions | Creating a new communication channel |  | C | When a stakeholder has high power/influence and high likelihood of conflict in a hybrid project, the project manager should avoid dismissing the stakeholder's opinions. Dismissing a powerful, conflict-prone stakeholder invites escalation. Giving special attention (A) is appropriate for high-power stakeholders. Escalating conflicts (B) follows proper governance. Creating new communication channels (D) improves engagement. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 하이브리드 프로젝트에서 PM이 이해관계자를 식별했다. 이해관계자 매트릭스에 따르면 한 부서장이 높은 권한/영향력과 높은 갈등 가능성을 가진다. PM이 피해야 할 것은? | 이 이해관계자에게 특별한 주의를 기울인다 | 프로젝트 내 갈등을 에스컬레이션한다 | 이해관계자의 의견을 무시한다 | 새로운 커뮤니케이션 채널을 생성한다 |  | C | 이해관계자가 높은 권한/영향력과 높은 갈등 가능성을 가질 때, PM은 이해관계자의 의견을 무시하는 것을 피해야 한다. 권력 있고 갈등 가능성이 높은 이해관계자의 의견을 무시하면 프로젝트에 심각한 방해가 될 수 있다. 특별한 주의(A)는 적절한 접근이다. 에스컬레이션(B)은 상황에 따라 필요할 수 있다. 새 커뮤니케이션 채널(D)은 참여를 개선할 수 있다.
1175 | The project manager has recently received funding approval for a training program for the entire project team but has not yet defined the most effective training course. One team member submitted a request for specialized training that is required for the project. How should the project manager handle this request? | Approve the request for the specialized training. | Send this change request to the change control board (CCB) for approval. | Validate if the training is within scope and budget. | Reject the request as it does not impact the project deliverables. |  | C | When a team member requests specialized training needed for the project and the PM has training funding but no course defined, the project manager should validate if the training is within scope and budget. Verification ensures alignment with project needs before approval. Approving without validation (A) risks scope creep. Sending to the CCB (B) is for changes outside the baseline. Rejecting because it does not impact deliverables (D) may miss a valid requirement. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Finance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | PM이 최근 전체 팀 교육 프로그램의 예산 승인을 받았으나 과정이 정의되지 않았다. 팀원이 프로젝트에 필요한 전문 교육을 요청한다. PM은 무엇을 해야 하는가? | 전문 교육 요청을 승인한다 | 이 변경 요청을 변경통제위원회(CCB)에 승인을 위해 보낸다 | 교육이 범위와 예산 내에 있는지 검증한다 | 프로젝트 인도물에 영향을 미치지 않으므로 요청을 거부한다 |  | C | 교육 예산이 있으나 과정이 정의되지 않은 상황에서 팀원이 전문 교육을 요청할 때, PM은 교육이 범위와 예산 내에 있는지 검증해야 한다. 검증이 적절한 사용을 보장한다. 바로 승인(A)은 범위 확인을 건너뛴다. CCB 회부(B)는 예산이 이미 승인되어 과도하다. 거부(D)는 프로젝트에 필요한 교육을 무시한다.
1176 | A government approved the construction of a river dam to enable year-round farming in a community. At the project kickoff meeting, a key stakeholder in the community disagrees with the location of the dam. What should the project manager do first? | Review the stakeholder engagement plan to confirm that all key stakeholders were consulted. | Explain to the key stakeholder that final approval has already been obtained. | Meet with the key stakeholder to review the stakeholder engagement plan. | Schedule a meeting with all stakeholders to discuss the view of this key stakeholder. |  | A | When a key stakeholder disagrees with the dam location at the kickoff meeting, the project manager should first review the stakeholder engagement plan to confirm all key stakeholders were consulted. Verifying the engagement process identifies whether the concern stems from inadequate consultation. Explaining that final approval was obtained (B) is dismissive. Meeting the stakeholder to review the engagement plan (C) assumes the plan is complete. Scheduling a meeting with all stakeholders (D) is premature without verification. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | 정부가 커뮤니티의 연중 농업을 위한 강 댐 건설을 승인했다. 착수 회의에서 핵심 이해관계자가 댐 위치에 동의하지 않는다. PM은 무엇을 먼저 해야 하는가? | 이해관계자 참여 계획을 검토하여 모든 핵심 이해관계자가 상담되었는지 확인한다 | 핵심 이해관계자에게 최종 승인이 이미 받아졌다고 설명한다 | 핵심 이해관계자와 만나 이해관계자 참여 계획을 검토한다 | 모든 이해관계자 회의를 예약하여 이 핵심 이해관계자의 견해를 논의한다 |  | A | 핵심 이해관계자가 착수 회의에서 댐 위치에 동의하지 않을 때, PM은 먼저 이해관계자 참여 계획을 검토하여 모든 핵심 이해관계자가 상담되었는지 확인해야 한다. 계획 검증이 프로세스 격차를 식별한다. 최종 승인 설명(B)은 이해관계자 우려를 무시한다. 개별 회의(C)는 검토 후 다음 단계가 될 수 있다. 전체 회의(D)는 검증 전에 시기상조이다.
1177 | Project stakeholders have provided a team with requirements that will take at least one year to complete. The project sponsor advised that they need to see some return on investment (ROI) soon. What should the project manager do? | Acknowledge that the benefits cannot be realized any sooner due to the nature of the requirements. | Request additional funding from the project sponsor to accelerate delivery. | Discuss reducing the requirements with the project sponsor in order to release the product earlier. | Prioritize the work into incremental features that can be delivered iteratively. |  | B | The correct answer is B. Request additional funding from the project sponsor to accelerate delivery. Stakeholder engagement requires proactive communication and alignment. The PM should understand stakeholder needs, maintain transparency, and address concerns to ensure project success. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Stakeholder & Communication Mgmt | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 이해관계자가 완료에 최소 1년이 걸리는 요구사항을 제공했다. 스폰서가 더 빠른 혜택 실현을 원한다. PM은 무엇을 해야 하는가? | 요구사항의 특성상 혜택을 더 빨리 실현할 수 없음을 인정한다 | 프로젝트 스폰서에게 전달 가속화를 위한 추가 자금을 요청한다 | 제품을 더 일찍 출시하기 위해 프로젝트 스폰서와 요구사항 축소를 논의한다 | 반복적으로 전달할 수 있는 점진적 기능으로 작업 우선순위를 정한다 |  | B | 정답은 B이다. 전달 가속화를 위해 프로젝트 스폰서에게 추가 자금을 요청한다. 이해관계자 참여는 사전적 의사소통과 정렬이 필요하다. PM은 이해관계자의 요구와 기대를 이해하고 스폰서와 협력하여 일정을 단축해야 한다. 혜택 실현 불가 인정(A)은 스폰서 요구에 대응하지 않는다. 요구사항 축소(C)는 가치를 줄인다. 점진적 전달(D)은 유용하지만 추가 자금이 가속화에 더 직접적이다.
1178 | A few key stakeholders are concerned about how the project team is planning to develop some features for a new product. They know that the requirements associated with these features are unstable but are also highly strategic for adding value to the product and the customer. What should the project manager do? | Review the project governance to validate the policies procedures and guidelines used to prioritize the project | Suggest an agile approach to refine these requirements and prioritize them according to the project objectives | Ask the stakeholders to refine these requirements at a level of detail that becomes more stable and measurable | Validate the prioritization of all requirements with the sponsor and share the results with the stakeholders |  | B | When stakeholders are concerned about features with unstable but strategically valuable requirements, the project manager should suggest an agile approach to refine these requirements and prioritize them according to project objectives. Agile accommodates changing requirements through iterative feedback and incremental delivery. Reviewing project governance (A) does not address requirement instability. Asking stakeholders to refine requirements to stability (C) may not be realistic for genuinely unstable requirements. Validating prioritization with the sponsor (D) adds approval but not refinement methodology. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 핵심 이해관계자가 프로젝트 팀의 신제품 기능 개발 방식에 우려를 표명한다. 요구사항은 불안정하지만 전략적으로 가치가 있다. PM은 무엇을 해야 하는가? | 프로젝트 거버넌스를 검토하여 정책, 절차 및 지침을 검증한다 | 애자일 접근법을 제안하여 요구사항을 정제하고 프로젝트 비전에 따라 우선순위를 정한다 | 이해관계자에게 더 안정적인 세부 수준까지 요구사항을 정제하도록 요청한다 | 스폰서와 모든 요구사항의 우선순위를 검증하고 결과를 이해관계자와 공유한다 |  | B | 이해관계자가 불안정하지만 전략적으로 가치 있는 요구사항이 있는 기능에 우려를 표명할 때, PM은 애자일 접근법을 제안하여 요구사항을 정제하고 우선순위를 정해야 한다. 반복적 정제가 불확실성을 관리한다. 거버넌스 검토(A)는 정책 중심이지 요구사항 관리가 아니다. 이해관계자에 정제 요청(C)은 팀의 적극적 참여가 부족하다. 스폰서 검증(D)은 일방적이다.
1179 | A project is using a Scrum team from a new vendor to deliver a component. Engaging a new vendor was identified as a delivery risk that, if eventuated, must be escalated to the board. The project manager and product owner work well with the Scrum team, but the vendor misses the first release by a couple of weeks. What should the project manager do? | Work with the product owner and the Scrum team to add 2 weeks to the release schedule. | Work with the product owner and the Scrum team to recover the delay before the last release. | Escalate the issue to the board with opportunities to recover the delay as soon as possible. | Escalate the issue to the board and plan for the engagement to be terminated. |  | C | The correct answer is C. Escalate the issue to the board with opportunities to recover the delay as soon as possible. The product owner is responsible for managing the product backlog and defining priorities. The PM should facilitate proper collaboration between the team and product owner while maintaining agile practices. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 프로젝트가 새 벤더의 스크럼 팀을 사용하여 구성 요소를 전달한다. 새 벤더 참여는 전달 리스크로 식별되었다. 마지막 릴리스에서 2주 지연이 발생했다. PM은 무엇을 해야 하는가? | 제품 책임자 및 스크럼 팀과 협력하여 릴리스 일정에 2주를 추가한다 | 제품 책임자 및 스크럼 팀과 협력하여 마지막 릴리스 전에 지연을 회복한다 | 이사회에 이슈를 에스컬레이션하고 가능한 빨리 지연을 회복할 기회를 제시한다 | 이사회에 이슈를 에스컬레이션하고 계약 종료를 계획한다 |  | C | 정답은 C이다. 이사회에 이슈를 에스컬레이션하고 가능한 빨리 지연을 회복할 기회를 제시한다. 새 벤더 참여가 리스크로 식별되었고 2주 지연이 발생했으므로, 이사회에 보고하고 회복 방안을 제시하는 것이 적절하다. 일정에 2주 추가(A)는 지연을 수용하는 것이다. 팀 내 회복(B)은 이사회 가시성이 부족하다. 계약 종료(D)는 과도한 대응이다.
1180 | In an ongoing project, stakeholders have been approaching team members for status reports and changes without consulting the project manager. What should the project manager do to ensure a successful project? | Send the project charter to all stakeholders for information. | Send an email to all stakeholders directing them to approach the project managerdirectly. | Review the stakeholder engagement plan and inform the stakeholders. | Review the change management plan and ask the change control board (CCB) to beinvolved. |  | C | When stakeholders bypass the project manager to approach team members for status and changes, the project manager should review the stakeholder engagement plan and inform stakeholders of proper communication channels. Reestablishing communication protocols prevents confusion and delays. Sending the charter (A) provides general information but does not address the behavior. Emailing stakeholders to approach the PM directly (B) is directive without context. Reviewing the change management plan and CCB involvement (D) addresses changes but not status inquiries. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 진행 중인 프로젝트에서 이해관계자가 PM을 거치지 않고 팀원에게 직접 상태 보고와 변경을 요청한다. PM은 무엇을 해야 하는가? | 모든 이해관계자에게 프로젝트 헌장을 정보 제공 목적으로 보낸다 | 모든 이해관계자에게 PM에게 직접 접근하도록 안내하는 이메일을 보낸다 | 이해관계자 참여 계획을 검토하고 이해관계자에게 알린다 | 변경 관리 계획을 검토하고 변경통제위원회(CCB) 참여를 요청한다 |  | C | 이해관계자가 PM을 거치지 않고 팀원에게 직접 상태 보고와 변경을 요청할 때, PM은 이해관계자 참여 계획을 검토하고 이해관계자에게 적절한 커뮤니케이션 채널을 알려야 한다. 프로젝트 헌장(A)은 참여 프로세스를 다루지 않는다. 이메일(B)은 지시적이며 관계적이지 않다. CCB(D)는 변경 관리이지 커뮤니케이션 문제가 아니다.
1181 | At the end of a project, one of the suppliers is facing financial difficulties and is pushing the project manager to obtain financial, legal, and administrative approval in order to communicate formal project closure and ensure the transfer of liability. What should the project manager do next? | Compare the achieved results to the contract requirements. | Escalate to higher management to expedite the approval. | Transfer the remaining variances and close the project. | Make the final payment as the project is completed. |  | A | When a supplier facing financial difficulties pushes for formal closure approval to transfer liability, the project manager should first compare the achieved results to the contract requirements. This ensures all contractual obligations are fulfilled before making final payments and closing the project. Escalating to higher management (B) bypasses due diligence. Transferring remaining variances and closing (C) may leave obligations unverified. Making final payment (D) is premature without verifying contract fulfillment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Closing | Embed Quality | Close Project or Phase | Traditional PM | 프로젝트 종료 시 공급업체가 재정적 어려움을 겪으며 PM에게 책임 이전을 위한 공식 종료 승인을 서두르도록 압박한다. PM은 무엇을 먼저 해야 하는가? | 달성된 결과를 계약 요구사항과 비교한다 | 승인을 촉진하기 위해 상위 경영진에 에스컬레이션한다 | 남은 차이를 이전하고 프로젝트를 종료한다 | 프로젝트가 완료되었으므로 최종 결제를 수행한다 |  | A | 재정적 어려움을 겪는 공급업체가 책임 이전을 위해 공식 종료를 서두르도록 압박할 때, PM은 먼저 달성된 결과를 계약 요구사항과 비교해야 한다. 이는 적절한 실사를 보장한다. 에스컬레이션(B)은 검토 전에 시기상조이다. 차이 이전(C)은 검증 없이 리스크가 있다. 최종 결제(D)는 결과 검증 전에 성급하다.
1182 | In an agile project, the Scrum Master noticed that in the last few iterations, the team consistently delivered less than the amount of work they committed in the sprint planning meeting. The Scrum leader looked at the burn-down chart and found that the team was unable to meet the initial commitments due to the Product Owner adding new user stories after the sprint started. In this case, what should the Scrum lead point out to the product owner? | The team is accepting too much work in the sprint after it has started. | The product owner should not ask the team to change their sprint commitments. | The team is not meeting the expectations of the product owner. | The team should have stopped on day 4 and started a new sprint. |  | C | The correct answer is C. The team is not meeting the expectations of the product owner. The product owner is responsible for managing the product backlog and defining priorities. The PM should facilitate proper collaboration between the team and product owner while maintaining agile practices. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 애자일 프로젝트에서 스크럼 마스터가 최근 몇 번의 이터레이션에서 팀이 일관되게 약속보다 적게 전달함을 발견했다. 제품 책임자가 5일차에 추가 사용자 스토리를 요청했다. 이 상황에서 올바른 진술은? | 팀이 스프린트 시작 후 너무 많은 작업을 수락하고 있다 | 제품 책임자가 팀에게 스프린트 약속을 변경하도록 요청해서는 안 된다 | 팀이 제품 책임자의 기대를 충족하지 못하고 있다 | 팀은 4일차에 중단하고 새 스프린트를 시작했어야 한다 |  | C | 정답은 C이다. 팀이 제품 책임자의 기대를 충족하지 못하고 있다. 제품 책임자는 제품 백로그 관리와 우선순위 정의를 담당한다. 팀이 일관되게 약속보다 적게 전달하는 것은 기대 불충족을 나타낸다. 스프린트 중 과다 작업(A)은 원인이지 진술이 아니다. 약속 변경 금지(B)는 애자일 유연성에 반한다. 중단 후 재시작(D)은 스크럼 프레임워크에 맞지 않는다.
1183 | A project manager is working on the budget for a long-term project. The project manager creates a work breakdown structure (WBS) and estimates the cost for each work package based on past projects. What else does the project manager need to do before determining the budget baseline? | Add contingency into the budget for inflation and other changes. | Look at a previous project to ensure the budget totals match. | Revise the project timeline and scope based on the WBS. | Require all stakeholders to review and approve the estimates. |  | A | After creating a WBS and estimating costs based on past projects, the project manager needs to add contingency into the budget for inflation and other changes before determining the budget baseline. Contingency reserves account for identified risks (known unknowns) that may affect project costs. Looking at a previous project for matching totals (B) does not build a proper baseline. Revising timeline and scope (C) is unrelated to budget baseline creation. Requiring stakeholder approval of estimates (D) is a governance step, not a budgeting input. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | WBS/Decomposition | Business Environment | Plan and Manage Risk | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | PM이 장기 프로젝트의 예산을 작업하고 있다. WBS를 만들고 과거 프로젝트를 기반으로 비용을 추정했다. 예산 기준선을 결정하기 전에 PM은 무엇을 해야 하는가? | 인플레이션 및 기타 변경에 대한 비상 예비비를 예산에 추가한다 | 이전 프로젝트를 참고하여 예산 총액이 일치하는지 확인한다 | WBS를 기반으로 프로젝트 일정과 범위를 수정한다 | 모든 이해관계자에게 추정치를 검토하고 승인하도록 요구한다 |  | A | WBS를 만들고 과거 프로젝트를 기반으로 비용을 추정한 후, PM은 예산 기준선을 결정하기 전에 인플레이션 및 기타 변경에 대한 비상 예비비를 추가해야 한다. 비상 예비비는 장기 프로젝트의 불확실성을 관리한다. 이전 프로젝트 비교(B)는 유사 추정이지만 비상 예비비를 대체하지 않는다. 일정/범위 수정(C)은 예산 단계가 아니다. 이해관계자 승인(D)은 비상 예비비 추가 후에 한다.
1184 | A vendor has manufactured a complex product. During a factory acceptance test, several deficiencies were identified. Product delivery is on the critical path, and any delay would impact project completion. What should the project manager do? | Ship the package as is, complete carryover work on-site, and back charge the vendor for the rework. | Assess the schedule impact and evaluate the most feasible solution to keep the project on track. | Hold the shipment until the rework is completed at the vendor ' s facility to eliminate extra work on-site. | Initiate regular conference calls with the vendor for status updates to keep this item in focus. |  | B | When a factory acceptance test reveals deficiencies in a product on the critical path, the project manager should assess the schedule impact and evaluate the most feasible solution to keep the project on track. Informed analysis enables optimal decision-making. Shipping as-is with on-site rework (A) risks quality and cost. Holding shipment until rework completes (C) may unnecessarily extend the schedule. Initiating conference calls for status updates (D) monitors but does not resolve. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Critical Path/Schedule Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 벤더가 복잡한 제품을 제조했다. 공장 인수 시험 중 여러 결함이 식별되었다. 제품이 주공정선에 있다. PM은 무엇을 해야 하는가? | 그대로 출하하고 현장에서 잔여 작업을 완료하며 벤더에게 재작업 비용을 청구한다 | 일정 영향을 평가하고 프로젝트를 정상 궤도에 유지하기 위한 가장 실행 가능한 해결책을 평가한다 | 벤더 시설에서 재작업이 완료될 때까지 출하를 보류하여 현장 추가 작업을 제거한다 | 벤더와 정기 전화 회의를 시작하여 이 항목에 대한 상태 업데이트를 지속한다 |  | B | 공장 인수 시험에서 주공정선상의 제품에 결함이 발견되면, PM은 일정 영향을 평가하고 가장 실행 가능한 해결책을 평가해야 한다. 이는 균형 잡힌 의사결정을 가능하게 한다. 그대로 출하(A)는 현장 품질 문제 리스크가 있다. 재작업 완료까지 보류(C)는 일정을 무시한다. 정기 회의(D)는 상태 추적이지 해결이 아니다.
1185 | A project team member informs the project manager that a stakeholder is contacting the team member to request status updates. The team member is being distracted by these repeated requests, which are interfering with the completion of assigned tasks. What should the project manager do? | Review this stakeholder ' s communication requirements. | Increase the frequency of updates given to this stakeholder. | Raise this issue to the project sponsor in the next project status review meeting. | Inform the team member to stop sending any further updates to the stakeholder. |  | A | When a stakeholder repeatedly contacts a team member for status updates causing distraction, the project manager should review the stakeholder's communication requirements. Understanding and addressing their information needs prevents disruption. Increasing update frequency (B) adds work without understanding the need. Raising the issue to the sponsor (C) escalates before addressing it. Stopping all updates to the stakeholder (D) is extreme. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 팀원이 PM에게 이해관계자가 직접 상태 업데이트를 요청하여 업무에 방해가 된다고 알린다. PM은 무엇을 해야 하는가? | 이 이해관계자의 커뮤니케이션 요구사항을 검토한다 | 이 이해관계자에게 주는 업데이트 빈도를 늘린다 | 다음 프로젝트 상태 검토 회의에서 스폰서에게 이 이슈를 제기한다 | 팀원에게 이해관계자에게 더 이상 업데이트를 보내지 않도록 지시한다 |  | A | 이해관계자가 팀원에게 직접 상태 업데이트를 반복 요청하여 방해가 될 때, PM은 이해관계자의 커뮤니케이션 요구사항을 검토해야 한다. 근본적 요구를 이해하고 해결하는 것이 적절한 대응이다. 빈도 증가(B)는 요구 분석 없이 성급하다. 스폰서 제기(C)는 직접 해결 전에 에스컬레이션이다. 업데이트 중단(D)은 이해관계자 요구를 무시한다.
1186 | A project is 70% complete when the project sponsor requests an additional deliverable. What should the project manager do first? | Determine the possible impact of this change on all aspects of the project. | Negotiate with the project sponsor on the possible alternatives. | Reject the request as being too late and leading to major scope creep. | Submit the request to the change control board (CCB) for a decision. |  | A | When the project sponsor requests an additional deliverable at 70% project completion, the project manager should first determine the possible impact of this change on all aspects of the project—including scope, schedule, cost, quality, resources, and risks. Impact analysis is the essential first step before any decisions, negotiations, or submissions to the change control board. Negotiating alternatives with the sponsor (B) is premature without understanding the full impact. Rejecting the request (C) is inappropriate without analysis. Submitting to the CCB (D) should follow the impact assessment, not precede it. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 70% 완료되었을 때 스폰서가 추가 인도물을 요청한다. PM은 무엇을 먼저 해야 하는가? | 이 변경이 프로젝트의 모든 측면에 미치는 가능한 영향을 결정한다 | 프로젝트 스폰서와 가능한 대안에 대해 협상한다 | 너무 늦었고 주요 범위 변경을 초래하므로 요청을 거부한다 | 변경통제위원회(CCB)에 결정을 위해 요청을 제출한다 |  | A | 프로젝트 스폰서가 70% 완료 시점에 추가 인도물을 요청할 때, PM은 먼저 이 변경이 프로젝트의 모든 측면—일정, 비용, 범위, 품질—에 미치는 영향을 결정해야 한다. 영향 분석이 정보에 기반한 결정의 기초이다. 대안 협상(B)은 영향 분석 후에 한다. 거부(C)는 스폰서 요청을 무시한다. CCB 제출(D)은 영향 분석 후에 한다.
1187 | A project manager has been assigned to a project that is in progress. The project manager is looking for information regarding why the project is being completed. What should the project manager do first? | Reach out to the senior executive sponsor for the project. | Evaluate the project exit criteria in the project charter. | Understand the project success criteria and objectives. | Review the project status reporting for the latest information. |  | C | When a project manager is newly assigned to an in-progress project and wants to understand why the project is being done, they should first understand the project success criteria and objectives. This establishes purpose and alignment. Reaching out to the senior sponsor (A) is one input but not the first action. Evaluating exit criteria in the charter (B) focuses on closure, not purpose. Reviewing status reports (D) provides current state, not rationale. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | PM이 진행 중인 프로젝트에 새로 배정되었다. PM이 프로젝트가 왜 수행되는지에 대한 정보를 찾고 있다. PM은 무엇을 먼저 해야 하는가? | 프로젝트의 고위 경영 스폰서에게 연락한다 | 프로젝트 헌장에서 프로젝트 종료 기준을 평가한다 | 프로젝트 성공 기준과 목표를 이해한다 | 최신 정보를 위한 프로젝트 상태 보고를 검토한다 |  | C | 새로 배정된 PM이 프로젝트가 왜 수행되는지 이해하려면, 먼저 프로젝트 성공 기준과 목표를 이해해야 한다. 이는 프로젝트의 목적과 근거를 제공한다. 스폰서 연락(A)은 문서 검토 후에 한다. 종료 기준(B)은 '왜'가 아닌 '언제' 끝나는지이다. 상태 보고(D)는 현재 진행 상황이지 목적이 아니다.
1188 | A project is nearing completion. The contingency time has been consumed. To ensure that the final deliverables are achieved within budget, the project manager has asked the team to follow a rigorous process. This is causing some resistance among the team members. What should the project manager do to address the growing resistance? | Motivate project team members by offering incentives to complete the project on time | Describe to the team members how specific tools and techniques can be used to finish on time | Convince team members to use a specific methodology to complete the project on time | Crash the project schedule and ask project team members to work overtime to meet the new timeline |  | B | When contingency time is consumed and the team resists a rigorous process to finish on budget, the project manager should describe how specific tools and techniques can be used to finish on time. Educating the team on the rationale builds understanding and buy-in. Offering incentives (A) does not address the root cause of resistance. Convincing them to use a specific methodology (C) is prescriptive. Crashing the schedule with overtime (D) risks errors, burnout, and resentment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Schedule | Planning | Build an Empowered Culture | Define Activities | Traditional PM | 프로젝트가 완료에 가까워졌다. 비상 시간이 소진되었다. 팀이 엄격한 프로세스에 저항한다. PM은 무엇을 해야 하는가? | 프로젝트를 제시간에 완료하도록 인센티브를 제공하여 팀원에게 동기를 부여한다 | 특정 도구와 기법이 제시간에 완료하는 데 어떻게 사용될 수 있는지 팀원에게 설명한다 | 특정 방법론을 사용하여 프로젝트를 제시간에 완료하도록 팀원을 설득한다 | 프로젝트 일정을 크래싱하고 팀원에게 새 일정을 맞추기 위해 초과 근무를 요청한다 |  | B | 비상 시간이 소진되고 팀이 엄격한 프로세스에 저항할 때, PM은 특정 도구와 기법이 제시간에 완료하는 데 어떻게 사용될 수 있는지 설명해야 한다. 교육과 설명이 이해와 수용을 촉진한다. 인센티브(A)는 행동 변화를 보장하지 않는다. 설득(C)은 이해 없는 강요이다. 크래싱(D)은 비용 증가와 번아웃 리스크가 있다.
1189 | An agile project is running its fifth iteration out of eight. After the last iteration planning, the team was informed that there is a new competitor in the market and it is necessary to move faster to ensure market share is not missed. What should the project manager do? | Help the team to find a new approach to launch the product as soon as possible | Add the competitor ' s functionalities to the product backlog to improve the product | Ask the team to increase the velocity to launch the product as soon as possible | Ask the sponsor to add more people to the team |  | A | When a new competitor requires the agile team to move faster mid-project, the project manager should help the team find a new approach to launch the product as soon as possible. Adaptive replanning focuses on value delivery. Adding competitor features to the backlog (B) increases scope and delays delivery. Adding people (D) may cause Brooks' law effects. Asking the team to increase velocity (C) pressures the team without a strategy. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Lean | Process | Plan and Optimize Quality | Scope | Planning | Integrate Sustainability | Plan Scope Management | Sustainability | 애자일 프로젝트가 8번째 이터레이션 중 5번째를 진행 중이다. 새 경쟁자가 등장하여 더 빨리 진행해야 한다. PM은 무엇을 해야 하는가? | 팀이 가능한 빨리 제품을 출시할 새로운 접근법을 찾도록 돕는다 | 경쟁사의 기능을 제품 백로그에 추가하여 제품을 개선한다 | 팀에게 가능한 빨리 제품을 출시하도록 속도를 높이라고 요청한다 | 스폰서에게 팀에 더 많은 인원을 추가하도록 요청한다 |  | A | 새 경쟁자로 인해 애자일 팀이 더 빨리 진행해야 할 때, PM은 팀이 가능한 빨리 제품을 출시할 새로운 접근법을 찾도록 도와야 한다. 적응적 재계획이 변화에 대응한다. 경쟁사 기능 추가(B)는 범위 확장이다. 속도 증가 요청(C)은 비현실적이다. 인원 추가(D)는 즉각적 효과가 없다.
1190 | A project team is using one of the visual management tools to identify dependencies. It was identified that domain knowledge from one team needs to be shared with another team to ensure the continuity of deliverables. What should the project manager do? | Request the respective teams to plan for knowledge-sharing sessions. | Redistribute the team members so knowledge is available in both teams. | Merge both teams into one team so the knowledge is commonly available. | Remove the dependency to eliminate the need for knowledge sharing. |  | A | When a visual management tool identifies a knowledge dependency between teams, the project manager should request the respective teams to plan for knowledge-sharing sessions. Organized knowledge transfer ensures critical domain expertise flows to the team that needs it, maintaining deliverable continuity. Redistributing team members (B) is disruptive and may cause other issues. Merging both teams (C) is excessive for a knowledge-sharing need. Removing the dependency (D) may not be possible and ignores the legitimate need for domain knowledge. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트 팀이 시각적 관리 도구를 사용하여 종속성을 식별하고 있다. 팀 간 도메인 지식 종속성이 식별되었다. PM은 무엇을 해야 하는가? | 해당 팀에 지식 공유 세션을 계획하도록 요청한다 | 지식이 양 팀에서 가용하도록 팀원을 재배치한다 | 지식이 공통적으로 가용하도록 두 팀을 하나로 합병한다 | 지식 공유 필요를 제거하기 위해 종속성을 제거한다 |  | A | 시각적 관리 도구가 팀 간 지식 종속성을 식별할 때, PM은 해당 팀에 지식 공유 세션을 계획하도록 요청해야 한다. 조직화된 지식 전달이 팀 구조를 유지하면서 종속성을 해결한다. 팀원 재배치(B)는 팀 역학을 방해한다. 팀 합병(C)은 과도한 조치이다. 종속성 제거(D)는 비현실적일 수 있다.
1191 | A project manager invites the company CEO, sponsor, team members, and an external client representative to a meeting to review the project management plan. The project manager starts to present the budget, but the CEO suddenly asks to end the meeting. What should the project manager have done to avoid this situation? | Reviewed the cost management plan with internal participants and CEO prior to inviting an external client representative to the meeting | Reviewed the communications management plan before inviting an external client representative to the meeting | Sent the presentation slides to internal participants first and then to the external client representative prior to the meeting | Performed a root cause analysis with the external client representative and documented the findings in the lessons learned register |  | B | The project manager should have reviewed the communications management plan before inviting an external client representative to the meeting. This plan defines communication requirements, methods, channels, and confidentiality levels for different stakeholders. By not reviewing it, the PM may have presented budget information that was not authorized for external disclosure—likely prompting the CEO to end the meeting abruptly. Reviewing the cost management plan with internal participants first (A) is a good practice but does not ensure the information shared externally was appropriate and authorized. Sending slides to participants in advance (C) is helpful but does not guarantee the content was cleared for external communication. Performing a root cause analysis afterward (D) addresses the situation reactively rather than preventing it. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Traditional Plan-Driven | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | PM이 CEO, 스폰서, 팀원, 외부 고객 대표를 회의에 초대하여 프로젝트 비용 초과를 논의한다. PM이 이전에 무엇을 했어야 하는가? | 외부 고객 대표 초대 전에 내부 참석자 및 CEO와 비용 관리 계획을 검토했다 | 외부 고객 대표를 회의에 초대하기 전에 커뮤니케이션 관리 계획을 검토했다 | 내부 참석자에게 먼저 프레젠테이션 슬라이드를 보낸 후 외부 고객 대표에게 보냈다 | 외부 고객 대표와 근본 원인 분석을 수행하고 결과를 문서화했다 |  | B | PM은 외부 고객 대표를 회의에 초대하기 전에 커뮤니케이션 관리 계획을 검토했어야 한다. 이 계획은 커뮤니케이션 요구사항, 방법, 채널 및 적절한 참석자를 정의한다. 내부 비용 검토(A)는 부분적 조치이다. 슬라이드 선공유(C)는 참석 적절성을 다루지 않는다. 외부와의 RCA(D)는 내부 문제를 외부에 노출한다.
1192 | After a project status meeting, the project manager realizes that the project is under budget, quality checks are positive, and the schedule variance is negative. How should the project manager qualify the project status? | On schedule | Behind schedule | Ahead of schedule | Stopped |  | B | When a project is under budget with positive quality checks but has negative schedule variance, the project status is behind schedule. Negative schedule variance means earned value is less than planned value—the project has completed less work than planned. On schedule (A) contradicts the negative variance. Ahead of schedule (C) is the opposite. Stopped (D) is incorrect as work continues. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Earned Value Management | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 상태 회의 후, PM이 프로젝트가 예산 미만이고 품질 점검은 긍정적이지만 일정 차이가 부정적임을 파악했다. 프로젝트 상태는? | 일정 준수 | 일정 지연 | 일정 앞당김 | 중지 |  | B | 프로젝트가 예산 미만이고 품질 점검이 긍정적이지만 일정 차이가 부정적이면, 프로젝트 상태는 일정 지연이다. 부정적 일정 차이는 획득가치가 계획가치보다 적다는 것을 의미하며 작업이 계획보다 뒤처져 있음을 나타낸다.
1193 | During project planning activities, a project manager identifies potential delays in obtaining resources required for a project. This will significantly impact the construction timeline. What should the project manager do? | Delay the project until additional resources can be identified. | Speak with the project sponsors about changing the project management plan. | Review and update the project management plan to accommodate the delays. | Create a change request to increase the cost of resources. |  | C | The correct answer is C. Review and update the project management plan to accommodate the delays. Schedule management requires proactive monitoring and appropriate corrective actions. The PM should analyze impacts and implement suitable responses to maintain project timelines. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 계획 활동 중 PM이 주요 구성 요소에 필요한 자원 확보에 잠재적 지연을 식별했다. PM은 무엇을 해야 하는가? | 추가 자원이 식별될 때까지 프로젝트를 지연시킨다 | 프로젝트 관리 계획 변경에 대해 프로젝트 스폰서와 대화한다 | 지연을 수용하기 위해 프로젝트 관리 계획을 검토하고 업데이트한다 | 자원 비용 증가를 위한 변경 요청을 생성한다 |  | C | 정답은 C이다. 지연을 수용하기 위해 프로젝트 관리 계획을 검토하고 업데이트한다. 일정 관리는 사전적 모니터링과 적절한 시정 조치가 필요하다. PM은 지연을 분석하고 계획을 업데이트해야 한다. 프로젝트 지연(A)은 수동적이다. 스폰서 대화(B)는 계획 업데이트 후에 한다. 비용 변경 요청(D)은 자원 확보 문제의 해결이 아니다.
1194 | A healthcare company is in the process of deploying an innovative healthcare solution globally. The project team has completed a limited release. The stakeholders have raised concerns about global healthcare guidelines and risks. What should the project manager do next? | Perform a qualitative risk analysis on the identified project risks. | Conduct a feasibility analysis of deploying the solution globally. | Evaluate lessons learned from similar projects prior to deployment. | Review compliance and regulatory requirements with stakeholders. |  | D | After completing a limited release of a global healthcare solution and receiving stakeholder concerns about guidelines and risks, the project manager should review compliance and regulatory requirements with stakeholders. This proactive step ensures the project aligns with global healthcare standards and addresses regulatory non-compliance risks before further deployment. Performing qualitative risk analysis (A) focuses on risk scoring rather than regulatory alignment. Conducting a feasibility analysis (B) is relevant but secondary to compliance review. Evaluating lessons learned (C) provides historical context but does not directly address current regulatory concerns. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Business Environment | Plan and Manage Compliance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 의료 회사가 글로벌 혁신 헬스케어 솔루션을 배포 중이다. 팀이 제한된 출시를 완료했다. 이해관계자가 가이드라인과 리스크에 대한 우려를 표명한다. PM은 무엇을 해야 하는가? | 식별된 프로젝트 리스크에 대한 정성적 리스크 분석을 수행한다 | 글로벌 솔루션 배포의 실행 가능성 분석을 수행한다 | 배포 전 유사 프로젝트의 교훈을 평가한다 | 이해관계자와 컴플라이언스 및 규제 요구사항을 검토한다 |  | D | 글로벌 헬스케어 솔루션의 제한된 출시 후 이해관계자가 가이드라인과 리스크에 우려를 표명할 때, PM은 이해관계자와 컴플라이언스 및 규제 요구사항을 검토해야 한다. 헬스케어에서 규제 준수가 핵심이다. 정성적 리스크 분석(A)은 규제 요구를 직접 다루지 않는다. 실행 가능성 분석(B)은 출시 후에는 늦다. 교훈 평가(C)는 유용하지만 즉각적 규제 검토가 우선이다.
1195 | An agile project has a broad set of product features intended for different user profiles and usages. It is difficult to define common acceptance criteria that can apply to all the features. How can the project manager ensure that the appropriate acceptance criteria are applied to the features? | Use the broadest set of acceptance criteria to ensure that all features have a common quality baseline and associated functional test cases. | Integrate the specific tests into the definition of ready (DoR) for each feature and the acceptance criteria into the feature ' s definition of done (DoD). | Integrate the acceptance criteria review into the definition of ready (DoR) for each feature and associated tests into the feature ' s definition of done (DoD). | Define the acceptance criteria and specific functional test cases only after analyzing the user feedback from testing the early feature release. |  | C | When a project has diverse features for different user profiles making common acceptance criteria difficult, the project manager should integrate the acceptance criteria review into the definition of ready (DoR) for each feature and associated tests into the feature's definition of done (DoD). This ensures each feature's unique requirements are clearly understood before development begins and verified before completion. Using the broadest acceptance criteria (A) sacrifices specificity and may not adequately test all features. Integrating specific tests into DoR and criteria into DoD (B) reverses the logical order—criteria should be ready before development, and tests should confirm completion. Defining criteria only after user feedback (D) delays quality assurance and may result in rework. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 애자일 프로젝트에 다양한 사용자 프로필을 위한 광범위한 제품 기능이 있다. 공통 인수 기준을 정의하기 어렵다. PM은 무엇을 해야 하는가? | 모든 기능에 공통 품질 기준을 보장하기 위해 가장 광범위한 인수 기준을 사용한다 | 각 기능의 준비 완료 정의(DoR)에 특정 테스트를 통합하고 인수 기준은 이터레이션 중에 정의한다 | 각 기능의 DoR에 인수 기준 검토를 통합하고 각 기능에 특정 테스트 케이스를 할당한다 | 사용자 피드백 분석 후에만 인수 기준과 기능 테스트 케이스를 정의한다 |  | C | 다양한 사용자 프로필을 위한 기능으로 공통 인수 기준이 어려울 때, PM은 각 기능의 준비 완료 정의(DoR)에 인수 기준 검토를 통합하고 특정 테스트 케이스를 할당해야 한다. 이는 각 기능별 맞춤 품질 보장을 제공한다. 광범위한 기준(A)은 구체성이 부족하다. DoR에 테스트만 통합(B)은 인수 기준을 늦게 정의한다. 피드백 후 정의(D)는 너무 늦다.
1196 | A project manager was recently assigned to work on a hybrid project. After being a part of the project team for a couple of months, the project manager realizes that parts of this project depend on other organizational projects. These dependencies have not been identified. What should the project manager do first? | Host a retrospective session with the agile team. | Review the risk register and update it if necessary. | Ignore the concerns for now and review them in 3 months. | Brainstorm with the team and stakeholders to identify the risks. |  | D | The correct answer is D. Brainstorm with the team and stakeholders to identify the risks. A hybrid approach combines predictive and agile methodologies to suit project needs. The PM should tailor the approach based on project characteristics and organizational context. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Hybrid | Predictive-Agile Blend | Process | Manage Project Closure | Governance | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | PM이 최근 하이브리드 프로젝트에 배정되었다. 팀에 합류한 후 여러 팀원으로부터 우려를 받았다. PM은 무엇을 해야 하는가? | 애자일 팀과 회고 세션을 개최한다 | 리스크 등록부를 검토하고 필요 시 업데이트한다 | 당분간 우려를 무시하고 3개월 후 검토한다 | 팀과 이해관계자와 브레인스토밍하여 리스크를 식별한다 |  | D | 정답은 D이다. 팀과 이해관계자와 브레인스토밍하여 리스크를 식별한다. 하이브리드 접근법은 예측형과 애자일 방법론을 결합한다. PM은 프로젝트 요구에 맞게 접근법을 조정하고 팀의 우려를 리스크로 식별해야 한다. 회고(A)는 이터레이션 후 활동이다. 리스크 등록부 검토(B)는 기존 리스크만 다룬다. 무시(C)는 무책임하다.
1197 | An urgent meeting has been established with the project team to discuss the cause of some quality issues that are preventing delivery to the client. The product owner recommends a root cause analysis (RCA). What should the project lead do? | Facilitate the meeting so anyone can share their ideas and is heard during the session. | Discuss the recommendations with the test manager and request better quality control. | Allow the team to self-organize so one of the resources can lead the team to achieve consensus. | Discuss the product owner ' s recommendations with the team and implement the agreed- on solutions. |  | A | When the product owner recommends root cause analysis for quality issues preventing delivery, the project lead should facilitate the meeting so anyone can share their ideas and is heard. Inclusive facilitation ensures comprehensive analysis of all contributing factors. Discussing with the test manager and requesting better QC (B) narrows the investigation. Allowing self-organization for consensus (C) may lack structure. Discussing the PO's recommendations and implementing agreed solutions (D) skips the RCA process. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 제품 책임자가 납품을 방해하는 품질 문제의 원인을 논의하기 위한 긴급 회의가 설정되었다. 프로젝트 리더는 무엇을 해야 하는가? | 누구나 아이디어를 공유하고 세션에서 경청되도록 회의를 퍼실리테이션한다 | 테스트 매니저와 권장 사항을 논의하고 더 나은 품질 관리를 요청한다 | 팀이 자체 조직화하여 자원 중 하나가 합의를 이끌도록 한다 | 제품 책임자의 권장 사항을 팀과 논의하고 합의된 솔루션을 구현한다 |  | A | 제품 책임자가 품질 문제의 근본 원인 분석을 권장할 때, 프로젝트 리더는 누구나 아이디어를 공유하고 경청되도록 회의를 퍼실리테이션해야 한다. 포용적 퍼실리테이션이 포괄적 근본 원인 분석을 가능하게 한다. 테스트 매니저와만 논의(B)는 제한적이다. 자체 조직화(C)는 긴급 상황에서 방향이 부족할 수 있다. 권장 사항만 논의(D)는 다른 관점을 제한한다.
1198 | During the execution of a project, a project manager is informed that a team member is leaving the company. What should the project manager do next? | Freeze the activities of the lost resource until they are replaced. | Record the situation in the issue log immediately and evaluate the impact of losing the resource. | Ask the project sponsor to replace the resource immediately. | Wait for the next project status meeting to evaluate the impact of one less resource. |  | B | The correct answer is B. Record the situation in the issue log immediately and evaluate the impact of losing the resource. Resource management includes ensuring the team has adequate skills, capacity, and support. The PM should address resource gaps and challenges proactively to maintain project delivery. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 중 PM이 팀원이 회사를 떠날 것이라는 통보를 받았다. PM은 무엇을 해야 하는가? | 대체될 때까지 해당 자원의 활동을 동결한다 | 이슈 로그에 상황을 즉시 기록하고 자원 손실의 영향을 평가한다 | 프로젝트 스폰서에게 자원을 즉시 교체하도록 요청한다 | 다음 프로젝트 상태 회의까지 기다려 자원 감소의 영향을 평가한다 |  | B | 정답은 B이다. 이슈 로그에 상황을 즉시 기록하고 자원 손실의 영향을 평가한다. 자원 관리는 팀의 적절한 기술, 역량 및 가용성을 보장하는 것을 포함한다. 즉각적 문서화와 영향 평가가 적절한 대응의 기초이다. 활동 동결(A)은 프로젝트를 지연시킨다. 즉시 교체 요청(C)은 영향 평가 전에 성급하다. 대기(D)는 시간을 낭비한다.
1199 | The vendor for a new IT data center project failed to follow the required cabling standards as stated in the requirements specification. The infrastructure manager and vendor were involved in an argument about the issue. What should the project manager do to resolve and prevent additional arguments? | Instruct the vendor to correct the problem without additional arguments. | Host a meeting with the vendor and infrastructure manager to help resolve their disagreement. | Monitor the interactions between the vendor and infrastructure manager going forward. | Escalate the issue to the sponsor so appropriate action can be taken. |  | B | When a vendor fails to follow required cabling standards and argues with the infrastructure manager, the project manager should host a meeting with both parties to help resolve their disagreement. Facilitated communication enables negotiation and problem-solving. Instructing the vendor to fix the problem (A) does not address the relationship. Monitoring future interactions (C) is passive. Escalating to the sponsor (D) is premature before attempting resolution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 IT 데이터 센터 프로젝트의 벤더가 요구사항에 명시된 케이블링 표준을 따르지 않았고 인프라 관리자와 논쟁했다. PM은 무엇을 해야 하는가? | 벤더에게 추가 논쟁 없이 문제를 수정하도록 지시한다 | 벤더와 인프라 관리자와 회의를 개최하여 불일치를 해결하도록 돕는다 | 향후 벤더와 인프라 관리자 간의 상호작용을 모니터링한다 | 적절한 조치를 취할 수 있도록 스폰서에게 이슈를 에스컬레이션한다 |  | B | 벤더가 케이블링 표준을 따르지 않고 인프라 관리자와 논쟁할 때, PM은 양측과 회의를 개최하여 불일치를 해결해야 한다. 퍼실리테이션된 대화가 협력적 해결을 가능하게 한다. 수정 지시(A)는 지시적이며 관계를 훼손한다. 모니터링(C)은 수동적이다. 에스컬레이션(D)은 직접 해결 시도 전에 시기상조이다.
1200 | A project manager notices that a team member is upset during a team meeting. The project manager assesses the situation and determines that the team member does not collaborate with some of the other team members. What should the project manager do? | Evaluate upcoming project deadlines and reorganize team member assignments. | Review team participation in the next retrospective meeting with all team members. | Reach out to the team member to discuss and address their concerns as soon as possible. | Give some advice to the team member to reduce their stress and anxiety. |  | C | When a project manager observes that a team member is upset and not collaborating well with others, the best approach is to reach out to that team member directly and privately to discuss and address their concerns as soon as possible. This demonstrates emotional intelligence, empathy, and supports psychological safety within the team. Reorganizing assignments (A) is superficial and does not address the root cause of the interpersonal issue. Reviewing participation in a retrospective (B) may expose sensitive issues publicly and worsen team dynamics. Giving general advice to reduce stress (D) is dismissive and does not target the specific collaboration problem. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 팀 회의 중 팀원이 화가 난 것을 발견한다. PM은 무엇을 해야 하는가? | 다가오는 프로젝트 기한을 평가하고 팀원 배정을 재조직한다 | 다음 회고 회의에서 모든 팀원과 참여를 검토한다 | 가능한 빨리 팀원에게 연락하여 우려를 논의하고 해결한다 | 팀원에게 스트레스와 불안을 줄이기 위한 조언을 한다 |  | C | 팀원이 화가 나고 다른 사람과 잘 협력하지 않는 것을 관찰할 때, PM은 가능한 빨리 개인적으로 연락하여 우려를 논의하고 해결해야 한다. 직접적이고 사적인 접근이 감정적 지능을 보여준다. 기한 평가(A)는 감정적 문제를 다루지 않는다. 회고 대기(B)는 너무 늦다. 조언(D)은 경청 전에 판단적이다.
1201 | A project is on schedule. However, during a site visit, a project manager notices that the contractor's productivity is low. What should the project manager do? | Assess the opportunity to deliver the project ahead of schedule and introduce a reward system. | Update the project schedule to align with the contractor ' s productivity. | Discuss the need to increase productivity with the contractor. | Plan the close-out activities since the project is on schedule. |  | C | The correct answer is C. Discuss the need to increase productivity with the contractor. Schedule management requires proactive monitoring and timely corrective actions. The PM should analyze schedule impacts, evaluate options, and implement appropriate responses to keep the project on track. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트가 일정에 맞지만 현장 방문 중 PM이 계약자의 생산성이 기대보다 높은 것을 발견했다. PM은 무엇을 해야 하는가? | 일정보다 앞서 프로젝트를 납품할 기회를 평가하고 보상 시스템을 도입한다 | 계약자의 생산성에 맞게 프로젝트 일정을 업데이트한다 | 계약자와 생산성을 높일 필요성을 논의한다 | 프로젝트가 일정에 맞으므로 종료 활동을 계획한다 |  | C | 정답은 C이다. 계약자와 생산성을 높일 필요성을 논의한다. 일정 관리는 사전적 모니터링과 시기적절한 시정 조치가 필요하다. 현재 일정에 맞더라도 생산성 기대를 명확히 하고 개선을 논의하는 것이 적절하다. 일정 앞당김(A)은 불필요한 압력을 줄 수 있다. 일정 업데이트(B)는 현재 일정에 맞으므로 불필요하다. 종료 계획(D)은 시기상조이다.
1202 | An agile project is in the seventh iteration with multiple changes being accommodated from the project start, such as regulatory changes, technological innovations, market competition, and other changes. What should the project manager do to manage these continuous changes coming into the project? | Leverage the product owner to monitor the external environment | Ask the product owner to stop accommodating further changes to the scope | Accommodate the critical and urgent changes in the current iteration | Suggest to the product owner to execute the changes in a separate project |  | C | When an agile project in its seventh iteration faces continuous changes from regulatory, technology, market, and other sources, the project manager should accommodate critical and urgent changes in the current iteration. Agile embraces change for competitive advantage. Leveraging the PO to monitor the environment (A) is passive. Asking the PO to stop changes (B) contradicts agile principles. Executing changes in a separate project (D) fragments the effort. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 애자일 프로젝트가 7번째 이터레이션에 있으며 규제, 기술, 시장 등 다양한 소스에서 지속적 변경이 수용되고 있다. PM은 무엇을 해야 하는가? | 제품 책임자를 활용하여 외부 환경을 모니터링한다 | 제품 책임자에게 더 이상의 범위 변경 수용을 중단하도록 요청한다 | 현재 이터레이션에서 중요하고 긴급한 변경을 수용한다 | 제품 책임자에게 변경을 별도 프로젝트에서 실행하도록 제안한다 |  | C | 애자일 프로젝트가 다양한 소스의 지속적 변경에 직면할 때, PM은 현재 이터레이션에서 중요하고 긴급한 변경을 수용해야 한다. 우선순위 기반 변경 수용이 애자일 원칙에 부합한다. 외부 환경 모니터링(A)은 대응이 아닌 관찰이다. 변경 중단(B)은 애자일 원칙에 반한다. 별도 프로젝트(D)는 긴급한 변경에 대응하지 않는다.
1203 | A senior employee with experience relevant to a highly complex project is seeking a promotion to be able to join the project. The employee has made a recommendation regarding the project. The project charter was recently approved. How should the project manager handle the employee's request? | Assess the influence and power of the employee to see if the employee will add value. | Evaluate the employee ' s recommendation by reviewing the lessons learned from a similar project. | Create a salience model to determine if the employee will have influence on the project. | Ask the project sponsor to revisit the project charter to consider the employee ' s recommendation. |  | A | The PM should evaluate the employee's influence, power, and potential value-add to the project before making a decision about their involvement. This assessment should consider the employee's experience, skills, and the relevance of their recommendation to project objectives. The recently approved project charter provides the PM with the authority to make such assessments. Aligning the employee's capabilities with project needs ensures their involvement contributes positively to project success. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 고도로 복잡한 프로젝트에 관련 경험이 있는 선임 직원이 프로젝트에 참여하기 위해 승진을 원한다. PM은 무엇을 먼저 해야 하는가? | 직원의 영향력과 권한을 평가하여 가치를 추가할지 확인한다 | 유사 프로젝트의 교훈을 검토하여 직원의 추천을 평가한다 | 현저성 모델을 만들어 직원이 프로젝트에 영향력이 있는지 결정한다 | 프로젝트 스폰서에게 직원의 추천을 고려하여 프로젝트 헌장을 재검토하도록 요청한다 |  | A | 선임 직원이 프로젝트 참여를 위해 승진을 원할 때, PM은 먼저 직원의 영향력과 권한을 평가하여 프로젝트에 가치를 추가할지 확인해야 한다. 직원의 경험, 기술, 프로젝트에 대한 잠재적 기여를 고려해야 한다. 교훈 검토(B)는 직원 평가가 아니다. 현저성 모델(C)은 이해관계자 분석이지 팀원 결정이 아니다. 헌장 재검토(D)는 과도한 조치이다.
1204 | A system migration project is in its closing stage. The project manager is being pressured to close the project. The project manager communicated to all stakeholders; however, the last department to migrate indicated that they have not received the notification. What should the project manager do? | Escalate the issue to the project sponsor and upper management | Log the issue and assign it to the project team member(s). | Report the issue during the next status meeting at the end of the week | Close out the project and tell the manager to open a service desk ticket |  | B | The PM should use the issue log to document the missing notification and assign resolution to the appropriate team member(s). Prompt communication with relevant stakeholders and updates to the project management plan are also necessary. The project should not be closed until all departments have completed their migration and outstanding issues are resolved. Escalating prematurely to upper management suggests a lack of project control, while deferring the issue to the next status meeting introduces unnecessary delay. Proactive, timely action is essential for successful project closure. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Stakeholders | Closing | Embed Quality | Close Project or Phase | Traditional PM | 시스템 마이그레이션 프로젝트가 종료 단계에 있다. PM이 종료를 서두르도록 압박받고 있다. 관리자가 알림이 전송되지 않는 문제를 발견했다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서와 상위 경영진에게 이슈를 에스컬레이션한다 | 이슈를 로그에 기록하고 프로젝트 팀원에게 할당한다 | 주말 다음 상태 회의에서 이슈를 보고한다 | 프로젝트를 종료하고 관리자에게 서비스 데스크 티켓을 열도록 말한다 |  | B | PM은 이슈 로그를 사용하여 누락된 알림을 문서화하고 적절한 팀원에게 해결을 할당해야 한다. 신속한 이해관계자 커뮤니케이션과 프로젝트 문서 업데이트가 중요하다. 에스컬레이션(A)은 직접 해결 시도 전에 과도하다. 상태 회의 대기(C)는 너무 늦다. 종료 후 티켓(D)은 프로젝트 책임을 방기한다.
1205 | A project manager who works for a company involved in several industries is asked to lead a software development project for a government agency. The company attempted to execute similar projects for other industries before but was unsuccessful. What should the project manager do to ensure project success? | Review the lessons learned registers from the previous projects. | Continue executing the project using expert judgment. | Develop a contingency plan to prepare for possible risks. | Document this information in the risk management plan. |  | A | When a company has failed at similar software development projects for other industries, the project manager should review the lessons learned registers from previous projects. Historical lessons identify root causes of failure and proven practices. Continuing with expert judgment alone (B) ignores available organizational knowledge. Developing a contingency plan (C) addresses risk but not root causes. Documenting in the risk management plan (D) is incomplete without learning from failures. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Integration & General PM | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 여러 산업에 걸쳐 사업하는 회사의 PM이 소프트웨어 개발 프로젝트를 이끌도록 요청받았다. 회사가 유사 프로젝트에서 실패한 적이 있다. PM은 무엇을 먼저 해야 하는가? | 이전 프로젝트의 교훈 등록부를 검토한다 | 전문가 판단을 사용하여 프로젝트 실행을 계속한다 | 가능한 리스크에 대비하기 위한 비상 계획을 개발한다 | 이 정보를 리스크 관리 계획에 문서화한다 |  | A | 회사가 유사 소프트웨어 개발 프로젝트에서 실패한 적이 있을 때, PM은 먼저 이전 프로젝트의 교훈 등록부를 검토해야 한다. 역사적 교훈이 패턴을 식별하고 같은 실수를 방지한다. 전문가 판단(B)은 교훈 검토를 보완하지만 대체하지 않는다. 비상 계획(C)은 리스크 식별 후에 한다. 리스크 계획 문서화(D)는 교훈 검토 후에 한다.
1206 | A project is halfway through its execution phase. The quality specifications for the project deliverables are formally accepted. However, a key stakeholder is dissatisfied, stating that the deliverables do not meet the quality specifications. What should the project manager do in this situation? | Inform the project sponsor of the stakeholder ' s dissatisfaction. | Notify the stakeholder that arbitration procedures will be followed. | Review the requirements traceability matrix and conduct inspections. | Document the issue in the issue log and send a report to management. |  | C | When a key stakeholder claims deliverables do not meet formally accepted quality specifications mid-execution, the project manager should review the requirements traceability matrix and conduct inspections. Objective verification resolves the dispute factually. Informing the sponsor (A) escalates without data. Notifying about arbitration (B) is confrontational. Documenting and reporting to management (D) is administrative without resolution. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트가 실행 단계 중반에 있다. 품질 사양이 공식 수락되었다. 주요 이해관계자가 인도물이 품질 사양을 충족하지 못한다고 주장한다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 이해관계자의 불만을 알린다 | 이해관계자에게 중재 절차가 따를 것임을 통보한다 | 요구사항 추적 매트릭스를 검토하고 검사를 실시한다 | 이슈 로그에 문제를 문서화하고 경영진에게 보고서를 보낸다 |  | C | 주요 이해관계자가 공식 수락된 품질 사양에 인도물이 부합하지 않는다고 주장할 때, PM은 요구사항 추적 매트릭스를 검토하고 검사를 실시해야 한다. 객관적 데이터로 주장을 검증하는 것이 적절한 대응이다. 스폰서 알림(A)은 사실 확인 전에 성급하다. 중재 통보(B)는 적대적이다. 이슈 로그 문서화(D)는 검증 없이 기록만 한다.
1207 | A new marketing vice president just joined a software startup and is concerned that the agile model does not provide the needed accountability for their role. What should the responsible project manager do to ensure the vice president is comfortable with the project meeting its agreements? | Foster an environment of open communication where all parties can discuss issues and agree on objectives. | Establish an executive review board where all stakeholders discuss and approve features and requirements. | Leverage the use of the review/demo sessions with the vice president to acknowledge that the agreements were met. | Require proper approval of all requirements from the marketing vice president and formally document the agreements. |  | A | When a new marketing VP is concerned about accountability in an agile model, the project manager should foster an environment of open communication where all parties can discuss issues and agree on objectives. Transparent collaboration ensures shared accountability. Establishing an executive review board (B) adds formal overhead. Leveraging review/demo sessions (C) demonstrates work but may not address accountability concerns comprehensively. Requiring formal approval from the VP (D) adds bureaucratic control contrary to agile principles. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 새 마케팅 부사장이 소프트웨어 스타트업에 합류했고 애자일 모델이 충분한 책임을 제공하지 않는다고 우려한다. PM은 무엇을 해야 하는가? | 모든 당사자가 문제를 논의하고 목표에 합의할 수 있는 개방적 커뮤니케이션 환경을 조성한다 | 모든 이해관계자가 기능과 요구사항을 논의하고 승인하는 경영진 검토 위원회를 설립한다 | 부사장과 검토/데모 세션을 활용하여 합의 과정을 인식하게 한다 | 마케팅 부사장으로부터 모든 요구사항의 적절한 승인을 요구하고 공식 문서화한다 |  | A | 새 마케팅 부사장이 애자일 모델의 책임성에 우려할 때, PM은 모든 당사자가 문제를 논의하고 목표에 합의할 수 있는 개방적 커뮤니케이션 환경을 조성해야 한다. 투명한 소통이 신뢰와 이해를 구축한다. 검토 위원회(B)는 관료적이다. 데모 세션 활용(C)은 부분적 해결이다. 공식 승인 요구(D)는 애자일 원칙에 반한다.
1208 | A project manager is implementing a new software system. Some department staff members are questioning the necessity of the change and feel the new system will impede their current processes. What should the project manager have done at the start of the project to prevent this resistance? | Involved stakeholders from all levels of the company so everyone understands the change | Created a communications management plan that outlined the method of communicating to stakeholders. | Encouraged leadership to discuss the change with departments that are typically resistant 353 to change | Ensured that the company culture encourages changes before accepting the project |  | A | To prevent resistance from staff who question the necessity of a new software system, the project manager should have involved stakeholders from all levels of the company so everyone understands the change. Early, broad stakeholder involvement builds understanding, reduces resistance, and fosters collaboration. Creating a communications management plan (B) supports information flow but does not ensure genuine stakeholder involvement and understanding. Encouraging leadership to discuss the change (C) relies on top-down communication without broad engagement. Ensuring the company culture encourages change (D) is aspirational but not an actionable first step for a specific project. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | PM이 새 소프트웨어 시스템을 구현 중이다. 일부 부서 직원이 시스템의 필요성에 의문을 제기한다. PM이 이전에 무엇을 했어야 하는가? | 모든 수준의 이해관계자를 참여시켜 모두가 변화를 이해하도록 했다 | 이해관계자에게 커뮤니케이션하는 방법을 설명하는 커뮤니케이션 관리 계획을 작성했다 | 일반적으로 변화에 저항하는 부서와 변화를 논의하도록 리더십을 격려했다 | 프로젝트를 수락하기 전에 회사 문화가 변화를 장려하는지 확인했다 |  | A | 새 소프트웨어 시스템에 대한 직원 저항을 방지하려면, PM은 모든 수준의 이해관계자를 참여시켜 모두가 변화를 이해하도록 했어야 한다. 포괄적 이해관계자 참여가 변화 수용을 촉진한다. 커뮤니케이션 계획(B)은 방법이지 참여가 아니다. 리더십 격려(C)는 간접적이다. 문화 확인(D)은 PM의 통제 범위 밖이다.
1209 | A project management plan needs to be updated due to recent product requirements changes, but the latest version of the document is missing. What should the project manager do to prevent this from happening again? | Improve the configuration management process. | Review the quality assurance (QA) processes. | Register an issue for the missing documents. 1133 | Ensure that the lessons learned register is up to date. |  | A | When the latest version of the project management plan is missing due to recent changes, the project manager should improve the configuration management process to prevent recurrence. Configuration management controls document versioning and storage. Reviewing QA processes (B) is broader. Registering an issue (C) is an immediate step but does not prevent recurrence. Updating lessons learned (D) is retrospective. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Baseline & Change Control | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 최근 요구사항 변경으로 프로젝트 관리 계획 업데이트가 필요하지만 최신 버전을 찾을 수 없다. PM은 무엇을 먼저 해야 하는가? | 구성 관리 프로세스를 개선한다 | 품질보증(QA) 프로세스를 검토한다 | 누락된 문서에 대한 이슈를 등록한다 | 교훈 등록부가 최신 상태인지 확인한다 |  | A | 최신 프로젝트 관리 계획이 누락되었을 때, PM은 재발을 방지하기 위해 구성 관리 프로세스를 개선해야 한다. 구성 관리가 프로젝트 산출물의 버전 관리와 접근성을 보장한다. QA 프로세스(B)는 품질 관련이지 문서 관리가 아니다. 이슈 등록(C)은 증상 대응이지 근본 해결이 아니다. 교훈 등록부(D)는 미래 프로젝트용이다.
1210 | A key team member has recently gone through some personal issues that has affected their performance. The project manager noticed that the team member's emotional situation has affected the rest of the team's performance. How should the project manager handle this situation? | Separate the key team member and replace them while they emotionally recover. | Meet with the team to discuss how to handle the performance problem. | Help all team members learn to deal with their emotions by building a culture of empathy. | Ask the human resources (HR) department for their support providing emotional help. |  | C | When a team member's personal issues affect both their own performance and the rest of the team's performance, the project manager should help all team members learn to deal with emotions by building a culture of empathy. This approach supports the affected individual while strengthening the entire team's resilience and emotional intelligence—key aspects of effective team development. Separating and replacing the team member (A) is punitive and ignores the team's collective needs. Meeting only with the team to discuss the problem (B) may exclude the affected member's perspective. Requesting HR support (D) may be appropriate for specific cases but does not build the team's internal capacity for emotional support. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 주요 팀원이 개인 문제를 겪고 있어 성과에 영향을 미치고 다른 팀원에게도 영향을 준다. PM은 무엇을 해야 하는가? | 주요 팀원을 분리하고 감정적으로 회복할 때까지 교체한다 | 팀과 회의하여 성과 문제를 어떻게 처리할지 논의한다 | 모든 팀원이 감정을 다루는 법을 배우도록 공감 문화를 구축한다 | 인사부(HR)에 감정적 도움 제공 지원을 요청한다 |  | C | 팀원의 개인 문제가 본인과 팀 전체 성과에 영향을 미칠 때, PM은 모든 팀원이 감정을 다루는 법을 배우도록 공감 문화를 구축해야 한다. 공감 문화가 지속적 지원 환경을 만든다. 분리/교체(A)는 비인간적이다. 팀 회의(B)는 개인 문제를 공개한다. HR 요청(D)은 유용하지만 팀 문화 구축이 우선이다.
1211 | Contract terms used during the tender phase for a new power-generation facility must be revised before signing with the successful bidder because the terms of the tender have been amended to accommodate the new financial regulations on company tax. Which approach should the project manager take to implement this amendment? | Retender the entire scope because the terms of the contract have changed significantly. | Amend the contract terms and sign a revised contract with the successful bidder. | Discuss the new terms with the successful bidder to assess its impact on the contract price. | Sign the contract as per the original terms but allow the successful bidder to submit a new contract price. |  | B | When contract terms must be revised before signing due to new financial regulations on company tax, the project manager should amend the contract terms and sign a revised contract with the successful bidder. This ensures both parties agree to compliant terms while maintaining the existing procurement relationship. Retendering the entire scope (A) is excessive and wasteful when only terms need updating. Discussing new terms to assess price impact (C) is part of the amendment process but does not complete it. Signing original terms while allowing a new price submission (D) creates legal inconsistency between terms and pricing. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 발전 시설의 입찰 단계에서 사용된 계약 조건이 새 세법으로 인해 서명 전 수정되어야 한다. PM은 무엇을 해야 하는가? | 계약 조건이 크게 변경되었으므로 전체 범위를 재입찰한다 | 계약 조건을 수정하고 낙찰자와 수정된 계약을 체결한다 | 낙찰자와 새 조건이 계약 가격에 미치는 영향을 논의한다 | 원래 조건대로 계약을 체결하되 낙찰자가 새 계약 가격을 제출하도록 허용한다 |  | B | 새 세법으로 계약 조건을 수정해야 할 때, PM은 계약 조건을 수정하고 낙찰자와 수정된 계약을 체결해야 한다. 직접적인 계약 수정이 가장 효율적이다. 재입찰(A)은 시간과 비용이 과도하다. 영향 논의(C)는 수정 전 단계이지만 결론이 아니다. 원래 조건 서명(D)은 규정 비준수 리스크가 있다.
1212 | An agile team has been assigned to a project that mandates the implementation of changes to key government products. The team has been given 6 months to fulfill this mandate. What should the team lead do next? | Create the project charter and statement of work (SOW) to estimate the changes and the scope of the change. | Create all of the stories just for the next sprint and skip the epics until the next sprint. | Create the epics at a high level for the requirements and begin grooming sessions. | Create all of the stories needed to fulfill this change, document them in the backlog, and prioritize them according to business value. |  | C | When an agile team has 6 months to implement mandated changes to government products, the team lead should create epics at a high level for requirements and begin grooming sessions. High-level planning with grooming enables iterative refinement. Creating a charter and SOW (A) is too formal for agile. Creating stories for only the next sprint (B) skips big-picture planning. Creating all stories and documenting in the backlog (D) is too detailed upfront. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 애자일 팀이 주요 정부 제품에 대한 변경 구현을 의무화하는 프로젝트에 배정되었다. 6개월이 주어졌다. 팀 리더는 무엇을 먼저 해야 하는가? | 프로젝트 헌장과 작업기술서(SOW)를 만들어 변경과 범위를 추정한다 | 다음 스프린트를 위한 스토리만 생성하고 에픽은 다음 스프린트까지 건너뛴다 | 요구사항에 대한 에픽을 상위 수준으로 생성하고 그루밍 세션을 시작한다 | 변경 이행에 필요한 모든 스토리를 생성하고 백로그에 문서화하여 우선순위를 정한다 |  | C | 애자일 팀이 6개월 내 정부 제품 변경을 구현해야 할 때, 팀 리더는 요구사항에 대한 에픽을 상위 수준으로 생성하고 그루밍 세션을 시작해야 한다. 상위 수준 계획이 전체 범위를 파악하게 하고 점진적으로 상세화한다. 헌장/SOW(A)는 예측형 접근이다. 스토리만(B)은 전체 그림이 없다. 모든 스토리(D)는 너무 상세하여 시간 낭비이다.
1213 | A project manager is working in a regulated industry. The minimum viable product (MVP) for the launch has been defined. The project manager learns that the regulatory body requires a prototype for inspection before the product can be launched; however, the prototype is not part of the MVP definition. What should the project manager do next? | Reschedule the launch of the product until the team can produce a prototype for inspection as required by the compliance team. | Speak with the product manager to prioritize the compliance-related activities high enough in the backlog to submit a prototype to the regulatory body. | Identify the missing requirements, prioritize the missing compliance work directly into the backlog, and assign the work to the team. | Create an MVP that contains the scope for the prototype and that will be prioritized with the compliance team. |  | B | The correct answer is B. Speak with the product manager to prioritize the compliance-related activities high enough in the backlog to submit a prototype to the regulatory body. Compliance and regulatory requirements must be addressed proactively. The PM should assess impacts, follow proper change management processes, and ensure the project meets all applicable standards. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 규제 산업에서 PM이 작업 중이다. MVP가 정의되었으나 규제 기관 제출용 프로토타입 요구사항이 발견되었다. PM은 무엇을 해야 하는가? | 팀이 규제 요구에 따른 검사용 프로토타입을 생산할 때까지 제품 출시를 연기한다 | 제품 관리자와 대화하여 컴플라이언스 관련 활동을 백로그에서 충분히 높은 우선순위로 지정한다 | 누락된 요구사항을 식별하고 컴플라이언스 작업을 백로그에 직접 우선순위화하여 통합한다 | 프로토타입 범위를 포함하는 MVP를 만들어 컴플라이언스 요구사항과 함께 우선순위화한다 |  | B | 정답은 B이다. 제품 관리자와 대화하여 컴플라이언스 관련 활동을 백로그에서 충분히 높은 우선순위로 지정한다. 규제 산업에서 컴플라이언스와 규제 요구사항이 최우선이다. 제품 관리자와의 협력이 적절한 우선순위화를 보장한다. 출시 연기(A)는 과도한 조치이다. 직접 우선순위화(C)는 제품 관리자 역할을 침해한다. MVP 변경(D)는 범위를 혼란스럽게 한다.
1214 | During project implementation, one team finds out that a key project deliverable was not budgeted. What should the project manager do first? | Meet with the team to discuss alternatives. | Escalate the issue to the project sponsor for resolution. | Hold the team accountable and ask for an immediate solution. | Remove the deliverable from the project scope. |  | A | When a key deliverable is discovered to be unbudgeted during implementation, the project manager should first meet with the team to discuss alternatives. Collaborative problem-solving generates options. Escalating to the sponsor (B) is premature before exploring solutions. Holding the team accountable (C) assigns blame. Removing the deliverable (D) may eliminate essential scope. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | 프로젝트 구현 중 팀이 주요 인도물이 예산에 포함되지 않았음을 발견했다. PM은 무엇을 해야 하는가? | 팀과 회의하여 대안을 논의한다 | 해결을 위해 프로젝트 스폰서에게 이슈를 에스컬레이션한다 | 팀에 책임을 묻고 즉각적 해결을 요청한다 | 프로젝트 범위에서 해당 인도물을 제거한다 |  | A | 주요 인도물이 예산에 포함되지 않은 것이 발견될 때, PM은 먼저 팀과 회의하여 대안을 논의해야 한다. 협력적 문제 해결이 다양한 옵션을 생성한다. 에스컬레이션(B)은 팀 논의 후에 한다. 책임 추궁(C)은 비생산적이다. 인도물 제거(D)는 범위를 축소하여 프로젝트 가치를 훼손한다.
1215 | A compliance manager announces a new policy issued by the government that may impact project development. How should the project manager respond? | Maximize delivery by including this policy in the process. | Analyze the circumstances that brought about this new policy. | Address any blockers to the project due to this policy and resolve them. | Continue with project execution as per the previously approved project plan. |  | C | When a new government compliance policy may impact project development, the project manager should address any blockers to the project due to this policy and resolve them. This proactive approach to risk and issue management ensures the project continues while maintaining compliance. Maximizing delivery by including the policy (A) ignores potential constraints. Analyzing circumstances behind the policy (B) provides context but is not immediately action-oriented. Continuing execution per the previous plan (D) ignores the new compliance requirement. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 컴플라이언스 관리자가 프로젝트 개발에 영향을 줄 수 있는 새 정부 정책을 발표했다. PM은 무엇을 해야 하는가? | 이 정책을 프로세스에 포함하여 납품을 극대화한다 | 이 새 정책을 가져온 상황을 분석한다 | 이 정책으로 인한 프로젝트 장애 요소를 다루고 해결한다 | 이전에 승인된 프로젝트 계획에 따라 프로젝트 실행을 계속한다 |  | C | 새 정부 컴플라이언스 정책이 프로젝트에 영향을 줄 수 있을 때, PM은 이 정책으로 인한 프로젝트 장애 요소를 다루고 해결해야 한다. 장애 요소에 대한 사전적 접근이 리스크를 최소화한다. 프로세스 포함(A)은 모호하다. 상황 분석(B)은 행동이 아닌 분석이다. 기존 계획 계속(D)은 새 정책을 무시한다.
1216 | A team shared a complaint regarding the scrum master during the last sprint review. The team expressed that they were delayed because the scrum master did not remove impediments, such as scheduling some meetings with external teams and obtaining a room to work collaboratively, among other critical blockers. What should the project manager do? | Request an additional resource to assist in solving all of the impediments listed by the team. | Determine and agree when a situation becomes an impediment to be solved by the scrum master. | Push back, explaining that a self-organized team should address all of the problems to get the work done. | Request the team review and prioritize the open impediments to resolve all of them as soon as possible. |  | B | When the team complains that the scrum master did not remove impediments such as scheduling meetings and obtaining a collaborative workspace, the project manager should determine and agree when a situation becomes an impediment to be solved by the scrum master. Clarifying the shared understanding of the scrum master's responsibilities prevents future misalignment. Requesting additional resources (A) adds cost without addressing the role clarity issue. Pushing back and insisting the team solve problems themselves (C) ignores legitimate impediments the scrum master should handle. Requesting the team prioritize and resolve impediments themselves (D) also avoids the core role-definition issue. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Traditional PM | 팀이 마지막 스프린트 리뷰에서 스크럼 마스터에 대한 불만을 공유했다. 회의 일정 잡기와 협업 공간 확보 같은 장애물이 제거되지 않았다. PM은 무엇을 해야 하는가? | 팀이 나열한 모든 장애물 해결을 지원할 추가 자원을 요청한다 | 상황이 스크럼 마스터가 해결할 장애물이 되는 시점을 결정하고 합의한다 | 자체 조직화된 팀이 작업을 완수하기 위해 모든 문제를 다루어야 한다고 반박한다 | 팀에게 미해결 장애물을 검토하고 우선순위를 정하여 가능한 빨리 모두 해결하도록 요청한다 |  | B | 팀이 스크럼 마스터가 장애물을 제거하지 않았다고 불만할 때, PM은 상황이 스크럼 마스터가 해결할 장애물이 되는 시점을 결정하고 합의해야 한다. 명확한 정의가 역할과 기대를 정립한다. 추가 자원(A)은 근본 문제를 해결하지 않는다. 반박(C)은 팀 우려를 무시한다. 팀에게 해결 요청(D)은 스크럼 마스터 역할을 무시한다.
1217 | A customer reviewed the plan for a project with high uncertainty. The customer expressed concern about the work requiring so many iterations with a risk of not reaching the mandatory delivery date. Which approach should the project manager use in this situation? | Predictive approach | Hybrid approach | Agile approach | Kanban approach |  | B | When a customer is concerned about high uncertainty, many iterations, and a mandatory delivery date, the project manager should use a hybrid approach. Hybrid combines predictive structure for fixed deadlines with agile flexibility for uncertain areas. A purely predictive approach (A) lacks adaptability. A purely agile approach (C) may not assure the delivery date. A Kanban approach (D) manages flow but does not address deadline concerns. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Hybrid/Tailoring | 고객이 높은 불확실성을 가진 프로젝트 계획을 검토했다. 고객이 많은 이터레이션과 필수 납기일에 대해 우려한다. 어떤 접근법을 사용해야 하는가? | 예측형 접근법 | 하이브리드 접근법 | 애자일 접근법 | 칸반 접근법 |  | B | 고객이 높은 불확실성, 많은 이터레이션, 필수 납기일에 우려할 때, 하이브리드 접근법을 사용해야 한다. 하이브리드는 고정 납기를 위한 예측형 구조와 불확실성을 위한 적응형 유연성을 결합한다. 예측형(A)은 불확실성에 부적합하다. 순수 애자일(C)은 고정 납기 보장이 어렵다. 칸반(D)은 연속 흐름에 적합하지 이터레이션에는 부적합하다.
1218 | A project manager is managing an internal software development project that is on schedule to complete in 1 month. The project should begin seeing value once the system is online, yet some stakeholders lack an understanding of how it will provide value to the organization. What should the project manager do next? | Direct the team to implement the benefits management plan and track achievements before the end of the project. | Update the work breakdown structure (WBS) and project schedule with tasks and resources to track benefits realization. | Ask the sponsor to identify requirements for a new project to monitor and report achievement of the benefits. | Coordinate with the stakeholders to ensure the benefits management plan is in alignment with the goals. |  | D | When stakeholders lack understanding of how a nearly complete software project will provide value, the project manager should coordinate with stakeholders to ensure the benefits management plan is in alignment with the goals. Direct stakeholder engagement ensures shared understanding of expected value and benefits realization. Directing the team to implement the benefits plan (A) excludes stakeholders. Updating the WBS with benefits tracking (B) is structural, not communicative. Asking the sponsor for a new project (C) is premature. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 1개월 후 완료 예정인 내부 소프트웨어 개발 프로젝트를 관리 중이다. 이해관계자가 프로젝트가 어떻게 가치를 제공할지 이해하지 못한다. PM은 무엇을 해야 하는가? | 팀에게 혜택 관리 계획을 구현하고 프로젝트 종료 전에 성과를 추적하도록 지시한다 | WBS와 프로젝트 일정을 혜택 추적 작업과 자원으로 업데이트한다 | 스폰서에게 혜택 달성을 모니터링하고 보고할 새 프로젝트의 요구사항을 식별하도록 요청한다 | 이해관계자와 협력하여 혜택 관리 계획이 목표와 일치하도록 한다 |  | D | 이해관계자가 프로젝트의 가치 제공을 이해하지 못할 때, PM은 이해관계자와 협력하여 혜택 관리 계획이 목표와 일치하도록 해야 한다. 이해관계자 참여가 이해와 수용을 촉진한다. 팀 지시(A)는 이해관계자 참여가 없다. WBS 업데이트(B)는 기술적 조치이지 이해 구축이 아니다. 새 프로젝트(C)는 과도하다.
1219 | A company in the manufacturing industry has started a new initiative to integrate project management and improve product innovation. What first step should the project manager take to increase transparency among the stakeholders? | Invite key stakeholders to retrospective and review sessions to receive feedback as often as possible. | Set up a project dashboard to show day-to-day project status across the company. | Define a plan on how communication throughout the project will be handled among the stakeholders. | Invite upper management to process workshops where current project statuses will be discussed. |  | C | The correct answer is C. Define a plan on how communication throughout the project will be handled among the stakeholders. This approach best addresses the situation described by following project management best practices. The other options either fail to address the root cause, bypass proper processes, or may create additional problems. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | Stakeholder & Communication Mgmt | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 제조업 회사가 프로젝트 관리를 통합하고 제품 품질을 개선하는 새 이니셔티브를 시작했다. PM은 무엇을 해야 하는가? | 주요 이해관계자를 회고 및 검토 세션에 초대하여 가능한 자주 피드백을 받는다 | 회사 전체 프로젝트 상태를 보여주는 프로젝트 대시보드를 설정한다 | 프로젝트 전반의 커뮤니케이션이 이해관계자 간에 어떻게 처리될지 계획을 정의한다 | 상위 경영진을 프로세스 워크숍에 초대하여 현재 프로젝트 상태를 논의한다 |  | C | 정답은 C이다. 프로젝트 전반의 커뮤니케이션이 이해관계자 간에 어떻게 처리될지 계획을 정의한다. 이는 프로젝트 관리 원칙에 따라 이해관계자 간 커뮤니케이션의 기초를 설정한다. 회고 초대(A)는 부분적이다. 대시보드(B)는 도구이지 계획이 아니다. 워크숍 초대(D)는 상위 경영진만 다룬다.
1220 | A project manager is managing a complex project with a high number of artifacts. Some of the stakeholders are having issues accessing the artifacts. How should the project manager address this situation? | Send an agile report to the stakeholders, which includes the list of the project artifacts. | Escalate the stakeholders ' project artifacts concerns to the project management office (PMO) for resolution. | Ensure that the project artifacts are kept up-to-date and shared with the stakeholders. | Invite the stakeholders to the daily standup to clarify any questions about the project artifacts. |  | C | When stakeholders have difficulty accessing project artifacts in a complex project, the project manager should ensure that artifacts are kept up-to-date and shared with all stakeholders. This promotes transparency and ensures everyone has the information they need for effective participation and decision-making. Sending an agile report listing artifacts (A) provides a summary but does not solve the underlying access problem. Escalating to the PMO (B) transfers responsibility rather than addressing the issue directly. Inviting stakeholders to daily standups (D) is inappropriate—standups are team synchronization events, not artifact review sessions. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 많은 산출물을 가진 복잡한 프로젝트를 관리 중이다. 일부 이해관계자가 프로젝트 산출물에 접근하는 데 어려움을 겪는다. PM은 무엇을 해야 하는가? | 프로젝트 산출물 목록을 포함하는 애자일 보고서를 이해관계자에게 보낸다 | 이해관계자의 산출물 우려를 해결하기 위해 PMO에 에스컬레이션한다 | 프로젝트 산출물이 최신 상태로 유지되고 이해관계자와 공유되도록 한다 | 이해관계자를 데일리 스탠드업에 초대하여 산출물에 대한 질문을 명확히 한다 |  | C | 이해관계자가 프로젝트 산출물에 접근하기 어려울 때, PM은 산출물이 최신 상태로 유지되고 이해관계자와 공유되도록 해야 한다. 투명성과 접근성이 이해관계자 참여를 촉진한다. 보고서 발송(A)은 목록일 뿐 접근이 아니다. PMO 에스컬레이션(B)은 과도하다. 스탠드업 초대(D)는 적절한 채널이 아니다.
1221 | Due to their different ideas regarding the execution of a project, a conflict has occurred between two stakeholders. What should the project manager do to resolve the conflict? | Assess the conflict based upon the stakeholders ' past disagreements. | Arrange a group meeting with the stakeholders to generate creative alternatives. | Address the conflict in a planned meeting with all stakeholders and project team members. | Focus on the personal issues between the stakeholders. |  | B | When two stakeholders conflict over project execution approaches, the project manager should arrange a group meeting with them to generate creative alternatives. Collaborative problem-solving finds mutually acceptable solutions. Assessing based on past disagreements (A) introduces bias. Including all stakeholders and team (C) may escalate the issue. Focusing on personal issues (D) deviates from the project context. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 실행에 대한 다른 아이디어로 인해 두 이해관계자 간 갈등이 발생했다. PM은 무엇을 먼저 해야 하는가? | 이해관계자의 과거 의견 불일치에 기반하여 갈등을 평가한다 | 이해관계자와 그룹 회의를 주선하여 창의적 대안을 생성한다 | 모든 이해관계자와 프로젝트 팀원이 참석하는 계획된 회의에서 갈등을 다룬다 | 이해관계자 간의 개인적 문제에 집중한다 |  | B | 두 이해관계자가 프로젝트 실행 접근법으로 갈등할 때, PM은 그룹 회의를 주선하여 창의적 대안을 생성해야 한다. 협력적 문제 해결이 상호 수용 가능한 해결책을 찾는다. 과거 기반 평가(A)는 편견이 있다. 전체 회의(C)는 불필요한 청중을 포함한다. 개인 문제 집중(D)은 비전문적이다.
1222 | An agile project has completed several iterations. The project manager has been asked to participate in a meeting with the executive functional manager, who is a company leader and the product owner's supervisor. The executive functional manager wants to know about the project deliverables. What should the project manager focus on for the required meeting? | Analyzing the project performance of the sprints | Reviewing the team ' s performance metrics | Demonstrating the actual working product | Reviewing the burndown chart and backlog |  | C | The correct answer is C. Demonstrating the actual working product. The product owner manages backlog priorities and defines requirements. The PM should support the product owner's role while facilitating team collaboration and maintaining agile practices. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 애자일 프로젝트가 여러 이터레이션을 완료했다. PM이 제품 책임자와의 회의에 참여하도록 요청받았다. 어떤 방법이 제품 책임자를 가장 잘 지원하는가? | 스프린트의 프로젝트 성과를 분석한다 | 팀의 성과 지표를 검토한다 | 실제 작동하는 제품을 시연한다 | 번다운 차트와 백로그를 검토한다 |  | C | 정답은 C이다. 실제 작동하는 제품을 시연한다. 제품 책임자가 백로그 우선순위를 관리하고 요구사항을 정의한다. PM은 제품 책임자의 역할을 지원하면서 이해관계자에게 실제 진행 상황을 보여주는 데 작동하는 제품 시연이 가장 효과적이다. 성과 분석(A)은 내부적이다. 성과 지표(B)는 팀 관리용이다. 차트/백로그(D)는 기술적 세부사항이다.
1223 | A project manager is leading a project with a team that is comprised of both experienced and inexperienced team members. What should the project manager do to ensure an effective project team? | Ask the least experienced team members to work as assistants to the more experienced team members so they can gain some project experience. | Ask the project sponsor to replace the least experienced team members with more experienced ones. | Assign critical project tasks to the most experienced team members as they are the only ones with the knowledge. | Identify how the team members with no experience can contribute according to their capabilities and provide training if needed. |  | D | The correct answer is D. Identify how the team members with no experience can contribute according to their capabilities and provide training if needed. Resource management includes ensuring team members have the necessary skills and support. The PM should identify gaps and address them through training, mentoring, or other appropriate measures. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 경험자와 미경험자로 구성된 팀으로 프로젝트를 이끌고 있다. PM은 어떻게 해야 하는가? | 미경험 팀원에게 경험 있는 팀원의 보조로 일하도록 하여 배울 수 있게 한다 | 프로젝트 스폰서에게 미경험 팀원을 경험 있는 팀원으로 교체하도록 요청한다 | 경험 있는 팀원에게만 중요 프로젝트 작업을 할당한다 | 미경험 팀원이 역량에 따라 어떻게 기여할 수 있는지 파악하고 필요 시 교육을 제공한다 |  | D | 정답은 D이다. 미경험 팀원이 역량에 따라 어떻게 기여할 수 있는지 파악하고 필요 시 교육을 제공한다. 자원 관리는 팀원의 기술과 역량을 보장하는 것을 포함한다. 보조 역할(A)은 성장을 제한한다. 교체(B)는 비현실적이고 비용이 많이 든다. 중요 작업만 경험자에게(C)는 팀 발전을 제한한다.
1224 | A project manager who is new to a matrix organization has just been assigned to an internal software development project that is intended to reduce conflicts in the company's internal tracking system. With over 1,000 people in the company who will benefit from the software, the project manager wants to ensure everyone is aware of the great progress the team is making. The project manager meets with the project team to decide upon the most effective way to communicate progress. What should the project manager do? | Ask the project sponsor to disseminate project progress across the organization ' s stakeholders. | Divide up the organization among the project team to provide direct project updates. | Set up an intranet site and allow stakeholders to access the relevant project information. | Send weekly emails to each stakeholder providing them with the project ' s progress. |  | C | For large organizations with many stakeholders, an intranet site provides an efficient pull communication method. Stakeholders access information as needed without being overwhelmed by direct communications. This approach aligns with PMI best practices for managing large volumes of project information—ensuring the right audience can retrieve relevant data at their convenience while maintaining a clear communication structure. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 매트릭스 조직에 처음인 PM이 내부 소프트웨어 개발 프로젝트에 배정되었다. 대규모 조직이다. 어떻게 프로젝트 업데이트를 전달해야 하는가? | 프로젝트 스폰서에게 조직의 이해관계자에게 프로젝트 진행을 전파하도록 요청한다 | 프로젝트 팀에게 조직을 나누어 직접 프로젝트 업데이트를 제공한다 | 인트라넷 사이트를 설정하고 이해관계자가 관련 프로젝트 정보에 접근하도록 한다 | 각 이해관계자에게 프로젝트 진행에 대한 주간 이메일을 보낸다 |  | C | 대규모 조직에서 많은 이해관계자에게 효율적으로 정보를 전달하려면, 인트라넷 사이트를 설정하여 이해관계자가 필요 시 정보에 접근하도록 해야 한다. 풀(Pull) 커뮤니케이션이 정보 과부하를 방지한다. 스폰서 전파(A)는 스폰서 역할이 아니다. 팀 분배(B)는 비효율적이다. 주간 이메일(D)은 정보 과부하를 일으킨다.
1225 | During the review of a project's list of deliverables, one of the stakeholders expressed concern that one of the requirements will not be addressed. What should the project manager do? | Check the approved list of requirements to see if there are any missing items. | Review the requirements traceability matrix with the concerned stakeholder | Work with the stakeholder to improve the requirements ' acceptance criteria | Discuss with the stakeholder which additional requirements should be added |  | B | The project manager should review the requirements traceability matrix (RTM) with the concerned stakeholder. The RTM links requirements to their origin and tracks them throughout the project life cycle, ensuring all requirements are addressed by project deliverables. This review allows the PM and stakeholder to verify whether the requirement is indeed missing, understand its source and status, and identify any gaps or inconsistencies. Checking the approved list of requirements (A) may confirm the requirement's existence but lacks the traceability context. Improving acceptance criteria (C) or discussing additional requirements (D) are premature actions that should follow the RTM review, not precede it. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Adopt a Holistic View | Plan Scope Management | Traditional PM | 프로젝트 인도물 목록 검토 중 이해관계자가 요구사항 중 하나가 누락되었을 수 있다고 우려를 표명했다. PM은 무엇을 해야 하는가? | 승인된 요구사항 목록을 확인하여 누락된 항목이 있는지 확인한다 | 우려하는 이해관계자와 요구사항 추적 매트릭스를 검토한다 | 이해관계자와 요구사항의 인수 기준을 개선하기 위해 협력한다 | 이해관계자와 어떤 추가 요구사항을 추가해야 하는지 논의한다 |  | B | 이해관계자가 요구사항 누락을 우려할 때, PM은 우려하는 이해관계자와 요구사항 추적 매트릭스(RTM)를 검토해야 한다. RTM은 요구사항을 기원에 연결하고 프로젝트 수명주기 동안 추적한다. 승인 목록 확인(A)은 추적성이 부족하다. 인수 기준 개선(C)은 누락 여부와 무관하다. 추가 요구사항 논의(D)는 범위 확장이다.
1226 | A project is ending its fifth out of six iterations. During the iteration review, a customer adds a new regulatory feature that exceeds the capacity of the remaining iteration. What should the project lead do? | Increase the team capacity to finish the project on time. | Invite the stakeholders to discuss a new prioritization. | Register an issue and escalate it to the project sponsor. | Estimate the impact and consult with the product owner. |  | D | When a customer adds a new regulatory feature exceeding the remaining iteration's capacity, the project lead should estimate the impact and consult with the product owner. This enables informed prioritization decisions about trade-offs between the new feature and existing scope. Increasing team capacity (A) may not be feasible within the remaining iteration. Inviting stakeholders for reprioritization (B) bypasses the product owner's role. Registering an issue and escalating to the sponsor (C) over-escalates before assessing options. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트가 6번의 이터레이션 중 5번째를 종료 중이다. 이터레이션 리뷰 중 고객이 남은 이터레이션 용량을 초과하는 새 규제 기능을 추가한다. PM은 무엇을 해야 하는가? | 프로젝트를 제시간에 끝내기 위해 팀 용량을 늘린다 | 새로운 우선순위화를 논의하기 위해 이해관계자를 초대한다 | 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션한다 | 영향을 추정하고 제품 책임자와 상의한다 |  | D | 고객이 남은 용량을 초과하는 새 규제 기능을 추가할 때, PM은 영향을 추정하고 제품 책임자와 상의해야 한다. 이를 통해 정보에 기반한 우선순위 결정이 가능하다. 용량 증가(A)는 비현실적이다. 이해관계자 초대(B)는 영향 분석 전에 시기상조이다. 에스컬레이션(C)은 분석 전에 성급하다.
1227 | A new agile team is forming and the project manager notices that the team is struggling in many areas. The team is experiencing both the inability to meet iteration commitments and team member conflicts. What should the project manager do next? | Coach the team both as a whole and individually | Involve management to help resolve the conflicts | Raise the issues in the retrospective and propose solutions | Inform management that commitments will not be met. |  | A | When a new agile team struggles to meet iteration commitments and experiences conflicts, the project manager should coach the team both as a whole and individually. Coaching builds skills, resolves conflicts, and improves collaboration. Involving management to resolve conflicts (B) undermines team autonomy. Raising issues in the retrospective (C) is one step but coaching is more comprehensive. Informing management about missed commitments (D) escalates without addressing root causes. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 애자일 팀이 형성 중이며 PM이 팀이 여러 영역에서 어려움을 겪는 것을 발견한다. 팀이 이터레이션 약속을 충족하지 못하고 갈등을 경험한다. PM은 무엇을 해야 하는가? | 팀 전체와 개인적으로 코칭한다 | 갈등 해결을 위해 경영진을 참여시킨다 | 회고에서 이슈를 제기하고 해결책을 제안한다 | 경영진에게 약속이 충족되지 않을 것임을 알린다 |  | A | 새 애자일 팀이 약속 충족과 갈등에 어려움을 겪을 때, PM은 팀 전체와 개인적으로 코칭해야 한다. 코칭이 기술을 구축하고 갈등을 해결하며 팀 역학을 강화한다. 경영진 참여(B)는 직접 해결 전에 과도하다. 회고 제기(C)는 부분적이다. 경영진 알림(D)은 수동적이다.
1228 | A project team is planning the next sprint review. The project lead receives an email from a senior manager asking for a project status using a template that is more detailed than the one used for monthly reports sent to the project management office (PMO). The team uses an electronic product backlog and a kanban board to track the progress. What should the project manager do next? | Modify the PMO template to include the information. | Organize a review of the kanban board with the manager. | Give the senior manager access to the product backlog. | Contact the senior manager and discuss their needs. |  | D | When a senior manager requests a more detailed project status than the standard PMO template while the team uses electronic backlog and kanban, the project manager should contact the senior manager and discuss their needs. Direct engagement identifies specific information requirements and enables tailored communication without unnecessary overhead. Modifying the PMO template (A) changes the organization-wide template for one stakeholder's needs. Organizing a kanban board review (B) may not meet the specific detail requested. Giving backlog access (C) provides raw data without context the manager needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 스프린트 리뷰를 계획 중 고위 관리자가 표준 PMO 템플릿보다 상세한 프로젝트 상태를 요청한다. 팀은 전자 백로그와 칸반을 사용한다. PM은 무엇을 해야 하는가? | PMO 템플릿을 수정하여 정보를 포함한다 | 관리자와 칸반 보드 검토를 조직한다 | 고위 관리자에게 제품 백로그 접근 권한을 부여한다 | 고위 관리자에게 연락하여 니즈를 논의한다 |  | D | 고위 관리자가 더 상세한 프로젝트 상태를 요청할 때, PM은 먼저 연락하여 니즈를 논의해야 한다. 요구사항 이해가 적절한 해결책의 기초이다. 템플릿 수정(A)은 니즈 파악 전에 성급하다. 칸반 검토(B)는 니즈를 모르고 제안한다. 백로그 접근(C)은 관리자에게 적합하지 않을 수 있다.
1229 | A project team's performance is being impacted by impeding internal procedures that are affecting the progress of activities and team autonomy. What should the project manager do first to address this situation? | Ask the organization to improve the internal procedures. | Discuss the issue in the next sprint review meeting. | Train the team members on the organization ' s procedures. | Try to remove the barriers and empower team members. |  | D | The PM should prioritize removing barriers that impede team performance and autonomy. This aligns with agile principles emphasizing team empowerment, decision-making ownership, and self-organization. By addressing internal procedural obstacles, the PM creates a more efficient environment where the team can focus on delivering value rather than navigating bureaucratic impediments. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 내부 절차가 팀 성과에 장애가 되고 있다. PM은 무엇을 해야 하는가? | 조직에 내부 절차 개선을 요청한다 | 다음 스프린트 리뷰에서 이슈를 논의한다 | 조직 절차에 대해 팀원을 교육한다 | 장벽을 제거하고 팀원에게 권한을 부여한다 |  | D | 내부 절차가 팀 성과에 장애가 될 때, PM은 장벽을 제거하고 팀원에게 권한을 부여해야 한다. 이는 팀 권한 부여와 자기 조직화를 강조하는 애자일 원칙에 부합한다. 절차 개선 요청(A)은 장기적이다. 스프린트 리뷰(B)는 적합한 포럼이 아니다. 교육(C)은 장벽 제거가 아니다.
1230 | A compliance strategy was created during the planning phase of a project. During execution, the project manager left the organization and another project manager was assigned to the team. What should the project manager do first to ensure the project is compliant? | Review the organizational process assets (OPAs) for compliance topics | Meet with the team to discuss compliance concerns | Review the compliance strategy and version history | Meet with the project sponsor to discuss their compliance concerns |  | C | The correct answer is C. Review the compliance strategy and version history. Compliance and regulatory requirements must be addressed proactively. The PM should assess impacts, follow proper change management processes, and ensure the project meets all applicable standards. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 계획 단계에서 컴플라이언스 전략이 작성되었다. 실행 중 PM이 떠나고 새 PM이 이해관계자의 컴플라이언스 우려를 받았다. PM은 무엇을 먼저 해야 하는가? | 컴플라이언스 주제에 대한 조직 프로세스 자산(OPA)을 검토한다 | 팀과 회의하여 컴플라이언스 우려를 논의한다 | 컴플라이언스 전략과 버전 이력을 검토한다 | 프로젝트 스폰서와 회의하여 컴플라이언스 우려를 논의한다 |  | C | 정답은 C이다. 컴플라이언스 전략과 버전 이력을 검토한다. 컴플라이언스와 규제 요구사항은 사전적으로 다루어야 한다. PM은 기존 전략과 변경 이력을 먼저 파악해야 한다. OPA 검토(A)는 일반적이다. 팀 회의(B)는 전략 검토 후에 한다. 스폰서 회의(D)는 전략 파악 후에 한다.
1231 | A project is going through its iterative design stage. One of the team members has been performing poorly. This is a critical project for the company and execution is about to start. What should the project manager do? | Provide feedback and coach the team member during the iterative design stage | Escalate the issue to the human resources manager and request that the team member be replaced | Request action from the functional manager regarding the team members poor performance | Avoid selecting the team member to the next project that has an iterative design stage |  | A | When a team member performs poorly during the iterative design stage of a critical project, the project manager should provide feedback and coach the team member. Constructive feedback with coaching addresses performance gaps proactively while maintaining team morale. Escalating to HR for replacement (B) is premature. Requesting functional manager action (C) escalates before direct coaching. Avoiding selecting them for future projects (D) does not address the current problem. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 이터레이션 설계 단계에서 팀원 한 명이 저조한 성과를 보이고 있다. 중요한 프로젝트이다. PM은 무엇을 해야 하는가? | 이터레이션 설계 단계에서 팀원에게 피드백을 제공하고 코칭한다 | 인사 관리자에게 이슈를 에스컬레이션하고 팀원 교체를 요청한다 | 기능 관리자에게 팀원의 저조한 성과에 대한 조치를 요청한다 | 다음 이터레이션 설계 단계가 있는 프로젝트에 해당 팀원을 선택하지 않는다 |  | A | 팀원이 중요 프로젝트의 이터레이션 설계 단계에서 저조한 성과를 보일 때, PM은 피드백을 제공하고 코칭해야 한다. 건설적 피드백과 코칭이 성과 향상의 기회를 제공한다. 에스컬레이션(B)은 직접 개입 전에 과도하다. 기능 관리자 요청(C)은 PM 역할을 위임한다. 미래 배제(D)는 현재 문제를 해결하지 않는다.
1232 | During the last two iterations of a project, one of the team members had low performance. The project manager conducted two feedback sessions with the team member and escalated the issue to the resource manager and project sponsor, but there has been no improvement. What should the project manager do next? | Review this obstacle during the daily standup meeting. | Escalate the situation again to the project sponsor. | Request a new resource to execute the activities. | Provide feedback to the resource at the sprint review. |  | C | When a team member's low performance persists after two feedback sessions and escalation to both the resource manager and sponsor, the project manager should request a new resource to execute the activities. Continued poor performance despite all corrective measures necessitates resource change to protect project objectives. Reviewing the obstacle at daily standup (A) revisits an already-addressed issue. Escalating to the sponsor again (B) repeats a step with no improvement. Providing sprint review feedback (D) is too late and ineffective. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 마지막 두 이터레이션에서 팀원의 성과가 저조했다. PM이 피드백을 두 번 제공하고 자원 관리자와 스폰서에게 에스컬레이션했으나 변화가 없다. PM은 무엇을 해야 하는가? | 데일리 스탠드업에서 이 장애물을 검토한다 | 프로젝트 스폰서에게 다시 에스컬레이션한다 | 활동을 수행할 새 자원을 요청한다 | 스프린트 리뷰에서 자원에게 피드백을 제공한다 |  | C | 두 번의 피드백과 에스컬레이션 후에도 성과가 개선되지 않을 때, PM은 활동을 수행할 새 자원을 요청해야 한다. 기존 조치가 실패했으므로 자원 교체가 필요하다. 스탠드업 검토(A)는 적절한 포럼이 아니다. 재에스컬레이션(B)은 이미 시도되었다. 스프린트 리뷰 피드백(D)은 공개적이고 부적절하다.
1233 | A project manager is leading a hybrid project for the development of dental equipment with five team members. A dentist, who is also one of the major investors, attends a sprint review meeting and raises questions and doubt about the concept and expected performance of the equipment. What should the project manager do? | invite the investor to the design review meeting to present the concept and expected performance of the equipment and include a QSA session m the meeting | invite the product owner and the team to a discussion about the concept and expected performance of the equipment | invite the investor to a sprint retrospective meeting to discuss the improvements of the concept and expected performance of the equipment with the team | invite the protect sponsor to the sprint review meeting and nave a QSA session about the concept and expected performance of the equipment |  | D | When a major investor raises questions about the concept and expected performance of dental equipment during a sprint review, the project manager should invite the product owner and the team to a focused discussion about these concerns. This ensures the right people—those with design and technical knowledge—address the investor's questions directly and collaboratively. Inviting the investor to a design review with a Q&A session (A) is a reasonable option but may not engage the agile team appropriately. Inviting the investor to a sprint retrospective (C) is inappropriate since retrospectives are internal team improvement meetings. Inviting the project sponsor to the sprint review (D) adds a stakeholder but does not directly address the technical concerns raised. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Governance | Planning | Focus on Value | Develop Project Management Plan | Hybrid/Tailoring | PM이 5명의 팀원으로 치과 장비 개발 하이브리드 프로젝트를 이끌고 있다. 스프린트 리뷰에서 주요 투자자가 컨셉과 예상 성과에 대해 질문한다. PM은 무엇을 해야 하는가? | 투자자를 설계 리뷰 회의에 초대하여 컨셉과 예상 성과를 발표한다 | 제품 책임자와 팀을 컨셉과 예상 성과에 대한 논의에 초대한다 | 투자자를 스프린트 회고에 초대하여 컨셉 개선을 논의한다 | 프로젝트 스폰서를 스프린트 리뷰에 초대하고 QSA 세션을 진행한다 |  | D | 주요 투자자가 스프린트 리뷰에서 컨셉과 성과에 대해 질문할 때, PM은 프로젝트 스폰서를 스프린트 리뷰에 초대하고 QSA 세션을 진행해야 한다. 스폰서의 참여가 투자자의 우려에 권위 있는 대응을 제공한다. 설계 리뷰(A)는 기술적 포럼이다. 팀 논의(B)는 내부적이다. 회고(C)는 팀 내부 프로세스 개선용이다.
1234 | A new project manager has been assigned to a project that is in its second phase. The product created in the first phase was transferred to operations. During a meeting, the project sponsor complained that some of the reports contain conflicting data on the product value. What should the new project manager do next? | Collect information from related departments | Review the benefits management plan | Refer to the lessons learned from the first phase | Consult the project reports from the previous project manager |  | D | When conflicting data on product value appears in project reports, the new project manager should consult the project reports from the previous project manager. Historical reports provide context on data sources, methodologies, and potential discrepancies that led to the conflict. Collecting information from departments (A) is useful but does not address the specific data conflict. Reviewing the benefits management plan (B) covers expected benefits but not report discrepancies. Referring to first-phase lessons learned (C) may provide context but not the specific data in question. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 새 PM이 2단계에 있는 프로젝트에 배정되었다. 1단계에서 만든 제품의 가치에 대해 프로젝트 보고서에 상충되는 데이터가 있다. PM은 무엇을 먼저 해야 하는가? | 관련 부서에서 정보를 수집한다 | 혜택 관리 계획을 검토한다 | 1단계의 교훈을 참조한다 | 이전 PM의 프로젝트 보고서를 참조한다 |  | D | 제품 가치에 대한 상충 데이터가 있을 때, 새 PM은 이전 PM의 프로젝트 보고서를 참조해야 한다. 역사적 보고서가 데이터 차이에 대한 맥락과 결정 근거를 제공한다. 부서 정보 수집(A)은 시간이 많이 든다. 혜택 관리 계획(B)은 일반적이다. 교훈(C)은 유용하지만 구체적 데이터 분석이 아니다.
1235 | An organization has historically executed most projects using a predictive approach. The organization now wants to change over to an agile approach. Which strategy will be useful to effectively help prepare the organization for this change? | Take a big bang approach of moving the whole organization to agile at once | Add multiple layers of managers who will be accountable for the agile execution | Create a task force of executives who will monitor agile projects on a daily basis | Improve organizational readiness by addressing impediments to agile in the organization. |  | D | The most effective strategy for transitioning from predictive to agile is improving organizational readiness by addressing impediments to agile adoption. Impediments may include cultural, structural, procedural, or technical barriers. By identifying and removing these obstacles, the organization creates a supportive environment for change—through training, coaching, cross-functional teams, and streamlined processes. A big bang approach (A) overwhelms the organization with change and ignores varying levels of readiness across departments. Adding management layers (B) creates bureaucracy that contradicts agile values of trust and empowerment. Creating an executive task force for daily monitoring (C) implies top-down control that conflicts with agile principles of team autonomy and self-organization. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 조직이 역사적으로 예측형 접근법을 사용했다. 이제 애자일로 전환하려 한다. 최선의 전략은? | 전체 조직을 한 번에 애자일로 이동하는 빅뱅 접근법을 취한다 | 애자일 실행을 담당할 여러 층의 관리자를 추가한다 | 애자일 프로젝트를 매일 모니터링할 경영진 태스크포스를 만든다 | 조직의 애자일 장애물을 다루어 조직 준비성을 향상시킨다 |  | D | 예측형에서 애자일로 전환하는 가장 효과적인 전략은 애자일 장애물을 다루어 조직 준비성을 향상시키는 것이다. 문화적, 구조적, 프로세스 장애물 해결이 성공적 전환의 기초이다. 빅뱅(A)은 리스크가 높다. 관리 층 추가(B)는 애자일 원칙에 반한다. 경영진 모니터링(C)은 마이크로매니지먼트이다.
1236 | A company has hired a vendor to deliver a scope of work and assigned a project manager to oversee the project. The vendor advised that they completed the scope successfully and is asking for approval. What should the project manager do in response to this request? | Ask the vendor to validate the agreement for any deviations. | Update the project management plan and mark the milestone as completed. | Obtain approval from the project sponsor. | Set up a meeting with stakeholders to validate and confirm acceptance of the deliverables. |  | D | When a vendor claims they have completed the scope and requests approval, the project manager should set up a meeting with stakeholders to validate and confirm acceptance of the deliverables. Involving relevant stakeholders ensures satisfaction and proper acceptance criteria verification. Asking the vendor to validate for deviations (A) is self-assessment, not independent verification. Updating the project plan and marking milestones complete (B) skips validation. Obtaining only sponsor approval (C) excludes other stakeholders from the acceptance process. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 벤더가 작업 범위를 완료했다고 주장하고 승인을 요청한다. PM은 무엇을 해야 하는가? | 벤더에게 합의에서 편차가 있는지 검증하도록 요청한다 | 프로젝트 관리 계획을 업데이트하고 마일스톤을 완료로 표시한다 | 프로젝트 스폰서의 승인을 받는다 | 이해관계자와 회의를 설정하여 인도물의 수락을 검증하고 확인한다 |  | D | 벤더가 범위 완료를 주장할 때, PM은 이해관계자와 회의를 설정하여 인도물의 수락을 검증하고 확인해야 한다. 이해관계자 참여가 합의된 품질과 범위 충족을 보장한다. 벤더 자체 검증(A)은 편향될 수 있다. 바로 완료 표시(B)는 검증 없이 성급하다. 스폰서 승인만(C)은 이해관계자 참여가 부족하다.
1237 | During the execution of a project, the finance team identified that they were not involved in building the business case for the project and will not approve the estimated return on investment (ROI). What should the project manager do? | Revisit the communications management plan and make necessary adjustments | Revisit the scope management plan and note this as a risk | Continue developing based on the project management plan and address the issue post delivery | Schedule a meeting with the product owner and finance team to agree on course 612 corrections |  | D | When the finance team was not involved in the business case and will not approve the estimated ROI, the project manager should schedule a meeting with the product owner and finance team to agree on course corrections. Direct engagement clarifies expectations and aligns stakeholders on the business case. Revisiting the communications plan (A) addresses process, not the substantive disagreement. Revisiting the scope management plan (B) does not address financial alignment. Continuing development and addressing post-delivery (C) defers a critical issue. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 실행 중 재무팀이 비즈니스 케이스 구축에 참여하지 않았고 예상 ROI를 승인하지 않을 것이라고 확인했다. PM은 무엇을 해야 하는가? | 커뮤니케이션 관리 계획을 재검토하고 필요한 조정을 한다 | 범위 관리 계획을 재검토하고 이를 리스크로 기록한다 | 프로젝트 관리 계획에 따라 개발을 계속하고 납품 후 이슈를 다룬다 | 제품 책임자와 재무팀과의 회의를 일정 잡아 시정 조치에 합의한다 |  | D | 재무팀이 비즈니스 케이스에 참여하지 않아 ROI를 승인하지 않을 때, PM은 제품 책임자와 재무팀과의 회의를 일정 잡아 시정 조치에 합의해야 한다. 직접적 협업이 문제를 해결한다. 커뮤니케이션 계획 조정(A)은 근본 문제를 다루지 않는다. 리스크 기록(B)은 행동이 아니다. 납품 후 처리(C)는 너무 늦다.
1238 | An email arrives shortly after the beginning of a sprint. It is from a key project stakeholder who is unfamiliar with agile approaches and has a serious complaint about future work that has been scheduled. The stakeholder is insisting that a future work package be removed from the backlog entirely, claiming that it is unnecessary. What should the project manager do? | Invite the stakeholder to the backlog refinement meeting to discuss their request. | Discuss the stakeholder ' s request at the next retrospective meeting. | Alter the backlog to accommodate the stakeholder ' s request. | Address the stakeholder ' s request at the daily standup and ask for the team ' s opinion. |  | A | The correct answer is A. Invite the stakeholder to the backlog refinement meeting to discuss their request. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 스프린트 시작 직후 주요 이해관계자로부터 새 요구사항을 추가해달라는 이메일이 도착한다. 이해관계자는 애자일에 익숙하지 않다. PM은 무엇을 해야 하는가? | 이해관계자를 백로그 정제 회의에 초대하여 요청을 논의한다 | 다음 회고에서 이해관계자의 요청을 논의한다 | 이해관계자의 요청을 수용하기 위해 백로그를 변경한다 | 데일리 스탠드업에서 이해관계자의 요청을 다루고 팀의 의견을 구한다 |  | A | 정답은 A이다. 이해관계자를 백로그 정제 회의에 초대하여 요청을 논의한다. 애자일 실천은 반복적 전달, 팀 권한 부여, 지속적 개선을 강조한다. 백로그 정제가 새 요구사항을 논의하기에 적절한 포럼이다. 회고(B)는 프로세스 개선용이다. 바로 백로그 변경(C)은 적절한 검토 없이 성급하다. 스탠드업(D)은 일일 동기화용이다.
1239 | During a risk review meeting early in a project, the project team flags the possibility that a key team member might be away during the implementation of a key work package. Unfortunately, this team member is currently the only resource with the knowledge to perform this work, although it is possible someone else could do it with training. What should the project manager do? | Establish a long-term training program for the junior team members. | Ensure team members collaborate throughout the project to share knowledge. | Reassign the tasks among team members to allow them to split the workload. | Ask team members to document knowledge assets for all the tasks. |  | B | When a key team member might be unavailable during a critical work package and they are the only one with the knowledge, the project manager should ensure team members collaborate throughout the project to share knowledge. Continuous collaboration enables knowledge transfer proactively. Establishing a long-term training program (A) is too slow. Reassigning tasks to split workload (C) does not address the knowledge gap. Documenting knowledge assets (D) supports but does not replace hands-on collaboration. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 리스크 검토 회의 초기에 프로젝트 팀이 주요 팀원이 중요 작업 패키지 동안 불가용할 수 있다고 플래그한다. 그 팀원만이 해당 지식을 보유한다. PM은 무엇을 해야 하는가? | 주니어 팀원을 위한 장기 교육 프로그램을 설립한다 | 프로젝트 전반에 걸쳐 팀원들이 지식을 공유하도록 협업을 보장한다 | 팀원들에게 작업을 재할당하여 업무 부담을 분배한다 | 팀원들에게 모든 작업에 대한 지식 자산을 문서화하도록 요청한다 |  | B | 주요 팀원이 중요 시기에 불가용할 수 있고 유일한 지식 보유자일 때, PM은 프로젝트 전반에 걸쳐 팀원들이 지식을 공유하도록 협업을 보장해야 한다. 지속적 협업이 단일 장애점을 제거한다. 장기 교육(A)은 즉각적이지 않다. 작업 재할당(C)은 지식 전달이 아니다. 문서화(D)는 유용하지만 협업이 더 효과적이다.
1240 | A sales director is upset that progress has been slow on the delivery of critical features to the customer. After consulting with the team, the project manager learns that a subject matter expert (SME) on the customer side is not cooperative in providing the input needed to complete the definition of ready (DoR). What should the project manager do to avoid the same problem in future projects? | Rely on internal SMEs for expert input on implementing the user stories. | Include a contractual penalty for delays created by the customer. | Require customer SMEs to attend at least half of the daily meetings. | Review the responsibility matrix at the customer kick-off meeting. |  | C | The correct answer is C. Require customer SMEs to attend at least half of the daily meetings. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 영업 이사가 고객에 대한 중요 기능 납품 진행이 느리다고 불만이다. 상의 결과 고객 SME가 일부 사용자 스토리 작성에 필요하다. PM은 무엇을 해야 하는가? | 사용자 스토리 구현에 대한 전문 입력을 위해 내부 SME에 의존한다 | 고객으로 인한 지연에 대한 계약적 패널티를 포함한다 | 고객 SME가 최소 데일리 미팅의 절반에 참석하도록 요구한다 | 고객 킥오프 미팅에서 책임 매트릭스를 검토한다 |  | C | 정답은 C이다. 고객 SME가 최소 데일리 미팅의 절반에 참석하도록 요구한다. 이 접근법은 고객과의 효과적 관계를 유지하면서 상황을 해결한다. 내부 SME(A)는 고객 지식을 대체하지 못한다. 패널티(B)는 관계를 훼손한다. 책임 매트릭스(D)는 킥오프 시점이라 현재 해결이 아니다.
1241 | The start of a 12-month project has been delayed by 2 months. The project has a fixed budget, deadline, and product specifications. What should the project manager do next? | Meet with the risk manager to identify potential threats related to the schedule delay. | Start the project plan for the scope and quality and identify options to deliver and meet stakeholders expectations | Schedule a time to negotiate a trade-off regarding the quality of the product with the customer | Set up a meeting with the project sponsor and submit a change request to the scope of the product |  | B | When a 12-month project with fixed constraints is delayed by 2 months, the project manager should start the project plan for scope and quality and identify options to deliver and meet stakeholder expectations. Reassessing the plan within constraints is proactive. Meeting with the risk manager (A) is one input but not the full response. Negotiating quality trade-offs (C) is premature. Meeting the sponsor for a scope change request (D) assumes scope change before exploring options. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 12개월 프로젝트가 2개월 지연되어 시작된다. 예산, 기한, 제품 사양이 고정되어 있다. PM은 무엇을 해야 하는가? | 일정 지연과 관련된 잠재적 위협을 식별하기 위해 리스크 관리자와 회의한다 | 범위와 품질에 대한 프로젝트 계획을 시작하고 이해관계자 기대를 충족할 옵션을 식별한다 | 고객과 제품 품질에 대한 트레이드오프를 협상할 시간을 정한다 | 프로젝트 스폰서와 회의를 설정하고 제품 범위에 대한 변경 요청을 제출한다 |  | B | 고정 제약이 있는 12개월 프로젝트가 2개월 지연될 때, PM은 범위와 품질에 대한 프로젝트 계획을 시작하고 이해관계자 기대를 충족할 옵션을 식별해야 한다. 계획과 옵션 식별이 제약 내 최적 해결책을 찾는다. 리스크 식별(A)은 유용하지만 계획이 우선이다. 품질 트레이드오프(C)는 성급하다. 범위 변경(D)은 고정 사양을 무시한다.
1242 | A product is facing performance issues that will significantly decrease the manufacturing yield expected, increasing the cost. This will be an issue as it will limit one of the high-margin contracted goals. Because it is a breakthrough development, the speed to market is key. What should the project manager do? | Engage with the sales team to increase the sales price since it is a breakthrough product. | Evaluate the most cost-effective containment action and use their influence to implement it. | Assess what corrective action is appropriate and use their influence to implement it. | Negotiate with operations to absorb the cost while the product is launched and remediate the issue. |  | B | When a breakthrough product faces performance issues decreasing manufacturing yield and increasing costs with time-to-market pressure, the project manager should evaluate the most cost-effective containment action and use their influence to implement it. Targeted containment balances speed and cost. Engaging sales to increase price (A) is a commercial decision. Assessing corrective action broadly (C) may delay launch. Negotiating with operations to absorb cost (D) may undermine profitability. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 혁신 제품이 성능 문제로 제조 수율이 크게 감소하여 비용이 증가할 것이다. 시장 출시 압박이 있다. PM은 무엇을 해야 하는가? | 혁신 제품이므로 판매가를 올리기 위해 영업팀에 참여한다 | 가장 비용 효과적인 봉쇄 조치를 평가하고 영향력을 사용하여 구현한다 | 적절한 시정 조치를 평가하고 영향력을 사용하여 구현한다 | 제품이 출시되는 동안 비용을 흡수하도록 운영팀과 협상하고 문제를 해결한다 |  | B | 혁신 제품이 성능 문제로 비용 증가와 시장 출시 압박에 직면할 때, PM은 가장 비용 효과적인 봉쇄 조치를 평가하고 영향력을 사용하여 구현해야 한다. 봉쇄 조치가 즉각적 손상을 제한한다. 가격 인상(A)은 시장 수용을 훼손한다. 시정 조치(C)는 장기적이며 즉각적 봉쇄가 우선이다. 비용 흡수(D)는 재무적으로 지속 불가능하다.
1243 | The project manager realizes that the product owner has a lot of potential but is lacking communication skills. How should the project manager help the product owner to develop these skills while executing the project? | Suggest that the product owner attend a training session about assertive communication. | Suggest that the product owner shadow colleagues who are good presenters. | Ensure there are opportunities for the product owner to present project reviews to the stakeholders. | Recommend a specialized article about delivering effective presentations to the product owner. |  | A | When a product owner has potential but lacks communication skills, the project manager should suggest attending a training session about assertive communication. Formal training develops foundational skills. Suggesting shadowing good presenters (B) provides observation but not structured learning. Ensuring opportunities for presentations (C) provides practice but not skill development. Recommending an article (D) is insufficient for skill building. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 제품 책임자가 잠재력이 있지만 커뮤니케이션 기술이 부족하다. PM은 어떻게 도와야 하는가? | 제품 책임자에게 주장적 커뮤니케이션 교육에 참석하도록 제안한다 | 좋은 발표자인 동료를 관찰하도록 제안한다 | 이해관계자에게 프로젝트 리뷰를 발표할 기회를 제공한다 | 효과적 발표에 대한 전문 기사를 추천한다 |  | A | 제품 책임자가 잠재력이 있지만 커뮤니케이션이 부족할 때, PM은 주장적 커뮤니케이션 교육에 참석하도록 제안해야 한다. 공식 교육이 기초적 커뮤니케이션 기술을 개발한다. 동료 관찰(B)은 보충적이다. 발표 기회(C)는 기술 없이 경험을 주는 것이다. 기사 추천(D)은 실천적이지 않다.
1244 | A project sponsor asks the project manager to explore a hybrid approach for a new project. The product manager for this project has already prepared a detailed specification for the product. What should the project manager do to proceed with the project management plan? | Explore with the product manager to determine if there are viable opportunities todeliver value incrementally and increase business value. | Ask the team to assess whether the product specification can be expressed in userstories to enable a Scrum or Kanban approach. | Ask the product manager whether they are prepared to act as product owner for theproject in order to participate in iterative planning and reviews. | Recommend to the project sponsor that a predictive approach is appropriate for theproject due to the stable product requirements. |  | D | When the sponsor asks to explore a hybrid approach and the product manager has detailed specifications, the project manager should explore with the product manager to determine if there are viable opportunities to deliver value incrementally. Collaborative exploration identifies where adaptive methods add value alongside predictive planning. Assessing user story expression (B) assumes agile methodology. Recommending predictive approach (C) disregards the sponsor's hybrid request. Asking the product manager to act as product owner (D) conflates roles. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 스폰서가 PM에게 하이브리드 접근법을 탐색하도록 요청한다. 제품 관리자가 상세한 제품 사양을 이미 가지고 있다. PM은 무엇을 해야 하는가? | 제품 관리자와 탐색하여 가치를 점진적으로 전달할 기회가 있는지 결정한다 | 팀에게 제품 사양이 사용자 스토리로 표현될 수 있는지 평가하도록 요청한다 | 제품 관리자가 프로젝트의 제품 책임자 역할을 할 준비가 되었는지 묻는다 | 상세한 사양으로 인해 예측형 접근법이 적절하다고 스폰서에게 권고한다 |  | D | 스폰서가 하이브리드 접근법을 요청하고 상세한 사양이 있을 때, PM은 제품 관리자와 탐색하여 점진적 전달 기회가 있는지 결정해야 한다. 그러나 상세한 사양이 이미 있으므로 예측형 접근법이 적절할 수 있다고 스폰서에게 권고하는 것이 전문적 판단이다. 사용자 스토리 변환(B)은 사양이 이미 상세하면 불필요할 수 있다. PO 역할(C)은 조직 결정이다.
1245 | A key import supply has suffered a delay of 6 months. The delay affects a functionality that is needed to complete the project on time. The project manager learns from the project team that another team is working on a product that could work as a solution, but it is still a prototype. What should the project manager do to accelerate this solution? | Prioritize the backlog with the customer to remove the feature | Perform iterative planning with the team to use the prototype | Contact the other project team and ask them to organize a demo of the prototype | Check the burnup charts to see what progress has been made to integrate the solution |  | B | When a key import supply is delayed 6 months and another team has a prototype that could work as a solution, the project manager should perform iterative planning with the team to use the prototype. Iterative planning enables adaptive integration and testing of the new solution. Prioritizing the backlog to remove the feature (A) eliminates functionality. Contacting the other team for a demo (C) is informational but not actionable. Checking burnup charts (D) monitors progress but does not accelerate the solution. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 주요 수입 공급이 6개월 지연되었다. 이 지연이 프로젝트 완료에 필요한 기능에 영향을 준다. 다른 팀이 해결책으로 사용할 수 있는 프로토타입을 가지고 있다. PM은 무엇을 해야 하는가? | 고객과 백로그를 우선순위화하여 기능을 제거한다 | 팀과 이터레이션 계획을 수행하여 프로토타입을 사용한다 | 다른 프로젝트 팀에 연락하여 프로토타입 데모를 조직하도록 요청한다 | 번업 차트를 확인하여 솔루션 통합에 어떤 진행이 있었는지 확인한다 |  | B | 주요 공급이 6개월 지연되고 다른 팀의 프로토타입이 해결책이 될 수 있을 때, PM은 팀과 이터레이션 계획을 수행하여 프로토타입을 사용해야 한다. 반복적 계획이 대안 솔루션의 통합을 가능하게 한다. 기능 제거(A)는 가치를 줄인다. 데모 요청(C)은 행동 계획이 아니다. 번업 차트 확인(D)은 모니터링이지 해결이 아니다.
1246 | A specialized team member has just received news that they must leave the office for several weeks. They have approximately two workdays until they will leave and then they will become unavailable through any communication channels. There is a key deadline approaching. What should the agile project manager do? | Ask the team member to work with their peers to knowledge share | Ask the team member to host a special team meeting. | Ask the team member to complete as much as they can now. | Ask the team member to identify their specialist tasks |  | A | When a specialized team member must leave for several weeks with only two workdays before departure and a key deadline approaching, the agile project manager should ask the team member to work with peers to knowledge share. Knowledge transfer preserves critical expertise. Hosting a special meeting (B) takes time but is less focused. Completing as much work as possible (C) addresses output, not continuity. Identifying specialist tasks (D) documents but does not transfer knowledge. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 전문 팀원이 몇 주간 사무실을 떠나야 한다는 소식을 받았다. 출발 전 약 2일의 근무일이 남아있고 주요 기한이 다가온다. PM은 무엇을 해야 하는가? | 팀원에게 동료와 지식을 공유하도록 요청한다 | 팀원에게 특별 팀 회의를 개최하도록 요청한다 | 팀원에게 지금 가능한 한 많이 완료하도록 요청한다 | 팀원에게 전문 작업을 식별하도록 요청한다 |  | A | 전문 팀원이 2일 후 떠나야 할 때, PM은 동료와 지식을 공유하도록 요청해야 한다. 지식 공유가 팀 연속성을 보장한다. 특별 회의(B)는 시간 제약에 비해 비효율적이다. 작업 완료(C)는 지식 전달이 없다. 작업 식별(D)은 부분적이다.
1247 | The team architect resigned from the company. The new architect identifies a design flaw during a planning meeting that may potentially affect the final quality. What should the project manager do first? | Update the design with changes. | Update the quality management plan | Review the scope management plan. | Request an architecture review. |  | D | Requesting an architecture review is the appropriate first step when a design flaw is identified that may compromise final quality. This evaluation process assesses the system design against requirements, standards, best practices, and quality attributes. It enables relevant experts—including architects, the QA team, and stakeholders—to evaluate the flaw's impact and agree on necessary corrections. The review also informs updates to scope, schedule, cost, and quality baselines as needed. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 팀 아키텍트가 사임했다. 새 아키텍트가 계획 회의 중 최종 품질을 위태롭게 할 수 있는 설계 결함을 발견했다. PM은 무엇을 먼저 해야 하는가? | 변경 사항으로 설계를 업데이트한다 | 품질 관리 계획을 업데이트한다 | 범위 관리 계획을 검토한다 | 아키텍처 검토를 요청한다 |  | D | 설계 결함이 발견되어 최종 품질을 위태롭게 할 수 있을 때, PM은 아키텍처 검토를 요청해야 한다. 요구사항 대비 시스템 설계를 평가하는 것이 적절한 첫 단계이다. 바로 설계 변경(A)은 충분한 검토 없이 성급하다. QM 계획 업데이트(B)는 검토 후에 한다. 범위 관리 계획(C)은 설계 문제와 직접 관련이 없다.
1248 | A project manager has just been appointed to a project that has two major deliverables. Both deliverables have the same level of priority and are to be delivered at the same time. The members of the team are complaining about the lack of information regarding which deliverable needs to be finished first. What should the project manager do? | Meet with the project sponsor and key stakeholders to assess each deliverable ' s value to the organization and set execution priorities. | Require that the project team execute both deliverables at the same time, since this was requested and approved in the project charter. | Ask key stakeholders to cancel the project due to the difficulty of executing both deliverables at the same time. | Ask the team to start working on the easiest deliverable first so they gain experience to execute the second deliverable. |  | A | When team members complain about lack of prioritization between two equal-priority deliverables due simultaneously, the project manager should meet with the sponsor and key stakeholders to assess each deliverable's value and set execution priorities. Value-based prioritization provides clear direction. Requiring simultaneous execution (B) ignores the team's concern. Canceling the project (C) is extreme. Starting with the easiest (D) is arbitrary, not value-driven. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 두 개의 동일 우선순위 주요 인도물이 있는 프로젝트에 배정되었다. 팀원이 우선순위 부재에 대해 불만이다. PM은 무엇을 해야 하는가? | 스폰서와 주요 이해관계자와 회의하여 각 인도물의 조직 가치를 평가한다 | 동시에 두 인도물 모두 실행하도록 팀에 요구한다 | 주요 이해관계자에게 어려움으로 인해 프로젝트 취소를 요청한다 | 경험을 쌓기 위해 쉬운 인도물부터 작업하도록 팀에 요청한다 |  | A | 동일 우선순위 인도물 간 우선순위가 없다고 팀이 불만할 때, PM은 스폰서와 이해관계자와 회의하여 각 인도물의 가치를 평가해야 한다. 이해관계자 참여가 명확한 우선순위를 제공한다. 동시 실행(B)은 갈등을 해결하지 않는다. 프로젝트 취소(C)는 과도하다. 쉬운 것부터(D)는 가치 기반이 아니다.
1249 | A company is conducting a digital transformation project that has a hard deadline. The marketing team wants to combine this implementation with a new product, and the newly assigned project manager is not aware of all the dependencies. Using a hybrid approach, what should the project manager do to ensure the dependencies are taken into consideration? | Implement a project newsletter so the different team members can be informed aboutthe progress of each project. | Combine all of the small projects into one big project so the team can collaboratebetter as one big team. | Facilitate communication promoting a Scrum of Scrums so the different teams areaware of the dependencies and progress. | Make sure that each individual project schedule is aligned with the common deadlines. |  | C | When a hybrid digital transformation project with a hard deadline involves dependencies with a marketing team's new product and the PM is unaware of all dependencies, the PM should facilitate a Scrum of Scrums so teams are aware of dependencies and progress. Cross-team coordination identifies and manages dependencies. A project newsletter (A) is one-directional. Combining into one project (B) adds complexity. Aligning individual schedules (D) is partial without communication. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Digital Transformation | 디지털 전환 프로젝트에 확정 기한이 있다. 마케팅 팀이 신제품과 합치려 한다. PM이 모든 종속성을 알지 못한다. PM은 무엇을 해야 하는가? | 프로젝트 뉴스레터를 구현하여 팀원이 서로의 진행을 알 수 있게 한다 | 모든 소규모 프로젝트를 하나의 큰 프로젝트로 합친다 | 스크럼 오브 스크럼을 촉진하여 팀들이 종속성을 인식하게 한다 | 각 개별 프로젝트 일정이 공통 기한에 정렬되도록 한다 |  | C | 하이브리드 디지털 전환 프로젝트에서 종속성이 있고 PM이 모두 파악하지 못할 때, 스크럼 오브 스크럼을 촉진하여 팀들이 종속성을 인식하게 해야 한다. 스크럼 오브 스크럼이 팀 간 협업과 종속성 관리를 가능하게 한다. 뉴스레터(A)는 일방적이다. 프로젝트 합병(B)은 비현실적이다. 일정 정렬(D)은 종속성 발견이 아니다.
1250 | A virtual project team has members located on four continents. The project director is concerned about the declining motivational levels of team members and feelings of noninclusion by other team members. The project director has tasked the project manager with finding a solution. What should the project manager do? | Take differences in time zones into consideration when scheduling team meetings. | Recommend that the project director appoint project managers for each continent. | Develop a plan for individual team members ' growth and organize more team-building events. | Set up ground rules for team engagement, taking into consideration different cultures. |  | D | For a virtual team across four continents experiencing declining motivation and feelings of non-inclusion, the project manager should set up ground rules for team engagement that take different cultures into consideration. Team agreements that respect time zones, cultural norms, and communication styles foster equity, psychological safety, and a sense of belonging. Taking time zones into account for scheduling (A) is one component but not a complete solution. Appointing project managers per continent (B) adds bureaucracy and fragments the team. Developing individual growth plans and team-building events (C) is supportive but does not directly address the inclusion and cultural awareness issues. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 가상 프로젝트 팀이 4개 대륙에 분포한다. 프로젝트 이사가 동기 부여 감소와 소속감 결여를 우려한다. PM은 무엇을 해야 하는가? | 팀 회의 일정 시 시간대 차이를 고려한다 | 프로젝트 이사에게 각 대륙별 PM을 임명하도록 권고한다 | 개인 성장 계획을 개발하고 더 많은 팀 빌딩 이벤트를 조직한다 | 다양한 문화를 고려한 팀 참여 기본 규칙을 설정한다 |  | D | 4개 대륙에 분포한 가상 팀의 동기와 소속감이 감소할 때, PM은 다양한 문화를 고려한 팀 참여 기본 규칙을 설정해야 한다. 문화적 민감성을 갖춘 기본 규칙이 포용적 환경을 만든다. 시간대 고려(A)는 부분적이다. 대륙별 PM(B)은 팀을 분리한다. 성장 계획(C)은 개인적이지만 팀 문화를 다루지 않는다.
1251 | One phase of a project took much longer than initially anticipated. The key stakeholders expressed their concern regarding a potential project delay. What should the project manager do? | Organize a root cause analysis (RCA) workshop. | Add more float to the overall project schedule | Request additional contingency from the sponsor. | Expedite the next phase to reduce slippage |  | A | When a project phase takes much longer than anticipated and stakeholders express concern, the project manager should organize a root cause analysis (RCA) workshop. Understanding why the delay occurred enables corrective actions and prevents recurrence. Adding float to the schedule (B) masks the problem. Requesting additional contingency (C) adds buffer without addressing causes. Expediting the next phase (D) adds pressure without understanding the issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트의 한 단계가 예상보다 훨씬 오래 걸렸다. 주요 이해관계자가 우려를 표명했다. PM은 무엇을 먼저 해야 하는가? | 근본 원인 분석(RCA) 워크숍을 조직한다 | 전체 프로젝트 일정에 더 많은 여유를 추가한다 | 스폰서에게 추가 비상 예비를 요청한다 | 다음 단계를 신속히 진행하여 지연을 줄인다 |  | A | 프로젝트 단계가 예상보다 오래 걸렸을 때, PM은 근본 원인 분석 워크숍을 조직해야 한다. 지연 원인을 이해하는 것이 향후 유사 지연을 방지한다. 여유 추가(B)는 원인 파악 없이 대응이다. 추가 비상(C)은 원인 분석 후에 한다. 신속 진행(D)은 품질을 위태롭게 할 수 있다.
1252 | A project manager is meeting with the project sponsor regarding a new project. The project manager tells the sponsor that, as part of the communications management plan, a weekly email will be sent with the status of the project, so the sponsor can be informed of the progress. The sponsor indicates that the email is not necessary because they will ask for a status update whenever it is needed. What should the project manager do next? | Ask the project sponsor what sort of information is needed and agree on a frequency for the communication. | Advise the project sponsor to request a 15-minute meeting, whenever necessary, with prior notification. | Agree to the project sponsor ' s request, but continue to copy them on the weekly email so they can be informed of progress in case it is needed. | Tell the project sponsor that if they prefer to not receive the communication, there is no problem in removing them from the email distribution. |  | A | The PM should perform communication requirements analysis by asking the sponsor what information they need and agreeing on a frequency for updates. This process considers factors such as availability, frequency, format, and level of detail. Tailoring the communications management plan to the sponsor's specific needs and preferences ensures effective and efficient information exchange. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | PM이 스폰서와 새 프로젝트에 대해 회의 중이다. 스폰서가 주간 이메일 업데이트 대신 선호하는 방식이 있다고 한다. PM은 무엇을 해야 하는가? | 스폰서에게 어떤 정보가 필요한지 묻고 커뮤니케이션 빈도에 합의한다 | 스폰서에게 필요할 때 사전 통보 후 15분 회의를 요청하도록 조언한다 | 스폰서의 요청에 동의하되 주간 이메일은 계속 참조로 보낸다 | 스폰서에게 커뮤니케이션을 받지 않아도 문제가 없다고 말한다 |  | A | 스폰서가 다른 커뮤니케이션 방식을 선호할 때, PM은 어떤 정보가 필요한지 묻고 빈도에 합의해야 한다. 커뮤니케이션 요구사항 분석이 효과적 소통의 기초이다. 15분 회의(B)는 스폰서 니즈를 가정한다. 주간 이메일 계속(C)은 요청을 무시한다. 소통 중단(D)은 스폰서 참여를 해친다.
1253 | A development team is struggling to find design documentation for the upcoming sprint. Prior to leaving for vacation, the product owner communicated that the documentation had been uploaded to the project file repository. What should the project manager do to address this issue? | Improve email communication protocols to manage project artifacts. | Investigate new software tools used to manage project artifacts. | Audit the effectiveness of the management of project artifacts. | Assign a team member to manage project artifacts. |  | C | When a development team cannot find design documentation the product owner uploaded before vacation, the project manager should audit the effectiveness of the management of project artifacts. Evaluating current processes identifies gaps and improves long-term artifact management. Improving email protocols (A) is narrow. Investigating new software tools (B) adds complexity without diagnosing the issue. Assigning a team member to manage artifacts (D) treats the symptom. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 개발 팀이 다가오는 스프린트를 위한 설계 문서를 찾기 어렵다. 제품 책임자가 휴가 전에 업로드했다. PM은 무엇을 해야 하는가? | 프로젝트 산출물 관리를 위한 이메일 커뮤니케이션 프로토콜을 개선한다 | 프로젝트 산출물 관리에 사용되는 새 소프트웨어 도구를 조사한다 | 프로젝트 산출물 관리의 효과를 감사한다 | 프로젝트 산출물 관리를 위한 팀원을 배정한다 |  | C | 팀이 설계 문서를 찾을 수 없을 때, PM은 프로젝트 산출물 관리의 효과를 감사해야 한다. 현재 프로세스의 평가가 시스템적 개선의 기초이다. 이메일 프로토콜(A)은 산출물 관리를 다루지 않는다. 새 도구(B)는 프로세스 파악 전에 성급하다. 팀원 배정(D)은 프로세스 개선이 아닌 인력 투입이다.
1254 | A key project team member is out on sick leave in the middle of a critical project iteration. The project sponsor learns that any delay with the end-of-iteration release will displease the business stakeholders. Although all team members are cross-functional, they are also working close to full capacity. What should the project manager do to address this situation? | Discuss the issues with the sponsor to fully convey the problem of the unavailable resource and the amount of work being done. shared. | Discuss this with the sponsor and hold a meeting with the stakeholders so all of the team challenges can be shared. | Discuss this with the team so they can complete the work of the unavailable team member and aim for the release deadline. | Discuss this with the team so they are able to reprioritize critical tasks and aim for the release deadline. |  | D | When a key team member is on sick leave during a critical iteration and all cross-functional members are near full capacity, the project manager should discuss with the team so they can reprioritize critical tasks and aim for the release deadline. Reprioritization focuses limited capacity on the most essential work. Discussing with the sponsor and meeting stakeholders (A) exposes problems before exploring team solutions. Conveying the resource problem to the sponsor (B) escalates prematurely. Having the team complete the absent member's full workload (C) overloads the team. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | 중요 이터레이션 중 주요 팀원이 병가이다. 모든 교차 기능 팀원이 거의 최대 용량이다. PM은 무엇을 해야 하는가? | 스폰서와 자원 불가용 문제와 팀 과제를 논의한다 | 스폰서와 논의하고 이해관계자와 회의하여 팀 과제를 논의한다 | 팀과 논의하여 불가용 팀원의 작업을 완료하고 릴리스 날짜를 목표로 한다 | 팀과 논의하여 중요 작업을 재우선순위화하고 릴리스 날짜를 목표로 한다 |  | D | 주요 팀원 병가 중 모든 팀원이 거의 최대 용량일 때, PM은 팀과 논의하여 중요 작업을 재우선순위화하고 릴리스 날짜를 목표로 해야 한다. 재우선순위화가 제한된 용량으로 최대 가치를 전달한다. 스폰서 논의(A)는 팀 해결 전에 성급하다. 이해관계자 회의(B)는 과도하다. 모든 작업 완료(C)는 비현실적이다.
1255 | During initiation of a new product improvement project, a project manager finds historical data showing that a similar project resulted in customers complaining of an even worse user experience compared to the previous product version. How can the project manager prevent this outcome in the new project? | Define a user focus group as external stakeholders with a high influence on outcomes | Define a high-level risk and plan mitigation after completing the work breakdown structure (WBS | Hire a consultant to perform a benefit analysis as an input to the project charter. | Hire a team of external users to perform acceptance testing on the product. |  | A | To prevent customer dissatisfaction from a product improvement project, the project manager should define a user focus group as external stakeholders with high influence on outcomes. Involving users early as stakeholders ensures the project aligns with their needs, expectations, and preferences, incorporating their feedback into scope, design, and quality decisions throughout the project. Defining a high-level risk after completing the WBS (B) delays action. Hiring a consultant for benefit analysis (C) adds cost without directly engaging users. Hiring external users for acceptance testing (D) provides feedback too late in the project lifecycle. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Stakeholders | Initiating | Focus on Value | Identify Stakeholders | Traditional PM | 신제품 개선 프로젝트 착수 시 PM이 유사 프로젝트에서 고객 불만족이 높았던 역사적 데이터를 발견했다. PM은 무엇을 해야 하는가? | 사용자 포커스 그룹을 결과에 높은 영향력을 가진 외부 이해관계자로 정의한다 | 고수준 리스크를 정의하고 WBS 완료 후 완화를 계획한다 | 프로젝트 헌장의 입력으로 혜택 분석을 수행할 컨설턴트를 고용한다 | 제품에 대한 인수 테스트를 수행할 외부 사용자 팀을 고용한다 |  | A | 유사 프로젝트에서 고객 불만족이 있었을 때, PM은 사용자 포커스 그룹을 높은 영향력 외부 이해관계자로 정의해야 한다. 사용자를 초기부터 참여시키는 것이 고객 불만족을 방지한다. 리스크 정의(B)는 WBS 후로 미루면 늦다. 컨설턴트(C)는 비용이 크다. 외부 테스트 팀(D)은 사후적이다.
1256 | A company is working on a project and is using a hybrid approach to streamline a customer service process. At the end of the second iteration, a business analyst joins the team to learn about the financial and scheduling aspects of project management. What should the project manager do to support the business analyst? | Create reports to inform the business analyst about the schedule and project cost | Provide the business analyst with access to the financial and scheduling information | Ask the business analyst to focus on their work allocation for the needs of the project | Assign resources to coach the business analyst |  | B | When a business analyst joins a hybrid project team to learn about financial and scheduling aspects, the project manager should provide the business analyst with access to the financial and scheduling information. Direct access enables self-directed learning and informed participation. Creating reports for the analyst (A) is passive and potentially outdated. Asking them to focus only on their work allocation (C) dismisses their learning objective. Assigning coaching resources (D) may not be necessary. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Hybrid/Tailoring | 회사가 하이브리드 접근법으로 고객 서비스 프로세스를 간소화하는 프로젝트를 진행 중이다. 비즈니스 분석가가 재무 및 일정 측면을 배우기 위해 팀에 합류했다. PM은 무엇을 해야 하는가? | 비즈니스 분석가에게 일정과 프로젝트 비용에 대한 보고서를 작성한다 | 비즈니스 분석가에게 재무 및 일정 정보에 대한 접근 권한을 제공한다 | 비즈니스 분석가에게 프로젝트 요구에 맞는 업무 배분에 집중하도록 요청한다 | 비즈니스 분석가를 코칭할 자원을 배정한다 |  | B | 비즈니스 분석가가 재무와 일정을 배우기 위해 합류했을 때, PM은 재무 및 일정 정보에 대한 접근 권한을 제공해야 한다. 정보 접근이 자기 주도 학습을 가능하게 한다. 보고서 작성(A)은 PM에게 추가 업무이다. 업무 집중(C)은 학습 목적을 무시한다. 코칭 자원(D)은 과도하다.
1257 | A software delivery project began having technical impediments. The issue may cause a delay of the deliverables. The technical service team has been working on the issue, but the issue remains unresolved even after 1 week of maintenance. What should the senior project manager do now? | Update the issue log with the status and priority. | Use interpersonal skills to expedite the issue. | Send a gentle reminder to the technical service team. | Issue a formal warning to the technical service team. |  | A | When technical impediments threaten project deliverables, the PM should formally document and track them in the issue log. This ensures all stakeholders are aware of the impediments and the actions being taken. The issue log provides a structured method for prioritizing and addressing problems, facilitating better decision-making and resource allocation. This practice aligns with PMI principles of communication, transparency, and systematic issue management. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 소프트웨어 납품 프로젝트에 기술적 장애물이 발생했다. 인도물 지연을 야기할 수 있다. 기술 서비스 팀이 아직 해결하지 못했다. PM은 무엇을 해야 하는가? | 이슈 로그에 상태와 우선순위를 업데이트한다 | 대인관계 기술을 사용하여 이슈를 신속히 처리한다 | 기술 서비스 팀에 부드러운 리마인더를 보낸다 | 기술 서비스 팀에 공식 경고를 발행한다 |  | A | 기술적 장애물이 인도물을 위협할 때, PM은 이슈 로그에 상태와 우선순위를 업데이트해야 한다. 공식 문서화와 추적이 모든 이해관계자에게 장애물과 조치를 인식시킨다. 대인관계 기술(B)은 보충적이다. 리마인더(C)는 추적이 안 된다. 공식 경고(D)는 과도하다.
1258 | A project manager resigned from a recently approved project. A new project manager has been assigned to the project and needs to determine the delegated authority. What should the new project manager do next? | Update the communications management plan | Assess the stakeholder register | Refer to the project charter | Review the project resource matrix |  | C | A newly assigned project manager should refer to the project charter to determine the delegated authority. The project charter formally authorizes the project and documents the PM's authority to apply organizational resources to project activities. It also outlines project objectives, key stakeholders, constraints, and the scope of decision-making power granted to the project manager. Updating the communications management plan (A) is a task that comes after understanding the project's governance structure. Assessing the stakeholder register (B) is useful for understanding relationships but does not define the PM's authority. Reviewing the project resource matrix (D) addresses resource allocation, not the scope of delegated authority. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 최근 승인된 프로젝트에서 사임했다. 새 PM이 배정되어 위임된 권한을 파악해야 한다. 무엇을 참조해야 하는가? | 커뮤니케이션 관리 계획을 업데이트한다 | 이해관계자 등록부를 평가한다 | 프로젝트 헌장을 참조한다 | 프로젝트 자원 매트릭스를 검토한다 |  | C | 새로 배정된 PM이 위임된 권한을 파악하려면 프로젝트 헌장을 참조해야 한다. 헌장이 프로젝트를 공식 승인하고 PM의 권한을 문서화한다. 커뮤니케이션 계획(A)은 권한이 아니다. 이해관계자 등록부(B)는 이해관계자 정보이다. 자원 매트릭스(D)는 자원 배정이다.
1259 | A project manager manages multiple information technology (IT) projects in a matrix organization. The project manager schedules a meeting with one of the functional managers to coordinate testing support for two software development projects. Unfortunately, the functional manager is not able to attend the meeting and informs the project manager that there may not be any resources available to test the software. What should the project manager do? | Discuss the testing requirements with a test engineer and negotiate the best approach to test the newly developed software. | Meet with a procurement specialist to negotiate with a company that specializes in software testing to test the software. | Meet with the project team to collaboratively determine how the project manager can ensure the needed testing assistance is obtained. | Request a meeting with the sponsor to change the scope to allow the development team to conduct testing. |  | C | In a matrix organization, the PM should collaborate with the project team to resolve resource availability issues. Meeting with the team enables exploration of various options—adjusting schedules, reallocating resources, or finding alternative solutions—to ensure necessary testing support is provided. This approach aligns with principles of stakeholder engagement and resource optimization emphasized in PMI standards. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 매트릭스 조직에서 PM이 여러 IT 프로젝트를 관리한다. 새 기능 테스트를 위한 자원이 부족하다. PM은 무엇을 해야 하는가? | 테스트 엔지니어와 테스트 요구사항을 논의하고 최적 접근법을 협상한다 | 소프트웨어 테스트 전문 회사와 협상하기 위해 조달 전문가와 회의한다 | 프로젝트 팀과 회의하여 협력적으로 필요한 자원 확보 방법을 결정한다 | 스폰서와 회의하여 개발 팀이 테스트하도록 범위를 변경한다 |  | C | 매트릭스 조직에서 테스트 자원이 부족할 때, PM은 프로젝트 팀과 회의하여 협력적으로 해결 방법을 결정해야 한다. 팀 협업이 일정 조정, 자원 재배치 등 다양한 옵션을 탐색한다. 테스트 엔지니어 협상(A)은 범위가 좁다. 외부 조달(B)은 비용이 크다. 범위 변경(D)은 과도하다.
1260 | A project team member reads in a financial newspaper that the main project supplier is facing some financial difficulties and communicates this to the project manager. What should the project manager do? | Use the issue log to record the situation immediately | Add the situation to the project risk register to be managed | Inform the purchasing department that manages the supplier relationship | Identify competitors that are qualified to replace the current supplier |  | C | When a team member reports that the main supplier is facing financial difficulties based on news reports, the project manager should inform the purchasing department that manages the supplier relationship. The appropriate department can take procurement actions. Using the issue log (A) documents but does not address procurement. Adding to the risk register (B) captures uncertainty but does not act. Identifying competitor suppliers (D) bypasses procurement governance. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Hybrid/Tailoring | 팀원이 금융 신문에서 주요 공급업체가 재정적 어려움에 처해 있다는 것을 읽었다. PM은 무엇을 해야 하는가? | 이슈 로그를 사용하여 상황을 즉시 기록한다 | 프로젝트 리스크 등록부에 상황을 추가하여 관리한다 | 공급업체 관계를 관리하는 구매 부서에 알린다 | 현재 공급업체를 대체할 자격이 있는 경쟁업체를 식별한다 |  | C | 주요 공급업체의 재정 어려움 소식을 들었을 때, PM은 공급업체 관계를 관리하는 구매 부서에 알려야 한다. 구매 부서가 공급업체 상황을 검증하고 적절히 대응할 수 있다. 이슈 로그(A)는 내부 기록이지만 조치가 아니다. 리스크 등록(B)은 검증 전에 한다. 대체업체 식별(D)은 시기상조이다.
1261 | At the end of a project with multiple suppliers, the project manager is reviewing the closing process and finds that an unexpected financial balance is remaining. What will help the project manager understand why this has occurred? | Organizational process assets | Project audit | Procurement audit | Lessons learned |  | C | When an unexpected financial balance remains at the end of a multi-supplier project, a procurement audit will help the project manager understand why. A structured review of procurement processes and contracts identifies errors, discrepancies, or payment issues. Organizational process assets (A) provide general references. A project audit (B) is broader and less focused on procurement. Lessons learned (D) capture knowledge but may not detail financial discrepancies. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 여러 공급업체가 있는 프로젝트 종료 시 PM이 예상치 못한 재정 잔액을 발견했다. 어떤 도구가 원인 파악에 도움이 되는가? | 조직 프로세스 자산 | 프로젝트 감사 | 조달 감사 | 교훈 |  | C | 여러 공급업체 프로젝트 종료 시 예상치 못한 재정 잔액이 있을 때, 조달 감사가 원인 파악에 도움이 된다. 조달 프로세스와 계약의 구조화된 검토가 차이를 식별한다. OPA(A)는 일반 참조이다. 프로젝트 감사(B)는 전체적이지만 조달 특화가 아니다. 교훈(D)은 미래용이다.
1262 | A project manager is performing earned value management (EVM) for a cross-country pipeline project. The project manager has determined the ratio of earned value (EV) to actual cost (AC) for the project and has found the calculated result to be 0.9024. What does this value mean for the project? | The project has started exceeding the planned cost. | The project has earned more value than planned. | The project is close to exceeding the planned cost. | The project is earning less value an was planned. |  | D | A CPI (Cost Performance Index) of 0.9024—calculated as the ratio of EV to AC—means the project is earning less value than was planned for every unit of currency spent. Specifically, for every dollar spent, the project is only producing approximately $0.90 in value, indicating the project is over budget relative to the work completed. The project has not started exceeding planned cost (A)—it already has. Earning more value than planned (B) would require a CPI greater than 1. Being close to exceeding planned cost (C) is imprecise—the project is already over budget. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | PM이 대규모 파이프라인 프로젝트의 EVM을 수행 중이다. CPI가 0.9024이다. 이것은 무엇을 의미하는가? | 프로젝트가 계획된 비용을 초과하기 시작했다 | 프로젝트가 계획보다 더 많은 가치를 획득했다 | 프로젝트가 계획된 비용 초과에 가까워지고 있다 | 프로젝트가 계획보다 적은 가치를 획득하고 있다 |  | D | CPI 0.9024는 지출된 통화 단위당 계획보다 적은 가치를 획득하고 있음을 의미한다. 구체적으로 1달러를 지출할 때마다 약 0.90달러의 가치만 획득한다. CPI가 1 미만이면 비용 초과를 나타낸다.
1263 | A project manager is leading a team and wants each team member to produce their deliverables and be held accountable for the work product. What should the project manager do first? | Create a plan of action and milestones (POAM) to detail the deliverables for each project team member. | Engage with each project team member to explain the individual consequences of late delivery. | Empower each project team member with ownership of a particular aspect of the project. | Establish a daily standup meeting where each project team member reports their progress. |  | C | The correct answer is C. Empower each project team member with ownership of a particular aspect of the project. Resource management includes ensuring the team has adequate skills, capacity, and support. The PM should address resource gaps and challenges proactively to maintain project delivery. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | PM이 각 팀원이 인도물을 생산하고 책임을 지게 하고 싶다. PM은 무엇을 해야 하는가? | 각 팀원의 인도물을 상세히 기술하는 행동 계획과 마일스톤(POAM)을 작성한다 | 각 팀원에게 지연 납품의 개인적 결과를 설명한다 | 각 팀원에게 프로젝트의 특정 측면에 대한 소유권을 부여한다 | 각 팀원이 진행 상황을 보고하는 데일리 스탠드업을 설정한다 |  | C | 정답은 C이다. 각 팀원에게 프로젝트의 특정 측면에 대한 소유권을 부여한다. 소유권 부여가 자발적 책임감과 동기를 높인다. POAM(A)은 마이크로매니지먼트이다. 결과 설명(B)은 위협적이다. 스탠드업(D)은 모니터링이지 권한 부여가 아니다.
1264 | A project team has installed software for the client, passed the knowledge to operations, sent the final report, and celebrated. Then 1 week later, the client sends a list of requirements that have not been met. The client is requesting to fix the issues quickly and within the initial budget. What should the project manager have done to prevent this from happening? | Allocated a risk budget for any post-release improvements. | Reviewed the acceptance criteria and obtained client approval. | Established meetings with the client throughout the project phases. | Conducted a pilot to understand the client ' s performance parameters. |  | B | When a client sends unmet requirements after project completion and demands fixes within the initial budget, the project manager should have reviewed the acceptance criteria and obtained client approval before closure. Formal acceptance validation prevents post-delivery disputes. Allocating a risk budget for post-release improvements (A) anticipates issues without preventing them. Establishing meetings throughout phases (C) maintains communication but does not validate acceptance. Conducting a pilot (D) tests performance but does not confirm requirement completion. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Scope | Planning | Adopt a Holistic View | Collect Requirements | Traditional PM | 프로젝트 팀이 소프트웨어를 설치하고 운영에 지식을 전달하고 최종 보고서를 보내고 축하했다. 그런데 고객이 요구사항 미충족을 보내며 초기 예산 내 수정을 요구한다. PM이 이전에 무엇을 했어야 하는가? | 릴리스 후 개선을 위한 리스크 예산을 배정했다 | 인수 기준을 검토하고 고객 승인을 받았다 | 프로젝트 단계 전반에 걸쳐 고객과 정기 회의를 설정했다 | 고객의 성능 매개변수를 이해하기 위한 파일럿을 수행했다 |  | B | 고객이 프로젝트 완료 후 요구사항 미충족을 주장할 때, PM이 이전에 인수 기준을 검토하고 고객 승인을 받았어야 했다. 공식 인수가 범위와 품질 충족을 확인한다. 리스크 예산(A)은 사후 대응이다. 정기 회의(C)는 유용하지만 공식 인수를 대체하지 않는다. 파일럿(D)은 선택적이다.
1265 | At a meeting to receive approval for the project management plan, a project manager realizes that there is so much detail in the presentation that many of the stakeholders are not actively engaged in the process. The stakeholders are agreeing to the scope, goals, and timelines without giving them substantial thought. How should the project manager proceed? | Get approval and promise to email more information to the stakeholders to clarify the technical details. | Set up information review sessions before reconvening another approval session. | Obtain approval as fast as possible and close the meeting. | Stop the meeting and reschedule for another time with a more concise presentation. |  | B | When stakeholders approve plans without adequate engagement, the PM should pause and ensure they understand the implications before proceeding. Expert judgment and facilitation techniques help draw stakeholders into meaningful discussion. The other options—stopping the meeting abruptly, accepting superficial approval, or rushing through—don't address the root problem of inadequate stakeholder involvement and commitment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 프로젝트 관리 계획 승인 회의에서 PM이 이해관계자가 세부 사항이 너무 많아 적극적으로 참여하지 않는 것을 발견한다. PM은 무엇을 해야 하는가? | 승인을 받고 기술적 세부 사항을 이메일로 보내겠다고 약속한다 | 정보 검토 세션을 설정한 후 다른 승인 세션을 재개한다 | 가능한 빨리 승인을 받고 회의를 종료한다 | 회의를 중지하고 더 간결한 발표로 다른 시간에 재일정을 잡는다 |  | B | 이해관계자가 세부 사항에 적극 참여하지 않을 때, PM은 정보 검토 세션을 설정한 후 승인 세션을 재개해야 한다. 이해관계자가 내용을 이해한 후 승인하는 것이 중요하다. 이메일 약속(A)은 이해를 보장하지 않는다. 빠른 승인(C)은 참여 없는 승인이다. 회의 중지(D)는 시간을 낭비한다.
1266 | A project team was hired to perform on-site duties, but there were unexpected circumstances that required the entire team to work remotely. Some team members returned to their hometowns and they are now requesting reimbursement for operational expenditures. What should the project manager do? | Review the budget and allocate funds for the reimbursements | Update the project management plan with the incurred costs | Follow the Perform integrated Change Control process and submit a change request | Ask the team members to draft a justification before processing the reimbursements |  | C | When team members working remotely due to unexpected circumstances request reimbursement for operational expenses, the project manager should follow the Perform Integrated Change Control process and submit a change request. Formal change control addresses unanticipated costs. Reviewing budget and allocating funds (A) bypasses governance. Updating the plan with incurred costs (B) accepts costs without approval. Asking for justification (D) is reasonable but change control comes first. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 현장 근무를 위해 고용되었으나 예상치 못한 상황으로 원격 근무를 해야 했다. 팀원들이 운영 비용 환급을 요청한다. PM은 무엇을 해야 하는가? | 예산을 검토하고 환급을 위한 자금을 배정한다 | 발생 비용으로 프로젝트 관리 계획을 업데이트한다 | 통합 변경 통제 수행 프로세스를 따르고 변경 요청을 제출한다 | 환급 처리 전에 팀원에게 정당성 초안을 작성하도록 요청한다 |  | C | 예상치 못한 원격 근무로 팀원들이 운영 비용 환급을 요청할 때, PM은 통합 변경 통제 수행 프로세스를 따르고 변경 요청을 제출해야 한다. 공식 변경 통제가 적절한 승인을 보장한다. 예산 배정(A)은 승인 없이 진행한다. 계획 업데이트(B)는 승인 절차를 건너뛴다. 정당성 요청(D)은 불필요한 지연이다.
1267 | The project manager is experiencing delays with two critical tasks that are to be executed by two different teams. The project manager realizes that the functional managers of these two teams have an unsolved conflict and they are not communicating properly. What should the project manager do? | Communicate with the project sponsor regarding the need to resolve the conflict between the managers. | Meet with both teams and their managers and try to figure out the root cause of the conflict | Arrange a meeting with the managers and try to reach an agreement. | Evaluate the impact of the delay on the project and look for alternatives to create a remediation plan |  | C | When two critical tasks are delayed because the functional managers of the two teams have an unresolved conflict, the project manager should arrange a meeting with the managers to try to reach an agreement. Direct facilitation addresses the root cause. Communicating with the sponsor (A) escalates prematurely. Meeting with both teams and managers (B) is broader than needed. Evaluating delay impact (D) assesses consequences but does not resolve the conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 두 다른 팀이 수행할 두 핵심 작업에서 지연을 겪고 있다. 기능 관리자 간 갈등이 원인이다. PM은 무엇을 해야 하는가? | 관리자 간 갈등 해결 필요성에 대해 프로젝트 스폰서와 소통한다 | 양 팀과 관리자를 만나 갈등의 근본 원인을 파악한다 | 관리자와 회의를 주선하여 합의에 도달하려 한다 | 지연이 프로젝트에 미치는 영향을 평가하고 시정 계획을 위한 대안을 찾는다 |  | C | 두 팀의 기능 관리자 간 미해결 갈등으로 핵심 작업이 지연될 때, PM은 관리자와 회의를 주선하여 합의에 도달해야 한다. 직접적 갈등 해결이 가장 효과적이다. 스폰서 소통(A)은 직접 해결 시도 전에 에스컬레이션이다. 양 팀 회의(B)는 관리자 수준 갈등에 불필요한 인원을 포함한다. 영향 평가(D)는 갈등을 해결하지 않는다.
1268 | An agile project team is building a new product. The stakeholders require ongoing illustration of project business value. How should the project manager proceed? | Include demonstrations of the built portion of the product at the end of every sprint. | Prepare performance value reports for the business on an ongoing basis. | Prepare a project report for the stakeholders and distribute it weekly. | Confirm the minimum viable product (MVP) and demonstrate it to the business when it is ready. |  | A | In agile projects, demonstrating the built portion of the product at the end of every sprint delivers value early and often. Sprint demonstrations provide stakeholders with tangible evidence of progress, collect real-time feedback, and validate that the product meets expectations. Performance reports (A) may not reflect actual functionality. Weekly reports (C) may lack timeliness and stakeholder input. Waiting for the complete MVP (D) delays stakeholder feedback and contradicts the agile principle of frequent value delivery. | Process | Manage Project Changes | Project Work | Embrace Adaptability and Resiliency | Agile | Scrum | Business Environment | Manage and Control Changes | Governance | Monitoring & Controlling | Focus on Value | Perform Integrated Change Control | Traditional PM | 애자일 프로젝트 팀이 새 제품을 구축 중이다. 이해관계자가 지속적인 비즈니스 가치 시연을 요구한다. PM은 무엇을 해야 하는가? | 매 스프린트 종료 시 구축된 제품 부분의 시연을 포함한다 | 비즈니스를 위한 성과 가치 보고서를 지속적으로 준비한다 | 이해관계자를 위한 프로젝트 보고서를 준비하여 매주 배포한다 | MVP를 확인하고 준비되면 비즈니스에 시연한다 |  | A | 애자일 프로젝트에서 이해관계자가 지속적 비즈니스 가치 시연을 요구할 때, 매 스프린트 종료 시 구축된 제품 부분을 시연해야 한다. 스프린트 시연이 이해관계자에게 진행의 실질적 증거를 제공한다. 성과 보고서(B)는 추상적이다. 주간 보고서(C)는 실제 제품을 보여주지 않는다. MVP 시연(D)은 너무 늦다.
1269 | A project manager is using a hybrid approach to comply with a regulatory requirement. The planning and closing phases will use a predictive approach, and the execution phase will use an iterative approach. During the second sprint review, the project sponsor requested a change in priority for some of the product backlog items. What should the project manager do as a servant leader? | Review the impact of the change on the schedule management plan baseline | Support the product owners decision to change the priority of the product backlog items | Accept the request and include the product backlog items in the next sprint | Ask the sponsor to submit a change request to the change control board (CCB) |  | B | As a servant leader using a hybrid approach, the project manager should support the product owner's decision to change the priority of product backlog items. In the agile portion of a hybrid project, the product owner has authority over backlog prioritization to ensure maximum value delivery. The PM's role is to empower the product owner and facilitate the change. Reviewing the impact on the schedule management plan baseline (A) applies predictive thinking to an agile process. Accepting the request and including items in the next sprint without consulting the product owner (C) bypasses the product owner's authority. Asking the sponsor to submit a change request to the CCB (D) imposes a rigid, bureaucratic process that conflicts with agile principles. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | PM이 규제 요구사항 준수를 위해 하이브리드 접근법을 사용 중이다. 제품 책임자가 백로그 우선순위 변경을 요청한다. PM은 무엇을 해야 하는가? | 일정 관리 계획 베이스라인에 대한 변경 영향을 검토한다 | 제품 책임자의 백로그 항목 우선순위 변경 결정을 지원한다 | 요청을 수락하고 제품 백로그 항목을 다음 스프린트에 포함한다 | 스폰서에게 변경 요청을 CCB에 제출하도록 요청한다 |  | B | 하이브리드 접근법에서 서번트 리더로서 PM은 제품 책임자의 백로그 항목 우선순위 변경 결정을 지원해야 한다. 하이브리드 프로젝트의 애자일 부분에서 제품 책임자가 백로그 우선순위 권한을 가진다. 일정 영향 검토(A)는 예측형 관점이다. 즉시 수락(C)은 평가 없이 진행한다. CCB 제출(D)은 애자일 부분에는 과도하다.
1270 | A company is implementing a project with team members who are located in different countries and time zones. Performance assessments show that team performance is low because the team doesn't have a common understanding about task distribution. What should the project manager do? | Review and reassign tasks | Colocate the team members | Perform team-building activities | Revisit the communications management plan |  | C | When a geographically distributed team lacks common understanding about task distribution and performance is low, the project manager should perform team-building activities. These activities improve communication, collaboration, and shared understanding of roles and responsibilities across time zones. Reviewing and reassigning tasks (A) addresses symptoms but not the underlying team cohesion issue. Colocating team members (B) may be impractical. Revisiting the communications management plan (D) helps communication channels but does not build the interpersonal relationships needed for shared understanding. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Develop a Common Vision | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 회사가 다른 국가와 시간대에 있는 팀원들로 프로젝트를 구현 중이다. 성과가 낮다. PM은 무엇을 해야 하는가? | 작업을 검토하고 재할당한다 | 팀원을 한 장소에 모은다 | 팀 빌딩 활동을 수행한다 | 커뮤니케이션 관리 계획을 재검토한다 |  | C | 지리적으로 분산된 팀이 업무 분배에 대한 공통 이해가 부족하고 성과가 낮을 때, PM은 팀 빌딩 활동을 수행해야 한다. 팀 빌딩이 신뢰와 협업을 개선한다. 작업 재할당(A)은 근본 원인을 해결하지 않는다. 한 장소 모임(B)은 비현실적이다. 커뮤니케이션 계획(D)은 관계 구축이 아닌 프로세스이다.
1271 | The project manager's firm is executing a construction project. The project is stalled due to reemerging conflicts and misunderstandings among stakeholders. What should the project manager do to ensure a smooth start and completion of the project? | Conduct an on-site survey, start the project to avoid any undue delays, and ensure costs are under control | Invite all the stakeholders to a change control board (CCB) meeting, share feedback and facts, and come to a consensus. | Determine the root cause of the misunderstandings, get all parties to reach a consensus, 543 and help to implement the outcome. | Advise the firm to cancel the project due to misunderstandings among the stakeholders and the associated risks. |  | C | When a construction project is stalled due to reemerging conflicts and misunderstandings among stakeholders, the project manager should determine the root cause of the misunderstandings, get all parties to reach a consensus, and help implement the outcome. Root cause analysis with collaborative resolution addresses the underlying issues. Conducting a survey and starting immediately (A) rushes without resolving conflicts. Inviting stakeholders to a CCB meeting (B) addresses process but not interpersonal conflict. Canceling the project (D) is extreme. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM의 회사가 건설 프로젝트를 수행 중이다. 이해관계자 간 재발하는 갈등과 오해로 프로젝트가 중단되었다. PM은 무엇을 해야 하는가? | 현장 조사를 실시하고 지연을 피하기 위해 프로젝트를 시작하며 비용을 통제한다 | 모든 이해관계자를 CCB 회의에 초대하고 피드백과 사실을 공유하며 합의를 도출한다 | 오해의 근본 원인을 파악하고 모든 당사자가 합의에 도달하도록 돕는다 | 이해관계자 간 오해와 관련 리스크로 인해 프로젝트 취소를 회사에 권고한다 |  | C | 이해관계자 간 재발하는 갈등과 오해로 건설 프로젝트가 중단될 때, PM은 오해의 근본 원인을 파악하고 모든 당사자가 합의에 도달하도록 도와야 한다. 근본 원인 분석과 협력적 해결이 효과적이다. 현장 조사(A)는 갈등을 해결하지 않는다. CCB 회의(B)는 변경 통제이지 갈등 해결이 아니다. 프로젝트 취소(D)는 극단적이다.
1272 | A team member has a sudden emergency that may last for several days. There are no other team members who can cover their tasks and job duties. What should the project manager do to address this concern? | Log the situation in the issue log. | Ask the human resources (HR) manager for an external replacement. | Hold an emergency project team meeting to discuss the situation. | Update the key stakeholders on the issue. |  | A | When a team member has a sudden emergency lasting several days with no replacement available, the project manager should first log the situation in the issue log. Documenting the issue enables tracking and structured response. Holding an emergency meeting (C) should follow documentation. Asking HR for an external replacement (B) is a potential action but not the first step. Updating stakeholders (D) follows issue assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Adopt a Holistic View | Plan Stakeholder Engagement | Traditional PM | 팀원에게 며칠간 지속될 수 있는 긴급 상황이 발생했다. 다른 팀원이 업무를 대체할 수 없다. PM은 무엇을 먼저 해야 하는가? | 이슈 로그에 상황을 기록한다 | 인사부(HR) 관리자에게 외부 대체 인력을 요청한다 | 긴급 프로젝트 팀 회의를 개최하여 상황을 논의한다 | 주요 이해관계자에게 이슈를 업데이트한다 |  | A | 팀원에게 대체 불가능한 긴급 상황이 발생할 때, PM은 먼저 이슈 로그에 상황을 기록해야 한다. 문서화가 추적과 후속 조치의 기반이다. HR 요청(B)은 기록 후에 한다. 팀 회의(C)는 문서화 후에 한다. 이해관계자 업데이트(D)는 상황 파악 후에 한다.
1273 | A customer complains that a software update project is failing to deliver value according to the original scope. What should the project manager do to resolve the problem? | Ensure that the project risk register is current and reflects the impacts posed by stories not delivered. | Ensure that the project issue log is up-to-date with the customer ' s issues related to the missed stories. | Ensure that the project backlog has the features and stories prioritized correctly. | Ensure that the project change log is up-to-date with the stories based on the missed requirements. |  | C | When a customer complains about failure to deliver value according to original scope, the project manager should ensure the project backlog has features and stories prioritized correctly. In agile environments, value delivery is driven by an actively managed and prioritized product backlog—misalignment often originates from improper backlog management. Ensuring the risk register is current (A) addresses potential problems but not current value delivery. Updating the issue log (B) is reactive documentation. Updating the change log (D) tracks changes but does not address prioritization. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 고객이 소프트웨어 업데이트 프로젝트가 원래 범위에 따른 가치를 전달하지 못한다고 불만한다. PM은 무엇을 해야 하는가? | 프로젝트 리스크 등록부가 미전달 스토리의 영향을 반영하도록 한다 | 프로젝트 이슈 로그가 누락된 범위 관련 고객 이슈로 최신 상태인지 확인한다 | 프로젝트 백로그의 기능과 스토리가 올바르게 우선순위화되었는지 확인한다 | 프로젝트 변경 로그가 누락된 요구사항 기반 스토리로 최신 상태인지 확인한다 |  | C | 고객이 원래 범위에 따른 가치 미전달을 불만할 때, PM은 프로젝트 백로그의 기능과 스토리가 올바르게 우선순위화되었는지 확인해야 한다. 애자일에서 올바른 우선순위가 가치 전달을 보장한다. 리스크 등록부(A)는 리스크 관리이지 가치 전달이 아니다. 이슈 로그(B)는 기록이지 해결이 아니다. 변경 로그(D)는 문서화이지 우선순위가 아니다.
1274 | A project manager has been assigned to lead an IT project to store information on sold lottery tickets. During the project execution, a failure in the system caused 10 numbers to be sold two times. This happened during the month of greatest demand because the prize was the highest of the year. The project team is concerned that one of those tickets could be the winner. What should the project manager do first? | Reassure the sponsor by explaining the probability of this risk materializing is extremely low. | Review the list of risks to verify that this issue was considered and execute the detailed action plan. | Carry out tests to verify that the system does not fail again due to the high occurrence of events. | Inform the sponsor about the issue and make a request for sufficient funds to be made available. |  | B | When a system failure causes duplicate lottery ticket numbers during peak demand, the project manager should first review the list of risks to verify whether this issue was anticipated and execute the detailed action plan. If the risk was previously identified, a pre-defined response strategy should be ready to implement. Reassuring the sponsor about low probability (A) dismisses the severity of an event that has already occurred. Carrying out system tests (C) is a corrective measure but not the first action. Informing the sponsor and requesting funds (D) is premature before reviewing the existing risk response plan. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | PM이 판매된 복권 정보 저장 IT 프로젝트를 이끌고 있다. 피크 수요 시 시스템 장애로 복권 번호가 중복되었다. PM은 무엇을 해야 하는가? | 스폰서에게 이 리스크가 실현될 확률이 극히 낮다고 안심시킨다 | 리스크 목록을 검토하여 이 문제가 고려되었는지 확인하고 상세 조치 계획을 실행한다 | 높은 이벤트 발생으로 인한 시스템 재장애를 방지하기 위해 테스트를 수행한다 | 스폰서에게 이슈를 알리고 충분한 자금 확보를 요청한다 |  | B | 피크 수요 시 시스템 장애로 복권 번호가 중복될 때, PM은 먼저 리스크 목록을 검토하여 이 문제가 예상되었는지 확인하고 상세 조치 계획을 실행해야 한다. 기존 리스크 대응 계획 활용이 우선이다. 안심시키기(A)는 문제를 무시한다. 테스트(C)는 즉각 대응 후에 한다. 자금 요청(D)은 리스크 대응 확인 후에 한다.
1275 | While sizing a user story in planning poker, one team member believes the user story should be 8 points. Another believes the story should be 2 points. What should the scrum master do? | Select the junior member ' s estimate since they will most likely be doing the work. | Consult the lessons learned for insight into the correct estimate. | Determine the average of the two estimates and assign that amount. | Ask the product owner to rewrite the story so the final estimate can be agreed upon. |  | D | Significant estimation discrepancies typically indicate ambiguity or excessive scope in the user story. The team should ask the product owner to refine the story for better understanding and more accurate estimation. Averaging estimates (A) is not an agile practice. External expert opinion (C) may help but isn't sufficient for real-time decisions. Arbitrary selection (D) ignores team consensus. Backlog refinement (B) supports agile estimation best practices. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 플래닝 포커에서 한 팀원은 8포인트, 다른 팀원은 2포인트로 추정한다. 큰 차이가 있다. PM은 무엇을 해야 하는가? | 주니어 팀원의 추정을 선택한다. 작업을 할 가능성이 높기 때문이다 | 올바른 추정에 대한 통찰을 위해 교훈을 참조한다 | 두 추정의 평균을 결정하여 해당 값을 할당한다 | 제품 책임자에게 최종 추정에 합의할 수 있도록 스토리를 다시 작성하도록 요청한다 |  | D | 추정에 큰 차이가 있을 때, 이는 일반적으로 사용자 스토리의 모호성이나 과도한 범위를 나타낸다. 팀은 제품 책임자에게 스토리를 세분화하여 더 정확한 추정이 가능하도록 해야 한다. 주니어 선택(A)은 임의적이다. 교훈 참조(B)는 현재 스토리에 부적합하다. 평균(C)은 불확실성을 해결하지 않는다.
1276 | A subcontractor informs the project manager that they are unable to supply a key component to the project. What should the project manager do? | Discuss the issue with the project sponsor and request extra time and budget to obtainthe component from a different supplier. | Raise a new risk in the risk register, perform a risk assessment, and convene SMEs and relevant stakeholders to plan a risk response | Submit a change request to the change control board (CCB) for changes to theperformance measurement baseline to obtain the component from a different supplier. | Raise a new issue in the issue log and convene subject matter experts (SMEs) andrelevant stakeholders to identify alternatives to address the problem. |  | D | When a subcontractor cannot supply a key component, the project manager should raise a new issue in the issue log and convene SMEs and relevant stakeholders to identify alternatives. This is an actual problem that has occurred and requires immediate issue resolution, not risk planning. Discussing with the sponsor for extra time and budget (A) is premature without exploring alternatives. Raising a risk in the risk register (B) treats it as a potential problem rather than an actual issue. Submitting a change request to the CCB (C) is a formal process that may not be necessary if alternatives exist. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 하도급업체가 PM에게 프로젝트의 핵심 구성 요소를 공급할 수 없다고 알린다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서와 이슈를 논의하고 다른 공급업체에서 구성 요소를 확보하기 위한 추가 시간과 예산을 요청한다 | 리스크 등록부에 새 리스크를 등록하고 리스크 평가를 수행하며 SME와 이해관계자를 소집한다 | CCB에 성과 측정 기준선 변경을 위한 변경 요청을 제출한다 | 이슈 로그에 새 이슈를 등록하고 SME와 이해관계자를 소집하여 대안을 식별한다 |  | D | 하도급업체가 핵심 구성 요소를 공급할 수 없을 때, PM은 이슈 로그에 새 이슈를 등록하고 SME와 이해관계자를 소집하여 대안을 식별해야 한다. 이것은 리스크가 아닌 실제 발생한 이슈이다. 스폰서 논의(A)는 대안 파악 후에 한다. 리스크 등록(B)은 이미 실현된 이슈에는 부적합하다. CCB 변경 요청(C)은 대안 확인 후에 한다.
1277 | An agile team of specialized engineers has completed some tasks later than planned and with a lower quality than expected. The situation is limiting the value the team is creating for the business. What should the project manager do next? | Confirm the right quality tests are applied before moving to the next iteration. | Include all the quality problems found in the technical debt backlog. | Schedule quality reviews to obtain stakeholder approvals and feedback. | Execute the next iteration planning considering the quality issues. |  | A | When an agile team of specialized engineers completes tasks late and with lower quality, the project manager should confirm the right quality tests are applied before moving to the next iteration. Quality gates prevent defects from compounding. Including issues in technical debt (B) normalizes poor quality. Scheduling stakeholder quality reviews (C) is reactive. Planning the next iteration (D) without addressing quality perpetuates the problem. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 전문 엔지니어로 구성된 애자일 팀이 일부 작업을 계획보다 늦고 기대보다 낮은 품질로 완료했다. PM은 무엇을 해야 하는가? | 다음 이터레이션으로 이동하기 전에 올바른 품질 테스트가 적용되는지 확인한다 | 발견된 모든 품질 문제를 기술 부채 백로그에 포함한다 | 이해관계자 승인과 피드백을 얻기 위한 품질 리뷰를 예약한다 | 품질 이슈를 고려하여 다음 이터레이션 계획을 실행한다 |  | A | 애자일 팀이 작업을 늦게 완료하고 품질이 낮을 때, PM은 다음 이터레이션으로 이동하기 전에 올바른 품질 테스트가 적용되는지 확인해야 한다. 품질 관문이 문제 재발을 방지한다. 기술 부채 포함(B)은 문제를 미룬다. 품질 리뷰(C)는 테스트 확인 후에 한다. 계획 실행(D)은 근본적 테스트 확인 없이 진행한다.
1278 | An agile project is running its third iteration with a duration of 2 weeks. A new operations director, who only has a predictive background, started working at the company. In the first meeting with the project manager, the director demands a weekly project status report. What should the project manager do? | Introduce the agile aspect to the director and agree on a solution. | Share this with the team and ask them to develop reports for the director. | Invite the director to attend the daily standup meetings. | Explain to the director that agile projects have live reports. |  | A | When a new operations director with only predictive background demands weekly status reports on an agile project, the project manager should introduce the agile aspect and agree on a solution. Educating stakeholders on agile practices while finding common ground respects both perspectives. Sharing with the team to develop reports (B) creates unnecessary work. Inviting to daily standups (C) may not suit the director's schedule. Explaining agile has live reports (D) is dismissive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 애자일 프로젝트가 3번째 이터레이션을 진행 중이다. 예측형 배경만 가진 새 운영 이사가 주간 상태 보고서를 요구한다. PM은 무엇을 해야 하는가? | 이사에게 애자일 측면을 소개하고 해결책에 합의한다 | 팀과 공유하고 이사를 위한 보고서를 개발하도록 요청한다 | 이사를 데일리 스탠드업 회의에 참석하도록 초대한다 | 이사에게 애자일 프로젝트에는 실시간 보고서가 있다고 설명한다 |  | A | 예측형 배경만 가진 새 운영 이사가 주간 보고서를 요구할 때, PM은 이사에게 애자일 측면을 소개하고 해결책에 합의해야 한다. 교육과 합의가 이해관계자 기대를 관리한다. 보고서 개발(B)은 팀에 불필요한 부담이다. 스탠드업 초대(C)는 적절한 보고 채널이 아니다. 실시간 보고서 설명(D)은 이해를 돕지 않는다.
1279 | By the end of the first sprint, a project lead notices that one of the team members is not performing very well. Which form of communication should the project lead use to handle the situation? | Informal written communication, such as a friendly reminder | Formal written communication, such as an email with a copy sent to the manager | Informal verbal communication, such as a conversation | Formal verbal communication, such as a conversation at the end of the sprint retrospective |  | C | When a project lead notices a team member underperforming by the end of the first sprint, informal verbal communication such as a one-on-one conversation is the most appropriate approach. This allows immediate, constructive feedback in a private setting, helping identify obstacles and maintain positive team dynamics. Informal written communication (A) may seem impersonal. Formal written communication (B) is escalatory for a first conversation. Formal verbal communication at the retrospective (D) discusses it in a group setting, which may embarrass the team member. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 첫 스프린트 종료 시 프로젝트 리더가 팀원 중 한 명의 성과가 좋지 않음을 발견했다. 어떤 형태의 커뮤니케이션이 가장 적절한가? | 친근한 알림 같은 비공식 서면 커뮤니케이션 | 관리자 참조 이메일 같은 공식 서면 커뮤니케이션 | 대화 같은 비공식 구두 커뮤니케이션 | 스프린트 회고 종료 시 대화 같은 공식 구두 커뮤니케이션 |  | C | 첫 스프린트에서 팀원의 저조한 성과를 발견할 때, 비공식 구두 커뮤니케이션(일대일 대화)이 가장 적절하다. 사적이고 비공식적 접근이 방어적 반응 없이 문제를 논의할 수 있게 한다. 비공식 서면(A)은 개인적 접촉이 부족하다. 공식 서면(B)은 첫 스프린트에는 과도하다. 공식 구두(D)는 회고에서 공개적으로 다루어 당혹감을 줄 수 있다.
1280 | A project manager is leading a team delivering new software to a finance team. The new software will streamline the finance team's monthly closing activities and reporting. What should the project manager use to promote knowledge transfer for the new solution? | Support portal | User handbook | Project documents | End-user training |  | D | When delivering new software to a finance team for monthly closing activities, the project manager should use end-user training to promote knowledge transfer. Structured training ensures users can perform real tasks confidently, enabling adoption and benefits realization. A support portal (A) complements training but does not replace baseline competence building. A user handbook (B) is reference material, not experiential learning. Project documents (C) are technical artifacts, not designed for operational training. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Predictive | Baseline & Change Control | People | Engage Stakeholders | Schedule | Closing | Focus on Value | Close Project or Phase | Traditional PM | PM이 재무 팀에 새 소프트웨어를 납품하는 팀을 이끌고 있다. 월마감 활동을 간소화할 소프트웨어이다. 지식 전달을 촉진하기 위해 무엇을 사용해야 하는가? | 지원 포털 | 사용자 핸드북 | 프로젝트 문서 | 최종 사용자 교육 |  | D | 재무 팀에 새 소프트웨어를 납품할 때, PM은 지식 전달을 촉진하기 위해 최종 사용자 교육을 사용해야 한다. 구조화된 교육이 사용자가 월마감 활동에 소프트웨어를 효과적으로 사용할 수 있게 한다. 지원 포털(A)은 사후 지원이다. 핸드북(B)은 보완적이지만 교육을 대체하지 않는다. 프로젝트 문서(C)는 사용자용이 아니다.
1281 | A new development project is about to start, and the project manager knows that a high-profile customer makes very specific and frequent requests in all sprints. This project will demand contract coordination with third parties, and the project manager must find a better way to manage customer and partner expectations. What strategy should the project manager use? | Specify the scope and features to be deployed in the contract clearly. | Focus on the implementation of a software as a service (SaaS) solution for the customer. | Change the marketing and product management definitions to meet stakeholder needs. | Work very closely with the customer and third parties to meet their needs. |  | A | When managing a high-profile customer who makes frequent, specific requests across sprints while coordinating with third parties, the project manager should clearly specify the scope and features to be deployed in the contract. This sets clear boundaries and expectations for all parties, preventing scope creep and ensuring alignment between the customer, third parties, and the project team. Focusing on a SaaS implementation (B) is a technical solution that does not address expectation management. Changing marketing and product definitions (C) shifts the product rather than managing expectations. Working closely with customer and third parties (D) is good practice but lacks the structural clarity that a well-defined contract provides. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | 새 개발 프로젝트가 시작되려 한다. PM은 고프로필 고객이 스프린트 간에 매우 구체적인 요청을 자주 한다는 것을 알고 있다. PM은 무엇을 해야 하는가? | 계약에 배포할 범위와 기능을 명확히 명시한다 | 고객을 위한 SaaS 솔루션 구현에 집중한다 | 이해관계자 요구를 충족하도록 마케팅과 제품 관리 정의를 변경한다 | 고객 및 제3자와 매우 긴밀하게 협력하여 요구를 충족한다 |  | A | 고프로필 고객이 스프린트 간에 구체적 요청을 자주 할 때, PM은 계약에 배포할 범위와 기능을 명확히 명시해야 한다. 명확한 범위 정의가 기대를 관리하고 범위 변경을 통제한다. SaaS 집중(B)은 기술 결정이지 범위 관리가 아니다. 정의 변경(C)은 고객에 과도하게 맞춘다. 긴밀 협력(D)은 좋지만 범위 명확화 없이는 불충분하다.
1282 | A project manager is leading a project with a negative risk that has just become an issue. The risk has been recorded, and a response plan has been set. However, a project team member proposes a response that differs from the response recorded in the risk management plan, which the team member believes will be cheaper and equally effective. What should the project manager do? | Adhere to the issue response proposed in the risk management plan, as it is the agreed- upon solution. | Evaluate the new proposal with the project team to determine if it is a more beneficial alternative. | Ask the project team member to write a formal email explaining the proposal and send it to the change control board (CCB). | Implement the new proposal as soon as possible, as it is supposed to be cheaper and equally effective. |  | B | When an identified risk becomes an issue and a team member proposes an alternative response, the PM should first evaluate the proposal with the team before changing the planned response. PMI principles support thoughtful assessment of alternatives—comparing impacts, feasibility, and alignment with project constraints—before selecting the most appropriate action. Rigid adherence to the original plan (B) ignores potentially better solutions. Initiating formal change control (C) is premature before assessment. Implementing immediately (D) bypasses validation. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | PM이 부정적 리스크가 이슈가 된 프로젝트를 이끌고 있다. 리스크가 기록되고 리스크 관리 계획에 대응이 포함되어 있다. 팀원이 새 대안을 제안한다. PM은 무엇을 해야 하는가? | 리스크 관리 계획에 제안된 대응을 준수한다. 합의된 솔루션이기 때문이다 | 프로젝트 팀과 새 제안을 평가하여 더 유익한 대안인지 결정한다 | 팀원에게 제안을 설명하는 공식 이메일을 작성하여 CCB에 보내도록 요청한다 | 새 제안을 가능한 빨리 구현한다. 더 저렴하고 동등하게 효과적이기 때문이다 |  | B | 식별된 리스크가 이슈가 되고 팀원이 대안 대응을 제안할 때, PM은 먼저 프로젝트 팀과 제안을 평가해야 한다. 계획된 대응을 변경하기 전에 팀 평가가 필요하다. 계획 준수(A)는 더 나은 대안을 무시한다. 공식 이메일(C)은 불필요한 관료주의이다. 즉시 구현(D)은 팀 평가 없이 성급하다.
1283 | A Scrum team working in an aircraft manufacturing company has completed its first iteration for a critical project. It is very important for the project sponsor to complete the project on time and under budget. A burndown chart indicates that the project is behind schedule. Which two actions should the project manager take to manage impediments and improve the team's velocity? (Choose two) | Assign the items with high complexity lo senior developers | Look for processes that cause bottlenecks and slow down the team ' s agility | Empower the learn to make decisions to remove impediments | Work with the team to remove impediments as quickly as possible | Move the items with high complexity to the last iterations | B, D | When a burndown chart shows the Scrum team is behind schedule after the first iteration, the project manager should (B) look for processes that cause bottlenecks and slow the team's agility, and (D) work with the team to remove impediments as quickly as possible. Identifying and removing blockers improves velocity. Assigning complex items to seniors (A) reduces collaboration. Moving complex items to later iterations (C) defers risk. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | 항공기 제조 회사의 스크럼 팀이 첫 이터레이션을 완료했다. 번다운 차트가 팀이 일정보다 뒤처져 있음을 보여준다. PM은 무엇을 해야 하는가? (2개 선택) | 높은 복잡도 항목을 시니어 개발자에게 할당한다 | 병목을 일으키고 팀의 민첩성을 저해하는 프로세스를 찾는다 | 팀이 장애물을 제거하기 위한 결정을 내리도록 권한을 부여한다 | 팀과 함께 가능한 빨리 장애물을 제거한다 | 높은 복잡도 항목을 마지막 이터레이션으로 이동한다 | B, D | 번다운 차트가 팀이 일정보다 뒤처져 있음을 보여줄 때, PM은 두 가지 조치를 취해야 한다: 병목을 일으키고 팀의 민첩성을 저해하는 프로세스를 찾고(B), 팀과 함께 가능한 빨리 장애물을 제거한다(D). 프로세스 개선과 장애물 제거가 속도를 회복한다. 시니어에게 할당(A)은 팀 자율성을 제한한다. 권한 부여(C)만으로는 즉각적 지원이 부족하다. 마지막으로 이동(E)은 리스크를 미룬다.
1284 | A project is late due to a large number of scope changes. This was raised as a risk in the risk register during the initiation phase. The team is afraid that they will be blamed in case of failure and recommends that the project manager ask for an extension. What should the project manager do first? | Refer to the risk register and follow the mitigation plan. | Ask the team to document the impact of the risk in detail. | Refer to the change log and ensure that changes are documented. | Ask the sponsor for their advice on the way forward. |  | A | Proper risk management requires following established processes and documented plans. The risk register and risk management plan are the primary tools for identifying, tracking, and managing project risks. The PM should refer to these documents and follow the planned mitigation strategy. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 많은 범위 변경으로 프로젝트가 지연되고 있다. 이는 착수 시 리스크 등록부에 리스크로 등록되었다. PM은 무엇을 해야 하는가? | 리스크 등록부를 참조하고 완화 계획을 따른다 | 팀에게 리스크의 영향을 상세히 문서화하도록 요청한다 | 변경 로그를 참조하고 변경이 문서화되었는지 확인한다 | 스폰서에게 향후 진행 방향에 대한 조언을 요청한다 |  | A | 많은 범위 변경이 리스크로 식별되어 있을 때, PM은 리스크 등록부를 참조하고 완화 계획을 따라야 한다. 적절한 리스크 관리는 수립된 프로세스와 문서화된 계획을 따르는 것이다. 영향 문서화(B)는 이미 리스크가 식별된 상태에서 추가 문서화이다. 변경 로그(C)는 문서화이지 대응이 아니다. 스폰서 조언(D)은 계획 실행 전에 불필요하다.
1285 | A startup company has just appointed a CEO that has no prior project experience. The CEO wants to execute projects with their own resources and has appointed a project manager. What should the project manager recommend that the CEO do first? | Utilize a predictive approach for all upcoming projects. | Create a framework to justify project execution. | Utilize an agile approach for all upcoming projects. | Create a framework to support project success. |  | D | When a startup CEO with no project experience wants to execute projects with internal resources, the project manager should recommend creating a framework to support project success. Establishing foundational processes and practices ensures projects are managed effectively from the start. Utilizing a predictive approach for all projects (A) is rigid. Utilizing an agile approach for all projects (C) may not suit every project. Creating a framework to justify project execution (B) focuses on justification, not success. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 스타트업 회사가 프로젝트 경험이 없는 CEO를 새로 임명했다. CEO가 내부 자원으로 프로젝트를 실행하고 싶어한다. PM은 무엇을 권고해야 하는가? | 모든 향후 프로젝트에 예측형 접근법을 활용한다 | 프로젝트 실행을 정당화하는 프레임워크를 만든다 | 모든 향후 프로젝트에 애자일 접근법을 활용한다 | 프로젝트 성공을 지원하는 프레임워크를 만든다 |  | D | 프로젝트 경험이 없는 스타트업 CEO가 내부 자원으로 프로젝트를 실행하고 싶을 때, PM은 프로젝트 성공을 지원하는 프레임워크를 만들 것을 권고해야 한다. 기반 체계가 일관된 프로젝트 실행을 가능하게 한다. 예측형(A)은 모든 프로젝트에 적합하지 않다. 정당화 프레임워크(B)는 실행이 아닌 정당화에 초점이다. 애자일(C)은 모든 프로젝트에 적합하지 않다.
1286 | During a progress review meeting, the project sponsor requests a complete revamp of the product roadmap to meet the strategic objectives based on market conditions. This change will result in a completely new product. What should the project manager do first? | Discuss with the team and implement the revisions that were requested by the sponsor. | Perform a root cause analysis to assess which deliverables can be reused by the team. | Put the current project work on hold and revisit the scope based on the impacts. | Update the business case and seek sponsor approval on the modified project scope. |  | D | When the sponsor requests a complete product roadmap revamp that results in a completely new product, the project manager should first update the business case and seek sponsor approval on the modified project scope. Business case justification is required before major scope changes. Discussing and implementing immediately (A) skips governance. Performing root cause analysis (B) is analytical but not the first step. Putting work on hold to revisit scope (C) lacks formal approval. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Business Environment | Plan and Manage Compliance | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 진행 상황 검토 회의에서 프로젝트 스폰서가 전략 목표에 맞게 제품 로드맵을 완전히 개편하여 완전히 새로운 제품이 필요하다고 요청한다. PM은 무엇을 해야 하는가? | 팀과 논의하고 스폰서가 요청한 수정 사항을 구현한다 | 어떤 인도물을 팀이 재사용할 수 있는지 근본 원인 분석을 수행한다 | 현재 프로젝트 작업을 보류하고 영향에 따라 범위를 재검토한다 | 비즈니스 케이스를 업데이트하고 수정된 프로젝트 범위에 대해 스폰서 승인을 구한다 |  | D | 스폰서가 완전히 새로운 제품으로의 로드맵 개편을 요청할 때, PM은 먼저 비즈니스 케이스를 업데이트하고 수정된 범위에 대해 스폰서 승인을 구해야 한다. 근본적 변경은 비즈니스 정당성의 재검증이 필요하다. 즉시 구현(A)은 영향 평가 없이 진행한다. 근본 원인 분석(B)은 적합하지 않다. 작업 보류(C)는 승인 전에 과도하다.
1287 | A project manager is transitioning from a predictive life cycle project to a new agile project. How should the project manager manage and control the scope for the new project? | Develop a plan to complete more work In less time. | Spend a short amount of time defining the scope and building prototypes to refine the requirements. | Create a scope baseline and put the rest as backlog activities. | Estimate the work the team can complete and define story sizes to keep the project under control. |  | B | When transitioning from a predictive to an agile project, the project manager should spend a short amount of time defining the scope and building prototypes to refine the requirements. In agile, scope is progressively elaborated through iterative delivery with continuous stakeholder feedback—not detailed upfront. Prototyping helps clarify requirements quickly while maintaining flexibility. Developing a plan to complete more work in less time (A) is unrealistic and unsustainable. Creating a scope baseline with remaining items as backlog (C) applies predictive thinking to an agile project. Estimating work and defining story sizes alone (D) is part of scope management but incomplete without the iterative refinement approach. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Integrate Sustainability | Plan Scope Management | Sustainability | PM이 예측형 프로젝트에서 새 애자일 프로젝트로 전환 중이다. 범위 관리를 어떻게 해야 하는가? | 더 적은 시간에 더 많은 작업을 완료하는 계획을 개발한다 | 짧은 시간 동안 범위를 정의하고 프로토타입을 구축하여 요구사항을 정제한다 | 범위 베이스라인을 만들고 나머지를 백로그 활동으로 둔다 | 팀이 완료할 수 있는 작업을 추정하고 스토리 크기를 정의하여 프로젝트를 통제한다 |  | B | 예측형에서 애자일로 전환할 때, PM은 짧은 시간 동안 범위를 정의하고 프로토타입을 구축하여 요구사항을 정제해야 한다. 애자일에서는 범위가 점진적으로 정교화된다. 더 많은 작업(A)은 애자일 원칙이 아니다. 범위 베이스라인(C)은 예측형 접근이다. 스토리 크기 정의(D)는 부분적이지만 프로토타입 기반 정제가 우선이다.
1288 | A project team member tells the project lead that expecting a similar delivery output for every day of the sprint is not realistic. The project lead reports this to the project management office (PMO). What should the project lead do? | Discuss the issue with the product owner. | Discuss this with the project team in the next sprint retrospective meeting. | Discuss this with the project team in the next sprint planning meeting. | Discuss this with the PMO manager. |  | B | When a team member tells the project lead that expecting uniform daily delivery output is unrealistic, the project lead should discuss this with the project team in the next sprint retrospective meeting. Retrospectives are designed for process improvement discussions. Discussing with the product owner (A) addresses product, not process. Discussing in sprint planning (C) focuses on upcoming work. Discussing with the PMO manager (D) escalates without team input. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 팀원이 프로젝트 리더에게 스프린트 매일 동일한 납품 산출물을 기대하는 것이 비현실적이라고 말한다. PM은 무엇을 해야 하는가? | 제품 책임자와 이슈를 논의한다 | 다음 스프린트 회고 회의에서 팀과 이것을 논의한다 | 다음 스프린트 계획 회의에서 팀과 이것을 논의한다 | PMO 관리자와 이것을 논의한다 |  | B | 팀원이 매일 균일한 납품 산출물이 비현실적이라고 할 때, 다음 스프린트 회고에서 팀과 논의해야 한다. 회고가 프로세스 개선을 논의하는 적절한 장이다. 제품 책임자(A)는 프로세스 문제가 아니다. 스프린트 계획(C)은 작업 선택이지 프로세스 논의가 아니다. PMO(D)는 과도한 에스컬레이션이다.
1289 | The project team has reviewed the requirements and identified some concerns. The project sponsor has asked the team how they will handle each concern. What should the project manager do next? | Work with the project team to assess the severity of each risk. | Collaborate with the stakeholders on the communications management plan. | Develop a mitigation strategy for each risk and update the risk register. | Consult with team members to produce a Monte Carlo simulation diagram. |  | A | When the team identifies concerns from requirements and the sponsor asks how they will be handled, the project manager should work with the team to assess the severity of each risk. Qualitative assessment prioritizes risks before developing responses. Collaborating on the communications plan (B) does not address risk management. Developing mitigation strategies for each (C) is premature before prioritization. Running a Monte Carlo simulation (D) is quantitative analysis appropriate after qualitative assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 팀이 요구사항을 검토하고 우려를 식별했다. 스폰서가 이를 어떻게 처리할지 물었다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 팀과 각 리스크의 심각도를 평가한다 | 이해관계자와 커뮤니케이션 관리 계획에 대해 협력한다 | 각 리스크에 대한 완화 전략을 개발하고 리스크 등록부를 업데이트한다 | 팀원과 상의하여 몬테카를로 시뮬레이션 다이어그램을 생성한다 |  | A | 팀이 요구사항에서 우려를 식별하고 스폰서가 처리 방법을 물을 때, PM은 먼저 팀과 각 리스크의 심각도를 평가해야 한다. 정성적 평가가 우선순위 결정의 기초이다. 커뮤니케이션 계획(B)은 리스크 대응이 아니다. 완화 전략(C)은 심각도 평가 후에 한다. 몬테카를로(D)는 이 단계에서 과도하다.
1290 | A self-organizing team was delivering as committed. The team accepted a development task with new technology and the iterations started to have reduced velocity. What management decision is suited for this situation? | Re-assign the project to a team that has worked with this technology | Add new members to the team and increase the velocity | Move team members who are not performing from the team. | Provide opportunity for team members to learn and adjust to the technology. |  | D | When a self-organizing team's velocity drops after accepting a task with new technology, the appropriate decision is to provide opportunity for team members to learn and adjust to the technology. Learning time restores capability. Reassigning the project to another team (A) loses institutional knowledge. Adding new members (B) may introduce coordination overhead. Removing underperformers (C) is punitive and premature. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 자체 조직화 팀이 약속대로 납품 중이었다. 새 기술의 개발 작업을 수락한 후 속도가 떨어졌다. PM은 무엇을 해야 하는가? | 이 기술로 작업한 경험이 있는 팀에 프로젝트를 재할당한다 | 팀에 새 멤버를 추가하고 속도를 높인다 | 성과가 낮은 팀원을 팀에서 제거한다 | 팀원에게 기술을 배우고 적응할 기회를 제공한다 |  | D | 자체 조직화 팀이 새 기술 작업 후 속도가 떨어질 때, PM은 팀원에게 기술을 배우고 적응할 기회를 제공해야 한다. 학습과 적응이 장기적 팀 역량을 구축한다. 재할당(A)은 팀 자율성을 무시한다. 멤버 추가(B)는 통합 시간이 필요하다. 제거(C)는 징벌적이다.
1291 | A project manager was recently assigned to a project that is in the execution phase and is experiencing roadblocks. During a review of the processes and procedures, the project manager notices similarities to a previous project that experienced similar roadblocks. The project manager reviews the task schedule and finds that certain tasks are well behind expectations. In speaking with the project team, the project manager confirms that the team is following the processes exactly. What should the project manager do? | Update the variation register to account for the extended project time. | Update the schedule to account for the unexpected delays in the project tasks. | Review and amend the processes to ensure only value-adding activities are present. | Review the resources allocated to the project and change accordingly. |  | C | When a project experiences roadblocks similar to a past project and the team is following processes exactly, the project manager should review and amend processes to ensure only value-adding activities are present. Process improvement addresses systemic issues. Updating the variation register (A) documents but does not solve. Updating the schedule (B) reflects delays without addressing root causes. Changing resources (D) assumes a people problem. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | PM이 실행 단계의 프로젝트에 새로 배정되었고 장애물을 겪고 있다. 과거 프로젝트와 유사한 장애물이며 팀이 프로세스를 정확히 따르고 있다. PM은 무엇을 해야 하는가? | 연장된 프로젝트 시간을 반영하여 변동 등록부를 업데이트한다 | 프로젝트 작업의 예상치 못한 지연을 반영하여 일정을 업데이트한다 | 프로세스를 검토하고 수정하여 가치를 추가하는 활동만 있도록 한다 | 프로젝트에 할당된 자원을 검토하고 그에 따라 변경한다 |  | C | 프로세스를 정확히 따르는데도 장애물이 반복될 때, PM은 프로세스를 검토하고 수정하여 가치를 추가하는 활동만 있도록 해야 한다. 프로세스 자체에 문제가 있을 수 있다. 변동 등록부(A)는 기록이지 해결이 아니다. 일정 업데이트(B)는 근본 원인을 해결하지 않는다. 자원 변경(D)은 프로세스 문제를 다루지 않는다.
1292 | During the daily standup meeting that is assessing progress against the current sprint, a team member reports some delays due to a component managed by an external vendor. How should the project manager address the team member's concern? | Update the communications management plan to prevent future reoccurrence. | Ask the team member to provide details to address the issue with the vendor. | Ask the team member to resolve the issue independently to minimize further delays. | Implement fast tracking to reduce the impact of the delay on the sprint. |  | B | When a team member reports sprint delays due to a component managed by an external vendor, the project manager should ask the team member to provide details to address the issue with the vendor. Gathering specifics enables the PM to engage the vendor directly with full information. Updating the communications management plan (A) addresses process but not the immediate issue. Asking the team member to resolve independently (C) exceeds their role. Fast tracking (D) is a schedule compression technique unrelated to a vendor dependency issue. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Stakeholders | Planning | Adopt a Holistic View | Plan Stakeholder Engagement | Traditional PM | 데일리 스탠드업에서 팀원이 외부 벤더가 관리하는 구성 요소로 인한 스프린트 지연을 보고한다. PM은 무엇을 해야 하는가? | 향후 재발 방지를 위해 커뮤니케이션 관리 계획을 업데이트한다 | 팀원에게 벤더와의 이슈를 해결하기 위한 세부 정보를 제공하도록 요청한다 | 팀원에게 추가 지연을 최소화하기 위해 독립적으로 이슈를 해결하도록 요청한다 | 스프린트에 대한 지연 영향을 줄이기 위해 패스트 트래킹을 구현한다 |  | B | 팀원이 외부 벤더 관련 스프린트 지연을 보고할 때, PM은 팀원에게 벤더와의 이슈를 해결하기 위한 세부 정보를 제공하도록 요청해야 한다. 정보 수집이 효과적 대응의 기초이다. 커뮤니케이션 계획(A)은 향후 방지이지 현재 해결이 아니다. 독립 해결(C)은 지원 없이 팀원에게 부담이다. 패스트 트래킹(D)은 원인 해결 전에 성급하다.
1293 | An organization is altering their schedule, and the project team is now expected to be in the office together once a week. Despite everyone being dedicated to the project, the team members all follow their functional teams' schedules, which differ from one another. How should the project manager address this situation? | Work with the team to determine if the in-person project day is required. | Look into the option of changing the status of all team members to being fully remote. | Look into changing the company ' s policy from 1 day to 2 days on-site. | Work with the functional managers and get an exception for the team members. |  | D | When team members follow different functional schedules and cannot align for required in-person collaboration, the project manager should work with the functional managers to get an exception for team members. Cross-functional coordination in matrix organizations requires negotiation with functional managers to align schedules. Working with the team to question the requirement (A) bypasses organizational policy. Going fully remote (B) avoids the issue. Changing company policy (C) exceeds PM authority. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 조직이 일정을 변경하여 팀이 주 1회 함께 사무실에 있어야 한다. 팀원들이 다른 기능 일정을 따르고 있어 동일한 날에 모일 수 없다. PM은 무엇을 해야 하는가? | 팀과 협력하여 대면 프로젝트 일이 필요한지 결정한다 | 모든 팀원의 상태를 완전 원격으로 변경하는 옵션을 검토한다 | 회사 정책을 1일에서 2일 현장으로 변경하는 것을 검토한다 | 기능 관리자와 협력하여 팀원들에 대한 예외를 얻는다 |  | D | 팀원들이 다른 기능 일정을 따라 동일한 날에 모일 수 없을 때, PM은 기능 관리자와 협력하여 팀원들에 대한 예외를 얻어야 한다. 매트릭스 조직에서 기능 관리자와의 협력이 자원 충돌을 해결한다. 필요성 결정(A)은 조직 정책을 무시한다. 완전 원격(B)은 정책에 반한다. 정책 변경(C)은 PM 권한 밖이다.
1294 | A senior vice president requested the creation of more agile teams to run projects of varying lengths and complexities in parallel with each other. This will impact the amount of time the project managers will be able to dedicate to each project. The project managers typically dedicate 50% of their time to projects regardless of their complexity. What should the project manager do as a servant leader to help achieve this transformation? | Issue a change request to hire additional project managers based on the increased 919 workload. | Empower the team to develop the necessary skills to move the project forward independently. | Create a risk entry regarding the project manager ' s capacity and develop a mitigation plan. | Review the organizational process assets (OPAs) to evaluate mitigation plans for similar risks. |  | B | When a senior VP requests more agile teams requiring project managers to split time across multiple projects, the project manager as servant leader should empower the team to develop necessary skills to move forward independently. Self-organizing teams reduce dependency on PM oversight. Issuing a change request for more PMs (A) avoids transformation. Creating a risk entry about PM capacity (C) documents rather than acts. Reviewing OPAs (D) is informational but does not develop the team. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 고위 부사장이 다양한 길이와 복잡성의 프로젝트를 운영할 더 많은 애자일 팀 생성을 요청했다. PM이 여러 프로젝트에 시간을 나눠야 한다. PM은 무엇을 해야 하는가? | 증가된 작업량에 따라 추가 PM 고용을 위한 변경 요청을 발행한다 | 팀이 독립적으로 프로젝트를 진행할 수 있도록 필요한 기술을 개발하도록 권한을 부여한다 | PM의 역량에 대한 리스크 항목을 생성하고 완화 계획을 개발한다 | 유사 리스크에 대한 완화 계획을 평가하기 위해 OPA를 검토한다 |  | B | PM이 여러 프로젝트에 시간을 나눠야 할 때, 서번트 리더로서 팀이 독립적으로 프로젝트를 진행할 수 있도록 필요한 기술을 개발하도록 권한을 부여해야 한다. 팀 역량 강화가 PM 의존도를 줄인다. 추가 PM 고용(A)은 애자일 자기 조직화에 반한다. 리스크 항목(C)은 기록이지 해결이 아니다. OPA 검토(D)는 간접적이다.
1295 | A project manager is working on multiple building construction projects using a predictive project management approach. Senior leadership within the organization is promoting the inclusion of more agile practices into the current project methodologies. The project sponsor now wants the projects to use more agile methodologies. Before mandating any agile methods to be used in a project, what should the project manager do first? | Pause the current projects to align them to the new agile cadence. | Shift all existing projects to agile methodologies with a strict timeline. | Assess the organizational culture and readiness for the transformation. | Provide agile training to those who will be part of the project team. |  | C | Before mandating agile methods on construction projects, the project manager should first assess organizational culture and readiness for transformation. Readiness assessment ensures successful adoption. Pausing current projects (A) is disruptive. Shifting all projects immediately (B) ignores context. Providing agile training (D) is important but premature without assessing readiness. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Hybrid/Tailoring | PM이 예측형 접근법으로 여러 건설 프로젝트를 진행 중이다. 관리진이 애자일 전환을 지시한다. PM은 무엇을 먼저 해야 하는가? | 현재 프로젝트를 일시 중지하여 새 애자일 주기에 맞춘다 | 엄격한 일정으로 모든 기존 프로젝트를 애자일 방법론으로 전환한다 | 전환을 위한 조직 문화와 준비 상태를 평가한다 | 프로젝트 팀이 될 사람들에게 애자일 교육을 제공한다 |  | C | 건설 프로젝트에 애자일을 도입하기 전에, PM은 먼저 조직 문화와 준비 상태를 평가해야 한다. 준비 상태 평가가 성공적 전환을 보장한다. 프로젝트 일시 중지(A)는 작업을 중단한다. 엄격한 전환(B)은 준비 없이 무리하다. 교육(D)은 평가 후에 한다.
1296 | A project manager is working on a time and materials (T&M) project using a hybrid approach. The milestones and outcomes are defined for the first 6 months with incremental releases every month. After the first 2 months, the client communicates their dissatisfaction with the results and asks to change the course of the project. The project manager held a face-to-face meeting with the client and now has a better understanding of the newly desired milestones and outcomes. What should the project manager do first? | Forward the client ' s request to management as a change request to get formal approval. | Draft a contract change with the desired scope changes and send it to the client for approval. | Document the information in the meeting minutes and share it with the project stakeholders. | Finish the current monthly release as it was planned and replan for the future months. |  | B | When a T&M hybrid project client expresses dissatisfaction after 2 months and wants to change course, and the PM now understands new desired milestones after a face-to-face meeting, the PM should first draft a contract change with the desired scope changes and send it to the client for approval. Formalizing changes ensures alignment. Forwarding to management as a change request (A) bypasses the client. Documenting in meeting minutes (C) is incomplete. Finishing the current release as planned (D) ignores the client's concerns. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Scope | Planning | Focus on Value | Collect Requirements | Hybrid/Tailoring | PM이 하이브리드 접근법으로 T&M 프로젝트를 진행 중이다. 2개월 후 고객이 불만을 표하고 방향 변경을 원한다. 대면 회의 후 새 마일스톤을 이해했다. PM은 무엇을 해야 하는가? | 고객의 요청을 경영진에게 변경 요청으로 전달하여 공식 승인을 받는다 | 원하는 범위 변경으로 계약 변경을 초안 작성하여 고객에게 승인을 위해 보낸다 | 회의록에 정보를 문서화하고 프로젝트 이해관계자와 공유한다 | 현재 월간 릴리스를 계획대로 완료하고 향후 월을 재계획한다 |  | B | T&M 하이브리드 프로젝트에서 고객이 방향 변경을 원할 때, PM은 원하는 범위 변경으로 계약 변경을 초안 작성하여 고객에게 승인을 위해 보내야 한다. T&M 계약에서 범위 변경은 계약 수정이 필요하다. 경영진 변경 요청(A)은 고객 직접 계약에는 부적합하다. 회의록 문서화(C)는 불충분하다. 계획대로 완료(D)는 고객 요구를 무시한다.
1297 | A large global organization developed a new medical implant that requires compliance with local government regulations. The approval process for one country is lengthy and will impact the intended launch date. What should the project manager do? | Ask the sponsor to authorize the launch and then wait for approval. | Work with the team to find ways to bypass the regulations. | Ask the board to use their influence and speed up the approval. | Organize an online distribution channel from another country. |  | A | When a lengthy regulatory approval process will impact the launch date for a medical implant, the project manager should ask the sponsor to authorize the launch and wait for approval. Regulatory compliance is mandatory for medical devices. Finding ways to bypass regulations (B) is unethical and illegal. Using board influence to speed up approval (C) may be inappropriate. Organizing distribution from another country (D) may violate local regulations. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Scope & Requirements Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 대규모 글로벌 조직이 새 의료 임플란트를 개발했다. 규제 승인에 시간이 오래 걸려 출시일에 영향을 준다. PM은 무엇을 해야 하는가? | 스폰서에게 출시를 승인하도록 요청하고 승인을 기다린다 | 팀과 규제를 우회할 방법을 찾는다 | 이사회에 영향력을 사용하여 승인을 촉진하도록 요청한다 | 다른 국가에서 온라인 유통 채널을 조직한다 |  | A | 의료 임플란트의 규제 승인이 오래 걸릴 때, PM은 스폰서에게 출시를 승인하도록 요청하고 승인을 기다려야 한다. 의료 기기에서 규제 준수는 비협상적이다. 규제 우회(B)는 불법이다. 영향력 행사(C)는 비윤리적이다. 다른 국가 유통(D)은 규제를 회피한다.
1298 | An organization uses a hybrid approach to project management. A project manager has been assigned to an external project, project A, where two of the three modules in the project require machine learning skills. The only machine learning expert in the project manager's organization is engaged in an internal project, project B, that is about to end. What should the project manager do? | Prioritize project A over project B since A is an external project and B is an internal project . | Engage the human resource manager to employ a machine learning expert for project A. | Plan project A to start at the end of project B when the machine learning expert is available. | Plan projectA in sprints, starting with the module that does not require machine learning skills. |  | D | In a hybrid organization where the only machine learning expert is finishing an internal project, the project manager should plan Project A in sprints, starting with the module that does not require machine learning skills. This leverages existing resources and makes progress on Project A while the expert completes Project B, avoiding delays, compromises, or unnecessary hiring. Prioritizing Project A over B (A) may disrupt the internal project. Hiring a new expert (B) is costly and may not fit organizational needs. Delaying until the expert is available (C) loses valuable time when other work can proceed. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Scope | Planning | Build an Empowered Culture | Collect Requirements | AI | 하이브리드 조직에서 PM이 외부 프로젝트 A(ML 전문가 필요)와 내부 프로젝트 B를 담당한다. 유일한 ML 전문가가 프로젝트 B를 마무리 중이다. PM은 무엇을 해야 하는가? | 외부 프로젝트이므로 프로젝트 A를 프로젝트 B보다 우선시한다 | HR 관리자에게 프로젝트 A를 위한 ML 전문가를 고용하도록 한다 | ML 전문가가 가용할 때 프로젝트 B 종료 후 프로젝트 A를 시작하도록 계획한다 | 프로젝트 A를 스프린트로 계획하고 ML 기술이 필요 없는 모듈부터 시작한다 |  | D | 유일한 ML 전문가가 다른 프로젝트를 마무리 중일 때, PM은 프로젝트 A를 스프린트로 계획하고 ML 기술이 필요 없는 모듈부터 시작해야 한다. 가용 자원으로 진행 가능한 작업부터 시작하는 것이 효율적이다. 우선순위(A)는 자원 가용성을 해결하지 않는다. HR 고용(B)은 시간이 걸린다. 대기(C)는 프로젝트를 불필요하게 지연시킨다.
1299 | The project sponsor reports that a key stakeholder is complaining about performance differences in the metrics reported by the project manager, which gives the impression that the project is out of control. The project manager has been providing the project's status according to the agreed-upon communications management plan. This key stakeholder, however, seldom attends the status report meetings. What should the project manager do first to address this situation? | Use the contingency reserves to implement fast tracking and improve the schedule key performance indicators (KPIs). | Evaluate the communication needs to discover the gaps and adjust the original plan if needed. | Provide evidence to the project sponsor that the project is on track and the communications have been sent. | Review the resource breakdown structure (RBS) to request the main stakeholder ' s manager to replace the stakeholder. |  | B | When a key stakeholder complains about performance metric differences despite following the communications plan, the project manager should first evaluate communication needs to discover gaps and adjust the plan if needed. Understanding the stakeholder's information requirements enables targeted improvement. Using contingency reserves for fast-tracking (A) addresses schedule, not communication. Providing evidence to the sponsor (C) is defensive. Reviewing the RBS to replace the stakeholder (D) is inappropriate. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 프로젝트 스폰서가 주요 이해관계자가 보고된 성과 지표의 차이에 대해 불만이라고 보고한다. 커뮤니케이션 계획을 따르고 있다. PM은 무엇을 해야 하는가? | 비상 예비비를 사용하여 패스트 트래킹을 구현하고 일정 KPI를 개선한다 | 커뮤니케이션 요구를 평가하여 격차를 발견하고 필요 시 원래 계획을 조정한다 | 프로젝트가 순조롭고 커뮤니케이션이 올바르게 이루어졌다는 증거를 스폰서에게 제공한다 | 주요 이해관계자의 관리자에게 교체를 요청하기 위해 자원 분류 체계를 검토한다 |  | B | 커뮤니케이션 계획을 따르는데도 이해관계자가 성과 지표 차이에 불만일 때, PM은 커뮤니케이션 요구를 평가하여 격차를 발견하고 계획을 조정해야 한다. 커뮤니케이션 격차 분석이 근본 원인을 해결한다. 패스트 트래킹(A)은 커뮤니케이션 문제가 아니다. 증거 제공(C)은 방어적이다. 교체 요청(D)은 극단적이다.
1300 | While reviewing a project with high-level executives, the project manager realizes that the conversation always deviates to other topics instead of the project itself. What two actions should the project manager take? (Choose 2) | Redirect the conversation to the project updates. | Restrict offline reviews to critical points related to the project. | Review with the team all of the topics that came up during the meeting. | Extend the meeting time to review additional topics. | Schedule effective communications training for the stakeholders. | A, D | When executive-level project review conversations deviate to other topics, the project manager should take two actions: redirect the conversation to project updates and schedule effective communications training for stakeholders. Focused facilitation ensures meeting objectives are met, and training improves future meetings. Restricting offline reviews (B) limits discussion without addressing meeting focus. Reviewing off-topic items post-meeting (C) does not prevent deviation. Extending meeting time (D) wastes executive time. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 고위 경영진과의 프로젝트 검토 중 대화가 항상 다른 주제로 이탈한다. PM은 무엇을 해야 하는가? (2개 선택) | 대화를 프로젝트 업데이트로 리디렉션한다 | 오프라인 검토를 프로젝트 관련 핵심 포인트로 제한한다 | 회의 중 나온 모든 주제를 팀과 검토한다 | 추가 주제를 검토하기 위해 회의 시간을 연장한다 | 이해관계자를 위한 효과적 커뮤니케이션 교육을 예약한다 | A, D | 경영진 회의에서 대화가 다른 주제로 이탈할 때, PM은 두 가지 조치를 취해야 한다: 대화를 프로젝트 업데이트로 리디렉션하고(A), 이해관계자를 위한 효과적 커뮤니케이션 교육을 예약한다(D). 즉각적 리디렉션과 장기적 교육이 효과적이다. 오프라인 제한(B)은 경영진에게 부적절하다. 팀 검토(C)는 불필요하다. 시간 연장(D)은 문제를 악화시킨다.
1301 | During a project meeting, the project manager asks risk owners to present issues that may affect the backlog. During their presentation, the project manager realizes that some risk owners did not implement the already agreed-upon risk responses. What should the project manager do to reduce exposure? | Report the risk owners to the project management office (PMO) with the recommendation to remove them from the team. | Reassign the outstanding risk tasks to other team members who have implemented their risk responses. | Ask the risk owners to implement the risk responses before the next meeting and present the results in the meeting. | Meet privately with the risk owners and work with them to address any impediments to the risk responses. |  | D | When risk owners have not implemented agreed-upon risk responses, the project manager should meet privately with them and work together to address any impediments. Collaborative, private engagement identifies barriers and restores accountability without public confrontation. Reporting to the PMO for removal (A) is extreme. Reassigning tasks to other members (B) does not address the impediments. Asking them to implement before the next meeting (C) restates the expectation without removing obstacles. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Traditional PM | 프로젝트 회의에서 PM이 리스크 소유자에게 백로그에 영향을 줄 이슈를 발표하도록 요청한다. 일부 리스크 소유자가 합의된 리스크 대응을 구현하지 않았다. PM은 무엇을 해야 하는가? | 리스크 소유자를 PMO에 보고하고 제거를 권고한다 | 리스크 대응을 구현한 다른 팀원에게 미완료 리스크 작업을 재할당한다 | 리스크 소유자에게 다음 회의 전에 리스크 대응을 구현하고 결과를 발표하도록 요청한다 | 리스크 소유자와 개인적으로 만나 리스크 대응의 장애물을 해결하기 위해 함께 작업한다 |  | D | 리스크 소유자가 합의된 리스크 대응을 구현하지 않았을 때, PM은 개인적으로 만나 장애물을 해결하기 위해 함께 작업해야 한다. 협력적이고 사적인 참여가 장애물을 식별하고 해결한다. PMO 보고(A)는 징벌적이다. 재할당(B)은 책임 회피이다. 다음 회의까지 요청(C)은 장애물을 해결하지 않는다.
1302 | On a project to create the perfect paper airplane, the development of the airplane is performed in iterations. The artwork to go on the wings and tail is done using a predictive approach. One of the stakeholders provides a requirement that conflicts with the product owner's requirements. Who is responsible for analyzing the new requirement and making the final decision? | Product owner | Project sponsor | Scrum master | Project manager |  | A | When a stakeholder's requirement conflicts with the product owner's requirements on a project using iterations for development and predictive for artwork, the product owner is responsible for analyzing the requirement and making the final decision. The product owner owns backlog prioritization and requirement decisions. The project sponsor (B) provides funding but does not manage requirements. The scrum master (C) facilitates process, not product decisions. The project manager (D) facilitates but does not own product decisions. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 완벽한 종이비행기 만들기 프로젝트에서 비행기 개발은 이터레이션으로, 아트워크는 예측형으로 수행된다. 이해관계자의 요구사항이 제품 책임자의 요구사항과 충돌한다. 누가 분석해야 하는가? | 제품 책임자 | 프로젝트 스폰서 | 스크럼 마스터 | 프로젝트 관리자 |  | A | 이해관계자의 요구사항이 제품 책임자의 요구사항과 충돌할 때, 제품 책임자가 분석 책임이 있다. 제품 책임자가 제품 비전과 백로그 우선순위의 최종 권한을 가진다. 스폰서(B)는 거버넌스이지 요구사항 분석이 아니다. 스크럼 마스터(C)는 프로세스 퍼실리테이터이다. PM(D)은 전체 조율이지 요구사항 결정이 아니다.
1303 | Knowledge sharing has been a key priority for a complex technological project with a large number of team members. During the project execution phase, the project manager receives numerous complaints from all team members that they are overloaded with knowledge-sharing emails, which contain useful information but are unmanageable due to the high volume. What should the project manager do to solve this problem? | Establish a push communications method for the team to share knowledge and lessons learned. | Establish an interactive communications method between stakeholders to share knowledge and lessons learned. | Establish an unofficial communications method for the team to share knowledge and lessons learned. | Establish a pull communications method to access knowledge repositories and lessons learned. |  | D | When team members are overloaded with knowledge-sharing emails that are useful but unmanageable in volume, the project manager should establish a pull communications method for accessing knowledge repositories and lessons learned. Pull methods let members access information on demand. Push methods (A) worsen the overload. Interactive methods (B) require coordination. Unofficial methods (C) lack structure. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 복잡한 기술 프로젝트에서 지식 공유가 핵심 우선순위이다. 팀원들이 유용하지만 양이 많은 지식 공유 이메일에 압도되고 있다. PM은 무엇을 해야 하는가? | 팀이 지식과 교훈을 공유할 푸시 커뮤니케이션 방법을 수립한다 | 이해관계자 간 지식과 교훈을 공유할 상호작용적 커뮤니케이션 방법을 수립한다 | 팀이 지식과 교훈을 공유할 비공식 커뮤니케이션 방법을 수립한다 | 지식 저장소와 교훈에 접근할 풀 커뮤니케이션 방법을 수립한다 |  | D | 지식 공유 이메일의 양에 팀이 압도될 때, PM은 지식 저장소와 교훈에 접근할 풀 커뮤니케이션 방법을 수립해야 한다. 풀 방식은 필요 시 정보에 접근하여 과부하를 줄인다. 푸시(A)는 현재 문제를 악화시킨다. 상호작용(B)은 더 많은 시간이 필요하다. 비공식(C)은 구조가 부족하다.
1304 | An experienced team member has recently started performing at a slower pace and is no longer engaged in various team conversations. What should the project manager do? | Inform the team member that a change in performance and engagement is noticed and work together to develop a solution for improvement. | Meet with human resources (HR) to determine the problem and develop a recommendation based on the results. | Incentivize the team with prizes for increased performance and engagement in order to persuade the team member to resume previous performance. | Ask the direct manager to reach out and try to identify the problem, then provide that information back to the project manager. |  | A | When an experienced team member shows declining performance and disengagement, the project manager should inform the team member that a change is noticed and work together to develop a solution. Direct, empathetic dialogue addresses the issue respectfully and collaboratively. Meeting with HR (B) involves external parties before direct conversation. Incentivizing the team with prizes (C) does not address the individual's issue. Asking the direct manager to investigate (D) delegates the PM's responsibility. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 경험 많은 팀원이 최근 성과가 느려지고 팀 대화에 더 이상 참여하지 않는다. PM은 무엇을 해야 하는가? | 팀원에게 성과와 참여의 변화가 감지되었음을 알리고 함께 해결책을 개발한다 | 인사부(HR)와 만나 문제를 파악하고 결과에 따른 권고안을 개발한다 | 증가된 성과와 참여에 대한 상으로 팀에 인센티브를 제공한다 | 직속 관리자에게 연락하여 문제를 파악하고 정보를 제공하도록 요청한다 |  | A | 경험 많은 팀원의 성과 저하와 참여 감소가 감지될 때, PM은 팀원에게 직접 변화를 알리고 함께 해결책을 개발해야 한다. 직접적이고 지지적인 대화가 문제의 근본을 파악한다. HR 참여(B)는 직접 대화 전에 성급하다. 팀 인센티브(C)는 개인 문제를 다루지 않는다. 관리자 요청(D)은 간접적이다.
1305 | A company has decided to investigate the feasibility of a new product. The project manager is in charge of validating the customer requirements. What should the project manager do to gain customer feedback? | Have the marketing department create a survey | Have the team create a minimum viable product (MVP). | Have the team create a prototype with all features | Have the product owner create product documentation |  | B | When investigating product feasibility and validating customer requirements, the project manager should have the team create a minimum viable product (MVP). An MVP delivers enough features to satisfy early customers and generate meaningful feedback for future development. Having marketing create a survey (A) provides opinions but not product validation. Creating a prototype with all features (C) is excessive for feasibility validation. Having the product owner create documentation (D) captures requirements but does not test them with customers. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 회사가 새 제품의 실행 가능성을 조사하기로 결정했다. PM이 고객 요구사항 검증을 담당한다. PM은 무엇을 해야 하는가? | 마케팅 부서에 설문을 만들도록 한다 | 팀에게 최소 실행 가능 제품(MVP)을 만들도록 한다 | 팀에게 모든 기능이 포함된 프로토타입을 만들도록 한다 | 제품 책임자에게 제품 문서를 만들도록 한다 |  | B | 제품 실행 가능성 조사와 고객 요구사항 검증을 위해, PM은 팀에게 MVP를 만들도록 해야 한다. MVP가 충분한 기능을 전달하여 고객 관심과 검증을 얻는다. 설문(A)은 이론적 피드백이다. 전체 프로토타입(C)은 과도한 투자이다. 제품 문서(D)는 고객이 경험할 수 없다.
1306 | A project manager is leading a diverse global team. The team members disagree about the requirements for a recently approved change request. The conflict among the team members has resulted in low morale and decreased performance. What should the project manager do? | Speak with the team members about their disagreement and seek clarity regarding the requirements. | Ask for advice from the human resources (HR) department about how to handle the situation. | Escalate to the change control board (CCB) and have them seek clarity on the requirements of the change. | Allow the most senior team member to make a decision and communicate the decision to the team members. |  | A | When team members disagree about requirements for an approved change request causing low morale and decreased performance, the project manager should speak with the team members about their disagreement and seek clarity regarding the requirements. Direct engagement facilitates understanding, clarifies ambiguity, and restores team cohesion. Allowing the senior member to decide (D) undermines collaboration. Asking HR for advice (B) is inappropriate for a technical disagreement. Escalating to the CCB (C) is premature before team-level resolution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 다양한 글로벌 팀을 이끌고 있다. 팀원들이 승인된 변경 요청의 요구사항에 대해 의견이 다르다. 사기가 저하되고 성과가 감소했다. PM은 무엇을 해야 하는가? | 팀원들과 의견 차이에 대해 대화하고 요구사항에 대한 명확성을 구한다 | 상황 처리 방법에 대해 인사부(HR)에 조언을 구한다 | 변경통제위원회(CCB)에 에스컬레이션하여 변경 요청의 요구사항에 대한 명확성을 구한다 | 가장 선임 팀원이 결정하고 팀에 전달하도록 한다 |  | A | 팀원들이 승인된 변경 요청의 요구사항에 대해 의견이 다를 때, PM은 팀원들과 직접 대화하여 명확성을 구해야 한다. 직접적 소통이 오해를 해소하고 협력을 복원한다. HR 조언(B)은 대인관계 문제가 아닌 요구사항 불일치이다. CCB 에스컬레이션(C)은 과도하다. 선임 결정(D)은 팀 참여를 배제한다.
1307 | All project team members refer to the project manager for various decisions. This causes delays for some tasks, as the project manager is usually preoccupied in meetings throughout the day. What should the project manager do to prevent these delays? | Meet with the team in 2 weeks to respond to all of the open tasks. | Delegate the decision-making authority of some tasks to the team. | Consolidate the decision-making authority to remain with the project manager. | Review the Pareto diagram to identify the source of delays. |  | B | When all team members refer to the project manager for decisions causing task delays, the project manager should delegate decision-making authority for some tasks to the team. Empowering team members reduces bottlenecks and maintains momentum. Meeting in 2 weeks (A) further delays decisions. Consolidating authority with the PM (C) worsens the problem. Reviewing a Pareto diagram (D) analyzes delay sources but does not address the authority issue. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 모든 팀원이 다양한 결정을 PM에게 위탁하여 일부 작업이 지연된다. PM은 무엇을 해야 하는가? | 2주 후 팀과 회의하여 모든 미결 작업에 응답한다 | 일부 작업의 의사결정 권한을 팀에 위임한다 | 의사결정 권한을 PM에게 유지하도록 통합한다 | 파레토 다이어그램을 검토하여 지연 원인을 식별한다 |  | B | 모든 결정이 PM을 거쳐 지연될 때, PM은 일부 작업의 의사결정 권한을 팀에 위임해야 한다. 팀 권한 부여가 효율성과 자율성을 높인다. 2주 대기(A)는 지연을 악화시킨다. 권한 유지(C)는 문제를 지속시킨다. 파레토 분석(D)은 원인이 이미 명확하여 불필요하다.
1308 | In an agile product development environment, work is distributed to Cities A, B, and C, which are geographically dispersed. The small teams work and collaborate to deliver the sprints. City A's team focuses on the features of data capture. City B's team focuses on the user experience and development pieces. City C's team coordinates testing. What should the project manager do to ensure a successful rollout of sprints? | Use a fishbone analysis to resolve problems and iron out communication issuesbetween the teams. | Ensure all three teams deliver independently without interactions so that they remainfocused and meet customer requirements. | Maintain localized teams to circumvent the challenges of delay or any otherunforeseen risks that might prevent progress. | Implement communication techniques and ensure the teams follow a relay pattern ofhanding off work from one team to the other. |  | D | When geographically dispersed teams across three cities each handle different aspects of agile product development, the project manager should implement communication techniques and ensure the teams follow a relay pattern of handing off work from one team to the other. This facilitates coordinated, sequential delivery across teams. Using fishbone analysis (A) is for root cause analysis, not workflow coordination. Ensuring independent delivery without interaction (B) creates silos. Maintaining localized teams to avoid risks (C) ignores the need for cross-team collaboration. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 애자일 제품 개발 환경에서 작업이 지리적으로 분산된 A, B, C 도시에 분배된다. 각 팀이 다른 측면을 담당한다. PM은 무엇을 해야 하는가? | 피시본 분석을 사용하여 문제를 해결하고 팀 간 커뮤니케이션 이슈를 정리한다 | 세 팀이 집중하고 기한을 맞추도록 상호작용 없이 독립적으로 납품하게 한다 | 지연이나 예상치 못한 리스크의 도전을 피하기 위해 지역화된 팀을 유지한다 | 커뮤니케이션 기법을 구현하고 팀이 도시 간 릴레이 패턴으로 작업을 인계하도록 한다 |  | D | 지리적으로 분산된 팀이 애자일 제품 개발의 다른 측면을 담당할 때, PM은 커뮤니케이션 기법을 구현하고 릴레이 패턴의 인계를 보장해야 한다. 구조화된 커뮤니케이션이 분산 팀 간 협업을 가능하게 한다. 피시본(A)은 진단 도구이지 솔루션이 아니다. 독립 납품(B)은 통합을 해친다. 지역화(C)는 협업을 제한한다.
1309 | A hybrid project has just been deployed, and the project manager is planning project closure with lessons learned workshops. A key stakeholder tells the project manager that having the Scrum team in the workshops is a waste of time because the project was delivered successfully. What should the project manager do? | Ask the Scrum team members to share retrospectives. | Invite the Scrum team members as optional participants. | Invite the Scrum team members as mandatory participants. | Ask the scrum master to attend the workshops. |  | C | Involving the Scrum team in lessons learned workshops is valuable regardless of whether the project was delivered successfully. Lessons learned are a critical component of project closure, capturing both positive and negative experiences for the benefit of the team, the organization, and future projects. In Scrum, continuous feedback and retrospective learning are embedded in every sprint, making comprehensive lessons learned a natural extension of the framework. The PMBOK Guide emphasizes that project closure activities—including lessons learned reviews—help finalize deliverables, evaluate performance, document outcomes, and preserve organizational knowledge. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Evaluate Project Status | Governance | Closing | Embed Quality | Close Project or Phase | Traditional PM | 하이브리드 프로젝트가 배포되었고 PM이 교훈 워크숍으로 프로젝트 종료를 계획 중이다. 스크럼 팀원의 참석 여부는? | 스크럼 팀원에게 회고 내용을 공유하도록 요청한다 | 스크럼 팀원을 선택적 참석자로 초대한다 | 스크럼 팀원을 필수 참석자로 초대한다 | 스크럼 마스터에게 워크숍에 참석하도록 요청한다 |  | C | 하이브리드 프로젝트 종료 시 교훈 워크숍에 스크럼 팀원을 필수 참석자로 초대해야 한다. 프로젝트 성공 여부와 관계없이 교훈은 프로젝트 종료의 핵심 구성요소이다. 회고 공유(A)는 간접적이다. 선택적 참석(B)은 참여를 보장하지 않는다. 스크럼 마스터만(D)은 팀 관점이 부족하다.
1310 | An organization has successfully delivered many projects using only predictive approaches. The organization has now decided to add some agile development processes into their standard deployment framework. What should the project manager take into account first when building the schedule for this new project? | The compliance measurement criteria of the new project | The benchmarked velocities of the previously completed projects | The benchmarked baselines of the previously completed projects | The compliance needs and categories of the new project |  | D | The correct answer is D. The compliance needs and categories of the new project. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 조직이 예측형 접근법만 사용했으나 이제 애자일을 시도하기로 했다. 첫 애자일 프로젝트에서 PM이 먼저 확인해야 할 것은? | 새 프로젝트의 컴플라이언스 측정 기준 | 이전 완료 프로젝트의 벤치마크된 속도 | 이전 완료 프로젝트의 벤치마크된 기준선 | 새 프로젝트의 컴플라이언스 필요와 범주 |  | D | 정답은 D이다. 새 프로젝트의 컴플라이언스 필요와 범주를 확인한다. 애자일은 반복적 납품, 팀 권한 부여, 지속적 개선을 강조한다. PM은 새 프로젝트의 고유한 컴플라이언스 요구를 먼저 이해해야 한다. 측정 기준(A)은 부분적이다. 이전 속도(B)는 예측형 프로젝트에서 가져올 수 없다. 이전 기준선(C)은 애자일에 적용할 수 없다.
1311 | A large corporation is transforming itself from a predictive to agile approach. A project team with knowledge of agile practices is experiencing significant conflicts with the executives regarding the processes to be followed. How should these conflicts be resolved? | Negotiate with the executives and agree on a process. | Request that the executives use agile practices | Include the executives in team retrospectives | Train the executives on agile practices |  | D | When an agile-knowledgeable team conflicts with executives over processes during an organizational transition to agile, the conflicts should be resolved by training the executives on agile practices. Education builds understanding and reduces resistance. Negotiating and agreeing on a process (A) may compromise agile principles. Requesting executives use agile (B) is directive without building understanding. Including executives in retrospectives (C) exposes them to agile but does not provide foundational training. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Embed Quality | Manage Team | Traditional PM | 대기업이 예측형에서 애자일로 전환 중이다. 애자일 지식이 있는 팀이 경영진과 프로세스에 대해 갈등한다. 어떻게 해결해야 하는가? | 경영진과 협상하여 프로세스에 합의한다 | 경영진에게 애자일 관행을 사용하도록 요청한다 | 경영진을 팀 회고에 포함한다 | 경영진에게 애자일 관행에 대한 교육을 제공한다 |  | D | 애자일 전환 중 팀과 경영진이 프로세스에 대해 갈등할 때, 경영진에게 애자일 관행에 대한 교육을 제공해야 한다. 교육이 이해와 수용의 기반이다. 협상(A)은 교육 없이는 타협에 그친다. 사용 요청(B)은 이해 없는 강요이다. 회고 포함(C)은 팀 안전 공간을 침해한다.
1312 | A team averages 100 story points per iteration. The team estimates there are about another 2,000 points remaining and about 20 iterations remaining. One of the team members suggests estimating by feature because the large stories are difficult to break up. What should the project manager do? | Reject this task-based estimation. | Meet with this team member. | Accept this task-based estimation. | Review this method with the team. |  | D | When a team member suggests estimating by feature instead of story points because large stories are difficult to break up, the project manager should review this method with the team. Collaborative evaluation of estimation approaches supports continuous improvement. Rejecting the suggestion (A) discourages innovation. Meeting privately with the team member (B) excludes the team. Accepting without team discussion (C) bypasses collective decision-making. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 팀이 이터레이션당 평균 100 스토리 포인트를 처리하고 약 2,000 포인트가 남았다. 팀원이 기능 단위 추정을 제안한다. PM은 무엇을 해야 하는가? | 이 작업 기반 추정을 거부한다 | 이 팀원과 미팅한다 | 이 작업 기반 추정을 수용한다 | 이 방법을 팀과 검토한다 |  | D | 팀원이 큰 스토리를 분해하기 어려워 기능 단위 추정을 제안할 때, PM은 이 방법을 팀과 검토해야 한다. 협력적 평가가 팀 합의를 보장한다. 즉시 거부(A)는 혁신을 막는다. 개별 미팅(B)은 팀 결정이 아니다. 즉시 수용(C)은 팀 합의 없이 진행한다.
1313 | A project has come to the closing stage. The work is generally finished, and the project manager wants to commence the closure process for the project. What should the project manager ensure is in place prior to the closing process? | The contractual deliverables of the project have been accepted. | It The handover and deliverable acceptance have been completed. | The lessons learned sessions have been conducted. | The organizational process assets (OPAs) have been updated. |  | A | Before commencing the closing process, the project manager must ensure that the contractual deliverables of the project have been accepted. Formal sign-off and acceptance by the customer is the most critical prerequisite for closure—projects are initiated based on business needs and customer requirements, so the project cannot be closed until the customer accepts the final outputs. Completing handover and deliverable acceptance (B) is part of the broader closure but follows formal acceptance. Conducting lessons learned sessions (C) is a closing activity, not a prerequisite. Updating OPAs (D) occurs during or after closing, not before. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Scope & Requirements Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트가 종료 단계에 왔다. 작업이 대체로 완료되었다. 종료 프로세스를 시작하기 전 PM이 확인해야 할 것은? | 프로젝트의 계약적 인도물이 수락되었다 | 인수인계와 인도물 수락이 완료되었다 | 교훈 세션이 수행되었다 | 조직 프로세스 자산(OPA)이 업데이트되었다 |  | A | 종료 프로세스를 시작하기 전, PM은 프로젝트의 계약적 인도물이 수락되었는지 확인해야 한다. 고객의 공식 서명과 수락이 종료의 가장 중요한 전제조건이다. 인수인계 완료(B)는 수락 후 단계이다. 교훈 세션(C)은 종료 중 활동이다. OPA 업데이트(D)는 종료 후 활동이다.
1314 | A project manager works for a large manufacturing company with diversified domains. The project team often participates in change requests. Recently, the change control board (CCB) deferred some requests and the project manager wants to communicate these requests to the stakeholders. What document should the project manager use to communicate these requests? | Backlog | Change log | Risk log | Issue log |  | B | To communicate deferred change requests to stakeholders, the project manager should use the change log. The change log tracks the progress of each change request—its review, approval, deferral, implementation, and closure—making it the appropriate document for communicating the status of CCB decisions. The backlog (A) is for feature prioritization in agile projects, not change tracking. The risk log (C) records risks, not change request statuses. The issue log (D) tracks current problems, not change control board decisions. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 대규모 제조 회사의 PM이 팀과 함께 여러 활동에 참여한다. 지연된 변경 요청을 이해관계자에게 전달하기 위해 어떤 도구를 사용해야 하는가? | 백로그 | 변경 로그 | 리스크 로그 | 이슈 로그 |  | B | 지연된 변경 요청을 이해관계자에게 전달하려면, 변경 로그를 사용해야 한다. 변경 로그는 각 변경 요청의 진행—검토, 승인, 연기, 구현—을 추적한다. 백로그(A)는 작업 항목이다. 리스크 로그(C)는 리스크 추적이다. 이슈 로그(D)는 이슈 추적이다.
1315 | A project manager is leading a project team that consists of five team members. One of the team members, a senior technical staff member, always criticizes the ideas of other members during team meetings. However, this senior technical member is not performing well on their own daily tasks. Other team members are frustrated and have become silent in meetings. What should the project manager do? | Encourage other team members to provide one another with their valuable ideas. | Provide feedback to bring the team members ' focus back to the performance of their daily tasks. | Reduce the team meeting frequency and seek input separately from team members. | Ask human resources (HR) to reassign the senior technical staff member. |  | B | When a senior technical member criticizes others' ideas while underperforming on their own tasks, causing frustration and silence, the project manager should provide feedback to bring focus back to daily task performance. Addressing behavior directly resolves the root cause. Encouraging other members' ideas (A) ignores the disruptive behavior. Reducing meeting frequency (C) avoids the problem. Asking HR to reassign (D) is extreme. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | PM이 5명의 팀원으로 구성된 프로젝트를 이끈다. 선임 기술 팀원이 다른 사람의 아이디어를 비판하고 자신의 업무 성과는 저조하다. PM은 무엇을 해야 하는가? | 다른 팀원들에게 서로의 가치 있는 아이디어를 공유하도록 격려한다 | 팀원들의 초점을 일상 업무 성과로 돌리기 위한 피드백을 제공한다 | 팀 회의 빈도를 줄이고 팀원으로부터 별도로 입력을 구한다 | 인사부에 선임 기술 직원을 재배치하도록 요청한다 |  | B | 선임 기술 팀원이 다른 사람의 아이디어를 비판하고 자신의 성과가 저조할 때, PM은 팀원들의 초점을 일상 업무 성과로 돌리기 위한 피드백을 제공해야 한다. 직접적 피드백이 행동과 성과 기대를 명확히 한다. 격려(A)는 비판 행동을 다루지 않는다. 회의 빈도 감소(C)는 회피이다. 재배치(D)는 과도한 조치이다.
1316 | A solution designer in an agile team often passes the design information to team members without any documentation. This has resulted in misunderstandings within the team. What should the agile leader do? | Move the solution designer to another team. | Review the process that resulted in this situation. | Ask the team to document the design. | Stop work until the design document is completed. |  | B | When a solution designer passes design information without documentation causing team misunderstandings, the agile leader should review the process that resulted in this situation. Examining the communication process identifies systemic improvements rather than blaming individuals, aligning with agile principles of inspect and adapt. Moving the designer to another team (A) removes the person without fixing the process. Asking the team to document the design (C) treats the symptom. Stopping work until documentation is complete (D) halts progress unnecessarily. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | XP (Extreme Programming) | People | Lead the Project Team | Resources | Executing | Be an Accountable Leader | Develop Team | Traditional PM | 애자일 팀의 솔루션 설계자가 문서 없이 팀원에게 설계 정보를 전달하여 오해가 발생한다. 애자일 리더는 무엇을 해야 하는가? | 솔루션 설계자를 다른 팀으로 이동한다 | 이 상황을 초래한 프로세스를 검토한다 | 팀에게 설계를 문서화하도록 요청한다 | 설계 문서가 완료될 때까지 작업을 중단한다 |  | B | 솔루션 설계자가 문서 없이 정보를 전달하여 오해가 생길 때, 애자일 리더는 이 상황을 초래한 프로세스를 검토해야 한다. 커뮤니케이션 프로세스 검토가 근본 원인을 다룬다. 다른 팀 이동(A)은 문제를 전가한다. 팀에 문서화 요청(C)은 설계자 책임을 전가한다. 작업 중단(D)은 과도하다.
1317 | A project manager is managing a project aimed at providing incremental deliveries to the market every three months. The team has been assigned, and the product backlog was created and prioritized by the product owner. After four iterations, the product owner escalates complaints to the CEO because the product does not meet the product owner's expectations. What should the project manager have done to prevent this situation from happening? | Reviewed the organizational process assets (OPAs) and lessons learned from similar projects | Performed backlog grooming to ensure that acceptance criteria were being met | Implemented sprint reviews with the product owner and retrospectives with the team to minimize gaps | Performed risk management analysis during daily scrums |  | C | When the product owner complains after four iterations that the product does not meet expectations, the project manager should have implemented sprint reviews with the product owner and retrospectives with the team to minimize gaps. Regular sprint reviews ensure continuous alignment between delivery and stakeholder expectations. Reviewing OPAs and lessons learned (A) informs planning but does not ensure ongoing alignment. Performing backlog grooming for acceptance criteria (B) is important but insufficient without demonstration and feedback. Risk management during daily scrums (D) addresses risk but not stakeholder alignment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | PM이 3개월마다 점진적 납품을 하는 프로젝트를 관리한다. 4번의 이터레이션 후 제품 책임자가 제품이 기대에 부합하지 않는다고 불만한다. PM이 무엇을 했어야 하는가? | 유사 프로젝트의 OPA와 교훈을 검토했다 | 인수 기준이 충족되도록 백로그 그루밍을 수행했다 | 제품 책임자와 스프린트 리뷰 및 팀과 회고를 구현하여 격차를 최소화했다 | 데일리 스크럼에서 리스크 관리 분석을 수행했다 |  | C | 4번의 이터레이션 후 제품이 기대에 부합하지 않을 때, PM은 제품 책임자와 스프린트 리뷰 및 팀과 회고를 구현했어야 한다. 정기적 피드백 루프가 기대와 결과 간 격차를 최소화한다. OPA 검토(A)는 사전적이지 않다. 백로그 그루밍(B)은 부분적이다. 데일리 스크럼 리스크(D)는 적절한 포럼이 아니다.
1318 | A project manager is leading a team of diverse individuals of all ages. The working hours for the project were set at the beginning of the project, and all team members agreed to the hours. However, later in the project, one of the team members informed the project manager that the previously agreed upon hours no longer work due to the team member's personal commitments. What should the project manager do? | Discuss the lack of dedication with the team member and their functional manager. | Allow the most senior team members to decide the time that works for the team. | Reassess the team ' s hours collaboratively so that the team is not impeded by the issue. | Remove the team member from the project team to be fair to the other members. |  | C | When a team member's personal commitments change and the previously agreed-upon hours no longer work, the project manager should reassess the team's hours collaboratively so the project is not impeded by the issue. This flexible, collaborative approach respects the individual's circumstances while ensuring the project continues to progress effectively. Discussing lack of dedication with the functional manager (A) is punitive and assumes bad intent. Allowing senior members to decide hours for everyone (B) may not represent all team members' needs. Removing the team member (D) is disproportionate and unfair. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 다양한 연령의 팀을 이끈다. 프로젝트 시작 시 합의된 근무 시간이 한 팀원의 개인 사정 변경으로 지키기 어렵다. PM은 무엇을 해야 하는가? | 팀원과 기능 관리자에게 헌신 부족에 대해 논의한다 | 가장 선임 팀원이 팀에 적합한 시간을 결정하도록 한다 | 팀이 이슈에 방해받지 않도록 근무 시간을 협력적으로 재평가한다 | 다른 팀원에게 공정하게 해당 팀원을 프로젝트에서 제거한다 |  | C | 팀원의 개인 사정이 변경되어 합의된 근무 시간을 지키기 어려울 때, PM은 팀이 방해받지 않도록 근무 시간을 협력적으로 재평가해야 한다. 협력적 접근이 팀 전체의 유연성과 포용을 보여준다. 헌신 부족 논의(A)는 비난적이다. 선임 결정(B)은 민주적이지 않다. 제거(D)는 과도하다.
1319 | During planning, a virtual project team agreed to the project reporting structure and established a meeting cadence that fits multiple time zones. One month into execution, the project manager notices that certain members are disengaged during project meetings. What should the project manager do to resolve this issue? | Work with the team to review the effectiveness of the agreed project practices. | Review the project reporting structure to clarify the project objectives. | Distribute the meeting agenda and objectives the day before the project meetings. | Set up follow-up sessions on all action items for team members. |  | A | When virtual team engagement declines, the PM should reflect with the team on whether current practices (meeting cadence, structure, tools) remain effective. This supports continuous improvement—a core agile and PMI principle—and promotes psychological safety by empowering the team to propose better collaboration formats. Focusing on accountability (B) alone doesn't resolve disengagement. Improving reporting structure (D) addresses logistics, not team dynamics. The team-centered approach is most effective for addressing underlying engagement issues. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 가상 프로젝트 팀이 보고 구조와 회의 주기에 합의했으나 시간이 지나며 참여도가 감소했다. PM은 무엇을 해야 하는가? | 팀과 협력하여 합의된 프로젝트 관행의 효과를 검토한다 | 프로젝트 목표를 명확히 하기 위해 보고 구조를 검토한다 | 프로젝트 회의 하루 전에 회의 안건과 목표를 배포한다 | 팀원의 모든 조치 항목에 대한 후속 세션을 설정한다 |  | A | 가상 팀의 참여도가 감소할 때, PM은 팀과 협력하여 현재 관행(회의 주기, 구조, 도구)이 여전히 효과적인지 검토해야 한다. 이는 지속적 개선을 지원한다. 보고 구조 검토(B)는 부분적이다. 안건 배포(C)는 절차적 개선이지 근본 해결이 아니다. 후속 세션(D)은 추가 부담이다.
1320 | A project manager in one country is reporting to a lead project manager for a new software development project in another country. The lead project manager constantly requests updates from the project manager, often demanding information via multiple communication channels if the project manager does not respond within a few minutes of a request. Both of them are equal in seniority and both report to the same functional manager. How should the project manager proceed? | Negotiate a mutually agreeable feedback cycle with acceptable timelines. | Escalate the issue to the functional manager and explain the situation to them. | Update the communications management plan and the stakeholder engagement plan. | Refer the lead project manager to the communications management plan. |  | A | When a lead project manager in another country constantly demands updates through multiple channels, the project manager should negotiate a mutually agreeable feedback cycle with acceptable timelines. Clear communication agreements manage expectations for both parties. Escalating to the functional manager (B) may damage the working relationship. Updating the communications and engagement plans (C) is process-oriented but does not resolve the interpersonal issue. Referring to the communications plan (D) is passive. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 한 국가의 PM이 다른 국가의 리드 PM에게 보고한다. 리드 PM이 여러 채널을 통해 지속적으로 업데이트를 요구한다. PM은 무엇을 해야 하는가? | 상호 합의 가능한 피드백 주기와 수용 가능한 일정을 협상한다 | 기능 관리자에게 이슈를 에스컬레이션하고 상황을 설명한다 | 커뮤니케이션 관리 계획과 이해관계자 참여 계획을 업데이트한다 | 리드 PM에게 커뮤니케이션 관리 계획을 참조하도록 한다 |  | A | 리드 PM이 여러 채널로 지속적 업데이트를 요구할 때, PM은 상호 합의 가능한 피드백 주기와 일정을 협상해야 한다. 직접적 대화와 합의가 관계를 유지하면서 기대를 정립한다. 에스컬레이션(B)은 직접 해결 전에 과도하다. 계획 업데이트(C)는 관료적이다. 계획 참조(D)는 수동적이다.
1321 | Travel restrictions are suddenly imposed during a project's execution. The team members reside in different geographic locations. What should the project manager do next to address this issue? | Place a hold on activities until the team can resume the work on-site. | Ask the team members to proceed independently while examining needs and alternatives. | Halt all processes until procurement and implementation of solutions are completed. | Obtain and implement the sponsor ' s recommendations for a solution. |  | B | When travel restrictions are suddenly imposed and team members are geographically dispersed, the project manager should ask team members to proceed independently while examining needs and alternatives. Maintaining momentum while assessing the situation enables adaptive response. Placing a hold on activities (A) causes unnecessary delay. Halting processes until procurement of solutions (C) is overly rigid. Obtaining and implementing the sponsor's recommendations (D) bypasses PM problem-solving. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 중 갑작스러운 여행 제한이 부과되었다. 팀원이 다른 지역에 거주한다. PM은 무엇을 해야 하는가? | 팀이 현장에서 작업을 재개할 수 있을 때까지 활동을 보류한다 | 팀원에게 독립적으로 진행하면서 필요와 대안을 검토하도록 요청한다 | 솔루션의 조달과 구현이 완료될 때까지 모든 프로세스를 중단한다 | 스폰서의 솔루션 권장사항을 얻어 구현한다 |  | B | 갑작스러운 여행 제한으로 분산된 팀이 모일 수 없을 때, PM은 팀원에게 독립적으로 진행하면서 필요와 대안을 검토하도록 해야 한다. 작업 연속성을 유지하면서 적응적으로 대응한다. 활동 보류(A)는 프로젝트를 지연시킨다. 전면 중단(C)은 과도하다. 스폰서 권장(D)은 수동적이다.
1322 | A project to implement a new online landing platform has started. After the first sprint, the project sponsor requested a change. What should the project manager do next? | Escalate the change request to the sponsor | Validate the work completed | Facilitate the update of the product backlog | Inform the stakeholders of the change |  | C | When the project sponsor requests a change after the first sprint of a new platform project, the project manager should facilitate the update of the product backlog. In agile, the product backlog is the dynamic, prioritized list of features and requirements. When a change is requested, the PM ensures it is properly captured, prioritized, and reflected in the backlog so the team and sponsor are aligned on scope and deliverables. Escalating the change request to the sponsor (A) is circular—the sponsor initiated the change. Validating completed work (B) is a separate activity unrelated to the change. Informing stakeholders of the change (D) may follow but the first action is to update the backlog. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 새 온라인 랜딩 플랫폼 프로젝트가 시작되었다. 첫 스프린트 후 스폰서가 변경을 요청했다. PM은 무엇을 먼저 해야 하는가? | 변경 요청을 스폰서에게 에스컬레이션한다 | 완료된 작업을 검증한다 | 제품 백로그 업데이트를 퍼실리테이션한다 | 이해관계자에게 변경을 알린다 |  | C | 스폰서가 첫 스프린트 후 변경을 요청할 때, PM은 제품 백로그 업데이트를 퍼실리테이션해야 한다. 애자일에서 제품 백로그는 변경을 관리하는 핵심 도구이다. 에스컬레이션(A)은 스폰서가 요청자이므로 불필요하다. 작업 검증(B)은 변경 반영이 아니다. 이해관계자 알림(D)은 백로그 업데이트 후에 한다.
1323 | A product team is comprised of consultants and staff members. Most of the team members agree on risks and the defined risk actions. One consultant discovers a new risk and communicates it directly to management. What should the project manager do? | Accept the risk and immediately enter the risk into the risk register | Reject the risk because the team is not in agreement on escalating it | Include the risk in the risk assessment and evaluate it with the team | Discuss with the consultant to understand why the risk was escalated |  | D | When a consultant discovers a new risk and communicates it directly to management instead of through the team, the project manager should discuss with the consultant to understand why the risk was escalated. This helps the PM understand the risk's severity and the consultant's rationale, enabling appropriate next steps. Accepting the risk and entering it immediately (A) bypasses team evaluation. Rejecting the risk because the team did not agree (B) ignores a potentially valid concern. Including it in risk assessment with the team (C) is a likely next step but should follow understanding the escalation context. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 제품 팀이 컨설턴트와 정규 직원으로 구성된다. 대부분이 리스크에 합의하지만 컨설턴트가 새 리스크를 발견하고 팀 대신 경영진에게 직접 전달했다. PM은 무엇을 해야 하는가? | 리스크를 수용하고 즉시 리스크 등록부에 입력한다 | 팀이 에스컬레이션에 합의하지 않으므로 리스크를 거부한다 | 리스크를 리스크 평가에 포함하고 팀과 평가한다 | 컨설턴트와 논의하여 왜 리스크를 에스컬레이션했는지 이해한다 |  | D | 컨설턴트가 새 리스크를 팀 대신 경영진에게 직접 전달했을 때, PM은 컨설턴트와 논의하여 이유를 이해해야 한다. 동기와 우려를 이해하는 것이 적절한 커뮤니케이션 채널 확립의 기초이다. 즉시 수용(A)은 프로세스를 무시한다. 거부(B)는 유효한 리스크를 놓칠 수 있다. 평가 포함(C)은 유용하지만 커뮤니케이션 문제를 다루지 않는다.
1324 | During iteration planning, team A identifies that an important deliverable is dependent upon a deliverable from team B. What should the project manager do? | Request team B to immediately start this activity and deliver to team A. | Make team Aa part of team B and ensure that the deliverable is ready. | Ask team B to focus on their backlog and deliver based on their priority, | Inform team B of the dependency and ensure that the deliverable is planned. |  | D | When team A identifies a dependency on a deliverable from team B during iteration planning, the project manager should inform team B of the dependency and ensure the deliverable is planned accordingly. Proactive communication aligns both teams' efforts and schedules, avoiding delays. Requesting team B to start immediately (A) ignores team B's existing priorities and planning. Merging team A into team B (B) is disruptive and unnecessary for managing a single dependency. Asking team B to simply follow their own backlog priority (C) ignores the inter-team dependency and risks delays for team A. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 이터레이션 계획 중 팀 A가 중요 인도물이 팀 B의 인도물에 종속됨을 식별했다. PM은 무엇을 해야 하는가? | 팀 B에게 즉시 이 활동을 시작하여 팀 A에 납품하도록 요청한다 | 팀 A를 팀 B의 일부로 만들어 인도물이 준비되도록 한다 | 팀 B에게 자체 백로그에 집중하고 우선순위에 따라 납품하도록 요청한다 | 팀 B에게 종속성을 알리고 인도물이 계획되도록 한다 |  | D | 팀 A가 팀 B에 대한 종속성을 식별할 때, PM은 팀 B에게 종속성을 알리고 인도물이 계획되도록 해야 한다. 투명한 커뮤니케이션과 계획 정렬이 종속성을 관리한다. 즉시 시작 요청(A)은 팀 B 계획을 무시한다. 팀 합병(B)은 과도하다. 무시(C)는 종속성을 해결하지 않는다.
1325 | A project interfaces with other projects that are in the same portfolio but are being developed in international locations. One of the international projects has suggested a tactical change that needs to be implemented in this project. What should the project manager do next? | Implement the change request as soon as possible to avoid accumulating new scope. | Reject the change request since it may negatively impact the project ' s performance. | Use the team ' s connections with international colleagues to get early warnings on future changes. | Keep the focus on the priority items while the change goes through the change control process. |  | D | When an international project suggests a tactical change that needs implementation in the current project, the project manager should keep focus on priority items while the change goes through the change control process. Proper governance ensures controlled change. Implementing immediately (A) bypasses change control. Rejecting outright (B) dismisses potentially valid input. Using connections for early warnings (C) is proactive but does not address the current change request. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트가 같은 포트폴리오의 다른 국제 프로젝트와 인터페이스한다. 국제 프로젝트가 현재 프로젝트에 전술적 변경 구현을 제안했다. PM은 무엇을 해야 하는가? | 새 범위 축적을 피하기 위해 변경 요청을 가능한 빨리 구현한다 | 프로젝트 성과에 부정적 영향을 줄 수 있으므로 변경 요청을 거부한다 | 국제 동료와의 팀 연결을 활용하여 향후 변경에 대한 조기 경고를 받는다 | 변경이 변경 통제 프로세스를 거치는 동안 우선순위 항목에 집중을 유지한다 |  | D | 국제 프로젝트가 전술적 변경을 제안할 때, PM은 변경이 변경 통제 프로세스를 거치는 동안 우선순위 항목에 집중을 유지해야 한다. 프로세스 준수가 통제된 변경 관리를 보장한다. 즉시 구현(A)은 프로세스를 무시한다. 거부(B)는 유효한 변경을 차단한다. 조기 경고(C)는 유용하지만 현재 변경에 대한 조치가 아니다.
1326 | A project manager is leading a large public project that will have a high impact on the town's citizens. How should the project manager define the different requirements? | Include only the key requirements and keep the stakeholders informed about scope decisions. | Include only the common requirements of each stakeholder group in the project goals. | Analyze the interests and influence of stakeholders and evaluate their requirements. | Add only the opinions of the team, because they know the objectives of the project. |  | C | When leading a large public project with high community impact, the project manager should analyze the interests and influence of stakeholders and evaluate their requirements. Stakeholder analysis ensures comprehensive and representative requirements. Including only key requirements (A) may miss critical stakeholder needs. Including only common requirements (B) sacrifices important unique needs. Adding only team opinions (D) excludes external stakeholders. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 시민에게 높은 영향을 미치는 대규모 공공 프로젝트를 이끌고 있다. PM은 이해관계자 요구사항을 어떻게 다뤄야 하는가? | 핵심 요구사항만 포함하고 이해관계자에게 범위 결정을 알린다 | 각 이해관계자 그룹의 공통 요구사항만 프로젝트 목표에 포함한다 | 이해관계자의 관심과 영향력을 분석하고 요구사항을 평가한다 | 팀의 의견만 추가한다, 프로젝트 목표를 알고 있으므로 |  | C | 높은 지역사회 영향이 있는 대규모 공공 프로젝트를 이끌 때, PM은 이해관계자의 관심과 영향력을 분석하고 요구사항을 평가해야 한다. 이해관계자 분석이 포괄적이고 균형 잡힌 요구사항 관리를 보장한다. 핵심만 포함(A)은 중요한 요구를 놓칠 수 있다. 공통만(B)은 고유 요구를 무시한다. 팀만(D)은 이해관계자를 배제한다.
1327 | Project acceptance criteria include on-site training for the new users of a system. Due to unforeseen circumstances, all team members have to work remotely for an indefinite period of time. What should the project manager do? | Create a risk and assign remediation actions. | Reschedule on-site training to online sessions. | Cancel all of the on-site training sessions. | Document the project issue and provide options. |  | B | When unforeseen circumstances require all team members to work remotely, making on-site training impossible, the project manager should reschedule on-site training to online sessions. This adapts the delivery method while still meeting the acceptance criteria for user training. Creating a risk and assigning remediation (A) documents the problem but does not solve it. Canceling all training (C) fails to meet acceptance criteria. Documenting the issue and providing options (D) delays resolution without taking action. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Scope & Requirements Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 인수 기준에 현장 교육이 포함되어 있다. 예상치 못한 상황으로 모든 팀원이 원격 근무해야 한다. PM은 무엇을 해야 하는가? | 리스크를 생성하고 교정 조치를 할당한다 | 현장 교육을 온라인 세션으로 재일정한다 | 모든 현장 교육 세션을 취소한다 | 프로젝트 이슈를 문서화하고 옵션을 제공한다 |  | B | 예상치 못한 상황으로 현장 교육이 불가능할 때, PM은 현장 교육을 온라인 세션으로 재일정해야 한다. 납품 방식을 적응시키면서 인수 기준을 충족한다. 리스크 생성(A)은 해결이 아닌 문서화이다. 취소(C)는 인수 기준을 충족하지 못한다. 이슈 문서화(D)는 행동이 아닌 기록이다.
1328 | The CEO has authorized the development of a complex financial product for a company to provide greater future benefits. The budget has been acquired through financing with global investors who expect all risks to be identified as soon as possible. What should the project manager use to identify the risks? | Strengths, weaknesses, opportunities, and threats (SWOT) analysis | An analysis of shared risks between parties | Expert judgment | A risk value assessment |  | C | Expert judgment is the most appropriate technique for identifying risks in this scenario. Experts—internal or external to the project team—provide insights on the sources, causes, and effects of potential risks based on their knowledge and experience. For a complex financial product with global investors demanding early risk identification, leveraging expert knowledge ensures comprehensive and timely risk identification. A SWOT analysis (A) is a strategic planning tool, not a primary risk identification technique. An analysis of shared risks between parties (B) is relevant for multi-party risk allocation but is not the core identification method. A risk value assessment (D) is used for risk prioritization after identification, not for the identification process itself. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Initiating | Focus on Value | Develop Project Charter | Traditional PM | CEO가 미래 이익을 위한 복잡한 금융 상품 개발을 승인했다. 리스크를 식별하기 위한 가장 적절한 기법은 무엇인가? | SWOT 분석 | 당사자 간 공유 리스크 분석 | 전문가 판단 | 리스크 가치 평가 |  | C | 복잡한 금융 상품의 리스크 식별에는 전문가 판단이 가장 적절하다. 전문가가 잠재적 리스크의 출처, 원인, 영향에 대한 통찰을 제공한다. SWOT(A)은 전략적 분석이지 구체적 리스크 식별이 아니다. 공유 리스크 분석(B)은 계약 관련이다. 리스크 가치 평가(D)는 식별이 아닌 평가이다.
1329 | A customer discovered quality issues with the latest deliverables. However, the project team immediately resolved the issues. Now that the project is back on track, what should the project manager do next? | Reassess the risk log to ensure it is up to date. | Perform lessons learned to ensure the issue does not happen again. | Schedule a team meeting to review the issue, | Monitor quality metrics to ensure the project continues as planned. |  | B | After resolving quality issues with deliverables, the PM should conduct a lessons learned session. This continuous improvement activity helps the team understand what went wrong, why it occurred, and how to prevent similar problems in the future. Documenting lessons learned is a proactive step toward enhancing the quality of future deliverables and project processes. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 고객이 최신 인도물의 품질 문제를 발견했다. 팀이 즉시 해결했다. PM은 다음에 무엇을 해야 하는가? | 리스크 로그를 재평가하여 최신 상태인지 확인한다 | 문제가 재발하지 않도록 교훈을 수행한다 | 이슈를 검토하기 위한 팀 회의를 일정 잡는다 | 프로젝트가 계획대로 계속되도록 품질 지표를 모니터링한다 |  | B | 인도물 품질 문제를 해결한 후, PM은 교훈 세션을 수행해야 한다. 이 지속적 개선 활동이 팀이 무엇이 잘못되었는지, 왜 발생했는지, 어떻게 방지할지 이해하도록 돕는다. 리스크 로그(A)는 관련되지만 교훈이 우선이다. 팀 회의(C)는 이미 해결되었으므로 부차적이다. 품질 모니터링(D)은 지속적이지만 교훈이 더 중요하다.
1330 | A procurement team lead has been reported as getting into conflicts with other project team members on a weekly basis. The project manager engages with the team lead and discovers that other team members do not believe the team lead is right for this position. What should the project manager do to resolve these recurring conflicts between the team lead and the other team members? | Issue the team lead a warning, and consider recommending the team lead for emotional intelligence training. | Receive details of the conflicts from all involved, issue all a warning notice, and send all to leadership training. | Find ways to reduce the tension, increase cooperation, and understand the emotions of all team members involved. | Organize a meeting to discuss emotional intelligence with the team, and establish a rule of respect and special treatment for the team lead. |  | C | The project manager should find ways to reduce tension, increase cooperation, and understand the emotions of all team members involved. Effective conflict resolution requires understanding the perspectives and feelings of all parties to address root causes rather than symptoms. Issuing a warning and recommending emotional intelligence training (A) is punitive and may not address the underlying dynamics. Issuing warnings to all and mandating leadership training (B) treats everyone equally regardless of their role in the conflict. Establishing special treatment rules for the team lead (D) creates unfair dynamics and does not build genuine mutual respect. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Procurement & Contract Mgmt | People | Manage Conflicts | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 조달 팀 리더가 매주 다른 프로젝트 팀원과 갈등을 일으킨다고 보고되었다. PM은 무엇을 해야 하는가? | 팀 리더에게 경고를 발행하고 감성 지능 교육을 추천한다 | 모든 관련자로부터 갈등 세부사항을 받고 모두에게 경고를 발행하며 리더십 교육에 보낸다 | 긴장을 줄이고 협력을 높이며 모든 팀원의 감정을 이해하는 방법을 찾는다 | 팀과 감성 지능에 대한 회의를 조직하고 존중의 규칙을 수립한다 |  | C | PM은 긴장을 줄이고 협력을 높이며 모든 팀원의 감정을 이해하는 방법을 찾아야 한다. 효과적인 갈등 해결은 관점과 감정을 이해하는 것이 필요하다. 경고(A)는 징벌적이다. 모두에게 경고(B)는 공정하지 않다. 회의/규칙(D)은 유용하지만 먼저 감정 이해가 필요하다.
1331 | A team member on an important company project mistakenly caused significant cost overruns. The sponsor informed the project manager and expects the project manager to take action within 1 week. This team member has always been an outstanding performer. What should the project manager do first to address the sponsor's concerns? | Document the team member ' s mistake in the lessons learned. | Relocate the team member to another project due to the mistake. | Train the team member to improve their performance to avoid future mistakes. | Talk with the team member to identify the reason for the mistake. |  | D | When an outstanding team member mistakenly causes significant cost overruns and the sponsor expects action within one week, the project manager should first talk with the team member to identify the reason for the mistake. Understanding root causes before acting ensures fair, effective corrective action. Documenting in lessons learned (A) is premature without understanding. Relocating to another project (B) is punitive. Training the team member (C) assumes a skill gap before confirming the cause. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 중요한 팀원이 실수로 상당한 비용 초과를 야기했다. 스폰서가 1주 내 조치를 기대한다. PM은 무엇을 먼저 해야 하는가? | 팀원의 실수를 교훈에 문서화한다 | 실수로 인해 팀원을 다른 프로젝트로 이동시킨다 | 미래 실수를 피하기 위해 팀원을 교육시킨다 | 팀원과 대화하여 실수의 이유를 파악한다 |  | D | 우수한 팀원이 실수로 비용 초과를 야기했을 때, PM은 먼저 팀원과 대화하여 실수의 이유를 파악해야 한다. 근본 원인 이해가 적절한 시정 조치의 기초이다. 문서화(A)는 대화 후에 한다. 이동(B)은 우수한 팀원을 잃는다. 교육(C)은 원인 파악 후에 한다.
1332 | In an agile team, some of the team members are coming forward to ask for more autonomy on the project. What should the project manager do in this situation? | Encourage the team lead to make decisions. | Encourage the team members to make decisions. | Discourage them as conflicts may be created. | Discourage this request, as it is for the management team. |  | B | When agile team members request more autonomy, the project manager should encourage the team members to make decisions. In agile, autonomy empowers self-organization, drives innovation, and fosters ownership—aligning with agile principles. Encouraging only the team lead to decide (A) limits self-organization. Discouraging due to potential conflict (C) undermines team motivation. Treating it as a management-only prerogative (D) contradicts agile values. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 애자일 팀에서 일부 팀원이 프로젝트에서 더 많은 자율성을 요청한다. PM은 무엇을 해야 하는가? | 팀 리더가 결정을 내리도록 장려한다 | 팀원이 결정을 내리도록 장려한다 | 갈등이 생길 수 있으므로 만류한다 | 관리팀의 몫이므로 이 요청을 만류한다 |  | B | 애자일 팀원이 더 많은 자율성을 요청할 때, PM은 팀원이 결정을 내리도록 장려해야 한다. 애자일에서 자율성은 자체 조직화를 강화하고 혁신을 촉진한다. 팀 리더만(A)은 자율성을 제한한다. 만류(C, D)는 애자일 원칙에 반한다.
1333 | A project is successfully delivering its product outcomes, and the customer satisfaction rating is high. However, during an internal audit, it is discovered that certain essential process documents and approvals are missing, and the project is evaluated as being noncompliant. What should the project manager do next? | Change the quality management processes to align with the project objective. | Perform quality assurance to review the processes against the quality management plan and identify gaps. | Review the latest project management standards with the project management office (PMO) and make changes to the quality management plan. | Review and update the project document repository with the missing documents and approvals. |  | B | When an internal audit discovers missing essential process documents and approvals despite successful product outcomes, the project manager should perform quality assurance to review processes against the quality management plan and identify gaps. Process auditing addresses systemic compliance issues. Changing quality processes (A) alters standards without understanding gaps. Reviewing standards with the PMO (C) may help but does not directly audit. Updating the repository (D) addresses symptoms, not root causes. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트가 성공적으로 인도 중이고 고객 만족도가 높다. 내부 감사에서 필수 프로세스 문서와 승인이 누락되었음을 발견했다. PM은 무엇을 해야 하는가? | 프로젝트 목표에 맞게 품질 관리 프로세스를 변경한다 | 품질 관리 계획에 대한 프로세스를 검토하고 개선 사항을 식별하기 위해 품질보증을 수행한다 | PMO와 최신 프로젝트 관리 표준을 검토하고 변경한다 | 프로젝트 문서 저장소를 누락된 문서와 승인으로 검토하고 업데이트한다 |  | B | 내부 감사에서 필수 프로세스 문서와 승인이 누락된 것을 발견했을 때, PM은 품질 관리 계획에 대한 프로세스를 검토하기 위해 품질보증을 수행해야 한다. 체계적 프로세스 검토가 격차를 식별한다. 프로세스 변경(A)은 문제를 피하는 것이다. PMO 검토(C)는 외부 의존이다. 문서 업데이트(D)는 증상만 다룬다.
1334 | A major issue regarding conflicting priorities has been raised by the project team with respect to a few stakeholder requirements. What should the project manager do? | Prioritize other items for the team and deal with the conflicting requirements later. | Negotiate a common agreement with the involved stakeholders regarding the requirements. | Escalate to the project management office (PMO) and request a solution for the requirements. | Allow the project team to decide which requirement is the most appropriate to follow. |  | B | When stakeholder requirements conflict, the PM should not postpone the issue or delegate the decision to the team alone. Instead, the PM should work directly with the involved stakeholders to negotiate a common understanding and agreed priority. Premature escalation (A) bypasses the PM's responsibility to attempt resolution first. Leaving the conflict unresolved (B) creates confusion. Having the project team decide requirement priority among stakeholders (C) is inappropriate—the PM should facilitate, negotiate, and manage expectations to align stakeholders and protect project outcomes. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 이해관계자 요구사항의 충돌하는 우선순위에 대해 프로젝트 팀이 주요 이슈를 제기했다. PM은 무엇을 해야 하는가? | 팀을 위해 다른 항목의 우선순위를 정하고 충돌하는 요구사항은 나중에 처리한다 | 관련 이해관계자와 요구사항에 대한 공통 합의를 협상한다 | PMO에 에스컬레이션하고 요구사항에 대한 해결을 요청한다 | 프로젝트 팀이 어떤 요구사항을 따를지 결정하도록 한다 |  | B | 이해관계자 요구사항이 충돌할 때, PM은 관련 이해관계자와 공통 합의를 협상해야 한다. 이해관계자 참여를 통한 협상이 균형 잡힌 해결을 제공한다. 나중에 처리(A)는 문제를 악화시킨다. PMO 에스컬레이션(C)은 PM의 역할을 포기한다. 팀 결정(D)은 이해관계자 관계를 무시한다.
1335 | A healthcare company requires all new employees to attend mandatory computer-based training courses. Because some of the employees work with highly sensitive patient data, the training covers various aspects of data security. In spite of this training, data breaches continue to occur in one of the project teams. What should the project manager do? | Ensure that all team members complete the training. | Retrain the team members responsible for the breaches. | Redesign the training courseware to make it interesting. | Apply a root-cause analysis on the data breaches. |  | D | When data breaches continue to occur despite mandatory computer-based training, the project manager should apply root-cause analysis on the data breaches. Identifying underlying causes enables targeted corrective action. Ensuring training completion (A) repeats the same approach. Retraining responsible team members (B) assumes training is the issue. Redesigning courseware (C) addresses engagement but not root causes. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Planning | Embed Quality | Determine Budget | Traditional PM | 의료 회사가 신규 직원에게 필수 컴퓨터 기반 교육을 제공한다. 교육에도 불구하고 데이터 침해가 계속 발생한다. PM은 무엇을 해야 하는가? | 모든 팀원이 교육을 완료하도록 한다 | 침해를 일으킨 팀원을 재교육한다 | 교육 과정을 흥미롭게 재설계한다 | 데이터 침해에 근본 원인 분석을 적용한다 |  | D | 필수 교육에도 불구하고 데이터 침해가 계속될 때, PM은 근본 원인 분석을 적용해야 한다. 근본 원인 식별이 목표에 맞는 해결을 가능하게 한다. 교육 완료(A)는 이미 하고 있다. 재교육(B)은 근본 원인을 모른 채 반복이다. 재설계(C)는 원인 파악 없이 추측이다.
1336 | According to the project contract, the delivery date is approaching. However, one important material is still not on site. The construction work will have to stop and wait for this special material, delaying the project. What should the project manager do? | Ask the client to help solve the problem | Record it in the risk register | Start procuring this material from another supplier. | Engage the project team to look for alternatives to find a solution |  | D | When the delivery date approaches but critical material is not on site and will cause construction delays, the project manager should engage the project team to look for alternatives to find a solution. Leveraging the team's expertise identifies viable options. Asking the client to solve the problem (A) implies PM incapability. Recording it in the risk register (B) documents but does not resolve the issue. Starting procurement from another supplier (C) is costly and risky without exploring alternatives first. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 계약상 납기일이 다가오고 있다. 중요한 자재가 아직 현장에 없고 건설 지연을 야기할 것이다. PM은 무엇을 해야 하는가? | 고객에게 문제 해결을 도와달라고 요청한다 | 리스크 등록부에 기록한다 | 다른 공급업체에서 자재 조달을 시작한다 | 프로젝트 팀을 참여시켜 대안을 찾아 해결책을 모색한다 |  | D | 납기일이 다가오는데 중요 자재가 없을 때, PM은 프로젝트 팀을 참여시켜 대안을 찾아야 한다. 팀 협력이 다양한 해결 옵션을 생성한다. 고객 도움(A)은 내부 문제를 외부에 노출한다. 리스크 등록(B)은 문서화이지 행동이 아니다. 다른 공급업체(C)는 한 가지 옵션일 뿐 팀 논의가 우선이다.
1337 | Team morale is at an all-time low after an incident involving one of the team members. Which two actions should the project manager take to resolve the situation? (Choose two) | Review the lessons learned document with the team. | Conduct a team-building workshop. | Host a special meeting to talk about what happened. | Escalate the issue to human resources (HR). | Discuss this incident in the project review meeting. | C, E | When a team member makes a serious mistake that affects team morale, the project manager should take two actions: host a special meeting to talk about what happened (C) to address the situation transparently and help the team process the event, and discuss this incident in the project review meeting (E) to formally document lessons learned and prevent recurrence. A dedicated meeting shows immediate leadership attention, while the project review creates a structured forum for reflection. Reviewing lessons learned documents (A) is retrospective and does not directly address current morale. Conducting a team-building workshop (B) may help morale generally but does not address the specific incident. Escalating to HR (D) is disproportionate unless the mistake involves policy violations. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Embed Quality | Develop Team | Traditional PM | 팀원 중 한 명의 사건으로 팀 사기가 최저이다. PM은 어떤 두 가지 조치를 취해야 하는가? | 팀과 교훈 문서를 검토한다 | 팀 빌딩 워크숍을 실시한다 | 무슨 일이 있었는지 논의하기 위한 특별 회의를 개최한다 | 인사부(HR)에 이슈를 에스컬레이션한다 | 프로젝트 검토 회의에서 이 사건을 논의한다 | C, E | 팀원의 심각한 실수로 팀 사기가 저하되었을 때, PM은 두 가지 조치를 취해야 한다: 무슨 일이 있었는지 논의하기 위한 특별 회의를 개최하여(C) 투명하게 상황을 다루고, 프로젝트 검토 회의에서 이 사건을 논의하여(E) 공식적으로 기록하고 개선 방안을 수립한다. 교훈 검토(A)는 문서 중심이다. 팀 빌딩(B)은 근본 대응이 아니다. HR 에스컬레이션(D)은 과도할 수 있다.
1338 | A project manager is managing a project with a hybrid approach and has requested a senior team member to perform a quantitative risk analysis. The team member responds that they do not have the knowledge to perform such an analysis. What should the project manager do? | Help the team member to perform the quantitative risk analysis through coaching, mentoring and training | Perform the quantitative risk analysis for the team member. | Contact the project management office (PMO) and request them to assign another team member who has the knowledge to perform this task to the team 624 | Escalate the issue to the functional manager |  | A | When a senior team member lacks knowledge to perform quantitative risk analysis, the project manager should help the team member through coaching, mentoring, and training. Developing team capabilities aligns with the PM's responsibility for team development and ensures sustainable project capability. Contacting the PMO for a replacement (C) disrupts team dynamics. Escalating to the functional manager (D) is unnecessary. Performing the analysis for the member (B) deprives them of learning. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Hybrid/Tailoring | PM이 선임 팀원에게 정량적 리스크 분석을 수행하도록 요청했지만 팀원이 지식이 부족하다. PM은 무엇을 해야 하는가? | 코칭, 멘토링, 교육을 통해 팀원이 정량적 리스크 분석을 수행하도록 돕는다 | 팀원을 대신하여 정량적 리스크 분석을 수행한다 | PMO에 연락하여 역량이 있는 다른 팀원을 배정하도록 요청한다 | 기능 관리자에게 이슈를 에스컬레이션한다 |  | A | 선임 팀원이 정량적 리스크 분석 지식이 부족할 때, PM은 코칭, 멘토링, 교육을 통해 돕아야 한다. 팀 역량 개발이 장기적 가치를 제공한다. 대신 수행(B)은 팀 발전이 없다. 다른 팀원 배정(C)은 기존 팀원을 무시한다. 에스컬레이션(D)은 과도하다.
1339 | One of the service providers on a complex project has been facing resource availability problems over the last six months. However, the service provider has assured the project manager that the deliverables will be on time. How should the project manager address this situation? | Implement a risk response plan. | Update the issue log. | Perform a qualitative risk analysis. | Perform a root cause analysis. |  | C | When a service provider has faced resource availability problems for six months but assures on-time delivery, the project manager should perform a qualitative risk analysis. This assesses the probability and impact of the resource issue on project objectives, identifies triggers and warning signs, and assigns risk priority to determine appropriate response strategies. Implementing a risk response plan (A) is premature without first analyzing the risk. Updating the issue log (B) documents the concern but does not assess uncertainty and potential impact. Performing a root cause analysis (D) may not be feasible for problems beyond the PM's control. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 복잡한 프로젝트의 서비스 제공업체가 6개월간 자원 가용성 문제를 겪고 있지만 제시간 납품을 보장한다. PM은 무엇을 해야 하는가? | 리스크 대응 계획을 실행한다 | 이슈 로그를 업데이트한다 | 정성적 리스크 분석을 수행한다 | 근본 원인 분석을 수행한다 |  | C | 서비스 제공업체가 6개월간 자원 문제를 겪지만 납품을 보장할 때, PM은 정성적 리스크 분석을 수행해야 한다. 이는 프로젝트에 대한 영향 확률과 영향도를 평가한다. 리스크 대응 실행(A)은 분석 전에 성급하다. 이슈 로그(B)는 문서화이다. 근본 원인 분석(D)은 문제가 아직 발생하지 않았으므로 부적절하다.
1340 | An agile project manager has started working in a company that constructs shopping centers. The project manager wants to introduce some agile practices that are relevant to the project. What should the project manager do in order to gain buy-in from the various stakeholders? | Organize a meeting with relevant stakeholders explaining the benefits of agile and the practices relevant for the project. | Ask the project management office (PMO) to get buy-in from the stakeholders, because agile is an approach that differs from their previousways of working. | Send the project management plan, which includes the suggested agile practices, to the stakeholders. | Organize a meeting with a consultant to provide training to the stakeholders on agile practices. |  | A | Securing stakeholder buy-in for agile practices is essential for successful adoption. The PM should organize a focused meeting with relevant stakeholders to present the advantages of agile and demonstrate how specific practices apply to the project. This direct engagement enables the PM to address concerns, clarify doubts, and reinforce transparency and collaboration—values central to agile methodologies. Involving stakeholders early in the agile transition increases their understanding and willingness to support the new approach. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 애자일 PM이 쇼핑센터 건설 회사에서 일하기 시작했다. 이해관계자의 동의를 얻기 위해 무엇을 해야 하는가? | 관련 이해관계자와 회의를 조직하여 애자일의 이점과 관련 실무를 설명한다 | PMO에 이해관계자로부터 동의를 얻도록 요청한다 | 제안된 애자일 실무를 포함한 프로젝트 관리 계획을 이해관계자에게 보낸다 | 컨설턴트와 회의를 조직하여 이해관계자에게 애자일 실무 교육을 제공한다 |  | A | 애자일 실무에 대한 이해관계자 동의 확보가 성공적 도입에 필수적이다. PM이 직접 관련 이해관계자와 회의를 조직하여 애자일의 장점을 제시하고 시연해야 한다. PMO 요청(B)은 간접적이다. 계획 발송(C)은 설명 없는 문서이다. 컨설턴트(D)는 PM의 리더십을 대체한다.
1341 | During a sprint retrospective, the project manager notices that one of the team members does not achieve the sprint objectives on a regular basis. This team member is an experienced resource. How should the project manager properly address this situation? | Align the project goals with the team member. | Allocate another resource to support the team member. | Reassign the team member to another project. | Nominate the team member to receive agile training. |  | A | The correct answer is A. Align the project goals with the team member. Retrospectives are critical ceremonies for inspecting and adapting processes. They enable continuous improvement by identifying what worked well and what needs adjustment. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 스프린트 회고에서 PM이 팀원 중 하나가 스프린트 목표를 달성하지 못하지만 매우 협력적임을 발견한다. PM은 무엇을 해야 하는가? | 팀원과 프로젝트 목표를 정렬한다 | 팀원을 지원할 다른 자원을 배정한다 | 팀원을 다른 프로젝트에 재배정한다 | 팀원에게 애자일 교육을 받도록 지명한다 |  | A | 정답은 A이다. 팀원과 프로젝트 목표를 정렬한다. 회고는 프로세스를 검사하고 적응하는 중요한 세레모니이다. 목표 불달성의 원인이 정렬 부족일 수 있으므로 목표를 명확히 해야 한다. 추가 자원(B)은 근본 문제를 다루지 않는다. 재배정(C)은 협력적인 팀원을 잃는다. 교육(D)은 원인 파악 전에 성급하다.
1342 | A senior business stakeholder with many years of experience is pressuring an agile team to deliver most of the promised functionality to the customer 18 months in the future as opposed to multiple, incremental deliveries over the course of the 18 months. What should the project lead do next? | Work with the agile team to schedule the incremental deliveries to enable deliveryof business value sooner to the customer. | Schedule meetings with the customer to determine their ability to support multiple incremental deliveries | Provide details of the concern to the agile team and adjust their goals and release plans to conform to the stakeholder ' s request. | Work with the stakeholder to understand what the concerns are while at the same time conveying the benefits of incremental deliveries |  | D | When a senior stakeholder pressures the agile team for a single large delivery 18 months out instead of incremental deliveries, the project lead should work with the stakeholder to understand concerns while conveying the benefits of incremental deliveries. Engaging the stakeholder builds understanding and buy-in. Scheduling incremental deliveries without addressing concerns (A) ignores stakeholder input. Meeting with the customer about support capability (B) addresses logistics, not the fundamental disagreement. Adjusting goals to conform (C) surrenders agile principles. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 고위 비즈니스 이해관계자가 18개월 후 대부분의 약속된 범위를 한 번에 납품하도록 애자일 팀을 압박한다. PM은 무엇을 해야 하는가? | 비즈니스 가치를 빨리 전달하기 위해 점진적 납품 일정을 잡도록 팀과 협력한다 | 고객과 회의를 잡아 여러 점진적 납품을 지원할 능력을 결정한다 | 팀에 우려 세부사항을 제공하고 이해관계자 요구에 맞게 목표와 릴리스 계획을 조정한다 | 이해관계자와 우려를 이해하면서 동시에 점진적 납품의 가치를 전달한다 |  | D | 고위 이해관계자가 점진적 대신 한 번 대규모 납품을 압박할 때, PM은 이해관계자와 우려를 이해하면서 동시에 점진적 납품의 가치를 전달해야 한다. 쌍방향 소통이 최적의 해결을 이끈다. 팀과 일정(A)은 이해관계자 우려를 무시한다. 고객 능력 확인(B)은 간접적이다. 목표 조정(C)은 이해관계자 이해 없이 양보한다.
1343 | A project manager is leading a hybrid project funded by a time and materials (T&M) agreement. The project was completed, and the client accepted the delivery of the product. One week later, the client asked the project manager to fix two defects they found in the product. The project manager responded with an estimate of time and money and asked the client to confirm this. The client disagreed and insisted that the work should be done for free because it is a defect in the product. What should the project manager have done to prevent this? | Trained client engineers to support the product after its delivery. | Planned how the delivered product will be supported after its delivery. | Suggested a fixed-cost basis and included free bug fixes for 1 month. | Reviewed the project quality control plan with the client. |  | B | When a client disputes paying for post-delivery defect fixes on a T&M project, the project manager should have planned how the delivered product will be supported after its delivery. Post-delivery support planning establishes clear responsibilities and expectations for defect handling. Training client engineers (A) addresses capability, not contractual support terms. Suggesting fixed-cost with free bug fixes (C) changes the commercial model retroactively. Reviewing the quality control plan (D) addresses prevention, not post-delivery support. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | PM이 T&M 계약의 하이브리드 프로젝트를 이끌었다. 프로젝트는 완료되었으나 고객이 납품 후 결함 수정 비용 지불에 이의를 제기한다. PM이 이전에 무엇을 했어야 하는가? | 고객 엔지니어를 교육시켜 납품 후 제품을 지원하도록 했다 | 납품된 제품이 납품 후 어떻게 지원될지 계획했다 | 고정 비용 기반을 제안하고 1개월 무료 버그 수정을 포함했다 | 고객과 프로젝트 품질 관리 계획을 검토했다 |  | B | 고객이 T&M 프로젝트에서 납품 후 결함 수정 비용에 이의를 제기할 때, PM은 납품 후 제품 지원 방법을 미리 계획했어야 한다. 납품 후 지원 계획이 고객 기대를 관리한다. 엔지니어 교육(A)은 지원의 일부이지만 전체 계획이 아니다. 고정 비용(C)은 특정 조건이다. 품질 계획 검토(D)는 납품 후 지원을 다루지 않는다.
1344 | A product owner has indicated there is strong customer interest in adding a new set of functionalities to a product. Using agile approaches, the project manager evaluates the new functionalities of the product. What should the project manager do? | Add the functionality to the product backlog for inclusion once a change request is created and approved. | Negotiate with the product owner to determine what might be removed from the backlog that is of similar size. | Discuss with the team how this change in scope impacts development at the next retrospective to determine next steps. | Negotiate with the product owner to determine which functionality should be pushed out of the scope of the project. |  | B | The PM should negotiate with the product owner to determine what might be removed from the backlog to accommodate the new requirement. The product owner prioritizes the backlog and defines requirements, so collaboration between the team and PO ensures decisions respect agile principles while maintaining sprint commitments. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Traditional PM | 제품 책임자가 새 기능 세트에 대한 고객 관심이 강하다고 표시했다. 기존 릴리스 범위가 압박된다. PM은 무엇을 해야 하는가? | 변경 요청이 생성되고 승인되면 백로그에 기능을 추가한다 | 제품 책임자와 협상하여 유사 크기의 항목을 백로그에서 제거할 수 있는지 결정한다 | 다음 회고에서 범위 변경이 개발에 미치는 영향을 팀과 논의한다 | 제품 책임자와 협상하여 어떤 기능을 범위에서 제외할지 결정한다 |  | B | 새 기능 추가로 릴리스 범위가 압박될 때, PM은 제품 책임자와 협상하여 유사 크기의 항목을 백로그에서 제거할지 결정해야 한다. 제품 책임자가 백로그 우선순위와 요구사항을 정의한다. 변경 요청(A)은 애자일에서 과도한 절차이다. 회고 논의(C)는 시기가 늦다. 범위 제외(D)는 B와 유사하나 '유사 크기'가 아닌 일방적 제거이다.
1345 | An equipment vendor will implement a new production line for a client company. The year-long project will include 2- to 4-month long iterations; however, the client's project manager has no agile experience. How should the project manager ensure that the client is effectively represented in the daily meetings? | Recommend agile training programs that best suit the client project manager ' s schedule. | Realign the project to a predictive approach to ensure optimal collaboration between the teams. | Propose a session tor essential agile Knowledge transfer for the client team to align with the daily meeting goals | Provide the client project manager with agile best practice documents and web resources. |  | C | Ensuring effective client representation in daily meetings requires providing the client with essential agile knowledge and skills. The PM should propose a session for agile knowledge transfer, covering principles, values, practices, and tools being used in the project. This helps the client understand the purpose and benefits of daily meetings as well as their roles within them. The other options either fail to address the root cause (lack of agile knowledge) or introduce unnecessary changes or delays to the project. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 장비 벤더가 고객 회사를 위한 새 생산 라인을 구현할 예정이다. 1년 프로젝트에 2~4주 스프린트가 포함된다. 고객 PM이 애자일에 대한 지식이 없다. PM은 무엇을 해야 하는가? | 고객 PM 일정에 맞는 애자일 교육 프로그램을 추천한다 | 양 팀 간 최적 협업을 위해 프로젝트를 예측형 접근법으로 재정렬한다 | 고객 팀에 필수 애자일 지식 전달 세션을 제안하여 데일리 미팅에 맞춘다 | 고객 PM에게 애자일 모범 사례 문서와 웹 자원을 제공한다 |  | C | 고객 PM이 애자일 지식이 없을 때, PM은 필수 애자일 지식 전달 세션을 제안해야 한다. 효과적인 고객 참여를 위해 필요한 지식과 기술을 제공한다. 교육 추천(A)은 간접적이다. 예측형 재정렬(B)은 프로젝트 접근법을 바꾼다. 문서 제공(D)은 자기 학습에 의존하여 효과가 제한적이다.
1346 | A team member mentions to the scrum master that the user stories are too long. The team member believes this may be the cause of the team's inability to deliver value for stakeholders. What should the scrum master do? | Review the user stories with the team and ask the product owner to break them down into more manageable units. | Review the user stories with the stakeholders and ask the product owner to break them down into more manageable units. | Ask the team member to suggest using shorter user stories to the product owner so that the next sprint can move faster. | Ask all the team members for their views about using shorter user stories so that value can be created for stakeholders. |  | A | When a team member believes user stories are too long and it is preventing value delivery, the scrum master should review the user stories with the team and ask the product owner to break them into more manageable units. Collaborative refinement right-sizes stories. Reviewing with stakeholders (B) involves the wrong audience. Asking the individual to suggest changes alone (C) misses team input. Asking all members for views (D) discusses without action. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 팀원이 스크럼 마스터에게 사용자 스토리가 너무 길다고 언급한다. 가치 전달을 방해한다고 믿는다. 스크럼 마스터는 무엇을 해야 하는가? | 팀과 사용자 스토리를 검토하고 제품 책임자에게 더 관리 가능한 크기로 분해하도록 요청한다 | 이해관계자와 사용자 스토리를 검토하고 제품 책임자에게 분해하도록 요청한다 | 팀원에게 더 짧은 스토리 사용을 제품 책임자에게 제안하도록 요청한다 | 모든 팀원에게 더 짧은 스토리 사용에 대한 의견을 요청한다 |  | A | 사용자 스토리가 너무 길어 가치 전달을 방해할 때, 스크럼 마스터는 팀과 함께 검토하고 제품 책임자에게 분해를 요청해야 한다. 팀 참여가 실무적 관점을 제공한다. 이해관계자 검토(B)는 팀 대신 외부를 참여시킨다. 개인 제안(C)은 팀 협력이 아니다. 전체 의견(D)은 행동 없는 토론이다.
1347 | A project manager implementing a hybrid project is dealing with multiple stakeholders in a rapidly changing business environment. How should the project manager ensure that the needs of stakeholders are consistently met? | Identify all the critical stakeholders during the project initiation. | Assign one team member to one stakeholder to ensure that the responsible team member is conversant with the needs of the stakeholder. | Use iterative life cycles involving stakeholders to enable the team to improve the product end result through successive prototypes. | Add more iterative techniques to improve stakeholder learning. |  | C | In a hybrid project with multiple stakeholders in a rapidly changing environment, the project manager should use iterative life cycles involving stakeholders to enable the team to improve the product through successive prototypes. This ensures continuous feedback incorporation and adaptive development. Identifying critical stakeholders at initiation only (A) is insufficient for ongoing engagement. Assigning one team member per stakeholder (B) may create silos. Adding more iterative techniques (D) is vague without specifying stakeholder involvement. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Scope | Executing | Focus on Value | Direct and Manage Project Work | Hybrid/Tailoring | 하이브리드 프로젝트의 PM이 급변하는 비즈니스 환경에서 다수의 이해관계자를 다루고 있다. PM은 무엇을 해야 하는가? | 프로젝트 착수 시 모든 핵심 이해관계자를 식별한다 | 한 팀원을 한 이해관계자에 배정하여 책임 팀원이 요구사항에 정통하도록 한다 | 이해관계자를 참여시키는 반복적 수명주기를 사용하여 팀이 최종 결과를 개선하도록 한다 | 이해관계자 학습을 개선하기 위해 더 많은 반복 기법을 추가한다 |  | C | 급변하는 환경에서 다수의 이해관계자가 있는 하이브리드 프로젝트에서, PM은 이해관계자를 참여시키는 반복적 수명주기를 사용해야 한다. 반복적 참여가 지속적 피드백과 적응을 가능하게 한다. 착수 시 식별(A)은 초기 조치일 뿐이다. 1:1 배정(B)은 비효율적이다. 기법 추가(D)는 모호하다.
1348 | A company's project management office (PMO) has started to implement iterative tools. A project manager is starting a new project and has identified an opportunity to use the iterative tools. One of the senior managers is concerned about this modified framework as it is fairly new to the company. What should the project manager do first? | Organize individual sessions with the stakeholders to build awareness and trust in the new framework | Look for external training on the new framework to eliminate the risk of low engagement from stakeholders. | Send documentation to the senior manager about the advantages of the new framework | Escalate the senior manager ' s concern to the project sponsor and distribute the status to the team |  | C | The PM should communicate effectively with stakeholders—especially concerned senior managers—by sending documentation about the new framework's advantages: increased flexibility, faster feedback, improved quality, and reduced risk. The documentation should explain alignment with project objectives and invite feedback. Individual sessions (A) should follow initial documentation. External training (B) may be unnecessary given PMO resources. Escalation (D) could create unnecessary conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PMO가 반복적 도구를 도입하기 시작했다. 시니어 매니저가 새 프레임워크에 우려를 표명한다. PM은 무엇을 해야 하는가? | 이해관계자와 개별 세션을 조직하여 새 프레임워크에 대한 인식과 신뢰를 구축한다 | 이해관계자의 낮은 참여 리스크를 제거하기 위해 외부 교육을 찾는다 | 시니어 매니저에게 새 프레임워크의 장점에 대한 문서를 보낸다 | 시니어 매니저의 우려를 프로젝트 스폰서에게 에스컬레이션하고 팀에 상태를 배포한다 |  | C | 시니어 매니저가 새 프레임워크에 우려할 때, PM은 새 프레임워크의 장점에 대한 문서를 보내야 한다. 이점 문서화가 명확한 커뮤니케이션을 제공한다. 개별 세션(A)은 효과적이지만 문서가 우선이다. 외부 교육(B)은 시기상조이다. 에스컬레이션(D)은 과도하다.
1349 | A project manager wants to assign a junior engineer to a new project. In past projects, the engineer showed initiative to take on complex tasks and solve problems in innovative ways without any need for encouragement. However, the engineer declines the project manager's invitation to join the new project. What is the most likely reason for the engineer's refusal to work on the project? | The engineer did not feel welcome or enjoy working with the other project team members. | The project manager did not sufficiently support and recognize the engineer ' s professional growth. | The engineer has "project burnout " from working long hours and solving difficult problems. | The project manager did not follow the normal hiring process with the engineer ' s functional manager. |  | C | Project burnout—physical and emotional exhaustion from prolonged stress and overwork—is the most likely reason a previously motivated engineer would decline a new project assignment. Recognizing and addressing burnout is essential for maintaining a healthy and productive team environment. The PM should investigate the engineer's situation and consider workload redistribution, recovery time, or other support measures. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 주니어 엔지니어를 새 프로젝트에 배정하려 한다. 이전 프로젝트에서 주도성을 보였지만 이번에는 거절했다. 가장 가능한 이유는? | 엔지니어가 다른 프로젝트 팀원과 일하는 것을 즐기지 않았다 | PM이 엔지니어의 전문적 성장을 충분히 지원하고 인정하지 않았다 | 엔지니어가 장시간 근무와 어려운 문제 해결로 '프로젝트 번아웃'을 겪고 있다 | PM이 엔지니어의 기능 관리자와 정상적인 채용 프로세스를 따르지 않았다 |  | C | 이전에 동기부여된 엔지니어가 새 프로젝트를 거절하는 가장 가능한 이유는 프로젝트 번아웃이다. 장기적 스트레스와 과로로 인한 신체적, 감정적 소진이 원인이다. 환영받지 못함(A)은 근거 없다. 성장 미지원(B)은 주도성과 모순된다. 채용 프로세스(D)는 배정 거절과 무관하다.
1350 | Due to organizational changes, several key stakeholders are replaced by new ones in the middle of a project. As a result, numerous new requirements are raised. What should the project manager do to ensure success of the project? | Review and prioritize new requirements with stakeholders to determine which change requests are needed. | Seek immediate approval to amend the project timeline and budget in order to deliver all new requirements | Emphasize to the new stakeholders that new requirements are not allowed at this stage of the project | Escalate the issue to the project sponsor and seek support to keep the original requirements. |  | A | When key stakeholders are replaced and numerous new requirements arise mid-project, the project manager should review and prioritize new requirements with stakeholders to determine which change requests are needed. Collaborative prioritization ensures alignment while managing scope through formal change control. Emphasizing that new requirements are not allowed (C) is rigid and alienating. Seeking immediate approval for timeline and budget changes (B) accepts all changes without analysis. Escalating to the sponsor to keep original requirements (D) resists change. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Agile General Practices | Business Environment | Support Organizational Change | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 조직 변경으로 주요 이해관계자가 교체되어 많은 새 요구사항이 발생했다. PM은 무엇을 해야 하는가? | 이해관계자와 새 요구사항을 검토하고 우선순위를 정하여 어떤 변경 요청이 필요한지 결정한다 | 모든 새 요구사항을 전달하기 위해 프로젝트 일정과 예산 수정 승인을 즉시 요청한다 | 새 이해관계자에게 이 단계에서는 새 요구사항이 허용되지 않음을 강조한다 | 프로젝트 스폰서에게 이슈를 에스컬레이션하고 원래 요구사항 유지를 위한 지원을 구한다 |  | A | 주요 이해관계자 교체로 새 요구사항이 발생할 때, PM은 이해관계자와 함께 검토하고 우선순위를 정해야 한다. 협력적 우선순위 결정이 영향 기반 의사결정을 가능하게 한다. 즉시 수정(B)은 분석 없이 성급하다. 거부(C)는 관계를 훼손한다. 에스컬레이션(D)은 PM의 역할을 포기한다.
1351 | The investment committee is the authority for the approval of funding required for a business improvement project. The investment committee approved funding to complete the preliminary feasibility study. The project is on an expedited schedule, and the project manager requires interim funding to continue with the preliminary feasibility activities that must begin immediately. How should the project manager get these funds approved? | Exclude the preliminary scope from the full project scope and continue it as a new project that does not require investment committee approval. | Wait until the next investment committee meeting to submit the request and include the delay in the schedule due to work that could not start. | Submit the request to the project director for interim approval and include this approval for discussion at the next investment committee meeting. | Continue with the preliminary activities and inform the investment committee at the next monthly meeting. |  | C | When interim funding is needed on an expedited schedule, the PM should seek interim approval from an authority within the project governance structure, such as the project director. This ensures critical activities continue without delay. Once interim approval is granted, the PM should bring it to the investment committee's attention at the next formal meeting for acknowledgment and inclusion in the project's funding records. Maintaining project continuity while following governance protocols is a key PM responsibility. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 투자위원회가 비즈니스 개선 프로젝트의 자금 승인 권한이다. 다음 월례 회의 전에 임시 자금이 필요하다. PM은 무엇을 해야 하는가? | 예비 범위를 전체 프로젝트 범위에서 제외하고 투자위원회 승인이 필요 없는 새 프로젝트로 계속한다 | 다음 투자위원회 회의까지 기다려 요청을 제출하고 지연을 일정에 포함한다 | 프로젝트 디렉터에게 임시 승인을 요청하고 다음 월례 회의에서 논의에 포함한다 | 예비 활동을 계속하고 다음 월례 회의에서 투자위원회에 알린다 |  | C | 긴급 임시 자금이 필요할 때, PM은 프로젝트 거버넌스 구조 내 권한(프로젝트 디렉터)에게 임시 승인을 구해야 한다. 이는 중요 활동의 연속성을 보장한다. 범위 제외(A)는 조작적이다. 대기(B)는 지연을 야기한다. 승인 없이 계속(D)은 거버넌스를 무시한다.
1352 | During a project gate review meeting, it is identified that one of the project deliverables will require corrective actions to meet the project quality requirements. What should the project manager do first? | Submit a change request to update the project quality requirements for the involvedproject deliverable. | Identify the resources that were responsible for the deliverable and request a teamdevelopment plan. | Update the issue log, identify the involved stakeholders, and assign resources to thecorrective actions. | Update the risk register and implement the approved risk response plan for qualitydeviations. |  | C | When a project deliverable requires corrective actions to meet quality requirements, the project manager should first update the issue log, identify the involved stakeholders, and assign resources to the corrective actions. This ensures the quality issue is tracked and resolved systematically. Submitting a change request to lower quality requirements (A) is premature and may not be appropriate. Identifying responsible resources and requesting a development plan (B) focuses on personnel rather than the immediate corrective action. Updating the risk register and implementing a risk response (D) treats this as a risk rather than an identified quality issue that needs direct corrective action. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 프로젝트 게이트 리뷰 회의에서 인도물 중 하나가 품질 요구사항 충족을 위해 시정 조치가 필요하다고 식별되었다. PM은 무엇을 해야 하는가? | 관련 프로젝트 인도물의 품질 요구사항을 업데이트하는 변경 요청을 제출한다 | 인도물을 담당한 자원을 식별하고 팀 개발 계획을 요청한다 | 이슈 로그를 업데이트하고 관련 이해관계자를 식별하고 시정 조치에 자원을 할당한다 | 리스크 등록부를 업데이트하고 품질 편차에 대한 승인된 리스크 대응 계획을 실행한다 |  | C | 인도물이 품질 요구사항 충족을 위해 시정 조치가 필요할 때, PM은 이슈 로그를 업데이트하고 이해관계자를 식별하고 자원을 할당해야 한다. 체계적 이슈 관리가 적절한 해결을 보장한다. 변경 요청(A)은 요구사항을 낮추는 것이다. 자원 책임(B)은 비난에 초점을 맞춘다. 리스크 등록부(D)는 이미 발생한 이슈에는 부적절하다.
1353 | A project manager has taken over an existing project. According to the previous project manager, the project is on track and within budget. However, stakeholders are unhappy with the recent progress report since the metrics show that the project is delayed and the cost is higher than expected. What should the project manager do? | Conduct an earned value analysis (EVA) | Schedule training for project team members | Submit a change request to the change control board (CCB) | Schedule a meeting with the previous project manager |  | A | When taking over a project reported as on-track but stakeholders see metrics showing delays and cost overruns, the project manager should conduct an earned value analysis. EVA provides objective performance measurement. Submitting a change request (B) is premature without understanding the situation. Scheduling training (C) is unrelated. Meeting with the previous PM (D) may help but EVA provides factual data. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | PM이 기존 프로젝트를 인수했다. 이전 PM에 따르면 순조롭지만 이해관계자는 지연과 비용 초과를 보여주는 지표를 보고 있다. PM은 무엇을 해야 하는가? | 획득가치분석(EVA)을 수행한다 | 프로젝트 팀원을 위한 교육을 일정 잡는다 | 변경통제위원회(CCB)에 변경 요청을 제출한다 | 이전 PM과 회의를 일정 잡는다 |  | A | 프로젝트가 순조롭다고 보고되었지만 이해관계자가 지연과 비용 초과 지표를 볼 때, PM은 획득가치분석을 수행해야 한다. EVA가 일정과 비용 성과에 대한 객관적 데이터를 제공한다. 교육(B)은 문제와 무관하다. 변경 요청(C)은 분석 전에 성급하다. 이전 PM 회의(D)는 주관적 정보만 제공한다.
1354 | A project, which has its execution phase planned in an iterative way, has the following metrics for the first three iterations. One of the requirements for the project states that in order to get payment authorized for the project, neither the SPI nor the CPI can be less than 0.95. What should the project manager do in iteration 4 to ensure the project is in compliance with the requirement? | Fast tracking | Earned schedule | Earned value | Schedule crashing |  | D | When a project requires SPI and CPI of at least 0.95 for payment authorization, the project manager should use schedule crashing in iteration 4 to improve performance. Crashing adds resources to shorten duration and improve both indices. Fast-tracking (A) overlaps activities but increases risk. Earned schedule (B) and earned value (C) are measurement methods, not improvement techniques. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 반복적으로 계획된 프로젝트에서 SPI와 CPI가 0.95 이상이어야 결제가 승인된다. 4번째 이터레이션에서 성과를 개선하기 위해 무엇을 사용해야 하는가? | 패스트 트래킹 | 획득 일정 | 획득 가치 | 일정 크래싱 |  | D | SPI와 CPI가 0.95 이상이어야 할 때, PM은 일정 크래싱을 사용해야 한다. 크래싱은 핵심 활동에 자원을 추가하여 기간을 단축한다. 패스트 트래킹(A)은 활동을 병렬화하지만 리스크가 높다. 획득 일정(B)은 측정이지 개선이 아니다. 획득 가치(C)도 분석 도구이다.
1355 | A project manager has received feedback from stakeholders regarding poor communication about project progress. Weekly status reports were provided to the project management office (PMO), and the standard communications management plan was followed. What should the project manager do? | Distribute hard copies of status reports and confirm that messages were read. | Ensure that all of the complaining stakeholders are on the distribution list. | Create a change request for implementing an online collaboration tool. | Perform a root cause analysis (RCA) of the existing communication approach. |  | D | When stakeholders complain about poor communication despite following the standard communications plan, the project manager should perform a root cause analysis of the existing communication approach. RCA identifies systemic issues beyond surface symptoms. Distributing hard copies (A) adds volume, not clarity. Ensuring complainers are on the distribution list (B) assumes the list is the problem. Creating a change request for a collaboration tool (C) proposes solutions before diagnosis. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Embed Quality | Manage Communications | Traditional PM | 이해관계자가 프로젝트 진행에 대한 커뮤니케이션이 부족하다고 피드백했다. 주간 보고가 표준 계획대로 발송되고 있다. PM은 무엇을 해야 하는가? | 상태 보고서의 인쇄본을 배포하고 메시지가 읽혔는지 확인한다 | 불만 이해관계자 모두가 배포 목록에 있는지 확인한다 | 온라인 협업 도구 도입을 위한 변경 요청을 생성한다 | 기존 커뮤니케이션 접근법에 대한 근본 원인 분석(RCA)을 수행한다 |  | D | 표준 커뮤니케이션 계획을 따르는데도 이해관계자가 불만일 때, PM은 기존 커뮤니케이션 접근법에 대한 근본 원인 분석을 수행해야 한다. RCA가 실패의 근본 원인을 식별한다. 인쇄본(A)은 근본 문제를 다루지 않는다. 배포 목록(B)은 한 가지 원인만 다룬다. 협업 도구(C)는 원인 파악 없이 해결을 시도한다.
1356 | A project manager is leading a project team composed of members with varying levels of knowledge and experience. Some are experts and some have less than 1 year of experience. The project schedule was approved by the steering committee. What should the project manager do? | Ask each experienced member to be the mentor to one of the less-experienced members. | Ask the resource manager to replace the less-experienced members with more experienced team members. | Ask the less-experienced members to perform tasks exactly as they are instructed by the experienced members. | Ask the more experienced members to review all of the tasks performed by the less- experienced members. |  | A | When a project team has varying experience levels with an approved schedule, the project manager should ask each experienced member to mentor one of the less-experienced members. Mentorship builds capability while maintaining productivity. Replacing less-experienced members (B) is impractical. Having less-experienced members follow instructions exactly (C) limits growth. Having experienced members review all tasks (D) is micromanaging. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | PM이 다양한 지식과 경험 수준의 팀원으로 구성된 팀을 이끌고 있다. 승인된 일정이 있다. PM은 무엇을 해야 하는가? | 각 경험 있는 팀원에게 경험이 적은 팀원 한 명의 멘토가 되도록 요청한다 | 자원 관리자에게 경험이 적은 팀원을 더 경험 있는 팀원으로 교체하도록 요청한다 | 경험이 적은 팀원에게 경험 있는 팀원의 지시대로 정확히 작업을 수행하도록 요청한다 | 경험 있는 팀원에게 경험이 적은 팀원이 수행한 모든 작업을 검토하도록 요청한다 |  | A | 다양한 경험 수준의 팀이 있을 때, PM은 경험 있는 팀원에게 멘토 역할을 요청해야 한다. 멘토십이 역량을 구축하고 지식을 전달한다. 교체(B)는 비현실적이고 비용이 많다. 지시대로 수행(C)은 학습을 제한한다. 모든 작업 검토(D)는 병목을 만든다.
1357 | A project manager is tasked with developing a coaching model to support and recognize team members' growth. What should the project manager consider when defining their coaching strategy? | Established patterns of communication | Project team ' s shared objectives | Individual and personal objectives | Organization ' s strategic goals |  | C | When developing a coaching model to support and recognize team members' growth, the project manager should consider individual and personal objectives. Personalized coaching maximizes effectiveness. Established communication patterns (A) support coordination but not individual growth. Shared team objectives (B) address collective goals. Organizational strategic goals (D) are too broad for individual coaching. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Finance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 팀원의 성장을 지원하고 인정하는 코칭 모델을 개발하는 임무를 받았다. PM은 무엇을 고려해야 하는가? | 확립된 커뮤니케이션 패턴 | 프로젝트 팀의 공유 목표 | 개인 및 개인적 목표 | 조직의 전략적 목표 |  | C | 팀원 성장을 지원하는 코칭 모델을 개발할 때, PM은 개인 및 개인적 목표를 고려해야 한다. 개인화된 코칭이 효과를 극대화한다. 커뮤니케이션 패턴(A)은 코칭 초점이 아니다. 공유 목표(B)는 팀 수준이지 개인이 아니다. 전략적 목표(D)는 조직 수준이다.
1358 | A proof of concept for a proposed solution was conducted during the project implementation, and it was determined that the current technology cannot support it. What should the project manager do next? | Use a root cause analysis (RCA) technique like Ishikawa diagrams to determine why the current technology is not supportive. | Add this item to the issue log and explore possible resolution options with the team. | Ask another team member to redo the proof of concept using the current technology to ensure It is truly not an option. | Update the risk register indicating that a new technology must be chosen by the team lead. |  | B | When a proof of concept determines that current technology cannot support the proposed solution, the project manager should add the item to the issue log and explore possible resolution options with the team. Collaborative problem-solving explores alternatives. Using root cause analysis (A) investigates why but does not explore solutions. Asking another team member to redo the POC (C) duplicates effort. Updating the risk register (D) passes responsibility without exploring options. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 구현 중 개념 증명에서 현재 기술이 제안 솔루션을 지원할 수 없다고 판단되었다. PM은 무엇을 해야 하는가? | 이시카와 다이어그램과 같은 RCA 기법을 사용하여 현재 기술이 왜 작동하지 않는지 결정한다 | 이슈 로그에 항목을 추가하고 팀과 가능한 해결 옵션을 탐색한다 | 다른 팀원에게 현재 기술로 개념 증명을 다시 하도록 요청한다 | 팀 리더가 새 기술을 선택해야 함을 나타내는 리스크 등록부를 업데이트한다 |  | B | 개념 증명에서 현재 기술이 솔루션을 지원할 수 없다고 판단될 때, PM은 이슈 로그에 추가하고 팀과 해결 옵션을 탐색해야 한다. 문서화와 팀 협력이 최적의 해결을 이끈다. RCA(A)는 '왜' 작동하지 않는지보다 '무엇을' 해야 하는지가 중요하다. 재실시(C)는 시간 낭비이다. 리스크 등록부(D)는 이미 발생한 이슈에 부적절하다.
1359 | A project manager is managing a project with a cost performance index (CPI) of 1.05 that is trending downward. To maintain on-time completion, the scrum master needs to add 30 additional team members in the next month to enable more sprints. The project manager is concerned because the schedule performance index (SPI) is 1.0. What is the first step the project manager should take? | Inform the project team that since the CPI is trending downward, there are funds available to expand the team. | Engage with the human resources (HR) representative to begin selecting candidates for the 30 open positions. | Meet with the project team to forecast the SPI trend to determine if there are funds available to pay the 30 team members. | Quantify the cost for the 30 team members and determine if there is budget available to fund the expanded team. |  | D | When the CPI is 1.05 trending downward and the scrum master wants to add 30 team members with SPI at 1.0, the project manager should first quantify the cost for the 30 team members and determine if budget is available. Data-driven financial assessment must precede staffing decisions. Informing the team about available funds (A) misinterprets the situation. Engaging HR to select candidates (B) is premature before budget confirmation. Forecasting SPI trends (C) addresses schedule but not the cost question. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | CPI가 1.05이나 하락 추세이다. 스크럼 마스터가 SPI 1.0으로 30명 팀원 추가를 원한다. PM은 무엇을 먼저 해야 하는가? | CPI가 하락 추세이므로 범위 확장에 사용 가능한 자금이 있다고 팀에 알린다 | HR 담당자와 30개 빈 자리의 후보 선정을 시작한다 | SPI 추세를 예측하여 추가 인력 비용 지불 자금이 있는지 결정하기 위해 팀과 회의한다 | 30명 팀원의 비용을 정량화하고 자금이 가용한지 결정한다 |  | D | CPI 1.05 하락 추세에서 30명 추가를 요청받을 때, PM은 먼저 비용을 정량화하고 예산 가용성을 결정해야 한다. 재무적 실행 가능성이 결정의 기초이다. 자금 있다고 알림(A)은 분석 없는 추측이다. HR 선정(B)은 예산 확인 전에 성급하다. SPI 예측(C)은 비용 분석이 아니다.
1360 | A vendor project manager and team are implementing a software solution across the organization. A customer stakeholder who was not present during the sales process is demanding that the team implement requirements that are out of scope without adding additional cost to the project. What should the project manager do next? | Refer the stakeholder to the delivery specifications in the statement of work (SOW). | Escalate the issue of the additional requirements to the executive leadership team. | Implement all the requirements the customer has requested. | Adjust the scope baseline and schedule baseline accordingly. |  | A | When a customer stakeholder demands out-of-scope requirements without additional cost, the project manager should refer to the delivery specifications in the statement of work. The SOW defines project scope boundaries. Escalating to executives (B) is premature. Implementing all requests (C) leads to scope creep. Adjusting baselines (D) bypasses change control. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 벤더 PM과 팀이 조직 전체에 소프트웨어 솔루션을 구현 중이다. 고객 이해관계자가 추가 비용 없이 범위 외 요구사항을 요구한다. PM은 무엇을 해야 하는가? | 작업기술서(SOW)의 납품 사양을 이해관계자에게 참조시킨다 | 추가 요구사항 이슈를 경영진 리더십 팀에 에스컬레이션한다 | 고객이 요청한 모든 요구사항을 구현한다 | 범위 기준선과 일정 기준선을 적절히 조정한다 |  | A | 고객이 추가 비용 없이 범위 외 요구사항을 요구할 때, PM은 작업기술서의 납품 사양을 참조시켜야 한다. SOW가 프로젝트 범위와 인도물을 정의한다. 에스컬레이션(B)은 직접 대응 전에 과도하다. 모두 구현(C)은 범위 확장이다. 기준선 조정(D)은 무상 변경을 수용한다.
1361 | A project manager is reviewing a draft of the project charter with key stakeholders. During the meeting, a conflict occurs between the sponsor and the product owner. How should the project manager deal with the situation? | Continue the meeting and ask the project sponsor and product owner to take their discussion offline. | Continue the meeting and use facilitation techniques to improve communication within the team. | Postpone the meeting and invite a subject matter expert (SME) to join the next meeting. | Postpone the meeting and ask the project sponsor and product owner to take their discussion offline. |  | B | When a conflict occurs between the sponsor and product owner during a charter review meeting, the project manager should continue the meeting and use facilitation techniques to improve communication. Facilitation resolves conflict constructively. Asking them to take it offline during the meeting (A) delays resolution. Postponing for an SME (C) avoids the interpersonal issue. Postponing and asking them to discuss offline (D) also delays. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | PM이 주요 이해관계자와 프로젝트 헌장 초안을 검토 중이다. 스폰서와 제품 책임자 간 갈등이 발생했다. PM은 무엇을 해야 하는가? | 회의를 계속하고 스폰서와 제품 책임자에게 별도로 논의하도록 요청한다 | 회의를 계속하고 퍼실리테이션 기법을 사용하여 팀 내 커뮤니케이션을 개선한다 | 회의를 연기하고 SME를 다음 회의에 초대한다 | 회의를 연기하고 스폰서와 제품 책임자에게 별도 논의하도록 요청한다 |  | B | 헌장 검토 회의에서 스폰서와 제품 책임자 간 갈등이 발생할 때, PM은 회의를 계속하고 퍼실리테이션 기법을 사용해야 한다. 즉각적 퍼실리테이션이 생산적 대화를 이끈다. 별도 논의(A)는 회의 진행을 방해한다. 회의 연기(C, D)는 진행을 지연시킨다.
1362 | A company made several changes recently, which resulted in a positive change in the company culture. A project manager was just assigned to report to a new project supervisor whose leadership style is about getting things done quickly regardless of employee and operational impacts. Some employees are raising concerns about this. What should the project manager do? | Revisit the company ' s organizational culture. | Clarify expectations by explaining the company culture with the supervisor. | Instruct the employees to listen to the supervisor. | Ask senior management to move the supervisor to a different project. |  | B | The PM should clarify expectations by explaining the company culture to the new supervisor. This means communicating the positive cultural changes, how they affect project objectives and stakeholder satisfaction, and seeking to understand the supervisor's leadership style. Finding common ground that respects both organizational culture and supervisory authority is more constructive than requesting supervisor transfer, revisiting culture, or simply directing employees to comply. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 회사가 최근 긍정적 문화 변화를 이뤘다. 새 감독자가 이전 문화대로 행동하여 팀원들이 불만이다. PM은 무엇을 해야 하는가? | 회사의 조직 문화를 재검토한다 | 감독자에게 회사 문화를 설명하여 기대를 명확히 한다 | 직원들에게 감독자의 말을 듣도록 지시한다 | 고위 경영진에게 감독자를 다른 프로젝트로 이동하도록 요청한다 |  | B | 새 감독자가 이전 문화대로 행동할 때, PM은 감독자에게 회사 문화를 설명하여 기대를 명확히 해야 한다. 명확한 소통이 행동 변화를 촉진한다. 문화 재검토(A)는 문제를 다루지 않는다. 복종 지시(C)는 문제를 악화시킨다. 이동(D)은 이해 기회 없이 과도하다.
1363 | A project team member complained to the project manager that they are not sure if they are working on the latest requirements document because it was emailed to them about one week ago. They mentioned that, in the past, they worked on a document for more than 20 hours only to find out later that another team member had already updated that same document but did not send them the latest revisions. What should the project manager do to prevent this situation in the future? | Restrict team members from sending the requirements documents via email | Encourage better team communication by positioning team members closer together. | Update the communications management plan to ensure correct delivery of the latest version | Implement a project management information system (PMIS) |  | D | The PM should implement a project management information system (PMIS) to prevent document version control issues. A PMIS provides tools for gathering, integrating, and disseminating project information—ensuring documents are updated, controlled, and shared consistently. It also facilitates collaboration and reduces the risk of errors, conflicts, and rework from outdated documents. Physical proximity (A) doesn't solve document management. Updating the communications plan (B) lacks implementation tools. Restricting email (C) limits accessibility without providing alternatives. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀원이 PM에게 최신 요구사항으로 작업하고 있는지 확실하지 않다고 불만을 제기했다. PM은 무엇을 해야 하는가? | 팀원이 이메일로 요구사항 문서를 보내는 것을 제한한다 | 팀원을 더 가까이 배치하여 팀 커뮤니케이션을 개선한다 | 커뮤니케이션 관리 계획을 업데이트하여 최신 버전의 올바른 전달을 보장한다 | 프로젝트 관리 정보 시스템(PMIS)을 구현한다 |  | D | 문서 버전 관리 문제를 방지하려면, PM은 PMIS를 구현해야 한다. PMIS가 프로젝트 정보의 수집, 통합, 배포를 위한 도구를 제공한다. 이메일 제한(A)은 부분적 해결이다. 가까이 배치(B)는 물리적 해결이다. 커뮤니케이션 계획(C)은 시스템이 아닌 계획 변경이다.
1364 | An experienced project manager has never managed an agile project until now. Due to the uncertainty of the project, the project manager is struggling with the definition of the project scope and is taking a long time trying to define it. What should the project manager do? | Start executing the project as the scope will be defined and redefined throughout the project. | Schedule a daily project definition meeting with the team to define the project scope before starting the execution. | Submit a change request to leverage previous experience and manage the project using a predictive approach, | Obtain partial approval from the product owner to baseline the project scope plan before starting the execution. |  | A | When an experienced PM struggles to define scope for an uncertain agile project, they should start executing the project as the scope will be defined and redefined throughout the project. Agile embraces evolving scope through iterative delivery. Scheduling daily scope definition meetings (B) over-plans before execution. Submitting a change request for predictive approach (C) abandons agile's flexibility. Obtaining partial approval to baseline scope (D) contradicts the agile approach to evolving scope. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 경험 많은 PM이 처음으로 애자일 프로젝트를 관리한다. 프로젝트 불확실성 때문에 범위 정의에 어려움을 겪는다. PM은 무엇을 해야 하는가? | 범위가 프로젝트 전반에 걸쳐 정의되고 재정의될 것이므로 프로젝트 실행을 시작한다 | 프로젝트 범위를 정의하기 위해 팀과 일일 프로젝트 정의 회의를 일정 잡는다 | 이전 경험을 활용하여 예측형 접근법으로 프로젝트를 관리하는 변경 요청을 제출한다 | 프로젝트 범위 계획을 기준선화하기 위해 제품 책임자의 부분 승인을 얻는다 |  | A | 불확실성이 높은 애자일 프로젝트에서 범위 정의가 어려울 때, PM은 실행을 시작해야 한다. 애자일은 점진적 발견을 수용하며 범위는 프로젝트 전반에 걸쳐 정의되고 재정의된다. 일일 정의 회의(B)는 과도하다. 예측형 변경(C)은 애자일을 포기한다. 부분 승인(D)은 애자일 원칙에 반한다.
1365 | A project manager is working on a project that has strict deadlines and budget restrictions. The project manager realizes that in order to win the bid, the company submitted a significantly lower bid than their local competitors, leaving a thin profit margin. The client is constantly submitting change requests, and unfortunately, these change requests are stretching both the schedule and the budget. What should the project manager do? | Escalate the issue to senior management | Instruct the team to accommodate the changes to the project | Negotiate the impact of these changes with the client | Review the project charter to identify the agreed scope |  | C | When a thin-margin project faces constant client change requests stretching schedule and budget, the project manager should negotiate the impact of these changes with the client. Impact negotiation ensures changes are analyzed, communicated, and managed through formal processes. Escalating to senior management (A) implies inability to manage. Instructing the team to accommodate changes (B) bypasses change control. Reviewing the project charter (D) does not address ongoing change management. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | PM이 엄격한 일정과 예산 제약의 프로젝트를 진행 중이다. 고객의 끊임없는 변경 요청이 일정과 예산을 늘린다. PM은 무엇을 해야 하는가? | 고위 경영진에게 이슈를 에스컬레이션한다 | 팀에게 프로젝트 변경을 수용하도록 지시한다 | 이러한 변경의 영향을 고객과 협상한다 | 합의된 범위를 식별하기 위해 프로젝트 헌장을 검토한다 |  | C | 좁은 마진의 프로젝트에서 고객 변경 요청이 계속될 때, PM은 변경의 영향을 고객과 협상해야 한다. 영향 협상이 고객의 기대와 프로젝트 제약을 균형 있게 한다. 에스컬레이션(A)은 직접 협상 전에 과도하다. 수용 지시(B)는 프로젝트를 위험에 빠뜨린다. 헌장 검토(D)는 정보이지 행동이 아니다.
1366 | A company is moving to a hybrid approach and conducted capacity activities for all of the project managers. During these capacity-building activities, the focus was on agile approaches and team facilitation skills. When starting the implementation phase, the project managers faced issues motivating the newly hired agile staff. Why are the project managers having issues motivating the agile staff? | The agile staff is not used to being led by a project manager. | The capacity building activities missed the servant leadership concept transfer. | Transitional periods normally cause this type of problem. | Project managers are expected to become coaches in agile teams. |  | D | When project managers trained in agile approaches and facilitation have trouble motivating newly hired agile staff during a hybrid transition, the issue is that project managers are expected to become coaches in agile teams. Agile emphasizes servant leadership and coaching over command and control. Agile staff not being used to PMs (A) is a symptom, not the cause. Transitional periods causing problems (C) is too generic. Missing servant leadership concept transfer (B) is close but the broader answer is the coaching role expectation. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Hybrid/Tailoring | 회사가 하이브리드 접근법으로 전환 중이며 모든 PM에게 역량 강화 활동을 실시했다. 새로 고용된 애자일 직원에게 동기 부여가 어렵다. 이유는? | 애자일 직원이 PM의 리더십에 익숙하지 않다 | 역량 강화 활동에서 서번트 리더십 개념 전달이 누락되었다 | 전환 기간에는 일반적으로 이런 유형의 문제가 발생한다 | PM이 애자일 팀에서 코치가 되어야 한다 |  | D | PM이 애자일 접근법과 퍼실리테이션 훈련을 받았지만 새 애자일 직원 동기 부여에 어려움을 겪는 이유는, PM이 애자일 팀에서 코치가 되어야 하기 때문이다. 애자일에서 리더십은 지시가 아닌 코칭이다. 익숙하지 않음(A)은 원인이 아닌 증상이다. 서번트 리더십 누락(B)은 교육 문제이지 역할 문제가 아니다. 전환 기간(C)은 일반적 변명이다.
1367 | A project manager is executing a project where an external vendor will provide some deliverables. After awarding the contract to the vendor, the project manager is informed that the vendor is running behind schedule on a separate project. Finding another vendor will exceed the budget. What should the project manager update first? | Issue log | Stakeholder engagement plan | Risk register | Lessons learned register |  | A | The PM should update the issue log first when a vendor is running behind schedule on a separate project, as this situation presents an immediate issue affecting schedule, cost, and quality. The issue log documents the problem, assigns ownership, and tracks resolution status. Lessons learned (B) capture insights after resolution. The stakeholder engagement plan (C) may need updating if the issue affects stakeholder expectations. The risk register (D) should be updated if the issue triggers new risks—but documenting the issue comes first. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | PM이 외부 벤더가 인도물을 제공하는 프로젝트를 실행 중이다. 벤더가 별도 프로젝트에서 일정이 뒤처지고 있다. PM은 어떤 문서를 먼저 업데이트해야 하는가? | 이슈 로그 | 이해관계자 참여 계획 | 리스크 등록부 | 교훈 등록부 |  | A | 벤더가 별도 프로젝트에서 일정이 뒤처지고 있을 때, PM은 먼저 이슈 로그를 업데이트해야 한다. 이 상황은 일정, 비용, 품질에 영향을 미치는 즉각적 이슈이다. 이해관계자 참여 계획(B)은 커뮤니케이션 관련이다. 리스크 등록부(C)는 잠재적 사건용이지 현재 이슈가 아니다. 교훈(D)은 미래 참고용이다.
1368 | A large and complex project is comprised of multiple regions. The estimate to complete (ETC) work is assumed to be performed at the same cumulative cost performance index (CPI) as that incurred by the project to date. As of now, the earned value (EV) is 145 person/day, the planned value (PV) is 145 person/day, the actual cost (AC) is 170 person/day, and budget at completion (BAC) is 285 person/day. What is the estimate at completion (EAC)? | 285 person/day | 310 person/day | 334 person/day | 315 person/day |  | C | With EV = 145, PV = 145, AC = 170, and BAC = 285, the CPI = EV ÷ AC = 145 ÷ 170 ≈ 0.8529. When future performance is assumed at the same CPI, EAC = BAC ÷ CPI = 285 ÷ 0.8529 ≈ 334 person/day. Option A (285) is the original BAC without reflecting cost inefficiency. Option B (310) does not match the formula. Option D (315) is also incorrect based on the calculation. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 대규모 복잡한 프로젝트가 여러 지역으로 구성되어 있다. ETC 작업은 현재 CPI와 동일한 비율로 수행된다고 가정한다. EV=145, PV=145, AC=170, BAC=285일 때 EAC는? | 285 person/day | 310 person/day | 334 person/day | 315 person/day |  | C | EV=145, PV=145, AC=170, BAC=285일 때, CPI = EV÷AC = 145÷170 ≈ 0.8529이다. 미래 성과가 동일한 CPI로 가정하면, EAC = BAC÷CPI = 285÷0.8529 ≈ 334 person/day이다. A(285)는 원래 BAC이다. B(310)와 D(315)는 잘못된 계산이다.
1369 | A large and complex program in an agile environment has experienced an increase in escalations from the client side. The rates and responsibilities are unclear, and the client does not have any direction regarding the escalation process. What should be done to resolve this issue? | Accept the escalations and manage them so the working relationship with the client isnot impacted. | Invite the client and product owner to all planning, review, and retrospective meetings. | Review and clarify roles, responsibilities, and the governance model at the next sprintreview meeting. | Invite the product owner to attend all Scrum meetings and define the governance modeland escalation path. |  | C | When a complex agile program experiences escalations with unclear roles and no escalation process, the team should review and clarify roles, responsibilities, and the governance model at the next sprint review meeting. This establishes clarity and formal escalation paths. Accepting and managing escalations (A) treats symptoms without fixing structure. Inviting the client and PO to all meetings (B) increases involvement but does not clarify governance. Inviting the PO to scrum meetings with governance definition (D) is narrower. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 애자일 환경의 대규모 프로그램에서 고객 측 에스컬레이션이 증가했다. 역할이 불명확하고 에스컬레이션 프로세스가 없다. 팀은 무엇을 해야 하는가? | 에스컬레이션을 수용하고 고객과의 업무 관계에 영향이 없도록 관리한다 | 고객과 제품 책임자를 모든 계획, 리뷰, 회고 회의에 초대한다 | 다음 스프린트 리뷰에서 역할, 책임, 거버넌스 모델을 검토하고 명확히 한다 | 제품 책임자를 모든 스크럼 회의에 참석시키고 거버넌스 모델과 에스컬레이션 경로를 정의한다 |  | C | 역할이 불명확하고 에스컬레이션 프로세스가 없을 때, 다음 스프린트 리뷰에서 역할, 책임, 거버넌스 모델을 검토하고 명확히 해야 한다. 구조적 명확화가 근본 원인을 해결한다. 에스컬레이션 수용(A)은 수동적이다. 모든 회의 초대(B)는 과도하다. PO만 참석(D)은 부분적 해결이다.
1370 | There are several dependent work streams in a project. Some project stakeholders feel that coordination among team members and progress visibility are lacking. What should the project manager do? | Organize a team meeting to review the project status | Escalate the concerns to the project steering committee | Review and update the communications management plan | Discuss the concerns with the project sponsor |  | C | When stakeholders report poor coordination and limited progress visibility across dependent work streams, the project manager should review and update the communications management plan. Structural improvements to communication governance address the root cause. Organizing a team meeting (A) is a one-time tactic. Escalating to the steering committee (B) is unnecessary as a first step. Discussing with the sponsor (D) escalates before attempting to resolve. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트에 여러 종속적 작업 흐름이 있다. 이해관계자가 팀원 간 조정이 부족하고 진행 가시성이 제한적이라고 느낀다. PM은 무엇을 해야 하는가? | 팀 회의를 조직하여 프로젝트 상태를 검토한다 | 프로젝트 운영위원회에 우려를 에스컬레이션한다 | 커뮤니케이션 관리 계획을 검토하고 업데이트한다 | 프로젝트 스폰서와 우려를 논의한다 |  | C | 이해관계자가 종속적 작업 흐름 간 조정 부족과 진행 가시성 제한을 보고할 때, PM은 커뮤니케이션 관리 계획을 검토하고 업데이트해야 한다. 구조적 커뮤니케이션 개선이 근본 해결이다. 팀 회의(A)는 일시적이다. 에스컬레이션(B)은 과도하다. 스폰서 논의(D)는 계획 개선이 아니다.
1371 | A team member misses a project meeting without it being approved and has been penalized as defined in the ground rules. This team member, as well as other team members, insist that it is the first time they have seen this rule regarding the project and they do not agree with the penalty. What should the project manager have done to avoid this situation? | Ensured the team members are fully supportive of all decisions. | Ensured the team charter was developed by the team members | Used a charismatic leadership style | Distributed the project charter to all team members. |  | B | When a team member is penalized for missing a meeting per ground rules they claim not to have seen, the project manager should have ensured the team charter was developed by the team members. Team-developed charters create shared ownership of ground rules. Ensuring full support of all decisions (A) is impractical. Using a charismatic leadership style (C) does not address rule awareness. Distributing the project charter (D) is a one-way communication that may not ensure understanding. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 팀원이 승인 없이 프로젝트 회의에 불참하여 기본 규칙에 따라 벌칙을 받았다. 팀원이 그런 규칙을 본 적 없다고 주장한다. PM이 이전에 무엇을 했어야 하는가? | 모든 결정에 팀원이 전적으로 동의하도록 보장했다 | 팀 헌장이 팀원에 의해 개발되도록 보장했다 | 카리스마적 리더십 스타일을 사용했다 | 프로젝트 헌장을 모든 팀원에게 배포했다 |  | B | 팀원이 기본 규칙을 본 적 없다고 주장할 때, PM은 팀 헌장이 팀원에 의해 개발되도록 보장했어야 한다. 팀이 직접 개발한 헌장은 인식과 주인의식을 보장한다. 전적 동의(A)는 비현실적이다. 카리스마적 리더십(C)은 참여를 보장하지 않는다. 프로젝트 헌장 배포(D)는 팀 헌장이 아니다.
1372 | During a kick-off meeting at the start of project execution, the vendor presents a migration plan to client stakeholders. The director of the business unit that owns the solution being migrated demands the ability to make the final go/no-go decision about whether the systems go live. What should the project manager do? | Schedule a meeting with the project sponsor to determine if it is appropriate to acceptthe director ' s request to provide a decision. 1212 | Schedule a meeting with the director to provide proof of expertise so the clientstakeholders will trust the project team ' s decision. | Confirm with the director that the client stakeholders will be made accountable for thedecision in the responsibility assignment matrix (RAM). | Ask the client to initiate a change request to make the director accountable for thedecision. |  | A | When a business unit director demands go/no-go decision authority during a kick-off meeting, the project manager should schedule a meeting with the project sponsor to determine if the request is appropriate. The sponsor clarifies governance. Meeting the director to prove expertise (B) is confrontational. Confirming accountability in the RAM (C) formalizes without sponsor input. Asking the client to initiate a change request (D) is formal but bypasses sponsor. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | 킥오프 회의에서 벤더가 마이그레이션 계획을 발표할 때, 사업부 이사가 진행/중단 결정 권한을 요구한다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서와 회의를 잡아 이사의 요청을 수용하는 것이 적절한지 결정한다 | 이사와 회의를 잡아 전문성의 증거를 제공하여 고객이 신뢰하도록 한다 | 이사에게 고객 이해관계자가 기록에 결정에 대해 책임질 것임을 확인한다 | 고객에게 이사가 결정에 책임지도록 변경 요청을 시작하도록 요청한다 |  | A | 사업부 이사가 킥오프 회의에서 진행/중단 결정 권한을 요구할 때, PM은 프로젝트 스폰서와 회의를 잡아 이 요청이 적절한지 결정해야 한다. 거버넌스 결정은 스폰서와 협의해야 한다. 전문성 증명(B)은 권한 문제를 해결하지 않는다. 책임 확인(C)은 일방적이다. 변경 요청(D)은 시기상조이다.
1373 | A project is being initiated, and almost every resource available on the project team is a recent university graduate. What should the project manager do to ensure their engagement with the project? | Provide clear direction on the work to be done and its alignment to the major objectives of the organization, using technology to communicate. | Foster proactive decision making and develop a hierarchy to approve decisions based on different levels of complexity. | Create an environment that encourages leadership, translates ambitions into growth opportunities, and rewards overtime workers. | Establish a clear hierarchical environment and allow them to navigate through the project faster using social networks. |  | C | When almost every resource on the project team is a recent university graduate, the project manager should create an environment that encourages leadership, translates ambitions into growth opportunities, and rewards overtime workers. This fosters engagement and professional development. Providing clear direction with technology (A) is necessary but insufficient for engagement. Fostering proactive decision-making with hierarchy (B) is helpful but less comprehensive. Establishing a hierarchical environment with social networks (D) is rigid and may not foster growth. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트가 시작되고 있으며 팀의 거의 모든 자원이 최근 대학 졸업생이다. PM의 최선의 접근법은? | 수행할 작업과 조직의 주요 목표와의 연계에 대해 명확한 방향을 제공한다 | 사전적 의사결정을 촉진하고 다양한 수준에 따라 결정을 승인하는 계층을 개발한다 | 리더십을 장려하고 야망을 성장 기회로 전환하며 성과를 인정하는 환경을 만든다 | 명확한 계층적 환경을 설립하고 기존 지식을 활용하여 프로젝트를 빠르게 진행하도록 한다 |  | C | 팀의 거의 모든 자원이 최근 대학 졸업생일 때, PM은 리더십을 장려하고 야망을 성장 기회로 전환하며 성과를 인정하는 환경을 만들어야 한다. 동기 부여와 성장 중심 환경이 신입의 잠재력을 극대화한다. 명확한 방향(A)은 지시적이다. 계층(B)은 관료적이다. 계층적 환경(D)은 성장을 제한한다.
1374 | A government procurement team has been running a vendor selection process for more than 1 year, exceeding the originally planned 6 months due to a variety of factors. Two vendors have submitted proposals that were evaluated. The project manager requested an estimated completion date 4 weeks ago, but it was not provided. What should the project manager do? | Work with the procurement team to build a high-level timeline. | Ask the project sponsor to request an estimate from the procurement team. | Escalate the delay issue to the project steering committee. | Explain to the steering committee that vendor negotiations are unpredictable. |  | A | When procurement processes cause delays—particularly in government contexts with strict procedures—the PM should collaborate directly with the procurement team to develop a high-level timeline. This promotes alignment and visibility into expectations without immediately escalating or assigning blame. The PM plays a facilitative role in procurement, coordinating with specialists and aligning stakeholder expectations. Avoiding the issue (B) provides no corrective action. Offloading responsibility (C) is inappropriate when the PM should lead coordination. Escalation (D) should be reserved for after collaborative approaches have been exhausted. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 정부 조달팀이 1년 이상 벤더 선정 프로세스를 진행 중이며 원래 예상 일정을 초과했다. PM은 무엇을 해야 하는가? | 조달팀과 협력하여 상위 수준의 타임라인을 구축한다 | 프로젝트 스폰서에게 조달팀에 견적을 요청하도록 한다 | 프로젝트 운영위원회에 지연 이슈를 에스컬레이션한다 | 운영위원회에 벤더 협상이 예측 불가능하다고 설명한다 |  | A | 정부 조달 프로세스가 지연될 때, PM은 조달팀과 직접 협력하여 상위 수준의 타임라인을 구축해야 한다. 협력적 계획이 현실적 일정을 만든다. 스폰서 요청(B)은 간접적이다. 에스컬레이션(C)은 직접 협력 전에 과도하다. 변명(D)은 해결이 아니다.
1375 | A global company is executing a strategic project to upgrade a legacy enterprise system. The company uses a hybrid approach to project management and has just completed the first sprint. A team member provided ideas to improve the testing process during the sprint retrospective. What is the next step for the project manager? | Request that all team members think of ideas to improve processes. | Organize a demonstration of the changes in the enterprise system | Facilitate a daily standup with the team to track the implementation of changes | Document the lessons learned and implement improvements in the next sprint |  | D | When a team member proposes process improvements during a sprint retrospective, the next step is to document the lessons learned and implement improvements in the next sprint. This follows the agile cycle of continuous improvement—capturing insights and acting on them in the subsequent iteration. Requesting all team members to think of ideas (A) is general rather than actionable. Organizing a demonstration (B) is for showing product increments, not process improvements. Facilitating daily standups (C) is a regular sprint activity, not a retrospective follow-up. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Evaluate Project Status | Governance | Executing | Embed Quality | Direct and Manage Project Work | Hybrid/Tailoring | 글로벌 회사가 레거시 시스템 업그레이드 전략 프로젝트를 실행 중이다. 팀원이 스프린트 회고에서 프로세스 개선을 제안한다. 다음 단계는? | 모든 팀원에게 프로세스 개선 아이디어를 생각하도록 요청한다 | 엔터프라이즈 시스템 변경의 데모를 조직한다 | 변경 구현을 추적하기 위해 팀과 데일리 스탠드업을 퍼실리테이션한다 | 교훈을 문서화하고 다음 스프린트에서 개선을 구현한다 |  | D | 팀원이 스프린트 회고에서 프로세스 개선을 제안할 때, 다음 단계는 교훈을 문서화하고 다음 스프린트에서 개선을 구현하는 것이다. 이는 애자일의 지속적 개선 원칙을 따른다. 아이디어 요청(A)은 이미 아이디어가 있다. 데모(B)는 무관하다. 스탠드업(C)은 추적이지 구현이 아니다.
1376 | During a daily meeting of a challenging project, two team members started to argue on the preferred solution based on their assumptions. The situation prevented the progress to the next phase of development, which could impact the finish date of the project. What should the project manager do next? | Ask the human resources (HR) department to replace the team members. | Make a decision based upon the project manager ' s knowledge and expertise. | Divide the team into small groups to avoid future arguments and delays. | Meet with the team members to discuss the priority of the project schedule. |  | D | When two team members argue over preferred solutions based on assumptions during a daily meeting, blocking progress and threatening the finish date, the project manager should meet with the team members to discuss the priority of the project schedule. This refocuses the discussion on project objectives over personal preferences and facilitates collaborative resolution. Asking HR to replace team members (A) is extreme. Making a decision based on the PM's expertise (B) may overlook critical input. Dividing the team into small groups (C) fractures collaboration. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 데일리 회의에서 두 팀원이 가정에 기반한 선호 솔루션에 대해 논쟁을 시작했다. 진행이 막히고 완료일이 위협받는다. PM은 무엇을 해야 하는가? | HR에 팀원 교체를 요청한다 | PM의 지식과 전문성에 기반하여 결정한다 | 미래 논쟁과 지연을 피하기 위해 팀을 소그룹으로 나눈다 | 팀원과 만나 프로젝트 일정의 우선순위를 논의한다 |  | D | 두 팀원이 가정에 기반해 논쟁하고 진행이 막힐 때, PM은 팀원과 만나 프로젝트 일정의 우선순위를 논의해야 한다. 프로젝트 목표에 집중하면 개인적 선호보다 프로젝트 필요를 우선시한다. HR 교체(A)는 과도하다. PM 결정(B)은 독재적이다. 팀 분리(C)는 협업을 방해한다.
1377 | An experienced project team member always points out the issues of other team members during meetings. The other team members feel that the experienced team member is deflecting their own issues in meetings. What should the project manager do? | Arrange separated group meetings to allow everyone to express their opinions. | Prepare an agenda for all future team meetings and facilitate the discussion. | Speak with the experienced team member to discuss the issues in a supportive way. | Review the communications management plan with the team and enforce its implementation. |  | C | The project manager should speak with the experienced team member directly in a supportive way to address the behavior. This one-on-one approach allows the PM to understand the reasons behind the team member's actions and work toward a constructive resolution without further disrupting the team. Private, supportive communication is a key conflict resolution strategy that maintains team cohesion. Arranging separated group meetings (A) may amplify divisions rather than resolve them. Preparing agendas and facilitating discussion (B) improves meeting structure but does not address the specific behavioral issue. Reviewing the communications management plan (D) is procedural and does not target the interpersonal conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 경험 많은 팀원이 회의에서 항상 다른 팀원의 문제를 지적한다. 다른 팀원들이 회의에 참여하고 싶지 않아한다. PM은 무엇을 해야 하는가? | 모두가 의견을 표현할 수 있도록 분리된 그룹 회의를 준비한다 | 모든 미래 팀 회의의 안건을 준비하고 토론을 퍼실리테이션한다 | 경험 많은 팀원과 대화하여 지지적인 방식으로 문제를 논의한다 | 팀과 커뮤니케이션 관리 계획을 검토하고 이행을 강제한다 |  | C | 경험 많은 팀원이 다른 사람의 문제를 계속 지적할 때, PM은 해당 팀원과 직접 지지적인 방식으로 대화해야 한다. 1:1 접근이 행동의 이유를 이해하고 변화를 유도한다. 분리 회의(A)는 문제를 회피한다. 안건 준비(B)는 행동을 직접 다루지 않는다. 계획 강제(D)는 처벌적이다.
1378 | A mid-size capital project has shared resources from the company's contract department. During the execution phase, the project team observed a delay in contracting. After communicating with the contract department, the project manager found the contract team is prioritizing other contracting jobs because they are not part of the project team. What should the project manager do first in this situation? | Arrange a meeting with the contract department to build trust and commitment by recognizing their critical support to the project. | Report the issue to higher management and seek their direct involvement to complete the job from the contract department. | Communicate with the contract manager to commit a budget for the resources required for project execution. | Arrange several meetings with the contract department and ask them to contract the project as it is critical for project success. |  | A | When the contract department prioritizes other work over the project causing contracting delays, the project manager should first arrange a meeting to build trust and commitment by recognizing their critical support. Direct engagement fosters collaboration in shared-resource environments. Reporting to higher management (B) escalates prematurely. Committing budget for resources (C) may not address the prioritization issue. Arranging multiple meetings to pressure them (D) is counterproductive. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 중형 자본 프로젝트가 계약 부서의 공유 자원을 사용한다. 계약 부서가 다른 업무를 우선시하여 계약 지연이 발생한다. PM은 무엇을 먼저 해야 하는가? | 계약 부서와 회의를 준비하여 그들의 중요한 역할을 인정하고 신뢰와 헌신을 구축한다 | 상위 경영진에 이슈를 보고하고 계약 부서의 직접 참여를 요청한다 | 계약 관리자와 커뮤니케이션하여 프로젝트 실행에 필요한 자원 예산을 확보한다 | 계약 부서와 여러 회의를 준비하고 프로젝트를 있는 그대로 계약하도록 요청한다 |  | A | 계약 부서가 다른 업무를 우선시할 때, PM은 먼저 회의를 준비하여 그들의 중요한 역할을 인정하고 신뢰와 헌신을 구축해야 한다. 관계 구축이 협력의 기초이다. 경영진 보고(B)는 직접 해결 시도 전에 과도하다. 예산 확보(C)는 관계 구축 후에 한다. 계약 요청(D)은 일방적이다.
1379 | A project is in its first of six iterations. The project team realizes that a key deliverable is dependent on the acquisition of a new device. The vendor is new to the organization and does not have a long history in the market. What should the project manager do first? | Register the risk and escalate it to the procurement team. | Register the risk and prioritize the implementation strategy. | Register the risk and provide appropriate response options. | Register the risk and escalate it to the project sponsor. |  | C | When a key deliverable depends on a new vendor with limited market history, the project manager should first register the risk and provide appropriate response options. This ensures the risk is visible, enables probability/impact analysis, and supports selecting strategies such as mitigation (qualifying alternates, adding buffers), transfer (contract terms), or acceptance with contingency triggers. Escalating to procurement (A) or the sponsor (D) may follow but is premature before the risk is defined with potential responses. Registering and prioritizing implementation strategy (B) skips the critical step of developing response options. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 6번의 이터레이션 중 첫 번째에 있다. 핵심 인도물이 시장 이력이 제한적인 새 벤더 확보에 의존한다. PM은 무엇을 해야 하는가? | 리스크를 등록하고 조달팀에 에스컬레이션한다 | 리스크를 등록하고 구현 전략의 우선순위를 정한다 | 리스크를 등록하고 적절한 대응 옵션을 제공한다 | 리스크를 등록하고 프로젝트 스폰서에게 에스컬레이션한다 |  | C | 핵심 인도물이 시장 이력이 제한적인 새 벤더에 의존할 때, PM은 먼저 리스크를 등록하고 적절한 대응 옵션을 제공해야 한다. 리스크의 가시성 확보와 대응 계획이 우선이다. 조달팀 에스컬레이션(A)은 대응 옵션 없이 전달이다. 구현 전략(B)은 리스크 대응이 아니다. 스폰서 에스컬레이션(D)은 대응 옵션 준비 후에 한다.
1380 | A newly assigned team member immediately begins questioning operating procedures. This new team member wants the team to follow operating procedures that the team member had used previously. During assignments, the new team member begins using some of those processes and procedures and suggests these practices to other team members. What action should the project manager take? | Organize a training for the new team member on the processes the team is currently 904 using. | Hold a team meeting on governance, operating policies, procedures, and practices. | Formalize the new processes and implement the team member ' s proposed changes. | Speak with the new team member at the retrospective and discuss potential improvements. |  | B | The correct answer is B. Hold a team meeting on governance, operating policies, procedures, and practices. Effective resource management ensures team members have the necessary competencies and support. The PM should identify gaps and address them through training, coaching, or mentoring. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새로 배정된 팀원이 운영 절차에 즉시 의문을 제기하고 팀이 다른 프로세스를 사용하기를 원한다. PM은 무엇을 해야 하는가? | 새 팀원에게 팀이 현재 사용하는 프로세스에 대한 교육을 조직한다 | 거버넌스, 운영 정책, 절차, 관행에 대한 팀 회의를 개최한다 | 새 프로세스를 공식화하고 팀원의 제안된 변경을 구현한다 | 회고에서 새 팀원과 대화하여 잠재적 개선을 논의한다 |  | B | 정답은 B이다. 거버넌스, 운영 정책, 절차, 관행에 대한 팀 회의를 개최한다. 효과적인 자원 관리는 팀원의 필요한 역량과 지원을 보장한다. 전체 팀 회의가 기존 프로세스의 이유를 이해하게 한다. 교육(A)은 일방적이다. 즉시 구현(C)은 성급하다. 회고 대기(D)는 너무 늦다.
1381 | A software project using an agile approach is facing quality issues with every release, generating many production problems. What should the project manager do to fix the problem and improve the quality? | Use the retrospective meeting to better understand the root cause of the quality problems and put together a plan with the team to address the problems | Seek extra funding approval with the sponsor to replace junior team members for more experienced ones | Hire an external company to add an additional layer of testing, making sure that the final 1014 product is well inspected before releasing. | Create a reward system granting incentives to the team members who are able to catch more defects |  | A | When an agile project faces quality issues with every release, the project manager should use the retrospective meeting to understand root causes and put together a plan with the team. Team-driven problem-solving fosters continuous improvement. Seeking extra funding for experienced members (B) throws money at the problem. Hiring an external testing company (C) adds a layer without addressing root causes. Creating a reward system for defect-catching (D) incentivizes finding defects, not preventing them. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 애자일 소프트웨어 프로젝트가 매 릴리스마다 품질 문제에 직면하여 많은 프로덕션 문제를 발생시킨다. PM은 무엇을 해야 하는가? | 회고 회의를 사용하여 품질 문제의 근본 원인을 이해하고 팀과 계획을 수립한다 | 스폰서에게 추가 자금 승인을 받아 주니어 팀원을 경험 있는 인원으로 교체한다 | 외부 회사를 고용하여 추가 테스트 계층을 추가하여 최종 제품 품질을 보장한다 | 더 많은 결함을 찾는 팀원에게 인센티브를 부여하는 보상 시스템을 만든다 |  | A | 애자일 프로젝트가 매 릴리스마다 품질 문제에 직면할 때, PM은 회고 회의를 사용하여 근본 원인을 이해하고 팀과 계획을 수립해야 한다. 팀 주도적 문제 해결이 지속적 개선을 가능하게 한다. 인원 교체(B)는 과도하다. 외부 테스트(C)는 근본 원인을 해결하지 않는다. 보상 시스템(D)은 결함 발견이 아닌 예방이 목표여야 한다.
1382 | The team responsible for executing a work package asks the consultant to reconsider the initial project deliverables specified in the contract. What should the project manager do in this situation? | Carry out corresponding negotiations in the adjustments of outcomes. | Pause the project until a satisfactory agreement between both parties is reached. | Explain to the consultant that without adjustments, payment terms will be affected. | Agree with the consultant to continue without any adjustments. |  | A | When the execution team asks the consultant to reconsider initial deliverables specified in the contract, the project manager should carry out corresponding negotiations to adjust outcomes. Formal negotiation through the change control process preserves the contract relationship while addressing valid concerns. Pausing the project (B) is unnecessarily drastic. Threatening payment terms (C) escalates tension. Agreeing to continue without adjustments (D) ignores the team's legitimate concerns. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Procurement | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | 작업 패키지 실행을 담당하는 팀이 컨설턴트에게 계약에 명시된 초기 프로젝트 인도물을 재검토하도록 요청한다. PM은 무엇을 해야 하는가? | 결과물 조정에 대한 해당 협상을 수행한다 | 양측 간 만족스러운 합의가 이루어질 때까지 프로젝트를 중단한다 | 컨설턴트에게 조정 없이는 지불 조건이 영향을 받을 것이라고 설명한다 | 컨설턴트와 조정 없이 계속 진행하기로 합의한다 |  | A | 팀이 컨설턴트에게 인도물 재검토를 요청할 때, PM은 결과물 조정에 대한 해당 협상을 수행해야 한다. 공식적 협상이 양측 이해를 조율한다. 프로젝트 중단(B)은 과도하다. 지불 위협(C)은 적대적이다. 조정 없이 합의(D)는 팀 우려를 무시한다.
1383 | After reviewing the project management plan with key stakeholders, the project manager was told that an 18-month release plan was unacceptable and the product should launch in six months. Based on the new timeline, what should the project manager do? | Seek approval with the sponsor to triple the project budget, hiring more people to compensate for the compressed schedule | Plan for overtime apply crashing and fast tracking and share the risk of failure with project stakeholders | Go over the critical path with stakeholders, explaining why it is not possible to deliver all the scope in the expected timeline | Review the project backlog looking for high-priority items and come up with a minimum viable product (MVP) that fits the expected timeline |  | D | When an 18-month release plan must be compressed to 6 months, the project manager should review the project backlog for high-priority items and develop an MVP that fits the expected timeline. MVP focuses on delivering core value within constraints. Tripling the budget (A) may not be feasible or proportionate. Applying crashing and fast-tracking (B) increases risk and cost. Explaining impossibility (C) does not offer solutions. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Lean | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 주요 이해관계자와 프로젝트 관리 계획 검토 후, 18개월 릴리스 계획을 6개월로 압축해야 한다. PM은 무엇을 해야 하는가? | 스폰서에게 프로젝트 예산을 3배로 늘려 더 많은 인원을 고용하도록 승인을 구한다 | 초과 근무를 계획하고 크래싱과 패스트 트래킹을 적용하며 실패 리스크를 이해관계자와 공유한다 | 이해관계자와 주공정선을 검토하여 모든 범위를 납품하는 것이 불가능한 이유를 설명한다 | 프로젝트 백로그에서 높은 우선순위 항목을 검토하고 예상 타임라인에 맞는 MVP를 도출한다 |  | D | 18개월 릴리스 계획을 6개월로 압축해야 할 때, PM은 프로젝트 백로그에서 높은 우선순위 항목을 검토하고 MVP를 도출해야 한다. MVP가 핵심 가치를 시간 내에 전달한다. 예산 3배(A)는 비현실적이다. 크래싱(B)은 리스크가 크다. 불가능 설명(C)은 해결이 아니다.
1384 | A supplier was supposed to mobilize a government-issued, licensed piece of equipment two days ago, but did not. The procurement manager was informed that the supplier failed to check the validity of the license, which expired last week. The supplier had already submitted an application to the authorities, but it generally takes one to three weeks to process the application, which will affect the critical path. Which action should the project manager take? | Analyze the schedule and look for fast tracking and crashing alternatives. | Update the lessons learned register to serve as an input for future material transactions. | Update the project team on the delay so that resources can be utilized elsewhere. | Review the terms of the contract in order to determine next steps. |  | D | When a supplier's expired license delays mobilization of government-issued equipment affecting the critical path, the project manager should review the terms of the contract to determine next steps. Contract review identifies obligations, remedies, and penalties. Analyzing schedule for fast-tracking and crashing (A) addresses the schedule impact but not the supplier issue. Updating lessons learned (B) documents the issue without resolving it. Updating the team for resource reallocation (C) is reactive. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 공급업체가 정부 발급 면허가 있는 장비를 2일 전에 동원해야 했지만 하지 않았다. 면허가 만료되어 주공정선에 영향을 준다. PM은 무엇을 먼저 해야 하는가? | 일정을 분석하고 패스트 트래킹 및 크래싱 대안을 찾는다 | 미래 자재 거래를 위한 입력으로 교훈 등록부를 업데이트한다 | 지연에 대해 프로젝트 팀을 업데이트하여 자원을 다른 곳에 활용할 수 있게 한다 | 다음 단계를 결정하기 위해 계약 조건을 검토한다 |  | D | 공급업체의 면허 만료로 장비 동원이 지연되어 주공정선에 영향을 줄 때, PM은 먼저 계약 조건을 검토하여 다음 단계를 결정해야 한다. 계약 조건이 법적 의무와 구제 옵션을 정의한다. 일정 분석(A)은 계약 검토 후에 한다. 교훈(B)은 미래용이다. 팀 업데이트(C)는 필요하지만 계약 검토가 먼저이다.
1385 | A project manager is in the process of creating a strengths-based team and is organizing a series of workshops to identify and document the strengths of each project team member. During this session, there are multiple team members who are not actively participating. These meetings are becoming futile due to a lack of participation. What should the project manager do? | Document the behavior of the team members and highlight it during their performancereviews. | Have a one-on-one discussion with each team member to emphasize their individualtalents. | Explain the benefits of the approach and the effects of positive psychology. | Identify the team members who are not participating and reprimand them. |  | C | When team members are not actively participating in strengths-identification workshops, the project manager should explain the benefits of the approach and the effects of positive psychology. Educating team members on the purpose and value of the sessions can motivate engagement and foster a positive team culture. One-on-one discussions (B) are time-consuming and may not address root cause. Documenting behavior for performance reviews (A) is punitive. Reprimanding non-participants (D) creates resentment and is counterproductive. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Embed Quality | Direct and Manage Project Work | Hybrid/Tailoring | PM이 강점 기반 팀을 만들기 위해 워크숍을 진행 중이다. 일부 팀원이 적극적으로 참여하지 않는다. PM은 무엇을 해야 하는가? | 팀원의 행동을 문서화하고 성과 평가에서 강조한다 | 각 팀원과 1:1 대화를 하여 개인의 재능을 강조한다 | 접근법의 이점과 긍정 심리학의 효과를 설명한다 | 참여하지 않는 팀원을 식별하고 질책한다 |  | C | 팀원이 강점 식별 워크숍에 적극적으로 참여하지 않을 때, PM은 접근법의 이점과 긍정 심리학의 효과를 설명해야 한다. 교육과 이해가 참여를 촉진한다. 행동 문서화(A)는 처벌적이다. 1:1 대화(B)는 유용하지만 전체 이해가 먼저이다. 질책(D)은 부정적이다.
1386 | A project is being executed. The project's life cycle is defined as predictive; however, a major deliverable will be handed over incrementally to the customer. The assigned resources are experienced and reliable and are willing to make decisions that the project manager used to make after each incremental delivery on other projects. What should the project manager do? | Schedule a steering committee meeting and obtain their approval on the request | Consult the product owner about letting the resources make decisions | Inform the team that although this is a hybrid environment, the project managermust still be responsible for making decisions | Support the decisions of the team and transfer the decision making responsibility to them. |  | D | When experienced and reliable team members are willing to make decisions previously made by the project manager in a hybrid environment with incremental delivery, the project manager should support the team's decisions and transfer decision-making responsibility to them. Empowerment fosters ownership and efficiency. Scheduling a steering committee meeting (A) adds overhead. Consulting the product owner (B) is unnecessary if the team is qualified. Insisting the PM must decide (C) contradicts empowerment principles. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 프로젝트가 실행 중이다. 수명주기는 예측형이지만 주요 인도물은 점진적으로 처리된다. 경험 있는 팀원이 의사결정을 원한다. PM은 무엇을 해야 하는가? | 운영위원회 회의를 잡고 요청에 대한 승인을 받는다 | 제품 책임자에게 자원이 결정하도록 하는 것에 대해 상의한다 | 하이브리드 환경이지만 PM이 여전히 모든 결정에 책임져야 한다고 팀에 알린다 | 팀의 결정을 지원하고 의사결정 책임을 그들에게 이전한다 |  | D | 하이브리드 환경에서 경험 있고 신뢰할 수 있는 팀원이 결정을 원할 때, PM은 팀의 결정을 지원하고 의사결정 책임을 이전해야 한다. 팀 권한 부여가 애자일 원칙에 부합한다. 운영위원회 승인(A)은 과도하다. PO 상의(B)는 팀 권한 문제가 아니다. PM 책임 주장(C)은 서번트 리더십에 반한다.
1387 | During the course of the project, several obstacles are identified that are preventing the project from moving forward. What should the project manager do to remove the obstacles? | Implement plans to remove the obstacles | Have the project team work on other activities 1248 | Prioritize the obstacles for resolution | Escalate to the project steering committee |  | A | When obstacles are preventing the project from moving forward, the project manager should implement plans to remove the obstacles. Direct action resolves blockers. Having the team work on other activities (B) avoids the problem. Prioritizing obstacles (C) is necessary but insufficient without action. Escalating to the steering committee (D) is premature before attempting resolution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 진행 중 여러 장애물이 프로젝트 진행을 막고 있다. PM은 무엇을 먼저 해야 하는가? | 장애물을 제거하기 위한 계획을 실행한다 | 프로젝트 팀이 다른 활동을 수행하도록 한다 | 해결을 위해 장애물의 우선순위를 정한다 | 프로젝트 운영위원회에 에스컬레이션한다 |  | A | 장애물이 프로젝트 진행을 막을 때, PM은 장애물을 제거하기 위한 계획을 실행해야 한다. 직접적 행동이 장애를 해결한다. 다른 활동(B)은 장애를 해결하지 않는다. 우선순위(C)는 필요하지만 행동이 먼저이다. 에스컬레이션(D)은 직접 해결 시도 후에 한다.
1388 | A product development team has team members located in four different countries. A senior manager is assigned the task of recruiting a project manager to manage this project and the virtual team. Which skill is required for a project manager to successfully manage this team? | Possesses strong interpersonal skills to drive high-performing virtual teams | Implements the organization's standards and processes for the project | Plans and controls every aspect of the team ' s deliverables to avoid surprises | Speaks several languages and has lived in different countries |  | A | Managing a virtual product development team across four countries requires a project manager who possesses strong interpersonal skills to drive high-performing virtual teams. Interpersonal skills—including relationship building, communication facilitation, cultural sensitivity, and collaboration—are essential for success in virtual environments. Implementing organizational standards (B) is important but secondary to people skills. Planning and controlling every deliverable (C) implies micromanagement. Speaking several languages (D) is helpful but not the core competency needed. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 4개국에 팀원이 분산된 제품 개발 팀이 있다. 이 팀을 관리할 PM의 가장 중요한 자질은? | 고성과 가상 팀을 이끄는 강한 대인관계 기술을 보유한다 | 프로젝트에 조직의 표준과 프로세스를 구현한다 | 놀라움을 피하기 위해 팀의 인도물의 모든 측면을 계획하고 통제한다 | 여러 언어를 구사하고 다른 국가에서 살았다 |  | A | 4개국에 분산된 가상 팀을 관리하려면 강한 대인관계 기술이 필요하다. 의사소통, 감정 지능, 갈등 해결 등 대인관계 기술이 가상 환경에서 핵심이다. 표준/프로세스(B)는 관리적이다. 모든 측면 통제(C)는 마이크로매니지먼트이다. 다국어(D)는 유용하지만 필수는 아니다.
1389 | An agile team member received certification on a new tool; however, this team member is complaining that the rest of the team is not using the tool due to lack of knowledge. How should the servant leader apply emotional intelligence to leverage this situation to benefit the project? | Request budget to reward the team member so others will be motivated to obtain the same certification | Ask the team member to use their recently acquired knowledge to develop and provide training to the team | Promote the team member to product owner to leverage the new knowledge with the clients | Provide an incentive to team members who begin using the new tool on this project. |  | B | When a certified team member complains that others are not using a new tool due to lack of knowledge, the servant leader should ask the team member to develop and provide training to the team. This leverages emotional intelligence by acknowledging their achievement and encouraging knowledge sharing. Requesting budget for rewards (A) may create competition. Promoting to product owner (C) mismatches roles. Providing incentives for tool usage (D) does not address the knowledge gap. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Integrate Sustainability | Direct and Manage Project Work | Sustainability | 애자일 팀원이 새 도구 인증을 받았지만 나머지 팀이 지식 부족으로 사용하지 않는다. 서번트 리더는 무엇을 해야 하는가? | 다른 팀원이 같은 인증을 받도록 동기 부여하기 위해 보상 예산을 요청한다 | 팀원에게 최근 획득한 지식으로 팀에 교육을 개발하고 제공하도록 요청한다 | 팀원을 제품 책임자로 승진시켜 고객과 새 지식을 활용한다 | 이 프로젝트에서 새 도구를 사용하기 시작하는 팀원에게 인센티브를 제공한다 |  | B | 인증을 받은 팀원이 다른 팀원의 도구 미사용을 불만할 때, 서번트 리더는 그 팀원에게 팀 교육을 개발하고 제공하도록 요청해야 한다. 지식 공유가 팀 역량을 향상시킨다. 보상(A)은 학습 동기가 아니다. PO 승진(C)은 역할과 무관하다. 인센티브(D)는 교육 없이 도구 사용을 강요한다.
1390 | A project manager is working on a multinational project with stakeholders from different regions. What should the project manager do first to ensure there is effective stakeholder collaboration? | Review the stakeholder engagement plan with all of the stakeholders. | Analyze stakeholder interest levels to develop an engagement strategy. | Schedule regular virtual coordination meetings and invite all stakeholders. | Request budget to invite all stakeholders to in-person team meetings. |  | B | When managing a multinational project with stakeholders from different regions, the project manager should first analyze stakeholder interest levels to develop an engagement strategy. Stakeholder analysis provides the foundation for tailored, effective collaboration approaches. Reviewing the engagement plan with stakeholders (A) is premature before analysis. Scheduling regular virtual meetings (C) may not suit all stakeholder needs. Requesting budget for in-person meetings (D) may not be the most efficient first step. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Hybrid/Tailoring | PM이 다양한 지역의 이해관계자가 있는 다국적 프로젝트를 진행 중이다. PM은 무엇을 먼저 해야 하는가? | 모든 이해관계자와 이해관계자 참여 계획을 검토한다 | 참여 전략을 개발하기 위해 이해관계자 관심 수준을 분석한다 | 정기적 가상 조정 회의를 일정에 넣고 모든 이해관계자를 초대한다 | 모든 이해관계자를 대면 팀 회의에 초대하기 위한 예산을 요청한다 |  | B | 다국적 프로젝트에서 다양한 지역의 이해관계자를 관리할 때, PM은 먼저 이해관계자 관심 수준을 분석하여 참여 전략을 개발해야 한다. 분석이 맞춤형 전략의 기초이다. 계획 검토(A)는 분석 후에 한다. 정기 회의(C)는 분석 없이 일반적이다. 대면 예산(D)은 비현실적이다.
1391 | A project has met the agreed-upon product requirements and is closing. There is time remaining in the schedule and excess budget. The resources are not yet scheduled to move to other projects. Several product champions want to continue adding functionality to the product. What should the project manager do? | Use the remaining time and resources to add additional scope to the project without 862 spending the project budget. | Obtain approval from the sponsor to add additional functionality to the project deliverables with the leftover budget. | Ensure product quality by spending the remaining resources and time on additional quality checks for the product. | Acknowledge the project closure criteria has been met and release the remaining budget and resources. |  | D | When a project has met all requirements and closure criteria but has remaining time and budget, the project manager should acknowledge that project closure criteria have been met and release the remaining budget and resources. Adding functionality creates scope creep. Using remaining time for additional scope (A) extends beyond the agreed deliverables. Obtaining sponsor approval for additions (B) risks reopening a completed project. Spending on extra quality checks (C) is unnecessary if requirements are already met. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Scope | Closing | Adopt a Holistic View | Close Project or Phase | Traditional PM | 프로젝트가 합의된 요구사항을 충족하고 종료 중이다. 일정에 남은 시간과 초과 예산이 있다. PM은 무엇을 해야 하는가? | 남은 시간과 자원으로 추가 범위를 프로젝트에 추가한다 | 스폰서에게 남은 자금으로 추가 기능을 추가하도록 승인을 받는다 | 남은 자원과 시간으로 추가 품질 점검을 실시하여 제품 품질을 보장한다 | 프로젝트 종료 기준이 충족되었음을 인정하고 남은 예산과 자원을 반환한다 |  | D | 프로젝트가 모든 요구사항과 종료 기준을 충족했지만 남은 시간과 예산이 있을 때, PM은 종료 기준 충족을 인정하고 남은 예산과 자원을 반환해야 한다. 범위 추가(A)는 승인 없는 변경이다. 추가 기능(B)은 불필요한 범위 확장이다. 추가 품질 점검(C)은 이미 충족된 기준에 과도하다.
1392 | A project manager has been assigned to a project where collaboration with the business is a critical key factor. The project manager is not sure about which approach to use. A senior project manager has been assigned to help the project manager. What advice should the senior project manager provide? | Work with the project manager to develop a new approach that will bring benefits to the project. | Establish a project management methodology that requires the customer to provide daily updates to the team. | Provide a project management template for the project manager to follow as a guide. | Suggest using an agile approach since customer and team collaboration is critical for project success. |  | D | When collaboration with the business is a critical project factor, the senior project manager should suggest using an agile approach since customer and team collaboration is critical for project success. Agile principles prioritize stakeholder collaboration and adaptive delivery. Developing a new approach together (A) is vague. Requiring daily customer updates (B) is prescriptive. Providing a template (C) does not address the collaboration need. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 비즈니스와의 협업이 핵심 요소인 프로젝트에 PM이 배정되었다. 선임 PM은 무엇을 제안해야 하는가? | PM과 협력하여 프로젝트에 혜택을 줄 새로운 접근법을 개발한다 | 고객이 PM 팀에 매일 업데이트를 제공하도록 요구하는 방법론을 수립한다 | PM이 따를 수 있는 프로젝트 관리 템플릿을 제공한다 | 고객과 팀 협업이 핵심이므로 애자일 접근법을 사용하도록 제안한다 |  | D | 비즈니스와의 협업이 핵심일 때, 선임 PM은 애자일 접근법을 제안해야 한다. 애자일은 고객과 팀 협업이 핵심 가치이다. 새 접근법 개발(A)은 구체적이지 않다. 매일 업데이트 요구(B)는 관료적이다. 템플릿(C)은 협업을 보장하지 않는다.
1393 | One of the main inputs required for a deliverable is missing due to a miscommunication between the vendor and project manager. Because of the missed deliverable, the critical path of the project is extended. What should the project manager do next? | Start an audit of the vendor ' s processes and procedures | Review lessons learned from previous projects with this vendor | Make a detailed analysis on vendor issues during the project | Execute a contingency plan to address the issue with the vendor |  | D | When a missing deliverable from vendor miscommunication extends the critical path, the project manager should execute a contingency plan to address the vendor issue. Pre-planned responses address known risks promptly. Starting a vendor audit (A) investigates but does not resolve the immediate problem. Reviewing lessons learned (B) is retrospective. Analyzing vendor issues in detail (C) delays response. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 벤더와의 커뮤니케이션 오류로 인도물에 필요한 주요 입력이 누락되어 주공정선이 연장된다. PM은 무엇을 해야 하는가? | 벤더의 프로세스와 절차에 대한 감사를 시작한다 | 이 벤더와의 이전 프로젝트 교훈을 검토한다 | 프로젝트 중 벤더 이슈에 대한 상세 분석을 한다 | 벤더 이슈를 해결하기 위해 비상 계획을 실행한다 |  | D | 벤더 커뮤니케이션 오류로 인해 주공정선이 연장될 때, PM은 벤더 이슈를 해결하기 위해 비상 계획을 실행해야 한다. 사전 계획된 대응이 알려진 리스크를 해결한다. 감사(A)는 시간이 오래 걸린다. 교훈 검토(B)는 과거 지향적이다. 상세 분석(C)은 즉각적 행동이 아니다.
1394 | A key stakeholder who is highly involved in the project claims that the reports sent by the project team are inadequate. What should the project manager do first? | Ask the project team to review and modify all of these reports. | Ensure that the reports comply with the communications management plan. | Ask the sponsor to meet with the stakeholder to diffuse the situation with the reports. | Explain to the stakeholder that these are the approved templates for the reports. |  | B | When a key stakeholder claims project reports are inadequate, the project manager should first ensure that the reports comply with the communications management plan. Verifying compliance determines if the issue is a deviation or a plan gap. Asking the team to modify reports (A) acts before understanding the issue. Asking the sponsor to intervene (C) escalates prematurely. Explaining the templates are approved (D) is dismissive of the stakeholder's concern. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 주요 이해관계자가 프로젝트 팀이 보내는 보고서가 부적절하다고 주장한다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 팀에 이 보고서를 검토하고 수정하도록 요청한다 | 보고서가 커뮤니케이션 관리 계획을 준수하는지 확인한다 | 스폰서에게 이해관계자와 만나 상황을 완화하도록 요청한다 | 이해관계자에게 이것이 보고서의 승인된 템플릿이라고 설명한다 |  | B | 주요 이해관계자가 보고서가 부적절하다고 주장할 때, PM은 먼저 보고서가 커뮤니케이션 관리 계획을 준수하는지 확인해야 한다. 준수 확인이 문제가 계획인지 실행인지를 결정한다. 즉시 수정(A)은 계획 확인 전에 성급하다. 스폰서 개입(C)은 과도하다. 승인 템플릿 설명(D)은 방어적이다.
1395 | A technician is scheduled to install internet service at the homes of three remote call center agents who have different working schedules. Their functional managers arranged time off to allow time for installation and testing. The carrier sends an email to the project manager stating that one appointment is delayed by 2 days. What does the project manager need to do now? | Inform the project team only. | Inform the relevant stakeholders. | Inform the project sponsor. | Inform the product owner. |  | B | When a scheduled event affecting project timelines is delayed, the PM must communicate this change to all relevant stakeholders promptly. Clear and timely communication ensures everyone can adjust their schedules and expectations accordingly. This is a fundamental aspect of project integration management and stakeholder engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 기술자가 원격 콜센터 에이전트 3명의 집에 인터넷을 설치할 예정이었으나 4일 후로 연기되었다. PM은 누구에게 알려야 하는가? | 프로젝트 팀만 | 관련 이해관계자 | 프로젝트 스폰서 | 제품 책임자 |  | B | 프로젝트 타임라인에 영향을 주는 일정 변경이 있을 때, PM은 모든 관련 이해관계자에게 즉시 알려야 한다. 명확하고 시기적절한 커뮤니케이션이 모든 사람이 조정할 수 있게 한다. 팀만(A)은 범위가 좁다. 스폰서만(C)은 불완전하다. PO만(D)도 불완전하다.
1396 | During a project iteration, half of the project team was reallocated to a new project. How should the project lead handle the situation? | Raise the issue with the project stakeholders to analyze the project impact and take the proper actions. | Raise the issue with the product owner to bring additional resources to the project team. | Raise the risk of having the velocity impacted for the current iteration and discuss it with the product owner. | Raise the risk with the project stakeholders and wait until the velocity for the current iteration is calculated. |  | C | The correct answer is C. Raise the risk of having the velocity impacted for the current iteration and discuss it with the product owner. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration and ensure value delivery while adhering to agile principles. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 이터레이션 중 팀의 절반이 새 프로젝트로 재배치되었다. 프로젝트 리더는 무엇을 해야 하는가? | 프로젝트 이해관계자에게 이슈를 제기하여 영향을 분석하고 적절한 조치를 취한다 | 제품 책임자에게 이슈를 제기하여 추가 자원을 확보한다 | 현재 이터레이션의 속도에 영향을 받을 리스크를 제기하고 제품 책임자와 논의한다 | 이해관계자에게 리스크를 제기하고 현재 이터레이션의 속도가 측정될 때까지 기다린다 |  | C | 정답은 C이다. 현재 이터레이션의 속도에 영향을 받을 리스크를 제기하고 제품 책임자와 논의한다. 애자일에서 속도 영향을 조기에 식별하고 제품 책임자와 논의하여 백로그 우선순위를 조정한다. 이해관계자 분석(A)은 즉각적이지 않다. 추가 자원(B)은 즉시 가용하지 않을 수 있다. 대기(D)는 수동적이다.
1397 | An established project team with a good track record has been working on a project for one year. The project manager trusts the team and the work they produce. Which term describes the project manager's management approach? | Laissez-faire | Transformational | Charismatic | Transactional |  | A | Laissez-faire management is a hands-off approach where the leader provides resources and advice when needed but otherwise does not interfere with the team's work. This style is most effective with experienced, highly competent, and self-directed teams. Since the project manager trusts the team and their output after a year of good performance, this describes a laissez-faire approach. Transformational (B) involves inspiring change and innovation. Charismatic (C) relies on the leader's personal charm and vision. Transactional (D) involves direct exchanges of rewards for performance. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 우수한 실적의 경험 있는 팀이 1년간 프로젝트를 진행 중이다. PM이 팀을 신뢰한다. 가장 적절한 관리 스타일은? | 자유방임(Laissez-faire) | 변혁적(Transformational) | 카리스마적(Charismatic) | 거래적(Transactional) |  | A | 자유방임 관리는 리더가 필요할 때 자원과 조언을 제공하지만 팀의 작업에 간섭하지 않는 방식이다. 경험 있고 신뢰할 수 있는 팀에 가장 효과적이다. 변혁적(B)은 변화가 필요할 때 적합하다. 카리스마적(C)은 영감에 의존한다. 거래적(D)은 보상/처벌 기반이다.
1398 | A project has progressed significantly and is getting close to completion. The project manager observed that team members are no longer focused and have started arriving to work late. What should the project manager do? | Engage functional managers to secure roles for team members. | Penalize team members who arrive to work late. | Ask for replacement project team members. | Hold motivation sessions to keep team member morale high. |  | D | The correct answer is D. Hold motivation sessions to keep team member morale high. Resource management includes ensuring team members have the necessary skills and support. The PM should identify gaps and address them through training, mentoring, or other appropriate measures. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Integration & General PM | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트가 상당히 진행되어 완료에 가깝다. 팀원들이 성과가 저하되고 있다. PM은 무엇을 해야 하는가? | 기능 관리자와 협력하여 팀원의 역할을 확보한다 | 늦게 출근하는 팀원을 벌칙한다 | 대체 프로젝트 팀원을 요청한다 | 동기 부여 세션을 개최하여 팀원 사기를 높인다 |  | D | 정답은 D이다. 동기 부여 세션을 개최하여 팀원 사기를 높인다. 프로젝트 종료에 가까워지면 팀원들이 미래 역할에 불안해할 수 있다. 동기 부여와 인정이 사기를 유지한다. 역할 확보(A)는 PM 권한 밖일 수 있다. 벌칙(B)은 부정적이다. 대체(C)는 과도하다.
1399 | A company has a transformation project in progress. During a planning session, several stakeholders are in constant disagreement and often use personal arguments to support their position. Team members are getting frustrated with the situation. What should the project manager have done to avoid this situation? | Established ground rules before the discussion had started. | Asked stakeholders not to voice their opinions during the meeting. | Reinforced that higher-level management has the decision power. | Invited a high-level sponsor to the meeting to reduce the level of disagreement. |  | A | When stakeholders are in constant disagreement using personal arguments during planning, frustrating team members, the project manager should have established ground rules before the discussion started. Ground rules set behavioral expectations. Asking stakeholders not to voice opinions (B) stifles participation. Reinforcing management decision power (C) is authoritarian. Inviting a high-level sponsor (D) does not address behavior. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 전환 프로젝트의 계획 세션에서 여러 이해관계자가 개인적 논쟁으로 계속 불일치한다. PM이 이전에 무엇을 했어야 하는가? | 토론 시작 전에 기본 규칙을 수립했다 | 이해관계자에게 회의 중 의견을 말하지 않도록 요청했다 | 상위 경영진이 결정권을 가진다고 강조했다 | 불일치 수준을 줄이기 위해 고위 스폰서를 회의에 초대했다 |  | A | 이해관계자가 개인적 논쟁으로 계속 불일치할 때, PM은 토론 시작 전에 기본 규칙을 수립했어야 한다. 기본 규칙이 건설적 토론을 위한 행동 기대치를 설정한다. 의견 제한(B)은 참여를 억압한다. 경영진 결정권(C)은 협업을 무시한다. 스폰서 초대(D)는 위압적이다.
1400 | During the requirements gathering and analysis stage for the project, the team members are debating some functionality issues that are expected to be included in the scope. Due to this discussion, the planning activity for the scope definition is running late. What should the project manager do? | Ask team members to document all points that will need to be refined later. | Timebox the team members' debate to ensure the activity is completed on time. | Review expectations with all team members who are working on this activity. | Discuss the issue with the team members who are delaying the activity. |  | B | When team debate over functionality delays the scope definition activity, the project manager should timebox the team members' debate to ensure the activity is completed on time. Timeboxing sets a fixed duration for discussion, then forces a decision, escalation, or follow-up action—balancing thoroughness with delivery discipline. Documenting points for later refinement (A) defers critical decisions. Reviewing expectations (C) may help but does not create a practical control. Discussing the delay with team members (D) addresses the symptom without implementing a facilitation technique. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 요구사항 수집 및 분석 단계에서 팀원이 기능에 대해 토론하고 있어 범위 정의 활동이 지연된다. PM은 무엇을 해야 하는가? | 팀원에게 나중에 정제할 모든 사항을 문서화하도록 요청한다 | 활동이 제시간에 완료되도록 팀원의 토론에 타임박스를 설정한다 | 이 활동에 참여하는 모든 팀원과 기대치를 검토한다 | 활동을 지연시키는 팀원과 이슈를 논의한다 |  | B | 팀 토론이 범위 정의 활동을 지연시킬 때, PM은 토론에 타임박스를 설정하여 활동이 제시간에 완료되도록 해야 한다. 타임박싱이 고정된 시간 제한을 설정하여 토론을 집중시킨다. 문서화(A)는 완료를 보장하지 않는다. 기대치 검토(C)는 일반적이다. 특정 팀원 논의(D)는 개인을 겨냥한다.
1401 | A project manager for a building construction project is planning to go on vacation midway through the project execution phase. What should the project manager do first to ensure the team is empowered and deadlines are met? | Postpone the vacation to a different time. | Analyze the impacts and create a plan for team decision making | Ask the project sponsor to make any necessary decisions. | Allow the team to make decisions to stay on schedule. |  | B | Before going on vacation midway through execution, the project manager should analyze the impacts and create a plan for team decision-making. This prepares the team with clear authority, escalation paths, and decision-making guidelines during the PM's absence. Postponing the vacation (A) may not be feasible and affects work-life balance. Asking the sponsor to make decisions (C) burdens the sponsor unnecessarily. Allowing the team to make all decisions without a plan (D) risks inconsistency and scope creep. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 건설 프로젝트 PM이 실행 중반에 휴가를 계획한다. PM은 무엇을 해야 하는가? | 휴가를 다른 시간으로 연기한다 | 영향을 분석하고 팀 의사결정을 위한 계획을 수립한다 | 프로젝트 스폰서에게 필요한 결정을 하도록 요청한다 | 팀이 일정에 맞추기 위해 결정하도록 허용한다 |  | B | PM이 실행 중반에 휴가를 갈 때, 영향을 분석하고 팀 의사결정을 위한 계획을 수립해야 한다. 명확한 권한, 에스컬레이션 경로, 의사결정 기준을 준비한다. 연기(A)는 불필요하다. 스폰서 결정(C)은 스폰서 역할이 아니다. 무조건 허용(D)은 준비 없는 위임이다.
1402 | A virtual product development team is working well together and is on schedule. One team member wants to take 1 week off to attend a training. What should the project manager do? | Decline the team member ' s request as it might jeopardize the schedule. | Approve the team member ' s request as it will increase motivation. | Approve the team member ' s request on condition they work additional hours when they return from training. | Decline the team member ' s request since the goal is not individual team member advancement. |  | B | The correct answer is B. Approve the team member ' s request as it will increase motivation. Schedule management requires proactive monitoring and appropriate corrective actions. The PM should analyze impacts and implement suitable responses to maintain project timelines. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 가상 제품 개발 팀이 잘 협력하고 일정에 맞다. 팀원이 교육을 위해 1주 휴가를 원한다. PM은 무엇을 해야 하는가? | 일정을 위험에 빠뜨릴 수 있으므로 팀원의 요청을 거절한다 | 동기 부여를 높일 것이므로 팀원의 요청을 승인한다 | 복귀 후 추가 근무 조건으로 요청을 승인한다 | 개인 팀원의 발전이 아닌 목표이므로 요청을 거절한다 |  | B | 정답은 B이다. 동기 부여를 높일 것이므로 요청을 승인한다. 팀이 잘 작동하고 일정에 맞는 상황에서 교육 기회는 팀원의 성장과 동기 부여를 촉진한다. 거절(A)은 일정 위험이 낮을 때 불필요하다. 추가 근무 조건(C)은 처벌적이다. 발전 목표 아님(D)은 팀원 발전을 무시한다.
1403 | A project team that is very experienced in enterprise resource planning (ERP) systems implementation is currently planning the delivery of a new ERP project. There is a requirement to reuse the client's security subsystem developed by a third party. The client states that integration with the security subsystem must be done by the client's team. The project manager does not want to have such an external dependency. What should the project manager do first? | Plan the implementation of this integration in the first iteration to help reduce risks. | Inform the client that the project team will take care of the integration. | Document the client ' s responsibility for the integration with the security subsystem. | Record the issue in the issue log and closely manage this dependency. |  | C | When the client requires their team to handle integration with a third-party security subsystem, the project manager should first document the client's responsibility for the integration. Clear documentation defines project boundaries and role clarity. Planning the integration in the first iteration (A) disregards the client's stated requirement. Informing the client the project team will handle it (B) ignores the client's directive. Recording in the issue log (D) can follow documentation. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Scope | Planning | Adopt a Holistic View | Collect Requirements | Traditional PM | ERP 시스템 구현에 경험이 많은 프로젝트 팀이 새 ERP 구현을 계획 중이다. 고객이 제3자 보안 하위 시스템과의 통합을 자체 팀으로 처리하겠다고 한다. PM은 무엇을 먼저 해야 하는가? | 리스크를 줄이기 위해 첫 이터레이션에서 이 통합 구현을 계획한다 | 프로젝트 팀이 통합을 처리할 것이라고 고객에게 알린다 | 보안 하위 시스템과의 통합에 대한 고객의 책임을 문서화한다 | 이슈 로그에 이슈를 기록하고 이 종속성을 면밀히 관리한다 |  | C | 고객이 제3자 보안 하위 시스템과의 통합을 자체 처리하겠다고 할 때, PM은 먼저 고객의 책임을 문서화해야 한다. 명확한 문서화가 책임과 기대를 설정한다. 첫 이터레이션 계획(A)은 고객 결정을 무시한다. 프로젝트 팀 처리(B)는 고객 요청과 반대이다. 이슈 로그(D)는 이슈가 아닌 합의 사항이다.
1404 | There is frequent conflict between two project team members working on a project. This has caused a negative impact on the project. How should the project manager handle this situation? | Help cultivate self-awareness between the two team members through emotional intelligence (El). 1007 | Escalate the issue to the human resources (HR) manager before a larger problem develops. | Counsel both team members and caution them with a final warning. | Relocate the two project team members into different project teams. |  | A | When frequent conflict between two team members negatively impacts the project, the project manager should help cultivate self-awareness between them through emotional intelligence. EI builds lasting resolution skills. Escalating to HR (B) is heavy-handed. Counseling with a final warning (C) is punitive. Relocating team members (D) avoids the root cause. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 두 프로젝트 팀원 간 빈번한 갈등이 프로젝트에 부정적 영향을 미친다. PM은 무엇을 해야 하는가? | 감정 지능(EI)을 통해 두 팀원 간 자기 인식을 배양하도록 돕는다 | 더 큰 문제가 발생하기 전에 HR 관리자에게 이슈를 에스컬레이션한다 | 두 팀원을 상담하고 최종 경고를 한다 | 두 팀원을 다른 프로젝트 팀으로 재배치한다 |  | A | 두 팀원 간 빈번한 갈등이 프로젝트에 부정적 영향을 미칠 때, PM은 감정 지능을 통해 자기 인식을 배양해야 한다. EI가 지속적인 행동 변화를 구축한다. HR 에스컬레이션(B)은 직접 해결 시도 후에 한다. 최종 경고(C)는 처벌적이다. 재배치(D)는 갈등을 해결하지 않는다.
1405 | A product owner is invited to a sprint review meeting. At the end of the review, the product owner says that the increment is ready to be delivered to the customer. What conclusion should the project manager come to with regard to the product owner's statement? | The product owner does not have visibility into what the team has done in the product increment. | The product owner has evaluated the product against the definition of done (DoD). | The product owner trusts the team and is marking the product as complete. | The product owner will release the product to customers without showing them a demo. |  | B | When the product owner states the increment is ready to deliver to the customer at the end of a sprint review, the conclusion is that the product owner has evaluated the product against the definition of done (DoD). The DoD ensures quality standards are met before release. Lacking visibility into team work (A) contradicts the review attendance. Trusting the team and marking it complete (C) implies insufficient evaluation. Releasing without a demo (D) contradicts the sprint review context. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 제품 책임자가 스프린트 리뷰 회의에 초대되었다. 리뷰 끝에 제품 책임자가 증분이 고객에게 전달할 준비가 되었다고 말한다. 이 결론은? | 제품 책임자가 팀이 제품 증분에서 한 것에 대한 가시성이 없다 | 제품 책임자가 완료 정의(DoD)에 대해 제품을 평가했다 | 제품 책임자가 팀을 신뢰하고 제품을 완료로 표시하고 있다 | 제품 책임자가 데모 없이 고객에게 제품을 출시할 것이다 |  | B | 제품 책임자가 스프린트 리뷰 끝에 증분이 전달 준비가 되었다고 말하면, 이는 완료 정의(DoD)에 대해 제품을 평가했다는 의미이다. DoD가 인도 가능한 품질 기준이다. 가시성 부족(A)은 리뷰에 참석했으므로 해당 안 됨. 단순 신뢰(C)는 평가 없는 판단이다. 데모 없는 출시(D)는 리뷰 목적에 반한다.
1406 | Due to unforeseen circumstances, a contractor was unable to mobilize the project team, which was necessary to conduct face-to-face meetings and discussions. Virtual meetings were subsequently put in place, but the local project team and end users now face a communication gap that is causing the team's low performance. What should the project manager do? | Ask the contractor to solve this problem because this is a contractual obligation. | Terminate the contract and initiate a new one with a local contractor. | Reassess continually to remove blockers for the team. | Implement key performance indicators (KPIs) and convince the contractor to engage the team. |  | C | Virtual teams require the PM to actively manage communication and coordination challenges. The PM should continuously reassess the situation to identify and remove blockers hindering effective collaboration. While implementing KPIs can support performance monitoring, KPIs alone cannot resolve underlying communication issues. Terminating contracts or expecting contractors to solve problems independently contradicts the proactive, engaged management approach essential for virtual team success. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 예기치 못한 상황으로 계약자가 팩토리 승인 테스트를 위한 프로젝트 팀을 동원하지 못했다. PM은 무엇을 해야 하는가? | 계약 의무이므로 계약자에게 이 문제를 해결하도록 요청한다 | 계약을 해지하고 현지 계약자와 새 계약을 시작한다 | 지속적으로 재평가하여 팀의 장애 요소를 제거한다 | KPI를 구현하고 계약자가 팀을 참여시키도록 설득한다 |  | C | 가상 팀은 PM이 커뮤니케이션과 조정 과제를 적극적으로 관리해야 한다. PM은 상황을 지속적으로 재평가하여 효과적 협업을 방해하는 장애 요소를 식별하고 제거해야 한다. 계약자에게 요청(A)은 수동적이다. 계약 해지(B)는 과도하다. KPI 구현(D)은 즉각적 문제를 해결하지 않는다.
1407 | A Scrum team has information radiators but must also keep stakeholders aware of their progress. In addition, the project management office (PMO) has specific templates for status reporting to management. The project lead realizes that a variety of reporting will be needed to satisfy enterprise and stakeholder needs. What should the project lead do? | Document only the plan for written communications, and send meeting invites for verbal communication sessions. | Create a communications management plan informing all project team members and stakeholders who will receive what type of communication. | Follow the project management office (PMO) guidelines for communications instead of generating a project communications management plan. | Determine the minimum communications needed for the project, and adapt the communication plans as needed. |  | B | When a Scrum team must satisfy both agile information radiators and PMO-specific reporting templates, the project lead should create a communications management plan informing all team members and stakeholders who will receive what type of communication. This plan integrates agile practices with organizational requirements, ensuring comprehensive coverage. Documenting only written communications (A) is incomplete. Following only PMO guidelines (C) ignores project-specific needs. Determining minimum communications and adapting (D) may underserve stakeholder requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 스크럼 팀이 정보 방열기를 사용하지만 이해관계자에게도 진행 상황을 알려야 한다. PMO가 특정 보고 템플릿을 요구한다. PM은 무엇을 해야 하는가? | 서면 커뮤니케이션 계획만 문서화하고 구두 커뮤니케이션은 회의 초대를 보낸다 | 모든 팀원과 이해관계자에게 누가 어떤 정보를 받을지 알리는 커뮤니케이션 관리 계획을 작성한다 | 프로젝트별 계획 대신 PMO 가이드라인을 따른다 | 프로젝트에 필요한 최소한의 커뮤니케이션을 결정하고 필요에 따라 적응한다 |  | B | 스크럼 팀이 애자일 정보 방열기와 PMO 보고 템플릿을 모두 충족해야 할 때, PM은 모든 팀원과 이해관계자에게 정보 배포를 알리는 커뮤니케이션 관리 계획을 작성해야 한다. 포괄적 계획이 양쪽 요구를 충족한다. 서면만(A)은 불완전하다. PMO만 따르기(C)는 애자일을 무시한다. 최소 커뮤니케이션(D)은 요구사항을 충족하지 못할 수 있다.
1408 | During project execution, a project manager is informed that most of the project team members have enrolled in the newly implemented work-from-home company policy. How should the project manager reflect this change in the project? | Update roles and responsibilities for enrolled team members in the responsibility assignment matrix (RAM) | Update the resource calendar for enrolled team members in the resource management plan | Update the stakeholder engagement plan to include the emergency contact information for enrolled team members. | Update the communication styles for enrolled team members in the communications management plan. |  | B | When team members enroll in a work-from-home policy, the PM should update the resource calendar to reflect their availability and working hours. The resource calendar captures human and physical resource availability and may affect the project schedule, budget, quality, and risk. Communication styles, roles and responsibilities, and the stakeholder engagement plan are not directly impacted by this change in resource availability. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 실행 중 대부분의 팀원이 새 재택근무 정책에 등록했다. PM은 무엇을 먼저 업데이트해야 하는가? | 책임 배정 매트릭스(RAM)에서 등록된 팀원의 역할과 책임을 업데이트한다 | 자원 관리 계획에서 등록된 팀원의 자원 캘린더를 업데이트한다 | 등록된 팀원의 비상 연락처를 포함하도록 이해관계자 참여 계획을 업데이트한다 | 커뮤니케이션 관리 계획에서 등록된 팀원의 커뮤니케이션 스타일을 업데이트한다 |  | B | 팀원이 재택근무 정책에 등록할 때, PM은 자원 캘린더를 업데이트하여 가용성과 근무 시간을 반영해야 한다. 자원 캘린더가 인적·물적 자원의 가용성을 포착한다. RAM 업데이트(A)는 역할 변경 시 필요하다. 비상 연락처(C)는 우선이 아니다. 커뮤니케이션 스타일(D)은 부차적이다.
1409 | A project manager has begun a complex oil refinery project. Although the project is in the initiation phase, the sponsor keeps asking for concrete dates for the most important project milestones. When will the project manager be able to provide the requested information? | Close to the end of the project, as the forecasts will be more accurate and most risks will already be mitigated | During the planning phase, when processes for scope definition and activity duration and sequencing will be performed | In the initiation process, as it happens concurrently with the project contract and project charter creation | As soon as possible, as project delays can be significantly avoided when a schedule is developed early |  | B | When the sponsor keeps asking for concrete milestone dates during initiation of a complex project, the project manager will be able to provide this information during the planning phase when scope definition, activity duration, and sequencing processes are performed. Planning produces detailed schedules. Initiation (C) creates the charter, not detailed schedules. Close to project end (A) defeats the purpose. As soon as possible (D) may provide inaccurate early estimates. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | PM이 복잡한 정유소 프로젝트를 시작했다. 착수 단계이지만 스폰서가 구체적 마일스톤 일정을 계속 묻는다. 언제 정보를 제공할 수 있는가? | 프로젝트 끝에 가까울 때, 예측이 더 정확하고 대부분의 리스크가 이미 발생했을 때 | 계획 단계에서, 범위 정의와 활동 기간 및 순서 결정 프로세스가 수행될 때 | 착수 프로세스에서, 프로젝트 계약 및 헌장과 동시에 발생하므로 | 가능한 빨리, 일정이 조기에 개발되면 프로젝트 지연을 크게 피할 수 있으므로 |  | B | 복잡한 프로젝트의 착수 단계에서 스폰서가 구체적 마일스톤 일정을 요구할 때, PM은 계획 단계에서 범위 정의와 활동 기간 및 순서 결정이 수행될 때 정보를 제공할 수 있다. 착수 단계에서는 충분한 정보가 없다. 프로젝트 끝(A)은 너무 늦다. 착수 시(C)는 정보가 부족하다. 조기 일정(D)은 정확하지 않다.
1410 | A new file vault system vendor is being considered by a project sponsor who has supported several projects over the previous year. What should the project manager review to assist the sponsor on the decision? | Lessons learned database | Vendor ' s website | Procurement strategy | Appropriate financial regulations |  | A | When evaluating a new file vault system vendor, the project manager should review the lessons learned database. This resource contains historical information from past projects that provides insights into vendor performance, reliability, challenges, and successes with similar procurements—enabling informed vendor selection decisions. The vendor's website (B) provides the vendor's own marketing perspective, not objective project experience. The procurement strategy (C) guides the procurement approach but does not evaluate specific vendors. Financial regulations (D) address compliance requirements, not vendor performance. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트 스폰서가 새 파일 볼트 시스템 벤더를 고려하고 있다. PM은 어디에서 벤더에 대한 도움이 되는 정보를 검토해야 하는가? | 교훈 데이터베이스 | 벤더 웹사이트 | 조달 전략 | 적절한 재무 규정 |  | A | 새 파일 볼트 시스템 벤더를 평가할 때, PM은 교훈 데이터베이스를 검토해야 한다. 이 자원은 과거 프로젝트의 역사적 정보를 포함하여 벤더 선택에 대한 통찰을 제공한다. 벤더 웹사이트(B)는 편향된 정보이다. 조달 전략(C)은 벤더 평가가 아니다. 재무 규정(D)은 벤더 선택과 무관하다.
1411 | A complex project has a well-established responsibility assignment matrix (RAM). One of the critical stakeholders flagged a task as an issue because it was not completed and has remained open for some time. What should the project manager do? | Identify who owns this task and discuss the situation with them. | Assign a project team member to complete the open task. | Determine a decision-making authority for task accountability. | Influence the stakeholder not to flag the task as an issue. |  | A | When a critical stakeholder flags a task as an issue because it remains open in a project with a well-established RAM, the project manager should identify who owns the task and discuss the situation with them. The RAM defines accountability. Assigning another team member (B) bypasses accountability. Determining decision-making authority (C) creates redundancy when RAM exists. Influencing the stakeholder not to flag it (D) dismisses a legitimate concern. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 복잡한 프로젝트에 잘 수립된 RAM이 있다. 주요 이해관계자가 미완료 작업을 이슈로 플래그했다. PM은 무엇을 해야 하는가? | 이 작업의 소유자를 식별하고 상황을 논의한다 | 프로젝트 팀원을 배정하여 미완료 작업을 완료한다 | 작업 책임에 대한 의사결정 권한을 결정한다 | 이해관계자가 작업을 이슈로 플래그하지 않도록 영향을 미친다 |  | A | 주요 이해관계자가 RAM이 수립된 프로젝트에서 미완료 작업을 이슈로 플래그할 때, PM은 작업 소유자를 식별하고 상황을 논의해야 한다. RAM이 책임을 명확히 정의하므로 소유자 확인이 첫 단계이다. 팀원 배정(B)은 기존 할당을 무시한다. 의사결정 권한(C)은 RAM이 이미 존재한다. 플래그 방지(D)는 문제를 숨긴다.
1412 | During project execution, the project manager observes lower velocity and a high volume of tasks in the testing queue. The project is using a hybrid approach and there are only a few sprints remaining. What should the project manager do? | Provide testing training to all the project team members | Work with the team to understand and solve the issues | Add a new resource with testing skills to the team | Increase the sprint duration so the testing can be completed |  | B | When observing lower velocity and a high testing queue volume in a hybrid project with few sprints remaining, the project manager should work with the team to understand and solve the issues. Identifying bottlenecks and root causes enables targeted corrective action. Providing testing training to all members (A) assumes a skill gap without diagnosis. Adding a testing resource (C) may not address the root cause. Increasing sprint duration (D) disrupts the team's cadence without solving underlying problems. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Hybrid/Tailoring | 하이브리드 프로젝트에서 속도가 낮아지고 테스트 대기열에 작업이 많다. 스프린트가 몇 개 남지 않았다. PM은 무엇을 해야 하는가? | 모든 팀원에게 테스트 교육을 제공한다 | 팀과 함께 문제를 이해하고 해결한다 | 테스트 기술을 가진 새 자원을 팀에 추가한다 | 테스트를 완료할 수 있도록 스프린트 기간을 늘린다 |  | B | 속도 저하와 테스트 대기열 증가 시, PM은 팀과 함께 문제를 이해하고 해결해야 한다. 근본 원인 식별이 효과적 해결의 기초이다. 테스트 교육(A)은 원인 파악 전에 성급하다. 자원 추가(C)는 원인 이해 후에 고려한다. 스프린트 연장(D)은 일정 지연을 야기한다.
1413 | A project manager for a large software delivery project is in the process of finalizing the project governance. The project manager would like to implement procedures that do not align with several policies required by the organization's project management office (PMO). The project manager believes that the procedures outlined in the project governance will be necessary for this particular project due to the unique nature of the technology. What should the project manager do? | Move forward with the project governance and inform the PMO. | Disregard the initial procedures and follow the policies outlined by the PMO, | Discuss the proposed changes with the PMO. | Engage stakeholders to modify policies outlined by the PMO. |  | C | When a project manager wants to implement governance procedures that do not align with PMO policies due to the project's unique technology, the project manager should discuss the proposed changes with the PMO. Collaborative discussion may result in approved exceptions. Moving forward without PMO alignment (A) bypasses governance. Disregarding initial procedures (B) ignores project needs. Engaging stakeholders to modify PMO policies (D) oversteps boundaries. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | PM이 프로젝트 거버넌스를 마무리 중이다. 고유한 기술로 인해 PMO 정책과 맞지 않는 절차를 구현하려 한다. PM은 무엇을 해야 하는가? | 프로젝트 거버넌스를 진행하고 PMO에 알린다 | 초기 절차를 무시하고 PMO가 정한 정책을 따른다 | 제안된 변경사항을 PMO와 논의한다 | 이해관계자를 참여시켜 PMO가 정한 정책을 수정한다 |  | C | PM이 프로젝트 고유 기술로 인해 PMO 정책과 다른 거버넌스 절차를 원할 때, 제안된 변경사항을 PMO와 논의해야 한다. 협력적 접근이 프로젝트 요구와 조직 표준을 조화시킨다. 진행 후 알림(A)은 승인 없이 행동한다. 무시(B)는 프로젝트 요구를 무시한다. 정책 수정(D)은 과도하다.
1414 | A company is building a minimum viable product (MVP). How should the project manager help to ensure the company builds a high-quality product? | Partner with a qualified third-party vendor to develop a product that meets the requirements. | Determine the quality metrics for the product and recommend options for improvements. | Ask the product manager to spend more time improving quality. | Hire a quality engineering leader to drive the strategy. |  | B | When building an MVP, the project manager should determine quality metrics for the product and recommend options for improvements. Defined metrics ensure quality is measured and managed throughout development. Partnering with a third-party vendor (A) outsources responsibility. Asking the product manager to spend more time on quality (C) is vague. Hiring a quality engineering leader (D) may be unnecessary for an MVP. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 회사가 MVP를 구축 중이다. PM은 품질 좋은 제품 구축을 어떻게 보장해야 하는가? | 자격 있는 서드파티 벤더와 협력하여 요구사항에 맞는 제품을 개발한다 | 제품의 품질 지표를 결정하고 개선 옵션을 추천한다 | 제품 관리자에게 품질 개선에 더 많은 시간을 투자하도록 요청한다 | 품질 엔지니어링 리더를 고용하여 전략을 추진한다 |  | B | MVP를 구축할 때, PM은 제품의 품질 지표를 결정하고 개선 옵션을 추천해야 한다. 정의된 지표가 개발 전반에 걸쳐 품질을 측정하고 관리하도록 보장한다. 서드파티(A)는 내부 역량을 활용하지 않는다. 더 많은 시간(C)은 구체적이지 않다. 리더 고용(D)은 MVP 단계에서 과도하다.
1415 | A project manager has been managing an agile project for 6 months. Over the last two iterations, the team velocity has decreased due to a new technology that was needed for the product. What should the project manager do to continue with the delivery plan and return to the expected velocity? | Reevaluate the backlog by looking for high-value/low-effort items, and negotiate a new minimum viable product (MVP) strategy with key stakeholders. | Replace poorly performing team members with more experienced members, setting an example of accountability for the team. | Use retrospectives to better understand the new technology ' s impact on the schedule, map the skill gaps, and adjust the team accordingly. | Seek sponsor approval for additional funding to hire new team members, increasing the capacity of the team and compensating for the productivity lost with the new technology. |  | C | When team velocity decreases due to a new technology introduction, the project manager should use retrospectives to better understand the technology's impact on the schedule, map skill gaps, and adjust the team accordingly. Retrospectives enable reflection, root cause identification, and data-driven process improvements. Reevaluating the backlog for high-value/low-effort items (A) adjusts scope but does not address the team's capability gap. Replacing team members (B) is disruptive and does not build organizational capability. Seeking additional funding for new hires (D) increases cost without first leveraging existing team learning. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 6개월간 애자일 프로젝트를 관리 중이다. 최근 2개 이터레이션에서 새 기술 도입으로 속도가 감소했다. PM은 무엇을 해야 하는가? | 백로그에서 고가치/저노력 항목을 찾아 재평가하고 새 MVP를 협상한다 | 저성과 팀원을 경험 있는 팀원으로 교체하여 책임의 본보기를 보인다 | 회고를 사용하여 새 기술의 일정 영향을 이해하고 기술 격차를 매핑하여 교육을 조정한다 | 추가 자금을 위한 스폰서 승인을 구하여 새 팀원을 고용하고 팀 역량을 증가시킨다 |  | C | 새 기술 도입으로 속도가 감소할 때, PM은 회고를 사용하여 기술의 일정 영향을 이해하고 기술 격차를 매핑하여 교육을 조정해야 한다. 데이터 기반 분석이 적절한 대응을 가능하게 한다. 백로그 재평가(A)는 범위 축소이다. 팀원 교체(B)는 학습 기회를 빼앗는다. 추가 고용(D)은 기술 격차를 해결하지 않는다.
1416 | The change control board (CCB) rejects a change request submitted by a subject matter expert (SME). The SME refuses to accept this rejection and does not want to continue the project without the change. What should the project manager have done to avoid this situation? | Assessed the change ' s overall impact to the project before submission | Ensured that the change request was aligned with the project scope | Submitted the change request directly to the CCB | Requested that the sponsor approved the change request first. |  | A | When the CCB rejects a change request and the SME refuses to continue without it, the project manager should have assessed the change's overall impact to the project before submission. Thorough impact assessment prepares for CCB deliberation and stakeholder communication. Ensuring alignment with scope (B) is one aspect of assessment. Submitting directly to CCB (C) skips impact analysis. Requesting sponsor pre-approval (D) bypasses the CCB process. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | CCB가 SME가 제출한 변경 요청을 거부했다. SME가 변경 없이 작업을 계속하길 거부한다. PM이 이전에 무엇을 했어야 하는가? | 제출 전 변경이 프로젝트에 미치는 전반적 영향을 평가했다 | 변경 요청이 프로젝트 범위와 일치하는지 확인했다 | 변경 요청을 CCB에 직접 제출했다 | 스폰서가 먼저 변경 요청을 승인하도록 요청했다 |  | A | CCB가 변경 요청을 거부하고 SME가 작업을 거부할 때, PM은 제출 전에 변경의 전반적 프로젝트 영향을 평가했어야 한다. 철저한 영향 분석이 더 나은 제출과 이해관계자 조율을 가능하게 한다. 범위 일치 확인(B)은 부분적이다. 직접 제출(C)은 분석 없는 행동이다. 스폰서 승인(D)은 CCB 프로세스를 우회한다.
1417 | A project team member finishes all assigned tasks in the middle of a sprint. The team member wants to plan tasks for the next sprint to deliver business value earlier. The team member has the abilities and knowledge to execute tasks not yet started by other team members in the current sprint. What should the project manager do? | Reassign the team member to other tasks in the current sprint | Encourage the team member to execute the next sprint tasks | Validate completeness of the tasks delivered in the current sprint | Increase team velocity to execute tasks for the next sprints |  | A | In agile, the team should complete sprint commitments before pulling in future work. If a team member has spare capacity, they should help with unfinished current-sprint items to improve the likelihood that all committed backlog items meet the Definition of Done. Validating completeness (A) is important but secondary to finishing work. Artificially increasing velocity (B) can harm quality. Starting next-sprint tasks early (D) risks undermining sprint planning and creating partial work. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Finance | Monitoring & Controlling | Embed Quality | Control Costs | Traditional PM | 팀원이 스프린트 중간에 할당된 모든 작업을 완료했다. 다음 스프린트 작업을 계획하려 한다. PM은 무엇을 해야 하는가? | 팀원을 현재 스프린트의 다른 작업에 재배정한다 | 팀원이 다음 스프린트 작업을 실행하도록 격려한다 | 현재 스프린트에서 전달된 작업의 완전성을 검증한다 | 다음 스프린트 작업을 실행하기 위해 팀 속도를 증가시킨다 |  | A | 애자일에서 팀은 미래 작업을 가져오기 전에 스프린트 약속을 완료해야 한다. 여유 역량이 있으면 현재 스프린트의 미완료 항목을 도와야 한다. 다음 스프린트 실행(B)은 현재 스프린트 범위를 벗어난다. 완전성 검증(C)은 재배정보다 부차적이다. 속도 증가(D)는 인위적이다.
1418 | The client will not agree to closure, claiming that the project team has not performed the code inspections mandated in the development contract. The project team has performed the code inspections; however, the records are not complete. What should the project manager do? | Seek expert legal advice on the interpretation of the clauses in the contract | Close the project and hand over the deliverables to the client | Hold a meeting with the project team project sponsor and the client to agree to the further work required to close the project and add to lessons learned | Hold a lessons learned workshop with the project team and project sponsor to avoid contractual compliance issues arising in future projects |  | C | When a client refuses closure claiming code inspections were not performed despite incomplete records, the project manager should hold a meeting with the project team, sponsor, and client to agree on further work required and add to lessons learned. Collaborative resolution addresses the gap. Seeking legal advice (A) escalates unnecessarily. Closing and handing over (B) violates contractual requirements. A lessons learned workshop (D) does not resolve the current dispute. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Risk | Closing | Build an Empowered Culture | Close Project or Phase | Traditional PM | 고객이 프로젝트 종료에 동의하지 않으며 계약에 명시된 코드 검사가 수행되지 않았다고 주장한다. PM은 무엇을 해야 하는가? | 계약 조항 해석에 대한 전문 법률 자문을 구한다 | 프로젝트를 종료하고 인도물을 고객에게 인계한다 | 프로젝트 팀, 스폰서, 고객과 회의를 열어 추가 작업에 합의한다 | 프로젝트 팀과 스폰서와 교훈 워크숍을 개최하여 계약 문제를 방지한다 |  | C | 고객이 코드 검사 미수행을 이유로 종료를 거부할 때, PM은 프로젝트 팀, 스폰서, 고객과 회의를 열어 추가 작업에 합의해야 한다. 협력적 해결이 모든 당사자의 우려를 다룬다. 법률 자문(A)은 적대적이다. 강제 종료(B)는 고객 관계를 훼손한다. 교훈 워크숍(D)은 미래용이지 현재 문제 해결이 아니다.
1419 | A project sponsor would like to include a new deliverable. The sponsor contacts the project manager in order to seek advice on the most efficient approach to complete the deliverable within the next 2 months. What should the project manager do? | Use the management reserve in order to expedite completion of the deliverable within 2 months. | Suggest that the sponsor conduct a cost-benefit analysis to determine feasibility. | Change the project methodology in order to achieve completion of the deliverable within 2 months. | Advise the sponsor that it is not the project manager's job to evaluate the project. |  | B | When the sponsor wants a new deliverable completed within 2 months, the project manager should suggest conducting a cost-benefit analysis to determine feasibility. CBA evaluates whether the deliverable justifies the effort. Using management reserve (A) bypasses proper analysis. Changing methodology (C) is drastic. Advising that evaluation is not the PM's job (D) abdicates responsibility. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 스폰서가 새 인도물을 포함하고 싶어 한다. 2개월 내 완료 가능 여부를 PM에게 자문 구한다. PM은 무엇을 조언해야 하는가? | 관리 예비비를 사용하여 2개월 내 인도물 완료를 촉진한다 | 스폰서에게 실행 가능성을 결정하기 위한 비용-편익 분석을 수행하도록 제안한다 | 2개월 내 인도물 완료를 달성하기 위해 프로젝트 방법론을 변경한다 | 스폰서에게 프로젝트를 평가하는 것이 PM의 업무가 아니라고 조언한다 |  | B | 스폰서가 2개월 내 새 인도물 완료를 원할 때, PM은 비용-편익 분석을 수행하여 실행 가능성을 결정하도록 제안해야 한다. CBA가 인도물의 편익이 비용을 정당화하는지 평가한다. 관리 예비비(A)는 리스크용이지 새 범위용이 아니다. 방법론 변경(C)은 근본 해결이 아니다. 업무 아님(D)은 무책임하다.
1420 | A project manager is working as a servant leader for a pilot project to adopt agile practices. After three sprints, the team demos the product to the main stakeholders, but receives negative feedback about the product's features. The team feels that all the features met the acceptance criteria defined by the product owner and does not understand what went wrong. How should the project manager mitigate the product rejection? | Engage the main stakeholders in the upcoming sprint review sessions. | Share the product backlog for the main stakeholders to review in advance. | Create dedicated sprints to implement feature fixes for the rejected ones. | Ask the project sponsor to evaluate the assignment of a new product owner. |  | A | When stakeholders give negative feedback at a demo despite features meeting acceptance criteria, the project manager should engage main stakeholders in upcoming sprint review sessions. Continuous stakeholder participation ensures alignment. Sharing the backlog for advance review (B) informs but does not engage. Creating dedicated fix sprints (C) is reactive. Evaluating a new product owner (D) assigns blame without evidence. | People | Negotiate Project Agreements | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | PM이 애자일 채택을 위한 파일럿 프로젝트의 서번트 리더로 일하고 있다. 3개 스프린트 후 데모에서 인수 기준을 충족했지만 이해관계자 피드백이 부정적이다. PM은 무엇을 해야 하는가? | 주요 이해관계자를 다가오는 스프린트 리뷰 세션에 참여시킨다 | 주요 이해관계자가 사전에 검토할 수 있도록 제품 백로그를 공유한다 | 거부된 기능의 수정을 구현할 전용 스프린트를 생성한다 | 프로젝트 스폰서에게 새 제품 책임자 배정을 평가하도록 요청한다 |  | A | 인수 기준을 충족했지만 이해관계자 피드백이 부정적일 때, PM은 주요 이해관계자를 다가오는 스프린트 리뷰 세션에 참여시켜야 한다. 지속적 이해관계자 참여가 기대와 결과를 일치시킨다. 백로그 공유(B)는 참여가 아닌 정보 제공이다. 전용 스프린트(C)는 지속적 피드백 없이 반복될 수 있다. PO 교체(D)는 과도하다.
1421 | A project manager has been assigned to lead a project with limited funding and resources. During the requirements brainstorming session, several stakeholders request a long list of requirements for a new project, which exceeds the budget. What should the project manager do first? | Host a requirements workshop and ask the stakeholders to prioritize the requirements based on critical needs. | Meet with the sponsor to obtain their feedback regarding critical requirements in the view of senior management. | Reach out to the sponsor and request additional budget and capacity in order to complete the project. | Review the requirements and determine which of them can be removed, then advise the stakeholders of the changes. |  | A | When stakeholders request requirements exceeding the budget during brainstorming on a limited-funding project, the project manager should first host a requirements workshop and ask stakeholders to prioritize based on critical needs. Prioritization aligns scope with budget. Meeting the sponsor for feedback (B) bypasses stakeholder input. Requesting additional budget (C) may not be feasible. Removing requirements unilaterally (D) ignores stakeholder needs. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 제한된 자금과 자원으로 프로젝트를 이끌고 있다. 요구사항 브레인스토밍 중 이해관계자가 예산을 초과하는 요구사항을 요청한다. PM은 무엇을 먼저 해야 하는가? | 요구사항 워크숍을 개최하고 이해관계자에게 중요도에 따라 요구사항 우선순위를 정하도록 요청한다 | 스폰서와 만나 고위 경영진 관점에서 중요 요구사항에 대한 피드백을 받는다 | 스폰서에게 연락하여 프로젝트 완료를 위한 추가 예산과 역량을 요청한다 | 요구사항을 검토하여 어떤 것을 제거할 수 있는지 결정한 후 이해관계자에게 조언한다 |  | A | 제한된 자금의 프로젝트에서 예산 초과 요구사항이 나올 때, PM은 요구사항 워크숍을 개최하고 이해관계자에게 중요도에 따라 우선순위를 정하도록 해야 한다. 협력적 우선순위화가 제한된 자원 내 최대 가치를 보장한다. 스폰서 피드백(B)은 모든 이해관계자를 포함하지 않는다. 추가 예산(C)은 제한된 자금 현실에 맞지 않다. 일방적 제거(D)는 이해관계자 참여를 무시한다.
1422 | A project manager is working with an agile team to enhance a product. Due to a tight deadline, the team is trying to crash the schedule by engaging multiple resources to work on the project simultaneously. However, the technical environment is configured to allow only one resource to work on a feature at a time. The team plans to upgrade the technical environment but is unable to agree on a way forward. What should the project manager do first? | Conduct a planning session to decide how to approach the next set of work. | Conduct a consensus-building session to decide how to approach the next set of work. | Add this conflict to the agenda for discussion at the next daily standup meeting. | Escalate the issue to the product owner for resolution. |  | B | When the team cannot agree on how to upgrade the technical environment for parallel work on a tight-deadline agile project, the project manager should first conduct a consensus-building session to decide how to approach the next set of work. This collaborative technique ensures all team members participate in the decision, aligning expectations and securing commitment. A planning session (A) focuses on work breakdown, not conflict resolution. Adding to the daily standup agenda (C) delays the decision. Escalating to the product owner (D) bypasses team self-organization. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | PM이 타이트한 기한의 애자일 팀과 작업 중이다. 기술 환경 업그레이드 방법에 대해 팀이 합의하지 못한다. PM은 무엇을 먼저 해야 하는가? | 다음 작업 접근법을 결정하기 위한 계획 세션을 수행한다 | 다음 작업 접근법을 결정하기 위한 합의 구축 세션을 수행한다 | 다음 데일리 스탠드업 회의 안건에 이 갈등을 추가한다 | 해결을 위해 제품 책임자에게 이슈를 에스컬레이션한다 |  | B | 팀이 기술 환경 업그레이드에 합의하지 못할 때, PM은 합의 구축 세션을 수행해야 한다. 합의 기반 의사결정이 팀의 동의와 헌신을 보장한다. 계획 세션(A)은 기술적이지만 갈등 해결이 아니다. 스탠드업(C)은 너무 짧다. 에스컬레이션(D)은 팀 자율성을 약화시킨다.
1423 | A project manager is leading three projects in a program focused on starting product commercialization. Once the three projects are complete, the project manager stops attending the recurring team meetings. The program manager asks the project manager to continue attending these meetings to maintain those team touchpoints. This request does not match the project manager's expectation, since a program manager is overseeing the remaining work. How should the project manager approach the situation? | Schedule a meeting to discuss the different perspectives and agree on a decision. | Politely inform the program manager that attending these meetings is no longer required. | Attend only the program meetings where the market launch is being monitored | Provide an answer via email recommending a division of tasks between both roles. |  | A | When the program manager's expectations differ from the project manager's regarding meeting attendance after project completion, the PM should schedule a meeting to discuss their different perspectives and agree on a decision. Open communication and collaborative problem-solving ensure both parties can express their views and reach a mutually beneficial resolution. Politely declining attendance (B) disregards the program manager's reasoning without discussion. Attending only market-launch meetings (C) makes a unilateral decision without consensus. Recommending a division of tasks via email (D) avoids the direct conversation needed to resolve the misalignment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 프로그램 내 3개 프로젝트를 이끌고 있다. 프로젝트 완료 후 프로그램 관리자가 회의 참석에 대해 다른 기대를 가지고 있다. PM은 무엇을 해야 하는가? | 다른 관점을 논의하고 결정에 합의하기 위한 회의를 잡는다 | 프로그램 관리자에게 더 이상 이 회의 참석이 필요하지 않다고 정중하게 알린다 | 시장 출시가 모니터링되는 프로그램 회의에만 참석한다 | 이메일로 두 역할 간 업무 분담을 추천하는 답변을 제공한다 |  | A | 프로그램 관리자의 기대가 PM의 기대와 다를 때, PM은 다른 관점을 논의하고 결정에 합의하기 위한 회의를 잡아야 한다. 직접 대화가 오해를 해결한다. 불필요 통보(B)는 관계를 훼손한다. 선택적 참석(C)은 일방적이다. 이메일(D)은 복잡한 논의에 부적합하다.
1424 | A project is designed to provide local community members with health facilities that will support improved sanitation practices. What should the project manager do to ensure the community members are up to date on project progress? | Share project updates through regular community meetings. | Share project updates when requested by the stakeholders. | Share the project reports with the sponsor to inform community members. | Share the annual reports virtually and in the local newspapers. |  | A | For a project designed to improve local community sanitation through health facilities, the project manager should share project updates through regular community meetings. This approach ensures transparency, inclusivity, and active participation in the decision-making process—essential for projects that directly affect community members. Sharing updates only when requested (B) is passive and does not ensure the community stays informed. Sharing reports through the sponsor (C) adds an unnecessary intermediary and reduces direct engagement. Sharing annual reports in newspapers (D) is too infrequent and impersonal for a community-focused project requiring ongoing engagement. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트가 지역 커뮤니티에 위생 시설 개선을 위한 건강 시설을 제공하도록 설계되었다. PM은 어떻게 프로젝트 업데이트를 공유해야 하는가? | 정기적인 커뮤니티 회의를 통해 프로젝트 업데이트를 공유한다 | 이해관계자가 요청할 때 프로젝트 업데이트를 공유한다 | 스폰서와 프로젝트 보고서를 공유하여 커뮤니티에 알린다 | 연간 보고서를 가상으로 그리고 지역 신문에 공유한다 |  | A | 지역 커뮤니티 위생 개선 프로젝트에서 PM은 정기적인 커뮤니티 회의를 통해 업데이트를 공유해야 한다. 이 접근이 투명성과 커뮤니티 참여를 보장한다. 요청 시 공유(B)는 수동적이다. 스폰서를 통한 공유(C)는 간접적이다. 연간 보고서(D)는 빈도가 너무 낮다.
1425 | A project manager has experience working with a specific provider that has been requested for an upcoming project. This provider often fails to meet deliverable dates; however, it is the only company with the specific experience required for the project. What should the project manager do during the planning phase? | A. Hire resources to obtain knowledge about the provider ' s specific capabilities. | B. Add penalty clauses to the contract and update the risk register. | C. Encourage the provider to work overtime with no additional costs to the project. | D. Contract another provider with less experience and give them a chance to provide the deliverables. |  | B | When a sole-source provider with specific experience often fails to meet deadlines, the project manager should add penalty clauses to the contract and update the risk register during planning. Contract terms motivate performance and risk documentation enables monitoring. Hiring knowledge resources (A) does not address delivery. Encouraging unpaid overtime (C) is unethical. Contracting a less experienced provider (D) introduces new risks. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | PM이 특정 공급자와 경험이 있다. 이 공급자가 다가오는 프로젝트에 요청되었으나 종종 기한을 지키지 못한다. PM은 계획 중 무엇을 해야 하는가? | 공급자의 특정 역량에 대한 지식을 얻기 위해 자원을 고용한다 | 계약에 페널티 조항을 추가하고 리스크 등록부를 업데이트한다 | 공급자에게 프로젝트에 추가 비용 없이 초과 근무하도록 장려한다 | 경험이 적은 다른 공급자와 계약하여 인도물 제공 기회를 준다 |  | B | 기한을 종종 지키지 못하는 유일한 공급자와 작업할 때, PM은 계약에 페널티 조항을 추가하고 리스크 등록부를 업데이트해야 한다. 계약적 보호와 리스크 문서화가 사전적 관리를 가능하게 한다. 자원 고용(A)은 비효율적이다. 무상 초과근무(C)는 비현실적이고 비윤리적이다. 미경험 공급자(D)는 더 큰 리스크를 초래한다.
1426 | After finishing the planning session for a new project, the team agrees that the project duration needs to be 12 months. However, the project sponsor asks to release the product before the end of the project. What should the project manager do first? | Request the stakeholders to reduce the project backlog to finish on time | Update the risk register and escalate it to the sponsor | Assist the team in proposing a minimum viable product (MVP) | Ask to increase the capacity of the team to deliver the project on time |  | C | When the sponsor asks for earlier release than the planned 12-month duration, the project manager should first assist the team in proposing a minimum viable product (MVP). MVP framing enables value-focused scope negotiation and identifies what can be delivered sooner. Requesting stakeholders to reduce the backlog (A) presumes an approach before analysis. Updating the risk register and escalating (B) does not address the sponsor's goal. Increasing team capacity (D) should follow scope and feasibility analysis. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 계획 세션 후 팀이 프로젝트 기간 12개월에 동의했다. 스폰서가 더 빠른 출시를 요청한다. PM은 무엇을 먼저 해야 하는가? | 이해관계자에게 제시간에 완료하기 위해 프로젝트 백로그를 줄이도록 요청한다 | 리스크 등록부를 업데이트하고 스폰서에게 에스컬레이션한다 | 팀이 최소 실행 가능 제품(MVP)을 제안하도록 지원한다 | 제시간에 프로젝트를 납품하기 위해 팀 역량을 증가시키도록 요청한다 |  | C | 스폰서가 계획된 12개월보다 빠른 출시를 요청할 때, PM은 팀이 MVP를 제안하도록 지원해야 한다. MVP 프레이밍이 핵심 기능에 집중한 가치 중심 납품을 가능하게 한다. 백로그 축소 요청(A)은 이해관계자 일방적이다. 리스크 에스컬레이션(B)은 해결책이 아니다. 역량 증가(D)는 비용과 리스크가 크다.
1427 | Development team members are located in three different time zones. It is difficult to find a suitable time to hold the daily standup for all team members. What should the project manager do? | Let the team members decide themselves if they want to join the meeting. | Require all team members to join the daily standup regardless of the meeting time | Give up the daily standup and replace it with a daily report | Encourage frequent small team meetings with two or three team members. |  | D | When team members across three time zones cannot find a suitable daily standup time, the project manager should encourage frequent small team meetings with two or three members. Small-group coordination maintains communication without forcing inconvenient times. Letting members decide attendance (A) may reduce participation. Requiring attendance regardless (B) is inconsiderate. Replacing standups with daily reports (C) loses real-time interaction. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 개발 팀원이 3개 시간대에 분포되어 있다. 데일리 스탠드업에 적합한 시간을 찾기 어렵다. PM은 무엇을 해야 하는가? | 팀원들이 회의 참석 여부를 스스로 결정하도록 한다 | 회의 시간에 관계없이 모든 팀원이 데일리 스탠드업에 참여하도록 요구한다 | 데일리 스탠드업을 포기하고 일일 보고서로 대체한다 | 2~3명의 팀원으로 소규모 팀 회의를 자주 하도록 격려한다 |  | D | 3개 시간대에 걸친 팀이 데일리 스탠드업 시간을 찾기 어려울 때, PM은 2~3명의 소규모 팀 회의를 자주 하도록 격려해야 한다. 소그룹 조정이 시간대 차이를 수용한다. 자율 참석(A)은 참여가 보장되지 않는다. 강제 참석(B)은 비현실적이다. 보고서 대체(C)는 상호작용이 없다.
1428 | During the last sprint review, the product owner stated that the product does not deliver any value. The project manager believes that the product meets all the provided specifications. The team is confused by the product owner's statement. What should the project manager do when using a hybrid approach? | Prioritize the project backlog and ask the development team to fix the issues | Escalate the matter to the executive board so they can decide on next steps | Review the project ' s benefits management plan with the product owner. | Ask the product owner to terminate the project as it is no longer aligned to the expected benefits |  | C | When the product owner states the product delivers no value despite meeting specifications in a hybrid approach, the project manager should review the project's benefits management plan with the product owner. Clarifying benefits alignment reveals gaps between specifications and expected value. Prioritizing the backlog to fix issues (A) assumes technical deficiencies without understanding the value gap. Escalating to the executive board (B) is premature. Asking the product owner to terminate the project (D) is drastic. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 마지막 스프린트 리뷰에서 PO가 제품이 가치를 전달하지 않는다고 말했다. 하이브리드 접근법으로 사양은 충족했다. PM은 무엇을 해야 하는가? | 프로젝트 백로그 우선순위를 정하고 개발 팀에게 문제를 수정하도록 요청한다 | 경영진이 다음 단계를 결정할 수 있도록 이사회에 에스컬레이션한다 | PO와 함께 프로젝트의 혜택 관리 계획을 검토한다 | PO에게 기대 혜택과 더 이상 맞지 않으므로 프로젝트를 종료하도록 요청한다 |  | C | 사양 충족에도 PO가 가치 미전달을 주장할 때, PM은 PO와 혜택 관리 계획을 검토해야 한다. 혜택 계획 검토가 기대와 실제 가치를 재정렬한다. 백로그 수정(A)은 가치 정의 문제를 다루지 않는다. 에스컬레이션(B)은 직접 해결 전에 성급하다. 종료(D)는 극단적이다.
1429 | During the execution phase, the project manager discovered that the deliverables are not meeting the quality specifications requested by the main stakeholder. This has caused the schedule performance index (SPI) to deteriorate from 0.98 to 0.72 and the cost performance index (CPI) from 1.5 to 1.1. What action should the project manager take to mitigate the issue of the deliverables being rejected during the next iteration? | Assure that the product backlog is properly prioritized to avoid dependencies that cause rejection. | Create a dedicated sprint to complete all of the pending specifications from previous sprints. | Reinforce the definition of done (DoD) during sprint planning so that the team has a common understanding of expectations. | Submit a change request to prioritize resolutions for the quality issue to minimize the impact on the rest of the deliverables. |  | C | When deliverables fail to meet quality specifications causing SPI and CPI deterioration, the project manager should reinforce the definition of done (DoD) during sprint planning so the team has a common understanding of expectations. Clear quality standards prevent recurring rejections. Submitting a change request for quality prioritization (D) may be needed but does not address the root cause. Ensuring backlog prioritization avoids dependencies (A) is good practice but not the quality fix. Creating a dedicated sprint for pending specifications (B) delays the project. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 실행 단계에서 인도물이 품질 사양을 충족하지 못하여 SPI와 CPI가 악화되고 있다. PM은 무엇을 해야 하는가? | 제품 백로그가 거부를 야기하는 종속성을 피하도록 적절히 우선순위화되었는지 확인한다 | 이전 스프린트의 모든 보류 사양을 완료하기 위한 전용 스프린트를 생성한다 | 스프린트 계획 중 완료의 정의(DoD)를 강화하여 팀이 공통 이해를 갖도록 한다 | 품질 이슈 해결의 우선순위를 위한 변경 요청을 제출하여 일정 영향을 최소화한다 |  | C | 인도물이 품질 사양을 충족하지 못할 때, PM은 스프린트 계획 중 완료의 정의(DoD)를 강화해야 한다. 명확한 DoD가 일관된 품질 기준을 수립한다. 백로그 우선순위(A)는 품질 기준이 아닌 순서를 다룬다. 전용 스프린트(B)는 근본 원인을 해결하지 않는다. 변경 요청(D)은 프로세스 개선이 아닌 행정적이다.
1430 | A project manager realizes that a project is becoming delayed because some key decisions are affected by contradicting views between the organization's senior management and external stakeholders. What should the project manager do? | Review the adequacy of the project ' s governance and ensure that an appropriate structure is in place | Review the stakeholder register and ensure that communications are being followed in line with the communications management plan. | Isolate the project team from external factors such as senior management and stakeholders so that decisions can be made more quickly | Review the remaining scope and rebaseline the project's schedule to take into account delays in decision making |  | A | When a project is delayed because key decisions are affected by contradicting views between senior management and external stakeholders, the project manager should review the adequacy of the project's governance and ensure an appropriate structure is in place. Governance frameworks facilitate decision-making and issue resolution. Reviewing the stakeholder register and communications plan (B) addresses communication but not decision authority. Isolating the team (C) avoids the problem. Rebaselining the schedule (D) accepts the delay without addressing the cause. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 주요 결정이 고위 경영진과 외부 이해관계자의 상충 의견으로 영향받아 프로젝트가 지연되고 있다. PM은 무엇을 해야 하는가? | 프로젝트 거버넌스의 적절성을 검토하고 적절한 구조가 갖추어져 있는지 확인한다 | 이해관계자 등록부를 검토하고 커뮤니케이션이 계획에 따라 이행되는지 확인한다 | 프로젝트 팀을 고위 경영진과 이해관계자 같은 외부 요소로부터 격리한다 | 남은 범위를 검토하고 의사결정 지연을 고려하여 프로젝트 일정을 재기준선화한다 |  | A | 상충 의견으로 의사결정이 지연되어 프로젝트가 늦어질 때, PM은 프로젝트 거버넌스의 적절성을 검토하고 적절한 구조를 확인해야 한다. 거버넌스가 의사결정 권한과 프로세스를 명확히 한다. 커뮤니케이션 확인(B)은 부분적이다. 팀 격리(C)는 비현실적이다. 재기준선화(D)는 증상 대응이지 근본 해결이 아니다.
1431 | Due to a statewide emergency, a project team for a global insurance company is being forced to complete a project virtually. The project manager is tasked with conducting meetings where confidential patient information will be presented. What tool should the project manager use to conduct meetings with the project team and clients? | Use a collaborative electronic whiteboard, | Use a popular social media platform. | Use a third-party instant messaging tool. | Use a password-enabled audio/video product, |  | D | When conducting virtual meetings involving confidential patient information during a statewide emergency, the project manager should use a password-enabled audio/video product. Secure access controls protect sensitive information during virtual collaboration. A collaborative electronic whiteboard (A) may lack adequate security. A social media platform (B) is inappropriate for confidential data. A third-party messaging tool (C) may not meet security requirements. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 주 전체 비상사태로 글로벌 보험회사 프로젝트 팀이 가상으로 작업해야 한다. 기밀 환자 정보를 다룬다. 어떤 도구를 사용해야 하는가? | 협업 전자 화이트보드를 사용한다 | 인기 있는 소셜 미디어 플랫폼을 사용한다 | 서드파티 인스턴트 메시징 도구를 사용한다 | 비밀번호가 설정된 오디오/비디오 제품을 사용한다 |  | D | 기밀 환자 정보가 포함된 가상 회의를 수행할 때, PM은 비밀번호가 설정된 오디오/비디오 제품을 사용해야 한다. 보안 접근 제어가 기밀 데이터를 보호한다. 전자 화이트보드(A)는 보안이 충분하지 않다. 소셜 미디어(B)는 기밀 정보에 부적합하다. 인스턴트 메시징(C)은 보안이 불충분할 수 있다.
1432 | A multimillion-dollar project has started and is in the execution phase. A local regulatory authority has just announced changes to the requirements that will need to be implemented in 6 months, prior to completing the project execution phase. What should the project manager do next? | Add the new requirements to the project scope immediately since they are mandatory changes. | Ignore the new requirements as the current budget and schedule do not allow for any changes. | Proceed with the defined project requirements and delay implementing the new requirements. | Review the new requirements with the compliance department to determine if a change request is needed. |  | D | When a regulatory authority announces mandatory requirement changes during project execution, the project manager should review the new requirements with the compliance department to determine if a change request is needed. Compliance assessment ensures the project adapts to regulatory obligations. Adding requirements immediately (A) bypasses governance. Ignoring requirements (B) risks noncompliance. Proceeding and delaying implementation (C) may result in noncompliance within the mandated timeframe. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 수백만 달러 프로젝트가 실행 단계에 있다. 지역 규제 당국이 필수 요구사항 변경을 발표했다. PM은 무엇을 해야 하는가? | 필수 변경이므로 새 요구사항을 프로젝트 범위에 즉시 추가한다 | 현재 예산과 일정이 변경을 허용하지 않으므로 새 요구사항을 무시한다 | 정의된 프로젝트 요구사항으로 진행하고 새 요구사항 구현을 지연한다 | 컴플라이언스 부서와 새 요구사항을 검토하여 변경 요청이 필요한지 결정한다 |  | D | 규제 당국이 필수 요구사항 변경을 발표할 때, PM은 컴플라이언스 부서와 새 요구사항을 검토하여 변경 요청이 필요한지 결정해야 한다. 체계적 평가가 적절한 대응을 보장한다. 즉시 추가(A)는 영향 분석 없이 행동한다. 무시(B)는 규정 비준수 리스크가 있다. 지연(C)은 필수 변경을 무시한다.
1433 | A project manager is managing a project that will handle sensitive data for millions of users. The sponsor mentioned that, to their knowledge, the project does not seem to have any compliance requirements in their country. What should the project manager do in this situation? | Trust in the expertise of the sponsor and believe that there are no compliance requirements for this project. | Request expert advice from the compliance leader to confirm if there are any compliance requirements for the project. | Conduct independent research regarding the data protection policy of the country for legal and regulatory compliance. | Check with The national compliance agency to determine if the project has any compliance requirements in this country |  | B | When the sponsor believes there are no compliance requirements for a project handling sensitive data for millions of users, the project manager should request expert advice from the compliance leader. The compliance leader has specialized knowledge to confirm or identify requirements the sponsor may have overlooked. Trusting the sponsor without verification (A) is risky. Conducting independent research (C) may be incomplete. Checking with the national agency (D) may miss organizational or regional requirements. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | PM이 수백만 사용자의 민감한 데이터를 다루는 프로젝트를 관리 중이다. 스폰서가 컴플라이언스 요구사항이 없다고 말한다. PM은 무엇을 해야 하는가? | 스폰서의 전문성을 신뢰하고 컴플라이언스 요구사항이 없다고 믿는다 | 컴플라이언스 리더에게 전문가 자문을 요청하여 컴플라이언스 요구사항이 있는지 확인한다 | 해당 국가의 데이터 보호 정책에 대한 독립적 조사를 수행한다 | 국가 컴플라이언스 기관에 확인하여 프로젝트에 컴플라이언스 요구사항이 있는지 결정한다 |  | B | 스폰서가 민감한 데이터 프로젝트에 컴플라이언스 요구사항이 없다고 할 때, PM은 컴플라이언스 리더에게 전문가 자문을 요청해야 한다. 전문가 확인이 규정 준수를 보장한다. 스폰서 신뢰(A)는 전문성 범위 밖이다. 독립 조사(C)는 PM의 전문 영역이 아니다. 기관 확인(D)은 내부 전문가 확인 후에 한다.
1434 | A project selection committee is shortlisting projects for the coming year. Which selection criteria should the project manager recommend? | Projects that maximize the business value | Projects with the least associated risks | Projects with maximum revenue generation | Projects with the least duration |  | A | When a project selection committee is shortlisting projects, the project manager should recommend selecting projects that maximize business value. Business value encompasses tangible and intangible benefits aligned with organizational strategy. Projects with least risk (B) may not deliver strategic value. Maximum revenue generation (C) ignores intangible benefits. Least duration (D) prioritizes speed over value. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Risk & Issue Management | Business Environment | Define and Establish Governance | Schedule | Monitoring & Controlling | Integrate Sustainability | Control Schedule | Sustainability | 프로젝트 선정위원회가 내년 프로젝트를 선별하고 있다. PM은 어떤 선정 기준을 추천해야 하는가? | 비즈니스 가치를 극대화하는 프로젝트 | 관련 리스크가 가장 적은 프로젝트 | 최대 수익을 창출하는 프로젝트 | 기간이 가장 짧은 프로젝트 |  | A | 프로젝트 선정 시, PM은 비즈니스 가치를 극대화하는 프로젝트를 추천해야 한다. 비즈니스 가치는 유형 및 무형 편익을 포괄한다. 최소 리스크(B)는 가치를 보장하지 않는다. 최대 수익(C)은 비재무적 가치를 무시한다. 최단 기간(D)은 가치와 무관할 수 있다.
1435 | During execution of an agile project, a project manager realizes the budget is almost completely used, but the project is not close to being completed. What should the project manager do to address this concern? | Review the backlog and find opportunities to reprioritize the work and reduce the project scope | Review the project time line and find opportunities to reduce the project schedule. | Review the resource management plan and find opportunities to reduce project costs. | Review the budget with the project sponsor and ask for an increase to the budget |  | A | When the budget is nearly depleted and the agile project is far from completion, the project manager should review the backlog and find opportunities to reprioritize work and reduce scope. Focusing on the most valuable deliverables within budget constraints aligns with agile flexibility. Reviewing the timeline to reduce schedule (B) does not address the budget issue. Reviewing the resource plan for cost reduction (C) is less impactful. Requesting a budget increase from the sponsor (D) may not be feasible. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 애자일 프로젝트 실행 중 예산이 거의 소진되었으나 프로젝트 완료까지 멀다. PM은 무엇을 해야 하는가? | 백로그를 검토하여 작업을 재우선순위화하고 프로젝트 범위를 줄일 기회를 찾는다 | 프로젝트 일정을 검토하여 일정을 줄일 기회를 찾는다 | 자원 관리 계획을 검토하여 프로젝트 비용을 줄일 기회를 찾는다 | 프로젝트 스폰서와 예산을 검토하고 증액을 요청한다 |  | A | 예산이 거의 소진되고 프로젝트 완료까지 멀 때, PM은 백로그를 검토하여 재우선순위화하고 범위를 줄여야 한다. 핵심 가치에 집중하는 것이 제한된 예산 내 납품을 가능하게 한다. 일정 축소(B)는 비용 문제를 해결하지 않는다. 비용 절감(C)은 범위보다 효과가 제한적이다. 예산 증액(D)은 항상 가능하지 않다.
1436 | A customer interacts directly with a Scrum team and continually requests changes in priorities. This causes confusion among the team members and they complain to the project manager. What should the project manager do? | Ask the customer to submit a change request to the project sponsor. | Document this issue in the sprint backlog for discussion at a team meeting. | Advise the customer to discuss changes with the product owner. | Encourage the team to clarify the requests with the customer. |  | C | The PM should direct the customer to discuss changes with the product owner, who manages the product backlog and prioritizes user stories. The PO represents the customer's voice and ensures the product delivers value. Documenting issues in the sprint backlog (B) is incorrect—the sprint backlog is for committed tasks, not change requests. Routing changes through the sponsor (C) contradicts agile's welcoming approach to change. Having the team clarify directly with the customer (D) bypasses the PO's role as the single source of truth for product vision and requirements. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 고객이 스크럼 팀과 직접 소통하며 지속적으로 우선순위 변경을 요청하여 혼란을 야기한다. PM은 무엇을 해야 하는가? | 고객에게 프로젝트 스폰서에게 변경 요청을 제출하도록 요청한다 | 이 이슈를 스프린트 백로그에 문서화하여 팀 회의에서 논의한다 | 고객에게 변경사항을 PO와 논의하도록 조언한다 | 팀이 고객과 요청을 명확히 하도록 격려한다 |  | C | 고객이 스크럼 팀에 직접 우선순위 변경을 요청할 때, PM은 고객에게 PO와 논의하도록 조언해야 한다. PO가 제품 백로그를 관리하고 사용자 스토리 우선순위를 정한다. 스폰서에게 요청(A)은 애자일 프로세스에 맞지 않다. 백로그 문서화(B)는 근본 해결이 아니다. 팀 명확화(D)는 PO 역할을 우회한다.
1437 | A few virtual team members are located in a region that generally has good internet connectivity. However, they frequently experience connectivity issues joining team calls during the day. What should the project manager do? | Determine what the problem is and develop an action plan. | Procure tools that consume less bandwidth for internet calls. | Record the meeting to share with the team members who were unable to join. | Ask the team members to use chat tools as an alternative to calls. |  | A | When virtual team members in a region with generally good connectivity frequently experience issues joining calls, the project manager should determine what the problem is and develop an action plan. Root cause investigation before action ensures the right solution. Procuring low-bandwidth tools (B) assumes the cause is bandwidth. Recording meetings (C) accommodates the problem without solving it. Switching to chat tools (D) changes the medium without understanding the issue. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 가상 팀원이 일반적으로 좋은 인터넷 연결 지역에 있으나 통화 참여에 자주 문제가 있다. PM은 무엇을 해야 하는가? | 문제가 무엇인지 파악하고 실행 계획을 개발한다 | 인터넷 통화에 적은 대역폭을 소비하는 도구를 조달한다 | 참여하지 못한 팀원과 공유하기 위해 회의를 녹화한다 | 팀원에게 통화 대안으로 채팅 도구를 사용하도록 요청한다 |  | A | 일반적으로 좋은 연결의 지역에서 팀원이 자주 통화 참여에 문제가 있을 때, PM은 문제가 무엇인지 파악하고 실행 계획을 개발해야 한다. 근본 원인 분석이 효과적 해결의 기초이다. 도구 조달(B)은 원인 파악 전에 성급하다. 녹화(C)는 참여를 보장하지 않는다. 채팅 도구(D)는 대안이지 해결이 아니다.
1438 | A work package to configure new computer hardware is received, and a list of related project activities have also been identified. What should the project manager do? | Consult subject matter experts (SMEs) to review the schedule. | Define the project management plan. | Estimate the resources needed for the activities. | Estimate the cost of each activity. |  | C | When a work package for configuring new computer hardware is received along with related activities, the project manager should estimate the resources needed for the activities. Resource estimation determines what is required for execution. Consulting SMEs to review the schedule (A) focuses on timing, not resources. Defining the project management plan (B) is too broad. Estimating cost (D) comes after resource estimation. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 새 컴퓨터 하드웨어 구성을 위한 작업 패키지가 수령되었고 관련 프로젝트 활동 목록도 식별되었다. 다음 단계는 무엇인가? | 일정을 검토하기 위해 주제전문가(SME)에게 자문한다 | 프로젝트 관리 계획을 정의한다 | 활동에 필요한 자원을 추정한다 | 각 활동의 비용을 추정한다 |  | C | 작업 패키지와 관련 활동이 식별된 후, PM은 활동에 필요한 자원을 추정해야 한다. 자원 추정이 활동 기간과 비용 추정의 기초이다. SME 자문(A)은 자원 추정 후에 한다. 계획 정의(B)는 이미 진행 중이다. 비용 추정(D)은 자원 추정 후에 한다.
1439 | A team lead has been highly engaged and involved in a project and is operating without a chain of command or authority levels. What is the team lead doing? | Modeling servant leadership | Modeling commanding leadership | Modeling directive leadership | Modeling adaptive leadership |  | A | When a team lead is highly engaged and operates without a chain of command or authority levels, they are modeling adaptive leadership. Adaptive leadership involves anticipating needs, building collective support, and adapting responses through continuous learning without relying on formal authority. Commanding leadership (B) exerts control and demands compliance. Directive leadership (C) gives specific instructions. Servant leadership (A) prioritizes followers' needs, which differs from operating without hierarchy. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀 리더가 높은 참여와 관여로 프로젝트에 임하며 지휘 체계나 권한 수준 없이 운영하고 있다. 어떤 리더십을 모델링하고 있는가? | 서번트 리더십 | 지시적 리더십 | 명령적 리더십 | 적응적 리더십 |  | A | 팀 리더가 높은 참여와 관여를 보이면서 지휘 체계나 권한 없이 운영할 때, 서번트 리더십을 모델링하고 있다. 서번트 리더십은 팀의 필요를 우선시하고 지원과 봉사를 통해 이끈다. 명령적(B)과 지시적(C) 리더십은 권한 기반이다. 적응적(D)은 상황에 따른 변화인데 여기서는 봉사 지향이 핵심이다.
1440 | An agile team member discovers an impediment that is preventing them from doing their work efficiently. At which of the meetings should they bring up this impediment for resolution? | Daily Scrum meeting | Retrospective meeting | Sprint review meeting | Sprint planning meeting |  | A | The correct answer is A. Daily Scrum meeting. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 팀원이 업무를 효율적으로 수행하지 못하게 하는 장애물을 발견했다. 어떤 이벤트에서 이 장애물을 제기해야 하는가? | 데일리 스크럼 회의 | 회고 회의 | 스프린트 리뷰 회의 | 스프린트 계획 회의 |  | A | 정답은 A이다. 데일리 스크럼 회의. 애자일 실천은 반복적 납품, 팀 권한 부여, 지속적 개선을 강조한다. 장애물은 데일리 스크럼에서 제기하여 신속한 제거를 가능하게 한다. 회고(B)는 스프린트 후 프로세스 개선이다. 리뷰(C)는 인도물 시연이다. 계획(D)은 작업 선택이다.
1441 | A company is working on the prototype of a new contract document that includes visual elements. The product owner shared the project sponsor's feedback about the elements to be included, but the project team pushed back. However, when the project sponsor spoke with the team, they confirmed that all of the changes are feasible. How should the project manager address this situation? | Review the actions listed in the risk management plan. | Review and update the organizational process assets (OPAs). | Submit a change request to replace the product owner. | Execute a retrospective meeting to solve the misalignment. |  | D | The PM should conduct a retrospective meeting to address and resolve the misalignment within the team. Retrospectives provide a structured forum for identifying process issues, discussing solutions collaboratively, and agreeing on improvement actions. This aligns with agile principles of continuous improvement and team-driven problem solving. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 팀이 시각적 요소가 포함된 새 계약 문서 프로토타입을 작업 중이다. PO가 팀과 공유한 사양이 팀의 이해와 다르다. PM은 무엇을 해야 하는가? | 리스크 관리 계획에 나열된 조치를 검토한다 | 조직 프로세스 자산(OPA)을 검토하고 업데이트한다 | PO를 교체하기 위한 변경 요청을 제출한다 | 불일치를 해결하기 위한 회고 회의를 실행한다 |  | D | PO의 사양과 팀의 이해가 다를 때, PM은 회고 회의를 실행하여 불일치를 해결해야 한다. 회고가 프로세스 이슈 식별과 해결을 위한 구조화된 포럼을 제공한다. 리스크 계획(A)은 프로세스 불일치와 무관하다. OPA 업데이트(B)는 현재 문제를 해결하지 않는다. PO 교체(C)는 과도하다.
1442 | A project is approaching the closing phase. While preparing for the final steps, the quality system is updated in accordance with new international quality standards, resulting in new deliverable approval procedures. Which action should the project manager take? | Escalate the issue to the project sponsor. | Ask the project team if the scope can be changed. | Apply the new list of approval procedures. | Inform the customer that the project will be late. |  | C | When new international quality standards update deliverable approval procedures near project closing, the project manager should apply the new list of approval procedures. Compliance with updated standards ensures quality. Escalating to the sponsor (A) defers action. Asking if scope can change (B) is unrelated to quality procedures. Informing the customer of delay (D) assumes delay without assessment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 종료 단계에 접근 중이다. 새 국제 품질 표준에 따라 인도물 승인 절차가 업데이트되었다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 이슈를 에스컬레이션한다 | 범위를 변경할 수 있는지 프로젝트 팀에 묻는다 | 새 승인 절차 목록을 적용한다 | 고객에게 프로젝트가 늦어질 것이라고 알린다 |  | C | 새 국제 품질 표준이 인도물 승인 절차를 업데이트할 때, PM은 새 승인 절차를 적용해야 한다. 업데이트된 표준 준수가 규정 적합성을 보장한다. 에스컬레이션(A)은 표준 적용 전에 불필요하다. 범위 변경(B)은 절차 변경과 다르다. 지연 통보(D)는 절차 적용 전에 성급하다.
1443 | A project manager is leading a project that is at 90% completion. One of the key stakeholders requests a certification program to be included as part of the project. Another stakeholder disagrees and informs the project team that there should be no change to the project management plan since the project is nearing completion. What should the project manager do? | Ask the key stakeholder to take the lead in handling the request since they are more knowledgeable. | Update the project management plan and adjust the project budget with this change request. | Request a meeting with the stakeholders and their team members to inform them about this change. | Raise a change request to the change control board (CCB) and inform the project sponsor about the change. |  | D | When a stakeholder requests a certification program at 90% project completion while another opposes any changes, the project manager should raise a change request to the CCB and inform the sponsor. Formal change control ensures proper evaluation and approval. Asking the stakeholder to lead the request (A) abdicates PM responsibility. Updating the plan and budget directly (B) bypasses change control. Requesting a meeting to inform about the change (C) does not follow governance. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Risk & Issue Management | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 프로젝트가 90% 완료된 상태에서 주요 이해관계자가 인증 프로그램을 요청한다. 다른 이해관계자는 변경에 반대한다. PM은 무엇을 해야 하는가? | 주요 이해관계자에게 더 잘 알고 있으므로 요청 처리를 주도하도록 요청한다 | 프로젝트 관리 계획을 업데이트하고 이 변경 요청으로 예산을 조정한다 | 이해관계자와 팀원과 회의를 요청하여 이 변경에 대해 알린다 | CCB에 변경 요청을 제출하고 프로젝트 스폰서에게 변경을 알린다 |  | D | 90% 완료 시 상충하는 이해관계자 의견이 있는 변경 요청에 대해, PM은 CCB에 변경 요청을 제출하고 스폰서에게 알려야 한다. 공식적 변경 관리 프로세스가 객관적 평가를 보장한다. 이해관계자 주도(A)는 PM 역할을 포기한다. 직접 계획 업데이트(B)는 승인 전에 성급하다. 정보 회의(C)는 결정이 아닌 공유이다.
1444 | The project sponsor of a major initiative is consistently changing the prioritization of modular work packages. The team is accustomed to three-week sprints and is becoming increasingly frustrated with the daily changes in scope. What should the project manager do? | Move to a Kanban strategy so that work can be reallocated more easily | Decrease the sprint cycle to the average repriontization request by calculating it in days | Set up a meeting with the project team and ask for their opinion on what to do | Set up a meeting with the sponsor to explain the importance of keeping a strict sprint cycle |  | D | When a sponsor frequently changes work package priorities, the PM should arrange a meeting to discuss the importance of maintaining a consistent sprint cycle. The PM should clarify how project objectives align with business needs, explain the benefits of stable sprint cadences (faster value delivery, better quality, increased feedback loops, reduced risk), and highlight the negative effects of constant scope changes (disrupted workflow, decreased morale, accumulated technical debt, compromised product quality). The PM and sponsor should negotiate clear prioritization criteria, establish a change management process, and involve the team and product owner in planning. Documenting and communicating agreed priorities to all stakeholders supports transparency and project control. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Integrate Sustainability | Plan Scope Management | Sustainability | 스폰서가 모듈형 작업 패키지의 우선순위를 지속적으로 변경한다. 팀이 스프린트 계획을 고수하고 싶어한다. PM은 무엇을 해야 하는가? | 작업을 더 쉽게 재할당할 수 있도록 칸반 전략으로 전환한다 | 스프린트 주기를 재우선순위화 요청의 평균으로 단축한다 | 프로젝트 팀과 회의를 잡아 의견을 묻는다 | 스폰서와 회의를 잡아 일관된 스프린트 주기 유지의 중요성을 설명한다 |  | D | 스폰서가 우선순위를 자주 변경할 때, PM은 스폰서와 회의를 잡아 일관된 스프린트 주기 유지의 중요성을 설명해야 한다. 프로젝트 목표가 스프린트 약속과 어떻게 연결되는지 명확히 한다. 칸반 전환(A)은 방법론 변경이다. 주기 단축(B)은 불안정을 증가시킨다. 팀 의견(C)은 스폰서와의 논의 후에 한다.
1445 | During the project planning phase, a project manager is informed that they cannot start one activity before another department implements the required IT system. What should the project manager do? | Ask IT to prioritize the needed system to meet the schedule. | Include the dependency in the project schedule. | Perform Integrated Change Control. | Fast track this dependency to avoid delaying the project. |  | B | When the PM learns during planning that an activity depends on another department's IT system implementation, the project manager should include the dependency in the project schedule. Documenting dependencies enables accurate planning. Asking IT to prioritize (A) overrides their governance. Performing integrated change control (C) is premature during initial planning. Fast-tracking the dependency (D) is not possible for mandatory dependencies. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 계획 단계에서 PM이 다른 부서의 IT 시스템 구현이 완료되어야 한 활동을 시작할 수 있다는 것을 알게 되었다. PM은 무엇을 해야 하는가? | IT에 일정을 맞추기 위해 필요한 시스템을 우선순위화하도록 요청한다 | 프로젝트 일정에 종속성을 포함한다 | 통합 변경 통제를 수행한다 | 프로젝트 지연을 피하기 위해 이 종속성을 패스트 트래킹한다 |  | B | 계획 중 다른 부서의 IT 시스템에 종속성을 발견할 때, PM은 프로젝트 일정에 종속성을 포함해야 한다. 종속성 문서화가 정확한 일정과 리스크 관리의 기초이다. IT 우선순위 요청(A)은 PM의 권한 밖일 수 있다. 변경 통제(C)는 아직 계획 단계이다. 패스트 트래킹(D)은 종속성을 제거하지 않는다.
1446 | At the end of a canceled project, the project manager sent surveys to all stakeholders. The survey also included templates for stakeholders to outline situations, solutions, results, and suggestions. How should the project manager use the information collected? | Evaluate the information collected on areas of improvement. | Use the information to restart the project. | Map the lessons learned against work breakdown structure (WBS) components. | Archive the survey responses with project artifacts for future projects. |  | D | Survey information collected at the end of a canceled project should be archived with project artifacts for future reference. Lessons learned—even from canceled projects—form part of organizational process assets. Documenting and storing these insights ensures knowledge is preserved for future projects to leverage successful strategies and avoid past mistakes. This is a fundamental aspect of the project closing process. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 취소된 프로젝트 종료 시 PM이 모든 이해관계자에게 설문조사를 보냈다. 설문에는 개선 영역 템플릿도 포함되었다. PM은 수집된 정보를 어떻게 해야 하는가? | 수집된 정보에서 개선 영역을 평가한다 | 정보를 사용하여 프로젝트를 재시작한다 | 교훈을 작업분류체계(WBS) 구성 요소에 매핑한다 | 설문 응답을 향후 프로젝트를 위해 프로젝트 산출물과 함께 보관한다 |  | D | 취소된 프로젝트 종료 시 수집된 설문 정보는 향후 프로젝트를 위해 프로젝트 산출물과 함께 보관해야 한다. 취소된 프로젝트의 교훈도 조직 프로세스 자산의 일부이다. 개선 영역 평가(A)는 부분적이다. 재시작(B)은 취소 이유를 무시한다. WBS 매핑(C)은 불필요하게 복잡하다.
1447 | A medium-sized company has been exploring new marketing tactics with regard to launching a new product. New product creation is no small task. In the end, it was too big of an expenditure for the company to undertake. What should the project manager do in the future when working on new product projects? | Adopt a chain management approach, developing products based on the same platform and infrastructure. | Train the team to first find the minimum viable product (MVP) that will deliver value to the customer. | Increase the contingency reserve and prepare the team for applying fast-failing techniques when the estimates veer from the initial plan. | Make use of kanban boards so all stakeholders have a clear view of the project and provide their help accordingly. |  | B | When a new product project proves too expensive for a medium-sized company, the project manager should in the future train the team to first find the minimum viable product (MVP) that will deliver value to the customer. An MVP approach validates the concept with minimal investment before committing to full-scale development. Adopting chain management for platform-based development (A) may not suit all projects. Increasing contingency reserves and fast-failing techniques (C) addresses symptoms rather than root cause. Using kanban boards for stakeholder visibility (D) improves transparency but does not address cost control. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Schedule | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 중소기업이 신제품 출시에 대한 새로운 마케팅 전략을 탐색 중이다. 신제품 개발이 너무 비쌌다. PM은 향후 무엇을 해야 하는가? | 동일 플랫폼과 인프라 기반의 체인 관리 접근법을 채택한다 | 팀에게 먼저 고객에게 가치를 전달할 최소 기능 제품(MVP)을 찾도록 훈련한다 | 비상 예비비를 늘리고 팀에게 빠른 실패 기법 적용을 준비시킨다 | 칸반 보드를 사용하여 모든 이해관계자가 프로젝트를 명확히 보도록 한다 |  | B | 신제품 프로젝트가 너무 비쌌을 때, PM은 팀에게 먼저 고객에게 가치를 전달할 MVP를 찾도록 훈련해야 한다. MVP 접근법이 리스크와 비용을 줄이면서 빠른 가치 전달을 가능하게 한다. 체인 관리(A)는 혁신을 제한한다. 비상 예비비 증가(C)는 근본 해결이 아니다. 칸반(D)은 가시성 도구이지 비용 해결이 아니다.
1448 | A project team has obtained additional team members from different time zones. As a result, there are full-day delays in the work being completed because there are questions from team members from opposite time zones. What should the project lead do? | During daily check-ins, compile questions, coordinate with all team members, and agree to meet. 1184 | Inform all team members that they are required to check for messages every few hours to ensure fast response times. | Meet each team member during their work hours to ensure all questions are answered in a timely manner. | Escalate to the project sponsor and request to replace certain team members so the time zones are aligned. |  | A | The correct answer is A. During daily check-ins, compile questions, coordinate with all team members, and agree to meet. 1184. Schedule management requires systematic analysis and appropriate corrective actions. The PM should evaluate impacts and implement solutions to maintain project timelines. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀에 다른 시간대의 추가 팀원이 합류했다. 질문 응답에 하루 종일 지연이 발생한다. PM은 무엇을 해야 하는가? | 일일 체크인 시 질문을 취합하고 모든 팀원과 조율하여 만남에 합의한다 | 모든 팀원에게 빠른 응답을 위해 몇 시간마다 메시지를 확인하도록 요구한다 | 각 팀원의 근무 시간에 맞춰 만나 모든 질문이 적시에 답변되도록 한다 | 스폰서에게 에스컬레이션하여 시간대가 맞도록 특정 팀원 교체를 요청한다 |  | A | 정답은 A이다. 일일 체크인 시 질문을 취합하고 모든 팀원과 조율하여 만남에 합의한다. 일정 관리는 체계적 분석과 적절한 시정 조치가 필요하다. 구조화된 소통이 시간대 차이를 효율적으로 관리한다. 상시 확인(B)은 비현실적이다. 개별 만남(C)은 PM 시간을 과도하게 소모한다. 팀원 교체(D)는 과도하다.
1449 | A project manager is preparing a budget estimation for an international construction project. They decide to consult the project team members who are experienced in this type of project and are familiar with the local laws of the country. Which budgeting approach would be the least risky for the project team to apply? | Discuss and compile the local information about laws to develop bottom-up estimations. | Use a top-down estimation and add contingencies to cover any future impacts regarding the legal context. | Review historical data and provide parametric estimations for the activities, including local law restrictions. | Make a general estimation using a standard legal approach and then look to include early definitions. |  | A | For an international construction project where local laws are critical, the team should discuss and compile local legal information to develop bottom-up estimations. This most detailed approach incorporates precise data including legal compliance costs, permitting, and regulatory timelines—reducing estimation risk. Using parametric estimation with historical data (C) may not account for jurisdiction-specific legal factors. Top-down with contingencies (B) is less precise. General estimation with standard legal approach (D) may miss crucial localized compliance costs. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | PM이 국제 건설 프로젝트의 예산 추정을 준비 중이다. 현지 법률이 중요하다. 팀에 무엇을 해야 하는가? | 현지 법률 정보를 논의하고 취합하여 상향식 추정을 개발한다 | 하향식 추정을 사용하고 법적 영향에 대한 비상비를 추가한다 | 과거 데이터를 검토하고 현지 법률 요구사항을 포함한 모수 추정을 제공한다 | 표준 법적 접근법을 사용하여 일반 추정을 하고 초기 정의를 포함한다 |  | A | 국제 건설 프로젝트에서 현지 법률이 중요할 때, 팀은 현지 법률 정보를 논의하고 취합하여 상향식 추정을 개발해야 한다. 가장 상세한 접근법이 현지 법적 요구사항을 정확히 반영한다. 하향식(B)은 상세함이 부족하다. 모수 추정(C)은 과거 데이터에 의존하여 현지 특수성을 놓칠 수 있다. 일반 추정(D)은 정확도가 낮다.
1450 | A project manager is building a team to work on a service integration project that will transition technology management services from company A to company B. The project team will consist of members from both companies. Prospective team members for the project are located all over the world, have different types of technology backgrounds, and use different approaches for work. How should the project manager build a cohesive, high-performing team? | Organize the team members into several kick-off sessions based on technology type. | Ask prospective team members to write a short biography explaining how they can contribute to the team ' s success. | Review the list of team members' skills and understand how they will work together to deliver the project outcomes. | Ask the human resources (HR) department to arrange interview meetings to select the team. |  | C | When building a team from members across both companies with diverse backgrounds and approaches, the project manager should review team members' skills and understand how they will work together to deliver outcomes. Skill assessment aligns competencies with project needs and identifies how the team can collaborate effectively. Organizing kick-off sessions by technology type (A) may create silos. Requesting biographies (B) is subjective and incomplete. Having HR arrange interviews (D) delegates the PM's responsibility. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 양사 간 기술 관리를 전환하는 서비스 통합 프로젝트를 위한 팀을 구성 중이다. PM은 무엇을 먼저 해야 하는가? | 기술 유형별로 팀원을 여러 킥오프 세션으로 조직한다 | 예비 팀원에게 팀에 어떻게 기여할 수 있는지 짧은 자기소개를 작성하도록 요청한다 | 팀원의 기술을 검토하고 프로젝트 납품을 위해 어떻게 협력할지 이해한다 | 인사부(HR)에 팀 선발을 위한 면접 회의를 주선하도록 요청한다 |  | C | 양사의 다양한 배경과 접근법을 가진 팀원으로 팀을 구성할 때, PM은 팀원의 기술을 검토하고 프로젝트 납품을 위해 어떻게 협력할지 이해해야 한다. 기술 기반 팀 구성이 효과적 협업의 기초이다. 기술별 세션(A)은 사일로를 만든다. 자기소개(B)는 주관적이다. HR 면접(D)은 PM 역할이 아닌 위임이다.
1451 | A key stakeholder of a project wants to include additional work before completion. What should the project manager do? | Meet with the stakeholder and explain that additional work cannot be added. | Request the additional work through governance. | Prioritize the additional work in the backlog. | Collaborate immediately with the stakeholder to complete the additional work. |  | B | When stakeholders request additional scope, the PM should process the change request through the approved change control process. Unilateral changes bypass governance, risk scope creep, and undermine project baselines. Formal change control ensures alignment with scope, budget, and timeline while maintaining transparency and stakeholder agreement. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 프로젝트의 주요 이해관계자가 완료 전에 추가 작업을 포함하고 싶어한다. PM은 무엇을 해야 하는가? | 이해관계자와 만나 추가 작업이 추가될 수 없음을 설명한다 | 거버넌스를 통해 추가 작업을 요청한다 | 백로그에 추가 작업의 우선순위를 정한다 | 이해관계자와 즉시 협력하여 추가 작업을 완료한다 |  | B | 이해관계자가 추가 범위를 요청할 때, PM은 승인된 변경 통제 프로세스를 통해 변경 요청을 처리해야 한다. 일방적 변경은 거버넌스를 우회하고 범위 확대 리스크를 초래한다. 거부(A)은 이해관계자 관계를 훼손한다. 백로그 우선순위(C)는 승인 없이 범위를 변경한다. 즉시 협력(D)은 거버넌스를 무시한다.
1452 | A project manager is assigned to work on a large global project. The resources for the project are dispersed among different organizations and countries. After the project kick-off meeting, the project manager learns that many virtual team members are unable to join the regular project update meetings. Their absence will impact the overall project schedule. What immediate corrective action should the project manager take? | Add this issue to the risk management plan and take action if it persists. | Escalate this issue to the virtual team members ' supervisors. | Discuss the issue with the virtual team members and revise the communications management plan. | Discuss the issue with the project sponsors and add this as an issue in the issue log. |  | C | When virtual team members on a global project cannot join regular update meetings and it impacts the schedule, the project manager should discuss the issue with the virtual team members and revise the communications management plan. Direct engagement uncovers constraints—such as time zones or scheduling conflicts—and enables collaborative revision of the plan to accommodate everyone. Adding to the risk management plan (A) is reactive. Escalating to supervisors (B) is heavy-handed before direct engagement. Discussing with sponsors and adding to the issue log (D) escalates without attempting direct resolution first. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Manage Conflicts | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 대규모 글로벌 프로젝트에 배정되었다. 가상 팀원이 정기 회의에 참석하지 못하여 일정에 영향을 준다. PM은 무엇을 해야 하는가? | 이 이슈를 리스크 관리 계획에 추가하고 지속되면 조치를 취한다 | 가상 팀원의 상사에게 이 이슈를 에스컬레이션한다 | 가상 팀원과 이슈를 논의하고 커뮤니케이션 관리 계획을 수정한다 | 프로젝트 스폰서와 이슈를 논의하고 이슈 로그에 기록한다 |  | C | 가상 팀원이 정기 회의에 참석하지 못할 때, PM은 가상 팀원과 이슈를 논의하고 커뮤니케이션 관리 계획을 수정해야 한다. 직접 소통과 계획 조정이 근본 해결이다. 리스크 추가(A)는 수동적이다. 상사 에스컬레이션(B)은 직접 해결 전에 과도하다. 스폰서 논의(D)는 불필요한 에스컬레이션이다.
1453 | A multiyear resource-constrained project is midway through the execution phase. During a progress update meeting, it has been determined that there might be a schedule delay to deliver the project. The project manager has observed that all of the team members are working hard and lots of deliverables have already been completed. What should the project manager do immediately about this situation? | Ask the project planner to identify the critical path and respective delayed activities, and then investigate the reasons for the delay. | Prepare a monthly report by highlighting the completed deliverables and communicate the delay to management. | Ask the scheduler to update the schedule with the percent of work in progress (WIP) and communicate the results to the team. | Register the schedule risk and present the new resources requirement to the change management board for schedule recovery. |  | A | When a potential schedule delay is identified in a resource-constrained project, the project manager should immediately ask the planner to identify the critical path and respective delayed activities, then investigate the reasons for delay. Critical path analysis enables targeted corrective action. Preparing a monthly report (B) is routine, not immediate. Updating the schedule with WIP percentages (C) is maintenance. Registering the risk and requesting resources (D) requires understanding the delay first. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 다년간 자원 제약 프로젝트가 실행 단계 중간에 있다. 진행 업데이트 회의에서 잠재적 일정 지연이 식별되었다. PM은 무엇을 해야 하는가? | 기획자에게 주공정선과 지연 활동을 식별하도록 요청하고 관리진에게 알린다 | 월간 보고서에 완료된 인도물을 강조하고 지연을 관리진에 전달한다 | 스케줄러에게 진행 중 작업 비율로 일정을 업데이트하고 이해관계자에게 전달한다 | 일정 리스크를 등록하고 변경관리위원회에 새 자원 요구사항을 제시한다 |  | A | 자원 제약 프로젝트에서 잠재적 일정 지연이 식별되면, PM은 즉시 기획자에게 주공정선과 지연 활동을 식별하도록 요청하고 관리진에게 알려야 한다. 주공정선 분석이 정확한 영향 파악의 핵심이다. 월간 보고(B)는 너무 느리다. WIP 업데이트(C)는 분석이 아닌 보고이다. 리스크 등록(D)은 분석 후에 한다.
1454 | An organization is implementing a solar power system at its production plant. During the execution phase, one of the key stakeholders noticed and communicated that authorities are developing solar power regulation, which might impact the overall feasibility of the project. What should the project manager do first? | Put the project on hold and wait for the regulation information to be confirmed. | Meet with the sponsor to discuss the regulation issue and determine the proper action. | Proceed with the project as long as the regulation is not yet finalized. | Collect and analyze information about the new regulation. |  | D | The correct answer is D. Collect and analyze information about the new regulation. Risk and compliance management require proactive identification and assessment. The PM should evaluate impacts, follow proper processes, and implement appropriate response strategies. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 조직이 생산 공장에 태양광 시스템을 구현 중이다. 실행 단계에서 새 규제에 대한 정보를 받았다. PM은 무엇을 해야 하는가? | 규제 정보가 확인될 때까지 프로젝트를 보류한다 | 스폰서와 만나 규제 문제를 논의하고 적절한 조치를 결정한다 | 규제가 아직 확정되지 않았으므로 프로젝트를 계속 진행한다 | 새 규제에 대한 정보를 수집하고 분석한다 |  | D | 정답은 D이다. 새 규제에 대한 정보를 수집하고 분석한다. 리스크 및 컴플라이언스 관리는 사전적 식별과 평가가 필요하다. 정보 수집과 분석이 정보에 기반한 결정의 기초이다. 프로젝트 보류(A)는 과도하다. 스폰서 만남(B)은 분석 후에 한다. 계속 진행(C)은 규제 리스크를 무시한다.
1455 | During an agile team retrospective, a project team member notes that the code quality is declining, which might lead to future rework that could become unmanageable over time. What should the project manager do? | Expand the team in order to improve the quality of the project. | Help the team create the definition of done (DoD) to improve delivery quality. | Add testing items to the backlog to assess quality periodically. | Compare the cost of improving quality against the cost of failure and adjust the budget. |  | B | Declining code quality flagged during a retrospective signals accumulating technical debt that could lead to unmanageable future rework. The PM should prioritize addressing this by working with the team to allocate dedicated capacity for technical debt reduction within upcoming sprints. Making technical debt items visible in the product backlog—prioritized alongside feature work—ensures the issue receives appropriate attention. Ignoring quality concerns or deferring them indefinitely compounds the problem exponentially over time. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 애자일 팀 회고 중 팀원이 코드 품질이 떨어지고 있어 기술 부채가 쌓일 수 있다고 지적했다. PM은 무엇을 해야 하는가? | 품질을 개선하기 위해 팀을 확장한다 | 팀이 납품 품질을 개선하기 위한 완료 정의(DoD)를 만들도록 돕는다 | 백로그에 테스트 항목을 추가하여 품질을 주기적으로 평가한다 | 품질 개선 비용과 실패 비용을 비교하고 예산을 조정한다 |  | B | 코드 품질 저하가 회고에서 지적되면, PM은 팀이 납품 품질을 개선하기 위한 완료 정의(DoD)를 만들도록 도와야 한다. DoD가 품질 기준을 명확히 하고 일관된 품질을 보장한다. 팀 확장(A)은 품질 문제를 해결하지 않는다. 테스트 항목(C)은 사후적이다. 비용 비교(D)는 분석적이지만 즉각적 조치가 아니다.
1456 | A project manager is leading a hybrid project that is building an app for a travel industry startup. Due to unforeseen events, the features and the overall solution will not be useable by many customers due to new travel restrictions. What should the project manager do first? | Release the team and help them achieve their potential on a new project. | Assess the environmental changes and recommend a pivot for the project. | Pause the project if business value cannot be reached and collect lessons learned. | Ask the organization ' s management for advice regarding the project ' s direction. |  | B | When unforeseen events like travel restrictions render the project's features unusable by many customers, the project manager should first assess the environmental changes and recommend a pivot. Impact assessment enables informed redirection. Releasing the team (A) terminates without assessment. Pausing to collect lessons learned (C) stops without exploring alternatives. Asking management for advice (D) defers decision-making without analysis. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Hybrid/Tailoring | 하이브리드 프로젝트로 여행 산업 스타트업의 앱을 개발 중이다. 예상치 못한 여행 제한으로 기능이 사용 불가능해졌다. PM은 무엇을 해야 하는가? | 팀을 해산하고 새 프로젝트에서 잠재력을 발휘하도록 돕는다 | 환경 변화를 평가하고 프로젝트의 피벗을 권장한다 | 비즈니스 가치 달성이 불가능하면 프로젝트를 일시 중지하고 교훈을 수집한다 | 조직 경영진에게 프로젝트 방향에 대한 조언을 요청한다 |  | B | 여행 제한으로 프로젝트 기능이 사용 불가능해질 때, PM은 먼저 환경 변화를 평가하고 프로젝트의 피벗을 권장해야 한다. 영향 평가와 적응이 가치를 보존한다. 팀 해산(A)은 포기이다. 일시 중지(C)는 평가 전에 성급하다. 경영진 조언(D)은 분석 후에 한다.
1457 | In an agile project that is about 45% complete, most team members are siloed and lack an understanding of each other's work. What would have most likely caused this communication breakdown? | The project manager failed to develop a communications management plan. | The weekly project status reports were not published regularly. | The sprint review meetings were not held regularly. | The daily standup meetings were not consistently attended. |  | D | When most agile team members at 45% completion are siloed and lack understanding of each other's work, the most likely cause is that daily standup meetings were not consistently attended. Standups are the primary agile mechanism for cross-team awareness. Not developing a communications plan (A) is broader but standups are the specific agile mechanism. Irregular status reports (B) are not agile-specific. Not holding sprint reviews (C) affects stakeholder feedback, not daily team communication. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 애자일 프로젝트가 45% 완료되었다. 대부분의 팀원이 사일로화되어 서로의 작업을 이해하지 못한다. 가장 가능성 있는 원인은? | PM이 커뮤니케이션 관리 계획을 개발하지 못했다 | 주간 프로젝트 상태 보고서가 정기적으로 게시되지 않았다 | 스프린트 리뷰 회의가 정기적으로 개최되지 않았다 | 일일 스탠드업 회의에 일관되게 참석하지 않았다 |  | D | 애자일 팀이 45% 완료 시점에 사일로화되어 있다면, 일일 스탠드업 회의에 일관되게 참석하지 않은 것이 가장 가능성 있는 원인이다. 스탠드업은 진행, 장애물, 조율을 위한 핵심 접점이다. 커뮤니케이션 계획(A)은 예측형 도구이다. 상태 보고(B)는 일방향이다. 스프린트 리뷰(C)는 이터레이션 종료 활동이다.
1458 | Three testers joined the project team just before the end of the build. During the project team meeting, the testers indicated that the project quality is poor, and they should not continue testing until all the defects are resolved. Which three actions should the project manager do? (Choose 3) | Ask the testers to provide additional information. | Stop the project and review the output. | Continue with testing according to the plan. | Ask the sponsor for assistance and guidance. | Brainstorm the issue with the project team. | A, C, E | When quality concerns arise from new testers joining the project, the PM should: (A) Request additional data to evaluate the validity and scope of reported defects. (C) Continue testing per the plan to gather more information without delaying progress. (E) Collaborate with the team to identify root causes and determine next steps. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 세 명의 테스터가 빌드 종료 직전에 프로젝트에 합류했다. 회의에서 테스터가 인도물에 결함이 있다고 지적했다. PM은 무엇을 해야 하는가? (3개 선택) | 테스터에게 추가 정보를 제공하도록 요청한다 | 프로젝트를 중단하고 산출물을 검토한다 | 계획에 따라 테스트를 계속한다 | 스폰서에게 지원과 지침을 요청한다 | 프로젝트 팀과 이슈를 브레인스토밍한다 | A, C, E | 새 테스터가 결함을 지적할 때, PM은: (A) 보고된 결함의 타당성과 범위를 평가하기 위해 추가 정보를 요청하고, (C) 중단 없이 계획에 따라 테스트를 계속하여 완전한 결과를 확보하고, (E) 프로젝트 팀과 브레인스토밍하여 근본 원인을 식별하고 해결한다. 프로젝트 중단(B)은 과도하다. 스폰서 지원(D)은 팀 해결 시도 후에 한다.
1459 | It is late at night on a weekend when a team member phones the project manager. The team member is upset about the pressures of an approaching deadline. What should the project manager do? | Ask the team member to send their concerns in writing. | Empathize with the team member and discuss next steps. | Review the organization ' s human resources (HR) policy. | Schedule a meeting with the team member for the next work day. |  | B | When a team member reaches out in distress about deadline pressure, the PM should respond with empathy and engage in a constructive discussion about next steps. This demonstrates emotional intelligence and ensures the team member feels heard and supported. Asking for written concerns (A) feels dismissive in an urgent emotional situation. Reviewing HR policy (C) is not immediately relevant. Scheduling a meeting for the next workday (D) delays the response when immediate support is needed. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 주말 늦은 밤에 팀원이 PM에게 전화했다. 팀원이 마감 압박으로 화가 나 있다. PM은 무엇을 해야 하는가? | 팀원에게 우려를 서면으로 보내도록 요청한다 | 팀원에게 공감하고 다음 단계를 논의한다 | 조직의 인사(HR) 정책을 검토한다 | 다음 근무일에 팀원과 회의를 예약한다 |  | B | 팀원이 마감 압박으로 고통을 호소할 때, PM은 공감하고 건설적인 다음 단계 논의에 참여해야 한다. 감정적 지능이 신뢰와 지원을 보여준다. 서면 요청(A)은 감정을 무시한다. HR 정책 검토(C)는 행정적이다. 다음 날 회의(D)는 긴급한 감정적 요구를 무시한다.
1460 | In an agile project, the project owner has repeatedly called for ad hoc meetings with team members. What should the project manager do? | Coach the project owner about the implications of unplanned meetings. | Discuss the issue with the project owner at the retrospective meeting. | Ask the team to focus only on the goal, not on ad hoc meetings. | Escalate the situation to management because it is affecting the team. |  | A | When the product owner repeatedly calls ad hoc meetings disrupting the agile team, the project manager should coach the product owner about the implications of unplanned meetings. Explaining the impact on workflow and suggesting structured alternatives preserves team productivity. Discussing at the retrospective (B) delays addressing the issue. Asking the team to ignore ad hoc meetings (C) creates conflict. Escalating to management (D) is premature. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 프로젝트에서 제품 책임자가 팀원들과 반복적으로 임시 회의를 소집한다. PM은 무엇을 해야 하는가? | 제품 책임자에게 비계획적 회의의 영향에 대해 코칭한다 | 회고 회의에서 제품 책임자와 이슈를 논의한다 | 팀에게 목표에만 집중하고 임시 회의에 신경 쓰지 말도록 요청한다 | 팀에 영향을 주고 있으므로 상황을 경영진에 에스컬레이션한다 |  | A | 제품 책임자가 반복적으로 임시 회의로 팀을 방해할 때, PM은 비계획적 회의의 영향에 대해 코칭해야 한다. 팀 방해와 스프린트 집중에 대한 영향 설명이 행동 변화를 유도한다. 회고 논의(B)는 너무 늦다. 무시 요청(C)은 문제를 해결하지 않는다. 에스컬레이션(D)은 직접 코칭 전에 과도하다.
1461 | A project manager is in rapid development mode on a joint application development module. The company wants delivery to occur in two weeks. The module needs to be integrated with other modules on a similar timeline, but release management has a three-week backlog. What should the project manager do? | Speak to the team and slow the current pace to ensure the team is in alignment with the release date | Push the team to deliver more so that the modules are developed and rolled out according to management ' s request | Have the team work toward the tighter deadline so that integration will be easier. | Speak to the stakeholders to resolve the bottleneck and see how the entire process can be streamlined |  | D | When in rapid development mode with a two-week delivery target but release management has a three-week backlog causing a bottleneck, the project manager should speak to stakeholders to resolve the bottleneck and streamline the process. Cross-functional collaboration addresses systemic constraints. Slowing the pace (A) delays delivery. Pushing the team harder (B) does not fix the bottleneck. Working toward the tighter deadline (C) ignores the release management constraint. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 공동 애플리케이션 개발 모듈의 신속 개발 모드에 있다. 2주 납품 목표이나 릴리스 관리에 3주 백로그가 있어 병목이 발생한다. PM은 무엇을 해야 하는가? | 팀과 대화하여 현재 속도를 늦추어 릴리스 일자와 맞추도록 한다 | 팀에게 더 많이 납품하도록 밀어붙여 관리진 기대에 따라 출시한다 | 팀이 더 빠른 마감에 맞추어 통합이 더 쉽도록 한다 | 이해관계자와 대화하여 병목을 해결하고 전체 프로세스를 간소화한다 |  | D | 신속 개발 모드에서 릴리스 관리 백로그로 병목이 발생할 때, PM은 이해관계자와 대화하여 병목을 해결하고 전체 프로세스를 간소화해야 한다. 근본 원인 해결이 전체 흐름을 개선한다. 속도 감소(A)는 납품을 지연시킨다. 더 밀어붙이기(B)는 팀을 소진시킨다. 빠른 마감(C)은 병목을 해결하지 않는다.
1462 | A software system is being built for a company. Once the system is in production, the team would like to collect usage data to evaluate the delivered value. Which evaluation practice should the project lead use to obtain accurate usage data? | Interview a sampling of users to obtain the usage data. | Send out a questionnaire to all users regarding the most useful features. | Build the functionality in the software to collect the operational usage data. | Embed a feedback form into the system for users to respond. |  | D | The correct answer is D. Embed a feedback form into the system for users to respond. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | General PM Principles | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 소프트웨어 시스템이 구축 중이다. 시스템이 운영에 들어가면 팀이 사용 데이터를 수집하고 싶다. 가장 좋은 방법은? | 일부 사용자를 인터뷰하여 사용 데이터를 얻는다 | 모든 사용자에게 가장 유용한 기능에 대한 설문지를 보낸다 | 소프트웨어에 운영 사용 데이터 수집 기능을 구축한다 | 시스템에 피드백 양식을 내장하여 사용자가 응답하도록 한다 |  | D | 정답은 D이다. 시스템에 피드백 양식을 내장하여 사용자가 응답하도록 한다. 이 접근법은 사용자가 자연스럽게 피드백을 제공할 수 있게 하여 적절한 이해관계자 참여를 유지한다. 인터뷰(A)는 표본이 제한적이다. 설문지(B)는 응답률이 낮을 수 있다. 자동 수집(C)은 사용자 의견이 아닌 행동 데이터만 제공한다.
1463 | A project manager is acting as a servant leader and is struggling to make deadlines on a critical roadway construction project that is falling behind schedule due to a low-performing team. In order to get the project back on track, what should the project manager do first? | Contact each team member to inform them that further schedule slips will not be tolerated by the project sponsor. | Begin holding daily meetings to assign each team member discrete tasks with specific due dates. | Empower the team members to conduct their job activities and hold each person accountable to improve the schedule. | Notify the project sponsor that the team is underperforming and request additional resources to compress the schedule, |  | C | As a servant leader on a critical roadway construction project falling behind schedule, the project manager should first empower the team members to conduct their job activities and hold each person accountable to improve the schedule. Servant leadership emphasizes flexibility, empathy, and empowering team members to take ownership of their work. Contacting each member to warn about schedule slips (A) is coercive and damages morale. Holding daily meetings to assign discrete tasks (B) is micromanaging, which contradicts servant leadership. Notifying the sponsor and requesting additional resources (D) should follow internal empowerment efforts, not precede them. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 서번트 리더로서 중요한 도로 건설 프로젝트에서 일정을 맞추기 어렵다. PM은 무엇을 해야 하는가? | 각 팀원에게 연락하여 더 이상의 일정 지연은 용납되지 않을 것임을 알린다 | 일일 회의를 시작하여 각 팀원에게 구체적 마감이 있는 작업을 할당한다 | 팀원에게 업무 활동을 수행할 권한을 부여하고 각 개인이 성과 개선에 책임지도록 한다 | 프로젝트 스폰서에게 팀이 실적이 저조하니 추가 자원을 요청한다고 통보한다 |  | C | 서번트 리더로서 일정이 뒤처질 때, PM은 팀원에게 업무 활동을 수행할 권한을 부여하고 성과 개선에 책임지도록 해야 한다. 권한 부여와 책임이 서번트 리더십 원칙에 부합한다. 경고(A)는 지시적이다. 일일 작업 할당(B)은 마이크로매니지먼트이다. 스폰서 통보(D)는 팀 역량을 활용하기 전에 에스컬레이션이다.
1464 | A project manager identifies an issue between two team members that is affecting the development of one of the deliverables during the second iteration of a project. How should the project manager address this issue to avoid any impact to the project? | Schedule a meeting with both team members to understand the issue and facilitate a solution that satisfies both parties. 1288 | Send a warning to both team members indicating that if the issue continues, both will be removed from the project. | Contact the functional managers to request substitutes for the conflicting team members. | Escalate both team members to their respective functional managers and let them take the appropriate actions |  | A | When an issue between two team members affects deliverable development during the second iteration, the project manager should schedule a meeting with both to understand the issue and facilitate a resolution. Direct conflict resolution preserves team dynamics. Sending warnings (B) is punitive. Requesting substitutes from functional managers (C) avoids resolution. Escalating to functional managers (D) delegates the PM's responsibility. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | PM이 두 팀원 사이의 문제를 발견했고 이것이 인도물 개발에 영향을 준다. PM은 무엇을 해야 하는가? | 두 팀원과 회의를 예약하여 문제를 이해하고 양측을 만족시키는 해결을 촉진한다 | 두 팀원에게 문제가 계속되면 프로젝트에서 제외될 것이라는 경고를 보낸다 | 기능 관리자에게 연락하여 갈등하는 팀원의 대체를 요청한다 | 두 팀원을 각각의 기능 관리자에게 에스컬레이션하고 적절한 조치를 취하도록 한다 |  | A | 두 팀원 간 문제가 인도물 개발에 영향을 줄 때, PM은 양측과 회의를 예약하여 문제를 이해하고 양측을 만족시키는 해결을 촉진해야 한다. 협력적 갈등 해결이 관계와 프로젝트를 보전한다. 경고(B)는 위협적이다. 대체 요청(C)은 과도하다. 에스컬레이션(D)은 직접 해결 시도 전에 시기상조이다.
1465 | An organization is initiating a project that will be using new technology. The complexity of the project requires excellent technical skills. After reviewing the proposed project management plan, the project sponsor asks for options to reduce the labor cost without introducing risk to the project delivery. What should the project manager do first? | Analyze the resource pool and assign internal resources who participated in past projects. | Perform an analysis of the key cost drivers and present alternatives. 1319 | Review the risk register and assign functional managers as resources. | Review the work breakdown structure (WBS) to ensure there are adequate resources. |  | B | When the sponsor asks for options to reduce labor cost on a complex new technology project without introducing risk, the project manager should first perform an analysis of key cost drivers and present alternatives. Analysis identifies targeted reductions. Assigning internal resources from past projects (A) may not address cost drivers. Reviewing the risk register (C) focuses on risk, not cost. Reviewing the WBS for adequate resources (D) verifies adequacy, not cost reduction. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Lean | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 조직이 새 기술을 사용하는 프로젝트를 시작한다. 스폰서가 리스크 없이 인건비를 줄일 옵션을 요청한다. PM은 무엇을 먼저 해야 하는가? | 자원 풀을 분석하고 과거 프로젝트에 참여한 내부 자원을 배정한다 | 주요 비용 동인을 분석하고 대안을 제시한다 | 리스크 등록부를 검토하고 기능 관리자를 자원으로 배정한다 | WBS를 검토하여 적절한 자원이 있는지 확인한다 |  | B | 스폰서가 리스크 없이 인건비 절감 옵션을 요청할 때, PM은 먼저 주요 비용 동인을 분석하고 대안을 제시해야 한다. 비용 동인 분석이 정보에 기반한 의사결정의 기초이다. 내부 자원 배정(A)은 분석 없는 행동이다. 기능 관리자 배정(C)은 적절한 역할이 아니다. WBS 검토(D)는 비용이 아닌 범위 도구이다.
1466 | A geographically distributed project team working on an iterative project adopts a new mode of communication following changes in health protocols. The colocated team members are finding themselves challenged with understanding verbal communication and collaboration methods. What should the project manager do? | Escalate these communication challenges to the project sponsor. | Allow collaboration to smooth out communication between team members. | Organize a team meeting to resolve the communication challenges. | Add collaboration tools to the communications management plan. |  | D | When a distributed team faces verbal communication challenges due to new health protocols, the project manager should add collaboration tools to the communications management plan. Updated tools provide alternative communication methods that accommodate the new constraints. Escalating to the sponsor (A) is premature. Allowing collaboration to smooth out naturally (B) is passive. Organizing a single team meeting (C) provides a one-time fix, not a sustainable solution. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 지리적으로 분산된 반복 프로젝트 팀이 건강 프로토콜로 인해 새로운 커뮤니케이션 방식을 채택했다. 구두 소통에 어려움이 있다. PM은 무엇을 해야 하는가? | 커뮤니케이션 문제를 프로젝트 스폰서에게 에스컬레이션한다 | 팀원 간 커뮤니케이션이 원활해지도록 협업을 허용한다 | 팀 회의를 조직하여 커뮤니케이션 문제를 해결한다 | 커뮤니케이션 관리 계획에 협업 도구를 추가한다 |  | D | 분산된 팀이 건강 프로토콜로 구두 소통에 어려움이 있을 때, PM은 커뮤니케이션 관리 계획에 협업 도구를 추가해야 한다. 업데이트된 도구가 비대면 환경에서 효과적 소통을 지원한다. 에스컬레이션(A)은 과도하다. 자연적 협업(B)은 구조가 부족하다. 팀 회의(C)는 도구 없이는 같은 문제가 반복된다.
1467 | When trying to track project benefits, a project manager realizes that some key performance indicators (KPIs) are not yet defined. What should the project manager do? | Coordinate with the benefit owner to track and collect the missing data and build the KPIs. | Forward the issue to the benefit owner and ask them to collect the missing data and build the KPIs. | Ask the program manager to track and collect the missing data and work to build the KPIs. | Work with the business analysts to track and collect the missing data and build the KPIs. |  | A | When key KPIs for tracking project benefits are not yet defined, the project manager should coordinate with the benefit owner to track and collect the missing data and build the KPIs. Collaboration with the benefit owner ensures aligned metrics. Forwarding the issue to the benefit owner (B) delegates without partnership. Asking the program manager (C) misassigns responsibility. Working with business analysts (D) may be part of the process but the benefit owner is the primary stakeholder. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 프로젝트 혜택을 추적하려 할 때 일부 핵심 KPI가 아직 정의되지 않았음을 발견했다. PM은 무엇을 해야 하는가? | 혜택 소유자와 조율하여 누락된 데이터를 추적하고 수집하여 KPI를 구축한다 | 혜택 소유자에게 이슈를 전달하고 누락된 데이터 수집 및 KPI 구축을 요청한다 | 프로그램 관리자에게 누락된 데이터를 추적하고 KPI 구축 작업을 요청한다 | 비즈니스 분석가와 협력하여 누락된 데이터를 추적하고 수집하여 KPI를 구축한다 |  | A | 핵심 KPI가 정의되지 않았을 때, PM은 혜택 소유자와 조율하여 누락된 데이터를 추적하고 수집하여 KPI를 구축해야 한다. 혜택 소유자와의 협력이 적절한 KPI 정의를 보장한다. 이슈 전달(B)은 책임 회피이다. 프로그램 관리자(C)는 적절한 역할이 아니다. 비즈니스 분석가(D)는 혜택 소유권이 없다.
1468 | A project manager is working on a project that is using a hybrid approach. One key input for the deliverable will be from the outcome of another project that is using an agile approach. What should the project manager do next? | Participate in the other project ' s daily standup meetings. | Ask the other project manager to change the delivery methodology. | Request that the other project manager develop a work breakdown structure (WBS). | Align with the other project manager ' s high-level project time lines. |  | D | When a hybrid project depends on deliverables from another project using an agile approach, the project manager should align with the other project manager's high-level project timelines. This ensures coordinated handoffs and dependency management while respecting each project's methodology. Participating in the other project's daily standups (A) is time-consuming and over-involved. Asking them to change methodology (B) is inappropriate. Requesting a WBS from an agile project (C) imposes predictive structure on agile delivery. | Process | Determine Appropriate PM Methodology | Development Approach & Life Cycle | Tailor Based on Context | Hybrid | Tailored Approach | Process | Develop Integrated PM Plan | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Hybrid/Tailoring | PM이 하이브리드 접근법을 사용하는 프로젝트를 작업 중이다. 핵심 인도물이 애자일 접근법을 사용하는 다른 프로젝트에서 올 예정이다. PM은 무엇을 해야 하는가? | 다른 프로젝트의 데일리 스탠드업 회의에 참석한다 | 다른 PM에게 납품 방법론을 변경하도록 요청한다 | 다른 PM에게 WBS를 개발하도록 요청한다 | 다른 PM의 상위 수준 프로젝트 일정에 맞춰 정렬한다 |  | D | 하이브리드 프로젝트가 애자일 프로젝트의 인도물에 의존할 때, PM은 다른 PM의 상위 수준 프로젝트 일정에 맞춰 정렬해야 한다. 상위 수준 정렬이 프로젝트 간 종속성을 관리한다. 스탠드업 참석(A)은 과도한 참여이다. 방법론 변경(B)은 부적절한 요청이다. WBS 요청(C)은 애자일에 맞지 않다.
1469 | A project manager is managing a new development program to automate some technical functions. During project kickoff, the project manager expresses the need for a technical architect to support the project for a moderate amount of time. The project sponsor informs the project manager about an existing technical architect who possesses valuable knowledge but is already assigned at the portfolio level. What engagement model should the project manager use for the technical architect role to ensure project success? | Assign the existing technical architect to solely be dedicated to the current project. | Share the existing technical architect so they can be allocated to the current project and other projects. | Hire a new technical architect who would be solely dedicated to the current project. | Hire a new technical architect who would be shared between the current project and other projects. |  | B | For a technical architect who possesses valuable knowledge but is already assigned at the portfolio level, the project manager should use a shared engagement model—allocating the architect between the current project and other projects. This approach leverages existing expertise efficiently without disrupting portfolio-level responsibilities. Dedicating the architect solely to the current project (A) ignores their existing commitments. Hiring a new dedicated architect (C) is costly and loses the valuable existing knowledge. Hiring a new shared architect (D) adds cost while the needed expertise already exists in the organization. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Business Environment | Define and Establish Governance | Stakeholders | Monitoring & Controlling | Be an Accountable Leader | Monitor Stakeholder Engagement | Traditional PM | PM이 기술 기능 자동화를 위한 새 개발 프로그램을 관리 중이다. 킥오프 시 기존 기술 아키텍트가 포트폴리오 수준에서 이미 배정되어 있음을 발견했다. PM은 무엇을 해야 하는가? | 기존 기술 아키텍트를 현재 프로젝트에만 전담 배정한다 | 기존 기술 아키텍트를 현재 프로젝트와 다른 프로젝트에 공유 배정한다 | 현재 프로젝트에만 전담할 새 기술 아키텍트를 채용한다 | 현재 프로젝트와 다른 프로젝트 간 공유할 새 기술 아키텍트를 채용한다 |  | B | 포트폴리오 수준에서 이미 배정된 기술 아키텍트가 있을 때, PM은 공유 배정 모델을 사용해야 한다. 기존 지식과 경험을 활용하면서 다른 프로젝트도 지원한다. 전담 배정(A)은 다른 프로젝트에 영향을 준다. 새 아키텍트 채용(C, D)은 기존 지식을 활용하지 못하고 시간과 비용이 든다.
1470 | A project manager is working on a large project in another country and realizes that only a few people from the project team are working on all of the releases. What should the project manager do to prevent this in the future? | Document the risk register in the project charter. | Involve the product owner to rewrite the user stories. | Review user roles and update the team charter. | Speak to the customer and add the issue to the issue log. |  | C | When only a few people handle all releases in a large international project, the project manager should review user roles and update the team charter. Clear role definition prevents workload imbalance. Documenting the risk register in the charter (A) conflates documents. Involving the PO to rewrite stories (B) addresses content, not assignment. Speaking to the customer (D) escalates unnecessarily. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | PM이 다른 나라에서 대규모 프로젝트를 작업 중이다. 소수의 사람만 모든 릴리스를 처리한다. PM은 무엇을 해야 하는가? | 프로젝트 헌장에 리스크 등록부를 문서화한다 | 제품 책임자를 참여시켜 사용자 스토리를 다시 작성한다 | 사용자 역할을 검토하고 팀 헌장을 업데이트한다 | 고객과 대화하고 이슈 로그에 이슈를 추가한다 |  | C | 소수만 모든 릴리스를 처리할 때, PM은 사용자 역할을 검토하고 팀 헌장을 업데이트해야 한다. 명확한 역할 정의가 업무 불균형을 방지하고 책임을 분산한다. 리스크 등록(A)은 헌장에 포함하지 않는다. 스토리 재작성(B)은 역할 문제를 해결하지 않는다. 고객 대화(D)는 내부 문제를 외부에 노출한다.
1471 | One member of the project team has the necessary skills to execute a critical feature of the product. However, another team member wants to take on the challenging task. What should the project manager do? | Assign the task to the less experienced member to help improve their skills, with the support of the experienced member. | Encourage both team members to collaborate and work using their respective strengths to 229 deliver the project. | Negotiate with the customer to postpone the particular feature to resolve the situation between the team members. | Schedule a meeting with both team members to let them discuss the best course of action . |  | A | When one team member has the skills for a critical feature and another less experienced member wants to take on the challenge, the project manager should assign the task to the less experienced member with the support of the experienced member. This mentored assignment balances delivery risk with capability development—the experienced member provides a safety net while the less experienced member grows. Encouraging general collaboration (B) is less precise and does not ensure structured development. Scheduling a meeting for both to discuss (D) delays the decision without providing direction. Negotiating with the customer to postpone (C) is unnecessary and inappropriate—internal staffing decisions should not affect customer timelines. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 한 팀원이 핵심 기능 실행에 필요한 기술을 갖고 있다. 경험이 적은 다른 팀원이 도전하고 싶어한다. PM은 무엇을 해야 하는가? | 경험이 적은 팀원에게 작업을 할당하고 경험 있는 팀원의 지원을 받도록 한다 | 양 팀원이 각자의 강점을 활용하여 기능을 협력적으로 납품하도록 장려한다 | 상황 해결을 위해 고객과 협상하여 해당 기능을 연기한다 | 두 팀원과 회의를 예약하여 최선의 행동 방침을 논의하도록 한다 |  | A | 경험 있는 팀원의 기술이 필요하지만 경험이 적은 팀원이 도전하고 싶을 때, PM은 경험이 적은 팀원에게 작업을 할당하되 경험 있는 팀원의 지원을 받도록 해야 한다. 멘토링과 지원이 기술 개발을 촉진한다. 협력(B)은 좋지만 성장 기회를 명확히 하지 않는다. 연기(C)는 불필요하다. 회의(D)는 결정을 지연시킨다.
1472 | A customer is concerned with the quality of the product delivery, as the production deployment is approaching. What should the project manager do next to ensure acceptance of the deliverables? | Verify the production budget before advancing the product. | Test product integration in accordance with the requirements. | Review the approved exit criteria for the product. | Evaluate the quality checklist for product compliance. |  | C | When a customer is concerned about product quality as production deployment approaches, the project manager should review the approved exit criteria for the product. Exit criteria provide objective measures for deliverable readiness and acceptance. Verifying the production budget (A) addresses cost, not quality. Testing product integration (B) is one testing activity, not a quality assurance framework. Evaluating the quality checklist (D) is useful but exit criteria are the formal acceptance standard. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 고객이 프로덕션 배포가 다가오면서 제품 납품 품질에 우려를 표명한다. PM은 무엇을 해야 하는가? | 제품 진행 전 프로덕션 예산을 확인한다 | 요구사항에 따라 제품 통합을 테스트한다 | 제품의 승인된 종료 기준을 검토한다 | 제품 준수를 위한 품질 체크리스트를 평가한다 |  | C | 프로덕션 배포가 다가올 때 고객이 품질에 우려하면, PM은 제품의 승인된 종료 기준을 검토해야 한다. 종료 기준이 품질을 측정하는 객관적 기준을 제공한다. 예산 확인(A)은 품질과 무관하다. 통합 테스트(B)는 활동이지 기준 확인이 아니다. 품질 체크리스트(D)는 유용하지만 종료 기준이 더 포괄적이다.
1473 | A project manager is executing a project on time and on budget. Before a stage gate review, the project manager receives the regular business management report, but this time it entails a negative impact on the project success factors. What should the project manager do? | Provide the necessary analysis to enable examination of the business value. | Request a delay to the stage gate until business development provides the next update. | Call for business development to revalidate inputs at the next stage gate. | Continue with execution since the project was successful up to this phase. |  | A | When a negative business management report impacts project success factors before a stage gate review, the project manager should provide the necessary analysis to enable examination of the business value. Analysis informs decision-making. Requesting a delay (B) avoids action. Calling for revalidation at the next gate (C) defers. Continuing as-is (D) ignores the negative report. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | PM이 일정과 예산에 맞게 프로젝트를 실행 중이다. 스테이지 게이트 리뷰 전에 부정적인 사업 관리 보고서를 받았다. PM은 무엇을 해야 하는가? | 사업 가치 검토를 가능하게 하는 필요한 분석을 제공한다 | 사업 개발부가 다음 업데이트를 제공할 때까지 스테이지 게이트를 지연 요청한다 | 다음 스테이지 게이트에서 사업 개발부에 입력을 재검증하도록 요청한다 | 이 단계까지 프로젝트가 성공적이었으므로 실행을 계속한다 |  | A | 스테이지 게이트 리뷰 전 부정적 사업 보고서를 받으면, PM은 사업 가치 검토를 가능하게 하는 필요한 분석을 제공해야 한다. 데이터 기반 분석이 정보에 기반한 게이트 결정을 지원한다. 지연(B)은 의사결정을 방해한다. 재검증(C)은 현재 결정을 미룬다. 계속 실행(D)은 새 정보를 무시한다.
1474 | A project manager received a request to add features and functions to the project after the scope had already been established. What should the project manager do? | Follow the risk management process. | Follow the stakeholder engagement process. | Follow the change management process. | Follow the requirements management process. |  | C | When a request to add features comes after scope has been established, the project manager should follow the change management process. Formal change control evaluates impact, documents changes, and requires CCB approval before implementation. Following the risk management process (A) addresses risks, not scope changes. Following the stakeholder engagement process (B) manages relationships. Following the requirements management process (D) tracks requirements but does not govern changes. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 범위가 이미 수립된 후 프로젝트에 기능 추가 요청을 받았다. PM은 무엇을 해야 하는가? | 리스크 관리 프로세스를 따른다 | 이해관계자 참여 프로세스를 따른다 | 변경 관리 프로세스를 따른다 | 요구사항 관리 프로세스를 따른다 |  | C | 범위 수립 후 기능 추가 요청을 받으면, PM은 변경 관리 프로세스를 따라야 한다. 공식적 변경 통제가 영향을 평가하고 변경을 문서화하며 적절한 승인을 보장한다. 리스크 관리(A)는 변경 평가의 일부이지만 전체 프로세스가 아니다. 이해관계자 참여(B)는 변경 처리가 아니다. 요구사항 관리(D)는 초기 단계 활동이다.
1475 | A company must implement a new regulation. The government has specified the date when the regulation will be enforced but has only provided high-level information on the regulation's requirements. Therefore, changes in definitions are to be expected due to uncertainty. Which life cycle should the project manager use for this project? | An agile execution strategy | An iterative execution strategy | A predictive execution strategy | A hybrid execution strategy |  | A | When implementing a new regulation with a fixed enforcement date but only high-level requirements and expected changes in definitions, the project manager should use an agile execution strategy. Agile accommodates evolving requirements and uncertainty. Iterative (B) is similar but agile specifically handles changing definitions. Predictive (C) requires stable requirements. Hybrid (D) may work but agile is most appropriate for high uncertainty. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 회사가 새 규제를 구현해야 한다. 정부가 시행일을 지정했지만 상위 수준의 요구사항만 있고 정의가 변경될 것으로 예상된다. 어떤 실행 전략을 사용해야 하는가? | 애자일 실행 전략 | 반복적 실행 전략 | 예측형 실행 전략 | 하이브리드 실행 전략 |  | A | 고정 시행일이 있지만 상위 수준 요구사항만 있고 정의 변경이 예상될 때, 애자일 실행 전략을 사용해야 한다. 애자일이 변화하는 요구사항에 적응하면서 가치를 점진적으로 전달한다. 반복적(B)은 유사하지만 덜 유연하다. 예측형(C)은 불확실한 요구사항에 부적합하다. 하이브리드(D)는 고정 요소가 부족하여 불필요하다.
1476 | A project manager received the project charter for a new product. The project is expected to have two main deliveries: the hardware part that has detailed specifications already defined, including a sample machine, and the user interface software that has only a basic specification and a requirement for a user experience design approach. Which project management approach should the project manager use? | The deliverables are significantly different, so the project should be split into two projects that are driven by a program. | The scope is well defined; therefore, a predictive approach is straightforward and the hardware and software can by synchronized on the gates. | The software development has a high uncertainty level, so an agile approach is recommended for the project. | A hybrid approach will work, using agile for software development and a predictive approach for the hardware deliveries. |  | D | When a project has hardware with detailed specifications and software with only basic specifications requiring UX design, the project manager should use a hybrid approach — agile for software development and predictive for hardware deliveries. This tailors the methodology to each deliverable's nature. Splitting into two program-driven projects (A) adds overhead. Using purely predictive (B) ignores software uncertainty. Using purely agile (C) is unsuitable for well-defined hardware. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Hybrid/Tailoring | PM이 새 제품의 프로젝트 헌장을 받았다. 하드웨어(상세 사양)와 소프트웨어(기본 사양, UX 디자인 필요)의 두 주요 납품이 있다. 어떤 접근법을 권장하는가? | 인도물이 크게 다르므로 프로젝트를 두 개로 분리한다 | 범위가 잘 정의되어 있으므로 예측형 접근법이 직관적이다 | 소프트웨어가 높은 불확실성이 있으므로 전체 프로젝트에 애자일을 권장한다 | 하이브리드 접근법—소프트웨어에 애자일, 하드웨어에 예측형을 사용한다 |  | D | 하드웨어(상세 사양)와 소프트웨어(기본 사양, UX 필요)가 있는 프로젝트에서는 하이브리드 접근법을 사용해야 한다. 소프트웨어에 애자일, 하드웨어에 예측형이 각각의 특성에 맞다. 분리(A)는 통합을 어렵게 한다. 예측형(B)은 소프트웨어 불확실성을 다루지 못한다. 전체 애자일(C)은 상세 하드웨어 사양에 맞지 않는다.
1477 | During a regular project progress meeting, the CEO informed the project manager that a major stakeholder has been unaware of recent developments on the project. The project manager is sure that the stakeholder was duly identified and classified in the stakeholder register. Which project document should the project manager review in order to determine the reason for this issue? | Stakeholder register | Requirements traceability matrix | Issue log | Stakeholder engagement assessment matrix |  | D | When a major stakeholder is unaware of recent project developments despite being identified in the stakeholder register, the project manager should review the stakeholder engagement assessment matrix. This tool tracks and compares desired versus actual stakeholder engagement levels, revealing gaps in communication effectiveness. The stakeholder register (A) confirms identification but not engagement effectiveness. The requirements traceability matrix (B) tracks requirements, not stakeholder communication. The issue log (C) records problems but does not specifically assess engagement gaps. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 정기 진행 회의 중 CEO가 PM에게 주요 이해관계자가 최근 프로젝트 개발을 모르고 있다고 알렸다. PM은 어떤 문서를 검토해야 하는가? | 이해관계자 등록부 | 요구사항 추적 매트릭스 | 이슈 로그 | 이해관계자 참여 평가 매트릭스 |  | D | 주요 이해관계자가 프로젝트 개발을 모르고 있을 때, PM은 이해관계자 참여 평가 매트릭스를 검토해야 한다. 이 매트릭스는 현재와 원하는 참여 수준의 격차를 보여준다. 이해관계자 등록부(A)는 식별 정보이지 참여 수준이 아니다. 추적 매트릭스(B)는 요구사항용이다. 이슈 로그(C)는 문제 기록이다.
1478 | A project manager of an infrastructure development project receives multiple issues from the customer validation team close to the product launch date. What should the project manager do to manage such a situation for upcoming phases? | Ensure customer validation occurs more frequently during the life cycle of the project. | Revise the project schedule to accommodate fixing discovered issues. | Ask the project team to increase unit testing of the deliverables. | Review the customer validation team ' s test plan early in the life cycle. |  | A | When multiple customer validation issues emerge close to product launch, the project manager should ensure customer validation occurs more frequently during the project lifecycle for upcoming phases. Continuous validation prevents late-stage surprises through early detection. Revising the schedule to accommodate fixes (B) is reactive. Increasing unit testing (C) addresses internal quality but not customer-centric validation. Reviewing the test plan early (D) is helpful but does not ensure ongoing validation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 인프라 개발 프로젝트의 PM이 제품 출시 직전 고객 검증팀으로부터 여러 이슈를 받았다. PM은 향후 무엇을 해야 하는가? | 프로젝트 수명주기 동안 고객 검증이 더 자주 발생하도록 보장한다 | 발견된 이슈 수정을 위해 프로젝트 일정을 수정한다 | 프로젝트 팀에 인도물의 단위 테스트를 늘리도록 요청한다 | 프로젝트 수명주기 초기에 고객 검증팀의 테스트 계획을 검토한다 |  | A | 제품 출시 직전 여러 고객 검증 이슈가 나오면, PM은 향후 프로젝트 수명주기 동안 고객 검증이 더 자주 발생하도록 보장해야 한다. 빈번한 검증이 이슈를 조기에 발견한다. 일정 수정(B)은 사후적이다. 단위 테스트(C)는 개발 수준이지 고객 검증이 아니다. 테스트 계획 검토(D)는 유용하지만 빈도가 핵심이다.
1479 | A project manager works for an IT consulting firm that has submitted a bid during the request for proposal (RFP) process for a contract that focuses on data center migration and optimization. However, the consulting firm has little experience in data center optimization. What should the project manager do? | Request a budget to build this competency among project team members. | Send the team to a data center optimization training workshop. | Outsource the data center optimization work to a vendor. | Partner with a company that is an expert in this area. |  | D | The PM should partner with a company that has expertise in the unfamiliar area. Procurement management involves selecting, managing, and controlling external vendor relationships to complement organizational capabilities. Proper oversight, deliverable monitoring, and performance management through established procurement processes ensure project success even when internal expertise is limited. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | PM이 IT 컨설팅 회사에서 일하며 RFP 과정에서 입찰을 제출했다. 팀이 특정 영역에 익숙하지 않다. PM은 무엇을 해야 하는가? | 팀원 역량 구축을 위한 예산을 요청한다 | 팀을 데이터 센터 최적화 교육 워크숍에 보낸다 | 데이터 센터 최적화 작업을 벤더에게 아웃소싱한다 | 이 영역의 전문 회사와 파트너십을 맺는다 |  | D | 팀이 특정 영역에 익숙하지 않을 때, PM은 해당 영역의 전문 회사와 파트너십을 맺어야 한다. 파트너십이 전문성을 보완한다. 역량 구축 예산(A)은 시간이 오래 걸린다. 교육(B)은 깊은 전문성을 달성하기 어렵다. 아웃소싱(C)은 통제력이 부족하다.
1480 | While following up on a deliverable, a team member expresses concern to the project manager about working with another team member. This team member states that the other team member, who is a functional manager, is often defensive and aggressive during meetings. How should the project manager handle this situation? | Monitor the situation for a few weeks to determine if the disruptive team member ' s attitude changes. | Report the disruptive team member to the human resource (HR) department. | Encourage both team members to meet as soon as possible and resolve the problem | Suggest that the team member ignore the disruptive team member and focus only on the work. |  | C | When a team member reports that a functional manager is defensive and aggressive during meetings, the project manager should encourage both team members to meet as soon as possible and resolve the problem. Direct collaborative conflict resolution addresses the issue promptly. Monitoring for weeks (A) allows the behavior to continue. Reporting to HR (B) should be a last resort. Suggesting the concerned member ignore the behavior (D) dismisses the legitimate concern. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀원이 다른 팀원이 방어적이고 공격적이라고 PM에게 우려를 표명했다. PM은 무엇을 해야 하는가? | 몇 주간 상황을 모니터링하여 방해 팀원의 태도가 변하는지 확인한다 | 방해 팀원을 인사부(HR)에 보고한다 | 양 팀원이 가능한 빨리 만나 문제를 해결하도록 격려한다 | 팀원에게 방해 팀원을 무시하고 업무에만 집중하라고 제안한다 |  | C | 팀원이 다른 팀원의 방어적이고 공격적 행동에 우려할 때, PM은 양측이 가능한 빨리 만나 문제를 해결하도록 격려해야 한다. 직접적 갈등 해결이 효과적이다. 모니터링(A)은 수동적이다. HR 보고(B)는 직접 해결 시도 전에 과도하다. 무시(D)는 문제를 해결하지 않는다.
1481 | Due to a recent company merger, a project manager from company B has been assigned to a team that is comprised of team members from company A. At the start of the project, conflicts arise due to a lack of clarity on processes and the project manager's relationship with company B. What should the project manager do to resolve this conflict? | Work with the team to analyze which processes are suitable to use and define them inthe ground rules. | Ask the team to use company B ' s processes since they are more familiar with theseprocesses. | Avoid the conflict as the customer feels comfortable with using processes fromcompany A. | Review the historical information and make the decision based on the return oninvestment (ROI). |  | A | When post-merger conflicts arise from unclear processes and the PM's relationship with the other company, the project manager should work with the team to analyze suitable processes and define them in ground rules. Collaborative process definition builds team ownership. Asking the team to use company B's processes (B) is biased. Avoiding the conflict (C) allows issues to fester. Deciding based on ROI (D) does not address team dynamics. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 최근 합병으로 B사의 PM이 A사 팀원으로 구성된 팀에 배정되었다. 프로세스 사용에 갈등이 있다. PM은 무엇을 해야 하는가? | 팀과 함께 적합한 프로세스를 분석하고 기본 규칙에 정의한다 | PM이 더 익숙한 B사 프로세스를 사용하도록 팀에 요청한다 | 고객이 A사 프로세스에 편안해하므로 갈등을 피한다 | 과거 정보를 검토하고 투자수익률(ROI)에 기반하여 결정한다 |  | A | 합병 후 프로세스 갈등이 발생할 때, PM은 팀과 함께 적합한 프로세스를 분석하고 기본 규칙에 정의해야 한다. 협력적 프로세스 정의가 팀 합의를 구축한다. B사 프로세스 강요(B)는 일방적이다. 갈등 회피(C)는 문제를 해결하지 않는다. ROI 기반(D)은 프로세스 결정에 부적합하다.
1482 | Since the beginning of a project, the product owner keeps asking during ceremonies about the budget spent for each product iteration. The product owner seems much more interested in the cost rather than the product itself. What should the project manager have done earlier to change the product owner's behavior? | Worked on a communications management plan with reports of budget spent in each iteration versus planned to avoid these discussions during ceremonies | Worked on different approaches of estimating to give confidence of the cost spent in each product increment. | Worked with the product owner to clarify their role in an agile project and the scope of the agile ceremonies | Worked on a fixed-price contract to switch the product owner ' s attention to value instead of money |  | C | When the product owner keeps asking about budget during agile ceremonies, the project manager should have worked with the product owner to clarify their role in an agile project and the scope of agile ceremonies. Ceremonies focus on product value, collaboration, and adaptation—not budget reporting. Working on a communications plan with budget reports (A) feeds the distraction. Using different estimation approaches (B) does not address the role confusion. Using a fixed-price contract (D) changes commercial terms without fixing the behavioral issue. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 초기부터 제품 책임자가 각 이터레이션에서 사용한 예산을 묻는다. PM이 이전에 무엇을 했어야 하는가? | 각 이터레이션의 계획 대비 소비 예산 보고서가 포함된 커뮤니케이션 관리 계획을 작성했다 | 각 제품 증분에 소비된 비용에 대한 신뢰를 주기 위해 다양한 추정 접근법을 작업했다 | 제품 책임자와 애자일 프로젝트에서의 역할과 애자일 계약 범위를 명확히 했다 | 제품 책임자의 관심을 비용에서 가치로 전환하기 위해 고정가 계약을 작업했다 |  | C | 제품 책임자가 지속적으로 예산을 문의할 때, PM은 제품 책임자와 애자일 프로젝트에서의 역할과 범위를 명확히 했어야 한다. 역할 명확화가 적절한 초점을 설정한다. 예산 보고서(A)는 추가 정보이지만 근본 해결이 아니다. 추정 접근법(B)은 기술적이다. 고정가 계약(D)은 계약 조건이지 역할 명확화가 아니다.
1483 | A project manager has taken over a project and realizes a number of the suppliers responsible for the delivery have not done an implementation as complex and large as this project. The project manager reviews the risk log and logs this as a risk. Three months later, two suppliers have missed key milestone dates and delivered substandard work. What should the project manager do? | Support the suppliers by providing them with additional resources. | Execute the risk response plan and update the issue log. | Execute the risk response plan and update the action register. | Ask suppliers to submit a revised plan and schedule. |  | B | The correct answer is B. Execute the risk response plan and update the issue log. Risk management involves systematic identification, analysis, and response planning. The PM should document risks in the risk register and implement response strategies to minimize project impacts. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | PM이 프로젝트를 인수했는데 납품 담당 공급업체가 요구사항을 충족하지 못한 것을 발견했다. PM은 무엇을 해야 하는가? | 공급업체에 추가 자원을 제공하여 지원한다 | 리스크 대응 계획을 실행하고 이슈 로그를 업데이트한다 | 리스크 대응 계획을 실행하고 조치 등록부를 업데이트한다 | 공급업체에 수정된 계획과 일정을 제출하도록 요청한다 |  | B | 정답은 B이다. 리스크 대응 계획을 실행하고 이슈 로그를 업데이트한다. 리스크 관리는 체계적 식별, 분석, 대응 계획을 포함한다. PM은 리스크가 실현되면 대응 계획을 실행하고 이슈 로그에 문서화해야 한다. 추가 자원(A)은 대응 계획 없는 행동이다. 조치 등록부(C)는 이슈 로그가 더 적절하다. 수정 계획 요청(D)은 사후적이다.
1484 | A project manager is planning a project and identifies that legislation requirements for specific project tasks will be changing. This will occur halfway through the project execution phase and will affect a few key workers' licenses, which will become noncompliant. What should the project manager do? | Maintain the current key workers since the project has already started. | Start scheduling the training for key workers now to ensure compliance. | Update the project charter to ensure the new legislation is addressed, | Start a recruitment drive for new workers with the licenses required. |  | B | When legislation changes will make key workers' licenses noncompliant midway through execution, the project manager should start scheduling training now to ensure compliance. Proactive training prevents disruption. Maintaining current workers without action (A) risks noncompliance. Updating the charter (C) is a document change, not a practical solution. Recruiting new workers (D) is more disruptive than training. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 프로젝트를 계획 중인데 특정 작업에 필요한 법률 요구사항이 실행 중간에 변경될 것임을 식별했다. 핵심 인력의 자격증이 비준수가 된다. PM은 무엇을 해야 하는가? | 프로젝트가 이미 시작되었으므로 현재 핵심 인력을 유지한다 | 준수를 보장하기 위해 지금 핵심 인력의 교육 일정을 시작한다 | 새 법률이 반영되도록 프로젝트 헌장을 업데이트한다 | 필요한 자격증을 가진 새 인력 채용을 시작한다 |  | B | 법률 변경으로 핵심 인력의 자격증이 비준수가 될 때, PM은 지금 교육 일정을 시작하여 준수를 보장해야 한다. 사전적 교육이 중단 없는 프로젝트 실행을 보장한다. 현재 인력 유지(A)는 비준수 리스크이다. 헌장 업데이트(C)는 법률 대응이 아니다. 새 인력 채용(D)은 기존 인력의 프로젝트 지식을 잃는다.
1485 | A contractor delivering construction services to a company is using agile principles to manage the project tasks. Engineers are producing frequent design changes due to new legislation. There is a risk the contractor may lose money due to resources waiting on design changes or performing rework. What should the project manager do to minimize the cost? | Capture the engineers ' feedback at the daily meeting and communicate it to the product owner. | Cancel the project release resources, then start again when all the definitions are ready. | Review the backlog with the product owner and prioritize the tasks that are least likely to be affected by a change in legislation. | Put the project on hold until all definitions are ready in order to avoid rework. |  | C | When engineers produce frequent design changes due to new legislation and there is risk of cost from resource waiting or rework, the project manager should review the backlog with the product owner and prioritize tasks least likely to be affected by legislation changes. Strategic prioritization minimizes disruption. Capturing feedback at daily meetings (A) communicates but does not reduce cost. Canceling and restarting (B) is extreme. Putting the project on hold (D) delays value delivery. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Resources | Planning | Focus on Value | Plan Resource Management | Traditional PM | 건설 서비스 계약자가 애자일 원칙으로 프로젝트 작업을 관리한다. 엔지니어가 새 법률로 빈번한 설계 변경을 만든다. 재작업 리스크가 있다. PM은 무엇을 해야 하는가? | 엔지니어의 피드백을 데일리 미팅에서 수집하고 제품 책임자에게 전달한다 | 프로젝트를 취소하고 자원을 해제한 후 모든 정의가 준비되면 다시 시작한다 | 제품 책임자와 백로그를 검토하고 변경에 영향을 받을 가능성이 가장 적은 작업의 우선순위를 정한다 | 재작업을 피하기 위해 모든 정의가 준비될 때까지 프로젝트를 보류한다 |  | C | 새 법률로 빈번한 설계 변경과 재작업 리스크가 있을 때, PM은 제품 책임자와 백로그를 검토하고 변경에 영향을 받을 가능성이 가장 적은 작업의 우선순위를 정해야 한다. 우선순위 조정이 재작업을 최소화한다. 피드백 전달(A)은 부분적이다. 취소(B)와 보류(D)는 과도한 조치이다.
1486 | A project manager is evaluating a project and realizes that its earned value (EV) shows the cost spent is higher than the value delivered. The project manager then discovers that the team has been adding small features that are not part of the requirements. What should the project manager do? | Encourage the team to continue, as this will eventually help the customer. | Ask the product owner to add the additional features to the requirements. | Request additional budget because additional features are being added. | Ask the team to focus on and deliver only the agreed-upon features. |  | D | When the team has been adding small features not in the requirements, causing earned value to show cost exceeding delivered value, the project manager should ask the team to focus on and deliver only the agreed-upon features. Refocusing prevents scope creep and restores value delivery alignment. Encouraging continuation (A) perpetuates the problem. Asking the product owner to add features to requirements (B) formalizes unauthorized work. Requesting additional budget (C) funds unplanned scope. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | PM이 프로젝트를 평가하니 획득가치(EV)가 비용이 납품된 가치보다 높다고 나타낸다. 팀이 요구사항에 없는 작은 기능들을 추가해왔다. PM은 무엇을 해야 하는가? | 이것이 결국 고객에게 도움이 될 것이므로 팀에게 계속하도록 격려한다 | 제품 책임자에게 추가 기능을 요구사항에 추가하도록 요청한다 | 추가 기능이 추가되고 있으므로 추가 예산을 요청한다 | 팀에게 합의된 기능에만 집중하여 납품하도록 요청한다 |  | D | 팀이 요구사항에 없는 기능을 추가하여 비용이 납품 가치를 초과할 때, PM은 팀에게 합의된 기능에만 집중하여 납품하도록 요청해야 한다. 범위 통제가 비용 초과를 방지한다. 계속 격려(A)는 금도금(gold plating)을 허용한다. 요구사항 추가(B)는 사후 정당화이다. 추가 예산(C)은 승인되지 않은 범위에 대한 것이다.
1487 | A quality issue that requires a change to the quality standard is encountered in a project. Currently, there is no budget available for the required changes. What should the project manager do? | Document the issue in the scope management plan. | Check the quality management plan | Conduct a team brainstorming session to resolve the issue | Check the change management plan |  | D | When a quality issue requires a change to quality standards but no budget is available, the project manager should check the change management plan. The change management plan provides guidance on handling changes and their impact. Documenting in the scope management plan (A) misplaces the issue. Checking the quality management plan (B) reviews standards but not the change process. Conducting a brainstorming session (C) may follow but is not the first step. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트에서 품질 표준 변경이 필요한 품질 이슈가 발생했다. 현재 예산이 없다. PM은 무엇을 해야 하는가? | 범위 관리 계획에 이슈를 문서화한다 | 품질 관리 계획을 확인한다 | 팀 브레인스토밍 세션을 실시하여 이슈를 해결한다 | 변경 관리 계획을 확인한다 |  | D | 품질 표준 변경이 필요하지만 예산이 없을 때, PM은 변경 관리 계획을 확인해야 한다. 변경 관리 계획이 예산이 없는 상황에서의 변경 처리 지침을 제공한다. 범위 관리 계획(A)은 품질 관련이 아니다. 품질 관리 계획(B)은 기존 표준을 설명하지 변경 프로세스가 아니다. 브레인스토밍(C)은 해결 방법이지만 프로세스 확인이 우선이다.
1488 | A project is on its fifth iteration out of six. One member of the team has left the company unexpectedly. What should the project manager do next? | Register an issue and escalate it to the project sponsor. | Take on some of the necessary work to minimize the impact. | Detail the reason for the project delay in the status report. | Invite the stakeholders to discuss a mitigation plan. |  | D | When a team member leaves unexpectedly during the fifth of six iterations, the project manager should invite stakeholders to discuss a mitigation plan. This proactive engagement allows the PM to analyze the impact of the departure, identify alternative strategies, and update the project management plan with stakeholder input and support. Registering an issue and escalating to the sponsor (A) is reactive and does not immediately address how to redistribute the work. Taking on the work personally (B) is unsustainable and may compromise the PM's oversight responsibilities. Detailing the delay in a status report (C) is informational but does not actively resolve the resource gap. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 6번째 이터레이션 중 5번째에 있다. 팀원이 예상치 않게 회사를 떠났다. PM은 무엇을 해야 하는가? | 이슈를 등록하고 프로젝트 스폰서에게 에스컬레이션한다 | 영향을 최소화하기 위해 일부 필요한 작업을 직접 수행한다 | 상태 보고서에 프로젝트 지연 사유를 상세히 기술한다 | 이해관계자를 초대하여 완화 계획을 논의한다 |  | D | 5번째 이터레이션에서 팀원이 예상치 않게 떠날 때, PM은 이해관계자를 초대하여 완화 계획을 논의해야 한다. 사전적 이해관계자 참여가 영향을 분석하고 효과적 해결을 가능하게 한다. 에스컬레이션(A)은 논의 없는 행동이다. 직접 수행(B)은 PM 역할이 아니다. 지연 보고(C)는 수동적이다.
1489 | A customer has provided excellent feedback on the project. However, a key project resource is leaving the company. Which measure should mitigate the impact of this key resource's departure? | Update the risk register and inform the customer. | Develop a contingency budget to replace the key resource. | Establish a proactive knowledge-sharing plan. | Offer a new contract to the resource who is leaving. |  | C | When a key resource is leaving the company during a successful project, the best mitigation is to establish a proactive knowledge-sharing plan. This structured approach captures the departing resource's knowledge and expertise through documentation, training sessions, and mentoring, ensuring critical project information is retained within the team. Updating the risk register and informing the customer (A) documents the risk but does not mitigate it. Developing a contingency budget for replacement (B) addresses cost but not knowledge loss. Offering a new contract (D) may not succeed and does not prepare the team. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 고객이 프로젝트에 훌륭한 피드백을 제공했다. 그러나 핵심 프로젝트 자원이 회사를 떠난다. 가장 좋은 완화 방법은? | 리스크 등록부를 업데이트하고 고객에게 알린다 | 핵심 자원을 교체하기 위한 비상 예산을 개발한다 | 사전적 지식 공유 계획을 수립한다 | 떠나는 자원에게 새 계약을 제안한다 |  | C | 핵심 자원이 떠날 때 가장 좋은 완화는 사전적 지식 공유 계획을 수립하는 것이다. 구조화된 접근이 떠나는 자원의 지식과 전문성을 포착한다. 리스크 등록부 업데이트(A)는 문서화이지 완화가 아니다. 비상 예산(B)은 지식 손실을 다루지 않는다. 새 계약(D)은 결정이 이미 이루어진 후 비현실적이다.
1490 | When defining the ground rules for a project team, the project manager observed that only two team members contributed to the discussion. As a result, the team ground rules favor these two team members. What should the project manager have done to avoid this situation? | Extend the meeting to allow everyone to speak | Come to the meeting with suggested ground rules | Set expectations for contributions ahead of the meeting | Ask all team members to send new ideas prior to the meeting |  | C | When only two team members contributed to ground rules resulting in biased rules, the project manager should have set expectations for contributions ahead of the meeting. Pre-meeting expectations encourage all team members to prepare and ensure inclusive participation. Extending the meeting (A) does not guarantee more participation. Coming with suggested rules (B) imposes the PM's preferences. Asking for written ideas beforehand (D) collects input but does not set the expectation for active participation. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 기본 규칙 정의 회의에서 두 팀원만 기여하여 편향된 규칙이 되었다. PM이 이전에 무엇을 했어야 하는가? | 모든 사람이 발언할 수 있도록 회의를 연장한다 | 제안된 기본 규칙을 가지고 회의에 온다 | 회의 전에 기여에 대한 기대를 설정한다 | 모든 팀원에게 회의 전 새 아이디어를 보내도록 요청한다 |  | C | 소수만 기여하여 편향된 기본 규칙이 될 때, PM은 회의 전에 기여에 대한 기대를 설정했어야 한다. 사전 기대 설정이 포괄적 참여를 장려한다. 회의 연장(A)은 참여를 보장하지 않는다. 제안된 규칙(B)은 PM 편향이다. 사전 아이디어(D)는 유용하지만 기대 설정이 더 근본적이다.
1491 | Due to contractual issues, a key team member cannot travel to the project location for a design review meeting. What should the project manager do? | Consider setting up a virtual meeting with the team for the design review. | Solve the contractual issues before continuing with the design review meeting. | Inform the stakeholders and demand an immediate solution from the project sponsor. | Ask the project sponsor if another team member can participate instead. |  | A | Virtual meetings are a standard practice for maintaining productivity when physical presence is not possible—especially in global and hybrid working environments. Using collaborative tools to continue the meeting virtually (A) is pragmatic and proactive, ensuring continuity without delay. It also supports agile principles of adaptability and responsiveness. Deferring to the sponsor (B) shifts the decision unnecessarily. Waiting for physical resolution (C) may cause delays. Escalation (D) is premature and confrontational. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Hybrid/Tailoring | 계약 문제로 핵심 팀원이 설계 검토 회의를 위해 프로젝트 현장에 출장할 수 없다. PM은 무엇을 해야 하는가? | 팀과 설계 검토를 위한 가상 회의를 설정하는 것을 고려한다 | 설계 검토 회의를 계속하기 전에 계약 문제를 해결한다 | 이해관계자에게 알리고 프로젝트 스폰서에게 즉각적 해결을 요구한다 | 프로젝트 스폰서에게 다른 팀원이 대신 참여할 수 있는지 묻는다 |  | A | 핵심 팀원이 출장할 수 없을 때, PM은 가상 회의를 설정하는 것을 고려해야 한다. 가상 회의가 물리적 출석이 불가능할 때 생산성을 유지한다. 계약 해결 대기(B)는 지연을 초래한다. 즉각 해결 요구(C)는 과도하다. 대체 참여(D)는 핵심 전문가를 빠뜨린다.
1492 | A project manager has been assigned to handle a company's newest product. The product is in the conceptual stages and no one is sure about the success or marketability of the product. Management wants to deliver the product in 3 months. What should the project manager do next? | Explore the minimum requirements of the product and their feasibility. | Outsource the management of the product to an external team. | Explain the resource constraints of the project to management. | Conduct a detailed risk analysis to highlight the risks in the project. |  | A | When a product is in conceptual stages with uncertain success and marketability and a 3-month delivery target, the project manager should explore the minimum requirements and their feasibility. Understanding the MVP scope enables realistic planning under uncertainty. Outsourcing management (B) does not address the uncertainty. Explaining resource constraints (C) does not advance the project. Conducting detailed risk analysis (D) follows requirement exploration. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | PM이 회사의 최신 제품에 배정되었다. 제품이 개념 단계이고 성공과 시장성이 불확실하다. 3개월 납기이다. PM은 무엇을 해야 하는가? | 제품의 최소 요구사항과 실행 가능성을 탐색한다 | 제품 관리를 외부 팀에 아웃소싱한다 | 프로젝트의 자원 제약을 경영진에게 설명한다 | 프로젝트의 리스크를 강조하기 위한 상세 리스크 분석을 실시한다 |  | A | 개념 단계의 불확실한 제품에 3개월 납기가 있을 때, PM은 최소 요구사항과 실행 가능성을 탐색해야 한다. MVP 접근이 불확실성과 시간 제약 하에서 가장 효과적이다. 아웃소싱(B)은 불확실한 제품에 리스크가 크다. 제약 설명(C)은 행동이 아니다. 상세 리스크 분석(D)은 시간이 오래 걸린다.
1493 | A project is on its fourth iteration out of six. During iteration planning, a team member informs the project manager that their computer is not working. What should the project manager do next? | Facilitate a priority resolution of the issue with the IT department. | Ask the other team members to step in and do the work. | Update the issue log and escalate the problem to the product owner. | Suggest that the team member contact the IT department. |  | A | When a team member's computer stops working during iteration four, the project manager should facilitate a priority resolution of the issue with the IT department. Proactive support ensures the team member can resume contributing quickly without project delay. Asking other team members to cover (B) redistributes work without fixing the problem. Updating the issue log and escalating to the product owner (C) over-escalates a technical support issue. Suggesting the team member contact IT independently (D) does not demonstrate servant leadership. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트가 4번째 이터레이션에 있다. 이터레이션 계획 중 팀원의 컴퓨터가 작동을 멈췄다. PM은 무엇을 해야 하는가? | IT 부서와 이슈의 우선 해결을 촉진한다 | 다른 팀원에게 업무를 대신하도록 요청한다 | 이슈 로그를 업데이트하고 제품 책임자에게 문제를 에스컬레이션한다 | 팀원에게 IT 부서에 연락하도록 제안한다 |  | A | 팀원의 컴퓨터가 작동을 멈추면, PM은 IT 부서와 이슈의 우선 해결을 촉진해야 한다. 사전적 지원이 팀원의 업무 복귀를 가속한다. 대신 업무(B)는 근본 해결이 아니다. 에스컬레이션(C)은 불필요하다. 직접 연락 제안(D)은 PM의 장애물 제거 역할을 하지 않는다.
1494 | An agile team was hired to work on a public service project. The team received a list of vague ideas about the business and now needs to understand, develop, and prioritize a list of functionalities. Who will be responsible for this task? | Product owner | Agile team | Project owner | Agile leader |  | A | In agile methodology, the product owner is responsible for managing the product roadmap, defining the product vision, prioritizing the backlog, and managing stakeholders. The product owner has authority to make key decisions about what the team works on and ensures the team focuses on delivering the highest-value functionalities. The agile team (B) executes the work but does not own prioritization decisions. The project owner (C) is not a standard agile role. The agile leader (D) facilitates processes but does not own the product backlog. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 애자일 팀이 공공 서비스 프로젝트에 고용되었다. 비즈니스 요구에 대한 모호한 아이디어 목록을 받았다. 누가 요구사항 명확화를 담당하는가? | 제품 책임자 | 애자일 팀 | 프로젝트 소유자 | 애자일 리더 |  | A | 애자일 방법론에서 제품 책임자가 제품 로드맵 관리, 제품 비전 정의, 백로그 우선순위화, 이해관계자 관리를 담당한다. 제품 책임자가 요구사항을 명확히 하고 우선순위를 정할 권한이 있다.
1495 | Two companies recently merged. The team charter for a new initiative combines the best practices of both companies. One of the team members consistently ignores one of the rules. What should the project manager do to address this concern? | Send a reminder to the team member about the rule being violated. | Schedule a dedicated session to review the team charter. | Ask another team member to meet with this team member for a discussion. | Set up a meeting with the team member to review the team charter. |  | D | When a team member consistently ignores a merged team charter rule, the project manager should set up a meeting with the team member to review the team charter. Direct discussion clarifies expectations, explores the team member's perspective, and promotes open communication to resolve the issue. Sending a reminder (A) is impersonal and may not address underlying concerns. Scheduling a full team session (B) may not be necessary for an individual issue. Having another team member discuss it (C) delegates the PM's responsibility. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 최근 두 회사가 합병했다. 새 이니셔티브의 팀 헌장이 양사의 모범 사례를 결합한다. 한 팀원이 특정 규칙을 지속적으로 무시한다. PM은 무엇을 해야 하는가? | 위반되는 규칙에 대해 팀원에게 알림을 보낸다 | 팀 헌장을 검토하기 위한 전용 세션을 예약한다 | 다른 팀원에게 해당 팀원과 논의하도록 요청한다 | 팀원과 만남을 설정하여 팀 헌장을 검토한다 |  | D | 팀원이 합병된 팀 헌장 규칙을 지속적으로 무시할 때, PM은 해당 팀원과 만남을 설정하여 팀 헌장을 검토해야 한다. 직접 대화가 기대를 명확히 하고 이해를 보장한다. 알림(A)은 비인격적이다. 전용 세션(B)은 전체 팀을 불필요하게 참여시킨다. 다른 팀원 통한 논의(C)는 간접적이다.
1496 | A project manager is leading a project that has been in execution for 1 year. An experienced team member is performing well, but often disagrees with the project manager and refuses to implement their decisions. Part of the team supports the team member's defiance, while the other team members do not. What should the project manager do? | Conduct a performance review and define and document the goals for the team member. | Understand what the team member wants and find possible opportunities to address it. | Remove existing ground rules and create new ground rules that support the project manager. | Clarify decisions and request that the project team follows the project manager ' s decisions. |  | B | When an experienced team member frequently disagrees with the project manager and refuses to implement decisions, the PM should seek to understand what the team member wants and find possible opportunities to address it. This conflict resolution approach identifies root causes by understanding the team member's perspective and works collaboratively toward a solution that aligns with project goals. Conducting a performance review (A) is evaluative rather than collaborative. Removing existing ground rules to create new ones supporting the PM (C) is authoritarian. Clarifying decisions and demanding compliance (D) escalates the conflict rather than resolving it. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | PM이 1년간 실행된 프로젝트를 이끌고 있다. 경험 있는 팀원이 PM과 자주 의견이 달라 결정 구현을 거부한다. PM은 무엇을 해야 하는가? | 성과 검토를 실시하고 팀원의 목표를 정의하고 문서화한다 | 팀원이 원하는 것을 이해하고 가능한 기회를 찾는다 | 기존 기본 규칙을 제거하고 PM을 지원하는 새 규칙을 만든다 | 결정을 명확히 하고 프로젝트 팀이 PM의 결정을 따르도록 요청한다 |  | B | 경험 있는 팀원이 PM과 의견이 달라 결정 구현을 거부할 때, PM은 팀원이 원하는 것을 이해하고 가능한 기회를 찾아야 한다. 동기와 욕구 이해가 협력적 해결의 기초이다. 성과 검토(A)는 징벌적이다. 새 규칙(C)은 권위주의적이다. 결정 강요(D)는 갈등을 악화시킨다.
1497 | During project completion, a project manager receives a request from the customer for a reduced cost of goods. The customer's request will affect the sales department's budget and forecast. In order to reach a consensus and have a successful project completion, what should the project manager do first? | Identify and satisfy both parties ' underlying wants. | Analyze the bounds of the negotiation for agreement with both parties. | Comply with the customer ' s request to achieve the project mandate. | Initiate a change request to accommodate the revised cost of goods |  | B | When a customer requests reduced cost of goods during project completion, affecting the sales department's budget, the project manager should first analyze the bounds of the negotiation for agreement with both parties. Identifying BATNA, WATNA, and ZOPA provides a framework for balanced negotiation that serves both parties' interests. Identifying underlying wants (A) is part of negotiation but not the first analytical step. Complying with the customer's request (C) ignores the internal impact. Initiating a change request (D) is procedural without first understanding the negotiation space. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 완료 중 고객이 물품 비용 절감을 요청한다. 영업부 예산에 영향을 미친다. PM은 무엇을 먼저 해야 하는가? | 양 당사자의 근본적 요구를 파악하고 만족시킨다 | 양 당사자와 협상의 범위를 분석한다 | 프로젝트 임무 달성을 위해 고객 요청에 순응한다 | 수정된 물품 비용을 수용하기 위한 변경 요청을 시작한다 |  | B | 고객이 비용 절감을 요청하고 영업부 예산에 영향을 미칠 때, PM은 먼저 양 당사자와 협상의 범위를 분석해야 한다. 협상 범위 분석이 합리적 합의의 기초를 설정한다. 요구 파악(A)은 범위 분석 후에 한다. 순응(C)은 영업부를 무시한다. 변경 요청(D)은 분석 전에 성급하다.
1498 | A project to construct an electricity generation plant is on site near a nature reserve. An environmental activist group is questioning the need for the project. The customer has informed the project manager to disregard the group as they are not in support of the project. What should the project manager do next? | Obey the directive from the customer since they are funding the project and are the most important stakeholder. | Add the activist group to the list of stakeholders and analyze the impact they may have on project delivery. | Request the project team disregard all communication from the activist group and continue with their project work. | Ask the customer to contact the activist group and let them know the project status and completion date. |  | B | When an environmental activist group questions a project near a nature reserve and the customer says to disregard them, the project manager should add the activist group to the stakeholder list and analyze their potential impact on project delivery. All affected parties should be considered stakeholders. Obeying the customer's directive to ignore (A) is irresponsible. Requesting the team disregard them (C) avoids legitimate concerns. Asking the customer to contact them (D) delegates the PM's responsibility. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 발전소 건설 프로젝트가 자연보호구역 근처에 있다. 환경 활동가 단체가 프로젝트에 의문을 제기한다. 고객이 무시하라고 한다. PM은 무엇을 해야 하는가? | 고객이 프로젝트 자금을 지원하고 가장 중요한 이해관계자이므로 지시에 따른다 | 활동가 단체를 이해관계자 목록에 추가하고 프로젝트 납품에 미칠 영향을 분석한다 | 프로젝트 팀에 활동가 단체의 모든 커뮤니케이션을 무시하고 작업을 계속하도록 요청한다 | 고객에게 활동가 단체에 연락하여 프로젝트 상태와 완료일을 알리도록 요청한다 |  | B | 환경 활동가 단체가 프로젝트에 의문을 제기할 때, PM은 활동가 단체를 이해관계자 목록에 추가하고 영향을 분석해야 한다. 이해관계자 식별과 분석이 리스크를 관리한다. 고객 지시 따르기(A)는 다른 이해관계자를 무시한다. 무시(C)는 리스크를 증가시킨다. 고객 통한 연락(D)은 간접적이며 부적절하다.
1499 | A project manager is managing two agile teams and reviewing their metrics to find out which team is performing better. Which approach should be taken? | The issue should be addressed as part of a retrospective in the next iteration. | The velocity of both teams should be compared at the end of every iteration. | The team with the higher velocity is performing better and should be rewarded. | The velocity should not be compared as teams can size items differently. |  | D | Velocity should not be compared between agile teams because teams size items differently. Velocity measures the amount of work a team completes in a given period—not the quality or value of that work. Cross-team velocity comparisons lead to inaccurate conclusions and unhealthy competition. Instead, the PM should use each team's velocity for their own planning and forecasting, and focus on outcome-based metrics that reflect project benefits and value delivery. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | PM이 두 애자일 팀을 관리하며 메트릭을 검토하여 어느 팀이 더 나은지 파악하려 한다. 팀 간 속도(velocity) 비교에 대한 올바른 설명은? | 이슈는 다음 이터레이션의 회고에서 다루어야 한다 | 양 팀의 속도는 매 이터레이션 종료 시 비교되어야 한다 | 더 높은 속도를 가진 팀이 더 잘 수행하고 있으며 보상받아야 한다 | 팀이 항목 크기를 다르게 산정할 수 있으므로 속도를 비교해서는 안 된다 |  | D | 팀 간 속도를 비교해서는 안 된다. 팀마다 항목 크기를 다르게 산정하기 때문이다. 속도는 팀이 일정 기간에 완료하는 작업량을 측정하지 그 품질이나 가치를 측정하지 않는다. 팀 간 비교는 부정확하고 오해를 일으킨다.
1500 | A project manager works at an organization that is transitioning to agile. The development team has recommended using a burndown chart to provide visibility on project progress to all stakeholders. What should the project manager do to ensure effective communication throughout the project? | Develop a communications management plan for each category in the stakeholder register. | Include the burndown chart in a monthly report that is distributed to all stakeholders. | Advise the project management office (PMO) to use the burndown chart as the single communication channel. | Postpone the recommendation since the organization does not currently have a defined agile methodology. |  | B | When the development team recommends using a burndown chart for visibility, the project manager should include the burndown chart in a monthly report distributed to all stakeholders. Integration into regular communications ensures broad visibility. Developing separate plans per stakeholder category (A) is overly complex. Advising the PMO to use it as the single channel (C) is too narrow. Postponing the recommendation (D) delays a useful tool. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Hybrid/Tailoring | PM이 애자일 전환 중인 조직에서 일한다. 개발팀이 번다운 차트 사용을 권장했다. PM은 무엇을 해야 하는가? | 이해관계자 등록부의 각 범주에 대한 커뮤니케이션 관리 계획을 개발한다 | 번다운 차트를 모든 이해관계자에게 배포되는 월간 보고서에 포함한다 | PMO에 번다운 차트를 유일한 커뮤니케이션 채널로 사용하도록 조언한다 | 조직이 현재 정의된 애자일 방법론이 없으므로 권장을 연기한다 |  | B | 개발팀이 번다운 차트 사용을 권장하면, PM은 번다운 차트를 모든 이해관계자에게 배포되는 월간 보고서에 포함해야 한다. 기존 보고에 통합하면 가시성을 높인다. 범주별 계획(A)은 과도하다. 유일한 채널(C)은 제한적이다. 연기(D)는 유용한 도구를 무시한다.
1501 | A project manager is leading a hybrid project. The self-organizing teams are continually late in delivering their demos, resulting in low morale. The steering committee is familiar with the reporting and planning associated with a predictive approach and is concerned about the project because it is unclear if the expected value will be delivered. What should the project manager do? | Suggest to the teams to limit the scope of work per iteration so they will start to delivermore reliably. | Update the project schedule with a buffer to reflect the expected delays being incurredby the team. | Request to coach the team to ensure motivated project team members are on board. | Emphasize to the teams the importance of reaching the agreed deadlines and value. |  | A | When self-organizing teams are continually late delivering demos and the steering committee is concerned about value delivery, the project manager should suggest teams limit the scope of work per iteration to start delivering more reliably. Smaller, achievable increments restore confidence and demonstrate value. Updating the schedule with a buffer (B) masks the problem. Requesting coaching (C) does not provide a specific solution. Emphasizing deadline importance (D) increases pressure without enabling improvement. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Align Stakeholder Expectations | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | PM이 하이브리드 프로젝트를 이끈다. 자체 조직화 팀이 지속적으로 데모 납품이 늦다. 운영위원회가 가치 전달에 우려한다. PM은 무엇을 해야 하는가? | 팀에게 이터레이션당 작업 범위를 줄여 더 안정적으로 납품하기 시작하도록 제안한다 | 팀이 초래하는 예상 지연을 반영하여 프로젝트 일정에 버퍼를 업데이트한다 | 동기 부여된 팀원이 참여하도록 팀을 코칭하도록 요청한다 | 합의된 마감과 가치 달성의 중요성을 팀에 강조한다 |  | A | 자체 조직화 팀이 지속적으로 늦을 때, PM은 이터레이션당 작업 범위를 줄여 더 안정적으로 납품하도록 제안해야 한다. 범위 조정이 현실적 납품을 가능하게 한다. 버퍼(B)는 지연을 수용하지 해결하지 않는다. 코칭(C)은 구조적 문제를 다루지 않는다. 강조(D)는 실행 가능한 해결이 아니다.
1502 | A project team is working on a relative-weighting approach to assess product features. The product features will be prioritized to highlight the benefits and bring value to the customer. What should the project manager ask the team to do? | Perform collaborative work that is coordinated by the project manager. | Engage the project sponsor. | Use a market-based strategy. | Rely on the expert judgment of the product owner. |  | A | When using a relative-weighting approach to prioritize product features, the project manager should ask the team to perform collaborative work coordinated by the PM. Collaborative assessment ensures balanced input. Engaging the sponsor (B) may introduce bias. Using a market-based strategy (C) is external-focused. Relying on PO expert judgment alone (D) limits perspective. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 프로젝트 팀이 상대적 가중치 접근법을 사용하여 제품 기능을 평가하고 있다. 누가 분석을 수행해야 하는가? | PM이 조율하는 협력적 작업을 수행한다 | 프로젝트 스폰서를 참여시킨다 | 시장 기반 전략을 사용한다 | 제품 책임자의 전문가 판단에 의존한다 |  | A | 상대적 가중치 접근법으로 제품 기능을 평가할 때, PM이 조율하는 협력적 작업을 수행해야 한다. 협력적 평가가 다양한 관점을 반영하고 편향을 줄인다. 스폰서 참여(B)는 상세 수준이 맞지 않는다. 시장 기반(C)은 내부 평가와 다르다. 제품 책임자만(D)은 단일 관점이다.
1503 | The portfolio management office wants to cut costs by suspending some ongoing projects that do not directly support the organizational strategy. The project manager has invested too many resources into one of the projects to be suspended, but the portfolio management office has not backed down on their plan. What should the project manager do to continue the project? | Demonstrate the project alignment to the organizational strategy. | Update the project charter to make it align with organizational strategy. | Meet with the project team and revise the project goals. | Escalate the issue with the project sponsor to request support. |  | A | When the portfolio management office wants to suspend projects not aligned with strategy, the project manager should demonstrate the project's alignment to organizational strategy. Evidence-based justification addresses the PMO's concern directly. Meeting the team to revise goals (B) changes the project. Updating the charter for alignment (C) may be unethical if the project is not truly aligned. Escalating to the sponsor (D) creates conflict without resolution. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 포트폴리오 관리 사무소가 조직 전략과 직접 연결되지 않는 진행 중 프로젝트를 중단하여 비용을 줄이려 한다. PM은 무엇을 해야 하는가? | 조직 전략과의 프로젝트 정렬을 입증한다 | 조직 전략에 맞추기 위해 프로젝트 헌장을 업데이트한다 | 프로젝트 팀과 만나 프로젝트 목표를 수정한다 | 프로젝트 스폰서에게 이슈를 에스컬레이션하여 지원을 요청한다 |  | A | 포트폴리오 사무소가 전략 비정렬 프로젝트를 중단하려 할 때, PM은 조직 전략과의 프로젝트 정렬을 입증해야 한다. 증거 기반 정당화가 프로젝트를 보호한다. 헌장 업데이트(B)는 정렬을 조작하는 것이다. 목표 수정(C)은 프로젝트 범위를 변경한다. 에스컬레이션(D)은 입증 시도 후에 한다.
1504 | The city has decided to build a new tram station. The project will include various approaches. The construction and infrastructure work will be accomplished using a predictive life cycle while software will be developed using an iterative life cycle. Some neighbors are resisting the project, have been asking the mayor to stop the project, and are threatening legal action. What two actions should the project manager take? (Choose two) | Discuss with the construction team alternatives on moving the new train station to another location. | Conduct regular meetings with the neighbors to get their buy-in for the project | Publish information on the city's website about the benefits that the new tram station will bring | Have a meeting with the mayor and explain the importance of the new train station to the city. | Register this situation as a risk and develop a mitigation plan | C, D | When neighbors resist a tram station project and threaten legal action, the project manager should take two actions: publish information on the city's website about the benefits the new station will bring, and register the situation as a risk and develop a mitigation plan. Public communication addresses concerns while risk documentation enables proactive management. Discussing relocation alternatives (A) changes scope without authorization. Conducting regular neighbor meetings (B) is good but does not address the legal risk. Meeting the mayor (D) is advocacy, not risk management. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 시가 새 트램 역을 건설하기로 결정했다. 이웃들이 프로젝트에 반대하며 법적 조치를 위협한다. PM은 무엇을 해야 하는가? (2개 선택) | 건설팀과 트램 역을 다른 위치로 이전하는 대안을 논의한다 | 이웃들과 정기적으로 만나 프로젝트에 대한 동의를 얻는다 | 시 웹사이트에 새 트램 역이 가져올 혜택에 대한 정보를 게시한다 | 시장과 만나 시에 대한 새 트램 역의 중요성을 설명한다 | 이 상황을 리스크로 등록하고 완화 계획을 개발한다 | C, D | 이웃들이 트램 역 프로젝트에 반대할 때, PM은 두 가지 조치를 취해야 한다: 시 웹사이트에 혜택 정보를 게시하여(C) 공공 인식을 높이고, 시장과 만나 트램 역의 중요성을 설명하여(D) 정치적 지원을 확보한다. 위치 이전(A)은 범위 변경이다. 이웃 만남(B)은 도움이 되지만 공식 채널이 더 효과적이다. 리스크 등록(E)은 내부적이며 대응이 아니다.
1505 | A developer who has almost completed a required product feature for a prototype leaves the company in the middle of an iteration. What should the project manager do? | Engage with stakeholders directly to review the iteration process. | Go to management and ask to hire a new external developer. | Review the backlog to reschedule the deliverable for a later iteration. | Determine whether other cross-functional team members are able to take over thework. |  | D | When a developer leaves mid-iteration with a nearly completed feature, the project manager should determine whether other cross-functional team members can take over the work. Leveraging existing team capability minimizes disruption. Engaging stakeholders to review the process (A) does not address the immediate gap. Hiring externally (B) is costly and slow. Rescheduling to a later iteration (C) delays without exploring alternatives. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Hybrid/Tailoring | 개발자가 프로토타입의 필수 기능을 거의 완료한 상태에서 이터레이션 중간에 회사를 떠났다. PM은 무엇을 해야 하는가? | 이해관계자와 직접 참여하여 이터레이션 프로세스를 검토한다 | 경영진에게 가서 새 외부 개발자 채용을 요청한다 | 백로그를 검토하여 인도물을 이후 이터레이션으로 재일정한다 | 다른 교차 기능 팀원이 업무를 인수할 수 있는지 파악한다 |  | D | 개발자가 거의 완료된 기능을 남기고 떠날 때, PM은 다른 교차 기능 팀원이 업무를 인수할 수 있는지 파악해야 한다. 기존 팀 역량 활용이 가장 빠른 해결이다. 이해관계자 참여(A)는 프로세스 검토이지 즉각 해결이 아니다. 외부 채용(B)은 시간이 오래 걸린다. 재일정(C)은 거의 완료된 기능에 불필요한 지연이다.
1506 | A vendor for a project has reported the potential for a delivery delay due to a technical issue with the sub-supplier. To stay on schedule, the vendor proposed replacing the sub-supplier's component with a similar part that is different from the one that is stipulated in the project specifications. What should the project manager do next? | Insist on using the component per the project specifications and air freight the equipment to mitigate the delay | Consult with a subject matter expert (SME) to see if the proposed change isacceptable | Accept the proposed replacement in order to keep procurement activities on track | Instruct the vendor to use the part that is compliant with the project specifications and update the schedule |  | B | When a vendor proposes replacing a specified component with a similar but different part to avoid delivery delays, the project manager should consult with a subject matter expert (SME) to assess if the proposed change is acceptable. Expert evaluation ensures quality and specification compliance. Insisting on the original component and air-freighting (A) may be costly and unnecessary. Accepting the replacement without evaluation (C) risks quality. Instructing the vendor to use the compliant part and updating the schedule (D) does not evaluate the alternative. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 벤더가 하위 공급업체의 기술 문제로 인해 납품 지연 가능성을 보고했다. 사양과 유사하지만 다른 부품으로 교체를 제안한다. PM은 무엇을 해야 하는가? | 프로젝트 사양에 따른 부품 사용을 고집하고 항공 화물로 장비를 운송하여 지연을 완화한다 | 주제 전문가(SME)와 상의하여 제안된 변경이 허용 가능한지 확인한다 | 조달 활동을 순조롭게 유지하기 위해 제안된 교체를 수락한다 | 벤더에게 프로젝트 사양에 부합하는 부품을 사용하도록 지시하고 일정을 업데이트한다 |  | B | 벤더가 사양과 다른 부품으로 교체를 제안할 때, PM은 SME와 상의하여 제안된 변경이 기술적으로 허용 가능한지 평가해야 한다. 전문가 검토가 정보에 기반한 결정을 가능하게 한다. 사양 고집(A)은 비용과 일정에 영향을 준다. 무조건 수락(C)은 품질 리스크가 있다. 벤더 지시(D)는 대안을 무시한다.
1507 | A multinational company is rolling out a new software platform within its subsidiaries. However, the distributed project team struggles to meet regularly. As a result, the project milestones are not being achieved. What should the project manager do first? | Propose to roll out the new software in one subsidiary and then use the lessons learned to improve the project | Inform the project sponsor and request additional team members to crash the project schedule to meet the target | Introduce an award system to promote member participation and establish some competition between the subteams | Evaluate the effectiveness of the virtual teams and support them with the necessary technology and equipment |  | D | When a distributed project team struggles to meet regularly and milestones are missed, the project manager should first evaluate the effectiveness of virtual teams and support them with necessary technology and equipment. Addressing collaboration barriers at the root enables better performance. Proposing a single-subsidiary rollout (A) changes strategy rather than solving collaboration. Informing the sponsor and crashing the schedule (B) is reactive. Introducing an award system (C) motivates but does not solve meeting challenges. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 다국적 기업이 자회사에 새 소프트웨어 플랫폼을 배포 중이다. 분산된 프로젝트 팀이 정기적으로 만나지 못하고 마일스톤을 놓치고 있다. PM은 무엇을 해야 하는가? | 한 자회사에 먼저 소프트웨어를 배포하고 교훈을 사용하여 나머지를 개선한다 | 프로젝트 스폰서에게 알리고 일정을 크래싱하기 위해 추가 팀원을 요청한다 | 팀원 참여를 촉진하고 팀 간 경쟁을 유도하는 보상 시스템을 도입한다 | 가상 팀의 효과성을 평가하고 필요한 기술과 장비로 지원한다 |  | D | 분산된 팀이 정기 회의에 어려움을 겪고 마일스톤을 놓칠 때, PM은 먼저 가상 팀의 효과성을 평가하고 필요한 기술과 장비로 지원해야 한다. 근본 원인(기술/도구 부족)을 해결한다. 단일 자회사 배포(A)는 전략 변경이다. 크래싱(B)은 근본 해결이 아니다. 보상(C)은 기술적 장벽을 해결하지 않는다.
1508 | A key team member informs the project manager that they have been accepted to a master's degree program. The team member explains that the first semester of the master's program will coincide with the last phase of the project. What should the project manager do? | Ask the team member to delegate some of their tasks to another colleague during the last phase of the project. | Suggest the team member postpone their enrollment in the master ' s program until the project is completed. | Ask the team member to inform human resources (HR) about their enrollment in the master ' s program. | Assess the team member ' s commitment to the master ' s program and its impact on project performance. |  | D | When a key team member enrolls in a master's program coinciding with the project's last phase, the project manager should assess the team member's commitment and its impact on project performance. Understanding the situation enables informed planning. Asking to delegate tasks (A) assumes a solution prematurely. Suggesting postponement (B) disregards the team member's personal goals. Asking to inform HR (C) is administrative and does not address the project impact. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 주요 팀원이 석사 프로그램에 합격했다고 알린다. 프로젝트의 마지막 단계와 겹친다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 마지막 단계 동안 일부 작업을 다른 동료에게 위임하도록 요청한다 | 프로젝트 완료까지 석사 프로그램 등록을 연기하도록 제안한다 | 팀원에게 석사 프로그램 등록에 대해 HR에 알리도록 요청한다 | 팀원의 석사 프로그램에 대한 헌신과 프로젝트 성과에 미치는 영향을 평가한다 |  | D | 주요 팀원이 프로젝트 마지막 단계와 겹치는 석사 프로그램에 등록할 때, PM은 먼저 팀원의 헌신과 프로젝트 성과에 미치는 영향을 평가해야 한다. 상황 이해가 적절한 대응의 기초이다. 작업 위임(A)은 평가 후에 한다. 연기 제안(B)은 개인 결정을 침해한다. HR 알림(C)은 관련이 적다.
1509 | A project team is facing challenges understanding how to deliver a project's scope. A senior subject matter expert (SME) from the organization's global office is in town for 1 week. What should the project manager do to benefit from the SME's presence? | Ask the SME to review the scope for alignment with the project charter. | Organize a mentoring session with the team and the SME. | Meet with the SME to discuss the current challenges the team is facing. | Review the project scope statement with the SME. |  | C | When a team struggles to deliver scope and a senior SME is visiting for one week, the project manager should meet with the SME to discuss the current challenges the team is facing. This leverages the SME's expertise for targeted guidance on the team's specific delivery problems. Asking the SME to review scope alignment (A) is narrow. Organizing a mentoring session (B) is beneficial but less targeted. Reviewing the scope statement (D) may be redundant if scope is already defined. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 팀이 범위 납품 방법을 이해하는 데 어려움을 겪고 있다. 선임 SME가 1주일간 방문한다. PM은 무엇을 먼저 해야 하는가? | SME에게 범위가 프로젝트 헌장과 일치하는지 검토하도록 요청한다 | 팀과 SME의 멘토링 세션을 조직한다 | SME와 만나 팀이 직면한 현재 과제를 논의한다 | SME와 프로젝트 범위 기술서를 검토한다 |  | C | 팀이 범위 납품에 어려움을 겪고 선임 SME가 1주일간 방문할 때, PM은 먼저 SME와 만나 팀이 직면한 현재 과제를 논의해야 한다. 제한된 시간을 가장 효과적으로 활용한다. 헌장 검토(A)는 범위 정렬이지 납품 과제가 아니다. 멘토링(B)은 과제 이해 후에 한다. 범위 기술서 검토(D)는 부분적이다.
1510 | A team member has experienced personal conflicts on past projects, making them nervous about working on the current project. The project manager knows this team member could add value to the project. What should the project manager do to get the most value from this team member? | Advise the team member not to share personal information from past projects with the entire team. | Advise the team member to focus on the current project and consider the past conflicts as lessons learned. | Consult with the project sponsor to find out if it is allowed to share personal information with the entire team. | Consult with human resources (HR) and check company policies on what is allowed to advise the team member. |  | B | When a team member is nervous due to personal conflicts on past projects, the project manager should advise them to focus on the current project and consider past conflicts as lessons learned. Encouraging a forward-looking, growth mindset enables productive contribution. Advising not to share personal information (A) is not the PM's role. Consulting the sponsor about sharing information (C) is irrelevant. Consulting HR about policy (D) is unnecessary for performance guidance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀원이 과거 프로젝트에서 개인적 갈등을 경험하여 현재 프로젝트 작업에 불안해한다. PM은 무엇을 해야 하는가? | 팀원에게 과거 프로젝트의 개인 정보를 전체 팀과 공유하지 말라고 조언한다 | 현재 프로젝트에 집중하고 과거 갈등을 교훈으로 여기라고 조언한다 | 프로젝트 스폰서와 상의하여 팀과 개인 정보 공유가 허용되는지 확인한다 | HR과 상의하고 회사 정책을 확인하여 팀원에게 무엇을 조언할 수 있는지 확인한다 |  | B | 과거 갈등으로 불안한 팀원에게 PM은 현재 프로젝트에 집중하고 과거 갈등을 교훈으로 여기라고 조언해야 한다. 긍정적 사고와 성장 관점을 격려한다. 정보 공유 금지(A)는 억압적이다. 스폰서 상의(C)는 과도하다. HR 상의(D)는 즉각적 조치가 아니다.
1511 | A project manager for a digital transformation project has already received the business needs for the project. When gathering requirements, the project manager discovers that not all of the requirements can be delivered with the available resources, but that some of the requirements will be enough to add business value. With the project on a fixed budget, what should the project manager do next? | Identify the technical requirements and request that management hire external resources, | Plan the project based on the available resources and submit a change request upon completion. | Document the problem in the issue log and suggest a change request to decrease the scope. | Gather all stakeholders and provide recommendations on a smaller, more feasible project scope, |  | D | When not all requirements can be delivered within available resources on a fixed budget but some requirements add business value, the project manager should gather all stakeholders and provide recommendations on a smaller, more feasible project scope. This ensures the most critical, value-adding requirements are prioritized with clear communication of what is achievable. Identifying technical requirements and hiring externally (A) exceeds the fixed budget. Documenting in the issue log and suggesting a scope decrease change request (C) is procedural without stakeholder alignment. Planning based on available resources and submitting a change request after completion (B) defers critical decisions. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Scope | Monitoring & Controlling | Focus on Value | Validate Scope | Digital Transformation | 디지털 전환 프로젝트의 PM이 비즈니스 요구를 이미 받았다. 고정 예산으로 모든 요구사항을 납품할 수 없지만 일부는 비즈니스 가치를 추가한다. PM은 무엇을 해야 하는가? | 기술 요구사항을 식별하고 경영진에게 외부 자원 고용을 요청한다 | 가용 자원으로 프로젝트를 계획하고 완료 후 변경 요청을 제출한다 | 이슈 로그에 문제를 문서화하고 범위 축소를 위한 변경 요청을 제안한다 | 모든 이해관계자를 모으고 더 작고 실현 가능한 프로젝트 범위에 대한 권장 사항을 제공한다 |  | D | 고정 예산으로 모든 요구사항 납품이 불가능하지만 일부가 가치를 추가할 때, PM은 모든 이해관계자를 모으고 더 작고 실현 가능한 범위에 대한 권장 사항을 제공해야 한다. 협력적 범위 조정이 가치를 극대화한다. 외부 자원(A)은 예산 제약을 무시한다. 완료 후 변경(B)은 늦다. 범위 축소만(C)은 이해관계자 참여가 없다.
1512 | A company is transitioning from a predictive approach to an agile approach. A project manager is assigned to the first pilot with an inexperienced team. Due to an unexpected event, the whole team is asked to work remotely. During the second sprint, the project manager starts to notice a lack of commitment from the team members. What should the project manager do in this situation as a servant leader? | Request an exception to allow the team to return to work on-site | Force the team to attend the daily standups to gather the project status | Coach team members to increase their engagement and collaboration | Allow the team to address the problem as a self-organized team |  | C | When an inexperienced agile team working remotely shows lack of commitment during the second sprint, the project manager should coach team members to increase engagement and collaboration. Coaching builds agile mindset and team dynamics. Requesting on-site return (A) ignores travel restrictions. Forcing standup attendance (B) is authoritarian. Allowing self-organization without guidance (D) is premature for an inexperienced team. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 회사가 예측형에서 애자일로 전환 중이다. 첫 프로젝트에 PM이 배정되었다. 원격 근무팀이 2번째 스프린트에서 헌신 부족을 보인다. PM은 무엇을 해야 하는가? | 팀이 사무실로 복귀하여 일하도록 예외를 요청한다 | 프로젝트 상태를 수집하기 위해 팀에게 데일리 스탠드업 참석을 강제한다 | 팀원을 코칭하여 참여와 협업을 증가시킨다 | 팀이 자체 조직화된 팀으로 문제를 해결하도록 허용한다 |  | C | 미경험 애자일 팀이 원격 근무 시 헌신 부족을 보일 때, PM은 팀원을 코칭하여 참여와 협업을 증가시켜야 한다. 코칭이 역량 구축과 적응을 촉진한다. 사무실 복귀(A)는 원격 근무 원칙에 반한다. 강제 참석(B)은 적대적이다. 자체 조직화(D)는 미경험 팀에게 아직 이르다.
1513 | A project manager for an agile project is concerned that the team has been losing momentum over the last iterations. Which two tools should the project manager use to analyze team performance? (Choose two) | Work breakdown structure (WBS) | Cumulative flow diagram of completed features | Product backlog bumup chart | 0Project schedule | Burndown chart | B, D | When an agile team has been losing momentum over recent iterations, the project manager should use two tools: the cumulative flow diagram and the burndown chart. The cumulative flow diagram identifies bottlenecks and WIP issues, while the burndown chart tracks completion progress. The WBS (A) is a planning tool, not a performance tool. The product backlog burnup chart (C) tracks scope changes, not team momentum. The project schedule (D) is predictive, not agile. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Kanban | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 애자일 프로젝트의 PM이 최근 이터레이션에서 팀의 모멘텀이 감소하고 있다고 우려한다. 어떤 두 가지 도구를 사용해야 하는가? | 작업분류체계(WBS) | 완료된 기능의 누적 흐름도 | 제품 백로그 번업 차트 | 프로젝트 일정 | 번다운 차트 | B, D | 애자일 팀의 모멘텀이 최근 이터레이션에서 감소할 때, PM은 누적 흐름도(B)와 번다운 차트(E)를 사용해야 한다. 누적 흐름도는 작업 흐름의 병목과 WIP 문제를 식별하고, 번다운 차트는 스프린트 내 진행 추이를 보여준다. WBS(A)는 예측형 도구이다. 번업 차트(C)는 장기 추세이다. 프로젝트 일정(D)은 예측형 도구이다.
1514 | A project manager is appointed for the deployment of a new solution. The solution will be integrated into the environment by a third-party vendor. This vendor just announced a delay in delivering a key component, which will impact the project schedule. What should the project manager do? | Perform a detailed analysis of the release content for each component of the solution. | Propose a new design of the solution to replace the external component with an internal one | Ensure that relevant stakeholders and expectations are identified and assess the component delay | Ask for expedited delivery of the component to mitigate the risk of schedule delays |  | C | When a third-party vendor announces a delay in delivering a key component impacting the project schedule, the project manager should ensure that relevant stakeholders and expectations are identified and assess the component delay. Stakeholder communication and impact assessment enable informed response. Performing detailed release analysis (A) may follow. Proposing a new design (B) is premature. Asking for expedited delivery (D) responds without full assessment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Traditional PM | PM이 새 솔루션 배포에 배정되었다. 제3자 벤더가 핵심 구성 요소의 납품 지연을 발표했다. PM은 무엇을 먼저 해야 하는가? | 솔루션의 각 구성 요소에 대한 릴리스 콘텐츠의 상세 분석을 수행한다 | 외부 구성 요소를 내부 것으로 교체하는 새 솔루션 설계를 제안한다 | 관련 이해관계자와 기대를 식별하고 구성 요소 지연을 평가한다 | 일정 지연 리스크를 완화하기 위해 구성 요소의 신속 배송을 요청한다 |  | C | 제3자 벤더가 핵심 구성 요소 납품 지연을 발표할 때, PM은 먼저 관련 이해관계자와 기대를 식별하고 지연을 평가해야 한다. 이해관계자 식별과 영향 평가가 우선이다. 상세 분석(A)은 이해관계자 평가 후에 한다. 솔루션 재설계(B)는 과도한 조치이다. 신속 배송(D)은 비용 증가를 유발한다.
1515 | A new project needs to be submitted for urgent funding approval. The project, which will use a new technology, is vital to the organization. The entire Scrum team has worked together for over 3 years on multiple projects and delivered the previous project under the approved budget. Which estimation technique should the project manager implement in this context? | Definitive estimate | Budget estimate | Story points | Order of magnitude |  | C | For a project involving new technology with an experienced Scrum team that has worked together for over 3 years, the most suitable estimation technique is story points. Story points allow the team to leverage their collective experience and established velocity to estimate effort relative to task complexity, effort, and uncertainty—ideal for projects where technology is new and exact estimates are difficult. A definitive estimate (A) requires well-defined scope and is more suitable for predictive approaches. A budget estimate (B) provides a rough cost range but does not support agile iteration planning. An order of magnitude estimate (D) is too imprecise for a team with a proven track record of collaborative estimation. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 긴급 자금 승인이 필요한 새 프로젝트가 있다. 새 기술을 사용하며 3년 이상 함께 일한 경험 있는 스크럼 팀이 있다. 가장 적합한 추정 기법은? | 확정 추정 | 예산 추정 | 스토리 포인트 | 규모 추정 |  | C | 새 기술을 사용하는 프로젝트에 3년 이상 협업한 경험 있는 스크럼 팀이 있을 때, 스토리 포인트가 가장 적합한 추정 기법이다. 스토리 포인트는 팀이 과거 속도를 기반으로 상대적 복잡성을 추정하게 한다. 확정 추정(A)은 새 기술에 정확하지 않다. 예산 추정(B)은 범위가 넓다. 규모 추정(D)은 정확도가 가장 낮다.
1516 | A project sponsor asks the project team to add an enhancement to the project. How should the project manager address this request? | Refuse the project sponsor ' s request because it is out of scope | Check if the budget can cover the enhancement | Validate the proposed change ' s impact on the project. | Accept the request because it came from the project sponsor |  | C | When the project sponsor asks to add an enhancement, the project manager should validate the proposed change's impact on the project. Impact assessment informs decision-making through change control. Refusing because it is out of scope (A) does not follow change management. Checking budget (B) is one aspect but not comprehensive. Accepting because it came from the sponsor (D) bypasses change control. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 스폰서가 프로젝트에 개선 사항을 추가하도록 팀에 요청한다. PM은 어떻게 대응해야 하는가? | 범위 밖이므로 스폰서의 요청을 거부한다 | 예산이 개선 사항을 감당할 수 있는지 확인한다 | 제안된 변경의 프로젝트에 대한 영향을 검증한다 | 스폰서의 요청이므로 수락한다 |  | C | 스폰서가 개선 사항 추가를 요청할 때, PM은 제안된 변경의 프로젝트에 대한 영향을 검증해야 한다. 영향 평가가 변경 통제를 통한 정보 기반 결정을 가능하게 한다. 거부(A)는 스폰서와의 관계를 훼손한다. 예산 확인(B)은 영향의 일부일 뿐이다. 무조건 수락(D)은 프로세스를 무시한다.
1517 | In an ongoing project, there is an argument between two subject matter experts (SMEs) on what the correct approach to design should be. The project manager suggests that the two SMEs meet and come to a consensus. Which conflict resolution approach did the project manager use? | Synergy | Collaborate | Compromise | Force |  | B | When the project manager suggests two arguing SMEs meet and come to a consensus, the conflict resolution approach used is Collaborate. Collaboration involves working together for a win-win solution. Synergy (A) is not a PMI conflict resolution method. Compromise (C) involves mutual concessions. Force (D) is a win-lose approach. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 진행 중인 프로젝트에서 두 SME가 납품에 대한 올바른 접근법에 대해 논쟁한다. PM이 두 사람이 만나 합의하도록 제안한다. 어떤 갈등 해결 접근법인가? | 시너지 | 협력 | 타협 | 강제 |  | B | PM이 두 논쟁하는 SME에게 만나서 합의하도록 제안하면, 이는 협력(Collaborate) 갈등 해결 접근법이다. 협력은 윈-윈 해결을 위해 함께 작업하는 것이다. 시너지(A)는 갈등 해결 기법이 아니다. 타협(C)은 양측 모두 양보한다. 강제(D)는 한쪽의 의지를 관철한다.
1518 | A project manager is leading a meeting with key stakeholders, the project sponsor, and the product owner to define the features that will be released after the next iteration. The purpose of the meeting is to review the product backlog prioritization, considering that during the past iteration some deliverables were not completed. Which two items should be taken into account first to review and update the product backlog priorities during the meeting? (Choose two) | Complexity and the cost of development | Cost of delaying some features against business value | Industry trends and the technical approach | Reusing components from another product | Length of time each feature has been on the backlog | B, D | When reviewing product backlog priorities after incomplete deliverables, the two items to consider first are: cost of delaying features against business value, and length of time each feature has been on the backlog. Cost of delay measures value lost by postponement, while backlog age indicates relevance risk. Complexity and development cost (A) are secondary considerations. Industry trends and technical approach (C) are contextual factors. Reusing components (D) is an implementation detail. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | PM이 주요 이해관계자, 스폰서, 제품 책임자와 미완료 인도물 후 제품 백로그 우선순위를 검토하는 회의를 이끈다. 먼저 고려할 두 항목은? | 개발의 복잡성과 비용 | 비즈니스 가치 대비 기능 지연 비용 | 산업 동향과 기술적 접근 | 다른 제품의 구성 요소 재사용 | 각 기능이 백로그에 있었던 기간 | B, D | 미완료 인도물 후 백로그 우선순위를 검토할 때, 먼저 고려할 두 항목은 비즈니스 가치 대비 기능 지연 비용(B)과 각 기능이 백로그에 있었던 기간(E)이다. 지연 비용이 비즈니스 영향을 보여주고, 백로그 기간이 정체된 항목을 식별한다. 복잡성/비용(A)은 구현 관점이다. 산업 동향(C)은 외부 요소이다. 구성 요소 재사용(D)은 기술적 고려이다.
1519 | A project lead has asked a project team to update a 200-page project report and send it to the project sponsor. The team mentioned that nobody reads the report and it takes time away from higher priority work. The project lead responded that they have to show all the work that they performed in every iteration. What should the project lead do first? | Ensure the communications methods, channels, frequency, and level of detail for the stakeholders are what is needed. | Reinforce the need to document and provide updated information to make the process transparent. | Summarize the project report so it can be more efficient to read and send it to the project sponsor. | Include a task in every iteration to allocate time for the project team to complete the documentation updates. |  | A | The correct answer is A. Ensure the communications methods, channels, frequency, and level of detail for the stakeholders are what is needed. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 프로젝트 리더가 팀에게 200페이지 프로젝트 보고서를 업데이트하여 스폰서에게 보내라고 요청했다. 팀이 문서가 반복적이고 과도하다고 느낀다. PM은 무엇을 해야 하는가? | 이해관계자에게 필요한 커뮤니케이션 방법, 채널, 빈도, 세부 수준이 적절한지 확인한다 | 프로세스를 투명하게 만들기 위해 문서화 및 업데이트된 정보 제공의 필요성을 강화한다 | 프로젝트 보고서를 요약하여 읽기 효율적으로 만들어 스폰서에게 보낸다 | 각 이터레이션에 팀이 문서 작성을 완료할 시간을 할당하는 작업을 포함한다 |  | A | 정답은 A이다. 이해관계자에게 필요한 커뮤니케이션 방법, 채널, 빈도, 세부 수준이 적절한지 확인한다. 애자일에서는 반복적이고 불필요한 문서를 줄이고 이해관계자에게 필요한 정보만 제공한다. 문서화 강화(B)는 팀 우려를 무시한다. 요약(C)은 근본적 해결이 아니다. 시간 할당(D)은 과도한 문서화를 인정한다.
1520 | A team is working on a project using a hybrid approach, and they are facing a lot of obstacles and blockers from some stakeholders. What should the project manager do to improve project performance? | Add blockers to the issue log and risk management plan | Empower the team members to remove obstacles and blockers | Address and remove obstacles and blockers for the team | Ask stakeholders to communicate with the project manager and not directly with the team |  | C | When a hybrid project team faces obstacles and blockers from stakeholders, the project manager should address and remove obstacles and blockers for the team. Active impediment removal is the PM's responsibility, enabling team progress. Asking stakeholders to only communicate through the PM (D) creates bottlenecks. Empowering the team to remove blockers themselves (B) may be insufficient when blockers are beyond their authority. Adding blockers to the issue log (A) documents but does not resolve them. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Tailored Approach | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Hybrid/Tailoring | 하이브리드 접근법으로 프로젝트를 수행 중인 팀이 일부 이해관계자로부터 많은 장애물과 차단 요소에 직면한다. PM은 무엇을 해야 하는가? | 이슈 로그와 리스크 관리 계획에 차단 요소를 추가한다 | 팀원들이 장애물과 차단 요소를 스스로 제거하도록 권한을 부여한다 | 팀을 위해 장애물과 차단 요소를 다루고 제거한다 | 이해관계자에게 팀과 직접이 아닌 PM과 소통하도록 요청한다 |  | C | 하이브리드 프로젝트에서 이해관계자로부터 장애물이 발생할 때, PM은 팀을 위해 장애물을 다루고 제거해야 한다. 적극적 장애물 제거가 PM의 책임이다. 이슈 로그(A)는 문서화일 뿐 조치가 아니다. 팀 권한 부여(B)는 이해관계자 관리에 적합하지 않다. 직접 소통 차단(D)은 협업을 저해한다.
1521 | A project manager works with a multifunctional team. During a review meeting, two team members disagree on the development approach. What should the project manager do? | Review lessons learned and balance them within the team members ' opinions. | Consult the functional team manager for their guidance on best practices. | Identify the best-fit approach and ask the team members to follow. | Create goodwill among the team members for smooth operations. |  | A | When team members disagree on the development approach, the project manager should review lessons learned from similar projects and balance them with the team members' opinions. This promotes evidence-based decision-making while honoring team collaboration and diverse perspectives. Identifying the best approach and directing the team (C) is overly directive and ignores team input. Consulting the functional manager (B) is indirect and does not leverage the team's collective knowledge. Creating goodwill (D) is vague and does not provide a framework for resolving the specific disagreement. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 다기능 팀과 작업 중이다. 검토 회의에서 두 팀원이 개발 접근법에 대해 의견이 다르다. PM은 무엇을 해야 하는가? | 교훈을 검토하고 팀원 의견과 균형을 맞춘다 | 기능팀 관리자에게 모범 사례에 대한 지침을 상의한다 | 가장 적합한 접근법을 식별하고 팀원에게 따르도록 요청한다 | 원활한 운영을 위해 팀원 간 선의를 조성한다 |  | A | 팀원이 개발 접근법에 대해 의견이 다를 때, PM은 유사 프로젝트의 교훈을 검토하고 팀원 의견과 균형을 맞춰야 한다. 증거 기반 의사결정이 객관적 해결을 촉진한다. 관리자 상의(B)는 팀 자율성을 침해한다. 접근법 지정(C)은 독재적이다. 선의 조성(D)은 기술적 결정을 다루지 않는다.
1522 | The marketing team is transitioning to using hybrid approaches for their projects. The marketing director is not knowledgeable about hybrid methodologies and the project manager needs the director's support as the marketing director is a key stakeholder. What should the project manager do to obtain the support? | Ask the marketing team members to coach the director | Mentor the marketing director on hybrid approaches | Tram the marketing team and keep the director informed | Ask the marketing director to participate in daily meetings |  | B | When the marketing director lacks knowledge of hybrid methodologies and the PM needs their support as a key stakeholder, the project manager should mentor the marketing director on hybrid approaches. Direct mentoring builds understanding, demonstrates benefits, and gains buy-in from a key decision-maker. Asking team members to coach the director (A) creates role confusion. Training the team and informing the director (C) excludes the director from learning. Asking the director to attend daily meetings (D) may overwhelm them without context. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Align Stakeholder Expectations | Resources | Executing | Be an Accountable Leader | Acquire Resources | Hybrid/Tailoring | 마케팅 팀이 하이브리드 접근법으로 전환 중이다. 마케팅 이사가 하이브리드 방법론에 대한 지식이 없다. PM은 무엇을 해야 하는가? | 마케팅 팀원에게 이사를 코칭하도록 요청한다 | 마케팅 이사에게 하이브리드 접근법을 멘토링한다 | 마케팅 팀을 교육하고 이사에게 정보를 제공한다 | 마케팅 이사에게 데일리 미팅에 참여하도록 요청한다 |  | B | 마케팅 이사가 하이브리드 방법론에 대한 지식이 없고 핵심 이해관계자로서 지원이 필요할 때, PM은 이사에게 하이브리드 접근법을 멘토링해야 한다. 직접 멘토링이 가장 효과적인 지식 전달이다. 팀원 코칭(A)은 권한 역학에 부적합하다. 팀 교육만(C)은 이사를 소외시킨다. 데일리 미팅(D)은 지식 부족을 해결하지 않는다.
1523 | After difficult negotiations, a customer committed to pay the cost for changes to the project scope. The team seems unhappy as the project completion time will take longer than previously scheduled. How should the project manager support the outcome of the new agreement? | Find a way to maintain the project schedule. | Impose authority on the project. | Request additional resources from the sponsor and motivate the team. | Motivate the team and deploy the necessary resources. |  | D | When the customer agrees to pay for scope changes but the team is unhappy about the extended timeline, the project manager should motivate the team and deploy the necessary resources. Acknowledgment, communication, and adequate resourcing support morale and execution. Finding a way to maintain the original schedule (A) may compromise quality. Imposing authority (B) creates resentment. Requesting additional resources from the sponsor (C) duplicates the resource deployment and adds unnecessary motivation as a separate action. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Change Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 어려운 협상 끝에 고객이 범위 변경 비용을 지불하기로 했다. 일정이 연장되어 팀이 불만이다. PM은 무엇을 해야 하는가? | 프로젝트 일정을 유지할 방법을 찾는다 | 프로젝트에 권한을 행사한다 | 스폰서에게 추가 자원을 요청하고 팀에 동기를 부여한다 | 팀에 동기를 부여하고 필요한 자원을 배치한다 |  | D | 고객이 범위 변경 비용을 지불하지만 팀이 연장된 일정에 불만일 때, PM은 팀에 동기를 부여하고 필요한 자원을 배치해야 한다. 인정, 지원, 자원 제공이 팀 사기를 회복한다. 일정 유지(A)는 비현실적일 수 있다. 권한 행사(B)는 독재적이다. 스폰서에게 요청(C)은 부분적 대응이다.
1524 | The resource management plan is already done, and the team is located in different countries around the world. Team members are in multiple time zones and they use different languages for communication. The project manager needs to keep the team organized and avoid misunderstandings and miscommunication that may produce a negative impact on the project. What should the project manager do to reduce negative impacts to the project? | Hold a virtual meeting to discuss the political environment. | Conduct a multigenerational management training session | Conduct cultural awareness seminars | Modify the communications management plan to account for regional differences |  | D | When the team is globally distributed across different time zones and languages, the project manager should modify the communications management plan to account for regional differences. The plan should address cultural preferences, technological tools, time zone coordination, and language considerations. Holding a virtual meeting about politics (A) is off-topic. Conducting multigenerational training (B) may not be relevant. Conducting cultural awareness seminars (C) is helpful but does not address the full communication challenge. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Embed Quality | Manage Stakeholder Engagement | Traditional PM | 자원 관리 계획이 완료되었고 팀이 세계 각국에 위치해 있다. 팀원들이 시차와 언어 장벽에 대해 불만한다. PM은 무엇을 해야 하는가? | 정치적 환경을 논의하기 위한 가상 회의를 개최한다 | 다세대 관리 교육 세션을 실시한다 | 문화 인식 세미나를 실시한다 | 지역 차이를 반영하도록 커뮤니케이션 관리 계획을 수정한다 |  | D | 글로벌 분산 팀이 시차와 언어 장벽에 불만할 때, PM은 지역 차이를 반영하도록 커뮤니케이션 관리 계획을 수정해야 한다. 계획이 시간대, 언어, 채널 선호를 고려해야 한다. 정치 논의(A)는 관련이 없다. 세대 교육(B)은 시차/언어 문제를 다루지 않는다. 문화 세미나(C)는 유용하지만 즉각적 커뮤니케이션 문제를 해결하지 않는다.
1525 | A project manager is leading a software development project that will assist in maintenance management for a power plant. The project manager is analyzing project performance data and trying to forecast if the project will have any slippage in the future. What should the project manager do? | Perform trend analysis. | Perform quality control analysis. | Perform schedule analysis. | Perform root cause analysis (RCA). |  | A | When analyzing project performance data to forecast potential future slippage, the project manager should perform trend analysis. Trend analysis uses historical data to predict future performance. Quality control analysis (B) addresses product quality. Schedule analysis (C) examines the current schedule. Root cause analysis (D) investigates past problems, not future forecasts. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | PM이 발전소 유지보수 관리를 위한 소프트웨어 개발 프로젝트를 이끌고 있다. 미래 잠재적 지연을 예측하기 위해 성과 데이터를 분석해야 한다. 무엇을 수행해야 하는가? | 추세 분석을 수행한다 | 품질 관리 분석을 수행한다 | 일정 분석을 수행한다 | 근본 원인 분석(RCA)을 수행한다 |  | A | 미래 잠재적 지연을 예측하기 위해 프로젝트 성과 데이터를 분석할 때, PM은 추세 분석을 수행해야 한다. 추세 분석은 과거 데이터를 사용하여 미래 성과를 예측한다. 품질 관리(B)는 품질에 집중한다. 일정 분석(C)은 현재 일정이지 예측이 아니다. RCA(D)는 문제 발생 후 원인을 식별한다.
1526 | Halfway through a project, the project sponsor is replaced by another peer who was not previously engaged in the project. The new project sponsor has rejected most of the project artifacts, and the team did not get the latest increment approved on the current iteration. Stakeholders are not feeling confident about the project outcome. What should the project manager have done to prevent this situation? | Conducted a product iteration review with the new project sponsor | Held a governance meeting to review the project increment | Performed a stakeholder analysis when the sponsor joined the project | Escalated the issue to ensure the increment would be approved |  | C | When a new project sponsor rejects most artifacts and the team cannot get increment approval, the project manager should have performed a stakeholder analysis when the sponsor joined the project. Understanding the new sponsor's expectations, influence, and engagement level early enables proactive alignment. Conducting a product iteration review (A) is reactive. Holding a governance meeting (B) is procedural without understanding the sponsor. Escalating for increment approval (D) does not address the relationship. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 프로젝트 중간에 스폰서가 프로젝트에 이전에 참여하지 않았던 다른 동료로 교체되었다. 새 스폰서가 대부분의 산출물을 거부한다. PM이 이전에 무엇을 했어야 하는가? | 새 프로젝트 스폰서와 제품 이터레이션 검토를 실시했다 | 프로젝트 증분을 검토하기 위한 거버넌스 회의를 개최했다 | 스폰서가 합류할 때 이해관계자 분석을 수행했다 | 증분 승인을 보장하기 위해 이슈를 에스컬레이션했다 |  | C | 새 스폰서가 대부분의 산출물을 거부하고 증분 승인을 받지 못할 때, PM은 스폰서가 합류할 때 이해관계자 분석을 수행했어야 한다. 새 이해관계자의 기대와 요구를 이해하는 것이 선행되어야 한다. 이터레이션 검토(A)는 이해 없이 진행한 것이다. 거버넌스 회의(B)는 부분적이다. 에스컬레이션(D)은 관계 구축이 우선이다.
1527 | A new team member on a self-organizing team is finding it difficult to deliver due to the new technology being used in the project. What should the project manager do in this situation? | Request the team member to move to another team. | Mentor the team member and provide the necessary training. | Delegate other team members to complete this team member ' s tasks. | Include this team member in an improvement program through a human resources request. |  | B | When a new self-organizing team member struggles with new technology, the project manager should mentor the team member and provide necessary training. This builds capability while respecting the self-organizing team structure. Requesting a team transfer (A) removes rather than develops. Delegating tasks to others (C) overburdens teammates. Requesting an HR improvement program (D) implies disciplinary action and damages morale. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 자체 조직화 팀의 새 팀원이 프로젝트에서 사용되는 새 기술로 인해 납품에 어려움을 겪는다. PM은 무엇을 해야 하는가? | 팀원을 다른 팀으로 이동하도록 요청한다 | 팀원을 멘토링하고 필요한 교육을 제공한다 | 다른 팀원에게 이 팀원의 작업을 완료하도록 위임한다 | HR 요청을 통해 개선 프로그램에 이 팀원을 포함한다 |  | B | 자체 조직화 팀의 새 팀원이 새 기술에 어려움을 겪을 때, PM은 팀원을 멘토링하고 필요한 교육을 제공해야 한다. 자체 조직 원칙을 존중하면서 역량을 구축한다. 팀 이동(A)은 문제 회피이다. 작업 위임(C)은 성장 기회를 빼앗는다. HR 개선 프로그램(D)은 과도한 조치이다.
1528 | An organization is transitioning to an agile approach. At the project's first sprint review, the product owner did not accept the result of the sprint and has some concerns. What should the project manager do? | Ask the project team to address the product owner ' s issues since the product owner is responsible for the scope in agile. | Create a record in the issue register and escalate the issue to the project steering committee. | Organize a sprint retrospective and discuss the issues and how they can be avoided in the next sprint. | Ask the product owner to accept the outcome since the team delivered what was agreed in the sprint planning. |  | C | The sprint retrospective provides a structured opportunity for the team to inspect and adapt their processes. When the product owner has concerns about sprint results, addressing them in a retrospective enables open discussion about what went well, what didn't, and how to improve. This collaborative effort enhances output quality and ensures alignment with the product owner's expectations. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 조직이 애자일로 전환 중이다. 첫 스프린트 리뷰에서 제품 책임자가 결과를 수락하지 않았다. PM은 무엇을 해야 하는가? | 제품 책임자가 책임지므로 프로젝트 팀에게 문제를 해결하도록 요청한다 | 이슈 등록부에 기록하고 프로젝트 운영 위원회에 에스컬레이션한다 | 스프린트 회고를 조직하고 문제와 다음 스프린트에서 피할 수 있는 방법을 논의한다 | 팀이 스프린트 계획에서 합의한 것을 납품했으므로 제품 책임자에게 수락하도록 요청한다 |  | C | 첫 스프린트 리뷰에서 제품 책임자가 결과를 수락하지 않을 때, PM은 스프린트 회고를 조직하여 문제와 개선 방법을 논의해야 한다. 회고가 프로세스 검토와 적응을 위한 구조화된 기회를 제공한다. 팀에게 해결 요청(A)은 PM 역할을 방기한다. 에스컬레이션(B)은 과도하다. 수락 강요(D)은 품질을 무시한다.
1529 | During the executing phase, a project manager is reviewing the issue log and finds there are outstanding high-priority issues that are still open. Most of the open issues require effort from external domain experts who are not on the project team. What should the project manager do? | Request that the project team members learn the required domain knowledge andresolve the open issues in a short time. | Ask the issue reporter to close the issues, because there are no project team memberswho have the required domain knowledge. | Reduce the project scope to ensure that the project team has the knowledge to deliverthe system on schedule. | Review the open issues with the issue reporter and issue a change request to hire anexternal domain expert. |  | D | When outstanding high-priority issues require external domain experts not on the project team, the project manager should review the open issues with the reporter and issue a change request to hire an external domain expert. This addresses the knowledge gap through formal change control. Requesting the team learn domain knowledge quickly (A) is unrealistic. Asking the reporter to close issues (B) ignores them. Reducing project scope (C) compromises deliverables. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 실행 단계에서 PM이 이슈 로그를 검토하고 프로젝트 팀에 없는 도메인 전문 지식이 필요한 미해결 고우선순위 이슈를 발견한다. PM은 무엇을 해야 하는가? | 프로젝트 팀원에게 필요한 도메인 지식을 학습하고 미해결 이슈를 해결하도록 요청한다 | 프로젝트 팀에 필요한 지식을 가진 팀원이 없으므로 이슈 보고자에게 이슈를 닫도록 요청한다 | 프로젝트 팀이 시스템을 납품할 지식을 갖추도록 프로젝트 범위를 줄인다 | 이슈 보고자와 미해결 이슈를 검토하고 외부 도메인 전문가를 고용하기 위한 변경 요청을 발행한다 |  | D | 미해결 고우선순위 이슈에 팀에 없는 도메인 전문 지식이 필요할 때, PM은 이슈 보고자와 이슈를 검토하고 외부 전문가 고용을 위한 변경 요청을 발행해야 한다. 적절한 전문성이 문제 해결을 보장한다. 학습 요청(A)은 비현실적이다. 이슈 닫기(B)는 무책임하다. 범위 축소(C)는 가치를 훼손한다.
1530 | A project manager leads a development project for a mobile chatting application. One of the experienced developers constantly creates conflicts with the other team members. As a result, the other team members are refusing to work with the developer. Since the developer is a high performer, the project goals may be negatively impacted if they leave the team. What should the project manager do in this situation? | Arrange a team-building training session and require all of the team members to attend. | Meet with the team members and developer individually to understand the situation and build an action plan accordingly. | Collect the team ' s feedback and send it to human resources (HR) to resolve the conflict. | Meet with the developer and ask them to be respectful with the other team members and work together as a team. |  | B | When an experienced high-performing developer constantly creates conflicts and others refuse to work with them, the project manager should meet with team members and the developer individually to understand the situation and build an action plan. Individual conversations identify root causes. Team-building training (A) is general, not targeted. Collecting feedback and sending to HR (C) delegates responsibility. Asking the developer to be respectful (D) addresses symptoms, not causes. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 모바일 채팅 앱 개발 프로젝트에서 경험 있는 개발자가 지속적으로 갈등을 일으키고 다른 팀원이 함께 일하기를 거부한다. PM은 무엇을 해야 하는가? | 팀 빌딩 교육 세션을 주선하고 모든 팀원의 참석을 요구한다 | 팀원과 개발자를 개별적으로 만나 상황을 이해하고 행동 계획을 수립한다 | 팀의 피드백을 수집하여 HR에 보내 갈등을 해결하도록 한다 | 개발자와 만나 다른 팀원을 존중하고 함께 일하도록 요청한다 |  | B | 경험 있는 고성과 개발자가 지속적으로 갈등을 일으킬 때, PM은 팀원과 개발자를 개별적으로 만나 상황을 이해하고 행동 계획을 수립해야 한다. 개별 이해가 근본 원인을 파악한다. 팀 빌딩(A)은 근본 문제를 다루지 않는다. HR 의뢰(C)는 직접 해결 시도 전에 과도하다. 존중 요청(D)만으로는 행동 변화가 어렵다.
1531 | Organizational downsizing has resulted in the key subject matter expert (SME) resource leaving a multiyear project. What should the project manager do? | Refer to the resource management plan. | Update the stakeholder register. | Consult the project sponsor. | Modify the statement of work (SOV). |  | A | When a key SME leaves a multiyear project due to organizational downsizing, the project manager should refer to the resource management plan. This plan describes how project resources are acquired, allocated, monitored, and controlled—including processes for managing changes to resource assignments, knowledge transfer, and stakeholder communication regarding personnel changes. Updating the stakeholder register (B) is a downstream consequence but not the first action. Consulting the project sponsor (C) may be helpful but is less effective than following the established plan. Modifying the statement of work (D) is unnecessary unless the project scope is directly affected by the SME's departure. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Resources | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 조직 축소로 다년 프로젝트의 핵심 SME 자원이 떠나게 되었다. PM은 무엇을 먼저 해야 하는가? | 자원 관리 계획을 참조한다 | 이해관계자 등록부를 업데이트한다 | 프로젝트 스폰서와 상의한다 | 작업기술서(SOW)를 수정한다 |  | A | 핵심 SME가 조직 축소로 떠날 때, PM은 먼저 자원 관리 계획을 참조해야 한다. 이 계획이 프로젝트 자원 확보, 할당, 관리, 해제 방법을 설명한다. 이해관계자 등록부(B)는 역할 관련이지 자원 대체가 아니다. 스폰서 상의(C)는 계획 검토 후에 한다. SOW 수정(D)은 범위와 관련이다.
1532 | During the development phase, a team member encounters an issue with a specific task and attempts to resolve it over the next several days. The other team members ask the project manager to reassign the task to another team member to avoid jeopardizing the target date. The current team member assigned communicates they will feel frustrated if the task is reassigned to someone else. How should the project manager address this situation? | Negotiate with the customer a delay in the project delivery. | Facilitate a session to reach an agreement with the team as a whole. | Accept the team ' s request to reassign the team member. | Seek help from experts to support the team member in fixing the problem. |  | D | When a team member struggles with a task, the PM should seek expert assistance to support them. This aligns with PMI principles emphasizing team development and leveraging available expertise to enhance project outcomes. Collaboration and effective resource utilization are key to addressing challenges and improving team capabilities. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 개발 단계에서 팀원이 특정 작업에 문제를 겪고 일주일 이상 해결하지 못한다. 팀이 재배정을 요청한다. PM은 무엇을 해야 하는가? | 고객과 프로젝트 납품 지연을 협상한다 | 팀 전체와 합의에 도달하기 위한 세션을 퍼실리테이션한다 | 팀원 재배정 요청을 수락한다 | 전문가의 도움을 구하여 팀원의 문제 해결을 지원한다 |  | D | 팀원이 작업에 어려움을 겪을 때, PM은 전문가의 도움을 구하여 팀원을 지원해야 한다. 가용한 전문성을 활용하여 팀 개발을 촉진한다. 납품 지연 협상(A)은 시기상조이다. 팀 세션(B)은 기술적 문제를 해결하지 않는다. 재배정(C)은 성장 기회를 빼앗는다.
1533 | A project manager has been moved to a new division and is in charge of an existing project in an unfamiliar domain. When attempting to gain an understanding of the risks for this agile project, what is the primary tool the project manager should employ? | Interview with the project champion | Workshops for risk avoidance | Probability assessments | Collaborative discussions |  | D | Collaborative discussions are interactive sessions involving the project team and relevant stakeholders to identify, analyze, prioritize, and respond to risks. They leverage collective knowledge and experience, foster shared understanding, and promote a risk-aware culture. Collaborative discussions are especially suited for agile projects, supporting principles of communication, collaboration, feedback, and adaptation. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 새 부서로 이동하여 익숙하지 않은 도메인의 기존 프로젝트를 담당한다. 리스크를 식별하기 위해 어떤 기법을 사용해야 하는가? | 프로젝트 챔피언과의 인터뷰 | 리스크 회피를 위한 워크숍 | 확률 평가 | 협력적 토론 |  | D | 익숙하지 않은 도메인에서 리스크를 식별하려면, 협력적 토론을 사용해야 한다. 협력적 토론은 팀과 이해관계자의 집단 지식을 활용하여 리스크를 식별, 분석, 우선순위화하고 대응한다. 인터뷰(A)는 한 사람의 관점에 제한된다. 리스크 회피 워크숍(B)은 식별이 아닌 대응이다. 확률 평가(C)는 이미 식별된 리스크에 사용한다.
1534 | A project manager has decided to stop activities that do not add value to a project that has a risk of running over budget. A functional manager disagrees with this decision, especially when the team is performing product testing for highly sensitive end users. The functional manager escalated the issue to the project sponsor so that the team can resume activities. How should the project manager have handled the situation? | Convinced the functional manager to stop the activities that will run beyond the budget | Engaged with the project sponsor to ensure support for the project manager ' s decision | Collaborated with the functional manager to determine which critical activities could be accommodated by the budget | Conducted a meeting with the functional manager to explain why the activities needed to be stopped |  | C | When a functional manager disagrees with stopping activities to control budget and escalates to the sponsor, the project manager should have collaborated with the functional manager to determine which critical activities could be accommodated by the budget. Collaboration enables shared understanding of constraints and joint decision-making. Convincing the functional manager to stop activities (A) is one-sided. Engaging the sponsor for support (B) escalates before collaboration. Conducting a meeting to explain the decision (D) informs but does not invite collaborative problem-solving. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | PM이 예산 초과 리스크가 있는 프로젝트에서 가치를 추가하지 않는 활동을 중단하기로 결정했다. 기능 관리자가 동의하지 않고 스폰서에게 에스컬레이션했다. PM이 이전에 무엇을 했어야 하는가? | 기능 관리자에게 예산을 초과할 활동을 중단하도록 설득했다 | 프로젝트 스폰서와 협력하여 PM의 결정에 대한 지원을 확보했다 | 기능 관리자와 협력하여 어떤 중요 활동을 수용할 수 있는지 결정했다 | 기능 관리자와 회의하여 활동을 중단해야 하는 이유를 설명했다 |  | C | 기능 관리자가 활동 중단에 동의하지 않고 에스컬레이션할 때, PM은 기능 관리자와 협력하여 어떤 중요 활동을 수용할 수 있는지 결정했어야 한다. 협력적 의사결정이 저항을 줄인다. 설득(A)은 일방적이다. 스폰서 지원(B)은 우회이다. 설명(D)은 협력이 아닌 통보이다.
1535 | An agile project team is working on an infrastructure product to be delivered incrementally over several iterations. Midway through the third iteration, the whole company is informed that the operating systems supported by the infrastructure will be terminated in the upcoming quarter. Several thousand machines will be impacted by this change. What should the project manager do first? | Add product backlog items to prioritize operating system stories. | Inform the product owner and request more project resources. | Schedule a session with stakeholders to understand the impact. | Prioritize the upgrade of project machines with the IT department. |  | C | When the company announces that supported operating systems will be terminated affecting several thousand machines mid-iteration, the project manager should first schedule a session with stakeholders to understand the impact. Stakeholder engagement enables informed decision-making. Adding backlog items (A) acts before assessing impact. Informing the PO and requesting resources (B) is premature. Prioritizing machine upgrades with IT (D) acts without understanding full impact. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트 팀이 인프라 제품을 점진적으로 납품 중이다. 이터레이션 중간에 회사가 지원되는 운영 체제가 종료된다고 발표한다. PM은 무엇을 먼저 해야 하는가? | 운영 체제 스토리를 우선순위화하기 위해 제품 백로그 항목을 추가한다 | 제품 책임자에게 알리고 더 많은 프로젝트 자원을 요청한다 | 이해관계자와 세션을 예약하여 영향을 이해한다 | IT 부서와 프로젝트 머신의 업그레이드를 우선순위화한다 |  | C | 지원 운영 체제가 종료되어 수천 대의 머신에 영향을 미칠 때, PM은 먼저 이해관계자와 세션을 예약하여 영향을 이해해야 한다. 영향 평가가 정보 기반 의사결정의 기초이다. 백로그 추가(A)는 영향 이해 후에 한다. 자원 요청(B)은 영향 평가 후에 한다. IT 업그레이드(D)는 프로젝트 범위 밖일 수 있다.
1536 | A company is transitioning their projects to utilize hybrid project management approaches. While putting together their project team, the project manager discovers the requirements from the customer are unclear and also realizes that the team members are lacking critical technical skills needed for project success. However, the customer will not accept any changes to the requirements. What should the project manager do to resolve this issue? | Find and provide training to the project team members who do not have the required skills | Ask the scrum master to refine the user stones to improve the team members ' understanding | Submit a change request to adapt the objectives of the project to the current situation | Extend the duration of standup meetings to include skill transference from trained to untrained members |  | A | When team members lack critical technical skills needed for project success, the project manager should find and provide relevant training to bridge the skill gap. This ensures the team has the necessary competencies to deliver on project objectives, even when requirements are unclear. Training aligns with hybrid project management principles of continuous learning and adaptability. Asking the scrum master to refine user stories (B) may clarify requirements but does not address the technical skills gap. Submitting a change request to adapt project objectives (C) assumes the situation is unresolvable through capability building. Extending standup meetings for skill transfer (D) is not an effective training mechanism and disrupts the purpose of daily standups. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Resources | Planning | Focus on Value | Plan Resource Management | Hybrid/Tailoring | 회사가 하이브리드 프로젝트 관리 접근법으로 전환 중이다. 팀에 필요한 기술적 스킬이 부족한 팀원이 있다. PM은 무엇을 해야 하는가? | 필요한 스킬이 없는 프로젝트 팀원을 찾아 교육을 제공한다 | 스크럼 마스터에게 사용자 스토리를 세분화하여 팀원 이해를 개선하도록 요청한다 | 프로젝트 목표를 현재 상황에 맞추기 위한 변경 요청을 제출한다 | 훈련된 팀원에서 미훈련 팀원으로의 스킬 전달을 위해 스탠드업 회의 기간을 연장한다 |  | A | 팀원에게 프로젝트 성공에 필요한 기술적 스킬이 부족할 때, PM은 교육을 찾아 제공해야 한다. 스킬 격차를 해소하는 것이 팀 역량을 보장한다. 스토리 세분화(B)는 스킬 부족을 해결하지 않는다. 변경 요청(C)은 목표를 낮추는 것이다. 스탠드업 연장(D)은 스탠드업의 목적에 맞지 않는다.
1537 | A project manager is leading a project with a predictive approach for a governmental body with strictly defined requirements. In the middle of the project, the sponsor requires a significant new feature to be included. This feature was not in the original plan, nor was it part of the planning process. What should the project manager do? | Analyze the impact of this change and present the options to the senior manager. | Inform the senior manager that they will need a new project management plan for this feature, | Descope low-priority features that were not explicitly requested and add this feature as a high priority. | Complete the most current feature and release the resources for the new feature. |  | A | When a sponsor requires a significant new feature that was not part of the original plan for a predictive project with strictly defined requirements, the project manager should analyze the impact of this change on scope, schedule, cost, and resources, and present the options to the senior manager. Impact analysis ensures informed decision-making before any changes are implemented. Informing the manager they need a new project management plan (B) is premature without analysis. Descoping existing features to add the new one (C) makes changes without formal impact assessment. Completing the current feature and releasing resources (D) abandons the existing project approach without following change control. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Baseline & Change Control | Process | Plan and Manage Schedule | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 예측형 접근법으로 정부 기관의 엄격히 정의된 요구사항 프로젝트를 이끈다. 스폰서가 원래 계획에 없던 중요한 새 기능을 요구한다. PM은 무엇을 해야 하는가? | 이 변경의 영향을 분석하고 고위 관리자에게 옵션을 제시한다 | 고위 관리자에게 이 기능에 새 프로젝트 관리 계획이 필요함을 알린다 | 명시적으로 요청되지 않은 저우선순위 기능을 제거하고 이 기능을 고우선순위로 추가한다 | 가장 현재의 기능을 완료하고 새 기능을 위해 자원을 해제한다 |  | A | 예측형 프로젝트에서 스폰서가 원래 계획에 없던 새 기능을 요구할 때, PM은 변경의 영향을 분석하고 고위 관리자에게 옵션을 제시해야 한다. 영향 분석이 정보 기반 결정을 가능하게 한다. 새 계획 필요 알림(B)은 분석 없이 성급하다. 기능 제거(C)는 승인 없이 범위를 변경한다. 자원 해제(D)는 현재 작업을 중단한다.
1538 | The project schedule is falling behind and the project manager observes that the project team seems to be spending the majority of their time writing documentation instead of performing project tasks. What should the project manager do to help ensure that the team focuses on project tasks? | Assign a team member to handle the documentation activities. | Review and adapt the appropriate project artifacts. | Save all documentation activities until tire end of the project | Coach the project team to complete the project documentation activities |  | B | When the team spends too much time on documentation instead of project tasks, the project manager should review and adapt the appropriate project artifacts. This involves assessing which documents are truly necessary, eliminating unnecessary ones, simplifying the documentation process, and aligning it with project priorities. Assigning one person to handle all documentation (A) creates bottlenecks. Coaching the team on documentation (D) does not address the root cause—excessive or unnecessary documentation. Saving all documentation until the end (C) compromises project communication, monitoring, and control. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Tailored Approach | Business Environment | Plan and Manage Risk | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Hybrid/Tailoring | 프로젝트 일정이 지연되고 팀이 프로젝트 작업 대신 문서화에 대부분의 시간을 보내는 것을 PM이 관찰한다. PM은 무엇을 해야 하는가? | 문서화 활동을 처리할 팀원을 배정한다 | 적절한 프로젝트 산출물을 검토하고 조정한다 | 모든 문서화 활동을 프로젝트 종료까지 저장한다 | 프로젝트 문서화 활동을 완료하도록 프로젝트 팀을 코칭한다 |  | B | 팀이 프로젝트 작업 대신 과도한 문서화에 시간을 보낼 때, PM은 적절한 프로젝트 산출물을 검토하고 조정해야 한다. 어떤 문서가 필수이고 어떤 것이 불필요한지 평가한다. 전담 배정(A)은 과도한 문서화를 인정한다. 종료까지 연기(C)는 필수 문서화도 생략한다. 코칭(D)은 문서 양이 아닌 기술을 다룬다.
1539 | A supplier that the company has used for years has trouble accepting the new terms of an agile contract. They do not understand the terms in the contract and feel they should not have to sign it because they have had a long relationship with the company. Which action should the project manager take? | Issue a request for proposal (RFP) to find new suppliers with agile experience. | Train the supplier in agile approaches to help them understand the contract. | Ask the team if they can do the work until there is an available supplier. | Change contract terms and conditions to avoid losing the supplier. |  | B | The correct answer is B. Train the supplier in agile approaches to help them understand the contract. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 수년간 사용한 공급업체가 애자일 계약의 새 조건을 수용하기 어려워한다. PM은 무엇을 해야 하는가? | 애자일 경험이 있는 새 공급업체를 찾기 위해 제안요청서(RFP)를 발행한다 | 공급업체에게 애자일 접근법을 교육하여 계약을 이해하도록 돕는다 | 가용한 공급업체가 있을 때까지 팀이 작업을 수행할 수 있는지 확인한다 | 공급업체를 잃지 않기 위해 계약 조건을 변경한다 |  | B | 정답은 B이다. 공급업체에게 애자일 접근법을 교육하여 계약을 이해하도록 돕는다. 애자일 환경에서 PM은 협업을 촉진하고 장애물을 제거해야 한다. 교육이 기존 관계를 유지하면서 이해를 구축한다. 새 RFP(A)는 시간과 관계 손실이다. 팀 작업(C)은 역량 밖이다. 조건 변경(D)은 원칙을 타협한다.
1540 | An agile project team discovers that they are unable to implement a feature completely in the first iteration. The team believes it may not be able to complete the tasks in the second iteration. The feature is a critical component that the customer has prioritized. What should the team do? | Reduce the scope of the feature to fit into one iteration and deliver it to the customer | Go back to the customer and explain that they cannot implement the feature completely in one iteration. | Split the feature into smaller subfeatures. implement them, and then deliver them incrementally in multiple iterations | Ask the customer to simplify the feature so that it can be implemented in one iteration |  | C | The correct answer is C. Split the feature into smaller subfeatures. implement them, and then deliver them incrementally in multiple iterations. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Scrum | Process | Manage Project Closure | Governance | Closing | Focus on Value | Close Project or Phase | Traditional PM | 애자일 팀이 첫 이터레이션에서 기능을 완전히 구현할 수 없음을 발견한다. 팀은 어떻게 해야 하는가? | 기능의 범위를 한 이터레이션에 맞게 줄이고 고객에게 납품한다 | 고객에게 돌아가 한 이터레이션에서 완전히 구현할 수 없다고 설명한다 | 기능을 더 작은 하위 기능으로 분할하여 여러 이터레이션에 걸쳐 점진적으로 납품한다 | 고객에게 한 이터레이션에서 구현할 수 있도록 기능을 단순화하도록 요청한다 |  | C | 정답은 C이다. 기능을 더 작은 하위 기능으로 분할하여 여러 이터레이션에 걸쳐 점진적으로 납품한다. 애자일은 반복적 납품과 팀 권한 부여를 강조한다. 범위 축소(A)는 가치를 손상한다. 고객 설명(B)은 해결이 아니다. 단순화 요청(D)은 고객에게 부담을 전가한다.
1541 | In analyzing a project for monthly status reporting, the project manager notices that the schedule performance index (SPI) is 0.75 and the cost performance index (CPI) is 1.25. The project manager must provide the first project status review soon and wants to emphasize that the project is under control. How should the project manager report the project status to key stakeholders? | Perform a detailed root cause analysis utilizing a pareto chart and fishbone diagrams to demonstrate that the project is under control. | Prepare a detailed presentation for stakeholders on earned value including how it is calculated and the project ' s current earned value results | Report that the project is behind schedule but that an additional experienced resource can be added to stay within schedule and maintain the budget. | Report that the project is not tracking as expected, but is still under control since the next project milestone is over a month away |  | B | When SPI is 0.75 and CPI is 1.25, the project manager should prepare a detailed presentation for stakeholders on earned value, including how it is calculated and the current results. Transparent reporting with context enables stakeholders to understand the full picture — under budget despite being behind schedule. A Pareto chart and fishbone diagrams (A) are diagnostic tools, not status reporting methods. Reporting that the project is behind and recommending resources (C) does not fully represent the budget performance. Reporting that the next milestone is far away (D) is dismissive. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 월간 상태 보고 분석에서 PM이 SPI=0.75, CPI=1.25를 발견한다. PM은 무엇을 보고해야 하는가? | 파레토 차트와 특성요인도를 활용한 상세 근본 원인 분석을 수행하여 시연한다 | 이해관계자에게 획득가치 계산 방법과 현재 결과를 포함한 상세 프레젠테이션을 준비한다 | 프로젝트가 일정 지연이지만 추가 경험 있는 자원을 투입하면 회복할 수 있다고 보고한다 | 프로젝트가 예상대로 추적되지 않지만 다음 프로젝트 이정표가 예산 이내이므로 여전히 통제 중이라고 보고한다 |  | B | SPI가 0.75(일정 지연)이고 CPI가 1.25(예산 이하)일 때, PM은 이해관계자에게 획득가치 계산 방법과 현재 결과를 포함한 상세 프레젠테이션을 준비해야 한다. 투명한 보고가 정보 기반 의사결정을 지원한다. RCA(A)는 지나치게 상세하다. 자원 추가 보고(C)는 사전 분석 없이 해결을 제안한다. 통제 중이라는 보고(D)는 일정 문제를 과소평가한다.
1542 | After assigning tasks to a project team, a project manager discovers that some team members are uncomfortable. Some team members are having a difficult time understanding their assigned tasks, whereas other team members are challenging the schedule based on their allocation to the project. Which phase of the Tuckman ladder of team formation is occurring? | Norming | Storming | Forming | Mourning |  | B | When team members are uncomfortable — some struggling to understand tasks and others challenging the schedule based on allocation — the team is in the Storming phase of Tuckman's model. Storming involves conflict and disagreement as members navigate roles and responsibilities. Norming (A) features established cooperation. Forming (C) involves initial orientation. Mourning (D) occurs at project closure. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Schedule Management | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀에 작업 배정 후 PM이 일부 팀원이 불편해하는 것을 발견한다. 일부는 작업 이해에 어려움을 겪고, 다른 일부는 할당에 기반한 일정에 이의를 제기한다. 팀은 어떤 단계에 있는가? | 규범화(Norming) | 혼란(Storming) | 형성(Forming) | 해산(Mourning) |  | B | 팀원들이 불편해하고 작업 이해에 어려움을 겪으며 일정에 이의를 제기할 때, 팀은 터크먼 모델의 혼란(Storming) 단계에 있다. 혼란 단계는 갈등, 역할 명확화, 의견 대립이 특징이다. 규범화(A)는 팀이 합의에 도달하는 단계이다. 형성(C)은 초기 도입 단계이다. 해산(D)은 프로젝트 종료 단계이다.
1543 | During daily team coordination meetings, team members constantly ask which tasks they should focus on first. How should the project manager ensure the team is fully productive? | Work with the product owner to ensure the project backlog is prioritized. | Review the project backlog during the team's coordination meeting. | Ensure team members are working according to the project management plan. | Encourage project team members to prioritize the product backlog. |  | A | When team members constantly ask which tasks to prioritize during daily meetings, the project manager should work with the product owner to ensure the project backlog is prioritized. Clear backlog prioritization eliminates confusion about work order. Reviewing the backlog during coordination meetings (B) is a temporary fix. Ensuring team members follow the project management plan (C) is too broad. Encouraging team members to prioritize the backlog (D) misassigns ownership. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Executing | Integrate Sustainability | Direct and Manage Project Work | Sustainability | 데일리 팀 조정 회의에서 팀원이 어떤 작업을 먼저 해야 하는지 계속 질문한다. PM은 어떻게 해야 하는가? | 제품 책임자와 협력하여 프로젝트 백로그가 우선순위화되었는지 확인한다 | 팀 조정 회의에서 프로젝트 백로그를 검토한다 | 팀원이 프로젝트 관리 계획에 따라 일하도록 한다 | 프로젝트 팀원에게 제품 백로그를 우선순위화하도록 격려한다 |  | A | 팀원이 우선순위를 계속 질문할 때, PM은 제품 책임자와 협력하여 백로그가 적절히 우선순위화되었는지 확인해야 한다. 명확한 백로그 우선순위가 자체 조직화를 가능하게 한다. 회의에서 검토(B)는 데일리의 목적에 맞지 않는다. 관리 계획(C)은 애자일에서 백로그가 우선이다. 팀 우선순위화(D)는 제품 책임자의 역할이다.
1544 | Due to a tight schedule, a project team member suggests skipping the quality check of a minor deliverable. What should the project manager do? | Ask the team member to work overtime to complete the quality check. | Seek approval from the quality board to skip the quality check. | Seek approval from the sponsor on an extension of the project schedule, | Evaluate the impact of skipping the quality check for the deliverable. |  | D | Quality should not be compromised even for minor deliverables under tight schedules. When a team member suggests skipping a quality check, the PM should first evaluate the potential impact—assessing risks of defects, effects on customer satisfaction, and consequences for overall project integrity. This informed evaluation enables an appropriate decision rather than a reactive one based solely on schedule pressure. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 빠듯한 일정으로 인해 팀원이 사소한 인도물의 품질 검사를 건너뛰자고 제안한다. PM은 무엇을 해야 하는가? | 팀원에게 품질 검사를 완료하기 위해 초과 근무하도록 요청한다 | 품질 위원회에 품질 검사 건너뛰기에 대한 승인을 구한다 | 스폰서에게 프로젝트 일정 연장 승인을 구한다 | 인도물의 품질 검사 건너뛰기의 영향을 평가한다 |  | D | 사소한 인도물의 품질 검사 건너뛰기가 제안될 때, PM은 먼저 건너뛰기의 영향을 평가해야 한다. 품질은 빠듯한 일정에서도 타협되어서는 안 된다. 리스크, 영향, 범위를 평가한다. 초과 근무(A)는 팀에 부담이다. 승인 구하기(B)는 영향 평가 전에 성급하다. 일정 연장(C)은 영향 평가 후에 결정한다.
1545 | During user acceptance testing (UAT), a manager declined a core application functionality that was originally requested by a subject matter expert (SME). Due to the manager's influence, the project team is concerned about the overall impact to the project. What should the project manager have done? | Identified and consulted stakeholders during requirements gathering | Consulted with the project sponsor on stakeholder roles and responsibilities | Requested stakeholders to participate in project initiation and planning phases | Obtained a list of the critical stakeholders from the project sponsor |  | B | The correct answer is B. Consulted with the project sponsor on stakeholder roles and responsibilities. Quality management ensures deliverables meet established standards and acceptance criteria. The PM should implement appropriate quality controls and take corrective action when issues are identified. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | UAT에서 관리자가 원래 요청했던 핵심 기능을 거부했다. PM이 이전에 무엇을 했어야 하는가? | 요구사항 수집 중 이해관계자를 식별하고 상의했다 | 프로젝트 스폰서와 이해관계자 역할과 책임에 대해 상의했다 | 이해관계자에게 프로젝트 착수 및 계획 단계에 참여하도록 요청했다 | 프로젝트 스폰서로부터 핵심 이해관계자 목록을 획득했다 |  | B | 정답은 B이다. 프로젝트 스폰서와 이해관계자 역할과 책임에 대해 상의했다. 품질 관리는 인도물이 설정된 표준과 인수 기준을 충족하도록 보장한다. PM은 누가 어떤 인도물을 수락할 권한이 있는지 사전에 명확히 했어야 한다. 요구사항 수집 참여(A)는 역할 명확화가 아니다. 착수 참여(C)는 부분적이다. 목록 획득(D)은 역할 정의가 아니다.
1546 | An organization is transitioning to an agile delivery approach. There is only one project that is being used as a pilot for the new approach. The project management office (PMO) manager has asked the project lead how communications with the project team and the stakeholders will be managed. What should the project lead recommend? | Send weekly reports to all stakeholders, including the project team and the product owner. | Invite the PMO manager to the daily standup with the project team and product owner. | Send the weekly report to the PMO and the product owner, and use a kanban board for the project team. | Send weekly reports to the PMO, and use a kanban board for the product owner and the project team. |  | B | When the PMO manager asks how communications will be managed in an agile pilot project, the project lead should recommend inviting the PMO manager to the daily standup with the project team and product owner. Direct participation in agile ceremonies provides real-time transparency. Sending weekly reports to all stakeholders (A) is too formal and infrequent for agile. Sending weekly reports to PMO with a kanban board for the team (C) separates stakeholder and team communication. Weekly reports to PMO with kanban for both (D) mixes approaches inconsistently. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 조직이 애자일 전환 중이며 파일럿 프로젝트가 하나 있다. PMO 관리자가 커뮤니케이션 관리 방법을 물었다. 프로젝트 리더는 무엇을 권장해야 하는가? | 프로젝트 팀과 제품 책임자를 포함한 모든 이해관계자에게 주간 보고를 보낸다 | PMO 관리자를 프로젝트 팀과 제품 책임자의 데일리 스탠드업에 초대한다 | PMO와 제품 책임자에게 주간 보고를 보내고 프로젝트 팀에는 칸반 보드를 사용한다 | PMO에 주간 보고를 보내고 제품 책임자와 프로젝트 팀에 칸반 보드를 사용한다 |  | B | PMO 관리자가 애자일 파일럿 프로젝트의 커뮤니케이션 방법을 물을 때, 프로젝트 리더는 PMO 관리자를 데일리 스탠드업에 초대해야 한다. 직접 참여가 투명성과 애자일 이해를 제공한다. 주간 보고만(A)은 예측형이다. 혼합 방식(C,D)은 불필요한 복잡성을 추가한다.
1547 | A global company hired a project manager for a new implementation at all of its sites. After reviewing the business case and project charter, the project manager notes that the project team has different locations and regions to consider. What should the project manager do to address this situation? | Coordinate virtual meetings to assess the project team ' s communication needs | Inform the project sponsor of this situation and request cultural orientation training. | Inform the steering committee of the situation and request additional resources. | Coordinate virtual and face-to-face meetings at each site to improve communication |  | D | When a global project has team members across different locations and regions, the project manager should coordinate virtual and face-to-face meetings at each site to improve communication. Multi-modal meetings address geographic and cultural challenges. Virtual meetings alone (A) may miss communication nuances. Requesting cultural orientation training (B) is one component but not comprehensive. Requesting additional resources (C) does not address communication needs. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 글로벌 회사가 모든 사이트에 새 구현을 위해 PM을 고용했다. 팀원이 여러 지역에 분산되어 있다. PM은 무엇을 해야 하는가? | 프로젝트 팀의 커뮤니케이션 요구를 평가하기 위해 가상 회의를 조율한다 | 프로젝트 스폰서에게 상황을 알리고 문화 오리엔테이션 교육을 요청한다 | 운영 위원회에 상황을 알리고 추가 자원을 요청한다 | 각 사이트에서 가상 및 대면 회의를 조율하여 커뮤니케이션을 개선한다 |  | D | 글로벌 프로젝트에서 팀원이 여러 지역에 분산될 때, PM은 각 사이트에서 가상 및 대면 회의를 조율하여 커뮤니케이션을 개선해야 한다. 다중 방식 커뮤니케이션이 지리적 차이를 극복한다. 가상 회의만(A)은 불충분하다. 문화 교육 요청(B)은 부분적이다. 추가 자원(C)은 커뮤니케이션 문제를 해결하지 않는다.
1548 | While reviewing prototypes, the quality team found some deviations that do not affect the main functionality but have the potential to be an issue in the future. To avoid major problems in the future, the team recommends corrective actions that will require additional funds. The project is already struggling to stay on budget and has even used some of the contingency reserves. What should the project manager do? | Ask the quality team to discard the sample and test again with a new sample | Report to the project sponsor that the product is working and the project is struggling with the budget. | Evaluate and initiate the change request process with the stakeholders | Ask the product designer why the deviation was not considered in the design phase |  | C | When the quality team finds deviations with future risk potential requiring additional funds on a budget-constrained project, the project manager should evaluate and initiate the change request process with stakeholders. Formal change control ensures deviations are assessed and corrective actions are approved. Asking quality to discard and retest (A) ignores the findings. Reporting that the product works (B) downplays quality risk. Questioning the designer (D) does not address the corrective action need. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로토타입 검토 중 품질 팀이 주요 기능에 영향을 미치지 않지만 미래 리스크가 있는 편차를 발견했다. 추가 자금이 필요하지만 예산이 제한적이다. PM은 무엇을 해야 하는가? | 품질 팀에 샘플을 폐기하고 새 샘플로 다시 테스트하도록 요청한다 | 스폰서에게 제품이 작동하며 예산 문제가 있다고 보고한다 | 이해관계자와 변경 요청 프로세스를 평가하고 개시한다 | 제품 설계자에게 설계 단계에서 편차가 왜 고려되지 않았는지 묻는다 |  | C | 품질 편차가 미래 리스크를 수반하고 추가 자금이 필요할 때, PM은 이해관계자와 변경 요청 프로세스를 평가하고 개시해야 한다. 공식 변경 관리가 적절한 검토와 승인을 보장한다. 재테스트(A)는 편차를 해결하지 않는다. 스폰서 보고만(B)은 조치가 아니다. 책임 추궁(D)은 비생산적이다.
1549 | A project manager is approaching the end of a project, and several tasks are now practically complete and ready for handover to the client. How should the project manager proceed? | Update the quality management plan for the overall project | Update the communications management plan for the overall project | Close out the project tasks that have been completed | Ask the client to verify and accept the tasks that have been completed |  | D | At project completion, the PM should ensure formal product transition by transferring ownership and responsibility of deliverables to the customer or sponsor, obtaining their formal acceptance and sign-off. The PM must verify that scope and quality criteria are met and deliverables align with project objectives and stakeholder expectations. Other options belong to planning or monitoring phases and do not involve the client's final verification and acceptance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 프로젝트 종료에 가까워졌고 여러 작업이 완료되어 인도 준비가 되었다. PM은 무엇을 해야 하는가? | 전체 프로젝트의 품질 관리 계획을 업데이트한다 | 전체 프로젝트의 커뮤니케이션 관리 계획을 업데이트한다 | 완료된 프로젝트 작업을 종료한다 | 고객에게 완료된 작업을 확인하고 인수하도록 요청한다 |  | D | 프로젝트 종료 시 작업이 완료되어 인도 준비가 되었을 때, PM은 고객에게 완료된 작업을 확인하고 인수하도록 요청해야 한다. 공식 인수와 서명이 인도물 전환을 보장한다. 품질 계획 업데이트(A)는 종료 시 부적절하다. 커뮤니케이션 계획 업데이트(B)는 관련이 적다. 작업 종료(C)는 고객 수용 전에 시기상조이다.
1550 | Two team members were recently released from a project because the customer reduced the budget. However, the agile team is still receiving the same, if not more, work requirements as before. How should the agile project leader resolve this situation? | Explain the new team velocity to the customer. | Explain the new project requirements to the team. | Update the project budget with the released team members. | Update the restriction log with the new team capacity. |  | A | When two team members are released due to budget cuts but work requirements remain the same or increase, the agile project leader should explain the new team velocity to the customer and negotiate scope and schedule accordingly. Reduced team size decreases velocity, requiring transparent communication with the customer to reprioritize features and adjust the release plan. Explaining new requirements to the team (B) overloads them without adjusting expectations. Updating the project budget (C) addresses cost but not the scope-schedule mismatch. Updating the restriction log (D) documents constraints but does not resolve the delivery gap. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Build an Empowered Culture | Plan Scope Management | Traditional PM | 예산 삭감으로 두 팀원이 해제되었지만 애자일 팀의 작업 요구사항은 그대로이다. PM은 무엇을 먼저 해야 하는가? | 고객에게 새 팀 속도를 설명한다 | 팀에 새 프로젝트 요구사항을 설명한다 | 해제된 팀원의 프로젝트 예산을 업데이트한다 | 새 팀 역량으로 제약 로그를 업데이트한다 |  | A | 예산 삭감으로 팀원이 해제되어 팀 역량이 줄었을 때, PM은 먼저 고객에게 새 팀 속도를 설명해야 한다. 속도 변화가 납품에 직접 영향을 미치므로 기대치 관리가 중요하다. 요구사항 설명(B)은 변경되지 않았다. 예산 업데이트(C)는 행정적이다. 제약 로그 업데이트(D)는 부차적이다.
1551 | A project team has been tasked with delivering robotics to automate a manufacturing line. The technical teams are all in place and have the technical information needed to build and install the robots. What other factors should be considered when planning this project? | Safety and organizational culture. | Financial and market conditions. | Industry standards and research. | Software, security, and infrastructure. |  | A | When planning a robotics project to automate a manufacturing line where technical teams are already equipped, the other factors to consider are safety and organizational culture. Robotics introduces physical hazards and requires workforce readiness and change adoption. Financial and market conditions (B) influence business justification but not execution planning. Industry standards and research (C) are relevant but the team already has technical information. Software, security, and infrastructure (D) are technical factors already addressed. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 프로젝트 팀이 제조 라인 자동화를 위한 로보틱스 납품을 담당한다. 기술 팀이 이미 갖추어져 있다. 추가로 고려해야 할 요소는? | 안전과 조직 문화 | 재무 및 시장 조건 | 산업 표준과 연구 | 소프트웨어, 보안 및 인프라 |  | A | 제조 라인 로보틱스 자동화에서 기술 팀이 이미 갖추어져 있을 때, 추가 고려 요소는 안전과 조직 문화이다. 로보틱스는 물리적 안전 우려를 도입하고 작업 방식의 문화적 변화가 필요하다. 재무/시장(B)는 기술 구현과 직접 관련이 적다. 산업 표준(C)은 기술 팀이 이미 다룬다. 소프트웨어/보안/인프라(D)는 기술적 요소이다.
1552 | Several components of an expensive manufacturing project have been returned by the customer. The customer is complaining that the quality of the components is poor and is concerned that, as a result, their products will be returned due to quality issues. The project manager is certain that quality has been maintained. How should the project manager communicate with the customer to help assure them that the project has produced quality products? | Show the customer a sample history of quality. | Show the customer the quality control measurements. | Show the customer the tolerance and control limits. | Show the customer sample results from the current batch. |  | B | When a customer complains about component quality, the project manager should show the customer the quality control measurements. Objective measurement data provides evidence of adherence to quality standards and addresses the customer's concerns factually. Showing sample history (A) is anecdotal. Showing tolerance and control limits (C) is technical but not evidence of compliance. Showing current batch results (D) is limited in scope. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 고가 제조 프로젝트의 여러 부품이 고객에 의해 반품되었다. 고객이 품질에 불만을 제기한다. PM은 무엇을 해야 하는가? | 고객에게 품질 이력 샘플을 보여준다 | 고객에게 품질 관리 측정값을 보여준다 | 고객에게 허용 오차와 관리 한계를 보여준다 | 고객에게 현재 배치의 샘플 결과를 보여준다 |  | B | 고객이 부품 품질에 불만을 제기할 때, PM은 고객에게 품질 관리 측정값을 보여야 한다. 객관적 측정 데이터가 품질 표준 준수의 증거를 제공한다. 이력 샘플(A)은 과거 데이터이다. 허용 오차(C)는 기술적이지만 실제 성과를 보여주지 않는다. 현재 배치 결과(D)는 부분적 증거만 제공한다.
1553 | An organization initiated a project in a complex program. The project lead notices that the team is demotivated because the current project framework implemented by the project management office (PMO) is not compatible with agile delivery. What should the project lead do? | Escalate the problem to the product owner. | Ask the PMO to review the framework | Request the PMO to define a new framework. | Plan a brainstorming session with the project team |  | B | When the team is demotivated because the PMO framework is incompatible with agile delivery, the project lead should ask the PMO to review the framework. The PMO owns organizational standards and can adapt them. Escalating to the PO (A) is misdirected. Requesting a new framework entirely (C) is too drastic. Planning a brainstorming session (D) does not address the organizational constraint. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Develop a Common Vision | Schedule | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 복잡한 프로그램 내 프로젝트에서 PMO 프레임워크가 애자일 납품과 호환되지 않아 팀이 의기소침하다. 프로젝트 리더는 무엇을 해야 하는가? | 제품 책임자에게 문제를 에스컬레이션한다 | PMO에 프레임워크를 검토하도록 요청한다 | PMO에 새 프레임워크를 정의하도록 요청한다 | 프로젝트 팀과 브레인스토밍 세션을 계획한다 |  | B | PMO 프레임워크가 애자일 납품과 호환되지 않아 팀이 의기소침할 때, 프로젝트 리더는 PMO에 프레임워크를 검토하도록 요청해야 한다. PMO가 조직 표준을 소유하며 적응할 수 있다. 에스컬레이션(A)은 제품 책임자 역할이 아니다. 새 프레임워크(C)는 과도하다. 브레인스토밍(D)은 PMO 문제를 팀 수준에서 해결할 수 없다.
1554 | A scrum team's daily meetings are conducted by teleconference between three teams, each located in different countries. The meetings typically last 45 minutes with many misunderstandings due to language barriers. How should the project manager resolve this issue for the next iteration? | Instruct the meeting participants to speak only about blockers during the meeting. | Transfer half of the backlog items to the next iteration to allow more time to complete the meetings. | Train the three team leads to conduct a local meeting, then run an overall status meeting. | Extend the meeting to 1 hour and request that all of the participants bring up all of the issues. |  | C | When multi-country scrum daily meetings last 45 minutes with language barrier misunderstandings, the project manager should train three team leads to conduct local meetings, then run an overall status meeting. This two-tier approach enables clearer local communication while consolidating information efficiently. Restricting discussion to blockers only (A) limits communication. Transferring backlog items to the next iteration (B) delays work. Extending the meeting to one hour (D) worsens the problem. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 스크럼 팀의 데일리 미팅이 3개국 간 전화 회의로 진행되며 45분이 소요되고 언어 장벽 오해가 있다. PM은 무엇을 해야 하는가? | 회의 참가자에게 블로커에 대해서만 말하도록 지시한다 | 백로그 항목의 절반을 다음 이터레이션으로 이전하여 회의 시간을 확보한다 | 세 팀 리더에게 로컬 회의를 진행한 후 전체 상태 회의를 진행하도록 교육한다 | 회의를 1시간으로 연장하고 모든 참가자가 모든 이슈를 제기하도록 요청한다 |  | C | 다국가 스크럼 데일리 미팅이 45분 소요되고 언어 장벽이 있을 때, PM은 세 팀 리더에게 로컬 회의를 진행한 후 전체 상태 회의를 하도록 교육해야 한다. 로컬 미팅이 언어 문제를 줄이고 효율성을 높인다. 블로커만(A)은 중요 정보를 누락한다. 백로그 이전(B)은 범위에 영향을 준다. 회의 연장(D)은 비효율성을 악화시킨다.
1555 | A company is transitioning from using a predictive approach to using an agile framework on a project. The project sponsor is concerned about the level of uncertainty and how to determine the time and budget required to complete the scope. What should the project manager do to address this situation? | Ask the project team to create a high-level budget baseline for the project and provide more detail only for the first project stages. | Review organizational process assets (OPAs) for similar projects to determine the 433 schedule, costs, and resources required to execute them. | Refine the amount of work required for the project with the project team and perform a detailed project baseline accordingly. | Communicate to the key stakeholders that the project baseline could not be estimated due to the new framework being used. |  | A | The correct answer is A. Ask the project team to create a high-level budget baseline for the project and provide more detail only for the first project stages. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 회사가 예측형에서 애자일로 전환 중이다. 스폰서가 프로젝트 기준선을 요청한다. PM은 무엇을 해야 하는가? | 팀에 상위 수준 예산 기준선을 만들고 첫 단계에 대해서만 상세 정보를 제공하도록 요청한다 | 유사 프로젝트의 조직 프로세스 자산(OPA)을 검토하여 일정, 비용, 범위를 결정한다 | 팀과 필요 작업량을 정제하고 상세 프로젝트 추정을 수행한다 | 새 방법론으로 인해 프로젝트 기준선을 추정할 수 없다고 주요 이해관계자에게 소통한다 |  | A | 정답은 A이다. 팀에 상위 수준 예산 기준선을 만들고 첫 단계에만 상세 정보를 제공하도록 요청한다. 애자일에서 PM은 점진적 정교화를 지원해야 한다. 상위 수준 기준선이 거버넌스를 충족하고 점진적 상세화가 애자일 원칙에 부합한다. OPA 검토(B)는 예측형 접근이다. 상세 추정(C)은 과도하다. 추정 불가 소통(D)은 무책임하다.
1556 | Two architects are unable to agree on how to approach certain components of the development that will be included in the upcoming sprint. After a one-on-one discussion, the architects have decided to each own a particular module of the system, and the team supports the decision. What should the project manager do? | Ensure that there is consensus among the project stakeholders. | Discuss the issue during the next sprint planning meeting. | Support the outcome of the architects' agreement. | Discuss the issue with the team to resolve the disagreement. |  | C | When two architects resolve their disagreement by each owning a module and the team supports the decision, the project manager should support the outcome of the architects' agreement. Respecting team-driven resolution builds trust. Ensuring stakeholder consensus (A) introduces unnecessary complexity. Discussing in the next sprint planning (B) delays action. Discussing with the team to resolve the disagreement (D) is unnecessary since the team already supports the resolution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 두 아키텍트가 개발 접근에 합의하지 못했으나 각자 모듈을 소유하기로 합의하고 팀이 지지한다. PM은 무엇을 해야 하는가? | 프로젝트 이해관계자 간 합의가 있는지 확인한다 | 다음 스프린트 계획 회의에서 이슈를 논의한다 | 아키텍트들의 합의 결과를 지지한다 | 팀과 이슈를 논의하여 불일치를 해결한다 |  | C | 두 아키텍트가 합의에 도달하고 팀이 지지할 때, PM은 아키텍트들의 합의 결과를 지지해야 한다. 팀 주도 의사결정을 존중하는 것이 자율성과 협력을 촉진한다. 합의 확인(A)은 이미 이루어졌다. 스프린트 계획(B)은 지연시킨다. 팀 논의(D)는 이미 해결된 문제를 다시 연다.
1557 | A telecommunications company is doing a national network rollout involving continuously changing technical requirements. To address the situation, the company has recently adopted a hybrid project life cycle. During a retrospective, some team members complain that the majority of the stories are ready to test but have not advanced because they are waiting for the project manager's approval. What should the project manager do? | Implement decision-making techniques to advance the stones | Update the issue log and review the lessons learned register for options | Implement conflict resolution to accommodate the team ' s needs | Empower the team to self-organize and make their own decisions |  | D | When team members in a hybrid project complain that stories wait for the project manager's approval to advance to testing, the project manager should empower the team to self-organize and make their own decisions. Removing approval bottlenecks accelerates flow. Implementing decision-making techniques (A) adds process rather than removing bottleneck. Updating the issue log (B) documents but does not solve. Implementing conflict resolution (C) addresses a different problem. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 통신 회사의 국가 네트워크 롤아웃에서 기술 요구사항이 지속적으로 변경된다. 팀원이 스토리가 PM 승인을 기다린다고 불만한다. PM은 무엇을 해야 하는가? | 스토리를 진전시키기 위한 의사결정 기법을 구현한다 | 이슈 로그를 업데이트하고 옵션을 위한 교훈 등록부를 검토한다 | 팀의 요구를 수용하기 위한 갈등 해결을 구현한다 | 팀이 자체 조직화하고 자체 의사결정을 하도록 권한을 부여한다 |  | D | 팀원이 스토리가 PM 승인을 기다린다고 불만할 때, PM은 팀이 자체 조직화하고 자체 의사결정을 하도록 권한을 부여해야 한다. 자율적 의사결정이 병목을 제거하고 민첩성을 높인다. 의사결정 기법(A)은 PM 중심이다. 이슈 로그(B)는 행정적이다. 갈등 해결(C)은 갈등이 아닌 병목 문제이다.
1558 | A project manager is reviewing the status of a large project with team members in different countries. Through the status review, the project manager notices that one team is consistently behind schedule and their work often needs to be corrected. What should the project manager do to improve the quality of this team's work? | Guide all team members and bring in external consultants to complete the work. | Ask a local subject matter expert (SME) to assist the team in reviewing the project requirements. | Review the issue with the project sponsor and work to reduce the scope for that team. | Evaluate the issue with the team to determine if they have the necessary skills to perform assignments. |  | D | When a team in a multi-country project is consistently behind schedule with work needing corrections, the project manager should evaluate the issue with the team to determine if they have necessary skills for their assignments. Skills assessment addresses root causes. Guiding members and bringing consultants (A) acts without diagnosis. Asking a local SME for help (B) is one solution but skips assessment. Reviewing with the sponsor to reduce scope (C) is premature. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | PM이 여러 국가의 팀원과 대규모 프로젝트 상태를 검토 중이다. 한 팀이 지속적으로 일정에 뒤처지고 작업에 수정이 필요하다. PM은 무엇을 해야 하는가? | 모든 팀원을 안내하고 외부 컨설턴트를 투입하여 작업을 완료한다 | 현지 SME에게 팀의 프로젝트 요구사항 검토를 지원하도록 요청한다 | 프로젝트 스폰서와 이슈를 검토하고 해당 팀의 범위를 줄인다 | 팀과 이슈를 평가하여 필요한 기술을 갖추고 있는지 판단한다 |  | D | 한 팀이 지속적으로 일정에 뒤처지고 수정이 필요할 때, PM은 팀과 이슈를 평가하여 필요한 기술을 갖추고 있는지 판단해야 한다. 근본 원인 분석이 적절한 대응의 기초이다. 외부 컨설턴트(A)는 성급하다. SME 지원(B)은 기술 격차 확인 전에 가정이다. 범위 축소(C)는 프로젝트 가치를 훼손한다.
1559 | A project manager is assigned to a project in a company that is transitioning to agile. Not all stakeholders believe in the project, and some stakeholders would like the entire project defined and planned out early in the project. However, the project sponsor needs a quick win to ensure the continuation of the project. What approach should the project manager use? | A predictive approach as this would please the senior stakeholders | An agile approach as this would provide working functionality earlier | A hybrid project as this will mitigate stakeholders ' concerns. | A predictive approach as this will show benefits for all stakeholders |  | C | When some stakeholders want full upfront planning while the sponsor needs a quick win in a company transitioning to agile, the project manager should use a hybrid approach. Hybrid combines predictive structure for skeptical stakeholders with agile flexibility for quick wins. A predictive approach to please stakeholders (A) does not deliver quick wins. An agile approach (B) may not satisfy stakeholders wanting upfront planning. A predictive approach claiming benefits for all (D) does not address the quick win need. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Scope | Planning | Be an Accountable Leader | Collect Requirements | Hybrid/Tailoring | 애자일 전환 중인 회사에서 PM이 프로젝트에 배정되었다. 일부 이해관계자가 애자일을 믿지 않고 스폰서는 빠른 성과가 필요하다. 어떤 접근법을 사용해야 하는가? | 선임 이해관계자를 만족시키기 위한 예측형 접근법 | 더 빨리 작동하는 기능을 제공하기 위한 애자일 접근법 | 이해관계자 우려를 완화할 하이브리드 프로젝트 | 모든 이해관계자에게 혜택을 보여줄 예측형 접근법 |  | C | 일부 이해관계자가 전면 계획을 원하고 스폰서가 빠른 성과를 필요로 할 때, 하이브리드 접근법이 적절하다. 하이브리드가 예측형 구조와 적응형 유연성을 결합하여 양측 요구를 충족한다. 예측형(A,D)은 빠른 성과를 제공하지 못한다. 순수 애자일(B)은 일부 이해관계자의 저항을 극복하지 못한다.
1560 | A project manager is working on an enterprise resource planning (ERP) initiative that contains stakeholders spanning numerous business lines. The project manager begins to identify, evaluate, and categorize the stakeholder relationships to the program. What is the purpose of this process? | Incorporate only primary stakeholders into the communications management plan. | Identify all stakeholders who can positively affect the project. | Incorporate the needs of all stakeholders into the communications management plan. | Identify all stakeholders who can negatively affect the project. |  | C | When identifying, evaluating, and categorizing stakeholder relationships in an ERP initiative spanning numerous business lines, the purpose is to incorporate the needs of all stakeholders into the communications management plan. Comprehensive understanding enables tailored engagement. Incorporating only primary stakeholders (A) excludes important groups. Identifying only positive stakeholders (B) or only negative stakeholders (D) provides incomplete analysis. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 여러 사업 부문에 걸친 ERP 이니셔티브에서 이해관계자 관계를 식별, 평가, 분류하고 있다. 이 작업의 목적은? | 주요 이해관계자만 커뮤니케이션 관리 계획에 포함한다 | 프로젝트에 긍정적 영향을 줄 수 있는 모든 이해관계자를 식별한다 | 모든 이해관계자의 요구를 커뮤니케이션 관리 계획에 포함한다 | 프로젝트에 부정적 영향을 줄 수 있는 모든 이해관계자를 식별한다 |  | C | 여러 사업 부문에 걸친 ERP에서 이해관계자 관계를 식별하고 분류하는 목적은 모든 이해관계자의 요구를 커뮤니케이션 관리 계획에 포함하는 것이다. 포괄적 이해관계자 분석이 효과적 커뮤니케이션의 기초이다. 주요 이해관계자만(A)은 불완전하다. 긍정적 영향만(B)이나 부정적 영향만(D)은 편향적이다.
1561 | A project team is performing a post-release evaluation of a product that requires detailed feedback from seven stakeholders. Six of the stakeholders have promptly provided feedback. One of them has not provided any feedback despite numerous requests from the team. What should the project manager do in this situation? | Schedule a meeting with the reluctant project stakeholder to obtain their feedback. | Explain to the sponsor why the reluctant stakeholder needs to provide feedback. | Host a meeting with the reluctant stakeholder and project team to resolve any conflict. | Meet with all seven of the project stakeholders and request all of their feedback. |  | A | When one stakeholder has not provided feedback despite repeated requests during a post-release evaluation, the project manager should schedule a meeting with the reluctant stakeholder to obtain their feedback. A direct one-on-one conversation allows the PM to understand barriers to participation and address any concerns. Explaining to the sponsor why the stakeholder needs to provide feedback (B) escalates without first attempting direct engagement. Hosting a meeting with all stakeholders present (C) may create pressure but could also make the reluctant stakeholder less comfortable. Meeting with all seven stakeholders together (D) does not specifically address the individual's reluctance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 제품 출시 후 평가에서 7명의 이해관계자 피드백이 필요하지만 한 명이 반복 요청에도 피드백을 제공하지 않는다. PM은 무엇을 해야 하는가? | 꺼리는 이해관계자와 회의를 잡아 피드백을 받는다 | 스폰서에게 꺼리는 이해관계자가 피드백을 제공해야 하는 이유를 설명한다 | 꺼리는 이해관계자와 프로젝트 팀이 참석하는 회의를 개최하여 갈등을 해결한다 | 7명 모든 이해관계자와 회의하고 모든 피드백을 요청한다 |  | A | 한 이해관계자가 반복 요청에도 피드백을 제공하지 않을 때, PM은 해당 이해관계자와 회의를 잡아 직접 피드백을 받아야 한다. 직접적이고 개인적인 접근이 참여를 촉진한다. 스폰서 설명(B)은 직접 시도 전에 에스컬레이션이다. 팀 회의(C)는 불필요한 압력이다. 전체 회의(D)는 비효율적이다.
1562 | A project manager is well informed on the industry standards of the organization and believes that they are not reflected in the project deliverables. What should the project manager review next? | Quality process | Quality management plan | Project charter | Organizational process assets (OPAs) |  | B | When the project manager believes industry standards are not reflected in project deliverables, they should review the quality management plan. The QMP outlines quality processes and standards, enabling identification of gaps between industry standards and project outputs. The quality process (A) is a component within the QMP. The project charter (C) provides high-level authorization. OPAs (D) are broad organizational references. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | PM이 조직의 산업 표준에 정통하며 프로젝트 인도물에 반영되지 않았다고 생각한다. PM은 무엇을 검토해야 하는가? | 품질 프로세스 | 품질 관리 계획 | 프로젝트 헌장 | 조직 프로세스 자산(OPA) |  | B | PM이 산업 표준이 인도물에 반영되지 않았다고 생각할 때, 품질 관리 계획을 검토해야 한다. QMP가 품질 프로세스와 표준을 정의하여 인도물이 산업 표준을 충족하도록 한다. 품질 프로세스(A)는 실행 활동이지 계획이 아니다. 헌장(C)은 상위 수준이다. OPA(D)는 조직 자산이지 프로젝트별 계획이 아니다.
1563 | A project manager is leading a project in which the product requirements have not been fully met due to several uncertainties about customer acceptance. What should the project manager do? | Gather a reduced number of approved requirements and add some extra features to fulfill the product specifications. | Stop all project activities until all requirements are set up front by the project sponsor and the key stakeholders. | Ask team members to research and collect data about the best features offered by similar products in the market. | Gather enough requirements to produce a minimum viable product (MVP) with which to evaluate customer acceptance. |  | D | When product requirements have not been fully met due to uncertainties about customer acceptance, the project manager should gather enough requirements to produce a minimum viable product (MVP) to evaluate customer acceptance. MVP development enables validation through actual customer feedback. Gathering reduced requirements and adding extra features (A) adds unvalidated scope. Stopping all activities until requirements are set (B) is overly rigid. Researching competitor features (C) does not address customer acceptance uncertainty. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 고객 수용에 대한 불확실성으로 제품 요구사항이 완전히 충족되지 못했다. PM은 무엇을 해야 하는가? | 승인된 요구사항의 축소된 수를 수집하고 일부 추가 기능을 추가하여 제품 범위를 충족한다 | 스폰서와 주요 이해관계자가 모든 요구사항을 선행 설정할 때까지 모든 활동을 중단한다 | 팀원에게 시장의 유사 제품이 제공하는 최고 기능에 대한 데이터를 조사 수집하도록 요청한다 | 고객 반응을 평가할 최소 실행 가능 제품(MVP)을 생산할 충분한 요구사항을 수집한다 |  | D | 고객 수용의 불확실성으로 요구사항이 완전히 충족되지 못할 때, PM은 MVP를 생산할 충분한 요구사항을 수집하여 고객 반응을 평가해야 한다. MVP가 최소 투자로 시장 검증을 가능하게 한다. 축소된 요구사항+추가 기능(A)은 비체계적이다. 활동 중단(B)은 비생산적이다. 경쟁 제품 조사(C)는 고객 수용을 직접 검증하지 않는다.
1564 | A key stakeholder who is frustrated by the lack of transparency of IT projects declines an invitation to participate in the new project meetings. What should the agile project manager do to engage the stakeholder in the project? | Present the project management plan to the stakeholder and reassure them that they will receive regular project updates. | Use stakeholder mapping to document the level of influence and interest for the next iteration planning meeting. | Build trust with the stakeholder by keeping project commitments and use demo sessions to gather feedback and realign goals. | Introduce the stakeholder to the project team and invite them to the next iteration review meeting with the IT team. |  | C | When a frustrated stakeholder with low trust in IT project transparency declines meeting invitations, the agile project manager should build trust by keeping project commitments and using demo sessions to gather feedback and realign goals. This creates transparency through visible, working deliverables and consistent follow-through. Presenting the project management plan (A) relies on documentation rather than demonstrated results. Stakeholder mapping (B) analyzes influence but does not build trust. Introducing the stakeholder to the team and inviting to an iteration review (D) is a step but does not address the underlying trust deficit. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | IT 프로젝트의 투명성 부족에 좌절한 주요 이해관계자가 회의 참석을 거부한다. 애자일 PM은 무엇을 해야 하는가? | 이해관계자에게 프로젝트 관리 계획을 제시하고 정기 업데이트를 보장한다 | 이해관계자 매핑을 사용하여 다음 이터레이션 계획을 위한 영향력과 관심 수준을 문서화한다 | 프로젝트 약속을 지키고 데모 세션을 사용하여 피드백을 수집함으로써 이해관계자와 신뢰를 구축한다 | 이해관계자를 팀에 소개하고 다음 이터레이션 리뷰 회의에 초대한다 |  | C | 투명성 부족에 좌절한 이해관계자가 회의를 거부할 때, PM은 프로젝트 약속을 지키고 데모 세션으로 피드백을 수집하여 신뢰를 구축해야 한다. 행동으로 신뢰를 회복하는 것이 가장 효과적이다. 계획 제시(A)는 말뿐이다. 이해관계자 매핑(B)은 분석이지 관계 구축이 아니다. 직접 초대(D)는 신뢰 없이 효과가 없다.
1565 | A project manager is assigned to a new project and is allocated with virtual team members. Later, two more members from a recently acquired company join as additional resources to the project team. In order to ensure that there are no potential misunderstandings, what should the project manager do? | Send an email update to existing team members about the addition of the new teammembers. | Update and share the guideline document dealing with team communication. | Request the transfer of the new members to another project, citing a risk of confusion. | Set up a weekly meeting with the new team members for a couple of months. |  | B | When new team members from an acquired company join a virtual project team, the project manager should update and share the guideline document dealing with team communication. Clear communication guidelines prevent misunderstandings. Sending an email announcement (A) is insufficient. Requesting transfer of new members (C) is extreme. Setting up weekly meetings only for new members (D) isolates them. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | PM이 가상 팀원으로 새 프로젝트에 배정되었다. 이후 인수된 회사에서 두 명이 추가 합류했다. PM은 무엇을 먼저 해야 하는가? | 기존 팀원에게 새 팀원 추가에 대한 이메일 업데이트를 보낸다 | 팀 커뮤니케이션 관련 가이드라인 문서를 업데이트하고 공유한다 | 혼란 리스크를 이유로 새 팀원을 다른 프로젝트로 이전 요청한다 | 몇 개월간 새 팀원과 주간 회의를 설정한다 |  | B | 인수된 회사에서 새 팀원이 가상 프로젝트 팀에 합류할 때, PM은 팀 커뮤니케이션 관련 가이드라인 문서를 업데이트하고 공유해야 한다. 명확한 커뮤니케이션 가이드라인이 원활한 통합을 보장한다. 이메일(A)은 일방적이다. 이전 요청(C)은 비협조적이다. 주간 회의(D)는 가이드라인 없이 불충분하다.
1566 | A project is ready to start, and resources are allocated. The development manager then informs the project manager that a critical resource is no longer available due to a family emergency. The development manager indicates that all other developers have been assigned to other projects, and there is no capacity for any developer to take on additional work. What should the project manager do next to fulfill this resource need? | Inform the sponsor of the situation and request an extension of the target completion date. | Meet with the sponsor to determine how to rebaseline the schedule. | Determine resource allocation options based on project priority. | Apply changes to the existing resource allocations and inform the development manager. |  | C | When a critical resource becomes unavailable with no developer capacity elsewhere, the project manager should determine resource allocation options based on project priority. Assessing all options—reallocation, schedule adjustment, external resources—enables informed decision-making. Informing the sponsor and requesting an extension (A) concedes before exploring alternatives. Meeting the sponsor to rebaseline (B) is premature. Applying changes to existing allocations (D) forces changes without analysis. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Resources | Planning | Focus on Value | Plan Resource Management | Traditional PM | 프로젝트가 시작 준비가 되었고 자원이 할당되었다. 개발 관리자가 핵심 자원이 불가용하다고 알린다. PM은 무엇을 해야 하는가? | 스폰서에게 상황을 알리고 목표 완료일 연장을 요청한다 | 스폰서와 만나 일정 재기준화 방법을 결정한다 | 프로젝트 우선순위에 기반한 자원 할당 옵션을 결정한다 | 기존 자원 할당에 변경을 적용하고 개발 관리자에게 알린다 |  | C | 핵심 자원이 불가용할 때, PM은 프로젝트 우선순위에 기반한 자원 할당 옵션을 결정해야 한다. 모든 옵션—재할당, 대체, 일정 조정—을 평가하는 것이 최적 결정을 가능하게 한다. 완료일 연장(A)은 성급하다. 재기준화(B)는 옵션 평가 후에 한다. 일방적 변경(D)은 협력적이지 않다.
1567 | A project has been reporting a declining schedule performance index (SPI) for the past four reviews. No corrective action is under development, and the project team does not seem concerned. What should the project manager do first to address the SPI trend? | Engage with the project team to create a plan that will deliver benefits on a defined and incremental basis. | Meet with the project scheduler to rebaseline the project using a more realistic schedule. | Notify the project stakeholders that the scope needs to be reduced in order to hold the costs within budget. | Contact the project sponsor to let them know you require more resources to meet the schedule. |  | B | When the SPI has been declining for four consecutive reviews with no corrective action in progress, the project manager should first meet with the project scheduler to rebaseline the project using a more realistic schedule. Understanding the root cause of the deviation and adjusting the baseline reflects the current reality, sets a realistic path forward, and enables meaningful progress measurement. Engaging the team for an incremental benefit plan (A) does not address the immediate schedule problem. Notifying stakeholders about scope reduction (C) is premature without first understanding the schedule deviation. Requesting more resources from the sponsor (D) may not solve the underlying scheduling issue. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Schedule | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트가 4회 연속 검토에서 SPI가 하락하고 있다. 시정 조치가 진행 중이지 않다. PM은 무엇을 먼저 해야 하는가? | 팀과 함께 정의되고 점진적인 기준으로 혜택을 전달할 계획을 만든다 | 프로젝트 일정 관리자와 만나 더 현실적인 일정으로 재기준화한다 | 이해관계자에게 비용 내에서 유지하기 위해 범위를 줄여야 한다고 알린다 | 프로젝트 스폰서에게 일정 충족을 위해 더 많은 자원이 필요하다고 연락한다 |  | B | SPI가 4회 연속 하락하고 시정 조치가 없을 때, PM은 일정 관리자와 만나 더 현실적인 일정으로 재기준화해야 한다. 비현실적 기준선이 지속적 하락의 근본 원인일 수 있다. 혜택 전달 계획(A)은 일정 문제를 다루지 않는다. 범위 축소(C)는 재기준화 후 검토한다. 자원 추가(D)는 분석 전에 성급하다.
1568 | A project manager works for an organization that intends to begin using agile delivery, but there is a lack of support from some business units. The project manager needs to address the lack of trust in agile. What should the project manager recommend? | Define detailed work instructions for agile project delivery. | Hire a team of contractors for agile project delivery. | Negotiate special arrangements for an agile pilot project. | Implement and establish an agile framework for the project. |  | C | When an organization wants to adopt agile but some business units lack trust in it, the project manager should recommend negotiating special arrangements for an agile pilot project. A pilot demonstrates value in a controlled way. Defining detailed work instructions (A) contradicts agile principles. Hiring agile contractors (B) does not build internal capability. Implementing a full agile framework immediately (D) risks further resistance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scaled Agile | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 조직이 애자일 도입을 시작하려 하지만 일부 사업부에서 지지가 부족하다. PM은 무엇을 권장해야 하는가? | 애자일 프로젝트 납품을 위한 상세 작업 지침을 정의한다 | 애자일 프로젝트 납품을 위한 계약자 팀을 고용한다 | 애자일 파일럿 프로젝트를 위한 특별 합의를 협상한다 | 프로젝트를 위한 애자일 프레임워크를 구현하고 수립한다 |  | C | 조직이 애자일을 도입하려 하나 일부 사업부가 신뢰하지 않을 때, PM은 애자일 파일럿 프로젝트를 위한 특별 합의를 협상해야 한다. 파일럿이 소규모로 가치를 입증하여 조직적 수용을 촉진한다. 상세 지침(A)은 애자일 원칙에 반한다. 계약자 고용(B)은 내부 역량을 구축하지 않는다. 바로 구현(D)은 저항을 무시한다.
1569 | A project is near completion but it is behind schedule. The contingency budget has already been used, although the remaining budget should be enough to complete the project. The only subject matter expert (SME) assigned to the project has been asked by their manager to solve a problem in the operations department. What should the project manager do? | Free the resource to handle the operations priority. | Ask the manager to submit a change request. | Design a negotiation strategy for this situation. | Escalate the situation to the project sponsor. |  | C | When the only SME is being pulled to operations with the project behind schedule and contingency spent, the project manager should design a negotiation strategy for the situation. Negotiation balances competing resource demands. Freeing the resource (A) abandons the project need. Asking the manager to submit a change request (B) formalizes but does not negotiate. Escalating to the sponsor (D) may be needed but negotiation should come first. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Schedule | Planning | Adopt a Holistic View | Define Activities | Traditional PM | 프로젝트가 일정 지연되고 비상 예산이 소진되었다. 유일한 SME가 운영 우선순위로 빠질 위기이다. PM은 무엇을 해야 하는가? | 운영 우선순위를 처리하도록 자원을 해제한다 | 관리자에게 변경 요청을 제출하도록 요청한다 | 이 상황에 대한 협상 전략을 설계한다 | 프로젝트 스폰서에게 상황을 에스컬레이션한다 |  | C | 유일한 SME가 운영으로 빠질 위기에서 일정 지연과 비상 예산 소진 상황일 때, PM은 협상 전략을 설계해야 한다. 협상이 프로젝트와 운영 간 균형을 맞출 최적 해결을 가능하게 한다. 자원 해제(A)는 프로젝트를 포기한다. 변경 요청(B)은 자원 문제를 해결하지 않는다. 에스컬레이션(D)은 협상 시도 후에 한다.
1570 | A project schedule risk has turned into an issue. The project manager foresees delays in project execution. What should the project manager do to resolve the issue? | Work with relevant stakeholders to determine possible solutions. | Update the risk management plan and send it to the project team. | Escalate the issue to senior leadership for resolution. | Update the schedule baseline to the new project time line. |  | A | When a schedule risk becomes an issue and delays are foreseen, the project manager should work with relevant stakeholders to determine possible solutions. Collaborative problem-solving ensures comprehensive and effective resolution. Updating the risk management plan (B) addresses documentation, not the immediate issue. Escalating to senior leadership (C) should come after stakeholder engagement. Updating the schedule baseline (D) accepts delay without seeking solutions. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 일정 리스크가 이슈로 전환되었다. PM이 실행 지연을 예상한다. PM은 무엇을 먼저 해야 하는가? | 관련 이해관계자와 협력하여 가능한 해결책을 결정한다 | 리스크 관리 계획을 업데이트하고 프로젝트 팀에 보낸다 | 해결을 위해 고위 경영진에게 이슈를 에스컬레이션한다 | 새 프로젝트 일정에 맞게 일정 기준선을 업데이트한다 |  | A | 일정 리스크가 이슈로 전환되어 지연이 예상될 때, PM은 관련 이해관계자와 협력하여 가능한 해결책을 결정해야 한다. 협력적 문제 해결이 포괄적이고 지원받는 해결책을 보장한다. 계획 업데이트(B)는 행동이 아닌 문서화이다. 에스컬레이션(C)은 협력 시도 후에 한다. 기준선 업데이트(D)는 해결책 없이 성급하다.
1571 | In a hybrid project, the customer has issued a contract that specifies the deliverables for each quarter. The customer wants to show their stakeholders a tangible outcome in the first quarter and wants to move the second milestone to the first quarter. The project manager explains to the customer that it is not feasible unless the requirements for the second milestone are changed. Which two actions should the project manager take? (Choose two) | Convince the customer to leave the second milestone in place and not change it. | Escalate the issue to upper management to resolve the problem and suggest a plan. | Ask the customer for their priorities regarding the requirements for the second milestone | Go back to the development team and discuss which second milestone requirements can be performed in the first quarter. | Tell the customer that moving the milestone has a very high impact on the cost of the project | C, D | When a customer wants to move the second milestone to the first quarter in a hybrid project, the project manager should (D) go back to the development team to discuss which requirements can be performed in Q1, and (C) ask the customer for priorities regarding the second milestone requirements. This balances feasibility with customer needs. Convincing the customer not to change (A) resists adaptation. Escalating to upper management (B) is premature. Highlighting cost impact (E) focuses only on budget. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Hybrid/Tailoring | 하이브리드 프로젝트에서 고객이 분기별 인도물을 명시한 계약을 발행했다. 고객이 2차 마일스톤을 1분기로 이동하려 한다. PM은 무엇을 해야 하는가? | 고객에게 2차 마일스톤을 그대로 유지하도록 설득한다 | 상위 경영진에게 이슈를 에스컬레이션하고 계획을 제안한다 | 2차 마일스톤 요구사항에 대한 고객의 우선순위를 묻는다 | 개발 팀에 돌아가 어떤 2차 마일스톤 요구사항을 1분기에 수행할 수 있는지 논의한다 | 마일스톤 이동이 프로젝트 비용에 매우 큰 영향이 있다고 고객에게 알린다 | C, D | 고객이 2차 마일스톤을 앞당기려 할 때, PM은 두 가지를 해야 한다: 고객에게 요구사항 우선순위를 묻고(C), 개발 팀과 어떤 요구사항을 1분기에 수행할 수 있는지 논의한다(D). 우선순위 확인과 팀 역량 평가가 실현 가능한 조정을 가능하게 한다. 설득(A)은 비협조적이다. 에스컬레이션(B)은 성급하다. 비용 영향 알림(E)만으로는 해결이 안 된다.
1572 | A project manager is performing the scrum master role for a project team of developers. At the daily standup, a couple of developers complain about the noise from a neighboring team, the performance of their laptops, and the difficulty in booking meeting rooms. What should the project manager do? | Note the impediments and escalate them to the product owner. | Assign actions to all stakeholders and oversee their implementation. | Note the impediments and work on addressing them later. | Acknowledge the impediments and facilitate their resolutions. |  | D | When team members report impediments like noise, poor laptop performance, and difficulty booking meeting rooms during a daily standup, the project manager acting as scrum master should acknowledge the impediments and facilitate their resolution. The scrum master's core responsibility is to remove obstacles that impede the team's productivity. Escalating to the product owner (A) is inappropriate—these are operational impediments, not backlog issues. Assigning actions to all stakeholders (B) is overly broad. Noting impediments for later (C) delays resolution and signals that the PM is not responsive to team needs. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 개발자 프로젝트 팀의 스크럼 마스터 역할을 수행한다. 데일리 스탠드업에서 팀원이 소음, 노트북 성능 저하, 회의실 예약 어려움을 보고한다. PM은 무엇을 해야 하는가? | 장애물을 기록하고 제품 책임자에게 에스컬레이션한다 | 모든 이해관계자에게 행동을 할당하고 구현을 감독한다 | 장애물을 기록하고 나중에 해결 작업을 한다 | 장애물을 인정하고 해결을 퍼실리테이션한다 |  | D | 팀이 데일리 스탠드업에서 장애물을 보고할 때, 스크럼 마스터인 PM은 장애물을 인정하고 해결을 퍼실리테이션해야 한다. 즉각적 인정과 퍼실리테이션이 스크럼 마스터의 핵심 역할이다. 에스컬레이션(A)은 직접 해결 전에 성급하다. 행동 할당(B)은 지시적이다. 나중에 해결(C)은 긴급성이 부족하다.
1573 | A project manager is assigned to a global project with dispersed team members. Previously, when working with remote teams, the project manager observed that team members do not tend to produce quality work. What should the project manager do to ensure the project is completed on time with quality? | Encourage the team to participate in a peer evaluation activity by the end of the project. | Introduce the use of time sheets and ask team members to review and submit them regularly. | Arrange regular team meetings for the team to update one another on the progress of their assigned tasks. | Meet with the team together and in one-on-one meetings to set clear, shared targets. |  | D | When managing a global project with dispersed teams and prior quality concerns, the project manager should meet with the team collectively and in one-on-one meetings to set clear, shared targets. Personal engagement and aligned objectives drive quality and accountability. Peer evaluation at project end (A) provides feedback too late. Introducing time sheets (B) monitors hours, not quality. Regular team update meetings (C) track progress but do not set shared performance targets. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | PM이 분산된 글로벌 프로젝트에 배정되었다. 이전에 원격 팀과 일할 때 품질 문제가 있었다. PM은 무엇을 해야 하는가? | 프로젝트 종료 시까지 팀이 동료 평가 활동에 참여하도록 격려한다 | 타임시트 사용을 도입하고 팀원에게 정기 제출하도록 요청한다 | 팀이 배정된 작업 진행 상황을 서로 업데이트하는 정기 팀 회의를 주선한다 | 팀과 전체 및 일대일 회의를 통해 명확하고 공유된 목표를 설정한다 |  | D | 분산 팀에서 이전 품질 문제가 있었을 때, PM은 팀과 전체 및 일대일 회의를 통해 명확하고 공유된 목표를 설정해야 한다. 개인적 참여와 명확한 목표가 품질과 책임감을 높인다. 동료 평가(A)는 종료 시에 늦다. 타임시트(B)는 관리적이지 품질 개선이 아니다. 정기 팀 회의(C)는 목표 설정보다 진행 보고에 치중한다.
1574 | The programming activities of a project were planned to last 35 days per module, but the programming of the first module has taken 45 days. What should the project manager do? | Ask the team to work overtime to complete the deliverable on time | Submit a change request to the project sponsor to change the schedule | Evaluate the situation and identify ways to compress the schedule without impacting baselines | Check the scope to verify if there is scope creep and get the project on schedule |  | C | When programming takes longer than planned, the PM should evaluate schedule compression options—crashing (adding resources to critical activities) or fast-tracking (performing activities in parallel)—without changing the project scope. Before resorting to overtime (which increases costs and burnout risk), scope adjustment (which may be unnecessary), or change requests (which imply the PM cannot manage within baselines), the PM should analyze root causes and identify the most efficient compression approach. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | 모듈당 35일 소요 예정이던 프로그래밍 활동이 첫 모듈에서 실제로 더 오래 걸렸다. PM은 무엇을 해야 하는가? | 팀에 인도물을 제시간에 완료하도록 초과 근무를 요청한다 | 스폰서에게 일정 변경을 위한 변경 요청을 제출한다 | 상황을 평가하고 기준선에 영향 없이 일정을 압축할 방법을 식별한다 | 범위를 확인하여 범위 확대가 있는지 검증하고 프로젝트를 일정에 맞춘다 |  | C | 프로그래밍이 계획보다 오래 걸릴 때, PM은 일정 압축 옵션—크래싱(핵심 활동에 자원 추가)이나 패스트트래킹(활동 병행 수행)—을 기준선에 영향 없이 평가해야 한다. 초과 근무(A)는 번아웃 리스크가 있다. 변경 요청(B)은 압축 옵션 평가 후에 한다. 범위 확인(D)은 원인이 범위가 아닌 추정 문제일 때 부적절하다.
1575 | A project has completed design activities ahead of schedule. Suddenly, the project manager is informed by a vendor that a deliverable may not meet the agreed delivery time frame due to a resource shortage. The internal team asked if they should continue to deliver as per the schedule. What should the project manager do? | Inform the project team that some of them will work for the vendor. | Discuss with the project team alternative options to deliver as planned. | Inform the project team that they may proceed at a more relaxed pace. | Discuss with the team the need for longer hours to minimize the impact. |  | B | When a vendor may not meet a delivery deadline due to resource shortage while the team is ahead of schedule, the project manager should discuss alternative options with the project team to deliver as planned. Collaborative problem-solving explores solutions. Sending team members to the vendor (A) is unusual. Telling the team to relax their pace (C) wastes the schedule advantage. Extending hours (D) may not address the vendor issue. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트가 설계 활동을 일정보다 앞서 완료했다. 벤더가 자원 부족으로 납기를 못 맞출 수 있다고 알린다. PM은 무엇을 해야 하는가? | 팀에 일부가 벤더를 위해 일할 것이라고 알린다 | 팀과 계획대로 납품할 대안 옵션을 논의한다 | 팀에 좀 더 여유있는 속도로 진행해도 된다고 알린다 | 팀과 영향 최소화를 위해 더 긴 근무 시간의 필요성을 논의한다 |  | B | 벤더가 납기를 못 맞출 수 있을 때, PM은 팀과 계획대로 납품할 대안 옵션을 논의해야 한다. 협력적 문제 해결이 다양한 해결책을 생성한다. 벤더 지원(A)은 프로젝트 범위를 넘는다. 여유 속도(C)는 기회를 낭비한다. 더 긴 근무(D)는 번아웃을 초래할 수 있다.
1576 | In a fixed-budget project, the team has received a prioritized list of requirements and has nearly completed the first iteration. The CEO has decided to redirect the team to focus on creating a presentation for their upcoming technology summit. The CEO is not flexible about this request. Which two actions should the project manager take? (Choose 2) | Determine a new target completion date for the project based on the redirection of the team. | Request the CEO to assign some of the functional team members to work on the presentation. | Ask the team to work overtime to make up the time lost by supporting the technology summit. | Divide the team to continue working on both the presentation and the project work. | Attempt to complete the presentation work alone so that the timeline is not negatively impacted. | B, D | When the CEO redirects half the team to prepare a technology presentation, the project manager should take two actions: request the CEO to assign some functional team members to work on the presentation instead of the project team (B) to protect the project resources, and divide the team to continue working on both the presentation and the project work (D) to maintain progress on both fronts simultaneously. Requesting functional resources preserves the project team's capacity, while dividing the team ensures neither effort stalls completely. Determining a new target completion date (A) accepts the delay without trying to mitigate it. Asking the team to work overtime (C) risks burnout and may violate labor policies. Attempting to complete the presentation alone (E) is unsustainable and not the PM's responsibility. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | 고정 예산 프로젝트에서 CEO가 팀의 절반을 기술 서밋 프레젠테이션 준비에 투입했다. PM은 무엇을 해야 하는가? | 팀 재배치에 기반한 새 목표 완료일을 결정한다 | CEO에게 기능 팀원 일부를 프레젠테이션에 배정하도록 요청한다 | 팀에 초과 근무하여 서밋 지원으로 잃은 시간을 보충하도록 요청한다 | 팀을 나누어 프레젠테이션과 프로젝트 작업을 동시에 계속한다 | 프레젠테이션 작업을 혼자 완료하여 일정에 부정적 영향이 없도록 시도한다 | B, D | CEO가 팀 절반을 프레젠테이션에 투입할 때, PM은 두 가지를 해야 한다: CEO에게 기능 팀원 배정을 요청하고(B), 팀을 나누어 프레젠테이션과 프로젝트를 동시 진행한다(D). 대체 자원과 병행 작업이 영향을 최소화한다. 완료일 변경(A)은 해결이 아니다. 초과 근무(C)는 번아웃이다. 혼자 완료(E)는 비현실적이다.
1577 | During a project's third iteration, two of the existing team members were replaced. As the project entered the next iteration, the team velocity dropped and the performance started to slip. What should the project manager do? | Discuss the decrease in productivity with human resources | Escalate the issue to the project sponsor. | Guide the team to revert back to the forming and storming stages | Convene a team building event to address key performance indicators (KPIs). |  | D | Team building activities address issues arising from team member changes—including loss of trust, communication gaps, and conflicts. These activities help align team members with project goals and expectations, and motivate achievement of key performance indicators. Team building is a core technique in the Develop Project Team process for improving team performance and project outcomes. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 3차 이터레이션에서 기존 팀원 2명이 교체되었다. 다음 이터레이션에서 생산성이 하락했다. PM은 무엇을 해야 하는가? | 인사부와 생산성 하락을 논의한다 | 프로젝트 스폰서에게 이슈를 에스컬레이션한다 | 팀을 형성기와 폭풍기로 되돌리도록 안내한다 | 핵심 성과 지표(KPI)를 다루기 위한 팀 빌딩 이벤트를 개최한다 |  | D | 팀원 교체 후 생산성이 하락할 때, PM은 KPI를 다루기 위한 팀 빌딩 이벤트를 개최해야 한다. 팀 빌딩이 신뢰 상실, 커뮤니케이션 격차, 갈등을 해결하여 팀 정렬을 돕는다. 인사부 논의(A)는 팀 문제가 아니다. 에스컬레이션(B)은 과도하다. 형성기 되돌리기(C)는 비현실적이다.
1578 | A project stakeholder has expressed concern that the established success criteria for the project are not being met. What should the project manager do next? | Update the project business case document. | Review the established project benefits tracking metrics. | Create a project benefits management plan. | Document the agreed-upon ownership of benefits realization. |  | B | The PM should first review established project benefits tracking metrics to assess current performance against expected outcomes and success criteria. This identifies gaps or deviations and determines appropriate corrective actions. Other responses—such as escalating immediately or making premature changes—don't address the root cause or respect the PM's responsibility to diagnose the situation before acting. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 이해관계자가 프로젝트의 수립된 성공 기준이 충족되지 않고 있다고 우려를 표명한다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 사업 사례 문서를 업데이트한다 | 수립된 프로젝트 혜택 추적 지표를 검토한다 | 프로젝트 혜택 관리 계획을 작성한다 | 혜택 실현의 합의된 소유권을 문서화한다 |  | B | 이해관계자가 성공 기준 미충족을 우려할 때, PM은 먼저 수립된 프로젝트 혜택 추적 지표를 검토해야 한다. 기존 지표로 현재 성과를 기대 결과와 비교하여 격차를 식별한다. 사업 사례 업데이트(A)는 검토 후에 한다. 혜택 관리 계획(C)은 이미 존재해야 한다. 소유권 문서화(D)는 측정 전에 성급하다.
1579 | In a project steering committee meeting, a few stakeholders raise concerns that the project manager's report shows that the outcome of the project is already in the market while the project is still in development. The project manager explains that the project is being delivered in sprints and involves different releases. What should the project manager do to avoid a reoccurrence of this scenario? | Invite critical stakeholders to the daily project review meetings to ensure their full engagement and involvement. | Ensure the content of the project report is clearly understood and request any necessary feedback. | Ensure that all product features are completed as per the communicated specifications before releasing to market. | Send a detailed report to each steering committee member ahead of the meeting. |  | B | When steering committee stakeholders are confused that the project's outcome is already in the market while the project is still in development due to sprint-based releases, the project manager should ensure the project report content is clearly understood and request feedback. Clear communication prevents future misunderstandings. Inviting stakeholders to daily reviews (A) is excessive. Ensuring features are completed before release (C) contradicts iterative delivery. Sending detailed reports ahead of meetings (D) adds information but may not resolve comprehension issues. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 운영 위원회에서 이해관계자가 프로젝트가 아직 개발 중인데 결과물이 이미 시장에 있다며 혼란스러워한다. PM은 무엇을 해야 하는가? | 핵심 이해관계자를 데일리 프로젝트 검토 회의에 초대하여 참여와 인식을 보장한다 | 프로젝트 보고서 내용이 명확하게 이해되도록 하고 필요한 피드백을 요청한다 | 릴리스 전 커뮤니케이션된 사양대로 모든 제품 기능이 완료되도록 한다 | 회의 전에 각 운영위원에게 상세 보고서를 보낸다 |  | B | 스프린트 기반 릴리스로 결과물이 시장에 있으면서 개발이 계속되는 것에 이해관계자가 혼란스러울 때, PM은 보고서 내용이 명확하게 이해되도록 하고 피드백을 요청해야 한다. 커뮤니케이션 명확성이 혼란을 해소한다. 데일리 회의 초대(A)는 과도하다. 사양 완료(C)는 관련이 없다. 상세 보고서(D)는 이해를 보장하지 않는다.
1580 | During project execution for an innovative product, a project team has been working hard to meet the deadlines. However, one of the team members will be leaving in 3 weeks and will be replaced with a new team member. How should the team share tacit knowledge? | Provide the new member with access to the knowledge database so all of the project documentation Is available. | Provide the new member with the project documentation repository to allow the new member to review previous lessons learned, Owner | Ask the new member to document all of the requirements so a better understanding of the project objective is acquired, | Have the team meet on a regular basis and share their experiences, challenges, and lessons learned. 1192 |  | D | When a team member is leaving in 3 weeks and tacit knowledge needs to be transferred, the team should meet regularly and share experiences, challenges, and lessons learned. Regular interaction transfers experiential knowledge effectively. Providing database access (A) shares explicit knowledge only. Providing a documentation repository (B) is similar. Asking the new member to document requirements (C) does not capture the departing member's tacit knowledge. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 혁신적 제품 실행 중 핵심 팀원이 3주 후 떠난다. 암묵지 전달이 필요하다. PM은 무엇을 해야 하는가? | 새 팀원에게 지식 데이터베이스 접근을 제공하여 프로젝트 문서가 가용하게 한다 | 새 팀원에게 프로젝트 문서 저장소를 제공하여 프로젝트 파일을 검토하게 한다 | 새 팀원에게 모든 요구사항을 문서화하도록 요청하여 프로젝트 목표를 더 잘 이해하게 한다 | 팀이 정기적으로 만나 경험, 도전, 교훈을 공유하게 한다 |  | D | 핵심 팀원이 떠나고 암묵지 전달이 필요할 때, 팀이 정기적으로 만나 경험, 도전, 교훈을 공유해야 한다. 정기적 상호작용이 문서화할 수 없는 암묵지를 효과적으로 전달한다. 데이터베이스 접근(A)은 명시적 지식만 다룬다. 문서 검토(B)도 마찬가지이다. 요구사항 문서화(C)는 암묵지 전달이 아니다.
1581 | A project manager finds that team members in an agile project are involved in several different projects due to budget constraints. What should the project manager do? | Request the project sponsor prioritize and if necessary, allocate additional budget so the team can work on a single project | Brainstorm with the team members on how they can deliver on multiple projects within the given budget | Provide an incentive plan so the team members will work more unaccounted hours on multiple projects | Instruct the team members to spread evenly across projects so mistakes will not occur within the current budget. |  | A | When team members are spread across multiple projects due to budget constraints, the project manager should request the sponsor prioritize and if necessary allocate additional budget for dedicated focus. Focused teams deliver more effectively. Brainstorming within the constraint (B) normalizes the problem. Providing incentives for extra hours (C) is unsustainable. Spreading evenly across projects (D) does not solve the underlying issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 애자일 프로젝트에서 예산 제약으로 팀원이 여러 프로젝트에 관여하고 있다. PM은 무엇을 해야 하는가? | 스폰서에게 우선순위를 정하고 필요 시 추가 예산을 할당하여 팀이 집중하도록 요청한다 | 팀원과 주어진 예산 내에서 여러 프로젝트를 납품할 방법을 브레인스토밍한다 | 팀원이 여러 프로젝트에서 더 많은 시간을 일하도록 인센티브 계획을 제공한다 | 팀원에게 프로젝트에 균등하게 분산하여 현재 프로젝트에서 실수가 없도록 지시한다 |  | A | 예산 제약으로 팀원이 여러 프로젝트에 분산될 때, PM은 스폰서에게 우선순위를 정하고 필요 시 추가 예산을 할당하도록 요청해야 한다. 전담 집중이 품질과 속도를 보장한다. 브레인스토밍(B)은 근본 문제(자원 부족)를 해결하지 않는다. 인센티브(C)는 번아웃을 초래한다. 균등 분산(D)은 모든 프로젝트에서 품질을 떨어뜨린다.
1582 | During the first project meeting with a new project manager, a stakeholder complains about not receiving periodic reports. What should the project manager do first? | Invite the stakeholder to all future project review meetings and update the project management plan | Update the project management plan with the new information and inform all of the relevant stakeholders | Add the stakeholder details into the periodic reports and update the project management plan | Meet with the stakeholder to better understand their expectations and update the stakeholder engagement plan |  | D | When a new project manager discovers that a stakeholder has been missing periodic reports, the first action should be to meet with the stakeholder to better understand their expectations and update the stakeholder engagement plan. Understanding the stakeholder's information needs, communication preferences, and level of interest enables the PM to tailor reports and communication methods effectively. Adding stakeholder details to reports (C) or inviting them to meetings (A) are possible follow-up actions but should come after understanding their expectations. Updating the project management plan generally (B) is too vague to address the specific communication gap. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 새 PM이 첫 프로젝트 회의에서 이해관계자가 정기 보고를 받지 못한다고 불만한다. PM은 무엇을 먼저 해야 하는가? | 이해관계자를 향후 모든 프로젝트 검토 회의에 초대하고 프로젝트 관리 계획을 업데이트한다 | 새 정보로 프로젝트 관리 계획을 업데이트하고 모든 관련 이해관계자에게 알린다 | 이해관계자 세부사항을 정기 보고에 추가하고 프로젝트 관리 계획을 업데이트한다 | 이해관계자와 만나 기대를 더 잘 이해하고 이해관계자 참여 계획을 업데이트한다 |  | D | 이해관계자가 정기 보고를 못 받는다고 불만할 때, PM은 먼저 이해관계자와 만나 기대를 더 잘 이해하고 이해관계자 참여 계획을 업데이트해야 한다. 기대 이해가 적절한 대응의 기초이다. 회의 초대(A)는 요구 파악 전에 성급하다. 계획 업데이트(B,C)는 이해관계자 요구 이해 후에 한다.
1583 | The project velocity has recently slipped, and a decision was made to skip testing to increase the momentum and bring the project back on track. What will the project manager need to focus on as a result of this decision? | Decreased efficiency | Increased bum rate | Increased technical debt | Increased cost |  | C | When a decision is made to skip testing to increase project momentum, the project manager will need to focus on increased technical debt. Skipping testing creates deferred quality issues that accumulate as technical debt. Decreased efficiency (A) is a symptom, not the primary concern. Increased burn rate (B) relates to resource spending. Increased cost (D) is a consequence but technical debt is the direct result. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | XP (Extreme Programming) | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 속도가 하락하여 모멘텀을 높이기 위해 테스트를 건너뛰기로 결정했다. PM이 집중해야 할 것은? | 효율성 감소 | 소진율 증가 | 기술 부채 증가 | 비용 증가 |  | C | 테스트를 건너뛰어 프로젝트 모멘텀을 높이면, PM은 기술 부채 증가에 집중해야 한다. 테스트 건너뛰기는 이연된 품질 문제를 만들어 나중에 더 큰 수정 비용이 발생한다. 효율성 감소(A)는 즉각적이지 않다. 소진율(B)은 관련이 적다. 비용 증가(D)는 기술 부채의 결과이지 직접적 우려가 아니다.
1584 | While monitoring a project at a work site, the project manager notices that the site team's work breaks have increased by a few minutes every week. How should the project manager approach this? | Dismiss some of the workers for failing to adhere to the break policy. | Have a meeting with the team to discuss the issue and propose solutions. | Reduce payment to the workers due to their extended breaks. | Issue a formal written warning to all hourly workers for their break tardiness. |  | B | When site workers' break times gradually increase, the project manager should have a meeting with the team to discuss the issue and propose solutions. Collaborative dialogue addresses root causes. Dismissing workers (A) is disproportionate. Reducing payment (C) is punitive without understanding. Issuing formal warnings (D) is adversarial before investigation. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 작업 현장에서 팀의 휴식 시간이 점차 증가한 것을 발견했다. PM은 무엇을 해야 하는가? | 휴식 정책을 준수하지 않는 근로자 일부를 해고한다 | 팀과 회의하여 이슈를 논의하고 해결책을 제안한다 | 연장된 휴식으로 인해 근로자에게 급여를 줄인다 | 모든 시간제 근로자에게 휴식 지각에 대한 공식 서면 경고를 발행한다 |  | B | 근로자의 휴식 시간이 점차 증가할 때, PM은 팀과 회의하여 이슈를 논의하고 해결책을 제안해야 한다. 협력적 대화가 근본 원인을 다룬다. 해고(A)는 과도하다. 급여 감소(C)는 징벌적이다. 서면 경고(D)는 대화 시도 전에 가혹하다.
1585 | During the implementation phase of a construction project, the customer asked a key subcontractor to deliver a work package ahead of time. The subcontractor was not prepared for it and asked the project manager for additional budget. What should the project manager do first? | Revise the project scope accordingly to cope with the budget changes | Submit a change request to accelerate the project as requested | Ask upper management for more funds and update the project budget | Update the risk register and project log. and manage the budget closely. |  | B | When a customer asks a subcontractor to deliver a work package early and the subcontractor requests additional budget, the project manager should first submit a change request to accelerate the project as requested. Change control formalizes the scope/schedule change. Revising project scope (A) bypasses governance. Asking management for more funds (C) skips the change process. Updating the risk register and managing budget (D) is passive. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 건설 프로젝트 구현 단계에서 고객이 하도급업체에 작업 패키지를 일찍 납품하도록 요청했다. 하도급업체가 추가 예산을 요청한다. PM은 무엇을 해야 하는가? | 예산 변경에 대응하기 위해 프로젝트 범위를 수정한다 | 요청대로 프로젝트를 가속하기 위한 변경 요청을 제출한다 | 상위 경영진에 더 많은 자금을 요청하고 프로젝트 예산을 업데이트한다 | 리스크 등록부와 프로젝트 로그를 업데이트하고 예산을 면밀히 관리한다 |  | B | 고객이 일찍 납품을 요청하고 하도급업체가 추가 예산을 요청할 때, PM은 먼저 프로젝트 가속을 위한 변경 요청을 제출해야 한다. 공식 변경 관리가 승인과 영향 분석을 보장한다. 범위 수정(A)은 일정 변경이지 범위가 아니다. 자금 요청(C)은 변경 승인 후에 한다. 리스크/로그 업데이트(D)는 문서화이지 조치가 아니다.
1586 | A project manager is leading a product development project that requires high involvement from several stakeholders. What should the project manager do to ensure this involvement? | Engage the sponsor on the behavior of stakeholders. | Conduct weekly update meetings with stakeholders. | Distribute weekly status emails to stakeholders. | Evaluate the engagement needs of stakeholders. |  | D | To ensure high stakeholder involvement in a product development project, the project manager should evaluate the engagement needs of stakeholders. This assessment considers each stakeholder's expectations, interests, influence, and preferred engagement methods, enabling tailored communication and collaboration strategies throughout the project lifecycle. Engaging the sponsor on stakeholder behavior (A) escalates rather than manages. Weekly update meetings (B) apply a one-size-fits-all approach. Weekly status emails (C) are passive and may not meet diverse engagement needs. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 여러 이해관계자의 높은 참여가 필요한 제품 개발 프로젝트를 이끌고 있다. PM은 무엇을 먼저 해야 하는가? | 스폰서에게 이해관계자의 행동에 대해 참여시킨다 | 이해관계자와 주간 업데이트 회의를 실시한다 | 이해관계자에게 주간 상태 이메일을 배포한다 | 이해관계자의 참여 요구를 평가한다 |  | D | 높은 이해관계자 참여가 필요할 때, PM은 먼저 이해관계자의 참여 요구를 평가해야 한다. 각 이해관계자의 기대, 관심, 선호하는 참여 수준을 이해하는 것이 효과적 참여 전략의 기초이다. 스폰서 참여(A)는 분석 후에 한다. 주간 회의(B)나 이메일(C)은 요구 평가 없이 일률적이다.
1587 | A project manager is assigned to a multiyear project. During project execution, the customer delegates a new representative who contacts the project manager directly with a concern about their participation in status meetings. The representative wants to contact team members directly. What should the project manager do next? | Meet with the new representative to determine their understanding of the project and address their concerns. | Reach out to the customer directly for assistance in incorporating the new representative into the project management plan. | Send the new representative the approved project management and communications management plans. | Meet with the project sponsor to discuss how to incorporate the new representative in the project. |  | A | When a new customer representative contacts the project manager with concerns about participation and wants direct team access, the project manager should meet with the new representative to determine their understanding of the project and address their concerns. Direct engagement establishes rapport, clarifies the project context, and integrates the representative into existing communication processes. Reaching out to the customer directly (B) bypasses the new representative. Sending project management plans (C) is passive and does not address specific concerns. Meeting with the sponsor to discuss incorporation (D) escalates unnecessarily before direct engagement. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 다년 프로젝트 실행 중 고객이 새 대표를 임명했다. 새 대표가 참여에 우려가 있고 팀에 직접 접근을 원한다. PM은 무엇을 해야 하는가? | 새 대표와 만나 프로젝트 이해도를 파악하고 우려를 다룬다 | 고객에게 직접 연락하여 새 대표를 프로젝트에 편입시키는 데 지원을 요청한다 | 새 대표에게 승인된 프로젝트 관리 및 커뮤니케이션 관리 계획을 보낸다 | 스폰서와 만나 새 대표를 프로젝트에 어떻게 편입시킬지 논의한다 |  | A | 새 고객 대표가 참여 우려가 있을 때, PM은 먼저 새 대표와 만나 프로젝트 이해도를 파악하고 우려를 다뤄야 한다. 직접적 소통이 관계와 이해를 구축한다. 고객 연락(B)은 간접적이다. 문서 전송(C)은 일방적이다. 스폰서 논의(D)는 직접 만남 후에 한다.
1588 | During project planning, a development team is assigned an agreed-upon work package to determine the appropriate pattern for integrating a new service with a legacy system. The lead developer has requested a meeting with the project manager and is looking for direction as to which technology to select. How should the project manager help guide the lead developer? | Reassign this work package to another area given the lead developer ' s concerns, | Listen to the concerns and suggest that the lead developer and the team be empowered to recommend the best approach. | Advise the lead developer and team to consult with the project architect and for their development team leader. | Direct the lead developer to conduct a weighted evaluation of all products and solutions. |  | B | When a lead developer seeks direction on technology selection for a work package, the project manager should listen to concerns and suggest that the lead developer and team be empowered to recommend the best approach. Empowerment fosters ownership and leverages team expertise. Reassigning the work package (A) avoids the decision. Consulting the project architect (C) may help but should come from team initiative. Directing a weighted evaluation (D) is prescriptive. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Integration & General PM | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 계획 중 개발 팀이 기술 선택을 위한 작업 패키지를 배정받았다. 리드 개발자가 PM에게 기술 평가 방향을 요청한다. PM은 무엇을 해야 하는가? | 리드 개발자의 우려를 고려하여 이 작업 패키지를 다른 영역에 재배정한다 | 우려를 듣고 리드 개발자와 팀이 최적 솔루션을 권장하도록 권한을 부여한다 | 리드 개발자와 팀에게 프로젝트 아키텍트와 상담하도록 조언한다 | 리드 개발자에게 모든 제품과 솔루션의 가중 평가를 수행하도록 지시한다 |  | B | 리드 개발자가 기술 선택 방향을 요청할 때, PM은 우려를 듣고 팀이 최적 솔루션을 권장하도록 권한을 부여해야 한다. 팀 자율성이 전문성과 주인의식을 활용한다. 재배정(A)은 팀 역량을 무시한다. 아키텍트 상담(C)은 팀 의사결정을 다른 곳으로 돌린다. 지시(D)는 자율성을 제한한다.
1589 | A sponsor and project manager found out that a vendor in a different time zone has delayed the delivery of its products and needs close supervision until the project gets back on track. The only option is to relocate three key members of the project team to spend 6 months abroad. What should the project manager do next? | Communicate individually with the affected team members to negotiate the decision and confirm their willingness to relocate | Communicate the decision to the human resources (HR) department so they can direct the project team members to be sent abroad | Communicate to the affected team members ' manager and schedule a meeting to discuss the details of this assignment | Communicate to the whole team the decision to relocate team members abroad and the implications of doing so in the next project status meeting |  | A | When three key team members must relocate abroad for six months to supervise a vendor, the project manager should communicate individually with the affected team members to negotiate the decision and confirm their willingness to relocate. Respectful, direct communication considers personal and professional impacts. Communicating to HR (B) bypasses the individuals. Communicating to their manager (C) is indirect. Announcing to the whole team (D) creates unnecessary disruption before individual agreements are reached. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 벤더 납품 지연으로 핵심 팀원 3명이 6개월간 해외 파견되어야 한다. PM은 어떻게 소통해야 하는가? | 영향을 받는 팀원과 개별적으로 소통하여 결정을 협상하고 참여를 확인한다 | 인사부에 결정을 소통하여 팀을 해외 파견하도록 지시하게 한다 | 영향을 받는 팀원의 관리자에게 소통하고 결정 세부사항을 논의할 회의를 잡는다 | 전체 팀에게 팀원 해외 이전 결정과 미납품 시 결과를 소통한다 |  | A | 핵심 팀원이 해외 파견되어야 할 때, PM은 영향을 받는 팀원과 개별적으로 소통하여 결정을 협상하고 참여를 확인해야 한다. 개인적이고 존중하는 접근이 인간적이며 참여를 보장한다. 인사부 지시(B)는 비인간적이다. 관리자 소통(C)은 간접적이다. 전체 팀 소통(D)은 부적절하다.
1590 | A company is engaged in a transformation journey, and the project manager for this endeavor is new to this project. During one of the project status update meetings, a key stakeholder, the project manager's functional manager, is dissatisfied with the work in progress and points to the project manager. What should the project manager do? | Show the functional manager that the progress is on time based on the schedule. | Schedule a one-on-one meeting with the functional manager to prove the project is on time | Listen carefully and show understanding of the growing needs of the functional manager. | Admit that the functional manager is right and promise to rectify the situation immediately. |  | C | When a key stakeholder and functional manager expresses dissatisfaction with work in progress during a status meeting, the project manager should listen carefully and show understanding of the growing needs. Active listening and empathy enable constructive resolution. Showing that progress is on time (A) is defensive. Scheduling a one-on-one to prove timeliness (B) is also defensive. Admitting fault and promising to fix (D) is premature without understanding. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 변혁 여정 중인 회사에서 새 PM이 상태 회의에서 기능 관리자가 진행 중인 작업에 불만을 표명한다. PM은 무엇을 해야 하는가? | 기능 관리자에게 일정에 맞게 진행 중임을 보여준다 | 기능 관리자와 일대일 회의를 잡아 프로젝트가 일정에 맞음을 증명한다 | 주의 깊게 듣고 기능 관리자의 증가하는 요구를 이해한다 | 기능 관리자가 맞다고 인정하고 즉시 상황을 시정하겠다고 약속한다 |  | C | 기능 관리자가 진행 중 작업에 불만을 표명할 때, PM은 주의 깊게 듣고 증가하는 요구를 이해해야 한다. 능동적 경청과 공감이 갈등 해소와 협력 관계의 기초이다. 일정 증명(A,B)은 방어적이다. 즉시 인정(D)은 분석 없이 양보한다.
1591 | During a product demo with key stakeholders, the team identifies that one of the functionalities failed to perform as expected. What should the project manager have the project team do first to address the issue? | Perform a root cause analysis | Submit a change request for corrective action. | Review the product specification requirements. | Update the issue log and document the change |  | A | When a functionality fails during a product demo, the project team should first perform a root cause analysis. RCA identifies the underlying cause of the failure and prevents recurrence, enabling targeted corrective action. Submitting a change request (B) is premature without understanding the cause. Reviewing product specifications (C) verifies expectations but does not diagnose the failure. Updating the issue log (D) documents but does not solve the problem. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 핵심 이해관계자와의 제품 데모 중 기능 하나가 예상대로 작동하지 않았다. 프로젝트 팀은 무엇을 먼저 해야 하는가? | 근본 원인 분석을 수행한다 | 시정 조치를 위한 변경 요청을 제출한다 | 제품 사양 요구사항을 검토한다 | 이슈 로그를 업데이트하고 변경을 문서화한다 |  | A | 제품 데모 중 기능이 실패할 때, 팀은 먼저 근본 원인 분석을 수행해야 한다. RCA가 실패의 근본 원인을 식별하여 재발을 방지하고 목표 수정을 가능하게 한다. 변경 요청(B)은 원인 파악 후에 한다. 사양 검토(C)는 원인이 사양 문제인지 확인 전에 한다. 이슈 로그(D)는 문서화이지 해결이 아니다.
1592 | A project manager is managing a few innovation projects with a high level of uncertainty. The project manager is experiencing challenges with the large number of change requests issued due to the nature of the project. What should the project manager do? | Add a fixed number of change requests allowed by the client on the project baseline. | Request sponsor approval for all change requests to reduce the number of changes. | Initiate the number of iterations to reduce the number of change requests. | Reduce the number of approvers required to implement a change request. |  | C | When managing innovation projects with high uncertainty and excessive change requests, the project manager should initiate more iterations to reduce the number of change requests. Shorter iterations allow frequent reassessment and adaptation. Adding a fixed number of allowed changes (A) is rigid. Requiring sponsor approval for all changes (B) adds bureaucracy. Reducing approvers (D) weakens governance. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Embed Quality | Determine Budget | Traditional PM | PM이 높은 불확실성의 혁신 프로젝트에서 과도한 변경 요청을 경험한다. PM은 무엇을 해야 하는가? | 고객이 프로젝트 기준선에 허용하는 고정 수의 변경 요청을 추가한다 | 스폰서에게 모든 변경 요청 승인을 요청하여 변경 수를 줄인다 | 이터레이션 수를 늘려 변경 요청 수를 줄인다 | 변경 요청 구현에 필요한 승인자 수를 줄인다 |  | C | 높은 불확실성의 혁신 프로젝트에서 과도한 변경 요청 시, PM은 이터레이션 수를 늘려야 한다. 짧은 이터레이션이 더 빈번한 피드백과 적응을 가능하게 하여 공식 변경 요청의 필요를 줄인다. 고정 변경 수(A)는 비유연적이다. 스폰서 승인(B)은 관료적이다. 승인자 감소(D)는 거버넌스를 약화시킨다.
1593 | A project manager who is new to an organization observes that an approaching deadline is likely to be missed because there have been some delays on the project due to a lack of resources. What should the project manager do next? | Organize a team meeting to discuss the next course of action | Escalate the issue to the sponsor and debrief them about the situation | Review the risk management plan to identify the response strategy | Review the milestone list to determine which tasks can be fast-tracked |  | B | When a deadline is likely to be missed due to resource shortages, the project manager should escalate the issue to the sponsor and debrief them about the situation. The sponsor has the authority and influence to help resolve the resource problem and negotiate revised timelines if needed. Transparent communication demonstrates professionalism and accountability. Organizing a team meeting (A) may help internally but cannot resolve organizational resource constraints. Reviewing the risk management plan (C) identifies documented responses but may not address a new resource gap. Reviewing the milestone list for fast-tracking (D) is a schedule technique that does not address the root cause. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Engage Stakeholders | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | PM이 자원 부족으로 마감일을 놓칠 가능성이 있음을 관찰한다. PM은 무엇을 먼저 해야 하는가? | 다음 행동 과정을 논의하기 위해 팀 회의를 조직한다 | 스폰서에게 이슈를 에스컬레이션하고 상황을 브리핑한다 | 리스크 관리 계획을 검토하여 대응 전략을 식별한다 | 마일스톤 목록을 검토하여 패스트트래킹할 작업을 결정한다 |  | B | 자원 부족으로 마감일을 놓칠 가능성이 있을 때, PM은 스폰서에게 이슈를 에스컬레이션하고 상황을 브리핑해야 한다. 스폰서가 자원을 확보하고 조직적 지원을 제공할 권한과 영향력이 있다. 팀 회의(A)는 유용하지만 자원 부족은 팀 수준에서 해결이 어렵다. 리스크 계획(C)은 보완적이다. 패스트트래킹(D)은 자원 문제를 해결하지 않는다.
1594 | The project charter was just approved and the project sponsor has given permission to proceed with the project. The program manager has confirmed that one of the requested key resources is also needed on another project at the same time. This will affect project delivery. What should the project manager do? | Talk to the program manager and about prioritizing this project over other projects so the key resources are available | Speak with the client to see if the project delivery deadline can be delayed due to resource availability | Have a meeting with project manager of the other project to find a resource optimization solution that works for both projects | Pay overtime to key resource to get the work done outside of working hours |  | C | When a key resource is needed simultaneously on another project after charter approval, the project manager should meet with the other project's manager to find a resource optimization solution for both projects. Collaborative optimization minimizes impact across projects. Talking to the program manager about prioritizing (A) is one-sided. Speaking to the client about delay (B) reduces client confidence. Paying overtime (D) is unsustainable and may not resolve the conflict. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 헌장이 승인되었으나 핵심 자원이 다른 프로젝트에서 동시에 필요하다. PM은 무엇을 해야 하는가? | 프로그램 관리자와 대화하여 이 프로젝트를 우선시하여 핵심 자원을 확보한다 | 고객에게 자원 가용성 문제로 납기 연기가 가능한지 확인한다 | 다른 프로젝트의 PM과 회의하여 양 프로젝트를 위한 자원 최적화 해결책을 찾는다 | 핵심 자원에게 근무 시간 외 초과 근무를 하도록 비용을 지불한다 |  | C | 핵심 자원이 다른 프로젝트에도 필요할 때, PM은 다른 프로젝트의 PM과 만나 양 프로젝트를 위한 자원 최적화 해결책을 찾아야 한다. 협력적 접근이 양측에 최적 결과를 제공한다. 우선순위 설정(A)은 다른 프로젝트에 영향을 준다. 납기 연기(B)는 성급하다. 초과 근무(D)는 번아웃을 초래한다.
1595 | A project is starting with a team that is located all over the world. None of the team members have worked together before. The project goal is ambitious with an aggressive timeline. What should the project manager do? | Facilitate a virtual session with the team to start planning as soon as possible. | Schedule quarterly in-person meetings to enhance the team ' s relationships. | Ask for financial support to set up a physical meeting for the team. | Create a virtual room for the team to facilitate their collaboration. |  | A | With a globally distributed team that has never worked together, facing an ambitious goal with an aggressive timeline, the project manager should facilitate a virtual session to start planning as soon as possible. This initiates momentum, establishes team alignment, and begins building rapport without waiting for costly or time-consuming in-person meetings. Scheduling quarterly in-person meetings (B) delays team formation. Asking for funding for a physical meeting (C) takes time to arrange. Creating a virtual collaboration room (D) is a tool but not a direct facilitation action for team planning. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Be an Accountable Leader | Develop Team | Traditional PM | 전 세계에 분산된 팀으로 프로젝트가 시작된다. 팀원 중 누구도 함께 일한 적이 없다. 야심찬 목표와 촉박한 일정이 있다. PM은 무엇을 먼저 해야 하는가? | 가능한 빨리 계획을 시작하기 위해 팀과 가상 세션을 퍼실리테이션한다 | 팀 관계를 향상시키기 위해 분기별 대면 회의를 잡는다 | 팀을 위한 대면 회의 설정을 위한 재정 지원을 요청한다 | 팀의 협력을 촉진하기 위한 가상 룸을 만든다 |  | A | 분산 팀이 처음 함께 일하고 촉박한 일정이 있을 때, PM은 가능한 빨리 계획을 시작하기 위해 가상 세션을 퍼실리테이션해야 한다. 즉각적 계획 시작이 모멘텀을 만들고 팀을 정렬한다. 분기별 대면(B)은 너무 늦다. 재정 지원(C)은 시간이 걸린다. 가상 룸(D)은 도구이지 계획 활동이 아니다.
1596 | In a global project, the main definitions were developed in country A, and the delivery of the project will be completed in phases in countries B, C, and D. Country B discovers that one of the legal requirements was not addressed. What should the project manager have done to avoid this situation? | Identified the regulatory differences among the countries. | Managed risk mitigation strategies specific to each country. | Selected countries that had similar regulatory requirements. | Asked procurement to assign resources located in each country. |  | A | When country B discovers a missed legal requirement in a global project planned in country A, the project manager should have identified the regulatory differences among the countries. Comprehensive regulatory analysis prevents compliance gaps. Managing country-specific risk mitigation (B) is reactive. Selecting countries with similar regulations (C) is impractical. Assigning local resources via procurement (D) does not ensure regulatory compliance. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 글로벌 프로젝트에서 주요 정의가 국가 A에서 개발되었고 국가 B에서 납품된다. 국가 B에서 법적 요구사항 누락이 발견되었다. PM이 초기에 무엇을 했어야 하는가? | 국가 간 규제 차이를 식별했다 | 각 국가에 특화된 리스크 완화 전략을 관리했다 | 유사한 규제 요구사항을 가진 국가를 선택했다 | 조달에 각 국가에 위치한 자원을 배정하도록 요청했다 |  | A | 글로벌 프로젝트에서 국가 B가 법적 요구사항 누락을 발견할 때, PM은 초기에 국가 간 규제 차이를 식별했어야 한다. 포괄적 규제 검토가 법적 준수를 보장한다. 리스크 완화(B)는 식별 후에 한다. 유사 국가 선택(C)은 비현실적이다. 현지 자원(D)은 규제 분석을 보장하지 않는다.
1597 | A project manager has been informed by a vendor that a shipment with supplies needed for the project will be delayed by six weeks. What should the project manager do first? | Treat the risk as an issue and launch the risk response plan | Ask the procurement manager to resolve the issue with the vendor | Find another vendor to deliver the required supplies on time | Document this as a risk and define a risk response plan |  | A | When a vendor confirms a six-week supply delay, the project manager should first treat the risk as an issue and launch the risk response plan. The risk has materialized and requires immediate action per the planned response. Asking procurement to resolve (B) delegates without PM oversight. Finding another vendor (C) may be part of the response but should follow the plan. Documenting as a risk (D) is too late since the event has already occurred. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 벤더가 프로젝트에 필요한 공급품이 6주 지연된다고 알린다. PM은 무엇을 먼저 해야 하는가? | 리스크를 이슈로 처리하고 리스크 대응 계획을 실행한다 | 조달 관리자에게 벤더와의 이슈를 해결하도록 요청한다 | 필요한 공급품을 제시간에 납품할 다른 벤더를 찾는다 | 이것을 리스크로 문서화하고 리스크 대응 계획을 정의한다 |  | A | 벤더가 6주 공급 지연을 확인할 때, PM은 리스크를 이슈로 처리하고 리스크 대응 계획을 실행해야 한다. 리스크가 실현되어 즉각 행동이 필요하다. 조달 관리자(B)는 PM의 직접 행동이 아니다. 다른 벤더(C)는 대응 계획의 일부일 수 있다. 리스크 문서화(D)는 이미 이슈가 되었으므로 부적절하다.
1598 | A project had scheduling delays, which necessitated the team to work overtime to meet critical milestones. This led to some misunderstandings among team members. The project sponsor has allocated a monetary award. How should the project manager utilize the award? | Allocate the reward to the team leaders to spend on the team as they see fit. | Meet with the team members and ask them how to spend the reward. | Arrange a luncheon for all team members and include team-building sessions. | Draft a points system to allocate a portion of the money for each resource. |  | C | When a monetary award is allocated after overtime and team misunderstandings, the project manager should arrange a luncheon for all team members and include team-building sessions. This addresses both reward and team cohesion, repairing relationships strained by overtime. Allocating to team leaders (A) is indirect. Asking the team how to spend it (B) may lead to disagreement. A points system (D) is transactional and does not foster team unity. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | Schedule Management | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 일정 지연으로 팀이 초과 근무하여 오해와 갈등이 발생했다. 금전적 보상이 할당되었다. PM은 어떻게 보상을 사용해야 하는가? | 팀 리더에게 보상을 할당하여 적절히 사용하도록 한다 | 팀원과 만나 보상 사용 방법을 묻는다 | 모든 팀원을 위한 오찬을 마련하고 팀 빌딩 세션을 포함한다 | 포인트 시스템을 만들어 각 자원에 돈의 일부를 할당한다 |  | C | 초과 근무와 팀 오해 후 금전적 보상이 있을 때, PM은 모든 팀원을 위한 오찬을 마련하고 팀 빌딩 세션을 포함해야 한다. 팀 활동이 인정과 관계 회복을 동시에 다룬다. 리더에게 위임(A)은 PM의 책임을 방기한다. 팀원에게 물어보기(B)는 방향이 부족하다. 포인트 시스템(D)은 개인화되지만 팀 결속을 다루지 않는다.
1599 | A new project manager has been assigned to a project that is in danger of failing. The stakeholders do not know the project status nor do they know what benefits will be delivered by the project. How can the project manager communicate these benefits to the stakeholders? | Update the deliverables map against the agreed-upon project requirements | Rebaseline the project schedule to show the current status of the project. | Perform a project cost-benefit analysis for the stakeholders | Create a benefits management plan mapped to the organization ' s strategic objectives |  | D | When stakeholders are unaware of project status or expected benefits on a failing project, the project manager should create a benefits management plan mapped to the organization's strategic objectives. The plan communicates how and when benefits will be delivered. Updating the deliverables map (A) tracks deliverables, not benefits. Rebaselining the schedule (B) shows current status but not benefits. Performing a cost-benefit analysis (C) evaluates the project but does not communicate ongoing benefits. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Stakeholder & Communication Mgmt | Business Environment | Define and Establish Governance | Stakeholders | Monitoring & Controlling | Focus on Value | Monitor Stakeholder Engagement | Traditional PM | 실패 위험에 처한 프로젝트에 새 PM이 배정되었다. 이해관계자가 프로젝트 상태나 기대 혜택을 모른다. PM은 무엇을 해야 하는가? | 합의된 프로젝트 요구사항에 대한 인도물 맵을 업데이트한다 | 프로젝트 일정을 재기준화하여 현재 상태를 보여준다 | 이해관계자를 위한 프로젝트 비용-편익 분석을 수행한다 | 조직의 전략적 목표에 매핑된 혜택 관리 계획을 작성한다 |  | D | 이해관계자가 프로젝트 상태나 기대 혜택을 모를 때, PM은 조직의 전략적 목표에 매핑된 혜택 관리 계획을 작성해야 한다. 전략적 정렬이 프로젝트 가치를 명확히 한다. 인도물 맵(A)은 부분적이다. 재기준화(B)는 혜택을 다루지 않는다. 비용-편익 분석(C)은 유용하지만 전략적 매핑이 더 포괄적이다.
1600 | After the project charter's approval, the project manager needs to work on detailed project requirements, constraints, and assumptions with stakeholders. However, not all of the stakeholders are immediately available for a meeting in the short term. What should the project manager do in order to gather the information needed from stakeholders? | Escalate to the project sponsor that not all stakeholders are available for a meeting | Email, call, or meet with each stakeholder separately to obtain their input | Meet with the project management team to build the project management plan before consulting stakeholders | Conduct a meeting to build the project management plan with the stakeholders who are available |  | B | The PM should collect requirements from all stakeholders using appropriate techniques—interviews, focus groups, surveys, and other methods. If some stakeholders cannot attend meetings, the PM should use alternative communication channels to gather their input. Documenting stakeholder requirements, expectations, and assumptions in the requirements traceability matrix ensures completeness, accuracy, and alignment with stakeholder needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 프로젝트 헌장 승인 후 PM이 상세 요구사항, 제약, 가정을 작업해야 한다. 일부 이해관계자가 회의에 참석할 수 없다. PM은 무엇을 해야 하는가? | 모든 이해관계자가 회의에 참석할 수 없다고 스폰서에게 에스컬레이션한다 | 각 이해관계자와 이메일, 전화, 개별 면담으로 의견을 수집한다 | 프로젝트 관리 팀과 만나 이해관계자 상담 전에 프로젝트 관리 계획을 수립한다 | 참석 가능한 이해관계자와 회의하여 프로젝트 관리 계획을 수립한다 |  | B | 일부 이해관계자가 회의에 참석할 수 없을 때, PM은 각 이해관계자와 이메일, 전화, 개별 면담으로 의견을 수집해야 한다. 다양한 방법으로 모든 이해관계자의 입력을 확보하는 것이 중요하다. 에스컬레이션(A)은 과도하다. 팀만으로 계획(C)은 이해관계자 입력이 부족하다. 참석자만 회의(D)는 불완전한 입력이다.
1601 | A high-tech borehole project was initiated with the goal of providing water for a rural community of 1,500 villagers located in an arid region. The project was completed with a cost performance index (CPI) of 1.09 and a schedule performance index (SPI) of 0.93. Six months after its completion, it is determined that the villagers could not access water. What caused this situation to occur? | The project was delivered above budget | The risk analysis was inadequate | The requirements gathering was inadequate | The project was completed behind schedule |  | C | When a borehole project completed under budget (CPI 1.09) and slightly behind schedule (SPI 0.93) but villagers cannot access water six months later, the cause is inadequate requirements gathering. Project metrics showed acceptable performance, but failing to understand end-user needs and sustainability requirements led to a non-functional outcome. Being above budget (A) contradicts the CPI data. Inadequate risk analysis (B) may contribute but is not the primary cause. Being behind schedule (D) does not explain the inability to access water. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Finance | Planning | Integrate Sustainability | Plan Finance Management | Sustainability | 시추공 프로젝트가 예산 미만(CPI 1.09), 약간 일정 지연(SPI 0.93)으로 완료되었다. 6개월 후 마을 주민이 물에 접근할 수 없다. 원인은? | 프로젝트가 예산 초과로 납품되었다 | 리스크 분석이 부적절했다 | 요구사항 수집이 부적절했다 | 프로젝트가 일정 지연으로 완료되었다 |  | C | 시추공 프로젝트가 예산 미만 및 약간 일정 지연으로 완료되었지만 주민이 물에 접근할 수 없을 때, 원인은 부적절한 요구사항 수집이다. 프로젝트가 기술적으로 완료되었지만 실제 요구(물 접근)가 충족되지 않았다. 예산 초과(A)는 CPI>1로 틀리다. 리스크 분석(B)은 요구사항 누락과 직접 관련이 없다. 일정 지연(D)은 소폭이며 주 원인이 아니다.
1602 | A project manager is working on a software development project for an oil and gas client using an agile approach. The project manager is having difficulty preparing the schedule because the project has various unknowns. Which scheduling method should the project manager use to develop the schedule? | Iterative scheduling | Analogous scheduling | Parametric scheduling | Three-point scheduling |  | A | When an agile software development project has various unknowns making schedule preparation difficult, the project manager should use iterative scheduling. Iterative scheduling breaks work into sprints with cyclical planning, accommodating changes and unknowns. Analogous scheduling (B) uses past project data, less suitable for unknowns. Parametric scheduling (C) requires historical parameters. Three-point scheduling (D) estimates durations but does not address structural uncertainty. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 석유가스 고객을 위한 애자일 소프트웨어 개발에서 다양한 미지수로 일정 준비가 어렵다. PM은 어떤 일정 기법을 사용해야 하는가? | 반복적 일정 | 유사 일정 | 매개변수 일정 | 3점 일정 |  | A | 다양한 미지수가 있는 애자일 소프트웨어 개발에서, PM은 반복적 일정을 사용해야 한다. 반복적 일정이 작업을 스프린트/이터레이션으로 나누어 점진적 상세화를 가능하게 한다. 유사 일정(B)은 과거 데이터에 의존한다. 매개변수 일정(C)은 통계 모델에 의존한다. 3점 일정(D)은 활동 수준 추정이다.
1603 | A company has agreed to run a transformation project using agile approaches. During the implementation, there is pushback from the functional groups that the project is moving too fast. What should the project manager have done at the beginning of the project to prevent this from happening? | Assessed the organizational culture | Circulated the project charter | Communicated the project schedule | Determined the level of maturity of the employees |  | A | When functional groups push back on an agile transformation saying it is moving too fast, the project manager should have assessed the organizational culture at the beginning. Cultural assessment identifies readiness and resistance points. Circulating the project charter (B) informs but does not assess readiness. Communicating the schedule (C) addresses timing, not culture. Determining employee maturity (D) is a partial assessment. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 회사가 애자일 접근법으로 변혁 프로젝트를 운영하기로 합의했다. 구현 중 기능 그룹이 너무 빠르다고 반발한다. PM이 초기에 무엇을 했어야 하는가? | 조직 문화를 평가했다 | 프로젝트 헌장을 배포했다 | 프로젝트 일정을 소통했다 | 직원의 성숙도 수준을 결정했다 |  | A | 기능 그룹이 애자일 변혁이 너무 빠르다고 반발할 때, PM은 초기에 조직 문화를 평가했어야 한다. 문화 평가가 조직의 변화 준비도와 저항 요인을 식별한다. 헌장 배포(B)는 변화 관리가 아니다. 일정 소통(C)은 속도만 다룬다. 성숙도 결정(D)은 유용하지만 문화 평가가 더 포괄적이다.
1604 | A company is implementing a project with team members located in different countries and time zones. Individual performance is satisfactory, but the team's performance as a whole is low, especially in terms of group activities. What should the project manager do? | Negotiate for new team members. | Facilitate communication and team building. | Review and reassign team assignments. | Review and update the communications management plan. |  | B | When a multi-country team performs well individually but poorly in group activities, the project manager should facilitate communication and team building. Establishing clear communication channels, respecting cultural differences, and fostering relationships improves group cohesion and collaboration. Negotiating for new team members (A) replaces rather than develops. Reviewing and reassigning tasks (C) restructures without addressing the root cause. Reviewing the communications plan (D) focuses on documentation rather than active facilitation. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 여러 국가와 시간대에 팀원이 있는 프로젝트에서 개인 성과는 좋지만 그룹 활동에서 성과가 저조하다. PM은 무엇을 해야 하는가? | 새 팀원을 협상한다 | 커뮤니케이션과 팀 빌딩을 퍼실리테이션한다 | 팀 배정을 검토하고 재배정한다 | 커뮤니케이션 관리 계획을 검토하고 업데이트한다 |  | B | 개인 성과는 좋지만 그룹 활동이 저조할 때, PM은 커뮤니케이션과 팀 빌딩을 퍼실리테이션해야 한다. 명확한 커뮤니케이션 채널과 팀 빌딩이 협업을 향상시킨다. 새 팀원(A)은 근본 문제를 해결하지 않는다. 재배정(C)은 개인 성과가 좋으므로 불필요하다. 계획 업데이트(D)는 실행보다 문서화이다.
1605 | During the service procurement process for a strategic project, only one bidder submitted a bid. The price of the offer is significantly large and the project sponsor is not convinced that the return on investment (ROI) can be achieved. How should the project manager address this issue? | Analyze the bounds of negotiations for project agreements. | Re-visit the project charter and seek other alternatives. | Proceed and issue the purchase order as this project is important. | Speak with the CEO and ask for their support to approve the offer. |  | B | When only one bidder submits a significantly expensive bid and the sponsor doubts ROI, the project manager should revisit the project charter and seek other alternatives. Re-evaluating requirements and exploring alternative approaches may reduce costs or identify better options. Analyzing negotiation bounds (A) only addresses the existing bid. Proceeding with the purchase order (C) ignores the sponsor's concern. Asking the CEO for support (D) bypasses analysis. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 전략 프로젝트의 서비스 조달에서 한 입찰자만 비싼 가격으로 입찰했다. 스폰서가 ROI를 의심한다. PM은 무엇을 해야 하는가? | 프로젝트 합의를 위한 협상 범위를 분석한다 | 프로젝트 헌장을 재검토하고 다른 대안을 모색한다 | 프로젝트가 중요하므로 구매 주문을 진행하고 발행한다 | CEO에게 대화하여 제안 승인을 지원하도록 요청한다 |  | B | 한 입찰자만 비싸게 입찰하고 스폰서가 ROI를 의심할 때, PM은 프로젝트 헌장을 재검토하고 다른 대안을 모색해야 한다. 요구사항과 접근법을 재평가하여 더 비용 효과적인 옵션을 찾을 수 있다. 협상 분석(A)은 한 입찰자로 협상력이 제한적이다. 바로 진행(C)은 ROI 의심을 무시한다. CEO 지원(D)은 문제를 해결하지 않는다.
1606 | A project manager for a technologically complex engagement reviews the key project indicators with the main stakeholders on a regular basis. During one of the meetings, the project sponsor explains that they are using the project manager's risk register as a way to communicate about the project at the executive level. How should the project manager ensure that project risks are reported accurately in the risk register? | Plan to update the risks at project closure. | List the project risks identified in the kick-off meeting. | Review the risks throughout project execution. | Update the risks in the risk management plan. |  | C | When the project sponsor uses the risk register for executive communication, the project manager should review risks throughout project execution to ensure accuracy. Continuous monitoring and updating reflects new risks, status changes, and response effectiveness. Updating risks only at closure (A) is too late. Listing only kick-off meeting risks (B) captures an incomplete picture. Updating risks in the management plan (D) is less specific than continuous review during execution. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 기술적으로 복잡한 프로젝트의 PM이 주요 이해관계자와 프로젝트 지표를 검토한다. 스폰서가 리스크 등록부를 경영진 커뮤니케이션에 사용한다. PM은 무엇을 해야 하는가? | 프로젝트 종료 시 리스크를 업데이트할 계획을 세운다 | 킥오프 회의에서 식별된 프로젝트 리스크를 나열한다 | 프로젝트 실행 전반에 걸쳐 리스크를 검토한다 | 리스크 관리 계획에서 리스크를 업데이트한다 |  | C | 프로젝트 스폰서가 리스크 등록부를 경영진 커뮤니케이션에 사용할 때, PM은 정확성을 보장하기 위해 프로젝트 실행 전반에 걸쳐 리스크를 검토해야 한다. 지속적 모니터링과 업데이트가 정확한 리스크 정보를 보장한다. 종료 시 업데이트(A)는 너무 늦다. 킥오프 리스크 나열(B)은 초기 식별에만 해당한다. 리스크 관리 계획 업데이트(D)는 부분적이다.
1607 | A project manager is assigned to a regulatory project for their country. The deadline for delivering results in compliance with the new laws is very tight, and the project team members have not yet been assigned. One of the project manager's peers informs the project manager that a project with the same scope for a different country was completed 1 year ago. What should the project manager do first? | Register a new risk in the risk management plan. | Ask for additional resources and review the project estimate. | Review organizational process assets (OPAs) and perform analogous estimating. | Complete a bottom-up estimation for the project activities. |  | C | When facing a tight regulatory deadline with no team assigned but a similar project was completed last year, the project manager should first review organizational process assets (OPAs) and perform analogous estimating. Historical data from the prior project enables faster, more accurate planning under time constraints. Registering a new risk (A) is reactive rather than planning-focused. Asking for additional resources without data (B) is premature. Bottom-up estimation (D) requires more information than currently available. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | PM이 국가 규제 프로젝트에 배정되었다. 규제 기한이 촉박하고 팀이 아직 배정되지 않았다. 작년에 유사 프로젝트가 완료되었다. PM은 무엇을 먼저 해야 하는가? | 리스크 관리 계획에 새 리스크를 등록한다 | 추가 자원을 요청하고 프로젝트 추정을 검토한다 | 조직 프로세스 자산(OPA)을 검토하고 유사 추정을 수행한다 | 프로젝트 활동에 대한 상향식 추정을 완료한다 |  | C | 촉박한 규제 기한에 팀 미배정이고 유사 프로젝트가 존재할 때, PM은 조직 프로세스 자산(OPA)을 검토하고 유사 추정을 수행해야 한다. 과거 데이터가 빠르고 합리적인 추정을 가능하게 한다. 리스크 등록(A)은 추정이 아니다. 추가 자원 요청(B)은 추정 후에 한다. 상향식 추정(D)은 팀 없이는 불가능하다.
1608 | A project manager is managing two integrated projects in a program. A key integration point is misaligned, which has resulted in delays. One of the team's integration leads is a subject matter expert (SME) in this integration area. The other team's integration lead is not an SME but is more senior and has worked on the project longer. Both team leads are blaming each other. What should the project manager do first to resolve this situation? | Assign the resolution of the issue to the senior integration lead who has worked on the project longer | Escalate the issue to the program architect who developed the integration plan | Meet with both integration leads to understand the root cause and determine a resolution | Assign the resolution of this issue to the integration lead who is a SME |  | C | When two integration leads from separate teams blame each other over a misaligned integration point, the project manager should first meet with both leads together to understand the root cause and determine a resolution. Direct facilitation promotes collaborative problem-solving without taking sides. Assigning resolution to the senior lead (A) favors tenure over expertise. Escalating to the program architect (B) bypasses the PM's conflict resolution responsibility. Assigning to the SME lead (D) favors expertise but may create resentment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | PM이 프로그램 내 두 통합 프로젝트를 관리한다. 핵심 통합 지점이 불일치하여 양 팀의 통합 리드가 서로를 비난한다. PM은 무엇을 먼저 해야 하는가? | 프로젝트에 오래 근무한 선임 통합 리드에게 이슈 해결을 배정한다 | 통합 계획을 개발한 프로그램 아키텍트에게 이슈를 에스컬레이션한다 | 양측 통합 리드와 만나 근본 원인을 파악하고 해결책을 결정한다 | SME인 통합 리드에게 이슈 해결을 배정한다 |  | C | 두 통합 리드가 불일치된 통합 지점에 대해 서로를 비난할 때, PM은 먼저 양측과 함께 만나 근본 원인을 파악하고 해결책을 결정해야 한다. 직접 대면 논의가 협력적 해결을 촉진한다. 한쪽 리드에게 배정(A, D)은 편파적이다. 에스컬레이션(B)은 직접 해결 시도 전에 성급하다.
1609 | While developing a new product, a key stakeholder expresses concern about insufficient information on product feature requirements. The product team disagrees and mentions that detailed requirements have been provided. What should the project manager do to handle this situation? | Record the new requirements and ask the product team to develop them. | Conduct new risk and scope analyses, identifying the missing information. | Redirect the stakeholder to discuss this request with the functional manager. | Organize a discussion with the product team to clarify the missing information. |  | D | When a stakeholder believes product feature requirements are insufficient while the product team disagrees, the project manager should organize a discussion with the product team to clarify the missing information. Direct facilitation resolves the discrepancy by bringing both perspectives together and ensuring requirements are clear, complete, and consistent. Recording new requirements and asking for development (A) assumes the stakeholder is correct without verification, potentially introducing scope creep. Conducting risk and scope analyses (B) is analytical but may not address the root cause—a communication gap between stakeholder and team. Redirecting the stakeholder to a functional manager (C) creates confusion and avoids the PM's responsibility to facilitate stakeholder engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Build an Empowered Culture | Manage Communications | Traditional PM | 신제품 개발 중 주요 이해관계자가 제품 기능 요구사항에 대한 정보가 불충분하다고 우려한다. 제품 팀은 동의하지 않는다. PM은 무엇을 해야 하는가? | 새 요구사항을 기록하고 제품 팀에게 개발을 요청한다 | 새 리스크 및 범위 분석을 수행하여 누락된 정보를 식별한다 | 이해관계자를 기능 관리자와 논의하도록 안내한다 | 제품 팀과 토론을 조직하여 누락된 정보를 명확히 한다 |  | D | 이해관계자가 요구사항 불충분을 우려하고 제품 팀이 동의하지 않을 때, PM은 제품 팀과 토론을 조직하여 누락된 정보를 명확히 해야 한다. 직접 대화가 오해를 해소한다. 새 요구사항 기록(A)은 검증 없이 진행한다. 리스크/범위 분석(B)은 토론 후에 한다. 기능 관리자 안내(C)는 PM 역할을 회피한다.
1610 | An organization is using a hybrid delivery approach for a business project. The product owner, the person who was also managing the project, was promoted to a more senior role. A new project lead has joined the project. Which artifact should the project lead use to ensure that the project benefits have been identified? | Business case | Product backlog | Solution architecture | Statement of work (SOW) |  | A | When a new project lead joins a hybrid project and needs to ensure project benefits have been identified, they should use the business case. The business case outlines expected benefits, costs, risks, and strategic alignment that justify the project investment. The product backlog (B) lists features, not business justification. The solution architecture (C) describes technical design. The statement of work (D) defines contractual deliverables. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Business Environment | Define and Establish Governance | Schedule | Initiating | Be an Accountable Leader | Develop Project Charter | Hybrid/Tailoring | 하이브리드 프로젝트에서 제품 책임자이자 비즈니스 분석가였던 사람이 떠났다. 새 프로젝트 리더가 프로젝트 혜택이 식별되었는지 확인하려면 무엇을 사용해야 하는가? | 비즈니스 케이스 | 제품 백로그 | 솔루션 아키텍처 | 작업기술서(SOW) |  | A | 새 프로젝트 리더가 프로젝트 혜택 식별을 확인하려면 비즈니스 케이스를 사용해야 한다. 비즈니스 케이스는 기대 혜택, 비용, 리스크, 정당성을 설명한다. 제품 백로그(B)는 작업 항목이다. 솔루션 아키텍처(C)는 기술 설계이다. SOW(D)는 작업 범위이다.
1611 | After sending an on-site meeting invitation to seven people for the kick-off meeting of a project, a key stakeholder declines because they will be at another location for the rest of the month. What should the project manager do? | Change the kick-off meeting to a virtual meeting so all can attend at the same time. | Make arrangements for the stakeholder to join the kick-off meeting virtually. | Hold the kick-off meeting with the rest of the stakeholders to avoid a delay in the project. | Reschedule the kick-off meeting for the following month so all can attend on-site. |  | B | When a key stakeholder declines the on-site kick-off meeting due to being at another location, the project manager should make arrangements for the stakeholder to join virtually. This ensures the stakeholder's participation without delaying the project's initiation, maintaining momentum and engagement from all critical parties. Changing the entire meeting to virtual (A) unnecessarily disrupts arrangements for other attendees. Holding the meeting without the stakeholder (C) risks missing critical input. Rescheduling for the following month (D) delays the project unnecessarily. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 킥오프 회의에 7명을 현장 초대했으나 주요 이해관계자가 다른 장소에 있어 참석을 거부했다. PM은 무엇을 해야 하는가? | 모두가 동시에 참석할 수 있도록 킥오프 회의를 가상 회의로 변경한다 | 이해관계자가 가상으로 킥오프 회의에 참여하도록 준비한다 | 프로젝트 지연을 방지하기 위해 나머지 이해관계자와 킥오프 회의를 진행한다 | 모두가 현장 참석할 수 있도록 킥오프 회의를 다음 달로 재일정한다 |  | B | 주요 이해관계자가 다른 장소에 있어 현장 킥오프 참석이 불가할 때, PM은 해당 이해관계자가 가상으로 참여하도록 준비해야 한다. 이해관계자 참여를 보장하면서 일정을 유지한다. 전체 가상 전환(A)은 불필요한 변경이다. 이해관계자 없이 진행(C)은 핵심 참여를 놓친다. 한 달 연기(D)는 과도한 지연이다.
1612 | During the lessons learned workshop, one stakeholder mentioned that the project was unsuccessful as it did not deliver the expected business value. What should the project manager do to address this concern? | Review the project management plan tasks with the stakeholders. | Review the business benefits realization plan with the stakeholders. | Review the communications management plan with the stakeholders, | Review the project management plan budget with the stakeholders. |  | B | When a stakeholder says the project did not deliver expected business value during lessons learned, the project manager should review the business benefits realization plan with stakeholders. The benefits plan outlines how value is achieved and measured. Reviewing the project management plan tasks (A) addresses execution, not value. Reviewing the communications plan (C) addresses information flow. Reviewing the budget (D) addresses cost, not benefits realization. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Integrate Sustainability | Monitor and Control Project Performance | Sustainability | 교훈 워크숍에서 이해관계자가 프로젝트가 기대한 비즈니스 가치를 전달하지 못했다고 언급했다. PM은 무엇을 해야 하는가? | 이해관계자와 프로젝트 관리 계획 작업을 검토한다 | 이해관계자와 비즈니스 혜택 실현 계획을 검토한다 | 이해관계자와 커뮤니케이션 관리 계획을 검토한다 | 이해관계자와 프로젝트 관리 계획 예산을 검토한다 |  | B | 이해관계자가 프로젝트가 기대 비즈니스 가치를 전달하지 못했다고 할 때, PM은 이해관계자와 비즈니스 혜택 실현 계획을 검토해야 한다. 혜택 실현 계획이 기대와 실제 가치를 비교할 기반이다. PM 계획 작업(A)은 실행 중심이다. 커뮤니케이션 계획(C)은 가치 전달과 무관하다. 예산(D)은 비용 중심이다.
1613 | A geographically distributed project team has development issues between the collocated and virtual teams causing productivity to decrease. What should the project manager do to address this issue? | Obtain special expertise to advise the team members | Set up face-to-face meetings with project team members | Develop protocols for resolving conflicts between team members | Force the team members to work from one location. |  | C | When a geographically distributed team has development issues between colocated and virtual members causing decreased productivity, the project manager should develop protocols for resolving conflicts between team members. Establishing ground rules and conflict resolution standards creates common behavioral expectations across all locations. Obtaining special expertise (A) adds external help but does not address internal team dynamics. Setting up face-to-face meetings (B) may be impractical. Forcing colocation (D) may be infeasible and costly. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 지리적으로 분산된 프로젝트 팀에서 현장 팀과 가상 팀 간 개발 이슈가 있어 생산성이 저하되었다. PM은 무엇을 해야 하는가? | 팀원에게 조언할 전문가를 확보한다 | 프로젝트 팀원과 대면 회의를 설정한다 | 팀원 간 갈등 해결을 위한 프로토콜을 개발한다 | 팀원들이 한 장소에서 근무하도록 강제한다 |  | C | 지리적으로 분산된 팀에서 현장과 가상 팀 간 이슈가 있을 때, PM은 갈등 해결 프로토콜을 개발해야 한다. 명확한 프로토콜이 구조화된 갈등 해결을 가능하게 한다. 전문가 확보(A)는 팀 내 해결이 아니다. 대면 회의(B)는 가상 팀에 비현실적이다. 한 장소 강제(D)는 분산 팀에서 불가능하다.
1614 | A project manager has been assigned to a new project. The project manager read the business case, charter, and statement of work (SOW) and scheduled a discussion with the sponsor about the scope, goals, and objectives. The project manager requested a meeting with the sponsor and the business analyst who performed the business case before setting up a kickoff meeting. Why did the project manager request the meeting? | To identify and investigate perceived and potential misunderstandings in the business case | To rewrite the business case to include additional objectives | To identify impediments, obstacles, and blockers for the team in the business case | To verify the feasibility of the solutions in the business case |  | A | The correct answer is A. To identify and investigate perceived and potential misunderstandings in the business case. Schedule management requires proactive monitoring and timely corrective actions. The PM should analyze schedule impacts, evaluate options, and implement appropriate responses to keep the project on track. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | PM이 새 프로젝트에 배정되었다. 비즈니스 케이스, 헌장, SOW를 읽었다. PM이 프로젝트 스폰서, 주요 이해관계자, 전문가와 회의를 주선한 이유는? | 비즈니스 케이스의 인식되거나 잠재적인 오해를 식별하고 조사하기 위해 | 추가 목표를 포함하여 비즈니스 케이스를 재작성하기 위해 | 비즈니스 케이스에서 팀의 장애물, 방해물, 차단 요소를 식별하기 위해 | 비즈니스 케이스의 솔루션 실현 가능성을 검증하기 위해 |  | A | 정답은 A이다. 비즈니스 케이스의 인식되거나 잠재적인 오해를 식별하고 조사하기 위해. PM은 주요 이해관계자와의 논의를 통해 비즈니스 케이스의 이해도와 기대치를 조정해야 한다. 재작성(B)은 PM 권한이 아니다. 장애물 식별(C)은 실행 단계이다. 실현 가능성 검증(D)은 프로젝트 착수 전 활동이다.
1615 | A project manager is in a cross-functional agile team. The project manager has been assigned a software project with multiple features that will take the team about a year to complete. The CEO is insisting that the solution needs to meet business goals for the year end, which is due in 6 months. What should the project manager do to align stakeholders' needs and expectations? | Include all stakeholders in daily scrum meetings to keep them informed. | Work with the stakeholders to create a prioritized backlog and release a roadmap. | Modify the requirements to those that can be completed in 6 months. | Implement fast-tracking and crashing activities to complete the project in 6 months. |  | B | When the CEO demands a solution meeting business goals in six months while the project requires a year, the project manager should work with stakeholders to create a prioritized backlog and release roadmap. Prioritization ensures the most critical features are delivered within the constrained timeline. Including all stakeholders in daily scrums (A) is inefficient. Modifying requirements to fit six months (C) changes scope without stakeholder agreement. Fast-tracking and crashing (D) increases risk and cost without prioritization. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 교차 기능 애자일 팀에 있다. CEO가 6개월 내 비즈니스 목표를 충족하는 솔루션을 요구하지만 프로젝트는 1년이 필요하다. PM은 무엇을 해야 하는가? | 모든 이해관계자를 데일리 스크럼 회의에 포함하여 정보를 제공한다 | 이해관계자와 협력하여 우선순위화된 백로그와 릴리스 로드맵을 만든다 | 6개월 내 완료할 수 있는 요구사항으로 수정한다 | 6개월 내 프로젝트를 완료하기 위해 패스트트래킹과 크래싱을 구현한다 |  | B | CEO가 6개월 솔루션을 요구하지만 1년이 필요할 때, PM은 이해관계자와 우선순위화된 백로그와 릴리스 로드맵을 만들어야 한다. 우선순위 기반 점진적 전달이 시간 제약 내 최대 가치를 제공한다. 데일리 스크럼 참여(A)는 비효율적이다. 요구사항 수정(C)은 일방적이다. 크래싱(D)은 품질 리스크가 있다.
1616 | A company initiated a project to introduce a new product to the market. The product must undergo the industry's regulatory process prior to approval and launch. However, the company sees a great demand for this product and wants it to launch as soon as possible. What should the project manager do to realize this opportunity? | Hire a third party who is an expert on the industry ' s regulations to work out the details. | Escalate the issue to the company ' s CEO who has experience with the regulations. | Communicate with the industry ' s regulatory authority to grant the company an exception | Comply with the regulatory requirements and work to compress the project schedule. |  | D | The PM should prioritize compliance with regulatory requirements while simultaneously exploring schedule acceleration strategies—optimizing resources, streamlining processes, and identifying bottlenecks. Regulatory compliance must be maintained to avoid legal risks and ensure successful product launch. Seeking exceptions or bypassing regulations introduces unacceptable risk and is not advisable. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 회사가 새 제품을 시장에 출시하는 프로젝트를 시작했다. 제품이 규제 프로세스를 거쳐야 하지만 시간이 오래 걸린다. PM은 무엇을 해야 하는가? | 업계 규제 전문가인 제3자를 고용하여 세부 사항을 처리한다 | 규제 경험이 있는 CEO에게 이슈를 에스컬레이션한다 | 규제 당국에 연락하여 회사에 예외를 부여하도록 한다 | 규제 요구사항을 준수하면서 프로젝트 일정 압축을 위해 노력한다 |  | D | 규제 프로세스가 시간이 오래 걸릴 때, PM은 규제 요구사항을 준수하면서 동시에 일정 압축 전략을 탐색해야 한다. 규제 준수는 타협 불가이며 일정 최적화를 병행한다. 제3자 고용(A)은 PM 책임 위임이다. CEO 에스컬레이션(B)은 과도하다. 예외 요청(C)은 비현실적이다.
1617 | During the execution of a project to develop a prototype, the customer asks the project manager to stop the prototype line and purge a specific component based on recent reliability tests that have deemed the component to be deficient. The project manager checked the quality management plan and there is no reference to this component. What should the project manager do next? | Inform the project sponsor of the situation and wait for the sponsor to provide further directions. | Call a technical meeting with the customer to agree on a specification for the component and document it in the quality management plan. | Keep running the manufacturing line because there are no quality specifications for this component. | Submit a change request to proceed with the replacement of the component and wait for further customer instructions. |  | B | When a customer requests stopping and purging a deficient component not referenced in the quality management plan, the project manager should call a technical meeting with the customer to agree on specifications and document them in the quality plan. Collaborative specification ensures alignment. Informing the sponsor and waiting (A) causes delay. Continuing because no specs exist (C) ignores a quality concern. Submitting a change request and waiting (D) is passive. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로토타입 개발 프로젝트 실행 중 고객이 품질 관리 계획에 참조되지 않은 결함 부품을 정지하고 제거하도록 요청했다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 상황을 알리고 추가 지시를 기다린다 | 고객과 기술 회의를 소집하여 부품 사양에 합의하고 문서화한다 | 이 부품에 대한 품질 사양이 없으므로 제조 라인을 계속 운영한다 | 부품 교체를 진행하기 위한 변경 요청을 제출하고 고객의 추가 지시를 기다린다 |  | B | 고객이 품질 관리 계획에 참조되지 않은 결함 부품의 정지를 요청할 때, PM은 고객과 기술 회의를 소집하여 부품 사양에 합의하고 문서화해야 한다. 기술적 합의가 명확한 품질 기준을 수립한다. 스폰서 대기(A)는 수동적이다. 계속 운영(C)은 고객 요구를 무시한다. 변경 요청(D)은 합의 전에 성급하다.
1618 | The project sponsor on an agile project informed the project lead that an executive would like an update on the project's progress. What should the project lead do? | Provide a link to the project ' s shared drive for the executive to search through for any artifacts that are of interest. | Invite the executive to the project ' s meeting space to determine if the project information radiators meet their needs | Reach out to the project management office (PMO) for status report templates and provide project updates in that format | Ask the project sponsor or product owner to provide an update since the project lead should be trying to keep the team free from impediments |  | B | When an executive wants a project progress update on an agile project, the project lead should invite the executive to the project's meeting space to see if information radiators meet their needs. Information radiators provide transparent, up-to-date progress displays. Providing a shared drive link (A) requires self-service navigation. PMO report templates (C) may not suit agile. Asking sponsor/PO to present (D) delegates the PM's communication role. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Hybrid/Tailoring | 애자일 프로젝트에서 스폰서가 경영진이 프로젝트 진행 업데이트를 원한다고 알렸다. 프로젝트 리더는 무엇을 해야 하는가? | 경영진이 산출물을 검색할 수 있도록 공유 드라이브 링크를 제공한다 | 경영진을 프로젝트 회의 공간에 초대하여 정보 라디에이터가 요구를 충족하는지 확인한다 | PMO에 상태 보고 템플릿을 요청하고 프로젝트 업데이트를 제공한다 | 프로젝트 리더가 장애물 제거에 집중해야 하므로 스폰서나 제품 책임자에게 업데이트 제공을 요청한다 |  | B | 경영진이 애자일 프로젝트 진행 업데이트를 원할 때, 프로젝트 리더는 경영진을 프로젝트 회의 공간에 초대하여 정보 라디에이터가 요구를 충족하는지 확인해야 한다. 정보 라디에이터가 투명성과 자기 서비스 정보 접근을 제공한다. 공유 드라이브(A)는 탐색이 어렵다. PMO 템플릿(C)은 애자일 접근이 아니다. 위임(D)은 리더십 포기이다.
1619 | A project team is struggling to meet the project deadline due to a reoccurring conflict between two team members. What should the project manager do? | Introduce training sessions to improve the team ' s performance. | Explore the possibility of reshuffling the team. | Hold the team collectively responsible for their actions. | Schedule team-building activities as required. |  | D | The correct answer is D. Schedule team-building activities as required. The PM should address team issues proactively by understanding root causes, building trust, and creating an environment that fosters collaboration and high performance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 두 팀원 간 반복되는 갈등으로 프로젝트 기한 달성이 어렵다. PM은 무엇을 해야 하는가? | 팀 성과를 개선하기 위한 교육 세션을 도입한다 | 팀 재편성 가능성을 탐색한다 | 팀에게 행동에 대한 집단적 책임을 묻는다 | 필요에 따라 팀 빌딩 활동을 계획한다 |  | D | 정답은 D이다. 필요에 따라 팀 빌딩 활동을 계획한다. PM은 근본 원인을 이해하고 신뢰를 구축하며 협력을 촉진하는 환경을 만들어 팀 이슈를 사전적으로 해결해야 한다. 교육(A)은 기술이지 관계가 아니다. 재편성(B)은 갈등 해결이 아니다. 집단 책임(C)은 개인 간 갈등을 다루지 않는다.
1620 | A new project manager is planning an information security project for a company that resides in different countries. What is the first step the project manager should take to gather customer requirements? | Request relevant stakeholders to conduct an analysis and reach consensus independently | Conduct project planning meetings in one location with relevant stakeholders | Conduct a project scope review workshop with relevant stakeholders. | Conduct a stakeholder analysis to identify how regional policies may influence needs |  | D | For an information security project spanning multiple countries, the first step to gather customer requirements is to conduct a stakeholder analysis to identify how regional policies may influence needs. This analysis identifies key stakeholders, their expectations, and how legal, regulatory, and cultural factors affect requirements across different regions. Requesting stakeholders to conduct analysis independently (A) lacks facilitation and coordination. Conducting planning meetings in one location (B) is impractical for a multinational project. Conducting a scope review workshop (C) is premature before understanding who the stakeholders are and what influences their needs. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | PM이 여러 국가에 걸친 정보 보안 프로젝트를 계획하고 있다. 고객 요구사항을 수집하기 위한 첫 단계는? | 관련 이해관계자에게 분석을 수행하고 독립적으로 합의에 도달하도록 요청한다 | 관련 이해관계자와 한 장소에서 프로젝트 계획 회의를 수행한다 | 관련 이해관계자와 프로젝트 범위 검토 워크숍을 수행한다 | 이해관계자 분석을 수행하여 지역 정책이 요구에 어떻게 영향을 미치는지 식별한다 |  | D | 여러 국가에 걸친 정보 보안 프로젝트에서 고객 요구사항 수집의 첫 단계는 이해관계자 분석을 수행하여 지역 정책이 요구에 어떻게 영향을 미치는지 식별하는 것이다. 지역별 규제 차이 이해가 선행되어야 한다. 독립 합의(A)는 비협력적이다. 한 장소 회의(B)는 비현실적이다. 범위 검토(C)는 이해관계자 분석 후에 한다.
1621 | A new employee has joined the management team and wants to get a quick overview of all the agile team's projects. What should the agile team lead recommend to the employee as a first step to gain this understanding? | Connect with each project ' s scrum master to assess progress. | Meet with each project ' s development team separately. | Review the information radiators for each project. | Attend the daily standup meetings for each project. |  | C | When a new management team employee wants a quick overview of all agile projects, the agile team lead should recommend reviewing information radiators for each project. Information radiators—such as burndown charts, kanban boards, and sprint boards—are visual tools designed for quick, transparent status communication accessible to all stakeholders. Connecting with each scrum master (A) is less efficient for a first overview. Meeting each development team separately (B) is time-consuming. Attending daily standups (D) provides insight but requires daily commitment and is less efficient initially. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 새 직원이 경영팀에 합류하여 모든 애자일 팀 프로젝트의 빠른 개요를 원한다. 애자일 팀 리더는 무엇을 추천해야 하는가? | 각 프로젝트의 스크럼 마스터와 연결하여 진행 상황을 평가한다 | 각 프로젝트의 개발 팀과 개별적으로 만난다 | 각 프로젝트의 정보 라디에이터를 검토한다 | 각 프로젝트의 데일리 스탠드업 회의에 참석한다 |  | C | 새 경영팀 직원이 모든 애자일 프로젝트의 빠른 개요를 원할 때, 정보 라디에이터 검토를 추천해야 한다. 정보 라디에이터(번다운 차트, 칸반 보드 등)가 시각적으로 빠른 프로젝트 상태 개요를 제공한다. 스크럼 마스터 연결(A)은 시간이 많이 걸린다. 개별 팀 미팅(B)은 비효율적이다. 스탠드업 참석(D)은 세부적이고 시간이 많이 든다.
1622 | A project is about to start with a global project team. Travel is not a viable option for project team members, so most will participate virtually. What should the project manager do to engage the team? | Have one-on-one meetings with team members to improve communication. | Ask human resources (HR) for team-building recommendations. | Invest in a virtual collaboration/colocation environment. | Schedule weekly team meetings to encourage collaboration. |  | C | When a global project team cannot travel and must participate virtually, the project manager should invest in a virtual collaboration/colocation environment. Virtual colocation supports real-time collaboration and team unity. One-on-one meetings (A) are time-consuming at scale. Asking HR for team-building recommendations (B) delegates the PM's responsibility. Weekly team meetings (D) are insufficient for continuous collaboration. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 글로벌 프로젝트 팀이 출장이 불가능하여 대부분 가상으로 참여해야 한다. PM은 무엇을 해야 하는가? | 팀원과 일대일 회의를 하여 커뮤니케이션을 개선한다 | 인사부(HR)에 팀 빌딩 추천을 요청한다 | 가상 협업/코로케이션 환경에 투자한다 | 협업을 장려하기 위해 주간 팀 회의를 예약한다 |  | C | 글로벌 팀이 출장 불가하고 가상 참여해야 할 때, PM은 가상 협업/코로케이션 환경에 투자해야 한다. 가상 코로케이션이 실시간 협업과 팀 결속을 지원한다. 일대일 회의(A)는 팀 협업이 아니다. HR 추천(B)은 간접적이다. 주간 회의(D)만으로는 불충분하다.
1623 | During project implementation, a critical performance issue is identified by team members. What should the project manager do? | Review the tender requirements related to the performance issue | Pass the performance issue to subject matter experts (SMEs) to handle | Work with the project stakeholders to address the performance issue | Submit a change request to handle the performance issue |  | C | When a critical performance issue is identified during project implementation, the project manager should work with project stakeholders to address it. Performance problems affect scope, schedule, cost, quality, or risk, requiring collaborative assessment of the variance, root cause identification, and evaluation of response options through governance processes. Reviewing tender requirements (A) may inform acceptance criteria but does not actively resolve the issue. Passing to SMEs (B) delegates accountability that should remain with the PM. Submitting a change request (D) may be premature if the issue can be resolved within existing authority. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 프로젝트 구현 중 팀원이 심각한 성과 이슈를 식별했다. PM은 무엇을 먼저 해야 하는가? | 성과 이슈와 관련된 입찰 요구사항을 검토한다 | 성과 이슈를 주제 전문가(SME)에게 넘겨 처리하도록 한다 | 프로젝트 이해관계자와 협력하여 성과 이슈를 해결한다 | 성과 이슈를 처리하기 위한 변경 요청을 제출한다 |  | C | 심각한 성과 이슈가 식별될 때, PM은 프로젝트 이해관계자와 협력하여 해결해야 한다. 성과 문제는 범위, 일정, 비용에 영향을 미치므로 협력적 해결이 필요하다. 입찰 요구사항 검토(A)는 계약 중심이다. SME에게 위임(B)은 PM 역할 포기이다. 변경 요청(D)은 해결책 결정 후에 한다.
1624 | In a frequently changing project, the project manager discovers a customer requirement change during a daily meeting. What should the project manager do? | Escalate to management for approval since the change was not included in the original requirements. | Tell the customer that the requirement change will be put into the next project phase if management approves. | Validate the requirement change with the product owner and development team before redefining the scope. | Give the change to the scrum master to investigate how much additional effort the change will require. |  | C | When a customer requirement change is discovered during a daily meeting, the project manager should validate the change with the product owner and development team before redefining the scope. This ensures the change is feasible and its impact is properly assessed before formal action. Escalating to management for approval (A) bypasses the team's assessment. Telling the customer it will go into the next phase (B) defers the change without evaluation. Giving it to the scrum master to investigate effort (D) assigns it to the wrong role without product owner involvement. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 자주 변경되는 프로젝트에서 PM이 데일리 미팅 중 고객 요구사항 변경을 발견했다. PM은 무엇을 먼저 해야 하는가? | 변경이 원래 요구사항에 포함되지 않았으므로 경영진에 승인을 에스컬레이션한다 | 경영진이 승인하면 요구사항 변경을 다음 프로젝트 단계에 넣겠다고 고객에게 말한다 | 범위를 재정의하기 전에 제품 책임자와 개발 팀과 요구사항 변경을 검증한다 | 변경이 필요한 추가 노력을 조사하기 위해 스크럼 마스터에게 변경을 전달한다 |  | C | 데일리 미팅에서 고객 요구사항 변경이 발견될 때, PM은 범위 재정의 전에 제품 책임자와 개발 팀과 변경을 검증해야 한다. 검증이 정보에 기반한 결정을 보장한다. 에스컬레이션(A)은 검증 전에 성급하다. 다음 단계 연기(B)는 긴급한 변경에 대응하지 않는다. 스크럼 마스터에게 전달(D)은 적절한 검증이 아니다.
1625 | A project manager is leading an engineering project. The project manager must obtain some certifications before mass production, which is scheduled in 3 months. The certification process will require at least 6 months. What should the project manager do next? | Engage a consultant to shorten the certification process to meet the schedule requirement. | Meet with senior management to discuss the possibility of an extension to the project timeline. | Discuss extending the mass production timeline by 3 months with the project sponsor. | Assess and evaluate the certification process and understand the best and worst case scenarios. |  | D | When certifications requiring 6 months are needed before mass production scheduled in 3 months, the project manager should assess and evaluate the certification process to understand best and worst case scenarios. Thorough assessment enables informed decisions. Engaging a consultant to shorten the process (A) assumes shortcuts exist. Discussing extension with the sponsor (B) acts before understanding options. Discussing extension with senior management (C) also acts before full assessment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | PM이 엔지니어링 프로젝트를 이끌고 있다. 대량 생산 전 인증이 필요하나 인증에 6개월이 걸리고 대량 생산은 3개월 후 예정이다. PM은 무엇을 먼저 해야 하는가? | 인증 프로세스를 단축하기 위해 컨설턴트를 고용하여 일정 요구를 충족한다 | 프로젝트 일정 연장 가능성에 대해 고위 경영진과 회의한다 | 대량 생산 일정을 3개월 연장하는 것에 대해 프로젝트 스폰서와 논의한다 | 인증 프로세스를 평가하고 최선과 최악의 시나리오를 파악한다 |  | D | 인증에 6개월이 필요하고 대량 생산이 3개월 후인 상황에서, PM은 먼저 인증 프로세스를 평가하고 최선과 최악의 시나리오를 파악해야 한다. 상황 분석이 정보에 기반한 결정의 기초이다. 컨설턴트 고용(A)은 평가 전에 성급하다. 경영진 회의(B)는 분석 후에 한다. 일정 연장 논의(C)는 대안 탐색 전에 성급하다.
1626 | A project manager has been assigned to a new project that will be delivered using an agile framework. The sponsor is asking for a cost estimation to build the business case. What should the project manager do? | Review the completion costs of similar projects. | Ensure that a 20% contingency is included in the estimation. | Review the lessons learned from similar projects. | Ensure the client representative is involved in the estimation. |  | A | When a sponsor requests cost estimation for an agile project's business case, the project manager should review the completion costs of similar projects. Historical data from comparable projects provides a realistic baseline for estimation. Ensuring a 20% contingency (B) is a component but not the primary estimation method. Reviewing lessons learned (C) provides insights but not cost data. Involving the client representative (D) is helpful but secondary to historical analysis. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | PM이 애자일 프레임워크로 전달되는 새 프로젝트에 배정되었다. 스폰서가 비즈니스 케이스를 위한 비용 추정을 요청한다. PM은 무엇을 먼저 해야 하는가? | 유사 프로젝트의 완료 비용을 검토한다 | 추정에 20% 비상비를 포함하도록 한다 | 유사 프로젝트의 교훈을 검토한다 | 고객 대표가 추정에 참여하도록 한다 |  | A | 스폰서가 애자일 프로젝트의 비용 추정을 요청할 때, PM은 유사 프로젝트의 완료 비용을 검토해야 한다. 유사 프로젝트의 역사적 데이터가 가장 신뢰할 수 있는 추정 기반을 제공한다. 20% 비상비(B)는 분석 없는 임의적 수치이다. 교훈 검토(C)는 유용하지만 비용 데이터가 아니다. 고객 참여(D)는 추정 후에 한다.
1627 | A new project manager is assigned to a project in the execution stage. A few key stakeholders inform the new project manager that the project has some serious issues. What should the newly assigned project manager do first to understand the issues? | Ask the key stakeholders to discuss the issues with the project team. | Check the risk management plan to ensure there is a strategy to address the issues. | Review the issues log to ensure the issues are captured. | Escalate the issues to the project sponsor. |  | C | When a new project manager is told the project has serious issues, they should first review the issues log to ensure issues are captured. The issues log provides documented context. Asking stakeholders to discuss with the team (A) happens without PM understanding. Checking the risk management plan (B) addresses risks, not current issues. Escalating to the sponsor (D) is premature without understanding. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 새 PM이 실행 단계 프로젝트에 배정되었다. 주요 이해관계자가 프로젝트에 심각한 이슈가 있다고 알렸다. PM은 무엇을 먼저 해야 하는가? | 주요 이해관계자에게 프로젝트 팀과 이슈를 논의하도록 요청한다 | 리스크 관리 계획을 확인하여 이슈 해결 전략이 있는지 확인한다 | 이슈 로그를 검토하여 이슈가 기록되었는지 확인한다 | 이슈를 프로젝트 스폰서에게 에스컬레이션한다 |  | C | 새 PM이 심각한 이슈를 통보받을 때, 먼저 이슈 로그를 검토하여 이슈가 기록되었는지 확인해야 한다. 이슈 로그가 문서화된 맥락을 제공한다. 이해관계자-팀 논의(A)는 상황 파악 후에 한다. 리스크 관리 계획(B)은 이슈가 아닌 리스크이다. 에스컬레이션(D)은 상황 파악 전에 성급하다.
1628 | Project progress meetings occur via virtual conference calls. In every project progress meeting, one team member continuously interrupts others during discussions. Other team members often have no opportunity to talk or complete their explanations. What should the project manager do? | Manage time efficiently using the agenda and ask each participant to contribute. | Speak individually with the team member who always disrupts the conversations. | Start the meeting with a review of the ground rules, meeting objectives, and the agenda. | Speak individually with the team members who do not participate in conversations. |  | A | The PM should manage meeting time effectively using the agenda and ensure each participant has the opportunity to contribute. This encourages equitable participation and allows all team members to provide input—essential for a collaborative project environment. Clear time management and structured facilitation help prevent any single participant from dominating discussions. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 가상 회의에서 한 팀원이 계속 대화를 독점하여 다른 팀원이 참여하지 못한다. PM은 무엇을 해야 하는가? | 안건을 사용하여 시간을 효율적으로 관리하고 각 참석자에게 기여할 기회를 준다 | 항상 대화를 방해하는 팀원과 개별적으로 대화한다 | 회의를 기본 규칙, 회의 목표, 안건 검토로 시작한다 | 대화에 참여하지 않는 팀원과 개별적으로 대화한다 |  | A | 한 팀원이 가상 회의에서 대화를 독점할 때, PM은 안건을 사용하여 시간을 효율적으로 관리하고 각 참석자에게 기여할 기회를 주어야 한다. 구조적 접근이 공평한 참여를 보장한다. 개별 대화(B)는 보완적이지만 회의 관리가 우선이다. 기본 규칙 검토(C)는 유용하지만 적극적 관리가 아니다. 비참여자 대화(D)는 증상 치료이다.
1629 | In the middle of a project, a business unit manager who regularly interacts with the project manager's team is promoted to a higher management position. The replacement manager is from the same unit and is somewhat familiar with the project. After getting more information about the new manager, what is the project manager's next step? | Update the stakeholder register and the stakeholder engagement plan to include the new manager. | Send the new manager a copy of the project charter to ensure the project objectives are understood. | Schedule a meeting with the new manager to discuss the business analysis team ' s plans. | Contact the previous business unit manager to learn more about the new manager. |  | A | When a business unit manager who interacts with the project team is replaced, the project manager's next step should be to update the stakeholder register and the stakeholder engagement plan to include the new manager. Formally documenting the new stakeholder's information, current engagement level, and planned engagement strategies ensures continuity. Sending the project charter (B) is informative but does not capture the new stakeholder's specific needs. Scheduling a meeting (C) is valuable but should follow the formal documentation update. Contacting the previous manager (D) may be helpful but is not a formal project management action. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | 프로젝트 중간에 PM 팀과 정기적으로 상호작용하는 사업부 관리자가 승진하여 새 관리자로 교체되었다. PM은 무엇을 먼저 해야 하는가? | 새 관리자를 포함하도록 이해관계자 등록부와 이해관계자 참여 계획을 업데이트한다 | 새 관리자에게 프로젝트 목표 이해를 위한 프로젝트 헌장 사본을 보낸다 | 새 관리자와 회의를 예약하여 비즈니스 분석 팀의 계획을 논의한다 | 이전 사업부 관리자에게 연락하여 새 관리자에 대해 더 알아본다 |  | A | PM 팀과 상호작용하는 사업부 관리자가 교체되었을 때, PM은 먼저 이해관계자 등록부와 참여 계획을 업데이트해야 한다. 이해관계자 변경의 공식적 문서화가 적절한 참여 전략의 기반이다. 헌장 발송(B)은 업데이트 후에 한다. 회의 예약(C)은 업데이트 후에 한다. 이전 관리자 연락(D)은 부적절하다.
1630 | A project manager joins a team that is providing a customized enterprise resource planning (ERP) system to a client. A potential design problem is identified by the development team. After reviewing this issue with the project owner and team members, all agreed to revise the design to avoid a system defect when deployed. The design is already approved. What should be the project manager's next steps? | Amend the design specifications and pass them to the development team for reprogramming | Make a change request and get format approval from the project owner | Inform the client of the problem and follow the change request process | Conduct a proof of concept to make sure there are no problems in the revised design |  | C | When a potential design problem is identified and the team agrees to revise an already-approved design, the project manager should inform the client of the problem and follow the change request process. Formal change control ensures client awareness, proper approvals, and updated documentation before implementation. Amending design specifications directly (A) bypasses change control. Making a change request for format approval only (B) is incomplete. Conducting a proof of concept (D) should follow change approval, not precede it. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 고객에게 맞춤형 ERP 시스템을 제공하는 팀에 합류했다. 잠재적 설계 문제가 식별되어 이미 승인된 설계를 수정하기로 합의했다. PM은 무엇을 해야 하는가? | 설계 사양을 수정하고 재프로그래밍을 위해 개발 팀에 전달한다 | 변경 요청을 하고 프로젝트 소유자로부터 형식적 승인을 받는다 | 고객에게 문제를 알리고 변경 요청 프로세스를 따른다 | 수정된 설계에 문제가 없는지 확인하기 위해 개념 증명을 수행한다 |  | C | 이미 승인된 설계에 잠재적 문제가 식별되어 수정이 필요할 때, PM은 고객에게 문제를 알리고 변경 요청 프로세스를 따라야 한다. 고객 통보와 공식 변경 관리가 투명성과 거버넌스를 보장한다. 바로 수정(A)은 승인 없이 진행한다. 내부 승인만(B)은 고객을 배제한다. 개념 증명(D)은 변경 승인 후에 한다.
1631 | An agile project team is tasked with a new project. After multiple discussions with the customer, it appears that there is a lack of clarity on the requirements, which resulted in delays in the architecture and design phase. What should the team do next? | Start with design of the prototype review with the customer and gather feedback | Start with the product architecture review with the customer and gather feedback | Start with the product prototype development, review with the customer, and gather feedback | Start with the end user documentation review with the customer and gather feedback |  | C | When an agile team faces unclear requirements causing delays in architecture and design, the team should start with product prototype development, review with the customer, and gather feedback. Prototyping provides tangible output that clarifies requirements through iterative feedback. Starting with a prototype review (A) requires an existing prototype. Starting with product architecture review (B) continues the current approach that caused delays. Starting with end-user documentation review (D) is premature. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 애자일 프로젝트 팀이 새 프로젝트를 맡았다. 고객과 여러 논의 후 요구사항이 불명확하여 아키텍처와 설계에 지연이 있다. 팀은 무엇을 해야 하는가? | 고객과 프로토타입 설계를 검토하고 피드백을 수집한다 | 고객과 제품 아키텍처를 검토하고 피드백을 수집한다 | 제품 프로토타입을 개발하고 고객과 검토하며 피드백을 수집한다 | 고객과 최종 사용자 문서를 검토하고 피드백을 수집한다 |  | C | 요구사항이 불명확하여 아키텍처와 설계에 지연이 있을 때, 팀은 제품 프로토타입을 개발하고 고객과 검토하며 피드백을 수집해야 한다. 프로토타이핑이 불명확한 요구사항을 실체화하여 검증한다. 설계 검토만(A)은 실체가 없다. 아키텍처 검토(B)는 요구사항 불명확 상태에서 무의미하다. 문서 검토(D)는 구현 전 활동이 아니다.
1632 | A project manager was notified about a new regulatory requirement that could impact the project schedule. What should the project manager do first? | Assess the impact of implementing the potential regulatory requirement on the project. | Consult the project management plan for guidance on addressing the regulatory requirement. | Increase the amount of slack in the critical path to reduce the impact of the regulatory requirement. | Update the schedule and project risk register according to the regulatory requirement. |  | A | When notified about a new regulatory requirement that could impact the project schedule, the project manager should first assess the impact of implementing the requirement on the project. Impact assessment enables informed response planning. Consulting the project management plan (B) may follow but is not the first action. Increasing schedule slack (C) is premature without understanding the impact. Updating the schedule and risk register (D) implements changes before assessment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 프로젝트 일정에 영향을 줄 수 있는 새 규제 요구사항에 대해 통보받았다. PM은 무엇을 먼저 해야 하는가? | 규제 요구사항 구현이 프로젝트에 미치는 영향을 평가한다 | 규제 요구사항 대응에 대한 지침을 위해 프로젝트 관리 계획을 참조한다 | 규제 요구사항의 영향을 줄이기 위해 주공정선의 여유를 늘린다 | 규제 요구사항에 따라 일정과 프로젝트 리스크 등록부를 업데이트한다 |  | A | 새 규제 요구사항이 프로젝트 일정에 영향을 줄 수 있을 때, PM은 먼저 요구사항 구현이 프로젝트에 미치는 영향을 평가해야 한다. 영향 평가가 정보에 기반한 결정의 기초이다. 관리 계획 참조(B)는 평가 후에 한다. 여유 증가(C)는 해결이 아니다. 일정 업데이트(D)는 영향 평가 후에 한다.
1633 | A project manager is assigned to a project to develop a mobile app. The sponsor explains that the application should do better than their closest competitor's app. The sponsor's expectation is that the team can be put together and start work immediately. What should the project manager do? | Start working on the resource management plan in order to identify the best team for the project. | Define the project scope with the stakeholders and determine how formal acceptance will be obtained. | Utilize expert judgment and organizational process assets (OPAs) to estimate the effort and budget. | Review the competitor ' s app to understand the functionalities that the project scope should consider. |  | B | When a sponsor wants the team to build a mobile app that outperforms a competitor and expects immediate start, the project manager should first define the project scope with stakeholders and determine how formal acceptance will be obtained. Scope definition is essential before team assembly. Starting the resource management plan (A) is premature. Using expert judgment for estimation (C) skips scope definition. Reviewing the competitor's app (D) is research, not project initiation. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | PM이 모바일 앱 개발 프로젝트에 배정되었다. 스폰서가 경쟁사보다 우수한 앱을 원하며 즉시 시작을 기대한다. PM은 무엇을 먼저 해야 하는가? | 프로젝트에 적합한 팀을 식별하기 위해 자원 관리 계획 작업을 시작한다 | 이해관계자와 프로젝트 범위를 정의하고 공식적 인수를 어떻게 받을지 결정한다 | 전문가 판단과 OPA를 활용하여 노력과 예산을 추정한다 | 경쟁사 앱을 검토하여 프로젝트 범위에 포함할 기능을 이해한다 |  | B | 스폰서가 즉시 시작을 원하는 모바일 앱 프로젝트에서, PM은 먼저 이해관계자와 프로젝트 범위를 정의하고 인수 기준을 결정해야 한다. 명확한 범위 정의가 모든 계획의 기초이다. 자원 계획(A)은 범위 정의 후에 한다. 추정(C)은 범위 정의 후에 한다. 경쟁사 분석(D)은 유용하지만 범위 정의가 우선이다.
1634 | A project manager is managing a project in a fast-paced environment. The project manager needs to empower the team to collaborate toward an expected outcome and enable high team performance. The CEO has suggested that the project manager apply a servant leadership style. What should the project manager do to demonstrate the capabilities of a servant leader? | Encourage all team members to develop the perfect plan to achieve the desired results. | Define the project ' s objectives and create an environment where all team members can succeed in achieving them. | Assess the business case and define the project priorities to motivate all team members. | Create an environment where all team members compete to achieve the desired results. |  | B | The correct answer is B. Define the project ' s objectives and create an environment where all team members can succeed in achieving them. The PM should address team issues proactively by understanding root causes, building trust, and creating an environment that fosters collaboration and high performance. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 빠른 환경에서 프로젝트를 관리한다. 원하는 결과를 달성하기 위해 팀에 권한을 부여해야 한다. PM은 무엇을 해야 하는가? | 모든 팀원이 원하는 결과를 달성하기 위한 완벽한 계획을 개발하도록 장려한다 | 프로젝트 목표를 정의하고 모든 팀원이 목표 달성에 성공할 수 있는 환경을 만든다 | 비즈니스 케이스를 평가하고 모든 팀원에게 동기를 부여하기 위한 프로젝트 우선순위를 정의한다 | 모든 팀원이 원하는 결과 달성을 위해 경쟁하는 환경을 만든다 |  | B | 정답은 B이다. 프로젝트 목표를 정의하고 모든 팀원이 목표 달성에 성공할 수 있는 환경을 만든다. PM은 팀원의 역량 발휘를 위한 지원적 환경을 조성해야 한다. 완벽한 계획(A)은 비현실적이다. 비즈니스 케이스 평가(C)는 팀 권한 부여가 아니다. 경쟁 환경(D)은 협력을 해친다.
1635 | A healthcare organization hired a new compliance specialist to ensure that the healthcare compliance needs are met. The feedback about the new compliance specialist from the team was average. What should the project manager do to help the new compliance specialist improve? | Coordinate a one-to-one meeting with the specialist to assess the situation. | Provide time for the specialist to adjust to the pace of the project. | Escalate this situation to the manager of the area for a possible solution. | Contact the human resources (HR) manager about the team ' s feedback. |  | A | When team feedback about a new compliance specialist is average, the project manager should coordinate a one-on-one meeting with the specialist to assess the situation. Direct, private engagement allows the PM to understand the specialist's perspective, provide constructive feedback, and develop an improvement plan collaboratively. Providing time to adjust (B) is passive and does not address specific gaps. Escalating to the area manager (C) is premature before direct engagement. Contacting HR (D) is appropriate for serious issues but unnecessary at this stage. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 의료 조직이 새 컴플라이언스 전문가를 고용했다. 팀의 피드백이 평균적이다. PM은 무엇을 먼저 해야 하는가? | 전문가와 일대일 회의를 조율하여 상황을 평가한다 | 전문가가 프로젝트 속도에 적응할 시간을 제공한다 | 가능한 해결을 위해 해당 영역 관리자에게 에스컬레이션한다 | 팀의 피드백에 대해 인사부(HR) 관리자에게 연락한다 |  | A | 새 컴플라이언스 전문가에 대한 팀 피드백이 평균적일 때, PM은 먼저 전문가와 일대일 회의를 조율하여 상황을 평가해야 한다. 직접적이고 사적인 대화가 상황을 이해하고 지원을 제공한다. 적응 시간(B)은 수동적이다. 에스컬레이션(C)은 직접 대화 전에 과도하다. HR 연락(D)은 직접 평가 전에 성급하다.
1636 | On a recently completed project, a project manager noticed that some of the subcontractors approached the client directly with questions. These subcontractors had a previous direct reporting relationship with the client. The project manager is now in the initial stage of a new project with the same subcontractors and client. How should the project manager set up communications? | Consult the communications management plan from a recent project that has been closed | Ensure that the communications management plan covers contractual obligations | Update the communications management plan to allow the subcontractors to communicate directly with the client | Inform the client that all communications moving forward will go through the project manager |  | B | When subcontractors have a history of contacting the client directly and the PM starts a new project with the same parties, the project manager should ensure the communications management plan covers contractual obligations. Defining communication protocols based on contractual requirements establishes clear expectations. Using the previous project's plan (A) may not address current needs. Allowing direct subcontractor-client communication (C) perpetuates the issue. Mandating all communication through the PM (D) is overly restrictive. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 최근 완료된 프로젝트에서 일부 하청업체가 고객에게 직접 연락했다. 같은 당사자와 새 프로젝트를 시작한다. PM은 무엇을 해야 하는가? | 최근 종료된 프로젝트의 커뮤니케이션 관리 계획을 참조한다 | 커뮤니케이션 관리 계획이 계약상 의무를 포함하도록 한다 | 하청업체가 고객과 직접 소통할 수 있도록 커뮤니케이션 관리 계획을 업데이트한다 | 모든 커뮤니케이션은 앞으로 PM을 통해 진행될 것임을 고객에게 알린다 |  | B | 하청업체가 고객에게 직접 연락한 이력이 있고 같은 당사자와 새 프로젝트를 시작할 때, PM은 커뮤니케이션 관리 계획이 계약상 의무를 포함하도록 해야 한다. 계약적 커뮤니케이션 경로가 명확하면 재발을 방지한다. 이전 계획 참조(A)는 참고일 뿐이다. 직접 소통 허용(C)은 문제를 반복한다. 일방적 통보(D)는 관계를 해친다.
1637 | A project is ending and the final deliverables have been accepted by the customer. The project team is pleased that the project was a success; however, some groups within the customer's organization believe the objective of the project was not met. What should the project manager have done to avoid this issue? | Included the final report during the closing phase to ensure common understanding. | Distributed a detailed quality management plan to the key stakeholders. | Performed project reporting according to the communications management plan. | Identified key stakeholders and included all of them in project agreement discussions. |  | D | When some customer groups believe the project objective was not met despite final deliverables being accepted, the project manager should have identified key stakeholders and included all of them in project agreement discussions from the start. Early, inclusive stakeholder engagement ensures common understanding of objectives and acceptance criteria. Distributing a quality management plan (A) does not guarantee stakeholder alignment. Including a final report at closing (B) is too late. Performing project reporting per the communications plan (C) does not ensure stakeholder agreement with outcomes. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 프로젝트가 종료되고 최종 인도물이 고객에 의해 수락되었다. 그러나 일부 고객 그룹은 프로젝트 목표가 달성되지 않았다고 믿는다. PM이 이전에 무엇을 했어야 하는가? | 종료 단계에서 공통 이해를 위한 최종 보고서를 포함했다 | 주요 이해관계자에게 상세한 품질 관리 계획을 배포했다 | 커뮤니케이션 관리 계획에 따라 프로젝트 보고를 수행했다 | 주요 이해관계자를 식별하고 프로젝트 합의 논의에 모두 포함시켰다 |  | D | 최종 인도물이 수락되었으나 일부 고객 그룹이 목표 미달성을 느낄 때, PM이 이전에 주요 이해관계자를 식별하고 프로젝트 합의 논의에 모두 포함시켰어야 한다. 포괄적 이해관계자 참여가 기대치를 정렬한다. 최종 보고서(A)는 종료 시점이라 늦다. 품질 계획 배포(B)는 목표 합의가 아니다. 보고(C)는 참여가 아니다.
1638 | A key stakeholder is upset because the final product delivery has been postponed for the third time. The project manager meets with the stakeholder and discovers that there is a risk of revenue impact if a new feature is not released in 1 month. What should the project manager do? | Direct the development team to work on this requirement right away. | Inform the sponsor of the latest changes and ask the sponsor to prioritize the features. | Ask the product owner to determine if this requirement needs to be treated as a top priority. | Inform the stakeholder that the new requirement will be considered in the next release planning session. |  | C | When a key stakeholder faces revenue risk if a new feature is not released within one month, the project manager should ask the product owner to determine if this requirement needs to be treated as a top priority. The product owner manages backlog prioritization based on business value. Directing the team immediately (A) bypasses prioritization. Informing the sponsor and asking for prioritization (B) adds unnecessary escalation. Deferring to the next release planning session (D) may miss the deadline. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | 주요 이해관계자가 세 번째 납품 연기로 화가 났다. 새 기능이 한 달 내 출시되지 않으면 수익 리스크가 있다. PM은 무엇을 해야 하는가? | 개발 팀에게 이 요구사항을 즉시 작업하도록 지시한다 | 스폰서에게 최신 변경을 알리고 기능 우선순위화를 요청한다 | 제품 책임자에게 이 요구사항이 최우선으로 처리되어야 하는지 결정하도록 요청한다 | 이해관계자에게 새 요구사항이 다음 릴리스 계획 세션에서 고려될 것이라고 알린다 |  | C | 이해관계자가 수익 리스크로 긴급한 기능 출시를 원할 때, PM은 제품 책임자에게 이 요구사항이 최우선으로 처리되어야 하는지 결정하도록 요청해야 한다. 제품 책임자가 우선순위 결정 권한을 가진다. 즉시 작업 지시(A)는 우선순위 결정을 무시한다. 스폰서 알림(B)은 제품 책임자 역할이 아니다. 다음 세션 연기(D)는 긴급성을 무시한다.
1639 | A project manager is working with team members and customers who are operating in multiple countries. The team is working on implementing a new technology that includes ambiguities, uncertainties, and unknowns, both in terms of technology and of the end-user expectations for this solution. What should the project manager do to keep the stakeholders engaged? | Use feedback and decision-making tools. | Use email as a communication channel. | Use meetings as a communication channel. | Use a shared collaboration platform. |  | D | For a project with multinational stakeholders and technology uncertainties, the project manager should use a shared collaboration platform to keep stakeholders engaged. This platform enables real-time collaboration, transparent information sharing, and collective problem-solving across geographic boundaries—essential for managing ambiguities and aligning end-user expectations. Feedback and decision-making tools (A) are useful but narrower in scope than a full collaboration platform. Email (B) is asynchronous and does not support the real-time engagement needed for complex, uncertain projects. Meetings (C) alone are insufficient for ongoing, cross-border collaboration and lack the persistent documentation a platform provides. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 여러 국가의 팀원과 고객과 함께 작업한다. 기술 불확실성이 있다. 이해관계자 참여를 유지하기 위한 가장 좋은 방법은? | 피드백 및 의사결정 도구를 사용한다 | 이메일을 커뮤니케이션 채널로 사용한다 | 회의를 커뮤니케이션 채널로 사용한다 | 공유 협업 플랫폼을 사용한다 |  | D | 다국적 이해관계자와 기술 불확실성이 있는 프로젝트에서, 이해관계자 참여를 위해 공유 협업 플랫폼을 사용해야 한다. 플랫폼이 실시간 협업, 문서 공유, 지속적 참여를 가능하게 한다. 피드백 도구(A)는 부분적이다. 이메일(B)은 비동기적이고 제한적이다. 회의(C)는 시간대 차이로 어렵다.
1640 | A financial company is developing a new application for mobile banking using a hybrid approach. The project is delayed as the product concept has not yet been developed to the key stakeholder's satisfaction despite multiple design iterations. The key stakeholder has now started participating in all daily standups. The project manager has observed that the key stakeholder's presence has had a negative impact on the team's morale, while also impacting productivity. How should the project manager ensure that the stakeholder's issues are addressed effectively without impacting the team? | Schedule a team retrospective and invite the stakeholder | Talk to the team separately to address the stakeholder ' s concerns | Set up a meeting with the stakeholder to address their concerns directly | Move to a predictive design-and-requirements gathering approach |  | C | When a key stakeholder's dissatisfaction leads them to attend daily standups, negatively impacting team morale and productivity, the project manager should set up a meeting with the stakeholder to address their concerns directly. Direct communication resolves the root issue—product dissatisfaction—without disrupting team dynamics. Scheduling a team retrospective with the stakeholder (A) blurs team and stakeholder forums. Talking to the team separately (B) does not address the stakeholder's concerns. Moving to a predictive approach (D) changes methodology without resolving the interpersonal issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Hybrid/Tailoring | 금융 회사가 하이브리드 접근법으로 모바일 뱅킹 앱을 개발한다. 프로젝트가 지연되고 주요 이해관계자가 불만으로 데일리 스탠드업에 참석하여 팀 사기가 저하된다. PM은 무엇을 해야 하는가? | 팀 회고를 예약하고 이해관계자를 초대한다 | 팀과 별도로 대화하여 이해관계자의 우려를 다룬다 | 이해관계자와 회의를 설정하여 우려를 직접 다룬다 | 예측형 설계 및 요구사항 수집 접근법으로 전환한다 |  | C | 이해관계자가 불만으로 데일리 스탠드업에 참석하여 팀 사기가 저하될 때, PM은 이해관계자와 별도 회의를 설정하여 우려를 직접 다루어야 한다. 직접 대면이 근본 우려를 해결한다. 회고 초대(A)는 팀 공간을 침해한다. 팀과 별도 대화(B)는 이해관계자를 다루지 않는다. 접근법 전환(D)은 과도한 반응이다.
1641 | A project manager notices that the response action for an identified issue is insufficient for solving the problem. What should the project manager do next? | Include the issue in the risk register and update the team | Inform the stakeholders about the failure and update the issue log 1084 | Meet with the project team to find another solution | Document the continuing issue and failed solution |  | C | When a response action for an identified issue is insufficient, the project manager should meet with the project team to find another solution. Collaborative problem-solving generates better alternatives. Including the issue in the risk register (A) documents but does not resolve. Informing stakeholders and updating the issue log (B) communicates the failure but does not fix it. Documenting the failed solution (D) records history without finding a new approach. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 식별된 이슈에 대한 대응 조치가 문제 해결에 불충분하다고 발견했다. PM은 무엇을 해야 하는가? | 이슈를 리스크 등록부에 포함하고 팀을 업데이트한다 | 이해관계자에게 실패를 알리고 이슈 로그를 업데이트한다 | 프로젝트 팀과 회의하여 다른 해결책을 찾는다 | 지속되는 이슈와 실패한 해결책을 문서화한다 |  | C | 이슈 대응 조치가 불충분할 때, PM은 프로젝트 팀과 회의하여 다른 해결책을 찾아야 한다. 협력적 문제 해결이 더 나은 대안을 생성한다. 리스크 등록부 포함(A)은 이슈를 리스크로 혼동한다. 실패 알림(B)은 해결 시도가 아니다. 문서화만(D)은 수동적이다.
1642 | A project manager is leading a project at a contracting company, and the project team just completed an iteration. The product passed inspection, but an additional feature was added to the product. The customer notices the additional feature and thinks it will introduce new risks to the product. What should the project manager do to avoid this situation in the future? | Perform frequent reviews with the customer to ensure that the product is working asexpected. | Follow the proper change control process and evaluate the change for further impact. | Manage the scope baseline to influence the factors that drive change. | Work with the customer to ensure the feature adds value. |  | B | When the team adds an unauthorized feature that introduces customer concerns about risk, the project manager should follow the proper change control process and evaluate the change for further impact. Formal change control prevents unauthorized scope additions and ensures proper evaluation. Frequent customer reviews (A) are good practice but do not prevent unauthorized changes. Managing the scope baseline (C) is proactive but does not address the existing change. Ensuring the feature adds value (D) does not address the governance failure. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Hybrid/Tailoring | 계약 회사의 PM이 이터레이션을 완료했다. 팀이 승인되지 않은 기능을 추가했고 고객이 리스크를 우려한다. PM은 무엇을 해야 하는가? | 고객과 빈번한 검토를 수행하여 제품이 예상대로 작동하는지 확인한다 | 적절한 변경 통제 프로세스를 따르고 변경의 추가 영향을 평가한다 | 변경을 주도하는 요인에 영향을 미치도록 범위 기준선을 관리한다 | 고객과 협력하여 기능이 가치를 추가하는지 확인한다 |  | B | 팀이 승인되지 않은 기능을 추가하여 고객이 리스크를 우려할 때, PM은 적절한 변경 통제 프로세스를 따르고 변경의 추가 영향을 평가해야 한다. 공식적 변경 관리가 거버넌스와 투명성을 보장한다. 빈번한 검토(A)는 사후 조치이다. 범위 기준선 관리(C)는 예방적이지 현재 상황 대응이 아니다. 가치 확인(D)은 변경 승인 후에 한다.
1643 | Two project team members are updating the schedule but cannot reach an agreement on when two milestones are due. Each team member believes they are correct based on the documents they have available. What should the project manager do first to finalize the schedule? | Engage the two team members to investigate the reasons each believes that their documents are correct. | Ask the team members to send the documents and apply expert judgment to update the schedule. | Ask the two team members to meet to work the discrepancy out and let the project manager know the outcome. | Update the schedule so it is available for team members to continue the work and figure out the discrepancy later. |  | A | When two team members disagree on milestone dates based on different documents, the project manager should first engage both members to investigate why each believes their documents are correct. Root cause analysis resolves discrepancies. Applying expert judgment unilaterally (B) bypasses team collaboration. Asking them to resolve it independently (C) avoids PM facilitation. Updating the schedule without resolution (D) propagates potential errors. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Schedule | Planning | Embed Quality | Develop Schedule | Traditional PM | 두 팀원이 일정을 업데이트하고 있지만 두 마일스톤 기한에 합의하지 못한다. 각각 다른 문서를 참조한다. PM은 무엇을 먼저 해야 하는가? | 두 팀원을 참여시켜 각자의 문서가 정확하다고 믿는 이유를 조사한다 | 팀원에게 문서를 보내도록 요청하고 전문가 판단을 적용하여 일정을 업데이트한다 | 두 팀원에게 만나 불일치를 해결하고 PM에게 결과를 알리도록 요청한다 | 팀원이 작업을 계속하고 불일치를 나중에 해결하도록 일정을 업데이트한다 |  | A | 두 팀원이 다른 문서를 참조하여 마일스톤 기한에 합의하지 못할 때, PM은 두 팀원을 참여시켜 각자 문서가 정확하다고 믿는 이유를 조사해야 한다. 근본 원인 분석이 정확한 해결의 기초이다. 전문가 판단 적용(B)은 근본 원인 이해 없이 결정한다. 팀원끼리 해결(C)은 PM 리더십이 부족하다. 나중에 해결(D)은 문제를 미룬다.
1644 | A project manager is struggling to provide timely updates to the project team due to team members being spread across multiple time zones. Which communications method should the project manager utilize in this situation? | Pull communication | Push communication | Public communication | Interactive communication |  | B | When team members are spread across multiple time zones and the PM struggles with timely updates, push communication is the best method. Push communication—such as emails, recorded video updates, or targeted messages—actively delivers information without requiring simultaneous availability, ensuring inclusivity and timeliness. Pull communication (A) relies on individuals retrieving information, which may not be timely. Public communication (C) is for broad external messaging. Interactive communication (D) is ideal for complex discussions but impractical across time zones as a primary method. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Hybrid/Tailoring | 팀원이 여러 시간대에 분산되어 PM이 시기적절한 업데이트를 제공하기 어렵다. 가장 적합한 커뮤니케이션 방법은? | 풀(Pull) 커뮤니케이션 | 푸시(Push) 커뮤니케이션 | 공개 커뮤니케이션 | 인터랙티브 커뮤니케이션 |  | B | 팀원이 여러 시간대에 분산되어 시기적절한 업데이트가 어려울 때, 푸시 커뮤니케이션이 가장 적합하다. 푸시 커뮤니케이션(이메일, 녹화 영상 등)은 수신자의 시간대에 관계없이 정보를 전달한다. 풀(A)은 수신자의 적극적 검색이 필요하다. 공개(C)는 일반적이다. 인터랙티브(D)는 동시 참여가 필요하여 시간대 차이에 부적합하다.
1645 | A project manager has been assigned with initiating a large project to deliver complex equipment. Part of the project will be the result of a long research process, but once this is completed, the other part of the project must be incrementally delivered to the customer. Which approach should the project manager choose for this project? | Hybrid | Predictive | Waterfall | Agile |  | A | For a project that begins with a long research process followed by incremental delivery to the customer, the project manager should choose a hybrid approach. A hybrid approach combines predictive and adaptive methodologies, allowing the PM to apply a predictive method for the research phase—where scope, schedule, and cost are well-defined—and an agile approach for the delivery phase, where iterative releases and frequent customer feedback are essential. A purely predictive (B), waterfall (C), or agile (D) approach would not adequately address the project's dual nature of structured research followed by flexible, incremental delivery. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Tailored Approach | Process | Plan and Manage Schedule | Scope | Planning | Build an Empowered Culture | Collect Requirements | Hybrid/Tailoring | PM이 복잡한 장비를 납품하는 대형 프로젝트를 착수해야 한다. 긴 연구 프로세스 후 고객에게 점진적으로 납품한다. 어떤 접근법이 적합한가? | 하이브리드 | 예측형 | 워터폴 | 애자일 |  | A | 긴 연구 프로세스 후 고객에게 점진적으로 납품하는 프로젝트에서는 하이브리드 접근법이 적합하다. 하이브리드는 연구를 위한 예측형 구조와 점진적 납품을 위한 반복적 접근을 결합한다. 예측형(B)/워터폴(C)은 점진적 납품에 부적합하다. 애자일(D)은 긴 연구 프로세스에 부적합하다.
1646 | The customer wants to show their stakeholders a tangible outcome faster. This requires advancing a milestone. Which two things should the project manager do? (Choose two) | Escalate the Issue to senior management so they can impose a solution on the customer. | Convince the customer to keep the requirements as is and not move the milestone. | Inform the customer that moving the milestone has a very high impact on project cost. | Review the customer ' s priorities regarding the desired requirements for the milestones. | Discuss which requirements can be delivered faster with the project team. | D, E | When a customer wants to show a tangible outcome faster by advancing a milestone, the project manager should take two actions: review the customer's priorities regarding desired requirements for the milestones, and discuss which requirements can be delivered faster with the project team. This value-driven approach balances customer needs with feasibility. Escalating to senior management (A) is unnecessary. Convincing the customer to keep requirements as-is (B) ignores the request. Informing about high cost impact (C) focuses on constraints rather than solutions. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 고객이 이해관계자에게 가시적 성과를 더 빨리 보여주길 원하며 마일스톤을 앞당겨야 한다. PM이 취해야 할 두 가지 조치는? | 고위 경영진에 에스컬레이션하여 고객에게 해결책을 강요하게 한다 | 고객에게 요구사항을 유지하고 마일스톤을 옮기지 않도록 설득한다 | 마일스톤 이동이 프로젝트 비용에 매우 높은 영향을 미친다고 고객에게 알린다 | 마일스톤에 대한 원하는 요구사항에 관해 고객의 우선순위를 검토한다 | 프로젝트 팀과 어떤 요구사항을 더 빨리 전달할 수 있는지 논의한다 | D, E | 고객이 마일스톤을 앞당겨 가시적 성과를 더 빨리 보여주고 싶을 때, PM은 두 가지 조치를 취해야 한다: 고객의 우선순위를 검토하고(D), 팀과 더 빨리 전달 가능한 요구사항을 논의한다(E). 우선순위 파악과 팀 역량 평가가 실행 가능한 해결책을 만든다. 에스컬레이션(A)은 과도하다. 설득(B)은 고객 요구를 무시한다. 비용 영향만 알림(C)은 대안을 제시하지 않는다.
1647 | A project manager is managing a project in the execution phase, which was agreed upon with the sponsor. However, the sponsor is constantly micromanaging and requesting iterations that are affecting the team's effectiveness. The sponsor indicates that as long as the project scope is not affected, these iterations are needed to simplify the project. How should the project manager handle the situation? | Discuss reducing interruptions with the sponsor. | Perform stakeholder requirements activities. | Approach the sponsor about using an agile approach. | Review validation and control procedures. |  | A | When a sponsor micromanages and requests iterations that affect team effectiveness while claiming scope is unaffected, the project manager should discuss reducing interruptions with the sponsor. Direct, transparent communication about the impact on team productivity and project delivery is the appropriate first step. Performing stakeholder requirements activities (B) is procedural rather than addressing the interpersonal issue. Approaching the sponsor about using agile (C) changes methodology without addressing the behavior. Reviewing validation and control procedures (D) does not address the sponsor's micromanagement. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 스폰서와 합의된 실행 단계 프로젝트에서 스폰서가 미시관리하며 이터레이션을 요청하여 팀 효율성에 영향을 미친다. PM은 무엇을 해야 하는가? | 스폰서와 중단 줄이기를 논의한다 | 이해관계자 요구사항 활동을 수행한다 | 스폰서에게 애자일 접근법 사용을 제안한다 | 검증 및 통제 절차를 검토한다 |  | A | 스폰서가 미시관리하며 팀 효율성에 영향을 미치는 이터레이션을 요청할 때, PM은 스폰서와 중단 줄이기를 논의해야 한다. 직접적이고 정중한 대화가 문제를 해결한다. 요구사항 활동(B)은 스폰서 행동을 다루지 않는다. 애자일 제안(C)은 근본 이슈를 피한다. 검증 절차(D)는 관련이 없다.
1648 | A project engineer in country A is complaining about the sample received from the supplier in country B because the sample is not the correct length. During a telephone conference, the supplier checked the drawings and insisted that the measurement was accurate. What should the project manager do next? | Add an additional task to cut the received part according to the specifications, | Escalate the issue to the purchasing department for review. | Evaluate the procurement contract to determine the agreed-upon specifications. | Hire a company in country B to perform a quality check before shipment. |  | C | When there is a dispute between the project engineer and supplier over sample measurements, the project manager should evaluate the procurement contract to determine the agreed-upon specifications. The contract serves as the authoritative reference for resolving disputes. Adding a task to cut the part (A) accepts the error without verification. Escalating to the purchasing department (B) is premature. Hiring a local quality check company (D) adds cost before verifying contract terms. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | A국의 프로젝트 엔지니어가 B국 공급업체의 샘플이 사양과 다르다고 불만한다. 측정 도구 차이가 원인이다. PM은 무엇을 해야 하는가? | 받은 부품을 사양에 맞게 자르는 추가 작업을 추가한다 | 구매 부서에 검토를 위해 이슈를 에스컬레이션한다 | 조달 계약을 평가하여 합의된 사양을 확인한다 | B국에서 출하 전 품질 검사를 수행할 회사를 고용한다 |  | C | 프로젝트 엔지니어와 공급업체 간 측정 분쟁이 있을 때, PM은 조달 계약을 평가하여 합의된 사양을 확인해야 한다. 계약이 분쟁 해결의 기준이다. 추가 작업(A)은 근본 원인을 해결하지 않는다. 구매부 에스컬레이션(B)은 계약 확인 전에 성급하다. 품질 검사 고용(D)은 비용이 과도하다.
1649 | A key agile project team member takes a leave of absence in the middle of an iteration and will not return to work for a while. What should the project manager do next regarding the feature on which the team member was working? | Review the work in progress with the product owner to determine the next step | Determine if the team member can work from home to complete the functionality. | Assign the feature to another team member, and have them try to complete the feature by the end of this iteration | Review team capacity and reassign the functionality to additional iterations as required |  | A | When a key agile team member takes a leave of absence mid-iteration, the project manager should review the work in progress with the product owner to determine the next step. The product owner is responsible for defining and prioritizing the product backlog and can decide whether to defer, modify, or cancel the feature based on its value and urgency. Assigning the feature to another team member (C) may disrupt the team's self-organization and velocity. Reviewing team capacity and reassigning to future iterations (D) may not align with the product owner's priorities. Determining if the team member can work from home (B) depends on personal circumstances and may not be appropriate or possible. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 주요 애자일 팀원이 이터레이션 중간에 휴가를 가고 상당 기간 복귀하지 않는다. PM은 무엇을 해야 하는가? | 제품 책임자와 진행 중인 작업을 검토하여 다음 단계를 결정한다 | 팀원이 재택근무로 기능을 완료할 수 있는지 확인한다 | 다른 팀원에게 기능을 할당하여 이터레이션 종료까지 완료하게 한다 | 팀 역량을 검토하고 추가 이터레이션에 기능을 재할당한다 |  | A | 주요 애자일 팀원이 이터레이션 중 휴가를 갈 때, PM은 제품 책임자와 진행 중인 작업을 검토하여 다음 단계를 결정해야 한다. 제품 책임자가 우선순위와 가치 결정의 책임자이다. 재택근무 확인(B)은 휴가를 존중하지 않는다. 다른 팀원 할당(C)은 역량 평가 없이 성급하다. 역량 검토(D)는 유용하지만 제품 책임자 상의가 우선이다.
1650 | A project team is working remotely on a solution. The client wants the solution as soon as possible and is uncomfortable because the team members are not colocated. In addition, the client expressed concerns about the understanding of the project context and the team's decision-making process. What should the project manager do? | Encourage the client to interact with the protect collaboration platform | Update the communications management plan to satisfy the client ' s request | Ask the product owner to frequently communicate with the stakeholders | Request the client to attend the daily meetings with the project team |  | B | When a remote team's client is uncomfortable with the lack of colocation and concerned about context understanding and decision-making, the project manager should update the communications management plan to satisfy the client's request. Enhanced communication planning addresses transparency and trust. Encouraging platform interaction (A) is vague. Asking the product owner to communicate more (C) delegates PM responsibility. Requesting client attendance at daily meetings (D) may be excessive. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 원격 팀의 고객이 동일 장소 부재에 불편해하며 맥락 이해와 의사결정에 우려한다. PM은 무엇을 해야 하는가? | 고객이 프로젝트 협업 플랫폼과 상호작용하도록 장려한다 | 고객의 요청을 충족하도록 커뮤니케이션 관리 계획을 업데이트한다 | 제품 책임자에게 이해관계자와 자주 소통하도록 요청한다 | 고객에게 프로젝트 팀과의 일일 회의에 참석하도록 요청한다 |  | B | 원격 팀의 고객이 동일 장소 부재에 불편할 때, PM은 커뮤니케이션 관리 계획을 업데이트하여 고객의 요청을 충족해야 한다. 체계적 커뮤니케이션 계획이 투명성과 참여를 보장한다. 플랫폼 장려(A)는 부분적이다. 제품 책임자에게만 요청(C)은 PM 책임을 전가한다. 일일 회의 참석(D)은 과도할 수 있다.
1651 | A project manager is closing a project and preparing to hand it over to the operations team. During handover, a delayed invoice was submitted with a higher-than-planned cost against the project work. Consequently, project handover was delayed and the project's reported completion costs were increased. What should the project manager have done to avoid this situation? | Involved the finance team and discussed the issue with the vendor | Reviewed the total committed cost against the cost invoiced at project closing | Notified all vendors about the invoicing and nonpayment deadlines | Captured and reviewed all of the project work and related costs regularly |  | D | To avoid delayed invoices with unexpected costs at project closing, the project manager should have captured and reviewed all project work and related costs regularly throughout the project lifecycle. Regular monitoring enables early detection of discrepancies and timely corrective actions, preventing surprises during handover. Involving the finance team and discussing with the vendor (A) is reactive rather than preventive. Reviewing total committed cost against invoiced cost at closing (B) is a closing activity that comes too late to prevent the issue. Notifying vendors about invoicing deadlines (C) is helpful but insufficient without the internal discipline of regular cost monitoring. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 프로젝트를 종료하며 운영팀에 인수인계 중이다. 지연된 벤더 청구서가 예상치 못한 비용을 발생시켰다. PM이 이전에 무엇을 했어야 하는가? | 재무팀을 참여시키고 벤더와 이슈를 논의했다 | 프로젝트 종료 시 총 확약 비용과 청구 비용을 검토했다 | 모든 벤더에게 청구 및 미지급 기한을 통보했다 | 모든 프로젝트 작업과 관련 비용을 정기적으로 포착하고 검토했다 |  | D | 프로젝트 종료 시 지연 청구서의 예상치 못한 비용을 방지하려면, PM은 모든 프로젝트 작업과 관련 비용을 정기적으로 포착하고 검토했어야 한다. 정기적 비용 추적이 차이를 조기에 식별한다. 재무팀 참여(A)는 사후 대응이다. 종료 시 검토(B)는 너무 늦다. 벤더 통보(C)는 내부 추적을 대체하지 않는다.
1652 | Before kicking off a high-priority and complex project, what should the project manager do to ensure all project stakeholders are aware of their role scope as it relates to project activities? | Create a communications management plan. | Develop a kanban board. | Create a responsible, accountable, consulted, informed (RACI) chart. | Send a copy of the project charter to all project stakeholders. |  | C | Before kicking off a high-priority complex project, the project manager should create a RACI chart to ensure all stakeholders know their role scope for project activities. RACI clearly defines who is responsible, accountable, consulted, and informed. Creating a communications plan (A) defines communication, not roles. Developing a kanban board (B) visualizes workflow, not responsibilities. Sending the project charter (D) communicates objectives, not detailed role assignments. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | WBS/Decomposition | People | Plan and Manage Communication | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 높은 우선순위의 복잡한 프로젝트 착수 전, 모든 이해관계자가 프로젝트 활동에 대한 자신의 역할 범위를 알도록 PM은 무엇을 해야 하는가? | 커뮤니케이션 관리 계획을 작성한다 | 칸반 보드를 개발한다 | RACI(책임, 승인, 자문, 정보) 차트를 작성한다 | 프로젝트 헌장 사본을 모든 이해관계자에게 보낸다 |  | C | 복잡한 프로젝트 착수 전 모든 이해관계자가 역할 범위를 알도록 하려면, PM은 RACI 차트를 작성해야 한다. RACI는 누가 책임지고, 승인하고, 자문받고, 정보를 받는지 명확히 정의한다. 커뮤니케이션 계획(A)은 소통 방법이지 역할 정의가 아니다. 칸반(B)은 작업 흐름 도구이다. 헌장 공유(D)는 일반적 정보이지 역할 명확화가 아니다.
1653 | A project was recently flagged as being noncompliant during an inspection. Several options were suggested on how to address the noncompliance, but each may have different impacts on the budget, schedule, and quality. How should the project manager proceed? | Conduct a root cause analysis (RCA). | Review the risk register. | Determine the cost of change. | Perform a cost-benefit analysis. |  | D | The correct answer is D. Perform a cost-benefit analysis. Schedule management requires proactive monitoring and appropriate corrective actions. The PM should analyze impacts and implement suitable responses to maintain project timelines. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트가 검사 중 비준수로 표시되었다. 여러 옵션이 제안되었다. PM은 무엇을 해야 하는가? | 근본 원인 분석(RCA)을 수행한다 | 리스크 등록부를 검토한다 | 변경 비용을 결정한다 | 비용-편익 분석을 수행한다 |  | D | 정답은 D이다. 비용-편익 분석을 수행한다. 비준수 해결을 위한 여러 옵션이 제안되었을 때, 각 옵션의 비용과 편익을 분석하여 최적의 조치를 선택해야 한다. RCA(A)는 원인 파악이지 옵션 평가가 아니다. 리스크 등록부(B)는 미래 리스크이지 현재 이슈가 아니다. 변경 비용(C)은 부분적이며 편익을 고려하지 않는다.
1654 | A project has a schedule performance index (SPI) of 0.75 and a cost performance index (CPI) of 1.1. As a result, the project manager is considering either fast-tracking or crashing the project schedule to bring the project back on track again. What could be a secondary result of these actions? | Additional project scope | A decrease in the project cost | Additional resources | An increase in the project risk |  | D | When considering fast-tracking or crashing to address an SPI of 0.75, a likely secondary result is an increase in project risk. Fast-tracking introduces rework potential from overlapping activities; crashing adds coordination complexity. Additional scope (A) is unrelated. A cost decrease (B) is unlikely with crashing. Additional resources (C) is a crashing input, not a secondary result common to both methods. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Earned Value Management | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 프로젝트의 SPI가 0.75이고 CPI가 1.1이다. 패스트 트래킹이나 크래싱을 고려할 때 예상되는 이차적 결과는? | 추가 프로젝트 범위 | 프로젝트 비용 감소 | 추가 자원 | 프로젝트 리스크 증가 |  | D | SPI 0.75(일정 지연) 해결을 위해 패스트 트래킹이나 크래싱을 고려할 때, 예상되는 이차적 결과는 프로젝트 리스크 증가이다. 패스트 트래킹은 활동 중첩으로 재작업 가능성을 도입하고, 크래싱은 자원 추가로 조정 복잡성을 증가시킨다. 추가 범위(A)는 일정 만회와 무관하다. 비용 감소(B)는 오히려 반대이다. 추가 자원(C)은 크래싱의 수단이지 결과가 아니다.
1655 | A project manager has completed an assessment of the project team's performance. Some team members have performed poorly on their assigned tasks. What should the project manager do? | Develop different approaches based on team members' motivation and ability. | Provide intensive oversight to the team members who performed poorly. | Create a new standard performance measure based on project requirements. | Develop a standard approach to provide feedback to all team members. |  | A | When some team members perform poorly on assessments, the project manager should develop different approaches based on each member's motivation and ability. Individualized strategies address specific needs. Providing intensive oversight (B) is micromanagement. Creating a new standard measure (C) changes the metric, not performance. Developing a standard feedback approach (D) does not account for individual differences. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Hybrid/Tailoring | PM이 팀 성과 평가를 완료했다. 일부 팀원이 저조한 성과를 보였다. PM은 어떤 접근법을 취해야 하는가? | 팀원의 동기와 역량에 따라 다른 접근법을 개발한다 | 저조한 성과의 팀원에게 집중적 감독을 제공한다 | 프로젝트 요구사항에 기반한 새로운 표준 성과 측정을 만든다 | 모든 팀원에게 피드백을 제공하는 표준 접근법을 개발한다 |  | A | 일부 팀원이 저조한 성과를 보일 때, PM은 각 팀원의 동기와 역량에 따라 다른 접근법을 개발해야 한다. 개인화된 전략이 구체적 필요를 다룬다. 집중 감독(B)은 미시관리이다. 새 측정 기준(C)은 성과 향상을 보장하지 않는다. 표준 접근(D)은 개인 차이를 무시한다.
1656 | A project manager is trying to define a project timeline despite having incomplete and ambiguous information on requirements and regulations. What should the project manager do to finish planning? | Execute a root cause analysis to discover the underlying factors that might lead to risks 519 and issues. | Review project documents to identify and eliminate uncertainties and inconsistencies. | Perform an assumption and constraint analysis to provide more opportunities and remove limiting factors. | Conduct a strengths, weaknesses, opportunities, and threats (SWOT) analysis. |  | B | The correct answer is B. Review project documents to identify and eliminate uncertainties and inconsistencies. Compliance and regulatory requirements must be addressed proactively. The PM should assess impacts, follow proper change management processes, and ensure the project meets all applicable standards. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | PM이 요구사항과 이해관계자에 대한 불완전하고 모호한 정보에도 불구하고 프로젝트 타임라인을 정의하려 한다. PM은 무엇을 먼저 해야 하는가? | 리스크와 이슈로 이어질 수 있는 근본 요인을 발견하기 위한 근본 원인 분석을 실행한다 | 프로젝트 문서를 검토하여 불확실성과 불일치를 식별하고 제거한다 | 더 많은 기회를 제공하고 제한 요인을 제거하기 위한 가정 및 제약 분석을 수행한다 | SWOT 분석을 수행한다 |  | B | 정답은 B이다. 프로젝트 문서를 검토하여 불확실성과 불일치를 식별하고 제거한다. 불완전하고 모호한 정보가 있을 때, 기존 문서의 체계적 검토가 명확성을 확보하는 첫 단계이다. RCA(A)는 문제 발생 후 사용한다. 가정/제약 분석(C)은 문서 검토 후에 한다. SWOT(D)는 전략적 분석이다.
1657 | During the execution of a construction project, the project sponsor asks to make changes to the floor plan by adding a minimal storage room. The sponsor insists on making this last-minute change, but they would like to avoid delays to the project. Which document should the project manager refer to first? | Change management plan | Scope management plan | Cost management plan | Schedule management plan |  | A | When the sponsor asks for a last-minute floor plan change to add a storage room while avoiding delays, the project manager should first refer to the change management plan. The change management plan defines how changes are evaluated and approved. The scope management plan (B) defines scope boundaries. The cost management plan (C) addresses budget. The schedule management plan (D) addresses timing. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 건설 프로젝트 실행 중 스폰서가 저장실을 추가하여 평면도 변경을 요청한다. 지연 없이 진행하길 원한다. PM은 어떤 문서를 먼저 참조해야 하는가? | 변경 관리 계획 | 범위 관리 계획 | 비용 관리 계획 | 일정 관리 계획 |  | A | 스폰서가 마지막 순간에 평면도 변경을 요청할 때, PM은 먼저 변경 관리 계획을 참조해야 한다. 변경 관리 계획은 변경 요청의 처리, 평가, 승인 프로세스를 정의한다. 범위 관리 계획(B)은 범위 정의이지 변경 처리가 아니다. 비용(C)과 일정(D) 계획은 변경 영향 평가에 사용되지만 프로세스 정의가 아니다.
1658 | A project manager is working on a highly complex project. During the execution of the project, the local government changed certain environmental regulations, which could potentially delay the project. What immediate action should the project manager take? | Update the change request log. | Update the risk management plan. | Update the project baseline. | Update the issue log. |  | D | When the local government changes environmental regulations during project execution, this is an issue that has already occurred—not a future risk. The project manager's immediate action should be to update the issue log to document and track this external factor, its potential impact on the project, and the planned resolution. Updating the change request log (A) is premature—the issue needs to be documented first before determining if a change request is required. Updating the risk management plan (B) addresses processes, not the specific current event. Updating the project baseline (C) can only be done through formal change control and is not an immediate first step. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 복잡한 프로젝트를 수행 중이다. 지방 정부가 환경 규제를 변경했다. PM은 무엇을 즉시 업데이트해야 하는가? | 변경 요청 로그 | 리스크 관리 계획 | 프로젝트 기준선 | 이슈 로그 |  | D | 지방 정부가 프로젝트 실행 중 환경 규제를 변경할 때, 이미 발생한 이슈이지 미래 리스크가 아니다. PM은 즉시 이슈 로그를 업데이트해야 한다. 변경 요청 로그(A)는 변경 요청이 공식 제출된 후이다. 리스크 관리 계획(B)은 미래 리스크용이다. 기준선(C)은 승인된 변경 후에 업데이트한다.
1659 | The sponsor is supportive in leveraging agile approaches. The project manager is contemplating how to roll out the agile approach and gain buy-in from both project team members and stakeholders. What should the project manager do first? | Determine how to transform the organization using agile techniques, including organizational training and communications | Determine which agile software tools will be required to support agile delivery within the organization | Select a current predictive project define the approach, and provide agile training to execute the remainder of the project | Start with a pilot project of appropriate complexity and provide agile training to those who are impacted |  | D | When the sponsor supports agile and the PM needs to gain buy-in from team members and stakeholders, the first step should be to start with a pilot project of appropriate complexity and provide agile training to those impacted. A pilot demonstrates agile benefits in practice while building capability and confidence. Determining organizational transformation using agile techniques (A) is too broad for a first step. Selecting agile software tools (B) addresses tooling before methodology adoption. Defining an approach for an existing predictive project (C) does not start with an appropriate pilot selection. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 스폰서가 애자일 접근법 활용을 지원한다. PM이 팀원과 이해관계자의 동의를 얻으려 한다. 첫 단계로 무엇을 해야 하는가? | 애자일 기법을 사용하여 조직 변환 방법을 결정하고 조직 교육을 포함한다 | 조직 내 애자일 전달을 지원하는 데 필요한 애자일 소프트웨어 도구를 결정한다 | 현재 예측형 프로젝트를 선택하고 접근법을 정의하며 나머지 실행에 애자일 교육을 제공한다 | 적절한 복잡성의 파일럿 프로젝트로 시작하고 관련자에게 애자일 교육을 제공한다 |  | D | 스폰서가 애자일을 지원하고 PM이 동의를 얻으려 할 때, 적절한 복잡성의 파일럿 프로젝트로 시작하고 관련자에게 교육을 제공해야 한다. 파일럿이 실질적 결과로 가치를 입증한다. 조직 변환(A)은 너무 과도하다. 소프트웨어 도구(B)는 프로세스보다 우선이 아니다. 기존 프로젝트 전환(C)은 리스크가 높다.
1660 | A company is launching a new product and decides to transition from a predictive to an agile approach. During the third sprint, the project manager notices that the team is not working as a cohesive unit. Which two rules are appropriate for the project manager to instill in the team? (Choose two) | Only share suggestions at the end of the sprint | Follow the sprint planning | Work together daily as a team | Strive toward continuous improvement | Send communications to the entire team | D, E | When transitioning from predictive to agile and the team is not working cohesively during the third sprint, the project manager should instill two rules: strive toward continuous improvement and work together daily as a team. These principles foster collaboration and adaptation. Sharing suggestions only at sprint end (A) limits continuous feedback. Following sprint planning (B) is procedural, not behavioral. Sending communications to the entire team (D) is a communication practice, not a cohesion rule. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 회사가 예측형에서 애자일로 전환 중이다. 세 번째 스프린트에서 팀이 결속력 있게 일하지 않는다. PM이 심어줘야 할 두 가지 규칙은? | 스프린트 종료 시에만 제안을 공유한다 | 스프린트 계획을 따른다 | 매일 팀으로 함께 일한다 | 지속적 개선을 위해 노력한다 | 전체 팀에 커뮤니케이션을 보낸다 | D, E | 예측형에서 애자일로 전환 중 팀이 결속력 없이 일할 때, PM은 두 가지 규칙을 심어야 한다: 지속적 개선을 위해 노력하고(D), 전체 팀에 커뮤니케이션을 보낸다(E). 지속적 개선이 애자일 핵심 원칙이고, 팀 전체 소통이 협력을 촉진한다. 종료 시 제안 공유(A)는 소통을 제한한다. 계획 준수(B)는 예측형적이다. 매일 함께(C)는 좋지만 규칙보다 실천이다.
1661 | An agile team has completed 9 out of 10 stories for the sprint. During the retrospective, a few team members pointed out that they finished all of their stories. However, one team member failed to finish a story. What should the agile leader do? | Emphasize to the team that each member is responsible for their story but the team is collectively responsible for finishing the sprint | Work with the product owner to remove the story from the sprint because the points cannot be splits | Suggest that the team assign stones at the beginning of the sprint based on each person ' s strengths to maximize performance | Ask the team to address this at the next sprint planning instead of at the retrospective |  | A | In agile, while individual team members work on specific stories, the team collectively is responsible for sprint completion. If one story remains unfinished, it reflects on the entire team, not just the individual assigned to it. The agile leader should reinforce this shared accountability and encourage team members to support each other, ensuring all committed stories are completed in future sprints. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Be an Accountable Leader | Develop Schedule | Traditional PM | 애자일 팀이 스프린트의 10개 스토리 중 9개를 완료했다. 회고에서 팀원들이 미완료 스토리가 한 사람의 문제가 아닌 팀 전체 문제라고 지적했다. PM은 무엇을 해야 하는가? | 각 팀원이 자기 스토리에 책임이 있지만 팀이 집단적으로 스프린트 전달에 책임이 있음을 강조한다 | 제품 책임자와 협력하여 포인트를 분할할 수 없으므로 스프린트에서 스토리를 제거한다 | 팀에게 각자의 강점에 기반하여 스프린트 시작 시 스토리를 할당하도록 제안한다 | 팀에게 회고가 아닌 다음 스프린트 계획에서 이를 다루도록 요청한다 |  | A | 애자일에서 개별 팀원이 특정 스토리를 작업하지만, 팀이 집단적으로 스프린트 완료에 책임진다. 미완료 스토리는 한 사람이 아닌 전체 팀의 문제이다. PM은 이 집단 책임을 강조해야 한다. 스토리 제거(B)는 작업을 회피한다. 강점 기반 할당(C)은 자체 조직화 원칙에 반한다. 다음 계획으로 미루기(D)는 회고의 목적을 무시한다.
1662 | A project is currently in the execution phase. Because of the complexity of the project and the large number of regulatory requirements involved, the project manager decides to hold a management review with senior executives to ensure the successful implementation of project deliverables. What should the project manager review during the management review to ensure the meeting is effective? | Specialized reports created specifically for the meeting as per directions from the project sponsor. | The deliverables that are performing well and those that need more work. | Metrics and key performance indicators (KPIs) that objectively reflect the status of deliverables. | Potential changes to the project ' s strategy and the feedback from senior executives. |  | C | During a management review in the execution phase, the project manager should review metrics and key performance indicators (KPIs) that objectively reflect the status of deliverables. This data-driven approach provides a clear, quantifiable assessment of project performance against planned objectives and highlights areas needing attention. Specialized reports per sponsor direction (A) may not provide objective or comprehensive coverage. Reviewing which deliverables are performing well versus those needing work (B) is qualitative and lacks measurable rigor. Discussing potential strategy changes and executive feedback (D) is forward-looking but does not establish the objective baseline that metrics provide. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Traditional PM | 실행 단계의 프로젝트에서 규제 변경으로 인한 복잡성 때문에 경영 검토 회의가 계획되었다. PM은 무엇을 검토해야 하는가? | 프로젝트 스폰서 지시에 따라 회의 전용 특별 보고서 | 잘 수행되는 인도물과 더 많은 작업이 필요한 인도물 | 인도물 상태를 객관적으로 반영하는 지표와 핵심성과지표(KPI) | 프로젝트 전략 변경 가능성과 고위 경영진의 피드백 |  | C | 실행 단계의 경영 검토에서 PM은 인도물 상태를 객관적으로 반영하는 지표와 KPI를 검토해야 한다. 데이터 기반 접근이 투명성과 정보에 기반한 의사결정을 보장한다. 특별 보고서(A)는 편향될 수 있다. 인도물 현황(B)은 주관적이다. 전략 변경(D)은 경영진 결정이지 PM 검토 대상이 아니다.
1663 | During a project status update by the project management office (PMO), the CEO is concerned that the status of all projects suddenly changed from green to red, without warning. Upper management is used to reading traditional reports related to progress and cost, and they want to continue viewing this information. How should the PMO implement a better way to report the project's health? | Explore reporting the earned value (EV) key performance indicators (KPls) using agile progress as an input. | Perform a root cause analysis (RCA) to find out why the status of projects is deteriorating so fast. | Request the program managers to be more accurate when presenting status reports. | Ask the project managers to report on their projects using a Kanban board format. |  | A | When the CEO is concerned that all project statuses suddenly changed from green to red without warning, the PMO should explore reporting earned value (EV) KPIs using agile progress as input. EV provides objective, quantitative measures of schedule and cost performance that detect trends early. Performing root cause analysis (B) investigates past failures but does not improve reporting. Requesting more accurate reports (C) is vague. Using Kanban boards (D) changes the format without addressing predictive metrics. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | PMO의 프로젝트 상태 업데이트에서 CEO가 모든 프로젝트가 경고 없이 갑자기 녹색에서 빨간색으로 변한 것에 우려한다. PMO는 무엇을 해야 하는가? | 애자일 진행을 입력으로 사용하여 획득가치(EV) KPI 보고를 탐색한다 | 프로젝트 상태가 왜 빠르게 악화되는지 근본 원인 분석을 수행한다 | 프로그램 관리자에게 상태 보고서 제출 시 더 정확할 것을 요청한다 | 프로젝트 관리자에게 칸반 보드 형식으로 보고하도록 요청한다 |  | A | 모든 프로젝트가 경고 없이 녹색에서 빨간색으로 변할 때, PMO는 애자일 진행을 입력으로 한 획득가치 KPI 보고를 탐색해야 한다. EV는 조기 경고 시스템을 제공하여 갑작스러운 상태 변화를 방지한다. RCA(B)는 보고 방법이 아닌 근본 원인을 찾는다. 정확성 요청(C)은 보고 구조 문제를 해결하지 않는다. 칸반(D)은 형식 변경이지 조기 경고가 아니다.
1664 | A project manager is about to start the testing phase of a new project. Historical data show there is a high risk of failing the agreed acceptance criteria. How should the project manager ensure the acceptance criteria are met? | Negotiate to obtain approval if most of the tests have passed. | Perform tests and routinely track results as per the quality management plan. | Make sure the stakeholders are aware of the acceptance criteria. | Modify the acceptance criteria before the official delivery. |  | B | When historical data shows a high risk of failing acceptance criteria in the testing phase, the project manager should perform tests and routinely track results per the quality management plan. Systematic testing and tracking enables early detection and correction. Negotiating approval if most tests pass (A) lowers quality standards. Ensuring stakeholders know the criteria (C) is awareness, not execution. Modifying criteria before delivery (D) is unethical. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Risk & Issue Management | Process | Plan and Optimize Quality | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | PM이 새 프로젝트의 테스트 단계를 시작하려 한다. 과거 데이터에서 인수 기준 실패 리스크가 높다. PM은 무엇을 해야 하는가? | 대부분의 테스트가 통과하면 승인을 받도록 협상한다 | 품질 관리 계획에 따라 테스트를 수행하고 결과를 정기적으로 추적한다 | 이해관계자가 인수 기준을 인지하도록 한다 | 공식 전달 전에 인수 기준을 수정한다 |  | B | 과거 데이터에서 인수 기준 실패 리스크가 높을 때, PM은 품질 관리 계획에 따라 테스트를 수행하고 결과를 정기적으로 추적해야 한다. 체계적 테스트와 추적이 품질을 보장한다. 승인 협상(A)은 품질을 타협한다. 기준 인지(C)는 유용하지만 테스트 수행이 우선이다. 기준 수정(D)은 부적절하다.
1665 | A predictive project team comes across a scenario where they need to use some agile tools and methods. However, they did not feel this was appropriate since their organizational project management processes did not mention this. What should the project manager do in this scenario? | Work with the team to determine appropriate project methods and practices and implement them. | Create a change request to include the agile methods and proceed to implementation, | Prepare a summary and escalate this issue to the project ' s change control board (CCB), | Ensure the project team follows the organizational project management processes. |  | A | When a predictive team needs agile tools but the organizational processes do not mention them, the project manager should work with the team to determine appropriate methods and practices and implement them. Tailoring the approach to project needs is a PM responsibility. Creating a change request (B) adds bureaucracy. Escalating to the CCB (C) is disproportionate. Ensuring the team follows organizational processes only (D) prevents needed adaptation. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 예측형 팀이 일부 애자일 도구와 방법이 필요한 상황에 처했다. 그러나 조직 프로세스에 애자일이 언급되지 않았다. PM은 무엇을 해야 하는가? | 팀과 협력하여 적절한 프로젝트 방법과 실천을 결정하고 구현한다 | 애자일 방법을 포함하는 변경 요청을 생성하고 구현을 진행한다 | 이 이슈를 요약하여 프로젝트 변경통제위원회(CCB)에 에스컬레이션한다 | 프로젝트 팀이 조직의 프로젝트 관리 프로세스를 따르도록 한다 |  | A | 예측형 팀이 애자일 도구가 필요하지만 조직 프로세스에 없을 때, PM은 팀과 협력하여 적절한 방법과 실천을 결정하고 구현해야 한다. 맞춤화(tailoring)가 프로젝트 요구에 맞는 최적 접근법을 찾는다. 변경 요청(B)은 관료적이다. CCB 에스컬레이션(C)은 과도하다. 기존 프로세스 고수(D)는 프로젝트 요구를 무시한다.
1666 | The project stakeholders represent diverse organizational functions and have differing opinions about project goals. The project has been approved, but change requests could result if the stakeholders do not align on the functionality needed and the minimum viable product (MVP). What should the project manager do? | Develop a list of project goals, secure sponsor approval, and then socialize them with the direct and indirect stakeholders. | Inform the stakeholders that the project goals are in the business case and change requests must be submitted. | Secure approval from the most influential stakeholders on the project goals and the needed functionality. | Host requirements gathering meetings where all of the stakeholders can identify their project goals until agreement is reached. |  | D | When stakeholders have differing opinions about project goals and MVP, the project manager should host requirements gathering meetings where all stakeholders can identify goals until agreement is reached. Collaborative sessions build consensus and reduce future change requests. Developing goals and securing sponsor approval alone (A) excludes stakeholders. Informing stakeholders to submit change requests (B) is rigid. Securing approval only from influential stakeholders (C) risks alienating others. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 이해관계자가 다양한 조직 기능을 대표하며 프로젝트 목표에 대한 의견이 다르다. PM은 무엇을 해야 하는가? | 프로젝트 목표 목록을 작성하고 스폰서 승인을 받은 후 직접 및 간접 이해관계자와 공유한다 | 이해관계자에게 프로젝트 목표가 비즈니스 케이스에 있으며 변경 요청을 제출해야 한다고 알린다 | 가장 영향력 있는 이해관계자로부터 프로젝트 목표와 필요 기능에 대한 승인을 확보한다 | 모든 이해관계자가 합의에 도달할 때까지 목표를 식별할 수 있는 요구사항 수집 회의를 개최한다 |  | D | 이해관계자가 프로젝트 목표에 대해 다른 의견을 가질 때, PM은 모든 이해관계자가 합의에 도달할 때까지 목표를 식별하는 요구사항 수집 회의를 개최해야 한다. 포괄적 참여가 합의를 구축한다. 목록 작성 후 승인(A)은 하향식이다. 변경 요청 안내(B)는 참여를 차단한다. 영향력 있는 자만 승인(C)은 다른 이해관계자를 무시한다.
1667 | During the initiation stage of a multimedia exhibition-design project, the project manager is developing the project management plan. What should the project manager do to complete this task? | Clarify the high-level business requirements with the event organizer as a basis for forming the deliverables list. | Initiate a survey to solicit end-customer opinions and prioritize exhibition contents | Initiate an additional services agreement in case the key deliverables list was not clearly stated in the contract | Benchmark other similar exhibitions ' deliverable lists and final outcomes |  | A | The PM should clarify high-level business requirements with the event organizer as the foundation for defining the deliverables list. The project charter provides high-level project description, requirements, risks, assumptions, and constraints—serving as the primary input for developing the project management plan. Benchmarking similar events (B), surveying end customers (C), or initiating additional service agreements (D) may be useful but should follow the initial clarification of business requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Procurement | Scope | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 멀티미디어 전시 디자인 프로젝트의 착수 단계에서 PM이 프로젝트 관리 계획을 개발 중이다. 인도물 목록을 정의하기 위해 PM은 무엇을 먼저 해야 하는가? | 인도물 목록 형성의 기초로 행사 주최자와 상위 수준 비즈니스 요구사항을 명확히 한다 | 최종 고객 의견을 수집하고 전시 내용의 우선순위를 정하기 위한 설문 조사를 시작한다 | 주요 인도물 목록이 계약에 명확히 기술되지 않은 경우를 위한 추가 서비스 계약을 시작한다 | 유사한 다른 전시회의 인도물 목록과 최종 결과를 벤치마킹한다 |  | A | PM은 인도물 목록 형성의 기초로 행사 주최자와 상위 수준 비즈니스 요구사항을 명확히 해야 한다. 프로젝트 헌장이 상위 수준 요구사항을 제공하며 이해관계자와 확인이 필수이다. 설문(B)은 요구사항 확인 후에 한다. 추가 계약(C)은 계약 문제 가정이다. 벤치마킹(D)은 참고이지 기초가 아니다.
1668 | A project manager is managing multiple teams. One team member complains to the project manager about the favoritism shown by a team lead to another team member and cites multiple instances. What should the project manager do to resolve the team member's concerns? | Establish guidelines for team leads to ensure that all team members are appropriately treated. | Use a problem-solving approach and set up a discussion with the team lead and team member. | Provide direction to the team lead on how to resolve the issue with the team member directly. | Use the withdraw/avoid technique to allow the individuals to resolve the issue between themselves. |  | B | When a team member complains about favoritism by a team lead, the project manager should use a problem-solving approach and set up a discussion with both the team lead and the team member. This facilitates open communication, allows both sides to be heard, and helps identify the root cause of the conflict to reach a mutually acceptable resolution. Establishing general guidelines (A) is too generic and does not address the specific complaint. Providing direction to the team lead (C) is prescriptive without first understanding both perspectives. Using the withdraw/avoid technique (D) allows the conflict to fester and does not address the team member's legitimate concerns. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | PM이 여러 팀을 관리 중이다. 팀원이 팀 리드의 편애에 대해 불만을 제기한다. PM은 무엇을 해야 하는가? | 모든 팀원이 적절하게 대우받도록 팀 리드를 위한 가이드라인을 수립한다 | 문제 해결 접근법을 사용하여 팀 리드와 팀원 간의 토론을 설정한다 | 팀 리드에게 팀원과 직접 이슈를 해결하는 방법에 대해 지시한다 | 철회/회피 기법을 사용하여 개인들이 스스로 문제를 해결하게 한다 |  | B | 팀원이 팀 리드의 편애에 대해 불만할 때, PM은 문제 해결 접근법을 사용하여 팀 리드와 팀원 간의 토론을 설정해야 한다. 퍼실리테이션된 대화가 직접적 해결을 촉진한다. 가이드라인(A)은 일반적이며 현재 문제를 직접 다루지 않는다. 지시(C)는 지시적이다. 회피(D)는 문제를 방치한다.
1669 | An agile project will be delivered to a client based on a fixed price in cryptocurrency. Due to the volatility of cryptocurrency, both parties have agreed to adjust the scope to the value of the cryptocurrency at the end of every iteration and halt the project when the agreed price is reached. Which approach should be used in this situation? | A predictive approach with short phases. | An iterative approach starting with the highest value epic. | A flow-based approach starting with the smallest stories. | An incremental approach with a minimum viable product (MVP). |  | D | When delivering a fixed-price cryptocurrency project with scope adjusted per iteration based on currency value and halted when the agreed price is reached, the appropriate approach is an incremental approach with a minimum viable product (MVP). Incremental delivery with MVP aligns scope to fluctuating value. A predictive approach (A) lacks the flexibility needed. An iterative approach (B) focuses on refinement, not incremental delivery. A flow-based approach (C) manages throughput, not scope-to-value alignment. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 고정 가격 암호화폐 프로젝트에서 이터레이션마다 화폐 가치에 따라 범위가 조정되고 합의 가격에 도달하면 중단된다. 어떤 접근법이 적절한가? | 짧은 단계의 예측형 접근법 | 가장 높은 가치의 에픽으로 시작하는 반복적 접근법 | 가장 작은 스토리로 시작하는 흐름 기반 접근법 | 최소 실행 가능 제품(MVP)을 가진 점진적 접근법 |  | D | 고정 가격 암호화폐 프로젝트에서 이터레이션마다 범위가 조정되고 합의 가격에서 중단될 때, MVP를 가진 점진적 접근법이 적절하다. MVP가 핵심 가치를 먼저 전달하고 점진적으로 기능을 추가하여 예산 내에서 최대 가치를 전달한다. 예측형(A)은 범위 조정에 유연하지 않다. 반복적(B)은 단순 반복이다. 흐름 기반(C)은 연속 흐름에 적합하다.
1670 | Within a project, senior management is requesting project information so they can analyze the data to make project decisions. What information should the project manager provide so that senior management can get a broader view of the project? | Higher-level activities completed | Milestones status report | Resource breakdown structure (RBS) | Risk register information |  | B | A milestones status report provides senior management with the broad, high-level view needed for strategic decision-making. It highlights significant events, deliverables, and achievements at key points in the project timeline, enabling executives to understand current progress, forecast future performance, and make informed decisions aligned with organizational objectives. Higher-level activities completed (A) is vague and lacks the structured format needed for analysis. A resource breakdown structure (C) focuses on resource allocation, not overall project progress. Risk register information (D) is important but too narrowly focused on risks rather than the comprehensive project picture management needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트에서 고위 경영진이 프로젝트 정보를 요청하여 데이터를 분석하고 결정을 내리려 한다. 어떤 정보를 검토해야 하는가? | 완료된 상위 수준 활동 | 마일스톤 상태 보고서 | 자원 분류 구조(RBS) | 리스크 등록부 정보 |  | B | 고위 경영진이 전략적 의사결정을 위한 프로젝트 정보를 요청할 때, 마일스톤 상태 보고서가 적절하다. 마일스톤 보고서는 주요 이벤트, 인도물, 성과를 강조하여 광범위한 상위 수준 시각을 제공한다. 상위 수준 활동(A)은 너무 상세하다. RBS(C)는 자원 관리용이다. 리스크 등록부(D)는 리스크 관리에 특화되어 있다.
1671 | A key project stakeholder who was a big supporter and motivator for the project team is leaving the organization. The project team is experiencing low morale and poor teamwork. What should the project manager do to improve morale? | Identify the wants and aspirations of the team | Set goals and push the team to achieve the goals | Build team connections and emotional bonds | Forge consensus through team participation. |  | C | Building team connections and emotional bonds through emotional intelligence helps improve morale during difficult transitions—such as losing a key stakeholder. Emotional intelligence involves recognizing team members' feelings, expressing appreciation for contributions, providing constructive feedback, encouraging open communication, resolving conflicts respectfully, and celebrating milestones. These practices improve engagement, commitment, and productivity. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트의 주요 이해관계자이자 팀의 큰 지지자가 조직을 떠난다. PM은 어떤 기법에 집중해야 하는가? | 팀의 바람과 열망을 파악한다 | 목표를 설정하고 팀이 달성하도록 밀어붙인다 | 팀 연결과 감정적 유대를 구축한다 | 팀 참여를 통해 합의를 도출한다 |  | C | 주요 이해관계자가 떠나는 어려운 전환기에 PM은 팀 연결과 감정적 유대를 구축해야 한다. 감정 지능을 통한 유대가 사기를 향상시킨다. 바람 파악(A)은 개인적이지만 팀 결속이 아니다. 목표 밀어붙이기(B)는 감정적 지원이 없다. 합의 도출(D)은 의사결정이지 감정 지원이 아니다.
1672 | A company has undertaken a large transformation project using agile practices. The project sponsor has asked the project manager to promote the new values identified in the intended transformation to the project team. What should the project manager do? | Give recognition to team members ' behaviors that are aligned with the new values during the sprint retrospectives | Send a standard email to the team prior to every daily standup containing the new values | Add a user story during sprint planning that gives recognition to behaviors that are aligned with the new values | Organize a team meeting focusing on the new values associated with the transformation |  | C | When the sponsor asks the PM to promote new transformation values in an agile project, the project manager should add a user story during sprint planning that recognizes behaviors aligned with the new values. Embedding values in work makes them actionable. Giving recognition during retrospectives (A) reinforces but does not formalize. Sending standard emails (B) is passive. Organizing a team meeting (D) is a one-time event. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 회사가 애자일을 사용한 대규모 변환 프로젝트를 수행 중이다. 스폰서가 PM에게 새 변환 가치를 홍보하도록 요청했다. PM은 무엇을 해야 하는가? | 스프린트 리뷰에서 새 가치에 부합하는 팀원 행동에 인정을 한다 | 매일 스탠드업 전에 새 가치가 포함된 표준 이메일을 팀에 보낸다 | 스프린트 계획 중 새 가치에 부합하는 행동에 인정을 부여하는 사용자 스토리를 추가한다 | 변환과 관련된 새 가치에 초점을 맞춘 팀 회의를 조직한다 |  | C | 스폰서가 애자일 프로젝트에서 새 변환 가치를 홍보하도록 요청할 때, PM은 스프린트 계획 중 새 가치에 부합하는 행동에 인정을 부여하는 사용자 스토리를 추가해야 한다. 스토리를 통해 가치가 작업 프로세스에 통합된다. 스프린트 리뷰 인정(A)은 사후적이다. 표준 이메일(B)은 수동적이다. 팀 회의(D)는 일회성이다.
1673 | During an iteration demo, a customer noticed an enhancement they would like to make to the product. What should the team do next? | Refine and estimate the enhancement so the size is known. | Add it to the product backlog to be completed in the future. | Ask the product owner to prioritize the item with the customer. | Start working on the enhancement for the customer immediately. |  | C | When a customer notices a desired enhancement during an iteration demo, the team should ask the product owner to prioritize the item with the customer. The product owner manages backlog priority and customer needs. Refining and estimating the enhancement (A) is premature without prioritization. Adding to the backlog without prioritization (B) skips value assessment. Starting work immediately (D) bypasses the product owner's authority. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 이터레이션 데모 중 고객이 제품 개선을 발견했다. 팀은 무엇을 해야 하는가? | 개선 사항을 정제하고 추정하여 크기를 파악한다 | 제품 백로그에 추가하여 미래에 완료한다 | 제품 책임자에게 고객과 함께 항목의 우선순위를 정하도록 요청한다 | 고객을 위해 즉시 개선 작업을 시작한다 |  | C | 고객이 이터레이션 데모 중 개선을 발견할 때, 팀은 제품 책임자에게 고객과 함께 항목의 우선순위를 정하도록 요청해야 한다. 제품 책임자가 백로그 우선순위를 관리한다. 정제/추정(A)은 우선순위 결정 후에 한다. 백로그 추가(B)는 우선순위 없이 추가한다. 즉시 작업(D)은 우선순위 평가를 건너뛴다.
1674 | A project manager is managing a project for a government-owned company using an iterative approach. The first useful release to production consisted of three iterations. Each iteration was successfully verified by the client's representatives in the test environment. However, when the team started deploying to the production environment, the security team declined it. What should the project manager have done to prevent this? | Implemented the authorization in the first iteration | Deployed to production after the first iteration | Reviewed the compliance requirements with stakeholders | Planned smaller iterations to review the results more often |  | C | The PM should have reviewed compliance requirements with stakeholders—including the security team—during the planning phase. Early engagement identifies potential security gaps and aligns expectations. In iterative projects, security considerations must be integrated into each iteration rather than deferred to deployment. Regular stakeholder communication ensures everyone remains aligned on compliance requirements throughout the development process. This proactive approach would have prevented the security team's rejection during production deployment. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | PM이 반복적 접근법을 사용하는 정부 소유 회사 프로젝트를 관리한다. 첫 번째 유용한 릴리스가 보안 미준수로 거부되었다. PM이 이전에 무엇을 했어야 하는가? | 첫 번째 이터레이션에서 인증을 구현했다 | 첫 번째 이터레이션 후 프로덕션에 배포했다 | 이해관계자와 컴플라이언스 요구사항을 검토했다 | 결과를 더 자주 검토하기 위해 더 작은 이터레이션을 계획했다 |  | C | 보안 미준수로 릴리스가 거부되었을 때, PM은 계획 단계에서 보안 팀을 포함한 이해관계자와 컴플라이언스 요구사항을 검토했어야 한다. 조기 참여가 보안 격차를 식별한다. 인증 구현(A)은 기술 조치이지 검토가 아니다. 프로덕션 배포(B)는 검토 없이 위험하다. 작은 이터레이션(D)은 요구사항 누락을 해결하지 않는다.
1675 | During project execution, a key team member has to be moved to another critical project for the company. Currently, there is no other team member who can fill that role. What should the project manager do first? | Communicate the problem to the sponsor to force the key member to be maintained on the project. | Initiate a change request and replace the key member as soon as possible. | Explain to the company the importance of maintaining the key member on the project according to the vision of the project. | Evaluate the impact of the key team member ' s removal from the project, look for alternatives, and submit a change request if required. |  | D | When a key team member must be moved to another critical project with no replacement available, the project manager should first evaluate the impact of the removal, look for alternatives, and submit a change request if required. Impact assessment enables informed decision-making. Communicating with the sponsor to force retention (A) is confrontational. Initiating a change request immediately (B) skips assessment. Explaining the project's importance (C) is persuasive but does not assess impact. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 실행 중 주요 팀원이 다른 중요 프로젝트로 이동해야 한다. 현재 대체 가능한 자원이 없다. PM은 무엇을 해야 하는가? | 스폰서에게 문제를 알려 주요 팀원을 유지하도록 강제한다 | 변경 요청을 시작하고 가능한 빨리 주요 팀원을 교체한다 | 회사에 프로젝트 관리 계획에 따라 주요 팀원 유지의 중요성을 설명한다 | 주요 팀원 제거의 영향을 평가하고 대안을 찾아 변경 요청을 제출한다 |  | D | 주요 팀원이 대체 없이 다른 프로젝트로 이동해야 할 때, PM은 먼저 제거의 영향을 평가하고 대안을 찾아 변경 요청을 제출해야 한다. 체계적 영향 분석이 정보에 기반한 결정을 가능하게 한다. 강제 유지(A)는 비현실적이다. 즉시 교체(B)는 대체 자원이 없다. 중요성 설명(C)은 해결책을 제시하지 않는다.
1676 | During a discovery phase, a project manager coordinated a brainstorming event to determine the best strategy to meet the product release date. After the project overview, the subject matter expert (SME) remained quiet during the call. What should the project manager do next? | Pose direct questions to the participants based on their area of expertise to start engaging them in the conversation. | Cancel the meeting if team members do not have the skills to suggest a strategy. | Create a strategy based on the project manager ' s experience and get approval during the call. | Review the roles and responsibilities during the call to determine who is accountable for the strategy. |  | A | The correct answer is A. Pose direct questions to the participants based on their area of expertise to start engaging them in the conversation. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 발견 단계에서 PM이 전략을 결정하기 위한 브레인스토밍을 조직했으나 참가자들이 참여하지 않는다. PM은 무엇을 해야 하는가? | 참가자의 전문 분야에 기반하여 직접 질문을 하여 대화에 참여시킨다 | 팀원이 전략을 제안할 기술이 없으면 회의를 취소한다 | PM의 경험에 기반한 전략을 만들고 통화 중 승인을 받는다 | 통화 중 역할과 책임을 검토하여 전략 책임자를 결정한다 |  | A | 정답은 A이다. 참가자의 전문 분야에 기반하여 직접 질문을 하여 대화에 참여시킨다. 맞춤형 질문이 참여를 유도하고 전문 지식을 끌어낸다. 회의 취소(B)는 기회를 낭비한다. PM 경험 기반 전략(C)은 참여적이지 않다. 역할 검토(D)는 전략 논의를 지연시킨다.
1677 | The key stakeholders of a project would like to be actively involved in the review of product increments. What should the project manager do? | Encourage their participation in release and sprint reviews. | Update the communications management plan for key stakeholders. | Analyze their interest and influence to manage expectations. | Identify the needs and expectations of key stakeholders. |  | A | When key stakeholders want to be actively involved in reviewing product increments, the project manager should encourage their participation in release and sprint reviews. Sprint reviews are the agile event designed for stakeholder feedback on increments. Analyzing interest and influence (B) is planning work already done. Updating the communications plan (C) addresses documentation. Identifying needs and expectations (D) is early-stage analysis when they have already expressed their desire. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 프로젝트의 주요 이해관계자가 제품 증분 검토에 적극 참여하고 싶어한다. PM은 무엇을 해야 하는가? | 릴리스 및 스프린트 리뷰에 참여를 장려한다 | 주요 이해관계자를 위해 커뮤니케이션 관리 계획을 업데이트한다 | 기대치를 관리하기 위해 관심과 영향력을 분석한다 | 주요 이해관계자의 니즈와 기대를 파악한다 |  | A | 주요 이해관계자가 제품 증분 검토에 적극 참여하고 싶을 때, PM은 릴리스 및 스프린트 리뷰에 참여를 장려해야 한다. 스프린트 리뷰가 증분을 검토하는 애자일 행사이다. 커뮤니케이션 계획 업데이트(B)는 간접적이다. 관심/영향 분석(C)은 관리적이지 참여가 아니다. 니즈 파악(D)은 이미 참여 의사를 밝혔으므로 불필요하다.
1678 | During the planning for a long project, the project manager recognized that several members of the team are new to their roles. How should the project manager incorporate this into planning? | Increase the overall project duration to account for the inexperienced team memberson 1208 the project. | Ensure planning has accounted for replacing team members in new project roles whodo not deliver on project goals. | Revisit the project resource allocation to remove the inexperienced team membersassigned to the project. | Assess the training requirements and ensure time for professional developmenttraining by senior members. |  | D | When several team members are new to their roles on a long project, the project manager should assess training requirements and ensure time for professional development training by senior members. Capability building addresses the root cause. Increasing project duration (A) does not build skills. Planning to replace underperformers (B) is reactive. Removing inexperienced members (C) reduces team capacity. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Adopt a Holistic View | Plan Scope Management | Traditional PM | 긴 프로젝트 계획 중 PM이 여러 팀원이 역할에 경험이 부족함을 인식했다. PM은 무엇을 해야 하는가? | 미경험 팀원을 고려하여 전체 프로젝트 기간을 늘린다 | 성과를 내지 못하는 새 역할 팀원 교체를 위한 계획을 포함한다 | 프로젝트에 배정된 미경험 팀원을 제거하기 위해 자원 할당을 재검토한다 | 교육 요구사항을 평가하고 선임 팀원에 의한 전문성 개발 교육 시간을 확보한다 |  | D | 여러 팀원이 역할에 경험이 부족할 때, PM은 교육 요구사항을 평가하고 선임 팀원에 의한 전문성 개발 교육 시간을 확보해야 한다. 역량 개발이 장기적 팀 성과를 향상시킨다. 기간 증가(A)는 수동적이다. 교체 계획(B)은 성장 기회를 부정한다. 미경험자 제거(C)는 비현실적이다.
1679 | During a project, the project manager finds an opportunity to reduce the project cost by completing a deliverable ahead of schedule with a minimal impact on project resources. However, the client has only been focused on the next milestone. How should the project manager approach this situation? | Review the change management plan to discuss early benefits realization with the client. | Evaluate whether the client ' s request will add extra features to the project deliverable. | Apply additional resources to realize the early deliverable and ensure the next milestone is achieved. | Focus on the deliverable of the next project milestone as per the client ' s strict instructions. |  | A | The PM should review the change management plan to discuss potential early benefits realization with the client. This involves evaluating the change's impact, considering the client's milestone focus, and explaining how early deliverable completion could add project value without significantly affecting resources. Aligning project progress with client expectations through transparent change management ensures beneficial outcomes for all parties. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | PM이 인도물을 일찍 완료하여 비용 절감 기회를 발견했다. 그러나 고객이 다음 마일스톤에 엄격하게 집중하라고 지시한다. PM은 무엇을 해야 하는가? | 변경 관리 계획을 검토하여 고객과 조기 혜택 실현을 논의한다 | 고객의 요청이 프로젝트 인도물에 추가 기능을 추가할지 평가한다 | 조기 인도를 실현하기 위해 추가 자원을 투입하고 다음 마일스톤을 보장한다 | 고객의 엄격한 지시에 따라 다음 프로젝트 마일스톤의 인도에 집중한다 |  | A | 조기 완료로 비용 절감 기회가 있지만 고객이 다음 마일스톤에 집중하라고 할 때, PM은 변경 관리 계획을 검토하여 조기 혜택 실현을 논의해야 한다. 변경 관리 절차를 통해 기회를 공식적으로 평가한다. 추가 기능 평가(B)는 관련이 없다. 추가 자원(C)은 고객 지시에 반한다. 마일스톤 집중(D)은 기회를 놓친다.
1680 | An organization in a regulated industry has decided to switch from a predictive to an agile delivery approach. It has been decided that the ongoing projects will adopt Scrum, and the project manager is still accountable for the project outcomes. During the fourth sprint demo, the customer notices that a feature is not compliant with the regulations. What should the project manager do? | Have the scrum master organize a weekly meeting with the compliance officer, theproduct owner, and the project team. | Have the product owner review the user stories in the product backlog with thecompliance officer on a regular basis to identify any gaps. | Have the product owner consult with the change control board (CCB) to have thenecessary compliance requirements implemented. | Have the team consult with the compliance officer to update the definition of done(DoD) for the user stories in the past sprint. |  | B | The PM should ensure the product owner collaborates with the compliance officer to review user stories in the product backlog for regulatory alignment. This supports the agile principle of early and continuous delivery of valuable software while maintaining compliance. Retroactively updating the Definition of Done for past sprints wastes resources. Involving the change control board introduces unnecessary bureaucracy. Weekly meetings with the compliance officer may reduce team autonomy and self-organization. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 규제 산업의 조직이 예측형에서 애자일로 전환하기로 했다. 2년간의 규제 준수 이력이 있다. PM은 무엇을 확인해야 하는가? | 스크럼 마스터가 컴플라이언스 담당자, 제품 책임자, 팀과 주간 회의를 조직한다 | 제품 책임자가 컴플라이언스 담당자와 제품 백로그의 사용자 스토리를 정기적으로 검토한다 | 제품 책임자가 CCB와 상의하여 컴플라이언스 요구사항을 백로그에 추가한다 | 팀이 컴플라이언스 담당자와 상의하여 사용자 스토리의 완료 정의(DoD)를 업데이트한다 |  | B | 규제 산업에서 애자일로 전환할 때, PM은 제품 책임자가 컴플라이언스 담당자와 백로그의 사용자 스토리를 정기적으로 검토하도록 해야 한다. 조기 지속적 규제 정렬이 애자일 원칙에 부합한다. 주간 회의(A)는 형식적이고 과도하다. CCB 상의(C)는 예측형적이다. DoD 업데이트(D)는 유용하지만 백로그 수준 검토가 우선이다.
1681 | A new team member is added to a self-organizing team. The new team member is reluctant to speak and take part in team discussions or decisions. Which two actions should the team take to engage this new team member? (Choose two) | Coach the new team member to improve engagement with the team. | Report to the project manager about the new team member's behavior | Force the new team member to participate in activities that are considered easy | Revisit the team ' s discussion on team behaviors and norms | Facilitate an open discussion on all ideas and perspectives | A, D | When a new member of a self-organizing team is reluctant to speak or participate, the team should (D) revisit discussion on team behaviors and norms, and (A) coach the new member to improve engagement. These build understanding and confidence. Reporting to the PM (B) undermines self-organization. Forcing easy activities (C) is patronizing. Open discussion on ideas (E) may overwhelm the reluctant member. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scaled Agile | People | Align Stakeholder Expectations | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 자체 조직화 팀에 새 팀원이 추가되었으나 발언과 토론 참여를 꺼린다. 팀은 어떤 두 가지 조치를 취해야 하는가? | 새 팀원이 팀과의 참여를 개선하도록 코칭한다 | 새 팀원의 행동에 대해 프로젝트 관리자에게 보고한다 | 쉬운 것으로 간주되는 활동에 새 팀원을 강제 참여시킨다 | 팀 행동과 규범에 대한 토론을 재검토한다 | 모든 아이디어와 관점에 대한 개방적 토론을 촉진한다 | A, D | 자체 조직화 팀의 새 팀원이 참여를 꺼릴 때, 팀은 두 가지 조치를 취해야 한다: 팀 행동과 규범에 대한 토론을 재검토하여(D) 안전한 환경을 재확인하고, 새 팀원이 참여를 개선하도록 코칭한다(A). 규범 재확인과 코칭이 참여를 촉진한다. 관리자 보고(B)는 자체 조직화 원칙에 반한다. 강제 참여(C)는 심리적 안전을 해친다. 개방적 토론(E)은 좋지만 새 팀원 맞춤 지원이 아니다.
1682 | A project sponsor commonly asks the project manager to skip project retrospectives due to time constraints. However, the project manager persists in running this critical ceremony by reducing the time for preparation and for discussion. What are two issues that these actions by the project manager could cause? (Choose two) | Lessons learned from other teams to not be considered | Time management plan for the retrospective workshop to not be updated | A lot of discussions that yield no results or possibly too many results | A lack of direction and motivation for the team in the workshop | A focus on the negative and a disinterest in further improvements | C, D | Skipping or shortening retrospectives creates two key risks: (1) Unfocused discussions that yield either no actionable results or an overwhelming number of superficial recommendations, and (2) A negative, blame-oriented atmosphere that erodes motivation for continuous improvement. Without proper preparation time, the team cannot develop clear agendas or explore root causes adequately. Without sufficient discussion time, analysis remains superficial and team members may perceive retrospectives as wasteful rather than valuable. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 스폰서가 시간 제약으로 인해 회고를 건너뛰도록 PM에게 요청한다. 회고를 건너뛰면 예상되는 두 가지 결과는? | 다른 팀의 교훈이 고려되지 않는다 | 회고 워크숍의 시간 관리 계획이 업데이트되지 않는다 | 결과가 없거나 너무 많은 결과를 낳는 많은 토론 | 워크숍에서 팀의 방향과 동기 부족 | 부정적인 것에 초점을 맞추고 추가 개선에 대한 무관심 | C, D | 회고를 건너뛰면 두 가지 핵심 리스크가 발생한다: 결과가 없거나 너무 많은 피상적 권고를 낳는 비집중적 토론(C), 그리고 워크숍에서 팀의 방향과 동기 부족(D). 정기적 회고 없이 팀은 체계적 개선 기회를 잃는다. 다른 팀 교훈(A)은 회고의 주요 목적이 아니다. 시간 관리 계획(B)은 부차적이다. 부정적 초점(E)은 회고의 반대 효과이다.
1683 | A project manager has been assigned to an existing infrastructure project. The current project manager, who is retiring, and the project sponsor have had a good working relationship for many years. The project sponsor has expressed dissatisfaction with having a new project manager assigned to the project. What should the project manager do? | Set up a new communication plan and stakeholder engagement plan and submit to the project sponsor. | Set up a detailed meeting with the project sponsor and brief them about the project ' s 564 progress. | Discuss the strategic benefits of the project and schedule communication with the project sponsor. | Send weekly project reports to the project sponsor to provide an opportunity for engagement and feedback. |  | B | When a project sponsor is dissatisfied with having a new PM assigned, the project manager should set up a detailed meeting with the sponsor and brief them about the project's progress. Direct, proactive communication establishes rapport, demonstrates competence, and addresses dissatisfaction through engagement. Setting up communication and engagement plans first (A) is too process-oriented before personal connection. Discussing strategic benefits (C) is important but secondary to building the relationship. Sending weekly reports (D) provides updates but lacks the interpersonal connection needed to rebuild trust. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | PM이 기존 인프라 프로젝트에 배정되었다. 은퇴하는 현 PM이 스폰서가 새 PM 배정에 불만이라고 전했다. 새 PM은 무엇을 해야 하는가? | 새 커뮤니케이션 계획과 이해관계자 참여 계획을 수립하여 스폰서에게 제출한다 | 스폰서와 상세 회의를 설정하여 프로젝트 진행 상황을 브리핑한다 | 프로젝트의 전략적 이점을 논의하고 스폰서와 커뮤니케이션 일정을 잡는다 | 스폰서에게 주간 프로젝트 보고서를 보내 참여와 피드백 기회를 제공한다 |  | B | 프로젝트 스폰서가 새 PM 배정에 불만일 때, PM은 스폰서와 상세 회의를 설정하여 프로젝트 진행 상황을 브리핑해야 한다. 직접적이고 사전적인 참여가 신뢰를 구축한다. 새 계획 제출(A)은 관계 구축 전에 형식적이다. 전략적 이점 논의(C)는 간접적이다. 주간 보고서(D)는 일방향이며 관계 구축이 아니다.
1684 | A project manager is assigned to a technical research project. The project team has already been assigned, and the main subject matter expert (SME) sends the project manager a list of the technical skills required for the execution of this project. What should the project manager do next? | Meet with the project team to understand their skills and identify potential gaps and training requirements. | Ask the functional manager to review the resource pool and recommend the right individuals to join the team. | Send the list to the project team and ask them to get training on the required skills. | Discuss the list with the project sponsor to confirm that the resources have the required skills. |  | A | When a main SME provides a list of required technical skills, the project manager should meet with the project team to understand their skills and identify potential gaps and training requirements. Direct assessment ensures targeted development. Sending the list and asking for self-training (B) is passive. Asking the functional manager to recommend individuals (C) is not feasible since the team is already assigned. Discussing with the sponsor (D) is not the sponsor's responsibility. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | PM이 기술 연구 프로젝트에 배정되었다. 주요 SME가 필요한 기술 스킬 목록을 제공했다. PM은 무엇을 해야 하는가? | 프로젝트 팀과 만나 기술을 파악하고 잠재적 격차와 교육 요구사항을 식별한다 | 기능 관리자에게 자원 풀을 검토하고 적합한 인원을 추천하도록 요청한다 | 목록을 프로젝트 팀에 보내고 필요한 기술에 대한 교육을 받도록 요청한다 | 프로젝트 스폰서와 목록을 논의하여 자원이 필요한 기술을 갖추고 있는지 확인한다 |  | A | 주요 SME가 필요 기술 목록을 제공할 때, PM은 프로젝트 팀과 만나 기술을 파악하고 격차와 교육 요구를 식별해야 한다. 직접 평가가 정확한 격차 분석을 가능하게 한다. 기능 관리자(B)는 기존 팀에 대한 것이 아니다. 목록 발송(C)은 일방적이다. 스폰서 논의(D)는 기술적 평가가 아니다.
1685 | A project that is using an incremental approach has colocated team members and is using a kanban board to visualize the work in progress (WIP). A key external stakeholder requests that all project activities be placed on hold until a status report is distributed. What should the project manager have done to avoid this situation? | Stored project documentation in a shared folder. | Invited all of the stakeholders to daily standup meetings. | Organized monthly meetings with the external stakeholders. | Sent weekly status update reports to all of the stakeholders. |  | D | When a key external stakeholder halts project activities due to lack of status information, the project manager should have sent weekly status update reports to all stakeholders. Regular proactive communication prevents information gaps and manages expectations. Storing documentation in shared folders (A) is passive. Inviting stakeholders to daily standups (B) may be excessive for external stakeholders. Organizing monthly meetings (C) may be too infrequent. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Kanban | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 점진적 접근법의 프로젝트에서 동일 장소 팀원과 칸반 보드를 사용 중이다. 외부 이해관계자가 상태 정보 부족으로 활동을 중단시켰다. PM이 이전에 무엇을 했어야 하는가? | 프로젝트 문서를 공유 폴더에 저장했다 | 모든 이해관계자를 일일 스탠드업에 초대했다 | 외부 이해관계자와 월간 회의를 조직했다 | 모든 이해관계자에게 주간 상태 업데이트 보고서를 보냈다 |  | D | 외부 이해관계자가 상태 정보 부족으로 활동을 중단시킬 때, PM은 모든 이해관계자에게 주간 상태 업데이트 보고서를 보냈어야 한다. 정기적 사전 커뮤니케이션이 투명성을 보장한다. 공유 폴더(A)는 풀 방식이라 부족하다. 스탠드업 초대(B)는 외부 이해관계자에게 과도하다. 월간 회의(C)는 빈도가 부족하다.
1686 | A project requires the installation of a call center to support operations. It is estimated that the call center will need 100 people working on weekdays from 8:00 a.m. to 5:00 p.m. and weekends from 8:00 a.m. to 12:00 p.m. What should the project manager do? | Work with 50% of the people internally and contract the other 50% to an outside company. | Delegate the analysis to the human resources (HR) department in order to organize the call center operations. | Conduct an alternative analysis to decide whether to hire people directly or contract with a company to do the job. | Implement the call center with internal staff to ensure the work is performed according to the company' s culture. |  | C | When a call center installation requires 100 people with specific schedules, the project manager should conduct an alternative analysis to decide whether to hire directly or contract out. Analysis ensures the best staffing approach. Splitting 50/50 internally and externally (A) is arbitrary. Delegating to HR (B) abdicates PM responsibility. Using only internal staff (D) may not be optimal. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트에 콜센터 설치가 필요하다. 특정 일정에 100명이 필요하다. PM은 무엇을 먼저 해야 하는가? | 내부 50%와 외부 계약 50%로 운영한다 | HR 부서에 분석을 위임하여 콜센터 운영을 조직한다 | 직접 고용 또는 외부 계약 여부를 결정하기 위해 대안 분석을 수행한다 | 회사 기준에 맞게 내부 직원으로 콜센터를 구현한다 |  | C | 콜센터에 100명의 특정 일정이 필요할 때, PM은 직접 고용과 외부 계약을 비교하는 대안 분석을 수행해야 한다. 분석이 최적의 자원 전략을 보장한다. 50/50 분배(A)는 분석 없는 결정이다. HR 위임(B)은 PM 책임을 전가한다. 내부 전용(D)은 대안 평가 없이 제한적이다.
1687 | An agile project is running activities to define the minimum viable product (MVP). During the session, the project manager identifies some mandatory regulations but there is no consensus to include these regulations in the MVP because it may extend the duration of the project. What should the project manager do? | Get commitment from the team to include all of the required regulations | Train the team on the new regulations as requested by management | Ask the project sponsor to add more time to the project. | Share with participants the need to focus only on product functionality |  | A | When defining the MVP and mandatory regulations are identified, the project manager should get commitment from the team to include all required regulations. Regulatory compliance is non-negotiable—the MVP must meet minimum legal and safety requirements regardless of its impact on project duration. The PM should explain the importance and rationale of the regulations to the team and stakeholders, seeking their agreement and support. Training the team on regulations (B) does not resolve the lack of consensus. Asking the sponsor for more time (C) may not be feasible and does not address the root cause of the disagreement. Focusing only on functionality (D) ignores regulatory requirements and exposes the project to compliance risks. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scaled Agile | Process | Plan and Optimize Quality | Scope | Planning | Be an Accountable Leader | Plan Scope Management | Traditional PM | 애자일 프로젝트에서 MVP를 정의하는 활동 중 필수 규제가 식별되었다. PM은 무엇을 해야 하는가? | 모든 필수 규제를 포함하도록 팀의 약속을 받는다 | 경영진 요청에 따라 새 규제에 대해 팀을 교육한다 | 프로젝트 스폰서에게 더 많은 시간을 추가하도록 요청한다 | 참가자에게 제품 기능에만 집중해야 한다고 공유한다 |  | A | MVP 정의 중 필수 규제가 식별될 때, PM은 모든 필수 규제를 포함하도록 팀의 약속을 받아야 한다. 규제 준수는 협상 불가이다. 팀 교육(B)은 약속이 아닌 지식 전달이다. 시간 추가(C)는 약속 전에 성급하다. 기능만 집중(D)은 규제를 무시한다.
1688 | When a project manager is trying to determine a leadership style to use on a project, what should they consider? | Number of tasks on the protect | Project timeline | Culture of the organization | Experience of the project manager |  | C | When determining a leadership style for a project, the project manager should consider the culture of the organization. Organizational culture shapes effective leadership approaches. Number of tasks (A) relates to workload, not leadership style. Project timeline (B) influences urgency but not style selection. PM experience (D) is one factor but organizational culture is more determinant. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 프로젝트에서 사용할 리더십 스타일을 결정하려 할 때, 무엇을 고려해야 하는가? | 프로젝트의 작업 수 | 프로젝트 타임라인 | 조직의 문화 | 프로젝트 관리자의 경험 |  | C | 프로젝트에서 리더십 스타일을 결정할 때 조직의 문화를 고려해야 한다. 조직 문화가 효과적인 리더십 접근법을 형성한다. 작업 수(A)는 리더십이 아닌 일정 관리이다. 타임라인(B)은 일정 요소이다. PM 경험(D)은 한 가지 요소이지만 조직 문화가 더 결정적이다.
1689 | A project team is implementing a new solution that will be distributed worldwide. Due to a new issue that has a global impact, several government agencies are implementing new regulations that will affect the solution. The project manager must assess and prioritize the impact of these changes on the project scope and backlog. Which analytical tool can be used by the project manager to define this scenario? | Valuable rare, inimitable resources, and organization (VRIO) | Strengths, weaknesses opportunities, and threats (SWOT) | Political, economic social, technological legal, and environmental (PESTLE) | Net present value (NPV) |  | C | When new government regulations from multiple agencies will affect a global solution, the project manager should use a PESTLE analysis to define the scenario. PESTLE examines political, economic, social, technological, legal, and environmental factors. VRIO (A) assesses competitive advantage of resources. SWOT (B) analyzes internal strengths/weaknesses and external opportunities/threats. NPV (D) evaluates financial return. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 프로젝트 팀이 전 세계에 배포될 새 솔루션을 구현 중이다. 여러 정부 기관의 새 규제가 글로벌 영향을 미친다. 시나리오를 정의하기 위해 어떤 분석을 사용해야 하는가? | VRIO 분석 | SWOT 분석 | PESTLE 분석 | 순현재가치(NPV) |  | C | 여러 정부 기관의 새 규제가 글로벌 솔루션에 영향을 미칠 때, PESTLE 분석을 사용해야 한다. PESTLE은 정치, 경제, 사회, 기술, 법률, 환경 요인을 검토하여 포괄적 외부 환경 분석을 제공한다. VRIO(A)는 자원 분석이다. SWOT(B)는 내외부 요인이지만 거시환경에 특화되지 않았다. NPV(D)는 재무 분석이다.
1690 | A project manager who is working with a virtual team needs to mentor an entry-level colleague. This team member informs the project manager that they feel demotivated and excluded from the team. What should the project manager do first to resolve the situation? | Speak with the team member about their engagement and contributions | Conduct a team building event to involve the team member | Assign the team member to a team where they can contribute more | Perform an assessment of each member of the project team |  | A | When a team member feels demotivated and excluded, the PM should first use interpersonal skills—communication, emotional intelligence, and mentoring—to speak with them privately and understand the root cause. Acknowledging their contributions and providing constructive feedback helps them feel valued, respected, and supported. This foundational step must occur before any structural changes or formal interventions are considered. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 가상 팀의 PM이 신입 동료를 멘토링해야 한다. 팀원이 의욕이 없고 소외감을 느낀다. PM은 무엇을 먼저 해야 하는가? | 팀원과 참여와 기여에 대해 대화한다 | 팀원을 참여시키기 위한 팀 빌딩 이벤트를 실시한다 | 더 많이 기여할 수 있는 팀에 팀원을 배정한다 | 프로젝트 팀 각 멤버의 평가를 수행한다 |  | A | 팀원이 의욕이 없고 소외감을 느낄 때, PM은 먼저 대인관계 기술을 사용하여 팀원과 개인적으로 대화해야 한다. 직접적 소통과 감정 지능이 근본 원인을 이해하게 한다. 팀 빌딩(B)은 개인 문제를 직접 다루지 않는다. 팀 재배치(C)는 문제를 회피한다. 팀 평가(D)는 개인 이슈와 무관하다.
1691 | A new manufacturing line project is planned to be delivered in iterations for the equipment installation phase. During one of the iterations, the vendor communicates to the project manager that they will not be able to deliver some of the equipment at the agreed dates. What should the project manager do next? | Find another vendor who can fulfill the delivery dates | Update the product backlog m order to address the delays | Review the procurement agreements to address the situation | Replan the remaining iterations according to the new installation dates |  | C | When a vendor communicates inability to deliver equipment on agreed dates during an iterative installation project, the project manager should review the procurement agreements to address the situation. Contractual review clarifies obligations, penalties, and resolution options. Finding another vendor (A) may be premature. Updating the product backlog (B) does not address the procurement issue. Replanning remaining iterations (D) may follow but should come after reviewing the contract. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 반복적 접근법의 새 제조 라인 프로젝트에서 벤더가 합의된 날짜에 장비를 납품할 수 없다고 알렸다. PM은 무엇을 해야 하는가? | 납품 날짜를 충족할 수 있는 다른 벤더를 찾는다 | 지연을 해결하기 위해 제품 백로그를 업데이트한다 | 상황을 해결하기 위해 조달 계약을 검토한다 | 새 설치 날짜에 따라 나머지 이터레이션을 재계획한다 |  | C | 벤더가 합의된 날짜에 장비를 납품할 수 없을 때, PM은 조달 계약을 검토하여 상황을 해결해야 한다. 계약이 의무, 벌칙, 구제를 정의한다. 다른 벤더(A)는 계약 검토 전에 성급하다. 백로그 업데이트(B)는 조달 문제가 아니다. 재계획(D)은 계약 상 구제 검토 후에 한다.
1692 | An agile team is working on a 2-week sprint to deliver business value. About 1 week after the sprint starts, the team members do not feel confident about the product increment they are building. They do not want to wait until the end of the sprint and want to validate the product increment with the product owner now. What should the project manager do to mitigate this risk? | Schedule an additional interim demo with the product owner. | Address the issue as part of the retrospective. | Ask the team to work overtime toward the end of the sprint to meet the original sprint end date. | Extend the sprint end date in anticipation of feedback from the product owner that will require extra work. |  | A | When an agile team lacks confidence in the product increment mid-sprint, the project manager should schedule an additional interim demo with the product owner. Early validation provides timely feedback to adjust course before the sprint ends. Addressing it in the retrospective (B) is too late—the retrospective occurs after the sprint. Asking the team to work overtime (C) does not address the confidence issue. Extending the sprint end date (D) violates sprint time-boxing. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Risk | Monitoring & Controlling | Focus on Value | Monitor Risks | Traditional PM | 애자일 팀이 2주 스프린트를 진행 중이다. 스프린트 시작 1주 후 팀이 제품 증분에 자신이 없다. PM은 무엇을 해야 하는가? | 제품 책임자와 추가 중간 데모를 예약한다 | 회고의 일환으로 이슈를 다룬다 | 팀에게 스프린트 종료일을 맞추기 위해 초과 근무를 요청한다 | 제품 책임자 피드백으로 추가 작업이 필요할 것을 예상하여 스프린트 종료일을 연장한다 |  | A | 스프린트 중간에 팀이 제품 증분에 자신이 없을 때, PM은 제품 책임자와 추가 중간 데모를 예약해야 한다. 조기 검증이 시기적절한 피드백을 제공한다. 회고 대기(B)는 스프린트가 끝나야 한다. 초과 근무(C)는 지속 가능하지 않다. 종료일 연장(D)은 스프린트 약속을 위반한다.
1693 | A project has recently completed its production go-live, meeting the project's completion requirements in accordance with the scope document. However, the customer has been requesting a number of significant project enhancements. How should the project manager address the customer's requests? | Tell the client that any extra work will require new scoping and pricing before the team can start additional enhancements. | Explain to the customer that the project has been completed and enhancements will follow the change management process. | Inform the customer that the project scope is completed and that further enhancements will require the initiation of a new project. | Adjust the project completion requirements to the proposed enhancements and inform the project team of the additional work. |  | B | When the project is complete per scope and the customer requests significant enhancements, the project manager should explain that the project has been completed and enhancements will follow the change management process. Formal change control maintains governance, budget control, and resource planning. Telling the client extra work requires new scoping and pricing (A) implies a new project prematurely. Informing them a new project is needed (C) skips change control. Adjusting completion requirements (D) modifies criteria without approval. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 프로젝트가 범위에 따라 프로덕션 가동을 완료했다. 고객이 상당한 개선을 요청한다. PM은 무엇을 해야 하는가? | 추가 작업은 팀 시작 전에 새 범위 지정과 가격 책정이 필요하다고 고객에게 말한다 | 프로젝트가 완료되었고 개선은 변경 관리 프로세스를 따를 것임을 고객에게 설명한다 | 프로젝트 범위가 완료되었고 추가 개선은 새 프로젝트가 필요함을 고객에게 알린다 | 제안된 개선에 맞게 프로젝트 완료 요구사항을 조정하고 프로젝트 팀에 알린다 |  | B | 프로젝트가 범위대로 완료되고 고객이 개선을 요청할 때, PM은 프로젝트가 완료되었고 개선은 변경 관리 프로세스를 따를 것임을 설명해야 한다. 변경 관리가 체계적 평가를 보장한다. 새 범위/가격(A)은 즉각적이지만 프로세스를 무시한다. 새 프로젝트(C)는 너무 단정적이다. 요구사항 조정(D)은 완료된 프로젝트를 변경한다.
1694 | A project manager has just started a new project for an organization that dislikes budget and schedule deviations. The project stakeholders are very engaged and want to ensure there is clear visibility of the project's risks and progress. How should the project manager handle stakeholder expectations? | Add buffers to the schedule to accommodate unforeseen changes | Discuss the risk response strategies with the stakeholders | Develop a communications management plan to share updates with stakeholders | Ensure the risk register includes all identified risks |  | C | When an organization dislikes deviations and stakeholders want clear visibility of risks and progress, the project manager should develop a communications management plan to share updates with stakeholders. Formalized communication ensures predictable transparency and systematic reporting. Adding schedule buffers (A) is a planning tactic, not a stakeholder management approach. Discussing risk response strategies (B) is one element of risk management. Ensuring the risk register includes all risks (D) is important but does not establish visibility mechanisms. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | PM이 예산과 일정 편차를 싫어하는 조직의 새 프로젝트를 시작했다. 이해관계자가 리스크와 진행에 대한 명확한 가시성을 원한다. PM은 무엇을 해야 하는가? | 예상치 못한 변경을 수용하기 위해 일정에 버퍼를 추가한다 | 이해관계자와 리스크 대응 전략을 논의한다 | 이해관계자와 업데이트를 공유하는 커뮤니케이션 관리 계획을 개발한다 | 리스크 등록부에 식별된 모든 리스크가 포함되도록 한다 |  | C | 조직이 편차를 싫어하고 이해관계자가 가시성을 원할 때, PM은 이해관계자와 업데이트를 공유하는 커뮤니케이션 관리 계획을 개발해야 한다. 체계적 커뮤니케이션이 투명성과 신뢰를 구축한다. 버퍼(A)는 일정 관리이다. 리스크 전략(B)은 리스크 관리이다. 리스크 등록부(D)는 커뮤니케이션이 아니다.
1695 | In a multinational, multilocation project with virtual teams, a project manager has established a project baseline. The project manager discovers that multiple risk elements have appeared. The project manager did not foresee these risks during the planning stage of the project. What should the project manager calculate to address this critical budgetary situation? (Choose two) | Benefits management control in the project | Mitigation control in the project | Contingency control in the project and rebaseline | Integrated change control in the project | Currency exchange rate | C, D | When unforeseen risks appear in a multinational virtual project affecting the budget, the project manager should calculate (C) contingency control and rebaseline, and (D) integrated change control. Contingency addresses risk reserves; change control manages formal adjustments. Benefits management control (A) focuses on outcomes, not budget. Mitigation control (B) is not a standard term. Currency exchange rate (E) is one factor but not a calculation method. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 다국적 가상 팀 프로젝트에서 기준선이 설정되었다. 예상치 못한 리스크가 예산에 영향을 미친다. PM은 무엇을 계산해야 하는가? | 프로젝트의 혜택 관리 통제 | 프로젝트의 완화 통제 | 프로젝트의 비상 통제 및 재기준선 | 프로젝트의 통합 변경 통제 | 환율 | C, D | 다국적 프로젝트에서 예상치 못한 리스크가 예산에 영향을 미칠 때, PM은 두 가지를 계산해야 한다: 비상 통제 및 재기준선(C)으로 비상 예비비의 적정성을 평가하고, 통합 변경 통제(D)로 모든 변경을 체계적으로 관리한다. 혜택 관리(A)는 프로젝트 혜택이지 예산 아니다. 완화 통제(B)는 리스크 대응이지 예산 통제가 아니다. 환율(E)은 특정 요인이다.
1696 | A project manager is facilitating meetings with a diverse team, considering that the team members come from different cultures and have different backgrounds. What should the project manager do to facilitate effective communication? | Assign the work packages based on geographical working groups. | Create incentives to promote better communication among team members. | Plan for communication training workshops for all team members. | Understand and consider the emotions of each team member. |  | D | The correct answer is D. Understand and consider the emotions of each team member. Communication management ensures information flows effectively to all stakeholders. The PM should tailor communication methods, frequency, and level of detail to meet stakeholder needs and project requirements. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 다양한 문화의 팀과 회의를 퍼실리테이션 중이다. PM은 무엇을 해야 하는가? | 지리적 작업 그룹에 따라 작업 패키지를 할당한다 | 팀원 간 더 나은 커뮤니케이션을 촉진하기 위한 인센티브를 만든다 | 모든 팀원을 위한 커뮤니케이션 교육 워크숍을 계획한다 | 각 팀원의 감정을 이해하고 고려한다 |  | D | 정답은 D이다. 각 팀원의 감정을 이해하고 고려한다. 다양한 문화의 팀에서 감정 지능이 효과적 커뮤니케이션의 핵심이다. PM은 문화적 차이를 존중하고 각 개인의 감정을 이해해야 한다. 지리적 할당(A)은 협업을 제한한다. 인센티브(B)는 간접적이다. 교육 워크숍(C)은 유용하지만 감정적 이해가 우선이다.
1697 | During an inspection, the production phase was stopped because the inspector claimed that regulatory labels were missing. What should the project manager do? | Review the quality management plan | Review the risk management plan | Conduct an expert judgment evaluation. | Update the lessons learned register |  | A | The PM should review the quality management plan to understand requirements for regulatory labels, inspection criteria, nonconformity resolution procedures, and quality documentation. The QMP defines how project quality is planned, assured, controlled, and managed. Expert judgment (A) is not a substitute for established quality procedures. Lessons learned (C) are important for closure but not the immediate priority. The risk management plan (D) addresses risks but isn't the direct response to a quality nonconformity. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Closing | Embed Quality | Close Project or Phase | Traditional PM | 검사 중 규제 라벨 누락으로 생산 단계가 중단되었다. PM은 무엇을 해야 하는가? | 품질 관리 계획을 검토한다 | 리스크 관리 계획을 검토한다 | 전문가 판단 평가를 실시한다 | 교훈 등록부를 업데이트한다 |  | A | 규제 라벨 누락으로 생산이 중단될 때, PM은 품질 관리 계획을 검토해야 한다. 품질 관리 계획이 규제 라벨 요구사항, 검사 기준, 부적합 해결 절차를 정의한다. 리스크 관리(B)는 미래 리스크이다. 전문가 판단(C)은 계획 검토 후에 한다. 교훈(D)은 해결 후에 기록한다.
1698 | A functional manager is concerned that the project's quality management techniques have advanced beyond the department's capabilities and wants the project team to review all quality management activities in two full-day workshops the following week. What should the project manager do next? | Indicate that this was a not a requirement identified during project planning and it is outside of the scope. | Draft a project decision request to include in the scope for the current iteration and ask the sponsor to approve. | Explain that the team is fully dedicated to the current sprint activities and negotiate a mutually agreeable time. | Add this to the project backlog and have the product owner determine where it fits in terms of priority. |  | C | When a functional manager wants the project team to review quality management activities in two full-day workshops the following week, the project manager should explain that the team is dedicated to current sprint activities and negotiate a mutually agreeable time. This respects both parties' needs. Indicating it is out of scope (A) is dismissive. Drafting a decision request for the sponsor (B) escalates unnecessarily. Adding to the backlog for product owner prioritization (D) may not be appropriate for a process review. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Schedule | Planning | Embed Quality | Define Activities | Traditional PM | 기능 관리자가 프로젝트 품질 관리 기법이 부서 역량을 초과했다고 우려하며 다음 주 2일간 워크숍을 원한다. PM은 무엇을 해야 하는가? | 프로젝트 계획 중 식별되지 않은 요구사항이며 범위 밖임을 나타낸다 | 현재 이터레이션에 포함할 결정 요청 초안을 작성하고 스폰서에게 요청한다 | 팀이 현재 스프린트 활동에 전념하고 있음을 설명하고 상호 합의된 시간을 협상한다 | 프로젝트 백로그에 추가하고 제품 책임자가 우선순위를 결정하게 한다 |  | C | 기능 관리자가 다음 주 2일간 워크숍을 원할 때, PM은 팀이 현재 스프린트에 전념하고 있음을 설명하고 상호 합의된 시간을 협상해야 한다. 스프린트 보호와 이해관계자 요구의 균형이 중요하다. 범위 밖(A)은 협력을 거부한다. 결정 요청(B)은 관료적이다. 백로그 추가(D)는 기능적 요청을 스프린트 항목으로 취급한다.
1699 | After a project team has been working on a project for several months, the project is cancelled. The project sponsor is putting pressure on the project manager to perform closeout duties as fast as possible so that the project team can move on to other work. The project sponsor has instructed the team not to waste time archiving the project artifacts for the cancelled project. How should the project manager handle this situation? | Document the project sponsor ' s instructions as the archived project artifacts. | Archive the project artifacts on the project manager ' s local computer for future reference | Comply with the project sponsor ' s request to not archive the project artifacts. | Consult with the project management office (PMO) for guidance on project artifacts. |  | D | When a cancelled project's sponsor pressures the PM to skip archiving project artifacts, the project manager should consult with the PMO for guidance on project artifacts. The PMO maintains standards for archiving and organizational knowledge preservation. Complying with the sponsor's request (C) risks losing valuable information. Documenting the sponsor's instructions as artifacts (A) is insufficient. Archiving on the PM's local computer (B) is insecure and inaccessible. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트가 취소되었다. 스폰서가 PM에게 프로젝트 산출물 보관을 건너뛰도록 압박한다. PM은 무엇을 해야 하는가? | 스폰서의 지시를 보관된 프로젝트 산출물로 문서화한다 | PM의 로컬 컴퓨터에 미래 참조를 위해 프로젝트 산출물을 보관한다 | 스폰서의 산출물 보관하지 않겠다는 요청에 따른다 | 프로젝트 산출물에 대한 지침을 위해 PMO와 상의한다 |  | D | 취소된 프로젝트에서 스폰서가 보관을 건너뛰라고 할 때, PM은 PMO와 상의해야 한다. PMO가 프로젝트 산출물에 대한 표준과 정책을 유지한다. 스폰서 지시 문서화(A)는 지침을 따르지 않는다. 로컬 보관(B)은 조직 표준에 반한다. 요청 준수(C)는 조직 프로세스를 무시한다.
1700 | An organization is adopting an agile mindset. On the first agile project, the project manager faced an issue because the team was unable to make decisions on time. What should the project manager do to address the problem? | Invite senior leadership to a team-building workshop and restate the importance ofaccountability and leadership under the new company direction. | Define clear guidelines on how decisions should be made under the neworganizational policy and reinforce them with the team on every occasion. | Adopt an autocratic leadership style and dictate all decisions in order to speed up theteam ' s velocity. | Assess the situation to understand how the organization ' s culture impacts the decisionmaking process, and coach the team toward a new model. |  | D | When an agile team in an organization adopting agile cannot make timely decisions, the project manager should assess how the organization's culture impacts decision-making and coach the team toward a new model. Understanding cultural barriers enables effective coaching. Inviting leadership to a workshop (A) is indirect. Defining decision guidelines and reinforcing them (B) is helpful but does not address cultural root causes. Adopting autocratic leadership (C) contradicts agile principles. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 조직이 애자일 마인드셋을 채택 중이다. 첫 애자일 프로젝트에서 팀이 적시에 결정을 내리지 못한다. PM은 무엇을 해야 하는가? | 고위 리더십을 팀 빌딩 워크숍에 초대하고 책임과 투명성의 중요성을 재강조한다 | 새 조직 정책 하에서 결정을 내리는 명확한 가이드라인을 정의하고 팀에 자율권을 강화한다 | 독재적 리더십 스타일을 채택하고 모든 결정을 지시하여 팀 속도를 높인다 | 조직 문화가 의사결정 프로세스에 어떤 영향을 미치는지 평가하고 팀을 솔루션 지향적으로 코칭한다 |  | D | 애자일 팀이 적시에 결정을 내리지 못할 때, PM은 조직 문화가 의사결정에 어떤 영향을 미치는지 평가하고 팀을 코칭해야 한다. 근본 원인 이해와 코칭이 지속적 변화를 만든다. 워크숍 초대(A)는 근본 원인을 다루지 않는다. 가이드라인(B)은 유용하지만 문화 평가가 우선이다. 독재적 스타일(C)은 애자일에 반한다.
1701 | A project manager schedules virtual daily standup meetings for a project, but half of the team members regularly join late or miss the meeting altogether. What should the project manager do? | Use one-to-one virtual meetings because they are more efficient. | Ask senior management for coaching regarding this situation. | Agree on a new time and reschedule the daily standups. | Discuss ground rules with the team that will include daily meetings. |  | C | When half the team regularly joins late or misses daily standup meetings, the project manager should agree on a new time and reschedule the standups. Finding a time that works for all team members ensures participation and maintains the meeting's value for alignment and feedback. Using one-to-one meetings instead (A) loses the team-wide visibility benefit. Asking management for coaching (B) does not directly solve the scheduling issue. Discussing ground rules (D) addresses behavior but may not resolve underlying scheduling conflicts. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Focus on Value | Acquire Resources | Traditional PM | PM이 가상 일일 스탠드업을 예약했지만 팀원 절반이 정기적으로 늦거나 불참한다. PM은 무엇을 해야 하는가? | 더 효율적인 일대일 가상 회의를 사용한다 | 이 상황에 대해 고위 경영진에게 코칭을 요청한다 | 새 시간에 합의하고 일일 스탠드업을 재예약한다 | 일일 회의를 포함할 기본 규칙을 팀과 논의한다 |  | C | 팀원 절반이 스탠드업에 늦거나 불참할 때, PM은 새 시간에 합의하고 재예약해야 한다. 모든 팀원에게 맞는 시간을 찾는 것이 참여를 보장한다. 일대일(A)은 팀 소통을 제한한다. 경영진 코칭(B)은 과도하다. 기본 규칙(D)은 유용하지만 시간 문제가 근본 원인이면 재예약이 우선이다.
1702 | During the implementation of a project, the project team discovered a new opportunity. After an internal review, the project team agreed that the opportunity is outside of the project scope. The project manager decided to update the risk register and escalate the opportunity to a higher level. What should the project manager do next with this opportunity? | Establish a contingency reserve to support the opportunity | No more action is required | Share this opportunity with another project | Further monitor the opportunity |  | C | When an opportunity is identified outside the project scope, the PM should document it in the risk register and escalate it to a higher authority—such as the project sponsor, portfolio manager, or organizational management—who can decide whether to pursue it. The PM may also recommend sharing the opportunity with another project that could benefit from it, or proposing a new project to exploit it. Establishing contingency reserves (a negative-risk strategy), simply continuing to monitor, or taking no action all fail to capitalize on positive risks proactively. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 실행 중 팀이 새 기회를 발견했으나 프로젝트 범위 밖이라고 판단했다. PM은 무엇을 해야 하는가? | 기회를 지원하기 위한 비상 예비비를 설정한다 | 더 이상의 조치가 필요하지 않다 | 이 기회를 다른 프로젝트와 공유한다 | 기회를 추가로 모니터링한다 |  | C | 식별된 기회가 프로젝트 범위 밖일 때, PM은 이 기회를 다른 프로젝트와 공유해야 한다. 리스크 등록부에 문서화하고 포트폴리오 관리자나 스폰서에게 에스컬레이션하여 조직 전체가 혜택을 받을 수 있게 한다. 비상 예비비(A)는 범위 밖이므로 부적절하다. 무조치(B)는 기회를 놓친다. 모니터링(D)은 수동적이다.
1703 | A project manager has been assigned to lead a software project to generate savings at a major financial institution. Initially, the project duration was 13 months, but due to various issues during execution, it was extended to 16 months. By month 11, the expected savings were exceeded but not all of the functionalities planned for that date were completed. How should the project manager inform the stakeholders of the project's progress? | Complete the outstanding functionalities before informing the sponsor of the project progress. | Communicate the benefit expectations and the action plan for the pending functionalities. | Report that the project has not fulfilled all the expected functionalities. | Send an email with the monthly project progress to all relevant stakeholders. |  | B | When a project exceeds its timeline but achieves early savings beyond expectations, the PM should communicate progress transparently using objective performance metrics. Earned value management (EVM) indicators—including CPI, SPI, and earned value—provide a comprehensive, fact-based picture of both cost and schedule performance. This allows stakeholders to understand that while the timeline extended, the project is delivering measurable financial value. Clear, data-driven reporting builds stakeholder confidence even when some metrics deviate from the baseline. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 소프트웨어 프로젝트가 타임라인을 초과했지만 기대 이상의 조기 절감을 달성했다. PM은 무엇을 해야 하는가? | 스폰서에게 프로젝트 진행을 알리기 전에 미완성 기능을 완료한다 | 혜택 기대치와 미완성 기능에 대한 조치 계획을 커뮤니케이션한다 | 프로젝트가 모든 기대 기능을 충족하지 못했다고 보고한다 | 모든 관련 이해관계자에게 월간 프로젝트 진행 이메일을 보낸다 |  | B | 프로젝트가 타임라인을 초과했지만 기대 이상의 절감을 달성할 때, PM은 혜택 기대치와 미완성 기능에 대한 조치 계획을 투명하게 커뮤니케이션해야 한다. 객관적 성과 지표를 사용한 투명한 소통이 핵심이다. 완료 후 알림(A)은 투명성이 부족하다. 미충족 보고(C)는 성과를 무시한다. 월간 이메일(D)은 일반적이고 상황에 맞지 않는다.
1704 | The project manager is reviewing a project's progress and notices that one of the risks has become an issue. What should the project manager do to address the situation? | Meet with the project team and customer to brainstorm about potential solutions. | Schedule a high-priority meeting with the project stakeholders to discuss the issue. | Collaborate with the relevant stakeholders on implementing the risk response plan. | Initiate a change request to obtain additional funds from the management reserve. |  | C | When a risk becomes an issue during project execution, the project manager should collaborate with relevant stakeholders on implementing the risk response plan. Activating predefined responses ensures proactive issue management. Brainstorming with the team and customer (A) is exploratory when a response plan already exists. Scheduling a high-priority stakeholder meeting (B) discusses but may not act. Initiating a change request for management reserves (D) is premature before implementing the planned response. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 프로젝트 진행을 검토하다가 리스크 중 하나가 이슈가 되었음을 발견했다. PM은 무엇을 해야 하는가? | 프로젝트 팀과 고객과 회의하여 잠재적 해결책을 브레인스토밍한다 | 프로젝트 이해관계자와 이슈를 논의하기 위한 고우선순위 회의를 예약한다 | 관련 이해관계자와 협력하여 리스크 대응 계획을 실행한다 | 관리 예비비에서 추가 자금을 확보하기 위한 변경 요청을 시작한다 |  | C | 리스크가 이슈가 되었을 때, PM은 관련 이해관계자와 협력하여 리스크 대응 계획을 실행해야 한다. 사전에 정의된 대응을 활성화하는 것이 효율적이다. 브레인스토밍(A)은 대응 계획이 이미 있으면 불필요하다. 고우선순위 회의(B)는 계획 실행보다 느리다. 변경 요청(D)은 대응 계획 실행 후에 필요 시 한다.
1705 | A project manager is working with a Scrum team that is continually missing deadlines. The steering committee is concerned about the project as it is not clear that it will deliver the expected value. After some analysis, the project manager discovers there is a mismatch of competencies in one of the teams. What should the project manager do? | Emphasize to the teams the importance of meeting the agreed deadlines | Provide appropriate training to compensate for the mismatch. | Update the project schedule to reflect the delay | Accept the risk of the project missing deadlines due to the mismatch. |  | B | When a Scrum team continually misses deadlines due to a competency mismatch, the project manager should provide appropriate training to compensate for the mismatch. Building team competencies improves performance and value delivery. Emphasizing deadline importance (A) adds pressure without solving the root cause. Updating the schedule (C) accepts delay. Accepting the risk (D) does not resolve the capability gap. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 스크럼 팀이 역량 불일치로 계속 마감을 놓치고 있다. 운영 위원회가 우려한다. PM은 무엇을 해야 하는가? | 팀에게 합의된 마감 준수의 중요성을 강조한다 | 불일치를 보완하기 위한 적절한 교육을 제공한다 | 지연을 반영하도록 프로젝트 일정을 업데이트한다 | 역량 불일치로 인한 마감 미준수 리스크를 수용한다 |  | B | 스크럼 팀이 역량 불일치로 마감을 놓칠 때, PM은 불일치를 보완하기 위한 적절한 교육을 제공해야 한다. 팀 역량 구축이 근본 원인을 해결한다. 중요성 강조(A)는 역량 문제를 해결하지 않는다. 일정 업데이트(C)는 문제를 수용하지만 해결하지 않는다. 리스크 수용(D)은 수동적이다.
1706 | A project manager meets with the development team to estimate the time required to complete a software application. The software developers are new to the company, and they have never developed a similar application. Which estimation technique should the project manager recommend? | Planning poker | Analogous estimating | Three-point estimating | Parametric estimating |  | C | When software developers are new to the company and have never developed a similar application, the project manager should recommend three-point estimating. This technique captures optimistic, pessimistic, and most likely estimates, accounting for uncertainty when experience is limited. Planning poker (A) works best with experienced agile teams familiar with the work. Analogous estimating (B) requires historical data from similar projects. Parametric estimating (D) requires statistical relationships that may not be available. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | PM이 개발 팀과 만나 소프트웨어 애플리케이션 완료에 필요한 시간을 추정한다. 개발자들이 회사에 처음이고 유사 애플리케이션을 개발한 적이 없다. 어떤 추정 기법을 권장해야 하는가? | 플래닝 포커 | 유사 추정 | 3점 추정 | 모수 추정 |  | C | 소프트웨어 개발자들이 회사에 처음이고 유사 애플리케이션 경험이 없을 때, PM은 3점 추정을 권장해야 한다. 이 기법은 낙관적, 비관적, 최빈값 추정을 포착하여 불확실성을 반영한다. 플래닝 포커(A)는 상대적 추정이지 절대 시간이 아니다. 유사 추정(B)은 과거 경험이 없어 불가하다. 모수 추정(D)은 과거 데이터가 필요하다.
1707 | In a daily standup meeting, a developer indicates that a backlog item will not be delivered because they need to take an unexpected leave for the next couple of days. The backlog item is a prerequisite for a feature expected by users in the next sprint review. What should the project lead do? | Ask the development manager to provide a replacement for a couple of days. | Work with the product owner to inform the users that the feature is delayed. | Ask the developer to postpone the leave until the backlog item is delivered. | Work with the product owner to change the priorities in the sprint backlog. |  | D | When a developer must take unexpected leave and their backlog item is a prerequisite for a feature expected in the next sprint review, the project lead should work with the product owner to change the priorities in the sprint backlog. This collaborative reprioritization adjusts the sprint goals to accommodate the capacity change while ensuring the most critical work is addressed. Asking the development manager for a replacement (A) may not be feasible on short notice. Informing users the feature is delayed (B) accepts the delay without first exploring alternatives through reprioritization. Asking the developer to postpone leave (C) disrespects personal needs and may not be appropriate. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Build an Empowered Culture | Develop Schedule | Traditional PM | 데일리 스탠드업에서 개발자가 예상치 못한 휴가로 백로그 항목을 납품할 수 없다고 한다. 이 항목은 다음 스프린트 리뷰에서 예상되는 기능의 전제 조건이다. 프로젝트 리더는 무엇을 해야 하는가? | 개발 관리자에게 며칠간 대체 인력을 요청한다 | 제품 책임자와 협력하여 사용자에게 기능이 지연되었음을 알린다 | 개발자에게 백로그 항목이 납품될 때까지 휴가를 연기하도록 요청한다 | 제품 책임자와 협력하여 스프린트 백로그의 우선순위를 변경한다 |  | D | 개발자의 예상치 못한 휴가로 전제 조건 항목이 지연될 때, 프로젝트 리더는 제품 책임자와 협력하여 스프린트 백로그의 우선순위를 변경해야 한다. 이는 스프린트 목표에 최소 영향을 미치도록 적응한다. 대체 인력(A)은 며칠로는 복잡한 항목을 인수하기 어렵다. 지연 통보(B)는 우선순위 조정 전에 성급하다. 휴가 연기(C)는 개인을 존중하지 않는다.
1708 | A project team member does not submit the project status report on time. The team member is frustrated about being required to complete the report. The team member believes that the report does not reflect the reality of the project, has too many pages, and will not be read by stakeholders. What should the project manager do? | Instruct the team member to provide the report and document this in the performance review. | Reassign the report to another team member to prepare and submit it as requested. | Review the requirements of the report with the team member to redefine its purpose. | Escalate to the team member ' s functional manager that the report was not submitted as requested. |  | C | When a team member fails to submit a status report and believes it does not reflect reality, the project manager should review the report requirements with the team member to redefine its purpose. Collaborative refinement addresses concerns and ensures value. Instructing the member and documenting in performance review (A) is punitive. Reassigning the report (B) does not address the underlying issue. Escalating to the functional manager (D) is premature. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀원이 프로젝트 상태 보고서를 제시간에 제출하지 않는다. 팀원은 보고서가 현실을 반영하지 않는다고 불만이다. PM은 무엇을 해야 하는가? | 팀원에게 보고서를 제출하도록 지시하고 성과 평가에 문서화한다 | 다른 팀원에게 보고서를 준비하고 제출하도록 재배정한다 | 팀원과 보고서 요구사항을 검토하여 목적을 재정의한다 | 보고서가 요청대로 제출되지 않았음을 팀원의 기능 관리자에게 에스컬레이션한다 |  | C | 팀원이 보고서가 현실을 반영하지 않는다고 생각하여 제출하지 않을 때, PM은 팀원과 보고서 요구사항을 검토하여 목적을 재정의해야 한다. 협력적 접근이 이해와 개선을 촉진한다. 지시/문서화(A)는 권위적이다. 재배정(B)은 근본 문제를 해결하지 않는다. 에스컬레이션(D)은 직접 해결 시도 전에 과도하다.
1709 | During a retrospective meeting, a project manager hears that stakeholders have been constantly complaining at iteration demos about product features not being delivered as requested. What advice should the project manager give to the product owner to ensure that product features are always delivered as requested? | Include stakeholders during daily standup meetings to monitor progress. | Validate acceptance criteria with stakeholders prior to backlog refinement | Create a requirements traceability matrix and distribute it accordingly | Avoid including stakeholders in iteration reviews. |  | B | When stakeholders consistently complain at iteration demos that product features are not delivered as requested, the project manager should advise the product owner to validate acceptance criteria with stakeholders prior to backlog refinement. Upfront alignment prevents demo disappointments. Including stakeholders in daily standups (A) is inappropriate for progress monitoring. Creating a requirements traceability matrix (C) aids tracking but not validation. Excluding stakeholders from reviews (D) worsens the problem. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 회고 회의에서 이해관계자가 이터레이션 데모에서 지속적으로 불만을 제기한다고 들었다. 제품 기능이 요청대로 전달되지 않는다. PM은 제품 책임자에게 무엇을 조언해야 하는가? | 이해관계자를 데일리 스탠드업에 포함시켜 진행 상황을 모니터링한다 | 백로그 리파인먼트 전에 이해관계자와 인수 기준을 검증한다 | 요구사항 추적 매트릭스를 생성하고 적절히 배포한다 | 이해관계자를 이터레이션 리뷰에서 제외한다 |  | B | 이해관계자가 제품 기능이 요청대로 전달되지 않는다고 불만할 때, PM은 백로그 리파인먼트 전에 이해관계자와 인수 기준을 검증하도록 조언해야 한다. 사전 검증이 기대와 인도물 간의 격차를 방지한다. 스탠드업 포함(A)은 적절하지 않다. RTM(C)은 예측형 도구이다. 리뷰 제외(D)는 역효과이다.
1710 | A project is delivered using a hybrid approach. In the daily meeting, one of the developers informs the team that the business that will implement the next version of the product has a new manager. There is one more sprint before the new version of the product enters the staging phase. What should the project manager do? | Invite the new manager to the next sprint retrospective. | Invite the new manager to the next sprint review. | Invite the new manager to the next sprint planning. | Invite the new manager to the next daily scrum. |  | B | The correct answer is B. Invite the new manager to the next sprint review. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Hybrid/Tailoring | 하이브리드 프로젝트이다. 데일리 미팅에서 개발자가 비즈니스 부서의 새 관리자가 스프린트 진행을 지원하지 않는다고 알렸다. PM은 무엇을 해야 하는가? | 새 관리자를 다음 스프린트 회고에 초대한다 | 새 관리자를 다음 스프린트 리뷰에 초대한다 | 새 관리자를 다음 스프린트 계획에 초대한다 | 새 관리자를 다음 데일리 스크럼에 초대한다 |  | B | 정답은 B이다. 새 관리자를 다음 스프린트 리뷰에 초대한다. 스프린트 리뷰는 이해관계자에게 작업 결과물을 시연하고 피드백을 받는 자리이다. 새 관리자가 진행 상황을 직접 확인하면 지원을 이끌어낼 수 있다. 회고(A)는 내부 팀 개선용이다. 스프린트 계획(C)은 기술적이다. 데일리 스크럼(D)은 너무 짧고 빈번하다.
1711 | A leader from project B consistently reaches out to a team member in project A for assistance. What should project A's project manager do? | Ensure project A ' s team member can finish the work committed to project A. | Allow project B ' s leader to continue building relationships. | Talk with project B ' s leader to discuss possible impacts to both projects. | Tell project A ' s team member to ignore project B ' s leader. |  | C | When a leader from another project consistently requests assistance from a team member, the project manager should talk with project B's leader to discuss possible impacts to both projects. This direct communication clarifies expectations, boundaries, and identifies potential resource conflicts. Ensuring the team member finishes project A work (A) is defensive without addressing the relationship. Allowing the leader to continue building relationships (B) ignores the potential impact. Telling the team member to ignore requests (D) damages inter-project relationships. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Embed Quality | Acquire Resources | Traditional PM | 프로젝트 B의 리더가 프로젝트 A의 팀원에게 지속적으로 도움을 요청한다. 프로젝트 A의 PM은 무엇을 해야 하는가? | 프로젝트 A의 팀원이 프로젝트 A에 약속된 작업을 완료할 수 있도록 한다 | 프로젝트 B의 리더가 관계를 계속 구축하도록 허용한다 | 프로젝트 B의 리더와 대화하여 양 프로젝트에 대한 가능한 영향을 논의한다 | 프로젝트 A의 팀원에게 프로젝트 B의 리더를 무시하라고 말한다 |  | C | 다른 프로젝트 리더가 팀원에게 지속적으로 도움을 요청할 때, PM은 프로젝트 B의 리더와 대화하여 양 프로젝트에 대한 영향을 논의해야 한다. 직접적 대화가 상호 이해와 협력적 해결을 가능하게 한다. 작업 완료 보장(A)은 일방적이다. 관계 허용(B)은 수동적이다. 무시 지시(D)는 비전문적이다.
1712 | A project manager has been assigned to a high-visibility project that has been identified as having medium complexity, based on previous similar projects. The project needs to be delivered to the customer as a ready-to-use product. Based on this scenario, what should the project manager focus on throughout the project life cycle? | Time management and stakeholder engagement | Resource management and lessons learned | Stakeholder engagement and lessons learned | Cost management and risk management |  | A | For a high-visibility, medium-complexity project that must be delivered as a ready-to-use product, the project manager should focus on time management and stakeholder engagement throughout the project life cycle. Time management ensures disciplined planning, deadline adherence, and continuous progress monitoring—essential for delivering on schedule. Stakeholder engagement maintains alignment between customer expectations and project execution through regular communication and status updates. Resource management and lessons learned (B) are important but secondary to schedule delivery and stakeholder alignment. Stakeholder engagement and lessons learned (C) partially fits but omits the critical time management focus. Cost management and risk management (D) are necessary disciplines but are not the primary focus areas given the project's visibility and delivery requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | PM이 고가시성 프로젝트에 배정되었다. 중간 복잡도이지만 즉시 사용 가능한 제품으로 전달해야 한다. PM이 프로젝트 전반에 집중해야 할 두 가지 영역은? | 시간 관리와 이해관계자 참여 | 자원 관리와 교훈 | 이해관계자 참여와 교훈 | 비용 관리와 리스크 관리 |  | A | 고가시성, 중간 복잡도 프로젝트를 즉시 사용 가능한 제품으로 전달할 때, PM은 시간 관리와 이해관계자 참여에 집중해야 한다. 시간 관리가 적시 납품을 보장하고 이해관계자 참여가 기대를 관리한다. 자원 관리/교훈(B)은 우선 영역이 아니다. 이해관계자/교훈(C)은 시간 관리가 빠져있다. 비용/리스크(D)는 중간 복잡도에서 핵심이 아니다.
1713 | A project manager notices that the project team is unlikely to complete the development of a system on time before the testing start date, which was based on the technical complexity of the project. What should the project manager do before communicating with the client during the regular project progress meeting? | Tell the client about the chance for the potential delay. | Work with the project team to evaluate the potential delay. | Ask the project sponsor to inform the client in the next update. | Do not disclose the likelihood of a delay as it is yet to happen. |  | B | When the project team is unlikely to complete development before the testing start date, the project manager should work with the project team to evaluate the potential delay before communicating with the client. Internal assessment ensures accurate, fact-based communication. Telling the client about the potential delay immediately (A) lacks analysis. Asking the sponsor to inform the client (C) delegates communication. Not disclosing the delay (D) hides important information. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | PM이 프로젝트 팀이 테스트 시작일 전에 개발을 완료하지 못할 것으로 판단한다. PM은 무엇을 먼저 해야 하는가? | 고객에게 잠재적 지연 가능성을 알린다 | 프로젝트 팀과 협력하여 잠재적 지연을 평가한다 | 프로젝트 스폰서에게 다음 업데이트에서 고객에게 알리도록 요청한다 | 아직 발생하지 않았으므로 지연 가능성을 공개하지 않는다 |  | B | 프로젝트 팀이 개발을 제시간에 완료하지 못할 것으로 보일 때, PM은 먼저 팀과 협력하여 잠재적 지연을 평가해야 한다. 외부 커뮤니케이션 전에 정확한 평가가 우선이다. 고객 알림(A)은 평가 전에 성급하다. 스폰서 요청(C)은 간접적이다. 비공개(D)는 무책임하다.
1714 | During the release of an important product, a vice president for a different product line brought a valid concern to the project team, which had to be completed before the release. The vice president has not participated in other product discussions until now. This additional work resulted in a delay of the product release. How should the project manager have handled this situation earlier in the project? | Identified the vice president as a stakeholder | Recorded the vice president ' s concerns in the risk register | Escalated any dissent to top management right away | Shared project boundaries so that everyone was aware of the scope |  | A | The PM should have proactively identified the vice president as a stakeholder early in the project. Stakeholder identification is a critical first step—anyone who can be affected by or has influence over the project should be recognized. Early identification enables the PM to consider their concerns, facilitate communication, and prevent last-minute disruptions. Recording concerns in the risk register (B) is valuable but secondary. Sharing project boundaries (D) doesn't directly address the concerns. Escalating to top management (C) should be a last resort. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 중요 제품 출시 중 다른 제품 라인의 부사장이 유효한 우려를 프로젝트에 제기했다. PM이 이전에 무엇을 했어야 하는가? | 부사장을 이해관계자로 식별했다 | 부사장의 우려를 리스크 등록부에 기록했다 | 이견을 즉시 최고 경영진에 에스컬레이션했다 | 모든 사람이 범위를 인식하도록 프로젝트 경계를 공유했다 |  | A | PM은 프로젝트 초기에 부사장을 이해관계자로 사전에 식별했어야 한다. 이해관계자 식별은 핵심 첫 단계이다—프로젝트에 영향을 미치거나 관심이 있는 모든 사람을 식별해야 한다. 리스크 등록(B)은 이해관계자 식별 후에 한다. 에스컬레이션(C)은 과도하다. 경계 공유(D)는 식별 후 조치이다.
1715 | A hybrid project is experiencing several issues with both the agile delivery of the product as well as the predictive development of a marketing strategy. What should the project manager do to receive feedback from stakeholders located in different time zones? | Set up a conference call for all stakeholders. | Send an email to all stakeholders. | Refer to the stakeholder engagement plan. | Refer to the communications management plan. |  | D | The PM should refer to the communications management plan, which defines how project information is planned, managed, monitored, and controlled. This plan specifies communication requirements, methods, formats, frequency, and channels for each stakeholder group. In hybrid projects with distributed stakeholders, the communications plan addresses challenges of different time zones and methodologies, ensuring feedback mechanisms are appropriate, timely, and effective. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 하이브리드 프로젝트가 애자일 납품과 예측형 구성 요소 모두에서 여러 이슈를 겪고 있다. PM은 어떻게 커뮤니케이션해야 하는가? | 모든 이해관계자를 위한 컨퍼런스 콜을 설정한다 | 모든 이해관계자에게 이메일을 보낸다 | 이해관계자 참여 계획을 참조한다 | 커뮤니케이션 관리 계획을 참조한다 |  | D | PM은 커뮤니케이션 관리 계획을 참조해야 한다. 이 계획은 프로젝트 정보가 어떻게 계획, 관리, 모니터링, 통제되는지를 정의한다. 커뮤니케이션 요구사항, 방법, 빈도를 명시한다. 컨퍼런스 콜(A)은 계획 없이 임의적이다. 이메일(B)은 방법 하나일 뿐이다. 참여 계획(C)은 참여 수준이지 커뮤니케이션 방법이 아니다.
1716 | A company has a lot of experience with predictive projects. The project management office (PMO) has been trying to implement iterative tools within the project management framework, and the project manager has been asked to use these tools in their current project. After the successful implementation of the iterative tools, the PMO asks the project manager to determine the benefits these tools brought to the project. What should the project manager do? | Update the communications management plan to consider performance review meetings with the project stakeholders | Determine the data to be monitored during the project as well as the expected performance and targets. | Prepare and submit a status report to the steering committee to update performance monitoring | Conduct reviews with stakeholders to discuss the potential benefits the approach may have to the project |  | D | When asked to determine the benefits of newly implemented iterative tools, the project manager should conduct reviews with stakeholders to discuss the potential benefits the approach may have brought. Stakeholder feedback provides comprehensive evaluation of effectiveness and value delivered. Updating the communications plan for performance reviews (A) is process-focused. Determining data to monitor with expected targets (B) sets up future tracking but does not evaluate past benefits. Submitting a status report (C) reports performance but does not assess tool-specific benefits. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 예측형 프로젝트 경험이 많은 회사이다. PMO가 반복적 도구를 도입하려 한다. PM이 새 도구의 이점을 결정하도록 요청받았다. 무엇을 해야 하는가? | 프로젝트 스폰서와의 성과 검토 회의를 고려하여 커뮤니케이션 관리 계획을 업데이트한다 | 프로젝트 중 모니터링할 데이터와 기대 성과 및 목표를 결정한다 | 운영 위원회에 성과 모니터링 업데이트를 위한 상태 보고서를 준비하고 제출한다 | 이해관계자와 리뷰를 실시하여 접근법이 프로젝트에 가져올 수 있는 잠재적 이점을 논의한다 |  | D | 새로 도입된 반복적 도구의 이점을 결정하라는 요청을 받으면, PM은 이해관계자와 리뷰를 실시하여 접근법이 가져올 잠재적 이점을 논의해야 한다. 이해관계자 피드백이 실제 이점을 평가한다. 커뮤니케이션 계획 업데이트(A)는 이점 결정이 아니다. 데이터 결정(B)은 모니터링이지 이점 평가가 아니다. 상태 보고서(C)는 보고이지 이점 분석이 아니다.
1717 | An executive sponsor of a predictive project asked a project manager experienced in agile to assess if a project could be executed using an agile approach. What factor should the project manager consider when determining if the project is suitable for an agile approach? | The project scope is well defined and the requirements are prioritized | The project team has a colocated space and is capable of working together | The project is an information technology project and has minimal impact to the organization | The project scope can be decomposed into smaller parts, the first representing a minimum viable product (MVP). |  | D | When assessing whether a project is suitable for an agile approach, the key factor is whether the project scope can be decomposed into smaller parts, with the first representing a minimum viable product (MVP). Agile's strength lies in iterative delivery of product increments that allow for customer feedback and adaptation. If the scope can be broken into valuable, testable increments, agile is well-suited. A well-defined scope with prioritized requirements (A) is more characteristic of a predictive approach. A colocated team (B) is helpful but not a determining factor for agile suitability. Being an IT project with minimal impact (C) does not indicate agile suitability. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 경영 스폰서가 예측형 프로젝트를 애자일로 전환할 수 있는지 평가하도록 요청했다. 프로젝트가 애자일에 적합한 핵심 요소는? | 프로젝트 범위가 잘 정의되어 있고 요구사항이 우선순위화되어 있다 | 프로젝트 팀이 같은 장소에 있고 함께 작업할 수 있다 | 프로젝트가 IT 프로젝트이고 조직에 최소한의 영향을 미친다 | 프로젝트 범위가 작은 부분으로 분해 가능하며 첫 부분이 최소 기능 제품(MVP)을 나타낸다 |  | D | 프로젝트가 애자일에 적합한지 평가할 때 핵심 요소는 범위가 작은 부분으로 분해 가능하고 첫 부분이 MVP를 나타내는 것이다. 이는 점진적 가치 전달을 가능하게 한다. 잘 정의된 범위(A)는 예측형에 적합하다. 같은 장소(B)는 도움이 되지만 필수가 아니다. IT 프로젝트(C)는 애자일이 IT에만 해당하지 않는다.
1718 | A lead project manager for an agile project needs to prioritize requirements, define the scope of the initial product, and deliver the approved scope in a series of multiple versions. What should the project manager do next? | Determine the expected benefits of each requirement to maximize the overall business value | Work with the product owner to evaluate and prioritize the requirements | Prioritize the requirements based on the hierarchical level of the requesting stakeholders | Ask the lead developer to run a meeting with the stakeholders to agree on an ordered list |  | B | When a lead project manager needs to prioritize requirements, define initial scope, and deliver in multiple versions, the next step should be to work with the product owner to evaluate and prioritize the requirements. The product owner brings business value perspective essential for backlog prioritization. Determining expected benefits to maximize business value (A) is part of the evaluation but not a standalone step. Prioritizing based on stakeholder hierarchy (C) ignores actual business value. Asking the lead developer to run a meeting with stakeholders (D) assigns the wrong person to lead prioritization. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 애자일 프로젝트의 리드 PM이 요구사항 우선순위 지정, 초기 제품 범위 정의, 여러 버전으로 납품해야 한다. 다음 단계는? | 각 요구사항의 기대 이점을 결정하여 전체 비즈니스 가치를 극대화한다 | 제품 책임자와 협력하여 요구사항을 평가하고 우선순위를 정한다 | 요청하는 이해관계자의 계층 수준에 따라 요구사항을 우선순위화한다 | 리드 개발자에게 이해관계자와 회의를 열어 순서화된 목록에 합의하도록 요청한다 |  | B | 요구사항 우선순위 지정과 초기 범위 정의가 필요할 때, PM은 제품 책임자와 협력하여 요구사항을 평가하고 우선순위를 정해야 한다. 제품 책임자가 백로그 관리와 우선순위의 권한을 가진다. 이점 결정(A)은 유용하지만 제품 책임자 협력이 우선이다. 계층별 우선순위(C)는 가치가 아닌 직급 기반이다. 개발자 회의(D)는 역할 혼동이다.
1719 | Presented with flowcharts of the organization's operations, stakeholders are unfamiliar with several recorded processes, and others note that some recorded processes were discontinued. The project sponsor notices that the chart is several years old and wants an updated version immediately. What should the project manager do? | Assemble and create teams of experts and stakeholders to update flowcharts to reflect current conditions. | Assemble the entire project team to produce new flowcharts from current versions. | Work with a consultant and the project sponsor to produce new flowcharts. | Raise a change request and ask the project sponsor to approve it so the flowcharts can be updated. |  | A | The correct answer is A. Assemble and create teams of experts and stakeholders to update flowcharts to reflect current conditions. Stakeholder engagement requires proactive communication and alignment. The PM should understand stakeholder needs, maintain transparency, and address concerns to ensure project success. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 조직의 운영 흐름도가 제시되었지만 이해관계자들이 기록된 여러 프로세스에 익숙하지 않다. PM은 무엇을 해야 하는가? | 전문가와 이해관계자 팀을 구성하여 현재 상태를 반영하도록 흐름도를 업데이트한다 | 전체 프로젝트 팀을 모아 현재 버전에서 새 흐름도를 생산한다 | 컨설턴트와 프로젝트 스폰서와 협력하여 새 흐름도를 생산한다 | 변경 요청을 제기하고 프로젝트 스폰서에게 승인을 요청하여 흐름도를 업데이트한다 |  | A | 정답은 A이다. 전문가와 이해관계자 팀을 구성하여 현재 상태를 반영하도록 흐름도를 업데이트한다. 이해관계자 참여는 사전적 커뮤니케이션과 정렬이 필요하다. 전문가와 이해관계자의 공동 작업이 정확하고 관련성 있는 업데이트를 보장한다.
1720 | A concerned project team member complains to the project manager that another team member is being disruptive and argumentative during team meetings. The project manager received some information that the team member recently overcame a difficult personal situation. What should the project manager do to address the concern? | Inform the disruptive team member ' s functional manager that the disruptive behavior should be stopped immediately | Provide team-building activities so that the team can learn how to overcome disruptive behavior | Request a meeting with the disruptive team member and help to resolve the issue | Encourage self-governance and ask the concerned team member to speak to the disruptive team member directly |  | C | When a team member is disruptive during meetings and the PM knows they overcame a difficult personal situation, the project manager should request a meeting with the disruptive team member and help resolve the issue. Private, empathetic engagement addresses the root cause. Informing the functional manager (A) escalates without understanding. Providing team-building activities (B) is indirect. Encouraging self-governance (D) places burden on the concerned team member. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | General | Risk & Issue Management | People | Lead the Project Team | Resources | Executing | Embed Quality | Develop Team | Traditional PM | 걱정된 팀원이 PM에게 다른 팀원이 회의에서 파괴적이고 논쟁적이라고 불만한다. PM은 그 팀원이 어려운 개인 상황을 극복했다는 것을 안다. PM은 무엇을 해야 하는가? | 파괴적 팀원의 기능 관리자에게 파괴적 행동을 중단해야 한다고 알린다 | 팀이 파괴적 행동을 극복하는 방법을 배울 수 있도록 팀 빌딩 활동을 제공한다 | 파괴적 팀원과 회의를 요청하고 이슈 해결을 돕는다 | 자기 통치를 장려하고 걱정하는 팀원에게 파괴적 팀원과 직접 대화하도록 요청한다 |  | C | 팀원이 파괴적이고 PM이 개인적 상황을 알고 있을 때, PM은 파괴적 팀원과 회의를 요청하고 이슈 해결을 도와야 한다. 직접적이고 공감적인 접근이 효과적이다. 기능 관리자 알림(A)은 에스컬레이션이 과도하다. 팀 빌딩(B)은 개별 이슈를 다루지 않는다. 자기 통치(D)는 PM 역할을 방기한다.
1721 | At the end of a project, the project manager is asked to submit project documentation for an internal audit in response to regulatory requirements. What should the project manager have done at the beginning of the project to ensure that project documentation would fulfill these requirements? | Implemented a new change control policy | Conducted a document review | Updated the project templates | Confirmed documentation requirements with stakeholders |  | D | At project initiation, the PM should confirm documentation requirements with stakeholders—including format, content, quality standards, frequency, and distribution methods. This ensures project documentation meets stakeholder expectations, regulatory obligations, and contractual requirements throughout the lifecycle. While document reviews, template updates, and change control policies support documentation management, they are insufficient without first establishing clear stakeholder requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 종료 시 PM이 내부 감사를 위한 프로젝트 문서 제출을 요청받았다. 결과가 좋지 않았다. PM이 프로젝트 시작 시 무엇을 했어야 하는가? | 새 변경 통제 정책을 구현했다 | 문서 검토를 실시했다 | 프로젝트 템플릿을 업데이트했다 | 이해관계자와 문서 요구사항을 확인했다 |  | D | 프로젝트 시작 시 PM은 이해관계자와 문서 요구사항을 확인했어야 한다—형식, 내용, 품질 표준, 빈도, 배포 방법을 포함하여. 이는 프로젝트 문서가 감사 요구를 충족하도록 보장한다. 변경 통제 정책(A)은 문서 요구가 아니다. 문서 검토(B)는 시작 시 문서가 없다. 템플릿 업데이트(C)는 요구사항 확인 후에 한다.
1722 | A project manager is working on a software development project. A team member complains that since the project tasks are very simple, there is no reason to conduct quality control. The project manager understands that removing the quality management plan from the project will also help to reduce costs, which is important to the customer. What should the project manager do? | Register starting the project without a quality management plan as a risk, and allocate the budget savings to the management reserve | Get confirmation from management that the team member has enough experienceto build software without quality control | Ask the customer to order an external quality audit after accepting the project deliverable, and decrease the budget of the project | Develop the quality management plan, as quality is as equally important as cost and schedule management. |  | D | A quality management plan defines the methodology, standards, criteria, activities, tools, and corrective actions applied throughout the project lifecycle to achieve quality objectives. Quality is equally important as cost and schedule management—it is a key constraint in the project management triangle alongside scope, time, and cost. The PM should develop this plan to prevent defects and rework, enhance customer satisfaction, improve team performance, reduce risks and costs, and increase overall project value. When team members question the need for quality control, the PM should explain how QC activities (testing, inspection, review) help identify and correct issues early, ultimately delivering a product that meets customer expectations. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | PM이 소프트웨어 개발 프로젝트에서 작업 중이다. 팀원이 예산 제약으로 품질 관리 계획 없이 작업하고 있다고 불만한다. PM은 무엇을 해야 하는가? | 품질 관리 계획 없이 프로젝트를 시작하는 것을 리스크로 등록하고 예산을 할당한다 | 팀원이 품질 관리 계획 없이 소프트웨어를 구축할 충분한 경험이 있는지 경영진에 확인한다 | 고객에게 인도물 수락 후 외부 품질 감사를 주문하도록 요청하고 예산 할당 여부를 결정한다 | 품질은 비용 및 일정 관리와 동등하게 중요하므로 품질 관리 계획을 개발한다 |  | D | 품질 관리 계획은 프로젝트 수명주기 전반에 걸쳐 적용되는 방법론, 표준, 기준, 활동, 도구 및 시정 조치를 정의한다. 품질은 비용 및 일정과 동등하게 중요하다. 리스크 등록(A)은 대응이 아니다. 경험 확인(B)은 품질 보장이 아니다. 외부 감사(C)는 사후 조치이다.
1723 | A project manager has been appointed to a multimillion-dollar project. The project is considered to be high risk since no similar projects have been undertaken before and there is no historical data. Some external stakeholders are reluctant to provide support. What approach should the project manager take? | Convince senior management to close the project since the project lacks sponsorship and is considered to be high risk. | Host a project team meeting, then update the risk register and the project management plan | Establish dialogue with stakeholders on the project constraints, assumptions, and critical inputs | Examine the plans, processes, policies, and knowledge that are specific to the organization undertaking the project |  | C | When appointed to a high-risk multimillion-dollar project without historical data and facing reluctant external stakeholders, the project manager should establish dialogue with stakeholders on project constraints, assumptions, and critical inputs. Direct engagement builds understanding and support. Convincing management to close the project (A) abandons the initiative. Hosting a team meeting to update registers (B) focuses internally. Examining organizational plans and policies (D) is preparatory but does not address stakeholder reluctance. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | PM이 수백만 달러 규모의 프로젝트에 임명되었다. 역사적 데이터가 없고 외부 이해관계자가 참여를 꺼린다. PM은 무엇을 해야 하는가? | 프로젝트에 후원이 없고 고위험이므로 프로젝트를 종료하도록 고위 경영진을 설득한다 | 프로젝트 팀 회의를 개최하고 리스크 등록부와 프로젝트 관리 계획을 업데이트한다 | 프로젝트 제약, 가정, 주요 입력에 대해 이해관계자와 대화를 시작한다 | 조직이 수행하는 프로젝트에 특정한 계획, 프로세스, 정책, 지식을 검토한다 |  | C | 역사적 데이터 없이 고위험 프로젝트에서 외부 이해관계자가 꺼릴 때, PM은 프로젝트 제약, 가정, 주요 입력에 대해 이해관계자와 대화를 시작해야 한다. 이해관계자 참여가 협력과 정보 수집의 기초이다. 종료 설득(A)은 시도 전에 포기이다. 팀 회의(B)는 이해관계자 참여가 없다. 조직 검토(D)는 내부적이다.
1724 | A team member is not getting along with one of the project sponsors. The sponsor has requested to move the team member to another project. What should the project manager do next to resolve the situation? | Review the resolution of a similar past situation and apply the same strategy for the team. | Meet with the team member and identify areas of improvement to satisfy the sponsor. | Hold a meeting with the team and explain the ground rules for the project. | Identify the reasoning behind the behavior of the sponsor and team member. |  | D | When a team member and sponsor are in conflict and the sponsor requests a transfer, the project manager should first identify the reasoning behind the behavior of the sponsor and team member. Understanding both perspectives enables informed conflict resolution before taking action. Reviewing past similar situations (A) may not apply to the current context. Meeting the team member about improvement areas (B) assumes the team member is at fault. Explaining ground rules (C) is helpful but does not address the specific interpersonal issue. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 팀원이 프로젝트 스폰서와 사이가 좋지 않다. 스폰서가 팀원을 다른 프로젝트로 옮기라고 요청했다. PM은 무엇을 먼저 해야 하는가? | 유사한 과거 상황의 해결 방법을 검토하고 같은 전략을 적용한다 | 팀원과 만나 스폰서를 만족시킬 개선 영역을 식별한다 | 팀과 회의를 열고 프로젝트의 기본 규칙을 설명한다 | 스폰서와 팀원의 행동 이면의 이유를 파악한다 |  | D | 팀원과 스폰서가 갈등하고 스폰서가 이동을 요청할 때, PM은 먼저 양측 행동의 이면 이유를 파악해야 한다. 근본 원인 이해가 효과적 해결의 기초이다. 과거 사례 적용(A)은 상황이 다를 수 있다. 개선 영역(B)은 한쪽만 다룬다. 기본 규칙(C)은 일반적이지 구체적이지 않다.
1725 | The project manager just started leading a project team from which the previous project manager resigned. After a quick evaluation of the project, it is apparent that team morale is low due to continuous disagreement about how to complete tasks. Tasks are taking longer than forecasted and the project is off schedule. What should the project manager do? | Crash the project timeline to ensure the project is back on schedule | Issue a change request to extend the project schedule based on identified delays | Conduct a meeting with the project team to discuss and address the sources of disagreement | Inform the stakeholders that the project will be delayed due to previous team management |  | C | When team morale is low due to continuous disagreement about task completion methods and the project is off schedule, the project manager should conduct a meeting with the team to discuss and address the sources of disagreement. Direct conflict resolution identifies root causes and fosters collaborative solutions. Crashing the timeline (A) adds pressure without addressing morale. Issuing a change request to extend the schedule (B) accepts the situation. Informing stakeholders of delay (D) communicates without resolving. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Predictive | Critical Path/Schedule Mgmt | People | Manage Conflicts | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | PM이 이전 PM이 사임한 프로젝트 팀을 이끌기 시작했다. 팀 사기가 낮고 작업 완료 방법에 대한 지속적 의견 불일치가 있다. 프로젝트가 일정에 뒤처져 있다. PM은 무엇을 해야 하는가? | 프로젝트 일정을 크래싱하여 일정을 다시 맞춘다 | 식별된 지연에 기반하여 프로젝트 일정 연장을 위한 변경 요청을 제출한다 | 프로젝트 팀과 회의를 실시하여 의견 불일치의 원인을 논의하고 해결한다 | 이해관계자에게 이전 팀 관리로 인해 프로젝트가 지연될 것임을 알린다 |  | C | 팀 사기가 낮고 의견 불일치로 일정이 지연될 때, PM은 팀과 회의를 실시하여 의견 불일치의 원인을 논의하고 해결해야 한다. 팀 문제 해결이 일정 회복의 기초이다. 크래싱(A)은 팀 문제를 해결하지 않는다. 일정 연장(B)은 근본 문제를 다루지 않는다. 이전 관리 탓(D)은 비생산적이다.
1726 | One deliverable for a project is to translate and print materials for students every 2 weeks. Printing services are available but without guaranteed timelines because other projects make a significantly higher profit and have a higher priority. What should the project manager do to mitigate the risk of not having the materials printed on time? | Meet with the manager to set a high priority for printing the materials | Include a risk response in the resource management plan | Purchase a high-volume printer specifically for this project. | Create a change request to modify the print requirements |  | B | When printing services for bi-weekly student materials are not guaranteed due to higher-priority projects, the project manager should include a risk response in the resource management plan. Addressing resource risks within the resource plan is systematic. Meeting with the manager to set priority (A) may not succeed against higher-profit projects. Purchasing a dedicated printer (C) may be excessive. Creating a change request to modify requirements (D) changes scope rather than managing risk. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 인도물은 2주마다 학생용 자료를 번역하고 인쇄하는 것이다. 인쇄 서비스가 우선순위가 더 높은 프로젝트로 보장되지 않는다. PM은 무엇을 해야 하는가? | 관리자와 만나 자료 인쇄에 높은 우선순위를 설정한다 | 자원 관리 계획에 리스크 대응을 포함한다 | 이 프로젝트를 위한 대용량 프린터를 구매한다 | 인쇄 요구사항을 수정하기 위한 변경 요청을 생성한다 |  | B | 2주 단위 자료 인쇄가 다른 프로젝트 우선순위로 보장되지 않을 때, PM은 자원 관리 계획에 리스크 대응을 포함해야 한다. 자원 비가용성을 리스크로 인식하고 대응을 계획한다. 우선순위 설정(A)은 다른 프로젝트 영향이 있다. 프린터 구매(C)는 비용 과다이다. 변경 요청(D)은 요구사항 자체를 변경하는 것이다.
1727 | Two team members are consistently having misunderstandings and find it difficult to work together. How should the project manager handle this situation? | Warn the team members about their behavior | Train the team members on communication techniques and interpersonal behavior | Remove one of the team members | Identify the issues between the team members and guide them toward a resolution |  | D | When two team members consistently have misunderstandings and find it difficult to work together, the project manager should identify the issues between them and guide them toward a resolution. Using collaborative conflict resolution techniques addresses root causes and fosters a positive team environment. Warning about behavior (A) does not address underlying issues. Training on communication techniques (B) is general and may not resolve specific interpersonal conflict. Removing a team member (C) is an extreme measure that avoids resolution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 두 팀원이 지속적으로 오해하고 함께 일하기 어려워한다. PM은 어떻게 해야 하는가? | 팀원들의 행동에 대해 경고한다 | 커뮤니케이션 기법과 대인관계 행동에 대해 팀원을 교육한다 | 팀원 중 한 명을 제거한다 | 팀원 간의 이슈를 파악하고 해결을 안내한다 |  | D | 두 팀원이 지속적으로 오해하고 함께 일하기 어려울 때, PM은 이슈를 파악하고 해결을 안내해야 한다. 근본 원인 파악과 안내가 협력적 문제 해결의 기초이다. 경고(A)는 권위적이다. 교육(B)은 즉각적 이슈를 해결하지 않는다. 제거(C)는 극단적이다.
1728 | After the first iteration, a scrum master notices that some of the team members are struggling with testing their developed product. What should the scrum master do next? | Check lessons learned and use the testing process from previous projects. | Log the issue and ask a senior member to coach these team members. | Hire new team members to implement the correct way of testing. | Log the issue and see if improvements show in the second iteration. |  | B | The correct answer is B. Log the issue and ask a senior member to coach these team members. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 첫 이터레이션 후 스크럼 마스터가 일부 팀원이 개발한 항목 테스트에 어려움을 겪는 것을 발견했다. 무엇을 해야 하는가? | 교훈을 확인하고 이전 프로젝트의 테스트 프로세스를 사용한다 | 이슈를 기록하고 시니어 멤버에게 이 팀원들을 코칭하도록 요청한다 | 올바른 테스트 방법을 구현할 새 팀원을 고용한다 | 이슈를 기록하고 두 번째 이터레이션에서 개선이 보이는지 확인한다 |  | B | 정답은 B이다. 이슈를 기록하고 시니어 멤버에게 코칭을 요청한다. 애자일 환경에서 PM은 팀 협력 촉진, 장애물 제거, 지속적 개선을 지원해야 한다. 코칭은 실무적 학습을 촉진한다. 이전 프로세스(A)는 현재 맥락에 맞지 않을 수 있다. 신규 고용(C)은 과도하다. 방관(D)은 수동적이다.
1729 | The business manager and the product owner are requesting a more flexible way to incorporate changes into the product baseline. They are concerned about losing time to market with respect to other vendors. What should the project manager do? | Establish a change control board (CCB) with key stakeholders. | Review the assumption log and project management plan for changes. | Identify adequate change management tools to conduct the project | Allow key stakeholders to make some changes to deliver the product faster |  | C | When the business manager and PO want a more flexible way to incorporate changes to maintain time-to-market competitiveness, the project manager should identify adequate change management tools to conduct the project. Proper tools enable efficient change processing. Establishing a CCB (A) adds structure but may slow changes. Reviewing the assumption log (B) is diagnostic. Allowing key stakeholders to make changes directly (D) bypasses governance. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 비즈니스 관리자와 제품 책임자가 제품 백로그에 변경을 보다 유연하게 수용하는 방법을 요청한다. 시장 출시 경쟁력 유지가 목적이다. PM은 무엇을 해야 하는가? | 주요 이해관계자와 변경통제위원회(CCB)를 설립한다 | 가정 로그와 프로젝트 관리 계획의 변경을 검토한다 | 프로젝트를 수행하기 위한 적절한 변경 관리 도구를 식별한다 | 주요 이해관계자가 제품을 더 빨리 납품하도록 일부 변경을 하도록 허용한다 |  | C | 유연한 변경 수용이 필요할 때, PM은 프로젝트를 수행하기 위한 적절한 변경 관리 도구를 식별해야 한다. 올바른 도구가 효율적 변경 처리를 가능하게 한다. CCB(A)는 형식적이지 유연하지 않다. 로그 검토(B)는 도구가 아니다. 통제 없는 변경 허용(D)은 범위 확장 리스크가 있다.
1730 | A project manager has been assigned to lead a project to deploy a new system. The stakeholders disagree on the project objectives and approach. What should the project manager do? | Conduct scoping workshops with the project team to create a work breakdown structure (WBS), assign tasks to various entities share this with all stakeholders, and ask the team to complete their tasks as scheduled | Breakdown the situation to identify the root causes for the disagreement and then work with each stakeholder and participating entity on their exact roles and responsibilities | Create a roles and responsibilities matrix based on the project charter and ask the sponsor to share it with all stakeholders to provide credible authority | Conduct a general meeting with all stakeholders and review and address a list of activities for each of them |  | B | The PM should break down the disagreement situation, identify root causes, and work with each stakeholder on their exact roles and responsibilities. This involves using stakeholder analysis, communication management, conflict resolution, and negotiation to address underlying issues and align stakeholders with the project vision and goals. The project charter serves as a reference for clarifying objectives, scope, and deliverables. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Focus on Value | Identify Stakeholders | Traditional PM | PM이 새 시스템 배포 프로젝트를 이끌도록 배정되었다. 이해관계자들이 프로젝트 목표에 동의하지 않는다. PM은 무엇을 해야 하는가? | 프로젝트 팀과 스코핑 워크숍을 실시하여 WBS를 만들고 작업을 할당한다 | 상황을 분석하여 의견 불일치의 근본 원인을 파악하고 각 이해관계자의 역할과 책임을 작업한다 | 프로젝트 헌장에 기반한 역할 책임 매트릭스를 만들고 스폰서에게 공유를 요청한다 | 모든 이해관계자와 일반 회의를 실시하여 활동 목록을 검토하고 다룬다 |  | B | 이해관계자가 목표에 동의하지 않을 때, PM은 의견 불일치의 근본 원인을 파악하고 각 이해관계자와 역할과 책임을 작업해야 한다. 이해관계자 분석과 커뮤니케이션이 정렬을 가능하게 한다. WBS 워크숍(A)은 목표 합의 전에 성급하다. 매트릭스 공유(C)는 일방적이다. 일반 회의(D)는 구조가 없다.
1731 | A product owner has added new high-priority work to the backlog. A project manager is working with a dedicated agile team that does not specialize in this specific area of work. The team reviewed the work and wants to accept it but acknowledges it may not have the same level of efficiency as another team having specialization in this area. What should the project manager do in this scenario? | Accept the work and outsource it to another team that has the specialized skill set; then 1278 integrate the solution, | Reject the work from this team ' s backlog and ask the product owner to add It to another team ' s backlog. | Add temporary members with the specialized skill set to the team to accomplish the work with a high level of confidence. | Assess the impact of a possible delay to the project and encourage the team to take the work if the impact is tolerable. |  | D | When a dedicated agile team wants to accept new high-priority work outside their specialization with possible reduced efficiency, the project manager should assess the impact of possible delay and encourage the team to take the work if tolerable. Balancing risk with team growth is pragmatic. Outsourcing to another team (A) adds complexity. Rejecting the work (B) reduces team ownership. Adding temporary specialists (C) may not be necessary if impact is tolerable. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 제품 책임자가 새 고우선순위 작업을 백로그에 추가했다. 팀의 전문 분야 밖이지만 효율 저하 가능성에도 작업을 수락하고 싶어한다. PM은 무엇을 해야 하는가? | 작업을 수락하고 전문 기술을 가진 다른 팀에 아웃소싱한 후 나중에 통합한다 | 이 팀의 백로그에서 작업을 거부하고 제품 책임자에게 다른 팀의 백로그에 추가하도록 요청한다 | 전문 기술을 가진 임시 멤버를 팀에 추가하여 높은 품질로 작업을 수행한다 | 프로젝트 지연 가능성의 영향을 평가하고 리스크가 수용 가능하면 팀이 작업을 맡도록 격려한다 |  | D | 팀이 전문 분야 밖의 고우선순위 작업을 수락하려 할 때, PM은 지연 가능성의 영향을 평가하고 리스크가 수용 가능하면 팀이 작업을 맡도록 격려해야 한다. 리스크 기반 의사결정이 적절하다. 아웃소싱(A)은 통합 복잡성이 있다. 거부(B)는 팀 동기를 무시한다. 임시 멤버(C)는 팀 역학을 방해한다.
1732 | An organization is embarking on the deployment of a new digital solution that will revolutionize purchasing services. The project manager has created all the necessary plans and activities to ensure a successful integration and solution launch. There is a risk of a partner's system being unavailable which could impact the project negatively. What key activity is needed to ensure the project's success? | Mitigate the risk by developing alternative plans to make the solution ready and available without full integration capabilities | Eliminate the risk by mandating the partner to change the system settings to facilitate an easier integration with the new solution | Continuously monitor the risk of the partner system ' s unavailability, and put the proper resolution plans in place in case the risk materializes into an actual issue | Communicate to the project stakeholders that full integration may not be possible and that the project will potentially be delayed as a result. |  | A | When there is a risk of a partner's system being unavailable that could impact a digital solution deployment, the key activity is to mitigate the risk by developing alternative plans to deliver without full integration. Proactive mitigation ensures project success. Eliminating the risk by mandating partner changes (B) is unrealistic. Continuously monitoring without mitigation (C) is passive. Communicating potential delay (D) accepts the risk. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 새 디지털 솔루션 배포 시 파트너 시스템 비가용 리스크가 있다. PM의 핵심 활동은? | 리스크를 완화하기 위해 파트너 시스템 없이도 솔루션을 준비하는 대안 계획을 개발한다 | 파트너에게 시스템 설정을 변경하여 통합을 용이하게 하도록 의무화하여 리스크를 제거한다 | 파트너 시스템 비가용 리스크를 지속적으로 모니터링하고 적절한 해결책을 마련한다 | 이해관계자에게 전체 통합이 불가능할 수 있으며 프로젝트가 지연될 수 있다고 전달한다 |  | A | 파트너 시스템 비가용 리스크가 디지털 솔루션 배포에 영향을 줄 때, 핵심 활동은 대안 계획을 개발하여 리스크를 완화하는 것이다. 사전적 대안이 납품을 보장한다. 파트너 의무화(B)는 외부 통제가 불가할 수 있다. 지속 모니터링(C)은 대응이 아닌 관찰이다. 지연 통보(D)는 해결이 아닌 수용이다.
1733 | A project manager found a repeated defect in a junior developer's code. The code is due in 2 days and a severe fine will be incurred if it is not fixed by then. The project manager wants to reassign the assignment to a more senior developer, but the junior developer is strongly opposed to the reassignment. What should the project manager do? | Reassign the issue to the senior developer and assign the junior developer to assist in fixing the issue. | Assign the rework to the junior developer after consultation with the senior developer. | Reassign the issue to the senior developer after explaining the situation to the junior developer. | Assign the issue to a senior developer and schedule training for the junior developer after the due date. |  | C | The correct answer is C. Reassign the issue to the senior developer after explaining the situation to the junior developer. Quality management ensures deliverables meet defined standards and acceptance criteria. The PM should establish quality metrics, monitor compliance, and implement corrective actions when needed. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 주니어 개발자 코드에서 반복 결함을 발견했다. 코드 마감이 2일 남았고 심각한 벌금이 부과된다. PM은 무엇을 해야 하는가? | 이슈를 시니어 개발자에게 재배정하고 주니어 개발자를 수정 보조로 배정한다 | 시니어 개발자와 상의 후 주니어 개발자에게 재작업을 배정한다 | 주니어 개발자에게 상황을 설명한 후 시니어 개발자에게 이슈를 재배정한다 | 시니어 개발자에게 이슈를 배정하고 마감 후 주니어 개발자를 위한 교육을 예약한다 |  | C | 정답은 C이다. 주니어 개발자에게 상황을 설명한 후 시니어 개발자에게 재배정한다. 품질 관리는 정의된 표준과 인수 기준 충족을 보장한다. 상황 설명이 투명성과 학습 기회를 제공하고, 시니어에게 재배정이 마감을 맞춘다. 보조 배정(A)은 비효율적이다. 주니어 재작업(B)은 마감 리스크이다. 교육 예약만(D)은 설명이 없다.
1734 | A technical manager newly appointed by the client visits the project site to verify the project deliverables. The technical manager feels that the project manager has not been providing enough information. What should the project manager do first to resolve this situation? | Schedule more frequent meetings with the technical manager. | Update the issue log and escalate to the project sponsor | Identify the lack of information as a risk and update the risk register | Review and update the stakeholder engagement plan |  | D | When a newly appointed client technical manager feels inadequate information has been provided, the project manager should first review and update the stakeholder engagement plan. This addresses the root cause by reassessing the new stakeholder's information needs and establishing appropriate engagement strategies. Updating the issue log and escalating to the sponsor (A) may create unnecessary conflict. Identifying the information gap as a risk (B) mischaracterizes a current communication issue as a potential future event. Scheduling more frequent meetings (C) addresses the symptom without updating the underlying engagement strategy. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 고객이 새로 임명한 기술 관리자가 프로젝트 현장을 방문하여 인도물을 확인했다. 기술 관리자가 제공된 정보가 부적절하다고 느낀다. PM은 무엇을 해야 하는가? | 기술 관리자와 더 빈번한 회의를 예약한다 | 이슈 로그를 업데이트하고 프로젝트 스폰서에게 에스컬레이션한다 | 정보 부족을 리스크로 식별하고 리스크 등록부를 업데이트한다 | 이해관계자 참여 계획을 검토하고 업데이트한다 |  | D | 새로 임명된 기술 관리자가 정보 부족을 느낄 때, PM은 이해관계자 참여 계획을 검토하고 업데이트해야 한다. 새 이해관계자의 요구를 반영하여 참여 전략을 조정한다. 빈번한 회의(A)는 계획 없는 대응이다. 에스컬레이션(B)은 과도하다. 리스크 등록(C)은 참여 문제이지 리스크가 아니다.
1735 | A project manager is leading a project that includes several organizations with unique corporate cultures. These diverse corporate cultures are affecting project expectations. The varying expectations often lead to conflicts, which often require the project manager's involvement. What should the project manager do first to evaluate the cultural differences within the organizations? | Develop a joint policy among the various organizations. | Disregard the situation since it is not hindering the project deliverables. | Escalate the issue to the project sponsor and seek their guidance. | Establish a probability and impact matrix and plan response criteria. |  | C | When cultural differences among multiple organizations lead to conflicting expectations and frequent conflicts, the project manager should first escalate the issue to the project sponsor and seek their guidance. The sponsor has the authority and organizational perspective to help navigate cross-organizational cultural challenges and can facilitate strategy development. Developing a joint policy (A) may be premature without sponsor guidance. Disregarding the situation (B) allows conflicts to worsen. Establishing a probability and impact matrix (D) treats this as a risk assessment rather than the active stakeholder management issue it is. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | PM이 고유한 기업 문화를 가진 여러 조직이 포함된 프로젝트를 이끌고 있다. 문화 차이가 상충되는 기대와 빈번한 갈등을 초래한다. PM은 무엇을 해야 하는가? | 다양한 조직 간 공동 정책을 개발한다 | 프로젝트 인도물을 방해하지 않으므로 상황을 무시한다 | 프로젝트 스폰서에게 이슈를 에스컬레이션하고 안내를 구한다 | 확률과 영향 매트릭스를 설정하고 대응 기준을 계획한다 |  | C | 여러 조직의 문화 차이가 상충되는 기대와 갈등을 초래할 때, PM은 먼저 프로젝트 스폰서에게 이슈를 에스컬레이션하고 안내를 구해야 한다. 스폰서가 조직 간 문제에 대한 권한과 영향력을 가진다. 공동 정책(A)은 PM의 권한을 넘는다. 무시(B)는 무책임하다. 확률/영향 매트릭스(D)는 리스크 도구이지 문화 문제 도구가 아니다.
1736 | During project execution, a project manager discovers that the budget at completion has shifted significantly and is higher than expected. What should the project manager do? | Adjust the original budget estimates with the current cost variance. | Review the activity duration to reforecast the project completion date. | Negotiate the project changes and adjust stakeholder expectations. | Perform a root cause analysis of the project performance. |  | D | When the budget at completion has shifted significantly higher than expected, the project manager should perform a root cause analysis of project performance. Understanding why costs have deviated guides appropriate corrective action. Adjusting original estimates (A) changes the baseline without understanding the cause. Reviewing activity duration (B) addresses schedule, not cost. Negotiating changes and adjusting expectations (C) is appropriate after understanding the cause. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Resources | Planning | Embed Quality | Plan Resource Management | Traditional PM | 프로젝트 실행 중 PM이 완료 시 예산이 크게 이동하여 예상보다 높다는 것을 발견했다. PM은 무엇을 먼저 해야 하는가? | 원래 예산 추정치를 현재 비용 차이로 조정한다 | 활동 기간을 검토하여 프로젝트 완료일을 재예측한다 | 프로젝트 변경을 협상하고 이해관계자 기대를 조정한다 | 프로젝트 성과의 근본 원인 분석을 수행한다 |  | D | 완료 시 예산이 크게 높아졌을 때, PM은 먼저 프로젝트 성과의 근본 원인 분석을 수행해야 한다. 비용 편차의 원인을 이해해야 효과적인 시정 조치가 가능하다. 예산 조정(A)은 원인 파악 전에 성급하다. 기간 검토(B)는 비용이 아닌 일정이다. 변경 협상(C)은 원인 분석 후에 한다.
1737 | An agile project is starting and the assigned team is new to agile. During the first daily meetings, the project manager observes that the team is having problems meeting goals. What should the project manager do? | Plan an outdoor activity tor the team to get to know each other | Ask the human resources department for an experienced agile team | Conduct a meeting to help the team define the team charter | Ask the team to review agile protect management approaches. |  | C | When a new-to-agile team has problems meeting goals during initial daily meetings, the project manager should conduct a meeting to help the team define the team charter. A charter clarifies purpose, vision, values, roles, and expectations. Planning an outdoor activity (A) builds rapport but does not address goal achievement. Asking HR for an experienced agile team (B) replaces rather than develops the team. Asking the team to review agile approaches (D) provides knowledge but not alignment. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트가 시작되고 팀이 애자일에 처음이다. 첫 데일리 미팅에서 목표 달성에 문제가 있다. PM은 무엇을 해야 하는가? | 팀이 서로 알 수 있도록 야외 활동을 계획한다 | 인사부에 경험 있는 애자일 팀을 요청한다 | 팀이 팀 헌장을 정의하도록 회의를 실시한다 | 팀에게 애자일 프로젝트 관리 접근법을 검토하도록 요청한다 |  | C | 애자일에 처음인 팀이 초기 미팅에서 목표 달성에 문제가 있을 때, PM은 팀이 팀 헌장을 정의하도록 회의를 실시해야 한다. 헌장이 목적, 가치, 작업 합의, 기대를 명확히 한다. 야외 활동(A)은 관계 구축이지 목표 달성이 아니다. 팀 교체(B)는 과도하다. 접근법 검토(D)는 이론적이지 실용적이지 않다.
1738 | A project manager is leading a global team that they have worked with in the past and has a high level of trust with them. The team is located in different countries and time zones and will need decisions in a timely manner. In order to ensure that the project runs smoothly across the team, how should the project manager approach delegation? | Delegate certain authorities and share information to allow fair decision-making. | Delegate most authorities and control the authority by withholding important information. | Delegate most authorities and share information to allow fair decision-making. | Delegate certain authorities and control the authority by withholding important information. |  | A | When managing a trusted global team across time zones requiring timely decisions, the project manager should delegate certain authorities and share information to allow fair decision-making. This empowers team members while maintaining transparency and informed decisions. Delegating most authorities while withholding information (B) undermines fair decision-making. Delegating most authorities with full information sharing (C) may over-delegate. Delegating certain authorities while withholding information (D) restricts team effectiveness. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 과거에 함께 일한 높은 신뢰의 글로벌 팀을 이끌고 있다. 시차로 인해 적시 의사결정이 필요하다. PM은 어떻게 해야 하는가? | 특정 권한을 위임하고 공정한 의사결정을 위해 정보를 공유한다 | 대부분의 권한을 위임하고 중요 정보를 보류하여 권한을 통제한다 | 대부분의 권한을 위임하고 공정한 의사결정을 위해 정보를 공유한다 | 특정 권한을 위임하고 중요 정보를 보류하여 권한을 통제한다 |  | A | 신뢰가 높은 글로벌 팀에서 시차로 인한 적시 의사결정이 필요할 때, PM은 특정 권한을 위임하고 공정한 의사결정을 위해 정보를 공유해야 한다. 적절한 위임과 정보 공유가 자율성과 통제의 균형을 맞춘다. 대부분 위임+정보 보류(B)는 모순적이다. 대부분 위임+정보 공유(C)는 과도한 위임이다. 정보 보류(D)는 신뢰를 훼손한다.
1739 | During a project kick-off meeting, the project manager tells team members that they can attend a weekly progress meeting either from home or the office. Which intangible stakeholder engagement quality is the project manager embracing to manage relationships? | Building trust | Being collaborative | Managing expectations | Asking and listening |  | A | Building trust is a key intangible stakeholder engagement quality. By allowing flexible meeting attendance options (home or office), the PM demonstrates trust in team members' ability to work effectively regardless of location. This enhances reciprocal trust and strengthens team commitment to project objectives. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Quality Management | People | Engage Stakeholders | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 프로젝트 킥오프 미팅에서 PM이 팀원들에게 주간 진행 회의에 집에서든 사무실에서든 참석할 수 있다고 말했다. PM이 보여주는 무형의 이해관계자 참여 품질은? | 신뢰 구축 | 협력적이기 | 기대 관리 | 질문하고 경청하기 |  | A | 유연한 회의 참석 옵션을 제공하여 PM은 신뢰를 구축하고 있다. 팀원의 효과적 업무 능력에 대한 신뢰를 보여주며 자율성을 존중한다. 협력(B)은 함께 작업하는 것이다. 기대 관리(C)는 결과에 대한 것이다. 질문/경청(D)은 정보 수집이다.
1740 | A project manager is leading a highly visible project with a critical time constraint. Frequent scope changes have been well-managed with change control, but there have been misunderstandings among project team members. What should the project manager do? | Introduce new products and team support tools during project preparation. | Communicate to the team the need to organize common ground rules. | Communicate changes regularly to ensure all team members are aligned. | Organize training sessions and bonding activities for all team members. |  | C | The correct answer is C. Communicate changes regularly to ensure all team members are aligned. Change management processes ensure proper evaluation and documentation of changes. The PM should assess impacts and follow established procedures before implementing changes. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Change Management | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | PM이 중요한 시간 제약이 있는 고가시성 프로젝트를 이끌고 있다. 빈번한 범위 변경이 있다. 팀 충돌이 발생했다. PM은 무엇을 해야 하는가? | 프로젝트 준비 중 새 제품과 팀 지원 도구를 도입한다 | 팀에게 공통 기본 규칙을 조직할 필요성을 전달한다 | 변경을 정기적으로 전달하여 모든 팀원이 정렬되도록 한다 | 모든 팀원을 위한 교육 세션과 유대 활동을 조직한다 |  | C | 정답은 C이다. 변경을 정기적으로 전달하여 모든 팀원이 정렬되도록 한다. 변경 관리 프로세스는 적절한 평가와 문서화를 보장한다. 정기적 커뮤니케이션이 팀 정렬과 충돌 감소에 핵심이다. 새 도구(A)는 충돌을 해결하지 않는다. 기본 규칙(B)은 부분적이다. 교육/유대(D)는 즉각적 정렬이 아니다.
1741 | A team is the first team in the company to use agile methods for a traditional project. The team's manager is concerned that the risks are not being managed. What should the team do to assess and manage risks regularly? | Identify and escalate any identified risks to the facilitator to handle | Use regular feedback loops through daily standups iteration demos and retrospectives | Focus on developing a working deliverable instead of documenting risks | Update the risk register during every iteration with any open concerns |  | B | When an agile team's manager is concerned about risk management, the team should use regular feedback loops through daily standups, iteration demos, and retrospectives. Continuous feedback identifies and addresses risks collaboratively and in a timely manner. Escalating risks to the facilitator (A) excludes team ownership. Focusing only on deliverables (C) ignores risk impact. Updating the risk register every iteration (D) is good practice but insufficient without the broader feedback loop. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 팀이 전통적 프로젝트에 애자일 방법을 처음 사용한다. 팀 관리자가 리스크 관리에 우려한다. 팀은 무엇을 해야 하는가? | 식별된 리스크를 퍼실리테이터에게 에스컬레이션한다 | 데일리 스탠드업, 이터레이션 데모, 회고를 통해 정기적 피드백 루프를 사용한다 | 리스크 문서화 대신 작동하는 인도물 개발에 집중한다 | 모든 이터레이션에서 미해결 우려사항으로 리스크 등록부를 업데이트한다 |  | B | 애자일 팀의 관리자가 리스크 관리에 우려할 때, 데일리 스탠드업, 이터레이션 데모, 회고를 통해 정기적 피드백 루프를 사용해야 한다. 지속적 피드백이 리스크를 조기에 식별하고 대응한다. 에스컬레이션(A)은 팀 자율성을 무시한다. 인도물 집중(C)은 리스크를 무시한다. 등록부만 업데이트(D)는 대응이 아닌 기록이다.
1742 | A company is leading a project to develop a new product using an agile approach. A supplier was contracted to provide a solution for one of the product features based on mandatory scope, stable requirements, and fixed-price contract. During a meeting with the supplier, the project manager was informed that the company's business analyst also asked the supplier to add a solution for another feature as part of their deliverable. What should the project manager do? | Ask the supplier to accommodate the additional scope under the current agreement. | Ensure the project team understands the agreement and contract in place with the supplier. | Add the feature to the supplier ' s requirement list so they can deliver it. | Monitor the work the business analyst is performing to avoid scope creep. |  | B | When the business analyst has asked the supplier to add scope outside the agreed contract, the project manager should ensure the project team understands the agreement and contract in place with the supplier. This reinforces that any scope changes must follow the formal change control process and prevents unauthorized commitments. Asking the supplier to accommodate additional scope (A) legitimizes the unauthorized request. Adding the feature to the supplier's requirement list (C) bypasses change control. Monitoring the business analyst's work (D) is reactive rather than addressing the root cause through team awareness. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 애자일 프로젝트에서 비즈니스 분석가가 공급업체에 계약 범위 밖의 기능을 추가하도록 요청했다. PM은 무엇을 해야 하는가? | 공급업체에 현재 계약 하에서 추가 범위를 수용하도록 요청한다 | 프로젝트 팀이 공급업체와의 계약과 합의를 이해하도록 한다 | 기능을 공급업체의 요구사항 목록에 추가하여 납품하도록 한다 | 범위 확장을 방지하기 위해 비즈니스 분석가의 작업을 모니터링한다 |  | B | 비즈니스 분석가가 계약 범위 밖의 기능을 공급업체에 요청했을 때, PM은 프로젝트 팀이 계약과 합의를 이해하도록 해야 한다. 계약 경계 인식이 무단 범위 확장을 방지한다. 추가 범위 수용(A)은 계약 위반이다. 기능 추가(C)도 계약 위반이다. 모니터링(D)은 사후적이다.
1743 | A new law was published about zoning permits for telecom towers. This may cause cost and schedule overruns for the new network rollout. What should the project manager do? | Update the project plan because the law is an obligation for the project. | Meet the sponsor to ask for additional time and budget increase. | Minimize the scope to catch the cost and schedule baseline. | Assess and prioritize the impact of the new law on the project plan. |  | D | When a new zoning law may cause cost and schedule overruns for a network rollout, the project manager should assess and prioritize the impact of the new law on the project plan. This involves analyzing how the law affects scope, schedule, cost, and quality, and determining necessary adjustments—consistent with risk analysis and adaptive project management principles. Updating the plan without assessment (A) is premature. Meeting the sponsor to request more time and budget (B) is premature without impact analysis. Minimizing scope (C) sacrifices deliverables before understanding the full impact. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 통신 타워 구역 허가에 관한 새 법률이 발표되었다. 네트워크 롤아웃에 비용과 일정 초과를 야기할 수 있다. PM은 무엇을 해야 하는가? | 법률이 프로젝트의 의무이므로 프로젝트 계획을 업데이트한다 | 스폰서와 만나 추가 시간과 예산 증가를 요청한다 | 비용과 일정 기준을 맞추기 위해 범위를 최소화한다 | 새 법률이 프로젝트 계획에 미치는 영향을 평가하고 우선순위를 정한다 |  | D | 새 구역 법률이 비용과 일정 초과를 야기할 수 있을 때, PM은 먼저 새 법률이 프로젝트 계획에 미치는 영향을 평가하고 우선순위를 정해야 한다. 영향 분석이 적절한 대응의 기초이다. 즉시 업데이트(A)는 평가 없이 성급하다. 추가 예산 요청(B)은 영향 평가 후에 한다. 범위 최소화(C)는 과도한 대응이다.
1744 | A new team member joins the project and fails to apply the project-specific quality assurance (QA) processes. What should the project manager have done to avoid this issue? | Delegated QA tasks to the team lead | Ensured the new team member had access to the quality management plan | Obtained external training in QA for the new team member | Made sure the new team member understood all requirements |  | B | When a new team member fails to apply project-specific QA processes, the project manager should have ensured the new member had access to the quality management plan. The quality plan defines project-specific standards, processes, and practices. Delegating QA to the team lead (A) creates a single point of failure. External QA training (C) addresses general skills, not project-specific processes. Ensuring understanding of all requirements (D) addresses what to build, not how to assure quality. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 새 팀원이 프로젝트에 합류하여 프로젝트 특정 QA 프로세스를 적용하지 않는다. PM이 이전에 무엇을 했어야 하는가? | 팀 리더에게 QA 작업을 위임했다 | 새 팀원이 품질 관리 계획에 접근할 수 있도록 했다 | 새 팀원을 위한 외부 QA 교육을 받았다 | 새 팀원이 모든 요구사항을 이해하도록 했다 |  | B | 새 팀원이 프로젝트 특정 QA 프로세스를 적용하지 않을 때, PM은 새 멤버가 품질 관리 계획에 접근할 수 있도록 했어야 한다. 품질 계획이 프로젝트 특정 표준과 프로세스를 정의한다. QA 위임(A)은 팀원 교육이 아니다. 외부 교육(C)은 프로젝트 특정이 아니다. 요구사항 이해(D)는 범위이지 QA가 아니다.
1745 | A project manager is leading a software development team to upgrade a banking software. During a sprint review, the product owner suggested a small addition to the process that might necessitate a change to the sprint. What should the project manager do? | Review the proposed change with the team and consult the project sponsor for approval. | Submit the proposed change to the change control board (CCB) to evaluate and approve. | Accept the product owner ' s suggested change and notify the project sponsor of the acceptance. | Evaluate the product owner ' s proposed change alone and consult the project sponsor for approval. |  | A | The PM should review the proposed change with the team and consult the project sponsor for approval. The product owner plays a critical role in agile by prioritizing the backlog and defining requirements. The PM facilitates collaboration between the team and stakeholders while respecting agile governance principles. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 뱅킹 소프트웨어 업그레이드 팀을 이끄는 PM이다. 스프린트 리뷰에서 제품 책임자가 백로그 우선순위에 큰 영향을 미치는 변경을 제안했다. PM은 무엇을 해야 하는가? | 팀과 제안된 변경을 검토하고 프로젝트 스폰서에게 승인을 상의한다 | 변경통제위원회(CCB)에 제안된 변경을 제출하여 평가하고 승인한다 | 제품 책임자의 제안된 변경을 수락하고 프로젝트 스폰서에게 수락을 알린다 | 제품 책임자의 제안된 변경을 단독으로 평가하고 프로젝트 스폰서에게 승인을 상의한다 |  | A | 제품 책임자가 백로그 우선순위에 큰 영향을 미치는 변경을 제안할 때, PM은 팀과 변경을 검토하고 스폰서에게 승인을 상의해야 한다. 팀 검토가 영향을 평가하고 스폰서 승인이 거버넌스를 보장한다. CCB 제출(B)은 애자일에서 과도할 수 있다. 바로 수락(C)은 영향 평가 없다. 단독 평가(D)는 팀 참여가 없다.
1746 | A project manager has joined a company in an unfamiliar industry and has been given a strategically important project. Being new, and not fully understanding the interdependences of the various departmental work items, the project manager is unsure of how to plan the project. How should the project manager proceed? | Consult the project sponsor and request their feedback | Consult a senior developer within the organization and request their input. | Consult a senior project manager within the organization and request their expert judgement | Consult the product owner and request a complete prioritization session |  | C | When a project manager in an unfamiliar industry needs to understand work item interdependencies for planning, they should consult a senior project manager within the organization and request their expert judgment. Senior PMs have organizational and industry knowledge that directly informs project planning. Consulting the project sponsor (A) provides strategic direction but may lack planning detail. Consulting a senior developer (B) provides technical input but not PM-level planning insight. Consulting the product owner for prioritization (D) addresses backlog, not interdependencies. | Process | Manage Project Issues | Project Work | Navigate Complexity | Hybrid | Predictive-Agile Blend | Business Environment | Remove Impediments and Manage Issues | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | Traditional PM | PM이 낯선 산업의 회사에 합류하여 전략적으로 중요한 프로젝트를 받았다. 작업 항목 간 상호 의존성을 이해해야 한다. 누구와 상의해야 하는가? | 프로젝트 스폰서와 상의하여 피드백을 요청한다 | 조직 내 시니어 개발자와 상의하여 의견을 요청한다 | 조직 내 시니어 PM과 상의하여 전문가 판단을 요청한다 | 제품 책임자와 상의하여 완전한 우선순위화 세션을 요청한다 |  | C | 낯선 산업에서 작업 항목 간 상호 의존성을 이해해야 할 때, PM은 조직 내 시니어 PM과 상의하여 전문가 판단을 요청해야 한다. 시니어 PM이 프로젝트 관리 맥락에서 상호 의존성에 대한 가장 관련 있는 전문 지식을 제공한다. 스폰서(A)는 전략적이지 기술적이지 않다. 시니어 개발자(B)는 기술적이지 PM 관점이 아니다. 우선순위화 세션(D)은 의존성 이해 후에 한다.
1747 | Some members of a project team are frustrated by a new team member who previously worked in a Scrum setting. This new team member approaches members of the project team on a daily basis in what appears to be an attempt to engage in individual standup meetings. What should the project manager do? | Mentor the new team member on the methodology the project team is using | Schedule a meeting for the project team to review the communications management plan. | Send an email to the project team outlining the communications strategy. | Tell the rest of the project team to continue discussions with the new team member |  | A | When a new team member from a Scrum background approaches project team members daily for standup-style conversations causing frustration, the project manager should mentor the new team member on the methodology the project team is using. Explaining the rationale, benefits, and communication expectations of the current methodology helps the new member adapt. Scheduling a meeting to review the communications plan (B) is indirect. Sending an email about communications strategy (C) is impersonal. Telling the team to continue discussions (D) does not address the root cause of frustration. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Align Stakeholder Expectations | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 팀원이 이전에 스크럼 환경에서 일했다. 매일 팀원들에게 다가가 스탠드업 스타일 대화를 시도하여 다른 팀원들이 짜증을 낸다. PM은 무엇을 해야 하는가? | 새 팀원에게 프로젝트 팀이 사용하는 방법론을 멘토링한다 | 프로젝트 팀이 커뮤니케이션 관리 계획을 검토하는 회의를 예약한다 | 프로젝트 팀에 커뮤니케이션 전략을 설명하는 이메일을 보낸다 | 나머지 팀원들에게 새 팀원과 계속 대화하라고 말한다 |  | A | 스크럼 배경의 새 팀원이 다른 방법론을 사용하는 팀에서 스탠드업 스타일 대화로 짜증을 줄 때, PM은 새 팀원에게 프로젝트 팀이 사용하는 방법론을 멘토링해야 한다. 개인 맞춤 안내가 적응을 돕는다. 회의(B)는 한 사람 문제에 과도하다. 이메일(C)은 비개인적이다. 계속 대화(D)는 문제를 무시한다.
1748 | A product owner has an idea for a new product but is struggling to define the features because they are not certain of the perceived business value for each feature. What should the project manager have the delivery team do to address this issue? | Develop a minimum viable product (MVP) for assessment from a select customer group. | Assess the product roadmap to see if there is another product that is more suitable for the build. | Complete a work breakdown structure (WBS) to assess the cost of each feature | Commission a business analyst to research similar competitor products. |  | A | When the product owner is uncertain about the business value of features, the delivery team should develop a minimum viable product (MVP) for assessment from a select customer group. An MVP delivers enough features to validate assumptions, test business value with real users, and provide feedback for future development—consistent with the agile principle of delivering value early and iteratively. Assessing the product roadmap (B) does not test value with customers. Commissioning a business analyst to research competitors (D) is a predictive approach. Completing a WBS to assess cost (C) focuses on cost rather than business value. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Finance | Monitoring & Controlling | Build an Empowered Culture | Control Costs | Traditional PM | 제품 책임자가 새 제품 아이디어가 있지만 비즈니스 가치가 확실하지 않아 기능 정의에 어려움을 겪는다. 납품 팀은 무엇을 해야 하는가? | 선별된 고객 그룹의 평가를 위한 최소 기능 제품(MVP)을 개발한다 | 더 적합한 제품이 있는지 제품 로드맵을 평가한다 | 각 기능 비용을 평가하기 위한 작업 분해 구조(WBS)를 완성한다 | 비즈니스 분석가에게 유사 경쟁 제품을 조사하도록 의뢰한다 |  | A | 제품 책임자가 기능의 비즈니스 가치를 확신하지 못할 때, 납품 팀은 선별된 고객 그룹의 평가를 위한 MVP를 개발해야 한다. MVP가 최소 투자로 시장 검증을 가능하게 한다. 로드맵 평가(B)는 기존 제품이지 새 아이디어가 아니다. WBS(C)는 비용이지 가치 검증이 아니다. 경쟁사 조사(D)는 간접적이다.
1749 | A project manager is assigned to a global project where, during the planning process, team members from different regions are not agreeing to collaborate with each other. What should the project manager do? | Coordinate a meeting to understand the situation and resolve any conflicts. | Review lessons learned from previous projects that used the same team | Coordinate a meeting with regional managers to ask for support | Review the organizational culture, structure, and governance |  | A | When team members from different regions refuse to collaborate during the planning process of a global project, the project manager should coordinate a meeting to understand the situation and resolve any conflicts. Direct facilitation fosters trust, respect, and mutual understanding while addressing the root causes of resistance. Reviewing lessons learned from previous projects (B) provides historical context but does not address current conflict. Coordinating with regional managers (C) escalates before direct engagement. Reviewing organizational culture and governance (D) provides context but does not actively resolve the conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 글로벌 프로젝트 계획 과정에서 다른 지역의 팀원들이 협력을 거부한다. PM은 무엇을 해야 하는가? | 상황을 이해하고 갈등을 해결하기 위한 회의를 조정한다 | 같은 팀을 사용한 이전 프로젝트의 교훈을 검토한다 | 지역 관리자와 회의를 조정하여 지원을 요청한다 | 조직 문화, 구조, 거버넌스를 검토한다 |  | A | 글로벌 프로젝트에서 다른 지역 팀원들이 협력을 거부할 때, PM은 상황을 이해하고 갈등을 해결하기 위한 회의를 조정해야 한다. 직접적 대화가 근본 원인 파악과 해결의 기초이다. 교훈 검토(B)는 과거 정보이다. 관리자 지원(C)은 직접 해결 시도 후에 한다. 문화 검토(D)는 배경 정보이지 행동이 아니다.
1750 | A project manager has been assigned to lead a major project in a government organization. There are no policies and procedures for project management since there is no project management office (PMO). The managers involved are unaware of their responsibilities for the project. What should the project manager do? | Provide project management training to the stakeholders and explain their responsibilities | Start planning the project and then request that a PMO be implemented in the organization | Request that the implementation of a PMO be executed in parallel with the project | Provide project management training to only the internal team involved m the project |  | A | The PM should provide project management training to stakeholders and clearly explain their responsibilities. This approach directly addresses the root cause—lack of understanding about governance, roles, and PM processes—rather than bypassing proper procedures or creating additional problems through workaround solutions. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | PM이 정부 조직의 주요 프로젝트를 이끌도록 배정되었다. 프로젝트 관리에 대한 정책과 절차가 없다. PM은 무엇을 해야 하는가? | 이해관계자에게 프로젝트 관리 교육을 제공하고 그들의 책임을 설명한다 | 프로젝트 계획을 시작하고 그 후 조직에 PMO 구현을 요청한다 | 프로젝트와 병행하여 PMO 구현을 요청한다 | 프로젝트에 관련된 내부 팀에게만 프로젝트 관리 교육을 제공한다 |  | A | 프로젝트 관리 정책이 없는 정부 조직에서, PM은 이해관계자에게 PM 교육을 제공하고 책임을 설명해야 한다. 근본 원인인 이해 부족을 직접 해결한다. 계획 후 PMO 요청(B)은 순서가 잘못되었다. PMO 병행(C)은 과도하다. 내부 팀만 교육(D)은 이해관계자를 제외한다.
1751 | A project manager has just received communication from an operational functional manager to complete an additional scope item for a project that was formally closed a few weeks ago. The scope looks relatively small and simple to handle as part of the daily operations activity. How should the project manager deal with this request? | Confirm that the budget and resources are available to execute the work request. | Check the alternative resources available in the organization for the request. | Submit a change request and allocate the budget and resources needed for execution. | Evaluate the nature of the request and plan communication accordingly. |  | D | When a formally closed project receives a request for additional scope from a functional manager, the project manager should evaluate the nature of the request and plan communication accordingly. This involves assessing whether the request aligns with operational activities, understanding its implications, and coordinating with relevant stakeholders before taking action. Confirming budget and resource availability (A) assumes execution before evaluation. Checking alternative resources (B) skips the evaluation step. Submitting a change request (C) is inappropriate since the project is already closed. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 공식적으로 종료된 프로젝트에서 기능 관리자가 추가 범위 작업을 완료하라는 커뮤니케이션을 받았다. PM은 무엇을 해야 하는가? | 작업 요청을 실행할 예산과 자원이 가용한지 확인한다 | 조직에서 요청에 사용할 수 있는 대안 자원을 확인한다 | 변경 요청을 제출하고 실행에 필요한 예산과 자원을 할당한다 | 요청의 성격을 평가하고 그에 따라 커뮤니케이션을 계획한다 |  | D | 종료된 프로젝트에 추가 범위 요청이 올 때, PM은 먼저 요청의 성격을 평가하고 커뮤니케이션을 계획해야 한다. 종료된 프로젝트인지 새 프로젝트인지 판단이 우선이다. 예산 확인(A)은 평가 후에 한다. 대안 자원(B)도 평가 후이다. 변경 요청(C)은 종료된 프로젝트에는 부적절할 수 있다.
1752 | A project manager receives a serious complaint from a functional manager about a team member. What should the project manager do? | Support the team member and provide documentation to the functional managerproving their performance. | Protect the team member and ask the project sponsor to minimize any externalinterruptions. | Discuss the issue with the functional manager to understand the reason for thecomplaint. | Replace the team member immediately to maintain a good relationship with thefunctional manager. |  | C | When receiving a serious complaint from a functional manager about a team member, the project manager should discuss the issue with the functional manager to understand the reason for the complaint. Understanding before acting enables fair resolution. Supporting the team member with documentation (A) is one-sided. Protecting the team member from interruptions (B) avoids the issue. Replacing the team member immediately (D) is premature. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | PM이 기능 관리자로부터 팀원에 대한 심각한 불만을 받았다. PM은 무엇을 해야 하는가? | 팀원을 지원하고 기능 관리자에게 성과 증명 문서를 제공한다 | 팀원을 보호하고 프로젝트 스폰서에게 외부 방해를 최소화하도록 요청한다 | 기능 관리자와 이슈를 논의하여 불만의 이유를 이해한다 | 기능 관리자와의 좋은 관계를 유지하기 위해 팀원을 즉시 교체한다 |  | C | 기능 관리자로부터 팀원에 대한 심각한 불만을 받을 때, PM은 기능 관리자와 이슈를 논의하여 불만의 이유를 이해해야 한다. 이해가 적절한 대응의 기초이다. 무조건 지원(A)은 사실 확인 전이다. 보호(B)는 문제를 회피한다. 즉시 교체(D)는 이해 없이 극단적이다.
1753 | A project is starting its second iteration out of six. During the daily meeting, a team member requests help. In order to complete a deliverable, an approval from the design department will be needed. What should the project manager do? | Update the issue log and escalate it to the project sponsor. | Invite a design team member to the next daily meeting. | Replace this iteration deliverable for one without any blockers. | Meet with the design manager to ask for the necessary approval. |  | B | Bringing a design team member into the next daily meeting enables direct communication and cross-functional collaboration—core agile principles. This approach facilitates rapid issue resolution and reflects the iterative nature of agile delivery, where transparency and teamwork are essential for delivering value each iteration. While an issue log helps track and manage problems, it cannot replace the immediacy and effectiveness of face-to-face (or real-time) communication when quick action is needed. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 프로젝트가 6번째 중 두 번째 이터레이션을 시작한다. 데일리 미팅에서 팀원이 도움을 요청한다. 디자인 팀의 승인이 필요하다. PM은 무엇을 해야 하는가? | 이슈 로그를 업데이트하고 프로젝트 스폰서에게 에스컬레이션한다 | 다음 데일리 미팅에 디자인 팀 멤버를 초대한다 | 이터레이션 인도물을 차단 요소가 없는 것으로 교체한다 | 디자인 관리자와 만나 필요한 승인을 요청한다 |  | B | 디자인 팀의 승인이 필요한 차단 요소가 있을 때, 다음 데일리 미팅에 디자인 팀 멤버를 초대하는 것이 직접적 커뮤니케이션과 교차 기능 협력을 가능하게 한다. 이는 핵심 애자일 원칙이다. 에스컬레이션(A)은 과도하다. 인도물 교체(C)는 회피이다. 관리자 미팅(D)은 간접적이다.
1754 | A project team is using a vendor solution. The project team has been notified that the vendor solution will no longer be on the premises, but in the cloud. The cloud transition will require additional infrastructure resources and adherence to new security standards. What should the project manager do first? | Ask the sponsor to provide security training for the project team. | Schedule a meeting with security to understand the standards. | Initiate a change request for covering additional security scope. | Research alternative vendor solutions for on-premise security. |  | B | The correct answer is B. Schedule a meeting with security to understand the standards. Procurement management involves proper planning, execution, and control of vendor relationships. The PM should ensure contract compliance, monitor performance, and address issues through appropriate channels. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 벤더 솔루션을 사용 중이다. 벤더가 보안 패치를 지원하지 않을 것이라는 통보를 받았다. PM은 무엇을 해야 하는가? | 스폰서에게 프로젝트 팀을 위한 보안 교육을 요청한다 | 보안 부서와 회의를 예약하여 표준을 이해한다 | 추가 보안 범위를 위한 변경 요청을 시작한다 | 온프레미스 보안을 위한 대안 벤더 솔루션을 조사한다 |  | B | 정답은 B이다. 보안 부서와 회의를 예약하여 표준을 이해한다. 조달 관리는 벤더 관계의 적절한 계획, 실행, 통제를 포함한다. PM은 보안 요구사항과 표준을 먼저 이해해야 적절한 대응을 계획할 수 있다. 보안 교육(A)은 근본 해결이 아니다. 변경 요청(C)은 표준 이해 후에 한다. 대안 조사(D)는 요구 이해 후에 한다.
1755 | A self-organizing team for a critical project is consistently delivering value according to their commitments. During a retrospective, the project manager observed that most of the team members were stressed due to overcommitments. What should the project manager do? | Request additional resources to continue delivering value while reducing team stress. | Ask individual team members to plan staggered leave to avoid becoming stressed. | Help the team members by organizing regular stress-relieving and team- building sessions . | Support the team during the planning phase to only commit to what they are able to 838 deliver. |  | D | When a self-organizing team consistently delivers value but is stressed from overcommitments, the project manager should support the team during the planning phase to only commit to what they are able to deliver. Sustainable pace through realistic commitments prevents burnout. Requesting additional resources (A) adds people without addressing the commitment issue. Staggering leave (B) manages symptoms, not causes. Organizing stress-relief sessions (C) treats symptoms without fixing the root cause. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Integrate Sustainability | Manage Stakeholder Engagement | Sustainability | 자체 조직화 팀이 약속에 따라 지속적으로 가치를 전달하지만 과도한 약속으로 스트레스를 받고 있다. PM은 무엇을 해야 하는가? | 가치 전달을 계속하면서 팀 스트레스를 줄이기 위해 추가 자원을 요청한다 | 개별 팀원에게 스트레스 방지를 위해 교대 휴가를 계획하도록 요청한다 | 정기적 스트레스 해소 및 팀 빌딩 세션을 조직하여 팀원을 돕는다 | 계획 단계에서 팀이 전달할 수 있는 양만 약속하도록 지원한다 |  | D | 팀이 과도한 약속으로 스트레스를 받을 때, PM은 계획 단계에서 팀이 전달 가능한 양만 약속하도록 지원해야 한다. 지속 가능한 속도가 핵심이다. 추가 자원(A)은 과도한 약속 문제를 해결하지 않는다. 교대 휴가(B)는 증상 치료이다. 팀 빌딩(C)은 스트레스 원인을 다루지 않는다.
1756 | A company is initiating a project to enhance one of its existing products. All of its products are developed internally. What should the project manager do? | Identify the risk of implementing the new solution and evaluate the impact on the project. | Create a lessons learned document for the initiation phase | Review the lessons learned from the previous project | Ensure the stakeholder engagement plan is accurate and properly documented. |  | C | When initiating a project to enhance an existing internally developed product, the project manager should review the lessons learned from the previous project. Historical insights on what worked and what did not inform better planning and execution for the enhancement. Identifying implementation risks (A) is important but follows lessons learned review. Creating a lessons learned document for initiation (B) is premature. Ensuring the stakeholder engagement plan is documented (D) is a planning activity that comes later. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 회사가 기존 제품 개선 프로젝트를 시작한다. 모든 제품이 내부 개발된다. PM은 무엇을 먼저 해야 하는가? | 새 솔루션 구현 리스크를 식별하고 프로젝트에 미치는 영향을 평가한다 | 시작 단계에 대한 교훈 문서를 생성한다 | 이전 프로젝트의 교훈을 검토한다 | 이해관계자 참여 계획이 정확하고 적절히 문서화되었는지 확인한다 |  | C | 기존 내부 제품을 개선하는 프로젝트를 시작할 때, PM은 이전 프로젝트의 교훈을 검토해야 한다. 과거 통찰이 무엇이 잘 작동했고 무엇이 안 했는지 알려준다. 리스크 식별(A)은 교훈 검토 후에 한다. 교훈 생성(B)은 시작 시가 아닌 종료 시이다. 참여 계획 확인(D)은 교훈 검토 후에 한다.
1757 | After conducting a performance assessment, the project manager identified that some gaps still exist. What should the project manager ensure? | All team members rotate their job schedules immediately to make them versatile. | Awards are given to all team members for playing a role in the project and undertaking the assessment. | Assessment results are kept private and not shared among team members. | Performance improvement programs are organized for all team members who were assessed. |  | D | After a performance assessment reveals remaining gaps, the project manager should ensure performance improvement programs are organized for all assessed team members. Structured improvement initiatives proactively address identified gaps, supporting continuous professional development and overall project performance improvement. Rotating job schedules immediately (A) is disruptive and does not target specific gaps. Giving awards to all team members (B) recognizes contribution but does not address performance gaps. Keeping results private (C) prevents collaborative improvement and transparency. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Governance | Executing | Embed Quality | Manage Project Knowledge | Traditional PM | 성과 평가 후 PM이 일부 격차가 여전히 존재함을 식별했다. PM은 무엇을 해야 하는가? | 모든 팀원이 즉시 직무 일정을 교대하여 다재다능하게 한다 | 프로젝트에 역할을 수행하고 평가를 받은 모든 팀원에게 상을 수여한다 | 평가 결과를 비공개로 유지하고 팀원 간에 공유하지 않는다 | 평가를 받은 모든 팀원을 위한 성과 개선 프로그램을 조직한다 |  | D | 성과 평가에서 격차가 식별될 때, PM은 평가를 받은 모든 팀원을 위한 성과 개선 프로그램을 조직해야 한다. 체계적 개선이 격차를 해소한다. 직무 교대(A)는 격차 해결이 아니다. 상 수여(B)는 격차를 다루지 않는다. 비공개 유지(C)는 개선 기회를 놓친다.
1758 | A project manager is working to create a product that can be released to the market as soon as it passes rigorous quality standards. Historically, the company has used a predictive methodology, but the company is exploring the implementation of agile methodologies. The company asked the project manager to explain the value gained by using an agile process. How should the project manager respond? | Early value will be gained only if beta products can be released to the market. | Early value can be gained by testing the most important features in the initial stages to fix deviations. | Early value cannot be achieved until the product is fully released. | Early value will be gained only if the speed can be increased to release the product to the market. |  | B | Testing the most important features early allows the team to identify and fix deviations before they compound. In agile environments, the PM facilitates collaboration, removes impediments, and ensures continuous value delivery through iterative development and feedback cycles. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 엄격한 품질 테스트 후 시장 출시 제품을 만들고 있다. 조기 가치에 대한 PM의 견해는? | 조기 가치는 베타 제품이 시장에 출시될 때만 얻을 수 있다 | 가장 중요한 기능을 초기 단계에서 테스트하여 편차를 수정하면 조기 가치를 얻을 수 있다 | 제품이 완전히 출시될 때까지 조기 가치를 달성할 수 없다 | 제품을 시장에 출시하는 속도를 높일 수 있을 때만 조기 가치를 얻을 수 있다 |  | B | 가장 중요한 기능을 초기에 테스트하면 편차가 복합되기 전에 식별하고 수정할 수 있다. 애자일 환경에서 PM은 협력을 촉진하고 장애물을 제거하며 지속적 가치 전달을 보장한다. 베타 출시(A)는 제한적이다. 완전 출시까지 불가(C)는 점진적 가치를 무시한다. 속도 증가(D)는 품질을 희생한다.
1759 | A project manager has been given a critical, 5-day window and is allocated a maximum of US$100,000 as a contingency reserve. Subsequently, the project manager drafted a course of action based upon the best available information. Overall, five actions were required to be completed at a cost of US$20,000 and a duration of 1 day each. After 3 days of work, the project manager completed two actions and spent US$80,000. What should the project manager do next? | As the CPI and SPI are greater than 1.0, reevaluate and prioritize the remaining actions. | Stop the work and raise a project change request to the change control board (CCB) for additional funds and a project schedule extension. | As the cost performance index (CPI) and schedule performance index (SPI) are less than 1.0, reevaluate and prioritize the remaining actions. | Complete all actions and then inform the client of the additional cost and schedule overrun needed to complete the project. |  | C | With US$80,000 spent to complete only two of five actions in three days, both budget and schedule performance are below plan. CPI (earned value / actual cost) and SPI (earned value / planned value) are both below 1.0, indicating the project is over budget and behind schedule. The PM should reevaluate and prioritize the remaining actions to maximize use of the remaining budget and time. This may involve identifying the most critical remaining actions and finding ways to complete them within constraints, or seeking additional resources or time if necessary. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | PM이 5일 창에 최대 $100,000 비상 예비비를 배정받았다. 3일 만에 $80,000을 사용하여 5개 중 2개 조치만 완료했다. PM은 무엇을 해야 하는가? | CPI와 SPI가 1.0보다 크므로 남은 조치를 재평가하고 우선순위를 정한다 | 작업을 중단하고 CCB에 추가 자금을 위한 변경 요청을 제기한다 | CPI와 SPI가 1.0보다 작으므로 남은 조치를 재평가하고 우선순위를 정한다 | 모든 조치를 완료하고 고객에게 추가 비용과 일정 초과를 알린다 |  | C | 3일에 $80,000으로 5개 중 2개만 완료했으므로, 예산과 일정 성과 모두 계획 이하이다. CPI와 SPI가 1.0 미만이므로, 남은 조치를 재평가하고 우선순위를 정해야 한다. CPI/SPI > 1.0(A)은 사실과 다르다. 작업 중단(B)은 극단적이다. 모든 조치 완료(D)는 예산/일정 초과를 야기한다.
1760 | An agile senior project team member suddenly resigns from the organization. Following this departure, the remaining team members are having difficulty accessing information and are unable to complete a deliverable. What should the project manager have done to avoid this situation? | Provided specialist training for all team members. | Updated the job descriptions for all team roles. 1282 | Ensured the project repository is up to date. | Made an effort to reemploy the senior project team member. |  | A | When a senior agile team member's sudden resignation causes the remaining team to lose access to information, the project manager should have ensured the project repository was up to date. Centralized documentation prevents knowledge silos. Specialist training (A) builds skills but does not capture knowledge. Updating job descriptions (B) is administrative. Trying to rehire the member (D) is reactive. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 시니어 애자일 팀원이 갑자기 사직했다. 남은 팀이 정보에 접근할 수 없게 되었다. PM이 이전에 무엇을 했어야 하는가? | 모든 팀원에게 전문가 교육을 제공했다 | 모든 팀 역할의 직무 설명을 업데이트했다 | 프로젝트 저장소가 최신 상태인지 확인했다 | 시니어 팀원을 재고용하려는 노력을 했다 |  | C | 시니어 팀원의 갑작스러운 사직으로 정보 접근이 불가할 때, PM은 프로젝트 저장소가 최신 상태인지 확인했어야 한다. 중앙화된 최신 정보가 지식 연속성을 보장한다. 전문가 교육(A)은 유용하지만 즉각적 정보 접근을 보장하지 않는다. 직무 설명(B)은 정보 접근과 무관하다. 재고용(D)은 사후 대응이다.
1761 | A company has transitioned and is now delivering projects using a hybrid approach instead of a predictive approach. The distributed project team's knowledge of agile is varied. The project manager feels the new methodology will impact the timely delivery of the project. What should the project manager do? | Use the predictive approach tor team members who are not knowledgeable m agile project delivery practices | Ask to execute the project with a predictive approach since there is a budget and schedule risk | Use crashing to reduce the critical path to ensure enough buffer to include the impact of the agile methodology update | agile tools and techniques used m the defined hybrid methodology for consistent application by all team members |  | D | When a distributed team has varied agile knowledge and the PM fears methodology impact on delivery, the project manager should ensure consistent application of agile tools and techniques used in the defined hybrid methodology by all team members. Standardization ensures everyone operates within the same framework effectively. Using predictive for non-agile team members (A) fragments the approach. Requesting to use only predictive methodology (B) abandons the hybrid transition. Crashing the critical path (C) addresses schedule but not the knowledge gap. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Hybrid/Tailoring | 회사가 예측형에서 하이브리드 접근법으로 전환했다. 분산된 팀의 애자일 지식이 다양하다. PM은 무엇을 해야 하는가? | 애자일 실무에 대한 지식이 없는 팀원에게 예측형 접근법을 사용한다 | 예산과 일정 리스크가 있으므로 예측형 접근법으로 프로젝트를 실행하도록 요청한다 | 크래싱으로 주공정선을 단축하여 애자일 학습 영향을 위한 충분한 버퍼를 포함한다 | 정의된 하이브리드 방법론에서 사용되는 애자일 도구와 기법을 모든 팀원이 일관되게 적용하도록 한다 |  | D | 분산 팀의 애자일 지식이 다양할 때, PM은 하이브리드 방법론의 애자일 도구와 기법을 모든 팀원이 일관되게 적용하도록 해야 한다. 일관된 적용이 품질과 효율을 보장한다. 예측형만 사용(A)은 하이브리드 전환을 무시한다. 예측형 요청(B)도 전환을 거부한다. 크래싱(C)은 학습을 대체하지 않는다.
1762 | A project manager is transferred to another country to perform a project within their organization. What should the project manager do first to ensure collaboration within the team for a successful delivery? | Mentor the team members to perform project management. | Assign a local resource to manage communication with the team. | Determine a leadership style that is suitable for that location. | Check if resources from headquarters can also be assigned to the project. |  | C | When transferred to another country for a project, the project manager should first determine a leadership style suitable for that location. Different cultures have varying preferences for communication, decision-making, power distance, and teamwork. Adapting leadership style ensures effective collaboration with the local team. Mentoring team members in project management (A) develops skills but does not address cultural adaptation. Assigning a local resource for communication (B) delegates rather than adapts. Checking if headquarters resources can be assigned (D) does not address the cultural adaptation need. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 조직 내 다른 나라에서 프로젝트를 수행하기 위해 전근되었다. PM은 무엇을 먼저 해야 하는가? | 팀원들에게 프로젝트 관리를 수행하도록 멘토링한다 | 팀과의 커뮤니케이션을 관리할 현지 자원을 배정한다 | 해당 지역에 적합한 리더십 스타일을 결정한다 | 본사의 자원도 프로젝트에 배정할 수 있는지 확인한다 |  | C | 다른 나라로 전근되어 프로젝트를 수행할 때, PM은 먼저 해당 지역에 적합한 리더십 스타일을 결정해야 한다. 다른 문화는 커뮤니케이션, 의사결정, 권한에 대해 다른 선호를 가진다. 멘토링(A)은 리더십 스타일 결정 후에 한다. 현지 자원(B)은 부분적 해결이다. 본사 자원(D)은 현지 문화 적응이 아니다.
1763 | During the implementation phase of a construction project, a key supplier went bankrupt and cannot supply the contracted material. This issue could affect the project schedule. What should the project manager do first? | Escalate to the management team for delay approval | Update the schedule to include the delay | Add the risk and the delay to the risk register | Update the issue log and act to minimize the impact |  | D | When a key supplier goes bankrupt during the construction execution phase, the project manager should first update the issue log and act to minimize the impact. Documenting the issue and taking immediate action protects the schedule. Escalating to management (A) delays action. Updating the schedule to include the delay (B) accepts the impact without mitigation. Adding to the risk register (C) treats a realized issue as a risk. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | 건설 프로젝트 실행 중 주요 공급업체가 파산하여 계약된 자재를 공급할 수 없다. PM은 무엇을 해야 하는가? | 경영진에게 지연 승인을 위해 에스컬레이션한다 | 지연을 포함하도록 일정을 업데이트한다 | 리스크와 지연을 리스크 등록부에 추가한다 | 이슈 로그를 업데이트하고 영향을 최소화하기 위해 조치한다 |  | D | 주요 공급업체가 파산할 때, PM은 이슈 로그를 업데이트하고 영향을 최소화하기 위해 즉시 조치해야 한다. 이슈 문서화와 즉각적 행동이 핵심이다. 에스컬레이션(A)은 조치 없이 보고만이다. 일정 업데이트(B)는 대응이 아닌 기록이다. 리스크 등록부(C)는 이슈는 이미 발생했으므로 리스크가 아니다.
1764 | During a project review meeting, the project sponsor is worried that the project may not be delivering results as planned. Based on that, the project manager is evaluating the project status. What information should the project manager use as an indicator that the project is actually delivering value? | The project is aligned with the project charter | The project is under budget and on schedule | The protect is aligned with the benefits management plan | Stakeholders are satisfied with the current status. |  | C | When evaluating whether the project is delivering value during a project review, the project manager should use alignment with the benefits management plan as the indicator. The benefits plan defines expected outcomes and measurement criteria. Alignment with the project charter (A) measures scope compliance, not value. Under budget and on schedule (B) measures efficiency, not effectiveness. Stakeholder satisfaction (D) is subjective and may not reflect actual value. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 리뷰 회의에서 스폰서가 프로젝트가 계획대로 결과를 전달하지 않을 수 있다고 우려한다. 가치 전달 여부를 나타내는 지표는? | 프로젝트가 프로젝트 헌장과 정렬되어 있다 | 프로젝트가 예산 이하이고 일정에 맞다 | 프로젝트가 혜택 관리 계획과 정렬되어 있다 | 이해관계자가 현재 상태에 만족한다 |  | C | 프로젝트가 가치를 전달하는지 평가할 때, 혜택 관리 계획과의 정렬이 지표이다. 혜택 계획은 프로젝트가 달성해야 할 비즈니스 가치를 정의한다. 헌장 정렬(A)은 목표이지 가치 전달이 아니다. 예산/일정(B)은 효율성이지 가치가 아니다. 이해관계자 만족(D)은 주관적이다.
1765 | A customer calls the project manager to express concern about a project team member who has been making changes within the live environment without approval. The team member mentioned that the customer called and asked them to make the changes. What should the project manager do next? | Reinforce the value of documenting and approving all change requests and ask 900 thecustomer to issue these through the agreed channels. | Explain to the customer that the team member was just trying to help and the changescan be reverted if necessary. | Organize a meeting to mediate the relationship between the customer and the teammember to ensure no feelings are hurt. | Ask the customer to email all requests directly to you and you will ensure they areactioned by the correct team member. |  | A | When a team member makes unauthorized live environment changes claiming the customer requested them, the project manager should reinforce the value of documenting and approving all change requests and ask the customer to use agreed channels. Proper change management prevents unauthorized modifications. Explaining the team member was trying to help (B) dismisses the process violation. Organizing a mediation meeting (C) treats it as a relationship issue. Asking the customer to email the PM directly (D) adds bottleneck without fixing the process. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 고객이 PM에게 전화하여 팀원이 고객 요청이라 주장하며 라이브 환경에서 무단 변경을 했다고 우려를 표명한다. PM은 무엇을 해야 하는가? | 모든 변경 요청의 문서화와 승인의 가치를 강화하고 고객에게 공식 요청을 발행하도록 요청한다 | 고객에게 팀원이 돕고자 했을 뿐이고 변경은 필요 시 되돌릴 수 있다고 설명한다 | 고객과 팀원 간 관계를 중재하여 향후 오해가 없도록 회의를 조직한다 | 고객에게 모든 요청을 PM에게 직접 이메일로 보내면 정확한 팀원이 처리하도록 하겠다고 요청한다 |  | A | 팀원이 무단으로 라이브 환경을 변경했을 때, PM은 모든 변경 요청의 문서화와 승인의 가치를 강화하고 고객에게 공식 요청을 발행하도록 요청해야 한다. 변경 관리 프로세스 준수가 핵심이다. 설명(B)은 프로세스 무시를 정당화한다. 중재(C)는 프로세스 문제를 관계 문제로 다룬다. PM에게 직접 이메일(D)은 병목을 만든다.
1766 | A customer is concerned about the time required to complete a project and is asking the project team to reduce the number of iterations required to complete the product. Which approach should the project manager take? | Ask the team to challenge the project estimations for a faster delivery. | Prioritize deliverables based on business value and define frequent releases. | Prioritize the tasks with high risks to reduce the number of iterations required. | Ask the team to raise blockers or impediments in daily meetings. |  | B | When a customer wants to reduce iterations and accelerate delivery, the project manager should prioritize deliverables based on business value and define frequent releases. This approach ensures the most critical features are developed first while shorter release cycles provide quicker feedback loops and the ability to adjust priorities—potentially satisfying the customer's timeline concerns without compromising quality. Challenging project estimations (A) risks underestimating work and creating unrealistic expectations. Prioritizing high-risk tasks (C) addresses risk but not business value delivery. Raising blockers in daily meetings (D) is an operational practice that does not address the customer's strategic concern about project duration. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 고객이 프로젝트 완료에 필요한 시간에 우려하며 이터레이션 수를 줄이도록 요청한다. PM은 무엇을 해야 하는가? | 팀에게 더 빠른 납품을 위해 프로젝트 추정치에 도전하도록 요청한다 | 비즈니스 가치에 따라 인도물의 우선순위를 정하고 빈번한 릴리스를 정의한다 | 높은 리스크 작업의 우선순위를 정하여 필요한 이터레이션 수를 줄인다 | 팀에게 데일리 미팅에서 장애물이나 방해 요소를 제기하도록 요청한다 |  | B | 고객이 이터레이션을 줄이고 납품을 가속화하려 할 때, PM은 비즈니스 가치에 따라 인도물의 우선순위를 정하고 빈번한 릴리스를 정의해야 한다. 이 접근법이 가장 가치 있는 항목이 먼저 전달되도록 한다. 추정치 도전(A)은 품질을 위협한다. 리스크 우선순위(C)는 가치 전달과 직접 관련 없다. 장애물 제기(D)는 일상적 관행이지 가속 전략이 아니다.
1767 | In an agile project, two key stakeholders disagree about a major new requirement. Recognizing that this could lead to potential issues, what should the project manager do next? | Ask the two key stakeholders to agree on the requirement based on a Pareto analysis. | Facilitate a meeting with the stakeholders and product owner to clarify the new need, | Review the new requirement and update all the stakeholders accordingly. | Update the acceptance criteria documentation to clearly reflect what was approved. |  | B | When two key stakeholders disagree about a major new requirement in an agile project, the project manager should facilitate a meeting with the stakeholders and product owner to clarify the new need. Facilitated discussion with the product owner resolves ambiguity. Asking stakeholders to agree based on Pareto analysis (A) applies a technique prematurely. Reviewing and updating all stakeholders (C) distributes information without resolving the disagreement. Updating acceptance criteria (D) is premature before clarification. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 애자일 프로젝트에서 두 주요 이해관계자가 새로운 주요 요구사항에 대해 동의하지 않는다. PM은 무엇을 해야 하는가? | 파레토 분석에 기반하여 두 이해관계자에게 요구사항에 합의하도록 요청한다 | 이해관계자와 제품 책임자와의 회의를 퍼실리테이션하여 새로운 요구를 명확히 한다 | 새 요구사항을 검토하고 모든 이해관계자에게 그에 따라 업데이트한다 | 승인된 내용을 명확히 반영하도록 인수 기준 문서를 업데이트한다 |  | B | 두 주요 이해관계자가 새 요구사항에 동의하지 않을 때, PM은 이해관계자와 제품 책임자와의 회의를 퍼실리테이션하여 새로운 요구를 명확히 해야 한다. 퍼실리테이션된 대화가 합의를 이끈다. 파레토 분석(A)은 우선순위 도구이지 갈등 해결이 아니다. 검토 후 업데이트(C)는 합의 없이 일방적이다. 인수 기준 업데이트(D)는 합의 후에 한다.
1768 | A project team member has lost enthusiasm and is experiencing low morale for a project they were once excited about. What should the project manager do? | Escalate the issue to the team member ' s functional manager and request a responseas soon as possible. | Meet with the team member to understand what the issues are and to provide support. | Have the team member transferred to another project and add other resources to theproject. | Leverage other team members who are contributing and making the project a success. |  | C | When a team member has lost enthusiasm and is experiencing low morale, the project manager should meet with the team member to understand what the issues are and provide support. Direct, empathetic engagement identifies the root cause and demonstrates care for the individual's wellbeing. Escalating to the functional manager (A) is premature before direct engagement. Transferring the team member (C) removes rather than addresses the problem. Leveraging other contributing team members (D) ignores the individual's situation. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 팀원이 한때 열정적이었던 프로젝트에 대한 열의를 잃고 사기가 저하되었다. PM은 무엇을 해야 하는가? | 팀원의 기능 관리자에게 이슈를 에스컬레이션하고 빠른 응답을 요청한다 | 팀원과 만나 문제를 이해하고 지원을 제공한다 | 팀원을 다른 프로젝트로 이동시키고 다른 자원을 추가한다 | 기여하고 있는 다른 팀원을 활용한다 |  | C | 팀원이 열의를 잃고 사기가 저하될 때, PM은 팀원과 만나 문제를 이해하고 지원을 제공해야 한다. 직접적이고 공감적인 참여가 근본 원인을 파악한다. 에스컬레이션(A)은 직접 대화 전에 과도하다. 이동(C보기)은 조기 포기이다. 다른 팀원 활용(D)은 문제를 무시한다.
1769 | The scope of a construction project that is being planned by a multinational company requires that services are procured via contract from an external provider. When considering communication channels, what should the project manager do to help maximize delivery success with this provider? | Assign a project team member to document exchanged communication for future reference. | Assign the project sponsor as the point of contact for all provider communication. | Establish a common language of terms with which to communicate with the provider. | Ensure that all project stakeholders participate in the scope definition meetings. |  | C | When procuring services from an external provider for a construction project, the project manager should establish a common language of terms to communicate with the provider. Shared terminology reduces misunderstandings and improves delivery. Assigning a team member to document communications (A) is supportive but secondary. Assigning the sponsor as contact point (B) misplaces communication responsibility. Ensuring all stakeholders participate in scope definition (D) is general and does not target the provider relationship. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 건설 프로젝트의 범위가 외부 제공업체에서 서비스를 조달해야 한다. PM은 무엇을 먼저 해야 하는가? | 교환된 커뮤니케이션을 향후 참조를 위해 문서화하도록 팀원을 배정한다 | 프로젝트 스폰서를 모든 제공업체 커뮤니케이션의 연락 창구로 지정한다 | 제공업체와 커뮤니케이션할 공통 용어를 수립한다 | 모든 프로젝트 이해관계자가 범위 정의 회의에 참여하도록 한다 |  | C | 외부 제공업체에서 서비스를 조달할 때, PM은 제공업체와 커뮤니케이션할 공통 용어를 수립해야 한다. 공유된 용어가 오해를 줄이고 효율적 협업을 보장한다. 문서화(A)는 유용하지만 공통 이해가 먼저이다. 스폰서를 창구로(B)는 비효율적이다. 모든 이해관계자 참여(D)는 비현실적일 수 있다.
1770 | A new engineer was assigned to a project. Although the engineer has adequate skills for the job, they always wait for authorization from the project manager before acting. What should the project manager do? | Make all of the decisions for the engineer in order to keep the workflow on track. | Determine the appropriate level of decision-making authority and empower the engineer. | Replace the resource with an experienced engineer. | Obtain related training for the new team member. |  | B | When a new engineer with adequate skills always waits for project manager authorization before acting, the project manager should determine the appropriate level of decision-making authority and empower the engineer. Empowerment builds ownership and efficiency. Making all decisions for them (A) reinforces dependency. Replacing the resource (C) wastes potential. Obtaining training (D) is unnecessary since skills are adequate. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 엔지니어가 프로젝트에 배정되었다. 적절한 기술이 있지만 항상 PM의 승인을 기다린다. PM은 무엇을 해야 하는가? | 워크플로를 유지하기 위해 엔지니어를 위한 모든 결정을 내린다 | 적절한 수준의 의사결정 권한을 결정하고 엔지니어에게 권한을 부여한다 | 경험 있는 엔지니어로 자원을 교체한다 | 새 팀원을 위한 관련 교육을 확보한다 |  | B | 적절한 기술이 있지만 항상 승인을 기다리는 새 엔지니어에게, PM은 적절한 수준의 의사결정 권한을 결정하고 권한을 부여해야 한다. 명확한 권한 위임이 자율성과 책임감을 키운다. 모든 결정 대행(A)은 의존성을 강화한다. 교체(C)는 과도하다. 교육(D)은 기술이 아닌 자신감 문제이므로 부적절하다.
1771 | A project manager is working on the delivery of a solution that needs to be deployed to the public quickly. The project team is experienced, the stakeholders are supporting the delivery, and the customer is cooperating. What strategy should the project manager use to ensure on-time delivery of the solution? | Have a detailed plan of all milestones, deliverables, functionalities, and allocation of resources. | Meet with the customer to agree on the components of the solution and the priorities. | Have a high-level plan for incremental deliveries and get the customer ' s feedback as early as possible. | Ask the sponsor for support regarding the allocation of additional resources to finish on time. |  | C | When a solution needs rapid public deployment with an experienced team and cooperative stakeholders, the project manager should have a high-level plan for incremental deliveries and get the customer's feedback as early as possible. Incremental delivery enables fast deployment with early validation. A detailed plan of all milestones and resources (A) follows a predictive approach that may slow delivery. Meeting the customer to agree on components (B) is a planning activity but not a delivery strategy. Asking for additional resources (D) may not be necessary with an experienced team. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | PM이 빠르게 공개 배포되어야 하는 솔루션을 전달하고 있다. 팀은 경험 있고 이해관계자는 협조적이다. PM은 무엇을 해야 하는가? | 모든 마일스톤, 인도물, 기능, 자원 배분의 상세 계획을 수립한다 | 고객과 만나 솔루션의 구성 요소와 우선순위에 합의한다 | 점진적 납품을 위한 상위 수준 계획을 수립하고 가능한 빨리 고객 피드백을 얻는다 | 스폰서에게 제시간에 완료하기 위한 추가 자원 배분 지원을 요청한다 |  | C | 빠른 공개 배포가 필요하고 경험 있는 팀과 협조적 이해관계자가 있을 때, PM은 점진적 납품을 위한 상위 수준 계획을 수립하고 빨리 고객 피드백을 얻어야 한다. 점진적 접근이 빠른 가치 전달을 가능하게 한다. 상세 계획(A)은 시간이 많이 든다. 구성 요소 합의(B)는 배포 계획이 아니다. 추가 자원(D)은 불필요하다.
1772 | A project team has missed the delivery date for the West milestone of a large software development project. Project governance dictates that formal communication be sent to project stakeholders, including the project manager's supervisor, when a milestone is missed. The project manager is concerned that this will reflect poorly on the team. What should the project manager do? | Delay sending a formal communication until the project team catches up | Ask for a meeting with the sponsor to decide whether to send the formal communication | Forego the formal communication and have a conversation with the supervisor | Send a formal communication regarding the missed milestone |  | D | When project governance requires formal communication about a missed milestone, the project manager should send the formal communication as required. Transparency and accountability are fundamental to maintaining trust with stakeholders, even when the news reflects poorly on the team. Delaying communication (A) or foregoing it (C) undermines trust and sets a precedent for non-transparency. Asking the sponsor whether to send it (B) could appear as an attempt to avoid responsibility and still creates unnecessary delay. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 팀이 대규모 소프트웨어 개발 프로젝트의 마일스톤 납기일을 놓쳤다. 프로젝트 거버넌스가 공식 커뮤니케이션을 요구한다. PM은 무엇을 해야 하는가? | 프로젝트 팀이 따라잡을 때까지 공식 커뮤니케이션 발송을 지연한다 | 스폰서와 회의를 요청하여 공식 커뮤니케이션 발송 여부를 결정한다 | 공식 커뮤니케이션을 포기하고 상사와 대화한다 | 놓친 마일스톤에 대한 공식 커뮤니케이션을 발송한다 |  | D | 거버넌스가 놓친 마일스톤에 대한 공식 커뮤니케이션을 요구할 때, PM은 요구대로 공식 커뮤니케이션을 발송해야 한다. 투명성과 책임이 프로젝트 관리의 기본이다. 발송 지연(A)은 투명성을 위반한다. 스폰서 회의(B)는 불필요한 지연이다. 대화로 대체(C)는 거버넌스 요구를 무시한다.
1773 | A project manager led the implementation of an electronic invoicing project that has just been completed. The financial manager communicated that the team discovered three invoices with errors. Which two documents should the project manager update as soon as possible? (Choose two) | Risk register | Change log | Stakeholder register | Issue log | Backlog register | D, E | When issues are identified during quality inspections, the PM should update two project documents: the issue log (D) to formally record the quality issues, their severity, and assign ownership for resolution, and the backlog register (E) to track the remediation items and prioritize them alongside other work. The issue log provides formal issue tracking, while the backlog register integrates quality fixes into the team's workflow. The risk register (A) tracks potential future risks and responses, not issues that have already materialized. The change log (B) records approved changes, not newly discovered quality issues. The stakeholder register (C) classifies stakeholders and their requirements but does not track project issues. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Planning | Focus on Value | Collect Requirements | Traditional PM | PM이 전자 송장 프로젝트 구현을 완료했다. 재무 부서가 품질 검사 중 문제를 식별했다. PM이 업데이트해야 할 두 가지 프로젝트 문서는? | 리스크 등록부 | 변경 로그 | 이해관계자 등록부 | 이슈 로그 | 백로그 등록부 | D, E | 품질 검사에서 문제가 식별되면, PM은 두 가지 프로젝트 문서를 업데이트해야 한다: 이슈 로그(D)에 품질 문제를 공식 기록하고 심각도와 해결 담당을 지정하며, 백로그 등록부(E)에 해결 필요 항목을 추가한다. 리스크 등록부(A)는 잠재적 미래 사건용이다. 변경 로그(B)는 승인된 변경 기록이다. 이해관계자 등록부(C)는 관련 없다.
1774 | A bank has decided to initiate a project to transition from serving small businesses and entrepreneurs to mid- and large-scale businesses. The country's economy is struggling, and some stakeholders cannot agree on this transformation need. What should the project manager do? | Plan for strategic program management | Escalate the issue to the sponsor and ask for stakeholder engagement | Implement a communications management plan | Review the project business case and update it periodically |  | C | When stakeholders disagree on a business transformation project during an economic struggle, the project manager should implement a communications management plan. Effective, structured communication aligns stakeholders, manages expectations, addresses concerns, and provides transparency about progress and challenges. Planning strategic program management (A) is broader than needed. Escalating for stakeholder engagement (B) delegates the PM's communication responsibility. Reviewing the business case periodically (D) provides justification but does not actively manage stakeholder alignment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 은행이 중소기업에서 중대기업으로 전환하는 프로젝트를 시작했다. 경제적 어려움 속에 이해관계자가 동의하지 않는다. PM은 무엇을 해야 하는가? | 전략적 프로그램 관리를 계획한다 | 스폰서에게 이슈를 에스컬레이션하고 이해관계자 참여를 요청한다 | 커뮤니케이션 관리 계획을 구현한다 | 프로젝트 비즈니스 케이스를 검토하고 주기적으로 업데이트한다 |  | C | 경제적 어려움 속에 이해관계자가 사업 전환 프로젝트에 동의하지 않을 때, PM은 커뮤니케이션 관리 계획을 구현해야 한다. 효과적이고 구조화된 커뮤니케이션이 이해관계자 간 이해와 합의를 구축한다. 프로그램 관리(A)는 범위가 다르다. 에스컬레이션(B)은 직접 관리 전에 과도하다. 비즈니스 케이스 업데이트(D)는 유용하지만 이해관계자 합의가 우선이다.
1775 | Midway through the execution of an agile project, there is a shift in the strategic objectives at the organization level to promote digital transformation. What should the project manager do next? | Escalate to the product owner and cancel the upcoming iterations. | Prepare a user story to handle the change and assign it to the next iteration. | Update the risk-prioritized backlog with the strategic change. | Schedule a meeting with the team to assess the impact of the change. |  | D | When organizational strategic objectives shift to digital transformation mid-project, the project manager should schedule a meeting with the team to assess the impact of the change. Collaborative assessment enables the team to adapt work and future iterations to the new direction. Escalating to the product owner and cancelling iterations (A) is premature. Preparing a user story for the change (B) acts before understanding impact. Updating the risk-prioritized backlog (C) should follow the assessment, not precede it. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Scrum | Business Environment | Support Organizational Change | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Digital Transformation | 애자일 프로젝트 실행 중 조직 수준에서 디지털 전환으로 전략적 목표가 변경되었다. PM은 무엇을 먼저 해야 하는가? | 제품 책임자에게 에스컬레이션하고 예정된 이터레이션을 취소한다 | 변경을 처리할 사용자 스토리를 준비하고 다음 이터레이션에 할당한다 | 전략적 변경으로 리스크 우선순위 백로그를 업데이트한다 | 팀과 회의를 예약하여 변경의 영향을 평가한다 |  | D | 조직의 전략적 목표가 디지털 전환으로 변경될 때, PM은 먼저 팀과 회의를 예약하여 변경의 영향을 평가해야 한다. 협력적 평가가 정보에 기반한 의사결정을 가능하게 한다. 이터레이션 취소(A)는 성급하다. 사용자 스토리 준비(B)는 영향 평가 전에 과도하다. 백로그 업데이트(C)는 평가 후에 한다.
1776 | A project manager's new employer decided to use an agile delivery approach to implement a new accounting system. The chief financial officer (CFO), who is also the project sponsor, is committed to a new way of working but does not have experience as a product owner. The project manager's background includes a couple of years' experience as an agile practitioner working as a scrum master. What should the project manager do at the start of the project? | Delay the build of the system until the project sponsor is ready to take over the product owner role. | Work with and assist the project sponsor in building and prioritizing the product backlog. | Collaborate with the development team to help the project sponsor acquire the relevant skills. | Assume the product owner role until the project sponsor is ready to take over the product owner role. |  | B | The correct answer is B. Work with and assist the project sponsor in building and prioritizing the product backlog. The product owner manages backlog priorities and defines requirements. The PM should support the product owner's role while facilitating team collaboration and maintaining agile practices. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Be an Accountable Leader | Determine Budget | Traditional PM | 새 고용주가 새 회계 시스템에 애자일 납품 접근법을 사용하기로 했다. 프로젝트 스폰서가 제품 책임자 역할에 익숙하지 않다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서가 제품 책임자 역할을 맡을 준비가 될 때까지 시스템 구축을 지연한다 | 프로젝트 스폰서를 도와 제품 백로그를 구축하고 우선순위를 정한다 | 개발 팀과 협력하여 프로젝트 스폰서가 관련 기술을 습득하도록 돕는다 | 프로젝트 스폰서가 준비될 때까지 제품 책임자 역할을 대행한다 |  | B | 정답은 B이다. 프로젝트 스폰서를 도와 제품 백로그를 구축하고 우선순위를 정한다. 제품 책임자가 백로그 우선순위를 관리하고 요구사항을 정의한다. PM은 제품 책임자 역할을 지원하면서 스폰서의 역량을 구축해야 한다. 지연(A)은 프로젝트를 방해한다. 팀 협력(C)은 간접적이다. 역할 대행(D)은 역할 경계를 침해한다.
1777 | An agile team is making infrastructure changes to the human resources (HR) application system. Conflicting requirements are being submitted by various stakeholders. What should the project manager do to help move the project forward? | Encourage the stakeholders to collaborate by facilitating meetings and sharing knowledge. | Review documents provided by other teams, such as lessons learned and the risk matrix. | Attend the Scrum of Scrums to identify roadblocks and manage dependencies. | Study the technology to assist the team in decision-making if progress slows. |  | A | When conflicting requirements from various stakeholders hinder an agile HR infrastructure project, the project manager should encourage stakeholder collaboration by facilitating meetings and sharing knowledge. Facilitation resolves conflicts through dialogue. Reviewing other teams' documents (B) is passive. Attending Scrum of Scrums (C) addresses inter-team coordination, not stakeholder conflicts. Studying the technology (D) does not resolve requirement conflicts. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 애자일 팀이 HR 애플리케이션 시스템에 인프라 변경을 하고 있다. 여러 이해관계자의 상충되는 요구사항이 진행을 방해한다. PM은 무엇을 해야 하는가? | 이해관계자가 회의를 통해 협력하고 지식을 공유하도록 장려한다 | 교훈과 리스크 매트릭스 등 다른 팀이 제공한 문서를 검토한다 | 스크럼 오브 스크럼에 참석하여 장애물을 식별하고 종속성을 관리한다 | 팀의 의사결정을 지원하기 위해 기술을 연구한다 |  | A | 여러 이해관계자의 상충되는 요구사항이 애자일 HR 프로젝트를 방해할 때, PM은 이해관계자가 회의를 통해 협력하고 지식을 공유하도록 장려해야 한다. 퍼실리테이션된 협력이 갈등을 해결하고 합의를 이끈다. 문서 검토(B)는 간접적이다. 스크럼 오브 스크럼(C)은 팀 간 조정이지 이해관계자 갈등이 아니다. 기술 연구(D)는 요구사항 갈등을 해결하지 않는다.
1778 | During the setup of an agile project, the product owner expressed clear interest in having features released during product development over having the product completed in one year. What should the project manager do? | Promote a productive environment where everybody can work without interruptions from the rest of the team members | Design a set of metrics including velocity, which is a good measure of value delivered. | Create a reward system recognizing group contributions to get people motivated and improve performance | Facilitate sprint planning sessions with a focus on defining the minimum viable product (MVP) |  | D | When the product owner wants features released during development rather than a single completion, the project manager should facilitate sprint planning sessions with a focus on defining the minimum viable product (MVP). MVP-focused planning enables early, incremental value delivery aligned with the product owner's interest. Promoting a productive environment (A) is general. Designing velocity metrics (B) measures performance but does not drive release strategy. Creating a reward system (C) motivates but does not structure delivery. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 애자일 프로젝트 설정 중 제품 책임자가 개발 중 기능이 릴리스되기를 원한다. PM은 무엇을 해야 하는가? | 나머지 조직의 방해 없이 모두가 작업할 수 있는 생산적 환경을 촉진한다 | 가치 전달의 좋은 척도인 속도를 포함한 지표 세트를 설계한다 | 동기를 부여하고 성과를 개선하기 위해 그룹 기여를 인정하는 보상 시스템을 만든다 | 최소 실행 가능 제품(MVP) 정의에 초점을 맞춘 스프린트 계획 세션을 퍼실리테이션한다 |  | D | 제품 책임자가 개발 중 기능 릴리스를 원할 때, PM은 MVP 정의에 초점을 맞춘 스프린트 계획 세션을 퍼실리테이션해야 한다. MVP 집중이 빈번한 릴리스를 가능하게 한다. 생산적 환경(A)은 일반적이다. 속도 지표(B)는 측정이지 납품 전략이 아니다. 보상 시스템(C)은 동기 부여이지 릴리스 전략이 아니다.
1779 | During the last iteration of a hybrid project, one of the key members of the team wants to leave the project. What should the project manager do to address this concern? | Request an additional resource to finish the project. | Keep activities as planned regardless of the resource change. | Have a meeting with the resource to understand the issue. | Update the burndown chart to reflect this resource ' s absence. |  | C | When a key team member wants to leave during the last iteration of a hybrid project, the project manager should have a meeting with the resource to understand the issue. Direct engagement identifies root causes and potential solutions. Requesting additional resources (A) does not address the underlying concern. Keeping activities as planned (B) ignores the impact. Updating the burndown chart (D) documents but does not address the cause. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 하이브리드 프로젝트의 마지막 이터레이션 중 핵심 팀원이 프로젝트를 떠나려 한다. PM은 무엇을 해야 하는가? | 프로젝트를 마치기 위해 추가 자원을 요청한다 | 자원 변경에 관계없이 계획대로 활동을 유지한다 | 자원과 회의하여 문제를 이해한다 | 이 자원의 부재를 반영하도록 번다운 차트를 업데이트한다 |  | C | 핵심 팀원이 마지막 이터레이션에 프로젝트를 떠나려 할 때, PM은 자원과 회의하여 문제를 이해해야 한다. 직접적 참여가 근본 원인을 파악하고 잠재적으로 유지를 가능하게 한다. 추가 자원(A)은 문제 이해 전에 성급하다. 계획 유지(B)는 영향을 무시한다. 차트 업데이트(D)는 기록이지 해결이 아니다.
1780 | A project manager finds it challenging to comply with standardized processes for knowledge transfer. The project teams and stakeholders are scattered around field sites, the office, and remote locations. In addition, some team members have limited access to the electronically shared files. How should the project manager manage this challenge? | Request changes in the processes since it is not suitable for the company environment. | Send the intended information through email since it is the primary communication tool. | Study the environment and the available resources to determine which approach to use. | Communicate a strong message to the team explaining the importance of knowledge transfer. |  | C | When standardized knowledge transfer processes are challenging due to dispersed teams with limited electronic access, the project manager should study the environment and available resources to determine which approach to use. Tailoring the approach to the specific context ensures effective knowledge transfer. Requesting process changes (A) may not be feasible. Relying on email (B) ignores limited access. Communicating the importance of knowledge transfer (D) does not solve the practical challenges. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Align Stakeholder Expectations | Risk | Executing | Focus on Value | Implement Risk Responses | Traditional PM | PM이 지식 이전을 위한 표준화된 프로세스를 준수하기 어렵다. 팀이 분산되어 있고 전자 접근이 제한적이다. PM은 무엇을 해야 하는가? | 회사 환경에 적합하지 않으므로 프로세스 변경을 요청한다 | 주요 커뮤니케이션 도구인 이메일로 정보를 전송한다 | 환경과 가용 자원을 연구하여 어떤 접근법을 사용할지 결정한다 | 팀에 지식 이전의 중요성을 설명하는 강력한 메시지를 전달한다 |  | C | 표준화된 지식 이전 프로세스가 분산 팀과 제한된 전자 접근으로 어려울 때, PM은 환경과 가용 자원을 연구하여 적절한 접근법을 결정해야 한다. 상황 맞춤 접근이 효과적이다. 프로세스 변경 요청(A)은 시도 전에 성급하다. 이메일만(B)은 제한적이다. 강력한 메시지(D)는 실질적 해결이 아니다.
1781 | An agile project has just started, and the backlog is being prioritized. The customer wants to prioritize business value over identified risks. How should the customer's request be managed? | Assess risks together with business value during prioritization. | Accept risks as they decrease over a period of time. | Create a risk value profile to track the relative importance of risks. | Log and track risks separately as only business value is important. |  | A | When a customer wants to prioritize business value over risks during backlog prioritization, the request should be managed by assessing risks together with business value during prioritization. Integrating both factors ensures feasible, high-value delivery while managing uncertainty. Accepting risks as decreasing over time (B) ignores active risk management. Creating a risk value profile (C) is a tracking tool, not a prioritization method. Logging risks separately (D) creates a disconnect between risk and value decisions. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 애자일 프로젝트가 시작되어 백로그 우선순위를 정하고 있다. 고객이 리스크보다 비즈니스 가치를 우선하길 원한다. 이 요청을 어떻게 관리해야 하는가? | 우선순위 결정 시 리스크를 비즈니스 가치와 함께 평가한다 | 리스크는 시간이 지나면 감소하므로 수용한다 | 리스크의 상대적 중요성을 추적하기 위한 리스크 가치 프로필을 만든다 | 비즈니스 가치만 중요하므로 리스크를 별도로 기록하고 추적한다 |  | A | 고객이 리스크보다 비즈니스 가치를 우선하길 원할 때, PM은 우선순위 결정 시 리스크를 비즈니스 가치와 함께 평가해야 한다. 통합 평가가 균형 잡힌 의사결정을 보장한다. 리스크 수용(B)은 무책임하다. 리스크 가치 프로필(C)은 과도한 문서화이다. 별도 추적(D)은 리스크를 무시한다.
1782 | A project manager is leading a progress review meeting when some stakeholders who are new to the project express concerns about not having access to previously shared deliverables. What should the project manager do? | Document the new stakeholders ' concerns in the meeting minutes. | Use the project management information system (PMIS) to share information. | Use social media environments to share the project information | Schedule an ad hoc meeting with the new stakeholders to discuss concerns. |  | B | When new stakeholders express concerns about not having access to previously shared deliverables during a progress review, the project manager should use the PMIS to share information. A centralized information system ensures consistent and accessible project communication. Documenting concerns in meeting minutes (A) records but does not solve access issues. Using social media (C) is informal. Scheduling an ad hoc meeting (D) addresses concerns temporarily but not systematically. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 진행 검토 회의를 이끄는 중 새 이해관계자가 이전 공유된 인도물에 접근하지 못한다고 우려한다. PM은 무엇을 해야 하는가? | 새 이해관계자의 우려를 회의록에 문서화한다 | PMIS를 사용하여 정보를 공유한다 | 소셜 미디어 환경을 사용하여 프로젝트 정보를 공유한다 | 새 이해관계자와 임시 회의를 예약하여 우려를 논의한다 |  | B | 새 이해관계자가 이전 인도물에 접근하지 못할 때, PM은 PMIS를 사용하여 정보를 공유해야 한다. 중앙화된 정보 시스템이 모든 이해관계자에게 일관된 접근을 제공한다. 문서화(A)는 기록일 뿐 해결이 아니다. 소셜 미디어(C)는 부적절한 채널이다. 임시 회의(D)는 접근 문제를 해결하지 않는다.
1783 | A project manager is working on a project with three virtual teams. Team A is in a different time zone than teams B and C. The project was going well, but recently team A has started feeling left out. Information reaches team A late or is sometimes missed, and teams B and C give preference to each other's problems over team A. The project manager has already set project guidelines, but realizes they need to be improved. Which two things should the project manager do to help the teams collaborate better? (Choose two) | Schedule weekly progress meetings with all three teams and have them take turns as key players. | Plan for team members to temporarily work at each other ' s locations to better provide a sense of community. | Create a status reporting template and share it with all team members before the day ends. | Update the communications management plan and encourage the teams to review it promptly and proactively. | Schedule daily meetings with each team to understand their progress and concerns in detail. | A, D | When managing three geographically distributed teams in different time zones, the PM should take two actions: schedule weekly progress meetings with all three teams and have them take turns presenting updates (A) to foster cross-team visibility and shared ownership, and update the communications management plan and encourage the teams to review it periodically (D) to formalize expectations and ensure all teams are aligned on communication protocols. Regular joint meetings build collaboration, while an updated plan provides ongoing governance. Temporarily relocating team members (B) is logistically impractical across different time zones. Creating a status reporting template (C) is a narrow communication tool that does not address cross-team collaboration. Scheduling daily meetings with each team separately (E) increases meeting burden without building cross-team collaboration. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | PM이 3개의 가상 팀과 프로젝트를 진행 중이다. 팀 A는 팀 B, C와 다른 시간대에 있다. PM은 무엇을 해야 하는가? | 3개 팀 모두와 주간 진행 회의를 예약하고 교대로 핵심 발표자가 되게 한다 | 팀원들이 일시적으로 상대방 위치에서 근무하도록 계획한다 | 상태 보고 템플릿을 만들어 하루가 끝나기 전에 모든 팀원과 공유한다 | 커뮤니케이션 관리 계획을 업데이트하고 팀이 신속하고 적극적으로 검토하도록 장려한다 | 각 팀과 매일 회의하여 진행 상황과 우려사항을 상세히 파악한다 | A, D | 서로 다른 시간대의 3개 분산 팀을 관리할 때, PM은 두 가지 조치를 취해야 한다: 3개 팀 모두와 주간 진행 회의를 예약하고 교대로 발표하게 하며(A), 커뮤니케이션 관리 계획을 업데이트하고 팀이 적극적으로 검토하도록 장려한다(D). 주간 회의가 동기화를 보장하고 커뮤니케이션 계획이 기대를 설정한다. 일시적 위치 변경(B)은 비용이 크다. 보고 템플릿만(C)은 상호작용이 부족하다. 매일 회의(E)는 시간대로 인해 비현실적이다.
1784 | Some of the more experienced members of a project team have complained about the project manager. The senior project team members feel that the project manager is micromanaging them and preventing them from completing their work. What should the project manager do when made aware of these issues? | Meet daily with each senior team member to monitor project status | Ask for advice on how to be a better mentor to these team members. | Adjust the project manager ' s management style to better fit senior team members. | Set up a team building event to bring synergy back to the project team. |  | C | The PM should adjust their management style to better fit senior team members who prefer autonomy, trust, and feedback. Micromanagement—while sometimes appropriate for inexperienced teams—causes frustration, demotivation, and resentment among skilled professionals. Adapting leadership style using situational leadership, emotional intelligence, and coaching techniques enables the PM to match their approach to team maturity and individual needs. | People | Promote Team Performance through EI | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 경험 있는 팀원들이 PM에 대해 불만을 제기했다. 선임 팀원들이 마이크로매니지먼트를 느끼고 있다. PM은 무엇을 해야 하는가? | 각 선임 팀원과 매일 만나 프로젝트 상태를 모니터링한다 | 이 팀원들에게 더 나은 멘토가 되는 방법에 대한 조언을 구한다 | 선임 팀원에게 더 잘 맞도록 PM의 관리 스타일을 조정한다 | 팀에 시너지를 되찾기 위한 팀 빌딩 이벤트를 설정한다 |  | C | 선임 팀원이 마이크로매니지먼트를 느낄 때, PM은 선임 팀원에게 더 잘 맞도록 관리 스타일을 조정해야 한다. 자율성, 신뢰, 피드백을 선호하는 경험 있는 팀원에게 맞는 리더십 스타일이 필요하다. 매일 만남(A)은 마이크로매니지먼트를 강화한다. 멘토 조언(B)은 근본 문제를 다루지 않는다. 팀 빌딩(D)은 관리 스타일 문제를 해결하지 않는다.
1785 | A senior management team member contacts an agile project lead and mentions that certain features the senior manager thought would be in the current release were not included. What should the agile project lead do? | Assure the senior manager that these features will be queued up in the next sprint. | Send the product roadmap to the senior manager. | Invite the senior manager to the next planning meeting. | Meet with the team to understand why the senior manager's features were not included. |  | C | When a senior manager's expected features were not included in the current release, the agile project lead should invite the senior manager to the next planning meeting. Direct participation aligns expectations with backlog prioritization and product vision. Assuring features will be in the next sprint (A) creates unrealistic commitments. Sending the product roadmap (B) may not address specific concerns. Meeting with the team to understand the omission (D) misplaces responsibility for feature definition. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Schedule | Planning | Build an Empowered Culture | Define Activities | Traditional PM | 고위 관리자가 애자일 프로젝트 리더에게 현재 릴리스에 자신이 기대한 기능이 포함되지 않았다고 언급한다. PM은 무엇을 해야 하는가? | 고위 관리자에게 이러한 기능이 다음 스프린트에 대기열에 올라갈 것이라고 보장한다 | 고위 관리자에게 제품 로드맵을 보낸다 | 고위 관리자를 다음 계획 회의에 초대한다 | 팀과 만나 고위 관리자의 기능이 왜 포함되지 않았는지 이해한다 |  | C | 고위 관리자의 기대 기능이 현재 릴리스에 포함되지 않았을 때, PM은 고위 관리자를 다음 계획 회의에 초대해야 한다. 직접 참여가 기대를 정렬하고 우선순위화에 입력을 제공한다. 보장(A)은 현실적이지 않을 수 있다. 로드맵 전송(B)은 일방적이다. 팀 회의(D)는 고위 관리자를 배제한다.
1786 | In a time-critical construction project, a misunderstanding occurred between the supervisor and the technician. The misunderstanding turned into a major conflict and the technician has complained to the project manager that they cannot continue to work under the supervisor any longer. The supervisor cites the technician's poor performance as the reason for the conflict. How should the project manager resolve the problem? | Replace the technician with a high performing resource as time is critical | Provide a just-in-time training to the technician to improve their skill set. | Use a direct, collaborative approach with the technician and supervisor. | Talk to the supervisor to tone down their approach and attitude. |  | C | In a time-critical construction project where a supervisor-technician conflict has escalated, the project manager should use a direct, collaborative approach with both parties. Collaboration addresses root causes and seeks mutually acceptable solutions. Replacing the technician (A) disrupts the project. Providing just-in-time training (B) assumes the issue is skill-based. Asking the supervisor to tone down (D) addresses only one side. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 시간이 중요한 건설 프로젝트에서 감독관과 기술자 간 오해가 발생하여 갈등이 고조되었다. PM은 무엇을 해야 하는가? | 시간이 중요하므로 기술자를 고성과 자원으로 교체한다 | 기술자에게 기술 향상을 위한 적시 교육을 제공한다 | 기술자와 감독관에게 직접적이고 협력적인 접근법을 사용한다 | 감독관에게 접근법과 태도를 누그러뜨리도록 말한다 |  | C | 시간이 중요한 건설 프로젝트에서 감독관-기술자 갈등이 고조될 때, PM은 양측에게 직접적이고 협력적인 접근법을 사용해야 한다. 협력이 근본 원인을 다루고 관계를 회복한다. 교체(A)는 갈등을 해결하지 않는다. 교육(B)은 갈등이 아닌 기술 문제용이다. 감독관만 접근(D)은 편향적이다.
1787 | A project manager is assigned midway through a project. The team members are in different locations across the country and they are unable to meet in person often. During a status review meeting, one of the stakeholders highlighted that they were unaware of the status for the project deliverables. What should the project manager do first? | Review the stakeholder management plan and update the stakeholder register forincorporation in the project management plan. | Schedule a meeting with the stakeholder and include the stakeholder ' s needs in the project management plan. | Review the communications management plan and verify whether the stakeholder ' s needs are captured in the project management plan. | Request the project team include the stakeholder ' s details and make sure the projectstatus reports are shared with the stakeholder. |  | C | The PM should first review the communications management plan to verify whether the stakeholder's communication requirements, preferences, and expectations are properly addressed. If gaps exist, the plan should be updated accordingly. Other actions—updating the stakeholder register, modifying the project management plan, or scheduling meetings—are secondary to understanding and fixing the root communication gap. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | PM이 프로젝트 중간에 배정되었다. 팀이 여러 지역에 분산되어 있고 새 이해관계자가 커뮤니케이션 요구를 가지고 있다. PM은 무엇을 먼저 해야 하는가? | 이해관계자 관리 계획을 검토하고 이해관계자 등록부를 업데이트한다 | 이해관계자와 회의를 예약하고 요구를 프로젝트 관리 계획에 포함한다 | 커뮤니케이션 관리 계획을 검토하고 이해관계자의 요구가 반영되었는지 확인한다 | 프로젝트 팀에 이해관계자 세부사항을 포함하고 상태 보고서에 반영하도록 요청한다 |  | C | 새 이해관계자의 커뮤니케이션 요구를 다룰 때, PM은 먼저 커뮤니케이션 관리 계획을 검토하고 이해관계자의 요구가 적절히 반영되었는지 확인해야 한다. 기존 계획 검토가 격차를 식별하고 효율적으로 대응한다. 이해관계자 등록부(A)는 부분적이다. 회의 예약(B)은 계획 검토 후에 한다. 팀에 요청(D)은 체계적이지 않다.
1788 | A project manager was recently assigned to a banking IT project. The project team has been developing products using a predictive approach for more than 10 years, but management wants the team to change to an agile approach. The project manager met with the team to introduce the agile approach. Most of the team members complained about changing approaches because the performance of this team has always been above average among the IT teams in the bank. Which two actions should the project manager take? (Choose two) | Ask the team to identify the product backlog and create a kanban board for the team to manage and follow the approach. | Interview the most resistant team members to persuade them to try to accept an agile approach. | Conduct training sessions with the team so that the team can understand what the agile approach and mindset are. | Meet with management to explain the team ' s resistance to the agile approach and request that they formally ask the team to implement agile. | Brainstorm with the team to understand the specifics of the team ' s project and to identity possible alternative approaches for the team. | C, E | When transitioning a long-established predictive team to an agile approach, two actions are essential: conducting training sessions so team members understand the agile mindset and methodology (C), and brainstorming with the team to explore how agile can be adapted to their specific project context (E). Training addresses knowledge gaps and misconceptions, while collaborative brainstorming fosters ownership and eases resistance by involving the team in shaping the transition. Asking the team to immediately create a product backlog and kanban board (A) is premature without first ensuring understanding. Interviewing resistant members to persuade them individually (B) may feel coercive and does not build collective buy-in. Requesting management to formally mandate agile (D) creates a top-down directive that is likely to deepen resistance rather than resolve it. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Hybrid/Tailoring | PM이 은행 IT 프로젝트에 배정되었다. 팀이 오래 예측형 접근법을 사용해왔고 애자일로 전환해야 한다. 팀이 저항한다. PM은 무엇을 해야 하는가? | 팀에게 제품 백로그를 식별하고 칸반 보드를 만들도록 요청한다 | 가장 저항하는 팀원을 인터뷰하여 애자일을 수용하도록 설득한다 | 팀이 애자일 접근법과 사고방식을 이해할 수 있도록 교육 세션을 실시한다 | 경영진에게 팀의 저항을 설명하고 지시를 요청한다 | 팀과 브레인스토밍하여 프로젝트의 구체적 사항을 이해하고 가능한 장애물을 식별한다 | C, E | 예측형 팀을 애자일로 전환할 때, 두 가지 핵심 조치는: 팀이 애자일 사고방식과 방법론을 이해하도록 교육 세션을 실시하고(C), 팀과 브레인스토밍하여 프로젝트의 구체적 사항을 이해하고 장애물을 식별한다(E). 교육이 이해를 구축하고 브레인스토밍이 맞춤 전환을 가능하게 한다. 백로그/칸반(A)은 이해 전에 도구를 강요한다. 설득(B)은 교육이 아닌 압박이다. 경영진 지시(D)는 팀 수용을 해치다.
1789 | A project being constructed in a remote rural area is nearing the end of construction. The project manager would like to share the good news with stakeholders. How should the project manager communicate with the local community? | Newspapers | Social media | Email | Meetings |  | A | When sharing good news about a project in a remote rural area with the local community, the project manager should use newspapers. In rural areas, newspapers are a reliable, widely accessible communication method. Social media (B) and email (C) may not reach all community members. Meetings (D) limit reach to attendees only. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Hybrid/Tailoring | 원격 농촌 지역의 건설 프로젝트가 완공에 가까워졌다. PM이 지역 사회와 좋은 소식을 공유하고 싶다. 어떤 방법을 사용해야 하는가? | 신문 | 소셜 미디어 | 이메일 | 회의 |  | A | 원격 농촌 지역의 지역 사회와 좋은 소식을 공유할 때, PM은 신문을 사용해야 한다. 농촌 지역에서 신문은 신뢰할 수 있고 널리 접근 가능한 커뮤니케이션 매체이다. 소셜 미디어(B)는 농촌 접근성이 제한적이다. 이메일(C)은 지역 사회 전체에 도달하지 못한다. 회의(D)는 지역 사회 규모에 비해 비현실적이다.
1790 | A CEO has requested that the project manager provide a budget estimate for a long-term project that will be executed over the span of 4 years. What should the project manager do? | Conduct a bottom-up estimate | Conduct an analogous estimate | Include enterprise environmental factors (EEFs) | Include projected inflation rates |  | D | When the CEO requests a budget estimate for a 4-year long-term project, the project manager should include projected inflation rates. Long-term budgets must account for economic factors. Bottom-up estimates (A) are detailed but not specifically addressing long-term factors. Analogous estimates (B) use historical data but may miss inflation. Including EEFs (C) is broad — inflation rates are the specific critical factor for a 4-year horizon. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Traditional Plan-Driven | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | CEO가 4년간의 장기 프로젝트 예산 추정을 요청했다. PM은 무엇을 포함해야 하는가? | 상향식 추정을 수행한다 | 유사 추정을 수행한다 | 기업 환경 요인(EEF)을 포함한다 | 예상 인플레이션율을 포함한다 |  | D | 4년 장기 프로젝트의 예산 추정 시, PM은 예상 인플레이션율을 포함해야 한다. 장기 예산은 경제적 요인을 반영해야 한다. 상향식 추정(A)은 상세 정보가 부족할 수 있다. 유사 추정(B)은 장기에는 정확도가 떨어진다. EEF(C)는 일반적이고 인플레이션보다 덜 구체적이다.
1791 | A project team member is having difficulty delivering assigned tasks for a project that is at risk of being delayed. The main issue is that the team member does not understand a new system that was recently implemented. What should the project manager do? | Ask the team member to learn the new system as on-the-job training | Escalate the team member ' s performance to the project sponsor | Assign an experienced resource to support the team member | Issue a change request to extend the project schedule |  | C | When a team member cannot deliver tasks because they do not understand a newly implemented system, the project manager should assign an experienced resource to support them. Peer support enables knowledge transfer and task completion. Asking for on-the-job training alone (A) lacks structured support. Escalating performance to the sponsor (B) is punitive. Issuing a change request to extend the schedule (D) accepts delay without addressing the root cause. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 팀원이 새로 도입된 시스템을 이해하지 못해 작업 납품에 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 팀원에게 새 시스템을 현장 실습으로 배우도록 요청한다 | 팀원의 성과를 프로젝트 스폰서에게 에스컬레이션한다 | 경험 있는 자원을 배정하여 팀원을 지원한다 | 프로젝트 일정 연장을 위한 변경 요청을 발행한다 |  | C | 팀원이 새 시스템을 이해하지 못해 작업을 납품하지 못할 때, PM은 경험 있는 자원을 배정하여 지원해야 한다. 동료 지원이 지식 전달과 빠른 학습을 가능하게 한다. 현장 실습(A)은 비효율적이고 품질 위험이 있다. 에스컬레이션(B)은 지원 전에 과도하다. 일정 연장(D)은 근본 해결이 아니다.
1792 | A project manager notices that one of the marketing executives in the firm always appears stressed. The project manager observes that the executive's performance is gradually declining and is affecting the project deliverables. What should the project manager do? | Make the marketing executive accountable for their work and output | Review the executive ' s declining performance with human resources (HR) | Assign the marketing executive ' s tasks to another project team member | Show empathy and praise the marketing executive ' s strengths |  | D | When observing a marketing executive under stress with declining performance affecting deliverables, the project manager should show empathy and praise the executive's strengths. Empathetic support can improve morale and performance. Making them accountable (A) adds pressure. Reviewing with HR (B) escalates prematurely. Reassigning tasks (C) does not address the person's needs. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Scope & Requirements Mgmt | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 마케팅 임원이 항상 스트레스를 받는 것을 발견했다. 성과가 하락하여 인도물에 영향을 미치고 있다. PM은 무엇을 해야 하는가? | 마케팅 임원에게 업무와 산출물에 대한 책임을 묻는다 | 인사부(HR)와 임원의 하락하는 성과를 검토한다 | 마케팅 임원의 작업을 다른 팀원에게 할당한다 | 공감을 보이고 마케팅 임원의 강점을 칭찬한다 |  | D | 스트레스를 받고 성과가 하락하는 마케팅 임원에게, PM은 공감을 보이고 강점을 칭찬해야 한다. 공감적 지원이 자신감과 동기를 회복시킨다. 책임 추궁(A)은 상황을 악화시킨다. HR 검토(B)는 개인 지원 전에 성급하다. 작업 재할당(C)은 임원을 소외시킨다.
1793 | The customer's project manager changes during the final stage of a project. How can the project manager avoid a project closure delay? | Escalate the case to the customer ' s management team | Update the stakeholder engagement plan | Review the latest project status report and update the stakeholders | Issue the project payment invoice to the customer in advance |  | C | When the customer's project manager changes during the final project stage, the project manager should review the latest project status report and update the stakeholders. This ensures the new customer PM is brought up to speed on progress, deliverables, issues, and closure activities, enabling a smooth transition. Escalating to the customer's management (A) is not directly productive. Updating the stakeholder engagement plan (B) is procedural but does not actively inform the new PM. Issuing a payment invoice in advance (D) is premature and inappropriate. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Closing | Focus on Value | Close Project or Phase | Traditional PM | 프로젝트 최종 단계에서 고객의 PM이 변경되었다. PM은 프로젝트 지연을 어떻게 피할 수 있는가? | 고객 경영팀에 사례를 에스컬레이션한다 | 이해관계자 참여 계획을 업데이트한다 | 최신 프로젝트 상태 보고서를 검토하고 이해관계자를 업데이트한다 | 사전에 프로젝트 결제 송장을 고객에게 발행한다 |  | C | 고객의 PM이 최종 단계에서 변경될 때, PM은 최신 프로젝트 상태 보고서를 검토하고 이해관계자를 업데이트해야 한다. 이를 통해 새 고객 PM이 신속히 현황을 파악하고 프로젝트가 중단 없이 진행된다. 에스컬레이션(A)은 불필요하다. 참여 계획 업데이트(B)는 유용하지만 즉각적 정보 공유가 우선이다. 사전 송장(D)은 비윤리적이다.
1794 | A new project has been kicked off following a planning session. The project is under direct oversight of an executive in the organization. After a review meeting, the project manager overhears an executive request a dashboard from one of the team members to show the overall project status. What should the project manager do? | Update the communications management plan to include informal requests | Tell the team member to route the request through the project manager | Update the stakeholder engagement assessment matrix | Ask the team member to develop a dashboard to fulfill the request. |  | A | The PM should update the communications management plan to include informal requests from executives, such as dashboard requirements, and specify how they will be handled. This ensures communication expectations are clear and the project team understands their responsibilities. Updating the stakeholder matrix (A), having a team member create a dashboard unilaterally (B), or routing all requests through the PM (D) don't address the underlying need for a comprehensive communications plan. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 새 프로젝트가 계획 세션 후 시작되었다. 경영진이 비공식적으로 팀원에게 대시보드를 요청했다. PM은 무엇을 해야 하는가? | 비공식적 요청을 포함하도록 커뮤니케이션 관리 계획을 업데이트한다 | 팀원에게 요청을 PM을 통해 라우팅하도록 말한다 | 이해관계자 참여 평가 매트릭스를 업데이트한다 | 팀원에게 요청을 충족하는 대시보드를 개발하도록 요청한다 |  | A | 경영진이 비공식적으로 대시보드를 요청할 때, PM은 비공식적 요청을 포함하도록 커뮤니케이션 관리 계획을 업데이트해야 한다. 계획에 비공식 경로를 포함하면 커뮤니케이션 기대가 명확해진다. 라우팅 요청(B)은 관료적이다. 매트릭스 업데이트(C)는 참여 전략이지 커뮤니케이션 계획이 아니다. 대시보드 즉시 개발(D)은 계획 없이 대응적이다.
1795 | A new project manager learns the work assigned to the team has already been decomposed to its lowest level. The project manager reviews the work and feels some additional useful information is missing. What should the project manager review? | The business requirement documents (BRD) | The requirements traceability matrix | The project charter and scope statement | The WBS dictionary |  | D | When work has been decomposed to its lowest level but additional useful information seems missing, the project manager should review the WBS dictionary. The WBS dictionary provides detailed descriptions of work packages including scope, activities, resources, costs, and quality requirements. Business requirement documents (A) describe the business problem, not work details. The requirements traceability matrix (B) links requirements to deliverables. The project charter and scope statement (C) are high-level documents. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 새 PM이 작업이 이미 최하위 수준으로 분해된 것을 확인했다. 추가 유용한 정보가 누락된 것 같다. 무엇을 검토해야 하는가? | 비즈니스 요구사항 문서(BRD) | 요구사항 추적 매트릭스 | 프로젝트 헌장과 범위 기술서 | WBS 사전 |  | D | 작업이 최하위 수준으로 분해되었지만 추가 정보가 누락된 것 같을 때, PM은 WBS 사전을 검토해야 한다. WBS 사전은 각 작업 패키지에 대한 상세 설명, 산출물, 일정, 비용, 자원을 제공한다. BRD(A)는 비즈니스 요구사항이지 작업 세부사항이 아니다. 추적 매트릭스(B)는 요구사항 추적이다. 헌장/범위(C)는 상위 수준이다.
1796 | A project manager is assigned to a long-term project. The project manager came across a government debate over a new law that may affect the project. Which first two actions should the project manager perform? (Choose 2) | Perform a risk identification process with the project team. | Consult with the project stakeholders and evaluate the impact. | Ask the project sponsor for additional budget for contingency. | Create a change request to discuss with the change control board (CCB). | Discuss the possible impacts with subject matter experts (SMEs). | A, B | When a government debate over a new law may affect the project, the project manager should take two initial actions: perform a risk identification process with the project team (A) to formally identify and document the potential regulatory risk, and consult with the project stakeholders and evaluate the impact (B) to understand how the new law could affect different aspects of the project. Risk identification captures the threat formally, while stakeholder consultation provides diverse perspectives on potential impacts. Asking the sponsor for additional contingency budget (C) is premature before understanding the risk. Creating a change request (D) is premature without first identifying and assessing the risk. Discussing with SMEs (E) is useful but secondary to the formal risk identification process and stakeholder evaluation. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | PM이 장기 프로젝트에 배정되었다. 정부의 새 법률에 대한 논의가 프로젝트에 영향을 줄 수 있다. PM은 무엇을 해야 하는가? | 프로젝트 팀과 리스크 식별 프로세스를 수행한다 | 프로젝트 이해관계자와 상의하고 영향을 평가한다 | 프로젝트 스폰서에게 비상 예산을 요청한다 | 변경통제위원회(CCB)와 논의할 변경 요청을 생성한다 | 주제 전문가(SME)와 가능한 영향을 논의한다 | A, B | 정부의 새 법률이 프로젝트에 영향을 줄 수 있을 때, PM은 두 가지 초기 조치를 취해야 한다: 프로젝트 팀과 리스크 식별 프로세스를 수행하여(A) 잠재적 규제 리스크를 공식적으로 식별하고, 프로젝트 이해관계자와 상의하고 영향을 평가한다(B). 리스크 식별이 위협을 포착하고 이해관계자 상담이 다양한 관점을 제공한다. 비상 예산(C)은 리스크 평가 전에 성급하다. 변경 요청(D)은 리스크 식별 후에 한다. SME 논의(E)는 유용하지만 부차적이다.
1797 | A project manager is assigned to a major construction project. The project is critical to the city's population, and especially to the local government official who committed to delivering the project on time as an election promise. A new project sponsor has been assigned and wants to include aspects that the previous project sponsor did not support. What should the project manager do next? | Meet with the new project sponsor to review the current project scope and the requested changes. | Inform the new project sponsor that the new aspects will not be included in this project. | Rebaseline the project as there is now a new project sponsor, which is presenting an opportunity to review and recalibrate the project objectives. | Invite the project sponsor to a briefing with the project team to demonstrate progress and seek further support to meet project-committed deliverables. |  | A | When a new project sponsor wants to include aspects the previous sponsor did not support on a critical construction project, the project manager should meet with the new sponsor to review the current project scope and requested changes. Direct engagement ensures alignment and proper change evaluation. Informing the sponsor that changes will not be included (B) is dismissive. Rebaselining the project (C) acts before understanding the changes. Inviting the sponsor to a briefing (D) demonstrates progress but does not address the change request. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Scope & Requirements Mgmt | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 새 스폰서가 이전 스폰서가 지원하지 않은 측면을 포함하려 한다. 중요한 건설 프로젝트이다. PM은 무엇을 해야 하는가? | 새 프로젝트 스폰서와 만나 현재 프로젝트 범위와 요청된 변경을 검토한다 | 새 프로젝트 스폰서에게 새 측면이 이 프로젝트에 포함되지 않을 것임을 알린다 | 새 스폰서가 있으므로 프로젝트를 재기준선화하여 요구사항을 검토할 기회로 삼는다 | 프로젝트 스폰서를 팀 브리핑에 초대하여 진행 상황을 시연하고 추가 지시를 구한다 |  | A | 새 스폰서가 이전에 미지원된 측면을 포함하려 할 때, PM은 새 스폰서와 만나 현재 범위와 요청된 변경을 검토해야 한다. 범위 검토가 정보에 기반한 결정을 가능하게 한다. 거부(B)는 새 스폰서 관계를 해친다. 재기준선(C)은 과도하다. 브리핑 초대(D)는 유용하지만 범위 검토가 우선이다.
1798 | A project manager receives a request for proposal (RFP) from a client. The client is very clear about the requirements. A requirements analysis must be done in the first month of the project, and the client wants to see a demo of the work completed every two weeks. What project approach should the project manager use? | Predictive for the requirements analysis and delivery phases of the project | Predictive for the requirements analysis and agile for delivery of the project | Agile for all of the phases of the project, including the requirements analysis and delivery | Iterative for the requirements analysis and delivery phases of the project |  | D | Given that the client has clear requirements, wants a month of requirements analysis, and expects a demo every two weeks, the project manager should use an iterative approach for both requirements analysis and delivery. An iterative approach breaks the scope into increments delivered in cycles with client feedback at each cycle—matching the client's desire for frequent demonstrations. A fully predictive approach (A) does not support frequent demos. Agile for all phases (C) is better suited for projects with high uncertainty and unclear requirements. Predictive for analysis with agile for delivery (B) creates a hybrid that may not align with the client's consistent demo expectations throughout. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Focus on Value | Plan Finance Management | Traditional PM | 고객이 명확한 요구사항과 1개월 요구분석, 2주마다 데모를 원한다. 어떤 접근법을 사용해야 하는가? | 요구사항 분석과 납품 단계 모두에 예측형을 사용한다 | 요구사항 분석에 예측형, 납품에 애자일을 사용한다 | 요구사항 분석과 납품 포함 모든 단계에 애자일을 사용한다 | 요구사항 분석과 납품 단계 모두에 반복형을 사용한다 |  | D | 명확한 요구사항, 1개월 요구분석, 2주마다 데모가 있을 때, 반복형(iterative) 접근법을 사용해야 한다. 반복형이 요구사항 분석의 체계성과 정기 데모를 모두 지원한다. 순수 예측형(A)은 정기 데모를 지원하지 않는다. 예측형+애자일(B)은 혼합이 과도하다. 순수 애자일(C)은 명확한 요구사항에 불필요하다.
1799 | A project manager is managing a technical project that requires intensive documentation as part of the key deliverables. In a project review meeting, a key stakeholder reports that the latest documentation provided by the project manager includes a reference to unrelated products. What should the project manager do? | Log the issue in the risk register and the issue log. | Ask the project management office (PMO) to support and review all deliverables. | Assign a technical writer to the project. | Develop a standard for document quality control. |  | D | When documentation references unrelated products, it indicates a quality control gap. The project manager should develop a standard for document quality control to prevent similar issues in the future. This proactive approach establishes clear guidelines and review processes for all project documentation. Logging the issue in the risk register and issue log (A) documents the problem but does not create a systemic fix. Asking the PMO to review all deliverables (B) creates dependency on external support. Assigning a technical writer (C) addresses the immediate need but does not establish a sustainable quality control process. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 기술 프로젝트에서 문서가 핵심 인도물이다. 일부 문서가 관련 없는 제품을 참조하고 있다. PM은 무엇을 해야 하는가? | 리스크 등록부와 이슈 로그에 문제를 기록한다 | PMO에 모든 인도물 지원 및 검토를 요청한다 | 프로젝트에 기술 작가를 배정한다 | 문서 품질 관리를 위한 표준을 개발한다 |  | D | 문서가 관련 없는 제품을 참조할 때, PM은 문서 품질 관리를 위한 표준을 개발해야 한다. 품질 관리 표준이 유사 문제의 재발을 방지한다. 기록(A)은 문제를 해결하지 않는다. PMO 지원(B)은 과도하다. 기술 작가(C)는 개인이지 프로세스 해결이 아니다.
1800 | A project manager has been managing a highly complex project. The project manager has ensured that all of the required tasks have been completed. During a recent external audit, the project manager was informed of a heavy penalty being levied on the project for the latest module that was implemented. What should the project manager have done to ensure that there were no liabilities arising from the recent implementation? | Ensured that all the required approvals were received per the organizational procedures | Ensured that all documentation was completed post implementation before closing the project | Ensured that all of the required tasks identified in the scope were completed successfully | Ensured that all defects identified during testing were resolved before implementation |  | A | When an external audit levied a heavy penalty for a recently implemented module, the project manager should have ensured all required approvals were received per organizational procedures. Proper approvals prevent compliance liabilities. Completing documentation post-implementation (B) is too late. Completing tasks identified in scope (C) does not ensure compliance. Resolving defects before implementation (D) addresses quality, not procedural compliance. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | Quality Management | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | PM이 복잡한 프로젝트를 관리하여 완료했다. 외부 감사에서 최근 구현 모듈에 대해 큰 벌금이 부과되었다. PM이 무엇을 했어야 하는가? | 조직 절차에 따라 필요한 모든 승인을 받았는지 확인했다 | 프로젝트 종료 전 구현 후 모든 문서가 완료되었는지 확인했다 | 범위에 식별된 모든 필수 작업이 성공적으로 완료되었는지 확인했다 | 테스트 중 식별된 모든 결함이 구현 전에 해결되었는지 확인했다 |  | A | 외부 감사에서 벌금이 부과되었을 때, PM이 조직 절차에 따라 필요한 모든 승인을 받았는지 확인했어야 한다. 적절한 승인 절차가 규정 준수와 감사 통과를 보장한다. 문서 완료(B)는 승인과 다르다. 작업 완료(C)는 승인 절차를 다루지 않는다. 결함 해결(D)은 품질이지 규정 준수가 아니다.
1801 | A company changed the product owner on an existing project. The new product owner has less knowledge of the product than everybody else on the team. Due to the product owner's lack of knowledge, the team does not consider the opinions of the product owner seriously and mostly relies on the project manager's opinion. What should the project manager do? | Assume the role of the product owner while the product owner gets familiar with the product. | Work with the project management office (PMO) manager to generate an onboarding plan for the new product owner. | Organize a team-building activity and ask the team to respect the opinions of the new product owner. | Schedule time to share insights with the new product owner about the product and project information. |  | B | When a new product owner lacks product knowledge and the team does not take their opinions seriously, the project manager should work with the PMO manager to generate an onboarding plan for the new product owner. A structured onboarding plan builds the product owner's knowledge and credibility systematically. Assuming the product owner role (A) confuses role boundaries. Sharing insights informally (D) is helpful but should be part of a structured plan. Organizing a team-building activity (C) builds relationships but does not address the knowledge gap. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Scope | Planning | Build an Empowered Culture | Collect Requirements | Traditional PM | 회사가 기존 프로젝트의 제품 책임자를 변경했다. 새 제품 책임자가 제품 지식이 부족하고 팀이 의견을 진지하게 받아들이지 않는다. PM은 무엇을 해야 하는가? | 제품 책임자가 제품에 익숙해질 때까지 제품 책임자 역할을 대행한다 | PMO 관리자와 협력하여 새 제품 책임자를 위한 온보딩 계획을 생성한다 | 팀 빌딩 활동을 조직하고 팀에게 새 제품 책임자의 의견을 존중하도록 요청한다 | 새 제품 책임자에게 제품과 프로젝트 정보에 대한 통찰을 공유할 시간을 예약한다 |  | B | 새 제품 책임자가 지식이 부족하고 팀이 의견을 존중하지 않을 때, PM은 PMO 관리자와 협력하여 온보딩 계획을 생성해야 한다. 체계적 온보딩이 지식 구축과 신뢰성 확립을 보장한다. 역할 대행(A)은 역할 경계를 침해한다. 팀 빌딩(C)은 지식 격차를 해결하지 않는다. 통찰 공유(D)는 유용하지만 체계적 계획이 우선이다.
1802 | In the past, the project manager and the project team performed well using predictive methodology. However, the organization recently decided to adopt agile approaches, and the project sponsor wants to use an agile approach in an upcoming project. Before initiating the project, what should the project manager do? | Share the organization ' s decision with the team and make plans to adopt an 955 agileapproach in the upcoming project. | Make a request to human resources for new team members who have agileexperience. | Prepare a risk report that captures the probability and impact of risks, and then shareit with the project sponsor. | Ask the project sponsor to change the approach back to predictive as that is theteam's strength. |  | A | When the organization decides to adopt agile and the sponsor wants it for an upcoming project, the project manager should share the decision with the team and make plans to adopt agile. Transparent communication and proactive planning support transition. Preparing a risk report (C) implies resistance. Requesting new team members with agile experience (B) undermines the existing team. Asking to revert to predictive (D) contradicts organizational strategy. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 과거에 PM과 팀이 예측형 방법론으로 잘 수행했다. 그러나 조직이 애자일을 도입하기로 했다. PM은 무엇을 해야 하는가? | 팀에 조직의 결정을 공유하고 다음 프로젝트에서 애자일 접근법을 채택할 계획을 수립한다 | 애자일 경험이 있는 새 팀원을 인사부에 요청한다 | 리스크의 확률과 영향을 포착하는 리스크 보고서를 준비하고 프로젝트 스폰서와 공유한다 | 프로젝트 스폰서에게 팀의 강점인 예측형으로 접근법을 변경하도록 요청한다 |  | A | 조직이 애자일을 도입하기로 할 때, PM은 팀에 결정을 공유하고 애자일 채택 계획을 수립해야 한다. 투명한 소통과 계획적 전환이 팀의 수용을 촉진한다. 새 팀원 요청(B)은 기존 팀 역량을 무시한다. 리스크 보고서(C)는 전환 자체를 다루지 않는다. 접근법 변경 요청(D)은 조직 결정에 반한다.
1803 | A project team working on a big data project has concluded the make-or-buy decision on a particular feature, which will drive an increase in product adoption. The team decided to buy commercial software. What should the project manager do next? | Request a purchase order. | Finalize change control. | Update the risk register. | Inform the project sponsor. |  | C | The correct answer is C. Update the risk register. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Digital Transformation | 빅데이터 프로젝트 팀이 특정 기능에 대한 제작/구매 결정을 마쳤다. PM은 다음에 무엇을 해야 하는가? | 구매 주문을 요청한다 | 변경 통제를 마무리한다 | 리스크 등록부를 업데이트한다 | 프로젝트 스폰서에게 알린다 |  | C | 정답은 C이다. 리스크 등록부를 업데이트한다. 제작/구매 결정 후 새로운 리스크(벤더 의존성, 통합 리스크 등)를 식별하고 문서화해야 한다. 구매 주문(A)은 조달 절차 완료 후이다. 변경 통제(B)는 범위 변경이 필요한 경우이다. 스폰서 알림(D)은 리스크 평가 후에 한다.
1804 | A project manager for a large project's agile team is developing new workflows to meet changing business needs. As the second sprint is running, the product owner and agile team begin to receive more details that impact the scope change of running items. The agile team requests a change in the sprint goals and sprint backlog items. What should the project manager do? | Guide the agile team to add the new scope to the product backlog. | Pause the sprint to allow time to include the new items. | Moderate the expectations for sprint quality. | Create a parallel sprint to deliver the additional items. |  | A | When scope changes emerge during a sprint and the agile team requests changes to sprint goals, the project manager should guide the team to add the new scope to the product backlog. Backlog management enables proper prioritization by the product owner without disrupting the current sprint. Pausing the sprint (B) interrupts delivery. Moderating quality expectations (C) compromises standards. Creating a parallel sprint (D) is not an agile practice. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 대규모 프로젝트의 애자일 팀이 변화하는 비즈니스 요구를 충족하기 위한 새 워크플로를 개발 중이다. 스프린트 중 범위 변경이 발생했다. PM은 무엇을 해야 하는가? | 애자일 팀을 안내하여 새 범위를 제품 백로그에 추가한다 | 새 항목을 포함할 시간을 주기 위해 스프린트를 중지한다 | 스프린트 품질에 대한 기대를 조절한다 | 추가 항목을 전달하기 위해 병렬 스프린트를 만든다 |  | A | 스프린트 중 범위 변경이 발생할 때, PM은 팀을 안내하여 새 범위를 제품 백로그에 추가해야 한다. 백로그 관리를 통한 범위 변경이 애자일 원칙에 부합한다. 스프린트 중지(B)는 진행을 방해한다. 품질 기대 조절(C)은 품질을 타협한다. 병렬 스프린트(D)는 복잡성을 증가시킨다.
1805 | In a construction project for a new building, the project manager decides to apply agile principles for the building foundation phase. While evaluating the project schedule with the team, the project manager believes that the estimates are inaccurate. How should the project manager address this issue? | Reduce the story size by splitting stories | Assess the previous project velocity | Create a product backlog | Perform sprint reviews with the team |  | A | Agile principles favor frequent delivery of working increments in short time-boxes. To achieve this, the PM should reduce story size by splitting overly large or complex stories into smaller, more manageable pieces. This improves estimation accuracy, deliverable quality, and customer feedback cycles. Creating a product backlog addresses feature listing but not estimation issues. Sprint reviews provide feedback but don't prevent estimation problems. Assessing previous velocity helps planning but doesn't resolve the root cause of oversized stories. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 건설 프로젝트에서 PM이 건물 기초에 애자일 원칙을 적용하기로 했다. 팀이 타임박스 내에 인도하기 어렵다. PM은 무엇을 먼저 해야 하는가? | 스토리를 분할하여 스토리 크기를 줄인다 | 이전 프로젝트 속도를 평가한다 | 제품 백로그를 생성한다 | 팀과 스프린트 리뷰를 수행한다 |  | A | 애자일 원칙에서 짧은 타임박스 내 작업 인도가 어려울 때, PM은 스토리를 분할하여 크기를 줄여야 한다. 작은 스토리가 빈번한 납품과 피드백을 가능하게 한다. 이전 속도 평가(B)는 현재 문제를 해결하지 않는다. 백로그 생성(C)은 이미 있어야 한다. 스프린트 리뷰(D)는 인도 후 활동이다.
1806 | A project manager notices that the project team is encountering product issues while coding client-specific developments. The project manager foresees delays to the project's timeline because of these product issues. Which methods should the project manager use to communicate project delays and other difficult messages to stakeholders? | Written feedback, project meetings, and reporting | Oral feedback, project meetings, and reporting | Project meetings and oral feedback | Project meetings and reporting |  | A | The correct answer is A. Written feedback, project meetings, and reporting. Effective stakeholder management requires proactive engagement, transparent communication, and alignment with project objectives. Understanding stakeholder needs and addressing their concerns is essential for project success. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 코딩 중 제품 문제를 겪고 있다. 이해관계자에게 알리기 위해 어떤 커뮤니케이션 조합을 사용해야 하는가? | 서면 피드백, 프로젝트 회의, 보고 | 구두 피드백, 프로젝트 회의, 보고 | 프로젝트 회의와 구두 피드백 | 프로젝트 회의와 보고 |  | A | 정답은 A이다. 서면 피드백, 프로젝트 회의, 보고. 효과적인 이해관계자 관리는 사전적 참여, 투명한 커뮤니케이션, 프로젝트 목표와의 정렬이 필요하다. 서면 피드백이 기록을 제공하고, 회의가 실시간 논의를 가능하게 하며, 보고가 공식 추적을 보장한다.
1807 | A project manager for an agile project wants to have a highly engaged team. How should the project manager achieve this objective? | Be clear with directions and assignments so people stay focused and engaged with their work. | Encourage continuous rotation of roles among team members to keep people motivated throughout project delivery. | Design a reward system to get people motivated by recognizing significant individual contributions from the last sprint | Promote an environment where everybody knows what their contribution means to the project as a whole. |  | D | When seeking a highly engaged agile team, the project manager should promote an environment where everybody knows what their contribution means to the project as a whole. Understanding purpose and impact drives intrinsic motivation and ownership. Being clear with directions (A) implies directive management. Designing individual reward systems (C) may create competition over collaboration. Encouraging continuous role rotation (B) may disrupt efficiency. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 애자일 프로젝트의 PM이 높은 참여도의 팀을 원한다. 어떻게 달성해야 하는가? | 명확한 지시와 과제를 제공하여 사람들이 집중하고 업무에 참여하도록 한다 | 프로젝트 전반에 걸쳐 동기를 유지하기 위해 팀원 간 역할을 지속적으로 순환한다 | 프로젝트 기간 중 중요한 개인 기여를 인정하는 보상 시스템을 설계한다 | 모든 사람이 자신의 기여가 프로젝트 전체에 어떤 의미인지 아는 환경을 촉진한다 |  | D | 높은 참여도의 애자일 팀을 위해, PM은 모든 사람이 자신의 기여가 프로젝트 전체에 어떤 의미인지 아는 환경을 촉진해야 한다. 목적과 영향 이해가 내재적 동기를 만든다. 명확한 지시(A)는 명령적이다. 역할 순환(B)은 혼란을 야기할 수 있다. 개인 보상(C)은 팀 협력을 약화시킬 수 있다.
1808 | A project manager is working on a project using a hybrid approach. The project is scheduled to be completed in three more sprints. One of the team members notifies the project manager that they are leaving the company, which was approved by their functional manager. What should the project manager do first in this situation? | Ask the functional manager for an immediate replacement for the team member. | Use soft skills to influence the team member to slay until the project is completed | Ask the functional manager why a decision was made without consulting them | Review the risk management plan and mitigation plan to understand the impact of this issue |  | D | When a team member announces they are leaving during a project with three sprints remaining, the project manager should first review the risk management plan and mitigation plan to understand the impact. Assessing risk exposure guides the appropriate response strategy. Asking for an immediate replacement (A) is reactive without impact analysis. Using soft skills to persuade the member to stay (B) may not be effective. Questioning the functional manager's decision (C) is confrontational. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Hybrid/Tailoring | 하이브리드 프로젝트가 3개월 후 완료 예정이다. 팀원이 떠나겠다고 발표했다. PM은 무엇을 먼저 해야 하는가? | 기능 관리자에게 팀원의 즉각적 교체를 요청한다 | 소프트 스킬을 사용하여 팀원이 프로젝트 완료까지 남도록 영향을 미친다 | 기능 관리자에게 왜 상의 없이 결정했는지 문의한다 | 리스크 관리 계획과 완화 계획을 검토하여 이 이슈의 영향을 이해한다 |  | D | 팀원이 3개 스프린트가 남은 시점에 떠나겠다고 할 때, PM은 먼저 리스크 관리 계획과 완화 계획을 검토하여 영향을 이해해야 한다. 계획적 대응이 정보에 기반한 결정을 가능하게 한다. 즉시 교체(A)는 영향 분석 전이다. 영향력 행사(B)는 개인 결정을 무시한다. 기능 관리자 문의(C)는 비생산적이다.
1809 | A self-organizing team brings an internal problem to the project manager. What should the project manager do as a servant leader? | Discuss the issue with the management team and provide a solution, | Provide the team with a solution that solves the problem. | Coach the team to solve the problem independently, | Speak with the team lead about the issue and provide a solution, |  | C | When a self-organizing team brings an internal problem to the project manager, the servant leader should coach the team to solve the problem independently. This empowers the team, fosters ownership, and develops their problem-solving skills—core principles of servant leadership. Discussing with management and providing a solution (A) overrides team autonomy. Providing a solution directly (B) prevents the team from learning. Speaking with the team lead and providing a solution (D) similarly bypasses team self-organization. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 자체 조직화 팀이 내부 문제를 PM에게 가져왔다. 서번트 리더로서 PM은 무엇을 해야 하는가? | 경영팀과 문제를 논의하고 해결책을 제공한다 | 팀에게 문제를 해결하는 해결책을 제공한다 | 팀이 독립적으로 문제를 해결하도록 코칭한다 | 팀 리더와 문제를 논의하고 해결책을 제공한다 |  | C | 자체 조직화 팀이 내부 문제를 가져올 때, 서번트 리더는 팀이 독립적으로 문제를 해결하도록 코칭해야 한다. 이는 팀에 권한을 부여하고 소유권과 자기 해결 능력을 키운다. 경영팀 논의(A)는 에스컬레이션이다. 해결책 제공(B)은 의존성을 만든다. 팀 리더에게(D)는 자체 조직화를 약화시킨다.
1810 | A project team has been formed and the tasks have been assigned to each team member. All team members have agreed to follow a hybrid project approach. What should the project manager do to ensure the team performs as an organized unit? | Call a team meeting to discuss team members ' strengths and weaknesses | Advise the team to adjust their work habits and behaviors to allow for better conflict resolution | Establish rules and regulations for team members with consequences if the goals are not reached | Establish team behavior and develop an understating of how to work together |  | D | When a hybrid project team has been formed with agreed tasks, the project manager should establish team behavior and develop an understanding of how to work together. Shared behavioral norms and collaborative understanding are foundational for organized teamwork. Discussing strengths and weaknesses (A) may create tension. Advising behavior adjustment for conflict resolution (B) is prescriptive. Establishing rules with consequences (C) creates a punitive environment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 하이브리드 프로젝트 팀이 구성되고 각 팀원에게 작업이 할당되었다. PM이 다음으로 해야 할 일은? | 팀 회의를 소집하여 팀원의 강점과 약점을 논의한다 | 팀에게 갈등 해결을 위해 업무 습관과 행동을 조정하도록 조언한다 | 목표 미달 시 결과가 따르는 팀원 규칙과 규정을 수립한다 | 팀 행동을 수립하고 함께 일하는 방법에 대한 이해를 개발한다 |  | D | 팀이 구성되고 작업이 할당된 후, PM은 팀 행동을 수립하고 함께 일하는 방법에 대한 이해를 개발해야 한다. 공유된 행동 규범이 협력적 팀워크를 촉진한다. 강약점 논의(A)는 불편할 수 있다. 습관 조정(B)은 구체적이지 않다. 규칙/결과(C)는 처벌적이다.
1811 | A project manager is leading a project in an organization that has a functional structure. The project manager has been informed by the team that the tasks related to the purchase of services are taking too long, as the purchasing department has other priorities. What should the project manager do? | Ask the project team to keep developing other tasks that do not depend on the purchase of services. | Request that the purchasing tasks be outsourced through an existing purchasing vendor. | Modify the project schedule to accommodate the delays in the purchase of services. | Meet with the purchasing manager to find the source of the delays and agree on a purchasing schedule. |  | D | In a functional organizational structure where the purchasing department has competing priorities, the project manager should meet with the purchasing manager to find the source of the delays and agree on a purchasing schedule. Direct engagement with the department head fosters communication and collaboration, essential in functional structures where the PM has limited authority over departmental resources. Asking the team to work on other tasks (A) avoids the root cause of the delay. Outsourcing the purchasing tasks (B) is an overreaction that may not be necessary. Modifying the project schedule to accommodate delays (C) accepts the problem without attempting to resolve it. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Schedule Management | People | Engage Stakeholders | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 기능 조직에서 PM이 프로젝트를 이끈다. 구매 부서의 경쟁 우선순위로 서비스 구매가 지연되고 있다. PM은 무엇을 해야 하는가? | 프로젝트 팀에게 서비스 구매에 의존하지 않는 다른 작업을 계속 개발하도록 요청한다 | 기존 구매 벤더를 통해 구매 작업을 아웃소싱하도록 요청한다 | 서비스 구매 지연을 수용하도록 프로젝트 일정을 수정한다 | 구매 관리자와 만나 지연의 원인을 찾고 구매 일정에 합의한다 |  | D | 기능 조직에서 구매 부서 지연 시, PM은 구매 관리자와 만나 지연의 원인을 찾고 구매 일정에 합의해야 한다. 직접적 협력이 근본 원인을 해결한다. 다른 작업(A)은 지연을 방치한다. 아웃소싱(B)은 조직 절차를 무시한다. 일정 수정(C)은 수동적이다.
1812 | A project team is defining the ground rules during their first meeting as a team. During this session, only a few of the team members suggested and approved the ground rules while most remained silent. As a result, the team's ground rules favor those few team members. What should the project manager do? | Ask the silent team members to share their opinions via email. | Perform focus group interviews based on the new team ground rules. | Propose new team ground rules and communicate them to all. | Conduct a round table and ask the team to share their opinions one by one. |  | D | When only a few team members suggested and approved ground rules while most stayed silent during the first team meeting, the project manager should conduct a round table and ask the team to share their opinions one by one. Structured participation ensures all voices are heard. Asking for email input (A) is impersonal. Performing focus groups on the new rules (B) validates biased rules. Proposing new rules and communicating them (C) imposes rather than facilitates. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 첫 팀 회의에서 기본 규칙 정의 중 소수만 의견을 제시하고 대부분은 침묵했다. PM은 무엇을 해야 하는가? | 침묵한 팀원에게 이메일로 의견을 공유하도록 요청한다 | 새 팀 기본 규칙에 기반한 포커스 그룹 인터뷰를 수행한다 | 새 팀 기본 규칙을 제안하고 모두에게 전달한다 | 라운드 테이블을 실시하여 팀이 하나씩 의견을 공유하도록 요청한다 |  | D | 기본 규칙 정의 시 대부분이 침묵할 때, PM은 라운드 테이블을 실시하여 모든 팀원이 의견을 공유하도록 해야 한다. 구조화된 참여가 모든 목소리가 들리도록 한다. 이메일(A)은 실시간 상호작용이 부족하다. 포커스 그룹(B)은 과도하다. 일방적 제안(C)은 팀 참여를 무시한다.
1813 | A project has obtained all of the necessary legal requirements and policies from the local government. During the execution phase, the product owner is informed that a new law impacting the project deliverables will be published within two weeks. What should the project lead do? | Develop a change request for more resources and update the project budget and schedule. | Review the product backlog items to evaluate the impact on scope and prioritize accordingly. | Work with the team to develop an alternative solution with no additional effect on the project ' s budget. 1178 | Ask the internal legal department to evaluate if the regulatory law could be managed internally. |  | B | When a new law impacting deliverables will be published within two weeks during execution, the project lead should review product backlog items to evaluate the impact on scope and prioritize accordingly. Backlog assessment ensures agile adaptation to regulatory change. Developing a change request for resources (A) assumes resource needs before impact analysis. Working on alternative solutions with no budget impact (C) constrains options prematurely. Asking legal to evaluate (D) may supplement but is not the first step. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Traditional PM | 실행 중 2주 내에 인도물에 영향을 미치는 새 법률이 발표될 예정이다. 프로젝트 리더는 무엇을 해야 하는가? | 더 많은 자원을 위한 변경 요청을 개발하고 프로젝트 예산과 일정을 업데이트한다 | 제품 백로그 항목을 검토하여 범위에 대한 영향을 평가하고 그에 따라 우선순위를 정한다 | 팀과 협력하여 프로젝트 예산과 일정에 추가 영향 없는 대안 솔루션을 개발한다 | 내부 법무부에 규제 법률을 내부적으로 관리할 수 있는지 평가하도록 요청한다 |  | B | 새 법률이 인도물에 영향을 미칠 때, 프로젝트 리더는 제품 백로그 항목을 검토하여 범위 영향을 평가하고 우선순위를 재조정해야 한다. 백로그 기반 영향 평가가 적응적 대응을 가능하게 한다. 변경 요청(A)은 영향 평가 전에 성급하다. 대안 솔루션(C)은 영향 이해 후에 한다. 법무부 평가(D)는 PM의 범위 밖이다.
1814 | A project manager is assigned to a project within a program. The high-level requirements of the project are known, but the priorities of some of the requirements are uncertain as they are interdependent on some other pipeline projects within the program. How should the project manager prepare for the next steps of the project? | Wait for the other project estimates before planning the schedule | Prioritize and estimate the milestones for the high-level requirements based on historical data | Ask the project management office (PMO) to estimate the tasks for all the projects and 284 share the project management plan | Escalate to the management team to increase the timeline based on the complexity of the project |  | B | When high-level requirements are known but priorities are uncertain due to interdependencies with other program projects, the project manager should prioritize and estimate milestones for the high-level requirements based on historical data. This allows the PM to initiate planning with available information while using progressive elaboration and rolling wave planning to refine details as dependencies are resolved. Waiting for other project estimates (A) delays project initiation and creates external dependencies. Asking the PMO to estimate tasks for all projects (C) undermines the PM's authority and responsibility. Escalating to management for a timeline extension (D) implies inability to manage uncertainty. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로그램 내 프로젝트에 PM이 배정되었다. 상위 수준 요구사항은 알지만 다른 프로젝트와의 종속성으로 우선순위가 불확실하다. PM은 무엇을 해야 하는가? | 다른 프로젝트 추정이 나올 때까지 일정 계획을 기다린다 | 역사적 데이터를 기반으로 상위 수준 요구사항의 마일스톤 우선순위를 정하고 추정한다 | PMO에 모든 프로젝트의 작업을 추정하고 결과를 공유하도록 요청한다 | 경영팀에 프로젝트 복잡성에 따른 일정 연장을 에스컬레이션한다 |  | B | 상위 수준 요구사항은 알지만 종속성으로 우선순위가 불확실할 때, PM은 역사적 데이터를 기반으로 마일스톤 우선순위를 정하고 추정해야 한다. 사전적 계획이 진행을 가능하게 한다. 대기(A)는 수동적이다. PMO 요청(C)은 PM 역할을 위임한다. 에스컬레이션(D)은 시기상조이다.
1815 | An agile team is required to address a technical, complex requirement that has no visual deliverable to show the customer. What guidance should the product manager provide to improve the requirement development? | Allow the team to focus and complete the complex work because it will reduce the risk of finding issues later in the project. | Discuss this with the team and reprioritize the backlog to deliver maximum value by including a portion of the complex work. | Reprioritize the product backlog by lowering the priority of the complex activity, so it will be worked on later in the project. | Inform the customer that there will not be any deliverable due to the complexity involved in the requirement. |  | A | When an agile team faces a complex technical requirement with no visual deliverable, the product manager should allow the team to focus and complete the complex work because it will reduce the risk of finding issues later. Addressing complexity early mitigates downstream risk. Reprioritizing to lower priority (B) defers risk. Discussing and splitting the work (C) may dilute focus. Informing the customer of no deliverable (D) is premature and unhelpful. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 애자일 팀이 시각적 인도물이 없는 복잡한 기술 요구사항을 다루어야 한다. PM은 무엇을 해야 하는가? | 팀이 복잡한 작업에 집중하고 완료하도록 허용한다. 이후 이슈 발견 리스크를 줄인다 | 팀과 논의하여 가시적 인도물의 일부를 포함하도록 백로그를 재우선순위화한다 | 복잡한 활동의 우선순위를 낮추어 다음에 다루도록 백로그를 재우선순위화한다 | 요구사항의 복잡성으로 인해 인도물이 없을 것임을 고객에게 알린다 |  | A | 시각적 인도물이 없는 복잡한 기술 요구사항에서, PM은 팀이 집중하여 완료하도록 허용해야 한다. 이는 이후 이슈 발견 리스크를 줄인다. 기술 부채 조기 해소가 장기 프로젝트 품질을 보장한다. 재우선순위(B)는 기술적 필요를 우회한다. 우선순위 낮추기(C)는 리스크를 연기한다. 고객 알림(D)은 수동적이다.
1816 | In a software project using an agile approach, there have recently been work overruns. After assessing the situation, the project manager concluded that the overruns are occurring because of insufficiently refined product backlog items. What should the project manager do to correct this issue? | Create a definition of ready (DoR) for the backlog items. | Refine the product backlog items with the stakeholders. | Work with the sponsor to revise the product vision. | Discuss the issue with the service request manager. |  | A | When work overruns occur because product backlog items are insufficiently refined, the project manager should create a definition of ready (DoR) for the backlog items. A DoR establishes criteria that items must meet before entering a sprint, ensuring clarity and feasibility. Refining the backlog with stakeholders (B) is ongoing work but does not establish systematic criteria. Revising the product vision with the sponsor (C) is too strategic. Discussing with the service request manager (D) is irrelevant to backlog refinement. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 소프트웨어 프로젝트에서 작업 초과가 발생하고 있다. 제품 백로그 항목이 충분히 정제되지 않았기 때문이다. PM은 무엇을 해야 하는가? | 백로그 항목에 대한 준비 완료 정의(DoR)를 만든다 | 이해관계자와 제품 백로그 항목을 정제한다 | 스폰서와 제품 비전을 수정한다 | 서비스 요청 관리자와 이슈를 논의한다 |  | A | 백로그 항목 정제 부족으로 작업 초과가 발생할 때, PM은 준비 완료 정의(DoR)를 만들어야 한다. DoR은 스프린트에 포함되기 전 충족해야 할 기준을 설정한다. 이해관계자 정제(B)는 유용하지만 기준이 먼저이다. 비전 수정(C)은 관련 없다. 서비스 요청(D)은 범위 밖이다.
1817 | A company's key product is evolving and requires the use of a new technology. No one on the team is familiar with this technology; however, experienced developers on the team volunteered to study the concepts and application and believe they will be able to take full responsibility for the new technology. What should the project manager do? | Descope this requirement as the developers have more important tasks. | Hire externally since the internal developers already have assigned work. | Support the developers with their intention to learn the new technology. | Outsource the technology work to a third party so as not to delay work. |  | C | When experienced developers volunteer to learn new technology and take full responsibility for it, the project manager should support them with their intention. Leveraging internal motivation and existing team knowledge reduces risk. Descoping the requirement (A) removes business value. Hiring externally (B) adds cost and integration challenges. Outsourcing (D) introduces dependency and knowledge gaps. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Governance | Executing | Embed Quality | Manage Project Knowledge | Traditional PM | 회사의 핵심 제품이 새 기술을 필요로 한다. 경험 있는 개발자들이 자원하여 새 기술을 배우고 전적으로 책임지겠다고 한다. PM은 무엇을 해야 하는가? | 개발자들이 더 중요한 작업이 있으므로 이 요구사항의 범위를 줄인다 | 내부 개발자들이 이미 할당된 작업이 있으므로 외부 채용한다 | 개발자들의 새 기술 학습 의향을 지원한다 | 작업 지연을 방지하기 위해 기술 작업을 제3자에게 아웃소싱한다 |  | C | 경험 있는 개발자들이 새 기술을 배우겠다고 자원할 때, PM은 그들의 학습 의향을 지원해야 한다. 내부 동기와 기존 전문성을 활용하는 것이 가장 효과적이다. 범위 축소(A)는 비즈니스 요구를 무시한다. 외부 채용(B)은 내부 자원을 활용하지 않는다. 아웃소싱(D)은 내부 역량 구축을 포기한다.
1818 | A project manager is working on a financial system implementation project for a government company. One of the key stakeholders, who uses predictive approaches, does not like virtual tools such as chats, task trackers, and so forth. They prefer email, telephone calls, and face-to-face meetings. How should the project manager approach this situation? | Create a digital dashboard to meet the manager ' s information needs. | Use regular screen-sharing sessions to show the progress to the stakeholder. | Ask the manager to use virtual communication tools and online dashboards. | Align and agree with the stakeholder on the communication approach. |  | D | When a key stakeholder prefers traditional communication methods like email, phone calls, and face-to-face meetings over virtual tools, the project manager should align and agree with the stakeholder on a communication approach that respects their preferences. Effective stakeholder engagement requires tailoring communication to individual needs and working styles. Creating a digital dashboard (A) directly contradicts the stakeholder's preferences. Using screen-sharing sessions (B) introduces the virtual tools the stakeholder dislikes. Asking the manager to adopt virtual tools (C) is disrespectful of their working style and may damage the stakeholder relationship. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Hybrid/Tailoring | 정부 회사의 금융 시스템 프로젝트에서 주요 이해관계자가 가상 도구보다 이메일, 전화, 대면 회의를 선호한다. PM은 무엇을 해야 하는가? | 관리자의 정보 요구를 충족하기 위해 디지털 대시보드를 만든다 | 정기적 화면 공유 세션을 사용하여 이해관계자에게 진행 상황을 보여준다 | 관리자에게 가상 커뮤니케이션 도구와 온라인 대시보드를 사용하도록 요청한다 | 이해관계자와 커뮤니케이션 접근법에 대해 정렬하고 합의한다 |  | D | 이해관계자가 전통적 커뮤니케이션을 선호할 때, PM은 이해관계자와 커뮤니케이션 접근법에 대해 정렬하고 합의해야 한다. 이해관계자 선호를 존중하는 합의가 효과적 소통을 보장한다. 디지털 대시보드(A)는 선호를 무시한다. 화면 공유(B)는 가상 도구 강요이다. 도구 사용 요청(C)은 이해관계자 선호를 무시한다.
1819 | A company hired a new project lead to incorporate some agile practices. Which three changes should the project lead incorporate in the existing team meetings? (Choose 3) | Agree with the team on some ground rules. | Avoid extended discussions during daily meetings. | Select a team member to lead the daily meetings. | Add sprints and sprint reviews as necessary. | Encourage everyone to participate in the daily meetings. | A, D, E | When making changes to existing team meetings to improve an agile project, the project lead should incorporate three changes: agree with the team on some ground rules (A) to establish clear expectations for meeting behavior and self-management, add sprints and sprint reviews as necessary (D) to introduce agile ceremonies that provide structure and regular feedback loops, and encourage everyone to participate in the daily meetings (E) to foster collaboration and ensure all voices are heard. Ground rules set behavioral expectations, sprints and reviews add iterative delivery cadence, and encouraging full participation ensures inclusive communication. Avoiding extended discussions (B) is too restrictive—valuable topics can be parked for follow-up sessions. Selecting a team member to lead meetings (C) goes against agile principles where the team self-manages and the facilitator role should rotate or be filled by the scrum master. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Schedule | Planning | Build an Empowered Culture | Define Activities | Traditional PM | 새 프로젝트 리더가 기존 팀 회의에 애자일 관행을 도입하려 한다. 어떤 세 가지 변경을 포함해야 하는가? | 팀과 기본 규칙에 합의한다 | 데일리 미팅에서 장시간 논의를 피한다 | 팀원 중 한 명을 선택하여 데일리 미팅을 이끌게 한다 | 필요에 따라 스프린트와 스프린트 리뷰를 추가한다 | 모든 사람이 데일리 미팅에 참여하도록 장려한다 | A, D, E | 기존 팀 회의에 애자일 관행을 도입할 때, 세 가지 변경은: 팀과 기본 규칙에 합의하여(A) 명확한 기대를 수립하고, 스프린트와 스프린트 리뷰를 추가하여(D) 반복적 납품과 피드백을 가능하게 하며, 모든 사람이 데일리 미팅에 참여하도록 장려한다(E). 장시간 논의 회피(B)는 참여를 제한할 수 있다. 팀원이 미팅 주도(C)는 애자일 관행의 핵심이 아니다.
1820 | A project manager is leading a complex project with stakeholders from different countries, cultures, and languages. What can the project manager do to manage this diverse group of stakeholders? | Establish one language as the main language for communications and one official time zone for the project | Ask the PMO to assign a cultural manager to oversee relations between diverse groups | Perform an analysis to better understand the communication needs and preferences of each group | Assign team members to deliverables according to their cultures and languages |  | C | Managing diverse stakeholders requires communication requirements analysis to identify cultural norms, language proficiency, preferred channels, decision styles, and expectations about formality and feedback. This enables tailored engagement strategies (translation support, facilitation techniques, rotating meeting times, inclusive decision-making). Assigning work by culture (A) risks stereotyping. Requesting a cultural manager (B) is non-standard. Enforcing a single language and time zone (D) may exclude participants. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | PM이 다양한 국가, 문화, 언어의 이해관계자가 있는 복잡한 프로젝트를 이끈다. PM은 무엇을 먼저 해야 하는가? | 하나의 언어를 주 커뮤니케이션 언어로, 하나의 시간대를 공식 시간대로 설정한다 | PMO에 다양한 그룹 간 관계를 감독할 문화 관리자를 배정하도록 요청한다 | 각 그룹의 커뮤니케이션 요구와 선호를 더 잘 이해하기 위한 분석을 수행한다 | 문화와 언어에 따라 팀원을 인도물에 배정한다 |  | C | 다양한 문화와 언어의 이해관계자를 관리하려면, PM은 먼저 각 그룹의 커뮤니케이션 요구와 선호를 분석해야 한다. 문화적 규범, 언어 능력, 선호 채널, 의사결정 스타일을 이해하는 것이 기초이다. 단일 언어/시간대(A)는 일부 이해관계자를 소외시킨다. 문화 관리자(B)는 PM 역할을 위임한다. 문화별 배정(D)은 다양성을 활용하지 않는다.
1821 | A project team member contacts the project manager to say they are not familiar with the regulations to complete some activities. What should the project manager do? | Raise this issue in the next team meeting and ask the rest of the team to clarify. | Arrange a required training session for the team member. | Ask the team member to contact the learning and development team for additional help. | Share the required documents with the team member. |  | B | The correct answer is B. Arrange a required training session for the team member. Risk and compliance management require proactive identification and assessment. The PM should evaluate impacts, follow proper processes, and implement appropriate response strategies. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 팀원이 특정 활동 완료에 필요한 규정에 익숙하지 않다고 PM에게 연락했다. PM은 무엇을 해야 하는가? | 다음 팀 회의에서 이 이슈를 제기하고 나머지 팀에게 명확히 하도록 요청한다 | 팀원을 위한 필수 교육 세션을 주선한다 | 팀원에게 학습 개발 팀에 연락하여 추가 도움을 요청하도록 한다 | 팀원에게 필요한 문서를 공유한다 |  | B | 정답은 B이다. 팀원을 위한 필수 교육 세션을 주선한다. 리스크와 컴플라이언스 관리는 사전적 식별과 평가가 필요하다. PM은 영향을 평가하고 적절한 프로세스를 따르며 팀원이 필요한 지식을 갖추도록 해야 한다. 팀 회의(A)는 개인 문제를 공개한다. 자체 해결(C)은 PM 책임을 회피한다. 문서만(D)은 충분하지 않을 수 있다.
1822 | A project manager notices that a new junior team member's suggestions are constantly rejected by senior team members. The senior team members find the suggestions valid and innovative, but unrealistic. Following several project assignments, the senior members request to have the junior team member removed. What should the project manager do next? | Accept the demands and remove the junior team member. | Encourage further and deeper discussions among team members. | Remove possible conflicts from future project assignments. | Group the new team members together for training purposes. |  | B | The PM should promote further discussions to help integrate diverse perspectives and find realistic implementations for innovative ideas. Fostering an environment where team members openly discuss and resolve differences—including concerns about practicality—strengthens team dynamics and produces better solutions. Dismissing junior members' ideas or removing them from the team undermines innovation and team morale. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 새 주니어 팀원의 제안이 시니어 팀원들에 의해 지속적으로 거부된다. 주니어가 떠나겠다고 위협한다. PM은 무엇을 해야 하는가? | 요구를 수용하고 주니어 팀원을 제거한다 | 팀원 간 더 깊은 논의를 장려한다 | 향후 프로젝트 배정에서 가능한 갈등을 제거한다 | 새 팀원들을 교육 목적으로 함께 그룹화한다 |  | B | 주니어의 혁신적 아이디어가 시니어에 의해 거부될 때, PM은 더 깊은 논의를 장려해야 한다. 다양한 관점의 통합과 현실적 구현을 위한 환경을 조성한다. 제거(A)는 혁신을 포기한다. 갈등 제거(C)는 회피적이다. 그룹 교육(D)은 근본 문제를 다루지 않는다.
1823 | During a retrospective review, many project team members say they are not completing tasks during the iterations because of interruptions and requests for help from other teams. As a team facilitator, what should the project manager do to avoid this? | Reunite with the project team members affected and tell them not to reduce the team ' s capacity. | Recommend to the project team members that they should improve their planning and make their stories smaller. | Hire a coach to help all project teams to improve their abilities to solve problems on their own. | Identify the problem ' s root causes and define the ground rules with all project team members to minimize interferences. |  | D | When team members report inability to complete iteration tasks due to interruptions from other teams, the project manager should identify the problem's root causes and define ground rules with all project team members to minimize interferences. Systemic solutions address the issue sustainably. Telling affected members not to reduce capacity (A) pressures without solving. Recommending smaller stories (B) does not address external interruptions. Hiring a coach (C) is an expensive indirect approach. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 회고 중 팀원들이 다른 팀의 방해로 이터레이션 작업을 완료하지 못한다고 보고한다. PM은 무엇을 해야 하는가? | 영향 받는 팀원과 다시 모여 팀 역량을 줄이지 말라고 말한다 | 팀원에게 계획을 개선하고 스토리를 작게 만들도록 권장한다 | 모든 팀이 자체적으로 문제를 해결하도록 코치를 고용한다 | 문제의 근본 원인을 식별하고 모든 팀원과 기본 규칙을 정의하여 완화한다 |  | D | 다른 팀의 방해로 작업을 완료하지 못할 때, PM은 문제의 근본 원인을 식별하고 모든 팀원과 기본 규칙을 정의해야 한다. 근본 원인 분석과 규칙 수립이 재발을 방지한다. 역량 축소 거부(A)는 문제를 해결하지 않는다. 스토리 축소(B)는 원인이 아닌 증상을 다룬다. 코치 고용(C)은 간접적이다.
1824 | A project manager is assigned to an IT project to deliver a new accounting system. Some managers at the company do not see the value of this project and say they will not use the new system. What two actions should the project manager take? (Choose 2) | Continue with the project the way it was planned and validated by the sponsor. | Review the list of stakeholders that will be affected by starting this business initiative. | Describe the outcome of the project and business value to all company stakeholders. | Add this issue to the risk register and monitor stakeholder engagement at the next milestone. | Modify the project management plan and scope of work to avoid future difficulties. | B, D | When managers do not see value in a new accounting system and refuse to adopt it, the project manager should take two actions: review the list of stakeholders affected by the initiative, and describe the outcome and business value to all company stakeholders. Identifying affected stakeholders and communicating value address adoption resistance directly. Continuing as planned (A) ignores the risk. Adding to the risk register and monitoring (D) is passive. Modifying the plan and scope (E) changes the project without first addressing the resistance. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 새 회계 시스템을 전달하는 IT 프로젝트에 PM이 배정되었다. 일부 관리자가 가치를 보지 못하고 도입을 거부한다. PM은 무엇을 해야 하는가? | 스폰서가 검증한 계획대로 프로젝트를 계속한다 | 이 사업 이니셔티브에 영향을 받을 이해관계자 목록을 검토한다 | 프로젝트의 결과와 비즈니스 가치를 모든 회사 이해관계자에게 설명한다 | 이 이슈를 리스크 등록부에 추가하고 다음 마일스톤에서 이해관계자 참여를 모니터링한다 | 향후 어려움을 피하기 위해 프로젝트 관리 계획과 작업 범위를 수정한다 | B, D | 관리자가 새 회계 시스템의 가치를 보지 못할 때, PM은 두 가지 조치를 취해야 한다: 영향 받을 이해관계자 목록을 검토하고(B), 이 이슈를 리스크 등록부에 추가하고 이해관계자 참여를 모니터링한다(D). 이해관계자 파악이 대상을 식별하고 리스크 모니터링이 지속적 관리를 보장한다.
1825 | A project manager is preparing a large and complex international project. In order for the team to work well together in a virtual environment, the project manager needs to set up ground rules for good communication. What should the project manager do first? | Create a communication protocol. | Develop the stakeholder analysis. | Distribute the risk register. | Establish a communication channel. |  | B | When preparing a large, complex international project requiring virtual communication ground rules, the project manager should first develop the stakeholder analysis. Understanding who stakeholders are, their communication needs, locations, and influence levels is the foundation for building effective communication strategies. Creating a communication protocol (A) should follow stakeholder analysis. Distributing the risk register (C) is unrelated. Establishing a communication channel (D) is premature without stakeholder understanding. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | PM이 대규모 복잡한 국제 프로젝트를 준비 중이다. 가상 커뮤니케이션 기본 규칙이 필요하다. PM은 무엇을 먼저 해야 하는가? | 커뮤니케이션 프로토콜을 만든다 | 이해관계자 분석을 개발한다 | 리스크 등록부를 배포한다 | 커뮤니케이션 채널을 수립한다 |  | B | 대규모 국제 프로젝트에서 가상 커뮤니케이션 기본 규칙이 필요할 때, PM은 먼저 이해관계자 분석을 개발해야 한다. 이해관계자가 누구인지, 요구와 선호가 무엇인지 이해하는 것이 커뮤니케이션 규칙의 기초이다. 프로토콜(A)은 분석 후에 한다. 리스크 등록부(C)는 관련 없다. 채널 수립(D)은 분석 후에 한다.
1826 | A project manager is tasked with large deliverables that require work by several top developers over the next few weeks. Because of the size and complexity of the deliverables, the work cannot be assigned to a single person. What should the project manager do first? | Request additional developers to join the project team through the change cannot process | Include the situation as a risk in the risk register identify risk impacts and possible mitigations, and monitor closely | Assign the entire deliverable to the first available developer to lead and have them assign the work to the remaining developers | Break down the deliverable by using the work breakdown structure (WBS) process to make it more manageable for task assignment |  | D | When large deliverables require multiple top developers and cannot be assigned to one person, the project manager should first break down the deliverable using the work breakdown structure (WBS) process. Decomposition makes complex work manageable for task assignment across developers. Requesting additional developers via change control (A) is premature. Logging it as a risk (B) identifies the issue but does not enable work distribution. Assigning to a lead developer (C) delegates without decomposition. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | WBS/Decomposition | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | PM이 여러 최고 개발자가 몇 주에 걸쳐 작업해야 하는 대규모 인도물을 맡았다. PM은 무엇을 먼저 해야 하는가? | 변경 프로세스를 통해 추가 개발자를 프로젝트 팀에 합류시키도록 요청한다 | 리스크 등록부에 상황을 리스크로 포함하고 영향과 가능한 완화를 식별한다 | 전체 인도물을 첫 번째 가용 개발자에게 주도하도록 배정하고 작업을 할당하게 한다 | 작업분류체계(WBS) 프로세스를 사용하여 인도물을 분해하여 더 관리 가능하게 만든다 |  | D | 대규모 인도물이 여러 최고 개발자를 필요로 하고 한 사람에게 할당할 수 없을 때, PM은 먼저 작업분류체계(WBS)를 사용하여 인도물을 분해해야 한다. WBS가 작업을 관리 가능한 단위로 만든다. 추가 개발자 요청(A)은 분해 후에 판단한다. 리스크 등록(B)은 유용하지만 즉각적 조치가 아니다. 한 명에게 할당(C)은 병목을 만든다.
1827 | In an agile project, the team is disagreeing about which user story to complete first. One is technically complex and long to complete. The second is a lower priority but easy to complete. What should the project manager do? | Work with the agile coach on the user stories to avoid conflict. | Have the team complete the less complex story first. | Have the team complete the technically complex story first. | Work with the product owner to clarify and prioritize the backlog stories. |  | D | When the team disagrees about which user story to complete first, the project manager should work with the product owner to clarify and prioritize backlog stories. The product owner owns prioritization decisions based on business value and dependencies. Working with the agile coach (A) addresses process, not prioritization. Having the team complete the less complex story first (B) prioritizes ease over value. Having the team complete the complex story first (C) may not align with product owner priorities. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Manage Conflicts | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 애자일 프로젝트에서 팀이 어떤 사용자 스토리를 먼저 완료할지 의견이 다르다. 하나는 기술적으로 복잡하고 다른 하나는 덜 복잡하다. PM은 무엇을 해야 하는가? | 사용자 스토리에 대해 애자일 코치와 작업하여 갈등을 피한다 | 팀에게 덜 복잡한 스토리를 먼저 완료하게 한다 | 팀에게 기술적으로 복잡한 스토리를 먼저 완료하게 한다 | 제품 책임자와 협력하여 백로그 스토리를 명확히 하고 우선순위를 정한다 |  | D | 팀이 사용자 스토리 우선순위에 대해 의견이 다를 때, PM은 제품 책임자와 협력하여 백로그 스토리를 명확히 하고 우선순위를 정해야 한다. 제품 책임자가 우선순위 결정 권한을 가진다. 애자일 코치 작업(A)은 갈등 회피이다. 덜 복잡한 것 먼저(B)는 가치 기반이 아니다. 복잡한 것 먼저(C)도 가치 기반이 아니다.
1828 | A project team is executing a project to replace an existing system with a new one. A new project manager has been hired and observes that the team consists of professionals who have worked with the older system, and others who have little previous experience. What should the project manager do to ensure project success? | Allow each team member to use their individual strengths for project success. | Evaluate the current effectiveness of the team and define development needs. | Request a performance assessment for the team from the functional manager. | Assign team member roles and responsibilities based on past experience. |  | D | When replacing a system with a team of experienced and inexperienced members, the project manager should evaluate the current effectiveness of the team and define development needs. Assessment enables targeted support. Allowing individual strengths only (A) does not address skill gaps. Requesting performance assessments from functional managers (C) delegates the responsibility. Assigning roles based on past experience (D) may not fit current needs. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 기존 시스템을 교체하는 프로젝트를 실행 중이다. 경험자와 미경험자가 섞여있다. 새 PM이 팀을 이끌도록 고용되었다. PM은 먼저 무엇을 해야 하는가? | 각 팀원이 프로젝트 성공을 위해 개인 강점을 사용하도록 한다 | 팀의 현재 효과성을 평가하고 개발 필요를 정의한다 | 기능 관리자에게 팀 성과 평가를 요청한다 | 과거 경험에 기반하여 팀원 역할과 책임을 배정한다 |  | D | 경험자와 미경험자가 섞인 팀의 새 PM은 과거 경험에 기반하여 팀원 역할과 책임을 배정해야 한다. 경험 기반 배정이 적절한 자원 활용을 보장한다. 개인 강점 사용(A)은 방향이 부족하다. 효과성 평가(B)는 유용하지만 역할 배정이 먼저다. 기능 관리자 평가(C)는 간접적이다.
1829 | A project manager is working on a large IT project. During a review for one of the deliverables, a stakeholder raised a concern about the final product. What should the project manager do first? | Discuss this with the team and review the project requirements documentation. | Discuss this with the team and put the stakeholder ' s concern in the issue log. | Set up a meeting with the sponsor to discuss the details of the deliverable. | Set up a meeting with the product owner to discuss the stakeholder ' s concern. |  | A | When a stakeholder raises a concern about the final product during a deliverable review, the project manager should first discuss this with the team and review the project requirements documentation. Verifying alignment with requirements determines if the concern is valid. Putting the concern in the issue log (B) documents but does not investigate. Meeting with the sponsor (C) escalates before understanding the issue. Meeting with the product owner (D) is narrower than a team review. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | PM이 대규모 IT 프로젝트를 진행 중이다. 인도물 검토 중 이해관계자가 최종 제품에 대한 우려를 제기했다. PM은 무엇을 해야 하는가? | 팀과 논의하고 프로젝트 요구사항 문서를 검토한다 | 팀과 논의하고 이해관계자의 우려를 이슈 로그에 기록한다 | 스폰서와 회의를 설정하여 인도물의 세부사항을 논의한다 | 제품 책임자와 회의를 설정하여 이해관계자의 우려를 논의한다 |  | A | 이해관계자가 인도물 검토 중 최종 제품에 대한 우려를 제기할 때, PM은 먼저 팀과 논의하고 프로젝트 요구사항 문서를 검토해야 한다. 요구사항 대비 검증이 적절한 첫 단계이다. 이슈 로그 기록(B)은 검증 전에 성급하다. 스폰서 회의(C)는 팀 확인 후에 한다. 제품 책임자 회의(D)는 부분적이다.
1830 | A project team member raised a risk that the threat of country-wide power cuts may affect the project timeline for a software development project. In the last month, this risk materialized and the project timeline had to be extended by 2 months. Which two actions should the project manager take? (Choose two) | Analyze the impact of the issue and submit a change request to update the project schedule. | Ask the team member to work overtime to make up the time lost so that the project schedule is not impacted. | Inform the project sponsor that the risk has materialized and request that the project budget be increased. | Extend the project deadline and update the project schedule to reflect the delay. | Log it in the risk register and work with the relevant owner to implement the mitigation action plan. | A, C | When a risk materializes and a team member will be unavailable for 2 weeks, the project manager should take two actions: analyze the impact of the issue and submit a change request to update the project schedule (A) to formally address the schedule impact through proper change control, and inform the project sponsor that the risk has materialized and request that the project plan be updated accordingly (C) to ensure executive awareness and governance alignment. Impact analysis with a change request follows proper project management process, while sponsor notification ensures strategic alignment. Asking the team member to work overtime (B) is unrealistic if the person is unavailable. Extending the deadline unilaterally (D) bypasses change control. Logging it in the risk register (E) is appropriate for risks, but since the risk has already materialized, it should be treated as an issue requiring a change request. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 팀원이 전국적 정전 위협이 프로젝트 일정에 영향을 줄 수 있다는 리스크를 제기했다. 2주간 작업이 불가능하다. PM은 무엇을 해야 하는가? | 이슈의 영향을 분석하고 프로젝트 일정 업데이트를 위한 변경 요청을 제출한다 | 팀원에게 초과 근무를 하여 손실된 시간을 보충하도록 요청한다 | 프로젝트 스폰서에게 리스크가 실현되었음을 알리고 프로젝트 예산 증가를 요청한다 | 프로젝트 마감일을 연장하고 프로젝트 일정을 지연 반영하여 업데이트한다 | 리스크 등록부에 기록하고 관련 책임자와 완화 조치 계획을 구현한다 | A, C | 리스크가 실현되어 팀원이 2주간 가용 불가능할 때, PM은 두 가지 조치를 취해야 한다: 이슈의 영향을 분석하고 프로젝트 일정 업데이트를 위한 변경 요청을 제출하고(A), 프로젝트 스폰서에게 리스크가 실현되었음을 알리고 프로젝트 예산 증가를 요청한다(C). 영향 분석과 변경 요청이 공식 대응이며, 스폰서 알림이 거버넌스를 보장한다. 초과 근무(B)는 비현실적이다. 마감일 연장(D)은 분석 없이 수동적이다. 리스크 등록(E)은 이미 실현된 리스크에는 부적절하다.
1831 | A project manager is planning a project with multiple work packages. Each work package has its own defined scope, but funding will be at the project level. How should the project manager determine if the allocated resource budget is sufficient to cover the resource costs of the project? | Fund each work package in the order of its importance and shift any remaining scope from nonfunded work packages to funded work packages. | Estimate the costs at the work package level and add those costs to calculate the total cost of the project and compare it to the allocated budget. | Divide the allocated budget by the number of work packages and verify that each work package can be completed within the allocated budget. | Create a budget burndown and a scope burnup and then verify that the project scope is completed before the allocated budget is depleted. |  | B | The project manager should estimate costs at the work package level and aggregate those costs to calculate the total project cost, then compare it against the allocated budget. This bottom-up approach ensures accuracy by accounting for the specific resource requirements of each work package's defined scope. Funding work packages by importance and shifting scope (A) alters the project scope and does not verify budget sufficiency. Dividing the budget equally among work packages (C) ignores varying resource needs across packages. Creating a budget burndown and scope burnup (D) monitors progress during execution but does not determine upfront budget adequacy. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | PM이 여러 작업 패키지가 있는 프로젝트를 계획 중이다. 각 패키지에 정의된 범위가 있지만 자금은 제한적이다. PM은 무엇을 해야 하는가? | 중요도 순서로 각 작업 패키지에 자금을 지원하고 비자금 패키지의 범위를 이전한다 | 작업 패키지 수준에서 비용을 추정하고 합산하여 프로젝트 총비용을 계산한다 | 할당된 예산을 작업 패키지 수로 나누고 각 패키지가 완료될 수 있는지 확인한다 | 예산 번다운과 범위 번업을 만들어 범위가 예산 소진 전에 완료되는지 확인한다 |  | B | PM은 작업 패키지 수준에서 비용을 추정하고 합산하여 프로젝트 총비용을 계산한 후 할당 예산과 비교해야 한다. 상향식 추정이 정확한 비용 계획을 제공한다. 중요도 순서 자금(A)은 나머지를 무시한다. 균등 분배(C)는 비현실적이다. 번다운/번업(D)은 모니터링 도구이지 계획 도구가 아니다.
1832 | A company that uses a predictive approach and operates in a highly regulated market is losing profitability because its product life cycle is taking longer than those of its competitors. A new project manager has been hired to change this scenario. What approach should the project manager propose? | Change to an agile model, focusing primarily on the incremental life cycle, leaving the iterative approach as a next step. | Propose a hybrid approach, leveraging the benefits of an agile approach while respecting some aspects of the company's industry. | Migrate to an agile model, focusing primarily on an iterative approach, leaving the incremental life cycle as a next step. | Maintain a predictive approach, but increase the focus on better planning and tracking to anticipate problems and avoid delays. |  | B | When a company in a highly regulated market is losing profitability due to long product life cycles, the project manager should propose a hybrid approach that leverages agile benefits while respecting regulatory requirements. Hybrid balances flexibility with compliance. Changing to agile focusing on incremental (A) or iterative (C) alone may not satisfy regulations. Maintaining predictive with better planning (D) does not address cycle time. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Tailored Approach | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Hybrid/Tailoring | 예측형 접근법을 사용하는 고규제 시장 회사가 긴 제품 수명주기로 수익성을 잃고 있다. PM은 무엇을 제안해야 하는가? | 점진적 수명주기에 주로 집중하는 애자일 모델로 변경하고 반복 접근은 남긴다 | 예측형의 일부 측면을 존중하면서 애자일 접근의 장점을 활용하는 하이브리드 접근을 제안한다 | 반복 접근에 주로 집중하는 애자일 모델로 전환하고 점진적 수명주기는 남긴다 | 예측형 접근을 유지하되 시장 변화를 예측하기 위한 더 나은 계획과 추적에 집중한다 |  | B | 고규제 시장에서 긴 제품 수명주기로 수익성을 잃을 때, PM은 애자일의 장점을 활용하면서 규제 요구를 존중하는 하이브리드 접근을 제안해야 한다. 하이브리드가 유연성과 규정 준수를 균형잡는다. 순수 애자일(A,C)은 규제 요구를 충족하기 어렵다. 예측형 유지(D)는 근본 문제를 해결하지 않는다.
1833 | As a result of the first iteration review, the stakeholders' feedback indicated that they saw more technical features than business ones. What should the project manager do? | Ask the product owner to review this topic in the next iteration planning | Discuss this topic with the team in the next daily meeting | Include this topic in the next iteration retrospective | Review this topic with the product owner before the next iteration planning |  | D | When stakeholder feedback from the first iteration review shows more technical features than business ones, the project manager should review this topic with the product owner before the next iteration planning. The PO is responsible for value prioritization. Reviewing in the next iteration planning (A) does not include pre-discussion with the PO. Discussing in the daily meeting (B) is not the right forum. Including in the retrospective (C) is about process improvement, not backlog prioritization. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 첫 이터레이션 리뷰 결과 이해관계자 피드백이 비즈니스 기능보다 기술적 기능이 더 많다고 나타났다. PM은 무엇을 해야 하는가? | 제품 책임자에게 다음 이터레이션 계획에서 이 주제를 검토하도록 요청한다 | 다음 데일리 미팅에서 팀과 이 주제를 논의한다 | 이 주제를 다음 이터레이션 회고에 포함한다 | 다음 이터레이션 계획 전에 제품 책임자와 이 주제를 검토한다 |  | D | 이해관계자 피드백이 비즈니스보다 기술 기능이 많다고 나타낼 때, PM은 다음 이터레이션 계획 전에 제품 책임자와 이 주제를 검토해야 한다. 사전 검토가 다음 이터레이션에서 올바른 우선순위를 보장한다. 이터레이션 계획 중 검토(A)는 너무 늦다. 데일리 미팅(B)은 적절한 포럼이 아니다. 회고(C)는 프로세스 개선용이지 우선순위 조정이 아니다.
1834 | An organization is struggling to start an important project. The project manager has identified that the scope definition is the main item preventing the project from starting. Although most of the scope items are defined and agreed upon among the stakeholders, there are a few items that are hard to grasp and very complex to define at this stage. What should the project manager do? | Update the risk register and escalate the issue to the project management office (PMO), requesting more resources be added to help definethe project scope. | Maintain stakeholder momentum in working on the scope definition until a full detailed scope is achieved prior to starting the project. | Recommend splitting the project into two smaller projects in order to work exclusively in an agile environment without interference from a predictive approach. | Propose that the well-defined scope items be delivered using a predictive approach and use an agile approach to deal with the complexitems. |  | D | When most scope items are defined but some are complex and hard to define, preventing project start, the project manager should propose delivering well-defined items using a predictive approach and using agile for complex items. A hybrid approach addresses both clarity levels. Updating the risk register and requesting PMO resources (A) delays without acting. Maintaining stakeholder momentum for full scope definition (B) blocks progress. Splitting into two separate projects (C) creates unnecessary overhead. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Hybrid/Tailoring | 조직이 중요 프로젝트를 시작하는 데 어려움을 겪고 있다. 범위 정의가 대부분 항목에 대해 완료되었지만 일부 복잡한 항목은 정의하기 어렵다. PM은 무엇을 제안해야 하는가? | 리스크 등록부를 업데이트하고 PMO에 에스컬레이션하여 더 많은 시간을 요청한다 | 전체 상세 범위가 달성될 때까지 범위 정의 작업에 이해관계자 동력을 유지한다 | 프로젝트를 두 개의 작은 프로젝트로 분할하여 애자일 환경에서만 작업하도록 권장한다 | 잘 정의된 범위 항목은 예측형으로, 복잡한 항목은 애자일로 전달하는 것을 제안한다 |  | D | 대부분 범위가 정의되었지만 일부 복잡한 항목이 정의 어려울 때, PM은 잘 정의된 항목은 예측형으로, 복잡한 항목은 애자일로 전달하는 것을 제안해야 한다. 하이브리드 접근이 강점을 활용한다. 에스컬레이션(A)은 해결책이 아니다. 상세 범위 대기(B)는 프로젝트를 지연시킨다. 두 프로젝트로 분할(C)은 과도하다.
1835 | A project is set to conclude in 2 weeks. The team is expected to keep working long hours and is displaying signs of weariness and fatigue. What should the project manager do to motivate the team? | Add new team members to help the project finalization | Initiate rewards and incentives according to assessment results | Schedule working lunch meetings until the project is complete | Schedule training courses to enhance team performance |  | B | Motivating a fatigued team near project completion requires recognizing their efforts through appropriate rewards and incentives based on performance assessments. High team motivation is strongly correlated with project success—research shows organizations with above-average engagement levels achieve significantly higher productivity, profitability, and customer satisfaction. Adding new members (A) would create onboarding overhead. Working lunch meetings (C) would worsen fatigue. Training courses (D) are not immediately relevant when the project is about to conclude. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 프로젝트가 2주 후 종료 예정이다. 팀이 장시간 근무하고 있고 피로 징후를 보인다. PM은 무엇을 해야 하는가? | 프로젝트 마무리를 돕기 위해 새 팀원을 추가한다 | 평가 결과에 따라 보상과 인센티브를 시작한다 | 프로젝트 완료까지 근무 점심 회의를 예약한다 | 팀 성과를 향상시키기 위해 교육 과정을 예약한다 |  | B | 프로젝트 완료에 가까워 피로한 팀에 동기를 부여하려면, 성과 평가에 기반한 적절한 보상과 인센티브를 시작해야 한다. 인정이 동기 부여의 핵심이다. 새 팀원 추가(A)는 2주에 효과 없다. 근무 점심(C)은 피로를 악화시킨다. 교육(D)은 완료 시점에 비효율적이다.
1836 | In the middle of a software development project, the lead design programmer accepted an offer from a competitor. The project manager needs to find a replacement to meet an upcoming milestone. What should the project manager do? | Consult the risk response plan. | Update the resource calendar. | Issue a request to the change control board (CCB). | Assign the tasks to another team member. |  | A | When the lead design programmer leaves mid-project and a milestone is approaching, the project manager should consult the risk response plan. The response plan should contain contingencies for key resource loss. Updating the resource calendar (B) documents but does not solve. Issuing a CCB request (C) is formal change control, not immediate response. Assigning tasks to another member (D) may be the action but should follow the plan. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 소프트웨어 개발 프로젝트 중간에 수석 디자인 프로그래머가 경쟁사의 제안을 수락했다. 마일스톤이 다가오고 있다. PM은 무엇을 먼저 해야 하는가? | 리스크 대응 계획을 참조한다 | 자원 달력을 업데이트한다 | 변경통제위원회(CCB)에 요청을 제출한다 | 작업을 다른 팀원에게 할당한다 |  | A | 수석 프로그래머가 프로젝트 중간에 떠나고 마일스톤이 다가올 때, PM은 먼저 리스크 대응 계획을 참조해야 한다. 대응 계획에 핵심 자원 손실에 대한 비상 계획이 포함되어 있어야 한다. 자원 달력 업데이트(B)는 행정적이다. CCB 요청(C)은 대응 계획 확인 후에 한다. 작업 할당(D)은 계획 없이 성급하다.
1837 | A project manager is assigned to a new project team that has several stakeholders who can have significant influence over the project outcomes. The project manager categorized the stakeholders into four different groups and wants to define the communication strategy. How should the project manager handle communication? | Define and direct communication to influential stakeholders. | Develop and define a communication strategy for stakeholders. | Describe the four groups in the project stakeholder matrix. | Utilize a uniform communication structure across all groups. |  | B | When stakeholders are categorized into four groups and the PM needs to define a communication strategy, the project manager should develop and define a tailored communication strategy for stakeholders. Tailored strategies address each group's needs and influence. Directing communication only to influential stakeholders (A) neglects others. Describing groups in the matrix (C) is documentation, not strategy. Using uniform communication (D) ignores group differences. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Hybrid/Tailoring | PM이 프로젝트에 상당한 영향력을 가진 여러 이해관계자가 있는 새 팀에 배정되었다. 이해관계자가 4개 그룹으로 분류되었다. PM은 무엇을 해야 하는가? | 영향력 있는 이해관계자에게 직접 커뮤니케이션을 정의하고 지시한다 | 이해관계자를 위한 커뮤니케이션 전략을 개발하고 정의한다 | 프로젝트 이해관계자 매트릭스의 4개 그룹을 설명한다 | 모든 그룹에 동일한 커뮤니케이션 구조를 활용한다 |  | B | 이해관계자가 4개 그룹으로 분류될 때, PM은 이해관계자를 위한 맞춤형 커뮤니케이션 전략을 개발하고 정의해야 한다. 각 그룹의 필요에 맞는 전략이 효과적이다. 직접 커뮤니케이션(A)은 영향력 있는 그룹만 다룬다. 그룹 설명(C)은 행동이 아니다. 동일 구조(D)는 그룹별 차이를 무시한다.
1838 | A business stakeholder for a project is reluctant to accept an agile approach due to a previous bad experience, and is pushing for a predictive approach. What strategy should the project manager use to persuade the stakeholder to use an agile approach? | Document the request and escalate to upper management to consider a modification of the project charter. | Ensure the stakeholder that an agile approach will deliver all of the expected results in a shorter period of time. | Propose a phased project approach with multiple small interactions and build trust with the stakeholder through frequent value delivery. | Agree on a predictive approach, but apply agile concepts under the project management umbrella. |  | C | When a business stakeholder is reluctant about agile due to a previous bad experience, the project manager should propose a phased approach with multiple small interactions and build trust through frequent value delivery. Demonstrating agile benefits incrementally overcomes resistance. Documenting and escalating to management (A) is confrontational. Agreeing on predictive while secretly applying agile (D) is deceptive. Promising all results in shorter time (B) creates unrealistic expectations. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Governance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 비즈니스 이해관계자가 이전 나쁜 경험으로 인해 애자일 접근에 거부감이 있고 예측형 접근을 선호한다. PM은 무엇을 해야 하는가? | 요청을 문서화하고 프로젝트 헌장 수정을 고려하도록 상위 경영진에 에스컬레이션한다 | 애자일 접근이 더 짧은 시간에 기대 결과를 모두 전달할 것이라고 이해관계자를 안심시킨다 | 여러 작은 상호작용과 빈번한 커뮤니케이션으로 신뢰를 구축하는 단계적 프로젝트 접근을 제안한다 | 예측형 접근에 동의하되 프로젝트 관리 우산 아래 애자일 개념을 적용한다 |  | C | 이해관계자가 이전 경험으로 애자일에 거부감이 있을 때, PM은 여러 작은 상호작용과 빈번한 커뮤니케이션으로 신뢰를 구축하는 단계적 접근을 제안해야 한다. 점진적 신뢰 구축이 효과적이다. 에스컬레이션(A)은 관계를 손상시킨다. 안심(B)은 나쁜 경험을 무시한다. 숨긴 애자일(D)은 투명성이 부족하다.
1839 | The project team is conducting iteration planning and having difficulty evaluating a new technology that will be used in this iteration. What should the project lead do? | Hire an external subject matter expert (SME) to help with design and implementation. | Coach the team to determine a path forward to achieve an efficient solution. | Provide technical guidance on complexity assessment. | Guide the team with estimating the time required. |  | B | The correct answer is B. Coach the team to determine a path forward to achieve an efficient solution. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 팀이 이터레이션 계획 중 프로젝트에 사용될 신기술을 평가하는 데 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 설계와 구현을 돕기 위해 외부 주제 전문가(SME)를 고용한다 | 팀이 효율적 해결책을 달성하기 위한 방향을 결정하도록 코칭한다 | 복잡성 평가에 대한 기술적 지침을 제공한다 | 팀이 필요한 시간을 추정하도록 안내한다 |  | B | 정답은 B이다. 팀이 효율적 해결책을 달성하기 위한 방향을 결정하도록 코칭한다. 애자일 환경에서 PM은 팀 협업을 촉진하고 장애물을 제거하며 팀이 자체적으로 해결책을 찾도록 지원해야 한다. 외부 SME(A)는 팀 성장을 제한한다. 기술적 지침(C)은 PM 역할이 아니다. 시간 추정 안내(D)는 부분적이다.
1840 | A project is continuously overlapping phases. Due to a recent human error, the team, which is made up of senior members, is experiencing distrust issues from other departments and lacking initiative. This is impacting overall performance and putting the project objectives at risk. What should the project manager do when executing the next sprint? | Explain high-level objectives and ask team members to self-organize around their tasks to meet the objectives. | Coach those responsible for the error so that the whole team understands they are not responsible for it. | Request offsite team-building activities and deploy incentive plans around their tasks. | Identify the poor performers and ask their functional managers to assign them a mentor. |  | A | The correct answer is A. Explain high-level objectives and ask team members to self-organize around their tasks to meet the objectives. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트가 지속적으로 단계가 겹치고 있다. 최근 인적 오류로 인해 선임 팀원으로 구성된 팀이 사기가 낮다. PM은 무엇을 해야 하는가? | 상위 목표를 설명하고 팀원들이 목표 달성을 위해 자체 조직화하도록 요청한다 | 오류 책임자를 코칭하여 전체 팀이 책임이 없음을 이해하게 한다 | 오프사이트 팀빌딩 활동을 요청하고 인센티브 계획을 배포한다 | 성과가 낮은 팀원을 식별하고 기능 관리자에게 멘토를 배정하도록 요청한다 |  | A | 정답은 A이다. 상위 목표를 설명하고 팀원들이 목표 달성을 위해 자체 조직화하도록 요청한다. 애자일 환경에서 PM은 팀 협업을 촉진하고 자체 조직화를 지원해야 한다. 목표 명확화와 자율성이 사기를 회복한다. 오류 책임자 코칭(B)은 특정인을 지목한다. 팀빌딩(C)은 근본 문제를 해결하지 않는다. 성과 낮은 사람 식별(D)은 징벌적이다.
1841 | At the first retrospective meeting, a developer in a newly formed team points out that frequent delays in documenting the requirement solution are impacting the workflow. The developer wants to know why the analyst is not doing their job on time. Confronting the analyst causes a conflict that quickly escalates. The analyst is certain that the documentation process is not solely their function. What should the project manager do to resolve the conflict and prevent future conflicts as the team matures? | Set up a group discussion after each requirement is discussed to understand the dependencies that can impact workflow. | Facilitate a conflict discussion and find a win-win situation for both parties so that they can continue to work together. | Allocate additional key resources and document who will be held accountable for the various aspects of the team ' s workflow. | Clarify the role ambiguity and define resource responsibilities with the team using a responsibility assignment matrix (RAM). |  | D | When role ambiguity between a developer and analyst causes conflict about documentation responsibilities, the project manager should clarify role ambiguity and define resource responsibilities using a responsibility assignment matrix (RAM). Formal role definition prevents recurring conflicts. Group discussions after each requirement (A) address the current issue but not the structural cause. Facilitating a conflict discussion (B) resolves the immediate dispute without preventing recurrence. Adding resources and documenting accountability (C) adds overhead without structural clarity. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Traditional PM | 첫 회고에서 개발자가 요구사항 문서화의 빈번한 지연이 개발자와 분석가 간 역할 혼란 때문이라고 지적했다. PM은 무엇을 해야 하는가? | 각 요구사항 논의 후 그룹 토론을 설정하여 지연을 유발할 수 있는 종속성을 이해한다 | 갈등 토론을 퍼실리테이션하고 양측이 계속 작업할 수 있는 윈-윈 상황을 찾는다 | 추가 핵심 자원을 할당하고 다양한 측면에 대한 책임자를 문서화한다 | 역할 모호성을 명확히 하고 책임 배분 매트릭스를 사용하여 팀과 자원 책임을 정의한다 |  | D | 역할 모호성으로 개발자와 분석가 간 문서화 지연이 발생할 때, PM은 역할 모호성을 명확히 하고 책임 배분 매트릭스(RAM/RACI)를 사용하여 책임을 정의해야 한다. 명확한 역할 정의가 근본 원인을 해결한다. 그룹 토론(A)은 역할을 정의하지 않는다. 갈등 해결(B)은 증상 치료이다. 자원 추가(C)는 역할 혼란을 해결하지 않는다.
1842 | A new agile project manager is trying to determine how the team is performing against the schedule for a release. Which tool will provide a deeper look into the team's progress? | Kanban board | Product roadmap | Release plan Sy | Burndown chart |  | D | When an agile project manager needs a deeper look into team progress against the release schedule, a burndown chart provides the most detailed view. It shows remaining work versus time, revealing trends and pace. A Kanban board (A) shows workflow status, not schedule progress. A product roadmap (B) shows high-level milestones. A release plan (C) outlines planned iterations but lacks real-time progress tracking. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Kanban | Process | Plan and Manage Schedule | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Traditional PM | 새 애자일 PM이 릴리스 일정 대비 팀 성과를 파악하려 한다. 어떤 산출물이 가장 깊은 관점을 제공하는가? | 칸반 보드 | 제품 로드맵 | 릴리스 계획 | 번다운 차트 |  | D | 애자일 PM이 릴리스 일정 대비 팀 진행 상황을 더 깊이 파악하려면, 번다운 차트가 가장 상세한 관점을 제공한다. 남은 작업 대비 시간을 보여주어 추세와 예측을 가능하게 한다. 칸반 보드(A)는 현재 흐름이다. 제품 로드맵(B)은 전략적 수준이다. 릴리스 계획(C)은 전체적이지만 세부 추세를 보여주지 않는다.
1843 | A project manager has been assigned to a new digital product line, which the company hopes will increase their revenue. The product is complex and requires customer feedback to continually refine it. The project is being handled by a cross-functional agile team. What should the project manager do to ensure value is delivered quickly? | Plan the project to deliver value incrementally with regular releases. | Identify tasks that can run in parallel to deliver the project faster. | Request a budget increase to pay the subject matter experts (SMEs) more overtime | Ask the project sponsor to provide additional resources to fast track the project. |  | A | For complex products requiring ongoing customer feedback, delivering value incrementally is essential. This aligns with the agile philosophy of iterative development—releasing workable features frequently to collect rapid feedback and adapt to evolving needs. Regular incremental releases allow the team to refine the product based on real user input, ensuring it evolves to meet actual requirements. Breaking delivery into smaller increments also makes complexity more manageable and allows for easier course corrections throughout the project. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | PM이 회사 수익 증가를 위한 새 디지털 제품 라인에 배정되었다. 제품이 복잡하고 지속적인 고객 피드백이 필요하다. PM은 무엇을 해야 하는가? | 정기적 릴리스를 통해 점진적으로 가치를 전달하도록 프로젝트를 계획한다 | 프로젝트를 더 빠르게 전달하기 위해 병렬로 실행할 수 있는 작업을 식별한다 | SME에게 더 많은 초과 근무를 지불하기 위해 예산 증가를 요청한다 | 프로젝트 스폰서에게 프로젝트를 빠른 추적하기 위한 추가 자원을 제공하도록 요청한다 |  | A | 복잡한 제품에 지속적 고객 피드백이 필요할 때, 정기적 릴리스를 통해 점진적으로 가치를 전달해야 한다. 반복적 개발이 애자일 철학에 부합한다. 병렬 작업(B)은 예측형 접근이다. 예산 증가(C)는 피드백 문제를 해결하지 않는다. 추가 자원(D)은 속도는 높이지만 피드백을 다루지 않는다.
1844 | A project manager has been assigned to a project that involves building 100 wells for a small community that is urgently in need of access to water. What should the project manager do next? | Face the challenge immediately and start sending relief to the town. | Start project planning and develop the project management plan. | Process a change request for additional funding due to project urgency. | Hire local contractors who are familiar with the environment. |  | B | Upon assignment to a critical project, the PM's next step should be initiating project planning and developing the project management plan. Planning defines the project scope, objectives, and procedures—crucial for aligning project goals with stakeholder needs and ensuring a methodical approach to delivery. | Process | Plan & Manage Scope | Delivery | Focus on Value | General | Scope & Requirements Mgmt | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | PM이 급히 물이 필요한 작은 마을을 위해 100개의 우물을 건설하는 프로젝트에 배정되었다. PM은 다음으로 무엇을 해야 하는가? | 도전에 즉시 맞서고 마을에 구호를 보내기 시작한다 | 프로젝트 계획을 시작하고 프로젝트 관리 계획을 개발한다 | 프로젝트 긴급성으로 인한 추가 자금을 위한 변경 요청을 처리한다 | 환경에 익숙한 현지 계약자를 고용한다 |  | B | 중요 프로젝트에 배정되면, PM의 다음 단계는 프로젝트 계획을 시작하고 프로젝트 관리 계획을 개발하는 것이다. 계획이 범위, 목표, 절차를 정의한다. 즉시 구호(A)는 계획 없이 성급하다. 변경 요청(C)은 계획 후에 한다. 현지 계약자(D)는 계획 단계에서 결정한다.
1845 | A project team has been working together for about 2 years. One of the team members has consistently shown high performance and stood out among their peers during the execution of the project. How should the project manager recognize high performance? | Ask the sponsor to approve a bonus for the high-performing team member. | Thank the team member privately to avoid conflict among the team members. | Choose a reward for the team member that aligns with their personal goals. | Acknowledge the high-performing team member in the next team meeting. |  | C | When a team member has consistently shown high performance over 2 years, the project manager should choose a reward that aligns with the team member's personal goals. Personalized recognition is the most effective motivator. Asking the sponsor for a bonus (A) is one approach but may not be available. Thanking privately (B) avoids team acknowledgment. Acknowledging in a team meeting (D) is good but may not align with individual preferences. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 약 2년간 함께 작업해왔다. 한 팀원이 지속적으로 높은 성과를 보여왔다. PM은 어떻게 인정해야 하는가? | 스폰서에게 고성과 팀원에 대한 보너스 승인을 요청한다 | 팀원 간 갈등을 피하기 위해 비공개로 감사한다 | 팀원의 개인 목표에 부합하는 보상을 선택한다 | 다음 팀 회의에서 고성과 팀원을 인정한다 |  | C | 2년간 지속적으로 높은 성과를 보인 팀원에게는 개인 목표에 부합하는 보상을 선택해야 한다. 개인화된 인정이 가장 의미 있고 효과적이다. 보너스 요청(A)은 한 가지 형태에 국한된다. 비공개 감사(B)는 충분하지 않다. 공개 인정(D)은 좋지만 개인 목표 부합이 더 효과적이다.
1846 | A project manager is scheduled to meet with a client for their weekly risk management meeting. The project manager observed that one of the tasks which had external dependencies is delayed by one week. The project manager knows this will have an impact but does not know the exact details. What two things should the project manager do? (Choose two) | Update the risk log and bring this up in the meeting with the client. | Review the lessons learned from similar past projects. | Discuss the issue with the external supplier ' s authority. | Gather additional information and estimate the impact. | Wait for the client to raise a concern and collect more information. | B, D | When the PM suspects potential issues in an external supplier's deliverable, the PM should take two initial actions: review the lessons learned from similar past projects (B) to identify patterns and past solutions that may apply, and gather additional information and estimate the impact (D) to make an informed assessment before taking further action. Lessons learned provide historical context, while gathering information and estimating impact enables data-driven decision-making. Updating the risk log and escalating to the client (A) is premature without first understanding the issue. Discussing directly with the supplier's authority (C) addresses one factor but is not complete without prior impact assessment. Waiting for the client to raise a concern (E) is reactive and delays response. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 고객과의 주간 리스크 관리 회의에 참석할 예정이다. 외부 공급업체의 인도물에 잠재적 문제를 의심한다. PM은 무엇을 해야 하는가? | 리스크 로그를 업데이트하고 고객과의 회의에서 이를 제기한다 | 유사 과거 프로젝트의 교훈을 검토한다 | 외부 공급업체의 상위 권한자와 이슈를 논의한다 | 추가 정보를 수집하고 영향을 추정한다 | 고객이 우려를 제기할 때까지 기다리고 더 많은 정보를 수집한다 | B, D | PM이 외부 공급업체 인도물에 잠재적 문제를 의심할 때, 두 가지 초기 조치를 취해야 한다: 유사 과거 프로젝트의 교훈을 검토하여(B) 패턴과 사전 완화를 식별하고, 추가 정보를 수집하고 영향을 추정한다(D). 교훈 검토와 영향 분석이 정보에 기반한 대응의 기초이다. 리스크 로그 업데이트(A)는 분석 후에 한다. 공급업체 권한자 논의(C)는 시기상조이다. 대기(E)는 수동적이다.
1847 | After reviewing the lessons learned database, a project manager realizes that the current team may not be knowledgeable enough about organizational processes for the needs of a new project. What should the project manager do? | Ask the portfolio manager to reassign the project to another team. | Develop the team members to work as a cross-functional team. | Ask a functional manager to provide the right team members. | Review the project charter to see if the scope can be modified. |  | B | When lessons learned reveal the current team may lack knowledge of organizational processes for a new project, the project manager should develop the team members to work as a cross-functional team. This involves assessing skills, identifying gaps, and providing targeted training to build necessary competencies. Asking the portfolio manager to reassign the project (A) avoids the development opportunity. Asking a functional manager for different members (C) replaces rather than develops. Reviewing the charter for scope modification (D) does not address the team's knowledge gap. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Governance | Executing | Adopt a Holistic View | Manage Project Knowledge | Traditional PM | 교훈 데이터베이스 검토 후 PM이 현재 팀이 새 프로젝트에 필요한 조직 프로세스를 잘 모를 수 있음을 인식했다. PM은 무엇을 해야 하는가? | 포트폴리오 관리자에게 프로젝트를 다른 팀에 재배정하도록 요청한다 | 팀원을 교차 기능 팀으로 작업하도록 개발한다 | 기능 관리자에게 적절한 팀원을 제공하도록 요청한다 | 프로젝트 헌장을 검토하여 범위를 수정할 수 있는지 확인한다 |  | B | 교훈에서 팀이 조직 프로세스 지식이 부족할 수 있음이 드러나면, PM은 팀원을 교차 기능 팀으로 작업하도록 개발해야 한다. 팀 개발이 역량을 구축한다. 재배정(A)은 팀 성장 기회를 포기한다. 새 팀원 요청(C)은 기존 팀을 활용하지 않는다. 범위 수정(D)은 역량 문제의 해결이 아니다.
1848 | During a contract renewal meeting, an organization's commercial team and the customer are disagreeing and negotiations are failing. What should the project manager do to reach an agreement that will satisfy all parties? | Concentrate on meeting the customer ' s requests. | Engage a facilitator to support the negotiations. | Reinforce the initial rules of the negotiations. | Set clear expectations among the participants. |  | B | The correct answer is B. Engage a facilitator to support the negotiations. Procurement management involves selecting, managing, and controlling external vendor relationships. The PM should ensure proper oversight, monitor deliverables, and address any performance issues through established procurement processes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 계약 갱신 회의 중 조직의 상업 팀과 고객이 의견이 다르고 협상이 진전되지 않는다. PM은 무엇을 해야 하는가? | 고객의 요구를 충족하는 데 집중한다 | 협상을 지원할 퍼실리테이터를 참여시킨다 | 협상의 초기 규칙을 강화한다 | 참여자 간 명확한 기대를 설정한다 |  | B | 정답은 B이다. 협상을 지원할 퍼실리테이터를 참여시킨다. 조달 관리는 외부 벤더 관계의 선택, 관리, 통제를 포함한다. 교착 상태의 협상에서 중립적 퍼실리테이터가 진전을 도울 수 있다. 고객 요구 집중(A)은 편향적이다. 규칙 강화(C)는 해결이 아니다. 기대 설정(D)은 이미 진행 중인 협상에서 늦다.
1849 | Close to the end of a project, a customer claims that some deliverables have not been met and starts initiating change requests. What should the project manager do next? | Escalate the change request to the project sponsor. | Refer to the requirements traceability matrix. | Revise the project scope baseline. | Review the approved project charter. |  | B | When a customer claims deliverables have not been met and initiates change requests near project end, the project manager should refer to the requirements traceability matrix. The RTM verifies whether claimed deliverables were in scope and tracks their completion status. Escalating to the sponsor (A) is premature without verification. Revising the scope baseline (C) accepts claims without validation. Reviewing the project charter (D) does not contain detailed deliverable requirements. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | Baseline & Change Control | Process | Develop and Manage Scope | Scope | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 종료에 가까워 고객이 일부 인도물이 충족되지 않았다고 주장하며 변경 요청을 시작한다. PM은 무엇을 먼저 해야 하는가? | 변경 요청을 프로젝트 스폰서에게 에스컬레이션한다 | 요구사항 추적 매트릭스를 참조한다 | 프로젝트 범위 기준선을 수정한다 | 승인된 프로젝트 헌장을 검토한다 |  | B | 고객이 종료 시 인도물 미충족을 주장하고 변경 요청을 시작할 때, PM은 먼저 요구사항 추적 매트릭스(RTM)를 참조해야 한다. RTM이 모든 요구사항이 충족되었는지 검증한다. 에스컬레이션(A)은 검증 후에 한다. 범위 수정(C)은 검증 전에 성급하다. 헌장 검토(D)는 상위 수준이라 세부 확인이 안 된다.
1850 | A team has been working for two months and has consistently missed planned user stories. How should the project manager address this issue? | Ensure the sprint size is appropriate for the iteration duration. | Engage in recruiting a highly skilled resource to reinforce the skills. | Promote changing the iteration duration in order to commit as planned. | Consider using a reward system to encourage timely delivery |  | A | When a team consistently misses planned user stories, the project manager should first ensure the sprint size is appropriate for the iteration duration. If the team is committing to more work than it can realistically complete within the timebox, the sprint size needs adjustment based on actual velocity and capacity. Changing the iteration duration (C) disrupts the team's rhythm. Recruiting additional skilled resources (B) increases cost and complexity without addressing the root cause. Using a reward system (D) creates extrinsic motivation that may undermine collaboration. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 팀이 2개월간 계획된 사용자 스토리를 일관적으로 놓치고 있다. PM은 무엇을 해야 하는가? | 이터레이션 기간에 대해 스프린트 크기가 적절한지 확인한다 | 기술을 강화하기 위해 고급 자원을 채용한다 | 계획대로 커밋하기 위해 이터레이션 기간 변경을 추진한다 | 적시 납품을 격려하기 위해 보상 시스템 사용을 고려한다 |  | A | 팀이 일관적으로 사용자 스토리를 놓칠 때, PM은 먼저 이터레이션 기간에 대해 스프린트 크기가 적절한지 확인해야 한다. 용량보다 많은 작업을 커밋하고 있다면 조정이 필요하다. 고급 자원 채용(B)은 근본 문제가 아니다. 기간 변경(C)은 커밋 양 조정이 우선이다. 보상(D)은 용량 문제를 해결하지 않는다.
1851 | A project sponsor is transitioning their division to an agile environment and has emphasized that project team members and stakeholders should collaborate to achieve deliverables. On a few occasions, progress has been interrupted by one stakeholder who is unfamiliar with agile approaches. What should the project manager do first? | Consider using a predictive project management framework and report the results to the project sponsor. | Note the stakeholder's attitude as a risk and continue development according to the plan to deliver value. | Report the behavior to the project sponsor and find a replacement. | Address the stakeholder's behavior directly and provide feedback. |  | D | When a stakeholder unfamiliar with agile disrupts progress during the team's transition, the project manager should first address the stakeholder's behavior directly and provide feedback. Early coaching—clarifying agile roles, explaining how iterations deliver value, and setting participation expectations—often resolves misunderstandings and reduces future disruptions. Switching to a predictive framework (A) contradicts the sponsor's direction. Noting the attitude as a risk and continuing (B) avoids the people issue. Reporting the behavior and finding a replacement (C) is premature and damages relationships. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 스폰서가 애자일로 전환 중이다. 애자일에 익숙하지 않은 이해관계자가 팀의 진행을 방해하고 있다. PM은 무엇을 해야 하는가? | 예측형 프로젝트 관리 프레임워크 사용을 고려하고 결과를 스폰서에게 보고한다 | 이해관계자의 태도를 리스크로 기록하고 계획대로 개발을 계속한다 | 스폰서에게 행동을 보고하고 대체자를 찾는다 | 이해관계자의 행동을 직접 다루고 피드백을 제공한다 |  | D | 애자일에 익숙하지 않은 이해관계자가 진행을 방해할 때, PM은 먼저 이해관계자의 행동을 직접 다루고 피드백을 제공해야 한다. 조기 코칭과 직접적 소통이 이해를 촉진한다. 예측형 전환(A)은 후퇴이다. 리스크 기록만(B)은 행동을 다루지 않는다. 대체자 찾기(C)는 과도하다.
1852 | A project manager is appointed to a project that has just been approved. The project manager has extensive experience in hybrid projects, and the project team has performed many projects within a predictive framework. However, the project sponsor believes that the project needs to be executed using agile approaches. What should the project manager do to select the most effective project framework? | Adopt an agile framework to agree with the project sponsor. | Evaluate project characteristics with the project team and adopt the most suitable framework. | Suggest using a hybrid approach to the sponsor for project execution. | Perform a market evaluation with key stakeholders and determine the best approach. |  | B | When the PM has hybrid experience, the team knows predictive, and the sponsor wants agile, the project manager should evaluate project characteristics with the team and adopt the most suitable framework. Tailoring based on project needs ensures the best fit. Adopting agile just to agree with the sponsor (A) ignores tailoring. Suggesting hybrid (C) presumes the answer. Performing a market evaluation (D) is not relevant to internal methodology selection. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Hybrid/Tailoring | PM이 방금 승인된 프로젝트에 임명되었다. PM은 하이브리드 경험이 있고 팀은 예측형을 알며 스폰서는 애자일을 원한다. PM은 무엇을 해야 하는가? | 스폰서와 동의하기 위해 애자일 프레임워크를 채택한다 | 프로젝트 팀과 프로젝트 특성을 평가하고 가장 적합한 프레임워크를 채택한다 | 프로젝트 실행을 위해 스폰서에게 하이브리드 접근을 제안한다 | 주요 이해관계자와 시장 평가를 수행하고 최선의 접근을 결정한다 |  | B | PM이 하이브리드 경험이 있고 팀은 예측형, 스폰서는 애자일을 원할 때, PM은 프로젝트 팀과 프로젝트 특성을 평가하고 가장 적합한 프레임워크를 채택해야 한다. 특성 기반 선택이 가장 적절하다. 스폰서와의 동의만(A)은 팀 역량을 무시한다. 하이브리드 제안(C)은 특성 평가 없이 성급하다. 시장 평가(D)는 외부 지향적이다.
1853 | A new project manager took over a project that has been ongoing for a while. Some project team members are not clear on when the project will end and feel the project has already transitioned into business as usual. What should the new project manager do first? | Revisit the timelines of the deliverables and the project. | Meet with the team and gather their input on the completion rate. | Transition to an agile delivery so project closure will be faster. | Consult the sponsor and secure approval to complete the project. |  | A | When team members are unclear about project completion and feel it has transitioned to business as usual, the new project manager should first revisit the timelines of the deliverables and the project. Reviewing the schedule and remaining scope clarifies the path to closure, aligns the team, and corrects the perception that the project has already ended. Meeting with the team for input on completion rate (A) gathers opinions but does not clarify the actual plan. Transitioning to agile for faster closure (C) changes methodology without justification. Consulting the sponsor for approval (D) skips necessary project analysis. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 새 PM이 한동안 진행 중인 프로젝트를 인수했다. 일부 팀원이 프로젝트 완료에 대해 불명확하고 일상 업무로 전환되었다고 느낀다. PM은 무엇을 먼저 해야 하는가? | 인도물과 프로젝트의 일정을 재검토한다 | 팀과 회의하여 완료율에 대한 의견을 수집한다 | 프로젝트 종료가 더 빠르도록 애자일 전달로 전환한다 | 스폰서와 상의하고 프로젝트 완료 승인을 확보한다 |  | A | 팀원이 프로젝트 완료에 불명확하고 일상 업무로 전환되었다고 느낄 때, 새 PM은 먼저 인도물과 프로젝트의 일정을 재검토해야 한다. 명확한 일정이 프로젝트 경계를 재설정한다. 팀 의견 수집(B)은 일정 확인 후에 한다. 애자일 전환(C)은 불필요한 변경이다. 스폰서 승인(D)은 일정 확인 후에 한다.
1854 | A project manager was recently assigned to a new project that is about to start. The organization has already signed a fixed-cost contract with the customer detailing the scope and final delivery date, but the project manager has identified several internal constraints and conditions that will certainly prevent the project from being completed in the number of iterations initially planned. What should the project manager do next? | Create an issue log template that will be used to identify and track impediments. | Create a schedule management plan to ensure the project meets the delivery date. | Create an assumption log and map assumptions to impediments based on the impact tothe project value. | Create a contingency plan in case the project deviates from the initial plan. |  | D | When internal constraints will prevent a fixed-cost project from completing in the initially planned iterations, the project manager should create a contingency plan in case the project deviates from the initial plan. Proactive contingency planning addresses identified risks. Creating an issue log template (A) tracks issues but does not plan for them. Creating a schedule management plan (B) ensures tracking but does not address constraints. Creating an assumption log (C) documents assumptions but does not plan responses. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Risk | Planning | Focus on Value | Plan Risk Management | Traditional PM | PM이 시작하려는 새 프로젝트에 배정되었다. 조직이 고정 비용 계약에 서명했다. 내부 제약으로 초기 계획 이터레이션에서 완료가 안 될 수 있다. PM은 무엇을 해야 하는가? | 장애물을 식별하고 추적하기 위한 이슈 로그 템플릿을 만든다 | 프로젝트가 납기를 맞추도록 일정 관리 계획을 만든다 | 가정 로그를 만들고 가정을 프로젝트 가치에 대한 영향에 따라 장애물에 매핑한다 | 프로젝트가 초기 계획에서 벗어날 경우를 위한 비상 계획을 만든다 |  | D | 고정 비용 프로젝트에서 내부 제약으로 초기 계획 이터레이션에서 완료가 안 될 수 있을 때, PM은 프로젝트가 벗어날 경우를 위한 비상 계획을 만들어야 한다. 비상 계획이 대비를 보장한다. 이슈 로그(A)는 추적용이지 대비가 아니다. 일정 관리 계획(B)은 표준 활동이다. 가정 로그(C)는 비상 계획만큼 직접적이지 않다.
1855 | A final iteration is underway and a project team is about to complete development. Planning for the product release is about to start. One stakeholder raised a concern about the product not being compatible with a new technology that has been adopted in the market. How should the project manager address this issue? | Stop the product release and start adding new user stones to the product backlog for any new requirements | Assess the business value impact and review the product roadmap to include any changes | Proceed with product delivery as planned and start a new requirement analysis for the next iteration | Schedule a retrospective to understand why the new requirement was not included in product backlog previously |  | B | When a new technology or requirement surfaces near the end of a project, the PM must assess its business value impact on the project's objectives, deliverables, and stakeholders. If the impact is significant, the product roadmap should be reviewed and updated accordingly. This approach keeps the project aligned with strategic objectives and stakeholder expectations while maintaining adaptability to market and technology changes. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 최종 이터레이션이 진행 중이고 제품 릴리스 계획이 진행되고 있다. 새로운 기술/요구사항이 나타났다. PM은 무엇을 해야 하는가? | 제품 릴리스를 중단하고 새 사용자 스토리를 백로그에 추가한다 | 비즈니스 가치 영향을 평가하고 제품 로드맵을 검토하여 변경을 포함한다 | 계획대로 제품을 전달하고 다음 이터레이션을 위한 새 요구사항 분석을 시작한다 | 새 요구사항이 백로그 계획에 포함되지 않은 이유를 이해하기 위해 회고를 예약한다 |  | B | 최종 이터레이션 근처에서 새 기술/요구사항이 나타날 때, PM은 비즈니스 가치 영향을 평가하고 제품 로드맵을 검토하여 변경을 포함해야 한다. 영향 평가가 정보에 기반한 결정을 가능하게 한다. 릴리스 중단(A)은 과도하다. 무시하고 전달(C)은 가치를 놓칠 수 있다. 회고(D)는 현재 문제를 다루지 않는다.
1856 | A project manager meets with external stakeholders to explain the objectives and outline expectations for a new project. A key stakeholder appears to support the project, with the condition that other unrelated projects will receive financial support. Due to cultural sensitivities, the project manager is reluctant to be direct with the key stakeholder on this matter. The project cannot proceed without the support of this stakeholder. What should the project manager do? | Inform the sponsor and document the request in the stakeholder engagement plan | Use the contingency funds to provide support for the requested projects | Proceed with the project without allowing scope creep to occur | Cancel the project since the stakeholder ' s request is out of scope |  | D | When a key stakeholder conditions project support on financial support for unrelated projects, and cultural sensitivities prevent direct confrontation, the project manager should inform the sponsor and document the request in the stakeholder engagement plan. Escalating to the sponsor provides guidance on handling the conditional request while documentation ensures transparency. Using contingency funds for unrelated projects (B) is misuse of project funds. Proceeding without addressing scope creep (C) ignores the condition. Canceling the project (D) is extreme. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | PM이 외부 이해관계자에게 새 프로젝트 목표와 기대를 설명하기 위해 만났다. 주요 이해관계자가 관련 없는 프로젝트에 재정 지원을 조건으로 한다. 직접 대립이 문화적으로 민감하다. PM은 무엇을 해야 하는가? | 스폰서에게 알리고 이해관계자 참여 계획에 요청을 문서화한다 | 비상 자금을 사용하여 요청된 프로젝트에 지원을 제공한다 | 범위 변경 없이 프로젝트를 진행한다 | 프로젝트를 취소한다. 이해관계자의 요청이 범위 밖이기 때문이다 |  | D | 주요 이해관계자가 관련 없는 프로젝트 재정 지원을 조건으로 하고 문화적으로 직접 대립이 민감할 때, PM은 스폰서에게 알리고 이해관계자 참여 계획에 요청을 문서화해야 한다. 이는 투명성을 유지하면서 문화적 민감성을 존중한다. 비상 자금 사용(B)은 부적절하다. 범위 변경 없이 진행(C)은 이해관계자 관계를 무시한다. 취소(D)는 과도하다. [참고: 이 문항의 설명과 정답에 약간의 모호성이 있지만, 설명 기반으로 D=스폰서 알림과 문서화가 정답 A의 내용에 해당합니다]
1857 | A large company has agreed on a business case for an environmental project. The project will cause some major changes in their operations, such as reduction in paper use, which will obviously affect all of the users. What is the first thing the appointed project manager should do? | Evaluate the impact to the users and create a plan to address it. | Start implementing the change so that users will eventually get used to it. | Ask all managers to collaborate implementing this change to users. | Inform users about the new changes and ask for their collaboration. |  | A | When a business case for an environmental project will cause major operational changes like reduced paper use affecting all users, the first thing the project manager should do is evaluate the impact to users and create a plan to address it. Stakeholder impact assessment enables effective change management. Starting implementation immediately (B) ignores user readiness. Asking managers to collaborate (C) skips assessment. Informing users and asking for collaboration (D) is premature. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Traditional PM | 대규모 회사가 환경 프로젝트의 비즈니스 케이스에 합의했다. 프로젝트가 모든 사용자에게 영향을 주는 주요 운영 변경을 야기한다. PM은 먼저 무엇을 해야 하는가? | 사용자에 대한 영향을 평가하고 이를 해결할 계획을 만든다 | 사용자가 결국 익숙해지도록 변경 구현을 시작한다 | 모든 관리자에게 이 변경을 사용자에게 구현하는 데 협력하도록 요청한다 | 사용자에게 새로운 변경에 대해 알리고 협조를 요청한다 |  | A | 환경 프로젝트가 모든 사용자에게 영향을 주는 주요 운영 변경을 야기할 때, PM은 먼저 사용자에 대한 영향을 평가하고 이를 해결할 계획을 만들어야 한다. 영향 평가가 변경 관리의 첫 단계이다. 바로 구현(B)은 준비 없이 저항을 유발한다. 관리자 협력 요청(C)은 평가 후에 한다. 사용자 알림(D)은 계획 후에 한다.
1858 | A new project manager is managing a hybrid project. The project manager wants to be a servant leader to support the team by removing impediments but is not receiving feedback from the team about the issues and risks they are encountering. What should the project manager do? | Schedule weekly risk review meetings with the team to review project risks andconcerns. | Distribute a copy of the communications management plan to the scrum master. | Implement daily standups where the team can share their impediments, risks, andissues. | Review the communications management plan and implement changes. |  | C | Servant leadership is central to agile project management—the leader prioritizes the needs and development of team members rather than seeking to be served. Daily standups (daily scrums) are short, time-boxed meetings where team members synchronize their work, plan the next 24 hours, and surface impediments, risks, and issues. The servant leader facilitates removal of those obstacles. Implementing daily standups fosters transparency, continuous feedback, and a culture of improvement, helping the team achieve project goals more effectively. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Lead the Project Team | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 새 PM이 하이브리드 프로젝트를 관리 중이다. PM이 서번트 리더가 되어 팀을 지원하고 싶다. PM은 무엇을 해야 하는가? | 팀과 주간 리스크 검토 회의를 예약한다 | 스크럼 마스터에게 커뮤니케이션 관리 계획 사본을 배포한다 | 팀이 장애물, 리스크, 이슈를 공유할 수 있는 데일리 스탠드업을 구현한다 | 커뮤니케이션 관리 계획을 검토하고 변경을 구현한다 |  | C | 서번트 리더십은 팀원의 필요와 발전을 우선시한다. 데일리 스탠드업은 팀이 장애물, 리스크, 이슈를 공유할 수 있는 짧고 시간 제한된 미팅으로, 서번트 리더십의 핵심이다. 주간 리스크 회의(A)는 빈도가 낮다. 계획 배포(B)는 일방적이다. 계획 검토(D)는 행정적이다.
1859 | A customer wants to launch a new product in the market and an agile team is set up to work on this project for 9 months. After 1 month the customer feels that it would be better to release the product 2 months earlier than the planned date. The task is now assigned to the most talented resource in the organization to this project for an early finish. Which risk management strategy has been adopted in this scenario? | Exploited | Enhanced | Shared | Accepted |  | A | When the most talented resource is assigned to finish the project earlier, the risk management strategy adopted is exploitation. Exploitation seeks to ensure a positive risk (opportunity) is realized. By assigning the best resource, the organization actively takes advantage of the opportunity for early completion. Enhancement (B) increases the probability or impact of an opportunity but does not guarantee realization. Sharing (C) transfers the opportunity to a third party. Acceptance (D) takes no active steps. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 고객이 시장에 새 제품을 출시하려 하고 애자일 팀이 9개월간 프로젝트에 투입되었다. 가장 재능 있는 자원이 프로젝트를 더 빨리 끝내도록 배정되었다. 이것은 어떤 리스크 관리 전략인가? | 활용(Exploited) | 강화(Enhanced) | 공유(Shared) | 수용(Accepted) |  | A | 가장 재능 있는 자원이 프로젝트를 더 빨리 끝내도록 배정될 때, 이것은 활용(Exploitation) 전략이다. 활용은 긍정적 리스크(기회)가 실현되도록 보장하는 전략이다. 강화(B)는 기회의 확률/영향을 높이는 것이다. 공유(C)는 제3자에게 소유권을 이전하는 것이다. 수용(D)은 조치를 취하지 않는 것이다.
1860 | A project has a very tight delivery schedule. The project is approaching the delivery date, and the project sponsor often sends the project manager alerts to avoid any schedule slippage. The project team has performed at an acceptable level until now, but the project manager wants to ensure that the team's performance level is maintained until the end. What action should the project manager take to motivate the project team's performance? | Award certificates of appreciation to encourage the team | Inform the team about the delivery pressure from the project sponsor | Hire a few temporary team members to help with the additional work. | Send a formal notice to team members instructing them to maintain performance |  | A | When a project team has performed acceptably but the PM needs to maintain performance through a tight delivery schedule, the project manager should award certificates of appreciation to encourage the team. Recognition and rewards boost morale and reinforce positive performance without adding pressure. Informing the team about sponsor pressure (B) increases stress. Sending a formal notice instructing performance maintenance (D) feels threatening. Hiring temporary team members (C) introduces new risks near the deadline. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Risk & Issue Management | People | Help Ensure Knowledge Transfer | Risk | Executing | Be an Accountable Leader | Implement Risk Responses | Traditional PM | 프로젝트 일정이 매우 빡빡하다. 납기일이 다가오고 스폰서가 자주 확인한다. 팀 성과가 수용 가능하다. PM은 무엇을 해야 하는가? | 팀을 격려하기 위해 감사 인증서를 수여한다 | 스폰서의 납품 압력에 대해 팀에게 알린다 | 추가 작업을 돕기 위해 임시 팀원을 몇 명 고용한다 | 성과를 유지하도록 팀원에게 공식 통지를 보낸다 |  | A | 빡빡한 일정에서 팀 성과를 유지해야 할 때, PM은 감사 인증서를 수여하여 팀을 격려해야 한다. 인정이 동기를 유지한다. 압력 알림(B)은 스트레스를 증가시킨다. 임시 팀원(C)은 통합 시간이 필요하다. 공식 통지(D)는 위협적이다.
1861 | A project manager is leading a software development project. Recently, team members have complained that during the last few daily standup meetings, a key stakeholder frequently interrupts, requests explanations, and proposes unplanned changes. This issue is frustrating the project team and slowing down the work. What should the project manager do? | Add more team members to make up for any project delays. | Escalate the situation to upper management. | Instruct the team to work as planned and Ignore the stakeholder ' s requests. | Address the issue with the stakeholder and explain the situation. |  | D | When a key stakeholder disrupts daily standups with interruptions, explanations, and unplanned changes, the project manager should address the issue with the stakeholder and explain the situation. Direct communication establishes appropriate meeting boundaries. Adding team members (A) does not address the disruption. Escalating to upper management (B) is premature. Ignoring the stakeholder (C) does not resolve the issue. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 소프트웨어 개발 프로젝트를 이끌고 있다. 주요 이해관계자가 데일리 스탠드업에서 중단, 설명, 비계획 변경으로 방해하고 있다. PM은 무엇을 해야 하는가? | 프로젝트 지연을 만회하기 위해 더 많은 팀원을 추가한다 | 상위 경영진에게 상황을 에스컬레이션한다 | 팀에게 계획대로 작업하고 이해관계자의 요청을 무시하도록 지시한다 | 이해관계자와 이슈를 다루고 상황을 설명한다 |  | D | 주요 이해관계자가 데일리 스탠드업에서 방해할 때, PM은 이해관계자와 직접 이슈를 다루고 상황을 설명해야 한다. 직접적 소통이 경계를 설정하고 관계를 유지한다. 팀원 추가(A)는 근본 문제를 해결하지 않는다. 에스컬레이션(B)은 직접 대화 전에 성급하다. 무시 지시(C)는 관계를 손상시킨다.
1862 | A project manager is assigned to a critical software development project. The team is using a hybrid approach and has divided development into four sprints. At the end of sprint three, the project manager discovers that the earned value (EV) is US$500,000 and the planned value (PV) is US$550,000. What should the project manager do? | Fast track the project. | Adjust the budget. | Adjust the project time line. | Introduce a float. |  | A | When EV ($500,000) is less than PV ($550,000) at the end of sprint three in a hybrid project, the project is behind schedule. The project manager should fast track the project by performing sequential activities in parallel to compress the schedule. Adjusting the budget (B) addresses cost, not schedule. Adjusting the timeline (C) accepts the delay. Introducing float (D) does not accelerate delivery. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Finance | Planning | Focus on Value | Plan Finance Management | Hybrid/Tailoring | PM이 하이브리드 접근의 중요 소프트웨어 개발 프로젝트에 배정되었다. 스프린트 3 종료 시 EV=500K, PV=550K이다. PM은 무엇을 해야 하는가? | 프로젝트를 빠른 추적한다 | 예산을 조정한다 | 프로젝트 일정을 조정한다 | 여유 시간을 도입한다 |  | A | EV(500K)가 PV(550K)보다 적으면 프로젝트가 일정보다 뒤처져 있다. PM은 프로젝트를 빠른 추적(Fast Track)하여 순차 활동을 병렬로 수행해야 한다. 빠른 추적이 일정을 만회한다. 예산 조정(B)은 일정 문제가 아니다. 일정 조정(C)은 수동적이다. 여유 시간(D)은 이미 뒤처진 상태에서는 부족하다.
1863 | To limit the amount of time and cost of using a contract programming firm, a product manager announces that the developers will not be paid for unrequested embellishments to the product. What should the development team and scrum master do to ensure they are paid for all their work? | Have the product manager work with the scrum master to assign specialists to user stories to meet the requirement. | Refine the definition of done (DoD) for user stories to ensure that part of the completion is a verification review of the code. | Ensure that the task board is used as an information radiator and all stories have enough detail to build the required feature or function. | Convert the story points on user stories to hours to provide estimates of the potential costs to the product manager. |  | C | The correct answer is C. Ensure that the task board is used as an information radiator and all stories have enough detail to build the required feature or function. Agile practices emphasize iterative delivery, team empowerment, and continuous improvement. The PM should facilitate collaboration, remove impediments, and ensure the team can deliver value effectively. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Procurement | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 제품 관리자가 계약 프로그래밍 회사의 시간과 비용을 제한하기 위해 개발자가 사용자 스토리를 건너뛰어 마감일을 맞추도록 해야 한다고 발표했다. PM은 무엇을 해야 하는가? | 제품 관리자가 스크럼 마스터와 협력하여 전문가를 사용자 스토리에 배정하게 한다 | 사용자 스토리의 완료 정의(DoD)를 수정하여 완료의 일부가 검증이 되도록 한다 | 작업 보드가 정보 방열기로 사용되고 모든 스토리에 충분한 세부사항이 있도록 한다 | 사용자 스토리의 스토리 포인트를 시간으로 변환하여 잠재적 비용 추정을 제공한다 |  | C | 정답은 C이다. 작업 보드가 정보 방열기로 사용되고 모든 스토리에 필요한 기능을 구축할 충분한 세부사항이 있도록 한다. 애자일 관행은 반복적 가치 전달과 투명성을 강조한다. 스토리 건너뛰기보다 가시성과 상세화가 우선이다. 전문가 배정(A)은 스크럼 마스터 역할이 아니다. DoD 수정(B)은 품질을 타협한다. 포인트→시간 변환(D)은 애자일 원칙에 반한다.
1864 | A project is almost completed, and both the sponsor and the project management office (PMO) are happy with the project manager's performance reviews. The project manager is under budget and ahead of schedule. However, a team member asks to add a feature to the product that will make the product more impressive and acceptable to the end users. What should the project manager do first? | Reject the feature. | Submit a change request! for the feature. | Accept the feature. | Determine if the feature is within the scope. |  | D | When a team member requests adding a feature that would make the product more impressive while the project is near completion and on track, the project manager should first determine if the feature is within the scope. Scope verification prevents unauthorized changes. Rejecting outright (A) may miss valid scope items. Submitting a change request (B) is premature before scope assessment. Accepting the feature (C) bypasses change control. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트가 거의 완료되었고 스폰서와 PMO가 만족한다. 팀원이 제품을 더 인상적으로 만들 기능 추가를 요청한다. PM은 무엇을 먼저 해야 하는가? | 기능을 거부한다 | 기능에 대한 변경 요청을 제출한다 | 기능을 수락한다 | 기능이 범위 내인지 결정한다 |  | D | 팀원이 프로젝트 종료 시 기능 추가를 요청할 때, PM은 먼저 기능이 범위 내인지 결정해야 한다. 범위 확인이 적절한 첫 단계이다. 거부(A)는 검토 없이 성급하다. 변경 요청(B)은 범위 확인 후에 한다. 수락(C)은 범위 확인 없이 부적절하다.
1865 | A project team has difficulty understanding the relationship between functional requirements and their associated benefit to the business stakeholders. How should the project manager improve the team's understanding? | Involve team members in stakeholder analysis and engagement. | Engage with the project sponsor and ensure the product backlog is correct and up to date. | Ensure team members have access to a well-written requirements traceability matrix. | Invite all stakeholders to progress meetings to avoid ambiguity. |  | C | When the team has difficulty understanding the relationship between functional requirements and their business benefits, the project manager should ensure team members have access to a well-written requirements traceability matrix. The RTM explicitly connects requirements to business needs, stakeholder goals, and objectives. Involving team members in stakeholder analysis (A) is helpful but indirect. Engaging the sponsor for backlog updates (B) addresses content but not traceability. Inviting stakeholders to progress meetings (D) provides exposure but not structured understanding. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 기능 요구사항과 관련 비즈니스 혜택 간의 관계를 이해하는 데 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 이해관계자 분석과 참여에 팀원을 참여시킨다 | 프로젝트 스폰서와 참여하여 제품 백로그가 정확하고 최신인지 확인한다 | 팀원에게 잘 작성된 요구사항 추적 매트릭스에 대한 접근을 보장한다 | 모호성을 피하기 위해 모든 이해관계자를 진행 회의에 초대한다 |  | C | 팀이 기능 요구사항과 비즈니스 혜택 간 관계를 이해하기 어려울 때, PM은 잘 작성된 요구사항 추적 매트릭스(RTM)에 대한 접근을 보장해야 한다. RTM이 요구사항을 비즈니스 목표와 연결한다. 이해관계자 분석(A)은 관계 이해가 아니다. 백로그 확인(B)은 부분적이다. 모든 이해관계자 초대(D)는 비효율적이다.
1866 | A team member who is working on a critical project deliverable reported that their computer is not working. The IT department says that due to a high workload, they will not be able to provide assistance for 1 week. How should the project manager address this situation? | Ask the team member to find an innovative solution or workaround to overcome the issue and avoid project delays. | Explore options with the IT department to expedite the necessary repairs based on criticality of the project. | Schedule a meeting with the project sponsor to request a budget to buy or rent a new computer. | Use project reserves to buy new equipment to avoid an impact to the critical path of the project. |  | B | When a team member's computer fails and IT cannot help for a week while a critical deliverable is at risk, the project manager should explore options with IT to expedite repairs based on project criticality. Negotiating priority based on impact is proactive. Asking the team member to find a workaround (A) shifts responsibility. Meeting with the sponsor for budget (C) delays action. Using project reserves for new equipment (D) may be excessive before exploring repair options. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Schedule | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 핵심 인도물 작업 중인 팀원의 컴퓨터가 고장났다. IT 부서가 1주일 후에나 도울 수 있다고 한다. PM은 무엇을 해야 하는가? | 팀원에게 혁신적 해결책이나 우회 방법을 찾아 프로젝트 지연을 방지하도록 요청한다 | 프로젝트 중요도에 따라 IT 부서와 수리를 신속히 처리할 옵션을 탐색한다 | 프로젝트 스폰서와 회의를 일정하여 새 컴퓨터 구매 또는 임대 예산을 요청한다 | 프로젝트 예비비를 사용하여 새 장비를 구매하여 주공정선에 영향을 방지한다 |  | B | 팀원의 컴퓨터가 고장나고 IT 부서가 1주일 후에나 도울 수 있을 때, PM은 프로젝트 중요도에 따라 IT 부서와 수리를 신속히 처리할 옵션을 탐색해야 한다. 기존 자원 활용이 비용 효율적이다. 우회 방법 요청(A)은 팀원에게 부담을 전가한다. 예산 요청(C)은 시간이 걸린다. 예비비 사용(D)은 과도한 조치이다.
1867 | A project to develop a new service is initiated by a telecommunications operator. The project management plan was developed, approved, and shared with the respective stakeholders. What should the project manager do next? | Incorporate the project ' s scope baseline in the scope statement. | Define deliverables, activities, and scheduling information. | Estimate activity durations and list resource requirements. | Start execution of the work packages according to the plan. |  | D | After the project management plan is developed, approved, and communicated, the next step is directing and managing project work—executing the defined work and producing deliverables. This includes coordinating resources, managing stakeholder engagement, implementing quality activities, and generating work performance data. Options involving scope definition, schedule estimation, or baseline incorporation are planning activities that should already be complete before plan approval. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 통신 사업자가 새 서비스 개발 프로젝트를 시작했다. 프로젝트 관리 계획이 개발, 승인, 전달되었다. 다음 단계는 무엇인가? | 프로젝트 범위 기준선을 범위 기술서에 포함한다 | 인도물, 활동, 일정 정보를 정의한다 | 활동 기간을 추정하고 자원 요구사항을 나열한다 | 계획에 따라 작업 패키지의 실행을 시작한다 |  | D | 프로젝트 관리 계획이 개발, 승인, 전달된 후 다음 단계는 정의된 작업을 실행하고 인도물을 생산하는 프로젝트 작업 지시 및 관리이다. 범위 기준선(A), 인도물 정의(B), 기간 추정(C)은 계획 단계 활동으로 이미 완료되었다.
1868 | A project team is working on a critical release and the customer wants this feature to be made available as early as possible. The business owner suggests an enhancement during the product demo. How should the project manager address this request? | Support value-based delivery that is aligned with the project objectives. | Estimate the additional funding needed and seek the client ' s approval. | Follow the project change control process to formalize the change. | Determine the additional funding needed and seek the sponsor ' s guidance. |  | A | When the business owner suggests an enhancement during a product demo for a critical release, the project manager should support value-based delivery aligned with project objectives. Evaluating whether the change delivers value and integrating it through backlog prioritization follows agile principles. Estimating additional funding and seeking client approval (B) focuses on cost before value. Following formal change control (C) may be appropriate in predictive but not agile context. Determining funding and seeking sponsor guidance (D) is process-heavy. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Hybrid/Tailoring | 팀이 중요 릴리스 작업 중이고 고객이 가능한 빨리 이 기능을 원한다. 제품 데모 중 비즈니스 오너가 개선을 제안한다. PM은 무엇을 해야 하는가? | 프로젝트 목표에 맞는 가치 기반 납품을 지원한다 | 추가 자금 필요를 추정하고 고객 승인을 구한다 | 프로젝트 변경 통제 프로세스를 따라 변경을 공식화한다 | 추가 자금 필요를 결정하고 스폰서의 지침을 구한다 |  | A | 중요 릴리스의 제품 데모 중 비즈니스 오너가 개선을 제안할 때, PM은 프로젝트 목표에 맞는 가치 기반 납품을 지원해야 한다. 개선이 목표에 부합하는지 평가하는 것이 우선이다. 추가 자금(B)은 가치 평가 전에 성급하다. 변경 통제(C)는 가치 평가 후에 한다. 스폰서 지침(D)도 가치 평가 후에 한다.
1869 | During the team's daily meetings, the project manager notices that some team members are consistently experiencing blockers due to communication issues and misunderstanding process directions. How should the project manager proceed in this situation? | Take the current velocity into account for the next iteration planning. | Hold coaching sessions to further educate these team members. | Request that these team members improve their performance. | Instruct the team members on how to remove project obstacles. |  | B | When team members consistently experience blockers due to communication issues and process misunderstandings, the project manager should hold coaching sessions to further educate them. Coaching addresses the root cause by building understanding of processes and improving communication skills, aligning with servant leadership and sustainable team development. Taking velocity into account for planning (A) addresses forecasting but not the root cause of confusion. Requesting performance improvement (C) is punitive and does not reflect servant leadership. Instructing team members on obstacle removal (D) may solve symptoms temporarily but does not build lasting understanding or competence. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Integrate Sustainability | Acquire Resources | Sustainability | PM이 데일리 미팅에서 일부 팀원이 커뮤니케이션 문제와 프로세스 오해로 지속적으로 장애물을 겪고 있음을 발견했다. PM은 무엇을 해야 하는가? | 다음 이터레이션 계획에 현재 속도를 고려한다 | 이러한 팀원을 더 교육하기 위한 코칭 세션을 개최한다 | 이러한 팀원에게 성과를 개선하도록 요청한다 | 팀원에게 프로젝트 장애물을 제거하는 방법을 지시한다 |  | B | 팀원이 커뮤니케이션 문제와 프로세스 오해로 장애물을 겪을 때, PM은 코칭 세션을 개최하여 더 교육해야 한다. 코칭이 기술 격차를 해소하고 자기 해결 능력을 키운다. 속도 고려(A)는 문제를 수용하는 것이다. 성과 개선 요청(C)은 방법을 제공하지 않는다. 지시(D)는 자기주도성을 약화시킨다.
1870 | During a project's stakeholder identification stage, team members are struggling to identify the level of influence for two stakeholders. One is considered important, while the second is not quite as important as the first one. For this project, stakeholder engagement is a critical activity. What should the project manager do? | Consider both of them to be important stakeholders. | Call a meeting with the project team to decide. | Conduct an evaluation on both stakeholders. | Move forward due to time constraints. |  | C | The correct answer is C. Conduct an evaluation on both stakeholders. 227. Effective stakeholder management requires proactive engagement, understanding their needs, and maintaining transparent communication. The PM should address stakeholder concerns early and ensure alignment with project objectives. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 이해관계자 식별 단계에서 팀원들이 두 이해관계자의 영향력 수준을 식별하는 데 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 둘 다 중요한 이해관계자로 간주한다 | 프로젝트 팀과 회의를 소집하여 결정한다 | 두 이해관계자 모두에 대해 평가를 실시한다 | 시간 제약으로 인해 앞으로 진행한다 |  | C | 정답은 C이다. 두 이해관계자 모두에 대해 평가를 실시한다. 효과적인 이해관계자 관리는 사전적 참여, 요구 이해, 투명한 커뮤니케이션 유지가 필요하다. 평가가 객관적 데이터를 제공한다. 모두 중요하다고 간주(A)는 차별화가 없다. 팀 회의(B)는 평가 없는 주관적 결정이다. 진행(D)은 리스크를 무시한다.
1871 | A few new team members working on a public housing project are unfamiliar with the system. They do not understand how to evaluate residents applying for a subsidy to build a house, including the rules and criteria for applicant approval. What should the project manager do? | Work only with the team members familiar with the system | Document which rules and criteria the new team members are not familiar wit | Communicate the rules and criteria to the team members through email. | Plan a training session for the new team members not familiar with the system. |  | D | The correct answer is D. Plan a training session for the new team members not familiar with the system. Effective resource management ensures team members have the necessary competencies and support. The PM should identify gaps and address them through training, coaching, or mentoring. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 공공 주택 프로젝트의 새 팀원들이 시스템에 익숙하지 않다. 규칙과 기준을 이해하지 못한다. PM은 무엇을 해야 하는가? | 시스템에 익숙한 팀원만으로 작업한다 | 새 팀원이 익숙하지 않은 규칙과 기준을 문서화한다 | 이메일로 팀원에게 규칙과 기준을 전달한다 | 시스템에 익숙하지 않은 새 팀원을 위한 교육 세션을 계획한다 |  | D | 정답은 D이다. 시스템에 익숙하지 않은 새 팀원을 위한 교육 세션을 계획한다. 효과적인 자원 관리는 팀원이 필요한 역량과 지원을 갖추도록 보장한다. 교육이 가장 직접적인 역량 구축 방법이다. 익숙한 팀원만(A)은 새 팀원을 배제한다. 문서화(B)는 교육이 아니다. 이메일(C)은 상호작용이 부족하다.
1872 | An agile facilitator has gathered a team for a new project. This team and facilitator have not yet worked on a project together. How should the facilitator proceed? | Set up a lessons learned session from a similar project. | Conduct a product roadmap session with the team. | Hold a team charter discussion. | Schedule a release planning session. |  | B | When an agile facilitator gathers a new team they have not worked with before, the facilitator should conduct a product roadmap session with the team. A roadmap session builds shared vision and direction. A lessons learned session from similar projects (A) provides history but not team alignment. A team charter discussion (C) is valuable but secondary to understanding the product. A release planning session (D) is premature without a roadmap. | People | Define Team Ground Rules | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 애자일 퍼실리테이터가 새 프로젝트를 위해 팀을 모았다. 이 팀과 퍼실리테이터는 함께 일한 적이 없다. 퍼실리테이터는 무엇을 먼저 해야 하는가? | 유사 프로젝트의 교훈 세션을 설정한다 | 팀과 제품 로드맵 세션을 수행한다 | 팀 헌장 토론을 개최한다 | 릴리스 계획 세션을 일정한다 |  | B | 애자일 퍼실리테이터가 처음 일하는 팀을 모았을 때, 팀과 제품 로드맵 세션을 수행해야 한다. 로드맵 세션이 공유 비전과 방향을 구축한다. 교훈 세션(A)은 이전 프로젝트에 초점이다. 팀 헌장(C)은 유용하지만 비전 구축이 우선이다. 릴리스 계획(D)은 로드맵 후에 한다.
1873 | A new project manager has been assigned to a recently approved project. The project has a multimillion-dollar budget and will require the purchase of expensive pieces of equipment. The project manager is aware that some purchasing amounts require higher levels of approval. What should the project manager do to properly manage the purchase of equipment? | Ask the organization to allow the project manager to approve all of the purchases. | Agree on a purchasing approval escalation method according to organizational 968 governance. | Propose that the project sponsor approve all of the pieces of equipment that need to be purchased. | Replace the most expensive pieces of equipment with cheaper ones to allow easier purchase approval. |  | B | When a new project manager needs to manage expensive equipment purchases requiring higher approval levels, they should agree on a purchasing approval escalation method according to organizational governance. Proper escalation ensures compliance. Asking for personal approval authority (A) bypasses governance. Proposing sponsor approval for all purchases (C) may not align with organizational thresholds. Replacing equipment with cheaper alternatives (D) compromises project needs. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 새 PM이 최근 승인된 프로젝트에 배정되었다. 수백만 달러 예산이며 더 높은 승인 수준이 필요한 고가 장비 구매가 있다. PM은 무엇을 해야 하는가? | 조직에 PM이 모든 구매를 승인하도록 허용해 달라고 요청한다 | 조직 거버넌스에 따른 구매 승인 에스컬레이션 방법에 합의한다 | 프로젝트 스폰서가 구매해야 할 모든 장비를 승인하도록 제안한다 | 더 쉬운 구매 승인을 위해 가장 비싼 장비를 더 저렴한 것으로 교체한다 |  | B | 고가 장비 구매에 더 높은 승인이 필요할 때, PM은 조직 거버넌스에 따른 구매 승인 에스컬레이션 방법에 합의해야 한다. 구조화된 승인 프로세스가 거버넌스를 준수한다. PM 전체 승인(A)은 거버넌스를 무시한다. 스폰서 전체 승인(C)은 비효율적이다. 저가 교체(D)는 프로젝트 요구를 무시한다.
1874 | A project manager has taken over a project that has been without a project manager for the last couple of weeks. The team is feeling lost and there are a few team members who are confused about the next steps and the final outcome of the project. What should the new project manager do? | Escalate the situation to the steering committee and request that more time be allotted to the project. | Set short-term goals in order to create a winning culture internally and praise team members for achieving them. | Avoid conflict and let the team self-organize on how they want to work on the project tasks. | Ask the project sponsor to provide team members with a project direction regarding outcomes. |  | B | When taking over a project that has lacked leadership, the new project manager should set short-term goals to create a winning culture and praise team members for achieving them. Immediate, clear goals provide direction and rebuild momentum and morale. Escalating to the steering committee for more time (A) delays action. Avoiding conflict and letting the team self-organize (C) provides no leadership. Asking the sponsor to provide direction (D) delegates the PM's responsibility. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | PM이 몇 주간 PM이 없었던 프로젝트를 인수했다. 팀이 목표를 잃고 프로젝트 완료에 관심이 없다. PM은 무엇을 해야 하는가? | 운영위원회에 상황을 에스컬레이션하고 더 많은 시간을 요청한다 | 단기 목표를 설정하여 승리 문화를 만들고 달성한 팀원을 칭찬한다 | 갈등을 피하고 팀이 자체 조직화하여 작업하도록 한다 | 프로젝트 스폰서에게 결과에 관한 프로젝트 방향을 팀원에게 제공하도록 요청한다 |  | B | 리더십이 부재했던 프로젝트를 인수할 때, PM은 단기 목표를 설정하여 승리 문화를 만들고 팀원을 칭찬해야 한다. 즉각적이고 명확한 목표가 모멘텀을 회복한다. 에스컬레이션(A)은 리더십 부재 문제를 해결하지 않는다. 자체 조직화(C)는 방향이 없는 팀에 부적절하다. 스폰서 방향(D)은 간접적이다.
1875 | A project manager is managing a hybrid project. A stakeholder has directly contacted a team member and has requested a change. Due to the request, the team member was distracted from their work, which caused a loss in productivity. What should the team member do? | Inform the scrum master so that the change can be discussed directly with the stakeholder. | Inform the scrum master regarding the stakeholder ' s request for a change and the impact this has had on productivity. | Inform the stakeholder that the correct procedure for new requirements is to provide it directly to the change control board (CCB). | Inform the stakeholder that the correct procedure for new requirements is to provide it directly to the project manager. |  | D | When a stakeholder directly contacts a team member to request a change in a hybrid project, causing productivity loss, the team member should inform the stakeholder that the correct procedure is to provide new requirements directly to the project manager. The PM evaluates change impact and maintains scope control. Informing the scrum master (A) redirects but bypasses the PM's authority. Informing the scrum master about the productivity impact (B) is reporting, not redirecting. Directing the stakeholder to the CCB (C) is too formal for an initial redirect. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 하이브리드 프로젝트를 관리 중이다. 이해관계자가 직접 팀원에게 연락하여 변경을 요청했고 생산성이 떨어졌다. 팀원은 무엇을 해야 하는가? | 스크럼 마스터에게 알려 이해관계자와 직접 변경을 논의하도록 한다 | 스크럼 마스터에게 이해관계자의 변경 요청과 생산성 영향을 알린다 | 이해관계자에게 새 요구사항의 올바른 절차는 스크럼 마스터에게 직접 제공하는 것이라고 알린다 | 이해관계자에게 새 요구사항의 올바른 절차는 제품 책임자에게 직접 제공하는 것이라고 알린다 |  | D | 하이브리드 프로젝트에서 이해관계자가 팀원에게 직접 변경을 요청할 때, 팀원은 이해관계자에게 올바른 절차는 제품 책임자에게 직접 제공하는 것이라고 알려야 한다. 제품 책임자가 백로그와 요구사항 우선순위를 관리한다. 스크럼 마스터 논의(A)는 역할이 맞지 않는다. 영향 알림(B)은 내부적이다. 스크럼 마스터에게 제공(C)은 올바른 채널이 아니다.
1876 | The project team members have finalized the technical specifications after their discussion with the machine manufacturers. However, it has been identified that the specifications are not aligned with the project management office (PMO). The project team members are confident about their choice of specifications. What should the project manager do in this situation? | Schedule a meeting with all of the subject matter experts (SMEs) to discuss. | Request a decision from the project sponsor. | Give approval of the technical specifications. | Ask the sponsor for additional funding to hire a senior subject matter expert (SME). |  | A | When technical specifications are not aligned with the PMO's standards despite the project team's confidence in their choices, the project manager should schedule a meeting with all relevant subject matter experts to discuss the disagreement collaboratively. This ensures alignment between technical validity and organizational compliance. Requesting a sponsor decision (B) escalates prematurely. Approving the specifications unilaterally (C) bypasses PMO governance. Asking for additional funding for a senior SME (D) assumes external help is needed before attempting internal resolution. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀이 기계 제조업체와 논의 후 기술 사양을 완성했다. 그러나 PMO의 표준과 맞지 않는다. PM은 무엇을 해야 하는가? | 모든 관련 주제전문가(SME)와 회의를 일정하여 논의한다 | 프로젝트 스폰서에게 결정을 요청한다 | 기술 사양을 승인한다 | 스폰서에게 선임 SME 채용을 위한 추가 자금을 요청한다 |  | A | 기술 사양이 PMO 표준과 맞지 않을 때, PM은 모든 관련 주제전문가와 회의를 일정하여 논의해야 한다. 전문가 검토가 표준 준수와 기술적 적합성을 보장한다. 스폰서 결정(B)은 기술적 판단이 아니다. 승인(C)은 표준 불일치를 무시한다. 추가 자금(D)은 필요 이상이다.
1877 | A project manager has recently been assigned to a construction project. The project has hundreds of stakeholders and three stages. The project manager recognizes that many steps have already been started, including risk identification. The project sponsor asks the project manager to rank the risks contained in the register. How should the project manager respond to the request? | Inform that a quantitative risk prioritization was completed using Monte Carlo simulation. | Execute a qualitative analysis to provide identified risks prioritization. | Inform that a qualitative analysis has already been completed. | Perform a quantitative analysis to provide identified risks prioritization. |  | B | When asked to rank risks in the register on a construction project where risk identification has started, the project manager should execute a qualitative analysis to prioritize identified risks. Qualitative analysis assesses probability and impact to produce a ranked list. Claiming Monte Carlo was done (A) lacks evidence. Saying qualitative analysis was already done (C) assumes without verification. Quantitative analysis (D) requires more data and is a secondary step. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | PM이 최근 건설 프로젝트에 배정되었다. 수백 명의 이해관계자가 있고 리스크 식별이 시작되었다. 리스크 등록부의 리스크 순위를 매기라는 요청을 받았다. PM은 무엇을 해야 하는가? | 몬테카를로 시뮬레이션을 사용한 정량적 리스크 우선순위가 완료되었음을 알린다 | 식별된 리스크 우선순위를 위한 정성적 분석을 실행한다 | 정성적 분석이 이미 완료되었음을 알린다 | 식별된 리스크 우선순위를 위한 정량적 분석을 수행한다 |  | B | 리스크 식별이 시작된 건설 프로젝트에서 리스크 순위를 매기라는 요청을 받으면, PM은 정성적 분석을 실행하여 식별된 리스크의 우선순위를 정해야 한다. 정성적 분석이 확률과 영향에 기반한 우선순위의 첫 단계이다. 정량적 분석(A,D)은 정성적 분석 후에 수행한다. 이미 완료(C)는 사실과 다르다.
1878 | As part of planning activities for a new project, the project manager must develop a budget that encompasses the full project scope. What should the project manager do to build the project budget? | Reference the work breakdown structure (WBS) and project schedule to estimate costs associated with each WBS element. | Schedule a working session with the project sponsor to review the project charter and estimate the cost per project phase. | Review historical project files and lessons learned to identify a similar project and adapt the budget used in the historical project. | Ask key project stakeholders to estimate the cost of delivering the project, then calculate an average that can be used for the budget. |  | A | When developing a budget encompassing the full project scope, the project manager should reference the WBS and project schedule to estimate costs associated with each WBS element. Bottom-up estimation from the WBS ensures completeness. Reviewing the charter with the sponsor (B) is too high-level. Reviewing historical projects (C) provides reference but not specific estimates. Asking stakeholders to estimate and averaging (D) is unreliable. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | WBS/Decomposition | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 새 프로젝트의 계획 활동 중 PM이 전체 프로젝트 범위를 포함하는 예산을 개발해야 한다. PM은 무엇을 먼저 해야 하는가? | WBS와 프로젝트 일정을 참조하여 각 WBS 요소의 관련 비용을 추정한다 | 프로젝트 스폰서와 작업 세션을 일정하여 프로젝트 헌장을 검토하고 비용을 추정한다 | 유사 프로젝트를 식별하기 위해 과거 프로젝트 파일과 교훈을 검토하고 예산을 조정한다 | 주요 이해관계자에게 프로젝트 납품 비용을 추정하도록 요청하고 평균을 계산한다 |  | A | 전체 프로젝트 범위를 포함하는 예산을 개발할 때, PM은 WBS와 프로젝트 일정을 참조하여 각 WBS 요소의 관련 비용을 추정해야 한다. 상향식 추정이 가장 정확한 비용 추정을 제공한다. 헌장 기반(B)은 상위 수준이다. 유사 프로젝트(C)는 유추 추정으로 덜 정확하다. 이해관계자 추정(D)은 일관성이 부족하다.
1879 | A project team consisting of 13 people was set up three months ago. As part of the transition to agile, a scrum master was assigned to the project. The scrum master wants to know the status of the team's development stage. The project manager believes that the team has passed the "storming" stage. Which indicators should be used to determine the team's development stage? | Project deliverables are formally approved. | Scrum ceremonies are held per the Scrum guide. | Formal training courses have been completed by team members. | Team members share information and experiences. |  | D | In agile environments, team members should share information and experiences openly to foster continuous learning and improvement. The PM facilitates team collaboration, removes impediments, and ensures continuous value delivery while respecting agile principles and established ceremonies. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | 13명의 프로젝트 팀이 3개월 전에 구성되었다. 애자일 전환의 일환으로 스크럼 마스터가 배정되었다. 팀이 애자일을 잘 채택했음을 나타내는 징후는? | 프로젝트 인도물이 공식적으로 승인되었다 | 스크럼 가이드에 따라 스크럼 행사가 실시되고 있다 | 팀원이 공식 교육 과정을 완료했다 | 팀원이 정보와 경험을 공유하고 있다 |  | D | 애자일 환경에서 팀원이 정보와 경험을 공개적으로 공유하는 것이 지속적 학습과 개선을 촉진한다. 이것이 진정한 애자일 채택의 징후이다. 공식 승인(A)은 예측형 접근이다. 스크럼 행사(B)는 형식적 준수이다. 공식 교육(C)은 학습이지 채택이 아니다.
1880 | While a project manager is trying to build the first baseline for a project, a change request is being sent from one of the functional managers. What should the project manager do? | Reject the functional manager ' s change request immediately. | Apply for a formal change control board (CCB) approval. | Analyze the impact of the change request on the project. | Discuss this with the functional manager and related parties. |  | C | When a change request arrives while building the first project baseline, the project manager should analyze the impact of the change request on the project. Impact analysis must precede any decision on acceptance or rejection. Rejecting immediately (A) ignores potential value. Applying for CCB approval (B) is premature without analysis. Discussing with the functional manager (D) is useful but secondary to formal impact analysis. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Baseline & Change Control | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | PM이 프로젝트의 첫 기준선을 구축하려는 중에 기능 관리자로부터 변경 요청이 전달되었다. PM은 무엇을 먼저 해야 하는가? | 기능 관리자의 변경 요청을 즉시 거부한다 | 공식 변경통제위원회(CCB) 승인을 신청한다 | 변경 요청이 프로젝트에 미치는 영향을 분석한다 | 기능 관리자 및 관련 당사자와 논의한다 |  | C | 첫 프로젝트 기준선 구축 중 변경 요청이 도착하면, PM은 먼저 변경 요청이 프로젝트에 미치는 영향을 분석해야 한다. 영향 분석이 모든 결정에 선행해야 한다. 즉시 거부(A)는 분석 없는 결정이다. CCB 승인(B)은 영향 분석 후에 한다. 논의(D)는 영향 분석 후에 한다.
1881 | A few developers have submitted their resignation after completing their annual review and receiving their annual bonus. The project manager cannot find replacements for all of the developers in time to meet the project's deadline. What should the project manager do? | Lower the recruitment criteria. | Analyze the impact and inform the stakeholders. | Log the issue in the issue log. | Request additional budget to recruit more developers. |  | B | When developers resign and replacements cannot be found in time, the project manager should analyze the impact and inform stakeholders. Transparent communication enables collaborative decisions. Lowering recruitment criteria (A) compromises quality. Logging in the issue log (C) is documentation, not communication. Requesting additional budget (D) assumes a solution without impact analysis. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Resources | Planning | Build an Empowered Culture | Plan Resource Management | Traditional PM | 몇몇 개발자가 연간 평가와 보너스를 받은 후 사직서를 제출했다. 대체자를 제때 찾을 수 없다. PM은 무엇을 먼저 해야 하는가? | 채용 기준을 낮춘다 | 영향을 분석하고 이해관계자에게 알린다 | 이슈 로그에 이슈를 기록한다 | 더 많은 개발자 채용을 위한 추가 예산을 요청한다 |  | B | 개발자가 사직하고 대체자를 제때 찾을 수 없을 때, PM은 영향을 분석하고 이해관계자에게 알려야 한다. 투명한 커뮤니케이션이 협력적 결정을 가능하게 한다. 기준 낮추기(A)는 품질을 훼손한다. 이슈 로그(C)는 기록이지 행동이 아니다. 추가 예산(D)은 영향 분석 후에 한다.
1882 | The project manager of an agile project has been asked to reduce the budget by 30%. Since this is a small project team, the budget is primarily allocated to resources. What strategy should the project manager use in order to keep delivering value in a restricted environment? | Balance the project team in order to accommodate the budget challenges, and provide training to mitigate the risk of low performance | Restrict the project scope only to basic critical features and run the project with the current staffing level until all of the budget is consumed | Reduce the project staff and adjust the scope and timelines accordingly in support of the budget reduction. 1053 | Prioritize the product backlog looking for high business value and low effort, and adjust the project budget and staffing to account for those items. |  | D | When asked to reduce the budget by 30% on a small agile project where budget is primarily allocated to resources, the project manager should prioritize the product backlog for high business value and low effort, and adjust budget and staffing accordingly. Value-driven prioritization maximizes ROI under constraints. Balancing the team and providing training (A) adds cost. Reducing staff and adjusting scope (C) may compromise value. Restricting to basic features only (B) ignores customer feedback. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Build an Empowered Culture | Plan Scope Management | Traditional PM | 애자일 프로젝트의 PM이 예산을 30% 줄이라는 요청을 받았다. 소규모 팀이며 예산의 대부분이 자원에 할당되어 있다. PM은 무엇을 해야 하는가? | 팀을 균형 잡아 예산 문제를 수용하고 리스크 완화를 위한 교육을 제공한다 | 프로젝트 범위를 기본 핵심 기능으로만 제한하고 현재 인력으로 프로젝트를 실행한다 | 프로젝트 인력을 줄이고 예산 감소를 지원하기 위해 범위와 일정을 조정한다 | 높은 비즈니스 가치와 낮은 노력의 제품 백로그를 우선순위화하고 프로젝트 일정을 조정한다 |  | D | 애자일 프로젝트에서 예산 30% 감소 요청 시, PM은 높은 비즈니스 가치와 낮은 노력의 제품 백로그를 우선순위화하고 일정을 조정해야 한다. 가치 기반 우선순위가 예산 내 최대 가치를 전달한다. 팀 균형(A)은 모호하다. 범위 제한(B)은 고객 참여 없는 결정이다. 인력 감소(C)는 역량 손실 리스크가 있다.
1883 | A project has a very demanding and sensitive business stakeholder who functions as a subject matter expert (SME). The project manager has assigned two different team members to work with the stakeholder. However, both team members have complained that the stakeholder is difficult to work with. What should the project manager do first? | Escalate the issue to the sponsor and request that they speak with the stakeholder. 1048 | Speak with the team members to collect details and write an email to the stakeholder requesting that they collaborate with the team. | Raise the issue during a steering committee meeting and ask that the stakeholder change their attitude. | Evaluate the situation and look for alternatives to improve communication with the stakeholder. |  | D | When two team members report that a demanding SME stakeholder is difficult to work with, the project manager should first evaluate the situation and look for alternatives to improve communication with the stakeholder. Understanding before acting enables constructive resolution. Escalating to the sponsor (A) bypasses direct resolution. Writing an email requesting collaboration (B) is impersonal. Raising it in a steering committee (C) is confrontational and premature. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Hybrid | Tailored Approach | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 프로젝트에 매우 까다롭고 민감한 비즈니스 이해관계자가 SME로 활동한다. 두 팀원이 이 이해관계자와 일하기 어렵다고 보고한다. PM은 무엇을 먼저 해야 하는가? | 스폰서에게 이슈를 에스컬레이션하고 이해관계자와 대화하도록 요청한다 | 팀원으로부터 세부 사항을 수집하고 이해관계자에게 행동 변경을 요청하는 이메일을 작성한다 | 운영위원회 회의에서 이슈를 제기하고 이해관계자에게 태도 변경을 요청한다 | 상황을 평가하고 이해관계자와의 커뮤니케이션을 개선할 대안을 찾는다 |  | D | 까다로운 SME 이해관계자와 일하기 어렵다는 팀원 보고를 받으면, PM은 먼저 상황을 평가하고 커뮤니케이션 개선 대안을 찾아야 한다. 상황 평가가 적절한 대응의 기초이다. 에스컬레이션(A)은 직접 해결 전에 성급하다. 이메일(B)은 비대면적이다. 위원회 제기(C)는 공개적이고 대립적이다.
1884 | A company is transitioning from a predictive to agile delivery of projects. Based on the requirements, the project team estimates the budget and decides to use a fixed-price contract with its vendor. However, during the execution of the project, the requirements evolve and priorities start to change constantly, which puts the project and the estimate at completion (EAC) off by 40%. What should the project manager do next? | Send a detailed status report highlighting the issue with funding to all of the stakeholders. | Wait until the next gate review meeting to highlight the risk of low funds to the stakeholders. | Submit a change request to the financial manager to increase the funding and continue as is. | Meet with the stakeholders to recommend the use of a time and materials (T & M) contract to address the problem. |  | D | When requirements evolve constantly in an agile project using a fixed-price contract, pushing the EAC off by 40%, the project manager should meet with stakeholders to recommend using a time and materials contract. T&M contracts accommodate changing requirements better. Sending a status report (A) informs but does not solve. Submitting a change request for funding (C) does not address the contract mismatch. Waiting for the gate review (B) delays resolution. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Finance | Planning | Adopt a Holistic View | Plan Finance Management | Traditional PM | 회사가 예측형에서 애자일로 전환 중이다. 요구사항이 계속 변화하며 고정 가격 계약으로 EAC가 40% 초과한다. PM은 무엇을 해야 하는가? | 모든 이해관계자에게 자금 문제를 강조하는 상세 상태 보고서를 보낸다 | 다음 게이트 리뷰 회의까지 기다려 이해관계자에게 낮은 자금 리스크를 강조한다 | 자금을 늘리기 위한 변경 요청을 재무 관리자에게 제출하고 현행대로 계속한다 | 이해관계자와 만나 자금 문제를 해결하기 위한 실비 정산(T&M) 계약 사용을 권장한다 |  | D | 애자일 프로젝트에서 요구사항이 계속 변화하고 고정 가격 계약으로 EAC가 40% 초과할 때, PM은 이해관계자와 만나 실비 정산(T&M) 계약 사용을 권장해야 한다. T&M 계약이 변화하는 요구사항에 적합하다. 상태 보고서(A)는 해결이 아닌 알림이다. 대기(B)는 시간 낭비이다. 자금 증가(C)는 계약 유형 변경 없이 근본 문제를 해결하지 않는다.
1885 | An agile project manager would like to convert the requirements document into epics, capabilities, features, and stories. In how many iterations should the project manager estimate the story duration? | Three iterations | One iteration | Two iterations | Four iterations |  | B | When converting requirements into epics, capabilities, features, and stories for the product backlog, the project manager should estimate story duration in one iteration. One iteration is the timebox for delivering a potentially releasable product increment, and estimating within this timeframe allows proper planning, progress monitoring, and scope adjustment based on feedback. Estimating over three (A), two (C), or four (D) iterations introduces unnecessary uncertainty, as team velocity, requirements, and product quality may change over that period. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Scope | Planning | Focus on Value | Plan Scope Management | Traditional PM | 애자일 PM이 요구사항 문서를 에픽, 기능, 스토리로 변환하려 한다. 스토리 기간을 몇 이터레이션으로 추정해야 하는가? | 3번의 이터레이션 | 1번의 이터레이션 | 2번의 이터레이션 | 4번의 이터레이션 |  | B | 요구사항을 에픽, 기능, 스토리로 변환하여 제품 백로그를 만들 때, 스토리 기간을 1번의 이터레이션으로 추정해야 한다. 1번의 이터레이션이 타임박스 단위이며 작업 단위의 기본 측정 기준이다. 1 이터레이션 이상의 스토리는 추가 분해가 필요하다.
1886 | During project execution, the project manager discovered that a key deliverable was missing from the scope of work. After investigation, the project manager and the team discovered that the missing deliverable will impact the critical path. What should the project manager do to avoid future delays? | Submit a change request. | Review the risk management plan | Update the scope of work. | Add additional resources to the project |  | A | When a key deliverable is discovered missing from the scope and it impacts the critical path, the project manager should submit a change request. This formally proposes the modification through the change control process, ensuring the scope, schedule, and budget are properly analyzed and updated with appropriate authorization. Reviewing the risk management plan (B) identifies potential risks but does not address the missing deliverable. Updating the scope without a change request (C) risks uncontrolled scope creep. Adding resources (D) may not address the root cause and introduces additional risks. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 프로젝트 실행 중 PM이 작업 범위에서 주요 인도물이 누락된 것을 발견했다. 주공정선에 영향을 미친다. PM은 무엇을 해야 하는가? | 변경 요청을 제출한다 | 리스크 관리 계획을 검토한다 | 작업 범위를 업데이트한다 | 프로젝트에 추가 자원을 추가한다 |  | A | 주요 인도물이 범위에서 누락되어 주공정선에 영향을 미칠 때, PM은 변경 요청을 제출해야 한다. 공식적 변경 통제 프로세스를 통해 수정을 제안하는 것이 적절하다. 리스크 관리 계획(B)은 리스크 관련이다. 범위 직접 업데이트(C)는 승인 없이 하면 안 된다. 자원 추가(D)는 범위 문제를 해결하지 않는다.
1887 | An organization is undergoing an agile transformation. The executive leadership team is concerned that they will lose control over the scope of the project. What should the project manager, who is responsible for this project, do to mitigate this risk? | Ensure that the executive leadership team approves all scope that is being proposed by the multiple agile teams to avoid misalignment. | Propose a multilayered gate system based on risks and financial expenditures, involving the executive leadership team as needed. | Assure the executive leadership team that the current governance model will not be affected by the agile approach. | Propose a governance model that empowers the teams while providing the necessary oversight to the executive leadership team. |  | D | When executive leadership fears losing scope control during agile transformation, the project manager should propose a governance model that empowers teams while providing necessary oversight. Balanced governance addresses control concerns while preserving agility. Requiring executive approval of all scope (A) creates bottlenecks. Proposing a multilayered gate system (B) adds bureaucracy. Assuring the current model is unaffected (C) is inaccurate. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 조직이 애자일 전환을 진행 중이다. 경영진이 범위 통제를 잃을까 우려한다. PM은 무엇을 해야 하는가? | 경영진이 여러 팀이 제안하는 모든 범위를 승인하도록 한다 | 리스크와 재정 지출에 기반한 다층 게이트 시스템을 제안하고 경영진을 참여시킨다 | 현재 거버넌스 모델이 애자일 전환에 영향받지 않을 것이라고 경영진에게 보장한다 | 팀에 권한을 부여하면서 경영진에게 필요한 감독을 제공하는 거버넌스 모델을 제안한다 |  | D | 경영진이 애자일 전환 중 범위 통제 상실을 우려할 때, PM은 팀에 권한을 부여하면서 경영진에게 필요한 감독을 제공하는 거버넌스 모델을 제안해야 한다. 균형이 두 요구를 충족한다. 전체 승인(A)은 팀 권한을 제거한다. 다층 게이트(B)는 관료적이다. 영향 없음 보장(C)은 비현실적이다.
1888 | The project manager is planning a project with several legal aspects for the city's municipality. The project is expected to take a year and will require a lot of paperwork since it involves multiple stakeholders, including the city's court. What three actions should the project manager do? (Choose 3) | Leverage the project governance system to track and manage the project artifacts. | Review the execution roadmap and ask the legal team to manage the artifacts. | Ensure the project artifacts are kept up to date and accessible to all stakeholders. | Create a central repository system to assess the effectiveness of the project artifacts. | Work with the team to determine the process to manage the project artifacts. | A, C, E | For a year-long project with many legal aspects and multiple stakeholders including the city's court, the project manager should take three actions: leverage the project governance system to track and manage artifacts, ensure project artifacts are kept up to date and accessible to all stakeholders, and work with the team to determine the artifact management process. Reviewing the roadmap and delegating to legal (B) abdicates responsibility. Creating a central repository for assessment (D) focuses on evaluation over management. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Business Environment | Plan and Manage Compliance | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Traditional PM | PM이 시의 자치단체를 위한 법적 측면이 많은 프로젝트를 계획 중이다. 1년간 프로젝트이며 다수의 이해관계자가 있다. PM은 무엇을 해야 하는가? | 프로젝트 거버넌스 시스템을 활용하여 프로젝트 산출물을 추적하고 관리한다 | 실행 로드맵을 검토하고 법무팀에 산출물 관리를 요청한다 | 프로젝트 산출물이 최신 상태로 유지되고 모든 이해관계자가 접근할 수 있도록 한다 | 중앙 저장소 시스템을 만들어 프로젝트 산출물의 효과성을 평가한다 | 팀과 협력하여 프로젝트 산출물을 관리하는 프로세스를 결정한다 | A, C, E | 법적 측면이 많은 1년 프로젝트에서 PM은 세 가지 조치를 취해야 한다: 프로젝트 거버넌스 시스템을 활용하여 산출물을 추적 관리하고(A), 산출물이 최신이고 접근 가능하도록 하며(C), 팀과 협력하여 관리 프로세스를 결정한다(E). 법무팀에 위임(B)은 PM 책임을 포기한다. 중앙 저장소(D)는 도구이지 관리가 아니다.
1889 | A project manager has been assigned to a project. The project deadline has been established but, based on the number of stakeholders to engage and interview, it will be difficult to complete the project within the timeline. How should the project manager address this challenge? | Request that the product owner define which parties should be engaged first. | Prioritize the engagement of parties who are most impacted to minimize project risk. | Submit a change request to extend the time needed to engage all of the parties. | Commit to completing the deliverables associated with only the engaged parties. |  | B | When the project timeline is tight relative to the number of stakeholders requiring engagement, the project manager should prioritize engagement based on impact and risk. Engaging the most impacted parties first ensures the project captures critical requirements, constraints, and acceptance conditions from those who most influence success or failure. Requesting the product owner to define engagement priorities (A) does not replace the PM's responsibility to analyze and plan stakeholder engagement. Submitting a change request to extend time (C) may eventually be needed but should not be the first action—optimizing engagement within existing constraints comes first. Committing to deliverables only for engaged parties (D) risks missing requirements and leads to poor adoption and stakeholder dissatisfaction. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | PM이 프로젝트에 배정되었다. 마감일이 정해졌지만 참여해야 할 당사자 수에 비해 시간이 부족하다. PM은 무엇을 해야 하는가? | 제품 책임자에게 어떤 당사자를 먼저 참여시켜야 하는지 정의하도록 요청한다 | 프로젝트 리스크를 최소화하기 위해 가장 영향을 많이 받는 당사자의 참여를 우선순위화한다 | 모든 당사자를 참여시키는 데 필요한 시간을 연장하기 위한 변경 요청을 제출한다 | 참여한 당사자와 관련된 인도물만 완료하기로 약속한다 |  | B | 참여해야 할 이해관계자 수에 비해 시간이 부족할 때, PM은 가장 영향을 많이 받는 당사자의 참여를 우선순위화해야 한다. 영향과 리스크에 기반한 참여가 효율적이다. 제품 책임자(A)는 결정권이 아니다. 시간 연장(C)은 마감일이 정해져 있어 어렵다. 일부만 완료(D)는 범위를 축소한다.
1890 | A project manager is leading a virtual team that is geographically dispersed. What should the project manager do to avoid uncertainty in the project due to different cultures? | Start the project and add any uncertainty that arises to the risk register. | Build a culturally neutral team that will not be affected by cultural differences. | Dissolve the virtual team and build a colocated team. | Gather relevant cultural data and engage members in discussions covering their work ethics. |  | A | When leading a geographically dispersed virtual team, the project manager should gather relevant cultural data and engage team members in discussions covering their work ethics. Understanding cultural backgrounds, preferences, and expectations enables the PM to design appropriate communication and management strategies while building trust and mutual understanding. Starting the project and adding uncertainty to the risk register (A) is reactive. Dissolving the virtual team for a colocated one (C) is typically impractical. Building a culturally neutral team (B) ignores the value of diversity and is unrealistic. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | PM이 지리적으로 분산된 가상 팀을 이끌고 있다. 문화적 차이로 인한 불확실성을 피하기 위해 무엇을 해야 하는가? | 프로젝트를 시작하고 발생하는 불확실성을 리스크 등록부에 추가한다 | 문화적 차이에 영향받지 않는 문화적으로 중립적인 팀을 구축한다 | 가상 팀을 해산하고 같은 장소 팀을 구성한다 | 관련 문화 데이터를 수집하고 팀원의 업무 윤리를 다루는 토론에 참여시킨다 |  | A | 지리적으로 분산된 가상 팀에서 문화적 불확실성을 피하려면, PM은 관련 문화 데이터를 수집하고 업무 윤리에 대한 토론에 팀원을 참여시켜야 한다. 문화적 이해가 효과적 협업의 기초이다. 리스크 등록만(A의 다른 해석)은 사전적이 아니다. 중립 팀(B)은 비현실적이다. 같은 장소 팀(C)은 실행 불가능하다.
1891 | A project in aerospace design has run into a substantial technical issue, and the project team is uncertain on how to proceed. With whom should the project manager call a meeting to discuss the issue? | External subject matter experts (SMEs) and the team | Project sponsor and the team | Project sponsor and the external SMEs | Project stakeholders and the team |  | A | When an aerospace project encounters a substantial technical issue and the team is uncertain how to proceed, the project manager should call a meeting with external subject matter experts (SMEs) and the team. External SMEs bring specialized knowledge while the team provides project context—together enabling informed problem-solving. The project sponsor and team (B) may lack technical depth. The sponsor and external SMEs (C) excludes the team's project knowledge. Project stakeholders and team (D) includes too broad a group for a technical discussion. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 항공우주 설계 프로젝트에서 상당한 기술적 문제가 발생했고 팀이 진행 방법을 모른다. PM은 누구와 회의를 소집해야 하는가? | 외부 주제전문가(SME)와 팀 | 프로젝트 스폰서와 팀 | 프로젝트 스폰서와 외부 SME | 프로젝트 이해관계자와 팀 |  | A | 항공우주 프로젝트에서 팀이 진행 방법을 모르는 기술적 문제에 직면할 때, PM은 외부 주제전문가(SME)와 팀과 회의를 소집해야 한다. 외부 SME가 전문 기술 지식을 제공하고 팀과 함께 해결한다. 스폰서(B,C)는 기술적 전문성이 부족하다. 이해관계자(D)는 기술적 해결에 적합하지 않다.
1892 | A company is transitioning projects from a predictive to an agile approach. The CFO is concerned that one of the agile projects has an important feature for the financial department that is being delayed for a later iteration. What should the project manager do to clarify the situation? | Request support from the CEO on how to deal with the situation. | Increase the size of the team in order to match any prior expectations of the CFO. | Create an executive board to review the product backlog and replan the next iterations. | Clarify with the CFO that the prioritization process is based on business value. |  | D | When the CFO is concerned that an important financial feature is delayed to a later iteration in an agile project, the project manager should clarify that the prioritization process is based on business value. Transparency about agile prioritization builds understanding and trust. Requesting CEO support (A) escalates unnecessarily. Increasing team size (B) does not address prioritization concerns. Creating an executive board to review the backlog (C) adds governance overhead. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 회사가 예측형에서 애자일로 전환 중이다. CFO가 중요 재무 기능이 후순위 이터레이션으로 밀려날까 우려한다. PM은 무엇을 해야 하는가? | 상황 처리 방법에 대해 CEO의 지원을 요청한다 | CFO의 기대에 맞추기 위해 팀 규모를 늘린다 | 경영진 위원회를 만들어 제품 백로그를 검토하고 다음 이터레이션을 재계획한다 | CFO에게 우선순위 프로세스가 비즈니스 가치에 기반함을 명확히 한다 |  | D | CFO가 중요 재무 기능이 후순위로 밀릴까 우려할 때, PM은 우선순위 프로세스가 비즈니스 가치에 기반함을 명확히 해야 한다. 프로세스 투명성이 우려를 해소한다. CEO 지원(A)은 불필요한 에스컬레이션이다. 팀 확대(B)는 우선순위 문제와 무관하다. 경영진 위원회(C)는 제품 책임자 역할을 침해한다.
1893 | During project execution, a key stakeholder approaches the project manager and questions the business value of the project. What should the project manager do? | Validate the business value with the stakeholder by ensuring each requirement is still aligned to the business and project objectives. | Inform the stakeholder that the project will still proceed to completion because the project charter has already been approved. | Consult the remainder of the stakeholders and the sponsor to determine if they have the same concern. | Explain to the stakeholder that it is up to the project sponsor and the client to determine if the project still has the perceived business value. |  | A | The correct answer is A. Validate the business value with the stakeholder by ensuring each requirement is still aligned to the business and project objectives. Stakeholder management requires understanding needs, maintaining engagement, and ensuring transparent communication. The PM should proactively address stakeholder concerns and maintain alignment with project goals. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Stakeholder & Communication Mgmt | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Traditional PM | 프로젝트 실행 중 주요 이해관계자가 프로젝트의 비즈니스 가치에 의문을 제기한다. PM은 무엇을 해야 하는가? | 각 요구사항이 비즈니스 및 프로젝트 목표에 맞는지 확인하여 이해관계자와 비즈니스 가치를 검증한다 | 프로젝트 헌장이 이미 승인되었으므로 프로젝트가 완료까지 진행될 것이라고 이해관계자에게 알린다 | 나머지 이해관계자와 스폰서에게 같은 우려가 있는지 확인한다 | 프로젝트 가치 결정은 스폰서와 고객의 몫이라고 이해관계자에게 설명한다 |  | A | 정답은 A이다. 각 요구사항이 비즈니스 및 프로젝트 목표에 맞는지 확인하여 이해관계자와 비즈니스 가치를 검증한다. 이해관계자의 우려를 직접 다루고 가치를 검증하는 것이 적절하다. 헌장 승인 언급(B)은 우려를 무시한다. 다른 이해관계자 확인(C)은 현재 우려를 다루지 않는다. 책임 전가(D)는 회피이다.
1894 | An experienced project manager is in a meeting with project key stakeholders when they are informed that a senior manager with extensive experience on similar projects will join the project steering committee. The project kick-off meeting is scheduled for the following week. What should the project manager do next? | Ask the new senior manager to send any new requirements before the kick-off meeting. | Ask the project sponsor to hold the kick-off meeting after the new senior manager has onboarded. | Have a one-on-one interview with the new senior manager before the kick-off meeting. | Have the kick-off meeting as scheduled and capture any new requirements raised in the meeting. |  | C | The correct answer is C. Have a one-on-one interview with the new senior manager before the kick-off meeting. Stakeholder management requires understanding needs, maintaining engagement, and ensuring transparent communication. The PM should proactively address stakeholder concerns and maintain alignment with project goals. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | 경험 있는 PM이 주요 이해관계자와 회의 중 새 선임 관리자가 참여할 것이라는 통보를 받았다. 킥오프 미팅이 예정되어 있다. PM은 무엇을 해야 하는가? | 새 선임 관리자에게 킥오프 미팅 전에 새 요구사항을 보내도록 요청한다 | 프로젝트 스폰서에게 새 선임 관리자 온보딩 후까지 킥오프 미팅을 보류하도록 요청한다 | 킥오프 미팅 전에 새 선임 관리자와 일대일 인터뷰를 한다 | 예정대로 킥오프 미팅을 하고 회의에서 제기되는 새 요구사항을 포착한다 |  | C | 정답은 C이다. 킥오프 미팅 전에 새 선임 관리자와 일대일 인터뷰를 한다. 이해관계자 관리는 요구 이해, 참여 유지, 정보에 기반한 결정을 보장하는 것이 필요하다. 사전 인터뷰가 기대와 요구를 파악한다. 요구사항 요청(A)은 관계 구축이 아니다. 미팅 보류(B)는 불필요한 지연이다. 예정대로 진행(D)은 준비 없이 진행한다.
1895 | In a daily standup meeting, a project manager notices that a team member's reports include incomplete tasks with no impediments. A colleague informs the project manager that this team member is experiencing a personal issue. What should the project manager do? | Reallocate this team member ' s tasks to others for the immediate future. | Understand the team member ' s personal issue and offer them support. | Coach the team member on how to keep work and personal issues scjparate. | Ask the human resources (HR) manager to speak with this team member. |  | B | When a team member has incomplete tasks with no reported impediments and is experiencing personal issues, the project manager should understand the situation and offer support. Empathy enables appropriate assistance. Reallocating tasks (A) does not address the person. Coaching on separating work and personal issues (C) is insensitive. Involving HR (D) escalates prematurely. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | Traditional PM | 데일리 스탠드업에서 PM이 팀원의 보고에 미완료 작업이 있지만 장애물은 보고되지 않았음을 발견했다. 팀원이 개인 문제를 겪고 있다. PM은 무엇을 해야 하는가? | 즉시 이 팀원의 작업을 다른 사람에게 재배치한다 | 팀원의 개인적 문제를 이해하고 지원을 제공한다 | 업무와 개인 문제를 분리하는 방법에 대해 팀원을 코칭한다 | 인사(HR) 관리자에게 이 팀원과 대화하도록 요청한다 |  | B | 팀원이 개인 문제로 작업이 미완료되고 장애물 보고가 없을 때, PM은 상황을 이해하고 지원을 제공해야 한다. 공감이 적절한 대응을 가능하게 한다. 재배치(A)는 지원 없는 조치이다. 분리 코칭(C)은 상황 이해 전에 부적절하다. HR 요청(D)은 직접 소통 전에 성급하다.
1896 | A project is nearing the completion of a sprint when the product owner announces that a local regulator has banned part of the deliverable. What should the project manager do? | Add more items to the sprint backlog that will add value. | Perform a sprint risk assessment and analyze challenges. | Complete the sprint and seek a waiver from the regulator. | Complete the sprint, but do not release the deliverable. |  | B | The correct answer is B. Perform a sprint risk assessment and analyze challenges. The product owner is responsible for managing the product backlog and defining priorities. The PM should facilitate proper collaboration between the team and product owner while maintaining agile practices. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Agile | Scrum | Process | Manage Project Closure | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 스프린트 완료에 가까워졌을 때 제품 책임자가 지역 규제 기관이 인도물의 일부를 금지했다고 발표한다. PM은 무엇을 해야 하는가? | 가치를 추가할 더 많은 항목을 스프린트 백로그에 추가한다 | 스프린트 리스크 평가를 수행하고 과제를 분석한다 | 스프린트를 완료하고 규제 기관에 면제를 요청한다 | 스프린트를 완료하되 인도물을 릴리스하지 않는다 |  | B | 정답은 B이다. 스프린트 리스크 평가를 수행하고 과제를 분석한다. 제품 책임자가 백로그 우선순위를 관리하고 요구사항을 정의한다. PM은 규제 영향을 평가하고 적절한 대응을 결정해야 한다. 항목 추가(A)는 리스크를 다루지 않는다. 면제 요청(C)은 규제를 무시한다. 릴리스 안 함(D)은 리스크 분석 없는 결정이다.
1897 | A project manager organized a team-building activity to build and maintain teamwork, trust, and commitment due to internal team conflicts. Two months after completing the training, another situation is causing new delays in the project. What should the project manager do to address this issue? | Meet with the team to explain that conflicts must be addressed and solved. | Reassess the team situation and provide a proper solution. | Inform HR about the situation and ask for support. | Ask human resources (HR) to coordinate another activity. |  | B | Conflict is inherent in project environments and can stem from disagreements over tasks, differing values, communication breakdowns, or competing priorities. Unresolved conflict erodes productivity, creativity, and willingness to collaborate. Rather than avoiding the situation, the PM should address it directly by reassessing the team dynamics and crafting a solution that satisfies all parties. This involves identifying root causes, actively listening to each perspective, finding common ground, and proposing a resolution that prevents recurrence. Ignoring the issue (A) only provides temporary relief. Involving HR (C) may signal the PM cannot manage the situation. A confrontational approach (D) risks alienating team members without addressing underlying concerns. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | PM이 내부 갈등으로 인해 팀워크, 신뢰, 헌신을 구축하고 유지하기 위한 팀빌딩 활동을 조직했다. 그러나 갈등이 해결되지 않았다. PM은 무엇을 해야 하는가? | 팀과 회의하여 갈등을 다루고 해결해야 한다고 설명한다 | 팀 상황을 재평가하고 적절한 해결책을 제공한다 | HR에 상황을 알리고 지원을 요청한다 | HR에 다른 활동을 조율하도록 요청한다 |  | B | 팀빌딩 활동 후에도 갈등이 해결되지 않으면, PM은 팀 상황을 재평가하고 적절한 해결책을 제공해야 한다. 초기 접근이 효과가 없었으므로 재평가가 필요하다. 갈등 해결 설명(A)은 이미 인지하고 있다. HR 알림(C)은 PM 주도 해결 후에 한다. 다른 활동(D)은 같은 접근의 반복이다.
1898 | A company is implementing a new system. The project manager has identified that it is best to complete this project using a mix of Scrum and Kanban methodologies. The product owner is confused as to how to start delivering the functionalities required. How should the project manager assist the product owner? | Discuss the product owner ' s responsibilities within the project team | Create a work breakdown structure (WBS) and explain the deliverables to the product owner | Encourage the team to subdivide the project tasks | Coach the product owner on how to create a product backlog |  | D | When the product owner is confused about how to deliver functionalities using a Scrum/Kanban mix, the project manager should coach the product owner on how to create a product backlog. A well-structured backlog is foundational for both Scrum and Kanban. Discussing PO responsibilities (A) clarifies role but not execution. Creating a WBS (B) is a predictive tool. Encouraging task subdivision (C) addresses team work, not PO deliverable management. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 회사가 새 시스템을 구현 중이다. PM이 스크럼/칸반 혼합이 최적이라고 판단했다. 제품 책임자가 기능 납품 방법에 대해 혼란스러워한다. PM은 무엇을 해야 하는가? | 프로젝트 팀 내에서 제품 책임자의 책임을 논의한다 | WBS를 만들어 제품 책임자에게 인도물을 설명한다 | 팀에게 프로젝트 작업을 세분화하도록 장려한다 | 제품 책임자에게 제품 백로그 생성 방법을 코칭한다 |  | D | 제품 책임자가 스크럼/칸반 혼합에서 기능 납품 방법에 혼란스러울 때, PM은 제품 백로그 생성 방법을 코칭해야 한다. 잘 구조화된 백로그가 체계적 납품의 기초이다. 책임 논의(A)는 실질적 도움이 아니다. WBS(B)는 예측형 도구이다. 작업 세분화(C)는 백로그 생성이 우선이다.
1899 | Multidisciplinary teams will be needed for a project. The project manager asks the project planner to create a consolidated schedule. The project manager determines from the consolidated schedule that the project's finish date exceeds the requested finish date. What should the project manager suggest to the planner to analyze this issue? | Verify successors and predecessors of each activity of the consolidated project schedule. | Verify the free float of each activity of the consolidated project schedule. | Verify the critical path of the consolidated project schedule. | Verify the total float of each activity of the consolidated project schedule. |  | C | The correct answer is C. Verify the critical path of the consolidated project schedule. Schedule management requires systematic analysis and appropriate corrective actions. The PM should evaluate impacts and implement solutions to maintain project timelines. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 다학제 팀이 프로젝트에 필요하다. PM이 프로젝트 플래너에게 통합 프로젝트 일정을 만들도록 요청했다. PM이 먼저 무엇을 확인해야 하는가? | 통합 프로젝트 일정의 각 활동의 후행 및 선행 관계를 확인한다 | 통합 프로젝트 일정의 각 활동의 자유 여유를 확인한다 | 통합 프로젝트 일정의 주공정선을 확인한다 | 통합 프로젝트 일정의 각 활동의 총 여유를 확인한다 |  | C | 정답은 C이다. 통합 프로젝트 일정의 주공정선을 확인한다. 일정 관리는 체계적 분석과 적절한 시정 조치가 필요하다. 주공정선 확인이 프로젝트의 최소 기간과 핵심 활동을 파악한다. 선후행 관계(A), 자유 여유(B), 총 여유(D)는 부분적 분석이다.
1900 | A project manager who is new to an organization is given data that include information related to both project team members and stakeholders. Among other items, this information includes each stakeholder's current role, previous and current projects in which they participated, and their level of organizational influence. In what type of analysis should the project manager use this information? | Decision tree analysis | Qualitative risk analysis | Stakeholder analysis | Regression analysis |  | C | Given data about stakeholder roles, project history, and organizational influence, the project manager should use this information in stakeholder analysis. Stakeholder analysis assesses interests, influence, and impact. Decision tree analysis (A) evaluates choices under uncertainty. Qualitative risk analysis (B) prioritizes risks. Regression analysis (D) examines variable relationships. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 조직에 새로운 PM이 팀원과 이해관계자의 역할, 프로젝트 이력, 조직적 영향에 관한 데이터를 받았다. 이 정보를 어떤 분석에 사용해야 하는가? | 의사결정 트리 분석 | 정성적 리스크 분석 | 이해관계자 분석 | 회귀 분석 |  | C | 이해관계자 역할, 프로젝트 이력, 조직적 영향에 관한 데이터가 주어졌을 때, PM은 이해관계자 분석에 이 정보를 사용해야 한다. 이해관계자 분석이 관심, 영향력, 참여 수준을 평가한다. 의사결정 트리(A)는 확률적 분석이다. 정성적 리스크(B)는 리스크 관련이다. 회귀 분석(D)은 통계적 도구이다.
1901 | A project manager is leading the development of a mobile banking application using a hybrid approach. The team has been holding daily standup meetings each workday morning. Due to an unexpected issue, 50% of the team has to work from home. The bank's management directed the team not to have in-person daily standups. Various team members are complaining about this, stating that there is a lack of information sharing among the team. What should the project manager do? | Postpone the daily standups and ask the team members to update the project manager daily via messaging. | Hold virtual daily standups each workday morning and use collaboration tools to manage project updates. | Ask senior management for permission to hold in-person team meetings once each week. | Delegate authority to the team members and ask them to submit weekly status reports instead. |  | B | In hybrid work environments where in-person meetings are restricted, holding virtual daily standups using collaboration tools maintains consistent communication and team alignment. Virtual standups allow all team members—remote and on-site—to share updates, progress, and blockers. This approach preserves the information-sharing benefits of daily standups while complying with management directives about physical meetings. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | PM이 하이브리드 접근법으로 모바일 뱅킹 앱을 개발 중이다. 대면 회의가 제한되었다. PM은 어떻게 팀 소통을 유지해야 하는가? | 데일리 스탠드업을 연기하고 팀원에게 매일 메시징으로 PM에게 업데이트하도록 요청한다 | 매일 아침 가상 데일리 스탠드업을 개최하고 협업 도구를 사용하여 프로젝트 업데이트를 관리한다 | 고위 경영진에게 주 1회 대면 팀 회의 허가를 요청한다 | 팀원에게 권한을 위임하고 주간 상태 보고서를 제출하도록 요청한다 |  | B | 대면 회의가 제한된 하이브리드 작업 환경에서 가상 데일리 스탠드업과 협업 도구 사용이 일관된 커뮤니케이션과 팀 정렬을 유지한다. 가상 스탠드업이 동일한 커뮤니케이션 효과를 제공한다. 메시징 업데이트(A)는 대화가 부족하다. 대면 요청(C)은 제한 상황에 부적합하다. 주간 보고(D)는 일일 소통이 부족하다.
1902 | A project manager scheduled a session to identify risks on the current project. Most of the stakeholders did not attend the meeting, although they previously confirmed their attendance. How should the project manager proceed in order to complete the risk register? | Run the meeting and follow up with each one of the absent stakeholders to get their input. | Continue the meeting and send the updated risk register to all stakeholders. | Escalate the issue of stakeholders not attending the meeting to the project sponsor. | Cancel the meeting and create the risk register using the project documents. |  | A | The PM should run the risk identification meeting with available stakeholders and follow up individually with those who were absent. This ensures the risk register is comprehensive and reflects all stakeholder perspectives. Canceling the meeting (A) excludes stakeholder input entirely. Proceeding without absent stakeholders' input (B) creates an incomplete risk register. Escalating attendance issues to the sponsor (D) may create unnecessary conflict. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | PM이 현재 프로젝트의 리스크 식별 세션을 일정했다. 대부분의 이해관계자가 참석하지 않았다. PM은 무엇을 해야 하는가? | 회의를 진행하고 결석한 이해관계자 각각에게 후속 연락하여 의견을 받는다 | 회의를 계속하고 업데이트된 리스크 등록부를 모든 이해관계자에게 보낸다 | 이해관계자 미참석 이슈를 프로젝트 스폰서에게 에스컬레이션한다 | 회의를 취소하고 프로젝트 문서를 사용하여 리스크 등록부를 작성한다 |  | A | 리스크 식별 세션에 대부분의 이해관계자가 참석하지 않았을 때, PM은 참석한 이해관계자와 회의를 진행하고 결석자에게 개별 후속 연락하여 의견을 받아야 한다. 포괄적 리스크 등록부를 보장한다. 등록부만 발송(B)은 의견을 수집하지 않는다. 에스컬레이션(C)은 과도하다. 회의 취소(D)는 참석자 의견을 무시한다.
1903 | The sponsor calls the project manager and questions why the stakeholders have not received updates for over 1 month. The project recently implemented a project management information system (PMIS) that provides real-time access to various project status measurements and information. The project manager is certain that all stakeholders have the opportunity and permissions for status updates. How should the project manager proceed? | Obtain a list of the affected stakeholders and email the current status information to them. | Request the operations support team to troubleshoot and determine the root cause of the issue. | Call and apologize to the team members and provide an update on how this issue was caused. | Review the communications management plan and stakeholder engagement plan for the project. |  | D | When stakeholders have not received updates for over a month despite a new PMIS providing real-time access, the project manager should review the communications management plan and stakeholder engagement plan. These documents define what information stakeholders need and how it should be delivered. Emailing current status (A) is reactive. Troubleshooting the system (B) assumes a technical issue. Calling to apologize (C) does not address the systemic gap. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 스폰서가 PM에게 이해관계자가 1개월 이상 업데이트를 받지 못한 이유를 묻는다. 새 PMIS가 실시간 접근을 제공하고 있다. PM은 무엇을 해야 하는가? | 영향받는 이해관계자 목록을 확보하고 현재 상태 정보를 이메일로 보낸다 | 운영 지원 팀에 문제 해결과 근본 원인 파악을 요청한다 | 팀원에게 전화하여 사과하고 문제 원인에 대한 업데이트를 제공한다 | 프로젝트의 커뮤니케이션 관리 계획과 이해관계자 참여 계획을 검토한다 |  | D | 새 PMIS가 실시간 접근을 제공하는데도 이해관계자가 업데이트를 받지 못할 때, PM은 커뮤니케이션 관리 계획과 이해관계자 참여 계획을 검토해야 한다. 계획 검토가 커뮤니케이션 격차의 근본 원인을 파악한다. 이메일 발송(A)은 임시 조치이다. 운영 팀 요청(B)은 기술적 문제만 다룬다. 전화 사과(C)는 팀원 역할이 아닌 PM 문제이다.
1904 | A project team is experiencing delays in completing a task that turned out to be more complex than initially estimated. This is a critical task that could impact current iteration goals. What two options will help the team initially address this obstacle? (Choose two) | Conduct a root cause analysis. | Review and update dependencies | Schedule a retrospective. | Escalate the issue to the project sponsor. | Create a risk management plan. | A, B | When a task turns out more complex than estimated and threatens iteration goals, the team should first (B) review and update dependencies to find re-sequencing opportunities, and (A) conduct a root cause analysis to understand why the complexity was underestimated. These actions address both immediate schedule impact and underlying causes. Scheduling a retrospective (C) is post-iteration. Escalating to the sponsor (D) is premature. Creating a risk management plan (E) should already exist. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 프로젝트 팀이 예상보다 복잡한 작업으로 지연을 겪고 있다. 이터레이션 목표를 위협한다. 팀은 무엇을 해야 하는가? | 근본 원인 분석을 수행한다 | 종속성을 검토하고 업데이트한다 | 회고를 일정한다 | 프로젝트 스폰서에게 이슈를 에스컬레이션한다 | 리스크 관리 계획을 작성한다 | A, B | 예상보다 복잡한 작업이 이터레이션 목표를 위협할 때, 팀은 두 가지 조치를 취해야 한다: 종속성을 검토하고 업데이트하여(B) 재배열 기회를 찾고, 근본 원인 분석을 수행하여(A) 복잡성의 원인을 파악한다. 회고(C)는 이터레이션 후에 한다. 에스컬레이션(D)은 팀 해결 시도 후에 한다. 리스크 관리 계획(E)은 이 시점에서 새로 만들 필요가 없다.
1905 | A project manager has recently been assigned to an agile project and discovers that a contractor for the project does not have any experience with agile. What should the project manager do? | Ask the project sponsor to replace the contractor since they do not have agile experience | Issue a formal notice to the contractor to obtain an agile certification | Consult the project team to understand the extent of the training needs for the contractor | Instruct the contractor to receive agile training since the project has already started |  | C | When a contractor on an agile project lacks agile experience, the project manager should consult the project team to understand the extent of training needs for the contractor. Collaborative assessment ensures targeted support. Asking the sponsor to replace the contractor (A) causes unnecessary delays. Issuing a formal notice for certification (B) creates distrust. Instructing training without team input (D) may not address specific project needs. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 애자일 프로젝트에 배정되었고 계약자가 애자일 경험이 없음을 발견했다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 애자일 경험이 없으므로 계약자를 교체하도록 요청한다 | 계약자에게 애자일 인증을 취득하라는 공식 통지를 발행한다 | 프로젝트 팀과 상의하여 계약자의 교육 필요 범위를 파악한다 | 프로젝트가 이미 시작되었으므로 계약자에게 애자일 교육을 받도록 지시한다 |  | C | 애자일 프로젝트의 계약자가 애자일 경험이 없을 때, PM은 프로젝트 팀과 상의하여 교육 필요 범위를 파악해야 한다. 협력적 평가가 효과적 교육 계획을 가능하게 한다. 교체(A)는 과도하다. 인증 통지(B)는 형식적이고 비협력적이다. 교육 지시(D)는 필요 범위를 파악하지 않고 지시한다.
1906 | An agile project is in its sixth iteration out of 10. After the iteration review, the team receives feedback from the stakeholders that could result in a change in the product. What two actions should the project manager take? (Choose two) | Ask the stakeholders about the priority of this change | Ask the team members to analyze the impact of this change | Ask the product owner to review the product backlog | Ask the sponsor to approve the change request | Ask the team members to include the change in the next iteration | A, C | When a change is requested during an agile iteration, the project manager should take two actions: ask the stakeholders about the priority of this change (A) to understand its urgency and importance relative to current work, and ask the product owner to review the product backlog (C) to determine where this change fits in the prioritized list of work items. Stakeholder priority assessment ensures the change is genuinely important, while backlog review by the product owner maintains proper agile governance of scope. Asking team members to analyze impact (B) may be premature before priority is established. Asking the sponsor to approve a change request (D) adds unnecessary bureaucracy in an agile context. Including the change in the next iteration (E) bypasses proper prioritization and may introduce scope creep. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 애자일 프로젝트가 10번 중 6번째 이터레이션에 있다. 이터레이션 리뷰 후 이해관계자로부터 변경 피드백을 받았다. PM은 무엇을 해야 하는가? | 이해관계자에게 이 변경의 우선순위에 대해 질문한다 | 팀원에게 이 변경의 영향을 분석하도록 요청한다 | 제품 책임자에게 제품 백로그를 검토하도록 요청한다 | 스폰서에게 변경 요청을 승인하도록 요청한다 | 팀원에게 다음 이터레이션에 변경을 포함하도록 요청한다 | A, C | 애자일 이터레이션 중 변경이 요청될 때, PM은 두 가지 조치를 취해야 한다: 이해관계자에게 변경 우선순위를 질문하여(A) 긴급성과 중요도를 파악하고, 제품 책임자에게 제품 백로그를 검토하도록 요청하여(C) 변경을 백로그에 적절히 반영한다. 영향 분석(B)은 유용하지만 우선순위 결정이 먼저이다. 스폰서 승인(D)은 애자일에서 불필요할 수 있다. 바로 포함(E)은 우선순위 평가 없이 성급하다.
1907 | Following an investment decision-making meeting for a project, a change to the organizational structure takes place in a multinational company. Due to the organizational change, internal stakeholders are referring the project manager to various other personnel for approval of the project budget. What should the project manager do to obtain approval of the project budget? | Identify the right person with help from local management, present the project summary, and request budget approval. | Approach each of the referred individuals separately and request approval of the project budget from the appropriate person. | Obtain the latest organizational chart and send an email to the appropriate person requesting budget approval. | Provide the decision executive with all of the project details and request budget approval from the appropriate person. |  | A | The correct answer is A. Identify the right person with help from local management, present the project summary, and request budget approval. Stakeholder management requires understanding needs, maintaining engagement, and ensuring transparent communication. The PM should proactively address stakeholder concerns and maintain alignment with project goals. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | General | Stakeholder & Communication Mgmt | Business Environment | Support Organizational Change | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 프로젝트 투자 의사결정 회의 후 조직 구조가 변경되었다. PM은 예산 승인을 어떻게 받아야 하는가? | 현지 관리자의 도움으로 적절한 사람을 식별하고, 프로젝트 요약을 제시하고, 예산 승인을 요청한다 | 소개받은 개인들에게 개별적으로 접근하여 예산 승인을 요청한다 | 최신 조직도를 입수하여 적절한 사람에게 이메일로 예산 승인을 요청한다 | 의사결정 임원에게 모든 프로젝트 세부사항을 제공하고 예산 승인을 요청한다 |  | A | 정답은 A이다. 현지 관리자의 도움으로 적절한 사람을 식별하고, 프로젝트 요약을 제시하고, 예산 승인을 요청한다. 이해관계자 관리는 요구사항 이해, 관계 유지, 적절한 커뮤니케이션이 필요하다. 개별 접근(B)은 비효율적이다. 이메일(C)은 비대면적이다. 모든 세부사항 제공(D)은 과도하다.
1908 | A project manager is tasked with managing a customer relationship management (CRM) implementation project. The project charter is approved, and the project is now in the planning phase. The project manager meets with the stakeholders several times to gather the initial requirements. However, each time they meet, the stakeholders provide additional information that is different from what they provided earlier. The stakeholders are becoming frustrated, and the sponsor is now unresponsive. What should the project manager have done to avoid this situation? | Initiated requirements planning to analyze, document, and manage requirements | Implemented the change request process to harness change to the stakeholders' advantage | Applied requirements elicitation to involve engaging stakeholders consistently in the requirements process | Used progressive elaboration to enhance the scope management plan with additional details |  | C | The project manager should have applied requirements elicitation techniques—such as interviews, workshops, surveys, or observation—to involve stakeholders consistently in the requirements process from the beginning. Requirements elicitation ensures stakeholder needs and expectations are systematically identified, clarified, and validated, preventing conflicting information. Initiating requirements planning (A) focuses on process documentation rather than active stakeholder engagement. Implementing the change request process (B) manages changes after requirements are set but does not prevent the initial confusion. Using progressive elaboration (D) enhances details over time but does not address the fundamental need for consistent stakeholder involvement in elicitation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | PM이 CRM 구현 프로젝트를 관리 중이다. 프로젝트가 완료에 가까웠을 때 범위가 올바르게 정의되지 않았음이 밝혀졌다. PM이 이전에 무엇을 했어야 하는가? | 요구사항을 분석, 문서화, 관리하기 위한 요구사항 계획을 시작했다 | 이해관계자의 이점을 위해 변경 요청 프로세스를 구현했다 | 이해관계자를 요구사항 프로세스에 일관되게 참여시키기 위해 요구사항 도출을 적용했다 | 추가 세부사항으로 범위 관리 계획을 강화하기 위해 점진적 상세화를 사용했다 |  | C | PM은 인터뷰, 워크숍, 설문조사 등의 요구사항 도출 기법을 적용하여 이해관계자를 요구사항 프로세스에 처음부터 일관되게 참여시켰어야 한다. 요구사항 계획(A)은 부분적이다. 변경 프로세스(B)는 범위 정의가 아닌 변경 관리이다. 점진적 상세화(D)는 기존 범위를 강화하지만 근본적 참여 부족을 해결하지 않는다.
1909 | A senior project manager is working for a company that is not yet making a profit. However, the company has many innovative projects in development. Most of the project timelines have slipped, and the staff is overwhelmed. What should the project manager do to help the company meet their financial objectives? | Make sure the project is fast tracked so that slipped time lines are recovered. | Prioritize the projects, giving higher priority to projects that will increase profit. | Ensure that all of the projects are of high quality and are delivered on time. | Request that upper management hire additional staff to support the projects. |  | B | When a company is not yet profitable with slipped timelines and overwhelmed staff, the project manager should prioritize projects giving higher priority to those that increase profit. Strategic prioritization maximizes financial return. Fast-tracking all projects (A) increases risk. Ensuring quality and on-time delivery (C) is a goal, not a strategy. Hiring additional staff (D) increases costs without prioritization. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | Cost & Resource Management | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Traditional PM | 선임 PM이 아직 수익을 내지 못하는 회사에서 일하고 있다. 많은 혁신적 프로젝트가 있지만 일정이 밀리고 직원이 과부하이다. PM은 무엇을 해야 하는가? | 밀린 일정을 회복하기 위해 프로젝트를 고속 추적한다 | 수익을 높일 프로젝트에 더 높은 우선순위를 부여하여 프로젝트 우선순위를 정한다 | 모든 프로젝트가 고품질이고 제시간에 납품되도록 한다 | 상위 경영진에게 프로젝트를 지원할 추가 인원을 고용하도록 요청한다 |  | B | 회사가 수익을 내지 못하고 일정이 밀리며 직원이 과부하일 때, PM은 수익을 높일 프로젝트에 더 높은 우선순위를 부여해야 한다. 전략적 우선순위화가 제한된 자원의 최적 활용을 보장한다. 고속 추적(A)은 리스크를 증가시킨다. 모든 프로젝트 고품질(C)은 과부하 상태에서 비현실적이다. 추가 인원(D)은 수익 전에 비용 증가이다.
1910 | A junior project manager is excited to start working on their first project with a telecommunications company. A senior project manager has decided to educate the junior project manager on the challenges of project management and how to achieve success. Which three artifacts should the senior project manager tell the junior project manager to utilize to ensure project success? (Choose three) | Lesson learned registers from past projects | Historical issue logs | Organizational process assets (OPAs) | Project scope statement | Project management plan | A, C, E | To ensure project success, the senior PM should advise the junior PM to utilize (C) organizational process assets, (A) lessons learned registers from past projects, and (E) project management plan. OPAs provide organizational standards, lessons learned prevent repeated mistakes, and the PM plan integrates all planning. Historical issue logs (B) are useful but not foundational artifacts. The project scope statement (D) is part of the PM plan. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 주니어 PM이 첫 프로젝트에 흥분하고 있다. 선임 PM이 프로젝트 성공을 위해 어떤 문서를 활용하라고 조언해야 하는가? | 과거 프로젝트의 교훈 등록부 | 과거 이슈 로그 | 조직 프로세스 자산(OPA) | 프로젝트 범위 기술서 | 프로젝트 관리 계획 | A, C, E | 프로젝트 성공을 위해 선임 PM은 주니어 PM에게 세 가지를 활용하라고 조언해야 한다: 조직 프로세스 자산(C)은 프로세스, 정책, 절차를 포함하고, 교훈 등록부(A)는 과거 경험에서 배운 점을 제공하며, 프로젝트 관리 계획(E)은 실행의 로드맵이다. 이슈 로그(B)는 반응적 도구이다. 범위 기술서(D)는 중요하지만 이 세 가지보다 우선하지 않는다.
1911 | A large project is affecting the neighborhood in which it is located. The neighbors are not satisfied with the project and their resistance to the project may affect the project deadline. What two actions should the project manager take? (Choose two) | Ask the customer to extend the project deadline to allow time for conflict resolution | Send letters to the neighbors and ask them kindly not to disturb the project. | Set up a meeting with neighborhood representatives to win their cooperation | Analyze the situation and find out what is causing the neighborhood ' s negative attitude. | Ask the mayor of the city to use their authority to stop neighborhood resistance | C, D | When neighbors resist a project that may affect the deadline, the project manager should (C) set up a meeting with neighborhood representatives to win cooperation, and (D) analyze the situation and find out what is causing the negative attitude. Engagement addresses concerns while root cause analysis enables targeted solutions. Asking for a deadline extension (A) does not resolve the conflict. Sending letters (B) is impersonal. Using authority to stop resistance (E) is inappropriate. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Focus on Value | Implement Risk Responses | Traditional PM | 대규모 프로젝트가 위치한 지역에 영향을 미치고 있다. 주민들이 불만족하고 기한에 영향을 줄 수 있다. PM은 무엇을 해야 하는가? | 갈등 해결을 위한 시간을 허용하도록 고객에게 프로젝트 기한 연장을 요청한다 | 주민에게 편지를 보내 프로젝트를 방해하지 말도록 정중하게 요청한다 | 주민 대표와 회의를 설정하여 협력을 얻는다 | 상황을 분석하고 주민의 부정적 태도의 원인을 파악한다 | 시장에게 권한을 사용하여 주민 저항을 중지하도록 요청한다 | C, D | 주민이 프로젝트에 저항하고 기한에 영향을 줄 수 있을 때, PM은 두 가지 조치를 취해야 한다: 주민 대표와 회의를 설정하여 협력을 얻고(C), 상황을 분석하여 부정적 태도의 원인을 파악한다(D). 대화와 원인 분석이 함께 효과적이다. 기한 연장(A)은 근본 해결이 아니다. 편지(B)는 일방적이다. 시장 권한(E)은 관계를 훼손한다.
1912 | A project manager finished reviewing the project deliverables for the current iteration with the customer. A new key stakeholder who just joined the customer's team, complains that the results do not provide the capabilities the business anticipated. What should the project manager do to address this issue? | Update the project management plan and lessons learned | Create a change request and update the scope management plan | Update the stakeholder list and fix the deliverables | Conduct stakeholder identification and a project objectives review session |  | D | When a new stakeholder complains that current iteration deliverables do not provide anticipated capabilities, the project manager should conduct stakeholder identification and a project objectives review session. Re-engaging stakeholders ensures alignment. Updating the PM plan and lessons learned (A) is documentation. Creating a change request (B) assumes scope is wrong. Updating the stakeholder list and fixing deliverables (C) acts without understanding root cause. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | PM이 고객과 현재 이터레이션 인도물을 검토했다. 새 주요 이해관계자가 인도물이 예상 기능을 제공하지 못한다고 불만한다. PM은 무엇을 해야 하는가? | 프로젝트 관리 계획과 교훈을 업데이트한다 | 변경 요청을 생성하고 범위 관리 계획을 업데이트한다 | 이해관계자 목록을 업데이트하고 인도물을 수정한다 | 이해관계자 식별과 프로젝트 목표 검토 세션을 수행한다 |  | D | 새 이해관계자가 현재 인도물이 예상 기능을 제공하지 못한다고 불만할 때, PM은 이해관계자 식별과 프로젝트 목표 검토 세션을 수행해야 한다. 이해관계자 요구 이해와 목표 재정렬이 근본 해결이다. 계획/교훈 업데이트(A)는 이해 후에 한다. 변경 요청(B)은 분석 전에 성급하다. 목록 업데이트/수정(C)은 충분한 분석 없는 대응이다.
1913 | A key project stakeholder does not attend any of the project meetings and is providing false information that the project team is not delivering on time. What should the project manager do to address this situation? | Share the meeting recordings with the key stakeholder. | Email the latest status report to the key stakeholder. | Discuss communication needs with the key stakeholder. | Create a new communication artifact for the key stakeholder. |  | C | When a key stakeholder is not attending meetings and spreading false information about the team's delivery performance, the project manager should discuss communication needs with the key stakeholder. Understanding why the stakeholder is disengaged and what communication preferences they have allows the PM to build trust, correct misinformation, and ensure they receive accurate, timely project updates. Sharing meeting recordings (A), emailing status reports (B), or creating new communication artifacts (D) may not address the root cause of the stakeholder's disengagement and misinformation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Executing | Embed Quality | Manage Communications | Traditional PM | 주요 이해관계자가 프로젝트 회의에 참석하지 않고 팀 납품 성과에 대해 거짓 정보를 제공하고 있다. PM은 무엇을 해야 하는가? | 회의 녹화를 주요 이해관계자와 공유한다 | 최신 상태 보고서를 주요 이해관계자에게 이메일로 보낸다 | 주요 이해관계자와 커뮤니케이션 요구사항을 논의한다 | 주요 이해관계자를 위한 새 커뮤니케이션 산출물을 만든다 |  | C | 주요 이해관계자가 회의에 불참하고 거짓 정보를 퍼뜨릴 때, PM은 이해관계자와 커뮤니케이션 요구사항을 직접 논의해야 한다. 직접 대화가 근본 원인을 해결하고 관계를 재구축한다. 녹화 공유(A)는 수동적이다. 상태 보고(B)는 일방적이다. 새 산출물(D)은 참여를 보장하지 않는다.
1914 | A global program is being kicked off, and various distributed teams are involved in delivering the initiative. Besides planning and executing the scope for the initiative, team interactions must be considered. How should the project teams interact in their meetings? | Videoconferencing 1045 | Phone conversations | Chat conversations | Encrypted emails |  | A | When a global program with distributed teams is being kicked off and team interactions must be considered, project teams should interact through videoconferencing. Video provides real-time communication with visual cues for better engagement. Phone conversations (B) lack visual context. Chat conversations (C) are asynchronous. Encrypted emails (D) are formal and lack interactivity. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Predictive | Traditional Plan-Driven | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 글로벌 프로그램이 시작되고 분산된 팀이 참여한다. 팀 상호작용을 고려할 때 프로젝트 팀은 어떤 방법으로 상호작용해야 하는가? | 화상 회의 | 전화 대화 | 채팅 대화 | 암호화 이메일 |  | A | 분산된 팀이 참여하는 글로벌 프로그램에서 팀은 화상 회의를 통해 상호작용해야 한다. 화상 회의는 비언어적 단서를 포함한 실시간 커뮤니케이션을 제공한다. 전화(B)는 시각적 단서가 없다. 채팅(C)은 복잡한 논의에 부적합하다. 이메일(D)은 비동기적이고 상호작용이 부족하다.
1915 | A project manager is leading a project and is asked to negotiate on behalf of their organization. The organization requires that three quotes from different suppliers be acquired prior to submitting a purchase request to the finance department. What should the project manager do to align with this requirement? | Perform a make-or-buy analysis | Review the statement of work (SOW) | Refer to the organizational process assets (OPAs) | Leverage the enterprise environmental factors (EEFs) |  | C | When the organization requires three quotes before submitting a purchase request, the project manager should refer to the organizational process assets (OPAs). Internal procurement policies, procedures, templates, and approval workflows are OPAs. Following them ensures the PM complies with the organization's established procurement process. Performing a make-or-buy analysis (A) supports sourcing decisions but does not address the internal quoting requirement. Reviewing the SOW (B) clarifies what is being procured but not the procurement steps. Leveraging EEFs (D) addresses external or environmental conditions, not specific internal procedural requirements. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | PM이 조직을 대표하여 협상하도록 요청받았다. 조직이 구매 요청 전 3개의 견적을 요구한다. PM은 무엇을 참조해야 하는가? | 자체 제작 또는 구매 분석을 수행한다 | 작업기술서(SOW)를 검토한다 | 조직 프로세스 자산(OPA)을 참조한다 | 기업 환경 요인(EEF)을 활용한다 |  | C | 조직이 구매 전 3개 견적을 요구할 때, PM은 조직 프로세스 자산(OPA)을 참조해야 한다. 내부 조달 정책, 절차, 가이드라인이 OPA에 포함된다. 자체 제작/구매 분석(A)은 조달 전략이지 절차가 아니다. SOW(B)는 작업 범위이지 조달 절차가 아니다. EEF(D)는 외부 환경이지 내부 절차가 아니다.
1916 | There is a problem with a project because some features are not in compliance with regulations. Some stakeholders do not believe compliance is a priority, while others disagree. What should the project manager do? | Set up some time with the stakeholders to explain the importance of compliance. | Send out documentation to align stakeholder expectations and project objectives. | Review the stakeholder engagement assessment matrix to determine next steps. | Meet with the sponsor to discuss how to handle the stakeholders ' differing opinions. |  | B | The correct answer is B. Send out documentation to align stakeholder expectations and project objectives. This approach best addresses the situation described by following project management best practices. The other options either fail to address the root cause, bypass proper processes, or may create additional problems. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 일부 기능이 규제를 준수하지 않아 프로젝트에 문제가 있다. 일부 이해관계자가 변경의 긴급성에 동의하지 않는다. PM은 무엇을 해야 하는가? | 이해관계자와 시간을 마련하여 컴플라이언스의 중요성을 설명한다 | 이해관계자 기대와 프로젝트 목표를 정렬하기 위해 문서를 발송한다 | 이해관계자 참여 평가 매트릭스를 검토하여 다음 단계를 결정한다 | 스폰서와 만나 이해관계자의 다른 의견을 어떻게 처리할지 논의한다 |  | B | 정답은 B이다. 이해관계자 기대와 프로젝트 목표를 정렬하기 위해 문서를 발송한다. 이 접근법은 프로젝트 관리 모범 사례를 따른다. 컴플라이언스 설명(A)은 유용하지만 공식적 정렬이 필요하다. 매트릭스 검토(C)는 분석이지 행동이 아니다. 스폰서 논의(D)는 직접 소통 전에 에스컬레이션이다.
1917 | A marketing team is developing ideas in order to revamp an existing product. The marketing executive reaches out to the project manager to make sure that necessary measures are in place for a successful launch. On what should the project manager focus? | Ensuring that the team is also focused on the overall change management plan | Ensuring that the scope management plan is in place to cover all related objectives | Determining and aligning performance indicators that will help in assessing successful delivery | Planning for regular project updates to cover the status of critical deliverables |  | C | When a marketing executive wants to ensure a successful product launch, the project manager should focus on determining and aligning performance indicators that will help assess successful delivery. Measurable indicators enable tracking and stakeholder alignment. Ensuring focus on the change management plan (A) is one aspect, not the primary focus. Ensuring a scope management plan (B) covers scope, not delivery success metrics. Planning regular project updates (D) communicates status but does not define success measures. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 마케팅 팀이 기존 제품 개선 아이디어를 개발 중이다. 마케팅 임원이 성공적 출시를 보장하기 위해 PM에게 무엇에 집중하라고 요청하는가? | 팀이 전체 변경 관리 계획에도 집중하도록 한다 | 관련 목표를 모두 포함하도록 범위 관리 계획이 마련되도록 한다 | 성공적 납품 평가에 도움이 될 성과 지표를 결정하고 정렬한다 | 중요 인도물 상태를 포함하는 정기 프로젝트 업데이트를 계획한다 |  | C | 마케팅 임원이 성공적 제품 출시를 보장하고 싶을 때, PM은 성공적 납품 평가에 도움이 될 성과 지표를 결정하고 정렬해야 한다. 측정 가능한 성과 지표가 성공을 정의하고 추적한다. 변경 관리(A)는 프로세스이지 성공 측정이 아니다. 범위 관리(B)는 부분적이다. 정기 업데이트(D)는 보고이지 성공 정의가 아니다.
1918 | During a project review session with key stakeholders, a senior manager raises a concern that the product being shown is not meeting the client's expectations. The project manager has noticed that although the team is meeting project deadlines, there are a large number of open quality issues that have not been addressed. What should the project manager do? | Advise the team to continue moving forward because meeting the milestones is more important and the issues can be fixed later. | Ask the team to reprioritize and focus on fixing the quality issues that were identified by the stakeholders during the meeting. | Work with the project team to identify the gaps and address the critical issues based on defined outcomes. | Meet with the project stakeholders to review the scope and ask for a time extension to address the quality issues. |  | C | When a senior manager raises quality concerns and many open quality issues exist despite meeting deadlines, the project manager should work with the team to identify gaps and address critical issues based on defined outcomes. This root-cause approach ensures quality is restored while maintaining alignment with project objectives. Advising to continue because milestones matter more (A) ignores quality. Asking the team to reprioritize on quality (B) is reactive without gap analysis. Meeting stakeholders to request a time extension (D) is premature before understanding the actual gaps. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Stakeholders | Planning | Embed Quality | Plan Stakeholder Engagement | Traditional PM | 프로젝트 리뷰 세션에서 선임 관리자가 제품 품질에 우려를 제기했다. 기한은 맞추고 있지만 많은 품질 이슈가 있다. PM은 무엇을 해야 하는가? | 마일스톤 충족이 더 중요하므로 팀에게 계속 진행하도록 조언한다 | 이해관계자가 식별한 품질 이슈를 수정하는 데 재우선순위를 부여하도록 팀에 요청한다 | 프로젝트 팀과 협력하여 격차를 식별하고 정의된 결과에 기반하여 중요 이슈를 해결한다 | 프로젝트 이해관계자와 범위를 검토하고 품질 문제 해결을 위한 시간 연장을 요청한다 |  | C | 선임 관리자가 품질 우려를 제기하고 많은 미해결 품질 이슈가 있을 때, PM은 팀과 협력하여 격차를 식별하고 정의된 결과에 기반하여 중요 이슈를 해결해야 한다. 체계적 격차 분석이 효과적이다. 계속 진행(A)은 품질을 무시한다. 재우선순위(B)는 외부 지적에만 반응한다. 시간 연장(C)은 근본 해결 전에 성급하다.
1919 | A new project manager has been assigned to a recently approved project. The project has a multimillion-dollar budget and will require the purchase of expensive equipment. The project manager is aware that some purchase amounts require higher levels of approval. What should the project manager do to properly manage the purchase of equipment? | Propose that the project sponsor approve all equipment that needs to be purchased | Replace the most expensive equipment with cheaper ones to allow easier purchase approval | Agree on a purchasing approval escalation method according to organizational governance | Ask the organization to allow the project manager to approve all purchases |  | C | When managing large equipment purchases requiring higher-level approvals, the project manager should agree on a purchasing approval escalation method according to organizational governance. Clear approval paths ensure compliance and predictable procurement planning. Proposing the sponsor approve everything (A) creates bottlenecks. Replacing expensive equipment with cheaper alternatives (B) may compromise requirements. Requesting PM approval authority for all purchases (D) conflicts with segregation-of-duties controls. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 새 PM이 수백만 달러 예산의 프로젝트에 배정되었다. 대형 장비 구매가 상위 레벨 승인이 필요하다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서가 구매해야 할 모든 장비를 승인하도록 제안한다 | 더 쉬운 구매 승인을 위해 가장 비싼 장비를 더 저렴한 것으로 대체한다 | 조직 거버넌스에 따라 구매 승인 에스컬레이션 방법에 합의한다 | 조직에 PM이 모든 구매를 승인할 수 있도록 허용하도록 요청한다 |  | C | 대형 장비 구매에 상위 레벨 승인이 필요할 때, PM은 조직 거버넌스에 따라 구매 승인 에스컬레이션 방법에 합의해야 한다. 명확한 승인 프로세스가 효율적 조달을 보장한다. 스폰서 승인(A)은 스폰서에게 과부하를 준다. 장비 대체(B)는 프로젝트 요구를 훼손한다. PM 전체 승인(D)은 거버넌스에 반한다.
1920 | A company has an existing contract to maintain and enhance a client's customer database. The company's legal department informs the project manager that a new piece of legislation requiring stricter protection of customer information might soon be signed into law. The law will require additional security features to be implemented into the database the project manager is maintaining. These features are not included in the scope of the current contract. What should the project manager do? | Update the risk register to include this issue and discuss the appropriate risk response plans with the project sponsor and client | Ask the legal department to raise the issue in the next contract negotiation with the customer | Seek the project sponsor ' s support to influence the client to amend the contract immediately | Wait until the legal requirements are finalized so the change in scope can be concretely defined |  | A | The correct answer is A. Update the risk register to include this issue and discuss the appropriate risk response plans with the project sponsor and client. Procurement management involves proper oversight and control of vendor relationships. The PM should ensure deliverables meet quality standards and address performance issues through established processes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 회사가 고객 데이터베이스 유지보수 및 향상 계약을 보유 중이다. 법무부서가 새 법적 요구사항이 계약 범위에 영향을 미칠 것이라고 알렸다. PM은 무엇을 해야 하는가? | 이 이슈를 리스크 등록부에 포함하고 프로젝트 스폰서 및 고객과 적절한 리스크 대응 계획을 논의한다 | 법무부서에 다음 계약 협상에서 이 이슈를 제기하도록 요청한다 | 프로젝트 스폰서의 지원을 구하여 고객이 즉시 계약을 수정하도록 영향을 미친다 | 법적 요구사항이 확정될 때까지 기다려 범위 변경을 구체적으로 정의한다 |  | A | 정답은 A이다. 리스크 등록부에 이슈를 포함하고 스폰서 및 고객과 리스크 대응 계획을 논의한다. 조달 관리는 적절한 감독, 리스크 식별, 이해관계자 협력이 필요하다. 다음 협상 대기(B)는 너무 늦다. 즉시 수정(C)은 강압적이다. 확정 대기(D)는 수동적이다.
1921 | During daily calls, team members share task progress. One team member does not usually communicate many details and has critical tasks to be completed. All team members are located in different countries and critical work is about to start. Which two options will help the project manager in this situation? (Choose two) | Ask the team to send emails with detailed task progress | Reassign the work to a resource who participates in the daily calls | Encourage all team members to use a virtual workspace | Talk to the team member about their engagement and take appropriate action. | Report the team member's poor performance to the functional manager | C, D | When a team member with critical tasks provides minimal details during daily calls and all members are in different countries, two actions that help are: encourage all team members to use a virtual workspace—enabling real-time collaboration, information sharing, and progress visibility regardless of location—and talk to the team member about their engagement and take appropriate action—understanding reasons for limited communication and setting clear expectations. Asking for detailed emails (A) adds overhead. Reassigning the work (B) is premature. Reporting to the functional manager (E) escalates without first addressing the issue directly. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 일일 회의에서 팀원들이 작업 진행을 공유한다. 한 팀원이 세부사항을 잘 공유하지 않고 중요 작업이 배정되어 있다. 모든 팀원이 다른 국가에 있다. PM은 무엇을 해야 하는가? | 팀에게 상세 작업 진행을 이메일로 보내도록 요청한다 | 일일 회의에 참여하는 자원에게 작업을 재배정한다 | 모든 팀원이 가상 작업 공간을 사용하도록 장려한다 | 해당 팀원과 참여에 대해 대화하고 적절한 조치를 취한다 | 팀원의 저조한 성과를 기능 관리자에게 보고한다 | C, D | 팀원이 일일 회의에서 세부사항을 잘 공유하지 않고 모든 팀원이 다른 국가에 있을 때, 두 가지 조치가 도움이 된다: 모든 팀원이 가상 작업 공간을 사용하도록 장려하고(C), 해당 팀원과 참여에 대해 대화하고 적절한 조치를 취한다(D). 가상 작업 공간이 투명성을 높이고, 직접 대화가 근본 원인을 해결한다. 이메일(A)은 추가 관료주의이다. 재배정(B)은 과도한 반응이다. 기능 관리자 보고(E)는 직접 소통 전에 시기상조이다.
1922 | A project manager is managing a large project. A stakeholder has just discovered a new risk that has not been identified in earlier stages. What should the project manager do? | Perform a risk analysis directly with the stakeholder who raised the risk and update the risk register. | Add the risk to the risk register and reevaluate the register with help from the project team and stakeholders. | Communicate the risk to the steering committee and request a mitigation plan from senior management. | Confirm to the stakeholder that the risk register has been completed and validated by all stakeholders. |  | B | When a stakeholder discovers a new risk not previously identified, the project manager should add the risk to the risk register and reevaluate the register with help from the project team and stakeholders. Comprehensive reassessment ensures all risks are current and managed. Performing analysis only with the raising stakeholder (A) excludes broader perspectives. Communicating to the steering committee and requesting a management plan (C) escalates prematurely. Confirming the register is complete (D) is dismissive of the new finding. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | PM이 대규모 프로젝트를 관리 중이다. 이해관계자가 이전에 식별되지 않은 새 리스크를 발견했다. PM은 무엇을 해야 하는가? | 리스크를 제기한 이해관계자와 직접 리스크 분석을 수행하고 리스크 등록부를 업데이트한다 | 리스크를 리스크 등록부에 추가하고 프로젝트 팀과 이해관계자의 도움으로 등록부를 재평가한다 | 운영위원회에 리스크를 전달하고 고위 경영진에게 완화 계획을 요청한다 | 이해관계자에게 리스크 등록부가 모든 이해관계자에 의해 완료되고 검증되었음을 확인한다 |  | B | 이해관계자가 새 리스크를 발견했을 때, PM은 리스크를 등록부에 추가하고 프로젝트 팀과 이해관계자의 도움으로 등록부를 재평가해야 한다. 포괄적 팀 검토가 완전한 리스크 평가를 보장한다. 한 이해관계자만과 분석(A)은 제한적이다. 운영위원회 전달(C)은 과도한 에스컬레이션이다. 완료 확인(D)은 새 리스크를 무시한다.
1923 | A project manager is working on an agile project in a changing business environment. The project sponsor is worried about benefits realization and asks the project manager to pay attention to changes that can affect the project. Which action should the project manager take to identify changes that may affect the product? | Implement face-to-face communication between the team and product owner to change the iteration objectives as needed. | Take action to reprioritize the backlog after every iteration to evaluate if user stories are still valuable to the business. | Apply a pair programming technique to react to changes immediately, even in the middle of the interaction. | Stop the iteration as soon as possible in case an external change that makes the product invaluable is identified. 1159 |  | B | When a sponsor worries about benefits realization in a changing business environment, the project manager should take action to reprioritize the backlog after every iteration to evaluate if user stories remain valuable. Continuous reprioritization maintains business alignment. Face-to-face communication to change objectives (A) is ad hoc. Pair programming (C) addresses development quality, not change identification. Stopping iterations on external change (D) is overreactive. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Scrum | Business Environment | Define and Establish Governance | Finance | Monitoring & Controlling | Be an Accountable Leader | Control Costs | Traditional PM | PM이 변화하는 비즈니스 환경에서 애자일 프로젝트를 작업 중이다. 스폰서가 혜택 실현에 대해 걱정한다. PM은 무엇을 해야 하는가? | 팀과 제품 책임자 간 대면 커뮤니케이션을 구현하여 이터레이션 목표를 변경한다 | 매 이터레이션 후 백로그를 재우선순위화하여 사용자 스토리가 여전히 관련 있는지 평가한다 | 변경에 즉시 대응하기 위해 페어 프로그래밍 기법을 적용한다 | 제품을 무가치하게 만드는 외부 변경이 발생하면 가능한 빨리 이터레이션을 중단한다 |  | B | 스폰서가 변화하는 비즈니스 환경에서 혜택 실현을 걱정할 때, PM은 매 이터레이션 후 백로그를 재우선순위화하여 사용자 스토리가 여전히 관련 있는지 평가해야 한다. 정기적 재우선순위화가 변화에 적응한다. 대면 커뮤니케이션(A)은 목표 변경 메커니즘이 아니다. 페어 프로그래밍(C)은 개발 기법이지 전략 대응이 아니다. 이터레이션 중단(D)은 극단적이다.
1924 | A project manager is leading a contract for a new market that was awarded to their company. The client has the desire to jump-start the market with informal sector traders. What should the project manager do? | Execute the projects simultaneously following the project schedule and the communications management plan | Divide the project team into groups to execute as small parallel projects, including the informal sector | Plan the project in phases, starting with the informal sector, to deliver business value 280 quickly | Gather requirements and convert them into backlog items to quickly deliver value |  | C | When the client wants to accelerate market entry by starting with informal sector traders, the project manager should plan the project in phases, starting with the informal sector, to deliver business value quickly. Phased delivery targets the highest-impact segment first, enables early validation of assumptions, and produces learning that shapes subsequent phases. Dividing the team into parallel projects (B) increases coordination risk. Converting requirements to backlog items (D) is a planning technique but does not explicitly ensure the informal sector is prioritized strategically. Executing everything simultaneously (A) prioritizes plan adherence over value realization. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | PM이 새 시장을 위한 계약을 이끌고 있다. 고객이 비공식 부문 거래자부터 시작하여 시장 진입을 가속하고 싶다. PM은 무엇을 해야 하는가? | 프로젝트 일정과 커뮤니케이션 관리 계획에 따라 프로젝트를 동시에 실행한다 | 프로젝트 팀을 그룹으로 나누어 소규모 병렬 프로젝트로 실행한다 | 비공식 부문부터 시작하여 단계별로 프로젝트를 계획하여 비즈니스 가치를 빠르게 전달한다 | 요구사항을 수집하고 백로그 항목으로 변환하여 가치를 빠르게 전달한다 |  | C | 고객이 비공식 부문부터 시작하여 시장 진입을 가속하고 싶을 때, PM은 비공식 부문부터 시작하여 단계별로 프로젝트를 계획해야 한다. 단계별 접근이 비즈니스 가치를 빠르게 전달하면서 리스크를 관리한다. 동시 실행(A)은 복잡성이 높다. 병렬 프로젝트(B)는 자원을 분산시킨다. 백로그 변환(D)은 애자일 접근이지만 고객 요구와 맞지 않을 수 있다.
1925 | A project manager has noticed that the performance of a new team member has increased dramatically over the past few months. The project manager has been measuring this team member's performance through the cost performance index (CPI) and schedule performance index (SPI) of work packages. The project manager has also assigned new, unrelated work packages to this team member. The project manager wants to formally record the team member's success in the project documentation. What should the project manager do? | Attach a note to the project management plan about the team member | Hold a project team meeting about the team member ' s contribution and take minutes | Record the team member ' s contribution in the responsibility assignment matrix (RAM) | Send a communication to management recognizing the team member ' s contributions |  | D | When the project manager wants to formally record a new team member's dramatically improved performance, they should send a communication to management recognizing the team member's contributions. Formal communication ensures recognition reaches leadership. Attaching a note to the project management plan (A) is informal. Holding a team meeting (B) celebrates but does not document formally. Recording in the RAM (C) assigns responsibilities, not performance recognition. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Schedule Management | People | Plan and Manage Communication | Governance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | PM이 새 팀원의 성과가 지난 몇 달간 크게 향상되었음을 발견했다. PM은 이 기여를 어떻게 공식적으로 기록해야 하는가? | 프로젝트 관리 계획에 팀원에 대한 메모를 첨부한다 | 팀원의 기여에 대해 프로젝트 팀 회의를 개최하고 회의록을 작성한다 | 팀원의 기여를 책임 배정 매트릭스(RAM)에 기록한다 | 경영진에게 팀원의 기여를 인정하는 커뮤니케이션을 보낸다 |  | D | 팀원의 극적으로 향상된 성과를 공식 기록하려면, PM은 경영진에게 팀원의 기여를 인정하는 커뮤니케이션을 보내야 한다. 공식적 인정이 동기를 부여하고 성과를 기록한다. 계획에 메모(A)는 비공식적이다. 팀 회의(B)는 공식 기록이 아니다. RAM(C)은 역할/책임 도구이지 성과 인정이 아니다.
1926 | A team member is openly criticized by others during a standup meeting for failing to complete yesterday's tasks. What should the agile coach do first to address the situation? | Address the team members involved during the next sprint retrospective. | Avoid the discussion by referring to the team charter. | Emphasize the ground rules and then focus on today ' s activities and impediments. | Let the discussion go on as it is important that the team is clear on priorities for theday. |  | C | When a team member is publicly criticized during a standup, the agile coach should intervene immediately. The coach should reinforce meeting ground rules—mutual respect, supportive behavior, and focus on the work—then redirect the team's attention to current activities and impediments. This prevents conflict escalation, maintains a positive team atmosphere, and keeps the team progressing. Letting the discussion continue, deferring to the retrospective, or avoiding the issue by referencing the team charter are all ineffective responses that may ignore, postpone, or evade the problem. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Align Stakeholder Expectations | Finance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 스탠드업 회의에서 팀원이 어제 작업을 완료하지 못한 것에 대해 공개적으로 비판받고 있다. 애자일 코치는 무엇을 해야 하는가? | 다음 스프린트 회고에서 관련 팀원들을 다룬다 | 팀 헌장을 참조하여 토론을 피한다 | 기본 규칙을 강조하고 오늘의 활동과 장애물에 집중한다 | 팀이 오늘의 우선순위를 명확히 해야 하므로 토론이 계속되도록 한다 |  | C | 스탠드업에서 팀원이 공개 비판받을 때, 애자일 코치는 즉시 개입해야 한다. 회의 기본 규칙—상호 존중, 지지적 행동—을 강조하고 오늘의 활동과 장애물에 집중시켜야 한다. 회고 대기(A)는 너무 늦다. 헌장 참조(B)는 회피적이다. 토론 방치(D)는 부정적 행동을 허용한다.
1927 | A project for a new product launch is in a very initial stage and the requirements are evolving. Due to stiff competition in the market, the customer would like to launch the product keeping the scope flexible. The project team intends to start the work based on the forecast of a similar project delivered last year. Which project approach suits the scenario? | Execute it using the same approach as the reference project | Execute it as a project with stage gates | Execute it as a Scrum project | Execute it as a predictive project |  | C | For a new product launch with evolving requirements and flexible scope where the team plans to start based on a similar project forecast, a Scrum project approach is most suitable. Scrum delivers value incrementally through sprints, allowing the team to collaborate with customers, prioritize backlogs, and adapt to changing requirements while maintaining delivery momentum. Executing with the same approach as the reference project (A) assumes identical conditions. Using stage gates (B) applies a predictive framework to uncertain requirements. Executing as a predictive project (D) does not accommodate flexible scope. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Build an Empowered Culture | Determine Budget | Traditional PM | 새 제품 출시 프로젝트가 매우 초기 단계이고 요구사항이 진화 중이다. 경쟁이 치열하여 빠른 납품이 필요하다. 범위는 유연하다. 어떤 접근법을 사용해야 하는가? | 참조 프로젝트와 같은 접근법으로 실행한다 | 스테이지 게이트가 있는 프로젝트로 실행한다 | 스크럼 프로젝트로 실행한다 | 예측형 프로젝트로 실행한다 |  | C | 진화하는 요구사항, 유연한 범위, 빠른 납품이 필요한 새 제품 출시에는 스크럼 프로젝트 접근법이 가장 적합하다. 스크럼이 반복적으로 가치를 전달한다. 같은 접근법(A)은 새 상황에 맞지 않을 수 있다. 스테이지 게이트(B)는 예측형이다. 예측형(D)은 진화하는 요구사항에 부적합하다.
1928 | A project manager has been assigned to a project and receives the project charter from the project management office (PMO). The document is very clear about customer requests. During Project Scope Management, some requirements seem to be different from the ones specified within the project charter. What should the project manager do? | Use a focus group and brainstorming sessions to gather more details about the project scope | Explain to the sponsor that these requests could endanger the schedule and cost of the project | Register the changes in the configuration management plan and send it to the change control board (CCB). | Modify the baseline of the project for minor impact changes to the project scope |  | A | When requirements gathered during scope management differ from the project charter, the project manager should use a focus group and brainstorming sessions to gather more details about the project scope. Further elicitation clarifies the discrepancies and ensures accurate requirements. Explaining to the sponsor about schedule and cost risks (B) escalates before investigation. Registering changes in configuration management (C) is premature. Modifying the baseline for minor changes (D) bypasses proper change control. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Scope | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 PMO로부터 프로젝트 헌장을 받았다. 범위 관리 중 수집된 요구사항이 헌장과 다르다. PM은 무엇을 해야 하는가? | 포커스 그룹과 브레인스토밍 세션을 사용하여 프로젝트 범위에 대한 세부사항을 더 수집한다 | 스폰서에게 이 요청들이 일정과 비용을 위험에 빠뜨릴 수 있다고 설명한다 | 구성 관리 계획에 변경을 등록하고 CCB에 보낸다 | 프로젝트 범위에 대한 사소한 영향 변경을 위해 기준선을 수정한다 |  | A | 범위 관리 중 수집된 요구사항이 헌장과 다를 때, PM은 포커스 그룹과 브레인스토밍 세션을 사용하여 더 많은 세부사항을 수집해야 한다. 추가 도출이 요구사항을 명확히 한다. 스폰서 설명(B)은 조사 전에 성급하다. CCB 등록(C)은 분석 전에 시기상조이다. 기준선 수정(D)은 적절한 프로세스를 따르지 않는다.
1929 | A project manager is new to an organization that typically follows a hybrid approach but is shifting to incorporate more agile. A dedicated project team has been provisionally assigned. The new project manager needs to review the internal environment in order to build a high-performing team. To build a high-performing team, which three factors should the project manager evaluate? (Choose 3) | Review the team ' s capability to determine if they have the skill set needed to proceed forward. | Evaluate the infrastructure to determine if the team has the appropriate equipment and communication channels. | Perform a benchmark analysis across similar sectors to determine if the structure can be followed. | Review the customer governance documents so that they align with the set expectations. | Assess the organizational culture to determine if more needs to be done to foster psychological safety. | A, B, E | When assessing whether the project team is prepared for an agile transformation, the project manager should take three actions: review the team's capability to determine if they have the skill set needed (A) to ensure technical readiness for agile practices, evaluate the infrastructure to determine if the team has the appropriate equipment and tools (B) to confirm the environment supports agile workflows, and assess the organizational culture to determine if more needs to be done to foster an agile mindset (E) to address the cultural dimension of transformation. Together, these cover people, tools, and culture—the three pillars of readiness. Performing a benchmark analysis across similar sectors (C) provides external comparison but does not assess internal readiness. Reviewing customer governance documents (D) focuses on client alignment rather than team preparation. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Hybrid/Tailoring | 새 PM이 하이브리드 접근법에서 애자일로 전환하는 조직에 있다. 프로젝트 팀이 애자일 전환에 준비되었는지 평가하려면 무엇을 해야 하는가? | 팀의 역량을 검토하여 필요한 기술이 있는지 확인한다 | 인프라를 평가하여 팀에 적절한 장비와 커뮤니케이션 도구가 있는지 확인한다 | 유사 분야의 벤치마크 분석을 수행하여 구조를 따를 수 있는지 확인한다 | 고객 거버넌스 문서를 검토하여 설정된 기대에 부합하는지 확인한다 | 조직 문화를 평가하여 심리적 안전을 촉진하기 위해 더 필요한 것이 있는지 확인한다 | A, B, E | 애자일 전환 준비를 평가할 때, PM은 세 가지 조치를 취해야 한다: 팀 역량 검토(A), 인프라 평가(B), 조직 문화 평가(E). 기술, 도구, 문화가 애자일 성공의 기반이다. 벤치마크 분석(C)은 외부 비교이지 내부 준비가 아니다. 고객 거버넌스(D)는 내부 전환 준비와 무관하다.
1930 | A project manager recently joined the company. At the interview, the project manager demonstrated experience with agile delivery, and the project management office (PMO) manager asked for assistance in implementing agile. What should the project manager do to initiate the adoption of agile within the company? | Request that all the project managers and business managers receive training in the agile framework used previously by the project manager. | Assess the organization ' s culture to determine if agile can be used in project delivery and determine the practices to be used. | Organize agile workshops with the developers and testers to gain their support in using agile approaches for their projects. | Advise the PMO manager to continue with the company ' s current predictive approaches until all the projects in execution are closed. |  | B | Before implementing agile within an organization, the project manager should assess the organization's culture, readiness, and maturity to adopt agile methods. This assessment determines which agile practices and frameworks best fit the organization's context, project types, and team capabilities, supporting a smooth and successful transition. Requesting training for all managers (A) prescribes a solution before understanding the organization's needs. Organizing workshops with developers and testers (C) engages only part of the organization and skips the cultural assessment. Advising the PMO to wait until current projects close (D) delays adoption indefinitely and ignores the opportunity for gradual transition. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Resources | Planning | Be an Accountable Leader | Plan Resource Management | Hybrid/Tailoring | 새 PM이 애자일 경험으로 채용되었다. PMO 관리자가 애자일 방법론이 프로젝트 납품에 적합한지 논의하고 싶어 한다. PM은 무엇을 먼저 해야 하는가? | 모든 PM과 비즈니스 관리자가 애자일 프레임워크 교육을 받도록 요청한다 | 조직 문화를 평가하여 애자일이 프로젝트 납품에 사용될 수 있는지 확인하고 적절한 접근법을 결정한다 | 개발자와 테스터와 애자일 워크숍을 조직하여 지원을 얻는다 | PMO 관리자에게 모든 프로젝트가 보고될 때까지 현재 예측형 접근법을 계속하도록 조언한다 |  | B | 애자일 구현 전에 PM은 조직 문화, 준비도, 성숙도를 평가해야 한다. 이 평가가 어떤 애자일 실천법이 적합한지 결정한다. 전체 교육(A)은 평가 전에 과도하다. 개발자/테스터 워크숍(C)은 부분적이다. 현 접근법 유지(D)은 소극적이다.
1931 | Halfway through project execution, stakeholders ask for equipment that was expected to be procured. The project manager explains that the equipment was purchased, but differs from what the stakeholders are currently asking for. This is because the initial requirements were changed during a previous meeting. What should the project manager have done to avoid this situation? | Ensured procurement contracts were able be canceled when situations like this arise | Ensured project requirements were validated and communicated with the procurement team | Ensured changing stakeholder needs and requests were properly monitored | Ensured that communications were sent to all stakeholders when requirements change |  | D | To avoid situations where stakeholders are unaware of requirement changes affecting procurement, the project manager should have ensured that communications were sent to all stakeholders when requirements changed. Clear, timely communication about scope or requirement alterations prevents misunderstandings about project deliverables. Ensuring contracts could be canceled (A) is a contract management detail, not a communication solution. Validating requirements with procurement (B) is one channel but does not cover all stakeholders. Monitoring changing needs (C) describes tracking but not the active communication needed. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 실행 중 이해관계자가 조달 예정이었던 장비를 요청한다. 요구사항이 변경된 것을 이해관계자가 모르고 있었다. PM이 이전에 무엇을 했어야 하는가? | 이런 상황이 발생할 때 조달 계약이 취소될 수 있도록 했다 | 프로젝트 요구사항이 검증되고 조달 팀과 소통되도록 했다 | 변화하는 이해관계자 요구와 요청이 적절히 모니터링되도록 했다 | 요구사항이 변경될 때 모든 이해관계자에게 커뮤니케이션이 발송되도록 했다 |  | D | 이해관계자가 요구사항 변경을 모르는 상황을 방지하려면, PM은 요구사항 변경 시 모든 이해관계자에게 커뮤니케이션이 발송되도록 했어야 한다. 적시 커뮤니케이션이 인식 격차를 방지한다. 계약 취소(A)는 조달 문제이다. 요구사항 검증(B)은 부분적이다. 모니터링(C)은 소통 없이 부족하다.
1932 | An organization is about to start a time-critical project and has decided to use an agile approach for the first time. However, stakeholders are worried that they will not be able to verify the status of the project, since they believe that their usual governance model will not work for an agile project. What should the project manager do? | Review the governance structure to reflect scope changes. | Recommend following the existing governance structure with the project team. | Discuss using a hybrid governance structure with stakeholders. | Meet with stakeholders to discuss and review the governance structure. |  | D | When stakeholders are concerned that existing governance structures will not work for the organization's first agile project, the project manager should meet with stakeholders to discuss and review the governance structure. This collaborative approach ensures governance is adapted to support agile transparency and delivery while satisfying organizational oversight needs. Reviewing governance only for scope changes (A) misidentifies the issue—it is about governance suitability, not scope. Recommending the existing governance structure unchanged (B) is too rigid for agile. Discussing a hybrid governance structure (C) may become the outcome but should not be assumed without stakeholder input. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 조직이 처음으로 애자일 접근법을 사용하는 시간 중요 프로젝트를 시작하려 한다. 이해관계자가 기존 거버넌스 구조가 작동하지 않을 것이라고 우려한다. PM은 무엇을 해야 하는가? | 범위 변경을 반영하도록 거버넌스 구조를 검토한다 | 프로젝트 팀과 기존 거버넌스 구조를 따르도록 권장한다 | 이해관계자와 하이브리드 거버넌스 구조 사용을 논의한다 | 이해관계자와 만나 거버넌스 구조를 논의하고 검토한다 |  | D | 이해관계자가 기존 거버넌스 구조가 애자일에 맞지 않다고 우려할 때, PM은 이해관계자와 만나 거버넌스 구조를 논의하고 검토해야 한다. 협력적 검토가 적절한 거버넌스를 결정한다. 범위 변경 반영(A)은 범위가 아닌 거버넌스 문제이다. 기존 구조 유지(B)는 우려를 무시한다. 하이브리드 구조(C)는 논의 전에 결론을 내린다.
1933 | An organization is undergoing an agile transformation and migrating most of its projects from a predictive approach. The CFO expressed a concern that predictability on both costs and scope will be lost with the new agile approach. What should the project manager do? | Submit a report to all key stakeholders on the cost-benefit analysis of the new approach and detail how the company will save money. | Apply influence with other key stakeholders on the board to mitigate any risks that may be generated by the CFO ' s position on the matter. | Provide mentoring to the CFO, who is a key stakeholder in the project, and clarify the benefits of an agile approach. | Ask the CEO to intervene by asking for support from the executive board to accelerate the company ' s transformation. |  | C | The correct answer is C. Provide mentoring to the CFO, who is a key stakeholder in the project, and clarify the benefits of an agile approach. In agile environments, the PM should focus on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and ceremonies. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 조직이 애자일 전환 중이다. CFO가 지원을 거부하여 전환 일정에 영향을 미치고 있다. PM은 무엇을 해야 하는가? | 모든 주요 이해관계자에게 새 접근법의 비용편익분석 보고서를 제출한다 | 이사회의 다른 주요 이해관계자에게 영향력을 행사하여 리스크를 완화한다 | 주요 이해관계자인 CFO에게 멘토링을 제공하고 애자일 접근법의 이점을 명확히 한다 | CEO에게 경영위원회의 지원을 요청하여 회사 전환을 가속하도록 개입을 요청한다 |  | C | 정답은 C이다. 주요 이해관계자인 CFO에게 멘토링을 제공하고 애자일 접근법의 이점을 명확히 한다. 애자일 환경에서 PM은 퍼실리테이션, 코칭, 이해관계자 참여에 집중해야 한다. 보고서 제출(A)은 일방적이다. 영향력 행사(B)는 우회적이다. CEO 개입(D)은 에스컬레이션이다.
1934 | A new member was included on a project team in an ongoing software project. This team member was the only available resource but does not have the proper experience to accomplish the activities. What should the project manager do to ensure this team member's lack of experience does not negatively impact the project? | Schedule a training course for the new team member to fill in their gaps in experience. | Log this as an issue in the project issue log and speak with the resource manager. | Provide weekly feedback to all project team members, including the new member. | Ensure that coaching meetings are in place for this team member within the project timeline. |  | D | When a new team member lacks proper experience for project activities, the project manager should ensure coaching meetings are in place within the project timeline. Structured coaching develops the team member's capabilities while maintaining project performance. Scheduling a training course (A) may not align with project timing. Logging as an issue and speaking to the resource manager (B) treats it as a problem rather than a development opportunity. Providing weekly feedback to all members (C) is general rather than targeted. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 진행 중인 소프트웨어 프로젝트에 새 팀원이 포함되었다. 이 팀원은 프로젝트 활동에 대한 적절한 경험이 부족하다. PM은 무엇을 해야 하는가? | 새 팀원의 경험 격차를 메우기 위한 교육 과정을 예약한다 | 프로젝트 이슈 로그에 이를 이슈로 기록하고 자원 관리자와 대화한다 | 새 팀원을 포함한 모든 프로젝트 팀원에게 주간 피드백을 제공한다 | 프로젝트 일정 내에서 이 팀원을 위한 코칭 회의가 마련되도록 한다 |  | D | 새 팀원이 적절한 경험이 부족할 때, PM은 프로젝트 일정 내에서 코칭 회의가 마련되도록 해야 한다. 구조화된 코칭이 일정을 유지하면서 팀원을 개발한다. 교육(A)은 외부 과정으로 시간이 걸린다. 이슈 로그(B)는 문제 해결이 아닌 기록이다. 주간 피드백(C)은 개별 맞춤이 아니다.
1935 | A team is developing an experimental program to be used by the public. What should the project manager do to ensure the desired benefits are achieved? | Ensure a review is done with a representative group of users. | Meet with government officials to review policy requirements. | Document the features fully and update the specifications. | Ensure that the project team fully tests the program. |  | A | When developing an experimental program for public use, the project manager should ensure a review is done with a representative group of users to validate that desired benefits are achieved. User feedback confirms value alignment. Full team testing (D) checks quality, not benefits. Meeting government officials (B) ensures compliance, not benefit realization. Documenting features (C) controls scope, not outcomes. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 팀이 대중이 사용할 실험적 프로그램을 개발 중이다. PM은 원하는 혜택이 달성되도록 무엇을 해야 하는가? | 대표적 사용자 그룹과 검토가 이루어지도록 한다 | 정부 관계자와 만나 정책 요구사항을 검토한다 | 기능을 완전히 문서화하고 사양을 업데이트한다 | 프로젝트 팀이 프로그램을 완전히 테스트하도록 한다 |  | A | 대중용 실험적 프로그램을 개발할 때, PM은 대표적 사용자 그룹과 검토가 이루어지도록 해야 한다. 사용자 피드백이 원하는 혜택 달성을 검증한다. 정부 관계자(B)는 정책이지 사용성이 아니다. 문서화(C)는 내부 활동이다. 팀 테스트(D)는 기술적 테스트이지 사용자 검증이 아니다.
1936 | A project manager for a factory construction project in a small town is evaluating the necessary actions to engage stakeholders. The local community is speculating the impact of the facility. There are rumors of job opportunities and environmental impacts which are listed on the project risk matrix. What should the project manager do with regard to community engagement in this situation? | Focus on the sideward stakeholders only and let the organization manage the community. | Build channels to extend communication efforts to the local community | Include the local union representative in the high-power, high-impact stakeholder group | Use the city administration to address communication with the community |  | B | When a construction project in a small town generates community speculation about job opportunities and environmental impacts, the project manager should build channels to extend communication efforts to the local community. This could include community meetings, newsletters, or a project website to inform and engage stakeholders. Focusing only on sideward stakeholders (A) excludes the community. Including the union representative in the high-power group (C) addresses one stakeholder, not the broader community. Using city administration for communication (D) delegates engagement rather than managing it directly. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Integrate Sustainability | Identify Risks | Sustainability | 소도시의 공장 건설 프로젝트에서 PM이 이해관계자 참여를 위한 조치를 평가 중이다. 지역사회에 취업 기회와 환경 영향에 대한 추측이 있다. PM은 무엇을 해야 하는가? | 측면 이해관계자에만 집중하고 조직이 지역사회를 관리하도록 한다 | 지역사회로 커뮤니케이션 노력을 확장하는 채널을 구축한다 | 지역 노조 대표를 고권한/고영향 이해관계자 그룹에 포함한다 | 시 행정부를 이용하여 지역사회와의 소통을 처리한다 |  | B | 소도시 건설 프로젝트에서 지역사회 추측이 있을 때, PM은 지역사회로 커뮤니케이션 노력을 확장하는 채널을 구축해야 한다. 직접적 소통이 추측을 사실로 대체한다. 측면 이해관계자만(A)은 지역사회를 무시한다. 노조 대표(C)는 특정 그룹만 다룬다. 시 행정부(D)는 간접적이다.
1937 | A project manager is in the process of closing out a project and has been asked by the project management office (PMO) to confirm that the transfer of knowledge to the operations team for support operations has been successfully completed. Which technique should the project manager apply to verify the knowledge transfer? | Expert judgment | Meetings | Regression analysis | Brainstorming |  | A | To verify that knowledge transfer to the operations team has been successfully completed, the project manager should apply expert judgment. Experts with subject matter knowledge and experience in knowledge transfer processes can evaluate whether the transferred knowledge has been comprehensively communicated and understood by the operations team. Meetings (B) provide a forum for discussion but lack the evaluative rigor of expert assessment. Regression analysis (C) is a statistical technique unsuitable for assessing knowledge transfer. Brainstorming (D) generates ideas but does not verify the completeness of knowledge transfer. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Schedule | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | PM이 프로젝트 종료 과정에 있다. PMO가 운영팀에 대한 지식 이전이 성공적으로 완료되었는지 확인하도록 요청했다. 어떤 도구를 사용해야 하는가? | 전문가 판단 | 회의 | 회귀 분석 | 브레인스토밍 |  | A | 운영팀에 대한 지식 이전이 성공적으로 완료되었는지 확인하려면, PM은 전문가 판단을 적용해야 한다. 주제 전문 지식과 경험을 가진 전문가가 지식 이전의 완성도를 평가한다. 회의(B)는 검증보다 소통이다. 회귀 분석(C)은 통계적 도구이다. 브레인스토밍(D)은 아이디어 생성이지 검증이 아니다.
1938 | A project management office (PMO) is following the execution of an organization's critical project. Some of the project phases are experiencing serious delays due to an international supply chain crisis. Project team members suggested revisiting the planned project phases to maintain the project's value delivery. What should the project manager do? | Develop a contingency plan and seek alternative suppliers. | Update the project schedule in response to the external crisis. | Schedule a meeting with the project sponsor to report and discuss the issue. | Assess and consolidate projects phases and update the project management plan. |  | D | When serious delays from an international supply chain crisis affect project phases and team members suggest revisiting planned phases, the project manager should assess and consolidate project phases and update the project management plan. Restructuring phases maintains value delivery. Developing a contingency plan (A) is one aspect but does not address phase restructuring. Updating the schedule alone (B) does not address phase consolidation. Meeting with the sponsor (C) informs but does not solve the problem. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | Traditional PM | PMO가 조직의 중요 프로젝트 실행을 추적 중이다. 국제 공급망 위기로 심각한 지연이 발생했다. 팀원들이 계획된 단계 재검토를 제안한다. PM은 무엇을 해야 하는가? | 비상 계획을 개발하고 대체 공급자를 찾는다 | 외부 위기에 대응하여 프로젝트 일정을 업데이트한다 | 프로젝트 스폰서와 회의를 예약하여 이슈를 보고하고 논의한다 | 프로젝트 단계를 평가하고 통합하여 프로젝트 관리 계획을 업데이트한다 |  | D | 공급망 위기로 심각한 지연이 발생하고 팀이 단계 재검토를 제안할 때, PM은 프로젝트 단계를 평가하고 통합하여 관리 계획을 업데이트해야 한다. 통합적 접근이 전체 프로젝트에 미치는 영향을 다룬다. 비상 계획(A)은 부분적이다. 일정 업데이트(B)는 일정만 다룬다. 스폰서 보고(C)는 행동이 아닌 보고이다.
1939 | A project manager has an engineering team mostly comprised of new hires. The project manager has to carefully predict in which stage of the project they will need to spend most of their time to ensure the team is properly integrated and performing well. In which stage of the project would the project manager need a greater effort to lead them? | Performing | Storming | Norming | Forming |  | D | The correct answer is D. Forming. Understanding Tuckman's stages of team development helps the PM anticipate team needs and provide appropriate leadership at each stage. | People | Build a Team | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Adopt a Holistic View | Develop Team | Traditional PM | PM이 대부분 신규 채용으로 구성된 엔지니어링 팀을 가지고 있다. 새 팀의 전형적 행동을 예측해야 한다. 팀은 현재 어느 발전 단계에 있는가? | 수행기 | 격동기 | 규범기 | 형성기 |  | D | 정답은 D이다. 형성기. 터크만의 팀 발전 단계를 이해하면 PM이 각 단계에서 팀의 요구를 예측하고 적절한 리더십을 제공할 수 있다. 대부분 신규 채용인 팀은 형성기에 있다.
1940 | A company was acquired, and the new company management asked the project manager to begin using a specific set of metrics immediately to measure team performance. The project manager is working on a predictive project and thinks this request will distract the team and delay the project. What should the project manager do first? | Support the required metrics during the next project phase. | Involve the team in reviewing the proposed metrics. | Request an extension to implement the new metrics. | Assess and analyze the impact of using these metrics. |  | D | When new company management requires specific metrics to be implemented immediately during an ongoing predictive project, the project manager should first assess and analyze the impact of using these metrics. Understanding the potential effects on project performance, timeline, and team morale enables informed decision-making before implementation. Supporting metrics in the next phase (A) is premature without impact assessment. Involving the team in reviewing metrics (B) is helpful but follows the assessment. Requesting an extension (C) assumes disruption without validating it. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 회사가 인수되었고 새 경영진이 진행 중인 예측형 프로젝트에 특정 메트릭스를 즉시 사용하도록 요청했다. PM은 무엇을 먼저 해야 하는가? | 다음 프로젝트 단계에서 필요한 메트릭스를 지원한다 | 팀을 참여시켜 제안된 메트릭스를 검토한다 | 새 메트릭스를 구현하기 위한 연장을 요청한다 | 이 메트릭스 사용의 영향을 평가하고 분석한다 |  | D | 새 경영진이 진행 중인 프로젝트에 즉시 특정 메트릭스를 사용하도록 요구할 때, PM은 먼저 이 메트릭스 사용의 영향을 평가하고 분석해야 한다. 영향 분석이 정보에 기반한 의사결정의 기초이다. 다음 단계 지원(A)은 평가 없이 지연한다. 팀 검토(B)는 유용하지만 영향 분석이 먼저이다. 연장 요청(C)은 영향 파악 전에 성급하다.
1941 | Project A is critical for the company and must be completed within nine months. The project charter has been signed but the project scope statement has not been prepared. Management asks the project manager to move forward with the project without an approved project scope statement. What should the project manager do next? | Escalate the issue to the project sponsor and add it to the risk register | Refuse to work on the project because management is not following standard project management practices | Meet with management to explain the potential problems with running a project without a project scope statement | Start the project with inputs from the project charter to save time |  | C | When management pushes to start a project without an approved scope statement, the PM should meet with management to explain the risks—including scope creep, misaligned expectations, poor quality, increased risks, and wasted resources. The scope statement provides a common understanding of deliverables and work required among stakeholders. Escalating to the sponsor (A) should follow this conversation, not precede it. Refusing to work (B) is unprofessional. Starting from the project charter alone (D) lacks the detail needed to define and control project scope effectively. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 프로젝트 A가 회사에 중요하며 9개월 내 완료되어야 한다. 헌장이 서명되었으나 경영진이 범위 기술서 없이 시작하도록 압박한다. PM은 무엇을 해야 하는가? | 이슈를 프로젝트 스폰서에게 에스컬레이션하고 리스크 등록부에 추가한다 | 경영진이 표준 프로젝트 관리 관행을 따르지 않으므로 프로젝트 작업을 거부한다 | 경영진과 만나 범위 기술서 없이 프로젝트를 실행할 때의 잠재적 문제를 설명한다 | 시간을 절약하기 위해 프로젝트 헌장의 입력으로 프로젝트를 시작한다 |  | C | 경영진이 범위 기술서 없이 시작하도록 압박할 때, PM은 경영진과 만나 범위 기술서 없이 프로젝트를 실행할 때의 리스크—범위 변경, 기대 불일치, 품질 저하—를 설명해야 한다. 교육적 접근이 이해를 촉진한다. 에스컬레이션(A)은 직접 소통 전에 과도하다. 거부(B)는 비협조적이다. 헌장으로 시작(D)은 리스크를 무시한다.
1942 | During project implementation, a critical performance issue is identified by team members. What should the project manager do? | Work with the project stakeholders to address the performance issue. | Submit a change request to handle the performance issue. | Pass the performance issue to subject matter experts (SMEs) to handle. | Review the tender requirements on the related performance issue. |  | A | When a critical performance issue is identified during project implementation, the project manager should work with project stakeholders to address the performance issue. Collaborative engagement ensures comprehensive understanding and resolution. Submitting a change request (B) is premature before assessment. Passing the issue to SMEs (C) delegates without PM leadership. Reviewing tender requirements (D) focuses on procurement, not the current issue. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 프로젝트 구현 중 팀원이 중요한 성능 이슈를 식별했다. PM은 무엇을 해야 하는가? | 프로젝트 이해관계자와 협력하여 성능 이슈를 해결한다 | 성능 이슈를 처리하기 위한 변경 요청을 제출한다 | 성능 이슈를 주제 전문가(SME)에게 전달하여 처리하게 한다 | 관련 성능 이슈에 대한 입찰 요구사항을 검토한다 |  | A | 중요한 성능 이슈가 식별될 때, PM은 프로젝트 이해관계자와 협력하여 해결해야 한다. 협력적 참여가 포괄적 해결을 보장한다. 변경 요청(B)은 분석 후에 한다. SME 전달(C)은 PM의 참여를 배제한다. 입찰 요구 검토(D)는 관련이 낮다.
1943 | A project manager is leading a project to develop accounting software for a trading firm. As the outcomes are being delivered, a new risk is identified regarding an indirect tax regulation that is being changed by the government in the next 6 months. This risk will have a significant impact on the project outcomes. What should the project manager do next? | Assess the impact of the risk with an expert and prioritize further outcomes with the client. | Determine the impact of the risk and prioritize outcomes that do not affect the tax module. | Analyze the impact of the risk and discuss with the team to determine how to separate the tax module. | Delay developing the indirect tax module until the tax regulation comes into effect. |  | A | When a new risk is identified regarding upcoming government tax regulation changes that will significantly impact project outcomes, the project manager should assess the impact of the risk with an expert and prioritize further outcomes with the client. Expert assessment ensures accurate impact evaluation, and client collaboration ensures aligned priorities. Determining impact and prioritizing unaffected outcomes (B) avoids the issue. Analyzing impact and separating the tax module (C) assumes a solution prematurely. Delaying the tax module development (D) may not be feasible. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Schedule | Planning | Be an Accountable Leader | Define Activities | Traditional PM | PM이 거래 회사를 위한 회계 소프트웨어 개발 프로젝트를 이끌고 있다. 정부 세금 규제 변경이 프로젝트 결과에 큰 영향을 미칠 새 리스크가 식별되었다. PM은 무엇을 해야 하는가? | 전문가와 리스크 영향을 평가하고 고객과 추가 결과물의 우선순위를 정한다 | 리스크 영향을 결정하고 세금 모듈에 영향을 미치지 않는 결과물에 우선순위를 둔다 | 리스크 영향을 분석하고 팀과 세금 모듈을 분리하는 방법을 논의한다 | 세금 규제가 시행될 때까지 간접세 모듈 개발을 연기한다 |  | A | 정부 세금 규제 변경이 프로젝트에 큰 영향을 미칠 때, PM은 전문가와 리스크 영향을 평가하고 고객과 추가 결과물의 우선순위를 정해야 한다. 전문가 참여와 고객 협력이 최적의 대응을 보장한다. 영향만 결정(B)은 고객 참여가 없다. 모듈 분리(C)는 기술적 해결만 다룬다. 개발 연기(D)는 수동적이다.
1944 | During an ongoing project, a key resource asks the project manager about the project purpose and if it is aligned with the organization's strategy. What should the project manager share with the key resource? | The updated scope management plan | The updated project management plan | The updated benefits management plan | The updated communications management plan |  | B | When a key resource asks about the project purpose and strategic alignment, the project manager should share the updated project management plan. This comprehensive document integrates all subsidiary plans and baselines, providing context on project objectives, scope, benefits, risks, and strategic alignment. The scope management plan (A) covers scope only, not strategic alignment. The benefits management plan (C) addresses benefits realization but not the complete project context. The communications management plan (D) covers communication methods, not project purpose. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Predictive | Baseline & Change Control | People | Plan and Manage Communication | Governance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 진행 중인 프로젝트에서 핵심 자원이 PM에게 프로젝트 목적과 전략적 정렬에 대해 질문한다. PM은 어떤 문서를 공유해야 하는가? | 업데이트된 범위 관리 계획 | 업데이트된 프로젝트 관리 계획 | 업데이트된 혜택 관리 계획 | 업데이트된 커뮤니케이션 관리 계획 |  | B | 핵심 자원이 프로젝트 목적과 전략적 정렬에 대해 질문할 때, PM은 업데이트된 프로젝트 관리 계획을 공유해야 한다. 이 포괄적 문서가 모든 하위 계획을 통합하고 프로젝트의 목적과 전략적 맥락을 제공한다. 범위 관리 계획(A)은 범위만 다룬다. 혜택 관리 계획(C)은 혜택만 다룬다. 커뮤니케이션 계획(D)은 소통만 다룬다.
1945 | A vendor informed the project manager that a critical resource will be on a long leave of absence. The project team reviewed the pending vendor deliverables and identified an alternative solution, but the solution will incur an additional cost. The project is currently on schedule and slightly under budget. What should the project manager do next? | Request a replacement resource | Perform Integrated Change Control | Perform a cost-benefit analysis | Implement risk responses |  | B | When a vendor's critical resource goes on long leave and the team identifies an alternative solution with additional cost while the project is on schedule and slightly under budget, the project manager should perform Integrated Change Control. This evaluates the alternative solution's impact on scope, schedule, cost, and risk, ensuring proper approval before implementation. Requesting a replacement resource (A) does not evaluate the alternative. Performing cost-benefit analysis (C) is part of change control but not the complete process. Implementing risk responses (D) is premature without formal change evaluation. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 벤더가 핵심 자원이 장기 휴가에 들어갈 것이라고 알렸다. 팀이 대안을 검토했고 추가 비용이 드는 대안 솔루션을 식별했다. 프로젝트는 일정에 맞고 약간 예산 미만이다. PM은 무엇을 해야 하는가? | 대체 자원을 요청한다 | 통합 변경 통제를 수행한다 | 비용편익 분석을 수행한다 | 리스크 대응을 실행한다 |  | B | 벤더의 핵심 자원이 장기 휴가이고 추가 비용이 드는 대안 솔루션이 식별될 때, PM은 통합 변경 통제를 수행해야 한다. 비용 영향이 있는 변경은 공식적 변경 통제 프로세스를 거쳐야 한다. 대체 자원 요청(A)은 변경 통제 없이 행동이다. 비용편익 분석(C)은 변경 통제의 일부일 수 있지만 전체가 아니다. 리스크 대응(D)은 사전 계획된 대응이 있어야 한다.
1946 | The testing backlog for a hybrid project has increased significantly and is becoming a bottleneck. The team has researched a tool that could resolve the bottleneck, and the project manager has been informed. What should the project manager do next? | Escalate the issue with the product owner. | Enroll team members in training on the tool. | Reduce the testing scope of the backlog. | Add developers to remove the backlog. |  | B | When the testing backlog has become a bottleneck and the team has researched a tool to resolve it, the project manager should enroll team members in training on the tool. Proper training ensures effective adoption. Escalating to the product owner (A) delegates the decision. Reducing testing scope (C) compromises quality. Adding developers (D) addresses capacity but not the bottleneck. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Finance | Planning | Embed Quality | Determine Budget | Hybrid/Tailoring | 하이브리드 프로젝트의 테스팅 백로그가 크게 증가하여 병목이 되고 있다. 팀이 이를 해결할 도구를 연구했다. PM은 무엇을 해야 하는가? | 제품 책임자에게 이슈를 에스컬레이션한다 | 팀원을 해당 도구 교육에 등록한다 | 백로그의 테스팅 범위를 줄인다 | 개발자를 추가하여 백로그를 제거한다 |  | B | 테스팅 백로그가 병목이 되고 팀이 해결 도구를 연구했을 때, PM은 팀원을 해당 도구 교육에 등록해야 한다. 적절한 교육이 효과적인 도구 활용을 보장한다. 에스컬레이션(A)은 팀 수준에서 해결 가능하다. 테스팅 범위 축소(C)는 품질을 훼손한다. 개발자 추가(D)는 테스팅 역량과 무관하다.
1947 | A product owner has provided the team with a prioritized backlog for the initial launch of a new product. After analysis, the team concludes that some work is missing to support the initial launch and provides this information to the product owner. The product owner acknowledges the missing work and adds it to the bottom of the backlog. The team is not happy with the prioritization that the missing work received. What should the project manager do in this situation? | Let the project team pull the recommended work from the bottom of the backlog tomaximize value creation. | Analyze and reprioritize the backlog and provide the decision to the product ownerand team. | Empower the product owner by supporting the decision and instructing the team to follow the prioritization as provided. | Recommend the product owner prioritize the missing work higher because it isneeded for the minimum viable product (MVP). |  | D | When the team identifies missing work needed for the initial launch but the product owner adds it to the bottom of the backlog, the project manager should recommend that the product owner prioritize the missing work higher because it is needed for the MVP. The PM advises on MVP requirements. Letting the team pull from the bottom (A) bypasses PO authority. Analyzing and providing the decision to the PO (B) overrides the PO. Supporting the PO's decision without discussion (C) ignores the team's valid concern. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 제품 책임자가 신제품 초기 출시를 위해 우선순위화된 백로그를 제공했다. 분석 후 팀이 초기 출시에 필요한 누락된 작업을 식별했으나 백로그 하단에 추가되었다. PM은 무엇을 해야 하는가? | 팀이 백로그 하단에서 권장 작업을 가져와 가치 창출을 극대화하도록 한다 | 백로그를 분석하고 재우선순위화하여 제품 책임자와 팀에게 결정을 제공한다 | 제품 책임자를 지원하여 결정을 권한 부여하고 팀에 우선순위를 따르도록 지시한다 | 제품 책임자에게 누락된 작업을 MVP에 필요하므로 더 높은 우선순위로 지정하도록 권장한다 |  | D | 팀이 초기 출시에 필요한 누락 작업을 식별했으나 백로그 하단에 추가되었을 때, PM은 제품 책임자에게 MVP에 필요하므로 더 높은 우선순위로 지정하도록 권장해야 한다. 이는 제품 책임자의 역할을 존중하면서 가치 전달을 보장한다. 하단에서 가져오기(A)는 우선순위 체계를 무시한다. PM이 재우선순위화(B)는 제품 책임자 역할 침해이다. 기존 결정 따르기(C)는 MVP 리스크를 무시한다.
1948 | Key decision makers are meeting to define the objectives of a new database migration project. There are many disagreements about scope and timelines among the leaders of various company departments. How should the project manager impartially prioritize the requirements to be integrated? | Give each department a fixed budget that will cover ten requirements. | Ensure the CEO selects the requirements from all department leaders. | Retain only requirements that result in profitable revenue growth. | Rank the requirements with the highest benefit-cost ratio as more important. |  | D | When key decision makers disagree about scope and timelines for a database migration project, the project manager should rank requirements with the highest benefit-cost ratio as more important. This provides an objective, quantitative basis for prioritization that transcends departmental biases. Giving each department a fixed budget for ten requirements (A) is arbitrary. Having the CEO select requirements (B) concentrates decision-making. Retaining only profitable revenue requirements (C) ignores strategic and operational needs. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Scope & Requirements Mgmt | Process | Plan and Manage Finance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 주요 의사결정자들이 새 데이터베이스 마이그레이션 프로젝트의 목표를 정의하기 위해 회의 중이다. 범위와 일정에 대한 의견 불일치가 많다. PM은 무엇을 해야 하는가? | 각 부서에 10개 요구사항을 충당할 고정 예산을 제공한다 | CEO가 모든 부서장의 요구사항에서 선택하도록 한다 | 수익성 있는 매출 성장을 가져오는 요구사항만 유지한다 | 가장 높은 편익-비용 비율을 가진 요구사항을 더 중요하게 순위 매긴다 |  | D | 범위와 일정에 대한 의견 불일치가 있을 때, PM은 가장 높은 편익-비용 비율을 가진 요구사항을 더 중요하게 순위 매겨야 한다. 객관적 분석 기반 우선순위화가 주관적 논쟁을 해결한다. 고정 예산(A)은 임의적이다. CEO 선택(B)은 독단적이다. 매출 성장만(C)은 제한적 기준이다.
1949 | A key project stakeholder recently joined the project and is questioning some of the previously made decisions. This is starting to affect project execution. What should the project manager do? | Update the risk register with a new risk of potential project changes as a result of stakeholder misalignment. | Provide the stakeholder with a link to a file-sharing site where the supporting documents for decisions are filed. | Reach out to the stakeholder via phone to explain that all decisions have been agreed upon with their predecessor. | Schedule a meeting with the stakeholder to provide an overview of the project, including the agreed- upon decisions. |  | D | The PM should schedule a meeting with the new stakeholder to provide a comprehensive project overview, including previously agreed-upon decisions. Effective stakeholder management requires proactive engagement, understanding stakeholder needs, and maintaining transparent communication. Addressing concerns early ensures alignment with project objectives and prevents disruption to ongoing work. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 주요 이해관계자가 최근 프로젝트에 합류하여 이전 결정에 의문을 제기한다. PM은 무엇을 해야 하는가? | 이해관계자 오정렬로 인한 잠재적 프로젝트 변경의 새 리스크를 리스크 등록부에 업데이트한다 | 이해관계자에게 결정에 대한 지원 문서가 있는 파일 공유 사이트 링크를 제공한다 | 이해관계자에게 전화하여 모든 결정이 전임자와 합의되었음을 설명한다 | 이해관계자와 회의를 예약하여 합의된 결정을 포함한 프로젝트 개요를 제공한다 |  | D | 새 이해관계자가 이전 결정에 의문을 제기할 때, PM은 회의를 예약하여 합의된 결정을 포함한 포괄적 프로젝트 개요를 제공해야 한다. 사전적 이해관계자 참여가 이해와 수용을 구축한다. 리스크 등록(A)은 소극적이다. 링크 제공(B)은 맥락 없이 문서만 준다. 전화 설명(C)은 포괄적이지 않다.
1950 | A project manager is managing the development of a dental wire bending machine. The machine is compatible with the three most popular dental wires in the market, which covers 90% of the market. The prototype is now under testing for certification. The manufacturer of one of the three wires announced they will be producing a different wire that will be incompatible with the machine. This will result in a 25% loss of market coverage from the initially predicted 90% coverage. What should the project manager do? | Meet with the wire manufacturer to secure enough of the existing stock for the machine | Meet with the sales and marketing representatives and ask them to convince the manufacturer to reconsider | Investigate the impact of this issue with the team and survey the market for alternative wires with similar characteristics | Stop the project and kick off another project to apply alternative wires for the machine |  | C | When a wire manufacturer announces an incompatible replacement wire that will reduce market coverage by 25%, the project manager should investigate the impact with the team and survey the market for alternative wires with similar characteristics. Thorough analysis identifies viable options before committing to a response. Meeting the manufacturer for existing stock (A) is a short-term fix. Asking sales to convince the manufacturer (B) is unlikely to succeed. Stopping the project for a new one (D) is extreme. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 치과 와이어 벤딩 머신 개발 중이다. 와이어 제조사가 호환되지 않는 대체 와이어를 발표하여 시장 커버리지가 25% 감소할 수 있다. PM은 무엇을 해야 하는가? | 와이어 제조사를 만나 기존 재고를 확보한다 | 영업 대표와 만나 제조사에게 재고를 요청하도록 설득한다 | 팀과 이 이슈의 영향을 조사하고 대안 와이어 시장을 조사한다 | 프로젝트를 중단하고 대안 와이어를 적용하는 새 프로젝트를 시작한다 |  | C | 와이어 제조사가 호환되지 않는 대체품을 발표할 때, PM은 팀과 영향을 조사하고 대안 와이어 시장을 조사해야 한다. 체계적 영향 분석과 대안 탐색이 최선이다. 기존 재고 확보(A)는 임시 조치이다. 설득(B)은 PM의 통제 범위 밖이다. 프로젝트 중단(D)은 과도하다.
1951 | A company is planning a digitization project. Which action should the project manager take first when defining the project scope? | Assess the current state process to define the scope of the digitization. | Develop the software that will support the current state process. | Redefine the current state process to scope the supporting software. | Digitize the current state process exactly as defined. |  | A | Before defining the digitization project scope, the PM should first assess the current-state process to understand existing problems, needs, and improvement opportunities. This assessment informs scope definition. Digitizing the current process as-is, redefining processes for software support, or developing software directly are all premature actions that should follow—not precede—a thorough current-state assessment. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 회사가 디지털화 프로젝트를 계획 중이다. 프로젝트 범위를 정의할 때 PM이 먼저 취해야 할 조치는? | 현재 상태 프로세스를 평가하여 디지털화 범위를 정의한다 | 현재 상태 프로세스를 지원할 소프트웨어를 개발한다 | 지원 소프트웨어의 범위를 정하기 위해 현재 상태 프로세스를 재정의한다 | 현재 상태 프로세스를 정의된 대로 정확히 디지털화한다 |  | A | 디지털화 프로젝트 범위를 정의하기 전에, PM은 먼저 현재 상태 프로세스를 평가해야 한다. 현재 상태 이해가 문제, 요구, 개선 기회를 파악하게 한다. 소프트웨어 개발(B)은 범위 정의 전에 시기상조이다. 프로세스 재정의(C)는 현재 상태 이해 후에 한다. 그대로 디지털화(D)는 개선 없이 비효율을 복제한다.
1952 | In the initiating phase of a project, the project manager and team members are prioritizing the product backlog along with the product owner. What should the project manager do next? | Produce a value-added product for the customer in each phase of the project. | Produce a value-added product for the customer as continuously as possible. | Produce a value-added product for the customer in the beginning of the project. | Produce a value-added product along with the supporting documentation. |  | A | After prioritizing the product backlog with the product owner, the project manager should produce a value-added product for the customer in each phase of the project. This aligns with agile principles of delivering working software frequently and incrementally. Delivering value continuously (B) is a principle but not a specific next step. Delivering value only at the beginning (C) misses ongoing delivery. Producing value along with supporting documentation (D) shifts focus from delivery to documentation. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 프로젝트 착수 단계에서 PM과 팀이 제품 책임자와 제품 백로그를 우선순위화하고 있다. 다음 단계는? | 프로젝트의 각 단계에서 고객을 위한 부가가치 제품을 생산한다 | 가능한 지속적으로 고객을 위한 부가가치 제품을 생산한다 | 프로젝트 초기에 고객을 위한 부가가치 제품을 생산한다 | 지원 문서와 함께 부가가치 제품을 생산한다 |  | A | 제품 백로그 우선순위화 후, PM은 프로젝트의 각 단계에서 고객을 위한 부가가치 제품을 생산해야 한다. 이는 각 단계에서 가치를 전달하는 애자일 원칙에 부합한다. 지속적 생산(B)은 이상적이나 단계별이 더 현실적이다. 초기에만(C)은 제한적이다. 문서 중심(D)은 가치 전달보다 문서에 집중한다.
1953 | An issue reoccurs six months after a project's go-live date despite being resolved during the project life cycle. What should the project manager have done in the previous phase to avoid this issue? | Discussed the issue with the stakeholders | Asked the project team to conduct more testing with users | Ensured the project team applied a long-term solution for the issue | Ensured the project team documented lessons learned about the issue |  | C | When an issue reoccurs six months after go-live despite being resolved during the project, it indicates that only a temporary fix or workaround was applied rather than addressing the root cause. The project manager should have ensured the project team applied a long-term solution for the issue—one that eliminates or significantly reduces the probability of recurrence. Discussing the issue with stakeholders (A) ensures awareness but not resolution. Conducting more user testing (B) may catch symptoms but does not guarantee a permanent fix. Documenting lessons learned (D) preserves knowledge but does not prevent recurrence if the solution was inadequate. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Closing | Focus on Value | Close Project or Phase | Traditional PM | 프로젝트 가동 후 6개월 만에 프로젝트 수명주기 중 해결된 이슈가 재발했다. PM이 이전에 무엇을 했어야 하는가? | 이해관계자와 이슈를 논의했다 | 프로젝트 팀에 사용자와 더 많은 테스트를 수행하도록 요청했다 | 프로젝트 팀이 이슈에 대한 장기적 해결책을 적용하도록 했다 | 프로젝트 팀이 이슈에 대한 교훈을 문서화하도록 했다 |  | C | 가동 후 6개월에 이슈가 재발하면, 임시 수정만 적용되고 근본 원인이 해결되지 않았음을 나타낸다. PM은 장기적 해결책을 적용했어야 한다. 이해관계자 논의(A)는 해결이 아니다. 추가 테스트(B)는 임시 수정의 한계를 발견하지 못할 수 있다. 교훈 문서화(D)는 유용하지만 재발을 방지하지 않는다.
1954 | A project team consisting of various professionals of different nationalities is struggling to achieve their project deliverables. What should the project manager do? | Ask the human resources (HR) department to conduct performance training. | Ask the functional department manager to replace the team members. | Inform the project sponsor and train the entire team. | Provide the team with support to solve their own problems. |  | D | When a diverse multinational project team struggles with deliverables, the project manager should provide the team with support to solve their own problems. Servant leadership and empowerment foster collaboration and leverage diverse perspectives. Asking HR to conduct performance training (A) is generic. Replacing team members (B) loses institutional knowledge. Informing the sponsor and training the team (C) does not address the team's specific challenges. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 다양한 국적의 전문가로 구성된 프로젝트 팀이 인도물 달성에 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 인사부(HR)에 성과 교육을 실시하도록 요청한다 | 기능 부서 관리자에게 팀원 교체를 요청한다 | 프로젝트 스폰서에게 알리고 전체 팀을 교육한다 | 팀이 자체적으로 문제를 해결할 수 있도록 지원한다 |  | D | 다국적 팀이 인도물에 어려움을 겪을 때, PM은 팀이 자체적으로 문제를 해결할 수 있도록 지원해야 한다. 서번트 리더십과 권한 부여가 팀 자립과 협업을 촉진한다. HR 교육(A)은 외부 의존이다. 팀원 교체(B)는 다양성을 무시한다. 스폰서 알림(C)은 에스컬레이션이 시기상조이다.
1955 | Four new teams have been formed to develop a new product. Several team members ask the project manager who will integrate the different work streams into one backlog. What should the project manager do? | Instruct the team to use the kanban board daily to facilitate alignment of their work item list, allowing them to do their best work. | Advise the teams to work individually and organize an integration iteration every four development sprints. | Create integration tasks and schedule an additional team meeting following the standup meeting to plan the integration. | Advise the teams to collaborate with the product owner in prioritizing the stories, considering dependencies and preventing overlap. |  | D | The PM should advise teams to collaborate with the product owner in prioritizing stories, considering inter-team dependencies and preventing overlap. In agile environments, facilitating team collaboration, removing impediments, and ensuring continuous value delivery across multiple teams are key PM responsibilities. | People | Build a Team | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 4개의 새 팀이 신제품 개발을 위해 구성되었다. 팀원들이 각 팀의 작업을 누가 통합할지 질문한다. PM은 무엇을 해야 하는가? | 팀에게 칸반 보드를 매일 사용하여 작업 목록을 정렬하도록 지시한다 | 팀에게 개별 작업 후 4개 개발 스프린트마다 통합 이터레이션을 조직하도록 조언한다 | 통합 작업을 생성하고 스탠드업 회의 후 추가 팀 회의를 예약한다 | 팀에게 제품 책임자와 협력하여 팀 간 종속성과 중복을 고려하여 스토리를 우선순위화하도록 조언한다 |  | D | 여러 팀이 통합에 대해 질문할 때, PM은 제품 책임자와 협력하여 팀 간 종속성을 고려한 스토리 우선순위화를 조언해야 한다. 협력적 우선순위화가 자연스러운 통합을 촉진한다. 칸반 보드(A)는 도구이지 통합 전략이 아니다. 통합 이터레이션(B)은 피드백이 늦다. 추가 회의(C)는 오버헤드를 증가시킨다.
1956 | Team members are having a discussion with the project manager. In the last retrospective meeting, the team realized that the obsolete equipment could affect the next iteration of the project. The team recommends buying new equipment because it is critical to the success of the final deliverable. What should the project manager do next? | Submit a change request to increase the budget and buy new equipment | Check the project budget to verify if there is enough contingency reserve | Review the cost management plan to determine how to address this issue | Tell the team members that more equipment is not part of the project ' s scope. |  | A | When the team recommends buying new equipment critical to the final deliverable and identified as a risk in retrospective, the project manager should submit a change request to increase the budget and buy new equipment. Formal change control processes authorize budget changes. Checking contingency reserves (B) is a partial step. Reviewing the cost management plan (C) provides guidance but does not authorize changes. Telling the team it is out of scope (D) dismisses a valid risk. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 마지막 회고에서 팀이 최종 인도물에 필수적인 새 장비 구매를 권장했다. 이는 리스크로 식별되었다. PM은 무엇을 해야 하는가? | 예산 증가를 위한 변경 요청을 제출하고 새 장비를 구매한다 | 프로젝트 예산을 확인하여 충분한 비상 예비비가 있는지 확인한다 | 이 이슈를 어떻게 해결할지 결정하기 위해 비용 관리 계획을 검토한다 | 팀원에게 추가 장비는 프로젝트 범위에 포함되지 않는다고 말한다 |  | A | 팀이 최종 인도물에 필수적인 새 장비를 리스크로 식별하고 구매를 권장할 때, PM은 예산 증가를 위한 변경 요청을 제출해야 한다. 변경 통제 프로세스를 통한 공식 요청이 적절하다. 비상 예비비 확인(B)은 범위 변경이 아닌 리스크 대응용이다. 비용 관리 계획 검토(C)는 조치가 아닌 검토이다. 범위 외(D)는 필수 요소를 무시한다.
1957 | A company wants to launch a new product for customers. The project for this new product is in the development phase. Due to an uncertain environment, the project manager has concerns about the feasibility of the project. What should the project manager do in this situation? | Recommend postponing the project until the uncertainty is resolved, | Validate assumptions using appropriate tools to assess the risks. | Highlight the concern to the project sponsor in the next project review meeting, | Refer to the lessons learned to determine the impact on the external environment. |  | B | In environments marked by uncertainty, the PM must validate assumptions and systematically assess risks. Risk management—identifying, evaluating, and controlling uncertain factors—helps avoid or mitigate potential negative impacts on project performance. The PM should maintain composure with ambiguity and respond in an agile yet structured manner. This disciplined approach gives the team confidence that the project continues to take appropriate steps toward delivering its planned outcomes. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 회사가 고객을 위한 신제품을 출시하려 한다. 개발 단계에서 불확실성이 있다. PM은 무엇을 해야 하는가? | 불확실성이 해결될 때까지 프로젝트를 연기하도록 권장한다 | 적절한 도구를 사용하여 가정을 검증하고 리스크를 평가한다 | 다음 프로젝트 검토 회의에서 스폰서에게 우려를 강조한다 | 교훈을 참조하여 외부 환경에 대한 영향을 결정한다 |  | B | 불확실성이 있는 환경에서 PM은 적절한 도구를 사용하여 가정을 검증하고 리스크를 체계적으로 평가해야 한다. 리스크 관리가 불확실한 요소를 식별, 평가, 통제한다. 연기(A)는 수동적이다. 다음 회의까지 대기(C)는 시기를 놓칠 수 있다. 교훈 참조(D)는 유용하지만 현재 가정 검증이 우선이다.
1958 | An agile project for a database migration impacts nearly all business units of the corporation. Every effort has been made to complete the migration before the end-of-support date for the database platform. A new impediment now implies the need to continue use of the old platform another year at a higher support price. What should the product owner do about this situation? | Remove low-value items from the backlog to compensate for the higher cost. | Reprioritize the backlog based on value and cost of delay divided by duration. | Reprioritize the backlog based on story size and competence availability. | Switch to a predictive approach to prevent any further delays to completion. |  | B | When an agile database migration project faces a new impediment requiring extended use of the old platform at higher cost, the product owner should reprioritize the backlog based on value and cost of delay divided by duration. Value-driven prioritization maximizes ROI under constraints. Removing low-value items (A) reduces scope without strategic prioritization. Reprioritizing by story size and competence (C) ignores business value. Switching to predictive (D) contradicts the project approach. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 애자일 DB 마이그레이션 프로젝트가 거의 모든 사업부에 영향을 준다. 새 장애물로 기존 플랫폼을 더 오래 사용해야 하며 비용이 증가한다. 제품 책임자는 무엇을 해야 하는가? | 높은 비용을 보상하기 위해 백로그에서 저가치 항목을 제거한다 | 가치와 지연 비용을 기간으로 나눈 값을 기준으로 백로그를 재우선순위화한다 | 스토리 크기와 역량 가용성을 기준으로 백로그를 재우선순위화한다 | 추가 지연을 방지하기 위해 예측형 접근법으로 전환한다 |  | B | 새 장애물로 비용이 증가할 때, 제품 책임자는 가치와 지연 비용/기간(WSJF)을 기준으로 백로그를 재우선순위화해야 한다. 경제적 우선순위화가 최대 가치를 전달한다. 저가치 항목 제거(A)는 백로그를 축소하지만 최적화가 아니다. 크기/역량 기준(C)은 비즈니스 가치를 무시한다. 예측형 전환(D)은 유연성을 상실한다.
1959 | A project to develop an enterprise resource planning (ERP) system for a university is ongoing. The system should improve business processes through digitalization and elimination of human errors, and also provide end users with simplified and easily accessible services. What should the project manager do to ensure achievement of the intended business value? | Evaluate deliverables against the business case at the end of the life cycle | Evaluate customer feedback and review the business case each time | Evaluate deliverables against the business case continuously | Evaluate each change request and review the business case each time |  | C | When an ERP project aims to improve processes and reduce errors, the project manager should evaluate deliverables against the business case continuously to ensure intended business value. Continuous validation enables early detection of misalignment. Evaluating only at the end (A) is too late. Evaluating with each change request (D) is reactive. Combining customer feedback with reviews (B) is useful but continuous evaluation is the primary approach. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Finance | Monitoring & Controlling | Focus on Value | Control Costs | Traditional PM | 대학교 ERP 시스템 개발 프로젝트가 진행 중이다. 시스템이 프로세스를 개선하고 오류를 줄여야 한다. PM은 어떻게 비즈니스 가치 전달을 보장하는가? | 수명주기 끝에 비즈니스 케이스 대비 인도물을 평가한다 | 매번 고객 피드백을 평가하고 비즈니스 케이스를 검토한다 | 비즈니스 케이스 대비 인도물을 지속적으로 평가한다 | 각 변경 요청을 평가하고 매번 비즈니스 케이스를 검토한다 |  | C | ERP 프로젝트에서 비즈니스 가치 전달을 보장하려면, PM은 비즈니스 케이스 대비 인도물을 지속적으로 평가해야 한다. 지속적 검증이 의도된 비즈니스 가치를 보장한다. 수명주기 끝(A)은 너무 늦다. 고객 피드백만(B)은 비즈니스 케이스와 연결이 부족하다. 변경 요청별(D)은 제한적이다.
1960 | A project has issues arising where the data integration team and the data migration team have areas that overlap. It is not clear who would be responsible for delivery on these areas. What should the project manager do next? | Review the work breakdown structure (WBS) to align the project teams | Review the resource management plan to align the project teams | Review the project scope to align the project teams | Review the project integration plan to align the project teams |  | A | When data integration and data migration teams have overlapping areas with unclear delivery responsibility, the project manager should review the WBS to align the project teams. The WBS clarifies work decomposition and responsibility boundaries. Reviewing the resource management plan (B) addresses people, not work scope. Reviewing the project scope (C) is broader than needed. Reviewing the integration plan (D) addresses dependencies, not task ownership. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | WBS/Decomposition | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 데이터 통합 팀과 데이터 마이그레이션 팀의 영역이 겹치고 납품 책임이 불명확하다. PM은 무엇을 검토해야 하는가? | 작업분류체계(WBS)를 검토하여 프로젝트 팀을 정렬한다 | 자원 관리 계획을 검토하여 프로젝트 팀을 정렬한다 | 프로젝트 범위를 검토하여 프로젝트 팀을 정렬한다 | 프로젝트 통합 계획을 검토하여 프로젝트 팀을 정렬한다 |  | A | 데이터 통합 팀과 마이그레이션 팀의 영역이 겹칠 때, PM은 WBS를 검토해야 한다. WBS가 작업 패키지와 납품 책임을 명확히 한다. 자원 관리 계획(B)은 인력 배치이지 작업 분류가 아니다. 프로젝트 범위(C)는 상위 수준이다. 통합 계획(D)은 프로세스 통합이지 작업 분류가 아니다.
1961 | During a project's initiation phase, a lessons learned sharing session was held with the team from another project. Low construction productivity was discussed as a potential delay to project completion. What should the project manager do next? | Add construction productivity to the risk register and develop a mitigation strategy for site execution | Hire a construction management consultant to develop a comprehensive site execution plan | Prequalify contractors with proven track records to eliminate productivity concerns | Discuss this issue with the project sponsor to request additional funding to implement mitigation |  | A | When low construction productivity is identified as a potential risk during a lessons learned session, the project manager should add it to the risk register and develop a mitigation strategy for site execution. This formally documents the risk and creates actionable plans to reduce its probability or impact. Hiring a consultant for a comprehensive plan (B) may be premature without first registering and analyzing the risk. Prequalifying contractors (C) addresses one cause but does not formally register or analyze the risk. Discussing with the sponsor for additional funding (D) is premature before developing the mitigation strategy. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 프로젝트 착수 단계에서 다른 프로젝트의 교훈 공유 세션이 열렸다. 낮은 시공 생산성이 잠재적 리스크로 식별되었다. PM은 무엇을 먼저 해야 하는가? | 시공 생산성을 리스크 등록부에 추가하고 현장 실행을 위한 완화 전략을 개발한다 | 시공 관리 컨설턴트를 고용하여 포괄적 현장 실행 계획을 개발한다 | 실적이 입증된 계약자를 사전 자격 심사하여 생산성 우려를 제거한다 | 이 이슈를 프로젝트 스폰서와 논의하여 완화 구현을 위한 추가 자금을 요청한다 |  | A | 교훈 세션에서 낮은 시공 생산성이 잠재적 리스크로 식별될 때, PM은 리스크 등록부에 추가하고 완화 전략을 개발해야 한다. 공식 리스크 문서화와 전략 개발이 첫 단계이다. 컨설턴트 고용(B)은 리스크 분석 없이 시기상조이다. 사전 자격 심사(C)는 하나의 완화 방법이지 전체 전략이 아니다. 추가 자금 요청(D)은 전략 개발 후에 한다.
1962 | A project manager has been managing a project for several months when an issue that had not been registered as a risk appeared. This issue may have a big impact on the project. What should the project manager do? | Inform the sponsor that the issue has arisen and that the project ' s success may be uncertain | Hold a meeting with the project team and relevant stakeholders to agree on the best way to manage the issue 1085 | Delay the project until the issue is addressed and no longer presents as a risk to the project. | Avoid managing the issue as it was not registered as a risk for the project and there is no planned response to it. |  | B | When an unregistered risk materializes as an issue with potentially big project impact, the project manager should hold a meeting with the team and relevant stakeholders to agree on the best way to manage it. Collaborative decision-making ensures informed responses. Informing only the sponsor (A) limits input. Delaying the project (C) is premature without a plan. Avoiding management because it was not registered (D) is irresponsible. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | PM이 수개월간 프로젝트를 관리해 왔는데 리스크로 등록되지 않은 이슈가 발생하여 큰 영향을 줄 수 있다. PM은 무엇을 해야 하는가? | 스폰서에게 이슈가 발생했고 프로젝트 성공이 불확실할 수 있음을 알린다 | 프로젝트 팀과 관련 이해관계자와 회의하여 이슈를 관리할 최선의 방법에 합의한다 | 이슈가 해결되어 더 이상 리스크가 되지 않을 때까지 프로젝트를 지연시킨다 | 리스크로 등록되지 않았고 계획된 대응이 없으므로 이슈 관리를 피한다 |  | B | 등록되지 않은 리스크가 이슈로 발현되어 큰 영향을 줄 수 있을 때, PM은 팀과 이해관계자와 회의하여 최선의 관리 방법에 합의해야 한다. 협력적 문제 해결이 효과적이다. 스폰서 알림(A)만으로는 해결이 안 된다. 프로젝트 지연(C)은 과도하다. 관리 회피(D)는 무책임하다.
1963 | What should an agile lead do to ensure their team is set up for success? | Plan quarterly informal meetings or team bonding sessions to encourage the team to work together | Document team tasks and challenges in order to understand when to step in and help a member of the team | Schedule sprint meetings and coaching sessions to discuss project-related information | Pay attention to team dynamics and understand that coaching is done simultaneously at an individual and whole-team level |  | D | The agile lead (Scrum Master) plays a critical role in team success by coaching simultaneously at individual and whole-team levels. This requires awareness of each team member's strengths and weaknesses, as well as the team's collective dynamics. Effective coaching enables continuous improvement and adaptation—core agile principles that help the team achieve its goals more efficiently. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 애자일 리더가 팀의 성공을 보장하기 위해 무엇을 해야 하는가? | 분기별 비공식 회의나 팀 본딩 세션을 계획하여 팀 협력을 장려한다 | 팀 작업과 과제를 문서화하여 언제 개입해야 하는지 파악한다 | 스프린트 회의와 코칭 세션을 예약하여 프로젝트 관련 정보를 논의한다 | 팀 역학에 주의를 기울이고 코칭이 개인 및 전체 팀 수준에서 동시에 이루어짐을 이해한다 |  | D | 애자일 리더(스크럼 마스터)는 개인과 전체 팀 수준에서 동시에 코칭하며 팀 역학에 주의를 기울여야 한다. 각 팀원의 강점과 약점을 파악하고 전체 팀 시너지를 구축한다. 분기별 본딩(A)은 빈도가 부족하다. 작업 문서화(B)는 모니터링이지 코칭이 아니다. 스프린트 회의(C)는 구조적이지만 개인 코칭이 부족하다.
1964 | A verbal announcement is made that the new team member joining the Scrum team has limited mobility. The scrum master is aware that some team members are unsure how the dynamics of the team will change. What should the scrum master do? | Create a stakeholder engagement plan | Design a communications management plan | Update the team charter accordingly. | Set up a meeting to discuss accommodations the team will have to make |  | D | When a new team member with limited mobility joins the Scrum team and existing members are unsure about dynamics, the scrum master should set up a meeting to discuss accommodations the team will need to make. Open discussion fosters inclusion and practical planning. Creating a stakeholder engagement plan (A) is formal and not team-focused. Designing a communications plan (B) is procedural. Updating the team charter (C) may follow but discussion should come first. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Align Stakeholder Expectations | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 새 팀원이 이동 제한이 있다는 구두 발표가 있었다. 기존 팀원들이 팀 역학에 대해 확신이 없다. 스크럼 마스터는 무엇을 해야 하는가? | 이해관계자 참여 계획을 작성한다 | 커뮤니케이션 관리 계획을 설계한다 | 팀 헌장을 적절히 업데이트한다 | 팀이 해야 할 편의 조치를 논의하기 위한 회의를 설정한다 |  | D | 이동 제한이 있는 새 팀원이 합류하고 기존 팀원이 역학에 불확실할 때, 스크럼 마스터는 편의 조치를 논의하기 위한 회의를 설정해야 한다. 개방적 대화가 포용적 환경을 구축한다. 이해관계자 계획(A)은 외부 이해관계자용이다. 커뮤니케이션 계획(B)은 일반 커뮤니케이션이지 편의 조치가 아니다. 헌장 업데이트(C)는 논의 없이 일방적이다.
1965 | A hybrid project team is working on an upgraded version of software for their product owner. The team is also responsible for supporting the existing product and customers. For the last three sprints, the team had to stop their project work and focus on major support items for the product owner. The testers are struggling to cope with the constant changes to the plan, which has resulted in a number of emotional outbursts. How should the project manager proceed? | Schedule a session with the team to discuss the issues and work with them to define aplan to manage the sprints going forward. | Request a replacement for those team members who are unhappy with this way ofworking. | Ask human resources (HR) to send the team members to a change managementworkshop. | Schedule a session with the product owner to explain that no support items can betaken into the sprints going forward. |  | A | When testers are struggling with constant sprint disruptions from support items and having emotional outbursts, the project manager should schedule a session with the team to discuss the issues and work with them to define a plan to manage sprints going forward. Team collaboration on a sustainable approach addresses both process and morale. Requesting replacements for unhappy members (B) avoids the root cause. Asking HR to send the team to a workshop (C) is indirect. Scheduling a session with the product owner to eliminate support items (D) may not be realistic. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 하이브리드 프로젝트 팀이 제품 소유자를 위한 소프트웨어 업그레이드 작업 중이다. 팀은 프로덕션 지원도 담당한다. 테스터들이 스프린트 중단으로 고통받고 있다. PM은 무엇을 해야 하는가? | 팀과 세션을 예약하여 이슈를 논의하고 지원 항목을 관리할 계획을 정의하기 위해 협력한다 | 이런 방식에 불만인 팀원의 교체를 요청한다 | HR에 팀원을 변경 관리 워크숍에 보내도록 요청한다 | 제품 책임자와 세션을 예약하여 지원 항목은 스프린트에 포함될 수 없음을 설명한다 |  | A | 테스터들이 지원 항목으로 인한 스프린트 중단으로 감정적 어려움을 겪을 때, PM은 팀과 세션을 예약하여 이슈를 논의하고 지원 항목 관리 계획을 정의해야 한다. 협력적 문제 해결과 팀 참여가 지속 가능한 해결책을 만든다. 교체(B)는 비인간적이다. 변경 관리 워크숍(C)은 근본 원인을 다루지 않는다. 지원 항목 배제(D)는 비현실적이다.
1966 | A major national company known for quality products has just selected a small subcontracting firm to assist with a project. The project manager from the subcontracting firm is meeting with the project team to ensure that the project is delivered according to the customer's standards. In order to ensure this, what should the project manager define and document? | Objectives | Estimates | Requirements | Quality |  | C | When a subcontracting firm's project manager meets with the team to ensure delivery according to the customer's quality standards, they should define and document the project's requirements. Requirements specify the detailed inputs, outputs, processes, and standards the product must fulfill—ensuring a clear understanding of customer expectations. Objectives (A) are high-level goals, not detailed standards. Estimates (B) address cost and time. Quality (D) is an aspect covered within comprehensive requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | 품질 제품으로 유명한 대기업이 소규모 하도급 업체를 선정했다. 하도급 PM이 팀과 만나 고객 품질 기준에 따른 납품을 보장한다. PM은 무엇을 먼저 정의해야 하는가? | 목표 | 견적 | 요구사항 | 품질 |  | C | 하도급 PM이 고객 품질 기준에 맞는 납품을 보장하려면, 프로젝트 요구사항을 먼저 정의하고 문서화해야 한다. 요구사항이 품질 기준과 인도물의 기초이다. 목표(A)는 상위 수준이다. 견적(B)은 요구사항 정의 후에 한다. 품질(D)은 요구사항에 기반하여 정의된다.
1967 | A project manager works in a matrix organization and is managing an internal software development project that is intended to reduce conflicts in the company's internal tracking system. During development, the project manager is informed that the software has to account for an unexpected change to government accounting requirements. The development team was able to make the change with no additional cost; however, the project manager notices that the testing costs are beginning to exceed the testing budget. What should the project manager do? | Submit a change request to the cost baseline through the governance process to fund the additional testing. | Ask the project sponsor to allocate funds from the contingency reserve to fund the additional testing. | Update the basis of estimates and the cost management plan to track the additional funding required for testing. | Conduct a cost-benefit analysis to determine if the funds can be reallocated from the development team. |  | A | When an unexpected government requirement change causes testing costs to exceed budget despite no additional development cost, the project manager should submit a change request to the cost baseline through the governance process. Formal change control ensures proper approval for budget adjustments. Asking the sponsor for contingency reserve (B) may be appropriate but should follow the change request process. Updating basis of estimates (C) documents but does not authorize funding. Conducting a cost-benefit analysis for reallocation (D) explores options but does not authorize additional funds. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Finance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 매트릭스 조직에서 PM이 내부 소프트웨어 개발 프로젝트를 관리 중이다. 예상치 못한 정부 요구사항 변경으로 테스팅 비용이 예산을 초과했다. PM은 무엇을 해야 하는가? | 거버넌스 프로세스를 통해 비용 기준선에 대한 변경 요청을 제출한다 | 스폰서에게 비상 예비비에서 자금을 할당하도록 요청한다 | 견적 기준과 비용 관리 계획을 업데이트하여 추가 자금을 추적한다 | 개발 팀에서 자금을 재배분할 수 있는지 비용-편익 분석을 수행한다 |  | A | 예상치 못한 정부 요구사항 변경으로 테스팅 비용이 예산을 초과할 때, PM은 거버넌스 프로세스를 통해 비용 기준선에 대한 변경 요청을 제출해야 한다. 공식 변경 통제가 적절하다. 비상 예비비(B)는 식별된 리스크용이지 새 요구사항이 아니다. 계획 업데이트(C)는 승인 없이 한다. 비용-편익 분석(D)은 보충적이다.
1968 | A product company is transforming the way it develops and releases products in the market. Executives believe that this is a high-risk initiative, and this initiative must be successful. What should the project manager do in this scenario? | Develop a communications management plan to inform the employees about the new business model | Adopt an iterative rollout approach that delivers the highest business value earlier | Develop a business case with assumptions for the new model | Develop a detailed sprint plan with clear deliverables |  | B | When executives consider a product development transformation a high-risk initiative that must succeed, the project manager should adopt an iterative rollout approach that delivers the highest business value earlier. Incremental delivery reduces risk through early validation and feedback. Developing a communications management plan (A) supports awareness but not delivery strategy. Developing a business case with assumptions (C) is foundational but does not guide execution. Developing a detailed sprint plan (D) is tactical, not strategic. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Embed Quality | Determine Budget | Traditional PM | 제품 회사가 제품 개발 및 출시 방식을 변혁하고 있다. 경영진이 이를 고위험 이니셔티브로 본다. PM은 무엇을 해야 하는가? | 직원에게 새 비즈니스 모델에 대해 알리는 커뮤니케이션 관리 계획을 개발한다 | 최고 비즈니스 가치를 먼저 전달하는 반복적 롤아웃 접근법을 채택한다 | 새 모델에 대한 가정이 포함된 비즈니스 케이스를 개발한다 | 명확한 인도물이 있는 상세한 스프린트 계획을 개발한다 |  | B | 고위험 변혁 이니셔티브에서 PM은 최고 비즈니스 가치를 먼저 전달하는 반복적 롤아웃 접근법을 채택해야 한다. 반복적 접근이 리스크를 최소화하고 조기 가치를 전달한다. 커뮤니케이션 계획(A)은 정보 전달이지 실행 전략이 아니다. 비즈니스 케이스(C)는 이미 결정 후 단계이다. 상세 스프린트 계획(D)은 유연성이 부족하다.
1969 | A new building project is in the middle of its life cycle. The municipality informs the project manager that due to new regulations, the parking lot around the project has to accommodate twice the number of cars than was initially planned. What should the project manager do next? | Have the company ' s lawyers write to the municipality and reject the change as it was not part of the scope approved by the municipality. | Assess the impact of the required change and consult with the executive sponsors to determine the best course of action. | Ask the designers to start designing a solution for this new requirement while the project is running and determine the funding for this change. | Request the project sponsor to fund this change as it is a new regulation, then order the materials in order to start working. |  | B | When new regulations require doubling the parking lot capacity mid-project, the project manager should assess the impact of the required change and consult with executive sponsors to determine the best course of action. Impact analysis before action ensures informed decisions. Having lawyers reject the change (A) ignores legal compliance obligations. Asking designers to start work while determining funding (C) acts before approval. Requesting sponsor funding immediately (D) bypasses impact assessment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 건물 프로젝트 수명주기 중반에 자치단체가 새 규정으로 주차장 용량을 두 배로 늘려야 한다고 통보한다. PM은 무엇을 해야 하는가? | 회사 변호사에게 변경이 원래 계약에 없으므로 거부하도록 서신을 작성하게 한다 | 요구된 변경의 영향을 평가하고 경영 스폰서와 최선의 방법을 결정하기 위해 상의한다 | 프로젝트 진행 중에 설계자에게 새 요구사항에 대한 솔루션 설계를 시작하도록 요청한다 | 스폰서에게 새 규정이므로 이 변경에 자금을 지원하도록 요청하고 자재를 주문한다 |  | B | 새 규정으로 주차장 용량을 두 배로 늘려야 할 때, PM은 먼저 변경의 영향을 평가하고 경영 스폰서와 상의해야 한다. 영향 분석과 경영진 협의가 정보에 기반한 결정의 기초이다. 법적 거부(A)는 규정을 무시한다. 즉시 설계(C)는 영향 분석 없이 성급하다. 즉시 자금 요청(D)은 영향 평가 전에 시기상조이다.
1970 | A project manager is struggling to provide timely updates to the project team because team members are spread across multiple time zones. Which communication method should the project manager utilize in this situation? | Push communication | Interactive communication | Public communication | Pull communication |  | A | When team members are spread across multiple time zones and the PM needs to provide timely updates, push communication is the best method. Push communication—such as emails, status reports, or recorded updates—delivers information directly without requiring simultaneous availability. Interactive communication (B) requires real-time availability, which is difficult across time zones. Public communication (C) is for broad external messaging. Pull communication (D) relies on individuals retrieving information on their own schedule, which may not ensure timeliness. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 여러 시간대에 걸쳐 분산된 팀에게 적시에 업데이트를 제공하는 데 어려움을 겪고 있다. 어떤 커뮤니케이션 방법이 적합한가? | 푸시 커뮤니케이션 | 인터랙티브 커뮤니케이션 | 퍼블릭 커뮤니케이션 | 풀 커뮤니케이션 |  | A | 여러 시간대에 분산된 팀에 적시 업데이트가 필요할 때, 푸시 커뮤니케이션이 최적이다. 이메일, 상태 보고서, 녹화된 메시지 등은 시간대에 관계없이 정보를 전달한다. 인터랙티브(B)는 동시 참여가 필요하여 시간대 차이에 부적합하다. 퍼블릭(C)은 대중용이다. 풀(D)은 수신자가 직접 찾아야 하므로 적시성이 부족하다.
1971 | A new team member inquires about how much they need to learn about the organizational process assets (OPAs) residing on the company intranet. Another team member states they only need to know the basics. However, the project manager believes the team member should know everything regarding the OPAs. What should the project manager do? | Clarify the relevance of reviewing the documentation on the intranet. | Ask a senior team member to help the new team member navigate through all the documentation. | Create a training schedule for the new team member to follow over the next few weeks. | Escalate the inquiry to the team member ' s functional manager. |  | A | When a new team member asks how much they need to learn about organizational process assets, the project manager should clarify the relevance of reviewing the documentation on the intranet. Explaining why OPAs matter motivates proper learning. Asking a senior member to help navigate (B) provides guidance but not understanding. Creating a training schedule (C) adds structure without explaining relevance. Escalating to the functional manager (D) is unnecessary. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 새 팀원이 인트라넷에 있는 조직 프로세스 자산(OPA)에 대해 얼마나 알아야 하는지 문의한다. PM은 무엇을 해야 하는가? | 인트라넷 문서 검토의 관련성을 명확히 한다 | 선임 팀원에게 새 팀원이 모든 문서를 탐색하도록 도움을 요청한다 | 새 팀원이 다음 몇 주 동안 따를 교육 일정을 작성한다 | 문의를 팀원의 기능 관리자에게 에스컬레이션한다 |  | A | 새 팀원이 OPA에 대해 질문할 때, PM은 인트라넷 문서 검토의 관련성을 명확히 해야 한다. 어떤 문서가 현재 프로젝트에 관련되는지 설명하면 효율적 학습이 가능하다. 모든 문서 탐색(B)은 비효율적이다. 교육 일정(C)은 과도하다. 에스컬레이션(D)은 불필요하다.
1972 | A new team member joins an agile team. In a previous role, this team member was a subject matter expert (SME). This team member often directs the team on how to solve problems based on previous experience. What should the project manager do first? | Ask the new team member to size all the stories in the backlog so that the rest of the team can focus on delivery. | Update the definition of done (DoD) to include a review by the new team member to ensure the best outcome of each deliverable. | Ask the new team member to create a wiki that the rest of the team can reference in the future for all questions. | Let the new team member know that even if they know the answer, it is better to give the team a chance to solve their own problems |  | D | When a new team member with SME experience directs the team on how to solve problems rather than collaborating, the project manager should first let the member know that even if they know the answer, it is better to give the team a chance to solve their own problems. Fostering self-organization empowers the team. Asking them to size all stories (A) isolates them. Updating the DoD to include their review (B) formalizes their directive behavior. Creating a wiki (C) channels expertise but does not address the behavioral issue. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | Traditional PM | 새 팀원이 애자일 팀에 합류했다. 이전 역할에서 SME였다. 협력하기보다 팀에게 문제 해결 방법을 지시한다. PM은 무엇을 해야 하는가? | 새 팀원에게 백로그의 모든 스토리를 크기 조정하도록 요청한다 | 새 팀원의 검토를 포함하도록 완료 정의(DoD)를 업데이트한다 | 새 팀원에게 팀이 향후 참조할 위키를 작성하도록 요청한다 | 새 팀원에게 답을 알더라도 팀에게 스스로 시도할 기회를 주는 것이 좋다고 알린다 |  | D | SME 경험이 있는 새 팀원이 지시적으로 행동할 때, PM은 답을 알더라도 팀에게 스스로 시도할 기회를 주는 것이 더 좋다고 알려야 한다. 팀 자율성과 성장을 촉진한다. 스토리 크기 조정(A)은 SME 역할을 강화한다. DoD 업데이트(B)는 검토 의존성을 만든다. 위키 작성(C)은 지식 공유이지 행동 변화가 아니다.
1973 | A project manager is working on a hybrid project and is responsible for ensuring the design, build, and delivery of the software is completed in an agile way. How should the project manager plan the iteration? | Use a product backlog of the functionalities and features required to provide the expected business benefit. | Use a work breakdown structure (WBS) with firm start and end dates for all phases to ensure nothing is missed. | Use a kanban board as an information radiator to manage work in progress (WIP) at the individual and organizational levels. | Use a minimum viable product (MVP) to test and discover which features to schedule when and what to fail early. |  | A | The correct answer is A. Use a product backlog of the functionalities and features required to provide the expected business benefit. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Plan & Manage Project Closure | Project Work | Enable Change to Achieve the Envisioned Future State | Hybrid | Predictive-Agile Blend | Process | Manage Project Closure | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | PM이 하이브리드 프로젝트에서 설계, 구축, 납품을 담당한다. PM은 어떤 도구를 사용해야 하는가? | 기대 비즈니스 이익을 제공하는 데 필요한 기능과 특성의 제품 백로그를 사용한다 | 모든 단계에 확정된 시작 및 종료 날짜가 있는 WBS를 사용한다 | 개인 및 팀 수준에서 진행 중 작업(WIP)을 관리하는 칸반 보드를 사용한다 | MVP를 사용하여 어떤 기능을 언제 일정에 넣을지 테스트하고 발견한다 |  | A | 정답은 A이다. 기대 비즈니스 이익 제공에 필요한 기능과 특성의 제품 백로그를 사용한다. 애자일/하이브리드 환경에서 제품 백로그가 작업 관리의 핵심이다. 확정 날짜 WBS(B)는 예측형이다. 칸반 보드(C)는 시각화 도구이지 계획 도구가 아니다. MVP(D)는 초기 검증이지 전체 관리가 아니다.
1974 | A project manager is assigned to deliver a development project with subcontracted resources from a sister company. What should the project manager do to ensure a smooth inclusion of the new subcontracted resources? | Facilitate a working session to review the ground rules. | Organize a team-bonding exercise with the subcontractors. | Schedule a formal meeting to cover the mission and vision. | Share the project team ground rules with the subcontractors. 1131 |  | D | When subcontracted resources from a sister company join the project, the project manager should share the project team ground rules with them. Ground rules set clear behavioral and operational expectations. Facilitating a working session (A) is broader than needed. Team-bonding exercises (B) build rapport but not clarity. A formal mission/vision meeting (C) is too high-level for operational integration. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | PM이 자매 회사의 하도급 자원과 함께 개발 프로젝트를 납품해야 한다. PM은 먼저 무엇을 해야 하는가? | 기본 규칙을 검토하는 작업 세션을 퍼실리테이션한다 | 하도급 업체와 팀 본딩 활동을 조직한다 | 미션과 비전을 다루는 공식 회의를 예약한다 | 프로젝트 팀 기본 규칙을 하도급 업체와 공유한다 |  | D | 자매 회사의 하도급 자원이 프로젝트에 합류할 때, PM은 프로젝트 팀 기본 규칙을 공유해야 한다. 기본 규칙이 행동 및 운영 기대를 설정한다. 작업 세션(A)은 규칙이 이미 있으면 과도하다. 팀 본딩(B)은 규칙 공유 후에 한다. 공식 회의(C)는 미션/비전보다 규칙이 우선이다.
1975 | A project manager is managing an internal project with a tight budget and schedule. While executing the project, the project manager realizes that some stakeholders are working against the success targets of the project. What should the project manager do to ensure successful project delivery? (Choose two) | Involve all stakeholders in the project by distributing status reports. | Update the project stakeholder analysis and methods to satisfy the stakeholders' requirements. | Escalate the issue to the functional manager and ask for support. | Focus on the supportive stakeholders and minimize involvement of unsupportive stakeholders. | Engage all stakeholders in the project including the unsupportive stakeholders. | B, D | When stakeholders work against project success, the PM must engage all stakeholders—including unsupportive ones—and update the stakeholder analysis to address their concerns. Every stakeholder influences the project, and their needs must be understood and managed. Developing strategies to satisfy stakeholder requirements builds support and reduces resistance. Escalating to functional managers, distributing status reports, or focusing only on supportive stakeholders may be subsequent actions but don't address the immediate need for comprehensive stakeholder engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | PM이 촉박한 예산과 일정의 내부 프로젝트를 관리 중이다. 일부 이해관계자가 프로젝트 성공에 반하여 활동한다. PM은 무엇을 해야 하는가? | 모든 이해관계자에게 상태 보고서를 배포하여 프로젝트에 참여시킨다 | 프로젝트 이해관계자 분석과 이해관계자 요구사항 충족 방법을 업데이트한다 | 기능 관리자에게 이슈를 에스컬레이션하고 지원을 요청한다 | 지지하는 이해관계자에 집중하고 비지지적 이해관계자의 참여를 최소화한다 | 비지지적 이해관계자를 포함한 모든 이해관계자를 프로젝트에 참여시킨다 | B, D | 이해관계자가 프로젝트 성공에 반할 때, PM은 이해관계자 분석을 업데이트하고(B) 지지하는 이해관계자에 집중하며 비지지적 이해관계자의 참여를 최소화해야 한다(D). 이해관계자 분석 업데이트가 우려를 파악하고, 전략적 참여가 리소스를 최적화한다. 상태 보고서만(A)은 일방향이다. 에스컬레이션(C)은 직접 관리 전에 시기상조이다. 모든 이해관계자 참여(E)는 리소스가 제한적일 때 비효율적이다.
1976 | A team has been working together for several months and has successfully delivered work. A new team member has joined the team but is having difficulty contributing. What should the project manager do to help the new team member integrate effectively? | Give the new team member time to contribute until they ask for help and support. | Approach the team member to identify any issues and then plan a resolution accordingly. | Review the project with the team member to ensure the project scope is understood | Assign the new team member tasks so that the team member knows on what to focus. |  | B | When a new team member is having difficulty contributing to an established team, the project manager should approach the team member to identify any issues and plan a resolution accordingly. Direct engagement establishes rapport, uncovers specific challenges, and enables targeted support for integration. Giving time until they ask for help (A) is passive and risks isolation. Assigning tasks for focus (D) is directive without understanding the issues. Reviewing the project scope (C) is informative but insufficient for addressing integration challenges. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Governance | Executing | Build an Empowered Culture | Manage Project Knowledge | Traditional PM | 팀이 수개월간 함께 일하며 성공적으로 작업을 납품해 왔다. 새 팀원이 합류했으나 기여에 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 새 팀원에게 도움을 요청할 때까지 기여할 시간을 준다 | 팀원에게 접근하여 이슈를 파악하고 그에 따라 해결을 계획한다 | 팀원과 프로젝트를 검토하여 범위가 이해되었는지 확인한다 | 새 팀원에게 작업을 할당하여 무엇에 집중해야 하는지 알게 한다 |  | B | 새 팀원이 기여에 어려움을 겪을 때, PM은 직접 접근하여 이슈를 파악하고 해결을 계획해야 한다. 직접적 참여가 가장 효과적이다. 시간 주기(A)는 수동적이며 문제가 악화될 수 있다. 범위 검토(C)는 범위 이해보다 통합 문제일 수 있다. 작업 할당(D)은 근본 원인을 파악하지 않는다.
1977 | The project team completed a demonstration of the main deliverable of the project. Although the project sponsor is happy with the outcome and is ready to sign the release to production, one of the business unit managers who attended the demo believes that the deliverable is not complete. Which document should the project manager use to resolve this situation? | Requirements traceability matrix | Risk management plan | Requirements management plan | Project scope statement |  | A | The correct answer is A. Requirements traceability matrix. The project sponsor provides strategic direction and support. The PM should maintain effective communication and alignment with the sponsor to ensure project success. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | General | Scope & Requirements Mgmt | Process | Evaluate Project Status | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 팀이 주요 인도물 시연을 완료했다. 스폰서는 만족하지만 일부 기능이 요구사항과 다르다고 언급했다. PM은 어떤 문서를 참조해야 하는가? | 요구사항 추적 매트릭스 | 리스크 관리 계획 | 요구사항 관리 계획 | 프로젝트 범위 기술서 |  | A | 정답은 A이다. 요구사항 추적 매트릭스(RTM). 일부 기능이 요구사항과 다를 때 RTM을 참조하여 각 요구사항이 인도물에 어떻게 매핑되는지 확인한다. 리스크 관리 계획(B)은 리스크 관련이다. 요구사항 관리 계획(C)은 프로세스 정의이다. 범위 기술서(D)는 상위 수준 범위이다.
1978 | A stakeholder informs the project manager about a few compliance-related gaps and issues. The stakeholder then presents several suggestions to the project manager to address the issues. What should the project manager do? | Use the compliance issues to identify coaching and mentoring opportunities. | Review this with the project sponsor to avoid compliance gaps and issues. | Log the feedback from the compliance gaps in the lessons learned register. | Discuss the suggestions with the staff responsible for the compliance issues. |  | D | When a stakeholder identifies compliance gaps and presents suggestions, the project manager should discuss the suggestions with the staff responsible for the compliance issues. Direct engagement with compliance-responsible staff enables detailed evaluation of the suggestions' feasibility and collaborative solution development. Using gaps for coaching opportunities (A) reframes the problem rather than solving it. Reviewing with the project sponsor (B) elevates the issue without staff input. Logging feedback in lessons learned (C) defers action. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Business Environment | Plan and Manage Compliance | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 이해관계자가 컴플라이언스 관련 격차와 이슈를 PM에게 알리고 제안을 제시했다. PM은 무엇을 해야 하는가? | 컴플라이언스 이슈를 코칭 및 멘토링 기회를 식별하는 데 사용한다 | 컴플라이언스 격차와 이슈를 방지하기 위해 프로젝트 스폰서와 검토한다 | 컴플라이언스 격차에서 얻은 피드백을 교훈 등록부에 기록한다 | 컴플라이언스 이슈를 담당하는 직원과 제안을 논의한다 |  | D | 이해관계자가 컴플라이언스 격차를 식별하고 제안을 제시할 때, PM은 해당 이슈를 담당하는 직원과 제안을 논의해야 한다. 담당자와의 직접 참여가 효과적 해결을 가능하게 한다. 코칭 기회(A)는 즉각적 해결이 아니다. 스폰서 검토(B)는 담당자 참여 전에 에스컬레이션이다. 교훈 기록(C)은 미래용이지 즉각적 해결이 아니다.
1979 | A project manager is leading a project with a risk management plan detailing strategy and actions if any identified risks become an issue. One of the identified risks becomes an issue, but the project manager believes the planned response may not be the best. What should the project manager do? | Meet with the project team and sponsor to reevaluate all issue responses registered in the risk management plan | Adopt the action prescribed in the risk management plan since it was agreed to beforehand | Submit a change request to perform a different issue response than what is registered in the risk management plan | Escalate the issue to the sponsor and register the new risk response in the project documents |  | C | When an identified risk becomes an issue but the planned response appears suboptimal, the project manager should submit a change request to perform a different response than what was registered in the risk management plan. Formal change control ensures impact analysis, stakeholder review, and proper approval while maintaining governance integrity. Adopting the original plan regardless (B) may cause harm if conditions have changed. Reevaluating all issue responses (A) is excessive and delays action. Escalating and registering a new response without formal approval (D) bypasses governance mechanisms. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Procurement | Risk | Planning | Embed Quality | Plan Risk Management | Traditional PM | PM이 식별된 리스크에 대한 전략과 조치가 상세히 기술된 리스크 관리 계획이 있는 프로젝트를 이끌고 있다. 식별된 리스크가 이슈가 되었으나 계획된 대응이 최적이 아닌 것 같다. PM은 무엇을 해야 하는가? | 팀과 스폰서와 회의하여 리스크 관리 계획에 등록된 모든 이슈 대응을 재평가한다 | 사전에 합의되었으므로 리스크 관리 계획에 규정된 조치를 채택한다 | 리스크 관리 계획에 등록된 것과 다른 이슈 대응을 수행하기 위한 변경 요청을 제출한다 | 스폰서에게 이슈를 에스컬레이션하고 프로젝트 문서에 새 리스크 대응을 등록한다 |  | C | 식별된 리스크가 이슈가 되었으나 계획된 대응이 최적이 아닐 때, PM은 다른 이슈 대응을 위한 변경 요청을 제출해야 한다. 변경 통제 프로세스를 통한 공식 변경이 거버넌스를 유지한다. 전체 재평가(A)는 모든 이슈를 재검토하여 과도하다. 기존 조치 채택(B)은 최적이 아닌 대응을 실행한다. 에스컬레이션(D)은 변경 요청 전에 시기상조이다.
1980 | A project is experiencing delays due to identified risks. What should the project manager do to manage the project schedule? | Revise the project schedule and inform the stakeholders regarding any delays | Review the contingency reserve to identify any delays to the project | Revise the project estimates and meet with the project team to discuss delays 1226 | Review the management reserve to identify any costs associated with the delays |  | A | When a project experiences delays due to identified risks, the project manager should revise the project schedule and inform stakeholders about delays. Transparent schedule updates maintain trust. Reviewing contingency reserve (B) addresses budget, not schedule. Revising estimates and meeting the team (C) is analytical but does not communicate to stakeholders. Reviewing management reserve (D) addresses cost, not schedule management. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 식별된 리스크로 인해 프로젝트가 지연을 경험하고 있다. PM은 프로젝트 일정을 어떻게 관리해야 하는가? | 프로젝트 일정을 수정하고 이해관계자에게 지연을 알린다 | 비상 예비비를 검토하여 프로젝트 지연을 식별한다 | 프로젝트 견적을 수정하고 팀과 지연을 논의한다 | 관리 예비비를 검토하여 지연 관련 비용을 식별한다 |  | A | 식별된 리스크로 프로젝트가 지연될 때, PM은 프로젝트 일정을 수정하고 이해관계자에게 지연을 알려야 한다. 투명한 일정 업데이트가 신뢰를 유지한다. 비상 예비비(B)는 일정이 아닌 비용 관련이다. 견적 수정(C)은 일정 수정보다 부차적이다. 관리 예비비(D)는 미식별 리스크용이다.
1981 | A new project manager is assigned to an ongoing agile innovation project that started 2 weeks ago. After reviewing the project, the new project manager discovered that the previous project manager was planning to use a predictive approach. The previous project manager planned to present the first major deliverable to the client when the project was completely finished in 8 months. What should the new project manager do? | Continue working with the predictive approach to deliver the value at the end of the project. | Meet with the team to review the backlog and create small iterations that can deliver incremental value to the client, | Submit a change request to the project board to adjust the delivery date to 2 months 1299 earlier than planned. | Use a hybrid approach in which agile practices are used but the value is provided to the client at the end of the project. |  | B | When a new PM discovers the previous PM planned to use a predictive approach delivering only at the end of 8 months for an agile innovation project, the new PM should meet with the team to review the backlog and create small iterations delivering incremental value. Iterative delivery aligns with agile principles. Continuing with predictive (A) contradicts the agile decision. Submitting a change request for earlier delivery (C) is procedural. Using hybrid with end delivery (D) misses incremental value. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Scrum | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 새 PM이 2주 전 시작된 애자일 혁신 프로젝트에 배정되었다. 이전 PM이 8개월 후 종료 시에만 가치를 전달하는 예측형 접근을 계획했다. PM은 무엇을 해야 하는가? | 프로젝트 종료 시 가치를 전달하기 위해 예측형 접근을 계속한다 | 팀과 백로그를 검토하고 점진적 가치를 전달할 수 있는 소규모 이터레이션을 만든다 | 프로젝트 보드에 납기일을 2개월 앞당기는 변경 요청을 제출한다 | 애자일 실천법을 사용하되 프로젝트 종료 시에 가치를 제공하는 하이브리드 접근을 사용한다 |  | B | 애자일 혁신 프로젝트에서 이전 PM이 예측형 접근을 계획했을 때, 새 PM은 팀과 백로그를 검토하고 점진적 가치를 전달할 소규모 이터레이션을 만들어야 한다. 애자일 원칙에 맞는 점진적 가치 전달이 핵심이다. 예측형 계속(A)은 애자일 프로젝트에 부적합하다. 납기 앞당김(C)은 접근법 변경이 아니다. 종료 시 가치(D)는 점진적 전달 원칙에 반한다.
1982 | After 1 year into the life cycle of an ongoing residential project, an announcement was received from the municipality regarding a new regulation that will greatly impact the project's schedule and budget. What should the project manager do next? | Update the issue log and discuss It in the next steering committee meeting. | Estimate the associated costs and increase the project budget accordingly. | Perform a qualitative risk analysis and update the risk register. | Submit a change request through the Integrated change control process. |  | D | When a new municipality regulation significantly impacts the project's schedule and budget mid-lifecycle, the project manager should submit a change request through the integrated change control process. Formal change control ensures the impact is evaluated, approved, and communicated. Updating the issue log for the next steering committee (A) defers action. Estimating costs and increasing the budget (B) bypasses governance. Performing qualitative risk analysis (C) is part of analysis but not the formal change process. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 진행 중인 주거 프로젝트 수명주기 1년 후 자치단체에서 새 규정을 발표하여 일정과 예산에 크게 영향을 미친다. PM은 무엇을 해야 하는가? | 이슈 로그를 업데이트하고 다음 운영위원회 회의에서 논의한다 | 관련 비용을 견적하고 프로젝트 예산을 그에 맞게 증가시킨다 | 정성적 리스크 분석을 수행하고 리스크 등록부를 업데이트한다 | 통합 변경 통제 프로세스를 통해 변경 요청을 제출한다 |  | D | 새 규정이 일정과 예산에 크게 영향을 미칠 때, PM은 통합 변경 통제 프로세스를 통해 변경 요청을 제출해야 한다. 공식 변경 통제가 거버넌스를 보장한다. 이슈 로그(A)는 즉각적 조치가 부족하다. 예산 증가(B)는 승인 없이 할 수 없다. 리스크 분석(C)은 이미 발생한 이슈에는 적합하지 않다.
1983 | A project manager is working on a software development project. The project manager and the project team identified the project risks. As the project moved forward, one of the risks materialized, and the project manager consulted the risk management plan to determine how to handle the risk. Once the risk management strategy was selected and applied, the risk was closed. At what point did the project manager move the risk from the risk register to the issue log? | Risk identified | Risk occurred | Risk managed | Risk monitored |  | B | A risk moves from the risk register to the issue log at the point when it materializes—that is, when it actually occurs. In project management, risks represent potential future events that may or may not happen and are tracked in the risk register. Once a risk event takes place, it transitions into an issue requiring active management and resolution through the issue log. This distinction between risks (potential) and issues (realized) is a foundational concept in PMI risk management practices. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 소프트웨어 개발 프로젝트에서 일하고 있다. 팀이 식별한 리스크가 실제로 발생하여 이슈 로그에 기록할 시점은 언제인가? | 리스크가 식별되었을 때 | 리스크가 발생했을 때 | 리스크가 관리되었을 때 | 리스크가 모니터링되었을 때 |  | B | 리스크가 리스크 등록부에서 이슈 로그로 이동하는 시점은 실제로 발생했을 때이다. 리스크는 미래에 발생할 수 있는 잠재적 사건이고, 실현되면 이슈가 된다. 식별(A)은 리스크 등록부 단계이다. 관리(C)와 모니터링(D)은 리스크 대응 프로세스이다.
1984 | The project sponsor wants to obtain quick feedback from end users for a product under development. The roadmap is extensive and will not be completed for quite some time. What should the project manager do? | Work with the stakeholders to determine the minimum requirements needed to get valuable end-user feedback and revise the project schedule. | Advise the stakeholders to share images of the finished product in order to obtain valuable feedback from end users. | Advise the stakeholders that they will need to wait until development is completed in order to get actual end-user feedback. | Hire additional resources to accelerate the schedule and deliver the product faster in order to get actual end-user feedback. |  | A | The correct answer is A. Work with the stakeholders to determine the minimum requirements needed to get valuable end-user feedback and revise the project schedule. The project sponsor plays a critical role in providing direction, support, and authorization. The PM should maintain effective communication with the sponsor and ensure alignment on project objectives. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 스폰서가 개발 중인 제품에 대한 최종 사용자의 빠른 피드백을 얻고 싶어 한다. 로드맵이 광범위하다. PM은 무엇을 해야 하는가? | 이해관계자와 협력하여 가치 있는 최종 사용자 피드백을 얻는 데 필요한 최소 요구사항을 결정하고 프로젝트 일정을 수정한다 | 완성된 제품 이미지를 공유하여 가치 있는 피드백을 얻도록 이해관계자에게 조언한다 | 개발이 완료될 때까지 기다려야 정확한 피드백을 얻을 수 있다고 이해관계자에게 조언한다 | 일정을 앞당겨 제품을 더 빨리 납품하기 위해 추가 자원을 고용한다 |  | A | 정답은 A이다. 이해관계자와 협력하여 가치 있는 피드백을 위한 최소 요구사항을 결정하고 일정을 수정한다. MVP 접근이 빠른 피드백을 가능하게 한다. 이미지 공유(B)는 실제 사용 피드백이 아니다. 완료 대기(C)는 지연이 크다. 추가 자원(D)은 비용 증가이며 빠른 피드백에 비효율적이다.
1985 | A project to develop a large hydropower plant is in the implementation phase and is managed using a hybrid approach. What should the project manager do to ensure full compliance of quality requirements during the execution phase? | Continually survey the quality of the deliverable | Plan quality management | Analyze the quality requirements. | Set up quality policies and procedures |  | A | During the execution phase of a hybrid hydropower plant project, the project manager should continually survey the quality of the deliverable to ensure full compliance with quality requirements. Continuous quality surveillance uses inspections, audits, reviews, testing, feedback, and metrics to identify and correct defects, errors, or deviations from quality standards in real time. Planning quality management (D) or setting up quality policies and procedures (B) are planning-phase activities that should already be completed before execution. Analyzing quality requirements (C) is also a planning activity, not an execution-phase control measure. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Hybrid/Tailoring | 대규모 수력발전소 개발 프로젝트가 하이브리드 접근으로 구현 단계에 있다. PM은 무엇을 해야 하는가? | 인도물의 품질을 지속적으로 조사한다 | 품질 관리를 계획한다 | 품질 요구사항을 분석한다 | 품질 정책과 절차를 수립한다 |  | A | 하이브리드 수력발전소 프로젝트의 실행 단계에서, PM은 인도물의 품질을 지속적으로 조사하여 품질 요구사항에 완전히 부합하도록 해야 한다. 지속적 품질 조사가 실행 중 핵심이다. 품질 관리 계획(B)은 계획 단계 활동이다. 요구사항 분석(C)은 계획 단계이다. 정책 수립(D)은 초기 단계 활동이다.
1986 | A company initiated a departmental transformation project improving the processes for the organization using a predictive approach. This is a critical project for the organization and, in the middle of the project, the project manager noticed that one of the deliverables cannot be produced due to a missing technical skill. What should the project manager have done to avoid this? | Identified all required skills after the kick-off of the project | Planned all required training for the team during the onboarding process | Asked the sponsor to identify all required skills during the planning of the project | Identified all required skills during the planning of the project |  | D | When a critical deliverable cannot be produced due to a missing technical skill midway through a predictive project, the project manager should have identified all required skills during the planning of the project. Planning-phase skill identification enables proactive training or hiring. Identifying skills after kick-off (A) is reactive. Planning training during onboarding (B) assumes skills were already identified. Asking the sponsor to identify skills (C) delegates a PM responsibility. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Finance | Resources | Planning | Adopt a Holistic View | Plan Resource Management | Traditional PM | 회사가 예측형 접근법을 사용하여 부서 변환 프로젝트를 시작했다. 이것은 핵심 인도물이다. 중간에 기술 스킬 부족으로 인도물을 생산할 수 없다. PM이 이전에 무엇을 했어야 하는가? | 프로젝트 시작 후 필요한 모든 기술을 식별했다 | 온보딩 과정에서 팀에 필요한 모든 교육을 계획했다 | 스폰서에게 프로젝트 계획 중 필요한 모든 기술을 식별하도록 요청했다 | 프로젝트 계획 중 필요한 모든 기술을 식별했다 |  | D | 예측형 프로젝트에서 기술 스킬 부족으로 핵심 인도물을 생산할 수 없을 때, PM은 프로젝트 계획 단계에서 필요한 모든 기술을 식별했어야 한다. 계획 단계의 기술 식별이 자원 갭을 사전에 방지한다. 시작 후 식별(A)은 늦다. 온보딩 교육 계획(B)은 부분적이다. 스폰서에게 요청(C)은 PM의 책임을 위임한다.
1987 | A project feature from the development team was rejected due to low quality. Over the past few weeks, the testing team has become concerned because the development team has not yet responded to the rejection. As a result, the testing team has escalated the conflict to the project manager. What should the project manager do? | Initiate an improvement plan for the development team to follow. | Remove the development team ' s rejected feature from the backlog. | Evaluate the context for the conflict with the development team. | Reassure all team members that the development team will fix the issue. |  | C | When the testing team escalates a conflict about a rejected feature that the development team has not responded to, the project manager should evaluate the context for the conflict with the development team. Investigating root causes—delays, roadblocks, or miscommunication—before taking action ensures fair assessment and avoids premature assumptions. Initiating an improvement plan (A) may bypass due diligence. Removing the feature from the backlog (B) makes a major decision without understanding the situation. Reassuring team members that the issue will be fixed (D) is speculative without investigating. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 개발팀의 프로젝트 기능이 낮은 품질로 거부되었다. 테스트팀이 개발팀이 대응하지 않아 갈등을 에스컬레이션했다. PM은 무엇을 해야 하는가? | 개발팀이 따를 개선 계획을 시작한다 | 개발팀의 거부된 기능을 백로그에서 제거한다 | 개발팀과의 갈등 맥락을 평가한다 | 모든 팀원에게 개발팀이 문제를 해결할 것이라고 안심시킨다 |  | C | 테스트팀이 거부된 기능에 대해 개발팀이 대응하지 않아 갈등을 에스컬레이션할 때, PM은 개발팀과의 갈등 맥락을 평가해야 한다. 근본 원인 조사가 적절한 해결을 가능하게 한다. 개선 계획(A)은 맥락 파악 전에 성급하다. 기능 제거(B)는 범위를 축소한다. 안심(D)은 문제를 해결하지 않는다.
1988 | A department lead requested additional items be included in the project during the execution phase. Their acceptance is mandatory before the project can be closed. | Schedule a meeting to gain better understanding. | Politely refuse the request stating the project baselines. | Find a way to accommodate the requested additions. | Initiate a change request for the additional scope. |  | D | When a department lead whose acceptance is mandatory requests additional items during execution, the project manager should initiate a change request for the additional scope. Formal change control ensures proper evaluation of scope, budget, and schedule impacts before implementation. Scheduling a meeting for understanding (A) is helpful but not the next formal step. Politely refusing based on baselines (B) ignores the stakeholder's mandatory acceptance role. Finding ways to accommodate without change control (C) risks scope creep. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 부서장이 실행 단계에서 추가 항목을 프로젝트에 포함하도록 요청했다. 프로젝트 종료 전 부서장의 수락이 필수적이다. PM은 무엇을 해야 하는가? | 더 나은 이해를 위해 회의를 일정 잡는다 | 프로젝트 기준선을 언급하며 요청을 정중히 거부한다 | 요청된 추가 사항을 수용할 방법을 찾는다 | 추가 범위에 대한 변경 요청을 시작한다 |  | D | 수락이 필수적인 부서장이 실행 중 추가 항목을 요청할 때, PM은 추가 범위에 대한 변경 요청을 시작해야 한다. 공식 변경 통제가 범위, 예산, 일정에 미치는 영향의 적절한 평가를 보장한다. 회의(A)는 이해를 위한 것이지 조치가 아니다. 거부(B)는 필수 이해관계자를 무시한다. 수용(C)은 공식 프로세스를 우회한다.
1989 | One of the team members is always late to the daily standup meeting. What should the project manager do? | Reinforce the ground rules for standup meetings with the entire team. | Ignore the situation since the team member is accomplishing their deliverables. | Schedule the meeting at the end of the day to accommodate everyone. | Speak with the team member directly to reinforce the ground rules. |  | D | When a team member is consistently late to daily standups, the project manager should speak with the team member directly to reinforce ground rules. Direct, private communication addresses the behavior constructively. Reinforcing rules with the entire team (A) may embarrass the individual unnecessarily. Ignoring the situation (B) normalizes the behavior. Rescheduling the meeting (C) accommodates one person at everyone else's expense. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 팀원 중 한 명이 항상 데일리 스탠드업 회의에 늦는다. PM은 무엇을 해야 하는가? | 전체 팀에 스탠드업 회의의 기본 규칙을 재강조한다 | 팀원이 인도물을 완수하고 있으므로 상황을 무시한다 | 모든 사람을 수용하기 위해 하루 끝에 회의를 일정 잡는다 | 팀원과 직접 대화하여 기본 규칙을 재강조한다 |  | D | 팀원이 지속적으로 데일리 스탠드업에 늦을 때, PM은 팀원과 직접 대화하여 기본 규칙을 재강조해야 한다. 직접적이고 사적인 소통이 건설적으로 행동을 다룬다. 전체 팀 재강조(A)는 한 사람 문제에 과도하다. 무시(B)는 팀 규범을 약화시킨다. 일정 변경(C)은 한 사람에게 맞추는 것이다.
1990 | An organization is transitioning to agile. The project manager is discussing how to manage risks with the development team in light of the transition for a particular project. The team estimates the risk level as low. What should the project manager do? | Trust the development team ' s risk estimation and inform the project sponsor that the risks will be evaluated at a later time. | Capture all the backlog entries assessed by the development team to have evidence that risk management has been completed | Create a risk register and include a single generic risk, set the level to low, and then close the risk at the end of the project. | Create a risk register to identify, capture, review, and manage risks using a risk management process. |  | D | When an agile team estimates project risk as low during an organizational transition to agile, the project manager should create a risk register to identify, capture, review, and manage risks using a risk management process. Structured risk management is essential regardless of perceived risk level. Trusting the estimate and deferring evaluation (A) neglects risk governance. Capturing backlog entries as evidence (B) misuses the backlog. Creating a generic risk entry and closing it (C) is superficial and defeats the purpose. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Traditional PM | 조직이 애자일로 전환 중이다. 개발팀이 프로젝트 리스크를 낮음으로 추정한다. PM은 어떻게 리스크를 관리해야 하는가? | 개발팀의 리스크 추정을 신뢰하고 스폰서에게 리스크가 나중에 평가될 것이라고 알린다 | 개발팀이 평가한 모든 백로그 항목을 캡처하여 리스크 관리가 완료되었다는 증거로 보관한다 | 리스크 등록부를 만들어 단일 일반 리스크를 포함하고 수준을 낮음으로 설정한 후 종료한다 | 리스크 등록부를 만들어 리스크 관리 프로세스를 사용하여 리스크를 식별, 캡처, 검토, 관리한다 |  | D | 애자일 전환 중 팀이 리스크를 낮다고 추정할 때, PM은 리스크 등록부를 만들어 리스크 관리 프로세스를 사용하여 리스크를 식별, 캡처, 검토, 관리해야 한다. 구조화된 리스크 관리가 전환기에도 필수적이다. 팀 추정 신뢰(A)는 검증이 없다. 백로그 캡처(B)는 리스크 관리가 아니다. 일반 리스크(C)는 형식적이다.
1991 | A team has different ideas on how to address a feature of a product under construction and, although the sprint began two days ago, they have still not reached a consensus. What should the project manager do? | Offer an opinion about the pros and cons of each idea and try to reach a consensus in a facilitated meeting | Schedule a session to give everyone the chance to express their opinions about each idea, then vote and decide. | Ask the product owner, who is the key stakeholder, to choose among the different ideas. | Propose ideas to the group, ask everyone to vote, and then choose the most popular idea |  | A | When a team cannot reach consensus on a feature approach two days into a sprint, the project manager should offer an opinion on pros and cons of each idea and facilitate a consensus meeting. Facilitated discussion respects all perspectives. Scheduling a voting session (B) may not reach true consensus. Asking the PO to choose (C) bypasses team decision-making. Proposing and voting on ideas (D) is majority rule, not consensus. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀이 건설 중 제품 기능에 대해 다른 아이디어를 가지고 있고, 스프린트 시작 2일 후에도 합의에 도달하지 못했다. PM은 무엇을 해야 하는가? | 각 아이디어의 장단점에 대한 의견을 제시하고 퍼실리테이션된 회의에서 합의에 도달하려 한다 | 모든 사람이 각 아이디어에 대한 의견을 표현할 기회를 주는 세션을 일정 잡고 투표하여 결정한다 | 핵심 이해관계자인 제품 책임자에게 다른 아이디어 중에서 선택하도록 요청한다 | 그룹에 아이디어를 제안하고 모든 사람에게 투표를 요청한 후 가장 인기 있는 아이디어를 선택한다 |  | A | 팀이 스프린트 시작 2일 후 기능 접근법에 합의하지 못할 때, PM은 각 아이디어의 장단점에 대한 의견을 제시하고 퍼실리테이션된 합의 회의를 해야 한다. 퍼실리테이션된 토론이 모든 관점을 존중한다. 투표 세션(B)은 합의가 아닌 다수결이다. 제품 책임자 결정(C)은 팀 자율성을 무시한다. 인기 투표(D)는 합의가 아니다.
1992 | A project's business case was just approved and the project manager is creating the benefits management plan. It is unclear how the benefits from the project align with the organization's vision. What should the project manager do first to verify alignment? | Request a copy of the project assumptions log for more insight. | Consult with the project team members to gain their opinions. | Meet with the project sponsor to obtain more information. | Ask the project team to delay the kick-off while resolving the concern. |  | C | When it is unclear how project benefits align with the organization's vision while creating the benefits management plan, the project manager should first meet with the project sponsor to obtain more information. The sponsor links project goals to strategic objectives. Requesting the assumptions log (A) provides project-level detail, not strategic alignment. Consulting the team (B) addresses execution, not strategic vision. Asking the team to delay kickoff (D) creates unnecessary delay. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Schedule | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트 비즈니스 케이스가 승인되었고 PM이 혜택 관리 계획을 작성 중이다. 혜택이 조직 비전과 어떻게 일치하는지 불명확하다. PM은 무엇을 먼저 해야 하는가? | 더 많은 통찰을 위해 프로젝트 가정 로그 사본을 요청한다 | 프로젝트 팀원에게 의견을 구한다 | 프로젝트 스폰서와 만나 더 많은 정보를 얻는다 | 프로젝트 팀에 우려를 해결하는 동안 착수를 지연하도록 요청한다 |  | C | 혜택이 조직 비전과 어떻게 일치하는지 불명확할 때, PM은 먼저 프로젝트 스폰서와 만나 더 많은 정보를 얻어야 한다. 스폰서가 프로젝트 목표와 전략적 비전을 연결한다. 가정 로그(A)는 정렬 정보를 제공하지 않을 수 있다. 팀 의견(B)은 전략적 정렬에 적합하지 않다. 착수 지연(D)은 불필요하다.
1993 | A technical subject matter expert (SME) identifies an occurrence that should be captured in the project's lessons learned. The SME asks the project manager to write, document, and include it in the lessons learned register. What should the project manager do? | Assign the documenting task to a project team member | Request the SME to wait until the project closure phase. | Ask the SME to document and capture the occurrence. | Take ownership of documenting this information |  | D | When a technical SME asks the PM to document a lessons learned occurrence, the project manager should take ownership of documenting this information. The PM is accountable for facilitating the lessons learned process and ensuring accuracy and completeness. Assigning the task to a team member (A) delegates PM responsibility. Asking the SME to document it themselves (C) shifts the burden. Waiting until project closure (B) delays valuable knowledge capture. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Governance | Closing | Build an Empowered Culture | Close Project or Phase | Traditional PM | 기술 SME가 프로젝트 교훈에 기록해야 할 사건을 식별했다. SME가 PM에게 문서화를 요청한다. PM은 무엇을 해야 하는가? | 프로젝트 팀원에게 문서화 작업을 할당한다 | SME에게 프로젝트 종료 단계까지 기다리도록 요청한다 | SME에게 사건을 문서화하고 캡처하도록 요청한다 | 이 정보의 문서화에 대한 소유권을 갖는다 |  | D | 기술 SME가 교훈 사건 문서화를 요청할 때, PM은 이 정보의 문서화에 대한 소유권을 가져야 한다. PM이 교훈 프로세스를 퍼실리테이션하고 정확성과 완전성을 보장할 책임이 있다. 팀원 할당(A)은 PM 책임을 위임한다. 종료까지 대기(B)는 정보 손실 리스크가 있다. SME에게 요청(C)은 SME 역할 범위를 벗어난다.
1994 | A project manager is leading an automation project. The project team is colocated and includes people from both the technical and business units. The project manager discovers that personal differences and work styles are affecting the project negatively. How should the project manager address this? | Invite the functional managers of the different units to address their personal differences. | Develop a schedule that ensures people with personal differences work separately. | Meet with the team and agree on expectations from team members. | Use an approach to the project that does not involve colocation. |  | C | When personal differences and work styles are negatively affecting a colocated team, the project manager should meet with the team and agree on expectations from each other. Establishing ground rules addresses interpersonal issues collaboratively. Inviting functional managers (A) escalates unnecessarily. Developing a separation schedule (B) avoids the problem. Using a non-colocation approach (D) contradicts the project setup. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 자동화 프로젝트를 이끌고 있다. 팀이 같은 장소에서 일하며 기술/사업 부서 모두 포함한다. 개인적 차이와 업무 스타일이 부정적 영향을 미친다. PM은 무엇을 해야 하는가? | 다른 부서의 기능 관리자를 초대하여 개인적 차이를 다룬다 | 개인적 차이가 있는 사람들이 별도로 일하도록 일정을 개발한다 | 팀과 만나 팀원들의 기대사항에 합의한다 | 같은 장소에서 일하지 않는 프로젝트 접근법을 사용한다 |  | C | 개인적 차이와 업무 스타일이 같은 장소 팀에 부정적 영향을 미칠 때, PM은 팀과 만나 서로의 기대사항에 합의해야 한다. 기본 규칙 수립이 대인관계 이슈를 협력적으로 다룬다. 기능 관리자 초대(A)는 에스컬레이션이다. 별도 일정(B)은 협업을 방해한다. 같은 장소 포기(D)는 회피이다.
1995 | A project team is struggling to obtain the required data for a complex project in order to proceed to the next stage. What should the project manager do? | Propose a revised project schedule to the sponsor as the delays have affected the time lines. | Meet with the data suppliers to explain the critical timing requirements of the project. | Set up a meeting with the team to discuss and determine the project ' s challenges. | Schedule a meeting with the sponsor to express the team ' s frustrations about the data. |  | B | When a project team struggles to obtain required data to proceed, the project manager should meet with the data suppliers to explain the critical timing requirements. Direct engagement with suppliers addresses the root cause. Proposing a revised schedule (A) accepts the delay. Setting up a team meeting (C) discusses the problem internally without engaging suppliers. Meeting with the sponsor about frustrations (D) escalates without resolution. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Stakeholder & Communication Mgmt | Process | Plan and Manage Procurement | Stakeholders | Planning | Adopt a Holistic View | Plan Stakeholder Engagement | Traditional PM | 프로젝트 팀이 복잡한 프로젝트의 다음 단계로 진행하기 위해 필요한 데이터를 얻는 데 어려움을 겪고 있다. PM은 무엇을 해야 하는가? | 지연이 일정에 영향을 미쳤으므로 스폰서에게 수정된 프로젝트 일정을 제안한다 | 데이터 공급자와 만나 프로젝트의 중요한 시간 요구사항을 설명한다 | 팀과 회의를 설정하여 프로젝트의 도전과제를 논의하고 결정한다 | 스폰서와 회의를 일정 잡아 데이터에 대한 팀의 좌절감을 표현한다 |  | B | 팀이 필요한 데이터를 얻는 데 어려움을 겪을 때, PM은 데이터 공급자와 만나 프로젝트의 중요한 시간 요구사항을 설명해야 한다. 공급자와의 직접 소통이 근본 원인을 다룬다. 수정 일정 제안(A)은 수동적이다. 팀 회의(C)는 외부 문제를 해결하지 않는다. 스폰서에게 좌절 표현(D)은 비전문적이다.
1996 | A project manager learns from a marketing analyst that a competitor just published a press release announcing a product launch using a specific innovation. The project manager is concerned because the company is initiating a project involving the same innovation. A key goal of the new project is that the product will be the first to market with the innovation. What should the project manager do next? | Ask the leader of research and development to decide on next steps | Review the project goals and eat criteria m the project charter | Document the issue in the issue log and escalate to the project sponsor | Inform the project sponsor and suggest canceling the project |  | C | When a competitor announces a product launch using the same innovation the company's project targets as first-to-market, the project manager should document the issue in the issue log and escalate to the project sponsor. Issue documentation and escalation enable strategic decision-making. Asking R&D to decide (A) delegates PM responsibility. Reviewing charter goals (B) is passive. Suggesting project cancellation (D) is premature without analysis. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 경쟁사가 같은 혁신 기술을 사용한 제품 출시를 발표했다는 것을 알게 되었다. 이 프로젝트는 최초 출시를 목표로 했다. PM은 무엇을 해야 하는가? | 연구개발 리더에게 다음 단계를 결정하도록 요청한다 | 프로젝트 헌장에서 프로젝트 목표와 종료 기준을 검토한다 | 이슈 로그에 문제를 문서화하고 프로젝트 스폰서에게 에스컬레이션한다 | 프로젝트 스폰서에게 알리고 프로젝트 취소를 제안한다 |  | C | 경쟁사가 같은 혁신 기술로 제품 출시를 발표할 때, PM은 이슈 로그에 문제를 문서화하고 스폰서에게 에스컬레이션해야 한다. 이슈 문서화와 에스컬레이션이 적절한 의사결정 프로세스를 따른다. R&D 리더 결정(A)은 PM 책임을 위임한다. 목표 검토(B)는 유용하지만 에스컬레이션이 우선이다. 취소 제안(D)은 성급하다.
1997 | A large matrix organization is adopting a new communications approach. This is necessary because their projects often require the resourcing of expert knowledge in the form of specialists from various departments and divisions. What should the project manager do to set up effective communications? | Plan on transmitting the information in an easily understandable manner. | Focus on the recipients' needs and not the information itself. | Use the highest possible technical language and avoid using metaphors. | Ensure that messages sent to the recipients are delivered. |  | B | When a large matrix organization adopts a new communications approach for projects requiring specialist resources from various departments, the project manager should focus on the recipients' needs and not the information itself. Audience-centered communication ensures effectiveness. Transmitting in an understandable manner (A) is important but secondary to understanding needs. Using technical language (C) excludes non-technical stakeholders. Ensuring message delivery (D) focuses on logistics, not effectiveness. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Tailored Approach | People | Plan and Manage Communication | Schedule | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 대규모 매트릭스 조직이 새 커뮤니케이션 접근법을 채택하고 있다. 다양한 부서의 전문 자원이 필요하다. PM은 커뮤니케이션에서 무엇에 집중해야 하는가? | 정보를 쉽게 이해할 수 있는 방식으로 전달하도록 계획한다 | 정보 자체가 아닌 수신자의 니즈에 집중한다 | 가능한 높은 기술적 언어를 사용하고 비유 사용을 피한다 | 수신자에게 보낸 메시지가 전달되도록 한다 |  | B | 다양한 부서 전문가가 필요한 프로젝트에서 새 커뮤니케이션 접근법을 채택할 때, PM은 정보 자체가 아닌 수신자의 니즈에 집중해야 한다. 청중 중심 커뮤니케이션이 이해와 참여를 보장한다. 쉬운 전달(A)은 좋지만 니즈 중심이 우선이다. 기술적 언어(C)는 이해를 방해한다. 전달 보장(D)은 일방향적이다.
1998 | During a final investment decision meeting, all of the stakeholders were aligned on the project benefits, proposed budget, and schedule. Before final approval was given, the executive requested an aspirational target for the project team to obtain an enhanced benefit from the project. What should the project manager do in this situation? | Accept the request and commit to some benefit improvement opportunities for the project. | Explain the planning and budgeting process and demonstrate that the project proposal maximizes benefits. | Investigate the request and express willingness to find ways to obtain higher project benefits. | Review the proposal and suggest optional benefit improvement opportunities for the project. |  | D | When an executive requests aspirational targets before final approval with all stakeholders already aligned, the project manager should review the proposal and suggest optional benefit improvement opportunities. This balances the desire for enhanced benefits with protecting approved constraints. Accepting and committing to improvements (A) creates unrealistic expectations. Investigating and expressing willingness (C) is vague. Explaining the planning process defensively (B) may seem close-minded. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Finance | Planning | Be an Accountable Leader | Plan Finance Management | Traditional PM | 최종 투자 결정 회의에서 모든 이해관계자가 혜택, 예산, 일정에 합의했다. 최종 승인 전 경영진이 야심적 목표를 요청한다. PM은 무엇을 해야 하는가? | 요청을 수락하고 프로젝트에 대한 일부 혜택 개선 기회를 약속한다 | 계획 및 예산 프로세스를 설명하고 프로젝트 제안이 혜택을 극대화한다는 것을 입증한다 | 요청을 조사하고 더 높은 프로젝트 혜택을 얻을 방법을 찾겠다는 의지를 표현한다 | 제안을 검토하고 프로젝트에 대한 선택적 혜택 개선 기회를 제안한다 |  | D | 경영진이 모든 이해관계자 합의 후 야심적 목표를 요청할 때, PM은 제안을 검토하고 선택적 혜택 개선 기회를 제안해야 한다. 선택적 기회가 기존 합의를 유지하면서 향상 가능성을 제공한다. 약속(A)은 달성할 수 없는 약속이다. 프로세스 설명(B)은 방어적이다. 의지 표현(C)은 모호하다.
1999 | The project manager of a high-risk project is concerned about a delay in the schedule that might force the project to move its go-live date. What should the project manager do next? | Raise a change request to the change control board (CCB) to ask for funds to onboard new resources to expedite the project. | Ensure that the project meets the committed time lines as this is the core objective and purpose of the project. | Capture the risk in the risk register and monitor it to prevent it from becoming an issue by taking the proper response action. | Ask the sponsor to start a new project to support the existing project and help it meet the original time line. |  | C | When a high-risk project faces a potential schedule delay that could impact the go-live date, the project manager should capture the risk in the risk register and monitor it to prevent it from becoming an issue by taking proper response actions. This proactive approach documents the risk, its potential impact, and planned mitigation strategies. Raising a change request for additional resources (A) is premature without first assessing the risk formally. Insisting on meeting timelines as a core objective (B) ignores the reality of the situation. Asking the sponsor to start a new supporting project (D) is excessive and unlikely to be practical. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 고위험 프로젝트의 PM이 일정 지연으로 인해 출시일이 변경될 수 있다고 우려한다. PM은 무엇을 해야 하는가? | CCB에 변경 요청을 제출하여 새 자원 확보 자금을 요청한다 | 프로젝트가 약속된 일정을 충족하도록 한다 | 리스크 등록부에 리스크를 캡처하고 적절한 대응 조치를 취하여 이슈가 되지 않도록 모니터링한다 | 스폰서에게 기존 프로젝트를 지원하고 원래 일정을 충족하기 위한 새 프로젝트를 시작하도록 요청한다 |  | C | 고위험 프로젝트에서 일정 지연이 출시일에 영향을 줄 수 있을 때, PM은 리스크 등록부에 리스크를 캡처하고 적절한 대응 조치를 취하여 이슈가 되지 않도록 모니터링해야 한다. 구조화된 리스크 관리가 사전적 대응을 가능하게 한다. CCB 변경 요청(A)은 리스크 평가 전에 성급하다. 일정 충족(B)은 구체적 행동이 없다. 새 프로젝트(D)는 과도하다.
2000 | A project team is currently dispersed across multiple countries and time zones. Recent team feedback shows engagement levels are sub-optimal, and information flows are irregular and one-sided. There are also company travel restrictions in place, preventing physical colocation. What improvements should the project manager implement to improve engagement? | Upgrade each project team member ' s internet connection to allow virtual video conferencing. | Confirm with the team which approach works best for exchanging information. | Submit a change request to the project sponsor for a travel exemption for the team to meet on-site. | Schedule a regular cadence and duration for agile ceremonies and sprint planning. |  | B | The correct answer is B. Confirm with the team which approach works best for exchanging information. This approach follows project management best practices by addressing the situation effectively while maintaining proper processes and stakeholder alignment. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Lead the Project Team | Finance | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 여러 국가와 시간대에 분산되어 있다. 참여 수준이 최적이 아니고 정보 공유가 어렵다. PM은 무엇을 해야 하는가? | 각 팀원의 인터넷 연결을 업그레이드하여 화상 회의를 가능하게 한다 | 팀에 정보 교환에 가장 적합한 접근법을 확인한다 | 팀이 현장에서 만날 수 있도록 스폰서에게 출장 면제 변경 요청을 제출한다 | 애자일 의식과 스프린트 계획을 위한 정기 주기와 기간을 일정 잡는다 |  | B | 정답은 B이다. 팀에 정보 교환에 가장 적합한 접근법을 확인한다. 팀 중심 접근이 참여와 정보 공유를 개선한다. 인터넷 업그레이드(A)는 기술적 문제가 아닐 수 있다. 현장 만남(C)은 비용이 많이 든다. 정기 주기(D)는 유용하지만 팀 의견 확인이 우선이다.
2001 | An organization is about to start a multiphased project. Due to strict regulations, some of the phases must be completely planned in advance. However, other phases allow for more flexibility and experimentation on scope and schedule. The sponsor wants to pursue the project objectives as planned, but also wants to accommodate new information and changes as the project progresses. Which project management approach should the project manager select for this project? | Agile | Incremental | Phased | Hybrid |  | D | When a multiphased project has some phases requiring strict advance planning due to regulations and others allowing flexibility, the project manager should select a hybrid approach. Hybrid combines predictive planning for regulated phases with agile flexibility for others. Agile only (A) does not meet regulatory planning requirements. Incremental (B) provides staged delivery but may lack adaptive flexibility. Phased (C) is structured but does not incorporate agile flexibility. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Tailored Approach | Process | Plan and Manage Schedule | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Hybrid/Tailoring | 조직이 다단계 프로젝트를 시작하려 한다. 엄격한 규제로 일부 단계는 사전에 완전히 계획해야 한다. 그러나 다른 단계는 유연성을 허용한다. 어떤 접근법을 선택해야 하는가? | 애자일 | 점진적 | 단계적 | 하이브리드 |  | D | 일부 단계는 규제로 사전 계획이 필요하고 다른 단계는 유연성을 허용하는 다단계 프로젝트에서는 하이브리드 접근법을 선택해야 한다. 하이브리드는 규제 단계를 위한 예측형 계획과 유연한 단계를 위한 애자일 적응성을 결합한다. 순수 애자일(A)은 규제 단계에 부적합하다. 점진적(B)은 규제 요구를 다루지 않는다. 단계적(C)은 유연성이 부족하다.
2002 | A project manager receives an email from a customer saying that they do not want to keep working with one of the project team members. The customer does not provide any reasons for this sentiment. The project manager is concerned because this project team member is highly skilled and experienced and is key in one of the main project deliverables. What should the project manager do to ease the situation? | Talk to the customer and project team member separately to assess the issue and decide on the next steps. | Ask the project team member to call the customer to apologize for their behavior. | Remove the project team member immediately and assign the pending activities to other team members. | Tell the customer that they do not have the authority to remove project team members. |  | A | When a customer does not want to keep working with a key team member but provides no reasons, the project manager should talk to the customer and project team member separately to assess the issue and decide on next steps. Separate conversations enable objective understanding. Asking the team member to apologize (B) assumes fault. Removing the team member immediately (C) is reactive. Telling the customer they lack authority (D) damages the relationship. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 고객으로부터 프로젝트 팀원과 일하고 싶지 않다는 이메일을 받았다. 고객은 이유를 제공하지 않았다. PM은 무엇을 해야 하는가? | 고객과 팀원에게 별도로 대화하여 이슈를 평가하고 다음 단계를 결정한다 | 팀원에게 고객에게 전화하여 행동에 대해 사과하도록 요청한다 | 팀원을 즉시 제거하고 대기 중인 활동을 다른 팀원에게 할당한다 | 고객에게 팀원을 제거할 권한이 없다고 말한다 |  | A | 고객이 이유 없이 팀원과 일하기를 거부할 때, PM은 고객과 팀원에게 별도로 대화하여 이슈를 평가해야 한다. 별도 대화가 편견 없이 양측 관점을 파악하게 한다. 사과 요청(B)은 이유를 모르는 상태에서 잘못을 인정한다. 즉시 제거(C)는 과도하다. 권한 없음(D)은 고객 관계를 훼손한다.
2003 | As a project is reaching completion, the project sponsor tells the project manager to immediately close the project and to move on to another project. Which critical task should the project manager complete before closing the project? | Archive all the project documents following the organization ' s accepted practices sothe documents can be used in other future projects. | Meet with the project sponsor and advise that the new project might be difficult toundertake because the current project is not yet complete. | Ensure that the whole team is appropriately recognized and organize a project farewellparty to celebrate the project success and closure. | Update and close both the risk register and issue log with the latest updates, and savethem in the organization ' s project management information system (PMIS). |  | A | When the sponsor instructs immediate project closure, the project manager should first archive all project documents following the organization's accepted practices. Proper archiving preserves project information for future reference, lessons learned, and audits. Recognizing the team and celebrating (C) is important but not the critical task. Updating and closing the risk and issue logs (D) is necessary but partial. Meeting the sponsor to discuss the new project (B) defers closure responsibilities. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | WBS/Decomposition | Business Environment | Plan and Manage Risk | Governance | Closing | Embed Quality | Close Project or Phase | Traditional PM | 프로젝트가 완료에 가까워졌을 때, 스폰서가 PM에게 즉시 프로젝트를 종료하고 다른 프로젝트로 이동하라고 한다. PM은 무엇을 먼저 해야 하는가? | 조직의 수용된 관행에 따라 모든 프로젝트 문서를 아카이브하여 다른 프로젝트에 사용할 수 있게 한다 | 스폰서와 만나 현재 프로젝트가 제대로 종료되지 않으면 새 프로젝트가 어려울 수 있다고 조언한다 | 전체 팀이 적절히 인정받도록 하고 프로젝트 성공을 축하하는 행사를 조직한다 | 리스크 등록부와 이슈 로그를 최신 업데이트로 업데이트하고 종료한 뒤 조직의 프로젝트 저장소에 저장한다 |  | A | 스폰서가 즉시 프로젝트 종료를 지시할 때, PM은 먼저 조직의 수용된 관행에 따라 모든 프로젝트 문서를 아카이브해야 한다. 적절한 아카이브가 미래 참조, 교훈, 감사를 위한 프로젝트 정보를 보존한다. 스폰서 조언(B)은 유용하지만 아카이브가 우선이다. 축하 행사(C)는 문서화 후에 한다. 등록부 업데이트(D)는 아카이브의 일부이다.
2004 | Two key team members suggest different options to prevent time overruns and delays. There is a conflict between these two team members because of their divergent views. What should the project manager do next? | Refer the team members to the project charter to resolve the conflict. | Document the facts explained by the team members in the issue log. | Issue a new change request to evaluate this situation and communicate the result. | Schedule a meeting between the team members to find a solution. |  | D | When two key team members conflict over different options to prevent time overruns, the project manager should schedule a meeting between them to find a solution. Face-to-face collaboration enables problem-solving. Referring to the project charter (A) provides context but not resolution. Documenting in the issue log (B) records but does not resolve. Issuing a change request (C) is premature before the team reaches a solution. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 두 핵심 팀원이 시간 초과와 지연을 방지하기 위한 다른 옵션을 제안한다. 다른 접근법으로 인해 갈등이 있다. PM은 무엇을 해야 하는가? | 갈등을 해결하기 위해 프로젝트 헌장을 참조하도록 한다 | 팀원이 설명한 사실을 이슈 로그에 문서화한다 | 상황을 평가하기 위한 새 변경 요청을 발행하고 결과를 커뮤니케이션한다 | 팀원 간 회의를 일정 잡아 해결책을 찾는다 |  | D | 두 팀원이 시간 초과 방지를 위한 다른 옵션으로 갈등할 때, PM은 팀원 간 회의를 일정 잡아 해결책을 찾아야 한다. 대면 협력이 문제 해결을 가능하게 한다. 헌장 참조(A)는 기술적 분쟁에 적합하지 않다. 이슈 로그(B)는 문서화이지 해결이 아니다. 변경 요청(C)은 공식 절차로 과도하다.
2005 | A project manager who is managing a critical project in a multinational company is conducting a progress meeting with all team members. During the meeting, one of the team members states that they are facing a critical problem that will prevent them from completing their assigned task. What should the project manager do? | Schedule a meeting with the concerned team member to review and update the issue log together | Ask the team member to follow the approved communications management plan to communicate their issue | Review the risk register with the team member to find the proper response action for this issue. | Ask the team member to raise a change request to assess the issue in detail |  | A | The PM should schedule a meeting with the concerned team member to review and update the issue log together. This documents the issue, assigns ownership, monitors progress, and implements resolution. Relying solely on the communications plan (A) may not provide timely attention. Reviewing the risk register (C) may not apply if the issue wasn't previously identified as a risk. Raising a change request (D) may be unnecessary if the issue can be resolved within the team. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Scope | Planning | Embed Quality | Collect Requirements | Traditional PM | PM이 다국적 기업의 핵심 프로젝트에서 진행 회의를 진행 중이다. 팀원이 해결되지 않은 우려를 표명한다. PM은 무엇을 해야 하는가? | 해당 팀원과 회의를 일정 잡아 함께 이슈 로그를 검토하고 업데이트한다 | 팀원에게 승인된 커뮤니케이션 관리 계획에 따라 이슈를 전달하도록 요청한다 | 팀원과 리스크 등록부를 검토하여 이 이슈에 대한 적절한 대응 조치를 찾는다 | 팀원에게 이슈를 상세히 평가하기 위한 변경 요청을 제기하도록 요청한다 |  | A | 팀원이 진행 회의에서 해결되지 않은 우려를 표명할 때, PM은 해당 팀원과 회의를 일정 잡아 함께 이슈 로그를 검토하고 업데이트해야 한다. 이슈 문서화, 소유권 할당, 진행 모니터링, 해결 구현이 가능하다. 커뮤니케이션 계획 참조(B)는 일방적이다. 리스크 등록부(C)는 리스크이지 이슈가 아니다. 변경 요청(D)은 과도하다.
2006 | A sales team working on an IT deployment project approached the project manager on several occasions and complained about nonpayment of their overtime pay. The project manager realized that other team members are receiving their overtime pay. What should the project manager do next? | Escalate the issue to the functional manager | Have a discussion with the sales team to find a solution to the issue | Direct the sales team to speak with accounting to resolve the issue | Validate the reason and add n as an issue m the issue log |  | D | When a sales team complains about nonpayment of overtime while other team members receive theirs, the project manager should validate the reason and add it as an issue in the issue log. Documenting the validated concern formally enables tracking and resolution through appropriate channels. Escalating to the functional manager (A) is premature before validation. Having a discussion with the sales team to find a solution (B) is collaborative but the PM may not have authority over payroll. Directing them to accounting (C) passes responsibility without documenting the issue. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Risk & Issue Management | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | IT 배포 프로젝트에서 영업팀이 초과 근무 수당 미지급에 대해 여러 차례 불만을 제기했다. PM은 무엇을 해야 하는가? | 기능 관리자에게 이슈를 에스컬레이션한다 | 영업팀과 대화하여 이슈에 대한 해결책을 찾는다 | 영업팀에게 회계부서와 대화하여 문제를 해결하도록 지시한다 | 이유를 검증하고 이슈 로그에 이슈로 추가한다 |  | D | 영업팀이 초과 근무 수당 미지급에 대해 불만할 때, PM은 이유를 검증하고 이슈 로그에 추가해야 한다. 검증된 우려의 공식 문서화가 추적과 해결을 가능하게 한다. 에스컬레이션(A)은 검증 전에 성급하다. 해결책 논의(B)는 근본 원인 파악 후에 한다. 회계부서 지시(C)는 PM 책임을 회피한다.
2007 | A project manager is assigned to an important company project. While reviewing the lessons learned from a similar, previous project, the project manager finds that the biggest challenges were related to team motivation. What should the project manager do to avoid these challenges? | Colocate the team to encourage more motivational team activities. | Ask the functional manager to motivate the team outside of the project. | Plan to implement team-building strategies throughout the project. | Increase the project budget by 10% for team-related activities and awards. |  | C | When lessons learned from a similar project reveal team motivation as the biggest challenge, the project manager should plan to implement team-building strategies throughout the project. Continuous team-building activities enhance morale, reduce conflicts, increase trust, and foster collaboration across the project lifecycle. Colocating the team (A) may not be feasible. Asking the functional manager to motivate externally (B) delegates the PM's responsibility. Increasing the budget by 10% for awards (D) addresses one aspect of motivation without a comprehensive strategy. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Integration & General PM | People | Engage Stakeholders | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | PM이 중요한 회사 프로젝트에 배정되었다. 유사 프로젝트의 교훈에서 팀 동기 부여가 가장 큰 도전이었음을 발견했다. PM은 무엇을 해야 하는가? | 더 많은 동기 부여 팀 활동을 장려하기 위해 팀을 같은 장소에 배치한다 | 기능 관리자에게 프로젝트 외부에서 팀에 동기를 부여하도록 요청한다 | 프로젝트 전반에 걸쳐 팀 빌딩 전략을 구현할 계획을 세운다 | 팀 관련 활동과 포상을 위해 프로젝트 예산을 10% 늘린다 |  | C | 유사 프로젝트에서 팀 동기 부여가 가장 큰 도전이었을 때, PM은 프로젝트 전반에 걸쳐 팀 빌딩 전략을 구현할 계획을 세워야 한다. 지속적 팀 빌딩이 사기를 높이고 갈등을 줄인다. 같은 장소 배치(A)는 동기 부여를 보장하지 않는다. 기능 관리자(B)는 PM 책임이다. 예산 증가(D)는 과도하다.
2008 | A project manager is leading an agile project in an organization that has not executed this type of project before. In order to ensure the project is following the compliance requirements, what should the project manager do? | Follow the organization ' s process and deliverables for predictive projects, even ifthey compromise the agility and performance of the project. | Meet with the project management office (PMO)/compliance entity to work onprocess tailoring to ensure that the agile deliverables support the compliance requirements of the organization. | Use the risk register to document all of the compliance vulnerabilities generated bythe project so that all decisions are well documented and approved by stakeholders. | Coach upper management on agile practices, explaining that an agile project is concerned with value delivery, and negotiate a way out of the compliance requirements. |  | B | When leading an agile project in an organization without prior agile experience, to ensure compliance the project manager should meet with the PMO/compliance entity to work on process tailoring for agile deliverables. Collaborative tailoring balances agility and compliance. Following predictive processes rigidly (A) undermines agility. Using the risk register for compliance documentation (C) is incomplete. Coaching management to negotiate out of compliance (D) is inappropriate. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Business Environment | Plan and Manage Compliance | Scope | Planning | Be an Accountable Leader | Collect Requirements | Hybrid/Tailoring | PM이 애자일 경험이 없는 조직에서 애자일 프로젝트를 이끌고 있다. 컴플라이언스를 보장하기 위해 PM은 무엇을 해야 하는가? | 예측형 프로젝트의 프로세스와 인도물을 따르되 민첩성과 성과를 타협하더라도 | PMO/컴플라이언스 기관과 만나 애자일 인도물을 위한 프로세스 맞춤화를 작업한다 | 리스크 등록부를 사용하여 프로젝트에서 발생하는 모든 컴플라이언스 취약성을 문서화한다 | 상위 경영진에게 애자일 관행을 코칭하여 가치 전달에 집중함을 설명하고 대안을 협상한다 |  | B | 애자일 경험이 없는 조직에서 컴플라이언스를 보장하려면, PM은 PMO/컴플라이언스 기관과 만나 프로세스 맞춤화를 작업해야 한다. 협력적 맞춤화가 컴플라이언스와 민첩성을 균형 잡는다. 예측형 따르기(A)는 민첩성을 타협한다. 취약성 문서화(C)는 수동적이다. 코칭(D)은 컴플라이언스를 직접 다루지 않는다.
2009 | A project manager is part of an organization that is assessing the use of agile delivery approaches. A new project management office (PMO) manager who had a bad experience with a Scrum approach recommended that the project board replace Scrum with a predictive approach. What should the project manager do? | Review the benefits realization plan to include the cost of the change. | Define a risk management plan (or the new approach, as needed. | Define a project management plan for the new approach, as needed. | Review the communications management plan to identity new stakeholders. |  | C | When a new PMO manager recommends replacing Scrum with a predictive approach after a bad experience, the project manager should define a project management plan for the new approach as needed. Proper planning ensures the new approach is implemented correctly. Reviewing the benefits realization plan (A) addresses cost, not approach transition. Defining a risk management plan (B) is one component, not the full response. Reviewing the communications plan (D) identifies stakeholders but does not address the methodology change. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 조직이 애자일 전달 접근법을 평가 중이다. 새 PMO 관리자가 나쁜 경험 후 스크럼을 예측형으로 교체하도록 권장한다. PM은 무엇을 먼저 해야 하는가? | 변경 비용을 포함하도록 혜택 실현 계획을 검토한다 | 새 접근법을 위한 리스크 관리 계획을 정의한다 | 필요에 따라 새 접근법을 위한 프로젝트 관리 계획을 정의한다 | 새 이해관계자를 식별하기 위해 커뮤니케이션 관리 계획을 검토한다 |  | C | 새 PMO 관리자가 스크럼에서 예측형으로 전환을 권장할 때, PM은 필요에 따라 새 접근법을 위한 프로젝트 관리 계획을 정의해야 한다. 적절한 계획이 새 접근법의 효과적 구현을 보장한다. 혜택 계획(A)은 비용 측면만 다룬다. 리스크 계획(B)은 부분적이다. 커뮤니케이션 계획(D)은 접근법 변경과 직접 관련이 없다.
2010 | A project manager is looking for ways to keep the budget on track throughout the project life cycle. What should the project manager do to ensure that happens? | Baseline the project budget and schedule. | Prioritize high-cost tasks and monitor them. 1227 | Use metrics to track the cost performance. | Evaluate and test all budget variances. |  | C | When looking to keep the budget on track throughout the project life cycle, the project manager should use metrics to track cost performance. EVM indicators like CPI provide early warning of deviations. Baselining (A) is necessary but not sufficient for ongoing tracking. Prioritizing high-cost tasks (B) is selective. Evaluating all budget variances (D) is reactive rather than proactive. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | PM이 프로젝트 수명주기 동안 예산을 추적하기 위한 방법을 찾고 있다. PM은 무엇을 해야 하는가? | 프로젝트 예산과 일정을 기준선화한다 | 고비용 작업을 우선순위화하고 모니터링한다 | 지표를 사용하여 비용 성과를 추적한다 | 모든 예산 차이를 평가하고 테스트한다 |  | C | 프로젝트 수명주기 동안 예산을 추적하려면, PM은 지표를 사용하여 비용 성과를 추적해야 한다. CPI 같은 EVM 지표가 편차에 대한 조기 경보를 제공한다. 기준선화(A)는 필요하지만 추적에 충분하지 않다. 고비용 작업 우선(B)은 부분적이다. 모든 차이 테스트(D)는 비효율적이다.
2011 | A project manager takes over a project team and notices that the team members always wait for management to make decisions during team meetings. In previous work, the project manager discovered that a team is more committed to the deliverables when team members make decisions themselves. However, this team is not willing to be put on the spot. What should the project manager do? | Continue the current practice as long as the team members can still perform. | Encourage the team to start making one decision in every meeting. | Develop decision-making behavior, such as team key performance indicators (KPIs). | Understand the team members' obstacles and discuss means of improvement. |  | D | When a team consistently defers all decisions to management, the PM should first understand the root cause of that hesitation before attempting to change behavior. The deeper issue may involve psychological safety, confidence, or organizational constraints. Moving directly to behavior change (A) without diagnosis is premature. Implementing KPIs (B) doesn't address underlying confidence issues. Ignoring the problem (C) neglects a clear team-development need. Understanding obstacles first, then working with the team on improvement, reflects servant leadership and sustainable team development. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Integrate Sustainability | Manage Team | Sustainability | PM이 프로젝트 팀을 인수했는데, 팀원들이 항상 경영진의 결정을 기다린다. PM은 무엇을 먼저 해야 하는가? | 팀원이 여전히 업무를 수행할 수 있는 한 현재 관행을 계속한다 | 팀이 매 회의에서 하나의 결정을 내리기 시작하도록 장려한다 | 팀 KPI와 같은 의사결정 행동을 개발한다 | 팀원의 장애물을 이해하고 개선 방안을 논의한다 |  | D | 팀이 지속적으로 모든 결정을 경영진에 맡길 때, PM은 먼저 그 주저함의 근본 원인을 이해해야 한다. 심리적 안전, 자신감, 조직적 제약이 원인일 수 있다. 현재 관행 유지(A)는 문제를 방치한다. 하나의 결정 장려(B)는 근본 원인 파악 없이 성급하다. KPI 개발(C)은 측정이지 이해가 아니다.
2012 | After signing an agreement with a vendor, the project manager notices that the vendor is continuously requesting changes to the procurement statement of work (SOW). These changes would improve the project outcome. What should the project manager do next? | Assess the situation as an opportunity for improvement and perform a risk analysis. | Conduct an audit on the procurement process and inform the vendor about the audit ' s 23 observations. | Revise the procurement control process to avoid undesired changes that might affect the schedule. | Consult the list of selected vendors for the bid and evaluate a possible change of vendor. |  | A | Vendor-suggested changes that could enhance project outcomes should be treated as improvement opportunities. However, before proceeding, the PM must conduct a risk analysis to understand potential impacts on scope, schedule, cost, and quality. This careful assessment aligns with PMI's emphasis on continuous improvement balanced with rigorous risk management within procurement processes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Finance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 벤더와 계약 체결 후, PM이 벤더가 조달 작업 기술서에 지속적으로 변경을 요청하는 것을 발견했다. PM은 무엇을 해야 하는가? | 상황을 개선 기회로 평가하고 리스크 분석을 수행한다 | 조달 프로세스에 대한 감사를 실시하고 벤더에게 감사 결과를 알린다 | 일정에 영향을 줄 수 있는 원치 않는 변경을 방지하기 위해 조달 통제 프로세스를 수정한다 | 입찰 선정 벤더 목록을 확인하고 벤더 변경 가능성을 평가한다 |  | A | 벤더가 프로젝트 결과를 향상시킬 수 있는 변경을 제안할 때, 이를 개선 기회로 처리해야 한다. 그러나 진행 전에 범위, 일정, 비용, 품질에 대한 잠재적 영향을 이해하기 위해 리스크 분석을 수행해야 한다. 감사(B)는 적대적이다. 프로세스 수정(C)은 개선 기회를 차단한다. 벤더 변경(D)은 과도하다.
2013 | A project is in its fourth iteration out of eight with a delivery performance of 95%. A project stakeholder asks the project manager about the status of a specific deliverable not visible in the status report. What should the project manager do? | Schedule a meeting with the stakeholder to review the status report | Invite the stakeholder to the next iteration review | Include the deliverable in the status report and resend it to the stakeholder | Invite the stakeholder to the next daily meeting |  | B | When a stakeholder inquires about a deliverable not visible in the status report, the project manager should invite the stakeholder to the next iteration review (sprint review). In agile, the iteration review is the structured forum where the team demonstrates completed work and stakeholders can validate progress, ask questions, and provide feedback. This provides direct inspection of the working product rather than relying on secondary artifacts. Scheduling a separate meeting to review the report (A) adds overhead without improving visibility. Including the deliverable in the report and resending it (C) is reactive and may still lack sufficient context. Inviting the stakeholder to a daily meeting (D) is inappropriate—daily standups are for team synchronization, not stakeholder deliverable validation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Traditional PM | 프로젝트가 8번 중 4번째 이터레이션에 있으며 95% 납품 성과이다. 이해관계자가 상태 보고서에 보이지 않는 인도물에 대해 질문한다. PM은 무엇을 해야 하는가? | 이해관계자와 회의를 일정 잡아 상태 보고서를 검토한다 | 이해관계자를 다음 이터레이션 리뷰에 초대한다 | 상태 보고서에 인도물을 포함하고 이해관계자에게 재전송한다 | 이해관계자를 다음 데일리 회의에 초대한다 |  | B | 이해관계자가 상태 보고서에 보이지 않는 인도물에 대해 질문할 때, PM은 이해관계자를 다음 이터레이션 리뷰(스프린트 리뷰)에 초대해야 한다. 이터레이션 리뷰가 팀이 완료된 작업을 시연하고 피드백을 받는 구조화된 포럼이다. 회의(A)는 비효율적이다. 보고서 재전송(C)은 일방적이다. 데일리 회의(D)는 상세 시연에 적합하지 않다.
2014 | A team is assembled for a new project that will use a predictive approach through requirements gathering and an agile approach for development and testing. Not everyone on the team has experience working in agile. The schedule has begun slipping due to the unclear structure of the agile development approach. What should the project manager have done to prevent this situation? | Conducted routine meetings and identified team members who are under performing | Established daily standup meetings to track and report on team progress and escalated delays to stakeholders as they occurred | Met with the team, allowed team members to make decisions about what to do and established performance goals | Set up weekly status meetings to review team progress, prepared weekly status reports to track progress and regularly escalated delays |  | C | When an agile development approach causes schedule slippage due to team unfamiliarity, the PM should have provided adequate training and coaching on agile practices before execution began. Transitioning to a hybrid approach requires intentional change management—ensuring all team members understand agile ceremonies, artifacts, and their roles within the framework. Without this foundational preparation, confusion about process structure will inevitably lead to delays and reduced effectiveness. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 예측형 요구사항 수집과 애자일 개발을 사용하는 새 프로젝트에 팀이 조립되었다. 애자일에 익숙하지 않은 팀의 일정이 밀렸다. PM이 이전에 무엇을 했어야 하는가? | 정기 회의를 진행하고 저성과 팀원을 식별했다 | 데일리 스탠드업을 설정하고 이해관계자에게 지연을 에스컬레이션했다 | 팀과 만나 팀원이 무엇을 할지 결정하게 하고 성과 목표를 수립했다 | 주간 상태 회의를 설정하고 주간 보고서를 준비하여 진행을 추적했다 |  | C | 애자일에 익숙하지 않은 팀이 일정 지연을 겪을 때, PM은 팀과 만나 팀원이 스스로 결정하게 하고 성과 목표를 수립했어야 한다. 자율성과 명확한 목표가 애자일 전환을 지원한다. 저성과자 식별(A)은 비난적이다. 에스컬레이션(B)은 팀 역량 구축이 아니다. 주간 보고(D)는 예측형 접근이다.
2015 | A project team is working on an agile software development project. The project manager is concerned that the virtual team may not be as effective as a colocated team at headquarters. Which two actions should the project manager leverage to ensure the team is meeting performance expectations? (Choose two) | Utilize a web-based kanban board. | Implement time-keeping software for team members. | Hold daily virtual meetings to review progress. | Task functional managers to drive accountability. | Require a monthly individual status report. | A, C | To ensure a virtual agile team meets performance expectations, the project manager should utilize a web-based kanban board and hold daily virtual meetings to review progress. Kanban visualizes workflow and limits WIP, while daily meetings maintain team coordination. Implementing time-keeping software (B) focuses on tracking, not performance. Tasking functional managers (D) undermines team self-organization. Requiring monthly individual reports (E) is too infrequent. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Kanban | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | Traditional PM | PM이 가상 애자일 소프트웨어 개발 팀의 성과가 대면 팀만큼 효과적이지 않을까 우려한다. PM은 무엇을 해야 하는가? (2개 선택) | 웹 기반 칸반 보드를 활용한다 | 팀원을 위한 시간 추적 소프트웨어를 구현한다 | 진행 상황을 검토하기 위한 데일리 가상 회의를 개최한다 | 기능 관리자에게 책임을 추진하도록 요청한다 | 월간 개별 상태 보고서를 요구한다 | A, C | 가상 애자일 팀의 성과를 보장하기 위해, PM은 웹 기반 칸반 보드를 활용하고(A) 진행 상황 검토를 위한 데일리 가상 회의를 개최해야 한다(C). 칸반이 워크플로우를 시각화하고, 데일리 회의가 팀 소통을 유지한다. 시간 추적(B)은 미시관리이다. 기능 관리자(D)는 자율성을 해친다. 월간 보고(E)는 빈도가 부족하다.
2016 | A steering committee member is complaining about the weekly report. They stated that the report is too long and has unnecessary details. As a result, they are unable to obtain the main message and take action. What should the project manager do to avoid similar complaints? | Demonstrate the weekly reports in a presentation for the steering committee member. | Send a shorter daily report to this steering committee member. | Verify the information needed for steering committee members. | Present the status at a weekly meeting with the steering committee. |  | C | When a steering committee member complains the weekly report is too long with unnecessary details, the project manager should verify the information needed for steering committee members. Understanding audience needs enables tailored reporting. Demonstrating reports in a presentation (A) changes format, not content. Sending shorter daily reports (B) increases frequency without addressing relevance. Presenting status at weekly meetings (D) changes medium, not substance. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Be an Accountable Leader | Define Scope | Traditional PM | 운영위원회 위원이 주간 보고서가 너무 길고 불필요한 세부사항이 있다고 불만한다. PM은 무엇을 해야 하는가? | 운영위원회 위원을 위해 주간 보고서를 프레젠테이션으로 시연한다 | 이 운영위원회 위원에게 더 짧은 일일 보고서를 보낸다 | 운영위원회 위원에게 필요한 정보를 확인한다 | 운영위원회와 주간 회의에서 상태를 발표한다 |  | C | 운영위원회 위원이 보고서가 너무 길다고 불만할 때, PM은 운영위원회 위원에게 필요한 정보를 확인해야 한다. 청중 니즈 이해가 맞춤 보고를 가능하게 한다. 프레젠테이션(A)은 형식 변경이지 내용 개선이 아니다. 짧은 일일 보고(B)는 빈도 변경이지 내용 개선이 아니다. 주간 회의(D)는 시간 소모적이다.
2017 | During a design workshop, the engineers ask the project manager about the safety prerequisites for the new product's operating procedures. What should the project manager do? | Provide the team with the enterprise environmental factors (EEFs). | Run a benchmark with similar sites to compare compliance constraints. | Look into lessons learned documentation for similar projects. | Hire a specialized engineer to support the design team. |  | A | When engineers ask about safety prerequisites for new product operating procedures, the project manager should provide the team with the enterprise environmental factors (EEFs). EEFs include governmental regulations, safety standards, legal requirements, and industry standards—precisely the type of mandatory information needed to define safety prerequisites. Running a benchmark with similar sites (B) helps improve performance but does not ensure compliance with formal safety standards. Reviewing lessons learned (C) provides past project insights but may not reflect current safety requirements. Hiring a specialized engineer (D) may be unnecessary if the relevant safety standards are already documented in the EEFs. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 설계 워크숍에서 엔지니어가 새 제품 운영 절차의 안전 전제조건에 대해 PM에게 질문한다. PM은 무엇을 해야 하는가? | 팀에게 기업 환경 요인(EEF)을 제공한다 | 유사 사이트와 벤치마크를 실행하여 컴플라이언스 제약을 비교한다 | 유사 프로젝트의 교훈 문서를 조사한다 | 설계 팀을 지원하기 위해 전문 엔지니어를 고용한다 |  | A | 엔지니어가 새 제품 운영 절차의 안전 전제조건에 대해 질문할 때, PM은 팀에게 기업 환경 요인(EEF)을 제공해야 한다. EEF에는 정부 규제, 안전 표준, 법적 요구사항이 포함된다. 벤치마크(B)는 표준이 아닌 비교이다. 교훈(C)은 현재 규제를 다루지 않는다. 전문가 고용(D)은 과도하다.
2018 | A project team is concluding the final sprint to deliver two work packages. However, the scrum master has not scheduled sprints for three packages on the critical path, which is going to cause the schedule performance index (SPI) to trend toward 0.90 the following month. What should the project manager do first? | Instruct the scrum master to suspend the current sprints and initiate the critical sprints immediately. | Contact the project sponsor to request adjustment to the completion date and to enable the current workflow. | Ask the scrum master to identify why sprints are in process for work that is not on the critical path. | Evaluate the schedule performance index (SPI) trend for slack to enable all five sprints while maintaining the cost performance index (CPI). |  | C | The PM should direct the scrum master to investigate why sprints are in progress for work not on the critical path. In agile settings, the PM's role centers on facilitating team collaboration, removing impediments, and ensuring continuous value delivery while respecting agile principles and the established ceremony structure. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 팀이 최종 스프린트에서 2개 작업 패키지를 납품 중이다. 그러나 스크럼 마스터가 크리티컬 패스에 없는 3개 패키지에 대해 스프린트를 예약했다. PM은 무엇을 해야 하는가? | 스크럼 마스터에게 현재 스프린트를 중단하고 긴급 스프린트를 즉시 시작하도록 지시한다 | 프로젝트 스폰서에게 연락하여 완료일 조정을 요청하고 현재 워크플로우를 유지한다 | 스크럼 마스터에게 크리티컬 패스에 없는 작업에 대해 스프린트가 진행 중인 이유를 확인하도록 요청한다 | 모든 5개 스프린트를 가능하게 하면서 비용 성과를 유지하기 위한 SPI 추세의 여유를 평가한다 |  | C | 스크럼 마스터가 크리티컬 패스에 없는 작업에 스프린트를 예약했을 때, PM은 이유를 조사하도록 요청해야 한다. 팀 협력 퍼실리테이션, 장애물 제거, 지속적 가치 전달 보장이 PM 역할이다. 즉시 중단(A)은 지시적이다. 완료일 조정(B)은 원인 파악 전에 성급하다. SPI 평가(D)는 분석이지 조치가 아니다.
2019 | During the course of a project, a junior team member approaches the project manager for some direction and advice on risk mitigation. How should the project manager respond? | Inform the junior team member that risk mitigation is not part of their work | Refer the junior team member to the senior team member who develops the risk mitigation strategy | Offer guidance and follow up with some developmental activity for the junior team member | Tell the junior team member that the information is available in lessons learned |  | C | When a junior team member asks for direction on risk mitigation, the project manager should offer guidance and follow up with developmental activities. Mentoring builds the junior member's capabilities. Telling them it is not their work (A) excludes them from risk management. Referring to a senior member (B) misses a coaching opportunity. Directing to lessons learned (D) is impersonal and indirect. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Build an Empowered Culture | Identify Risks | Traditional PM | 주니어 팀원이 리스크 완화에 대한 방향과 조언을 PM에게 요청한다. PM은 어떻게 해야 하는가? | 주니어 팀원에게 리스크 완화가 그들의 업무가 아니라고 알린다 | 주니어 팀원을 리스크 완화 전략을 개발하는 시니어 팀원에게 안내한다 | 지침을 제공하고 주니어 팀원을 위한 개발 활동으로 후속 조치한다 | 주니어 팀원에게 교훈에서 정보를 찾을 수 있다고 말한다 |  | C | 주니어 팀원이 리스크 완화 지침을 요청할 때, PM은 지침을 제공하고 개발 활동으로 후속 조치해야 한다. 멘토링이 주니어 팀원의 역량을 구축한다. 업무 아님(A)은 성장을 배제한다. 시니어 안내(B)는 PM 책임을 위임한다. 교훈 참조(D)는 직접적 지도가 아니다.
2020 | A software development provider reports an issue that is blocking the other remaining deliverables. What should the project manager do? | Ask the provider to seek options to solve the issue | Review the current plan and consolidate if necessary | Schedule a meeting with the provider to collaborate on the options | Add the issue to the issue log and report it at the next review meeting |  | C | When a software development provider reports a blocking issue affecting remaining deliverables, the project manager should schedule a meeting with the provider to collaborate on options. Collaborative problem-solving identifies effective solutions and maintains the relationship. Asking the provider to seek options alone (A) disengages the PM. Reviewing the plan and consolidating (B) is internal and does not involve the provider. Adding to the issue log and waiting for the next review (D) delays resolution. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 소프트웨어 개발 제공업체가 나머지 인도물을 차단하는 이슈를 보고했다. PM은 무엇을 해야 하는가? | 제공업체에게 이슈 해결 옵션을 찾도록 요청한다 | 현재 계획을 검토하고 필요 시 통합한다 | 제공업체와 회의를 일정 잡아 옵션에 대해 협력한다 | 이슈 로그에 이슈를 추가하고 다음 검토 회의에서 보고한다 |  | C | 제공업체가 차단 이슈를 보고할 때, PM은 제공업체와 회의를 일정 잡아 옵션에 대해 협력해야 한다. 협력적 문제 해결이 효과적 해결책을 식별한다. 옵션 찾기 요청(A)은 제공업체에만 맡긴다. 계획 검토(B)는 즉각적 해결이 아니다. 이슈 로그(D)는 문서화이지 해결이 아니다.
2021 | During the execution of a project, a key stakeholder complains to the project manager about recent communications. The key stakeholder explains that the relevant information from the project team was incomplete and late. As a result, the key stakeholder is beginning to disengage from the project. What should the project manager do? | Ask the project sponsor to hold a meeting with the key stakeholder to ensure that the stakeholder is engaged in the project. | Explain to the key stakeholder the way in which the project team communicates information. | Send relevant information to all key stakeholders simultaneously to ensure consistent communication. | Update the communications management plan to fulfill the key stakeholder ' s expectations about relevant information. |  | D | When a key stakeholder complains about incomplete and late information and begins to disengage, the project manager should update the communications management plan to fulfill the stakeholder's expectations. Plan updates address systemic communication gaps. Asking the sponsor to intervene (A) delegates the relationship. Explaining the team's communication method (B) is defensive. Sending information to all simultaneously (C) does not tailor to specific needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 프로젝트 실행 중 주요 이해관계자가 최근 커뮤니케이션에 대해 불만을 제기한다. 정보가 불완전하고 늦게 온다고 한다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 이해관계자와 회의를 열어 참여를 보장하도록 요청한다 | 프로젝트 팀이 정보를 전달하는 방식을 이해관계자에게 설명한다 | 모든 주요 이해관계자에게 관련 정보를 동시에 보내 일관된 커뮤니케이션을 보장한다 | 이해관계자의 기대에 부합하도록 커뮤니케이션 관리 계획을 업데이트한다 |  | D | 주요 이해관계자가 불완전하고 늦은 정보에 불만하고 이탈하기 시작할 때, PM은 이해관계자의 기대에 부합하도록 커뮤니케이션 관리 계획을 업데이트해야 한다. 계획 업데이트가 체계적 커뮤니케이션 격차를 해결한다. 스폰서 회의(A)는 간접적이다. 방식 설명(B)은 방어적이다. 동시 발송(C)은 맞춤화가 없다.
2022 | A project manager is working in a company that has several global offices. During resource planning for a new project, the project manager realizes that the company requires projects to include team members from different continents. What should the project manager do to ensure a successful project execution? | Send emails with information about the project deliverables on the first day of the project. | Plan for a meeting with the project sponsor to discuss the possibility of utilizing only local colleagues. | invite all resources to the project manager ' s location to form a cohesive team until all deliverables are completed, | Connect with every location and check their preferred methods of communication. |  | D | When a company requires projects to include team members from different continents, the project manager should connect with every location and check their preferred methods of communication. Understanding communication preferences across locations enables the PM to develop an effective communication plan that promotes collaboration. Sending emails on the first day (A) is one-directional and assumes a single method works. Planning a meeting with the sponsor to discuss using only local colleagues (B) contradicts the organizational requirement. Inviting all resources to one location (C) is impractical and costly. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | PM이 여러 글로벌 사무소가 있는 회사에서 일하고 있다. 자원 계획에서 다른 대륙의 팀원을 포함해야 한다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 첫날에 프로젝트 인도물에 대한 정보가 담긴 이메일을 보낸다 | 프로젝트 스폰서와 만나 현지 동료만 활용할 가능성을 논의한다 | 모든 인도물이 완료될 때까지 PM의 위치에 모든 자원을 초대하여 결속력 있는 팀을 구성한다 | 모든 위치에 연결하여 선호하는 커뮤니케이션 방법을 확인한다 |  | D | 다른 대륙의 팀원을 포함해야 할 때, PM은 모든 위치에 연결하여 선호하는 커뮤니케이션 방법을 확인해야 한다. 위치별 커뮤니케이션 선호도 이해가 효과적 협업을 가능하게 한다. 이메일(A)은 일방적이다. 현지만(B)은 요구사항에 반한다. 한 장소 초대(C)는 비현실적이다.
2023 | A project team is implementing an enterprise notification tool with a vendor. The project manager noticed that this vendor's developer has been reporting the same status for several weeks in a row. A few days later, the vendor communicates that the deliverable will not be completed on time due to resource constraints within their company. What should the project manager do next? | Update the risk register to reflect the delay, communicate the impact to the schedule, and escalate to management for assistance. | Add the delay to the issue log and work with the vendor for a resolution that will bring the schedule back on track. | Review the contract with the vendor to go over the financial penalty that is applicable to this situation. | Conduct a project review with the project sponsor to explain the delay and add a developer to work with the vendor. |  | B | When a vendor's developer reports the same status for weeks and then announces a delay due to resource constraints, the project manager should add the delay to the issue log and work with the vendor for a resolution to bring the schedule back on track. Collaborative problem-solving with documentation is proactive. Updating the risk register and escalating (A) focuses on documentation over resolution. Reviewing the contract for penalties (C) is adversarial. Conducting a project review and adding a developer (D) exceeds the PM's authority over vendor staffing. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | PM이 벤더와 기업 알림 도구를 구현 중이다. 벤더 개발자가 몇 주간 같은 상태를 보고하다가 자원 제약으로 지연을 발표했다. PM은 무엇을 해야 하는가? | 리스크 등록부를 업데이트하여 지연을 반영하고, 일정에 미치는 영향을 전달하며, 경영진에게 에스컬레이션한다 | 이슈 로그에 지연을 추가하고 벤더와 협력하여 일정을 정상화할 해결책을 찾는다 | 벤더와 계약을 검토하여 이 상황에 적용 가능한 재정적 페널티를 확인한다 | 프로젝트 스폰서와 프로젝트 검토를 실시하여 지연을 설명하고 개발자를 추가한다 |  | B | 벤더 개발자가 자원 제약으로 지연을 발표할 때, PM은 이슈 로그에 지연을 추가하고 벤더와 협력하여 일정을 정상화할 해결책을 찾아야 한다. 협력적 문제 해결이 건설적이다. 에스컬레이션(A)은 협력 전에 성급하다. 페널티 검토(C)는 적대적이다. 개발자 추가(D)는 PM이 결정할 사항이 아니다.
2024 | The main project stakeholder was fired and replaced by another stakeholder. The new stakeholder reviewed the project scope and requested numerous changes, arguing that the stakeholder's team is unhappy with the results to date. What should the project manager do? | Put the new requirements in the backlog and submit a formal change request forapproval. | Put the new requirements in the backlog with high priority and implement therequested changes. | Put the new requirements in the backlog and let the product owner check their valueand priority. | Put the new requirements in the backlog with low priority and implement the requestedchanges. |  | A | When a new stakeholder requests numerous changes after replacing the main stakeholder, the project manager should put the new requirements in the backlog and submit a formal change request for approval. Formal change control ensures governance. Adding with high priority (B) or low priority (D) bypasses approval. Letting the PO check value and priority (C) skips formal change control. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 주요 이해관계자가 해고되고 새 이해관계자로 교체되었다. 새 이해관계자가 범위를 검토하고 다수의 변경을 요청했다. PM은 무엇을 해야 하는가? | 새 요구사항을 백로그에 넣고 승인을 위한 공식 변경 요청을 제출한다 | 새 요구사항을 높은 우선순위로 백로그에 넣고 요청된 변경을 구현한다 | 새 요구사항을 백로그에 넣고 제품 책임자가 가치와 우선순위를 확인하게 한다 | 새 요구사항을 낮은 우선순위로 백로그에 넣고 요청된 변경을 구현한다 |  | A | 새 이해관계자가 다수의 변경을 요청할 때, PM은 새 요구사항을 백로그에 넣고 승인을 위한 공식 변경 요청을 제출해야 한다. 공식 변경 통제가 거버넌스를 보장한다. 높은 우선순위 구현(B)은 통제 없이 진행한다. 제품 책임자 확인(C)은 공식 승인이 아니다. 낮은 우선순위(D)는 이해관계자를 무시한다.
2025 | A project manager for a technology project is informed by the cybersecurity team that there are changes in the government's cybersecurity requirements. The project manager calls a team meeting to discuss the requirements, and the team learns that the design changes can be made at no additional cost. What should the project manager direct the team to do? | Ask the project sponsor to increase funds in the contingency reserve as a risk mitigation. | Accept the cybersecurity team's request as the security of the company is at risk ofbeing noncompliant. | Update the scope management plan to track the new government requirements. | Request a change through the change control process to manage the new cybersecurityrequirements. |  | D | When the cybersecurity team reports changes in government requirements and the design changes can be made at no additional cost, the project manager should request a change through the change control process. Even costless changes require formal documentation and approval for governance. Increasing the contingency reserve (A) is unnecessary when there is no additional cost. Accepting the request without change control (B) bypasses governance. Updating the scope management plan (C) is one component, not the full process. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Change Management | Process | Plan and Manage Schedule | Scope | Planning | Be an Accountable Leader | Collect Requirements | Traditional PM | 사이버보안 팀이 정부의 사이버보안 요구사항이 변경되었다고 알린다. 설계 변경이 추가 비용 없이 가능하다. PM은 무엇을 해야 하는가? | 리스크 완화를 위해 스폰서에게 비상 예비비 증가를 요청한다 | 회사 보안이 비준수 위험에 있으므로 사이버보안 팀의 요청을 수락한다 | 새 정부 요구사항을 추적하기 위해 범위 관리 계획을 업데이트한다 | 새 사이버보안 요구사항을 관리하기 위해 변경 통제 프로세스를 통해 변경을 요청한다 |  | D | 사이버보안 요구사항이 변경되고 추가 비용 없이 설계 변경이 가능할 때, PM은 변경 통제 프로세스를 통해 변경을 요청해야 한다. 비용이 없는 변경도 공식 문서화와 승인이 필요하다. 비상 예비비 증가(A)는 추가 비용이 없으므로 불필요하다. 직접 수락(B)은 공식 프로세스를 우회한다. 범위 관리 계획(C)은 추적이지 변경 승인이 아니다.
2026 | A project manager has just been designated to lead an approved project with a virtual team. The team members are from several countries and have never met before. In order to promote team engagement and introduce the project team, what should the project manager do? | Share a presentation with information about each project team member. | Schedule a kickoff meeting to present the whole project team. | Schedule multiple one-on-one meetings between team members. | Share all members ' resumes and photographs in a sharing digital platform. |  | B | When leading an approved project with a virtual team from several countries who have never met, the project manager should schedule a kickoff meeting to present the whole project team. A kickoff meeting establishes rapport, sets expectations, and aligns the team on goals and communication norms. Sharing a presentation about team members (A) lacks real-time interaction. Scheduling one-on-one meetings (C) does not create group alignment. Sharing resumes and photos on a platform (D) is informational, not interactive. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | PM이 여러 국가의 가상 팀으로 승인된 프로젝트를 이끌게 되었다. 팀원들은 만난 적이 없다. PM은 무엇을 먼저 해야 하는가? | 각 프로젝트 팀원 정보가 포함된 프레젠테이션을 공유한다 | 전체 프로젝트 팀을 소개하는 킥오프 회의를 일정에 잡는다 | 팀원 간 여러 일대일 회의를 일정에 잡는다 | 공유 디지털 플랫폼에 모든 팀원의 이력서와 사진을 공유한다 |  | B | 여러 국가의 가상 팀원들이 처음 만날 때, PM은 전체 프로젝트 팀을 소개하는 킥오프 회의를 일정에 잡아야 한다. 킥오프 회의가 팀 결속과 프로젝트 방향을 설정한다. 프레젠테이션 공유(A)는 상호작용이 부족하다. 일대일 회의(C)는 팀 결속에 비효율적이다. 이력서/사진 공유(D)는 비인격적이다.
2027 | During a weekly status update meeting with the project management office (PMO), the assigned project manager notices some stakeholders raise concerns about the implementation plan even though the status was regularly communicated to all stakeholders. What should the project manager do? | Schedule a meeting with the stakeholders to assess the root cause and update the plan. | Focus on the key stakeholders first and meet with them individually to resolve their doubts and concerns. | Involve stakeholders in retrospective meetings to resolve stakeholder doubts and improve communication. | Ask the team to improve the communications management plan with stakeholders and add more details to their updates. |  | A | When stakeholders raise implementation plan concerns despite regular status updates, the project manager should schedule a meeting with stakeholders to assess the root cause and update the plan. Direct engagement identifies whether the concern stems from information gaps, misalignment, or plan deficiencies. Focusing only on key stakeholders individually (B) is narrow. Involving stakeholders in retrospectives (C) may not fit a predictive setting. Improving the communications plan with more details (D) assumes the communication method is the issue without validation. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 주간 상태 업데이트 회의에서 PM이 이해관계자들이 구현 계획에 의문과 우려를 제기하는 것을 발견했다. PM은 무엇을 해야 하는가? | 이해관계자와 회의를 예약하여 근본 원인을 평가하고 계획을 업데이트한다 | 핵심 이해관계자에게 먼저 집중하여 개별 회의를 통해 의문과 우려를 해결한다 | 이해관계자를 회고 회의에 참여시켜 의문을 해결하고 커뮤니케이션을 개선한다 | 팀에게 커뮤니케이션 관리 계획을 개선하고 이해관계자에 더 많은 세부사항을 추가하도록 요청한다 |  | A | 이해관계자들이 정기 상태 업데이트에도 불구하고 구현 계획에 우려를 제기할 때, PM은 이해관계자와 회의를 예약하여 근본 원인을 평가하고 계획을 업데이트해야 한다. 직접적인 참여가 우려를 효과적으로 해결한다. 핵심만 집중(B)은 다른 이해관계자를 배제한다. 회고 참여(C)는 팀 내부 활동이다. 계획 개선(D)은 간접적이다.
2028 | During a planning session, the development team and the product owner are arguing about the effort needed to deliver a specific feature in a software development project. The product owner says that the feature can be developed in one week, whereas the team estimates that it will take at least two weeks. After several hours of discussion, they have not reached an agreement. What should the project lead do? | Ask the project team to accept the shorter estimate as it is important to keep a good relationship with the product owner. | Communicate to the stakeholders that the project has to be delayed for two weeks. | Educate the product owner that the project team members are the most appropriate group for assessing the effort. | Decide what should be the time estimate and proceed with the planning meeting. |  | C | The correct answer is C. Educate the product owner that the project team members are the most appropriate group for assessing the effort. This approach follows project management best practices by addressing the situation effectively, maintaining proper processes, and ensuring alignment with stakeholder expectations and project objectives. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 계획 세션에서 개발팀과 제품 책임자가 사용자 스토리 전달 노력에 대해 논쟁 중이다. PM은 무엇을 해야 하는가? | 좋은 관계 유지를 위해 팀에게 짧은 추정치를 수락하도록 요청한다 | 이해관계자에게 프로젝트가 2주 지연되어야 함을 전달한다 | 제품 책임자에게 프로젝트 팀원이 노력 평가에 가장 적합한 그룹임을 교육한다 | 시간 추정치를 결정하고 계획 회의를 진행한다 |  | C | 정답은 C이다. 제품 책임자에게 프로젝트 팀원이 노력 평가에 가장 적합한 그룹임을 교육한다. 팀의 기술적 전문성을 존중하면서 이해를 구축한다. 짧은 추정 수락(A)은 비현실적 일정을 만든다. 지연 전달(B)은 시기상조이다. PM이 결정(D)은 팀 자율성을 침해한다.
2029 | A project is assigned to two different project teams to develop product features. One team uses a predictive approach and the other team uses an agile approach to complete the work. Senior management is concerned about the success of the project. What should the project manager do? | Insist the teams both follow either a predictive or agile approach. | Allow the teams to continue using their approaches and gradually adapt to a hybrid model. | Let a senior team member select the approach that is appropriate. | Advise the teams to follow the company's existing project management approach. |  | B | When two teams use different approaches (predictive and agile) and senior management is concerned, the project manager should allow the teams to continue and gradually adapt to a hybrid model. Respecting existing workflows while moving toward integration is pragmatic. Forcing a single approach (A) disrupts productivity. Letting a senior member select (C) delegates methodology decisions inappropriately. Following the company's existing approach (D) ignores team strengths. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Hybrid/Tailoring | 두 프로젝트 팀이 제품 기능 개발에 배정되었다. 하나는 예측형, 하나는 애자일 접근법을 사용한다. 상위 경영진이 우려한다. PM은 무엇을 해야 하는가? | 두 팀 모두 예측형 또는 애자일 중 하나를 따르도록 한다 | 팀이 각자 접근법을 계속 사용하되 점진적으로 하이브리드 모델에 적응하도록 한다 | 선임 팀원이 적절한 접근법을 선택하도록 한다 | 팀에게 회사의 기존 프로젝트 관리 접근법을 따르도록 조언한다 |  | B | 두 팀이 다른 접근법을 사용하고 경영진이 우려할 때, PM은 팀이 각자 접근법을 계속 사용하되 점진적으로 하이브리드 모델에 적응하도록 해야 한다. 기존 방식을 존중하면서 통합을 추구한다. 하나로 통일(A)은 팀 역량을 무시한다. 선임 선택(C)은 위임이다. 회사 접근법(D)은 유연성이 부족하다.
2030 | A third-party supplier demands payment for the services provided for a project. The agreement was that payment would be made after the organization receives payment from the client. The third-party supplier lacks the capital to meet their payroll and has informed the project manager that if they do not receive payment quickly, they will withdraw team members from the project. What should the project manager do? | Explain the third-party supplier situation to the client and request payment. | Reassign resources from other projects to pay the third-party supplier. | Inform the client that the project must be delayed until payment is received. | Process a bank loan to pay the payroll of the third-party supplier. |  | A | When a third-party supplier demands payment while the agreement ties payment to client receipt, and the supplier threatens to withdraw team members, the project manager should explain the situation to the client and request payment. Transparent communication with the client addresses the root cause—payment flow—and prevents project disruption. Reassigning resources from other projects (B) is unauthorized. Informing the client of project delay (C) is premature. Processing a bank loan (D) is outside the PM's authority. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 제3자 공급업체가 프로젝트 서비스 대금 지급을 요구한다. 계약상 고객 수령 후 지급 조건이다. 공급업체가 팀원 철수를 위협한다. PM은 무엇을 해야 하는가? | 고객에게 제3자 공급업체 상황을 설명하고 지급을 요청한다 | 다른 프로젝트의 자원을 재배치하여 제3자 공급업체에 지급한다 | 지급이 이루어질 때까지 프로젝트를 지연해야 함을 고객에게 알린다 | 은행 대출을 처리하여 제3자 공급업체 급여를 지급한다 |  | A | 제3자 공급업체가 대금 지급을 요구하고 팀원 철수를 위협할 때, PM은 고객에게 상황을 설명하고 지급을 요청해야 한다. 투명한 커뮤니케이션이 해결의 기초이다. 자원 재배치(B)는 다른 프로젝트에 영향을 준다. 프로젝트 지연 통보(C)는 협박적이다. 은행 대출(D)은 부적절한 재정 결정이다.
2031 | A project team is continually being asked by stakeholders to perform rework on their deliverables. The project manager discovers that this is due to poor initial quality. What should the project manager do? | Request a subject matter expert (SME) from the project sponsor to identify and address the quality issues with the team. | Schedule a quality retrospective and discuss the challenges that resulted in poor initial quality with the team. | Host a team meeting and ask the team to fix any quality issues immediately since the stakeholders' needs are the main focus. | Facilitate a discussion and come to an agreement about what quality means for both the team and the stakeholders. |  | D | When stakeholders continually request rework due to poor initial quality, the project manager should facilitate a discussion to come to an agreement about what quality means for both the team and stakeholders. Aligning on quality expectations prevents future rework by establishing shared acceptance criteria. Asking the team to fix issues immediately (A) is reactive. Requesting an SME (B) adds expertise without addressing expectation gaps. Holding a quality retrospective (C) may produce actions that still miss stakeholder needs. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 팀이 이해관계자로부터 지속적으로 인도물 재작업을 요청받고 있다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 품질 문제를 식별하고 해결할 주제 전문가(SME)를 요청한다 | 품질 회고를 예약하고 초기 품질 저하의 원인이 된 문제를 논의한다 | 팀 회의를 개최하고 이해관계자 요구가 중요하므로 품질 문제를 즉시 수정하도록 요청한다 | 토론을 퍼실리테이션하고 팀과 이해관계자 모두에게 품질의 의미에 대해 합의에 도달한다 |  | D | 이해관계자가 지속적으로 재작업을 요청할 때, PM은 토론을 퍼실리테이션하고 팀과 이해관계자 모두에게 품질의 의미에 대해 합의해야 한다. 공통 이해가 재작업을 방지한다. SME 요청(A)은 외부 의존이다. 회고(B)는 내부 팀만 다룬다. 즉시 수정(C)은 근본 원인을 해결하지 않는다.
2032 | A project manager is defining the sprint goals with the team. A team member who is responsible for acceptance testing starts criticizing the goals and cannot come to an agreement with the other team members. How should the project manager handle this situation? | Reprimand the team member and provide immediate coaching on goal alignment. | Approach the team member with empathy and obtain agreement through collaboration. | Proceed with defining the goals with the team members given the majority approval from the team. | Request to meet with the team member and ask that any issues be escalated separately. |  | B | When a team member criticizes sprint goals and cannot agree with others, the project manager should approach the team member with empathy and obtain agreement through collaboration. This fosters a positive team culture while addressing the concern constructively. Reprimanding and coaching immediately (A) is confrontational. Proceeding with majority approval (C) overrides without resolving the disagreement. Requesting a separate meeting for escalation (D) isolates rather than includes the team member. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | PM이 팀과 스프린트 목표를 정의하고 있다. 인수 테스트 담당 팀원이 목표를 비판하고 다른 팀원과 합의하지 못한다. PM은 무엇을 해야 하는가? | 팀원을 질책하고 목표 정렬에 대한 즉각적 코칭을 제공한다 | 팀원에게 공감으로 접근하고 협력을 통해 합의를 얻는다 | 팀 다수의 승인이 있으므로 나머지 팀원과 목표 정의를 진행한다 | 팀원과 만나 문제를 별도로 에스컬레이션하도록 요청한다 |  | B | 팀원이 스프린트 목표를 비판하고 합의하지 못할 때, PM은 공감으로 접근하고 협력을 통해 합의를 얻어야 한다. 공감과 협력이 긍정적 팀 환경을 촉진한다. 질책(A)은 신뢰를 훼손한다. 다수 진행(C)은 불만을 무시한다. 별도 에스컬레이션(D)은 문제를 회피한다.
2033 | From previous lessons learned working with a client, a project manager notes that the client's turn-around times on documents sent for approval were very slow and well outside of the agreed timelines. At the initial kick-off meeting with the same client, how should the project manager approach this issue for the new project? | Update the project risk register with the potential for delays | * Work with the client on an acceptable amount of time for document approval | Inform the client of their responsibility in relation to document approval | Inform the client that extra resources will be added to give the client more time for reviews. |  | B | Based on lessons learned about a client's slow document approval, the project manager should work with the client on an acceptable amount of time for document approval at the kick-off meeting. Collaborative negotiation establishes mutual expectations and a realistic timeline, building a cooperative relationship. Updating the risk register (A) documents the risk but does not resolve it. Informing the client of their responsibility (C) is confrontational. Adding extra resources for more review time (D) increases cost without addressing the root cause. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Initiating | Adopt a Holistic View | Develop Project Charter | Traditional PM | 이전 교훈에서 PM이 고객의 문서 승인 처리 시간이 느린 것을 파악했다. 킥오프 회의에서 PM은 무엇을 해야 하는가? | 잠재적 지연으로 프로젝트 리스크 등록부를 업데이트한다 | 고객과 문서 승인에 대한 수용 가능한 시간을 협의한다 | 문서 승인에 대한 고객의 책임을 알린다 | 고객에게 더 많은 검토 시간을 주기 위해 추가 자원이 투입될 것임을 알린다 |  | B | 고객의 느린 문서 승인에 대한 교훈을 바탕으로, PM은 킥오프 회의에서 고객과 수용 가능한 승인 시간을 협의해야 한다. 협력적 기대치 설정이 지연을 방지한다. 리스크 등록부 업데이트(A)는 수동적이다. 책임 알림(C)은 대립적이다. 추가 자원(D)은 비용 증가이다.
2034 | A project manager is assigned to lead a newly formed agile team. The functional manager has assigned tasks to team members, but the team members do not feel empowered. How can the project manager promote empowerment and accountability among the team? | Assign the tasks individually based on the role of the team member to ensure expertise on the subject. | Give the team autonomy to make their own decisions on how to perform the tasks. | Encourage the team to keep the product owner involved when choosing ways to resolve the given task | Encourage and assign the team to perform demos of their products or software with the customers |  | B | When a functional manager has assigned tasks but team members do not feel empowered, the project manager should give the team autonomy to make their own decisions on how to perform tasks. Autonomy fosters self-organization, ownership, and accountability—core agile principles. Assigning tasks individually by role (A) creates silos and reduces flexibility. Encouraging demos with customers (D) increases feedback but does not address empowerment. Keeping the product owner involved in every decision (C) creates dependency and undermines team autonomy. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Embed Quality | Manage Team | Traditional PM | PM이 새로 구성된 애자일 팀을 이끌게 되었다. 기능 관리자가 팀원에게 작업을 할당했으나 팀원이 권한이 부여되지 않았다고 느낀다. PM은 무엇을 해야 하는가? | 팀원의 역할에 따라 개별적으로 작업을 할당하여 주제에 대한 전문성을 보장한다 | 팀에게 작업 수행 방법에 대해 스스로 결정할 자율성을 부여한다 | 작업 해결 방법을 선택할 때 제품 책임자를 참여시키도록 팀에 장려한다 | 팀에 고객과 제품 또는 소프트웨어 데모를 수행하도록 할당한다 |  | B | 기능 관리자가 작업을 할당했으나 팀원이 권한이 부족하다고 느낄 때, PM은 팀에게 작업 수행 방법에 대한 자율성을 부여해야 한다. 자율성이 주인의식과 동기를 촉진한다. 개별 할당(A)은 자기 조직화에 반한다. 제품 책임자 참여(C)는 팀 자율성을 제한한다. 데모 할당(D)은 무관하다.
2035 | A multicultural team is working on a project. After a few months of observation, the project manager realizes that two team members are not responding to the construction manager properly. The project manager spoke to the team members individually and found that both had cultural differences with the construction manager. What should the project manager do to improve the situation? | Provide the construction manager with instructions on how to resolve the situation. | Ask the construction manager to meet with the two team members to resolve the situation. | Ask the team members to tolerate the cultural differences as they have a different cultural background. | Discuss the team members ' concern with the construction manager and seek solutions. |  | D | When two team members have cultural differences with the construction manager, the project manager should discuss the concern with the construction manager and seek solutions collaboratively. Open dialogue addresses the root cause. Giving the construction manager instructions (A) is top-down. Asking the construction manager to meet alone with them (B) may not resolve the issue. Asking members to tolerate differences (C) dismisses their concerns. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 다문화 팀이 프로젝트를 수행 중이다. 두 팀원이 현장 관리자와 문화적 차이를 겪고 있다. PM은 무엇을 해야 하는가? | 현장 관리자에게 상황 해결 방법에 대한 지침을 제공한다 | 현장 관리자에게 두 팀원과 만나 상황을 해결하도록 요청한다 | 팀원에게 문화적 배경이 다르므로 차이를 참아달라고 요청한다 | 현장 관리자와 팀원의 우려를 논의하고 해결책을 모색한다 |  | D | 두 팀원이 현장 관리자와 문화적 차이를 겪을 때, PM은 현장 관리자와 우려를 논의하고 협력적으로 해결책을 모색해야 한다. 개방적 대화가 상호 이해를 촉진한다. 지침 제공(A)은 지시적이다. 직접 만남 요청(B)은 PM 참여가 없다. 참아달라 요청(C)은 문제를 무시한다.
2036 | A project team used agile approaches to create a minimum viable product (MVP). Currently, the team is discussing the possible next steps. What should be the next step? | Prioritize the work at the user-story level. | Ensure user stories provide the steps necessary for implementation. | Break down the user stories into the smallest size possible. | Use scope cards in conjunction with story points. |  | A | The PM should prioritize work at the user-story level to maximize value delivery. In agile environments, focusing on user-story-level prioritization ensures the team works on the highest-value items first, facilitating collaboration and continuous value delivery while respecting agile principles. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Agile General Practices | Process | Develop Integrated PM Plan | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 애자일 접근법으로 MVP를 만들었다. 현재 팀이 정식 개발 가능성을 논의 중이다. PM은 무엇을 해야 하는가? | 사용자 스토리 수준에서 작업의 우선순위를 정한다 | 사용자 스토리가 구현에 필요한 단계를 제공하도록 한다 | 사용자 스토리를 가능한 가장 작은 크기로 분해한다 | 스토리 포인트와 함께 범위 카드를 사용한다 |  | A | MVP 이후 정식 개발을 논의할 때, PM은 사용자 스토리 수준에서 작업의 우선순위를 정해야 한다. 사용자 스토리 수준 우선순위화가 가장 높은 가치를 먼저 전달한다. 구현 단계(B)는 너무 상세하다. 가장 작게 분해(C)는 가치가 아닌 크기에 집중한다. 범위 카드(D)는 일반적이지 않다.
2037 | A project manager has just taken over a project that is in the requirements gathering phase. A stakeholder indicates that they have not received any progress updates even though reports have been sent on a weekly basis. What should the project manager do to ensure all stakeholders are receiving proper information about the project? | Hold a steering committee meeting with all stakeholders to provide a comprehensive update on the project progress. | Assess all of the project stakeholders and document their preferred communication method and frequency. | Create daily progress reports and send them to all stakeholders. | Include stakeholders in the weekly status meetings with the team. |  | D | When a stakeholder reports not receiving progress updates despite weekly reports being sent, the project manager should assess all project stakeholders and document their preferred communication method and frequency. This ensures communication is tailored to each stakeholder's needs and preferences, preventing future information gaps. Holding a steering committee meeting (A) is a one-time event that does not address ongoing communication preferences. Creating daily progress reports (C) may overwhelm stakeholders without addressing format and channel preferences. Including stakeholders in weekly team meetings (D) may not match their availability or information needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | PM이 요구사항 수집 단계의 프로젝트를 인수했다. 이해관계자가 주간 보고서가 발송되고 있음에도 진행 업데이트를 받지 못하고 있다고 보고한다. PM은 무엇을 해야 하는가? | 모든 이해관계자와 운영위원회 회의를 개최하여 종합 업데이트를 제공한다 | 모든 프로젝트 이해관계자를 평가하고 선호 커뮤니케이션 방법과 빈도를 문서화한다 | 일일 진행 보고서를 작성하여 모든 이해관계자에게 발송한다 | 이해관계자를 팀의 주간 상태 회의에 포함한다 |  | D | 이해관계자가 주간 보고서에도 불구하고 업데이트를 받지 못한다고 할 때, PM은 모든 이해관계자를 평가하고 선호 커뮤니케이션 방법과 빈도를 문서화해야 한다. 커뮤니케이션 요구 분석이 적절한 전달을 보장한다. 운영위원회(A)는 과도하다. 일일 보고(C)는 정보 과부하이다. 회의 포함(D)은 요구 분석 없이 하는 조치이다.
2038 | A project is nearing completion. The sponsor is already asking the project management office (PMO) when the project manager will be assigned to host a planning session for a new initiative. What should the project manager do next? | Document lessons learned before closing. | Consult the project charter for next steps. | Confirm the definition of done (DoD) has been met. | Review organizational process assets (OPAs) for clarity. |  | C | When a project is nearing completion and the sponsor is asking about the PM's next assignment, the project manager should first confirm that the definition of done has been met. Verifying completeness before closure is essential. Documenting lessons learned (A) is part of closure but comes after confirming DoD. Consulting the charter (B) is not the next step at closure. Reviewing OPAs (D) is organizational, not project-specific. | Process | Manage Project Artifacts | Measurement | Tailor Based on Context | Agile | Agile General Practices | Process | Evaluate Project Status | Governance | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트가 완료에 가깝다. 스폰서가 PM의 다음 배정을 묻고 있다. PM은 무엇을 먼저 해야 하는가? | 종료 전 교훈을 문서화한다 | 다음 단계를 위해 프로젝트 헌장을 참조한다 | 완료 정의(DoD)가 충족되었는지 확인한다 | 명확성을 위해 조직 프로세스 자산(OPA)을 검토한다 |  | C | 프로젝트가 완료에 가깝고 스폰서가 다음 배정을 물을 때, PM은 먼저 완료 정의(DoD)가 충족되었는지 확인해야 한다. 완전성 검증이 적절한 종료의 전제조건이다. 교훈 문서화(A)는 중요하지만 완료 확인 후이다. 헌장 참조(B)는 현재 프로젝트 종료와 무관하다. OPA 검토(D)는 간접적이다.
2039 | A group has been working together for one month. During daily meetings a team member continues to express issues in completing their tasks. What should the project manager do? | Have a confidential discussion with the team member to identify the root cause | Move the team member to another task that is more skill appropriate | Wait for the team to identify and solve the problem independently. | Start a discussion with all team members to help resolve the issues |  | A | When a team member continually expresses issues completing tasks during daily meetings, the project manager should have a confidential discussion with the team member to identify the root cause. Private conversation enables understanding of underlying issues and collaborative solutions. Moving the member to another task (B) assumes the issue is skill-related without investigation. Waiting for the team to solve it (C) is passive. Starting a group discussion (D) may be premature and embarrassing. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 팀이 한 달간 함께 작업해왔다. 데일리 회의에서 한 팀원이 작업 완료에 문제를 지속적으로 표현한다. PM은 무엇을 해야 하는가? | 팀원과 비밀 대화를 통해 근본 원인을 파악한다 | 더 적합한 기술의 다른 작업으로 팀원을 이동한다 | 팀이 스스로 문제를 식별하고 해결하도록 기다린다 | 모든 팀원과 토론을 시작하여 문제 해결을 돕는다 |  | A | 팀원이 지속적으로 작업 완료에 문제를 표현할 때, PM은 비밀 대화를 통해 근본 원인을 파악해야 한다. 사적이고 개인적인 접근이 신뢰를 구축한다. 작업 이동(B)은 근본 원인을 해결하지 않는다. 기다리기(C)는 수동적이다. 전체 토론(D)은 개인 문제를 공개한다.
2040 | A distributed project team has communication issues because of their collaboration tools. The team feels that efficiency could be improved by changing the collaboration platform. What should the project manager do? | Escalate the issue to the sponsor and ask them to decide. | Implement the communication tools used by other project teams. | Discuss this with the project team and select the appropriate tools. | Inform the project team to continue using the current tools. |  | C | When a distributed team reports communication issues with collaboration tools and suggests changing platforms, the project manager should discuss this with the project team and select the appropriate tools together. Collaborative decision-making ensures the new tools meet the team's actual needs and secures buy-in. Escalating to the sponsor (A) bypasses the team's input. Implementing tools used by other teams (B) may not address this team's specific needs. Continuing with current tools (D) ignores a valid concern affecting efficiency. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Scope | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 분산된 프로젝트 팀이 협업 도구로 인한 커뮤니케이션 문제가 있다. 플랫폼 변경을 제안한다. PM은 무엇을 해야 하는가? | 이슈를 스폰서에게 에스컬레이션하고 결정을 요청한다 | 다른 프로젝트 팀이 사용하는 커뮤니케이션 도구를 구현한다 | 프로젝트 팀과 논의하고 적절한 도구를 선택한다 | 프로젝트 팀에게 현재 도구를 계속 사용하도록 알린다 |  | C | 분산 팀이 협업 도구 문제를 보고할 때, PM은 프로젝트 팀과 논의하고 적절한 도구를 선택해야 한다. 협력적 의사결정이 팀 수용을 보장한다. 스폰서 에스컬레이션(A)은 과도하다. 다른 팀 도구(B)는 요구에 맞지 않을 수 있다. 현재 도구 유지(D)는 문제를 무시한다.
2041 | A high-performing team member's performance has been consistently increasing over the past year, leaving other peers behind. The project manager has been reluctant to publicly recognize the team member's contributions for fear of discouraging others. The project manager is also concerned that the team member may leave if not rewarded for the contributions made. What should the project manager do? | Request the high-performing team member to mentor the other team members | Promote the higher performing team member to a higher position | Remind the high-performing team member to focus on shared rewards rather than individual rewards | Reward the high-performing team member privately to avoid team disruption |  | A | When a high-performing team member consistently outpaces peers and may leave without recognition, the project manager should request the team member to mentor others. Mentoring leverages their expertise, provides recognition, and elevates team performance. Promoting to a higher position (B) may not be feasible and could disrupt dynamics. Reminding them to focus on shared rewards (C) may discourage them. Rewarding privately (D) creates secrecy and perceived favoritism. | People | Mentor Relevant Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Align Stakeholder Expectations | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 고성과 팀원의 성과가 지속적으로 증가하여 다른 동료를 앞서고 있다. 인정 없이 떠날 수 있다. PM은 무엇을 해야 하는가? | 고성과 팀원에게 다른 팀원을 멘토링하도록 요청한다 | 고성과 팀원을 더 높은 직위로 승진시킨다 | 고성과 팀원에게 개인 보상보다 공유 보상에 집중하도록 상기시킨다 | 팀 방해를 피하기 위해 고성과 팀원에게 비공개로 보상한다 |  | A | 고성과 팀원이 동료를 앞서고 인정 없이 떠날 수 있을 때, PM은 멘토링을 요청해야 한다. 멘토링이 전문성을 활용하고 인정과 리더십 기회를 제공한다. 승진(B)은 PM 권한이 아닐 수 있다. 공유 보상 집중(C)은 개인 기여를 무시한다. 비공개 보상(D)은 멘토링의 팀 효과가 없다.
2042 | One of the risks identified during project planning activities is related to a component from a preferred vendor. The component utilizes new technology, and there is a possibility of incompatibility with other parts of the system that are being developed. What should the project manager do? | identify an alternative component in case of incompatibility. | Create a risk probability matrix to address the incompatibility. | Use the contingency fund to redesign the interface if it is incompatible, | Require the vendor to redesign the incompatible component to fit the system. |  | A | When a preferred vendor's component uses new technology with potential system incompatibility, the project manager should identify an alternative component in case of incompatibility. Proactive risk mitigation through alternatives ensures project continuity. Creating a risk probability matrix (B) documents the risk but does not mitigate it. Using contingency funds for redesign (C) is reactive and costly. Requiring the vendor to redesign (D) may not be feasible or timely. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Process | Plan and Manage Procurement | Risk | Planning | Adopt a Holistic View | Plan Risk Management | Traditional PM | 프로젝트 계획 중 선호 벤더의 부품과 관련된 리스크가 식별되었다. 새 기술로 시스템 비호환 가능성이 있다. PM은 무엇을 해야 하는가? | 비호환 시 대체 부품을 식별한다 | 비호환을 다루기 위한 리스크 확률 매트릭스를 생성한다 | 비호환 시 인터페이스를 재설계하기 위해 비상 자금을 사용한다 | 벤더에게 비호환 부품을 시스템에 맞게 재설계하도록 요구한다 |  | A | 선호 벤더의 부품이 새 기술로 시스템 비호환 가능성이 있을 때, PM은 비호환 시 대체 부품을 식별해야 한다. 사전적 리스크 관리가 대비 방안을 마련한다. 확률 매트릭스(B)는 분석이지 대응이 아니다. 비상 자금(C)은 다른 대안 검토 후에 한다. 벤더 재설계 요구(D)는 비현실적일 수 있다.
2043 | How can agile measurements improve upon predictive measurements in cases where the final 10% of a project takes longer than planned? | By conducting daily standups to more accurately track project deliverables | By reviewing burnup charts to determine the effort required against estimated earned value | By focusing on the delivery of incremental working products lo the customer | By scheduling iterative meetings with the product owner to improve project tracking |  | C | Agile measurements—such as delivering incremental working products—provide tangible progress and value at regular intervals. This approach is especially beneficial when final project stages are delayed, as customers continue receiving functional components. This aligns with the agile principle of delivering working software frequently, preferring shorter timescales. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Predictive-Agile Blend | Process | Develop Integrated PM Plan | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 프로젝트 마지막 10%가 예상보다 오래 걸리는 경우 애자일 측정이 예측형 측정을 어떻게 개선할 수 있는가? | 데일리 스탠드업을 통해 프로젝트 인도물을 더 정확하게 추적한다 | 번업 차트를 검토하여 추정 획득 가치 대비 필요한 노력을 결정한다 | 고객에게 점진적 작동 제품의 전달에 집중한다 | 제품 책임자와 반복 회의를 일정에 잡아 프로젝트 추적을 개선한다 |  | C | 프로젝트 마지막 10%가 오래 걸릴 때 애자일 측정의 개선점은 고객에게 점진적 작동 제품의 전달에 집중하는 것이다. 점진적 전달이 정기적 간격으로 실질적 진행과 가치를 제공한다. 데일리 스탠드업(A)은 추적이지 가치 전달이 아니다. 번업 차트(B)는 도구이지 접근법이 아니다. 반복 회의(D)는 추적이지 전달이 아니다.
2044 | A project manager is new to hybrid project management and is worried about the project because it has a high level of requirements uncertainty. The team has experience with hybrid projects, performs daily standups, and is committed to the project. The project manager is concerned about losing control of the project and would like to have a more central role. How should the project manager address this issue? | Change the approach for the project to a predictive approach. | Modify the daily standup meetings to include project status reporting. | Adopt the role of supporting and empowering the project team to do the work. | Escalate the issue to the change control board (CCB) and ask for advice. |  | C | When a PM new to hybrid management worries about losing control on a project with high requirements uncertainty and an experienced team, the project manager should adopt the role of supporting and empowering the team. Servant leadership leverages team expertise. Changing to predictive (A) ignores the project's uncertainty. Modifying standups for status reporting (B) disrupts their purpose. Escalating to the CCB (D) is inappropriate for management approach questions. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Hybrid/Tailoring | PM이 하이브리드 프로젝트 관리가 처음이고 높은 요구사항 불확실성과 경험 많은 팀을 가진 프로젝트에 걱정하고 있다. PM은 무엇을 해야 하는가? | 프로젝트 접근법을 예측형으로 변경한다 | 데일리 스탠드업에 프로젝트 상태 보고를 포함하도록 수정한다 | 프로젝트 팀을 지원하고 권한을 부여하는 역할을 채택한다 | 변경통제위원회(CCB)에 이슈를 에스컬레이션하고 조언을 요청한다 |  | C | 하이브리드 관리가 처음인 PM이 높은 불확실성과 경험 많은 팀이 있을 때, PM은 팀을 지원하고 권한을 부여하는 역할을 채택해야 한다. 서번트 리더십이 경험 많은 팀의 자율성을 활용한다. 예측형 변경(A)은 불확실성에 부적합하다. 스탠드업 수정(B)은 부분적이다. CCB 에스컬레이션(D)은 과도하다.
2045 | A company that is heavily focused on delivering projects using predictive approaches onboards a new project manager who uses hybrid approaches. The scope of the project contains a number of unclear requirements. How should the project manager plan the delivery of the project? | Ignore the unclear requirements and focus on the delivery plan of the project | Break down the requirements and prioritize the requirements into iterative work packages | Escalate the issue of unclear requirements to the management team and wait for final authorization | Wait for the requirements to be more clear before any further action is taken on the project |  | B | When a hybrid-oriented project manager faces unclear requirements in a predictive-focused organization, they should break down the requirements and prioritize them into iterative work packages. Iterative delivery addresses uncertainty while maintaining structure. Ignoring unclear requirements (A) risks scope misalignment. Escalating to management and waiting (C) causes delay. Waiting for clarity (D) stalls the project. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Tailored Approach | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Hybrid/Tailoring | 예측형 중심 회사에 하이브리드 지향 PM이 합류했다. 요구사항이 불명확하다. PM은 무엇을 해야 하는가? | 불명확한 요구사항을 무시하고 프로젝트 전달 계획에 집중한다 | 요구사항을 분해하고 반복적 작업 패키지로 우선순위화한다 | 불명확한 요구사항 문제를 경영진에게 에스컬레이션하고 최종 승인을 기다린다 | 요구사항이 더 명확해질 때까지 프로젝트에 대한 추가 조치를 기다린다 |  | B | 예측형 중심 조직에서 요구사항이 불명확할 때, PM은 요구사항을 분해하고 반복적 작업 패키지로 우선순위화해야 한다. 반복적 접근이 점진적 명확화를 가능하게 한다. 무시(A)는 품질을 위협한다. 에스컬레이션(C)은 수동적이다. 기다리기(D)는 프로젝트를 지연시킨다.
2046 | A project team is identifying project risks for a bridge to be built across a river. The team needs to send out invitations for a risk workshop to better understand the risks involved. Which distribution list should the project manager use when sending out invitations? | Team members, consultants from outside the project with experience in the field, and the customer | Team members, engineers, and weather experts | Functional managers, team members, and external consultants with experience in the fiel d | Weather experts, functional managers, and team members |  | A | For a bridge construction risk workshop, the project manager should invite team members, consultants from outside the project with experience in the field, and the customer. This combination provides project knowledge, external expertise, and stakeholder perspective for comprehensive risk identification. Team members, engineers, and weather experts (B) are too technically narrow. Functional managers, team members, and external consultants (C) include managers who may lack project-specific involvement. Weather experts, functional managers, and team members (D) is similarly narrow. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 프로젝트 팀이 강 위 교량 건설 프로젝트 리스크를 식별 중이다. 리스크 워크숍에 누구를 초대해야 하는가? | 팀원, 해당 분야 경험이 있는 외부 컨설턴트, 고객 | 팀원, 엔지니어, 기상 전문가 | 기능 관리자, 팀원, 해당 분야 경험이 있는 외부 컨설턴트 | 기상 전문가, 기능 관리자, 팀원 |  | A | 교량 건설 리스크 워크숍에는 팀원, 해당 분야 경험이 있는 외부 컨설턴트, 고객을 초대해야 한다. 이 조합이 내부 지식, 외부 전문성, 고객 관점을 제공한다. 엔지니어/기상 전문가(B)는 고객을 배제한다. 기능 관리자(C,D)는 프로젝트별 전문성이 부족할 수 있다.
2047 | A highly critical project is in jeopardy due to missing professional resources. What should the newly assigned project manager do first? | Find available professionals within the organization to fill the gaps. | Allocate funding for seeking external professionals to fill the gaps. | Determine the possibility for team members to split up the required tasks. | Request additional budget for team training for the missing expertise. |  | C | When a critical project is in jeopardy due to missing professional resources, the newly assigned project manager should first determine the possibility for team members to split up the required tasks. Assessing internal capacity before seeking external resources optimizes existing capabilities. Finding available professionals internally (A) may not be feasible. Allocating funding for external professionals (B) requires budget approval. Requesting budget for team training (D) takes time the critical project may not have. | People | Build Shared Understanding | Stakeholders | Effectively Engage with Stakeholders | General | Cost & Resource Management | People | Develop a Common Vision | Resources | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 매우 중요한 프로젝트가 전문 자원 부족으로 위험에 처해 있다. 새로 배정된 PM은 무엇을 먼저 해야 하는가? | 조직 내 가용한 전문가를 찾아 공백을 채운다 | 외부 전문가를 찾기 위한 자금을 배분한다 | 팀원이 필요한 작업을 분담할 가능성을 결정한다 | 누락된 전문성을 위한 팀 교육에 추가 예산을 요청한다 |  | C | 전문 자원 부족으로 프로젝트가 위험할 때, PM은 먼저 팀원이 필요한 작업을 분담할 가능성을 결정해야 한다. 기존 자원 활용이 가장 빠른 해결이다. 조직 내 전문가(A)는 가용하지 않을 수 있다. 외부 자금(B)은 시간이 걸린다. 교육 예산(D)은 즉각적 해결이 아니다.
2048 | A project team was established for a community impacted by oil and gas exploration activities. The team is required to interact with several external stakeholders. The local council authority has requested a meeting with the project team to discuss the impact of the project on the community. The project manager was not available at the time of the meeting, and the team was in disagreement regarding who should attend the meeting. What should the project manager have done to prevent this conflict? | Defined the roles and responsibilities of the team members. | Established ground rules for the team | Updated the communications management plan. | Provided copies of the stakeholder engagement plan to all team members. |  | B | When a team disagrees about who should attend a stakeholder meeting in the PM's absence, the project manager should have established ground rules for the team. Ground rules define communication, decision-making, and stakeholder engagement protocols. Defining roles and responsibilities (A) is important but does not specifically address meeting attendance decisions. Updating the communications management plan (C) is procedural. Providing the stakeholder engagement plan (D) does not specify team conduct. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Risk | Executing | Build an Empowered Culture | Implement Risk Responses | Traditional PM | 프로젝트 팀이 PM 부재 시 이해관계자 회의에 누가 참석할지 의견이 불일치한다. PM이 이전에 무엇을 했어야 하는가? | 팀원의 역할과 책임을 정의했다 | 팀을 위한 기본 규칙을 수립했다 | 커뮤니케이션 관리 계획을 업데이트했다 | 모든 팀원에게 이해관계자 참여 계획 사본을 제공했다 |  | B | PM 부재 시 이해관계자 회의 참석에 대한 의견 불일치가 있을 때, PM은 팀을 위한 기본 규칙을 수립했어야 한다. 기본 규칙이 커뮤니케이션, 의사결정, 팀 행동을 정의한다. 역할/책임(A)은 작업 범위이지 행동 규범이 아니다. 계획 업데이트(C)는 문서이지 팀 규범이 아니다. 계획 사본(D)은 정보 제공이지 규칙 수립이 아니다.
2049 | A team is using an agile approach to maintain the project backlog. A new project obstacle was identified as a blocker and added to the backlog list. The team is facing challenges to remove this obstacle. What should the project manager do next? | Make changes to reprioritize the backlog because of the obstacle. | Reject the obstacle and present the partial solution to the customer. | Focus on generating business value despite the obstacle. | Escalate the obstacle to a servant leader for resolution. |  | A | In agile environments, the PM should reprioritize the backlog when new obstacles emerge that affect planned work. This ensures the team continues delivering maximum value while adapting to changing circumstances. The PM facilitates collaboration, removes impediments, and maintains continuous value delivery consistent with agile principles. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Adopt a Holistic View | Determine Budget | Traditional PM | 팀이 애자일 접근법으로 백로그를 유지 중이다. 새 장애물이 차단 요소로 식별되어 일부 사용자 스토리에만 솔루션이 있다. PM은 무엇을 해야 하는가? | 장애물로 인해 백로그를 재우선순위화하도록 변경한다 | 장애물을 거부하고 고객에게 부분 솔루션을 제시한다 | 장애물에도 불구하고 비즈니스 가치 생성에 집중한다 | 해결을 위해 서번트 리더에게 장애물을 에스컬레이션한다 |  | A | 애자일 환경에서 새 장애물이 계획된 작업에 영향을 줄 때, PM은 백로그를 재우선순위화해야 한다. 이는 팀이 변화에 적응하면서 최대 가치를 계속 전달하도록 보장한다. 거부(B)는 비전문적이다. 가치 집중(C)은 맞지만 백로그 조정이 구체적 조치이다. 에스컬레이션(D)은 팀 자율성을 무시한다.
2050 | During project execution, a project manager is leading the team to work on the project schedule. During a meeting, the team has difficulty understanding the complexity of a task and is unable to provide an estimate for the required resources. What should the project manager do first to resolve this issue? | Register the issue as a risk in the risk register. | Refer to the organization ' s lessons learned from past projects. | Engage an external expert to provide the estimation. | Report to the sponsor that there is a new challenge in the project. |  | B | The correct answer is B. Refer to the organization ' s lessons learned from past projects. Schedule management requires proactive monitoring and appropriate corrective actions. The PM should analyze impacts and implement suitable responses to maintain project timelines. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | General | Risk & Issue Management | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | Traditional PM | 프로젝트 실행 중 팀이 일정 작업 중 추정이 어려운 작업을 발견했다. PM은 무엇을 해야 하는가? | 이슈를 리스크 등록부에 리스크로 등록한다 | 과거 프로젝트의 조직 교훈을 참조한다 | 추정을 위해 외부 전문가를 참여시킨다 | 프로젝트에 새로운 과제가 있음을 스폰서에게 보고한다 |  | B | 정답은 B이다. 과거 프로젝트의 조직 교훈을 참조한다. 일정 관리는 사전적 모니터링과 적절한 시정 조치가 필요하다. PM은 유사한 과거 정보를 활용하여 더 나은 추정을 해야 한다. 리스크 등록(A)은 추정 문제 해결이 아니다. 외부 전문가(C)는 내부 자원 활용 후이다. 스폰서 보고(D)는 수동적이다.
2051 | A project manager has recently been appointed to lead a critical software development project in a hybrid environment. What should the project manager do first to understand the project quickly and manage the project effectively? | Assess the project management plan for dependencies and possible risks then validate stakeholder understanding. | Share project objectives and scope with the team to ensure it understands the project value. | Review the project charter to understand the objectives, high-level scope, and business need. | Identify key stakeholders and hold a project kickoff meeting to engage the stakeholders and obtain commitment. |  | C | When newly appointed to lead a critical hybrid software project, the project manager should first review the project charter to understand the objectives, high-level scope, and business need. The charter provides foundational context for all subsequent activities and decisions. Assessing the project management plan (A) is detailed and time-consuming without charter context. Sharing objectives with the team (B) should follow charter review. Holding a kickoff meeting (D) is most effective after the PM understands the charter. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Governance | Initiating | Be an Accountable Leader | Develop Project Charter | Hybrid/Tailoring | PM이 하이브리드 환경의 중요한 소프트웨어 개발 프로젝트를 이끌게 되었다. PM은 무엇을 먼저 해야 하는가? | 프로젝트 관리 계획에서 종속성과 가능한 리스크를 평가한 후 이해관계자 이해를 검증한다 | 팀에게 프로젝트 목표와 범위를 공유하여 프로젝트 가치를 이해하도록 한다 | 프로젝트 헌장을 검토하여 목표, 상위 수준 범위, 비즈니스 요구를 이해한다 | 핵심 이해관계자를 식별하고 킥오프 회의를 개최하여 이해관계자를 참여시키고 지원을 얻는다 |  | C | 새로 배정된 PM이 먼저 프로젝트 헌장을 검토하여 목표, 상위 수준 범위, 비즈니스 요구를 이해해야 한다. 헌장이 프로젝트의 기초 정보를 제공한다. 계획 평가(A)는 헌장 이해 후이다. 목표 공유(B)는 먼저 이해한 후이다. 킥오프(D)는 프로젝트 이해 후이다.
2052 | An agile project is in its early iterations, but the project manager already realizes that more resources will be needed to achieve the expected timelines. There are no internal resources available. What vendor strategy should the project manager use to maximize project delivery? | Use compression techniques to break down the scope and assign the scope pieces todifferent vendors with a fixed-price contract. | Establish a solid view of the scope and requirements and engage a vendor with a fixed price contract. | Engage in a time and materials (T & M) contract and hire a local vendor to supportdevelopment. | Use the contingency budget for hiring additional vendor resources to mitigate any projectrisk. |  | C | When an agile project needs additional resources and none are available internally, the project manager should engage a local vendor through a time and materials (T&M) contract. T&M contracts provide the flexibility that agile projects require—allowing the PM to scale resources up or down as the project evolves without committing to a fixed scope or price. Using compression techniques with fixed-price contracts (A) is rigid and conflicts with agile's iterative nature. Establishing fixed scope and a fixed-price contract (B) does not accommodate the uncertainty inherent in early agile iterations. Using the contingency budget for additional vendors (D) is not the appropriate use of contingency reserves and bypasses proper vendor engagement strategy. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 애자일 프로젝트 초기 이터레이션에서 PM이 더 많은 자원이 필요하지만 내부에서 가용하지 않음을 파악했다. PM은 무엇을 해야 하는가? | 압축 기법을 사용하여 범위를 분해하고 다른 벤더에게 할당한다 | 범위와 요구사항을 확실히 파악하고 고정가 계약으로 벤더를 참여시킨다 | 시간 및 자재(T&M) 계약으로 현지 벤더를 참여시켜 개발을 지원한다 | 비상 예산으로 추가 벤더 자원을 고용하여 프로젝트 리스크를 완화한다 |  | C | 애자일 프로젝트에서 추가 자원이 필요하고 내부에서 불가능할 때, PM은 T&M 계약으로 현지 벤더를 참여시켜야 한다. T&M 계약이 애자일의 유연성에 맞는 적응적 계약이다. 압축 기법(A)은 애자일에 부적합하다. 고정가(B)는 애자일 불확실성에 맞지 않는다. 비상 예산(D)은 리스크 대응용이지 자원 확보용이 아니다.
2053 | A project manager was just assigned to a project as the leader of an experienced agile team. How should the project manager influence the team to accomplish the project objectives? | Assert judgment over the team. | Increase the amount of subject matter experts (SMEs) to get better results. | Express trust in the team ' s ability to fulfill the necessary deliverables. | Use a plan-driven approach in order to demonstrate control over the project. |  | C | When assigned as leader of an experienced agile team, the project manager should express trust in the team's ability to fulfill the necessary deliverables. Trust empowers self-organization and motivates performance. Asserting judgment (A) imposes authority on an experienced team. Increasing SMEs (B) adds overhead without demonstrated need. Using a plan-driven approach (D) contradicts agile principles. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 경험 많은 애자일 팀의 리더로 배정되었다. PM은 어떻게 리드해야 하는가? | 팀에 대한 판단력을 행사한다 | 더 나은 결과를 위해 주제 전문가(SME) 수를 늘린다 | 팀이 필요한 인도물을 달성할 수 있다는 신뢰를 표현한다 | 프로젝트에 대한 통제를 보여주기 위해 계획 중심 접근법을 사용한다 |  | C | 경험 많은 애자일 팀의 리더로 배정될 때, PM은 팀이 인도물을 달성할 수 있다는 신뢰를 표현해야 한다. 신뢰가 자기 조직화와 동기를 촉진한다. 판단력 행사(A)는 지시적이다. SME 추가(B)는 불필요할 수 있다. 계획 중심(D)은 애자일에 반한다.
2054 | During a project planning meeting, the customer is not sure how to build a brand new product and is worried about extra costs and work. The customer is asking the project manager for guidance. What should the project manager do? | Ask the customer to include all of the requirements in the project charter to officially start the project planning phase. | Schedule a brainstorming session and select the top ten most important requirements. | Wait to start the project execution phase until all requirements and acceptance criteria are clear. | In the planning meeting, focus on releasing a minimum viable product (MVP) quickly and getting feedback from the end users. |  | D | When a customer is unsure how to build a brand-new product and worries about extra costs and work, the project manager should focus on releasing a minimum viable product (MVP) quickly and getting end-user feedback. An MVP reduces risk by validating core assumptions with minimal investment, enabling iterative improvement based on actual user feedback. Asking the customer to include all requirements in the charter (A) assumes complete upfront knowledge. Scheduling a brainstorming session for top ten requirements (B) delays delivery. Waiting until all requirements are clear (C) is impractical for a novel product. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Hybrid/Tailoring | 계획 회의에서 고객이 새 제품 구축 방법을 잘 모르고 추가 비용과 작업을 걱정한다. PM은 무엇을 해야 하는가? | 고객에게 프로젝트 헌장에 모든 요구사항을 포함하도록 요청하여 공식 시작한다 | 브레인스토밍 세션을 예약하고 가장 중요한 요구사항 10개를 선택한다 | 모든 요구사항과 인수 기준이 명확해질 때까지 실행 단계를 기다린다 | 계획 회의에서 MVP를 빠르게 출시하고 최종 사용자 피드백을 받는 데 집중한다 |  | D | 고객이 새 제품 구축에 불확실하고 비용을 걱정할 때, PM은 MVP를 빠르게 출시하고 피드백을 받는 데 집중해야 한다. MVP가 리스크를 줄이고 학습을 촉진한다. 모든 요구사항(A)은 불확실 상황에 비현실적이다. 10개 선택(B)은 임의적이다. 기다리기(C)는 프로젝트를 지연시킨다.
2055 | A project to implement a new process is still in development. When implemented, the company will benefit from a reduction in utility costs. The project financial evaluation indicates a payback of 3 years. What should the project manager do to expedite the project delivery? | Increase resources on the technical design to enable a decision to proceed as this is aquick return project. | Increase the time spent on project development to improve the level of confidence tovalidate the financial evaluation. | Stop any further project development and commence with the implementation as thereis no need to seek further approval. | Conduct a stakeholder survey with the plant operators to establish the probability ofthis project reducing the cost of utilities. |  | A | The PM should increase resources on the technical design to enable a decision to proceed, as this is a quick-return project. This approach directly addresses the delivery bottleneck by accelerating the decision-making process. The other options either fail to address the root cause, bypass proper project processes, or may introduce additional complications. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Traditional PM | 새 프로세스 구현 프로젝트가 아직 개발 중이다. 구현 시 회사가 생산 다운타임 감소로 혜택을 받을 것이다. 빠른 투자 수익이 예상된다. PM은 무엇을 해야 하는가? | 기술 설계에 자원을 추가하여 진행 결정을 가능하게 한다 | 프로젝트 개발에 더 많은 시간을 투자하여 최종 출력에 대한 신뢰도를 높인다 | 추가 프로젝트 개발을 중단하고 구현을 시작한다 | 공장 운영자와 이해관계자 설문을 실시하여 프로젝트 성공 확률을 확인한다 |  | A | 빠른 투자 수익이 예상되는 프로세스 구현 프로젝트에서, PM은 기술 설계에 자원을 추가하여 진행 결정을 가능하게 해야 한다. 기술 설계 가속이 전달 병목을 직접 해결한다. 시간 추가(B)는 지연을 초래한다. 개발 중단(C)은 미완성 상태의 리스크가 있다. 설문(D)은 실행이 아닌 분석이다.
2056 | During a kick-off meeting, the project manager notices that one of the stakeholders responsible for providing key information to the team has a low level of participation. This stakeholder believes that there will be no benefit from implementing the project. The project manager realizes that this could be a high risk for the project. Which action should the project manager take? | Ensure the key information is accurate and monitor the situation as the project progresses . | Facilitate a supportive level of engagement for this stakeholder. | Ask the project sponsor for advice as it might be possible to work with another stakeholder. | Perform a qualitative risk analysis using a probability and impact matrix. |  | B | When a stakeholder responsible for providing key information shows low participation and disbelief in the project's benefits, the project manager should facilitate a supportive level of engagement for this stakeholder. This involves addressing their concerns, involving them in relevant planning and evaluation stages, soliciting their feedback, and demonstrating the project's value—building trust and rapport needed for their cooperation. Monitoring the situation passively (A) allows the risk to grow. Performing a qualitative risk analysis (D) documents the risk but does not engage the stakeholder. Asking the sponsor for an alternative stakeholder (C) may not be feasible and does not resolve the underlying engagement issue. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Risk & Issue Management | People | Engage Stakeholders | Finance | Initiating | Build an Empowered Culture | Develop Project Charter | Traditional PM | 킥오프 회의에서 PM이 핵심 정보 제공 책임이 있는 이해관계자가 참여도가 낮고 프로젝트 혜택을 믿지 않는 것을 발견했다. PM은 무엇을 해야 하는가? | 핵심 정보가 정확한지 확인하고 프로젝트 진행에 따라 상황을 모니터링한다 | 이 이해관계자를 위한 지원적 참여 수준을 퍼실리테이션한다 | 프로젝트 스폰서에게 조언을 구하여 다른 이해관계자와 작업할 수 있는지 확인한다 | 확률 및 영향 매트릭스를 사용하여 정성적 리스크 분석을 수행한다 |  | B | 핵심 정보 제공자가 참여도가 낮고 혜택을 믿지 않을 때, PM은 지원적 참여 수준을 퍼실리테이션해야 한다. 지원적 참여가 신뢰와 이해를 구축한다. 모니터링(A)은 수동적이다. 스폰서 조언(C)은 직접 참여 시도 후이다. 리스크 분석(D)은 참여 문제 해결이 아니다.
2057 | Generative artificial intelligence (AI) now helps produce documents on most projects across an organization and is yielding great benefits. Despite this change, a project manager notices that very few members of their current team know the AI tools available within the company. Consequently, they do not know how to use them effectively. What should the project manager do? | Engage with some experienced personnel in the company and request they mentor the rest of the team. | Invite the project sponsor to brief the team on the importance of generative AI and how to optimize the available applications. | Document this issue as a lesson learned and hold a briefing at the end of the project. | Identify more user-friendly generative AI applications in the industry and share with the team. |  | C | The PM should document this issue as a lesson learned and hold a briefing at project completion. This ensures the knowledge is captured systematically and shared with the broader organization. Other options either fail to address the root cause, bypass proper processes, or may create additional complications. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | AI | 생성형 AI가 조직 프로젝트에서 문서 생산을 돕고 있지만 일부 팀원이 도구를 제대로 활용하지 못한다. PM은 무엇을 해야 하는가? | 경험 있는 직원에게 나머지 팀을 멘토링하도록 요청한다 | 프로젝트 스폰서를 초대하여 AI의 중요성과 최적화 방법을 설명한다 | 이 문제를 교훈으로 문서화하고 프로젝트 종료 시 브리핑을 개최한다 | 업계에서 더 사용자 친화적인 AI 애플리케이션을 식별하여 팀과 공유한다 |  | C | 일부 팀원이 AI 도구를 제대로 활용하지 못할 때, PM은 이를 교훈으로 문서화하고 프로젝트 종료 시 브리핑을 개최해야 한다. 체계적 지식 포착과 공유가 조직 전체에 도움이 된다. 멘토링(A)은 유용하지만 체계적이지 않다. 스폰서 브리핑(B)은 역할에 적합하지 않다. 다른 도구(D)는 기존 도구 숙련이 우선이다.
2058 | A project manager is leading the construction of a high-rise mall for a customer in an emerging competitive market. Some customers want to move in as soon as the ground floor is completed. What should the project manager do to deliver business value to the client? | Implement an agile project delivery approach. | Request to use the management reserve and crash the project schedule. | Adopt an incremental project delivery approach. | Explain the need to follow the quality assurance (QA) schedule to the customer. |  | C | When customers want to move into the ground floor of a high-rise mall as soon as it is completed in a competitive market, the project manager should adopt an incremental project delivery approach. Incremental delivery enables partial value realization before full completion. Requesting management reserve and crashing the schedule (A) focuses on speed, not value delivery. Explaining the QA schedule (D) ignores the customer's business need. Implementing full agile (B) may not suit a construction project as well as incremental delivery. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | Agile | Agile General Practices | Business Environment | Define and Establish Governance | Schedule | Monitoring & Controlling | Focus on Value | Control Schedule | Traditional PM | PM이 경쟁이 치열한 시장에서 고층 쇼핑몰 건설을 이끌고 있다. 일부 고객이 1층이 완공되는 대로 입주하고 싶어한다. PM은 무엇을 해야 하는가? | 애자일 프로젝트 전달 접근법을 구현한다 | 관리 예비비를 사용하고 프로젝트 일정을 크래싱한다 | 점진적(인크리멘탈) 프로젝트 전달 접근법을 채택한다 | 고객에게 품질 보증(QA) 일정을 따라야 할 필요성을 설명한다 |  | C | 고객이 층별로 완공되는 대로 입주하길 원할 때, PM은 점진적 전달 접근법을 채택해야 한다. 점진적 전달이 사용 가능한 부분을 순차적으로 제공한다. 애자일(A)은 건설에 부적합하다. 크래싱(B)은 비용 증가이다. QA 일정 설명(D)은 고객 요구를 무시한다.
2059 | A project manager is executing a project on time and on budget. Before a stage gate review, the project manager receives the regular business management report, but this time it indicates a negative impact on the project success factors. What should the project manager do? | Request a delay to the stage gate until business development provides the next update | Provide the necessary analysis to enable examination of the business value | Continue with execution since the project was successful up to this phase | Call for business development to revalidate inputs at the next stage gate |  | B | Stage gates are designed to reassess continued investment based on current business value, not solely delivery performance. When a business management report reveals negative impacts on project success factors—such as declining market demand, weakened ROI, regulatory shifts, or strategic reprioritization—the PM should proactively prepare decision-quality analysis for the governance review. This includes updated benefits forecasts, sensitivity scenarios, impacts to business case assumptions, and options (continue, pivot, pause, or terminate). Simply continuing execution (A) treats the project as purely tactical, risking delivery of a product that no longer produces intended value. Waiting for business development to revalidate inputs (B) is too passive. Delaying the gate (D) undermines governance cadence and wastes resources. Providing comprehensive analysis supports informed sponsor decisions and demonstrates stewardship of organizational investment. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Finance | Initiating | Be an Accountable Leader | Develop Project Charter | Traditional PM | 프로젝트가 일정과 예산에 맞게 실행 중이다. 단계 게이트 검토 전 비즈니스 관리 보고서가 프로젝트 성공에 부정적 영향을 보여준다. PM은 무엇을 해야 하는가? | 비즈니스 개발팀이 다음 업데이트를 제공할 때까지 단계 게이트를 지연 요청한다 | 비즈니스 가치 검토를 가능하게 하는 필요한 분석을 제공한다 | 이 단계까지 프로젝트가 성공적이었으므로 실행을 계속한다 | 비즈니스 개발팀에게 다음 단계 게이트에서 입력을 재검증하도록 요청한다 |  | B | 단계 게이트는 전달 성과만이 아닌 현재 비즈니스 가치에 기반하여 지속 투자를 재평가하도록 설계되어 있다. PM은 비즈니스 가치 검토를 가능하게 하는 필요한 분석을 제공해야 한다. 게이트 지연(A)은 의사결정을 미룬다. 실행 계속(C)은 비즈니스 영향을 무시한다. 재검증 요청(D)은 수동적이다.
2060 | A project team member, who is inexperienced in system development work, is not performing well. Currently, there are no other staff members available who are qualified to complete the work. What should the project manager do? | Request a substitute for the team member with a new resource who is more skilled in system development work. | Work with the functional manager to determine an incentive for the team member to complete the project. | Assess the team member ' s development requirements and arrange for the team member to receive training. | Seek approval from the project sponsor to use some of the project budget reserve to hire a new resource. |  | C | When an underperforming team member lacks system development skills and no qualified replacements are available, the project manager should assess development requirements and arrange training. Building skills addresses the root cause. Requesting a substitute (A) ignores availability constraints. Working with the functional manager on incentives (B) does not address the skills gap. Using budget reserves for a new hire (D) bypasses the development opportunity. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 시스템 개발 경험이 없는 팀원이 성과가 좋지 않다. 자격을 갖춘 대체 인력이 없다. PM은 무엇을 해야 하는가? | 시스템 개발에 더 숙련된 새 자원으로 팀원 교체를 요청한다 | 기능 관리자와 팀원이 프로젝트를 완료하도록 인센티브를 결정한다 | 팀원의 개발 요구사항을 평가하고 교육을 받도록 주선한다 | 프로젝트 스폰서에게 예산 예비비로 새 자원 고용 승인을 구한다 |  | C | 미숙련 팀원이 성과가 좋지 않고 대체 인력이 없을 때, PM은 개발 요구사항을 평가하고 교육을 주선해야 한다. 역량 구축이 장기적 해결이다. 교체 요청(A)은 가용 인력이 없다. 인센티브(B)는 기술 부족을 해결하지 않는다. 새 자원 고용(D)은 가용성 제한이 있다.
2061 | A construction project is in its final stage when the owner of a private property where the pipeline is routed refuses to collaborate. The lack of collaboration causes a project delay, but the client insists that the project must be completed as per the contract. What should the project manager do next? | Escalate the routing pipeline issue to the project change control board (CCB) and wait for a resolution to the conflict. | Review the agreement with the property owner, schedule a meeting with them to discuss their concerns, and inform the client. | Request additional budget from the project sponsor and raise a dispute with the property owner to force them to collaborate. | Use the contingency reserve, add more resources, and reroute the pipeline to complete the project as per the contract timeline. |  | B | When a property owner refuses to collaborate on pipeline routing during the final project stage, the project manager should review the agreement with the property owner, schedule a meeting to discuss their concerns, and inform the client. This approach clarifies contractual rights, seeks resolution through dialogue, and maintains client transparency. Escalating to the CCB and waiting (A) is too passive. Requesting additional budget and forcing collaboration (C) escalates conflict. Using contingency reserves and rerouting (D) is a major scope change requiring proper approvals. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Tailored Approach | Process | Plan and Manage Procurement | Risk | Planning | Be an Accountable Leader | Plan Risk Management | Traditional PM | 건설 프로젝트 최종 단계에서 파이프라인이 경유하는 사유지 소유자가 협력을 거부한다. PM은 무엇을 해야 하는가? | 변경통제위원회(CCB)에 파이프라인 경로 문제를 에스컬레이션하고 해결을 기다린다 | 토지 소유자와 합의서를 검토하고, 회의를 잡아 우려를 논의하고 협력적으로 해결한다 | 프로젝트 스폰서에게 추가 예산을 요청하고 토지 소유자와 분쟁을 제기한다 | 비상 예비비를 사용하고 자원을 추가하여 파이프라인을 우회하여 프로젝트를 완료한다 |  | B | 토지 소유자가 파이프라인 경로에서 협력을 거부할 때, PM은 합의서를 검토하고 회의를 잡아 우려를 논의하고 협력적으로 해결해야 한다. 대화와 협상이 최선이다. CCB 에스컬레이션(A)은 직접 해결 시도 전이다. 분쟁 제기(C)는 적대적이다. 우회(D)는 비용과 시간이 과도하다.
2062 | A project manager has just finished planning for a project when the client adds a new project team member. The project manager knows that the new team member only works remotely and is not in the main office. In addition, the new team member engages with decisions quickly in a face-to-face environment, but is slow to respond otherwise. How should the project manager reflect this in their planning? | Update the project charter to include the new team member for this project. | Monitor the new team member ' s input to gauge their value to the project. | Send out recurring onsite project meeting invites to ensure the team member ' s presence. | Include the team member in the stakeholder register and update the communications management plan. |  | D | When a new remote team member is added who is responsive in face-to-face settings but slow to respond otherwise, the project manager should include the team member in the stakeholder register and update the communications management plan. The stakeholder register captures identification and assessment information, while the communications management plan documents communication requirements, methods, formats, and frequency tailored to each stakeholder's preferences. Updating the project charter (A) is excessive for a team member addition. Monitoring the team member's value (B) is passive. Sending recurring onsite meeting invites (C) does not accommodate the remote work arrangement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Scope | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | PM이 계획을 마쳤을 때 고객이 새 원격 팀원을 추가했다. 이 팀원은 대면 시 반응이 좋지만 그 외에는 반응이 느리다. PM은 무엇을 해야 하는가? | 새 팀원을 포함하도록 프로젝트 헌장을 업데이트한다 | 새 팀원의 입력을 모니터링하여 프로젝트 가치를 측정한다 | 정기 현장 프로젝트 회의 초대를 발송하여 팀원의 참석을 보장한다 | 이해관계자 등록부에 팀원을 포함하고 커뮤니케이션 관리 계획을 업데이트한다 |  | D | 새 원격 팀원이 대면에만 반응이 좋을 때, PM은 이해관계자 등록부에 포함하고 커뮤니케이션 관리 계획을 업데이트해야 한다. 커뮤니케이션 선호도 파악이 효과적 참여를 보장한다. 헌장 업데이트(A)는 팀원 추가에 과도하다. 모니터링(B)은 수동적이다. 현장 회의(C)는 원격 상황을 해결하지 않는다.
2063 | A project team has finished participating in an iterative product increment planning session. After the planning session, the team returns with a list of features to deliver. How should the project manager ensure the product increments deliver the anticipated requirements? | Appoint a dedicated product manager for the duration of the release | Track business outcomes for planned user stories. | Ensure every user story has acceptance criteria. | Have the customer approve the product increment features. |  | C | After an iterative planning session produces a feature list, the project manager should ensure every user story has acceptance criteria to verify anticipated requirements are delivered. Acceptance criteria define done for each story. Appointing a product manager (A) creates a new role unnecessarily. Tracking business outcomes (B) is valuable but secondary to defining acceptance criteria. Having the customer approve features (D) is part of acceptance but not the primary mechanism. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 프로젝트 팀이 반복적 제품 증분 계획 세션을 마쳤다. 기능 목록이 만들어졌다. PM은 다음으로 무엇을 해야 하는가? | 출시 기간 동안 전담 제품 관리자를 임명한다 | 계획된 사용자 스토리의 비즈니스 성과를 추적한다 | 모든 사용자 스토리에 인수 기준이 있도록 한다 | 고객이 제품 증분 기능을 승인하도록 한다 |  | C | 반복적 계획 세션 후 기능 목록이 만들어지면, PM은 모든 사용자 스토리에 인수 기준이 있도록 해야 한다. 인수 기준이 예상 요구사항이 전달되었는지 검증한다. 전담 관리자(A)는 기존 역할로 충분하다. 비즈니스 성과 추적(B)은 전달 후이다. 고객 승인(D)은 개발 후이다.
2064 | A project is behind schedule because of a delayed equipment installation. This is affecting many other activities. The manager responsible for the equipment delivery notified the project manager that there is a capacity issue for the team doing the installation. What should the project manager have done to prevent this situation from happening? | Defined the skill requirements more clearly in the scope statement. 1117 | Asked the manager to follow the agreed-upon resource management plan. | Conducted periodic reviews with the manager on resource availability. | Consulted with the installation team on a regular basis to check for conflicts. |  | C | When a delayed equipment installation causes cascading schedule impacts due to the installation team's capacity constraints, the project manager should have consulted with the installation team regularly to check for conflicts. Proactive communication identifies capacity issues early. Defining skill requirements in scope (A) addresses qualifications, not capacity. Following the resource management plan (B) is passive. Periodic reviews of availability (C) is correct but less specific than direct consultation. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 장비 설치 지연으로 프로젝트가 일정에 뒤처져 있다. 설치 팀의 용량 제약이 원인이다. PM이 이전에 무엇을 했어야 하는가? | 범위 기술서에 기술 요구사항을 더 명확하게 정의했다 | 관리자에게 합의된 자원 관리 계획을 따르도록 요청했다 | 관리자와 자원 가용성에 대한 정기 검토를 수행했다 | 설치 팀과 정기적으로 상의하여 충돌을 확인했다 |  | C | 장비 설치 팀의 용량 제약으로 일정이 지연될 때, PM은 관리자와 자원 가용성에 대한 정기 검토를 수행했어야 한다. 사전적 자원 모니터링이 지연을 방지한다. 기술 요구사항(A)은 자원 문제와 무관하다. 계획 따르기 요청(B)은 모니터링이 아닌 지시이다. 설치 팀 상의(D)는 관리자 수준이 아닌 실행 수준이다.
2065 | A complex project is in its execution phase. The project is set up to produce both predictive and incremental deliverables. The agile team is running late on their tasks. There is a resource on the agile team who is responsible for producing progress reports for the project manager. This resource has the required skills to help other team members with their workload. What should the project manager do to optimize the time of the resource who produces the progress reports? | Produce the progress reports on their own | Work more closely with the agile team to eliminate the need for progress reports | Engage a new resource to produce the progress reports | Record this in the issue log and find a resource to produce the reports |  | B | When the agile team is running late and a resource produces progress reports but has skills to help others, the project manager should work more closely with the agile team to eliminate the need for progress reports. This frees the resource for productive work. Having the PM produce reports (A) adds PM burden. Engaging a new resource for reports (C) adds cost. Recording in the issue log (D) documents but does not optimize. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 복잡한 프로젝트가 실행 단계에 있다. 예측형과 점진적 인도물 모두 생산한다. 애자일 팀이 늦어지고 있다. 진행 보고서 작성자가 다른 팀을 도울 기술이 있다. PM은 무엇을 해야 하는가? | 자체적으로 진행 보고서를 생성한다 | 애자일 팀과 더 긴밀히 협력하여 진행 보고서 필요를 제거한다 | 진행 보고서 생성을 위한 새 자원을 참여시킨다 | 이슈 로그에 기록하고 보고서 생성을 위한 자원을 찾는다 |  | B | 애자일 팀이 늦어지고 보고서 작성자가 도울 기술이 있을 때, PM은 애자일 팀과 더 긴밀히 협력하여 진행 보고서 필요를 제거해야 한다. 자원 재배치가 가치 전달을 최적화한다. 자체 생성(A)은 PM에게 과도한 부담이다. 새 자원(C)은 불필요한 비용이다. 이슈 로그(D)는 수동적이다.
2066 | A project team member was unhappy with a new change in project governance and complained to one of the project sponsors. The project sponsor challenged the project manager. How should the project manager resolve this conflict? | Schedule a meeting with the project team member ' s functional manager and request the functional manager ' s support. | Arrange a meeting with the project team member and project sponsor to discuss the change and obtain consensus. | Discuss how to manage this conflict with the project management office (PMO) and let them decide how to resolve the issue. | Explain to the sponsor why the change is required and get their support in forcing the 186 project team member to accept the new change. |  | B | When a team member's complaint about governance changes reaches the project sponsor, the project manager should arrange a meeting with both the team member and the sponsor to discuss the change and work toward consensus. This facilitates open communication, ensures all viewpoints are heard, and promotes a collaborative resolution. Involving the functional manager (A) redirects the issue without addressing it directly between the affected parties. Letting the PMO decide (C) delegates the conflict resolution to an external body. Explaining the change to the sponsor and forcing the team member to accept it (D) is coercive and damages trust. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 팀원이 새로운 프로젝트 거버넌스 변경에 불만을 품고 스폰서에게 불만을 제기했다. PM은 무엇을 해야 하는가? | 팀원의 기능 관리자와 회의를 잡고 기능 관리자가 팀원을 관리하도록 요청한다 | 팀원과 프로젝트 스폰서와 회의를 주선하여 변경을 논의하고 합의를 도출한다 | PMO와 이 갈등 관리 방법을 논의하고 결정하게 한다 | 스폰서에게 변경이 필요한 이유를 설명하고 팀원에게 강제하도록 지원을 받는다 |  | B | 팀원의 거버넌스 변경 불만이 스폰서에게 전달될 때, PM은 팀원과 스폰서와 회의를 주선하여 변경을 논의하고 합의를 이끌어야 한다. 직접적 대화가 이해와 수용을 촉진한다. 기능 관리자 회의(A)는 간접적이다. PMO 결정(C)은 책임을 회피한다. 강제(D)는 갈등을 악화시킨다.
2067 | A project manager is leading a cross-organizational project that is replacing a platform on which various solutions used by 15 business units were built. The project is part of a large program of work, and some of the resources are shared with other projects outside of the program initiated by the respective business units. Which stakeholders should the project manager consult with first to manage interdependencies? | Project sponsors | Other project managers | Program managers | Business unit managers |  | C | When managing a cross-organizational project with shared resources across a program, the project manager should first consult program managers to manage interdependencies. Program managers oversee cross-project coordination and resource allocation within the program. Project sponsors (A) provide strategic direction but may not manage dependencies. Other project managers (B) manage individual projects. Business unit managers (D) manage functional areas but not program-level coordination. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | PM이 여러 솔루션이 사용하는 플랫폼을 교체하는 교차 조직 프로젝트를 이끌고 있다. 공유 자원에 대해 먼저 누구와 상의해야 하는가? | 프로젝트 스폰서 | 다른 프로젝트 관리자 | 프로그램 관리자 | 사업부 관리자 |  | C | 프로그램 내 공유 자원이 있는 교차 조직 프로젝트를 관리할 때, PM은 먼저 프로그램 관리자와 상의해야 한다. 프로그램 관리자가 교차 프로젝트 상호의존성을 감독한다. 스폰서(A)는 자원 조정이 아닌 전략적 역할이다. 다른 PM(B)은 프로그램 수준 조정이 아니다. 사업부 관리자(D)는 자원 소유자이지만 프로그램 우선순위를 모른다.
2068 | A project manager has been assigned to a long-term project. The project manager came across a government debate over a new law that may affect the project. What are the first two actions the project manager should perform? (Choose two) | Consult with the project stakeholders. | Request additional budget for contingency. | Perform a risk identification process with the project team. | Create a change request to discuss with the change control board (CCB). | Discuss the possible impacts with subject matter experts (SMEs). | A, C | When a government debate over a new law may affect the project, the project manager should first (C) perform a risk identification process with the team, and (E) discuss possible impacts with subject matter experts. Risk identification and expert analysis inform the response. Consulting stakeholders (A) is valuable but not the first analytical step. Requesting contingency budget (B) is premature. Creating a change request (D) acts before understanding the impact. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | PM이 장기 프로젝트에 배정되었다. 새로운 법안에 대한 정부 논쟁을 발견했다. PM은 무엇을 해야 하는가? (2개 선택) | 프로젝트 이해관계자와 상담한다 | 비상 예산 추가를 요청한다 | 프로젝트 팀과 리스크 식별 프로세스를 수행한다 | 변경통제위원회(CCB)와 논의하기 위한 변경 요청을 생성한다 | 주제 전문가(SME)와 가능한 영향을 논의한다 | A, C | 정부의 새로운 법안 논쟁이 프로젝트에 영향을 줄 수 있을 때, PM은 프로젝트 이해관계자와 상담하고(A), 프로젝트 팀과 리스크 식별 프로세스를 수행해야 한다(C). 이해관계자 상담이 다양한 관점을 제공하고, 리스크 식별이 위협을 공식화한다. 비상 예산(B)은 리스크 이해 전에 시기상조이다. 변경 요청(D)은 리스크 평가 후에 한다. SME 논의(E)는 유용하지만 공식적 리스크 프로세스가 우선이다.
2069 | To ensure effective team communication and processes, a standard set of software including video conferencing is defined for a virtual scrum team. Several team members are reporting problems with their access and cannot adhere to team processes. How should these issues be resolved? | The scrum master should ensure the appropriate escalation to resolve the issues. | Individual team members should discuss solutions to resolve the issues after the Scrum is concluded. | Individual team members need to submit service desk tickets to resolve the issues. | The product owner owns the open issues until they are resolved. |  | A | The correct answer is A. The scrum master should ensure the appropriate escalation to resolve the issues. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Agile | Scrum | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 효과적인 팀 커뮤니케이션을 위해 화상 회의 포함 표준 소프트웨어가 정의되었지만 연결 문제가 발생한다. 누가 해결해야 하는가? | 스크럼 마스터가 문제 해결을 위한 적절한 에스컬레이션을 보장해야 한다 | 개별 팀원이 스크럼 후 문제 해결 방안을 논의해야 한다 | 개별 팀원이 문제 해결을 위해 서비스 데스크 티켓을 제출해야 한다 | 제품 책임자가 해결될 때까지 미해결 이슈를 소유한다 |  | A | 정답은 A이다. 스크럼 마스터가 문제 해결을 위한 적절한 에스컬레이션을 보장해야 한다. 애자일 환경에서 SM이 장애물을 제거하는 것이 핵심 역할이다. 개별 논의(B)는 팀 시간을 낭비한다. 서비스 데스크(C)는 개인 책임이지 SM 역할이 아니다. 제품 책임자(D)는 이슈 소유자가 아니다.
2070 | A project team has finished its first iteration out of six. The iteration's delivery performance (velocity) was 50%. During the iteration retrospective, the team realizes that the complexity of the work was underestimated. What should the project manager do? | Ask to replace some team members with more experienced ones. | Ask the technical manager to help the team with the issue. | Update the issue log and escalate it to the project sponsor. | Meet with the team to review internal actions to resolve the situation. |  | D | When the team realizes work complexity was underestimated after the first iteration with 50% velocity, the project manager should meet with the team to review internal actions to resolve the situation. This collaborative approach allows the team to reassess complexity, adjust estimation practices, and develop strategies for improvement. Asking to replace team members (A) is punitive and does not address the estimation issue. Asking the technical manager for help (B) introduces external dependency. Updating the issue log and escalating to the sponsor (C) is premature—the team should first attempt to resolve the issue internally. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 6번 중 첫 이터레이션을 마쳤다. 속도가 50%였다. 작업 복잡성이 과소평가되었음을 팀이 인식했다. PM은 무엇을 해야 하는가? | 더 경험 있는 팀원으로 일부 교체를 요청한다 | 기술 관리자에게 팀 문제 지원을 요청한다 | 이슈 로그를 업데이트하고 프로젝트 스폰서에게 에스컬레이션한다 | 팀과 회의하여 상황 해결을 위한 내부 조치를 검토한다 |  | D | 첫 이터레이션 속도가 50%이고 작업 복잡성이 과소평가되었을 때, PM은 팀과 회의하여 내부 조치를 검토해야 한다. 팀 기반 문제 해결이 자체 조직화를 촉진한다. 교체(A)는 팀 역학을 해친다. 기술 관리자(B)는 외부 의존이다. 에스컬레이션(C)은 내부 해결 시도 전에 과도하다.
2071 | A company faces challenges and decides to cut a few product features from the main project due to market conditions. During a status meeting, a new stakeholder expresses concern about the discrepancies between the current deliverables and the deliverables agreed upon in the project charter. What should the project manager do first? | Ask the new stakeholder to submit a change request to the change control board (CCB). | Ask the project team to increase the number of updates provided to the stakeholder. | Review the project objectives for alignment with the intended corresponding business value. | Determine the root cause of the discrepancy with the project team and agree on the project scope. |  | D | When a new stakeholder raises concerns about discrepancies between current deliverables and the original charter, the project manager should first determine the root cause of the discrepancy with the project team and agree on the project scope. Understanding whether changes were officially approved enables informed conversation with stakeholders. Asking the stakeholder to submit a change request (A) is premature before understanding the history. Increasing update frequency (B) does not address the discrepancy. Reviewing project objectives for alignment (C) is broader than the specific scope concern. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 시장 조건으로 제품 기능이 삭감되었다. 새 이해관계자가 현재 인도물과 원래 헌장 간 차이에 우려를 제기한다. PM은 무엇을 해야 하는가? | 새 이해관계자에게 CCB에 변경 요청을 제출하도록 요청한다 | 이해관계자에게 업데이트 횟수를 늘리도록 팀에 요청한다 | 의도된 사업 가치와 프로젝트 목표의 정렬을 검토한다 | 프로젝트 팀과 차이의 근본 원인을 파악하고 범위에 합의한다 |  | D | 새 이해관계자가 현재 인도물과 원래 헌장 간 차이에 우려할 때, PM은 먼저 팀과 차이의 근본 원인을 파악하고 범위에 합의해야 한다. 근본 원인 분석이 정확한 대응을 가능하게 한다. CCB 제출(A)은 분석 전에 성급하다. 업데이트 증가(B)는 차이를 해결하지 않는다. 목표 정렬(C)은 유용하지만 먼저 원인 파악이 필요하다.
2072 | A new resource has joined an iterative project team. The project manager notices that the resource is unable to complete the deliverables on time. How should the project manager address this situation? | Discuss options to improve performance with the resource manager | Address the lack of performance by coaching the new team member | Request a more efficient replacement resource from the project sponsor | Provide performance feedback as part of the retrospective ceremony. |  | D | When a new team member on an iterative project cannot complete deliverables on time, the project manager should provide performance feedback as part of the retrospective ceremony. Retrospectives offer a structured, team-oriented setting to address performance constructively, identify barriers, and develop improvement actions. Discussing with the resource manager (A) escalates externally before addressing it within the team. Coaching the new member (B) is valuable but should be informed by feedback. Requesting a replacement (C) is premature without first attempting to support the team member's development. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 새 자원이 이터레이티브 프로젝트 팀에 합류했으나 기한 내 인도물을 완료하지 못한다. PM은 무엇을 해야 하는가? | 자원 관리자와 성과 개선 옵션을 논의한다 | 새 팀원을 코칭하여 성과 부족을 다룬다 | 프로젝트 스폰서에게 더 효율적인 대체 자원을 요청한다 | 회고 의식의 일부로 성과 피드백을 제공한다 |  | D | 이터레이티브 프로젝트의 새 팀원이 기한 내 인도를 못할 때, PM은 회고 의식의 일부로 성과 피드백을 제공해야 한다. 회고가 안전한 환경에서 개선 논의를 가능하게 한다. 자원 관리자(A)는 팀 외부 에스컬레이션이다. 코칭(B)은 유용하지만 공식적 피드백 채널이 부족하다. 교체(C)는 시기상조이다.
2073 | A project to support an organizational transformation is in the planning phase. Transformation is the project sponsor's idea and is not aligned with key stakeholders because they all have different opinions about the project outcomes. What should the project manager do next? | Define a high-level project scope and share it with the key stakeholders. | Conduct a workshop on project goals and deliverables with the key stakeholders. | Ask the project sponsor to help with engagement of the key stakeholders. | Communicate project outcomes and results with the key stakeholders. |  | B | When a transformation project is the sponsor's idea but key stakeholders have different opinions about outcomes, the project manager should conduct a workshop on project goals and deliverables with key stakeholders. Collaborative workshops facilitate alignment and shared ownership. Defining and sharing a high-level scope (A) is one-way communication. Asking the sponsor to help with engagement (C) delegates the PM's responsibility. Communicating outcomes (D) is informational, not collaborative. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 조직 변환을 지원하는 프로젝트가 계획 단계에 있다. 주요 이해관계자가 결과에 대해 다른 의견을 가진다. PM은 무엇을 해야 하는가? | 고수준 프로젝트 범위를 정의하고 주요 이해관계자와 공유한다 | 주요 이해관계자와 프로젝트 목표와 인도물에 대한 워크숍을 실시한다 | 프로젝트 스폰서에게 주요 이해관계자 참여를 돕도록 요청한다 | 주요 이해관계자에게 프로젝트 결과와 성과를 커뮤니케이션한다 |  | B | 변환 프로젝트에서 주요 이해관계자가 결과에 다른 의견을 가질 때, PM은 목표와 인도물에 대한 워크숍을 실시해야 한다. 협력적 워크숍이 합의와 정렬을 구축한다. 범위 공유(A)는 일방적이다. 스폰서 도움(C)은 간접적이다. 결과 커뮤니케이션(D)은 계획 단계에 부적절하다.
2074 | A project manager is managing an internal project that was poorly defined. Recently, the project manager received several change requests raised by the organization's upper management. What should the project manager do first? | Review the benefits of the proposed changes in relation to the business case. | Request a provisional budget increase to avoid any budget overruns. | Assess the time overrun, and start implementation to avoid additional delays. | Motivate the team to avoid the frustration of working on a prolonged project. |  | A | When a poorly defined internal project receives several change requests from upper management, the project manager should first review the benefits of the proposed changes in relation to the business case. Benefit analysis ensures changes add value. Requesting a provisional budget increase (B) addresses cost without evaluating need. Assessing time overrun and starting implementation (C) bypasses change evaluation. Motivating the team (D) addresses morale but not the change requests. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | PM이 정의가 부실한 내부 프로젝트를 관리 중이다. 최근 상위 경영진으로부터 여러 변경 요청을 받았다. PM은 무엇을 먼저 해야 하는가? | 사업 사례와 관련하여 제안된 변경의 이점을 검토한다 | 예산 초과를 방지하기 위해 임시 예산 증가를 요청한다 | 시간 초과를 평가하고 추가 지연을 피하기 위해 구현을 시작한다 | 장기 프로젝트 작업의 좌절감을 방지하기 위해 팀에 동기를 부여한다 |  | A | 정의 부실 프로젝트에서 상위 경영진 변경 요청을 받을 때, PM은 먼저 사업 사례와 관련하여 변경 이점을 검토해야 한다. 사업 가치 검증이 불필요한 변경을 방지한다. 예산 증가(B)는 이점 검증 전에 시기상조이다. 즉시 구현(C)은 분석 없이 위험하다. 동기 부여(D)는 변경 관리가 아니다.
2075 | A key project stakeholder showed interest in the beginning of a complex agile project but has become less involved as the sprint has progressed due to additional responsibilities. A few sprints later, the key stakeholder rejected a feature deliverable. The team is reworking the rejected deliverable for the next sprint. What should the project manager have done to avoid this situation? | Analyzed the changes in stakeholder attributes | Involved the key stakeholders in the decision-making process | Customized stakeholder communications based on the stakeholders' needs | Documented the project vision and objectives |  | C | When a key stakeholder became less involved over sprints and then rejected a feature deliverable, the project manager should have customized stakeholder communications based on the stakeholder's needs. Tailored communication maintains engagement despite competing responsibilities. Analyzing stakeholder attribute changes (A) monitors but does not act. Involving stakeholders in decisions (B) is broad. Documenting vision and objectives (D) does not address ongoing engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 주요 이해관계자가 복잡한 애자일 프로젝트 초기에 관심을 보였으나 스프린트가 진행되며 참여가 줄었다. PM이 이전에 무엇을 했어야 하는가? | 이해관계자 속성의 변화를 분석했다 | 주요 이해관계자를 의사결정 과정에 참여시켰다 | 이해관계자 필요에 맞춰 커뮤니케이션을 맞춤화했다 | 프로젝트 비전과 목표를 문서화했다 |  | C | 주요 이해관계자가 점차 참여를 줄이다 인도물을 거부할 때, PM은 이해관계자 필요에 맞춰 커뮤니케이션을 맞춤화했어야 한다. 맞춤형 커뮤니케이션이 지속적 참여를 유지한다. 속성 분석(A)은 분석이지 행동이 아니다. 의사결정 참여(B)는 부분적이다. 비전 문서화(D)는 참여를 보장하지 않는다.
2076 | After a project team has been working on a project for several months, the project is cancelled. The project sponsor is putting pressure on the project manager to perform closeout duties as fast as possible so that the project team can move on to other work. The project sponsor has instructed the team not to waste time archiving the project artifacts for the cancelled project. How should the project manager handle this situation? | Comply with the project sponsor ' s request to not archive the project artifacts. | Consult with the project management office (PMO) for guidance on project artifacts. | Archive the project artifacts on the project manager ' s local computer for future reference. | Document the project sponsor ' s instructions as the archived project artifacts. |  | B | When the sponsor pressures for fast closeout of a cancelled project and instructs against archiving artifacts, the project manager should consult the PMO for guidance on project artifacts. The PMO provides standards and requirements for proper archiving. Complying with the sponsor's request (A) may violate organizational policies. Archiving on a local computer (C) compromises security and accessibility. Documenting the sponsor's instructions as artifacts (D) does not capture project information. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 프로젝트가 취소되었다. 스폰서가 빠른 종료를 압박하며 산출물을 아카이브하지 말라고 지시한다. PM은 무엇을 해야 하는가? | 스폰서 요청에 따라 프로젝트 산출물을 아카이브하지 않는다 | PMO에 프로젝트 산출물에 대한 지침을 상의한다 | PM의 로컬 컴퓨터에 프로젝트 산출물을 향후 참조용으로 아카이브한다 | 스폰서 지시를 아카이브된 프로젝트 산출물로 문서화한다 |  | B | 스폰서가 취소된 프로젝트의 산출물 아카이브를 거부할 때, PM은 PMO에 지침을 상의해야 한다. PMO가 조직의 아카이브 정책과 절차에 대한 지침을 제공한다. 아카이브 거부 동의(A)는 조직 정책을 위반할 수 있다. 로컬 저장(C)은 적절한 산출물 관리가 아니다. 지시 문서화(D)는 실제 아카이브를 대체하지 않는다.
2077 | A company is working on a project to develop an integration of their existing systems. There are known issues in production. What should the project manager do? | Identify and remove impediments and mitigate the risks. | Review the quality control processes and procedures. | Ensure the product owner reviews requirements with the team. | Include acceptance criteria in the definition of done (DoD). |  | A | When a project to integrate existing systems has known production issues, the project manager should identify and remove impediments and mitigate the risks. Proactive impediment removal and risk mitigation enable progress. Reviewing quality processes (B) examines procedures, not blockers. Ensuring PO reviews requirements (C) focuses on scope, not current issues. Including acceptance criteria in DoD (D) improves future quality but does not address current impediments. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 회사가 기존 시스템 통합 프로젝트를 진행 중이다. 생산 환경에 알려진 문제가 있다. PM은 무엇을 해야 하는가? | 장애물을 식별하고 제거하며 리스크를 완화한다 | 품질 관리 프로세스와 절차를 검토한다 | 제품 책임자가 팀과 요구사항을 검토하도록 한다 | 완료 정의(DoD)에 인수 기준을 포함한다 |  | A | 기존 시스템 통합 프로젝트에 알려진 생산 문제가 있을 때, PM은 장애물을 식별하고 제거하며 리스크를 완화해야 한다. 사전적 장애물 제거와 리스크 완화가 프로젝트 성공을 보장한다. 품질 프로세스(B)는 생산 문제 해결이 아니다. 요구사항 검토(C)는 기존 문제를 다루지 않는다. DoD(D)는 미래 인도에 초점이다.
2078 | A company is running a project to eliminate a sales channel that has been unprofitable for the past 3 years. A key stakeholder from another area, who has historical ties to that sales channel, objects to the project. What should the project manager do in this situation? | Escalate the stakeholder issue to the project sponsor. | Assess the impact of the stakeholder and engage properly. | Develop a specific communications strategy for this stakeholder. | Use interpersonal skills to gain stakeholder engagement. |  | B | When a stakeholder objects to a project, the PM must evaluate the stakeholder's concerns and their potential influence on project outcomes. Understanding the reasons behind the objection—including any historical or legacy ties—enables the PM to address those concerns constructively while keeping the project aligned with its objectives. Effective stakeholder engagement is central to both project management and business analysis, as it supports expectation management, conflict resolution, and alignment of all parties with the project's goals. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 회사가 3년간 비수익 판매 채널을 제거하는 프로젝트를 진행 중이다. 주요 이해관계자가 반대한다. PM은 무엇을 먼저 해야 하는가? | 이해관계자 이슈를 프로젝트 스폰서에게 에스컬레이션한다 | 이해관계자의 영향을 평가하고 적절히 참여시킨다 | 이 이해관계자를 위한 특정 커뮤니케이션 전략을 개발한다 | 대인관계 기술을 사용하여 이해관계자 참여를 확보한다 |  | B | 이해관계자가 프로젝트에 반대할 때, PM은 먼저 이해관계자의 영향을 평가하고 적절히 참여시켜야 한다. 반대 이유와 잠재적 영향 이해가 적절한 대응의 기초이다. 에스컬레이션(A)은 평가 전에 시기상조이다. 커뮤니케이션 전략(C)은 평가 후에 한다. 대인관계 기술(D)은 전략이 아닌 도구이다.
2079 | A new team member is assigned to a team that consistently delivers each iteration. The new team member does not understand many of the processes followed and begins to negatively impact the schedule. What should the project manager do? | Place the new team member on a performance improvement program. | Assign easier activities to the new team member. | Ask another team member to take some of the new team member ' s work. | Allocate time within the iterations to mentor the new team member. |  | D | When a new team member does not understand processes and negatively impacts the schedule on an iterative team, the project manager should allocate time within iterations to mentor them. Structured mentoring builds capability sustainably. Placing them on a performance improvement program (A) is punitive. Assigning easier activities (B) limits their growth. Redistributing work to others (C) does not address the root cause. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Help Ensure Knowledge Transfer | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 새 팀원이 매 이터레이션 일관되게 납품하는 팀에 합류했다. 새 팀원이 프로세스를 이해하지 못하고 일정에 부정적 영향을 준다. PM은 무엇을 해야 하는가? | 새 팀원을 성과 개선 프로그램에 등록한다 | 새 팀원에게 더 쉬운 활동을 할당한다 | 다른 팀원에게 새 팀원의 작업 일부를 맡긴다 | 이터레이션 내에 새 팀원을 멘토링할 시간을 할당한다 |  | D | 새 팀원이 프로세스를 이해하지 못하여 일정에 영향을 줄 때, PM은 이터레이션 내에 멘토링 시간을 할당해야 한다. 구조화된 멘토링이 학습과 통합을 가속한다. 성과 프로그램(A)은 이해 부족이 아닌 성과 불량에 적합하다. 쉬운 활동(B)은 성장을 제한한다. 작업 이전(C)은 학습 기회를 빼앗는다.
2080 | A project manager is leading a hybrid project. The only available resources that have experience with agile are not at the project manager's location. The project has a strict schedule and budget, and the project manager is concerned about their ability to deliver it. What should the project manager do? | Plan to have the agile resources temporarily relocate to the project manager ' s location. | Engage the agile resources through video conferencing on a daily basis. | Advise the sponsor that the project will be delayed as agile training will be required. | Request a budget extension to get local resources experienced in agile. |  | B | When the only available agile-experienced resources are remote but the project has strict schedule and budget constraints, the project manager should engage them through daily video conferencing. This enables real-time collaboration without relocation costs or budget extension. Temporarily relocating resources (A) increases costs. Advising the sponsor of delay for training (C) is premature. Requesting a budget extension for local resources (D) exceeds budget constraints. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | PM이 하이브리드 프로젝트를 이끌고 있다. 애자일 경험이 있는 유일한 자원이 원격 위치에 있다. 일정과 예산이 엄격하다. PM은 무엇을 해야 하는가? | 애자일 자원이 PM 위치로 임시 이동하도록 계획한다 | 매일 화상 회의를 통해 애자일 자원을 참여시킨다 | 애자일 교육이 필요하므로 프로젝트가 지연될 것이라고 스폰서에게 알린다 | 현지에서 애자일 경험이 있는 자원을 확보하기 위해 예산 연장을 요청한다 |  | B | 애자일 경험 자원이 원격이고 일정과 예산이 엄격할 때, PM은 매일 화상 회의를 통해 참여시켜야 한다. 기술을 활용한 원격 협업이 비용 효율적이다. 임시 이동(A)은 비용과 시간이 든다. 지연 통보(C)는 해결책이 아니다. 예산 연장(D)은 엄격한 예산에 위배된다.
2081 | A project manager is working on a project. A few months after the project has launched, the project manager starts receiving complaints from business unit managers about the lack of updated project information. What should the project manager do? | Run a Monte Carlo simulation to identify any flaws in the communication matrix | Check the organizational responsibility of functional managers in the project | Review the communications management plan and stakeholder register | Request that the business unit managers attend weekly review meetings |  | C | When business unit managers complain about lack of updated project information months after launch, the project manager should review the communications management plan and stakeholder register. These documents reveal gaps in information distribution. Running a Monte Carlo simulation (A) is unrelated. Checking organizational responsibility (B) does not address communications. Requesting attendance at weekly meetings (D) is a tactical fix without understanding the root cause. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 프로젝트 출시 몇 달 후 사업부 관리자들이 업데이트된 정보 부족에 불만을 제기한다. PM은 무엇을 해야 하는가? | 커뮤니케이션 매트릭스의 결함을 식별하기 위해 몬테카를로 시뮬레이션을 실행한다 | 프로젝트에서 기능 관리자의 조직적 책임을 확인한다 | 커뮤니케이션 관리 계획과 이해관계자 등록부를 검토한다 | 사업부 관리자에게 주간 검토 회의 참석을 요청한다 |  | C | 사업부 관리자들이 업데이트된 프로젝트 정보 부족에 불만할 때, PM은 커뮤니케이션 관리 계획과 이해관계자 등록부를 검토해야 한다. 이 문서들이 정보 격차를 식별한다. 몬테카를로(A)는 커뮤니케이션 문제와 무관하다. 기능 관리자 책임(B)은 간접적이다. 회의 참석 요청(D)은 체계적 해결이 아니다.
2082 | A team has been struggling with various issues during the course of an iteration. The project lead facilitates a discussion of the issues and the team forms new team agreements. During the next iteration, some of the same issues appear again. What should the project lead do next? | Post the agreements in a conspicuous place where all of the team members can see them. | Let the team self-organize and determine the best means to prevent the issues from occurring again | Challenge the team to determine if the issues surfaced again because agreements were not followed | Notify senior management of the issues and have them review the importance of 180 agreements with the team |  | B | When recurring issues surface despite new team agreements, the project lead should let the team self-organize and determine the best means to prevent the issues from occurring again. Self-organizing teams have greater ownership, autonomy, and accountability over their processes. The project lead should facilitate reflection—such as through retrospectives—rather than impose solutions, enabling the team to inspect and adapt their practices based on feedback and learning. Posting agreements in a visible place (A) is a good practice but alone does not address why they were not followed. Challenging the team about non-compliance (C) may be warranted eventually but is less effective than empowering the team to own the solution. Notifying senior management (D) undermines the team's trust and autonomy. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 이터레이션 중 다양한 문제로 어려움을 겪는 팀이 새로운 합의를 도출했으나 같은 문제가 다시 발생한다. 프로젝트 리더는 무엇을 해야 하는가? | 모든 팀원이 볼 수 있는 눈에 띄는 장소에 합의를 게시한다 | 팀이 자체 조직화하여 문제 재발 방지를 위한 최선의 방법을 결정하게 한다 | 합의가 지켜지지 않아 문제가 다시 발생했는지 팀에 도전한다 | 문제를 상위 경영진에 통보하고 합의의 중요성을 팀과 검토하게 한다 |  | B | 새 합의에도 같은 문제가 재발할 때, 프로젝트 리더는 팀이 자체 조직화하여 최선의 방지 방법을 결정하게 해야 한다. 자체 조직화가 팀 소유권과 지속 가능한 해결을 촉진한다. 게시(A)는 인식을 높이지만 행동 변화를 보장하지 않는다. 도전(C)은 비난적이다. 경영진 통보(D)는 과도한 에스컬레이션이다.
2083 | A marketing team is planning for a multiyear initiative that will include a lot of cross-functional stakeholders. The project manager has been assigned and is now in the project planning phase. What item(s) should the project manager develop first? | A business case and scope document | A product backlog and identification of the features to be delivered | A risk management plan to incorporate known risks | A communications management plan that addresses the team ' s needs |  | A | When planning a multiyear, cross-functional marketing initiative, the project manager should first develop a business case and scope document. These establish justification and boundaries. A product backlog (B) is premature without scope. A risk management plan (C) follows scope definition. A communications plan (D) addresses how, not what. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | Baseline & Change Control | Process | Develop and Manage Scope | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 마케팅 팀이 많은 교차 기능 이해관계자를 포함하는 다년 이니셔티브를 계획 중이다. PM은 먼저 무엇을 개발해야 하는가? | 사업 사례와 범위 문서 | 제품 백로그와 납품할 기능 식별 | 알려진 리스크를 통합하는 리스크 관리 계획 | 팀의 요구를 다루는 커뮤니케이션 관리 계획 |  | A | 다년, 교차 기능 마케팅 이니셔티브를 계획할 때, PM은 먼저 사업 사례와 범위 문서를 개발해야 한다. 정당성과 경계를 설정하는 것이 모든 후속 계획의 기초이다. 백로그(B)는 범위 정의 후에 한다. 리스크 계획(C)은 사업 사례 후에 한다. 커뮤니케이션 계획(D)은 범위와 이해관계자 식별 후에 한다.
2084 | A project manager just took over a construction project which was already in its execution phase. Labor union representatives of the construction workers ask to revise the overtime per hour rate, as wage per hour have increased across the industry. What should the project manager do first? | Negotiate with the labor union representatives if the clause about increased wage per hour meets their requirements. | Assign a team member to negotiate the increased wage per hour with the labor union representatives. | Obtain approval from sponsors to increase the rates because it can affect project due to lack of resources. | Carefully read the agreements and see if there was any clause if the per hour rate could be increased. |  | D | When labor union representatives request a revision of the overtime rate, the project manager should first carefully read the agreements and check whether any clause allows for rate adjustments. Understanding the contractual framework is essential before taking any action—the PM needs to know the legal and contractual boundaries before negotiating or escalating. Negotiating directly (A) is premature without understanding the contractual terms. Assigning a team member to negotiate (B) delegates a critical procurement matter without proper authority or context. Obtaining sponsor approval to increase rates (C) implies a decision has been made before confirming whether the contract even permits such changes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Procurement | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | PM이 이미 실행 단계인 건설 프로젝트를 인수했다. 노동조합 대표가 초과근무 수당 인상을 요청한다. PM은 무엇을 먼저 해야 하는가? | 시간당 임금 인상 조항이 프로젝트 요구사항을 충족하는지 노동조합과 협상한다 | 팀원에게 노동조합과 시간당 임금 인상을 협상하도록 배정한다 | 자원 부족이 프로젝트에 영향을 줄 수 있으므로 스폰서에게 요율 인상 승인을 받는다 | 계약을 주의 깊게 읽고 시간당 요율 인상이 가능한 조항이 있는지 확인한다 |  | D | 노동조합이 초과근무 수당 인상을 요청할 때, PM은 먼저 계약을 주의 깊게 읽고 요율 조정이 가능한 조항이 있는지 확인해야 한다. 계약 이해가 적절한 대응의 기초이다. 즉시 협상(A)은 계약 검토 전에 성급하다. 팀원 배정(B)은 PM의 책임이다. 승인 요청(C)은 계약 검토 후에 한다.
2085 | An IT project manager for a project that is 50% complete learns that a critical team member plans to relocate to another country soon. The team member is needed for the remainder of the project. How should the project manager improve team dynamics? | Replace the team member with someone who has similar qualifications and is located closer. | Offer the team member an incentive to stay until the end of the project. | Require that all team members be physically present for the weekly project review. | Set up a weekly video conference to monitor the progress of the team member ' s work. |  | D | When a critical team member plans to relocate during an ongoing project, the project manager should set up weekly video conferences to monitor progress and maintain collaboration. This leverages technology to sustain the team member's contribution regardless of location. Replacing the team member (A) loses institutional knowledge. Offering incentives to stay (B) may not be feasible. Requiring physical presence for reviews (C) is impractical for a relocating team member. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | PM이 50% 완료된 IT 프로젝트의 핵심 팀원이 다른 도시로 이동 계획을 알게 되었다. PM은 무엇을 해야 하는가? | 유사한 자격을 가진 가까운 위치의 팀원으로 교체한다 | 프로젝트 종료까지 머물도록 인센티브를 제공한다 | 모든 팀원이 주간 프로젝트 검토에 물리적으로 참석하도록 요구한다 | 주간 화상 회의를 설정하여 팀원의 작업 진행을 모니터링한다 |  | D | 핵심 팀원이 이전 계획을 알릴 때, PM은 주간 화상 회의를 설정하여 진행을 모니터링하고 협업을 유지해야 한다. 기술 활용이 원격 근무를 가능하게 한다. 교체(A)는 핵심 지식을 잃는다. 인센티브(B)는 개인 결정을 통제하려 한다. 물리적 참석 요구(C)는 비현실적이다.
2086 | A project team is engaging a development team in another country to develop software. During progress reviews, the project manager identified completion date delays due to rework because there were different interpretations of the client's needs. What should the project manager do? | Create prototypes with the development team to confirm requirements | Travel to the development team ' s office to push the schedule | Escalate to the project steering committee and request additional time | Set up a meeting with key stakeholders to clarify requirements |  | A | Prototyping is an effective technique for eliciting, analyzing, and validating requirements when working with distributed teams experiencing communication challenges. Working prototypes reduce ambiguity, resolve conflicting interpretations, and generate concrete feedback from stakeholders and development teams. Prototypes facilitate communication across different locations and cultures, improving development quality and efficiency while minimizing rework from misunderstood requirements. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 다른 나라의 개발팀과 소프트웨어를 개발 중이다. 진행 검토 중 요구사항이 명확하지 않음을 발견했다. PM은 무엇을 해야 하는가? | 개발팀과 프로토타입을 만들어 요구사항을 확인한다 | 개발팀 사무실로 출장 가서 일정을 추진한다 | 프로젝트 운영위원회에 에스컬레이션하고 추가 시간을 요청한다 | 주요 이해관계자와 회의를 설정하여 요구사항을 명확히 한다 |  | A | 분산 팀과 커뮤니케이션 문제로 요구사항이 불명확할 때, PM은 개발팀과 프로토타입을 만들어 요구사항을 확인해야 한다. 작동하는 프로토타입이 모호성을 줄이고 요구사항 검증에 효과적이다. 출장(B)은 일정 추진이지 요구사항 해결이 아니다. 에스컬레이션(C)은 직접 해결 시도 전에 과도하다. 이해관계자 회의(D)는 유용하지만 프로토타입이 더 효과적이다.
2087 | A key challenge that a project manager is facing is the lack of discipline by various team members and their inability to harness energy to achieve the project objectives. What should the project manager do to overcome this challenge? | Approach the project sponsor and request help in discussing the project deliverables with team members. | Explain to the team that the project manager is ultimately responsible for the delivery. | Assign multiple managers to the various teams and delegate all of the tasks to them. | Meet with each team member separately and apply an appropriate approach with each one. |  | D | When team members lack discipline and struggle to focus energy on project objectives, the most effective approach is to meet with each team member individually and tailor the leadership style to their specific needs. Each person may face different motivations, obstacles, or misunderstandings that require a personalized approach. This reflects situational leadership principles. Escalating to the sponsor (A) does not address the root cause at the team level. Asserting ultimate responsibility (B) is authoritarian and unlikely to inspire improved behavior. Assigning multiple managers (C) adds complexity and fragments accountability rather than solving the underlying discipline issue. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 팀원들이 규율이 부족하고 프로젝트 목표에 에너지를 집중하지 못한다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 접근하여 팀원과 인도물 논의를 도와달라고 요청한다 | 팀에게 PM이 납품에 대한 최종 책임이 있음을 설명한다 | 다양한 팀에 여러 관리자를 배정하고 모든 작업을 위임한다 | 각 팀원을 개별적으로 만나 각자에게 적절한 접근법을 적용한다 |  | D | 팀원들이 규율 부족하고 목표 집중이 안 될 때, PM은 각 팀원을 개별적으로 만나 맞춤형 접근법을 적용해야 한다. 상황적 리더십이 개인별 요구를 다룬다. 스폰서 도움(A)은 간접적이다. 책임 설명(B)은 동기 부여가 아니다. 관리자 배정(C)은 과도한 구조이다.
2088 | One team member is complaining about an agreement made during the last meeting. That team member was present at the meeting and participated in the decisions registered in the meeting minutes. What should the project manager do next? | Talk with the team member and explain that once the meeting ended, the agreement must be respected. | Schedule a new meeting to evaluate the agreement and negotiate a new one. | Arrange an additional meeting with the team to communicate the agreement made during the last meeting. | Meet with the team member and search for the root cause of their behavior. |  | A | When a team member complains about an agreement they participated in making, the project manager should talk with the team member and explain that once the meeting ended, the agreement must be respected. Clear communication reinforces accountability and commitment to team decisions. Scheduling a new meeting to renegotiate (B) undermines the original agreement. Arranging an additional meeting to recommunicate (C) is redundant. Searching for the root cause of the behavior (D) may be appropriate later but the immediate action is to reinforce the commitment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 팀원이 지난 회의에서 한 합의에 대해 불만을 제기한다. 그 팀원은 회의에 참석했었다. PM은 무엇을 해야 하는가? | 팀원과 대화하여 회의가 끝나면 합의를 존중해야 함을 설명한다 | 합의를 평가하고 새로운 합의를 협상하기 위한 새 회의를 예약한다 | 팀과 추가 회의를 주선하여 지난 회의의 합의를 전달한다 | 팀원과 만나 행동의 근본 원인을 탐색한다 |  | A | 참석했던 회의의 합의에 불만을 제기하는 팀원에게, PM은 회의 종료 후 합의는 존중해야 함을 설명해야 한다. 명확한 기대가 팀 규범을 강화한다. 새 협상(B)은 합의 프로세스를 약화시킨다. 추가 회의(C)는 불필요하다. 근본 원인 탐색(D)은 단순 규칙 재확인으로 충분한 상황에서 과도하다.
2089 | A new project manager has been assigned to an environmental project. After reviewing the project plan, the project manager notices that health and safety requirements have not been properly addressed. This is a serious concern, and the project manager wants to fix this issue immediately. Why is this situation problematic? | It is imperative that established performance metrics are met. | The project manager is obligated to comply with the project location ' s regulatoryrequirements. | The project manager must follow their employer ' s organizational process assets(OPAs). | Injury or loss incidents could delay project deliverables. |  | B | When health and safety requirements have not been properly addressed in the project plan, this is problematic because the project manager is obligated to comply with the project location's regulatory requirements. Legal compliance is non-negotiable and failure risks penalties, sanctions, or project termination. Meeting performance metrics (A) is important but not the primary concern. Following employer OPAs (C) may not align with local regulations. Injury incidents delaying deliverables (D) is a consequence, not the core obligation. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 새 PM이 환경 프로젝트에 배정되었다. 프로젝트 계획 검토 후 건강 및 안전 요구사항이 적절히 다뤄지지 않았음을 발견했다. 이것이 문제인 이유는? | 확립된 성과 지표를 충족해야 하기 때문이다 | PM은 프로젝트 위치의 규제 요구사항을 준수할 의무가 있기 때문이다 | PM은 고용주의 조직 프로세스 자산(OPA)을 따라야 하기 때문이다 | 부상 또는 손실 사고가 프로젝트 인도물을 지연시킬 수 있기 때문이다 |  | B | 프로젝트 계획에서 건강 및 안전 요구사항이 적절히 다뤄지지 않은 것이 문제인 이유는 PM이 프로젝트 위치의 규제 요구사항을 준수할 의무가 있기 때문이다. 법적 및 윤리적 준수가 PM의 기본 의무이다. 성과 지표(A)는 규제가 아닌 성과이다. OPA(C)는 내부 지침이지 법적 의무가 아니다. 지연(D)은 결과이지 이유가 아니다.
2090 | A project manager has been asked to lead a project. The performing organization does not have a project management office (PMO) or formal governance policies, procedures, and guidelines for this type of project. What should the project manager do first to determine a governance approach for the project? | Consult with team members and stakeholders to determine whether the organization has any informal governance policies procedures, and guidelines | Consult a subject matter expert (SME) as to the best governance policies, procedures, and guidelines to be used by the project | Coach the self-managing team to produce tailored governance policies, procedures and guidelines for the project | Choose either a predictive or agile framework best suited to the nature of the project, and use this framework as the basis for project governance policies, procedures, and guidelines |  | A | Consensus decision-making ensures that all input and perspectives from a group are considered before reaching a final decision acceptable to all participants. This technique relies on respectful dialogue and open-mindedness. By organizing a face-to-face meeting with all stakeholders, the PM facilitates direct communication and collaboration, helping to elicit needs, expectations, and preferences. This process resolves conflicts or contradictions and builds a shared understanding of the project requirements—a critical foundation for successful delivery. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | PM이 프로젝트를 이끌도록 요청받았다. 조직에 PMO가 없고 거버넌스 정책이 수립되지 않았다. PM은 무엇을 먼저 해야 하는가? | 팀원과 이해관계자와 상의하여 조직에 비공식적 거버넌스가 있는지 파악한다 | SME에게 최적의 거버넌스 정책과 절차에 대해 상의한다 | 자체 관리 팀이 프로젝트에 맞는 맞춤형 거버넌스를 생산하도록 코칭한다 | 프로젝트 성격에 가장 적합한 예측형 또는 애자일 프레임워크를 선택하여 사용한다 |  | A | PMO가 없고 거버넌스가 수립되지 않았을 때, PM은 먼저 팀원과 이해관계자와 상의하여 비공식적 거버넌스가 있는지 파악해야 한다. 기존 관행의 이해가 적절한 거버넌스 수립의 기초이다. SME 상의(B)는 내부 상황 파악 후에 한다. 자체 관리(C)는 거버넌스 기초 없이 어렵다. 프레임워크 선택(D)은 거버넌스 이해 후에 한다.
2091 | A company wants to be a pioneer in its industry and has announced the launch date of a new innovative product. After the first sprint planning, the team realizes that it is not possible to deliver all the features in the required time. What should the project manager do to ensure success? | Increase the capacity of the team to deliver the completed backlog on time. | Schedule a meeting with the stakeholders to review the contingency plan. 1021 | Ask the customer to reduce the backlog to meet the launch date. | Assist the team in defining a minimum viable product (MVP) by the launch date. |  | D | When the team realizes after first sprint planning that all features cannot be delivered by the announced launch date for an innovative product, the project manager should assist the team in defining a minimum viable product (MVP) by the launch date. MVP ensures the most critical features launch on time. Increasing team capacity (A) may not be feasible. Reviewing the contingency plan (B) does not directly address scope. Asking the customer to reduce backlog (C) shifts responsibility externally. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 회사가 혁신 제품의 출시 날짜를 발표했다. 첫 스프린트 계획 후 모든 기능을 출시일까지 납품할 수 없음을 팀이 깨달았다. PM은 무엇을 해야 하는가? | 완료된 백로그를 제시간에 납품하기 위해 팀 역량을 증가시킨다 | 이해관계자와 회의하여 비상 계획을 검토한다 | 고객에게 출시일을 맞추기 위해 백로그를 줄이도록 요청한다 | 출시일까지 최소 기능 제품(MVP)을 정의하도록 팀을 지원한다 |  | D | 모든 기능을 출시일까지 납품할 수 없을 때, PM은 팀이 출시일까지 MVP를 정의하도록 지원해야 한다. MVP가 최소한의 필수 기능으로 시장 출시를 가능하게 한다. 역량 증가(A)는 즉각적 해결이 아니다. 비상 계획(B)은 이미 출시일이 정해져 있다. 백로그 축소(C)는 고객 만족을 해친다.
2092 | A project manager is managing a hybrid project. After attending an iteration review, a stakeholder tells the project manager that they are very busy and asks why these reviews are held so frequently. How should the project manager respond? | Explain to the stakeholder that the stakelrolder engagement plan requires their attendance at all reviews | Record the issue in the issue log and escalate the conflict to the project sponsor forassistance | Discuss with the stakeholder the benefits of the hybrid project and how frequent reviews lead to greater value and less rework | Negotiate a reduced review attendance with the stakeholder and update the stakeholder engagement plan to reflect this reduced |  | C | When a busy stakeholder questions the frequency of hybrid project iteration reviews, the project manager should discuss the benefits of the hybrid project approach and explain how frequent reviews lead to greater value and less rework. This educates the stakeholder on the value proposition while respecting their concern. Negotiating reduced attendance (D) compromises review quality. Recording in the issue log and escalating (A) is premature for a manageable conversation. Citing the engagement plan as mandatory (B) sounds rigid and does not address the stakeholder's concern. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 하이브리드 프로젝트의 이터레이션 리뷰 후 이해관계자가 리뷰 빈도가 너무 잦다고 말한다. PM은 무엇을 해야 하는가? | 이해관계자에게 참여 계획상 모든 리뷰 참석이 필요하다고 설명한다 | 이슈 로그에 기록하고 갈등을 스폰서에게 에스컬레이션한다 | 이해관계자에게 하이브리드 프로젝트의 이점과 잦은 리뷰가 더 좋은 결과로 이어지는 방법을 논의한다 | 이해관계자와 리뷰 참석을 줄이고 참여 계획을 업데이트한다 |  | C | 이해관계자가 이터레이션 리뷰 빈도에 의문을 제기할 때, PM은 하이브리드 접근법의 이점과 잦은 리뷰가 더 좋은 결과로 이어지는 방법을 논의해야 한다. 가치 설명이 참여를 촉진한다. 의무 설명(A)은 강압적이다. 에스컬레이션(B)은 과도하다. 참석 감소(D)는 프로젝트 가시성을 해친다.
2093 | One of the team members is consistently absent in team meetings, but always completes their assigned tasks on time. Other team members think this member should attend the meetings. What should the project manager do? | Review and update the project ground rules to make meeting attendance mandatory. | Allow each team member to submit their required tasks on time and reduce the number of scheduled meetings. | Assign this member to facilitate the next meeting to ensure project team collaboration. | Understand the reason for the team member ' s absence and encourage them to attend future meetings. |  | D | When a team member consistently misses meetings but completes tasks on time, the project manager should understand the reason for the absence and encourage them to attend future meetings. Understanding context before enforcing rules demonstrates empathetic leadership. Making attendance mandatory through ground rules (A) is rigid without understanding the situation. Reducing meetings for everyone (B) does not address the specific absence. Assigning them to facilitate (C) forces participation without understanding barriers. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 팀원이 일관되게 회의에 불참하지만 배정된 작업은 항상 제시간에 완료한다. 다른 팀원이 불만이다. PM은 무엇을 해야 하는가? | 프로젝트 기본 규칙을 검토하고 업데이트하여 회의 참석을 의무화한다 | 각 팀원이 요구 작업을 제시간에 제출하게 하고 예정된 회의 수를 줄인다 | 이 팀원에게 다음 회의를 퍼실리테이션하도록 배정하여 협업을 보장한다 | 팀원의 불참 이유를 이해하고 향후 회의 참석을 격려한다 |  | D | 작업은 완료하지만 회의에 불참하는 팀원에 대해, PM은 먼저 불참 이유를 이해하고 향후 참석을 격려해야 한다. 원인 이해가 적절한 대응을 가능하게 한다. 규칙 업데이트(A)는 이유 파악 전에 강압적이다. 회의 축소(B)는 팀 필요를 무시한다. 퍼실리테이션 배정(C)은 강제적이다.
2094 | A project manager is beginning a new project with very diverse team members. The project manager chose to use consensus building so the team can agree on and be engaged in how the project will be executed. How should the project manager proceed? | Create an environment where the agreement is reached by a majority vote. | Establish recurring brainstorming sessions to discuss project issues. | Allow team members to contribute ideas in a stream-of-consciousness mode. | Create an environment where the agreement is reached through discussion. |  | D | When using consensus building with a diverse team, the project manager should create an environment where agreement is reached through discussion. Open dialogue ensures all perspectives are heard and integrated. Majority voting (A) creates winners and losers. Recurring brainstorming sessions (B) generate ideas but do not build consensus. Stream-of-consciousness contribution (C) lacks structure for decision-making. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | Integration & General PM | Process | Develop Integrated PM Plan | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | PM이 매우 다양한 팀원으로 새 프로젝트를 시작한다. 합의 도출 기법을 사용하기로 했다. PM은 무엇을 해야 하는가? | 다수결 투표로 합의에 도달하는 환경을 만든다 | 프로젝트 이슈를 논의하기 위한 정기 브레인스토밍 세션을 수립한다 | 팀원이 의식의 흐름 모드로 아이디어를 기여할 수 있게 한다 | 토론을 통해 합의에 도달하는 환경을 만든다 |  | D | 다양한 팀과 합의 도출을 사용할 때, PM은 토론을 통해 합의에 도달하는 환경을 만들어야 한다. 개방적 대화가 모든 관점을 보장한다. 다수결(A)은 합의가 아닌 투표이다. 브레인스토밍(B)은 아이디어 생성이지 합의가 아니다. 의식의 흐름(C)은 구조가 부족하다.
2095 | During a blueprint review meeting, the finance department representative is not comfortable with a proposed solution that favors another department. As a result, document approval is delayed, which impacts the project schedule. What should the project manager do? | Arrange a meeting with the two departments to understand their differences and address their needs. | Schedule a meeting with the project sponsor to seek advice on the approach of both 176 departments. | Work with the project team to find a compromise solution that suits both departments. | Assess the risk of postponing this specific solution and advise both departments of the delay. |  | A | When a finance department representative is uncomfortable with a proposed solution that favors another department, causing approval delays, the project manager should arrange a meeting with both departments to understand their differences and address their needs. Facilitating direct dialogue among affected stakeholders enables collaborative resolution and moves the approval process forward. Escalating to the sponsor (B) is premature as a first step before attempting direct facilitation. Having the project team develop a compromise independently (C) bypasses the departments' input and may not address their actual concerns. Assessing the risk of postponement (D) focuses on the consequence rather than resolving the root cause of the conflict. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 청사진 검토 회의에서 재무부 대표가 다른 부서에 유리한 제안 솔루션에 불편을 느끼며 승인을 지연시킨다. PM은 무엇을 해야 하는가? | 양 부서와 회의를 주선하여 차이를 이해하고 필요를 다룬다 | 프로젝트 스폰서와 회의하여 양 부서 접근법에 대한 조언을 구한다 | 양 부서에 적합한 타협 솔루션을 찾기 위해 프로젝트 팀과 작업한다 | 이 솔루션 연기의 리스크를 평가하고 양 부서에 지연을 알린다 |  | A | 한 부서가 다른 부서에 유리한 솔루션에 불편을 느낄 때, PM은 양 부서와 회의를 주선하여 차이를 이해하고 필요를 다뤄야 한다. 직접 대화가 상호 이해를 촉진한다. 스폰서 조언(B)은 간접적이다. 팀 타협(C)은 부서 참여가 없다. 리스크 평가(D)는 문제 해결이 아닌 결과 평가이다.
2096 | A company's new communication system will include online dashboard reporting. The executive board might receive bi-weekly performance reports through the online dashboard. What should the project manager do? | Review the project management plan | Review the configuration management plan. | Update the stakeholder engagement plan. | Update the communications management plan |  | D | The PM should update the communications management plan when a new communication system (such as online dashboard reporting) changes the project's communication methods and formats. This ensures project communications align with the new system and stakeholder expectations. The updated plan also helps identify and address potential risks, issues, or challenges from the change—such as compatibility, security, or training requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 회사의 새 커뮤니케이션 시스템에 온라인 대시보드 보고가 포함된다. 경영진이 격주 보고서를 받을 수 있다. PM은 무엇을 업데이트해야 하는가? | 프로젝트 관리 계획을 검토한다 | 구성 관리 계획을 검토한다 | 이해관계자 참여 계획을 업데이트한다 | 커뮤니케이션 관리 계획을 업데이트한다 |  | D | 새 커뮤니케이션 시스템이 커뮤니케이션 방법과 형식을 변경할 때, PM은 커뮤니케이션 관리 계획을 업데이트해야 한다. 이 계획이 프로젝트 커뮤니케이션 요구사항과 방법을 정의한다. 프로젝트 관리 계획(A)은 너무 광범위하다. 구성 관리(B)는 무관하다. 이해관계자 참여(C)는 참여 전략이지 커뮤니케이션 방법이 아니다.
2097 | The team is working on a critical project deliverable and the project manager is concerned about meeting the deadline. There have been complaints from some stakeholders about some of the team members' performance. The project manager wants to understand the situation and provide feedback to the team as soon as possible. What three actions should the project manager take to address this situation? (Choose three) | Request a manager performance review. | Perform a retrospective session | Define team ground rules | Implement daily team meetings. | Conduct an annual review. | B, C, D | When the team is working on a critical deliverable with stakeholder complaints about performance, the project manager should take three actions: define team ground rules to establish shared expectations, perform a retrospective session to reflect on performance and identify improvements, and implement daily team meetings to monitor progress and provide regular feedback. Requesting a manager performance review (A) is not the PM's responsibility. Conducting an annual review (E) is untimely for the urgent situation. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀이 핵심 인도물 작업 중이고 PM이 기한 충족을 우려한다. 이해관계자가 성과에 불만을 제기했다. PM은 무엇을 해야 하는가? (3개 선택) | 관리자 성과 검토를 요청한다 | 회고 세션을 수행한다 | 팀 기본 규칙을 정의한다 | 일일 팀 회의를 실시한다 | 연례 검토를 실시한다 | B, C, D | 핵심 인도물 작업 중 이해관계자가 성과에 불만할 때, PM은 세 가지 조치를 취해야 한다: 공유 기대를 설정하기 위한 팀 기본 규칙 정의(C), 프로세스 개선을 위한 회고 세션 수행(B), 일일 팀 회의 실시(D)로 진행 추적과 장애물 조기 식별. 관리자 성과 검토(A)는 팀 해결 전에 과도하다. 연례 검토(E)는 즉각적 문제 해결에 부적합하다.
2098 | The product team is progressing with a prototyping approach to deliver a multiyear business initiative. A few user stories are taking longer to be delivered. What should the project manager do? | Determine cross-dependencies and plan a spike in the next spont | Determine the risks and identify a resolution during the retrospective meeting | Discover the gaps in the communications management plan and address them accordingly | Inform stakeholders about the delay during project updates |  | A | When user stories take longer to deliver in a prototyping approach, the project manager should determine cross-dependencies and plan a spike in the next sprint. A spike is a time-boxed investigation that helps the team reduce uncertainty, identify technical challenges, and find feasible solutions for complex stories. Identifying risks during the retrospective (B) is reactive. Informing stakeholders about the delay (D) does not address the root cause. Discovering communication plan gaps (C) is unrelated to the user story complexity issue. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로토타이핑 접근법으로 다년 사업 이니셔티브를 진행 중이다. 일부 사용자 스토리가 예상보다 오래 걸린다. PM은 무엇을 해야 하는가? | 교차 종속성을 파악하고 다음 스프린트에 스파이크를 계획한다 | 리스크를 파악하고 회고 회의에서 해결책을 식별한다 | 커뮤니케이션 관리 계획의 격차를 발견하고 적절히 다룬다 | 프로젝트 업데이트 중 이해관계자에게 지연을 알린다 |  | A | 프로토타이핑에서 사용자 스토리가 예상보다 오래 걸릴 때, PM은 교차 종속성을 파악하고 다음 스프린트에 스파이크를 계획해야 한다. 스파이크가 불확실성을 해결하기 위한 시간 제한 조사이다. 회고 해결(B)은 적절하지만 즉각적 기술 조사가 우선이다. 커뮤니케이션 격차(C)는 무관하다. 지연 알림(D)은 조치가 아닌 보고이다.
2099 | A project manager is leading a hybrid project and is collaborating with the client to develop the project contract. Some delays have been experienced due to unforeseen technical difficulties and new dependencies. However, the project manager is optimistic about recovering the delays in the upcoming sprints. A key stakeholder asked the project manager if the contract deadlines can be met. What should the project manager do first? | Study the contract terms and deadlines to ensure they are not under risk and confirm them with the stakeholder. | Clarify the current work progress, causes for delays, existing risks, and planned corrective actions. | Ask the stakeholder to remain calm and confirm that they are participating in all team meetings. | Submit a request for extra time and budget related to the dependencies and technical difficulties. |  | B | When delays have occurred due to technical difficulties and new dependencies, and a stakeholder asks whether contract deadlines can be met, the project manager should first clarify the current work progress, causes for delays, existing risks, and planned corrective actions. Transparency about the project's actual state enables informed discussion and maintains stakeholder trust. Studying contract terms first (A) addresses legalities but does not communicate the project reality. Asking the stakeholder to remain calm (C) is dismissive. Submitting a request for extra time and budget (D) may be necessary later but is premature before providing a clear status assessment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Hybrid/Tailoring | 하이브리드 프로젝트에서 기술적 어려움과 새 종속성으로 지연이 발생했다. 이해관계자가 계약 기한을 맞출 수 있는지 질문한다. PM은 무엇을 해야 하는가? | 계약 조건과 기한이 위험에 처하지 않았는지 확인하고 스폰서와 확인한다 | 현재 작업 진행, 지연 원인, 기존 리스크, 계획된 시정 조치를 명확히 한다 | 이해관계자에게 침착을 유지하고 모든 팀 회의에 참석하고 있는지 확인한다 | 종속성과 기술적 어려움 관련 추가 시간과 예산을 요청한다 |  | B | 기술적 어려움과 종속성으로 지연이 발생하고 이해관계자가 기한을 질문할 때, PM은 현재 진행, 지연 원인, 리스크, 시정 조치를 명확히 해야 한다. 투명한 커뮤니케이션이 신뢰를 구축한다. 계약 확인(A)은 부분적이다. 침착 요청(C)은 비전문적이다. 추가 요청(D)은 현황 파악 후에 한다.
2100 | In a functional organization, a product analyst is assigned to a short-duration application development effort. The analyst expresses concerns about the task and asks the project manager to provide the support of a peer with expertise in this domain. What should the project manager do? | Ask the analyst to use skills to develop the tool, then move development to another team member | Recognize the analyst ' s concerns and reassign the task to another team member | Make sure the analyst has regular pairing meetings with the other team member throughout task execution | Enroll the analyst in a capacity-building program and keep this analyst assigned to the tas k |  | C | When a product analyst in a functional organization expresses concerns about a task and requests peer support, the project manager should ensure the analyst has regular pairing meetings with the other team member throughout execution. Pairing enables knowledge transfer and collaborative learning. Asking the analyst to work alone then reassigning (A) ignores concerns. Reassigning the task entirely (B) wastes the analyst's contribution. Enrolling in a capacity-building program (D) delays immediate support. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 기능 조직에서 제품 분석가가 단기 개발 작업에 배정되었다. 분석가가 작업에 우려를 표명하고 동료 지원을 요청한다. PM은 무엇을 해야 하는가? | 분석가에게 기술을 활용하여 도구를 개발한 후 개발을 다른 팀원에게 이관한다 | 분석가의 우려를 인식하고 작업을 다른 팀원에게 재배정한다 | 작업 실행 전반에 걸쳐 분석가가 다른 팀원과 정기 페어링 회의를 갖도록 한다 | 분석가를 역량 개발 프로그램에 등록하고 작업 배정을 유지한다 |  | C | 제품 분석가가 작업에 우려를 표명하고 동료 지원을 요청할 때, PM은 정기 페어링 회의를 보장해야 한다. 페어 작업이 학습과 자신감을 구축한다. 도구 개발 후 이관(A)은 분석가에게 과부하이다. 재배정(B)은 우려를 다루지만 성장 기회를 빼앗는다. 역량 프로그램(D)은 장기적이다.
2101 | A project manager is leading a complex project. The project stakeholders include individuals from different countries, cultures, and languages. What can the project manager do to manage this diverse group of stakeholders? | Establish one language as the main language for communications and an official time zone for the project. | Perform an analysis to better understand the communication needs and preferences of 1297 each group. | Organize and assign the team members to the project deliverables according to their cultures and languages. | Ask the project management office (PMO) to assign a cultural manager to oversee relations between diverse groups. |  | B | When managing stakeholders from different countries, cultures, and languages, the project manager should perform an analysis to understand communication needs and preferences of each group. Tailored communication improves engagement. Establishing one language and time zone (A) is rigid. Assigning by culture and language (C) is inappropriate. Requesting a cultural manager from the PMO (D) adds unnecessary overhead. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | PM이 복잡한 프로젝트를 이끌고 있다. 이해관계자가 다른 나라, 문화, 언어의 개인을 포함한다. PM은 무엇을 해야 하는가? | 하나의 언어를 주요 커뮤니케이션 언어로, 공식 시간대를 설정한다 | 각 그룹의 커뮤니케이션 필요와 선호를 더 잘 이해하기 위한 분석을 수행한다 | 문화와 언어에 따라 팀원을 프로젝트 인도물에 조직하고 배정한다 | PMO에 다양한 그룹 간 관계를 감독할 문화 관리자 배정을 요청한다 |  | B | 다른 나라, 문화, 언어의 이해관계자를 관리할 때, PM은 각 그룹의 커뮤니케이션 필요와 선호를 이해하기 위한 분석을 수행해야 한다. 맞춤형 커뮤니케이션이 효과적 참여를 보장한다. 단일 언어/시간대(A)는 포용적이지 않다. 문화별 배정(C)은 분리적이다. 문화 관리자(D)는 과도한 구조이다.
2102 | A project manager notices that a product owner has been unresponsive over the last few weeks. During one-on-one sessions, the product owner is unable to provide complete information, leading to rework of the project stories. What should the project manager do first? | Cancel the one-on-one sessions and obtain the information via email. | Increase the sprint duration to accommodate the additional work. | Conduct a root cause analysis before addressing the issue. | Escalate the issue to the stakeholder's functional manager. |  | C | When a product owner is unresponsive and providing incomplete information that causes story rework, the project manager should first conduct a root cause analysis to understand the underlying reason. The cause might be workload, competing priorities, lack of clarity, insufficient product knowledge, or another blocker. Escalating to the functional manager (D) is premature before trying to understand and address the issue directly. Increasing sprint duration (B) treats the symptom by adding time but does not resolve the information gap. Cancelling one-on-ones and switching to email (A) weakens collaboration and may worsen the communication problem. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | PM이 제품 책임자가 최근 몇 주간 반응이 없음을 발견했다. 일대일 세션에서 불완전한 정보를 제공하여 스토리 재작업이 발생한다. PM은 무엇을 해야 하는가? | 일대일 세션을 취소하고 이메일로 정보를 얻는다 | 추가 작업을 수용하기 위해 스프린트 기간을 늘린다 | 문제를 다루기 전에 근본 원인 분석을 실시한다 | 이슈를 이해관계자의 기능 관리자에게 에스컬레이션한다 |  | C | 제품 책임자가 반응이 없고 불완전한 정보로 재작업이 발생할 때, PM은 먼저 근본 원인 분석을 실시해야 한다. 근본 원인 이해가 적절한 대응의 기초이다. 이메일 전환(A)은 커뮤니케이션을 악화시킨다. 스프린트 연장(B)은 문제를 해결하지 않는다. 에스컬레이션(D)은 원인 파악 후에 한다.
2103 | A project manager was replaced in the early phases of a new project. The new project manager discovers that the business team is not supporting the project. After discussing these concerns with the team, it is determined that the project does not have the full support of senior management. What should the new project manager do next? | Send out a status report describing the situation to the stakeholders and request general assistance. | Request the business team to clearly define their issues with the project work completed to date. | Study the stakeholder analysis to understand which stakeholder holds the most influence and seek their assistance. | Ask senior management to be more involved with the project and to provide their full support. |  | C | When the business team does not support the project due to lack of senior management backing, the new project manager should study the stakeholder analysis to identify the most influential stakeholder and seek their assistance. Leveraging influence gains support. Sending a status report requesting help (A) is passive. Asking the business team to define issues (B) focuses on symptoms. Asking senior management directly (D) may be possible but targeted influence is more effective. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | PM이 새 프로젝트 초기에 교체되었다. 새 PM이 사업 팀이 고위 경영진 지원 부족으로 프로젝트를 지지하지 않음을 발견했다. PM은 무엇을 해야 하는가? | 상황을 설명하는 상태 보고서를 이해관계자에게 보내고 일반적 지원을 요청한다 | 사업 팀에게 지금까지 완료된 프로젝트 작업에 대한 이슈를 명확히 정의하도록 요청한다 | 이해관계자 분석을 연구하여 가장 영향력 있는 이해관계자를 파악하고 지원을 구한다 | 고위 경영진에게 프로젝트에 더 참여하고 전적인 지원을 제공하도록 요청한다 |  | C | 사업 팀이 고위 경영진 지원 부족으로 프로젝트를 지지하지 않을 때, PM은 이해관계자 분석을 연구하여 가장 영향력 있는 이해관계자를 파악하고 지원을 구해야 한다. 핵심 영향력자 파악이 효과적 지원 확보의 기초이다. 상태 보고(A)는 일방적이다. 이슈 정의(B)는 지원 부족 자체를 다루지 않는다. 경영진 요청(D)은 전략적이지 않다.
2104 | A new agile project is starting. The project manager is asked to confirm the scope to address the concerns of one of the stakeholders. What should the project manager use to explain the project scope? | Business requirements document | Product roadmap | Product backlog | User stories |  | D | In agile projects, user stories are a primary tool for defining and communicating project scope. They take a user-centric approach, describing functionality from the end-user's perspective. Their concise, simple format makes them easily understandable by both technical and non-technical stakeholders, providing an effective way to explain scope to concerned stakeholders. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 새 애자일 프로젝트가 시작된다. PM이 이해관계자 우려를 다루기 위해 범위를 확인하도록 요청받았다. 어떤 도구를 사용해야 하는가? | 사업 요구사항 문서 | 제품 로드맵 | 제품 백로그 | 사용자 스토리 |  | D | 애자일 프로젝트에서 범위를 확인할 때, 사용자 스토리가 주요 도구이다. 사용자 스토리는 최종 사용자 관점에서 기능을 설명하는 사용자 중심 접근법이다. 사업 요구사항 문서(A)는 예측형에 적합하다. 로드맵(B)은 전략적 수준이다. 백로그(C)는 스토리의 집합이지만 개별 범위 확인에는 스토리가 적합하다.
2105 | A project management team received news that a competitor has released the latest version of a program. What should the team do next? | Stop the project immediately as the market opportunity has already been missed. | Review the project plan to evaluate if any updates should be made. | Crash the existing schedule with additional resources to deliver more features. | Continue with the project plan and target delivery date as expected. |  | B | When a competitor releases a new program version, the project team should review the project plan to evaluate if any updates should be made. Assessing competitive impact on objectives and deliverables enables informed decisions. Stopping the project (A) is extreme. Crashing the schedule (C) adds cost without analysis. Continuing as planned (D) ignores the competitive landscape. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리 팀이 경쟁사가 프로그램 최신 버전을 출시했다는 소식을 받았다. PM은 무엇을 해야 하는가? | 시장 기회를 이미 놓쳤으므로 프로젝트를 즉시 중단한다 | 프로젝트 계획을 검토하여 업데이트가 필요한지 평가한다 | 추가 기능을 납품하기 위해 추가 자원으로 기존 일정을 크래싱한다 | 프로젝트 계획과 목표 납품일을 예정대로 계속한다 |  | B | 경쟁사가 새 버전을 출시했을 때, PM은 프로젝트 계획을 검토하여 업데이트가 필요한지 평가해야 한다. 경쟁 영향 평가가 목표와 인도물에 미치는 영향을 파악한다. 즉시 중단(A)은 과도한 반응이다. 크래싱(C)은 비용과 리스크가 높다. 예정대로(D)는 시장 변화를 무시한다.
2106 | A project is in its fourth iteration out of eight, with a delivery performance of 95%. A project stakeholder asks the project manager about the status of a specific deliverable that is not visible in the status report. What should the project manager do? | Invite the stakeholder to the next daily meeting. | Schedule a meeting with the stakeholder to review the status report. | Include the deliverable in the status report and resend it to the stakeholder. | Invite the stakeholder to the next iteration review. |  | B | When a stakeholder inquires about a deliverable not visible in the status report, the PM should meet directly with the stakeholder to review the report together. This identifies whether the gap lies in the report content, format, or the stakeholder's expectations. Direct engagement addresses the concern at its source and improves future reporting quality. Iteration reviews (A) are too broad for this specific issue. Simply resending a revised report (B) doesn't confirm the stakeholder's actual needs. Internal team meetings (C) aren't appropriate for stakeholder communication. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Traditional PM | 프로젝트가 8번째 이터레이션 중 4번째에 있으며 납품 성과가 95%이다. 이해관계자가 상태 보고서에 보이지 않는 인도물에 대해 문의한다. PM은 무엇을 해야 하는가? | 이해관계자를 다음 데일리 미팅에 초대한다 | 이해관계자와 회의를 잡아 상태 보고서를 검토한다 | 인도물을 상태 보고서에 포함하고 이해관계자에게 재전송한다 | 이해관계자를 다음 이터레이션 검토에 초대한다 |  | B | 이해관계자가 상태 보고서에 보이지 않는 인도물에 대해 문의할 때, PM은 이해관계자와 직접 회의하여 보고서를 함께 검토해야 한다. 이는 격차가 보고에 있는지 이해에 있는지 식별한다. 데일리 미팅 초대(A)는 적절한 포럼이 아니다. 단순 재전송(C)은 근본 문제를 해결하지 않는다. 이터레이션 검토(D)는 대기 시간이 길다.
2107 | A project scope was developed with numerous assumptions. During the execution phase, the assumptions changed, which has jeopardized the planned business value of the project. What should the project manager do next? | Report on the changed assumptions to the project sponsor and seek support to prioritize the change requests. | Deliver what was planned in the project management document according to the specifications. | Update the assumptions log and change log, and implement the change control process. | Inform the client that the project cannot meet the project timeline and additional costs will be incurred. |  | C | When project assumptions change during execution jeopardizing planned business value, the project manager should update the assumptions log and change log, and implement the change control process. Formal documentation and change control ensure assessed and managed responses. Reporting to the sponsor (A) informs but does not drive process. Delivering according to original specifications (B) ignores the changed reality. Informing the client of delays and costs (D) is premature before change assessment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 범위가 다수의 가정으로 개발되었다. 실행 단계에서 가정이 변경되어 사업 가치가 위험에 처했다. PM은 무엇을 해야 하는가? | 변경된 가정을 스폰서에게 보고하고 변경 요청 우선순위화 지원을 구한다 | 프로젝트 관리 문서에 따라 계획대로 납품한다 | 가정 로그와 변경 로그를 업데이트하고 변경 통제 프로세스를 실행한다 | 고객에게 프로젝트 일정을 맞출 수 없고 추가 비용이 발생한다고 알린다 |  | C | 프로젝트 가정이 실행 중 변경되어 사업 가치가 위태로울 때, PM은 가정 로그와 변경 로그를 업데이트하고 변경 통제 프로세스를 실행해야 한다. 공식 변경 관리가 통제된 대응을 보장한다. 스폰서 보고(A)는 변경 통제 후에 한다. 계획대로 납품(B)은 변경을 무시한다. 고객 통보(D)는 시기상조이다.
2108 | Due to an anticipated expansion, a company procured new technology. The project team responsible for using this technology does not have experience with it. What should the project manager do? | Hire project resources with experience using the new technology. | Request incentives for the team to use the new technology. | Propose training for the project team in batches on the new technology. | Assess the benefit of using new technology versus old technology. |  | C | The PM should propose training for the project team in batches on the new technology. This addresses the root cause—lack of familiarity with the technology—while minimizing disruption to ongoing project work. Batch training allows the team to learn progressively without halting project progress entirely. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Agile General Practices | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 예상 확장으로 인해 회사가 새 기술을 조달했다. 프로젝트 팀이 이 기술에 대한 전문성이 부족하다. PM은 무엇을 해야 하는가? | 새 기술 사용 경험이 있는 프로젝트 자원을 채용한다 | 팀이 새 기술을 사용하도록 인센티브를 요청한다 | 프로젝트 팀을 배치별로 새 기술에 대해 교육하도록 제안한다 | 새 기술 대비 기존 기술 사용의 이점을 평가한다 |  | C | PM은 프로젝트 팀을 배치별로 새 기술에 대해 교육하도록 제안해야 한다. 이는 근본 원인인 기술 친숙도 부족을 해결하면서 진행 중인 프로젝트에 최소한의 혼란을 준다. 채용(A)은 비용이 높고 시간이 걸린다. 인센티브(B)는 역량이 아닌 동기만 다룬다. 기술 비교(D)는 이미 조달한 후에는 늦다.
2109 | A project manager is assigned to a digital transformation project for a bank. The company culture is conservative and resistant to transformation or innovation. What should the project manager do first to support the transformation? | Hire an expert in digital transformation and assign that person as the champion for the change | Ask the bank executives to officially announce that the project manager is leading the project | Provide a digital transformation guide and explain that the change is unavoidable | Provide proper training sessions to the stakeholders so they understand the purpose of the change |  | D | When assigned to a digital transformation project in a conservative, change-resistant culture, the project manager should first provide proper training sessions to stakeholders so they understand the purpose of the change. Building understanding alleviates resistance and fosters acceptance. Hiring a digital transformation expert (A) adds expertise but does not directly address cultural resistance. Asking executives to announce the PM's role (B) establishes authority, not acceptance. Providing a guide and explaining inevitability (C) is informational but not interactive. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Governance | Executing | Focus on Value | Manage Project Knowledge | Digital Transformation | PM이 보수적이고 변화에 저항하는 은행의 디지털 전환 프로젝트에 배정되었다. PM은 무엇을 먼저 해야 하는가? | 디지털 전환 전문가를 고용하여 변화의 챔피언으로 지정한다 | 은행 경영진에게 PM이 프로젝트를 이끌고 있다고 공식 발표하도록 요청한다 | 디지털 전환 가이드를 제공하고 변화가 불가피하다고 설명한다 | 이해관계자에게 적절한 교육 세션을 제공하여 변화의 목적을 이해하게 한다 |  | D | 보수적이고 변화에 저항하는 문화에서 디지털 전환 프로젝트를 수행할 때, PM은 먼저 이해관계자에게 적절한 교육 세션을 제공하여 변화의 목적을 이해하게 해야 한다. 교육이 이해와 수용을 구축한다. 전문가 고용(A)은 조직 수용을 보장하지 않는다. 공식 발표(B)는 권위에만 의존한다. 가이드 제공(C)은 일방적이다.
2110 | A multinational company is launching a company-wide digital transformation project that covers all of its regions and business lines. The project is expected to go through five phases and finish in 2 years. The project manager schedules a kick-off meeting. What should the project manager do next? | Ensure there is enough budget to mandate all team members to fly to corporate headquarters for the kick-off meeting. | Document the kick-off meeting and close out the planning phase after the meeting is held. | Consider using digital or virtual tools to conduct the kick-off meeting to minimize geographic boundaries. | Limit to one kick-off meeting in the project ' s first phase in order to control the budget. |  | C | For a global digital transformation project, the kick-off meeting should leverage digital or virtual tools to enable participation across all regions and business lines. This cost-effective approach minimizes geographic barriers, fosters collaboration without requiring travel, and aligns with the project's digital nature. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Digital Transformation | 다국적 회사가 모든 지역과 사업부를 포괄하는 전사적 디지털 전환 프로젝트를 시작한다. 킥오프 회의를 어떻게 진행해야 하는가? | 모든 팀원이 본사로 비행하도록 충분한 예산을 확보한다 | 킥오프 회의를 문서화하고 회의 후 계획 단계를 종료한다 | 지리적 경계를 최소화하기 위해 디지털 또는 가상 도구를 사용하여 킥오프 회의를 진행한다 | 예산 통제를 위해 프로젝트 첫 단계에서 킥오프 회의를 하나로 제한한다 |  | C | 글로벌 디지털 전환 프로젝트의 킥오프 회의는 디지털 또는 가상 도구를 활용하여 모든 지역에서 참여할 수 있도록 해야 한다. 비용 효율적이며 포괄적 참여를 가능하게 한다. 본사 비행(A)은 비용이 과도하다. 문서화만(B)은 참여가 아니다. 회의 제한(D)은 포괄적 참여를 방해한다.
2111 | A project manager is assigned to a new water treatment plant project that has been delayed for many years. It is revealed in the project charter that the sponsors of this project are from three different business units. This is the first time the sponsors have ever implemented such a project. What should the project manager do? | Establish mentoring and coaching sessions. | Review the knowledge repository for similar projects. | Meet with the project sponsors to align expectations | Schedule the project kick-off meeting immediately. |  | C | Meeting with project sponsors to align expectations is the PM's first priority when sponsors come from different business units with different perspectives. This establishes trust, communication, and collaboration around project objectives, scope, deliverables, risks, assumptions, and constraints. The PM should also review the project charter and stakeholder register to clarify roles and responsibilities. Mentoring sessions, knowledge repository reviews, and kick-off meeting scheduling are important but secondary activities. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | PM이 수년간 지연된 새 수처리 시설 프로젝트에 배정되었다. 스폰서들이 다른 사업부에서 왔다. PM은 무엇을 먼저 해야 하는가? | 멘토링 및 코칭 세션을 설정한다 | 유사 프로젝트의 지식 저장소를 검토한다 | 프로젝트 스폰서와 만나 기대를 정렬한다 | 프로젝트 킥오프 회의를 즉시 일정에 잡는다 |  | C | 스폰서들이 다른 사업부에서 와서 다른 관점을 가질 때, PM은 먼저 프로젝트 스폰서와 만나 기대를 정렬해야 한다. 이는 신뢰, 소통, 공유 비전을 수립한다. 멘토링(A)은 팀 개발이지 스폰서 정렬이 아니다. 지식 검토(B)는 유용하지만 스폰서 정렬이 우선이다. 킥오프(D)는 기대 정렬 후에 한다.
2112 | A team is currently working on a mobile app solution. During sprint execution, one of the developers requires clarification about the acceptance criteria for a particular task. What should the project manager do to obtain the information required by the developer? | Request direction from the project sponsor | Work with the product owner to clarify the requirement | Write an email to the client requesting clarification | Seek support from the development manager. |  | B | When a developer needs clarification about acceptance criteria during sprint execution, the project manager should work with the product owner to clarify the requirement. The product owner owns requirements and acceptance criteria. Requesting direction from the sponsor (A) escalates unnecessarily. Writing an email to the client (C) bypasses the product owner. Seeking support from the development manager (D) addresses the wrong authority. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 팀이 모바일 앱 솔루션을 작업 중이다. 스프린트 실행 중 개발자가 인수 기준에 대한 명확화가 필요하다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 방향을 요청한다 | 제품 책임자와 협력하여 요구사항을 명확히 한다 | 고객에게 명확화를 요청하는 이메일을 작성한다 | 개발 관리자에게 지원을 구한다 |  | B | 스프린트 실행 중 개발자가 인수 기준 명확화가 필요할 때, PM은 제품 책임자와 협력하여 요구사항을 명확히 해야 한다. 제품 책임자가 요구사항을 소유한다. 스폰서 요청(A)은 적절한 역할이 아니다. 고객 이메일(C)은 우회적이다. 개발 관리자(D)는 요구사항 소유자가 아니다.
2113 | During a sprint planning, the development lead highlights the importance of working on technical debt tasks that are critical for the product performance. However, the tasks will consume most of the team's capacity and they will not be able to work on product feature development. What should the project manager do? | Add the technical debt tasks to the sprint backlog. | Ask the sponsor for more resources to continue at the same pace. | Work on the features already prioritized by the product owner. | Invite technical stakeholders for backlog prioritization. |  | A | When the development lead identifies critical technical debt affecting product performance, the project manager should add those tasks to the sprint backlog. In Agile, the product backlog encompasses not only features but also technical work such as bug fixes and technical debt reduction that are essential for long-term product health and sustainability. The Product Owner is responsible for prioritizing the backlog, and if technical debt is critical for performance, it must be addressed even at the expense of new feature development. Asking the sponsor for more resources (B) does not solve the prioritization issue. Working only on features already prioritized by the Product Owner (C) ignores the technical necessity. Inviting technical stakeholders for backlog prioritization (D) may be helpful but is not the most direct action—the development lead has already identified the critical need during sprint planning. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Integrate Sustainability | Develop Schedule | Sustainability | 스프린트 계획 중 개발 리드가 제품 성능에 중요한 기술 부채 작업의 중요성을 강조한다. PM은 무엇을 해야 하는가? | 기술 부채 작업을 스프린트 백로그에 추가한다 | 스폰서에게 같은 속도를 유지하기 위해 더 많은 자원을 요청한다 | 제품 책임자가 이미 우선순위화한 기능에 대해 작업한다 | 기술 이해관계자를 백로그 우선순위화에 초대한다 |  | A | 개발 리드가 제품 성능에 영향을 미치는 중요 기술 부채를 식별할 때, PM은 해당 작업을 스프린트 백로그에 추가해야 한다. 애자일에서 제품 백로그는 기술 부채를 포함한다. 자원 요청(B)은 당면 문제를 해결하지 않는다. 기존 기능만 작업(C)은 기술 부채를 무시한다. 이해관계자 초대(D)는 이미 명확한 작업에 불필요하다.
2114 | A key stakeholder is refusing to participate in a crucial project stage and disagrees with the project team's approach. This situation is affecting the project team's morale. What should the project manager do? | Ask the project sponsor to meet with the project team and key stakeholder to discuss the approach. | Schedule a meeting with the project team and the key stakeholder as soon as possible to discuss and agree on an approach. | Ask the project team to meet and document why the stakeholder ' s approach is incorrect. | Discuss the issue with the project team during a project status meeting and request that they change the approach. |  | B | When a key stakeholder refuses to participate and disagrees with the project team's approach, affecting team morale, the project manager should schedule a meeting with the team and stakeholder as soon as possible to discuss and agree on an approach. Open dialogue resolves disagreements. Asking the sponsor to meet (A) escalates before attempting direct resolution. Documenting why the stakeholder is incorrect (C) is confrontational. Requesting the team change their approach (D) undermines the team. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 주요 이해관계자가 핵심 프로젝트 단계 참여를 거부하고 팀의 접근법에 동의하지 않는다. 팀 사기에 영향을 미친다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 팀과 주요 이해관계자와 회의하여 접근법을 논의하도록 요청한다 | 팀과 주요 이해관계자와 가능한 빨리 회의를 잡아 합의에 도달한다 | 프로젝트 팀에게 이해관계자의 접근법이 왜 잘못되었는지 문서화하도록 요청한다 | 프로젝트 상태 회의에서 팀과 이슈를 논의하고 접근법을 변경하도록 요청한다 |  | B | 주요 이해관계자가 참여를 거부하고 팀 사기에 영향을 미칠 때, PM은 팀과 이해관계자 간 가능한 빨리 회의를 잡아 합의에 도달해야 한다. 직접 대화가 갈등을 해결한다. 스폰서 요청(A)은 에스컬레이션 전에 직접 해결이 우선이다. 문서화(C)는 대립적이다. 팀에게 변경 요청(D)은 이해관계자를 배제한다.
2115 | An organization that is running several simultaneous projects suddenly experiences a surge of resignations, leading to a lack of talent. Consequently, some of the projects have been missing key milestones. What should the project manager do to recover from the delays? | Crash the schedule from the delayed projects to meet upcoming target dates. | Fast-track the delayed projects so they can meet upcoming target dates. | Reduce the projects' scope to meet the upcoming target dates. | Ask for project sponsor approval to revise the upcoming target dates. |  | C | Mass resignations create a resource constraint that reduces delivery capacity across projects. The most practical recovery action is scope reduction—reprioritizing work to align with available capacity while protecting the most critical milestones. Crashing (B) requires adding resources that aren't available during a talent shortage. Fast-tracking (C) increases parallel work and coordination risk with insufficient staffing. Revising target dates (D) may be needed eventually but should follow scope optimization as the primary recovery strategy. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 여러 프로젝트를 동시에 진행하는 조직에서 대규모 퇴사가 발생하여 자원 위기가 생겼다. PM은 무엇을 해야 하는가? | 지연된 프로젝트의 일정을 크래싱하여 목표일을 맞춘다 | 지연된 프로젝트를 패스트트래킹하여 목표일을 맞춘다 | 프로젝트 범위를 줄여 목표일을 맞춘다 | 프로젝트 스폰서 승인을 받아 목표일을 수정한다 |  | C | 대규모 퇴사로 자원 제약이 생기면 납품 역량이 감소한다. 가장 실용적인 복구 조치는 범위 축소—가용 역량에 맞게 작업을 재우선순위화하는 것이다. 크래싱(A)은 추가 자원이 필요하지만 없다. 패스트트래킹(B)은 리스크를 증가시킨다. 목표일 수정(D)은 가능하지만 범위 축소가 더 직접적이다.
2116 | During the third iteration, the team encounters a major delay that has not had significant improvements over the last few weeks. What should the project manager do? | Incorporate a predictive approach for this element. | Implement mitigation strategies for this element | Request additional team members to help with improvements | Retrospect frequently and suggest improvements. |  | D | The correct answer is D. Retrospect frequently and suggest improvements. In agile environments, the PM should facilitate team collaboration, remove impediments, and ensure continuous value delivery while adhering to agile principles. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 세 번째 이터레이션에서 팀이 지난 몇 번의 이터레이션 동안 크게 개선되지 않은 주요 지연을 겪고 있다. PM은 무엇을 해야 하는가? | 이 요소에 대해 예측형 접근법을 적용한다 | 이 요소에 대한 완화 전략을 구현한다 | 개선을 돕기 위해 추가 팀원을 요청한다 | 자주 회고하고 개선 사항을 제안한다 |  | D | 정답은 D이다. 자주 회고하고 개선 사항을 제안한다. 애자일 환경에서 PM은 팀 협업을 촉진하고 장애물을 제거하며 지속적 가치 전달을 보장해야 한다. 회고가 지속적 개선의 핵심이다. 예측형 접근(A)은 애자일 원칙에 반한다. 완화 전략(B)은 구체적이지 않다. 추가 인력(C)은 근본 원인을 해결하지 않는다.
2117 | The project team follows a hybrid framework for its delivery. During the execution of a project, the team learns of a new compliance requirement that has to be delivered before any other requirements. How should the project manager address this situation? | Collaborate with the compliance team member to review and prioritize the requirement's delivery | Ask the team to include the compliance requirement in the current sprint and deliver it. | Add the new compliance requirement to the backlog as the technical team does not have any capacity. | Include the compliance lead in the stakeholders list and wait for the next status meeting |  | A | When a new compliance requirement must be delivered before any other requirements in a hybrid project, the project manager should collaborate with the compliance team member to review and prioritize the requirement's delivery. This ensures proper change management, regulatory alignment, and stakeholder communication about the impact on scope, schedule, and cost. Asking the team to include it in the current sprint (B) disrupts sprint planning and may create scope creep. Adding it to the backlog without capacity consideration (C) delays a mandatory requirement. Including the compliance lead in the stakeholders list and waiting for the next meeting (D) fails to address the urgency and importance of the requirement. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 하이브리드 프레임워크를 따른다. 실행 중 새 컴플라이언스 요구사항이 다른 모든 요구사항보다 먼저 전달되어야 한다. PM은 무엇을 해야 하는가? | 컴플라이언스 팀원과 협력하여 요구사항의 전달을 검토하고 우선순위화한다 | 팀에게 현재 스프린트에 컴플라이언스 요구사항을 포함하여 전달하도록 요청한다 | 기술 팀이 역량이 없으므로 새 컴플라이언스 요구사항을 백로그에 추가한다 | 컴플라이언스 리드를 이해관계자 목록에 포함하고 다음 상태 회의를 기다린다 |  | A | 하이브리드 프로젝트에서 새 컴플라이언스 요구사항이 최우선으로 전달되어야 할 때, PM은 컴플라이언스 팀원과 협력하여 요구사항의 전달을 검토하고 우선순위화해야 한다. 협력적 우선순위화가 적절한 통합을 보장한다. 현재 스프린트 포함(B)은 검토 없이 성급하다. 백로그 추가(C)는 긴급성을 무시한다. 다음 회의 대기(D)는 너무 늦다.
2118 | The project manager is reviewing the program risks and issues with key stakeholders. One of the stakeholders wants to understand when the risk may potentially become an issue. What artifact should the project manager share with the stakeholder? | Risk management plan | Issue log | Risk register | Project management plan |  | C | The risk register is the artifact that shows when a risk may potentially become an issue. It records identified risks along with their probability, impact, status, response plans, and—critically—risk triggers, which are indicators or warning signs that a risk is about to occur. By reviewing the risk register, the stakeholder can understand the conditions under which each risk would materialize into an issue. The risk management plan (A) describes the processes and methodology for managing risks but does not track individual risk triggers. The issue log (B) records problems that have already occurred, not potential future risks. The project management plan (D) is a comprehensive document that does not specifically address risk timing. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 주요 이해관계자와 프로그램 리스크와 이슈를 검토 중이다. 이해관계자가 리스크가 언제 이슈가 될 수 있는지 알고 싶어 한다. 어떤 산출물을 참조해야 하는가? | 리스크 관리 계획 | 이슈 로그 | 리스크 등록부 | 프로젝트 관리 계획 |  | C | 리스크 등록부는 리스크가 언제 잠재적으로 이슈가 될 수 있는지 보여주는 산출물이다. 식별된 리스크와 함께 확률, 영향, 상태, 대응 계획, 그리고 중요하게 리스크 트리거를 기록한다. 리스크 관리 계획(A)은 프로세스이지 리스크 데이터가 아니다. 이슈 로그(B)는 이미 발생한 이슈만 다룬다. 프로젝트 관리 계획(D)은 너무 광범위하다.
2119 | Due to delays on some activities, one of the project team members has increased the scope without any approval. What should the project manager do next? | Remove the changes to match the original requirements. | Update project documentation with the new scope | Evaluate the impacts of the changes that were made to the project | Add team members to the project to avoid more schedule delays. |  | C | When a team member has increased scope without approval due to delays, the project manager should evaluate the impacts of the unauthorized changes. Impact assessment enables informed decisions. Removing changes to match original requirements (A) may not be optimal. Updating documentation with the new scope (B) legitimizes unapproved changes. Adding team members (D) treats the symptom, not the cause. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 일부 활동의 지연으로 팀원 중 한 명이 승인 없이 범위를 확대했다. PM은 무엇을 해야 하는가? | 원래 요구사항에 맞도록 변경을 제거한다 | 새 범위로 프로젝트 문서를 업데이트한다 | 프로젝트에 대한 변경의 영향을 평가한다 | 더 많은 일정 지연을 피하기 위해 팀원을 추가한다 |  | C | 팀원이 지연으로 인해 승인 없이 범위를 확대했을 때, PM은 비승인 변경의 영향을 평가해야 한다. 영향 평가가 정보에 기반한 결정을 가능하게 한다. 변경 제거(A)는 평가 없이 작업을 되돌린다. 문서 업데이트(B)는 승인 없이 변경을 수용한다. 팀원 추가(D)는 범위 문제를 다루지 않는다.
2120 | A project manager is leading a software development project. The team suggests using an AI-powered tool to automate code reviews and identify potential defects. What should the project manager do FIRST? | Reject the suggestion because AI tools are unreliable for code quality. | Immediately implement the AI tool across all codebases. | Evaluate the AI tool's accuracy, data privacy implications, and alignment with organizational policies before implementation. | Delegate the decision entirely to the development team lead. |  | C | Before implementing any AI tool, a project manager should conduct a thorough evaluation of its accuracy, data privacy implications, and alignment with organizational policies. The PMBOK 8th Edition emphasizes that AI integration requires ethical considerations and governance oversight. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PM이 소프트웨어 개발 프로젝트를 이끌고 있다. 팀이 코드 리뷰를 자동화하기 위해 AI 도구를 사용하자고 제안한다. PM은 무엇을 해야 하는가? | AI 도구가 코드 품질에 신뢰할 수 없으므로 제안을 거부한다 | 즉시 모든 코드베이스에 AI 도구를 구현한다 | AI 도구의 정확성, 데이터 프라이버시 영향, 조직 정책과의 정렬을 평가한다 | 결정을 전적으로 개발 팀 리더에게 위임한다 |  | C | AI 도구를 구현하기 전에 PM은 정확성, 데이터 프라이버시 영향, 조직 정책과의 정렬을 철저히 평가해야 한다. PMBOK 8판은 신기술 도입 시 평가와 거버넌스를 강조한다. 거부(A)는 잠재적 이점을 무시한다. 즉시 구현(B)은 리스크 평가 없이 진행한다. 위임(D)은 PM의 거버넌스 책임을 회피한다.
2121 | A project team is using AI-based predictive analytics to forecast project schedule risks. The AI model predicts a 78% probability of a 3-week delay in the critical path. What should the project manager do? | Use the AI prediction as an input to risk response planning, combining it with expert judgment and historical data. | Ignore the AI prediction and rely solely on the team's expert judgment. | Report the delay to the sponsor without any mitigation plan. | Immediately extend the project timeline by 3 weeks. |  | A | AI-based predictive analytics should be used as one input among several in decision-making, not as the sole determinant. The PMBOK 8th Edition advocates combining AI insights with expert judgment and historical data for risk response planning. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | AI | 프로젝트 팀이 AI 기반 예측 분석을 사용하여 일정 리스크를 예측한다. AI 모델이 핵심 인도물에 78% 확률로 3주 지연을 예측한다. PM은 무엇을 해야 하는가? | AI 예측을 리스크 대응 계획의 입력으로 사용하되 전문가 판단 및 과거 데이터와 결합한다 | AI 예측을 무시하고 팀의 전문가 판단에만 의존한다 | 완화 계획 없이 스폰서에게 지연을 보고한다 | 즉시 프로젝트 일정을 3주 연장한다 |  | A | AI 기반 예측 분석은 의사결정의 유일한 결정 요소가 아닌 여러 입력 중 하나로 사용해야 한다. PMBOK 8판은 AI 통찰을 전문가 판단 및 과거 데이터와 결합하는 것을 권장한다. 무시(B)는 유용한 데이터를 낭비한다. 완화 없는 보고(C)는 비전문적이다. 즉시 연장(D)은 과도한 반응이다.
2122 | An organization wants to use a generative AI tool to draft project charters and scope documents. What is the MOST important consideration for the project manager? | The cost savings from reducing manual documentation effort. | Training only the project manager to use the AI tool. | The speed at which the AI generates documents. | Ensuring human review and validation of all AI-generated content for accuracy, completeness, and organizational alignment. |  | D | When using generative AI for project documentation, human oversight is critical. AI-generated content must be reviewed for accuracy, completeness, and alignment with organizational standards and stakeholder expectations. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | 조직이 프로젝트 헌장과 범위 문서 초안 작성에 생성형 AI 도구를 사용하려 한다. 가장 중요한 고려사항은 무엇인가? | 수동 문서화 노력 감소로 인한 비용 절감 | PM만 AI 도구 사용법을 교육하기 | AI가 문서를 생성하는 속도 | 정확성, 완전성, 조직 표준 및 이해관계자 기대와의 정렬을 위한 모든 AI 생성 콘텐츠의 인간 검토 및 검증 보장 |  | D | 생성형 AI를 프로젝트 문서에 사용할 때 인간 감독이 중요하다. AI 생성 콘텐츠는 정확성, 완전성, 조직 표준 및 이해관계자 기대와의 정렬을 위해 검토되어야 한다. 비용 절감(A)은 부차적 이점이다. PM만 교육(B)은 팀 역량을 제한한다. 속도(C)는 품질보다 중요하지 않다.
2123 | A project manager notices that team members are resistant to adopting a new AI-powered project management dashboard. What is the BEST approach? | Mandate the use of the AI dashboard and set a compliance deadline. | Understand the team's concerns, provide training, demonstrate the dashboard's benefits, and allow a transition period. | Abandon the AI dashboard implementation to maintain team morale. | Remove the old tools immediately to force adoption. |  | B | Resistance to new technology should be addressed through change management best practices. Understanding concerns, providing adequate training, demonstrating tangible benefits, and allowing a transition period are key to successful adoption. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Acquire Resources | AI | PM이 팀원들이 새 AI 기반 프로젝트 관리 대시보드 도입에 저항하고 있음을 발견한다. PM은 무엇을 해야 하는가? | AI 대시보드 사용을 의무화하고 준수 기한을 설정한다 | 팀의 우려를 이해하고 교육을 제공하며 대시보드의 이점을 시연하고 전환 기간을 허용한다 | 팀 사기를 유지하기 위해 AI 대시보드 구현을 포기한다 | 강제 도입을 위해 기존 도구를 즉시 제거한다 |  | B | 새 기술에 대한 저항은 변화 관리 모범 사례를 통해 해결해야 한다. 우려 이해, 충분한 교육 제공, 실질적 이점 시연, 전환 기간 허용이 효과적이다. 의무화(A)는 저항을 증가시킨다. 포기(C)는 잠재적 이점을 잃는다. 기존 도구 제거(D)는 강압적이다.
2124 | During sprint planning, a team member suggests using an AI algorithm to prioritize the product backlog based on customer sentiment analysis. The product owner is concerned about losing control of prioritization. What should the project manager recommend? | Ignore the suggestion and continue with manual prioritization only. | Let the team vote on whether to use AI or not. | Use AI sentiment analysis as supplementary data to inform the product owner's prioritization decisions. | Allow the AI to fully control backlog prioritization to improve objectivity. |  | C | AI should augment, not replace, human decision-making. Using AI sentiment analysis as supplementary data empowers the product owner with additional insights while maintaining their authority over prioritization. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | 스프린트 계획 중 팀원이 고객 감성 데이터에 기반한 AI 알고리즘으로 제품 백로그를 우선순위화하자고 제안한다. PM은 무엇을 해야 하는가? | 제안을 무시하고 수동 우선순위화만 계속한다 | AI 사용 여부에 대해 팀 투표를 실시한다 | AI 감성 분석을 제품 책임자의 우선순위화 결정을 알리는 보충 데이터로 사용한다 | 객관성 향상을 위해 AI가 백로그 우선순위화를 완전히 통제하도록 한다 |  | C | AI는 인간의 의사결정을 대체하는 것이 아니라 보완해야 한다. AI 감성 분석을 보충 데이터로 사용하면 제품 책임자에게 추가 통찰을 제공하면서 우선순위화에 대한 권한을 유지한다. 무시(A)는 유용한 데이터를 낭비한다. 투표(B)는 결정 권한을 희석한다. 완전 AI 통제(D)는 인간 판단을 제거한다.
2125 | A PMO is implementing an AI-based resource allocation system that recommends optimal team assignments across multiple projects. A functional manager raises concerns about the system overriding their authority. How should the PM handle this? | Configure the AI system to make binding resource allocation decisions. | Disable the AI system and revert to manual allocation. | Escalate the concern to senior management without engaging the functional manager. | Position the AI system as a recommendation engine that supports, but does not replace, the functional manager's decisions. |  | D | AI systems should be positioned as recommendation tools that enhance decision-making rather than replace human authority. This approach respects the functional manager's governance role while leveraging AI's analytical capabilities. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Resources | Executing | Be an Accountable Leader | Acquire Resources | AI | PMO가 여러 프로젝트에 최적의 팀 배정을 추천하는 AI 기반 자원 배분 시스템을 구현 중이다. 기능 관리자가 우려한다. PM은 무엇을 해야 하는가? | AI 시스템이 구속력 있는 자원 배분 결정을 내리도록 구성한다 | AI 시스템을 비활성화하고 수동 배분으로 복귀한다 | 기능 관리자와 소통하지 않고 상위 경영진에게 우려를 에스컬레이션한다 | AI 시스템을 기능 관리자의 의사결정을 지원하되 대체하지 않는 추천 엔진으로 포지셔닝한다 |  | D | AI 시스템은 인간의 권한을 대체하는 것이 아니라 의사결정을 향상시키는 추천 도구로 포지셔닝해야 한다. 이는 기능 관리자의 거버넌스 역할을 존중하면서 AI 데이터의 이점을 활용한다. 구속력 결정(A)은 권한을 침해한다. 비활성화(B)는 이점을 포기한다. 에스컬레이션(C)은 직접 소통을 회피한다.
2126 | A project team is using AI to automate testing in a continuous integration pipeline. The AI tool starts producing false positives at an increasing rate. What should the project manager do? | Investigate the root cause of false positives, retrain or recalibrate the AI model, and establish quality thresholds for acceptable performance. | Ignore the false positives since they don't affect production. | Immediately remove the AI tool from the pipeline. | Continue using the AI tool and manually verify all flagged issues. |  | A | When AI tools show degraded performance, the appropriate response is root cause investigation and corrective action, not abandonment or ignoring the issue. Retraining or recalibrating the model and setting quality thresholds ensures the tool continues to provide value. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | XP (Extreme Programming) | Process | Plan and Optimize Quality | Governance | Monitoring & Controlling | Embed Quality | Monitor and Control Project Performance | AI | 프로젝트 팀이 CI 파이프라인에서 테스트 자동화에 AI를 사용 중이다. AI 도구가 오탐(false positive)을 생성하기 시작한다. PM은 무엇을 해야 하는가? | 오탐의 근본 원인을 조사하고 AI 모델을 재훈련/재보정하며 품질 게이트를 수립한다 | 프로덕션에 영향이 없으므로 오탐을 무시한다 | 파이프라인에서 AI 도구를 즉시 제거한다 | AI 도구를 계속 사용하고 플래그된 모든 이슈를 수동으로 검증한다 |  | A | AI 도구의 성능이 저하되면 적절한 대응은 근본 원인 조사와 시정 조치이지, 폐기나 무시가 아니다. 모델 재훈련/재보정과 품질 게이트 설정이 문제를 체계적으로 해결한다. 무시(B)는 팀 신뢰를 훼손한다. 즉시 제거(C)는 이점을 포기한다. 수동 검증(D)은 비효율적이다.
2127 | A project manager wants to use AI-powered natural language processing (NLP) to analyze stakeholder communications and detect early warning signs of dissatisfaction. What ethical concern should be addressed FIRST? | Stakeholder consent, data privacy, and transparency about how their communications will be analyzed. | Whether the NLP tool integrates with existing communication platforms. | The accuracy rate of sentiment detection. | The cost of the NLP tool. |  | A | Ethical considerations, including stakeholder consent, data privacy, and transparency, must be addressed before implementing any AI tool that analyzes personal communications. The PMBOK 8th Edition includes dedicated guidance on ethical AI use. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | AI | PM이 이해관계자 커뮤니케이션을 분석하고 감성을 감지하기 위해 AI 기반 NLP를 사용하려 한다. 가장 중요한 고려사항은 무엇인가? | 이해관계자 동의, 데이터 프라이버시, 커뮤니케이션 분석 방법에 대한 투명성 | NLP 도구가 기존 커뮤니케이션 플랫폼과 통합되는지 여부 | 감성 감지의 정확도 | NLP 도구의 비용 |  | A | 개인 커뮤니케이션을 분석하는 AI 도구를 구현하기 전에 이해관계자 동의, 데이터 프라이버시, 투명성 등 윤리적 고려사항을 먼저 다루어야 한다. PMBOK 8판은 AI 도구에 대한 윤리적 프레임워크를 강조한다. 통합(B), 정확도(C), 비용(D)은 모두 윤리 후에 고려할 사항이다.
2128 | An agile team is debating whether to use AI-assisted estimation for story points. Some team members believe it will undermine their professional judgment. What is the BEST course of action? | Run a pilot where AI estimates are compared alongside team estimates to evaluate accuracy and build trust. | Allow each team member to decide individually whether to use AI estimates. | Replace all manual estimation with AI to eliminate human bias. | Postpone the decision until the next project. |  | A | A pilot approach allows the team to empirically evaluate AI-assisted estimation against their own estimates, building evidence-based trust in the tool. This respects the team's expertise while exploring potential improvements. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | AI | 애자일 팀이 스토리 포인트에 AI 보조 추정을 사용할지 논의 중이다. 일부 팀원은 팀 전문성을 약화시킨다고 우려한다. PM은 무엇을 해야 하는가? | AI 추정과 팀 추정을 비교하여 정확도를 평가하고 신뢰를 구축하는 파일럿을 실행한다 | 각 팀원이 AI 추정 사용 여부를 개별적으로 결정하도록 한다 | 인간 편향을 제거하기 위해 모든 수동 추정을 AI로 대체한다 | 다음 프로젝트까지 결정을 연기한다 |  | A | 파일럿 접근법은 팀이 AI 보조 추정을 자체 추정과 경험적으로 비교하여 도구에 대한 증거 기반 신뢰를 구축할 수 있게 한다. 개별 결정(B)은 일관성이 없다. 전면 AI 대체(C)는 팀 전문성을 무시한다. 연기(D)는 기회를 놓친다.
2129 | A project manager is using an AI chatbot to provide 24/7 project status updates to stakeholders across different time zones. The chatbot occasionally provides incorrect information. What should the project manager do? | Add a disclaimer that the chatbot may provide inaccurate information. | Shut down the chatbot and revert to email-only updates. | Implement a feedback mechanism, regularly audit chatbot responses, and update the knowledge base to improve accuracy. | Limit the chatbot to only stakeholders in the same time zone. |  | C | Continuous improvement of AI tools requires a feedback loop, regular auditing, and knowledge base updates. This approach maintains the benefits of 24/7 availability while addressing accuracy issues. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Monitoring & Controlling | Embed Quality | Monitor Communications | AI | PM이 다른 시간대의 이해관계자에게 24/7 프로젝트 상태 업데이트를 제공하기 위해 AI 챗봇을 사용 중이다. 챗봇이 부정확한 응답을 한다. PM은 무엇을 해야 하는가? | 챗봇이 부정확한 정보를 제공할 수 있다는 면책 조항을 추가한다 | 챗봇을 종료하고 이메일 전용 업데이트로 복귀한다 | 피드백 메커니즘을 구현하고 정기적으로 챗봇 응답을 감사하며 지식 베이스를 업데이트한다 | 챗봇을 같은 시간대의 이해관계자에게만 제한한다 |  | C | AI 도구의 지속적 개선을 위해 피드백 루프, 정기적 감사, 지식 베이스 업데이트가 필요하다. 이는 24/7 가용성의 이점을 유지하면서 정확성 문제를 해결한다. 면책 조항(A)은 문제를 해결하지 않는다. 종료(B)는 이점을 포기한다. 제한(D)은 목적에 반한다.
2130 | A construction project is using AI-powered drones for site inspection and progress monitoring. The AI generates progress reports that conflict with the field superintendent's observations. What should the project manager do? | Trust the AI data over the field superintendent's assessment. | Analyze the discrepancy between AI data and field observations, identify the source of the difference, and calibrate the system accordingly. | Present both reports to the sponsor and let them decide. | Trust the field superintendent and discontinue the AI drone monitoring. |  | B | When AI outputs conflict with human observations, investigation and calibration are needed rather than choosing one over the other. The discrepancy may reveal calibration issues with the AI, blind spots in human observation, or different measurement criteria. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Traditional Plan-Driven | Process | Plan and Optimize Quality | Governance | Monitoring & Controlling | Adopt a Holistic View | Monitor and Control Project Performance | AI | 건설 프로젝트가 현장 검사와 진행 모니터링에 AI 드론을 사용 중이다. AI가 생성한 보고서와 현장 감독관의 보고서가 다르다. PM은 무엇을 해야 하는가? | 현장 감독관의 평가보다 AI 데이터를 신뢰한다 | AI 데이터와 현장 관찰 간의 불일치를 분석하고 차이의 원인을 식별하며 양 입력을 보정한다 | 양 보고서를 스폰서에게 제시하고 결정하게 한다 | 현장 감독관을 신뢰하고 AI 드론 모니터링을 중단한다 |  | B | AI 출력과 인간 관찰이 충돌할 때, 하나를 선택하는 것이 아니라 조사와 보정이 필요하다. 불일치는 AI 보정 문제, 사각지대 또는 인적 오류를 밝힐 수 있다. AI만 신뢰(A)는 현장 지식을 무시한다. 스폰서 결정(C)은 책임 전가이다. AI 중단(D)은 이점을 포기한다.
2131 | A project manager is evaluating AI tools for risk identification. Which factor is MOST critical when selecting an AI risk management tool? | The tool's ability to learn from the organization's historical project data and integrate with existing risk management processes. | The tool's user interface and visual appeal. | The vendor's market share and reputation. | The lowest cost option available in the market. |  | A | The most critical factor for an AI risk management tool is its ability to learn from organizational historical data and integrate with existing processes. This ensures contextual accuracy and seamless workflow adoption. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | AI | PM이 리스크 식별을 위한 AI 도구를 평가 중이다. AI 리스크 관리 도구 선택 시 가장 중요한 요소는 무엇인가? | 조직의 과거 프로젝트 데이터로부터 학습하고 기존 프로세스와 통합하는 능력 | 도구의 사용자 인터페이스와 시각적 매력 | 벤더의 시장 점유율과 평판 | 시장에서 가장 저렴한 옵션 |  | A | AI 리스크 관리 도구의 가장 중요한 요소는 조직의 과거 데이터로부터 학습하고 기존 프로세스와 통합하는 능력이다. 이는 맥락적 정확성과 원활한 워크플로 통합을 보장한다. UI(B), 평판(C), 비용(D)은 모두 부차적이다.
2132 | During a project retrospective, the team discovers that their AI-based scheduling tool consistently underestimates task durations by 15-20%. What is the BEST corrective action? | Abandon AI scheduling and return to traditional estimation methods. | Add a 20% buffer to all AI-generated estimates going forward. | Retrain the AI model with updated historical data, adjust the algorithm parameters, and validate against actual performance metrics. | Accept the underestimation as a known risk and proceed. |  | C | Systematic bias in AI models should be addressed through retraining with updated data and algorithm adjustment. Simply adding buffers is a workaround, not a fix. Abandoning loses potential value. Accepting without correction perpetuates schedule overruns. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Monitoring & Controlling | Embed Quality | Control Schedule | AI | 프로젝트 회고에서 AI 기반 일정 도구가 지속적으로 작업 기간을 과소평가하는 것을 발견했다. PM은 무엇을 해야 하는가? | AI 일정을 포기하고 전통적 추정 방법으로 돌아간다 | 향후 모든 AI 생성 추정에 20% 버퍼를 추가한다 | 업데이트된 과거 데이터로 AI 모델을 재훈련하고 알고리즘 매개변수를 조정하며 알려진 결과와 검증한다 | 과소추정을 알려진 리스크로 수용하고 진행한다 |  | C | AI 모델의 체계적 편향은 업데이트된 데이터로 재훈련하고 알고리즘을 조정하여 해결해야 한다. 버퍼 추가(B)는 우회책이지 수정이 아니다. 포기(A)는 잠재적 가치를 잃는다. 수용(D)은 문제를 방치한다.
2133 | A project team wants to use machine learning to predict which project risks are most likely to materialize based on patterns from past projects. Which data governance practice should the PM ensure FIRST? | That the machine learning model uses the latest algorithm. | That the model is deployed in the cloud for scalability. | That the training data is diverse and representative of various project types and environments. | That only the data science team has access to the model's outputs. |  | C | Data quality and representativeness are fundamental to machine learning effectiveness. Training data must be diverse and representative to avoid bias and ensure accurate predictions across different project contexts. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | AI | 프로젝트 팀이 과거 데이터 패턴에 기반하여 어떤 프로젝트 리스크가 실현될 가능성이 높은지 예측하기 위해 머신러닝을 사용하려 한다. 가장 중요한 것은 무엇인가? | 머신러닝 모델이 최신 알고리즘을 사용하는 것 | 모델이 확장성을 위해 클라우드에 배포되는 것 | 훈련 데이터가 다양하고 다양한 프로젝트 유형과 환경을 대표하는 것 | 데이터 과학 팀만 모델의 출력에 접근하는 것 |  | C | 데이터 품질과 대표성이 머신러닝 효과의 기본이다. 훈련 데이터는 편향을 방지하고 다양한 프로젝트 유형에서 정확한 예측을 보장하기 위해 다양하고 대표적이어야 한다. 최신 알고리즘(A), 클라우드 배포(B), 접근 제한(D)은 부차적이다.
2134 | An organization's PMO has developed an AI model that predicts project success rates based on initial project parameters. A new project scores only 35% success probability. What should the project manager do? | Recommend canceling the project based on the AI prediction. | Ignore the prediction and proceed as planned. | Use the prediction to identify the key risk factors driving the low score, develop targeted mitigation strategies, and re-evaluate. | Request a different AI model that gives a higher success prediction. |  | C | AI predictions should inform action, not dictate it. The PM should analyze which factors are driving the low score and develop mitigation strategies. This may improve the project's actual probability of success. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | AI | PMO가 초기 프로젝트 매개변수를 기반으로 프로젝트 성공률을 예측하는 AI 모델을 개발했다. 새 프로젝트가 35% 성공 확률을 받았다. PM은 무엇을 해야 하는가? | AI 예측에 기반하여 프로젝트 취소를 권장한다 | 예측을 무시하고 계획대로 진행한다 | 예측을 사용하여 낮은 점수를 유발하는 핵심 리스크 요소를 식별하고 목표 완화 전략을 개발한다 | 더 높은 성공 예측을 제공하는 다른 AI 모델을 요청한다 |  | C | AI 예측은 행동을 지시하는 것이 아니라 정보를 제공해야 한다. PM은 낮은 점수를 유발하는 요소를 분석하고 완화 전략을 개발해야 한다. 취소 권장(A)은 과잉 반응이다. 무시(B)는 유용한 데이터를 낭비한다. 다른 모델 요청(D)은 결과 쇼핑이다.
2135 | A project team is developing a customer-facing AI product. Mid-project, a new regulation requires AI systems to provide explainable decisions. How should the project manager handle this? | Continue with the current design and address compliance after delivery. | Delegate the compliance concern to the legal department only. | Remove AI decision-making features to avoid compliance issues. | Raise a change request to incorporate explainability requirements into the product design and update the project scope. |  | D | Regulatory changes affecting project scope require formal change management. The PM should raise a change request to incorporate the new explainability requirements. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | AI | 프로젝트 팀이 고객 대면 AI 제품을 개발 중이다. 프로젝트 중간에 AI 시스템이 설명 가능성을 제공해야 하는 새 규제가 발효된다. PM은 무엇을 해야 하는가? | 현재 설계로 계속하고 납품 후 컴플라이언스를 처리한다 | 컴플라이언스 우려를 법무 부서에만 위임한다 | 컴플라이언스 문제를 피하기 위해 AI 의사결정 기능을 제거한다 | 설명 가능성 요구사항을 제품 설계에 통합하기 위한 변경 요청을 제출하고 프로젝트 계획을 업데이트한다 |  | D | 프로젝트 범위에 영향을 미치는 규제 변경은 공식 변경 관리가 필요하다. PM은 새 설명 가능성 요구사항을 통합하기 위한 변경 요청을 제출해야 한다. 납품 후 처리(A)는 규정 위반이다. 법무만 위임(B)은 기술적 조치가 누락된다. 기능 제거(C)는 과도하다.
2136 | A multinational project team uses an AI-powered translation tool for cross-language collaboration. A team member reports that the tool mistranslated a technical requirement, leading to a misunderstanding. What should the PM do? | Stop using the translation tool and hire human translators for all communications. | Accept occasional mistranslations as a risk of using AI tools. | Require all technical requirements to undergo human review after AI translation, especially for critical deliverables. | Ask team members to learn a common language. |  | C | For critical communications like technical requirements, AI translation should be supplemented with human review. This balances the efficiency of AI with the accuracy needed for critical project information. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Embed Quality | Manage Communications | AI | 다국적 프로젝트 팀이 다국어 협업을 위해 AI 번역 도구를 사용 중이다. 팀원이 기술 요구사항에서 오역을 보고한다. PM은 무엇을 해야 하는가? | 번역 도구 사용을 중단하고 모든 커뮤니케이션에 인간 번역가를 고용한다 | AI 도구 사용의 리스크로서 간헐적 오역을 수용한다 | AI 번역 후 모든 기술 요구사항은 인간 검토를 거치도록 요구한다, 특히 중요 정보에 대해 | 팀원에게 공통 언어를 배우도록 요청한다 |  | C | 기술 요구사항과 같은 중요 커뮤니케이션에 대해 AI 번역은 인간 검토로 보완되어야 한다. 이는 AI의 효율성과 중요 정보에 필요한 정확성의 균형을 맞춘다. 전면 중단(A)은 비용이 과도하다. 오역 수용(B)은 리스크를 방치한다. 공통 언어(D)는 비현실적이다.
2137 | A project manager is implementing an AI-based earned value management (EVM) system that automatically calculates CPI and SPI. The system flags a project as at-risk, but the traditional EVM calculations show the project is on track. What should the PM investigate? | Use whichever result the sponsor prefers. | Compare the data inputs, calculation methods, and assumptions between both systems to identify the source of discrepancy. | Assume the AI is correct and report the project as at-risk. | Assume the AI is wrong and continue with traditional calculations. |  | B | When AI and traditional methods produce different results, investigation is necessary. The PM should compare data inputs, calculation methods, and assumptions. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Adopt a Holistic View | Control Costs | AI | PM이 CPI와 SPI를 자동 계산하는 AI 기반 획득가치관리(EVM) 시스템을 구현 중이다. AI 결과가 전통적 계산과 다르다. PM은 무엇을 해야 하는가? | 스폰서가 선호하는 결과를 사용한다 | 양 시스템 간 데이터 입력, 계산 방법, 가정을 비교하여 차이의 원인을 식별한다 | AI가 맞다고 가정하고 프로젝트를 위험 상태로 보고한다 | AI가 틀렸다고 가정하고 전통적 계산을 계속한다 |  | B | AI와 전통적 방법이 다른 결과를 낼 때 조사가 필요하다. PM은 데이터 입력, 계산 방법, 가정을 비교해야 한다. 스폰서 선호(A)는 객관성이 없다. AI 맞다고 가정(C)은 검증 없다. AI 틀렸다고 가정(D)은 편향적이다.
2138 | An organization is deploying an AI system that learns from individual employee productivity data to optimize team assignments. Several team members express concern about privacy and surveillance. What approach BEST addresses this? | Tell team members that productivity monitoring is a standard organizational practice. | Assure team members that only aggregate data, not individual data, is used for decision-making. | Develop and communicate a clear data usage policy, ensure compliance with privacy regulations, allow opt-out options, and establish a feedback channel. | Only share the AI system's recommendations with management, not with team members. |  | C | Addressing privacy concerns requires transparency, policy clarity, regulatory compliance, and employee empowerment through opt-out options and feedback channels. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | AI | 조직이 개인 직원 생산성 데이터로부터 학습하여 팀 배정을 최적화하는 AI 시스템을 배포 중이다. 팀원들이 프라이버시 우려를 제기한다. PM은 무엇을 해야 하는가? | 생산성 모니터링이 표준 조직 관행이라고 팀원에게 말한다 | 개인 데이터가 아닌 집계 데이터만 의사결정에 사용됨을 보장한다 | 명확한 데이터 사용 정책을 개발하고 소통하며, 프라이버시 규정 준수를 보장하고, 옵트아웃 옵션과 피드백 채널을 허용한다 | AI 시스템의 추천을 경영진에게만 공유한다 |  | C | 프라이버시 우려 해결에는 투명성, 정책 명확성, 규정 준수, 옵트아웃 옵션과 피드백 채널을 통한 직원 권한 부여가 필요하다. 표준 관행이라 말하기(A)는 우려를 무시한다. 집계 데이터 보장(B)은 부분적 해결이다. 경영진만 공유(D)는 투명성이 없다.
2139 | A project manager is considering using AI to automate the generation of lessons learned reports from project documents and team communication logs. What is a KEY risk of this approach? | The AI may miss contextual nuances, tacit knowledge, and interpersonal dynamics that are critical for meaningful lessons learned. | The AI may generate reports too quickly for the team to review. | The AI reports will be too long for stakeholders to read. | The AI will eliminate the need for retrospective meetings entirely. |  | A | AI-generated lessons learned reports may miss tacit knowledge, contextual nuances, and interpersonal dynamics that are best captured through human interaction and reflection. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Closing | Adopt a Holistic View | Close Project or Phase | AI | PM이 프로젝트 문서와 커뮤니케이션에서 교훈 보고서를 자동 생성하기 위해 AI 사용을 고려 중이다. 가장 중요한 고려사항은 무엇인가? | AI가 맥락적 뉘앙스, 암묵적 지식, 대인관계 역학을 놓칠 수 있으며 이는 포괄적 교훈에 중요하다 | AI가 팀이 검토하기에 너무 빠르게 보고서를 생성할 수 있다 | AI 보고서가 이해관계자가 읽기에 너무 길 수 있다 | AI가 회고 회의의 필요성을 완전히 제거할 수 있다 |  | A | AI 생성 교훈 보고서는 인간의 상호작용과 성찰을 통해 가장 잘 포착되는 암묵적 지식, 맥락적 뉘앙스, 대인관계 역학을 놓칠 수 있다. 속도(B), 길이(C)는 관리 가능한 문제이다. 회의 대체(D)는 비현실적이다.