2140 | A project manager is using AI to analyze project documentation and automatically identify potential scope creep. The AI flags 15 items as potential scope changes. After review, only 3 are actual scope changes. What does this indicate? | The AI model needs fine-tuning to reduce false positives while maintaining its ability to detect real scope changes. | The AI tool is useless and should be discontinued. | The project has a serious scope creep problem. | The remaining 12 items should still be treated as scope changes to be safe. |  | A | A high false positive rate indicates the AI model needs fine-tuning, not abandonment. The tool demonstrated value by correctly identifying 3 actual scope changes. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Monitoring & Controlling | Embed Quality | Control Scope | AI | PM이 프로젝트 문서를 분석하여 범위 변경을 자동 식별하는 AI를 사용 중이다. AI가 15개 변경 항목을 플래그했지만 검토 결과 3개만 실제 범위 변경이었다. 이것은 무엇을 의미하는가? | 오탐률을 줄이면서 실제 범위 변경 감지 능력은 유지하도록 AI 모델의 미세 조정이 필요하다 | AI 도구가 쓸모없으므로 중단해야 한다 | 프로젝트에 심각한 범위 변경 문제가 있다 | 나머지 12개 항목도 안전을 위해 범위 변경으로 처리해야 한다 |  | A | 높은 오탐률은 AI 모델의 미세 조정이 필요함을 나타내지, 폐기가 아니다. 도구는 3개의 실제 범위 변경을 올바르게 식별하여 가치를 입증했다. 중단(B)은 가치를 포기한다. 심각한 문제(C)는 잘못된 해석이다. 모두 처리(D)는 과잉 반응이다.
2141 | A team member has developed an AI script that automates repetitive project reporting tasks, saving 10 hours per week. The script was not approved through the organization's IT governance process. What should the PM do? | Report the team member for violating IT policies. | Ask the team member to keep using the script quietly. | Immediately stop use of the script and work with IT governance to evaluate and formally approve it. | Allow the team member to continue using the script since it improves productivity. |  | C | Even beneficial AI tools must go through proper governance approval processes. Unapproved scripts may pose security, data privacy, or compliance risks. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | AI | 팀원이 반복적 프로젝트 보고 작업을 자동화하는 AI 스크립트를 개발하여 주당 10시간을 절약한다. 그러나 IT 거버넌스의 승인을 받지 않았다. PM은 무엇을 해야 하는가? | IT 정책 위반으로 팀원을 보고한다 | 팀원에게 스크립트를 조용히 계속 사용하도록 요청한다 | 즉시 스크립트 사용을 중단하고 IT 거버넌스와 협력하여 평가하고 공식 승인한다 | 생산성이 향상되므로 팀원이 스크립트를 계속 사용하도록 허용한다 |  | C | 유익한 AI 도구라도 적절한 거버넌스 승인 프로세스를 거쳐야 한다. 미승인 스크립트는 보안, 데이터 프라이버시, 컴플라이언스 리스크를 야기할 수 있다. 보고(A)는 징벌적이다. 조용히 사용(B)은 정책 위반이다. 계속 허용(D)은 거버넌스를 무시한다.
2142 | A project team is considering using AI to automatically assign tasks to team members based on skill profiles and workload. The AI identifies 200 requirements, but the stakeholders confirm only 150 are valid. What BEST describes the project manager's next step? | Review the 50 invalid requirements to understand why the AI misidentified them, refine the extraction criteria, and validate the remaining 150 with stakeholders. | Use only the 150 confirmed requirements without further analysis. | Accept all 200 requirements to avoid missing any. | Discard all AI-identified requirements and manually re-analyze transcripts. |  | A | Analyzing why the AI misidentified 50 requirements provides valuable feedback for improving the tool and may reveal edge cases or ambiguities in stakeholder communications. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | AI가 이해관계자 인터뷰 녹취록에서 200개 요구사항을 추출했으나, 검증 결과 150개만 유효하고 50개는 유효하지 않았다. PM은 무엇을 해야 하는가? | AI가 50개를 잘못 식별한 이유를 검토하고, 추출 기준을 개선하며, 향후 정확도를 높이기 위해 모델을 재훈련한다 | 150개 확인된 요구사항만 추가 분석 없이 사용한다 | 누락을 피하기 위해 200개 요구사항을 모두 수용한다 | AI 식별 요구사항을 모두 폐기하고 녹취록을 수동으로 재분석한다 |  | A | AI가 50개 요구사항을 잘못 식별한 이유를 분석하면 도구 개선에 가치 있는 피드백을 제공하고 이해관계자 커뮤니케이션의 모호성을 밝힐 수 있다. 확인된 것만 사용(B)은 개선 기회를 놓친다. 모두 수용(C)은 품질을 희생한다. 전면 폐기(D)는 비효율적이다.
2143 | A senior executive asks the project manager to use AI to replace the project's quality assurance team. What should the project manager explain? | AI can automate routine testing tasks but cannot fully replace human judgment for complex quality decisions, exploratory testing, and user experience evaluation. | AI can fully replace the QA team and reduce project costs significantly. | AI in QA is unreliable and should not be considered. | The QA team should decide whether to adopt AI tools. |  | A | AI excels at automating routine, repetitive testing tasks but has limitations in areas requiring human judgment, creativity, and contextual understanding. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | AI | 고위 경영진이 PM에게 AI로 프로젝트의 품질보증(QA) 팀을 대체하라고 요청한다. PM은 무엇을 해야 하는가? | AI는 일상적 테스트 작업을 자동화할 수 있지만 복잡한 품질 결정에 대한 인간 판단을 완전히 대체할 수 없다고 설명한다 | AI가 QA 팀을 완전히 대체하여 프로젝트 비용을 크게 줄일 수 있다고 설명한다 | QA에서 AI는 신뢰할 수 없으므로 고려하지 말아야 한다고 설명한다 | QA 팀이 AI 도구 도입 여부를 결정해야 한다고 설명한다 |  | A | AI는 일상적이고 반복적인 테스트 작업을 자동화하는 데 뛰어나지만 인간의 판단, 창의성, 맥락적 이해가 필요한 영역에는 한계가 있다. 완전 대체(B)는 비현실적이다. 신뢰할 수 없다(C)는 AI의 이점을 무시한다. 팀 결정(D)은 PM의 책임을 회피한다.
2144 | An agile project is using AI-based velocity prediction to plan upcoming sprints. The AI predicts a velocity of 45 story points, but the team historically averages 35. What should the Scrum Master recommend? | Ignore the AI prediction and stick with the historical average of 35. | Commit to 45 story points as the AI prediction suggests. | Plan for 35 story points based on historical performance, investigate why the AI predicts higher, and monitor if team capacity has genuinely increased. | Split the difference and plan for 40 story points. |  | C | Historical velocity should remain the primary planning input, but the AI prediction warrants investigation. The AI may have detected efficiency improvements or changed team composition. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | AI | 애자일 프로젝트가 AI 기반 속도 예측을 사용하여 다음 스프린트를 계획 중이다. AI가 45 스토리 포인트를 예측하지만 과거 평균은 35이다. PM은 무엇을 해야 하는가? | AI 예측을 무시하고 과거 평균 35를 고수한다 | AI 예측대로 45 스토리 포인트에 커밋한다 | 과거 성과에 기반하여 35 스토리 포인트를 계획하되, AI가 왜 더 높은 예측을 하는지 조사하고 향후 스프린트의 계획 정확도를 높이기 위해 결과를 사용한다 | 차이를 절충하여 40 스토리 포인트를 계획한다 |  | C | 과거 속도가 주요 계획 입력으로 남아야 하지만 AI 예측은 조사할 가치가 있다. AI가 효율성 향상이나 팀 구성 변화를 감지했을 수 있다. 무시(A)는 유용한 통찰을 놓친다. 45 커밋(B)은 검증 없이 과도하다. 절충(D)은 논리적 근거가 없다.
2145 | A project manager discovers that the AI tool used for vendor evaluation has a bias toward larger vendors due to the training data. How should this be addressed? | Manually override AI recommendations for smaller vendors. | Stop using AI for vendor evaluation permanently. | Audit the training data for bias, diversify the data sources, and implement fairness metrics in the evaluation algorithm. | Continue using the tool since larger vendors are generally more reliable. |  | C | AI bias in vendor evaluation must be addressed systematically through data auditing, diversification of training data, and implementation of fairness metrics. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PM이 벤더 평가에 사용하는 AI 도구가 훈련 데이터로 인해 대형 벤더에 편향이 있음을 발견한다. PM은 무엇을 해야 하는가? | 소형 벤더에 대해 AI 추천을 수동으로 재정의한다 | 벤더 평가에 AI 사용을 영구적으로 중단한다 | 훈련 데이터의 편향을 감사하고 데이터 소스를 다양화하며 평가 프로세스에 공정성 지표를 구현한다 | 대형 벤더가 일반적으로 더 신뢰할 수 있으므로 도구를 계속 사용한다 |  | C | 벤더 평가에서 AI 편향은 데이터 감사, 훈련 데이터 다양화, 공정성 지표 구현을 통해 체계적으로 해결해야 한다. 수동 재정의(A)는 근본 원인을 해결하지 않는다. 영구 중단(B)은 이점을 포기한다. 편향 수용(D)은 부당하다.
2146 | Which of the following BEST describes the role of AI in project management according to PMBOK 8th Edition? | AI is a supplementary tool that augments human decision-making, requiring ethical oversight and governance. | AI should replace project managers for routine projects. | AI is only applicable to software development projects. | AI should be avoided until it is fully mature and error-free. |  | A | The PMBOK 8th Edition positions AI as a supplementary tool that augments human decision-making rather than replacing it. It emphasizes the need for ethical oversight, governance, and appropriate human supervision. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PMBOK 8판에 따른 프로젝트 관리에서 AI의 역할을 가장 잘 설명하는 것은? | AI는 윤리적 감독과 거버넌스가 필요한 인간 의사결정을 보강하는 보조 도구이다 | AI는 일상적인 프로젝트에서 프로젝트 관리자를 대체해야 한다 | AI는 소프트웨어 개발 프로젝트에만 적용 가능하다 | AI는 완전히 성숙하고 오류가 없을 때까지 피해야 한다 |  | A | PMBOK 8판은 AI를 대체가 아닌 인간 의사결정을 보강하는 보조 도구로 위치시킨다. 윤리적 감독, 거버넌스, 적절한 인간 판단이 필요함을 강조한다. 대체(B)는 PMBOK 입장이 아니다. SW 전용(C)은 범위가 좁다. 회피(D)는 기술 활용을 무시한다.
2147 | A project team has implemented an AI-driven cost estimation model that uses historical cost data from similar projects. After several months, the model's predictions start becoming less accurate. What is the MOST likely cause? | The project team is not entering data correctly. | The AI model has a software bug. | The market conditions, resource costs, or project complexity have changed since the model was trained, causing data drift. | AI models always degrade over time regardless of external factors. |  | C | Data drift—when the statistical properties of the data the model was trained on change over time—is the most common cause of AI model degradation. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Embed Quality | Control Costs | AI | AI 기반 비용 추정 모델이 과거 데이터를 사용하지만 최근 정확도가 떨어지고 있다. 가장 가능한 원인은? | 프로젝트 팀이 데이터를 올바르게 입력하지 않고 있다 | AI 모델에 소프트웨어 버그가 있다 | 모델 학습 이후 시장 조건, 자원 비용 또는 프로젝트 복잡성이 변경되었다 | AI 모델은 외부 요인에 관계없이 항상 시간이 지나면 저하된다 |  | C | 데이터 드리프트—모델이 학습한 데이터의 통계적 속성이 시간에 따라 변경되는 것—가 AI 모델 저하의 가장 일반적인 원인이다. 시장 조건, 자원 비용, 프로젝트 복잡성 변화가 이에 해당한다. 데이터 입력 오류(A)는 체계적 저하를 설명하지 못한다. 버그(B)는 갑작스런 오류지 점진적 저하가 아니다. 항상 저하(D)는 부정확하다.
2148 | A project manager wants to use AI to identify the optimal project delivery approach (predictive, agile, or hybrid) for a new project. What input data would be MOST useful for the AI analysis? | The project sponsor's personal preference for methodology. | The budget allocated for project management tools. | Project characteristics including requirements stability, complexity, stakeholder engagement level, team experience, and organizational culture. | Industry benchmarks from unrelated project types. |  | C | The most useful inputs for AI-based methodology selection are project-specific characteristics: requirements stability, complexity, stakeholder engagement, team experience, and organizational culture. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Tailored Approach | Process | Develop Integrated PM Plan | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | AI | PM이 AI를 사용하여 최적의 프로젝트 전달 방식을 식별하려 한다. AI에 가장 유용한 입력은? | 프로젝트 스폰서의 방법론에 대한 개인적 선호 | 프로젝트 관리 도구에 할당된 예산 | 요구사항 안정성, 복잡성, 이해관계자 참여 수준, 팀 경험 등 프로젝트 특성 | 관련 없는 프로젝트 유형의 산업 벤치마크 |  | C | AI 기반 방법론 선택에 가장 유용한 입력은 프로젝트별 특성이다: 요구사항 안정성, 복잡성, 이해관계자 참여, 팀 경험, 조직 문화. 스폰서 선호(A)는 주관적이다. 도구 예산(B)은 방법론과 무관하다. 관련 없는 벤치마크(D)는 부적절하다.
2149 | A project team is developing an AI system for a healthcare client. Midway through the project, the team discovers that the AI training data contains patient information that may violate HIPAA regulations. What should the PM do FIRST? | Delete the data and find alternative training data without informing anyone. | Immediately halt the use of the non-compliant data, notify relevant stakeholders, engage the legal/compliance team, and assess the impact on the project. | Continue the project and address the data issue after delivery. | Anonymize the data and continue using it without further review. |  | B | Regulatory compliance violations require immediate action. The PM must halt the non-compliant activity, notify stakeholders, engage legal/compliance experts, and assess the project impact. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | AI | 의료 클라이언트용 AI 시스템 개발 중 학습 데이터가 데이터 보호 규정을 위반함을 발견했다. PM은 무엇을 해야 하는가? | 아무에게도 알리지 않고 데이터를 삭제하고 대체 학습 데이터를 찾는다 | 비준수 데이터 사용을 즉시 중단하고, 관련 이해관계자에게 통지하며, 법무/컴플라이언스 전문가를 참여시킨다 | 프로젝트를 계속하고 납품 후 데이터 문제를 해결한다 | 데이터를 익명화하고 추가 검토 없이 계속 사용한다 |  | B | 규제 준수 위반은 즉각적 조치가 필요하다. PM은 비준수 활동을 중단하고, 이해관계자에게 통지하며, 법무/컴플라이언스 전문가를 참여시키고, 프로젝트 영향을 평가해야 한다. 무통보 삭제(A)는 비윤리적이다. 납품 후 해결(C)은 리스크를 증가시킨다. 익명화만(D)은 불충분하다.
2150 | A hybrid project team is using AI for automated risk scoring. The tool assigns numerical risk scores, but team members find the scores difficult to interpret for decision-making. What should the project manager do? | Replace the AI tool with a simpler spreadsheet-based risk register. | Simplify the AI output by adding risk categories (High/Medium/Low), visual dashboards, and plain-language explanations alongside numerical scores. | Train the team in advanced data analytics to interpret the scores. | Ask the AI vendor to make the scores more intuitive. |  | B | AI outputs should be presented in ways that support decision-making. Adding risk categories, visual dashboards, and plain-language explanations makes the information actionable for all stakeholders. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Executing | Focus on Value | Implement Risk Responses | AI | AI 자동 리스크 점수 도구의 수치가 팀원에게 혼란을 줄 때 PM은 무엇을 해야 하는가? | AI 도구를 더 간단한 스프레드시트 기반 리스크 등록부로 대체한다 | 리스크 카테고리(높음/중간/낮음), 시각적 대시보드, 평이한 언어 설명을 추가하여 AI 출력을 간소화한다 | 팀에게 고급 데이터 분석을 교육하여 점수를 해석하게 한다 | AI 벤더에게 점수를 더 직관적으로 만들어 달라고 요청한다 |  | B | AI 출력은 의사결정을 지원하는 방식으로 표시되어야 한다. 리스크 카테고리, 시각적 대시보드, 평이한 언어 설명을 추가하면 모든 이해관계자가 활용할 수 있다. 도구 대체(A)는 AI 가치를 잃는다. 고급 교육(C)은 비현실적이다. 벤더 요청(D)은 내부 해결이 아니다.
2151 | A project team is considering using AI to automatically assign tasks to team members based on skill profiles and workload. What is the PRIMARY concern the PM should address? | Whether the AI assignments will reduce project costs. | Whether the AI can handle the volume of tasks in the project. | Whether the AI can integrate with the existing project management software. | Whether team members' professional development goals and preferences are considered alongside AI's optimization criteria. |  | D | AI-driven task assignment should consider not only efficiency but also team members' professional development goals, preferences, and well-being. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | AI | AI로 기술 프로필과 작업량 기반 자동 업무 배정을 고려할 때 가장 중요한 고려사항은? | AI 배정이 프로젝트 비용을 줄일 수 있는지 | AI가 프로젝트의 작업량을 처리할 수 있는지 | AI가 기존 프로젝트 관리 소프트웨어와 통합될 수 있는지 | 팀원의 전문 개발 목표와 선호가 AI의 최적화 기준과 함께 고려되는지 |  | D | AI 기반 업무 배정은 효율성뿐만 아니라 팀원의 전문 개발 목표, 선호, 웰빙도 고려해야 한다. 비용 절감(A)은 부차적이다. 작업량 처리(B)는 기술적 관심이다. SW 통합(C)은 기술적 요구이다.
2152 | An organization uses AI to predict budget overruns at the portfolio level. The AI predicts that a project will exceed its budget by 25%, but the PM's bottom-up estimate shows only a 5% overrun. What should the portfolio manager do? | Trust the PM's estimate since they know the project best. | Have the PM and the AI analytics team collaborate to reconcile the two estimates and identify which assumptions differ. | Trust the AI prediction since it uses portfolio-level data. | Reduce the project budget by 25% immediately. |  | B | When AI portfolio-level predictions and PM-level estimates conflict significantly, collaboration to reconcile differences is essential. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Adopt a Holistic View | Control Costs | AI | AI가 포트폴리오 수준에서 프로젝트 예산 초과 25%를 예측하지만 PM은 5%만 예상할 때 어떻게 해야 하는가? | PM이 프로젝트를 가장 잘 아므로 PM의 추정을 신뢰한다 | PM과 AI 분석팀이 협력하여 두 추정의 차이를 조정하고 어떤 가정이 다른지 식별한다 | 포트폴리오 수준 데이터를 사용하므로 AI 예측을 신뢰한다 | 프로젝트 예산을 즉시 25% 삭감한다 |  | B | AI 포트폴리오 수준 예측과 PM 수준 추정이 크게 상충할 때, 차이를 조정하기 위한 협력이 필수적이다. 일방적 신뢰(A,C)는 유용한 정보를 무시한다. 즉시 삭감(D)은 분석 없는 성급한 조치이다.
2153 | During a project review, a stakeholder asks whether AI can be used to replace the project's change control board (CCB) for faster decision-making. What is the BEST response? | AI can assist the CCB by analyzing change request impacts and providing recommendations, but final decisions should remain with the human-led CCB. | No, AI has no role in change management. | Yes, AI can make faster and more objective change decisions than a CCB. | Only minor change requests should be handled by AI. |  | A | AI can enhance the CCB's effectiveness by quickly analyzing change impacts, assessing schedule and cost effects, and providing data-driven recommendations. However, the final decision authority should remain with the human-led CCB. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | Change Management | Process | Develop Integrated PM Plan | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | AI | AI가 변경통제위원회(CCB)를 대체하여 변경 요청을 평가할 수 있는가? | AI는 변경 요청 영향을 분석하고 권고를 제공하여 CCB를 지원할 수 있지만, 최종 결정 권한은 인간에게 있어야 한다 | 아니오, AI는 변경 관리에서 역할이 없다 | 예, AI가 CCB보다 빠르고 객관적인 변경 결정을 할 수 있다 | 사소한 변경 요청만 AI가 처리해야 한다 |  | A | AI는 변경 영향을 빠르게 분석하고, 일정 및 비용 효과를 평가하며, 데이터 기반 권고를 제공하여 CCB의 효과를 높일 수 있다. 그러나 최종 결정 권한은 인간에게 있어야 한다. 역할 없음(B)은 부정확하다. 완전 대체(C)는 거버넌스 원칙에 반한다. 사소한 것만(D)은 제한적이다.
2154 | A project manager is implementing a machine learning model that improves its accuracy over time as it processes more project data. What type of AI learning does this represent? | Transfer learning that applies knowledge from one domain to another. | Unsupervised learning that identifies patterns without labeled data. | Supervised learning that requires labeled training data. | Reinforcement learning where the model learns from outcomes of its decisions. |  | D | When an AI model improves its accuracy based on the outcomes of its decisions over time, this represents reinforcement learning. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Executing | Embed Quality | Direct and Manage Project Work | AI | 시간이 지남에 따라 결정 결과를 처리하면서 정확도가 향상되는 ML 모델은 어떤 유형인가? | 한 도메인의 지식을 다른 도메인에 적용하는 전이 학습 | 레이블 없는 데이터에서 패턴을 식별하는 비지도 학습 | 레이블이 있는 학습 데이터가 필요한 지도 학습 | 결정의 결과로부터 학습하는 강화 학습 |  | D | AI 모델이 결정의 결과에 기반하여 시간에 따라 정확도가 향상되면, 이는 강화 학습을 나타낸다. 전이 학습(A)은 도메인 간 지식 이전이다. 비지도(B)는 패턴 발견이다. 지도(C)는 레이블 데이터가 필요하다.
2155 | A project manager needs to present AI implementation options to the project steering committee. The committee has limited technical AI knowledge. What presentation approach is MOST effective? | Ask the data science team to present directly to the committee. | Present detailed technical specifications of each AI algorithm. | Send a technical whitepaper before the meeting and expect committee members to review it. | Focus on business value, risk impact, implementation timeline, and cost-benefit analysis, using visual aids and practical examples. |  | D | When presenting to stakeholders with limited technical knowledge, focusing on business value, risk impact, timelines, and cost-benefit analysis is most effective. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | AI | PM이 기술 지식이 제한된 운영위원회에 AI 구현 옵션을 발표해야 한다. 가장 좋은 접근법은? | 데이터 과학팀에게 위원회에 직접 발표하도록 요청한다 | 각 AI 알고리즘의 상세 기술 사양을 발표한다 | 회의 전 기술 백서를 보내고 위원회 구성원이 검토하기를 기대한다 | 비즈니스 가치, 리스크 영향, 구현 일정, 비용-편익 분석에 초점을 맞추고 시각적 자료를 사용한다 |  | D | 기술 지식이 제한된 이해관계자에게 발표할 때, 비즈니스 가치, 리스크 영향, 일정, 비용-편익 분석에 초점을 맞추는 것이 가장 효과적이다. 데이터 과학팀 발표(A)는 기술적이다. 기술 사양(B)은 청중에 부적합하다. 백서(C)는 수동적이다.
2156 | An organization mandates the use of a specific AI tool for all projects. The project manager's team finds the tool unsuitable for their project type. What should the PM do? | Document the misfit with evidence, propose a tailored approach or alternative, and seek an exception through proper governance channels. | Ignore the mandate and use a different tool. | Complain to team members about organizational bureaucracy. | Use the tool as mandated regardless of its fit. |  | A | When organizational mandates don't fit a specific project, the PM should document the issues with evidence and seek exceptions through proper channels. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | AI | 조직이 모든 프로젝트에 특정 AI 도구 사용을 의무화하지만 PM 팀에 적합하지 않을 때 어떻게 해야 하는가? | 증거와 함께 부적합을 문서화하고, 맞춤형 접근법이나 대안을 제안하며, 적절한 채널을 통해 예외를 요청한다 | 지침을 무시하고 다른 도구를 사용한다 | 팀원에게 조직의 관료주의에 대해 불평한다 | 적합성에 관계없이 지침대로 도구를 사용한다 |  | A | 조직 지침이 특정 프로젝트에 맞지 않을 때, PM은 증거와 함께 문제를 문서화하고 적절한 채널을 통해 예외를 요청해야 한다. 무시(B)는 비준수이다. 불평(C)은 비생산적이다. 무조건 따르기(D)는 프로젝트에 해로울 수 있다.
2157 | A project uses AI to monitor team communication channels and flag potential conflicts early. What is the MOST important governance control to implement? | Establish clear policies on data collection scope, retention periods, usage limitations, and transparency with team members. | Use the data for annual performance reviews of team members. | Allow the AI to automatically intervene in detected conflicts. | Ensure only the PM has access to the conflict detection reports. |  | A | AI-based communication monitoring requires robust governance controls including clear policies on what data is collected, how long it's retained, how it's used, and transparency with those being monitored. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | AI | AI가 팀 커뮤니케이션 채널을 모니터링하여 잠재적 갈등을 조기 감지할 때 가장 중요한 고려사항은? | 데이터 수집 범위, 보존 기간, 사용 제한, 모니터링 대상자에 대한 투명성에 대한 명확한 정책을 수립한다 | 연간 성과 검토에 데이터를 사용한다 | AI가 감지된 갈등에 자동으로 개입하도록 허용한다 | PM만 갈등 감지 보고서에 접근하도록 한다 |  | A | AI 기반 커뮤니케이션 모니터링은 수집 대상, 보존 기간, 사용 방법, 모니터링 대상자에 대한 투명성을 포함하는 강력한 거버넌스 통제가 필요하다. 성과 검토(B)는 프라이버시 침해이다. 자동 개입(C)은 부적절하다. PM만 접근(D)은 투명성이 부족하다.
2158 | A data-driven project manager uses AI dashboards showing real-time project metrics. During a stakeholder meeting, a key stakeholder questions whether the AI metrics can be trusted. What is the BEST response? | Tell the stakeholder to trust the technology. | Switch back to manual reporting to satisfy the stakeholder. | Describe the data sources, validation processes, and accuracy benchmarks used to ensure the AI dashboard's reliability, and offer to review the methodology together. | Explain that AI is always more accurate than manual tracking. |  | C | Building trust in AI-driven metrics requires transparency about data sources, validation processes, and accuracy benchmarks. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | AI | AI 대시보드가 실시간 프로젝트 지표를 보여줄 때 이해관계자가 데이터 정확성을 의심하면 PM은 무엇을 해야 하는가? | 이해관계자에게 기술을 신뢰하라고 말한다 | 이해관계자를 만족시키기 위해 수동 보고로 전환한다 | AI 대시보드의 신뢰성을 보장하기 위해 사용된 데이터 소스, 검증 프로세스, 정확도 벤치마크를 설명한다 | AI가 항상 수동 추적보다 정확하다고 설명한다 |  | C | AI 기반 지표에 대한 신뢰 구축은 데이터 소스, 검증 프로세스, 정확도 벤치마크에 대한 투명성이 필요하다. 신뢰하라(A)는 설득력이 없다. 수동 전환(B)은 퇴보이다. 항상 정확(D)은 부정확한 주장이다.
2159 | Which of the following is an example of using AI to support the 'Focus on Value' principle from PMBOK 8th Edition? | Using AI to automatically generate project status emails. | Using AI analytics to identify which project features deliver the highest customer value and prioritize them in the backlog. | Using AI to format project documents consistently. | Using AI to track individual team member work hours. |  | B | Using AI to identify highest-value features and prioritize them directly supports the 'Focus on Value' principle by ensuring project efforts are directed toward maximum customer benefit. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | PMBOK 8판의 '가치에 집중' 원칙을 지원하는 AI 사용 예시는? | AI를 사용하여 프로젝트 상태 이메일을 자동 생성한다 | AI 분석을 사용하여 가장 높은 고객 가치를 제공하는 프로젝트 기능을 식별하고 우선순위를 정한다 | AI를 사용하여 프로젝트 문서를 일관되게 포맷한다 | AI를 사용하여 개별 팀원 근무 시간을 추적한다 |  | B | AI를 사용하여 최고 가치 기능을 식별하고 우선순위를 정하는 것은 프로젝트 노력이 최대 고객 혜택으로 향하도록 하여 '가치에 집중' 원칙을 직접 지원한다. 이메일 생성(A)은 행정적이다. 포맷(C)은 가치와 무관하다. 시간 추적(D)은 관리적이다.
2160 | A project team is building an AI model and needs a large dataset for training. The most available dataset contains biased historical data that underrepresents certain demographic groups. What should the PM recommend? | Wait until a perfect, unbiased dataset becomes available. | Only use the model for demographic groups well-represented in the data. | Use the dataset as-is since it's the most available. | Supplement the dataset with additional data to improve representation, implement bias detection techniques, and document known limitations. |  | D | The practical approach to biased training data is to supplement it, implement bias detection, and document limitations. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | AI 모델 학습에 가장 가용한 데이터셋에 인구통계학적 편향이 포함되어 있을 때 PM은 무엇을 해야 하는가? | 완벽하고 편향 없는 데이터셋이 가용할 때까지 기다린다 | 데이터에 잘 표현된 인구통계 그룹에만 모델을 사용한다 | 가장 가용하므로 데이터셋을 그대로 사용한다 | 대표성을 개선하기 위해 추가 데이터로 보충하고, 편향 감지 기법을 구현하며, 제한사항을 문서화한다 |  | D | 편향된 학습 데이터에 대한 실용적 접근은 보충, 편향 감지 구현, 제한사항 문서화이다. 완벽 대기(A)는 비현실적이다. 제한 사용(B)은 차별적이다. 그대로 사용(C)은 비윤리적이다.
2161 | An organization is implementing AI across all projects and asks the PMO to develop an AI governance framework. Which element is LEAST important to include? | A ranking of the best AI vendors in the market. | Data privacy and security standards for AI tools. | Decision authority framework for when AI recommendations conflict with human judgment. | Ethical guidelines for AI usage in projects. |  | A | An AI governance framework should include ethical guidelines, data privacy standards, and decision authority frameworks. A vendor ranking is a procurement activity, not a governance element. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PMO가 AI 거버넌스 프레임워크를 개발할 때 포함되지 않아야 하는 요소는? | 시장 최고 AI 벤더 순위 | AI 도구에 대한 데이터 프라이버시 및 보안 표준 | AI 권고가 인간 판단과 충돌할 때의 결정 권한 프레임워크 | 프로젝트에서 AI 사용에 대한 윤리 지침 |  | A | AI 거버넌스 프레임워크는 윤리 지침, 데이터 프라이버시 표준, 결정 권한 프레임워크를 포함해야 한다. 벤더 순위(A)는 조달 활동이지 거버넌스 요소가 아니다.
2162 | A project manager is considering using AI for stakeholder sentiment analysis during a complex organizational change project. The AI tool requires access to email and chat data. What should the PM prioritize? | Obtaining proper authorization, ensuring data privacy compliance, and establishing transparent communication about the AI's role to all affected parties. | Training only the communication team on the tool. | Selecting the cheapest AI tool available. | Getting the fastest implementation timeline. |  | A | When AI requires access to personal communication data, authorization, privacy compliance, and transparency are paramount. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | AI | 복잡한 조직 변화 프로젝트에서 AI를 이해관계자 감성 분석에 사용하려 할 때 가장 중요한 첫 단계는? | 적절한 승인 획득, 데이터 프라이버시 준수 보장, 모니터링 대상자와의 투명한 커뮤니케이션 수립 | 커뮤니케이션 팀만 도구에 대해 교육한다 | 가장 저렴한 AI 도구를 선택한다 | 가장 빠른 구현 일정을 확보한다 |  | A | AI가 개인 커뮤니케이션 데이터에 접근해야 할 때, 승인, 프라이버시 준수, 투명성이 가장 중요하다. 팀만 교육(B)은 불충분하다. 최저 비용(C)은 품질을 무시한다. 최단 일정(D)은 거버넌스를 무시한다.
2163 | A project manager is using AI to generate progress reports. The AI produces a report that highlights a critical risk that the PM had previously assessed as low probability. Upon investigation, the PM finds the AI identified a new pattern in the data. What lesson does this demonstrate? | AI reports should not be reviewed since they are algorithmically generated. | AI can detect patterns in data that humans may miss, making it a valuable complement to human risk assessment. | AI should be the sole source of risk assessments. | Human risk assessments are unreliable. |  | B | This scenario demonstrates AI's strength in pattern detection—identifying risks that human analysts might miss due to cognitive biases or data volume. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Monitoring & Controlling | Adopt a Holistic View | Monitor Risks | AI | AI가 진행 보고서에서 인간 분석가가 놓친 중요 리스크를 감지했다. 이것은 무엇을 보여주는가? | AI 보고서는 알고리즘으로 생성되므로 검토할 필요가 없다 | AI는 인간이 놓칠 수 있는 데이터 패턴을 감지할 수 있어 인간 리스크 평가의 가치 있는 보완이 된다 | AI가 리스크 평가의 유일한 소스여야 한다 | 인간 리스크 평가는 신뢰할 수 없다 |  | B | 이 시나리오는 AI의 패턴 감지 강점을 보여준다—인지 편향이나 데이터 양으로 인해 인간 분석가가 놓칠 수 있는 리스크를 식별한다. 검토 불필요(A)는 위험하다. 유일한 소스(C)는 과도하다. 인간 불신뢰(D)는 부정확하다.
2164 | A Scrum team is exploring using AI to automatically generate user stories from customer feedback. What should the product owner be MOST concerned about? | Whether the development team will accept AI-generated stories. | Whether AI-generated stories accurately capture customer intent, maintain proper story structure (As a/I want/So that), and reflect business value priorities. | Whether the AI tool costs more than manual story writing. | Whether the AI can generate stories faster than the team can develop them. |  | B | The product owner's primary concern should be the quality of AI-generated user stories—accuracy of customer intent, proper structure, and alignment with business value priorities. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | 스크럼 팀이 고객 피드백에서 AI로 사용자 스토리를 자동 생성하려 할 때 제품 책임자의 주요 관심사는? | 개발 팀이 AI 생성 스토리를 수용할지 | AI 생성 스토리가 고객 의도를 정확히 포착하고, 적절한 스토리 구조를 유지하며, 비즈니스 가치 우선순위와 일치하는지 | AI 도구가 수동 스토리 작성보다 비용이 더 드는지 | AI가 팀이 개발할 수 있는 것보다 빠르게 스토리를 생성할 수 있는지 |  | B | 제품 책임자의 주요 관심사는 AI 생성 사용자 스토리의 품질—고객 의도의 정확성, 적절한 구조, 비즈니스 가치 우선순위와의 일치—이어야 한다. 팀 수용(A)은 부차적이다. 비용(C)은 품질보다 중요하지 않다. 속도(D)는 품질보다 우선하지 않는다.
2165 | A project manager is building a business case for implementing AI tools across the project portfolio. Which metric would BEST demonstrate the value of AI investment to senior leadership? | Measurable improvements in project delivery metrics (schedule adherence, cost variance, defect rates) before and after AI implementation. | Number of team members trained on AI tools. | Number of AI tools implemented. | Amount of money spent on AI tools. |  | A | The most compelling business case compares measurable project delivery improvements before and after AI implementation. Senior leadership cares about results, not activities. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | AI | PM이 프로젝트 포트폴리오 전체에 AI 도구 도입을 위한 비즈니스 케이스를 구축할 때 고위 리더십을 가장 설득하는 지표는? | AI 구현 전후의 프로젝트 납품 지표(일정 준수, 비용 차이, 결함률)의 측정 가능한 개선 | AI 도구에 대해 교육받은 팀원 수 | 구현된 AI 도구 수 | AI 도구에 지출한 금액 |  | A | 가장 설득력 있는 비즈니스 케이스는 AI 구현 전후의 측정 가능한 프로젝트 납품 개선을 비교한다. 고위 리더십은 활동이 아닌 결과에 관심이 있다. 교육 인원(B)은 활동 지표이다. 도구 수(C)도 활동이다. 지출 금액(D)은 투자이지 결과가 아니다.
2166 | During an agile retrospective, a team member raises concern that AI tools are making junior team members overly dependent on automated suggestions and hindering their skill development. What should the Scrum Master do? | Assign junior members to non-AI projects for training. | Dismiss the concern since AI tools improve overall productivity. | Remove all AI tools from the team's workflow. | Facilitate a team discussion on balancing AI assistance with skill development, and implement guidelines for when to use AI versus manual methods. |  | D | The concern about AI dependency hindering skill development is valid and worth addressing. A balanced approach allows the team to benefit from AI while ensuring professional growth. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | AI | 애자일 회고에서 팀원이 AI 도구가 주니어 팀원을 과도하게 의존적으로 만든다고 우려한다. PM은 무엇을 해야 하는가? | 주니어 멤버를 비AI 프로젝트에 배정하여 훈련한다 | AI 도구가 전체 생산성을 향상시키므로 우려를 무시한다 | 팀 워크플로에서 모든 AI 도구를 제거한다 | AI 지원과 기술 개발의 균형에 대해 팀 토론을 촉진하고 지침을 구현한다 |  | D | AI 의존이 기술 개발을 저해한다는 우려는 타당하며 다루어야 한다. 균형 잡힌 접근이 팀이 AI 혜택을 누리면서 전문 성장을 보장한다. 비AI 프로젝트 배정(A)은 격리이다. 무시(B)는 비생산적이다. 도구 제거(C)는 과도하다.
2167 | A project team uses an AI-powered risk simulation tool that runs Monte Carlo simulations in real-time. The tool generates probability distributions for project completion dates. A stakeholder asks for a single definitive completion date. What should the PM communicate? | Average all simulation dates and provide that as the definitive date. | Provide the most optimistic date from the simulation. | Explain that AI simulations provide probability ranges, present the P50 and P80 dates with their confidence levels, and help the stakeholder understand the trade-offs. | Provide the most pessimistic date to set conservative expectations. |  | C | AI-based Monte Carlo simulations provide probability distributions, not single dates. The PM should educate stakeholders on probabilistic scheduling, presenting P50 and P80 dates. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Critical Path/Schedule Mgmt | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | AI | AI 리스크 시뮬레이션 도구가 몬테카를로 시뮬레이션을 실행하여 여러 완료일을 생성했다. 이해관계자가 하나의 날짜를 요청한다. PM은 무엇을 해야 하는가? | 모든 시뮬레이션 날짜의 평균을 확정 날짜로 제공한다 | 시뮬레이션에서 가장 낙관적인 날짜를 제공한다 | AI 시뮬레이션이 확률 범위를 제공한다고 설명하고, P50과 P80 날짜를 신뢰도와 함께 제시한다 | 보수적 기대를 설정하기 위해 가장 비관적인 날짜를 제공한다 |  | C | AI 기반 몬테카를로 시뮬레이션은 단일 날짜가 아닌 확률 분포를 제공한다. PM은 이해관계자에게 확률적 일정 관리를 교육하고 P50과 P80 날짜를 제시해야 한다. 평균(A)은 확률을 무시한다. 낙관적(B)은 리스크를 과소평가한다. 비관적(D)은 과도하게 보수적이다.
2168 | A project manager notices that AI-recommended process improvements consistently favor efficiency over team well-being. What action should the PM take? | Ask team members to adjust to the more efficient processes. | Configure the AI tool to include team well-being metrics (workload balance, overtime hours, satisfaction scores) in its optimization criteria. | Ignore AI recommendations entirely. | Implement all AI recommendations to maximize efficiency. |  | B | AI optimization criteria should be holistic, including both efficiency and human factors. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | AI | AI 프로세스 개선 권고가 팀 웰빙보다 효율성을 지속적으로 선호할 때 PM은 무엇을 해야 하는가? | 팀원에게 더 효율적인 프로세스에 적응하도록 요청한다 | AI 도구가 팀 웰빙 지표(작업량 균형, 초과근무 시간, 만족도)를 포함하도록 설정한다 | AI 권고를 완전히 무시한다 | 효율성을 극대화하기 위해 모든 AI 권고를 구현한다 |  | B | AI 최적화 기준은 효율성과 인적 요소를 모두 포함하는 전체론적이어야 한다. 적응 요청(A)은 웰빙을 무시한다. 완전 무시(C)는 가치를 잃는다. 모두 구현(D)은 팀에 해로울 수 있다.
2169 | Which of the following BEST describes the concept of 'data literacy' as emphasized in PMBOK 8th Edition in the context of AI? | The ability to build machine learning models from scratch. | The ability to read, understand, interpret, and communicate data-driven insights to make informed project decisions. | The ability to store and manage large databases. | The ability to write complex SQL queries and programming code. |  | B | Data literacy in the context of AI and PMBOK 8th Edition refers to the ability to understand, interpret, and communicate data-driven insights for decision-making. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | AI | PMBOK 8판에서 AI 맥락의 '데이터 리터러시' 개념을 가장 잘 설명하는 것은? | 처음부터 머신러닝 모델을 구축하는 능력 | 데이터 기반 인사이트를 읽고, 이해하고, 해석하고, 소통하여 정보에 기반한 프로젝트 결정을 내리는 능력 | 대규모 데이터베이스를 저장하고 관리하는 능력 | 복잡한 SQL 쿼리와 프로그래밍 코드를 작성하는 능력 |  | B | AI와 PMBOK 8판 맥락에서 데이터 리터러시는 의사결정을 위해 데이터 기반 인사이트를 이해, 해석, 소통하는 능력을 말한다. ML 구축(A)은 기술적이다. DB 관리(C)는 IT 기능이다. 코드 작성(D)은 개발 기술이다.
2170 | A project manager is planning a new construction project. The organization has adopted the PMBOK 8th Edition's 'Integrate Sustainability' principle. What should the PM do FIRST? | Wait for regulatory requirements before considering sustainability. | Focus only on minimizing project costs. | Assign sustainability responsibilities to the environmental department only. | Conduct an environmental impact assessment and incorporate sustainability criteria into the project charter and scope definition. |  | D | The 'Integrate Sustainability' principle in PMBOK 8th Edition requires proactive consideration of environmental, social, and economic impacts from project initiation. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Compliance | Governance | Initiating | Integrate Sustainability | Develop Project Charter | Sustainability | PMBOK 8판의 '지속가능성 통합' 원칙을 적용하여 건설 프로젝트를 계획 중이다. PM은 무엇을 먼저 해야 하는가? | 규제 요구사항이 나올 때까지 지속가능성 고려를 기다린다 | 프로젝트 비용 최소화에만 집중한다 | 환경부서에만 지속가능성 책임을 할당한다 | 환경 영향 평가를 실시하고 지속가능성 기준을 프로젝트 선정 기준에 통합한다 |  | D | PMBOK 8판의 '지속가능성 통합' 원칙은 프로젝트 착수부터 환경, 사회, 경제적 영향을 사전적으로 고려할 것을 요구한다. 규제 대기(A)는 수동적이다. 비용만(B)은 제한적이다. 환경부서만(C)은 부분적이다.
2171 | During project planning, a stakeholder requests that the project minimize its carbon footprint. The project team has no experience with green project management. What is the BEST approach? | Reject the request as it is outside the project scope. | Promise zero carbon emissions without assessing feasibility. | Hire a sustainability consultant to assess the project's environmental impact and develop practical green strategies that the team can implement. | Add a generic sustainability statement to the project plan without specific actions. |  | C | When the team lacks sustainability expertise, bringing in a specialist is the appropriate response. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Stakeholders | Planning | Integrate Sustainability | Plan Stakeholder Engagement | Sustainability | 이해관계자가 프로젝트의 탄소 발자국 최소화를 요청하지만 팀에 경험이 없을 때 PM은 무엇을 해야 하는가? | 프로젝트 범위 밖이라며 요청을 거부한다 | 실현 가능성 평가 없이 탄소 제로 배출을 약속한다 | 지속가능성 컨설턴트를 고용하여 프로젝트의 환경 영향을 평가하고 실용적 전략을 개발한다 | 구체적 조치 없이 일반적 지속가능성 성명을 프로젝트 계획에 추가한다 |  | C | 팀에 지속가능성 전문성이 부족할 때 전문가를 영입하는 것이 적절한 대응이다. 거부(A)는 이해관계자 요구를 무시한다. 무평가 약속(B)은 무책임하다. 일반 성명(D)은 실질적이지 않다.
2172 | A project team is selecting materials for a product development project. Option A is cheaper but has high environmental impact. Option B costs 15% more but is sustainably sourced with minimal environmental impact. What should the project manager recommend? | Always choose Option B regardless of budget constraints. | Present both options with a full cost-benefit analysis including environmental impact, long-term costs, and alignment with organizational sustainability goals to the sponsor for decision-making. | Let the procurement team decide independently. | Always choose Option A to minimize project costs. |  | B | Sustainable decision-making requires a holistic cost-benefit analysis that includes environmental impact alongside financial considerations. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 제품 개발에서 Option A(저렴하지만 환경 영향 높음)와 Option B(비싸지만 환경 친화적)를 선택해야 할 때 PM은 무엇을 해야 하는가? | 예산 제약에 관계없이 항상 Option B를 선택한다 | 환경 영향, 장기 비용, 이해관계자 가치를 포함한 전체 비용-편익 분석과 함께 두 옵션을 제시한다 | 조달팀이 독립적으로 결정하게 한다 | 프로젝트 비용을 최소화하기 위해 항상 Option A를 선택한다 |  | B | 지속가능한 의사결정은 재정적 고려와 함께 환경 영향을 포함하는 전체론적 비용-편익 분석이 필요하다. 항상 B(A)는 비현실적이다. 조달팀 독립 결정(C)은 PM 역할을 무시한다. 항상 A(D)는 지속가능성을 무시한다.
2173 | An agile project team is developing a software product. A team member suggests implementing energy-efficient coding practices to reduce the application's server power consumption. What should the project manager do? | Leave it to individual developers to decide. | Implement it only if it doesn't add any development time. | Include energy-efficient coding as a non-functional requirement, add it to the definition of done, and track energy metrics as a quality indicator. | Reject the idea as software sustainability is not a project management concern. |  | C | Software sustainability, including energy efficiency, is increasingly recognized as a quality attribute. Formalizing it as a non-functional requirement ensures consistent implementation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 소프트웨어 개발 시 에너지 효율적 코딩 관행을 팀원이 제안한다. PM은 무엇을 해야 하는가? | 개별 개발자가 결정하게 한다 | 개발 시간이 추가되지 않는 경우에만 구현한다 | 에너지 효율적 코딩을 비기능 요구사항으로 포함하고, 완료 정의에 추가하며, 관련 지표를 추적한다 | 소프트웨어 지속가능성은 프로젝트 관리 관심사가 아니라며 아이디어를 거부한다 |  | C | 에너지 효율을 포함한 소프트웨어 지속가능성은 점점 품질 속성으로 인정되고 있다. 비기능 요구사항으로 공식화하면 일관된 구현을 보장한다. 개별 결정(A)은 일관성이 없다. 시간 미추가시만(B)은 제한적이다. 거부(D)는 부적절하다.
2174 | A project manager is closing a large infrastructure project. What sustainability-related activity should be included in the project closure? | Only document the project's financial performance. | Archive all sustainability documents without review. | Conduct a sustainability assessment documenting environmental impact metrics, lessons learned on sustainable practices, and recommendations for future projects. | Transfer sustainability responsibilities to the operations team without documentation. |  | C | Project closure should include a sustainability assessment to capture environmental metrics, lessons learned, and recommendations. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Predictive | Traditional Plan-Driven | Process | Develop Integrated PM Plan | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 대규모 인프라 프로젝트 종료 시 지속가능성 관련 활동으로 포함해야 하는 것은? | 프로젝트의 재무 성과만 문서화한다 | 검토 없이 모든 지속가능성 문서를 보관한다 | 환경 영향 지표, 지속가능성 교훈, 향후 프로젝트 권고를 문서화하는 지속가능성 평가를 실시한다 | 문서화 없이 운영 팀에 지속가능성 책임을 이관한다 |  | C | 프로젝트 종료 시 환경 지표, 교훈, 권고를 포착하는 지속가능성 평가를 포함해야 한다. 재무만(A)은 불완전하다. 무검토 보관(B)은 가치가 없다. 무문서 이관(D)은 지식을 잃는다.
2175 | A project sponsor asks the project manager to reduce the project's environmental sustainability measures to cut costs by 10%. What should the PM do? | Explain the long-term costs of reduced sustainability (regulatory risks, reputation damage, lifecycle costs), present alternative cost-reduction options, and escalate if needed. | Immediately comply with the sponsor's request. | Reduce sustainability measures but don't document the change. | Ignore the sponsor's request and maintain all sustainability measures. |  | A | The PM should advocate for sustainability by explaining long-term implications including regulatory risks, reputation damage, and lifecycle costs. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Integrate Sustainability | Manage Stakeholder Engagement | Sustainability | 프로젝트 스폰서가 비용 절감을 위해 환경 지속가능성 조치를 줄이라고 요청할 때 PM은 무엇을 해야 하는가? | 지속가능성 감소의 장기 비용(규제 리스크, 평판 손상, 수명주기 비용)을 설명하고 대안을 제안한다 | 스폰서의 요청을 즉시 따른다 | 지속가능성 조치를 줄이되 변경을 문서화하지 않는다 | 스폰서의 요청을 무시하고 모든 지속가능성 조치를 유지한다 |  | A | PM은 규제 리스크, 평판 손상, 수명주기 비용을 포함한 장기적 함의를 설명하여 지속가능성을 옹호해야 한다. 즉시 따르기(B)는 장기 리스크를 무시한다. 무문서 축소(C)는 비윤리적이다. 무시(D)는 스폰서 관계를 훼손한다.
2176 | Which of the following BEST represents the 'Integrate Sustainability' principle from PMBOK 8th Edition? | Project managers should consider environmental, social, and economic impacts when planning, executing, and closing projects, making sustainability part of decision-making. | Sustainability is an optional consideration that only applies to environmental projects. | Sustainability is solely the responsibility of the organization's CSR department. | Sustainability only means reducing paper usage in project documentation. |  | A | The 'Integrate Sustainability' principle encompasses environmental, social, and economic dimensions across all project phases. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | PMBOK 8판의 '지속가능성 통합' 원칙을 가장 잘 나타내는 것은? | PM은 프로젝트 계획, 실행, 전달 시 환경, 사회, 경제적 영향을 고려해야 한다 | 지속가능성은 환경 프로젝트에만 적용되는 선택적 고려사항이다 | 지속가능성은 조직의 CSR 부서만의 책임이다 | 지속가능성은 프로젝트 문서의 종이 사용 줄이기만을 의미한다 |  | A | 지속가능성 통합' 원칙은 모든 프로젝트 단계에 걸쳐 환경, 사회, 경제적 차원을 포괄한다. 선택적(B)은 부정확하다. CSR만(C)은 범위가 좁다. 종이만(D)은 극히 제한적이다.
2177 | A construction project team identifies that using recycled concrete would reduce environmental impact by 40% but increase material costs by 8% and add 2 weeks to the schedule. How should the PM handle this trade-off? | Use recycled concrete only for non-structural elements. | Conduct a triple bottom line analysis (economic, environmental, social), present the findings to the governance board, and recommend based on organizational sustainability commitments. | Reject recycled concrete since it increases costs and schedule. | Use recycled concrete without informing the sponsor about the cost and schedule impact. |  | B | A triple bottom line analysis considers economic, environmental, and social dimensions, providing a comprehensive basis for decision-making. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 재활용 콘크리트 사용이 환경 영향을 40% 줄이지만 비용 15% 증가, 일정 3주 연장일 때 PM은 무엇을 해야 하는가? | 비구조적 요소에만 재활용 콘크리트를 사용한다 | 트리플 바텀 라인 분석(경제, 환경, 사회)을 수행하고 결과를 이해관계자에게 제시하며 정보에 기반한 결정을 촉진한다 | 비용과 일정이 증가하므로 재활용 콘크리트를 거부한다 | 비용과 일정 영향을 알리지 않고 재활용 콘크리트를 사용한다 |  | B | 트리플 바텀 라인 분석은 경제, 환경, 사회적 차원을 고려하여 의사결정의 포괄적 기초를 제공한다. 비구조만(A)은 부분적이다. 거부(C)는 환경 혜택을 무시한다. 무통보(D)는 비윤리적이다.
2178 | A project manager is developing a risk register for a renewable energy project. What type of risk is UNIQUE to sustainable projects? | Schedule delays. | Stakeholder conflict. | Budget overruns. | Greenwashing risk—where sustainability claims made by the project are exaggerated or unverifiable, leading to reputational and regulatory consequences. |  | D | Greenwashing risk—exaggerating or misrepresenting sustainability achievements—is unique to projects with sustainability goals. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Sustainability | 재생 에너지 프로젝트의 리스크 등록부에서 지속가능성에 고유한 리스크 유형은? | 일정 지연 | 이해관계자 갈등 | 예산 초과 | 그린워싱 리스크—프로젝트의 지속가능성 주장이 과장되거나 검증 불가능하여 평판과 규제 리스크를 초래 |  | D | 그린워싱 리스크—지속가능성 성과를 과장하거나 허위 표현하는 것—은 지속가능성 목표가 있는 프로젝트에 고유하다. 일정 지연(A), 갈등(B), 예산 초과(C)는 모든 프로젝트에 공통이다.
2179 | An organization requires all projects to report their carbon emissions as part of project performance reporting. The PM is unsure how to measure this. What is the BEST approach? | Delegate the measurement to the finance department. | Report zero emissions since the project is primarily office-based. | Establish a carbon measurement baseline, identify key emission sources specific to the project, use recognized standards (such as GHG Protocol), and track emissions throughout the project lifecycle. | Estimate carbon emissions based on general industry averages. |  | C | Accurate carbon measurement requires a structured approach: establishing baselines, identifying project-specific emission sources, using recognized standards like the GHG Protocol, and continuous tracking. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 조직이 모든 프로젝트에 탄소 배출량 보고를 요구한다. PM은 어떻게 측정해야 하는가? | 재무부서에 측정을 위임한다 | 사무실 기반 프로젝트이므로 배출량 제로를 보고한다 | 탄소 측정 기준선을 설정하고, 프로젝트별 주요 배출원을 식별하며, GHG 프로토콜 같은 인정된 표준을 사용하고, 지속적으로 추적한다 | 일반적 산업 평균에 기반하여 탄소 배출량을 추정한다 |  | C | 정확한 탄소 측정은 구조화된 접근이 필요하다: 기준선 설정, 프로젝트별 배출원 식별, GHG 프로토콜 같은 인정된 표준 사용, 지속적 추적. 재무 위임(A)은 부적절하다. 제로 보고(B)는 부정확하다. 산업 평균(D)은 프로젝트별 정확성이 부족하다.
2180 | A project team is designing a new office building. The architect proposes green building certification (LEED). The client says sustainability is nice but not a priority. How should the PM position sustainability? | Drop green certification since the client doesn't prioritize it. | Present the business case for green certification including long-term energy savings, higher property values, tenant attraction, and regulatory preparedness, letting the client make an informed decision. | Implement only the cheapest sustainability features. | Include green certification without telling the client to avoid debate. |  | B | The PM should present a compelling business case that connects sustainability to tangible business benefits. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Predictive | Traditional Plan-Driven | People | Engage Stakeholders | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Sustainability | 신규 사무실 건물 설계에서 건축가가 LEED 인증을 제안하지만 클라이언트가 우선시하지 않을 때 PM은 무엇을 해야 하는가? | 클라이언트가 우선시하지 않으므로 그린 인증을 포기한다 | 장기 에너지 절감, 자산 가치 상승, 세입자 매력을 포함한 그린 인증의 비즈니스 케이스를 제시한다 | 가장 저렴한 지속가능성 기능만 구현한다 | 논쟁을 피하기 위해 클라이언트에게 알리지 않고 그린 인증을 포함한다 |  | B | PM은 지속가능성을 실질적 비즈니스 혜택과 연결하는 설득력 있는 비즈니스 케이스를 제시해야 한다. 포기(A)는 가치를 잃는다. 최저 비용만(C)은 제한적이다. 무통보(D)는 비윤리적이다.
2181 | A manufacturing project produces significant waste. The PM implements a waste reduction program that decreases waste by 30% but slows production by 5%. How should this be reported to stakeholders? | Report only the production slowdown as a concern. | Report both the environmental benefit (30% waste reduction) and the production impact (5% slowdown) transparently, along with plans to optimize the balance. | Report only the positive waste reduction achievement. | Wait until both metrics improve before reporting. |  | B | Transparent reporting of both positive and negative impacts is essential for stakeholder trust and informed decision-making. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Monitoring & Controlling | Integrate Sustainability | Monitor Communications | Sustainability | 제조 프로젝트에서 폐기물 30% 감소 프로그램이 생산 5% 둔화를 초래할 때 PM은 어떻게 보고해야 하는가? | 생산 둔화만 우려로 보고한다 | 환경 혜택(30% 폐기물 감소)과 생산 영향(5% 둔화)을 모두 투명하게 보고하고 이해관계자가 결정하도록 한다 | 긍정적 폐기물 감소 성과만 보고한다 | 두 지표 모두 개선될 때까지 보고를 기다린다 |  | B | 긍정적 및 부정적 영향 모두의 투명한 보고가 이해관계자 신뢰와 정보에 기반한 의사결정에 필수적이다. 둔화만(A)은 편향적이다. 감소만(C)은 불완전하다. 대기(D)는 적시성이 부족하다.
2182 | A project team is evaluating vendors for a supply chain project. One vendor has lower costs but poor ESG (Environmental, Social, Governance) ratings. Another vendor has higher costs but excellent ESG ratings. What evaluation criteria should the PM use? | Include ESG criteria as weighted factors in the vendor evaluation scorecard alongside cost, quality, and delivery performance. | Exclude ESG from vendor evaluation as it's not relevant to procurement. | Select the vendor with the highest ESG rating regardless of cost. | Select the vendor with the lowest cost regardless of ESG. |  | A | Modern procurement evaluation should include ESG criteria as weighted factors alongside traditional metrics. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 공급망 프로젝트에서 비용은 낮지만 ESG 등급이 나쁜 벤더와 비용은 높지만 ESG가 우수한 벤더를 평가할 때 PM은 무엇을 해야 하는가? | 비용, 품질, 납기와 함께 ESG 기준을 가중 요소로 벤더 평가 스코어카드에 포함한다 | ESG는 조달과 관련이 없으므로 벤더 평가에서 제외한다 | 비용에 관계없이 ESG 등급이 가장 높은 벤더를 선택한다 | ESG에 관계없이 비용이 가장 낮은 벤더를 선택한다 |  | A | 현대 조달 평가는 전통적 지표와 함께 ESG 기준을 가중 요소로 포함해야 한다. 제외(B)는 지속가능성을 무시한다. ESG만(C)은 비현실적이다. 비용만(D)은 제한적이다.
2183 | A project manager is leading a digital transformation project. How can sustainability be integrated into a software project? | Sustainability doesn't apply to software projects. | Consider server energy efficiency, optimize code for reduced computational resources, minimize data storage waste, and design for digital accessibility and inclusion. | Only use recycled hardware. | Print project documents on recycled paper. |  | B | Software sustainability includes energy-efficient computing, optimized code, minimized data waste, and digital accessibility. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 디지털 전환 프로젝트에서 지속가능성을 소프트웨어 프로젝트에 어떻게 통합할 수 있는가? | 지속가능성은 소프트웨어 프로젝트에 적용되지 않는다 | 서버 에너지 효율, 코드 최적화로 계산 자원 감소, 데이터 낭비 최소화, 디지털 접근성을 고려한다 | 재활용 하드웨어만 사용한다 | 재활용 종이에 프로젝트 문서를 인쇄한다 |  | B | 소프트웨어 지속가능성은 에너지 효율적 컴퓨팅, 최적화된 코드, 데이터 낭비 최소화, 디지털 접근성을 포함한다. 비적용(A)은 부정확하다. 하드웨어만(C)은 제한적이다. 종이(D)는 소프트웨어와 무관하다.
2184 | A project's environmental impact assessment reveals that a planned activity will damage a local wetland. The activity is on the critical path. What should the PM do? | Proceed but plan to restore the wetland after the project. | Cancel the entire project. | Proceed with the activity since it's on the critical path and delays are unacceptable. | Evaluate alternative approaches that avoid wetland damage, assess schedule and cost impacts of each alternative, and present options to the governance board. |  | D | Environmental damage requires evaluation of alternatives, even for critical path activities. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Compliance | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 환경 영향 평가에서 계획된 활동이 지역 습지를 손상시킬 것임이 밝혀졌다. 이 활동은 주공정선에 있다. PM은 무엇을 해야 하는가? | 진행하되 프로젝트 후 습지를 복원할 계획을 세운다 | 전체 프로젝트를 취소한다 | 주공정선에 있고 지연이 불가하므로 활동을 진행한다 | 습지 손상을 피하는 대안 접근법을 평가하고, 각 대안의 일정 및 비용 영향을 평가하여 이해관계자에게 제시한다 |  | D | 환경 피해는 주공정선 활동이라도 대안 평가가 필요하다. 후복원(A)은 예방보다 부적절하다. 전체 취소(B)는 과도하다. 무조건 진행(C)은 환경 책임을 무시한다.
2185 | A project team has reduced paper usage by 90% through digital workflows. The PM wants to report this as a sustainability achievement. What additional context should be included? | Also report the energy consumption of digital infrastructure (cloud storage, servers, devices) to provide a complete environmental picture. | Report only the paper reduction percentage. | Report the cost savings from reduced paper purchases. | Compare with other projects' paper usage. |  | A | Comprehensive sustainability reporting should consider the full environmental picture, including the energy costs of digital alternatives. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Monitoring & Controlling | Integrate Sustainability | Monitor Communications | Sustainability | 디지털 워크플로로 종이 사용 90% 감소를 지속가능성 성과로 보고할 때 무엇을 추가해야 하는가? | 전체 환경 상황을 제공하기 위해 디지털 인프라(클라우드 스토리지, 서버, 디바이스)의 에너지 소비도 보고한다 | 종이 감소 비율만 보고한다 | 종이 구매 감소에 따른 비용 절감을 보고한다 | 다른 프로젝트의 종이 사용과 비교한다 |  | A | 포괄적 지속가능성 보고는 디지털 대안의 에너지 비용을 포함한 전체 환경 상황을 고려해야 한다. 감소만(B)은 불완전하다. 비용 절감(C)은 환경이 아닌 재무이다. 비교(D)는 자체 영향을 다루지 않는다.
2186 | A project team is implementing a circular economy approach in a product design project. What does this mean for project scope? | Circular economy only applies to manufacturing projects. | The project should use only recycled materials. | The scope includes designing for product longevity, repairability, recyclability, and responsible end-of-life disposal from the initial design phase. | The project only needs to deliver the product; end-of-life considerations are out of scope. |  | C | A circular economy approach requires considering the entire product lifecycle—including longevity, repairability, recyclability, and end-of-life—during the design phase. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Integrate Sustainability | Define Scope | Sustainability | 순환 경제 접근법을 제품 설계 프로젝트에 적용하는 것은 범위에 무엇을 의미하는가? | 순환 경제는 제조 프로젝트에만 적용된다 | 프로젝트는 재활용 재료만 사용해야 한다 | 범위에 제품 수명, 수리 가능성, 재활용 가능성, 책임 있는 수명 종료 설계가 포함된다 | 프로젝트는 제품만 전달하면 되고 수명 종료 고려는 범위 밖이다 |  | C | 순환 경제 접근법은 설계 단계에서 수명, 수리 가능성, 재활용 가능성, 수명 종료를 포함한 전체 제품 수명주기를 고려해야 한다. 제조만(A)은 범위가 좁다. 재활용만(B)은 부분적이다. 범위 밖(D)은 순환 경제와 모순된다.
2187 | A project manager is developing a sustainability-focused project. The sponsor asks how to measure project sustainability performance. What framework should the PM recommend? | Track only financial ROI. | Implement a sustainability balanced scorecard that includes environmental KPIs (carbon emissions, waste, energy), social KPIs (safety, diversity, community impact), and economic KPIs (lifecycle cost, value delivery). | Measure sustainability qualitatively through annual surveys. | Use standard earned value management metrics only. |  | B | A sustainability balanced scorecard provides comprehensive measurement across environmental, social, and economic dimensions. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 지속가능성 중심 프로젝트에서 스폰서가 성과 측정 방법을 물을 때 PM은 무엇을 권고해야 하는가? | 재무 ROI만 추적한다 | 환경 KPI(탄소 배출, 폐기물 전환), 사회적 KPI(지역사회 영향, 직원 웰빙), 경제적 KPI를 포함하는 지속가능성 균형 성과표를 구현한다 | 연간 설문을 통해 지속가능성을 정성적으로 측정한다 | 표준 EVM 지표만 사용한다 |  | B | 지속가능성 균형 성과표는 환경, 사회, 경제적 차원에 걸쳐 포괄적 측정을 제공한다. 재무만(A)은 제한적이다. 정성적(C)은 불충분하다. EVM만(D)은 지속가능성을 다루지 않는다.
2188 | A project team discovers that a key project component has a significantly higher carbon footprint than initially estimated. The project is 60% complete. What should the PM do? | Continue as planned since the project is too far along to change. | Raise a change request to evaluate lower-carbon alternatives for the remaining work, assess schedule and cost implications, and update the sustainability plan. | Halt the project immediately until a green alternative is found. | Offset the carbon through tree planting without changing the project. |  | B | A formal change request evaluates alternatives while maintaining project governance. Even at 60% completion, there may be opportunities to reduce carbon impact. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Predictive-Agile Blend | Process | Develop Integrated PM Plan | Governance | Monitoring & Controlling | Integrate Sustainability | Monitor and Control Project Performance | Sustainability | 프로젝트 60% 완료 시 핵심 구성요소의 탄소 발자국이 초기 추정보다 크게 높음이 발견되었다. PM은 무엇을 해야 하는가? | 프로젝트가 너무 진행되어 변경할 수 없으므로 계획대로 계속한다 | 잔여 작업의 저탄소 대안을 평가하는 변경 요청을 제기하고 일정 및 비용 영향을 평가한다 | 녹색 대안을 찾을 때까지 프로젝트를 즉시 중단한다 | 프로젝트를 변경하지 않고 나무 심기로 탄소를 상쇄한다 |  | B | 공식적 변경 요청이 프로젝트 거버넌스를 유지하면서 대안을 평가한다. 60% 완료에서도 탄소 영향 감소 기회가 있을 수 있다. 계속(A)은 무책임하다. 즉시 중단(C)은 과도하다. 상쇄만(D)은 근본적 해결이 아니다.
2189 | A project manager needs to select a project delivery approach for a sustainable building project. The sustainability requirements are evolving as new green technologies emerge. Which approach is MOST appropriate? | A hybrid approach that uses predictive planning for structural elements and agile iterations for sustainability features that may evolve as green technologies advance. | A purely predictive (waterfall) approach with all requirements defined upfront. | A fully agile approach with no upfront planning. | Delay the project until all green technologies are finalized. |  | A | A hybrid approach best accommodates the stability of structural requirements with the evolving nature of sustainability features. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Tailored Approach | Process | Develop Integrated PM Plan | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Sustainability | 지속가능한 건물 프로젝트에서 구조 요구사항은 안정적이지만 녹색 기술은 진화하고 있을 때 어떤 접근법이 가장 적합한가? | 구조 요소에 예측형 계획, 지속가능성 기능에 애자일 이터레이션을 사용하는 하이브리드 접근법 | 모든 요구사항을 사전 정의하는 순수 예측형(폭포수) 접근법 | 사전 계획 없는 완전한 애자일 접근법 | 모든 녹색 기술이 확정될 때까지 프로젝트를 지연한다 |  | A | 하이브리드 접근법이 구조적 요구사항의 안정성과 지속가능성 기능의 진화하는 특성을 가장 잘 수용한다. 순수 예측형(B)은 유연성이 부족하다. 완전 애자일(C)은 구조에 부적합하다. 지연(D)은 비현실적이다.
2190 | A project's stakeholder analysis reveals that a local community group is concerned about the project's environmental impact. The group is not a contractual stakeholder. Should the PM engage them? | No, only contractual stakeholders need to be engaged. | Engage them only through legal representatives. | Only engage them if they file a formal complaint. | Yes, proactively engage the community group, understand their concerns, share environmental mitigation plans, and establish ongoing communication channels. |  | D | PMBOK 8th Edition's sustainability and stakeholder principles emphasize engaging all affected parties, not just contractual ones. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Integrate Sustainability | Manage Stakeholder Engagement | Sustainability | 이해관계자 분석에서 지역 커뮤니티 그룹이 프로젝트의 환경 영향을 우려한다. 참여해야 하는가? | 아니오, 계약 이해관계자만 참여시키면 된다 | 법적 대리인을 통해서만 참여시킨다 | 공식 불만을 제기하는 경우에만 참여시킨다 | 예, 커뮤니티 그룹에 사전적으로 참여하고, 우려를 이해하며, 환경 완화 계획을 공유하고, 소통 채널을 수립한다 |  | D | PMBOK 8판의 지속가능성과 이해관계자 원칙은 계약 당사자뿐 아니라 영향을 받는 모든 당사자의 참여를 강조한다. 계약만(A)은 제한적이다. 법적 대리만(B)은 간접적이다. 불만 시만(C)은 수동적이다.
2191 | An IT project manager is migrating on-premise servers to a cloud provider. Which sustainability consideration should be included in the vendor selection criteria? | The cloud provider's renewable energy usage, data center energy efficiency (PUE rating), carbon offset programs, and sustainability certifications. | The cloud provider's office location and building design. | Whether the cloud provider uses the latest hardware. | Only the cloud provider's pricing model. |  | A | Cloud migration has significant environmental implications. Evaluating providers on renewable energy usage, energy efficiency metrics, and carbon programs ensures alignment with sustainability goals. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 온프레미스 서버를 클라우드로 마이그레이션할 때 가장 우선 고려해야 할 지속가능성 사항은? | 클라우드 제공자의 재생 에너지 사용, 데이터 센터 에너지 효율(PUE 등급), 탄소 상쇄 프로그램 | 클라우드 제공자의 사무실 위치와 건물 설계 | 클라우드 제공자가 최신 하드웨어를 사용하는지 | 클라우드 제공자의 가격 모델만 |  | A | 클라우드 마이그레이션은 상당한 환경적 영향이 있다. 재생 에너지 사용, 에너지 효율 지표, 탄소 프로그램으로 제공자를 평가하면 지속가능성 목표와의 정렬을 보장한다. 사무실(B)은 무관하다. 하드웨어(C)는 부분적이다. 가격만(D)은 제한적이다.
2192 | A project manager is planning team travel for a distributed project. How can sustainability be incorporated into travel planning? | Only consider travel costs, not environmental impact. | Cancel all team meetings to avoid travel completely. | Allow unlimited travel since face-to-face meetings are more productive. | Prioritize virtual meetings, offset necessary travel emissions, choose sustainable transportation options, and batch in-person meetings to minimize total travel. |  | D | Sustainable travel planning balances the need for in-person collaboration with environmental responsibility. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Planning | Integrate Sustainability | Determine Budget | Sustainability | 분산 프로젝트의 팀 출장을 계획할 때 지속가능성을 어떻게 통합할 수 있는가? | 환경 영향이 아닌 출장 비용만 고려한다 | 출장을 완전히 피하기 위해 모든 팀 회의를 취소한다 | 대면 회의가 더 생산적이므로 무제한 출장을 허용한다 | 가상 회의를 우선하고, 필수 출장 배출을 상쇄하며, 지속가능한 교통 옵션을 선택한다 |  | D | 지속가능한 출장 계획은 대면 협업의 필요와 환경적 책임의 균형을 맞춘다. 비용만(A)은 환경을 무시한다. 모두 취소(B)는 비현실적이다. 무제한(C)은 무책임하다.
2193 | A project delivers a product that meets all functional requirements but has a high energy consumption rate during operation. From a PMBOK 8th Edition perspective, is the project successful? | Not entirely—PMBOK 8th Edition's sustainability principle suggests that project success should also consider the product's long-term environmental impact during its operational lifecycle. | Yes, operational energy consumption is not the project team's responsibility. | Yes, because all functional requirements are met. | No, the project is a complete failure. |  | A | PMBOK 8th Edition expands the definition of project success to include sustainability considerations beyond functional requirements. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 프로젝트가 모든 기능 요구사항을 충족하지만 운영 시 에너지 소비가 높다. 이 프로젝트는 성공인가? | 완전히는 아니다—PMBOK 8판의 지속가능성 원칙은 기능 요구사항을 넘어 지속가능성 고려를 포함해야 한다고 제안한다 | 예, 운영 에너지 소비는 프로젝트 팀의 책임이 아니다 | 예, 모든 기능 요구사항이 충족되었으므로 | 아니오, 프로젝트는 완전한 실패이다 |  | A | PMBOK 8판은 기능 요구사항을 넘어 지속가능성 고려를 포함하도록 프로젝트 성공의 정의를 확장한다. 책임 아님(B)은 현대적 관점에 반한다. 기능만(C)은 제한적이다. 완전 실패(D)는 과도하다.
2194 | A project team working on an agile software project wants to implement 'green sprints'—dedicated sprints focused solely on reducing the application's environmental footprint. What should the Scrum Master recommend? | Sustainability should never be part of sprint work. | Only address sustainability in the final sprint before release. | Dedicate every 5th sprint exclusively to sustainability improvements. | Integrate sustainability improvements into the regular backlog alongside feature work, applying the same prioritization criteria based on business and environmental value. |  | D | Rather than isolating sustainability into separate sprints, integrating it into the regular backlog ensures continuous attention. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Integrate Sustainability | Define Scope | Sustainability | 애자일 소프트웨어 프로젝트에서 '그린 스프린트'—지속가능성 개선에만 전념하는 스프린트—를 구현하려 할 때 가장 좋은 접근법은? | 지속가능성은 스프린트 작업의 일부가 되어서는 안 된다 | 릴리스 전 마지막 스프린트에서만 지속가능성을 다룬다 | 매 5번째 스프린트를 지속가능성 개선에 전용한다 | 기능 작업과 함께 일반 백로그에 지속가능성 개선을 통합하고, 지속적 우선순위 원칙을 적용한다 |  | D | 지속가능성을 별도 스프린트로 격리하기보다 일반 백로그에 통합하면 지속적 관심을 보장한다. 제외(A)는 부적절하다. 마지막만(B)은 너무 늦다. 매 5번째(C)는 불연속적이다.
2195 | During risk identification for a new facility construction project, the team identifies climate change impacts (flooding, extreme heat) as potential risks. How should these be categorized? | Categorize them as force majeure and exclude from risk management. | Only consider them if the project is in a known high-risk area. | Document them in the risk register as external environmental risks, assess probability and impact using climate data, and develop appropriate response strategies (avoid, mitigate, transfer). | Ignore them since they are acts of nature and uncontrollable. |  | C | Climate change risks should be formally documented and managed like any other project risk. Using climate data for probability/impact assessment demonstrates proactive risk management. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Sustainability | 신규 시설 건설 리스크 식별에서 기후변화 영향(홍수, 극한 기온)이 식별되었다. PM은 무엇을 해야 하는가? | 불가항력으로 분류하고 리스크 관리에서 제외한다 | 프로젝트가 알려진 고위험 지역에 있는 경우에만 고려한다 | 리스크 등록부에 외부 환경 리스크로 문서화하고, 기후 데이터를 사용하여 확률 및 영향을 평가한다 | 자연재해이며 통제 불가능하므로 무시한다 |  | C | 기후변화 리스크는 다른 프로젝트 리스크와 마찬가지로 공식적으로 문서화하고 관리해야 한다. 확률/영향 평가에 기후 데이터를 사용하는 것이 사전적 리스크 관리를 보여준다. 불가항력(A)은 관리를 포기한다. 고위험 지역만(B)은 제한적이다. 무시(D)는 무책임하다.
2196 | A project manager is leading a product launch project. Marketing wants to promote the product as 'eco-friendly.' The PM knows the product meets some sustainability criteria but not all. What should the PM advise? | Recommend that marketing claims be specific, verifiable, and accurately reflect the product's actual sustainability achievements to avoid greenwashing. | Reject all sustainability marketing claims. | Let the marketing department handle messaging without PM involvement. | Approve the marketing claim since the product meets some criteria. |  | A | Marketing sustainability claims must be specific, verifiable, and accurate to avoid greenwashing. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Sustainability | 제품 출시 시 마케팅이 '친환경'으로 홍보하려 할 때 PM은 어떻게 해야 하는가? | 마케팅 주장이 구체적이고, 검증 가능하며, 제품의 실제 환경 성과를 정확히 반영하도록 권고한다 | 모든 지속가능성 마케팅 주장을 거부한다 | PM 관여 없이 마케팅 부서가 메시지를 처리하게 한다 | 제품이 일부 기준을 충족하므로 마케팅 주장을 승인한다 |  | A | 지속가능성 마케팅 주장은 그린워싱을 피하기 위해 구체적이고, 검증 가능하며, 정확해야 한다. 모두 거부(B)는 과도하다. 무관여(C)는 리스크이다. 일부 충족(D)은 불충분한 근거이다.
2197 | An organization is developing sustainability KPIs for its project portfolio. Which KPI set is MOST comprehensive for tracking sustainability across projects? | A multi-dimensional set including carbon footprint, water usage, waste diversion rate, energy efficiency, supply chain sustainability score, social impact metrics, and sustainable procurement percentage. | Only carbon emissions per project. | Employee satisfaction with sustainability programs. | Only financial savings from green initiatives. |  | A | Comprehensive sustainability KPIs span multiple environmental, social, and economic dimensions. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 조직이 프로젝트 포트폴리오의 지속가능성 KPI를 개발할 때 가장 포괄적인 KPI 세트는? | 탄소 발자국, 물 사용, 폐기물 전환율, 에너지 효율, 사회적 영향 지표, 공급망 지속가능성 점수를 포함하는 다차원 세트 | 프로젝트당 탄소 배출만 | 지속가능성 프로그램에 대한 직원 만족도 | 녹색 이니셔티브로 인한 재무 절감만 |  | A | 포괄적 지속가능성 KPI는 여러 환경, 사회, 경제적 차원에 걸쳐야 한다. 탄소만(B)은 단차원이다. 만족도(C)는 간접적이다. 재무만(D)은 제한적이다.
2198 | A project manager is closing a 2-year infrastructure project. What sustainability deliverable should be included in the project handover to operations? | A list of sustainability regulations that apply to the facility. | Only the standard operations manual. | A sustainability operations guide including environmental monitoring procedures, energy management protocols, waste management plans, and sustainability performance baselines for the operations team to maintain. | A one-time environmental audit report. |  | C | A comprehensive sustainability operations guide ensures that environmental practices are maintained after project handover. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Predictive | Traditional Plan-Driven | Process | Develop Integrated PM Plan | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 2년간의 인프라 프로젝트 종료 시 인도에 포함해야 할 지속가능성 산출물은? | 시설에 적용되는 지속가능성 규정 목록 | 표준 운영 매뉴얼만 | 환경 모니터링 절차, 에너지 관리 프로토콜, 폐기물 처리 지침, 지속가능성 KPI를 포함하는 지속가능성 운영 가이드 | 일회성 환경 감사 보고서 |  | C | 포괄적 지속가능성 운영 가이드는 프로젝트 인도 후 환경 관행이 유지되도록 보장한다. 규정 목록(A)은 운영 지침이 아니다. 표준 매뉴얼(B)은 지속가능성을 포함하지 않는다. 일회성(D)은 지속적이지 않다.
2199 | A project team is using a hybrid approach for a green building project. The team finds that sustainability requirements keep evolving as new environmental regulations are announced. How should the PM manage this? | Switch entirely to an agile approach mid-project. | Freeze all sustainability requirements at the start of the project. | Maintain a dynamic sustainability backlog that is regularly updated based on regulatory changes, with formal change impact assessments for requirements affecting the predictive scope. | Ignore new regulations until the project is complete. |  | C | A dynamic sustainability backlog accommodates evolving requirements while formal change assessments maintain governance for scope-impacting changes. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Monitoring & Controlling | Integrate Sustainability | Control Scope | Sustainability | 그린 빌딩 프로젝트에서 지속가능성 요구사항이 규제 변경으로 지속 진화할 때 PM은 무엇을 해야 하는가? | 프로젝트 중간에 완전한 애자일 접근법으로 전환한다 | 프로젝트 시작 시 모든 지속가능성 요구사항을 동결한다 | 규제 변경에 따라 정기적으로 업데이트되는 동적 지속가능성 백로그를 유지하되, 범위에 영향을 미치는 변경에 대한 공식 변경 평가를 수행한다 | 프로젝트가 완료될 때까지 새 규제를 무시한다 |  | C | 동적 지속가능성 백로그가 진화하는 요구사항을 수용하면서 범위에 영향을 미치는 변경에 대한 공식 평가로 거버넌스를 유지한다. 완전 전환(A)은 불안정하다. 동결(B)은 비현실적이다. 무시(D)는 비준수 리스크이다.
2200 | A project manager discovers that the project's supply chain includes a tier-2 supplier using child labor. This was not identified during initial procurement planning. What should the PM do FIRST? | Document the issue for the lessons learned report at project closure. | Ask the tier-1 supplier to handle the issue without the PM's involvement. | Continue since the tier-2 supplier is not a direct contract partner. | Immediately notify the procurement team and organizational leadership, initiate an investigation, and evaluate alternative suppliers to address the social sustainability violation. |  | D | Social sustainability violations such as child labor require immediate action regardless of the supply chain tier. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Business Environment | Plan and Manage Compliance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Sustainability | 프로젝트 공급망에서 2차 공급자가 아동 노동을 사용하는 것이 발견되었다. PM은 무엇을 해야 하는가? | 프로젝트 종료 시 교훈 보고서에 문제를 문서화한다 | 1차 공급자에게 PM 관여 없이 문제를 처리하도록 요청한다 | 2차 공급자가 직접 계약 파트너가 아니므로 계속한다 | 즉시 조달팀과 조직 리더십에 통보하고, 조사를 개시하며, 시정 조치를 개발한다 |  | D | 아동 노동 같은 사회적 지속가능성 위반은 공급망 단계에 관계없이 즉각적 조치가 필요하다. 종료 시 문서화(A)는 너무 늦다. 1차에 맡기기(B)는 책임을 회피한다. 계속(C)은 비윤리적이다.
2201 | A project team proposes using biodegradable packaging for the project's product deliverables. Testing reveals the biodegradable option degrades product protection by 10%. How should the PM approach this trade-off? | Delay the decision until more testing is available. | Evaluate whether the 10% degradation is within acceptable limits for the product type, explore hybrid packaging solutions, and involve quality and sustainability teams in the decision. | Use biodegradable packaging regardless of protection impact. | Choose conventional packaging since product protection is paramount. |  | B | Trade-offs between sustainability and functionality require careful evaluation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Executing | Embed Quality | Direct and Manage Project Work | Sustainability | 생분해성 포장이 제품 보호를 10% 저하시킬 때 PM은 무엇을 해야 하는가? | 더 많은 테스트가 가능할 때까지 결정을 지연한다 | 10% 저하가 제품 유형에 허용 범위 내인지 평가하고, 하이브리드 포장을 탐색하며, 비용-편익 분석을 실시한다 | 보호 영향에 관계없이 생분해성 포장을 사용한다 | 제품 보호가 최우선이므로 기존 포장을 선택한다 |  | B | 지속가능성과 기능 간 트레이드오프는 신중한 평가가 필요하다. 지연(A)은 결정을 미룬다. 무조건 사용(C)은 리스크를 무시한다. 무조건 기존(D)은 지속가능성을 무시한다.
2202 | A project manager notices that remote team members have significantly lower carbon footprints compared to office-based team members. How can this insight be leveraged? | Include remote work policies as a sustainability strategy, track carbon savings from reduced commuting, and use the data to support organizational sustainability reporting. | Only allow remote work for team members with long commutes. | Ignore the data since work arrangements are not a PM responsibility. | Force all team members to work remotely. |  | A | Remote work's sustainability benefits should be captured and reported as part of the project's environmental contribution. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Integrate Sustainability | Develop Team | Sustainability | 원격 팀원의 탄소 발자국이 사무실 기반보다 현저히 낮을 때 PM은 무엇을 해야 하는가? | 원격 근무 정책을 지속가능성 전략으로 포함하고, 통근 감소로 인한 탄소 절감을 추적하며, 결과를 보고한다 | 긴 통근 팀원에게만 원격 근무를 허용한다 | 근무 형태는 PM 책임이 아니므로 데이터를 무시한다 | 모든 팀원에게 원격 근무를 강제한다 |  | A | 원격 근무의 지속가능성 혜택은 프로젝트의 환경 기여로 포착하고 보고해야 한다. 긴 통근만(B)은 제한적이다. 무시(C)는 기회를 놓친다. 강제(D)는 과도하다.
2203 | An organization wants to embed sustainability into its project management methodology. What is the MOST effective approach? | Integrate sustainability considerations into every phase of the project lifecycle—from business case and charter to planning, execution, monitoring, and closure. | Add sustainability training to the annual PM conference. | Hire a Chief Sustainability Officer and make them responsible. | Create a separate sustainability checklist that PMs complete at project end. |  | A | Embedding sustainability means integrating it throughout the project lifecycle, not treating it as a separate checklist or afterthought. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | General | General PM Principles | Business Environment | Support Organizational Change | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 조직이 프로젝트 관리 방법론에 지속가능성을 내재화하고자 한다. 가장 효과적인 접근법은? | 비즈니스 케이스부터 종료까지 프로젝트 수명주기의 모든 단계에 지속가능성 고려사항을 통합한다 | 연례 PM 컨퍼런스에 지속가능성 교육을 추가한다 | 최고 지속가능성 책임자(CSO)를 고용하여 책임을 맡긴다 | PM이 프로젝트 종료 시 완료하는 별도의 지속가능성 체크리스트를 만든다 |  | A | 지속가능성 내재화는 별도의 체크리스트나 사후 고려가 아닌 프로젝트 수명주기 전반에 걸쳐 통합하는 것을 의미한다. 교육 추가(B)는 부분적이다. CSO 고용(C)은 책임을 한 사람에게 전가한다. 종료 시 체크리스트(D)는 사후 대응이다.
2204 | A project uses water-intensive processes. The project is located in a region experiencing drought. What should the PM include in the risk register? | Water risk is an operational concern, not a project risk. | Only schedule risk from potential water restrictions. | Water scarcity risk including regulatory restrictions, community opposition, reputational impact, increased water costs, and alternative water-sourcing strategies. | Only financial risk from increased water costs. |  | C | Water scarcity in drought regions presents multi-dimensional risks: regulatory, social, reputational, financial, and operational. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Integrate Sustainability | Identify Risks | Sustainability | 프로젝트가 물 집약적 공정을 사용한다. 프로젝트가 가뭄을 겪고 있는 지역에 위치한다. PM이 리스크 등록부에 무엇을 포함해야 하는가? | 물 리스크는 운영상 관심사이지 프로젝트 리스크가 아니다 | 잠재적 물 사용 제한으로 인한 일정 리스크만 | 규제 제한, 지역사회 반대, 평판 영향, 보험 등을 포함하는 물 부족 리스크 | 물 비용 증가로 인한 재무 리스크만 |  | C | 가뭄 지역의 물 부족은 다차원적 리스크를 제시한다: 규제적, 사회적, 평판적, 재무적, 운영적. 운영 관심사만(A)은 범위가 좁다. 일정 리스크만(B)은 부분적이다. 재무 리스크만(D)은 불완전하다.
2205 | A project manager is developing a scope statement for a wind farm project. Which sustainability consideration should be included that goes beyond traditional scope management? | Only the land acquisition requirements. | The project's net environmental impact including bird migration patterns, noise impact on nearby communities, visual landscape impact, and decommissioning plans for end-of-life turbines. | Only the energy output projections. | Only the number and capacity of wind turbines. |  | B | Sustainable scope management for a wind farm extends beyond energy output to include ecological impact, social impact, and lifecycle considerations. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | Traditional Plan-Driven | Process | Develop and Manage Scope | Scope | Planning | Integrate Sustainability | Define Scope | Sustainability | PM이 풍력 발전 프로젝트의 범위 기술서를 개발 중이다. 어떤 지속가능성 고려사항이 범위에 포함되어야 하는가? | 토지 취득 요구사항만 | 조류 이동 패턴, 인근 지역사회 소음 영향 등을 포함하는 프로젝트의 순 환경 영향 | 에너지 출력 전망만 | 풍력 터빈의 수와 용량만 |  | B | 풍력 발전 프로젝트의 지속가능한 범위 관리는 에너지 출력을 넘어 생태적 영향, 사회적 영향, 수명주기 고려사항을 포함한다. 토지 취득만(A), 에너지 출력만(C), 터빈 수만(D)은 모두 범위가 좁다.
2206 | A project team wants to implement a 'sustainability retrospective' at the end of each project phase. What topics should be covered? | Sustainability retrospectives are unnecessary—standard retrospectives are sufficient. | Only review whether the project stayed within the sustainability budget. | Review environmental performance metrics, identify sustainability lessons learned, recognize green achievements, and plan sustainability improvements for the next phase. | Only discuss what went wrong with sustainability efforts. |  | C | A sustainability retrospective should comprehensively review environmental metrics, capture lessons, celebrate achievements, and plan improvements. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Monitoring & Controlling | Integrate Sustainability | Monitor and Control Project Performance | Sustainability | 프로젝트 팀이 각 프로젝트 단계 종료 시 '지속가능성 회고'를 시행하고자 한다. 어떤 주제를 다루어야 하는가? | 지속가능성 회고는 불필요하다—표준 회고로 충분하다 | 프로젝트가 지속가능성 예산 내에 있었는지만 검토한다 | 환경 성과 지표 검토, 지속가능성 교훈 식별, 녹색 성과 인정, 개선 계획 수립 | 지속가능성 노력에서 잘못된 점만 논의한다 |  | C | 지속가능성 회고는 환경 지표를 종합적으로 검토하고, 교훈을 포착하고, 성과를 인정하며, 개선을 계획해야 한다. 불필요(A)는 지속가능성을 간과한다. 예산만(B)은 부분적이다. 잘못된 점만(D)은 부정적이다.
2207 | A project budget includes a 5% sustainability premium for eco-friendly materials. During execution, budget pressure mounts and the sponsor suggests eliminating this premium. What approach should the PM take? | Protect the sustainability budget at all costs, even if other deliverables are cut. | Present a value analysis showing the long-term benefits of the sustainability investment, explore creative cost optimization in other areas, and propose alternatives that maintain sustainability commitments. | Accept the cut but don't update the sustainability plan. | Immediately eliminate the sustainability premium. |  | B | The PM should advocate for sustainability through value-based arguments while being pragmatic about budget constraints. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Integrate Sustainability | Control Costs | Sustainability | 프로젝트 예산에 친환경 자재를 위한 5% 지속가능성 프리미엄이 포함되어 있다. 실행 중 예산 압박이 가중된다. PM은 무엇을 해야 하는가? | 다른 인도물이 삭감되더라도 지속가능성 예산을 어떤 대가를 치르더라도 보호한다 | 지속가능성 투자의 장기적 이점을 보여주는 가치 분석을 제시하고, 창의적 대안을 탐색한다 | 삭감을 수용하되 지속가능성 계획은 업데이트하지 않는다 | 지속가능성 프리미엄을 즉시 제거한다 |  | B | PM은 가치 기반 논거를 통해 지속가능성을 옹호하면서 예산 제약에 실용적이어야 한다. 무조건 보호(A)는 비현실적이다. 수용 후 미업데이트(C)는 무책임하다. 즉시 제거(D)는 지속가능성을 포기한다.
2208 | An organization requires all new projects to submit a Sustainability Impact Assessment (SIA) as part of the project initiation process. What should this assessment include? | Only the estimated carbon emissions of the project. | A statement that the project supports the organization's sustainability goals. | Assessment of the project's potential environmental, social, and economic impacts, identification of sustainability risks and opportunities, proposed mitigation measures, and sustainability KPIs. | Only a list of environmental regulations that apply to the project. |  | C | A comprehensive SIA covers all three dimensions of sustainability, identifies both risks and opportunities, proposes mitigations, and establishes measurable KPIs. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Initiating | Integrate Sustainability | Develop Project Charter | Sustainability | 조직이 모든 새 프로젝트에 지속가능성 영향 평가(SIA)를 프로젝트 착수의 일부로 제출하도록 요구한다. SIA에 무엇이 포함되어야 하는가? | 프로젝트의 예상 탄소 배출량만 | 프로젝트가 조직의 지속가능성 목표를 지원한다는 성명 | 프로젝트의 잠재적 환경, 사회, 경제적 영향 평가, 리스크 및 기회 식별, 완화 제안, 측정 가능한 KPI 설정 | 프로젝트에 적용되는 환경 규정 목록만 |  | C | 포괄적 SIA는 지속가능성의 세 가지 차원을 모두 다루고, 리스크와 기회를 식별하며, 완화 방안을 제안하고, 측정 가능한 KPI를 설정한다. 탄소만(A), 성명(B), 규정 목록만(D)은 모두 불완전하다.
2209 | A project team is using lean principles to reduce waste in a manufacturing project. They identify that 15% of raw materials are wasted during production. The team proposes investing in precision equipment that reduces waste to 3% but costs 20% more. What should the PM do? | Reject the investment since it increases costs. | Approve the investment immediately without financial analysis. | Implement partial waste reduction measures only. | Calculate the total cost of ownership including material savings, waste disposal cost reduction, environmental compliance benefits, and present a comprehensive business case. |  | D | A total cost of ownership analysis considers all dimensions—material savings, disposal costs, environmental compliance, and long-term operational benefits. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Lean | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Sustainability | 프로젝트 팀이 린 원칙을 사용하여 제조 프로젝트의 낭비를 줄이고 있다. 원자재 15%가 낭비된다. 폐기물 감소에 투자해야 하는가? | 비용이 증가하므로 투자를 거부한다 | 재무 분석 없이 즉시 투자를 승인한다 | 부분적 폐기물 감소 조치만 시행한다 | 자재 절감, 폐기물 처리 비용 절감, 환경 규정 준수, 장기 운영 이점을 포함하는 총소유비용을 계산한다 |  | D | 총소유비용 분석은 자재 절감, 처리 비용, 환경 준수, 장기 운영 이점 등 모든 차원을 고려한다. 투자 거부(A)는 장기적 가치를 무시한다. 분석 없는 승인(B)은 무책임하다. 부분 조치(C)는 최적화되지 않는다.
2210 | A project manager is leading a smart city initiative. Multiple projects within the program have overlapping sustainability goals. How should sustainability be managed across the program? | Establish a program-level sustainability framework with shared KPIs, coordinate cross-project sustainability initiatives, and consolidate sustainability reporting for the program. | Assign sustainability to the largest project only. | Let each project manage sustainability independently. | Create a separate sustainability project within the program. |  | A | Program-level sustainability management ensures coordination, avoids duplication, and maximizes collective impact. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Sustainability | PM이 스마트 시티 이니셔티브를 이끌고 있다. 프로그램 내 여러 프로젝트가 중복되는 지속가능성 목표를 가지고 있다. PM은 무엇을 해야 하는가? | 공유 KPI가 있는 프로그램 수준 지속가능성 프레임워크를 수립하고, 프로젝트 간 지속가능성 이니셔티브를 조정한다 | 가장 큰 프로젝트에만 지속가능성을 할당한다 | 각 프로젝트가 독립적으로 지속가능성을 관리하도록 한다 | 프로그램 내에 별도의 지속가능성 프로젝트를 만든다 |  | A | 프로그램 수준 지속가능성 관리는 조정을 보장하고, 중복을 방지하며, 집합적 영향을 극대화한다. 큰 프로젝트만(B)은 다른 프로젝트를 배제한다. 독립 관리(C)는 중복과 비효율을 야기한다. 별도 프로젝트(D)는 통합이 아니다.
2211 | A project's life cycle assessment (LCA) reveals that the operating phase accounts for 80% of the product's total environmental impact. The project team focused sustainability efforts primarily on the construction phase. What should the PM do? | Shift sustainability focus to include operational efficiency measures, design for lower operational impact, and establish sustainability monitoring protocols for the operating phase. | Complete the project as planned and recommend operational changes separately. | Accept the finding and document it for lessons learned. | The operating phase is outside the project's responsibility. |  | A | LCA findings should drive proactive changes. If 80% of environmental impact occurs during operations, the project should design for operational sustainability. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트의 수명주기 평가(LCA)에서 운영 단계가 제품 총 환경 영향의 80%를 차지함이 밝혀졌다. PM은 무엇을 해야 하는가? | 운영 효율성 조치를 포함하고, 운영 중 환경 영향이 낮도록 설계하는 방향으로 지속가능성 초점을 전환한다 | 계획대로 프로젝트를 완료하고 별도로 운영 변경을 권고한다 | 결과를 수용하고 교훈으로 문서화한다 | 운영 단계는 프로젝트 책임 범위 밖이다 |  | A | LCA 결과는 사전적 변경을 추진해야 한다. 환경 영향의 80%가 운영 중 발생하면, 프로젝트는 운영 지속가능성을 위해 설계해야 한다. 별도 권고(B)는 연결이 약하다. 문서화(C)는 수동적이다. 책임 밖(D)은 지속가능성을 무시한다.
2212 | A project team is developing a mobile application. How can the 'Integrate Sustainability' principle be applied to a purely digital product? | Optimize the app for energy efficiency (battery usage), minimize data transfer, design for device longevity (support older devices), and ensure digital accessibility for all user groups. | Sustainability doesn't apply to mobile applications. | Only use green-certified hosting providers. | Include a sustainability page in the app's documentation. |  | A | Digital sustainability encompasses energy efficiency, data optimization, device longevity, and accessibility. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트 팀이 모바일 앱을 개발 중이다. 순수 디지털 프로젝트에 '지속가능성 통합' 원칙을 어떻게 적용할 수 있는가? | 에너지 효율성(배터리 사용)을 위해 앱을 최적화하고, 데이터 전송을 최소화하며, 기기 수명을 위해 설계하고, 접근성을 보장한다 | 지속가능성은 모바일 앱에 적용되지 않는다 | 녹색 인증 호스팅 제공자만 사용한다 | 앱 문서에 지속가능성 페이지를 포함한다 |  | A | 디지털 지속가능성은 에너지 효율성, 데이터 최적화, 기기 수명, 접근성을 포함한다. 적용 불가(B)는 잘못된 인식이다. 녹색 호스팅만(C)은 부분적이다. 문서 페이지(D)는 실질적 조치가 아니다.
2213 | A project manager is asked to quantify the social return on investment (SROI) of a community development project. What should be included in the SROI calculation? | Only the number of beneficiaries. | The project's NPV calculated with standard discount rates. | Only the financial investment in the project. | Monetary value of social outcomes (jobs created, health improvements, education access, community well-being, reduced inequality) relative to the investment made. |  | D | SROI measures the social value generated relative to investment. It monetizes social outcomes like job creation, health improvements, education access, and community well-being. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Sustainability | PM이 커뮤니티 개발 프로젝트의 사회적 투자수익률(SROI)을 정량화하도록 요청받았다. SROI에 무엇이 포함되어야 하는가? | 수혜자 수만 | 표준 할인율로 계산된 프로젝트의 순현재가치(NPV) | 프로젝트의 재무 투자만 | 일자리 창출, 건강 개선, 교육 접근, 커뮤니티 안녕을 포함하는 사회적 성과의 금전적 가치 |  | D | SROI는 투자 대비 생성된 사회적 가치를 측정한다. 일자리 창출, 건강 개선, 교육 접근, 커뮤니티 안녕과 같은 사회적 성과를 금전화한다. 수혜자 수(A)는 영향 측정이 아니다. NPV(B)는 재무적이다. 재무 투자(C)는 투입만 다룬다.
2214 | A project team identifies an opportunity to reuse 40% of materials from a decommissioned facility for the new project. This would reduce costs by 12% and waste by 60%. What risk should the PM also consider? | Only the reputational risk of using 'secondhand' materials. | Quality and safety risks of reused materials, including structural integrity, contamination, regulatory compliance for reused components, and compatibility with new specifications. | Only the schedule risk of sorting and preparing reused materials. | No risks—reuse is always beneficial. |  | B | While material reuse has significant sustainability benefits, it also carries quality and safety risks. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Sustainability | 프로젝트 팀이 해체된 시설의 자재 40%를 새 프로젝트에 재사용할 기회를 식별했다. 어떤 리스크를 평가해야 하는가? | 중고 자재 사용의 평판 리스크만 | 구조적 무결성, 오염, 규제 준수 등을 포함하는 재사용 자재의 품질 및 안전 리스크 | 재사용 자재 분류 및 준비의 일정 리스크만 | 리스크 없음—재사용은 항상 유익하다 |  | B | 자재 재사용은 상당한 지속가능성 이점이 있지만 품질 및 안전 리스크도 수반한다. 평판만(A), 일정만(C)은 부분적이다. 리스크 없음(D)은 비현실적이다.
2215 | A project governance board wants to include sustainability criteria in the project go/no-go decision framework. What criterion is MOST important to add? | The percentage of recycled materials planned for use. | The project's net sustainability impact assessment—measuring expected environmental, social, and economic effects against organizational sustainability targets and thresholds. | Whether the project team has sustainability certifications. | Whether the project uses renewable energy. |  | B | A net sustainability impact assessment provides the most comprehensive basis for go/no-go decisions. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Initiating | Integrate Sustainability | Develop Project Charter | Sustainability | 프로젝트 거버넌스 위원회가 프로젝트 진행/중단(Go/No-go) 의사결정 프레임워크에 지속가능성 기준을 포함하고자 한다. 어떤 기준이 가장 효과적인가? | 재활용 자재 사용 비율 | 예상 환경, 사회, 경제적 영향을 측정하는 프로젝트의 순 지속가능성 영향 평가 | 프로젝트 팀의 지속가능성 인증 보유 여부 | 프로젝트의 재생 에너지 사용 여부 |  | B | 순 지속가능성 영향 평가가 진행/중단 결정을 위한 가장 포괄적인 기초를 제공한다. 재활용률(A), 인증(C), 재생 에너지(D)는 모두 단일 측면만 다룬다.
2216 | During a project, new environmental regulations are enacted that require the project's deliverables to meet stricter emission standards. The project is 45% complete. What is the MOST appropriate action? | Complete the project under the original standards and claim grandfathering. | Conduct a gap analysis between current deliverables and new standards, raise a change request for necessary modifications, and update the project plan including potentially reworking completed items. | Halt the project until legal provides a definitive interpretation. | Apply the new standards only to the remaining 55% of work. |  | B | New environmental regulations require a systematic gap analysis and formal change management. Some completed work may need rework to comply. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Compliance | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | Sustainability | 프로젝트 진행 중 새 환경 규제가 시행되어 인도물이 더 엄격한 배출 기준을 충족해야 한다. PM은 무엇을 해야 하는가? | 원래 기준으로 프로젝트를 완료하고 기존권(grandfathering)을 주장한다 | 현재 인도물과 새 기준 간의 갭 분석을 수행하고, 필요한 수정을 위한 변경 요청을 제기한다 | 법무팀이 확정적 해석을 제공할 때까지 프로젝트를 중단한다 | 남은 55% 작업에만 새 기준을 적용한다 |  | B | 새 환경 규제는 체계적 갭 분석과 공식적 변경 관리를 요구한다. 완료된 작업 일부도 준수를 위해 재작업이 필요할 수 있다. 기존권 주장(A)은 규제 리스크가 있다. 프로젝트 중단(C)은 과도하다. 부분 적용(D)은 비준수 리스크가 있다.
2217 | A project team is developing sustainability training for project managers in the organization. What topic should be given the HIGHEST priority? | How to write sustainability reports. | How to calculate carbon offsets. | How to obtain green certifications for the organization. | How to integrate sustainability thinking into everyday project decisions—from scope definition and procurement to risk management and stakeholder engagement. |  | D | The highest priority is teaching PMs to integrate sustainability into daily decision-making across all project management processes. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Help Ensure Knowledge Transfer | Resources | Executing | Integrate Sustainability | Acquire Resources | Sustainability | 프로젝트 팀이 조직의 프로젝트 관리자를 위한 지속가능성 교육을 개발 중이다. 가장 높은 우선순위를 받아야 하는 주제는? | 지속가능성 보고서 작성법 | 탄소 상쇄 계산법 | 조직을 위한 녹색 인증 획득법 | 범위 정의부터 조달까지 일상적 프로젝트 결정에 지속가능성 사고를 통합하는 방법 |  | D | 가장 높은 우선순위는 PM이 모든 프로젝트 관리 프로세스에 걸쳐 일상적 의사결정에 지속가능성을 통합하는 법을 가르치는 것이다. 보고서(A), 탄소 상쇄(B), 인증(C)은 모두 특정 측면이다.
2218 | A project manager is leading a data center construction project. The client wants the data center to achieve a Power Usage Effectiveness (PUE) of 1.2 or lower. During design, the team realizes this requires innovative cooling systems that add significant cost. What should the PM recommend? | Present a lifecycle cost analysis showing that lower PUE reduces long-term energy costs, potentially offsetting the upfront investment, and explore different innovative cooling options with varying cost-benefit profiles. | Tell the client that PUE 1.2 is technologically impossible. | Accept the additional cost without analysis. | Lower the PUE target to reduce costs. |  | A | A lifecycle cost analysis demonstrates that energy-efficient data centers often have lower total cost of ownership despite higher upfront costs. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Sustainability | PM이 데이터센터 건설 프로젝트를 이끌고 있다. 고객이 PUE(전력사용효율성) 1.2를 원하지만 비용이 증가한다. PM은 무엇을 해야 하는가? | 낮은 PUE가 장기 에너지 비용을 절감하여 잠재적으로 높은 초기 투자를 상쇄한다는 수명주기 비용 분석을 제시한다 | 고객에게 PUE 1.2는 기술적으로 불가능하다고 말한다 | 분석 없이 추가 비용을 수용한다 | 비용 절감을 위해 PUE 목표를 낮춘다 |  | A | 수명주기 비용 분석은 에너지 효율적 데이터센터가 높은 초기 비용에도 불구하고 총소유비용이 낮은 경우가 많다는 것을 보여준다. 불가능 주장(B)은 부정확하다. 분석 없는 수용(C)은 무책임하다. 목표 하향(D)은 고객 요구를 무시한다.
2219 | A project team completes a sustainable product that significantly exceeds environmental performance targets. The PM wants to leverage this success. What is the MOST strategic action? | Document the sustainability best practices, share them across the organization's project portfolio, and use the results to strengthen future project business cases for sustainability investments. | Move on to the next project without documenting the achievement. | Request a budget increase for the next project based on this success. | Publish the results on social media immediately. |  | A | Leveraging sustainability success strategically means documenting best practices for organizational learning, sharing across the portfolio, and using evidence to support future sustainability investments. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 프로젝트 팀이 환경 성과 목표를 크게 초과하는 지속가능한 제품을 완성했다. PM이 이 성공을 활용하고자 한다. PM은 무엇을 해야 하는가? | 지속가능성 모범 사례를 문서화하고, 조직의 프로젝트 포트폴리오 전반에 공유하며, 향후 지속가능성 투자를 지원하는 근거로 사용한다 | 성과를 문서화하지 않고 다음 프로젝트로 넘어간다 | 이 성공을 기반으로 다음 프로젝트의 예산 증가를 요청한다 | 소셜 미디어에 즉시 결과를 공개한다 |  | A | 지속가능성 성공을 전략적으로 활용하는 것은 조직 학습을 위해 모범 사례를 문서화하고, 포트폴리오 전반에 공유하며, 미래 지속가능성 투자를 지원하는 근거로 사용하는 것을 의미한다. 미문서화(B)는 교훈을 낭비한다. 예산 증가 요청(C)은 직접적 연결이 부족하다. 즉시 공개(D)는 조직 승인 없이 성급하다.

## PMBOK 7판 분류기준
3개의 Domain이 있고, 각 Domain별 Task가 있음
PMBOK 7 | 2021 ECO Domain and Task | [5 empty] | Performance Domain | Principle | 구분 | Methodology
| People |  | Process |  | Business Environment |  | Delivery | Be a Diligent, Respectful, and Caring Steward |  | Agile | Predictive | Hybrid | General
| Task | Manage Conflict | Task | Manage Communications | Task | Plan & Manage Compliance | Development Approach & Life Cycle | Build Quality into Processes and Deliverables | Methodology Detail | Agile General Practices | Traditional Plan-Driven | Predictive-Agile Blend | General PM Principles
|  | Lead a Team |  | Assess & Manage Risks |  | Evaluate & Deliver Project Benefits & Value | Measurement | Create a Collaborative Project Team Environment |  | Scrum | WBS/Decomposition | Tailored Approach | Integration & General PM
|  | Support Team Performance |  | Engage Stakeholders |  | Evaluate & Address External Environment Changes | Planning | Demonstrate Leadership Behaviors |  | Kanban | Critical Path/Schedule Mgmt |  | Stakeholder & Communication Mgmt
|  | Empower Team Members |  | Plan & Manage Budget & Resources |  | Support Organizational Change | Project Work | Effectively Engage with Stakeholders |  | Lean | Earned Value Management |  | Risk & Issue Management
|  | Ensure Team Members Are Adequately Trained |  | Plan & Manage Schedule |  |  | Stakeholders | Embrace Adaptability and Resiliency |  | XP |  |  | Scope & Requirements Mgmt
|  | Build a Team |  | Plan & Manage Quality |  |  | Team | Enable Change to Achieve the Envisioned Future State |  | Scaled Agile |  |  | Schedule Management
|  | Address Impediments to Team Performance |  | Plan & Manage Scope |  |  | Uncertainty | Focus on Value |  |  |  |  | Cost & Resource Management
|  | Negotiate Project Agreements |  | Integrate Project Planning Activities |  |  |  | Navigate Complexity |  |  |  |  | Quality Management
|  | Collaborate with Stakeholders |  | Manage Project Changes |  |  |  | Optimize Risk Responses |  |  |  |  | Procurement & Contract Mgmt
|  | Build Shared Understanding |  | Plan & Manage Procurement |  |  |  | Recognize, Evaluate, and Respond to System Interactions |  |  |  |  | Change Management
|  | Engage & Support Virtual Teams |  | Manage Project Artifacts |  |  |  | Tailor Based on Context |  |  |  |  | Baseline & Change Control
|  | Define Team Ground Rules |  | Determine Appropriate PM Methodology
|  | Mentor Relevant Stakeholders |  | Manage Project Issues
|  | Promote Team Performance through EI |  | Plan & Manage Project Closure

## PMBOK 8판 분류기준
3개의 Domain이 있고, 각 Domain별 Task가 있음
PMBOK 8 | 2026 ECO Domain and Task | [5 empty] | Principle | Performance Domain | Focus Area | Process 40 (Performace x Focus) | New Topics | 구분 | Methodology
| People |  | Process |  | Business Environment |  | Adopt a Holistic View | Finance | Closing | Acquire Resources | AI |  | Agile | Predictive | Hybrid | General
| Task | Align Stakeholder Expectations | Task | Develop Integrated PM Plan | Task | Define and Establish Governance | Be an Accountable Leader | Governance | Executing | Close Project or Phase | Digital Transformation | Methodology Detail | Agile General Practices | Traditional Plan-Driven | Predictive-Agile Blend | General PM Principles
|  | Develop a Common Vision |  | Develop and Manage Scope |  | Evaluate External Environment | Build an Empowered Culture | Resources | Initiating | Collect Requirements | Hybrid/Tailoring |  | Scrum | WBS/Decomposition | Tailored Approach | Integration & General PM
|  | Help Ensure Knowledge Transfer |  | Engage Stakeholders |  | Plan and Manage Compliance | Embed Quality | Risk | Monitoring & Controlling | Control Costs | Sustainability |  | Kanban | Critical Path/Schedule Mgmt |  | Stakeholder & Communication Mgmt
|  | Lead the Project Team |  | Evaluate Project Status |  | Support Organizational Change | Focus on Value | Schedule | Planning | Control Quality | Traditional PM |  | Lean | Earned Value Management |  | Risk & Issue Management
|  | Manage Conflicts |  | Manage Project Closure |  |  | Integrate Sustainability | Scope |  | Control Schedule |  |  | XP |  |  | Scope & Requirements Mgmt
|  |  |  | Manage and Control Changes |  |  |  | Stakeholders |  | Control Scope |  |  | Scaled Agile |  |  | Schedule Management
|  |  |  | Plan and Manage Communication | [5 empty] | Create WBS | [5 empty] | Cost & Resource Management
|  |  |  | Plan and Manage Finance | [5 empty] | Define Activities | [5 empty] | Quality Management
|  |  |  | Plan and Manage Procurement | [5 empty] | Define Scope | [5 empty] | Procurement & Contract Mgmt
|  |  |  | Plan and Manage Risk | [5 empty] | Determine Budget | [5 empty] | Change Management
|  |  |  | Plan and Manage Schedule | [5 empty] | Develop Project Charter | [5 empty] | Baseline & Change Control
|  |  |  | Plan and Manage Scope | [5 empty] | Develop Project Management Plan
|  |  |  | Plan and Optimize Quality | [5 empty] | Develop Schedule
|  |  |  | Remove Impediments and Manage Issues | [5 empty] | Develop Team
Direct and Manage Project Work
Estimate Activity Durations
Identify Risks
Identify Stakeholders
Implement Risk Responses
Manage Communications
Manage Project Knowledge
Manage Quality
Manage Stakeholder Engagement
Manage Team
Monitor Communications
Monitor Risks
Monitor Stakeholder Engagement
Monitor and Control Project Performance
Perform Integrated Change Control
Perform Qualitative Risk Analysis
Plan Communications Management
Plan Finance Management
Plan Procurement Management
Plan Resource Management
Plan Risk Management
Plan Scope Management
Plan Stakeholder Engagement
Validate Scope

## WEB 풀이 개발 필요 기능
1 | 유저별 이메일로 로그인 (이메일만 입력하면 로그인 가능)
2 | 관리자가 유저별(이메일) 유효기간 설정 가능
3 | 기본적으로 유효기간 3개월 셋팅
4 | PMP_All_Data의 문제 중에서 여러가지 기준으로 추출
5 | 기준은 PMBOK7판과 PBOK 8판의 분류기준으로 선택 가능
6 | 상위 카테고리 선택 시(All 포함) 하위카테고리 선택 가능
7 | 분류기준 외 오답 중에 고르기, PMP시험기준으로 고르기(7판 기준은 180문항, 8판 기준은 185문항)
8 | 랜덤으로 10개, 30개, 50개, 100개 고르기도 가능
9 | 문제를 풀고, '채점하기' 누르면 채점결과가 나옴
10 | 채점결과 나올때 설명이 정답보기 아래에 나옴 (미리 공간설정)
11 | 번역본 보고 싶으면 번역본 내용이 나오도록 문제/보기/해설 옆에 공간 두고, '번역 보이기' 선택으로 열었다 닫았다 가능한 구조
12 | 유저별 이메일 로그인 시 권한이 없더라도 무료로 50문제 풀어보기 가능(무료판은 50문제 모든문제가 같아야 하고 카테고리, 분류 등은 선택 불가)
13 | 유저별 오타 문제는 별도 데이터베이스에 저장하여 '오답'중에 고르기에서 문제 추출 가능
14 | 오답중에 고르기에서 맞춘 문제는 오답 데이터 베이스에서 삭제
15 | 유저별 정답률 데이터베이스에 두고, 별도 카테고리에서 확인 가능
16 | 정답률은 일자별, 분류기준별 다양하게 볼 수 있어야 함
17 | 모든 유저의 문제별 정답률을 데이터베이스화 하고, 관리자가 필요 시 문제별 정답률 표시 가능하도록 개발만 해놓기
18 | 결제란 만들어만 놓고 활성화 안하기. 나중에 관리자가 활성화 가능하도록 설정
19 | 모바일과 PC에서도 문제 없이 보이도록 개발
20 | 모바일에서 구현하기 어려운것은 PC에서만 가능하다고 표시하기. 문제풀이 모바일에서 반드시 가능
21 | 정답이 1개~3개까지 있으므로 고려해서 개발
22 | 하단에 문의 및 오류 신고하기 안내 (songdoinfo@naver.com)
23 | 카테고리는 문제 풀이, My Status (정답률, 유효기간 등)로 구분
24 | 문제 풀이 카테고리에서 분류기준이 너무 많다면 문제풀이(7판 기준), 문제풀이(8판 기준) 로 구분 가능
25 | 다른 PMP문제풀이 사이트의 우수한 점 있으면 적용해
26 | 채점하기 시 문제 분류기준 나오도록 정보제공