2063 | A project team has finished participating in an iterative product increment planning session. After the planning session, the team returns with a list of features to deliver. How should the project manager ensure the product increments deliver the anticipated requirements? | Appoint a dedicated product manager for the duration of the release | Track business outcomes for planned user stories. | Ensure every user story has acceptance criteria. | Have the customer approve the product increment features. |  | C | After an iterative planning session produces a feature list, the project manager should ensure every user story has acceptance criteria to verify anticipated requirements are delivered. Acceptance criteria define done for each story. Appointing a product manager (A) creates a new role unnecessarily. Tracking business outcomes (B) is valuable but secondary to defining acceptance criteria. Having the customer approve features (D) is part of acceptance but not the primary mechanism. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Adopt a Holistic View | Define Scope | Traditional PM | 프로젝트 팀이 반복형 제품 증분 계획 세션을 마쳤다. 세션 후 팀은 인도할 기능 목록을 가지고 돌아왔다. 제품 증분이 기대한 요구사항을 충족하도록 하려면 프로젝트 관리자는 어떻게 해야 하는가? | 출시 기간 동안 전담 제품 관리자를 임명한다 | 계획된 사용자 스토리의 비즈니스 성과를 추적한다 | 모든 사용자 스토리에 인수 기준이 있도록 한다 | 고객이 제품 증분 기능을 승인하도록 한다 |  | C | 반복형 계획 세션에서 기능 목록이 나왔다면, 프로젝트 관리자는 기대한 요구사항이 인도되었는지 검증할 수 있도록 모든 사용자 스토리에 인수 기준이 있게 해야 한다. 인수 기준은 스토리별 완료 기준을 정의한다. 제품 관리자를 새로 지정하는 것(A)은 불필요하게 새 역할을 만드는 것이다. 비즈니스 성과를 추적하는 것(B)은 가치 있지만 인수 기준 정의보다 부차적이다. 고객에게 기능을 승인받는 것(D)은 인수의 일부이지만 주된 수단이 아니다.
2064 | A project is behind schedule because of a delayed equipment installation. This is affecting many other activities. The manager responsible for the equipment delivery notified the project manager that there is a capacity issue for the team doing the installation. What should the project manager have done to prevent this situation from happening? | Defined the skill requirements more clearly in the scope statement. | Asked the manager to follow the agreed-upon resource management plan. | Conducted periodic reviews with the manager on resource availability. | Consulted with the installation team on a regular basis to check for conflicts. |  | C | The correct answer is C. The delay came from a capacity problem in the installation team, which is controlled by the manager who assigns those resources. Conducting periodic reviews with that manager on resource availability would have surfaced the problem early. Consulting the installation team (D) helps but does not address who controls availability, defining skills in scope (A) does not address capacity, and simply following the plan (B) is passive. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Traditional PM | 장비 설치가 지연되어 프로젝트 일정이 뒤처졌고, 이로 인해 다른 여러 활동도 영향을 받고 있다. 장비 납품을 책임지는 관리자는 설치 팀의 가용 인력에 문제가 있다고 프로젝트 관리자에게 알렸다. 이런 상황을 막으려면 프로젝트 관리자는 무엇을 했어야 하는가? | 범위 기술서에 기술 요구사항을 더 명확하게 정의했다 | 관리자에게 합의된 자원 관리 계획을 따르도록 요청했다 | 관리자와 자원 가용성에 대한 정기 검토를 수행했다 | 설치 팀과 정기적으로 상의하여 충돌을 확인했다 |  | C | 정답은 C이다. 지연은 설치팀의 가용 인력 문제에서 비롯되었고, 그 자원은 배정 권한이 있는 관리자가 통제한다. 그 관리자와 자원 가용성을 정기적으로 검토했다면 문제가 일찍 드러났을 것이다. 설치팀과 상의하는 것(D)은 도움이 되지만 가용성을 통제하는 사람을 다루지 못하고, 범위에 역량을 정의하는 것(A)은 인력 규모 문제를 다루지 못하며, 계획을 따르라고만 하는 것(B)은 수동적이다.
2065 | A complex project is in its execution phase. The project is set up to produce both predictive and incremental deliverables. The agile team is running late on their tasks. There is a resource on the agile team who is responsible for producing progress reports for the project manager. This resource has the required skills to help other team members with their workload. What should the project manager do to optimize the time of the resource who produces the progress reports? | Produce the progress reports on their own | Work more closely with the agile team to eliminate the need for progress reports | Engage a new resource to produce the progress reports | Record this in the issue log and find a resource to produce the reports |  | B | When the agile team is running late and a resource produces progress reports but has skills to help others, the project manager should work more closely with the agile team to eliminate the need for progress reports. This frees the resource for productive work. Having the PM produce reports (A) adds PM burden. Engaging a new resource for reports (C) adds cost. Recording in the issue log (D) documents but does not optimize. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Executing | Be an Accountable Leader | Manage Communications | Traditional PM | 복잡한 프로젝트가 실행 단계에 있다. 이 프로젝트는 예측형 인도물과 증분형 인도물을 모두 산출하도록 구성되어 있다. 애자일 팀은 작업이 늦어지고 있다. 애자일 팀에는 프로젝트 관리자를 위해 진척 보고서를 작성하는 인력이 한 명 있는데, 이 인력은 다른 팀원들의 작업을 도울 역량도 갖추고 있다. 진척 보고서를 작성하는 이 인력의 시간을 최적화하려면 프로젝트 관리자는 무엇을 해야 하는가? | 자체적으로 진행 보고서를 생성한다 | 애자일 팀과 더 긴밀히 협력하여 진행 보고서 필요를 제거한다 | 진행 보고서 생성을 위한 새 자원을 참여시킨다 | 이슈 로그에 기록하고 보고서 생성을 위한 자원을 찾는다 |  | B | 애자일 팀이 늦어지고 있는데 진척 보고서를 작성하는 인력이 다른 팀원을 도울 역량도 있다면, 프로젝트 관리자는 애자일 팀과 더 가까이 일해 진척 보고서가 필요 없게 만들어야 한다. 그러면 그 인력이 생산적인 작업에 투입될 수 있다. 프로젝트 관리자가 직접 보고서를 만드는 것(A)은 프로젝트 관리자의 부담을 늘린다. 보고서용 인력을 새로 투입하는 것(C)은 비용을 늘린다. 이슈 로그에 기록하는 것(D)은 기록일 뿐 최적화가 아니다.
2066 | A project team member was unhappy with a new change in project governance and complained to one of the project sponsors. The project sponsor challenged the project manager. How should the project manager resolve this conflict? | Schedule a meeting with the project team member's functional manager and request the functional manager's support. | Arrange a meeting with the project team member and project sponsor to discuss the change and obtain consensus. | Discuss how to manage this conflict with the project management office (PMO) and let them decide how to resolve the issue. | Explain to the sponsor why the change is required and get their support in forcing the project team member to accept the new change. |  | B | When a team member's complaint about governance changes reaches the project sponsor, the project manager should arrange a meeting with both the team member and the sponsor to discuss the change and work toward consensus. This facilitates open communication, ensures all viewpoints are heard, and promotes a collaborative resolution. Involving the functional manager (A) redirects the issue without addressing it directly between the affected parties. Letting the PMO decide (C) delegates the conflict resolution to an external body. Explaining the change to the sponsor and forcing the team member to accept it (D) is coercive and damages trust. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 한 팀원이 프로젝트 거버넌스의 새 변경에 불만을 품고 프로젝트 스폰서 중 한 명에게 불평했다. 그 스폰서가 프로젝트 관리자에게 문제를 제기했다. 프로젝트 관리자는 이 갈등을 어떻게 해결해야 하는가? | 팀원의 기능 관리자와 회의를 잡아 기능 관리자의 지원을 요청한다. | 팀원과 프로젝트 스폰서와 회의를 주선하여 변경을 논의하고 합의를 도출한다 | PMO와 이 갈등 관리 방법을 논의하고 결정하게 한다 | 스폰서에게 변경이 필요한 이유를 설명하고 팀원에게 강제하도록 지원을 받는다 |  | B | 거버넌스 변경에 대한 팀원의 불만이 프로젝트 스폰서에게 전달되었다면, 프로젝트 관리자는 팀원과 스폰서가 함께하는 회의를 마련해 변경 사항을 논의하고 합의를 이끌어 내야 한다. 이렇게 하면 열린 소통이 이루어지고 모든 관점이 반영되며 협력적인 해결이 촉진된다. 기능 관리자를 끌어들이는 것(A)은 당사자 간에 직접 다루지 않고 문제를 다른 곳으로 돌린다. PMO에 결정을 맡기는 것(C)은 갈등 해결을 외부 조직에 위임하는 것이다. 스폰서에게 변경을 설명하고 팀원에게 수용을 강요하는 것(D)은 강압적이며 신뢰를 해친다.
2067 | A project manager is leading a cross-organizational project that is replacing a platform on which various solutions used by 15 business units were built. The project is part of a large program of work, and some of the resources are shared with other projects outside of the program initiated by the respective business units. Which stakeholders should the project manager consult with first to manage interdependencies? | Project sponsors | Other project managers | Program managers | Business unit managers |  | C | When managing a cross-organizational project with shared resources across a program, the project manager should first consult program managers to manage interdependencies. Program managers oversee cross-project coordination and resource allocation within the program. Project sponsors (A) provide strategic direction but may not manage dependencies. Other project managers (B) manage individual projects. Business unit managers (D) manage functional areas but not program-level coordination. | Process | Engage Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 15개 사업부가 사용하는 여러 솔루션의 기반 플랫폼을 교체하는 전사 프로젝트를 이끌고 있다. 이 프로젝트는 대규모 프로그램의 일부이며, 일부 인력은 각 사업부가 착수한 프로그램 외부 프로젝트와 공유된다. 상호 의존 관계를 관리하기 위해 프로젝트 관리자가 가장 먼저 협의해야 할 이해관계자는 누구인가? | 프로젝트 스폰서 | 다른 프로젝트 관리자 | 프로그램 관리자 | 사업부 관리자 |  | C | 프로그램 전반에 걸쳐 인력을 공유하는 조직 간 프로젝트를 관리한다면, 프로젝트 관리자는 먼저 프로그램 관리자와 상의해 상호 의존 관계를 관리해야 한다. 프로그램 관리자는 프로그램 안에서 프로젝트 간 조율과 자원 배분을 감독한다. 프로젝트 스폰서(A)는 전략적 방향은 주지만 의존 관계를 관리하지 않을 수 있다. 다른 프로젝트 관리자(B)는 개별 프로젝트를 관리한다. 사업부 관리자(D)는 기능 영역을 관리할 뿐 프로그램 수준의 조율을 하지 않는다.
2068 | A project manager has been assigned to a long-term project. The project manager came across a government debate over a new law that may affect the project. What are the first two actions the project manager should perform? (Choose two) | Consult with the project stakeholders. | Request additional budget for contingency. | Perform a risk identification process with the project team. | Create a change request to discuss with the change control board (CCB). | Discuss the possible impacts with subject matter experts (SMEs). | C, E | The correct answers are C and E. A possible new law is a potential risk. The project manager should perform risk identification with the team and discuss the possible impacts with subject matter experts to understand the threat. Consulting all stakeholders (A) comes after the risk is understood, and requesting budget (B) or a change request (D) is premature because the law has not passed. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Risk | Planning | Focus on Value | Identify Risks | Traditional PM | 프로젝트 관리자가 장기 프로젝트에 배정되었다. 프로젝트 관리자는 프로젝트에 영향을 줄 수 있는 새 법안에 대한 정부 논의를 접했다. 프로젝트 관리자가 가장 먼저 수행해야 할 두 가지 조치는 무엇인가? (2개 선택) | 프로젝트 이해관계자와 상담한다 | 비상 예산 추가를 요청한다 | 프로젝트 팀과 리스크 식별 프로세스를 수행한다 | 변경통제위원회(CCB)와 논의하기 위한 변경 요청을 생성한다 | 주제 전문가(SME)와 가능한 영향을 논의한다 | C, E | 정답은 C와 E이다. 새 법안은 잠재적 리스크이다. 팀과 리스크 식별을 수행하고 SME와 가능한 영향을 논의해 위협을 이해해야 한다. 모든 이해관계자와 상의하는 것(A)은 리스크를 이해한 뒤의 일이고, 법이 통과되지 않았으므로 예산 요청(B)이나 변경 요청(D)은 성급하다.
2069 | To ensure effective team communication and processes, a standard set of software including video conferencing is defined for a virtual scrum team. Several team members are reporting problems with their access and cannot adhere to team processes. How should these issues be resolved? | The scrum master should ensure the appropriate escalation to resolve the issues. | Individual team members should discuss solutions to resolve the issues after the Scrum is concluded. | Individual team members need to submit service desk tickets to resolve the issues. | The product owner owns the open issues until they are resolved. |  | A | The correct answer is A. Several members cannot access the standard tools, which is an impediment to the team's process. Removing impediments is a core scrum master responsibility, so the scrum master should make sure the issue is escalated to whoever can resolve it. Leaving members to sort it out individually (B, C) slows resolution, and the product owner (D) is responsible for the backlog, not for team tooling issues. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | Agile | Scrum | People | Lead the Project Team | Governance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 효과적인 팀 커뮤니케이션과 프로세스를 위해 가상 스크럼 팀에 화상 회의를 포함한 표준 소프트웨어 세트가 정해져 있다. 여러 팀원이 접속에 문제가 있어 팀 프로세스를 따를 수 없다고 보고한다. 이 문제는 어떻게 해결해야 하는가? | 스크럼 마스터가 문제 해결을 위한 적절한 에스컬레이션을 보장해야 한다 | 개별 팀원이 스크럼 후 문제 해결 방안을 논의해야 한다 | 개별 팀원이 문제 해결을 위해 서비스 데스크 티켓을 제출해야 한다 | 제품 책임자가 해결될 때까지 미해결 이슈를 소유한다 |  | A | 정답은 A이다. 여러 팀원이 표준 도구에 접근하지 못하는 것은 팀 프로세스의 장애 요인이다. 장애 요인 제거는 스크럼 마스터의 핵심 책임이므로, 스크럼 마스터가 해결할 수 있는 사람에게 문제가 에스컬레이션되도록 해야 한다. 팀원 각자 해결하게 두는 것(B, C)은 해결을 늦추고, 제품 책임자(D)는 백로그를 책임질 뿐 팀의 도구 문제를 책임지지 않는다.
2070 | A project team has finished its first iteration out of six. The iteration's delivery performance (velocity) was 50%. During the iteration retrospective, the team realizes that the complexity of the work was underestimated. What should the project manager do? | Ask to replace some team members with more experienced ones. | Ask the technical manager to help the team with the issue. | Update the issue log and escalate it to the project sponsor. | Meet with the team to review internal actions to resolve the situation. |  | D | When the team realizes work complexity was underestimated after the first iteration with 50% velocity, the project manager should meet with the team to review internal actions to resolve the situation. This collaborative approach allows the team to reassess complexity, adjust estimation practices, and develop strategies for improvement. Asking to replace team members (A) is punitive and does not address the estimation issue. Asking the technical manager for help (B) introduces external dependency. Updating the issue log and escalating to the sponsor (C) is premature—the team should first attempt to resolve the issue internally. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 총 6회 중 첫 번째 이터레이션을 마쳤다. 이 이터레이션의 인도 성과(velocity)는 50%였다. 이터레이션 회고에서 팀은 작업의 복잡도를 과소평가했다는 것을 깨달았다. 프로젝트 관리자는 무엇을 해야 하는가? | 더 경험 있는 팀원으로 일부 교체를 요청한다 | 기술 관리자에게 팀 문제 지원을 요청한다 | 이슈 로그를 업데이트하고 프로젝트 스폰서에게 에스컬레이션한다 | 팀과 회의하여 상황 해결을 위한 내부 조치를 검토한다 |  | D | 첫 이터레이션의 속도가 50%에 그쳐 팀이 작업 복잡도를 과소평가했다는 것을 깨달았다면, 프로젝트 관리자는 팀과 만나 상황을 해결할 내부 조치를 검토해야 한다. 이런 협업적 접근을 통해 팀은 복잡도를 다시 평가하고, 산정 방식을 조정하며, 개선 전략을 세울 수 있다. 팀원 교체를 요청하는 것(A)은 징벌적이며 산정 문제를 해결하지 못한다. 기술 관리자에게 도움을 요청하는 것(B)은 외부 의존성을 만든다. 이슈 로그를 갱신하고 스폰서에게 에스컬레이션하는 것(C)은 성급하다. 팀이 먼저 내부적으로 해결해 봐야 한다.
2071 | A company faces challenges and decides to cut a few product features from the main project due to market conditions. During a status meeting, a new stakeholder expresses concern about the discrepancies between the current deliverables and the deliverables agreed upon in the project charter. What should the project manager do first? | Ask the new stakeholder to submit a change request to the change control board (CCB). | Ask the project team to increase the number of updates provided to the stakeholder. | Review the project objectives for alignment with the intended corresponding business value. | Determine the root cause of the discrepancy with the project team and agree on the project scope. |  | D | When a new stakeholder raises concerns about discrepancies between current deliverables and the original charter, the project manager should first determine the root cause of the discrepancy with the project team and agree on the project scope. Understanding whether changes were officially approved enables informed conversation with stakeholders. Asking the stakeholder to submit a change request (A) is premature before understanding the history. Increasing update frequency (B) does not address the discrepancy. Reviewing project objectives for alignment (C) is broader than the specific scope concern. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 어려움에 처한 한 회사가 시장 상황 때문에 주요 프로젝트에서 제품 기능 몇 가지를 빼기로 했다. 현황 회의에서 새로 합류한 이해관계자가 현재 인도물과 프로젝트 헌장에 합의된 인도물 사이의 차이에 우려를 표한다. 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 새 이해관계자에게 CCB에 변경 요청을 제출하도록 요청한다 | 이해관계자에게 업데이트 횟수를 늘리도록 팀에 요청한다 | 의도된 사업 가치와 프로젝트 목표의 정렬을 검토한다 | 프로젝트 팀과 차이의 근본 원인을 파악하고 범위에 합의한다 |  | D | 새 이해관계자가 현재 인도물과 원래 헌장 사이의 차이에 우려를 제기하면, 프로젝트 관리자는 먼저 프로젝트 팀과 함께 차이의 근본 원인을 파악하고 프로젝트 범위에 대해 합의해야 한다. 변경이 공식 승인되었는지 이해해야 이해관계자와 근거 있는 대화를 할 수 있다. 이해관계자에게 변경 요청을 제출하라고 하는 것(A)은 경위를 이해하기 전이라 성급하다. 업데이트 빈도를 늘리는 것(B)은 차이를 해결하지 못한다. 목표 정합성을 검토하는 것(C)은 구체적인 범위 우려에 비해 범위가 넓다.
2072 | A new resource has joined an iterative project team. The project manager notices that the resource is unable to complete the deliverables on time. How should the project manager address this situation? | Discuss options to improve performance with the resource manager | Address the lack of performance by coaching the new team member | Request a more efficient replacement resource from the project sponsor | Provide performance feedback as part of the retrospective ceremony. |  | D | When a new team member on an iterative project cannot complete deliverables on time, the project manager should provide performance feedback as part of the retrospective ceremony. Retrospectives offer a structured, team-oriented setting to address performance constructively, identify barriers, and develop improvement actions. Discussing with the resource manager (A) escalates externally before addressing it within the team. Coaching the new member (B) is valuable but should be informed by feedback. Requesting a replacement (C) is premature without first attempting to support the team member's development. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Initiating | Embed Quality | Develop Project Charter | Traditional PM | 반복형 프로젝트 팀에 새 인력이 합류했다. 프로젝트 관리자는 이 인력이 인도물을 제때 완료하지 못한다는 것을 알게 되었다. 프로젝트 관리자는 이 상황에 어떻게 대응해야 하는가? | 자원 관리자와 성과 개선 옵션을 논의한다 | 새 팀원을 코칭하여 성과 부족을 다룬다 | 프로젝트 스폰서에게 더 효율적인 대체 자원을 요청한다 | 회고 의식의 일부로 성과 피드백을 제공한다 |  | D | 반복형 프로젝트의 새 팀원이 인도물을 제때 완료하지 못한다면, 프로젝트 관리자는 회고 의식에서 성과 피드백을 제공해야 한다. 회고는 성과를 건설적으로 다루고, 장애물을 파악하며, 개선 조치를 마련하는 체계적이고 팀 중심적인 자리이다. 자원 관리자와 논의하는 것(A)은 팀 안에서 다루기 전에 외부로 에스컬레이션하는 것이다. 새 팀원을 코칭하는 것(B)은 가치 있지만 피드백을 바탕으로 해야 한다. 교체를 요청하는 것(C)은 팀원의 성장을 먼저 지원해 보기 전이라 성급하다.
2073 | A project to support an organizational transformation is in the planning phase. Transformation is the project sponsor's idea and is not aligned with key stakeholders because they all have different opinions about the project outcomes. What should the project manager do next? | Define a high-level project scope and share it with the key stakeholders. | Conduct a workshop on project goals and deliverables with the key stakeholders. | Ask the project sponsor to help with engagement of the key stakeholders. | Communicate project outcomes and results with the key stakeholders. |  | B | When a transformation project is the sponsor's idea but key stakeholders have different opinions about outcomes, the project manager should conduct a workshop on project goals and deliverables with key stakeholders. Collaborative workshops facilitate alignment and shared ownership. Defining and sharing a high-level scope (A) is one-way communication. Asking the sponsor to help with engagement (C) delegates the PM's responsibility. Communicating outcomes (D) is informational, not collaborative. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 조직 전환을 지원하는 프로젝트가 계획 단계에 있다. 전환은 프로젝트 스폰서의 아이디어이며, 핵심 이해관계자들은 프로젝트 결과에 대해 저마다 다른 의견을 갖고 있어 의견이 모이지 않는다. 프로젝트 관리자는 다음으로 무엇을 해야 하는가? | 고수준 프로젝트 범위를 정의하고 주요 이해관계자와 공유한다 | 주요 이해관계자와 프로젝트 목표와 인도물에 대한 워크숍을 실시한다 | 프로젝트 스폰서에게 주요 이해관계자 참여를 돕도록 요청한다 | 주요 이해관계자에게 프로젝트 결과와 성과를 커뮤니케이션한다 |  | B | 전환 프로젝트가 스폰서의 아이디어이고 핵심 이해관계자들의 결과에 대한 의견이 서로 다르다면, 프로젝트 관리자는 핵심 이해관계자와 프로젝트 목표와 인도물에 관한 워크숍을 열어야 한다. 협업 워크숍은 정렬과 공동 주인의식을 촉진한다. 개략적 범위를 정해 공유하는 것(A)은 일방적인 소통이다. 스폰서에게 참여 유도를 도와 달라고 하는 것(C)은 프로젝트 관리자의 책임을 넘기는 것이다. 결과를 알리는 것(D)은 정보 제공일 뿐 협업이 아니다.
2074 | A project manager is managing an internal project that was poorly defined. Recently, the project manager received several change requests raised by the organization's upper management. What should the project manager do first? | Review the benefits of the proposed changes in relation to the business case. | Request a provisional budget increase to avoid any budget overruns. | Assess the time overrun, and start implementation to avoid additional delays. | Motivate the team to avoid the frustration of working on a prolonged project. |  | A | When a poorly defined internal project receives several change requests from upper management, the project manager should first review the benefits of the proposed changes in relation to the business case. Benefit analysis ensures changes add value. Requesting a provisional budget increase (B) addresses cost without evaluating need. Assessing time overrun and starting implementation (C) bypasses change evaluation. Motivating the team (D) addresses morale but not the change requests. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Initiating | Embed Quality | Develop Project Charter | Traditional PM | PM이 정의가 부실한 내부 프로젝트를 관리 중이다. 최근 상위 경영진으로부터 여러 변경 요청을 받았다. PM은 무엇을 먼저 해야 하는가? | 사업 사례와 관련하여 제안된 변경의 이점을 검토한다 | 예산 초과를 방지하기 위해 임시 예산 증가를 요청한다 | 시간 초과를 평가하고 추가 지연을 피하기 위해 구현을 시작한다 | 장기 프로젝트 작업의 좌절감을 방지하기 위해 팀에 동기를 부여한다 |  | A | 정의가 부족한 내부 프로젝트에 상위 경영진의 변경 요청이 여러 건 들어오면, 프로젝트 관리자는 먼저 제안된 변경의 효익을 비즈니스 케이스와 비교해 검토해야 한다. 효익 분석을 해야 변경이 가치를 더하는지 확인할 수 있다. 임시 예산 증액을 요청하는 것(B)은 필요성을 평가하지 않고 비용만 다룬다. 일정 초과를 평가하고 바로 실행하는 것(C)은 변경 평가를 건너뛴다. 팀에 동기를 부여하는 것(D)은 사기를 다룰 뿐 변경 요청을 다루지 못한다.
2075 | A key project stakeholder showed interest in the beginning of a complex agile project but has become less involved as the sprint has progressed due to additional responsibilities. A few sprints later, the key stakeholder rejected a feature deliverable. The team is reworking the rejected deliverable for the next sprint. What should the project manager have done to avoid this situation? | Analyzed the changes in stakeholder attributes | Involved the key stakeholders in the decision-making process | Customized stakeholder communications based on the stakeholders' needs | Documented the project vision and objectives |  | C | When a key stakeholder became less involved over sprints and then rejected a feature deliverable, the project manager should have customized stakeholder communications based on the stakeholder's needs. Tailored communication maintains engagement despite competing responsibilities. Analyzing stakeholder attribute changes (A) monitors but does not act. Involving stakeholders in decisions (B) is broad. Documenting vision and objectives (D) does not address ongoing engagement. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Finance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Traditional PM | 복잡한 애자일 프로젝트 초기에 관심을 보였던 핵심 이해관계자가 추가 업무를 맡게 되면서 스프린트가 진행될수록 관여가 줄었다. 몇 스프린트 후 이 이해관계자가 기능 인도물 하나를 반려했다. 팀은 다음 스프린트에서 반려된 인도물을 다시 작업하고 있다. 이런 상황을 피하려면 프로젝트 관리자는 무엇을 했어야 하는가? | 이해관계자 속성의 변화를 분석했다 | 주요 이해관계자를 의사결정 과정에 참여시켰다 | 이해관계자 필요에 맞춰 커뮤니케이션을 맞춤화했다 | 프로젝트 비전과 목표를 문서화했다 |  | C | 핵심 이해관계자가 스프린트가 진행될수록 관여가 줄다가 기능 인도물을 반려했다면, 프로젝트 관리자는 이해관계자의 요구에 맞춰 소통을 맞춤화했어야 한다. 맞춤형 소통은 다른 업무가 늘어나도 참여를 유지하게 한다. 이해관계자 속성 변화를 분석하는 것(A)은 모니터링일 뿐 조치가 아니다. 이해관계자를 의사결정에 참여시키는 것(B)은 너무 광범위하다. 비전과 목표를 문서화하는 것(D)은 지속적인 참여를 다루지 못한다.
2076 | A project is being closed early because the parent organization sold the business unit. The new owner's representative tells the project manager to delete all project files immediately to save time. What should the project manager do? | Delete the files as instructed because the new owner now controls the project. | Keep a copy of the files on a personal drive in case they are needed later. | Check the closure and records-retention requirements with the PMO and legal before disposing of any project records. | Ignore the instruction and archive all files as usual. |  | C | The correct answer is C. Project records may be subject to contractual, legal, and organizational retention requirements, especially during a sale. The project manager should confirm those requirements with the PMO and legal before disposing of anything. Deleting immediately (A) risks non-compliance. Keeping personal copies (B) breaches information security. Ignoring the instruction (D) is not appropriate without clarifying the requirements. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Closing | Be an Accountable Leader | Close Project or Phase | Traditional PM | 모회사가 사업부를 매각해 프로젝트가 조기 종료된다. 새 소유주의 대리인이 시간을 아끼려면 프로젝트 파일을 모두 즉시 삭제하라고 프로젝트 관리자에게 말한다. 프로젝트 관리자는 무엇을 해야 하는가? | 이제 새 소유주가 프로젝트를 통제하므로 지시대로 파일을 삭제한다. | 나중에 필요할 수 있으니 개인 드라이브에 파일 사본을 보관한다. | 프로젝트 기록을 처분하기 전에 PMO·법무 부서와 종료 및 기록 보존 요건을 확인한다. | 지시를 무시하고 평소처럼 모든 파일을 보관한다. |  | C | 정답은 C이다. 프로젝트 기록은 특히 매각 과정에서 계약·법률·조직상 보존 요건의 적용을 받을 수 있다. 무엇이든 처분하기 전에 PMO와 법무 부서에 요건을 확인해야 한다. 즉시 삭제하는 것(A)은 규정 위반 위험이 있다. 개인 사본을 보관하는 것(B)은 정보 보안 위반이다. 요건을 확인하지 않고 지시를 무시하는 것(D)은 적절하지 않다.
2077 | A company is working on a project to develop an integration of their existing systems. There are known issues in production. What should the project manager do? | Identify and remove impediments and mitigate the risks. | Review the quality control processes and procedures. | Ensure the product owner reviews requirements with the team. | Include acceptance criteria in the definition of done (DoD). |  | A | When a project to integrate existing systems has known production issues, the project manager should identify and remove impediments and mitigate the risks. Proactive impediment removal and risk mitigation enable progress. Reviewing quality processes (B) examines procedures, not blockers. Ensuring PO reviews requirements (C) focuses on scope, not current issues. Including acceptance criteria in DoD (D) improves future quality but does not address current impediments. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 회사가 기존 시스템 통합 프로젝트를 진행 중이다. 생산 환경에 알려진 문제가 있다. PM은 무엇을 해야 하는가? | 장애물을 식별하고 제거하며 리스크를 완화한다 | 품질 관리 프로세스와 절차를 검토한다 | 제품 책임자가 팀과 요구사항을 검토하도록 한다 | 완료 정의(DoD)에 인수 기준을 포함한다 |  | A | 기존 시스템을 통합하는 프로젝트에 알려진 운영 문제가 있다면, 프로젝트 관리자는 장애물을 찾아 제거하고 리스크를 완화해야 한다. 선제적인 장애물 제거와 리스크 완화가 진척을 가능하게 한다. 품질 프로세스를 검토하는 것(B)은 장애가 아니라 절차를 점검하는 것이다. 제품 책임자가 요구사항을 검토하게 하는 것(C)은 현재 문제가 아니라 범위에 초점을 둔다. DoD에 인수 기준을 넣는 것(D)은 향후 품질을 개선하지만 현재 장애물을 다루지 못한다.
2078 | A company is running a project to eliminate a sales channel that has been unprofitable for the past 3 years. A key stakeholder from another area, who has historical ties to that sales channel, objects to the project. What should the project manager do in this situation? | Escalate the stakeholder issue to the project sponsor. | Assess the impact of the stakeholder and engage properly. | Develop a specific communications strategy for this stakeholder. | Use interpersonal skills to gain stakeholder engagement. |  | B | When a stakeholder objects to a project, the PM must evaluate the stakeholder's concerns and their potential influence on project outcomes. Understanding the reasons behind the objection—including any historical or legacy ties—enables the PM to address those concerns constructively while keeping the project aligned with its objectives. Effective stakeholder engagement is central to both project management and business analysis, as it supports expectation management, conflict resolution, and alignment of all parties with the project's goals. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 한 회사가 지난 3년간 수익을 내지 못한 판매 채널을 없애는 프로젝트를 진행하고 있다. 그 판매 채널과 오랜 인연이 있는 다른 부서의 핵심 이해관계자가 프로젝트에 반대한다. 이 상황에서 프로젝트 관리자는 무엇을 해야 하는가? | 이해관계자 이슈를 프로젝트 스폰서에게 에스컬레이션한다 | 이해관계자의 영향을 평가하고 적절히 참여시킨다 | 이 이해관계자를 위한 특정 커뮤니케이션 전략을 개발한다 | 대인관계 기술을 사용하여 이해관계자 참여를 확보한다 |  | B | 이해관계자가 프로젝트에 반대하면, 프로젝트 관리자는 그 이해관계자의 우려와 프로젝트 결과에 미칠 수 있는 영향력을 평가해야 한다. 과거의 인연이나 관계를 포함해 반대의 이유를 이해해야 프로젝트를 목표에 맞게 유지하면서 우려를 건설적으로 다룰 수 있다. 효과적인 이해관계자 참여는 기대 관리, 갈등 해결, 모든 당사자를 프로젝트 목표에 맞추는 일을 뒷받침하므로 프로젝트 관리와 비즈니스 분석 모두의 핵심이다.
2079 | A new team member is assigned to a team that consistently delivers each iteration. The new team member does not understand many of the processes followed and begins to negatively impact the schedule. What should the project manager do? | Place the new team member on a performance improvement program. | Assign easier activities to the new team member. | Ask another team member to take some of the new team member's work. | Allocate time within the iterations to mentor the new team member. |  | D | When a new team member does not understand processes and negatively impacts the schedule on an iterative team, the project manager should allocate time within iterations to mentor them. Structured mentoring builds capability sustainably. Placing them on a performance improvement program (A) is punitive. Assigning easier activities (B) limits their growth. Redistributing work to others (C) does not address the root cause. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Help Ensure Knowledge Transfer | Finance | Executing | Adopt a Holistic View | Direct and Manage Project Work | Traditional PM | 새 팀원이 매 이터레이션 일관되게 납품하는 팀에 합류했다. 새 팀원이 프로세스를 이해하지 못하고 일정에 부정적 영향을 준다. PM은 무엇을 해야 하는가? | 새 팀원을 성과 개선 프로그램에 등록한다 | 새 팀원에게 더 쉬운 활동을 할당한다 | 다른 팀원에게 새 팀원의 작업 일부를 맡긴다 | 이터레이션 내에 새 팀원을 멘토링할 시간을 할당한다 |  | D | 반복형 팀의 새 팀원이 프로세스를 이해하지 못해 일정에 나쁜 영향을 준다면, 프로젝트 관리자는 이터레이션 안에 그 팀원을 멘토링할 시간을 배정해야 한다. 체계적인 멘토링이 지속 가능하게 역량을 키운다. 성과 개선 프로그램에 넣는 것(A)은 징벌적이다. 쉬운 활동을 배정하는 것(B)은 성장을 제한한다. 업무를 다른 사람에게 재분배하는 것(C)은 근본 원인을 다루지 못한다.
2080 | A project manager is leading a hybrid project. The only available resources that have experience with agile are not at the project manager's location. The project has a strict schedule and budget, and the project manager is concerned about their ability to deliver it. What should the project manager do? | Plan to have the agile resources temporarily relocate to the project manager's location. | Engage the agile resources through video conferencing on a daily basis. | Advise the sponsor that the project will be delayed as agile training will be required. | Request a budget extension to get local resources experienced in agile. |  | B | When the only available agile-experienced resources are remote but the project has strict schedule and budget constraints, the project manager should engage them through daily video conferencing. This enables real-time collaboration without relocation costs or budget extension. Temporarily relocating resources (A) increases costs. Advising the sponsor of delay for training (C) is premature. Requesting a budget extension for local resources (D) exceeds budget constraints. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Engage Stakeholders | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 프로젝트를 이끌고 있다. 애자일 경험이 있는 가용 인력은 모두 프로젝트 관리자와 다른 지역에 있다. 프로젝트는 일정과 예산이 엄격해, 프로젝트 관리자는 제대로 인도할 수 있을지 걱정하고 있다. 프로젝트 관리자는 무엇을 해야 하는가? | 애자일 자원이 PM 위치로 임시 이동하도록 계획한다 | 매일 화상 회의를 통해 애자일 자원을 참여시킨다 | 애자일 교육이 필요하므로 프로젝트가 지연될 것이라고 스폰서에게 알린다 | 현지에서 애자일 경험이 있는 자원을 확보하기 위해 예산 연장을 요청한다 |  | B | 애자일 경험이 있는 가용 인력이 모두 원격지에 있고 일정·예산 제약이 엄격하다면, 프로젝트 관리자는 매일 화상 회의로 이들을 참여시켜야 한다. 이렇게 하면 이전 비용이나 예산 연장 없이 실시간 협업이 가능하다. 인력을 임시로 이동시키는 것(A)은 비용을 늘린다. 교육 때문에 지연된다고 스폰서에게 알리는 것(C)은 성급하다. 현지 인력을 위해 예산 연장을 요청하는 것(D)은 예산 제약을 넘어선다.
2081 | Regional sales managers tell the project manager that the monthly project report is too technical and that they cannot find the information relevant to their regions. What should the project manager do? | Send the report more frequently so the managers stay informed. | Ask the technical lead to explain the report to the managers in a meeting. | Analyze the managers' information needs and update the communications management plan to provide tailored content. | Shorten the report by removing technical details for all audiences. |  | C | The correct answer is C. The issue is that the content does not match the audience's needs. Understanding what the regional managers need and updating the communications management plan to tailor the information solves the root cause. Sending it more often (A) repeats the same problem. A one-off explanation (B) does not fix future reports. Removing technical detail for everyone (D) may harm audiences who need it. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Agile General Practices | Business Environment | Plan and Manage Risk | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | Traditional PM | 지역 영업 관리자들이 월간 프로젝트 보고서가 너무 기술적이어서 자기 지역에 관련된 정보를 찾을 수 없다고 프로젝트 관리자에게 말한다. 프로젝트 관리자는 무엇을 해야 하는가? | 관리자들이 계속 정보를 받을 수 있도록 보고서를 더 자주 보낸다. | 회의에서 기술 리드가 관리자들에게 보고서를 설명하게 한다. | 관리자들의 정보 요구를 분석하고, 맞춤형 내용을 제공하도록 커뮤니케이션 관리 계획을 갱신한다. | 모든 대상에게서 기술적 세부 내용을 빼 보고서를 줄인다. |  | C | 정답은 C이다. 문제는 내용이 대상의 요구와 맞지 않는다는 것이다. 지역 관리자들에게 무엇이 필요한지 파악하고 커뮤니케이션 관리 계획을 갱신해 정보를 맞춤화하면 근본 원인이 해결된다. 더 자주 보내는 것(A)은 같은 문제를 반복한다. 일회성 설명(B)은 이후 보고서를 고치지 못한다. 모든 대상에서 기술 내용을 빼는 것(D)은 그 정보가 필요한 대상에게 해가 될 수 있다.
2082 | A team has been struggling with various issues during the course of an iteration. The project lead facilitates a discussion of the issues and the team forms new team agreements. During the next iteration, some of the same issues appear again. What should the project lead do next? | Post the agreements in a conspicuous place where all of the team members can see them. | Let the team self-organize and determine the best means to prevent the issues from occurring again | Challenge the team to determine if the issues surfaced again because agreements were not followed | Notify senior management of the issues and have them review the importance of agreements with the team |  | B | When recurring issues surface despite new team agreements, the project lead should let the team self-organize and determine the best means to prevent the issues from occurring again. Self-organizing teams have greater ownership, autonomy, and accountability over their processes. The project lead should facilitate reflection—such as through retrospectives—rather than impose solutions, enabling the team to inspect and adapt their practices based on feedback and learning. Posting agreements in a visible place (A) is a good practice but alone does not address why they were not followed. Challenging the team about non-compliance (C) may be warranted eventually but is less effective than empowering the team to own the solution. Notifying senior management (D) undermines the team's trust and autonomy. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 팀이 한 이터레이션 동안 여러 문제로 어려움을 겪었다. 프로젝트 리드는 문제에 대한 논의를 이끌었고, 팀은 새로운 팀 합의를 만들었다. 그런데 다음 이터레이션에서 같은 문제 일부가 다시 나타났다. 프로젝트 리드는 다음으로 무엇을 해야 하는가? | 모든 팀원이 볼 수 있는 눈에 띄는 장소에 합의를 게시한다 | 팀이 자체 조직화하여 문제 재발 방지를 위한 최선의 방법을 결정하게 한다 | 합의가 지켜지지 않아 문제가 다시 발생했는지 팀에 도전한다 | 문제를 상위 경영진에 통보하고 합의의 중요성을 팀과 검토하게 한다 |  | B | 새 팀 합의를 만들었는데도 문제가 반복된다면, 프로젝트 리드는 팀이 자기조직화해 문제 재발을 막을 최선의 방법을 스스로 정하도록 해야 한다. 자기조직화 팀은 자신의 프로세스에 대해 더 큰 주인의식, 자율성, 책임감을 갖는다. 프로젝트 리드는 해결책을 강요하기보다 회고 등을 통해 성찰을 촉진해, 팀이 피드백과 학습을 바탕으로 관행을 점검하고 조정하게 해야 한다. 합의를 잘 보이는 곳에 게시하는 것(A)은 좋은 관행이지만 합의가 왜 지켜지지 않았는지는 해결하지 못한다. 합의 불이행을 추궁하는 것(C)은 언젠가 필요할 수 있지만 팀이 해결책을 주도하게 하는 것보다 효과가 떨어진다. 고위 경영진에 알리는 것(D)은 팀의 신뢰와 자율성을 훼손한다.
2083 | A marketing team is planning for a multiyear initiative that will include a lot of cross-functional stakeholders. The project manager has been assigned and is now in the project planning phase. What item(s) should the project manager develop first? | A business case and scope document | A product backlog and identification of the features to be delivered | A risk management plan to incorporate known risks | A communications management plan that addresses the team's needs |  | A | When planning a multiyear, cross-functional marketing initiative, the project manager should first develop a business case and scope document. These establish justification and boundaries. A product backlog (B) is premature without scope. A risk management plan (C) follows scope definition. A communications plan (D) addresses how, not what. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | Baseline & Change Control | Process | Develop and Manage Scope | Governance | Initiating | Focus on Value | Develop Project Charter | Traditional PM | 마케팅팀이 여러 기능 부서의 이해관계자가 대거 참여하는 다년 과제를 계획하고 있다. 배정된 프로젝트 관리자는 현재 프로젝트 계획 단계에 있다. 프로젝트 관리자가 가장 먼저 작성해야 할 것은 무엇인가? | 사업 사례와 범위 문서 | 제품 백로그와 납품할 기능 식별 | 알려진 리스크를 통합하는 리스크 관리 계획 | 팀의 요구를 다루는 커뮤니케이션 관리 계획 |  | A | 다년, 교차 기능 마케팅 이니셔티브를 계획할 때, PM은 먼저 사업 사례와 범위 문서를 개발해야 한다. 정당성과 경계를 설정하는 것이 모든 후속 계획의 기초이다. 백로그(B)는 범위 정의 후에 한다. 리스크 계획(C)은 사업 사례 후에 한다. 커뮤니케이션 계획(D)은 범위와 이해관계자 식별 후에 한다.
2084 | A project manager just took over a construction project which was already in its execution phase. Labor union representatives of the construction workers ask to revise the overtime per hour rate, as wage per hour have increased across the industry. What should the project manager do first? | Negotiate with the labor union representatives if the clause about increased wage per hour meets their requirements. | Assign a team member to negotiate the increased wage per hour with the labor union representatives. | Obtain approval from sponsors to increase the rates because it can affect project due to lack of resources. | Carefully read the agreements and see if there was any clause if the per hour rate could be increased. |  | D | When labor union representatives request a revision of the overtime rate, the project manager should first carefully read the agreements and check whether any clause allows for rate adjustments. Understanding the contractual framework is essential before taking any action—the PM needs to know the legal and contractual boundaries before negotiating or escalating. Negotiating directly (A) is premature without understanding the contractual terms. Assigning a team member to negotiate (B) delegates a critical procurement matter without proper authority or context. Obtaining sponsor approval to increase rates (C) implies a decision has been made before confirming whether the contract even permits such changes. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Process | Plan and Manage Procurement | Finance | Planning | Build an Empowered Culture | Plan Finance Management | Traditional PM | 프로젝트 관리자가 이미 실행 단계에 있는 건설 프로젝트를 막 넘겨받았다. 건설 노동자 노동조합 대표들이 업계 전반의 시간당 임금이 올랐다며 시간당 초과 근무 수당 인상을 요구한다. 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 시간당 임금 인상 조항이 노동조합의 요구를 충족하는지 노동조합 대표들과 협상한다. | 팀원에게 노동조합과 시간당 임금 인상을 협상하도록 배정한다 | 자원 부족이 프로젝트에 영향을 줄 수 있으므로 스폰서에게 요율 인상 승인을 받는다 | 계약을 주의 깊게 읽고 시간당 요율 인상이 가능한 조항이 있는지 확인한다 |  | D | 노동조합 대표들이 초과 근무 수당 조정을 요구하면, 프로젝트 관리자는 먼저 계약서를 꼼꼼히 읽고 요율 조정을 허용하는 조항이 있는지 확인해야 한다. 어떤 조치를 취하기 전에 계약상 틀을 이해하는 것이 필수이며, 협상이나 에스컬레이션 전에 법적·계약적 한계를 알아야 한다. 곧바로 협상하는 것(A)은 계약 조건을 이해하기 전이라 성급하다. 팀원에게 협상을 맡기는 것(B)은 적절한 권한이나 맥락 없이 중요한 조달 사안을 위임하는 것이다. 스폰서에게 요율 인상 승인을 받는 것(C)은 계약이 그런 변경을 허용하는지 확인하기도 전에 결정을 내린 셈이다.
2085 | An IT project manager for a project that is 50% complete learns that a critical team member plans to relocate to another country soon. The team member is needed for the remainder of the project. How should the project manager improve team dynamics? | Replace the team member with someone who has similar qualifications and is located closer. | Offer the team member an incentive to stay until the end of the project. | Require that all team members be physically present for the weekly project review. | Set up a weekly video conference to monitor the progress of the team member's work. |  | D | When a critical team member plans to relocate during an ongoing project, the project manager should set up weekly video conferences to monitor progress and maintain collaboration. This leverages technology to sustain the team member's contribution regardless of location. Replacing the team member (A) loses institutional knowledge. Offering incentives to stay (B) may not be feasible. Requiring physical presence for reviews (C) is impractical for a relocating team member. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 50% 완료된 프로젝트의 IT 프로젝트 관리자가 핵심 팀원이 곧 다른 나라로 이주할 계획이라는 것을 알게 되었다. 이 팀원은 프로젝트가 끝날 때까지 필요하다. 팀 역학을 개선하려면 프로젝트 관리자는 어떻게 해야 하는가? | 유사한 자격을 가진 가까운 위치의 팀원으로 교체한다 | 프로젝트 종료까지 머물도록 인센티브를 제공한다 | 모든 팀원이 주간 프로젝트 검토에 물리적으로 참석하도록 요구한다 | 주간 화상 회의를 설정하여 팀원의 작업 진행을 모니터링한다 |  | D | 핵심 팀원이 프로젝트 도중 이주할 계획이라면, 프로젝트 관리자는 매주 화상 회의를 잡아 진척을 모니터링하고 협업을 유지해야 한다. 기술을 활용하면 위치와 관계없이 그 팀원의 기여를 이어 갈 수 있다. 팀원을 교체하는 것(A)은 축적된 지식을 잃는다. 남도록 인센티브를 주는 것(B)은 현실적이지 않을 수 있다. 검토 때마다 직접 참석을 요구하는 것(C)은 이주하는 팀원에게 비현실적이다.
2086 | A project team is engaging a development team in another country to develop software. During progress reviews, the project manager identified completion date delays due to rework because there were different interpretations of the client's needs. What should the project manager do? | Create prototypes with the development team to confirm requirements | Travel to the development team's office to push the schedule | Escalate to the project steering committee and request additional time | Set up a meeting with key stakeholders to clarify requirements |  | A | Prototyping is an effective technique for eliciting, analyzing, and validating requirements when working with distributed teams experiencing communication challenges. Working prototypes reduce ambiguity, resolve conflicting interpretations, and generate concrete feedback from stakeholders and development teams. Prototypes facilitate communication across different locations and cultures, improving development quality and efficiency while minimizing rework from misunderstood requirements. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Scope | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 팀이 해외의 개발팀과 함께 소프트웨어를 개발하고 있다. 진척 검토 중에 프로젝트 관리자는 고객 요구를 서로 다르게 해석해 재작업이 생기면서 완료일이 늦어지고 있다는 것을 확인했다. 프로젝트 관리자는 무엇을 해야 하는가? | 개발팀과 프로토타입을 만들어 요구사항을 확인한다 | 개발팀 사무실로 출장 가서 일정을 추진한다 | 프로젝트 운영위원회에 에스컬레이션하고 추가 시간을 요청한다 | 주요 이해관계자와 회의를 설정하여 요구사항을 명확히 한다 |  | A | 소통에 어려움을 겪는 분산 팀과 일할 때, 프로토타이핑은 요구사항을 도출·분석·검증하는 효과적인 기법이다. 작동하는 프로토타입은 모호함을 줄이고, 서로 다른 해석을 해소하며, 이해관계자와 개발팀에게서 구체적인 피드백을 끌어낸다. 프로토타입은 서로 다른 지역과 문화 사이의 소통을 돕고, 요구사항 오해로 인한 재작업을 줄이면서 개발 품질과 효율을 높인다.
2087 | A key challenge that a project manager is facing is the lack of discipline by various team members and their inability to harness energy to achieve the project objectives. What should the project manager do to overcome this challenge? | Approach the project sponsor and request help in discussing the project deliverables with team members. | Explain to the team that the project manager is ultimately responsible for the delivery. | Assign multiple managers to the various teams and delegate all of the tasks to them. | Meet with each team member separately and apply an appropriate approach with each one. |  | D | When team members lack discipline and struggle to focus energy on project objectives, the most effective approach is to meet with each team member individually and tailor the leadership style to their specific needs. Each person may face different motivations, obstacles, or misunderstandings that require a personalized approach. This reflects situational leadership principles. Escalating to the sponsor (A) does not address the root cause at the team level. Asserting ultimate responsibility (B) is authoritarian and unlikely to inspire improved behavior. Assigning multiple managers (C) adds complexity and fragments accountability rather than solving the underlying discipline issue. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Hybrid/Tailoring | 프로젝트 관리자가 직면한 핵심 과제는 여러 팀원의 기강이 부족하고, 프로젝트 목표 달성에 에너지를 모으지 못한다는 것이다. 이 과제를 극복하려면 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서에게 접근하여 팀원과 인도물 논의를 도와달라고 요청한다 | 팀에게 PM이 납품에 대한 최종 책임이 있음을 설명한다 | 다양한 팀에 여러 관리자를 배정하고 모든 작업을 위임한다 | 각 팀원을 개별적으로 만나 각자에게 적절한 접근법을 적용한다 |  | D | 팀원들의 기강이 부족하고 프로젝트 목표에 힘을 모으지 못할 때 가장 효과적인 방법은 팀원 한 명 한 명과 개별적으로 만나 각자의 요구에 맞게 리더십 스타일을 조정하는 것이다. 사람마다 동기, 장애물, 오해가 달라 개인 맞춤형 접근이 필요하다. 이는 상황적 리더십 원칙을 반영한다. 스폰서에게 에스컬레이션하는 것(A)은 팀 차원의 근본 원인을 해결하지 못한다. 최종 책임이 자신에게 있다고 강조하는 것(B)은 권위적이며 행동 개선을 이끌어 내기 어렵다. 여러 관리자를 배정하는 것(C)은 복잡성을 높이고 책임을 분산시킬 뿐 기강 문제를 해결하지 못한다.
2088 | One team member is complaining about an agreement made during the last meeting. That team member was present at the meeting and participated in the decisions registered in the meeting minutes. What should the project manager do next? | Talk with the team member and explain that once the meeting ended, the agreement must be respected. | Schedule a new meeting to evaluate the agreement and negotiate a new one. | Arrange an additional meeting with the team to communicate the agreement made during the last meeting. | Meet with the team member and search for the root cause of their behavior. |  | A | When a team member complains about an agreement they participated in making, the project manager should talk with the team member and explain that once the meeting ended, the agreement must be respected. Clear communication reinforces accountability and commitment to team decisions. Scheduling a new meeting to renegotiate (B) undermines the original agreement. Arranging an additional meeting to recommunicate (C) is redundant. Searching for the root cause of the behavior (D) may be appropriate later but the immediate action is to reinforce the commitment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Be an Accountable Leader | Acquire Resources | Traditional PM | 한 팀원이 지난 회의에서 이루어진 합의에 불만을 제기하고 있다. 이 팀원은 그 회의에 참석했고, 회의록에 기록된 결정에도 참여했다. 프로젝트 관리자는 다음으로 무엇을 해야 하는가? | 팀원과 대화하여 회의가 끝나면 합의를 존중해야 함을 설명한다 | 합의를 평가하고 새로운 합의를 협상하기 위한 새 회의를 예약한다 | 팀과 추가 회의를 주선하여 지난 회의의 합의를 전달한다 | 팀원과 만나 행동의 근본 원인을 탐색한다 |  | A | 팀원이 자신도 참여해 만든 합의에 불만을 제기하면, 프로젝트 관리자는 그 팀원과 이야기해 회의가 끝난 뒤에는 합의를 존중해야 한다고 설명해야 한다. 명확한 소통은 팀 결정에 대한 책임과 헌신을 강화한다. 다시 협상하기 위해 새 회의를 잡는 것(B)은 원래 합의를 약화시킨다. 다시 알리기 위해 추가 회의를 여는 것(C)은 중복이다. 행동의 근본 원인을 찾는 것(D)은 나중에 필요할 수 있지만, 당장 할 조치는 약속을 재확인하는 것이다.
2089 | A new project manager has been assigned to an environmental project. After reviewing the project plan, the project manager notices that health and safety requirements have not been properly addressed. This is a serious concern, and the project manager wants to fix this issue immediately. Why is this situation problematic? | It is imperative that established performance metrics are met. | The project manager is obligated to comply with the project location's regulatory requirements. | The project manager must follow their employer's organizational process assets (OPAs). | Injury or loss incidents could delay project deliverables. |  | B | When health and safety requirements have not been properly addressed in the project plan, this is problematic because the project manager is obligated to comply with the project location's regulatory requirements. Legal compliance is non-negotiable and failure risks penalties, sanctions, or project termination. Meeting performance metrics (A) is important but not the primary concern. Following employer OPAs (C) may not align with local regulations. Injury incidents delaying deliverables (D) is a consequence, not the core obligation. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Risk & Issue Management | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 새 프로젝트 관리자가 환경 프로젝트에 배정되었다. 프로젝트 계획을 검토한 프로젝트 관리자는 보건·안전 요건이 제대로 반영되지 않았다는 것을 알게 되었다. 이는 심각한 문제여서 프로젝트 관리자는 즉시 바로잡으려 한다. 이 상황이 문제가 되는 이유는 무엇인가? | 확립된 성과 지표를 충족해야 하기 때문이다 | PM은 프로젝트 위치의 규제 요구사항을 준수할 의무가 있기 때문이다 | PM은 고용주의 조직 프로세스 자산(OPA)을 따라야 하기 때문이다 | 부상 또는 손실 사고가 프로젝트 인도물을 지연시킬 수 있기 때문이다 |  | B | 보건·안전 요구사항이 프로젝트 계획에 제대로 반영되지 않은 것이 문제가 되는 이유는, 프로젝트 관리자에게 프로젝트 소재지의 규제 요구사항을 준수할 의무가 있기 때문이다. 법규 준수는 타협할 수 없으며, 위반하면 벌금, 제재, 프로젝트 종료의 위험이 있다. 성과 지표 달성(A)은 중요하지만 가장 큰 우려는 아니다. 고용주의 OPA를 따르는 것(C)은 현지 규정과 맞지 않을 수 있다. 부상 사고로 인도물이 지연되는 것(D)은 결과일 뿐 핵심 의무가 아니다.
2090 | A project manager has been asked to lead a project. The performing organization does not have a project management office (PMO) or formal governance policies, procedures, and guidelines for this type of project. What should the project manager do first to determine a governance approach for the project? | Consult with team members and stakeholders to determine whether the organization has any informal governance policies procedures, and guidelines | Consult a subject matter expert (SME) as to the best governance policies, procedures, and guidelines to be used by the project | Coach the self-managing team to produce tailored governance policies, procedures and guidelines for the project | Choose either a predictive or agile framework best suited to the nature of the project, and use this framework as the basis for project governance policies, procedures, and guidelines |  | A | With no PMO and no formal governance, the project manager should first consult team members and stakeholders to find out whether the organization has any informal governance policies, procedures, or guidelines. Existing informal practices, expectations, and decision rights are the starting point for tailoring an appropriate governance approach. Relying on a single SME (B) ignores what the organization already does. Coaching the team to create governance from scratch (C) skips discovering existing practices. Choosing a delivery framework first (D) is a development-approach decision, not a governance assessment. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Resources | Executing | Build an Empowered Culture | Acquire Resources | Traditional PM | 프로젝트 관리자가 한 프로젝트를 이끌어 달라는 요청을 받았다. 수행 조직에는 프로젝트관리오피스(PMO)도 없고, 이런 유형의 프로젝트에 대한 공식 거버넌스 정책, 절차, 지침도 없다. 프로젝트의 거버넌스 방식을 정하기 위해 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 팀원과 이해관계자와 상의하여 조직에 비공식적 거버넌스가 있는지 파악한다 | SME에게 최적의 거버넌스 정책과 절차에 대해 상의한다 | 자체 관리 팀이 프로젝트에 맞는 맞춤형 거버넌스를 생산하도록 코칭한다 | 프로젝트 성격에 가장 적합한 예측형 또는 애자일 프레임워크를 선택하여 사용한다 |  | A | PMO도 공식 거버넌스도 없다면, 프로젝트 관리자는 먼저 팀원과 이해관계자에게 조직에 비공식적인 거버넌스 정책, 절차, 지침이 있는지 확인해야 한다. 기존의 비공식 관행, 기대, 의사결정 권한이 적절한 거버넌스 방식을 조정하는 출발점이 된다. SME 한 명에게만 의존하는 것(B)은 조직이 이미 하고 있는 방식을 무시한다. 팀에 거버넌스를 처음부터 만들게 하는 것(C)은 기존 관행을 파악하는 단계를 건너뛴다. 인도 프레임워크를 먼저 고르는 것(D)은 개발 방식에 관한 결정이지 거버넌스 평가가 아니다.
2091 | A company wants to be a pioneer in its industry and has announced the launch date of a new innovative product. After the first sprint planning, the team realizes that it is not possible to deliver all the features in the required time. What should the project manager do to ensure success? | Increase the capacity of the team to deliver the completed backlog on time. | Schedule a meeting with the stakeholders to review the contingency plan. | Ask the customer to reduce the backlog to meet the launch date. | Assist the team in defining a minimum viable product (MVP) by the launch date. |  | D | When the team realizes after first sprint planning that all features cannot be delivered by the announced launch date for an innovative product, the project manager should assist the team in defining a minimum viable product (MVP) by the launch date. MVP ensures the most critical features launch on time. Increasing team capacity (A) may not be feasible. Reviewing the contingency plan (B) does not directly address scope. Asking the customer to reduce backlog (C) shifts responsibility externally. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Scrum | Process | Develop Integrated PM Plan | Governance | Planning | Focus on Value | Develop Project Management Plan | Traditional PM | 업계의 선도 기업이 되고 싶은 한 회사가 혁신적인 신제품의 출시일을 발표했다. 첫 스프린트 계획 후, 팀은 요구된 기간 안에 모든 기능을 인도할 수 없다는 것을 깨달았다. 성공을 위해 프로젝트 관리자는 무엇을 해야 하는가? | 완료된 백로그를 제시간에 납품하기 위해 팀 역량을 증가시킨다 | 이해관계자와 회의하여 비상 계획을 검토한다 | 고객에게 출시일을 맞추기 위해 백로그를 줄이도록 요청한다 | 출시일까지 최소 기능 제품(MVP)을 정의하도록 팀을 지원한다 |  | D | 혁신 신제품의 첫 스프린트 계획 후 발표된 출시일까지 모든 기능을 인도할 수 없다는 것을 팀이 깨달았다면, 프로젝트 관리자는 팀이 출시일까지 인도할 최소 기능 제품(MVP)을 정의하도록 도와야 한다. MVP는 가장 중요한 기능이 제때 출시되도록 한다. 팀 역량을 늘리는 것(A)은 현실적이지 않을 수 있다. 비상 계획을 검토하는 것(B)은 범위를 직접 다루지 못한다. 고객에게 백로그를 줄여 달라고 하는 것(C)은 책임을 외부로 넘기는 것이다.
2092 | A senior stakeholder on a hybrid project says the monthly phase-gate reviews and the biweekly sprint demos overlap and asks to attend only the phase-gate reviews. What should the project manager do? | Agree and remove the stakeholder from all sprint demos. | Discuss the purpose of each review with the stakeholder and agree on which sessions are most valuable to attend, updating the stakeholder engagement plan. | Insist that the stakeholder attend every sprint demo as required by the plan. | Ask the product owner to represent the stakeholder in all reviews without informing the stakeholder. |  | B | The correct answer is B. The two reviews serve different purposes: demos give early feedback on the product, while phase gates support governance decisions. Explaining this and agreeing on the right level of participation keeps the stakeholder engaged without overloading them. Dropping all demos (A) may lose valuable feedback. Insisting on every demo (C) ignores the stakeholder's constraints. Substituting the product owner without telling the stakeholder (D) is not transparent. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Finance | Planning | Embed Quality | Plan Finance Management | Traditional PM | 하이브리드 프로젝트의 고위 이해관계자가 월간 단계 게이트 검토와 격주 스프린트 데모가 겹친다며 단계 게이트 검토에만 참석하겠다고 한다. 프로젝트 관리자는 무엇을 해야 하는가? | 동의하고 모든 스프린트 데모에서 이해관계자를 뺀다. | 각 검토의 목적을 이해관계자와 논의해 참석할 가치가 가장 큰 세션에 합의하고, 이해관계자 참여 계획을 갱신한다. | 계획상 필수이므로 모든 스프린트 데모에 참석하라고 요구한다. | 이해관계자에게 알리지 않고 제품 책임자가 모든 검토에서 그를 대신하게 한다. |  | B | 정답은 B이다. 두 검토는 목적이 다르다. 데모는 제품에 대한 조기 피드백을, 단계 게이트는 거버넌스 결정을 뒷받침한다. 이를 설명하고 적절한 참여 수준에 합의하면 부담을 주지 않으면서 이해관계자의 참여를 유지할 수 있다. 데모를 모두 빼는 것(A)은 귀중한 피드백을 잃을 수 있다. 모든 데모 참석을 고집하는 것(C)은 이해관계자의 제약을 무시한다. 알리지 않고 제품 책임자로 대신하는 것(D)은 투명하지 않다.
2093 | One of the team members is consistently absent in team meetings, but always completes their assigned tasks on time. Other team members think this member should attend the meetings. What should the project manager do? | Review and update the project ground rules to make meeting attendance mandatory. | Allow each team member to submit their required tasks on time and reduce the number of scheduled meetings. | Assign this member to facilitate the next meeting to ensure project team collaboration. | Understand the reason for the team member's absence and encourage them to attend future meetings. |  | D | When a team member consistently misses meetings but completes tasks on time, the project manager should understand the reason for the absence and encourage them to attend future meetings. Understanding context before enforcing rules demonstrates empathetic leadership. Making attendance mandatory through ground rules (A) is rigid without understanding the situation. Reducing meetings for everyone (B) does not address the specific absence. Assigning them to facilitate (C) forces participation without understanding barriers. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Risk | Executing | Embed Quality | Implement Risk Responses | Traditional PM | 한 팀원이 팀 회의에 계속 불참하지만, 배정된 작업은 항상 제때 완료한다. 다른 팀원들은 이 팀원도 회의에 참석해야 한다고 생각한다. 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 기본 규칙을 검토하고 업데이트하여 회의 참석을 의무화한다 | 각 팀원이 요구 작업을 제시간에 제출하게 하고 예정된 회의 수를 줄인다 | 이 팀원에게 다음 회의를 퍼실리테이션하도록 배정하여 협업을 보장한다 | 팀원의 불참 이유를 이해하고 향후 회의 참석을 격려한다 |  | D | 팀원이 회의에는 계속 빠지지만 작업은 항상 제때 끝낸다면, 프로젝트 관리자는 불참 이유를 이해하고 앞으로 회의에 참석하도록 권해야 한다. 규칙을 적용하기 전에 맥락을 이해하는 것이 공감하는 리더십이다. 그라운드 룰로 참석을 의무화하는 것(A)은 상황을 이해하지 않은 경직된 조치이다. 모두의 회의를 줄이는 것(B)은 특정 불참 문제를 다루지 못한다. 그 팀원에게 회의 진행을 맡기는 것(C)은 장애 요인을 이해하지 않은 채 참여를 강요하는 것이다.
2094 | A project manager is beginning a new project with very diverse team members. The project manager chose to use consensus building so the team can agree on and be engaged in how the project will be executed. How should the project manager proceed? | Create an environment where the agreement is reached by a majority vote. | Establish recurring brainstorming sessions to discuss project issues. | Allow team members to contribute ideas in a stream-of-consciousness mode. | Create an environment where the agreement is reached through discussion. |  | D | When using consensus building with a diverse team, the project manager should create an environment where agreement is reached through discussion. Open dialogue ensures all perspectives are heard and integrated. Majority voting (A) creates winners and losers. Recurring brainstorming sessions (B) generate ideas but do not build consensus. Stream-of-consciousness contribution (C) lacks structure for decision-making. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | Integration & General PM | Process | Develop Integrated PM Plan | Governance | Planning | Build an Empowered Culture | Develop Project Management Plan | Traditional PM | 프로젝트 관리자가 매우 다양한 팀원들과 새 프로젝트를 시작하고 있다. 프로젝트 관리자는 팀이 프로젝트 수행 방식에 합의하고 참여하도록 합의 형성(consensus building) 방식을 쓰기로 했다. 프로젝트 관리자는 어떻게 진행해야 하는가? | 다수결 투표로 합의에 도달하는 환경을 만든다 | 프로젝트 이슈를 논의하기 위한 정기 브레인스토밍 세션을 수립한다 | 팀원이 의식의 흐름 모드로 아이디어를 기여할 수 있게 한다 | 토론을 통해 합의에 도달하는 환경을 만든다 |  | D | 다양한 팀과 합의 형성 방식을 쓸 때, 프로젝트 관리자는 논의를 통해 합의에 이르는 환경을 만들어야 한다. 열린 대화는 모든 관점이 반영되고 통합되도록 한다. 다수결(A)은 이긴 쪽과 진 쪽을 만든다. 반복적인 브레인스토밍(B)은 아이디어는 만들지만 합의를 이루지 못한다. 떠오르는 대로 의견을 내게 하는 것(C)은 의사결정을 위한 구조가 없다.
2095 | During sign-off of the requirements specification, the IT security manager refuses to approve it because a feature requested by the marketing department would weaken customer data protection. Marketing insists the feature is essential. The approval delay is starting to affect the project schedule. What should the project manager do? | Arrange a meeting with the security manager and marketing to understand both concerns and work toward a solution that meets both needs. | Ask the sponsor to override the security manager so the specification can be approved. | Remove the feature from the specification without consulting marketing. | Proceed with development based on the current specification while the approval is pending. |  | A | The correct answer is A. The conflict is between two legitimate needs, so the project manager should bring both parties together, understand the underlying concerns, and look for a collaborative solution (for example, redesigning the feature with the required safeguards). Escalating to override security (B) skips collaboration and may create compliance risk, removing the feature unilaterally (C) ignores marketing's needs, and developing without approval (D) risks rework and violates governance. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 요구사항 명세서 승인 과정에서 IT 보안 관리자가 마케팅 부서가 요청한 기능이 고객 데이터 보호를 약화시킨다며 승인을 거부했다. 마케팅은 그 기능이 반드시 필요하다고 주장한다. 승인 지연이 프로젝트 일정에 영향을 주기 시작했다. 프로젝트 관리자는 무엇을 해야 하는가? | 보안 관리자와 마케팅이 함께하는 회의를 마련해 양측의 우려를 파악하고 두 요구를 모두 충족하는 해결책을 찾는다. | 명세서가 승인되도록 스폰서에게 보안 관리자의 결정을 뒤집어 달라고 요청한다. | 마케팅과 상의하지 않고 명세서에서 해당 기능을 삭제한다. | 승인을 기다리는 동안 현재 명세서대로 개발을 진행한다. |  | A | 정답은 A이다. 두 정당한 요구가 충돌하는 상황이므로, 프로젝트 관리자는 양측을 한자리에 모아 근본 우려를 파악하고 협력적 해결책(예: 필요한 보호 장치를 갖추도록 기능 재설계)을 찾아야 한다. 스폰서를 통해 보안 결정을 뒤집는 것(B)은 협업을 건너뛰고 컴플라이언스 리스크를 만들 수 있고, 일방적인 기능 삭제(C)는 마케팅의 요구를 무시하며, 승인 없이 개발하는 것(D)은 재작업 위험이 있고 거버넌스를 위반한다.
2096 | A company's new communication system will include online dashboard reporting. The executive board might receive bi-weekly performance reports through the online dashboard. What should the project manager do? | Review the project management plan | Review the configuration management plan. | Update the stakeholder engagement plan. | Update the communications management plan |  | D | The PM should update the communications management plan when a new communication system (such as online dashboard reporting) changes the project's communication methods and formats. This ensures project communications align with the new system and stakeholder expectations. The updated plan also helps identify and address potential risks, issues, or challenges from the change—such as compatibility, security, or training requirements. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Focus on Value | Manage Communications | Traditional PM | 회사의 새 커뮤니케이션 시스템에 온라인 대시보드 보고가 포함된다. 경영진이 격주 보고서를 받을 수 있다. PM은 무엇을 업데이트해야 하는가? | 프로젝트 관리 계획을 검토한다 | 구성 관리 계획을 검토한다 | 이해관계자 참여 계획을 업데이트한다 | 커뮤니케이션 관리 계획을 업데이트한다 |  | D | 새 커뮤니케이션 시스템이 커뮤니케이션 방법과 형식을 변경할 때, PM은 커뮤니케이션 관리 계획을 업데이트해야 한다. 이 계획이 프로젝트 커뮤니케이션 요구사항과 방법을 정의한다. 프로젝트 관리 계획(A)은 너무 광범위하다. 구성 관리(B)는 무관하다. 이해관계자 참여(C)는 참여 전략이지 커뮤니케이션 방법이 아니다.
2097 | The team is working on a critical project deliverable and the project manager is concerned about meeting the deadline. There have been complaints from some stakeholders about some of the team members' performance. The project manager wants to understand the situation and provide feedback to the team as soon as possible. What three actions should the project manager take to address this situation? (Choose three) | Request a manager performance review. | Perform a retrospective session | Define team ground rules | Implement daily team meetings. | Conduct an annual review. | B, C, D | When the team is working on a critical deliverable with stakeholder complaints about performance, the project manager should take three actions: define team ground rules to establish shared expectations, perform a retrospective session to reflect on performance and identify improvements, and implement daily team meetings to monitor progress and provide regular feedback. Requesting a manager performance review (A) is not the PM's responsibility. Conducting an annual review (E) is untimely for the urgent situation. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Finance | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 팀이 중요한 프로젝트 인도물을 작업하고 있으며, 프로젝트 관리자는 기한을 맞출 수 있을지 걱정하고 있다. 일부 이해관계자로부터 몇몇 팀원의 성과에 대한 불만도 있었다. 프로젝트 관리자는 상황을 파악하고 가능한 한 빨리 팀에 피드백을 주고 싶어 한다. 이 상황에 대응하기 위해 프로젝트 관리자가 취해야 할 세 가지 조치는 무엇인가? (3개 선택) | 관리자 성과 검토를 요청한다 | 회고 세션을 수행한다 | 팀 기본 규칙을 정의한다 | 일일 팀 회의를 실시한다 | 연례 검토를 실시한다 | B, C, D | 팀이 중요한 인도물을 작업하는데 이해관계자들이 성과에 불만을 제기한다면, 프로젝트 관리자는 세 가지 조치를 취해야 한다. 공통된 기대를 세우도록 팀 그라운드 룰을 정하고, 성과를 돌아보고 개선점을 찾도록 회고를 진행하며, 진척을 모니터링하고 정기적으로 피드백하도록 일일 팀 회의를 시행하는 것이다. 관리자에게 성과 평가를 요청하는 것(A)은 프로젝트 관리자의 책임이 아니다. 연간 평가를 하는 것(E)은 긴급한 상황에 시기가 맞지 않다.
2098 | The product team is progressing with a prototyping approach to deliver a multiyear business initiative. A few user stories are taking longer to be delivered. What should the project manager do? | Determine cross-dependencies and plan a spike in the next sprint | Determine the risks and identify a resolution during the retrospective meeting | Discover the gaps in the communications management plan and address them accordingly | Inform stakeholders about the delay during project updates |  | A | When user stories take longer to deliver in a prototyping approach, the project manager should determine cross-dependencies and plan a spike in the next sprint. A spike is a time-boxed investigation that helps the team reduce uncertainty, identify technical challenges, and find feasible solutions for complex stories. Identifying risks during the retrospective (B) is reactive. Informing stakeholders about the delay (D) does not address the root cause. Discovering communication plan gaps (C) is unrelated to the user story complexity issue. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Scrum | People | Plan and Manage Communication | Scope | Executing | Focus on Value | Direct and Manage Project Work | Traditional PM | 프로토타이핑 접근법으로 다년 사업 이니셔티브를 진행 중이다. 일부 사용자 스토리가 예상보다 오래 걸린다. PM은 무엇을 해야 하는가? | 교차 종속성을 파악하고 다음 스프린트에 스파이크를 계획한다 | 리스크를 파악하고 회고 회의에서 해결책을 식별한다 | 커뮤니케이션 관리 계획의 격차를 발견하고 적절히 다룬다 | 프로젝트 업데이트 중 이해관계자에게 지연을 알린다 |  | A | 프로토타이핑 방식에서 사용자 스토리 인도가 오래 걸린다면, 프로젝트 관리자는 상호 의존 관계를 파악하고 다음 스프린트에 스파이크(spike)를 계획해야 한다. 스파이크는 팀이 불확실성을 줄이고, 기술적 과제를 파악하며, 복잡한 스토리의 실현 가능한 해결책을 찾도록 돕는 시간 제한 조사 활동이다. 회고에서 리스크를 식별하는 것(B)은 사후 대응이다. 이해관계자에게 지연을 알리는 것(D)은 근본 원인을 다루지 못한다. 커뮤니케이션 계획의 공백을 찾는 것(C)은 사용자 스토리의 복잡도 문제와 관련이 없다.
2099 | A project manager is leading a hybrid project and is collaborating with the client to develop the project contract. Some delays have been experienced due to unforeseen technical difficulties and new dependencies. However, the project manager is optimistic about recovering the delays in the upcoming sprints. A key stakeholder asked the project manager if the contract deadlines can be met. What should the project manager do first? | Study the contract terms and deadlines to ensure they are not under risk and confirm them with the stakeholder. | Clarify the current work progress, causes for delays, existing risks, and planned corrective actions. | Ask the stakeholder to remain calm and confirm that they are participating in all team meetings. | Submit a request for extra time and budget related to the dependencies and technical difficulties. |  | B | When delays have occurred due to technical difficulties and new dependencies, and a stakeholder asks whether contract deadlines can be met, the project manager should first clarify the current work progress, causes for delays, existing risks, and planned corrective actions. Transparency about the project's actual state enables informed discussion and maintains stakeholder trust. Studying contract terms first (A) addresses legalities but does not communicate the project reality. Asking the stakeholder to remain calm (C) is dismissive. Submitting a request for extra time and budget (D) may be necessary later but is premature before providing a clear status assessment. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Process | Plan and Manage Procurement | Stakeholders | Planning | Build an Empowered Culture | Plan Stakeholder Engagement | Hybrid/Tailoring | 프로젝트 관리자가 하이브리드 프로젝트를 이끌며 고객과 함께 프로젝트 계약을 작성하고 있다. 예상치 못한 기술적 어려움과 새로운 의존 관계로 일부 지연이 발생했다. 그러나 프로젝트 관리자는 앞으로의 스프린트에서 지연을 만회할 수 있다고 낙관한다. 한 핵심 이해관계자가 계약 기한을 지킬 수 있는지 묻는다. 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 계약 조건과 기한을 검토해 위험에 처해 있지 않은지 확인하고 이해관계자에게 확답한다. | 현재 작업 진행, 지연 원인, 기존 리스크, 계획된 시정 조치를 명확히 한다 | 이해관계자에게 침착을 유지하고 모든 팀 회의에 참석하고 있는지 확인한다 | 종속성과 기술적 어려움 관련 추가 시간과 예산을 요청한다 |  | B | 기술적 어려움과 새로운 의존 관계로 지연이 발생했고 이해관계자가 계약 기한을 지킬 수 있는지 묻는다면, 프로젝트 관리자는 먼저 현재 작업 진척, 지연 원인, 현존 리스크, 계획된 시정 조치를 명확히 설명해야 한다. 프로젝트의 실제 상태를 투명하게 알리면 근거 있는 논의가 가능하고 이해관계자의 신뢰를 유지할 수 있다. 계약 조건부터 검토하는 것(A)은 법적 측면을 다룰 뿐 프로젝트 실정을 전달하지 못한다. 이해관계자에게 진정하라고 하는 것(C)은 무시하는 태도이다. 추가 시간과 예산을 요청하는 것(D)은 나중에 필요할 수 있지만 명확한 현황 평가를 제시하기 전이라 성급하다.
2100 | In a functional organization, a product analyst is assigned to a short-duration application development effort. The analyst expresses concerns about the task and asks the project manager to provide the support of a peer with expertise in this domain. What should the project manager do? | Ask the analyst to use skills to develop the tool, then move development to another team member | Recognize the analyst's concerns and reassign the task to another team member | Make sure the analyst has regular pairing meetings with the other team member throughout task execution | Enroll the analyst in a capacity-building program and keep this analyst assigned to the task |  | C | When a product analyst in a functional organization expresses concerns about a task and requests peer support, the project manager should ensure the analyst has regular pairing meetings with the other team member throughout execution. Pairing enables knowledge transfer and collaborative learning. Asking the analyst to work alone then reassigning (A) ignores concerns. Reassigning the task entirely (B) wastes the analyst's contribution. Enrolling in a capacity-building program (D) delays immediate support. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Hybrid | Predictive-Agile Blend | People | Help Ensure Knowledge Transfer | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | Traditional PM | 기능 조직에서 한 제품 분석가가 짧은 기간의 애플리케이션 개발 작업에 배정되었다. 분석가는 이 작업에 대해 우려를 표하며, 해당 분야 전문성을 가진 동료의 지원을 받게 해 달라고 프로젝트 관리자에게 요청한다. 프로젝트 관리자는 무엇을 해야 하는가? | 분석가에게 기술을 활용하여 도구를 개발한 후 개발을 다른 팀원에게 이관한다 | 분석가의 우려를 인식하고 작업을 다른 팀원에게 재배정한다 | 작업 실행 전반에 걸쳐 분석가가 다른 팀원과 정기 페어링 회의를 갖도록 한다 | 분석가를 역량 개발 프로그램에 등록하고 작업 배정을 유지한다 |  | C | 기능 조직의 제품 분석가가 작업에 대한 우려를 표하며 동료의 지원을 요청하면, 프로젝트 관리자는 실행 기간 내내 분석가가 그 동료와 정기적으로 페어링 미팅을 하도록 해야 한다. 페어링은 지식 이전과 협력 학습을 가능하게 한다. 혼자 일하게 한 뒤 재배정하는 것(A)은 우려를 무시한다. 작업을 완전히 재배정하는 것(B)은 분석가의 기여를 버리는 것이다. 역량 강화 프로그램에 등록하는 것(D)은 즉각적인 지원을 늦춘다.
2101 | A project manager is rolling out a new policy that affects employees in four countries. Early feedback shows that the same announcement was understood differently in each country, and some groups reacted negatively. What should the project manager do? | Send the same message again in English only so everyone receives identical wording. | Work with local representatives to tailor the messages to each cultural context and confirm understanding through feedback. | Reduce the frequency of communication to avoid further misunderstandings. | Ask human resources to take over all communication with the employees. |  | B | The correct answer is B. With culturally diverse stakeholders, effective communication means adapting the message to each audience and verifying that it was understood as intended. Local representatives know the cultural context and language nuances. Repeating the same English message (A) ignores the cause of the misunderstanding, communicating less (C) worsens engagement, and handing everything to HR (D) removes the project manager from a responsibility that belongs to the project. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 프로젝트 관리자가 4개국 직원들에게 영향을 주는 새 정책을 시행하고 있다. 초기 피드백을 보니 같은 공지가 나라마다 다르게 이해되었고, 일부 그룹은 부정적으로 반응했다. 프로젝트 관리자는 무엇을 해야 하는가? | 모두가 똑같은 문구를 받도록 같은 메시지를 영어로만 다시 보낸다. | 현지 대표들과 협력해 각 문화적 맥락에 맞게 메시지를 조정하고, 피드백으로 이해했는지 확인한다. | 추가 오해를 막기 위해 소통 빈도를 줄인다. | 직원과의 모든 소통을 인사팀에 맡긴다. |  | B | 정답은 B이다. 문화적으로 다양한 이해관계자와 효과적으로 소통하려면 대상에 맞게 메시지를 조정하고 의도대로 이해되었는지 확인해야 한다. 현지 대표들은 문화적 맥락과 언어의 미묘한 차이를 알고 있다. 같은 영어 메시지를 반복하는 것(A)은 오해의 원인을 무시하고, 소통을 줄이는 것(C)은 참여를 악화시키며, 모든 소통을 인사팀에 넘기는 것(D)은 프로젝트의 책임을 벗어나는 것이다.
2102 | A project manager notices that a product owner has been unresponsive over the last few weeks. During one-on-one sessions, the product owner is unable to provide complete information, leading to rework of the project stories. What should the project manager do first? | Cancel the one-on-one sessions and obtain the information via email. | Increase the sprint duration to accommodate the additional work. | Conduct a root cause analysis before addressing the issue. | Escalate the issue to the stakeholder's functional manager. |  | C | When a product owner is unresponsive and providing incomplete information that causes story rework, the project manager should first conduct a root cause analysis to understand the underlying reason. The cause might be workload, competing priorities, lack of clarity, insufficient product knowledge, or another blocker. Escalating to the functional manager (D) is premature before trying to understand and address the issue directly. Increasing sprint duration (B) treats the symptom by adding time but does not resolve the information gap. Cancelling one-on-ones and switching to email (A) weakens collaboration and may worsen the communication problem. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Manage Conflicts | Schedule | Executing | Embed Quality | Direct and Manage Project Work | Traditional PM | 프로젝트 관리자는 제품 책임자가 지난 몇 주간 응답이 없다는 것을 알아차렸다. 일대일 세션에서도 제품 책임자가 완전한 정보를 주지 못해 프로젝트 스토리를 재작업하게 되었다. 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 일대일 세션을 취소하고 이메일로 정보를 얻는다 | 추가 작업을 수용하기 위해 스프린트 기간을 늘린다 | 문제를 다루기 전에 근본 원인 분석을 실시한다 | 이슈를 이해관계자의 기능 관리자에게 에스컬레이션한다 |  | C | 제품 책임자가 응답이 없고 불완전한 정보를 줘서 스토리 재작업이 생긴다면, 프로젝트 관리자는 먼저 근본 원인 분석을 통해 그 이유를 파악해야 한다. 원인은 업무량, 우선순위 충돌, 명확성 부족, 제품 지식 부족 또는 다른 장애일 수 있다. 기능 관리자에게 에스컬레이션하는 것(D)은 문제를 이해하고 직접 해결해 보기 전이라 성급하다. 스프린트 기간을 늘리는 것(B)은 시간을 더해 증상만 다룰 뿐 정보 공백을 해결하지 못한다. 일대일 세션을 없애고 이메일로 바꾸는 것(A)은 협업을 약화시켜 소통 문제를 악화시킬 수 있다.
2103 | A project manager was replaced in the early phases of a new project. The new project manager discovers that the business team is not supporting the project. After discussing these concerns with the team, it is determined that the project does not have the full support of senior management. What should the new project manager do next? | Send out a status report describing the situation to the stakeholders and request general assistance. | Request the business team to clearly define their issues with the project work completed to date. | Study the stakeholder analysis to understand which stakeholder holds the most influence and seek their assistance. | Ask senior management to be more involved with the project and to provide their full support. |  | C | When the business team does not support the project due to lack of senior management backing, the new project manager should study the stakeholder analysis to identify the most influential stakeholder and seek their assistance. Leveraging influence gains support. Sending a status report requesting help (A) is passive. Asking the business team to define issues (B) focuses on symptoms. Asking senior management directly (D) may be possible but targeted influence is more effective. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | Traditional PM | 새 프로젝트의 초기 단계에 프로젝트 관리자가 교체되었다. 새 프로젝트 관리자는 사업팀이 프로젝트를 지지하지 않는다는 것을 알게 되었다. 팀과 이 우려를 논의한 결과, 프로젝트가 고위 경영진의 전폭적인 지지를 받지 못하고 있다는 것이 확인되었다. 새 프로젝트 관리자는 다음으로 무엇을 해야 하는가? | 상황을 설명하는 상태 보고서를 이해관계자에게 보내고 일반적 지원을 요청한다 | 사업 팀에게 지금까지 완료된 프로젝트 작업에 대한 이슈를 명확히 정의하도록 요청한다 | 이해관계자 분석을 연구하여 가장 영향력 있는 이해관계자를 파악하고 지원을 구한다 | 고위 경영진에게 프로젝트에 더 참여하고 전적인 지원을 제공하도록 요청한다 |  | C | 고위 경영진의 지지가 부족해 사업팀이 프로젝트를 지지하지 않는다면, 새 프로젝트 관리자는 이해관계자 분석을 살펴 가장 영향력 있는 이해관계자를 찾고 그의 도움을 구해야 한다. 영향력을 활용하면 지지를 얻을 수 있다. 도움을 요청하는 현황 보고서를 보내는 것(A)은 수동적이다. 사업팀에 문제를 정의하게 하는 것(B)은 증상에 초점을 둔다. 고위 경영진에게 직접 요청하는 것(D)도 가능하지만 목표에 맞춘 영향력 활용이 더 효과적이다.
2104 | A new agile project is starting. The project manager is asked to confirm the scope to address the concerns of one of the stakeholders. What should the project manager use to explain the project scope? | Business requirements document | Product roadmap | Product backlog | User stories |  | C | The correct answer is C. In an agile project, the product backlog is the ordered list of everything the product needs and is the best artifact to confirm scope with a stakeholder. Individual user stories (D) show only parts of the scope, a business requirements document (A) is a predictive artifact, and the product roadmap (B) shows high-level direction and timing rather than detailed scope. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | Traditional PM | 새 애자일 프로젝트가 시작된다. PM이 이해관계자 우려를 다루기 위해 범위를 확인하도록 요청받았다. 어떤 도구를 사용해야 하는가? | 사업 요구사항 문서 | 제품 로드맵 | 제품 백로그 | 사용자 스토리 |  | C | 정답은 C이다. 애자일 프로젝트에서 제품 백로그는 제품에 필요한 모든 것을 순서대로 정리한 목록이므로 이해관계자와 범위를 확인하기에 가장 적합한 산출물이다. 개별 사용자 스토리(D)는 범위의 일부만 보여 주고, 비즈니스 요구사항 문서(A)는 예측형 산출물이며, 제품 로드맵(B)은 상세 범위가 아니라 개략적인 방향과 시기를 보여 준다.
2105 | A project management team received news that a competitor has released the latest version of a program. What should the team do next? | Stop the project immediately as the market opportunity has already been missed. | Review the project plan to evaluate if any updates should be made. | Crash the existing schedule with additional resources to deliver more features. | Continue with the project plan and target delivery date as expected. |  | B | When a competitor releases a new program version, the project team should review the project plan to evaluate if any updates should be made. Assessing competitive impact on objectives and deliverables enables informed decisions. Stopping the project (A) is extreme. Crashing the schedule (C) adds cost without analysis. Continuing as planned (D) ignores the competitive landscape. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 관리 팀이 경쟁사가 프로그램 최신 버전을 출시했다는 소식을 받았다. PM은 무엇을 해야 하는가? | 시장 기회를 이미 놓쳤으므로 프로젝트를 즉시 중단한다 | 프로젝트 계획을 검토하여 업데이트가 필요한지 평가한다 | 추가 기능을 납품하기 위해 추가 자원으로 기존 일정을 크래싱한다 | 프로젝트 계획과 목표 납품일을 예정대로 계속한다 |  | B | 경쟁사가 새 버전을 출시했을 때, PM은 프로젝트 계획을 검토하여 업데이트가 필요한지 평가해야 한다. 경쟁 영향 평가가 목표와 인도물에 미치는 영향을 파악한다. 즉시 중단(A)은 과도한 반응이다. 크래싱(C)은 비용과 리스크가 높다. 예정대로(D)는 시장 변화를 무시한다.
2106 | Halfway through an agile project, a business stakeholder asks why a feature shown on the product roadmap three months ago is not in the latest increment. What should the project manager do? | Ask the team to add the feature to the current sprint immediately. | Explain that the roadmap is a forecast that changes with priorities, and arrange for the stakeholder to review the backlog priorities with the product owner. | Send the stakeholder the original roadmap to show that the feature was only planned. | Escalate the stakeholder's concern to the sponsor for a decision. |  | B | The correct answer is B. A roadmap is a forecast, and priorities change as the team learns. Explaining this and connecting the stakeholder with the product owner to review backlog priorities keeps the stakeholder informed and gives their view a proper channel. Adding the feature mid-sprint (A) disrupts committed work. Sending the old roadmap (C) is dismissive. Escalating (D) is unnecessary when the product owner can address it. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Scrum | Process | Plan and Optimize Quality | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Traditional PM | 애자일 프로젝트 중반에 한 사업 이해관계자가 3개월 전 제품 로드맵에 있던 기능이 왜 최신 증분에 없냐고 묻는다. 프로젝트 관리자는 무엇을 해야 하는가? | 팀에 그 기능을 현재 스프린트에 즉시 추가하라고 요청한다. | 로드맵은 우선순위에 따라 바뀌는 예측이라는 점을 설명하고, 이해관계자가 제품 책임자와 백로그 우선순위를 검토하도록 자리를 마련한다. | 그 기능은 계획만 되어 있었다는 것을 보여 주려고 원래 로드맵을 이해관계자에게 보낸다. | 이해관계자의 우려를 스폰서에게 에스컬레이션해 결정을 받는다. |  | B | 정답은 B이다. 로드맵은 예측이며 팀이 배우면서 우선순위는 바뀐다. 이를 설명하고 이해관계자를 제품 책임자와 연결해 백로그 우선순위를 검토하게 하면, 이해관계자에게 정보를 주면서 그의 의견을 반영할 적절한 경로도 제공한다. 스프린트 중간에 기능을 넣는 것(A)은 확약된 작업을 흔든다. 옛 로드맵을 보내는 것(C)은 무시하는 태도이다. 제품 책임자가 다룰 수 있는데 에스컬레이션하는 것(D)은 불필요하다.
2107 | A project scope was developed with numerous assumptions. During the execution phase, the assumptions changed, which has jeopardized the planned business value of the project. What should the project manager do next? | Report on the changed assumptions to the project sponsor and seek support to prioritize the change requests. | Deliver what was planned in the project management document according to the specifications. | Update the assumptions log and change log, and implement the change control process. | Inform the client that the project cannot meet the project timeline and additional costs will be incurred. |  | C | When project assumptions change during execution jeopardizing planned business value, the project manager should update the assumptions log and change log, and implement the change control process. Formal documentation and change control ensure assessed and managed responses. Reporting to the sponsor (A) informs but does not drive process. Delivering according to original specifications (B) ignores the changed reality. Informing the client of delays and costs (D) is premature before change assessment. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Scope | Planning | Embed Quality | Plan Scope Management | Traditional PM | 프로젝트 범위가 다수의 가정으로 개발되었다. 실행 단계에서 가정이 변경되어 사업 가치가 위험에 처했다. PM은 무엇을 해야 하는가? | 변경된 가정을 스폰서에게 보고하고 변경 요청 우선순위화 지원을 구한다 | 프로젝트 관리 문서에 따라 계획대로 납품한다 | 가정 로그와 변경 로그를 업데이트하고 변경 통제 프로세스를 실행한다 | 고객에게 프로젝트 일정을 맞출 수 없고 추가 비용이 발생한다고 알린다 |  | C | 실행 중에 프로젝트 가정이 바뀌어 계획한 비즈니스 가치가 위태로워지면, 프로젝트 관리자는 가정 로그와 변경 로그를 갱신하고 변경 통제 절차를 실행해야 한다. 공식 문서화와 변경 통제를 거쳐야 평가되고 관리된 대응이 가능하다. 스폰서에게 보고하는 것(A)은 정보는 주지만 절차를 이끌지 못한다. 원래 사양대로 인도하는 것(B)은 바뀐 현실을 무시한다. 고객에게 지연과 비용을 알리는 것(D)은 변경 평가 전이라 성급하다.
2108 | Due to an anticipated expansion, a company procured new technology. The project team responsible for using this technology does not have experience with it. What should the project manager do? | Hire project resources with experience using the new technology. | Request incentives for the team to use the new technology. | Propose training for the project team in batches on the new technology. | Assess the benefit of using new technology versus old technology. |  | C | The PM should propose training for the project team in batches on the new technology. This addresses the root cause—lack of familiarity with the technology—while minimizing disruption to ongoing project work. Batch training allows the team to learn progressively without halting project progress entirely. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Agile | Agile General Practices | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | Traditional PM | 예상 확장으로 인해 회사가 새 기술을 조달했다. 프로젝트 팀이 이 기술에 대한 전문성이 부족하다. PM은 무엇을 해야 하는가? | 새 기술 사용 경험이 있는 프로젝트 자원을 채용한다 | 팀이 새 기술을 사용하도록 인센티브를 요청한다 | 프로젝트 팀을 배치별로 새 기술에 대해 교육하도록 제안한다 | 새 기술 대비 기존 기술 사용의 이점을 평가한다 |  | C | PM은 프로젝트 팀을 배치별로 새 기술에 대해 교육하도록 제안해야 한다. 이는 근본 원인인 기술 친숙도 부족을 해결하면서 진행 중인 프로젝트에 최소한의 혼란을 준다. 채용(A)은 비용이 높고 시간이 걸린다. 인센티브(B)는 역량이 아닌 동기만 다룬다. 기술 비교(D)는 이미 조달한 후에는 늦다.
2109 | A project manager is assigned to a digital transformation project for a bank. The company culture is conservative and resistant to transformation or innovation. What should the project manager do first to support the transformation? | Hire an expert in digital transformation and assign that person as the champion for the change | Ask the bank executives to officially announce that the project manager is leading the project | Provide a digital transformation guide and explain that the change is unavoidable | Provide proper training sessions to the stakeholders so they understand the purpose of the change |  | D | When assigned to a digital transformation project in a conservative, change-resistant culture, the project manager should first provide proper training sessions to stakeholders so they understand the purpose of the change. Building understanding alleviates resistance and fosters acceptance. Hiring a digital transformation expert (A) adds expertise but does not directly address cultural resistance. Asking executives to announce the PM's role (B) establishes authority, not acceptance. Providing a guide and explaining inevitability (C) is informational but not interactive. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Help Ensure Knowledge Transfer | Governance | Executing | Focus on Value | Manage Project Knowledge | Digital Transformation | 프로젝트 관리자가 한 은행의 디지털 전환 프로젝트에 배정되었다. 회사 문화는 보수적이며 전환이나 혁신에 저항적이다. 전환을 지원하기 위해 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 디지털 전환 전문가를 고용하여 변화의 챔피언으로 지정한다 | 은행 경영진에게 PM이 프로젝트를 이끌고 있다고 공식 발표하도록 요청한다 | 디지털 전환 가이드를 제공하고 변화가 불가피하다고 설명한다 | 이해관계자에게 적절한 교육 세션을 제공하여 변화의 목적을 이해하게 한다 |  | D | 보수적이고 변화에 저항적인 문화에서 디지털 전환 프로젝트를 맡았다면, 프로젝트 관리자는 먼저 이해관계자에게 적절한 교육 세션을 제공해 변화의 목적을 이해시켜야 한다. 이해를 쌓아야 저항이 줄고 수용이 촉진된다. 디지털 전환 전문가를 채용하는 것(A)은 전문성은 더하지만 문화적 저항을 직접 다루지 못한다. 경영진에게 프로젝트 관리자의 역할을 발표해 달라고 하는 것(B)은 권위를 세울 뿐 수용을 이끌지 못한다. 안내서를 제공하고 불가피성을 설명하는 것(C)은 정보 제공일 뿐 상호작용이 없다.
2110 | A multinational company is launching a company-wide digital transformation project that covers all of its regions and business lines. The project is expected to go through five phases and finish in 2 years. The project manager schedules a kick-off meeting. What should the project manager do next? | Ensure there is enough budget to mandate all team members to fly to corporate headquarters for the kick-off meeting. | Document the kick-off meeting and close out the planning phase after the meeting is held. | Consider using digital or virtual tools to conduct the kick-off meeting to minimize geographic boundaries. | Limit to one kick-off meeting in the project's first phase in order to control the budget. |  | C | For a global digital transformation project, the kick-off meeting should leverage digital or virtual tools to enable participation across all regions and business lines. This cost-effective approach minimizes geographic barriers, fosters collaboration without requiring travel, and aligns with the project's digital nature. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Build an Empowered Culture | Identify Stakeholders | Digital Transformation | 한 다국적 기업이 모든 지역과 사업 부문을 아우르는 전사 디지털 전환 프로젝트를 시작한다. 프로젝트는 5단계를 거쳐 2년 후 완료될 예정이다. 프로젝트 관리자가 킥오프 회의를 잡았다. 프로젝트 관리자는 다음으로 무엇을 해야 하는가? | 모든 팀원이 본사로 비행하도록 충분한 예산을 확보한다 | 킥오프 회의를 문서화하고 회의 후 계획 단계를 종료한다 | 지리적 경계를 최소화하기 위해 디지털 또는 가상 도구를 사용하여 킥오프 회의를 진행한다 | 예산 통제를 위해 프로젝트 첫 단계에서 킥오프 회의를 하나로 제한한다 |  | C | 글로벌 디지털 전환 프로젝트의 킥오프 회의는 디지털 또는 가상 도구를 활용하여 모든 지역에서 참여할 수 있도록 해야 한다. 비용 효율적이며 포괄적 참여를 가능하게 한다. 본사 비행(A)은 비용이 과도하다. 문서화만(B)은 참여가 아니다. 회의 제한(D)은 포괄적 참여를 방해한다.
2111 | A project manager is assigned to a new water treatment plant project that has been delayed for many years. It is revealed in the project charter that the sponsors of this project are from three different business units. This is the first time the sponsors have ever implemented such a project. What should the project manager do? | Establish mentoring and coaching sessions. | Review the knowledge repository for similar projects. | Meet with the project sponsors to align expectations | Schedule the project kick-off meeting immediately. |  | C | Meeting with project sponsors to align expectations is the PM's first priority when sponsors come from different business units with different perspectives. This establishes trust, communication, and collaboration around project objectives, scope, deliverables, risks, assumptions, and constraints. The PM should also review the project charter and stakeholder register to clarify roles and responsibilities. Mentoring sessions, knowledge repository reviews, and kick-off meeting scheduling are important but secondary activities. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Initiating | Be an Accountable Leader | Identify Stakeholders | Traditional PM | 프로젝트 관리자가 수년째 지연되어 온 새 정수장 프로젝트에 배정되었다. 프로젝트 헌장을 보니 이 프로젝트의 스폰서가 서로 다른 세 사업부 출신이다. 스폰서들이 이런 프로젝트를 추진하는 것은 이번이 처음이다. 프로젝트 관리자는 무엇을 해야 하는가? | 멘토링 및 코칭 세션을 설정한다 | 유사 프로젝트의 지식 저장소를 검토한다 | 프로젝트 스폰서와 만나 기대를 정렬한다 | 프로젝트 킥오프 회의를 즉시 일정에 잡는다 |  | C | 스폰서들이 서로 다른 사업부 출신으로 관점이 다르다면, 프로젝트 관리자가 가장 먼저 할 일은 스폰서들과 만나 기대를 맞추는 것이다. 이를 통해 프로젝트 목표, 범위, 인도물, 리스크, 가정, 제약 조건을 둘러싼 신뢰, 소통, 협업이 자리 잡는다. 프로젝트 관리자는 프로젝트 헌장과 이해관계자 관리대장도 검토해 역할과 책임을 명확히 해야 한다. 멘토링 세션, 지식 저장소 검토, 킥오프 회의 일정 수립은 중요하지만 부차적인 활동이다.
2112 | A team is currently working on a mobile app solution. During sprint execution, one of the developers requires clarification about the acceptance criteria for a particular task. What should the project manager do to obtain the information required by the developer? | Request direction from the project sponsor | Work with the product owner to clarify the requirement | Write an email to the client requesting clarification | Seek support from the development manager. |  | B | When a developer needs clarification about acceptance criteria during sprint execution, the project manager should work with the product owner to clarify the requirement. The product owner owns requirements and acceptance criteria. Requesting direction from the sponsor (A) escalates unnecessarily. Writing an email to the client (C) bypasses the product owner. Seeking support from the development manager (D) addresses the wrong authority. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Build an Empowered Culture | Define Scope | Traditional PM | 팀이 모바일 앱 솔루션을 개발하고 있다. 스프린트 실행 중에 한 개발자가 특정 작업의 인수 기준에 대한 설명이 필요하다고 한다. 개발자에게 필요한 정보를 얻으려면 프로젝트 관리자는 무엇을 해야 하는가? | 프로젝트 스폰서에게 방향을 요청한다 | 제품 책임자와 협력하여 요구사항을 명확히 한다 | 고객에게 명확화를 요청하는 이메일을 작성한다 | 개발 관리자에게 지원을 구한다 |  | B | 스프린트 실행 중에 개발자가 인수 기준에 대한 설명이 필요하다면, 프로젝트 관리자는 제품 책임자와 협력해 요구사항을 명확히 해야 한다. 요구사항과 인수 기준의 책임자는 제품 책임자이다. 스폰서에게 방향을 요청하는 것(A)은 불필요한 에스컬레이션이다. 고객에게 이메일을 쓰는 것(C)은 제품 책임자를 건너뛴다. 개발 관리자에게 지원을 구하는 것(D)은 권한자를 잘못 짚은 것이다.
2113 | During a sprint planning, the development lead highlights the importance of working on technical debt tasks that are critical for the product performance. However, the tasks will consume most of the team's capacity and they will not be able to work on product feature development. What should the project manager do? | Add the technical debt tasks to the sprint backlog. | Ask the sponsor for more resources to continue at the same pace. | Work on the features already prioritized by the product owner. | Invite technical stakeholders for backlog prioritization. |  | D | The correct answer is D. Prioritizing technical debt against features is a backlog decision owned by the product owner. Inviting technical stakeholders to backlog prioritization lets the product owner weigh technical debt against product features with full information. Adding the work directly to the sprint backlog (A) bypasses the product owner, asking for more resources (B) is premature, and ignoring the technical debt (C) risks product performance. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Integrate Sustainability | Develop Schedule | Sustainability | 스프린트 계획 중에 개발 리드가 제품 성능에 매우 중요한 기술 부채 작업을 해야 한다고 강조한다. 그러나 이 작업은 팀 역량의 대부분을 차지해 제품 기능 개발을 할 수 없게 된다. 프로젝트 관리자는 무엇을 해야 하는가? | 기술 부채 작업을 스프린트 백로그에 추가한다 | 스폰서에게 같은 속도를 유지하기 위해 더 많은 자원을 요청한다 | 제품 책임자가 이미 우선순위화한 기능에 대해 작업한다 | 기술 이해관계자를 백로그 우선순위화에 초대한다 |  | D | 정답은 D이다. 기술 부채와 기능 사이의 우선순위는 제품 책임자가 결정하는 백로그 사안이다. 기술 이해관계자를 백로그 우선순위 논의에 초대하면 제품 책임자가 충분한 정보를 갖고 기술 부채와 기능을 비교할 수 있다. 스프린트 백로그에 바로 넣는 것(A)은 제품 책임자를 건너뛰고, 자원을 더 요청하는 것(B)은 성급하며, 기술 부채를 무시하는 것(C)은 제품 성능을 위험하게 한다.
2114 | A key stakeholder is refusing to participate in a crucial project stage and disagrees with the project team's approach. This situation is affecting the project team's morale. What should the project manager do? | Ask the project sponsor to meet with the project team and key stakeholder to discuss the approach. | Schedule a meeting with the project team and the key stakeholder as soon as possible to discuss and agree on an approach. | Ask the project team to meet and document why the stakeholder's approach is incorrect. | Discuss the issue with the project team during a project status meeting and request that they change the approach. |  | B | When a key stakeholder refuses to participate and disagrees with the project team's approach, affecting team morale, the project manager should schedule a meeting with the team and stakeholder as soon as possible to discuss and agree on an approach. Open dialogue resolves disagreements. Asking the sponsor to meet (A) escalates before attempting direct resolution. Documenting why the stakeholder is incorrect (C) is confrontational. Requesting the team change their approach (D) undermines the team. | People | Manage Conflict | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Manage Conflicts | Stakeholders | Executing | Build an Empowered Culture | Manage Stakeholder Engagement | Traditional PM | 주요 이해관계자가 핵심 프로젝트 단계 참여를 거부하고 팀의 접근법에 동의하지 않는다. 팀 사기에 영향을 미친다. PM은 무엇을 해야 하는가? | 프로젝트 스폰서에게 팀과 주요 이해관계자와 회의하여 접근법을 논의하도록 요청한다 | 팀과 주요 이해관계자와 가능한 빨리 회의를 잡아 합의에 도달한다 | 프로젝트 팀에게 이해관계자의 접근법이 왜 잘못되었는지 문서화하도록 요청한다 | 프로젝트 상태 회의에서 팀과 이슈를 논의하고 접근법을 변경하도록 요청한다 |  | B | 핵심 이해관계자가 참여를 거부하고 프로젝트 팀의 방식에 반대해 팀 사기에 영향을 준다면, 프로젝트 관리자는 가능한 한 빨리 팀과 이해관계자의 회의를 잡아 방식을 논의하고 합의해야 한다. 열린 대화가 이견을 해소한다. 스폰서에게 만나 달라고 요청하는 것(A)은 직접 해결을 시도하기 전에 에스컬레이션하는 것이다. 이해관계자가 왜 틀렸는지 문서화하는 것(C)은 대립적이다. 팀에 방식을 바꾸라고 요청하는 것(D)은 팀을 약화시킨다.
2115 | An organization that is running several simultaneous projects suddenly experiences a surge of resignations, leading to a lack of talent. Consequently, some of the projects have been missing key milestones. What should the project manager do to recover from the delays? | Crash the schedule from the delayed projects to meet upcoming target dates. | Fast-track the delayed projects so they can meet upcoming target dates. | Reduce the projects' scope to meet the upcoming target dates. | Ask for project sponsor approval to revise the upcoming target dates. |  | C | Mass resignations create a resource constraint that reduces delivery capacity across projects. The most practical recovery action is scope reduction—reprioritizing work to align with available capacity while protecting the most critical milestones. Crashing (A) requires adding resources that aren't available during a talent shortage. Fast-tracking (B) increases parallel work and coordination risk with insufficient staffing. Revising target dates (D) may be needed eventually but should follow scope optimization as the primary recovery strategy. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Planning | Focus on Value | Develop Schedule | Traditional PM | 여러 프로젝트를 동시에 진행하던 조직에서 갑자기 퇴사자가 몰리면서 인재가 부족해졌다. 그 결과 일부 프로젝트가 주요 마일스톤을 놓치고 있다. 지연을 만회하려면 프로젝트 관리자는 무엇을 해야 하는가? | 지연된 프로젝트의 일정을 크래싱하여 목표일을 맞춘다 | 지연된 프로젝트를 패스트트래킹하여 목표일을 맞춘다 | 프로젝트 범위를 줄여 목표일을 맞춘다 | 프로젝트 스폰서 승인을 받아 목표일을 수정한다 |  | C | 대규모 퇴사로 자원 제약이 생기면 납품 역량이 감소한다. 문제는 "다가오는 목표일을 맞추면서 지연을 복구"하는 방법을 묻고 있다. 크래싱(A)은 자원을 추가 투입하는 기법인데 투입할 인력 자체가 없어 불가능하다. 패스트트래킹(B)은 활동을 병행해 리스크와 재작업을 키우며 이 역시 추가 역량을 전제로 한다. 목표일 수정(D)은 일정 자체를 바꾸는 것이므로 "복구"가 아니라 재기준선 설정이다. 따라서 가용 역량에 맞게 작업을 재우선순위화하는 범위 축소(C)가 남는 유일한 실행 가능한 복구 수단이다. 다만 범위 축소는 PM이 단독으로 결정할 수 없으며, 변경요청을 제출해 스폰서·주요 이해관계자의 승인을 받아 통합 변경통제 절차를 거쳐야 한다.
2116 | During the third iteration, the team encounters a major delay that has not had significant improvements over the last few weeks. What should the project manager do? | Incorporate a predictive approach for this element. | Implement mitigation strategies for this element | Request additional team members to help with improvements | Retrospect frequently and suggest improvements. |  | D | The correct answer is D. A major delay has persisted for weeks without improvement, which suggests the team's way of working needs to change. Holding retrospectives more frequently lets the team inspect the causes and adapt quickly with concrete improvements. Switching that element to a predictive approach (A) is drastic, generic mitigation strategies (B) skip understanding the cause, and adding people (C) may slow the team further. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Agile | Scrum | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | 세 번째 이터레이션에서 팀이 지난 몇 번의 이터레이션 동안 크게 개선되지 않은 주요 지연을 겪고 있다. PM은 무엇을 해야 하는가? | 이 요소에 대해 예측형 접근법을 적용한다 | 이 요소에 대한 완화 전략을 구현한다 | 개선을 돕기 위해 추가 팀원을 요청한다 | 자주 회고하고 개선 사항을 제안한다 |  | D | 정답은 D이다. 큰 지연이 몇 주째 개선되지 않는다는 것은 팀의 일하는 방식이 바뀌어야 한다는 신호이다. 회고를 더 자주 하면 팀이 원인을 점검하고 구체적인 개선책으로 빠르게 적응할 수 있다. 그 요소를 예측형 방식으로 바꾸는 것(A)은 극단적이고, 일반적인 완화 전략(B)은 원인을 이해하는 과정을 건너뛰며, 인력을 추가하는 것(C)은 팀을 더 느리게 만들 수 있다.
2117 | The project team follows a hybrid framework for its delivery. During the execution of a project, the team learns of a new compliance requirement that has to be delivered before any other requirements. How should the project manager address this situation? | Collaborate with the compliance team member to review and prioritize the requirement's delivery | Ask the team to include the compliance requirement in the current sprint and deliver it. | Add the new compliance requirement to the backlog as the technical team does not have any capacity. | Include the compliance lead in the stakeholders list and wait for the next status meeting |  | A | When a new compliance requirement must be delivered before any other requirements in a hybrid project, the project manager should collaborate with the compliance team member to review and prioritize the requirement's delivery. This ensures proper change management, regulatory alignment, and stakeholder communication about the impact on scope, schedule, and cost. Asking the team to include it in the current sprint (B) disrupts sprint planning and may create scope creep. Adding it to the backlog without capacity consideration (C) delays a mandatory requirement. Including the compliance lead in the stakeholders list and waiting for the next meeting (D) fails to address the urgency and importance of the requirement. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 프로젝트 팀이 하이브리드 프레임워크를 따른다. 실행 중 새 컴플라이언스 요구사항이 다른 모든 요구사항보다 먼저 전달되어야 한다. PM은 무엇을 해야 하는가? | 컴플라이언스 팀원과 협력하여 요구사항의 전달을 검토하고 우선순위화한다 | 팀에게 현재 스프린트에 컴플라이언스 요구사항을 포함하여 전달하도록 요청한다 | 기술 팀이 역량이 없으므로 새 컴플라이언스 요구사항을 백로그에 추가한다 | 컴플라이언스 리드를 이해관계자 목록에 포함하고 다음 상태 회의를 기다린다 |  | A | 하이브리드 프로젝트에서 새 컴플라이언스 요구사항을 다른 모든 요구사항보다 먼저 인도해야 한다면, 프로젝트 관리자는 컴플라이언스 담당 팀원과 협력해 해당 요구사항의 인도를 검토하고 우선순위를 정해야 한다. 이렇게 해야 적절한 변경 관리, 규제 정합성, 그리고 범위·일정·원가 영향에 대한 이해관계자 소통이 보장된다. 팀에 현재 스프린트에 넣으라고 하는 것(B)은 스프린트 계획을 흔들고 범위 확대를 부를 수 있다. 가용 역량을 고려하지 않고 백로그에 추가하는 것(C)은 필수 요구사항을 늦춘다. 컴플라이언스 책임자를 이해관계자 목록에 넣고 다음 회의를 기다리는 것(D)은 요구사항의 긴급성과 중요성을 다루지 못한다.
2118 | The project manager is reviewing the program risks and issues with key stakeholders. One of the stakeholders wants to understand when the risk may potentially become an issue. What artifact should the project manager share with the stakeholder? | Risk management plan | Issue log | Risk register | Project management plan |  | C | The risk register is the artifact that shows when a risk may potentially become an issue. It records identified risks along with their probability, impact, status, response plans, and—critically—risk triggers, which are indicators or warning signs that a risk is about to occur. By reviewing the risk register, the stakeholder can understand the conditions under which each risk would materialize into an issue. The risk management plan (A) describes the processes and methodology for managing risks but does not track individual risk triggers. The issue log (B) records problems that have already occurred, not potential future risks. The project management plan (D) is a comprehensive document that does not specifically address risk timing. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Traditional PM | PM이 주요 이해관계자와 프로그램 리스크와 이슈를 검토 중이다. 이해관계자가 리스크가 언제 이슈가 될 수 있는지 알고 싶어 한다. 어떤 산출물을 참조해야 하는가? | 리스크 관리 계획 | 이슈 로그 | 리스크 등록부 | 프로젝트 관리 계획 |  | C | 리스크가 언제 이슈로 바뀔 수 있는지 보여 주는 산출물은 리스크 관리대장이다. 리스크 관리대장에는 식별된 리스크와 함께 발생 확률, 영향, 상태, 대응 계획, 그리고 특히 리스크가 곧 발생할 것임을 알려 주는 징후인 리스크 트리거가 기록된다. 리스크 관리대장을 보면 이해관계자는 각 리스크가 어떤 조건에서 이슈로 현실화되는지 이해할 수 있다. 리스크 관리 계획(A)은 리스크 관리 절차와 방법론을 설명할 뿐 개별 리스크 트리거를 추적하지 않는다. 이슈 로그(B)는 이미 발생한 문제를 기록하며 미래의 잠재 리스크를 다루지 않는다. 프로젝트관리계획서(D)는 포괄적인 문서로, 리스크 발생 시점을 구체적으로 다루지 않는다.
2119 | Due to delays on some activities, one of the project team members has increased the scope without any approval. What should the project manager do next? | Remove the changes to match the original requirements. | Update project documentation with the new scope | Evaluate the impacts of the changes that were made to the project | Add team members to the project to avoid more schedule delays. |  | C | When a team member has increased scope without approval due to delays, the project manager should evaluate the impacts of the unauthorized changes. Impact assessment enables informed decisions. Removing changes to match original requirements (A) may not be optimal. Updating documentation with the new scope (B) legitimizes unapproved changes. Adding team members (D) treats the symptom, not the cause. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | Traditional PM | 일부 활동의 지연으로 팀원 중 한 명이 승인 없이 범위를 확대했다. PM은 무엇을 해야 하는가? | 원래 요구사항에 맞도록 변경을 제거한다 | 새 범위로 프로젝트 문서를 업데이트한다 | 프로젝트에 대한 변경의 영향을 평가한다 | 더 많은 일정 지연을 피하기 위해 팀원을 추가한다 |  | C | 팀원이 지연으로 인해 승인 없이 범위를 확대했을 때, PM은 비승인 변경의 영향을 평가해야 한다. 영향 평가가 정보에 기반한 결정을 가능하게 한다. 변경 제거(A)는 평가 없이 작업을 되돌린다. 문서 업데이트(B)는 승인 없이 변경을 수용한다. 팀원 추가(D)는 범위 문제를 다루지 않는다.
2120 | A project manager is leading a software development project. The team suggests using an AI-powered tool to automate code reviews and identify potential defects. What should the project manager do FIRST? | Reject the suggestion because AI tools are unreliable for code quality. | Immediately implement the AI tool across all codebases. | Evaluate the AI tool's accuracy, data privacy implications, and alignment with organizational policies before implementation. | Delegate the decision entirely to the development team lead. |  | C | Before implementing any AI tool, a project manager should conduct a thorough evaluation of its accuracy, data privacy implications, and alignment with organizational policies. The PMBOK 8th Edition emphasizes that AI integration requires ethical considerations and governance oversight. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PM이 소프트웨어 개발 프로젝트를 이끌고 있다. 팀이 코드 리뷰를 자동화하기 위해 AI 도구를 사용하자고 제안한다. PM은 무엇을 해야 하는가? | AI 도구가 코드 품질에 신뢰할 수 없으므로 제안을 거부한다 | 즉시 모든 코드베이스에 AI 도구를 구현한다 | AI 도구의 정확성, 데이터 프라이버시 영향, 조직 정책과의 정렬을 평가한다 | 결정을 전적으로 개발 팀 리더에게 위임한다 |  | C | AI 도구를 구현하기 전에 PM은 정확성, 데이터 프라이버시 영향, 조직 정책과의 정렬을 철저히 평가해야 한다. PMBOK 8판은 신기술 도입 시 평가와 거버넌스를 강조한다. 거부(A)는 잠재적 이점을 무시한다. 즉시 구현(B)은 리스크 평가 없이 진행한다. 위임(D)은 PM의 거버넌스 책임을 회피한다.
2121 | A project team is using AI-based predictive analytics to forecast project schedule risks. The AI model predicts a 78% probability of a 3-week delay in the critical path. What should the project manager do? | Use the AI prediction as an input to risk response planning, combining it with expert judgment and historical data. | Ignore the AI prediction and rely solely on the team's expert judgment. | Report the delay to the sponsor without any mitigation plan. | Immediately extend the project timeline by 3 weeks. |  | A | AI-based predictive analytics should be used as one input among several in decision-making, not as the sole determinant. The PMBOK 8th Edition advocates combining AI insights with expert judgment and historical data for risk response planning. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | AI | 프로젝트 팀이 AI 기반 예측 분석을 사용하여 일정 리스크를 예측한다. AI 모델이 핵심 인도물에 78% 확률로 3주 지연을 예측한다. PM은 무엇을 해야 하는가? | AI 예측을 리스크 대응 계획의 입력으로 사용하되 전문가 판단 및 과거 데이터와 결합한다 | AI 예측을 무시하고 팀의 전문가 판단에만 의존한다 | 완화 계획 없이 스폰서에게 지연을 보고한다 | 즉시 프로젝트 일정을 3주 연장한다 |  | A | AI 기반 예측 분석은 의사결정의 유일한 결정 요소가 아닌 여러 입력 중 하나로 사용해야 한다. PMBOK 8판은 AI 통찰을 전문가 판단 및 과거 데이터와 결합하는 것을 권장한다. 무시(B)는 유용한 데이터를 낭비한다. 완화 없는 보고(C)는 비전문적이다. 즉시 연장(D)은 과도한 반응이다.
2122 | An organization wants to use a generative AI tool to draft project charters and scope documents. What is the MOST important consideration for the project manager? | The cost savings from reducing manual documentation effort. | Training only the project manager to use the AI tool. | The speed at which the AI generates documents. | Ensuring human review and validation of all AI-generated content for accuracy, completeness, and organizational alignment. |  | D | When using generative AI for project documentation, human oversight is critical. AI-generated content must be reviewed for accuracy, completeness, and alignment with organizational standards and stakeholder expectations. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | 조직이 프로젝트 헌장과 범위 문서 초안 작성에 생성형 AI 도구를 사용하려 한다. 가장 중요한 고려사항은 무엇인가? | 수동 문서화 노력 감소로 인한 비용 절감 | PM만 AI 도구 사용법을 교육하기 | AI가 문서를 생성하는 속도 | 정확성, 완전성, 조직 표준 및 이해관계자 기대와의 정렬을 위한 모든 AI 생성 콘텐츠의 인간 검토 및 검증 보장 |  | D | 생성형 AI를 프로젝트 문서에 사용할 때 인간 감독이 중요하다. AI 생성 콘텐츠는 정확성, 완전성, 조직 표준 및 이해관계자 기대와의 정렬을 위해 검토되어야 한다. 비용 절감(A)은 부차적 이점이다. PM만 교육(B)은 팀 역량을 제한한다. 속도(C)는 품질보다 중요하지 않다.
2123 | A project manager notices that team members are resistant to adopting a new AI-powered project management dashboard. What is the BEST approach? | Mandate the use of the AI dashboard and set a compliance deadline. | Understand the team's concerns, provide training, demonstrate the dashboard's benefits, and allow a transition period. | Abandon the AI dashboard implementation to maintain team morale. | Remove the old tools immediately to force adoption. |  | B | Resistance to new technology should be addressed through change management best practices. Understanding concerns, providing adequate training, demonstrating tangible benefits, and allowing a transition period are key to successful adoption. | People | Lead a Team | Team | Demonstrate Leadership Behaviors | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Acquire Resources | AI | PM이 팀원들이 새 AI 기반 프로젝트 관리 대시보드 도입에 저항하고 있음을 발견한다. PM은 무엇을 해야 하는가? | AI 대시보드 사용을 의무화하고 준수 기한을 설정한다 | 팀의 우려를 이해하고 교육을 제공하며 대시보드의 이점을 시연하고 전환 기간을 허용한다 | 팀 사기를 유지하기 위해 AI 대시보드 구현을 포기한다 | 강제 도입을 위해 기존 도구를 즉시 제거한다 |  | B | 새 기술에 대한 저항은 변화 관리 모범 사례를 통해 해결해야 한다. 우려 이해, 충분한 교육 제공, 실질적 이점 시연, 전환 기간 허용이 효과적이다. 의무화(A)는 저항을 증가시킨다. 포기(C)는 잠재적 이점을 잃는다. 기존 도구 제거(D)는 강압적이다.
2124 | During sprint planning, a team member suggests using an AI algorithm to prioritize the product backlog based on customer sentiment analysis. The product owner is concerned about losing control of prioritization. What should the project manager recommend? | Ignore the suggestion and continue with manual prioritization only. | Let the team vote on whether to use AI or not. | Use AI sentiment analysis as supplementary data to inform the product owner's prioritization decisions. | Allow the AI to fully control backlog prioritization to improve objectivity. |  | C | AI should augment, not replace, human decision-making. Using AI sentiment analysis as supplementary data empowers the product owner with additional insights while maintaining their authority over prioritization. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | 스프린트 계획 중에 한 팀원이 고객 감성 분석을 바탕으로 AI 알고리즘을 써서 제품 백로그 우선순위를 정하자고 제안한다. 제품 책임자는 우선순위 결정권을 잃을까 봐 우려한다. 프로젝트 관리자는 무엇을 권해야 하는가? | 제안을 무시하고 수동 우선순위화만 계속한다 | AI 사용 여부에 대해 팀 투표를 실시한다 | AI 감성 분석을 제품 책임자의 우선순위화 결정을 알리는 보충 데이터로 사용한다 | 객관성 향상을 위해 AI가 백로그 우선순위화를 완전히 통제하도록 한다 |  | C | AI는 인간의 의사결정을 대체하는 것이 아니라 보완해야 한다. AI 감성 분석을 보충 데이터로 사용하면 제품 책임자에게 추가 통찰을 제공하면서 우선순위화에 대한 권한을 유지한다. 무시(A)는 유용한 데이터를 낭비한다. 투표(B)는 결정 권한을 희석한다. 완전 AI 통제(D)는 인간 판단을 제거한다.
2125 | A PMO is implementing an AI-based resource allocation system that recommends optimal team assignments across multiple projects. A functional manager raises concerns about the system overriding their authority. How should the PM handle this? | Configure the AI system to make binding resource allocation decisions. | Disable the AI system and revert to manual allocation. | Escalate the concern to senior management without engaging the functional manager. | Position the AI system as a recommendation engine that supports, but does not replace, the functional manager's decisions. |  | D | AI systems should be positioned as recommendation tools that enhance decision-making rather than replace human authority. This approach respects the functional manager's governance role while leveraging AI's analytical capabilities. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Resources | Executing | Be an Accountable Leader | Acquire Resources | AI | PMO가 여러 프로젝트에 최적의 팀 배정을 추천하는 AI 기반 자원 배분 시스템을 구현 중이다. 기능 관리자가 우려한다. PM은 무엇을 해야 하는가? | AI 시스템이 구속력 있는 자원 배분 결정을 내리도록 구성한다 | AI 시스템을 비활성화하고 수동 배분으로 복귀한다 | 기능 관리자와 소통하지 않고 상위 경영진에게 우려를 에스컬레이션한다 | AI 시스템을 기능 관리자의 의사결정을 지원하되 대체하지 않는 추천 엔진으로 포지셔닝한다 |  | D | AI 시스템은 인간의 권한을 대체하는 것이 아니라 의사결정을 향상시키는 추천 도구로 포지셔닝해야 한다. 이는 기능 관리자의 거버넌스 역할을 존중하면서 AI 데이터의 이점을 활용한다. 구속력 결정(A)은 권한을 침해한다. 비활성화(B)는 이점을 포기한다. 에스컬레이션(C)은 직접 소통을 회피한다.
2126 | A project team is using AI to automate testing in a continuous integration pipeline. The AI tool starts producing false positives at an increasing rate. What should the project manager do? | Investigate the root cause of false positives, retrain or recalibrate the AI model, and establish quality thresholds for acceptable performance. | Ignore the false positives since they don't affect production. | Immediately remove the AI tool from the pipeline. | Continue using the AI tool and manually verify all flagged issues. |  | A | When AI tools show degraded performance, the appropriate response is root cause investigation and corrective action, not abandonment or ignoring the issue. Retraining or recalibrating the model and setting quality thresholds ensures the tool continues to provide value. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | XP (Extreme Programming) | Process | Plan and Optimize Quality | Governance | Monitoring & Controlling | Embed Quality | Monitor and Control Project Performance | AI | 프로젝트 팀이 CI 파이프라인에서 테스트 자동화에 AI를 사용 중이다. AI 도구가 오탐(false positive)을 생성하기 시작한다. PM은 무엇을 해야 하는가? | 오탐의 근본 원인을 조사하고 AI 모델을 재훈련/재보정하며 품질 게이트를 수립한다 | 프로덕션에 영향이 없으므로 오탐을 무시한다 | 파이프라인에서 AI 도구를 즉시 제거한다 | AI 도구를 계속 사용하고 플래그된 모든 이슈를 수동으로 검증한다 |  | A | AI 도구의 성능이 저하되면 적절한 대응은 근본 원인 조사와 시정 조치이지, 폐기나 무시가 아니다. 모델 재훈련/재보정과 품질 게이트 설정이 문제를 체계적으로 해결한다. 무시(B)는 팀 신뢰를 훼손한다. 즉시 제거(C)는 이점을 포기한다. 수동 검증(D)은 비효율적이다.
2127 | A project manager wants to use AI-powered natural language processing (NLP) to analyze stakeholder communications and detect early warning signs of dissatisfaction. What ethical concern should be addressed FIRST? | Stakeholder consent, data privacy, and transparency about how their communications will be analyzed. | Whether the NLP tool integrates with existing communication platforms. | The accuracy rate of sentiment detection. | The cost of the NLP tool. |  | A | Ethical considerations, including stakeholder consent, data privacy, and transparency, must be addressed before implementing any AI tool that analyzes personal communications. The PMBOK 8th Edition includes dedicated guidance on ethical AI use. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | AI | PM이 이해관계자 커뮤니케이션을 분석하고 감성을 감지하기 위해 AI 기반 NLP를 사용하려 한다. 가장 중요한 고려사항은 무엇인가? | 이해관계자 동의, 데이터 프라이버시, 커뮤니케이션 분석 방법에 대한 투명성 | NLP 도구가 기존 커뮤니케이션 플랫폼과 통합되는지 여부 | 감성 감지의 정확도 | NLP 도구의 비용 |  | A | 개인 커뮤니케이션을 분석하는 AI 도구를 구현하기 전에 이해관계자 동의, 데이터 프라이버시, 투명성 등 윤리적 고려사항을 먼저 다루어야 한다. PMBOK 8판은 AI 도구에 대한 윤리적 프레임워크를 강조한다. 통합(B), 정확도(C), 비용(D)은 모두 윤리 후에 고려할 사항이다.
2128 | An agile team is debating whether to use AI-assisted estimation for story points. Some team members believe it will undermine their professional judgment. What is the BEST course of action? | Run a pilot where AI estimates are compared alongside team estimates to evaluate accuracy and build trust. | Allow each team member to decide individually whether to use AI estimates. | Replace all manual estimation with AI to eliminate human bias. | Postpone the decision until the next project. |  | A | A pilot approach allows the team to empirically evaluate AI-assisted estimation against their own estimates, building evidence-based trust in the tool. This respects the team's expertise while exploring potential improvements. | People | Support Team Performance | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Lead the Project Team | Schedule | Executing | Build an Empowered Culture | Direct and Manage Project Work | AI | 애자일 팀이 스토리 포인트에 AI 보조 추정을 사용할지 논의 중이다. 일부 팀원은 팀 전문성을 약화시킨다고 우려한다. PM은 무엇을 해야 하는가? | AI 추정과 팀 추정을 비교하여 정확도를 평가하고 신뢰를 구축하는 파일럿을 실행한다 | 각 팀원이 AI 추정 사용 여부를 개별적으로 결정하도록 한다 | 인간 편향을 제거하기 위해 모든 수동 추정을 AI로 대체한다 | 다음 프로젝트까지 결정을 연기한다 |  | A | 파일럿 접근법은 팀이 AI 보조 추정을 자체 추정과 경험적으로 비교하여 도구에 대한 증거 기반 신뢰를 구축할 수 있게 한다. 개별 결정(B)은 일관성이 없다. 전면 AI 대체(C)는 팀 전문성을 무시한다. 연기(D)는 기회를 놓친다.
2129 | A project manager is using an AI chatbot to provide 24/7 project status updates to stakeholders across different time zones. The chatbot occasionally provides incorrect information. What should the project manager do? | Add a disclaimer that the chatbot may provide inaccurate information. | Shut down the chatbot and revert to email-only updates. | Implement a feedback mechanism, regularly audit chatbot responses, and update the knowledge base to improve accuracy. | Limit the chatbot to only stakeholders in the same time zone. |  | C | The correct answer is C. The chatbot provides value with 24/7 updates, but its accuracy must improve. A feedback mechanism, regular audits of its responses, and updates to its knowledge base create a continuous improvement loop that keeps the benefit while fixing the errors. A disclaimer (A) shifts the burden to stakeholders, shutting it down (B) loses the benefit, and limiting it to one time zone (D) defeats its purpose. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Hybrid | Predictive-Agile Blend | People | Plan and Manage Communication | Stakeholders | Monitoring & Controlling | Embed Quality | Monitor Communications | AI | PM이 다른 시간대의 이해관계자에게 24/7 프로젝트 상태 업데이트를 제공하기 위해 AI 챗봇을 사용 중이다. 챗봇이 부정확한 응답을 한다. PM은 무엇을 해야 하는가? | 챗봇이 부정확한 정보를 제공할 수 있다는 면책 조항을 추가한다 | 챗봇을 종료하고 이메일 전용 업데이트로 복귀한다 | 피드백 메커니즘을 구현하고 정기적으로 챗봇 응답을 감사하며 지식 베이스를 업데이트한다 | 챗봇을 같은 시간대의 이해관계자에게만 제한한다 |  | C | 정답은 C이다. 챗봇은 24시간 현황 제공이라는 가치를 주지만 정확도를 높여야 한다. 피드백 체계를 두고, 답변을 정기적으로 점검하며, 지식 베이스를 갱신하면 효익을 유지하면서 오류를 고치는 지속적 개선 고리가 만들어진다. 면책 문구를 다는 것(A)은 부담을 이해관계자에게 넘기고, 챗봇을 중단하는 것(B)은 효익을 잃으며, 한 시간대로 제한하는 것(D)은 도입 목적을 무너뜨린다.
2130 | A construction project is using AI-powered drones for site inspection and progress monitoring. The AI generates progress reports that conflict with the field superintendent's observations. What should the project manager do? | Trust the AI data over the field superintendent's assessment. | Analyze the discrepancy between AI data and field observations, identify the source of the difference, and calibrate the system accordingly. | Present both reports to the sponsor and let them decide. | Trust the field superintendent and discontinue the AI drone monitoring. |  | B | When AI outputs conflict with human observations, investigation and calibration are needed rather than choosing one over the other. The discrepancy may reveal calibration issues with the AI, blind spots in human observation, or different measurement criteria. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Predictive | Traditional Plan-Driven | Process | Plan and Optimize Quality | Governance | Monitoring & Controlling | Adopt a Holistic View | Monitor and Control Project Performance | AI | 건설 프로젝트가 현장 검사와 진행 모니터링에 AI 드론을 사용 중이다. AI가 생성한 보고서와 현장 감독관의 보고서가 다르다. PM은 무엇을 해야 하는가? | 현장 감독관의 평가보다 AI 데이터를 신뢰한다 | AI 데이터와 현장 관찰 간의 불일치를 분석하고 차이의 원인을 식별하며 양 입력을 보정한다 | 양 보고서를 스폰서에게 제시하고 결정하게 한다 | 현장 감독관을 신뢰하고 AI 드론 모니터링을 중단한다 |  | B | AI 출력과 인간 관찰이 충돌할 때, 하나를 선택하는 것이 아니라 조사와 보정이 필요하다. 불일치는 AI 보정 문제, 사각지대 또는 인적 오류를 밝힐 수 있다. AI만 신뢰(A)는 현장 지식을 무시한다. 스폰서 결정(C)은 책임 전가이다. AI 중단(D)은 이점을 포기한다.
2131 | A project manager is evaluating AI tools for risk identification. Which factor is MOST critical when selecting an AI risk management tool? | The tool's ability to learn from the organization's historical project data and integrate with existing risk management processes. | The tool's user interface and visual appeal. | The vendor's market share and reputation. | The lowest cost option available in the market. |  | A | The most critical factor for an AI risk management tool is its ability to learn from organizational historical data and integrate with existing processes. This ensures contextual accuracy and seamless workflow adoption. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | AI | PM이 리스크 식별을 위한 AI 도구를 평가 중이다. AI 리스크 관리 도구 선택 시 가장 중요한 요소는 무엇인가? | 조직의 과거 프로젝트 데이터로부터 학습하고 기존 프로세스와 통합하는 능력 | 도구의 사용자 인터페이스와 시각적 매력 | 벤더의 시장 점유율과 평판 | 시장에서 가장 저렴한 옵션 |  | A | AI 리스크 관리 도구의 가장 중요한 요소는 조직의 과거 데이터로부터 학습하고 기존 프로세스와 통합하는 능력이다. 이는 맥락적 정확성과 원활한 워크플로 통합을 보장한다. UI(B), 평판(C), 비용(D)은 모두 부차적이다.
2132 | During a project retrospective, the team discovers that their AI-based scheduling tool consistently underestimates task durations by 15-20%. What is the BEST corrective action? | Abandon AI scheduling and return to traditional estimation methods. | Add a 20% buffer to all AI-generated estimates going forward. | Retrain the AI model with updated historical data, adjust the algorithm parameters, and validate against actual performance metrics. | Accept the underestimation as a known risk and proceed. |  | C | Systematic bias in AI models should be addressed through retraining with updated data and algorithm adjustment. Simply adding buffers is a workaround, not a fix. Abandoning loses potential value. Accepting without correction perpetuates schedule overruns. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Agile General Practices | Process | Plan and Manage Schedule | Schedule | Monitoring & Controlling | Embed Quality | Control Schedule | AI | 프로젝트 회고에서 AI 기반 일정 도구가 지속적으로 작업 기간을 과소평가하는 것을 발견했다. PM은 무엇을 해야 하는가? | AI 일정을 포기하고 전통적 추정 방법으로 돌아간다 | 향후 모든 AI 생성 추정에 20% 버퍼를 추가한다 | 업데이트된 과거 데이터로 AI 모델을 재훈련하고 알고리즘 매개변수를 조정하며 알려진 결과와 검증한다 | 과소추정을 알려진 리스크로 수용하고 진행한다 |  | C | AI 모델의 체계적 편향은 업데이트된 데이터로 재훈련하고 알고리즘을 조정하여 해결해야 한다. 버퍼 추가(B)는 우회책이지 수정이 아니다. 포기(A)는 잠재적 가치를 잃는다. 수용(D)은 문제를 방치한다.
2133 | A project team wants to use machine learning to predict which project risks are most likely to materialize based on patterns from past projects. Which data governance practice should the PM ensure FIRST? | That the machine learning model uses the latest algorithm. | That the model is deployed in the cloud for scalability. | That the training data is diverse and representative of various project types and environments. | That only the data science team has access to the model's outputs. |  | C | Data quality and representativeness are fundamental to machine learning effectiveness. Training data must be diverse and representative to avoid bias and ensure accurate predictions across different project contexts. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | AI | 프로젝트 팀이 과거 데이터 패턴에 기반하여 어떤 프로젝트 리스크가 실현될 가능성이 높은지 예측하기 위해 머신러닝을 사용하려 한다. 가장 중요한 것은 무엇인가? | 머신러닝 모델이 최신 알고리즘을 사용하는 것 | 모델이 확장성을 위해 클라우드에 배포되는 것 | 훈련 데이터가 다양하고 다양한 프로젝트 유형과 환경을 대표하는 것 | 데이터 과학 팀만 모델의 출력에 접근하는 것 |  | C | 데이터 품질과 대표성이 머신러닝 효과의 기본이다. 훈련 데이터는 편향을 방지하고 다양한 프로젝트 유형에서 정확한 예측을 보장하기 위해 다양하고 대표적이어야 한다. 최신 알고리즘(A), 클라우드 배포(B), 접근 제한(D)은 부차적이다.
2134 | An organization's PMO has developed an AI model that predicts project success rates based on initial project parameters. A new project scores only 35% success probability. What should the project manager do? | Recommend canceling the project based on the AI prediction. | Ignore the prediction and proceed as planned. | Use the prediction to identify the key risk factors driving the low score, develop targeted mitigation strategies, and re-evaluate. | Request a different AI model that gives a higher success prediction. |  | C | AI predictions should inform action, not dictate it. The PM should analyze which factors are driving the low score and develop mitigation strategies. This may improve the project's actual probability of success. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | AI | PMO가 초기 프로젝트 매개변수를 기반으로 프로젝트 성공률을 예측하는 AI 모델을 개발했다. 새 프로젝트가 35% 성공 확률을 받았다. PM은 무엇을 해야 하는가? | AI 예측에 기반하여 프로젝트 취소를 권장한다 | 예측을 무시하고 계획대로 진행한다 | 예측을 사용하여 낮은 점수를 유발하는 핵심 리스크 요소를 식별하고 목표 완화 전략을 개발한다 | 더 높은 성공 예측을 제공하는 다른 AI 모델을 요청한다 |  | C | AI 예측은 행동을 지시하는 것이 아니라 정보를 제공해야 한다. PM은 낮은 점수를 유발하는 요소를 분석하고 완화 전략을 개발해야 한다. 취소 권장(A)은 과잉 반응이다. 무시(B)는 유용한 데이터를 낭비한다. 다른 모델 요청(D)은 결과 쇼핑이다.
2135 | A project team is developing a customer-facing AI product. Mid-project, a new regulation requires AI systems to provide explainable decisions. How should the project manager handle this? | Continue with the current design and address compliance after delivery. | Delegate the compliance concern to the legal department only. | Remove AI decision-making features to avoid compliance issues. | Raise a change request to incorporate explainability requirements into the product design and update the project scope. |  | D | The correct answer is D. A new regulation that changes product requirements in mid-project affects scope, so it must go through formal change management. Raising a change request to add the explainability requirements, and updating the scope, keeps the product compliant and the plan accurate. Deferring compliance until after delivery (A) risks releasing a non-compliant product, handing it only to legal (B) ignores the design impact, and removing AI features (C) sacrifices the product's core value. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | AI | 프로젝트 팀이 고객 대면 AI 제품을 개발 중이다. 프로젝트 중간에 AI 시스템이 설명 가능성을 제공해야 하는 새 규제가 발효된다. PM은 무엇을 해야 하는가? | 현재 설계로 계속하고 납품 후 컴플라이언스를 처리한다 | 컴플라이언스 우려를 법무 부서에만 위임한다 | 컴플라이언스 문제를 피하기 위해 AI 의사결정 기능을 제거한다 | 설명 가능성 요구사항을 제품 설계에 통합하기 위한 변경 요청을 제출하고 프로젝트 계획을 업데이트한다 |  | D | 정답은 D이다. 프로젝트 도중 제품 요구사항을 바꾸는 새 규정은 범위에 영향을 주므로 공식 변경 관리를 거쳐야 한다. 설명 가능성 요구사항을 추가하는 변경 요청을 제기하고 범위를 갱신하면 제품의 규정 준수와 계획의 정확성을 유지할 수 있다. 인도 후로 준수를 미루는 것(A)은 규정에 맞지 않는 제품을 출시할 위험이 있고, 법무 부서에만 맡기는 것(B)은 설계에 미치는 영향을 무시하며, AI 기능을 빼는 것(C)은 제품의 핵심 가치를 희생한다.
2136 | A multinational project team uses an AI-powered translation tool for cross-language collaboration. A team member reports that the tool mistranslated a technical requirement, leading to a misunderstanding. What should the PM do? | Stop using the translation tool and hire human translators for all communications. | Accept occasional mistranslations as a risk of using AI tools. | Require all technical requirements to undergo human review after AI translation, especially for critical deliverables. | Ask team members to learn a common language. |  | C | For critical communications like technical requirements, AI translation should be supplemented with human review. This balances the efficiency of AI with the accuracy needed for critical project information. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | Agile | Agile General Practices | People | Plan and Manage Communication | Stakeholders | Executing | Embed Quality | Manage Communications | AI | 다국적 프로젝트 팀이 다국어 협업을 위해 AI 번역 도구를 사용 중이다. 팀원이 기술 요구사항에서 오역을 보고한다. PM은 무엇을 해야 하는가? | 번역 도구 사용을 중단하고 모든 커뮤니케이션에 인간 번역가를 고용한다 | AI 도구 사용의 리스크로서 간헐적 오역을 수용한다 | AI 번역 후 모든 기술 요구사항은 인간 검토를 거치도록 요구한다, 특히 중요 정보에 대해 | 팀원에게 공통 언어를 배우도록 요청한다 |  | C | 기술 요구사항과 같은 중요 커뮤니케이션에 대해 AI 번역은 인간 검토로 보완되어야 한다. 이는 AI의 효율성과 중요 정보에 필요한 정확성의 균형을 맞춘다. 전면 중단(A)은 비용이 과도하다. 오역 수용(B)은 리스크를 방치한다. 공통 언어(D)는 비현실적이다.
2137 | A project manager is implementing an AI-based earned value management (EVM) system that automatically calculates CPI and SPI. The system flags a project as at-risk, but the traditional EVM calculations show the project is on track. What should the PM investigate? | Use whichever result the sponsor prefers. | Compare the data inputs, calculation methods, and assumptions between both systems to identify the source of discrepancy. | Assume the AI is correct and report the project as at-risk. | Assume the AI is wrong and continue with traditional calculations. |  | B | The correct answer is B. When the AI-based and traditional EVM calculations disagree, the project manager should find out why by comparing their data inputs, calculation methods, and assumptions. Only then can the true project status be reported. Choosing the result the sponsor prefers (A) is unethical, and assuming either the AI (C) or the traditional method (D) is correct without investigation may lead to a wrong decision. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Adopt a Holistic View | Control Costs | AI | PM이 CPI와 SPI를 자동 계산하는 AI 기반 획득가치관리(EVM) 시스템을 구현 중이다. AI 결과가 전통적 계산과 다르다. PM은 무엇을 해야 하는가? | 스폰서가 선호하는 결과를 사용한다 | 양 시스템 간 데이터 입력, 계산 방법, 가정을 비교하여 차이의 원인을 식별한다 | AI가 맞다고 가정하고 프로젝트를 위험 상태로 보고한다 | AI가 틀렸다고 가정하고 전통적 계산을 계속한다 |  | B | 정답은 B이다. AI 기반 EVM과 기존 EVM의 계산 결과가 다르면, 두 시스템의 입력 데이터, 계산 방법, 가정을 비교해 그 이유를 밝혀야 한다. 그래야 실제 프로젝트 상태를 보고할 수 있다. 스폰서가 선호하는 결과를 쓰는 것(A)은 비윤리적이고, 조사 없이 AI(C)나 기존 방식(D) 중 하나가 맞다고 가정하면 잘못된 결정을 내릴 수 있다.
2138 | An organization is deploying an AI system that learns from individual employee productivity data to optimize team assignments. Several team members express concern about privacy and surveillance. What approach BEST addresses this? | Tell team members that productivity monitoring is a standard organizational practice. | Assure team members that only aggregate data, not individual data, is used for decision-making. | Develop and communicate a clear data usage policy, ensure compliance with privacy regulations, allow opt-out options, and establish a feedback channel. | Only share the AI system's recommendations with management, not with team members. |  | C | The correct answer is C. Privacy concerns about individual productivity data require transparency and safeguards: a clear data usage policy, compliance with privacy regulations, an opt-out option, and a feedback channel. Calling monitoring standard practice (A) dismisses the concern, assuring only aggregate use (B) does not match a system that learns from individual data, and hiding the recommendations from the team (D) increases distrust. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | General | Stakeholder & Communication Mgmt | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | AI | 조직이 개인 직원 생산성 데이터로부터 학습하여 팀 배정을 최적화하는 AI 시스템을 배포 중이다. 팀원들이 프라이버시 우려를 제기한다. PM은 무엇을 해야 하는가? | 생산성 모니터링이 표준 조직 관행이라고 팀원에게 말한다 | 개인 데이터가 아닌 집계 데이터만 의사결정에 사용됨을 보장한다 | 명확한 데이터 사용 정책을 개발하고 소통하며, 프라이버시 규정 준수를 보장하고, 옵트아웃 옵션과 피드백 채널을 허용한다 | AI 시스템의 추천을 경영진에게만 공유한다 |  | C | 정답은 C이다. 개인 생산성 데이터에 대한 프라이버시 우려를 해소하려면 투명성과 보호 장치가 필요하다. 명확한 데이터 사용 정책, 개인정보 규정 준수, 거부(opt-out) 선택권, 피드백 채널을 마련해야 한다. 모니터링이 표준 관행이라고 말하는 것(A)은 우려를 무시하고, 집계 데이터만 쓴다고 안심시키는 것(B)은 개인 데이터로 학습하는 시스템과 맞지 않으며, 추천 결과를 팀에 숨기는 것(D)은 불신을 키운다.
2139 | A project manager is considering using AI to automate the generation of lessons learned reports from project documents and team communication logs. What is a KEY risk of this approach? | The AI may miss contextual nuances, tacit knowledge, and interpersonal dynamics that are critical for meaningful lessons learned. | The AI may generate reports too quickly for the team to review. | The AI reports will be too long for stakeholders to read. | The AI will eliminate the need for retrospective meetings entirely. |  | A | The correct answer is A. Meaningful lessons learned depend on context, tacit knowledge, and interpersonal dynamics that are often absent from documents and logs. AI can help summarize, but it may miss these nuances, which are best captured through human discussion and reflection. Reports generated too quickly (B) or too long (C) are minor, manageable issues, and AI does not and should not eliminate retrospectives (D). | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Closing | Adopt a Holistic View | Close Project or Phase | AI | PM이 프로젝트 문서와 커뮤니케이션에서 교훈 보고서를 자동 생성하기 위해 AI 사용을 고려 중이다. 가장 중요한 고려사항은 무엇인가? | AI가 맥락적 뉘앙스, 암묵적 지식, 대인관계 역학을 놓칠 수 있으며 이는 포괄적 교훈에 중요하다 | AI가 팀이 검토하기에 너무 빠르게 보고서를 생성할 수 있다 | AI 보고서가 이해관계자가 읽기에 너무 길 수 있다 | AI가 회고 회의의 필요성을 완전히 제거할 수 있다 |  | A | 정답은 A이다. 의미 있는 교훈은 문서와 기록에 잘 남지 않는 맥락, 암묵지, 대인 관계의 역학에 달려 있다. AI는 요약에 도움이 되지만 이런 미묘한 부분을 놓칠 수 있으며, 이는 사람 간의 논의와 성찰로 가장 잘 포착된다. 보고서가 너무 빨리 나오는 것(B)이나 너무 긴 것(C)은 사소하고 관리 가능한 문제이고, AI가 회고를 없애지도 않으며 없애서도 안 된다(D).
2140 | A project manager is using AI to analyze project documentation and automatically identify potential scope creep. The AI flags 15 items as potential scope changes. After review, only 3 are actual scope changes. What does this indicate? | The AI model needs fine-tuning to reduce false positives while maintaining its ability to detect real scope changes. | The AI tool is useless and should be discontinued. | The project has a serious scope creep problem. | The remaining 12 items should still be treated as scope changes to be safe. |  | A | The correct answer is A. The AI flagged 15 items but only 3 were real scope changes, so it produces many false positives while still catching real changes. The right response is to fine-tune the model to reduce false positives without losing detection. Calling the tool useless (B) ignores that it found the real changes, concluding there is serious scope creep (C) misreads the data, and treating all 15 as changes (D) creates unnecessary work and noise. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Monitoring & Controlling | Embed Quality | Control Scope | AI | PM이 프로젝트 문서를 분석하여 범위 변경을 자동 식별하는 AI를 사용 중이다. AI가 15개 변경 항목을 플래그했지만 검토 결과 3개만 실제 범위 변경이었다. 이것은 무엇을 의미하는가? | 오탐률을 줄이면서 실제 범위 변경 감지 능력은 유지하도록 AI 모델의 미세 조정이 필요하다 | AI 도구가 쓸모없으므로 중단해야 한다 | 프로젝트에 심각한 범위 변경 문제가 있다 | 나머지 12개 항목도 안전을 위해 범위 변경으로 처리해야 한다 |  | A | 정답은 A이다. AI가 15건을 표시했지만 실제 범위 변경은 3건뿐이므로, 실제 변경은 잡아내면서도 오탐이 많은 상태이다. 탐지 능력을 유지하면서 오탐을 줄이도록 모델을 미세 조정하는 것이 올바른 대응이다. 도구가 쓸모없다고 보는 것(B)은 실제 변경을 찾아낸 점을 무시하고, 심각한 범위 확대가 있다고 결론 내리는 것(C)은 데이터를 잘못 읽은 것이며, 15건을 모두 변경으로 취급하는 것(D)은 불필요한 작업과 혼선을 만든다.
2141 | A team member has developed an AI script that automates repetitive project reporting tasks, saving 10 hours per week. The script was not approved through the organization's IT governance process. What should the PM do? | Report the team member for violating IT policies. | Ask the team member to keep using the script quietly. | Immediately stop use of the script and work with IT governance to evaluate and formally approve it. | Allow the team member to continue using the script since it improves productivity. |  | C | The correct answer is C. Even a helpful tool must go through IT governance, because an unapproved script may create security, privacy, or compliance risks. The project manager should stop its use and work with IT governance to evaluate and approve it, preserving the benefit through the proper channel. Reporting the team member (A) is punitive, using it quietly (B) or continuing as is (D) ignores the risk and the policy. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | AI | 팀원이 반복적 프로젝트 보고 작업을 자동화하는 AI 스크립트를 개발하여 주당 10시간을 절약한다. 그러나 IT 거버넌스의 승인을 받지 않았다. PM은 무엇을 해야 하는가? | IT 정책 위반으로 팀원을 보고한다 | 팀원에게 스크립트를 조용히 계속 사용하도록 요청한다 | 즉시 스크립트 사용을 중단하고 IT 거버넌스와 협력하여 평가하고 공식 승인한다 | 생산성이 향상되므로 팀원이 스크립트를 계속 사용하도록 허용한다 |  | C | 정답은 C이다. 유용한 도구라도 IT 거버넌스를 거쳐야 한다. 승인되지 않은 스크립트는 보안, 개인정보, 규정 준수 리스크를 만들 수 있기 때문이다. 프로젝트 관리자는 사용을 중단하고 IT 거버넌스와 함께 평가·승인을 받아, 올바른 경로로 효익을 살려야 한다. 팀원을 신고하는 것(A)은 징벌적이고, 몰래 계속 쓰게 하거나(B) 그대로 허용하는 것(D)은 리스크와 정책을 무시한다.
2142 | A project team uses AI to extract requirements from stakeholder interview transcripts. The AI identifies 200 requirements, but the stakeholders confirm only 150 are valid. What BEST describes the project manager's next step? | Review the 50 invalid requirements to understand why the AI misidentified them, refine the extraction criteria, and validate the remaining 150 with stakeholders. | Use only the 150 confirmed requirements without further analysis. | Accept all 200 requirements to avoid missing any. | Discard all AI-identified requirements and manually re-analyze transcripts. |  | A | The correct answer is A. The AI extracted 50 requirements that stakeholders did not confirm. Reviewing why they were misidentified helps refine the extraction criteria and may reveal ambiguous statements in the interviews, while the 150 valid ones are confirmed with stakeholders. Using the 150 without analysis (B) loses the learning, accepting all 200 (C) adds invalid scope, and discarding all AI output (D) wastes the useful work. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | 프로젝트 팀이 이해관계자 인터뷰 녹취록에서 AI로 요구사항을 추출했다. AI는 요구사항 200개를 식별했지만, 이해관계자들은 그중 150개만 유효하다고 확인했다. 프로젝트 관리자의 다음 단계로 가장 적절한 것은 무엇인가? | 유효하지 않은 50개를 AI가 왜 잘못 식별했는지 검토하고 추출 기준을 개선한 뒤, 나머지 150개를 이해관계자와 검증한다. | 150개 확인된 요구사항만 추가 분석 없이 사용한다 | 누락을 피하기 위해 200개 요구사항을 모두 수용한다 | AI 식별 요구사항을 모두 폐기하고 녹취록을 수동으로 재분석한다 |  | A | 정답은 A이다. AI가 추출한 요구사항 중 50건은 이해관계자가 확인하지 않았다. 왜 잘못 식별했는지 검토하면 추출 기준을 개선할 수 있고 인터뷰의 모호한 표현도 드러날 수 있으며, 유효한 150건은 이해관계자와 확인한다. 분석 없이 150건만 쓰는 것(B)은 배울 기회를 잃고, 200건을 모두 받아들이는 것(C)은 유효하지 않은 범위를 더하며, AI 결과를 전부 버리는 것(D)은 유용한 작업을 낭비한다.
2143 | A senior executive asks the project manager to use AI to replace the project's quality assurance team. What should the project manager explain? | AI can automate routine testing tasks but cannot fully replace human judgment for complex quality decisions, exploratory testing, and user experience evaluation. | AI can fully replace the QA team and reduce project costs significantly. | AI in QA is unreliable and should not be considered. | The QA team should decide whether to adopt AI tools. |  | A | The correct answer is A. AI can automate routine, repetitive testing, but complex quality decisions, exploratory testing, and user-experience evaluation still require human judgment. The project manager should explain this balance to the executive. Claiming AI can fully replace QA (B) is unrealistic, dismissing AI entirely (C) ignores real benefits, and leaving the decision to the QA team alone (D) avoids the project manager's advisory role. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Embed Quality | Develop Project Management Plan | AI | 고위 경영진이 PM에게 AI로 프로젝트의 품질보증(QA) 팀을 대체하라고 요청한다. PM은 무엇을 해야 하는가? | AI는 일상적 테스트 작업을 자동화할 수 있지만 복잡한 품질 결정에 대한 인간 판단을 완전히 대체할 수 없다고 설명한다 | AI가 QA 팀을 완전히 대체하여 프로젝트 비용을 크게 줄일 수 있다고 설명한다 | QA에서 AI는 신뢰할 수 없으므로 고려하지 말아야 한다고 설명한다 | QA 팀이 AI 도구 도입 여부를 결정해야 한다고 설명한다 |  | A | 정답은 A이다. AI는 반복적인 일상 테스트를 자동화할 수 있지만, 복잡한 품질 판단, 탐색적 테스트, 사용자 경험 평가에는 여전히 사람의 판단이 필요하다. 프로젝트 관리자는 이 균형을 임원에게 설명해야 한다. AI가 QA를 완전히 대체할 수 있다는 주장(B)은 비현실적이고, AI를 아예 배제하는 것(C)은 실제 효익을 무시하며, QA 팀에게만 결정을 맡기는 것(D)은 프로젝트 관리자의 조언 역할을 회피하는 것이다.
2144 | An agile project is using AI-based velocity prediction to plan upcoming sprints. The AI predicts a velocity of 45 story points, but the team historically averages 35. What should the Scrum Master recommend? | Ignore the AI prediction and stick with the historical average of 35. | Commit to 45 story points as the AI prediction suggests. | Plan for 35 story points based on historical performance, investigate why the AI predicts higher, and monitor if team capacity has genuinely increased. | Split the difference and plan for 40 story points. |  | C | The correct answer is C. Historical velocity is the most reliable planning input, so the team should plan around 35 points. The higher AI prediction should not be ignored, though; the scrum master should investigate why it is higher and monitor whether capacity has really changed. Ignoring the AI entirely (A) loses a possible insight, committing to 45 (B) risks overcommitment, and splitting the difference (D) is arbitrary. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Agile | Scrum | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | AI | 애자일 프로젝트가 AI 기반 속도 예측을 사용하여 다음 스프린트를 계획 중이다. AI가 45 스토리 포인트를 예측하지만 과거 평균은 35이다. PM은 무엇을 해야 하는가? | AI 예측을 무시하고 과거 평균 35를 고수한다 | AI 예측대로 45 스토리 포인트에 커밋한다 | 과거 성과에 기반하여 35 스토리 포인트를 계획하되, AI가 왜 더 높은 예측을 하는지 조사하고 향후 스프린트의 계획 정확도를 높이기 위해 결과를 사용한다 | 차이를 절충하여 40 스토리 포인트를 계획한다 |  | C | 정답은 C이다. 과거 속도가 가장 신뢰할 만한 계획 근거이므로 35포인트를 기준으로 계획해야 한다. 다만 더 높은 AI 예측을 무시하지 말고, 왜 높게 나왔는지 조사하고 팀의 역량이 실제로 바뀌었는지 모니터링해야 한다. AI를 완전히 무시하는 것(A)은 가능한 통찰을 놓치고, 45포인트를 약속하는 것(B)은 과도한 약속의 위험이 있으며, 중간값으로 정하는 것(D)은 근거가 없다.
2145 | A project manager discovers that the AI tool used for vendor evaluation has a bias toward larger vendors due to the training data. How should this be addressed? | Manually override AI recommendations for smaller vendors. | Stop using AI for vendor evaluation permanently. | Audit the training data for bias, diversify the data sources, and implement fairness metrics in the evaluation algorithm. | Continue using the tool since larger vendors are generally more reliable. |  | C | The correct answer is C. The bias comes from the training data, so it must be fixed systematically: audit the data for bias, diversify the data sources, and add fairness metrics to the evaluation. Manually overriding recommendations for small vendors (A) is ad hoc and inconsistent, abandoning AI permanently (B) discards its benefits, and continuing because larger vendors seem more reliable (D) accepts an unfair and possibly costly bias. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PM이 벤더 평가에 사용하는 AI 도구가 훈련 데이터로 인해 대형 벤더에 편향이 있음을 발견한다. PM은 무엇을 해야 하는가? | 소형 벤더에 대해 AI 추천을 수동으로 재정의한다 | 벤더 평가에 AI 사용을 영구적으로 중단한다 | 훈련 데이터의 편향을 감사하고 데이터 소스를 다양화하며 평가 프로세스에 공정성 지표를 구현한다 | 대형 벤더가 일반적으로 더 신뢰할 수 있으므로 도구를 계속 사용한다 |  | C | 정답은 C이다. 편향은 학습 데이터에서 비롯되므로 체계적으로 바로잡아야 한다. 데이터의 편향을 감사하고, 데이터 출처를 다양화하며, 평가 알고리즘에 공정성 지표를 넣어야 한다. 소규모 업체에 대한 추천을 수동으로 뒤집는 것(A)은 임시방편이라 일관성이 없고, AI 사용을 영구 중단하는 것(B)은 효익을 버리는 것이며, 대형 업체가 더 믿을 만하다는 이유로 계속 쓰는 것(D)은 불공정하고 비용이 클 수 있는 편향을 받아들이는 것이다.
2146 | Which of the following BEST describes the role of AI in project management according to PMBOK 8th Edition? | AI is a supplementary tool that augments human decision-making, requiring ethical oversight and governance. | AI should replace project managers for routine projects. | AI is only applicable to software development projects. | AI should be avoided until it is fully mature and error-free. |  | A | The PMBOK 8th Edition positions AI as a supplementary tool that augments human decision-making rather than replacing it. It emphasizes the need for ethical oversight, governance, and appropriate human supervision. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | General PM Principles | Process | Develop Integrated PM Plan | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | PMBOK 8판에 따른 프로젝트 관리에서 AI의 역할을 가장 잘 설명하는 것은? | AI는 윤리적 감독과 거버넌스가 필요한 인간 의사결정을 보강하는 보조 도구이다 | AI는 일상적인 프로젝트에서 프로젝트 관리자를 대체해야 한다 | AI는 소프트웨어 개발 프로젝트에만 적용 가능하다 | AI는 완전히 성숙하고 오류가 없을 때까지 피해야 한다 |  | A | PMBOK 8판은 AI를 대체가 아닌 인간 의사결정을 보강하는 보조 도구로 위치시킨다. 윤리적 감독, 거버넌스, 적절한 인간 판단이 필요함을 강조한다. 대체(B)는 PMBOK 입장이 아니다. SW 전용(C)은 범위가 좁다. 회피(D)는 기술 활용을 무시한다.
2147 | A project team has implemented an AI-driven cost estimation model that uses historical cost data from similar projects. After several months, the model's predictions start becoming less accurate. What is the MOST likely cause? | The project team is not entering data correctly. | The AI model has a software bug. | The market conditions, resource costs, or project complexity have changed since the model was trained, causing data drift. | AI models always degrade over time regardless of external factors. |  | C | The correct answer is C. A model that was accurate and then gradually becomes less accurate is most likely affected by data drift: market conditions, resource costs, or project complexity have changed since it was trained, so the historical patterns no longer fit. Data entry errors (A) or a software bug (B) would usually show different symptoms, and models do not degrade on their own regardless of external factors (D); they need monitoring and retraining. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Embed Quality | Control Costs | AI | 프로젝트 팀이 유사 프로젝트의 과거 원가 데이터를 사용하는 AI 기반 원가 산정 모델을 도입했다. 몇 달이 지나자 모델의 예측 정확도가 떨어지기 시작했다. 가장 가능성 높은 원인은 무엇인가? | 프로젝트 팀이 데이터를 올바르게 입력하지 않고 있다 | AI 모델에 소프트웨어 버그가 있다 | 모델 학습 이후 시장 상황, 자원 원가, 프로젝트 복잡도가 바뀌어 데이터 드리프트가 발생했다. | AI 모델은 외부 요인에 관계없이 항상 시간이 지나면 저하된다 |  | C | 정답은 C이다. 처음에는 정확하던 모델이 점차 부정확해진다면 데이터 드리프트일 가능성이 가장 크다. 모델을 학습시킨 이후 시장 상황, 자원 원가, 프로젝트 복잡도가 바뀌어 과거의 패턴이 더는 맞지 않는 것이다. 데이터 입력 오류(A)나 소프트웨어 버그(B)는 보통 다른 증상으로 나타나고, 모델이 외부 요인과 무관하게 저절로 나빠지는 것(D)은 아니며, 모니터링과 재학습이 필요하다.
2148 | A project manager wants to use AI to identify the optimal project delivery approach (predictive, agile, or hybrid) for a new project. What input data would be MOST useful for the AI analysis? | The project sponsor's personal preference for methodology. | The budget allocated for project management tools. | Project characteristics including requirements stability, complexity, stakeholder engagement level, team experience, and organizational culture. | Industry benchmarks from unrelated project types. |  | C | The most useful inputs for AI-based methodology selection are project-specific characteristics: requirements stability, complexity, stakeholder engagement, team experience, and organizational culture. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Tailored Approach | Process | Develop Integrated PM Plan | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | AI | 프로젝트 관리자가 새 프로젝트에 가장 적합한 인도 방식(예측형, 애자일, 하이브리드)을 AI로 판단하려 한다. AI 분석에 가장 유용한 입력 데이터는 무엇인가? | 프로젝트 스폰서의 방법론에 대한 개인적 선호 | 프로젝트 관리 도구에 할당된 예산 | 요구사항 안정성, 복잡도, 이해관계자 참여 수준, 팀 경험, 조직 문화 등 프로젝트 특성 | 관련 없는 프로젝트 유형의 산업 벤치마크 |  | C | AI 기반 방법론 선택에 가장 유용한 입력은 프로젝트별 특성이다: 요구사항 안정성, 복잡성, 이해관계자 참여, 팀 경험, 조직 문화. 스폰서 선호(A)는 주관적이다. 도구 예산(B)은 방법론과 무관하다. 관련 없는 벤치마크(D)는 부적절하다.
2149 | A project team is developing an AI system for a healthcare client. Midway through the project, the team discovers that the AI training data contains patient information that may violate HIPAA regulations. What should the PM do FIRST? | Delete the data and find alternative training data without informing anyone. | Immediately halt the use of the non-compliant data, notify relevant stakeholders, engage the legal/compliance team, and assess the impact on the project. | Continue the project and address the data issue after delivery. | Anonymize the data and continue using it without further review. |  | B | The correct answer is B. Training data that may violate HIPAA is a serious compliance issue that requires immediate, transparent action: stop using the non-compliant data, notify the relevant stakeholders, involve legal and compliance, and assess the impact on the project. Deleting data without telling anyone (A) hides a possible breach, continuing until delivery (C) compounds the violation, and anonymizing without review (D) may not meet regulatory requirements. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Compliance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | AI | 프로젝트 팀이 의료 분야 고객을 위한 AI 시스템을 개발하고 있다. 프로젝트 중반에 팀은 AI 학습 데이터에 HIPAA 규정을 위반할 수 있는 환자 정보가 포함되어 있다는 것을 발견했다. 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 아무에게도 알리지 않고 데이터를 삭제하고 대체 학습 데이터를 찾는다 | 규정 위반 소지가 있는 데이터의 사용을 즉시 중단하고, 관련 이해관계자에게 알리며, 법무/컴플라이언스팀을 참여시키고, 프로젝트 영향을 평가한다. | 프로젝트를 계속하고 납품 후 데이터 문제를 해결한다 | 데이터를 익명화하고 추가 검토 없이 계속 사용한다 |  | B | 정답은 B이다. HIPAA를 위반할 수 있는 학습 데이터는 즉각적이고 투명한 조치가 필요한 중대한 규정 준수 문제이다. 문제의 데이터 사용을 중단하고, 관련 이해관계자에게 알리며, 법무·컴플라이언스 팀을 참여시키고, 프로젝트에 미칠 영향을 평가해야 한다. 아무에게도 알리지 않고 데이터를 지우는 것(A)은 위반 가능성을 숨기는 것이고, 인도 후까지 계속 쓰는 것(C)은 위반을 키우며, 검토 없이 익명화해 쓰는 것(D)은 규정 요건을 충족하지 못할 수 있다.
2150 | A hybrid project team is using AI for automated risk scoring. The tool assigns numerical risk scores, but team members find the scores difficult to interpret for decision-making. What should the project manager do? | Replace the AI tool with a simpler spreadsheet-based risk register. | Simplify the AI output by adding risk categories (High/Medium/Low), visual dashboards, and plain-language explanations alongside numerical scores. | Train the team in advanced data analytics to interpret the scores. | Ask the AI vendor to make the scores more intuitive. |  | B | The correct answer is B. The scores are accurate enough to use but hard to interpret, so the output should be presented in a form that supports decisions: risk categories, visual dashboards, and plain-language explanations alongside the numbers. Replacing the tool with a spreadsheet (A) loses its analytical value, training everyone in advanced analytics (C) is excessive, and simply asking the vendor (D) is less direct than adapting how the results are presented. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Executing | Focus on Value | Implement Risk Responses | AI | 하이브리드 프로젝트 팀이 AI로 리스크 점수를 자동 산정하고 있다. 도구가 리스크 점수를 숫자로 부여하지만, 팀원들은 의사결정에 이 점수를 해석하기 어렵다고 느낀다. 프로젝트 관리자는 무엇을 해야 하는가? | AI 도구를 더 간단한 스프레드시트 기반 리스크 등록부로 대체한다 | 리스크 카테고리(높음/중간/낮음), 시각적 대시보드, 평이한 언어 설명을 추가하여 AI 출력을 간소화한다 | 팀에게 고급 데이터 분석을 교육하여 점수를 해석하게 한다 | AI 벤더에게 점수를 더 직관적으로 만들어 달라고 요청한다 |  | B | 정답은 B이다. 점수 자체는 쓸 만하지만 해석이 어렵기 때문에, 결과를 의사결정에 도움이 되는 형태로 보여 줘야 한다. 숫자와 함께 리스크 등급, 시각적 대시보드, 쉬운 설명을 제공하는 것이다. 스프레드시트로 바꾸는 것(A)은 분석 가치를 잃고, 모든 팀원에게 고급 분석 교육을 하는 것(C)은 과하며, 벤더에게 요청만 하는 것(D)은 결과 표시 방식을 직접 조정하는 것보다 덜 직접적이다.
2151 | A project team is considering using AI to automatically assign tasks to team members based on skill profiles and workload. What is the PRIMARY concern the PM should address? | Whether the AI assignments will reduce project costs. | Whether the AI can handle the volume of tasks in the project. | Whether the AI can integrate with the existing project management software. | Whether team members' professional development goals and preferences are considered alongside AI's optimization criteria. |  | D | The correct answer is D. AI-based task assignment can optimize for efficiency, but people are not interchangeable resources. The primary concern is whether team members' development goals, preferences, and well-being are considered alongside the optimization criteria, which affects engagement and retention. Cost (A), task volume (B), and integration (C) are practical considerations, but they are secondary to the impact on the team. | People | Empower Team Members | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Manage Team | AI | 프로젝트 팀이 역량 프로필과 업무량을 바탕으로 AI가 팀원에게 작업을 자동 배정하는 방안을 검토하고 있다. 프로젝트 관리자가 가장 중요하게 다뤄야 할 우려 사항은 무엇인가? | AI 배정이 프로젝트 비용을 줄일 수 있는지 | AI가 프로젝트의 작업량을 처리할 수 있는지 | AI가 기존 프로젝트 관리 소프트웨어와 통합될 수 있는지 | 팀원의 전문 개발 목표와 선호가 AI의 최적화 기준과 함께 고려되는지 |  | D | 정답은 D이다. AI 기반 작업 배정은 효율을 최적화할 수 있지만 사람은 서로 바꿔 끼울 수 있는 자원이 아니다. 가장 중요한 우려는 최적화 기준과 함께 팀원의 성장 목표, 선호, 안녕이 고려되는지이며, 이는 참여와 이직에 영향을 준다. 원가(A), 작업량 처리(B), 기존 소프트웨어와의 연동(C)은 실무적인 고려 사항이지만 팀에 미치는 영향보다는 부차적이다.
2152 | An organization uses AI to predict budget overruns at the portfolio level. The AI predicts that a project will exceed its budget by 25%, but the PM's bottom-up estimate shows only a 5% overrun. What should the portfolio manager do? | Trust the PM's estimate since they know the project best. | Have the PM and the AI analytics team collaborate to reconcile the two estimates and identify which assumptions differ. | Trust the AI prediction since it uses portfolio-level data. | Reduce the project budget by 25% immediately. |  | B | The correct answer is B. The AI predicts a 25% overrun while the project manager's bottom-up estimate shows 5%, a large gap that needs explanation. Having the project manager and the analytics team work together to compare assumptions and data reconciles the estimates and improves both. Trusting either source blindly (A, C) ignores possibly valid information, and cutting the budget immediately (D) acts before the cause is understood. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Earned Value Management | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Adopt a Holistic View | Control Costs | AI | 한 조직이 AI로 포트폴리오 차원의 예산 초과를 예측한다. AI는 한 프로젝트가 예산을 25% 초과할 것으로 예측하지만, 프로젝트 관리자의 상향식 산정은 5% 초과에 그친다. 포트폴리오 관리자는 무엇을 해야 하는가? | PM이 프로젝트를 가장 잘 아므로 PM의 추정을 신뢰한다 | PM과 AI 분석팀이 협력하여 두 추정의 차이를 조정하고 어떤 가정이 다른지 식별한다 | 포트폴리오 수준 데이터를 사용하므로 AI 예측을 신뢰한다 | 프로젝트 예산을 즉시 25% 삭감한다 |  | B | 정답은 B이다. AI는 25% 초과를, 프로젝트 관리자의 상향식 산정은 5% 초과를 예측해 설명이 필요한 큰 차이가 있다. 프로젝트 관리자와 분석팀이 함께 가정과 데이터를 비교하면 두 산정치를 조정하고 양쪽을 모두 개선할 수 있다. 어느 한쪽을 맹목적으로 믿는 것(A, C)은 타당할 수 있는 정보를 무시하고, 예산을 즉시 줄이는 것(D)은 원인을 이해하기 전에 행동하는 것이다.
2153 | During a project review, a stakeholder asks whether AI can be used to replace the project's change control board (CCB) for faster decision-making. What is the BEST response? | AI can assist the CCB by analyzing change request impacts and providing recommendations, but final decisions should remain with the human-led CCB. | No, AI has no role in change management. | Yes, AI can make faster and more objective change decisions than a CCB. | Only minor change requests should be handled by AI. |  | A | AI can enhance the CCB's effectiveness by quickly analyzing change impacts, assessing schedule and cost effects, and providing data-driven recommendations. However, the final decision authority should remain with the human-led CCB. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | General | Change Management | Process | Develop Integrated PM Plan | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | AI | 프로젝트 검토 중에 한 이해관계자가 더 빠른 의사결정을 위해 프로젝트의 변경통제위원회(CCB)를 AI로 대체할 수 있는지 묻는다. 가장 적절한 답변은 무엇인가? | AI는 변경 요청 영향을 분석하고 권고를 제공하여 CCB를 지원할 수 있지만, 최종 결정 권한은 인간에게 있어야 한다 | 아니오, AI는 변경 관리에서 역할이 없다 | 예, AI가 CCB보다 빠르고 객관적인 변경 결정을 할 수 있다 | 사소한 변경 요청만 AI가 처리해야 한다 |  | A | AI는 변경 영향을 빠르게 분석하고, 일정 및 비용 효과를 평가하며, 데이터 기반 권고를 제공하여 CCB의 효과를 높일 수 있다. 그러나 최종 결정 권한은 인간에게 있어야 한다. 역할 없음(B)은 부정확하다. 완전 대체(C)는 거버넌스 원칙에 반한다. 사소한 것만(D)은 제한적이다.
2154 | A project manager is implementing a machine learning model that improves its accuracy over time by learning from the outcomes of its previous recommendations. What type of AI learning does this represent? | Transfer learning that applies knowledge from one domain to another. | Unsupervised learning that identifies patterns without labeled data. | Supervised learning that requires labeled training data. | Reinforcement learning where the model learns from outcomes of its decisions. |  | D | The correct answer is D. The model improves by learning from the outcomes of its previous recommendations, which is how reinforcement learning works: actions are taken, results are observed, and future decisions are adjusted. Transfer learning (A) reuses knowledge from another domain, unsupervised learning (B) finds patterns in unlabeled data, and supervised learning (C) learns from labeled examples rather than from the consequences of its own decisions. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Executing | Embed Quality | Direct and Manage Project Work | AI | 프로젝트 관리자가 이전 추천의 결과로부터 학습하며 시간이 지날수록 정확도가 높아지는 머신러닝 모델을 도입하고 있다. 이는 어떤 유형의 AI 학습인가? | 한 도메인의 지식을 다른 도메인에 적용하는 전이 학습 | 레이블 없는 데이터에서 패턴을 식별하는 비지도 학습 | 레이블이 있는 학습 데이터가 필요한 지도 학습 | 결정의 결과로부터 학습하는 강화 학습 |  | D | 정답은 D이다. 모델이 이전 추천의 결과로부터 학습하며 개선되는 것은 강화 학습의 방식이다. 행동을 하고, 결과를 관찰하고, 이후의 결정을 조정한다. 전이 학습(A)은 다른 분야의 지식을 재사용하고, 비지도 학습(B)은 레이블 없는 데이터에서 패턴을 찾으며, 지도 학습(C)은 자기 결정의 결과가 아니라 레이블이 있는 예시로부터 학습한다.
2155 | A project manager needs to present AI implementation options to the project steering committee. The committee has limited technical AI knowledge. What presentation approach is MOST effective? | Ask the data science team to present directly to the committee. | Present detailed technical specifications of each AI algorithm. | Send a technical whitepaper before the meeting and expect committee members to review it. | Focus on business value, risk impact, implementation timeline, and cost-benefit analysis, using visual aids and practical examples. |  | D | The correct answer is D. The committee has limited AI knowledge, so the presentation should speak to what they need to decide: business value, risk impact, timeline, and cost-benefit, supported by visuals and practical examples. Having the data science team present (A) or showing technical specifications (B) is too technical for this audience, and sending a whitepaper in advance (C) assumes time and expertise they may not have. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Focus on Value | Manage Stakeholder Engagement | AI | 프로젝트 관리자가 프로젝트 운영위원회에 AI 도입 방안을 발표해야 한다. 위원회의 AI 기술 지식은 제한적이다. 가장 효과적인 발표 방식은 무엇인가? | 데이터 과학팀에게 위원회에 직접 발표하도록 요청한다 | 각 AI 알고리즘의 상세 기술 사양을 발표한다 | 회의 전 기술 백서를 보내고 위원회 구성원이 검토하기를 기대한다 | 비즈니스 가치, 리스크 영향, 도입 일정, 비용-편익 분석에 초점을 맞추고, 시각 자료와 실제 사례를 활용한다. |  | D | 정답은 D이다. 위원회는 AI 지식이 부족하므로, 발표는 그들이 결정해야 할 내용, 즉 비즈니스 가치, 리스크 영향, 일정, 비용-편익에 맞춰야 하며 시각 자료와 실제 사례로 뒷받침해야 한다. 데이터 과학팀이 직접 발표하거나(A) 기술 사양을 보여 주는 것(B)은 이 청중에게 너무 기술적이고, 백서를 미리 보내는 것(C)은 그들에게 없을 수 있는 시간과 전문성을 가정하는 것이다.
2156 | An organization mandates the use of a specific AI tool for all projects. The project manager's team finds the tool unsuitable for their project type. What should the PM do? | Document the misfit with evidence, propose a tailored approach or alternative, and seek an exception through proper governance channels. | Ignore the mandate and use a different tool. | Complain to team members about organizational bureaucracy. | Use the tool as mandated regardless of its fit. |  | A | The correct answer is A. The mandated tool does not fit the project, but the mandate is still organizational governance. The project manager should document the misfit with evidence, propose a tailored approach or alternative, and seek an exception through the proper channels. Ignoring the mandate (B) bypasses governance, complaining to the team (C) is unprofessional, and using an unsuitable tool regardless (D) may harm the project. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | AI | 조직이 모든 프로젝트에 특정 AI 도구 사용을 의무화하지만 PM 팀에 적합하지 않을 때 어떻게 해야 하는가? | 증거와 함께 부적합을 문서화하고, 맞춤형 접근법이나 대안을 제안하며, 적절한 채널을 통해 예외를 요청한다 | 지침을 무시하고 다른 도구를 사용한다 | 팀원에게 조직의 관료주의에 대해 불평한다 | 적합성에 관계없이 지침대로 도구를 사용한다 |  | A | 정답은 A이다. 지정된 도구가 프로젝트에 맞지 않지만, 그 지시도 조직의 거버넌스이다. 프로젝트 관리자는 맞지 않는 점을 근거와 함께 문서화하고, 조정된 방식이나 대안을 제안하며, 정식 경로로 예외를 요청해야 한다. 지시를 무시하는 것(B)은 거버넌스를 우회하고, 팀원에게 불평하는 것(C)은 전문가답지 않으며, 맞지 않는 도구를 그대로 쓰는 것(D)은 프로젝트에 해가 될 수 있다.
2157 | A project uses AI to monitor team communication channels and flag potential conflicts early. What is the MOST important governance control to implement? | Establish clear policies on data collection scope, retention periods, usage limitations, and transparency with team members. | Use the data for annual performance reviews of team members. | Allow the AI to automatically intervene in detected conflicts. | Ensure only the PM has access to the conflict detection reports. |  | A | AI-based communication monitoring requires robust governance controls including clear policies on what data is collected, how long it's retained, how it's used, and transparency with those being monitored. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | AI | AI가 팀 커뮤니케이션 채널을 모니터링하여 잠재적 갈등을 조기 감지할 때 가장 중요한 고려사항은? | 데이터 수집 범위, 보존 기간, 사용 제한, 모니터링 대상자에 대한 투명성에 대한 명확한 정책을 수립한다 | 연간 성과 검토에 데이터를 사용한다 | AI가 감지된 갈등에 자동으로 개입하도록 허용한다 | PM만 갈등 감지 보고서에 접근하도록 한다 |  | A | AI 기반 커뮤니케이션 모니터링은 수집 대상, 보존 기간, 사용 방법, 모니터링 대상자에 대한 투명성을 포함하는 강력한 거버넌스 통제가 필요하다. 성과 검토(B)는 프라이버시 침해이다. 자동 개입(C)은 부적절하다. PM만 접근(D)은 투명성이 부족하다.
2158 | A data-driven project manager uses AI dashboards showing real-time project metrics. During a stakeholder meeting, a key stakeholder questions whether the AI metrics can be trusted. What is the BEST response? | Tell the stakeholder to trust the technology. | Switch back to manual reporting to satisfy the stakeholder. | Describe the data sources, validation processes, and accuracy benchmarks used to ensure the AI dashboard's reliability, and offer to review the methodology together. | Explain that AI is always more accurate than manual tracking. |  | C | The correct answer is C. Trust in AI-driven metrics comes from transparency. Explaining the data sources, validation processes, and accuracy benchmarks, and offering to review specific metrics together, gives the stakeholder evidence rather than assurances. Asking them to simply trust the technology (A) or claiming AI is always more accurate (D) is unsupported, and switching back to manual reporting (B) gives up a useful tool without addressing the concern. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | AI | 데이터 중심의 프로젝트 관리자가 실시간 프로젝트 지표를 보여 주는 AI 대시보드를 사용한다. 이해관계자 회의에서 한 핵심 이해관계자가 AI 지표를 믿을 수 있는지 의문을 제기한다. 가장 적절한 대응은 무엇인가? | 이해관계자에게 기술을 신뢰하라고 말한다 | 이해관계자를 만족시키기 위해 수동 보고로 전환한다 | AI 대시보드의 신뢰성을 보장하기 위해 쓰인 데이터 출처, 검증 절차, 정확도 기준을 설명하고, 방법론을 함께 검토하자고 제안한다. | AI가 항상 수동 추적보다 정확하다고 설명한다 |  | C | 정답은 C이다. AI 기반 지표에 대한 신뢰는 투명성에서 나온다. 데이터 출처, 검증 절차, 정확도 기준을 설명하고 특정 지표를 함께 검토하자고 제안하면, 이해관계자에게 말로 안심시키는 대신 근거를 줄 수 있다. 기술을 그냥 믿으라고 하는 것(A)이나 AI가 항상 더 정확하다고 주장하는 것(D)은 근거가 없고, 수동 보고로 돌아가는 것(B)은 우려를 해소하지 않은 채 유용한 도구를 포기하는 것이다.
2159 | Which of the following is an example of using AI to support the 'Focus on Value' principle from PMBOK 8th Edition? | Using AI to automatically generate project status emails. | Using AI analytics to identify which project features deliver the highest customer value and prioritize them in the backlog. | Using AI to format project documents consistently. | Using AI to track individual team member work hours. |  | B | The correct answer is B. The Focus on Value principle is about directing effort toward the outcomes that matter most to customers and the business. Using AI analytics to identify which features deliver the most customer value and prioritizing them in the backlog applies that principle directly. Generating status emails (A) and formatting documents (C) are efficiency gains, and tracking individual work hours (D) monitors activity rather than value. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Agile General Practices | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | PMBOK 8판의 '가치에 집중' 원칙을 지원하는 AI 사용 예시는? | AI를 사용하여 프로젝트 상태 이메일을 자동 생성한다 | AI 분석을 사용하여 가장 높은 고객 가치를 제공하는 프로젝트 기능을 식별하고 우선순위를 정한다 | AI를 사용하여 프로젝트 문서를 일관되게 포맷한다 | AI를 사용하여 개별 팀원 근무 시간을 추적한다 |  | B | 정답은 B이다. '가치에 집중' 원칙은 고객과 비즈니스에 가장 중요한 성과에 노력을 집중하는 것이다. AI 분석으로 고객 가치가 가장 큰 기능을 찾아 백로그에서 우선순위를 높이는 것은 이 원칙을 직접 적용한 예이다. 현황 이메일을 자동 생성하거나(A) 문서 서식을 맞추는 것(C)은 효율 향상이고, 개인 근무 시간을 추적하는 것(D)은 가치가 아니라 활동을 감시하는 것이다.
2160 | A project team is building an AI model and needs a large dataset for training. The most available dataset contains biased historical data that underrepresents certain demographic groups. What should the PM recommend? | Wait until a perfect, unbiased dataset becomes available. | Only use the model for demographic groups well-represented in the data. | Use the dataset as-is since it's the most available. | Supplement the dataset with additional data to improve representation, implement bias detection techniques, and document known limitations. |  | D | The correct answer is D. A perfect dataset is rarely available, so the practical approach is to reduce bias: supplement the data to improve representation, apply bias detection techniques, and document known limitations. Waiting for perfect data (A) may stall the project indefinitely, restricting the model to well-represented groups (B) is discriminatory, and using the data as is (C) builds the bias into the model. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | 프로젝트 팀이 AI 모델을 구축하며 학습용 대규모 데이터셋이 필요하다. 가장 구하기 쉬운 데이터셋에는 특정 인구 집단이 과소 대표된 편향된 과거 데이터가 들어 있다. 프로젝트 관리자는 무엇을 권해야 하는가? | 완벽하고 편향 없는 데이터셋이 가용할 때까지 기다린다 | 데이터에 잘 표현된 인구통계 그룹에만 모델을 사용한다 | 가장 가용하므로 데이터셋을 그대로 사용한다 | 대표성을 높이도록 추가 데이터로 보완하고, 편향 탐지 기법을 적용하며, 알려진 한계를 문서화한다. |  | D | 정답은 D이다. 완벽한 데이터셋은 거의 없으므로 현실적인 방법은 편향을 줄이는 것이다. 대표성을 높이도록 데이터를 보완하고, 편향 탐지 기법을 적용하며, 알려진 한계를 문서화해야 한다. 완벽한 데이터를 기다리는 것(A)은 프로젝트를 무기한 멈출 수 있고, 데이터에 잘 반영된 집단에만 모델을 쓰는 것(B)은 차별적이며, 데이터를 그대로 쓰는 것(C)은 편향을 모델에 그대로 심는 것이다.
2161 | An organization is implementing AI across all projects and asks the PMO to develop an AI governance framework. Which element is LEAST important to include? | A ranking of the best AI vendors in the market. | Data privacy and security standards for AI tools. | Decision authority framework for when AI recommendations conflict with human judgment. | Ethical guidelines for AI usage in projects. |  | A | The correct answer is A. An AI governance framework sets the rules for how AI is used: data privacy and security standards (B), a decision authority framework for when AI and human judgment conflict (C), and ethical guidelines (D). A ranking of the best AI vendors is a procurement or market-research activity, not a governance element, so it is the least important to include. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Planning | Be an Accountable Leader | Develop Project Management Plan | AI | 한 조직이 모든 프로젝트에 AI를 도입하며 PMO에 AI 거버넌스 프레임워크를 개발해 달라고 요청한다. 포함할 요소 중 가장 덜 중요한 것은 무엇인가? | 시장 최고 AI 벤더 순위 | AI 도구에 대한 데이터 프라이버시 및 보안 표준 | AI 권고가 인간 판단과 충돌할 때의 결정 권한 프레임워크 | 프로젝트에서 AI 사용에 대한 윤리 지침 |  | A | 정답은 A이다. AI 거버넌스 체계는 AI 사용 규칙을 정한다. 데이터 개인정보·보안 기준(B), AI 추천과 사람의 판단이 충돌할 때의 의사결정 권한 체계(C), 윤리 지침(D)이 이에 해당한다. 최고 AI 벤더 순위는 조달이나 시장 조사 활동이지 거버넌스 요소가 아니므로 포함할 필요성이 가장 낮다.
2162 | A project manager is considering using AI for stakeholder sentiment analysis during a complex organizational change project. The AI tool requires access to email and chat data. What should the PM prioritize? | Obtaining proper authorization, ensuring data privacy compliance, and establishing transparent communication about the AI's role to all affected parties. | Training only the communication team on the tool. | Selecting the cheapest AI tool available. | Getting the fastest implementation timeline. |  | A | The correct answer is A. Sentiment analysis on email and chat data uses personal communications, so the first priorities are proper authorization, compliance with privacy requirements, and transparency with everyone affected about how the AI is used. Training only the communication team (B), choosing the cheapest tool (C), or rushing implementation (D) ignores the legal and ethical risks and could damage trust during an already sensitive change. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Planning | Be an Accountable Leader | Plan Stakeholder Engagement | AI | 프로젝트 관리자가 복잡한 조직 변화 프로젝트에서 이해관계자 감성 분석에 AI를 활용하려 한다. 이 AI 도구는 이메일과 채팅 데이터에 접근해야 한다. 프로젝트 관리자가 우선해야 할 것은 무엇인가? | 적절한 승인을 받고, 데이터 프라이버시 규정을 준수하며, 영향을 받는 모든 당사자에게 AI의 역할을 투명하게 알린다. | 커뮤니케이션 팀만 도구에 대해 교육한다 | 가장 저렴한 AI 도구를 선택한다 | 가장 빠른 구현 일정을 확보한다 |  | A | 정답은 A이다. 이메일과 채팅 데이터로 감정 분석을 하면 개인의 소통 내용을 쓰게 되므로, 적절한 승인, 개인정보 규정 준수, 영향을 받는 모든 사람에게 AI 사용 방식을 투명하게 알리는 것이 최우선이다. 소통팀만 교육하는 것(B), 가장 싼 도구를 고르는 것(C), 도입을 서두르는 것(D)은 법적·윤리적 리스크를 무시하며, 가뜩이나 민감한 변화 과정에서 신뢰를 해칠 수 있다.
2163 | A project manager is using AI to generate progress reports. The AI produces a report that highlights a critical risk that the PM had previously assessed as low probability. Upon investigation, the PM finds the AI identified a new pattern in the data. What lesson does this demonstrate? | AI reports should not be reviewed since they are algorithmically generated. | AI can detect patterns in data that humans may miss, making it a valuable complement to human risk assessment. | AI should be the sole source of risk assessments. | Human risk assessments are unreliable. |  | B | The correct answer is B. The AI found a new pattern that changed the assessment of a risk the project manager had rated as low probability. This shows AI's value in detecting patterns humans may miss because of data volume or cognitive bias, as a complement to human judgment. AI reports still need human review (A), AI should not be the sole source of risk assessment (C), and one missed pattern does not make human assessment unreliable (D). | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Hybrid | Predictive-Agile Blend | Business Environment | Plan and Manage Risk | Risk | Monitoring & Controlling | Adopt a Holistic View | Monitor Risks | AI | 프로젝트 관리자가 AI로 진척 보고서를 만들고 있다. AI가 작성한 보고서에, 프로젝트 관리자가 이전에 발생 확률이 낮다고 평가했던 리스크가 중대한 리스크로 표시되었다. 조사해 보니 AI가 데이터에서 새로운 패턴을 찾아낸 것이었다. 이 사례가 보여 주는 교훈은 무엇인가? | AI 보고서는 알고리즘으로 생성되므로 검토할 필요가 없다 | AI는 인간이 놓칠 수 있는 데이터 패턴을 감지할 수 있어 인간 리스크 평가의 가치 있는 보완이 된다 | AI가 리스크 평가의 유일한 소스여야 한다 | 인간 리스크 평가는 신뢰할 수 없다 |  | B | 정답은 B이다. AI가 새로운 패턴을 찾아내, 프로젝트 관리자가 발생 확률이 낮다고 평가했던 리스크의 평가가 달라졌다. 이는 데이터 양이나 인지 편향 때문에 사람이 놓칠 수 있는 패턴을 AI가 찾아내는 가치를 보여 주며, AI는 사람의 판단을 보완하는 역할을 한다. AI 보고서도 사람이 검토해야 하고(A), AI가 리스크 평가의 유일한 근거가 되어서는 안 되며(C), 한 번 놓친 패턴으로 사람의 평가 전체를 믿을 수 없다고 할 수는 없다(D).
2164 | A Scrum team is exploring using AI to automatically generate user stories from customer feedback. What should the product owner be MOST concerned about? | Whether the development team will accept AI-generated stories. | Whether AI-generated stories accurately capture customer intent, maintain proper story structure (As a/I want/So that), and reflect business value priorities. | Whether the AI tool costs more than manual story writing. | Whether the AI can generate stories faster than the team can develop them. |  | B | The correct answer is B. The product owner is accountable for the quality of the backlog, so the main concern is whether AI-generated stories accurately reflect customer intent, follow a proper story structure, and align with business value. Developer acceptance (A), cost (C), and generation speed (D) are secondary; poor-quality stories would lead the team to build the wrong things. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Focus on Value | Define Scope | AI | 스크럼 팀이 고객 피드백에서 AI로 사용자 스토리를 자동 생성하려 할 때 제품 책임자의 주요 관심사는? | 개발 팀이 AI 생성 스토리를 수용할지 | AI 생성 스토리가 고객 의도를 정확히 포착하고, 적절한 스토리 구조를 유지하며, 비즈니스 가치 우선순위와 일치하는지 | AI 도구가 수동 스토리 작성보다 비용이 더 드는지 | AI가 팀이 개발할 수 있는 것보다 빠르게 스토리를 생성할 수 있는지 |  | B | 정답은 B이다. 제품 책임자는 백로그의 품질을 책임지므로, 가장 큰 관심사는 AI가 만든 스토리가 고객의 의도를 정확히 담고, 올바른 스토리 구조를 따르며, 비즈니스 가치와 맞는지이다. 개발팀의 수용 여부(A), 비용(C), 생성 속도(D)는 부차적이다. 품질이 낮은 스토리는 팀이 잘못된 것을 만들게 한다.
2165 | A project manager is building a business case for implementing AI tools across the project portfolio. Which metric would BEST demonstrate the value of AI investment to senior leadership? | Measurable improvements in project delivery metrics (schedule adherence, cost variance, defect rates) before and after AI implementation. | Number of team members trained on AI tools. | Number of AI tools implemented. | Amount of money spent on AI tools. |  | A | The correct answer is A. Senior leadership wants evidence of results. Comparing measurable delivery outcomes, such as schedule adherence, cost variance, and defect rates, before and after AI implementation demonstrates the value of the investment. The number of people trained (B), tools implemented (C), or money spent (D) measures activity or cost, not benefit. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | AI | PM이 프로젝트 포트폴리오 전체에 AI 도구 도입을 위한 비즈니스 케이스를 구축할 때 고위 리더십을 가장 설득하는 지표는? | AI 구현 전후의 프로젝트 납품 지표(일정 준수, 비용 차이, 결함률)의 측정 가능한 개선 | AI 도구에 대해 교육받은 팀원 수 | 구현된 AI 도구 수 | AI 도구에 지출한 금액 |  | A | 정답은 A이다. 고위 경영진은 결과에 대한 근거를 원한다. AI 도입 전후의 일정 준수, 원가 편차, 결함률 같은 측정 가능한 인도 성과를 비교하면 투자 가치를 입증할 수 있다. 교육받은 인원(B), 도입한 도구 수(C), 지출 금액(D)은 효익이 아니라 활동이나 비용을 측정하는 것이다.
2166 | During an agile retrospective, a team member raises concern that AI tools are making junior team members overly dependent on automated suggestions and hindering their skill development. What should the Scrum Master do? | Assign junior members to non-AI projects for training. | Dismiss the concern since AI tools improve overall productivity. | Remove all AI tools from the team's workflow. | Facilitate a team discussion on balancing AI assistance with skill development, and implement guidelines for when to use AI versus manual methods. |  | D | The correct answer is D. The concern that junior members are becoming too dependent on AI is valid and affects long-term capability. Facilitating a team discussion and agreeing on guidelines for when to use AI and when to work manually balances productivity with skill development. Moving juniors to other projects (A) avoids the issue, dismissing it (B) ignores a real risk, and removing all AI tools (C) gives up the benefits. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | Agile | Scrum | People | Help Ensure Knowledge Transfer | Resources | Executing | Build an Empowered Culture | Acquire Resources | AI | 애자일 회고에서 한 팀원이 AI 도구 때문에 주니어 팀원들이 자동 제안에 지나치게 의존해 역량 개발이 저해되고 있다고 우려를 제기한다. 스크럼 마스터는 무엇을 해야 하는가? | 주니어 멤버를 비AI 프로젝트에 배정하여 훈련한다 | AI 도구가 전체 생산성을 향상시키므로 우려를 무시한다 | 팀 워크플로에서 모든 AI 도구를 제거한다 | AI 지원과 역량 개발의 균형에 관해 팀 토론을 이끌고, AI와 수작업을 언제 쓸지에 대한 지침을 마련한다. |  | D | 정답은 D이다. 주니어 팀원들이 AI에 지나치게 의존한다는 우려는 타당하며 장기적인 역량에 영향을 준다. 팀 논의를 촉진해 언제 AI를 쓰고 언제 직접 작업할지 지침에 합의하면 생산성과 역량 개발의 균형을 맞출 수 있다. 주니어를 다른 프로젝트로 보내는 것(A)은 문제를 피하는 것이고, 우려를 일축하는 것(B)은 실제 리스크를 무시하며, AI 도구를 모두 없애는 것(C)은 효익을 포기하는 것이다.
2167 | A project team uses an AI-powered risk simulation tool that runs Monte Carlo simulations in real-time. The tool generates probability distributions for project completion dates. A stakeholder asks for a single definitive completion date. What should the PM communicate? | Average all simulation dates and provide that as the definitive date. | Provide the most optimistic date from the simulation. | Explain that AI simulations provide probability ranges, present the P50 and P80 dates with their confidence levels, and help the stakeholder understand the trade-offs. | Provide the most pessimistic date to set conservative expectations. |  | C | The correct answer is C. Monte Carlo simulation produces a probability distribution, not a single certain date. The project manager should explain this and present dates with their confidence levels, such as P50 and P80, so the stakeholder can choose a date that matches their risk tolerance. Averaging all dates (A) hides the uncertainty, and giving only the most optimistic (B) or most pessimistic date (D) misrepresents the likely outcome. | Process | Plan & Manage Schedule | Planning | Tailor Based on Context | Predictive | Critical Path/Schedule Mgmt | Process | Plan and Manage Schedule | Schedule | Planning | Adopt a Holistic View | Develop Schedule | AI | 프로젝트 팀이 실시간으로 몬테카를로 시뮬레이션을 실행하는 AI 기반 리스크 시뮬레이션 도구를 사용한다. 도구는 프로젝트 완료일의 확률 분포를 산출한다. 한 이해관계자가 확정된 완료일 하나를 요구한다. 프로젝트 관리자는 무엇을 전달해야 하는가? | 모든 시뮬레이션 날짜의 평균을 확정 날짜로 제공한다 | 시뮬레이션에서 가장 낙관적인 날짜를 제공한다 | AI 시뮬레이션은 확률 범위를 제공한다고 설명하고, P50·P80 날짜를 신뢰 수준과 함께 제시하며, 이해관계자가 그 트레이드오프를 이해하도록 돕는다. | 보수적 기대를 설정하기 위해 가장 비관적인 날짜를 제공한다 |  | C | 정답은 C이다. 몬테카를로 시뮬레이션은 하나의 확정 날짜가 아니라 확률 분포를 만든다. 프로젝트 관리자는 이를 설명하고 P50, P80처럼 신뢰 수준과 함께 날짜를 제시해, 이해관계자가 자신의 리스크 허용 수준에 맞는 날짜를 고를 수 있게 해야 한다. 모든 날짜를 평균 내는 것(A)은 불확실성을 감추고, 가장 낙관적인 날짜(B)나 가장 비관적인 날짜(D)만 주는 것은 가능성 높은 결과를 왜곡한다.
2168 | A project manager notices that AI-recommended process improvements consistently favor efficiency over team well-being. What action should the PM take? | Ask team members to adjust to the more efficient processes. | Configure the AI tool to include team well-being metrics (workload balance, overtime hours, satisfaction scores) in its optimization criteria. | Ignore AI recommendations entirely. | Implement all AI recommendations to maximize efficiency. |  | B | The correct answer is B. The AI is optimizing only for efficiency because that is what it was configured to measure. Adding team well-being metrics, such as workload balance, overtime, and satisfaction, to its optimization criteria produces balanced recommendations. Asking the team to simply adjust (A) or implementing everything (D) ignores the human cost, and ignoring the AI entirely (C) throws away useful insight. | People | Address Impediments to Team Performance | Team | Demonstrate Leadership Behaviors | General | General PM Principles | People | Lead the Project Team | Resources | Executing | Build an Empowered Culture | Develop Team | AI | AI 프로세스 개선 권고가 팀 웰빙보다 효율성을 지속적으로 선호할 때 PM은 무엇을 해야 하는가? | 팀원에게 더 효율적인 프로세스에 적응하도록 요청한다 | AI 도구가 팀 웰빙 지표(작업량 균형, 초과근무 시간, 만족도)를 포함하도록 설정한다 | AI 권고를 완전히 무시한다 | 효율성을 극대화하기 위해 모든 AI 권고를 구현한다 |  | B | 정답은 B이다. AI가 효율만 최적화하는 것은 그렇게 측정하도록 설정되어 있기 때문이다. 업무량 균형, 초과 근무, 만족도 같은 팀 안녕 지표를 최적화 기준에 넣으면 균형 잡힌 추천이 나온다. 팀에 그냥 적응하라고 하는 것(A)이나 모든 추천을 실행하는 것(D)은 사람이 치르는 비용을 무시하고, AI를 완전히 무시하는 것(C)은 유용한 통찰을 버리는 것이다.
2169 | Which of the following BEST describes the concept of 'data literacy' as emphasized in PMBOK 8th Edition in the context of AI? | The ability to build machine learning models from scratch. | The ability to read, understand, interpret, and communicate data-driven insights to make informed project decisions. | The ability to store and manage large databases. | The ability to write complex SQL queries and programming code. |  | B | The correct answer is B. Data literacy means being able to read, understand, interpret, and communicate data-driven insights so that project decisions are well informed. It does not require building machine learning models (A), managing databases (C), or writing SQL and code (D); those are specialist technical skills rather than the literacy every project professional needs. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Executing | Adopt a Holistic View | Manage Communications | AI | PMBOK 8판에서 AI 맥락의 '데이터 리터러시' 개념을 가장 잘 설명하는 것은? | 처음부터 머신러닝 모델을 구축하는 능력 | 데이터 기반 인사이트를 읽고, 이해하고, 해석하고, 소통하여 정보에 기반한 프로젝트 결정을 내리는 능력 | 대규모 데이터베이스를 저장하고 관리하는 능력 | 복잡한 SQL 쿼리와 프로그래밍 코드를 작성하는 능력 |  | B | 정답은 B이다. 데이터 리터러시란 데이터 기반 통찰을 읽고, 이해하고, 해석하고, 전달해 근거 있는 프로젝트 결정을 내리는 능력이다. 머신러닝 모델을 직접 만들거나(A), 데이터베이스를 관리하거나(C), SQL과 코드를 작성하는 능력(D)이 필요한 것은 아니다. 이는 모든 프로젝트 전문가에게 필요한 리터러시가 아니라 전문 기술 역량이다.
2170 | A project manager is planning a new construction project. The organization has adopted the PMBOK 8th Edition's 'Integrate Sustainability' principle. What should the PM do FIRST? | Wait for regulatory requirements before considering sustainability. | Focus only on minimizing project costs. | Assign sustainability responsibilities to the environmental department only. | Conduct an environmental impact assessment and incorporate sustainability criteria into the project charter and scope definition. |  | D | The correct answer is D. Integrating sustainability means considering environmental, social, and economic impacts from the start, not as an afterthought. An environmental impact assessment and sustainability criteria built into the charter and scope set that direction early. Waiting for regulations (A) is reactive, focusing only on cost (B) ignores the principle, and leaving it to the environmental department (C) keeps sustainability out of the project's own decisions. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Compliance | Governance | Initiating | Integrate Sustainability | Develop Project Charter | Sustainability | PMBOK 8판의 '지속가능성 통합' 원칙을 적용하여 건설 프로젝트를 계획 중이다. PM은 무엇을 먼저 해야 하는가? | 규제 요구사항이 나올 때까지 지속가능성 고려를 기다린다 | 프로젝트 비용 최소화에만 집중한다 | 환경부서에만 지속가능성 책임을 할당한다 | 환경 영향 평가를 실시하고 지속가능성 기준을 프로젝트 선정 기준에 통합한다 |  | D | 정답은 D이다. 지속가능성을 통합한다는 것은 환경·사회·경제적 영향을 나중이 아니라 처음부터 고려하는 것이다. 환경 영향 평가를 하고 헌장과 범위에 지속가능성 기준을 넣으면 일찍부터 방향이 잡힌다. 규제를 기다리는 것(A)은 사후 대응이고, 원가에만 집중하는 것(B)은 원칙을 무시하며, 환경 부서에 맡기는 것(C)은 지속가능성을 프로젝트 자체의 결정에서 빼 버린다.
2171 | During project planning, a stakeholder requests that the project minimize its carbon footprint. The project team has no experience with green project management. What is the BEST approach? | Reject the request as it is outside the project scope. | Promise zero carbon emissions without assessing feasibility. | Hire a sustainability consultant to assess the project's environmental impact and develop practical green strategies that the team can implement. | Add a generic sustainability statement to the project plan without specific actions. |  | C | The correct answer is C. The request is legitimate, but the team lacks expertise. Bringing in a sustainability consultant to assess the environmental impact and develop practical strategies the team can implement fills the gap. Rejecting the request (A) ignores the stakeholder, promising zero emissions (B) sets an unrealistic commitment, and a generic statement (D) gives the appearance of action without substance. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Stakeholders | Planning | Integrate Sustainability | Plan Stakeholder Engagement | Sustainability | 프로젝트 계획 중에 한 이해관계자가 프로젝트의 탄소 발자국을 최소화해 달라고 요청한다. 프로젝트 팀은 친환경 프로젝트 관리 경험이 없다. 가장 좋은 접근 방식은 무엇인가? | 프로젝트 범위 밖이라며 요청을 거부한다 | 실현 가능성 평가 없이 탄소 제로 배출을 약속한다 | 지속가능성 컨설턴트를 고용해 프로젝트의 환경 영향을 평가하고, 팀이 실행할 수 있는 실용적인 친환경 전략을 수립한다. | 구체적 조치 없이 일반적 지속가능성 성명을 프로젝트 계획에 추가한다 |  | C | 정답은 C이다. 요청은 타당하지만 팀에 전문성이 없다. 지속가능성 컨설턴트를 투입해 환경 영향을 평가하고 팀이 실행할 수 있는 현실적인 전략을 마련하면 격차를 메울 수 있다. 요청을 거절하는 것(A)은 이해관계자를 무시하고, 탄소 배출 제로를 약속하는 것(B)은 비현실적인 약속이며, 일반적인 선언문만 넣는 것(D)은 실질 없이 겉모양만 갖추는 것이다.
2172 | A project team is selecting materials for a product development project. Option A is cheaper but has high environmental impact. Option B costs 15% more but is sustainably sourced with minimal environmental impact. What should the project manager recommend? | Always choose Option B regardless of budget constraints. | Present both options with a full cost-benefit analysis including environmental impact, long-term costs, and alignment with organizational sustainability goals to the sponsor for decision-making. | Let the procurement team decide independently. | Always choose Option A to minimize project costs. |  | B | The correct answer is B. The decision involves a trade-off between cost and environmental impact, so decision makers need the full picture: a cost-benefit analysis that includes environmental impact, long-term costs, and alignment with the organization's sustainability goals. Always choosing the sustainable option (A) or the cheapest option (D) ignores the trade-off, and leaving it to procurement (C) removes the project manager's analysis from a strategic choice. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트 팀이 제품 개발 프로젝트의 자재를 고르고 있다. A안은 저렴하지만 환경 영향이 크다. B안은 15% 비싸지만 지속가능하게 조달되며 환경 영향이 적다. 프로젝트 관리자는 무엇을 권해야 하는가? | 예산 제약에 관계없이 항상 Option B를 선택한다 | 환경 영향, 장기 비용, 조직의 지속가능성 목표와의 정합성을 포함한 전체 비용-편익 분석과 함께 두 안을 스폰서에게 제시해 결정하도록 한다. | 조달팀이 독립적으로 결정하게 한다 | 프로젝트 비용을 최소화하기 위해 항상 Option A를 선택한다 |  | B | 정답은 B이다. 이 결정은 원가와 환경 영향 사이의 트레이드오프이므로, 의사결정자에게 전체 그림이 필요하다. 환경 영향, 장기 비용, 조직의 지속가능성 목표와의 정합성을 포함한 비용-편익 분석을 제시해야 한다. 항상 지속가능한 대안(A)이나 가장 싼 대안(D)을 고르는 것은 트레이드오프를 무시하고, 조달팀에 맡기는 것(C)은 전략적 선택에서 프로젝트 관리자의 분석을 빼는 것이다.
2173 | An agile project team is developing a software product. A team member suggests implementing energy-efficient coding practices to reduce the application's server power consumption. What should the project manager do? | Leave it to individual developers to decide. | Implement it only if it doesn't add any development time. | Include energy-efficient coding as a non-functional requirement, add it to the definition of done, and track energy metrics as a quality indicator. | Reject the idea as software sustainability is not a project management concern. |  | C | The correct answer is C. Energy efficiency is a quality attribute of the software. Making it a non-functional requirement, adding it to the definition of done, and tracking energy metrics ensures it is applied consistently rather than depending on individuals. Leaving it to each developer (A) leads to inconsistency, accepting it only if it adds no time (B) undervalues it, and rejecting it (D) ignores a growing sustainability expectation. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 애자일 프로젝트 팀이 소프트웨어 제품을 개발하고 있다. 한 팀원이 애플리케이션의 서버 전력 소비를 줄이기 위해 에너지 효율적인 코딩 관행을 도입하자고 제안한다. 프로젝트 관리자는 무엇을 해야 하는가? | 개별 개발자가 결정하게 한다 | 개발 시간이 추가되지 않는 경우에만 구현한다 | 에너지 효율적 코딩을 비기능 요구사항으로 포함하고, 완료 정의에 추가하며, 관련 지표를 추적한다 | 소프트웨어 지속가능성은 프로젝트 관리 관심사가 아니라며 아이디어를 거부한다 |  | C | 정답은 C이다. 에너지 효율은 소프트웨어의 품질 속성이다. 이를 비기능 요구사항으로 정하고, 완료 정의에 넣고, 에너지 지표를 추적하면 개인에게 맡기지 않고 일관되게 적용할 수 있다. 개발자마다 알아서 하게 하는 것(A)은 일관성이 없어지고, 개발 시간이 늘지 않을 때만 적용하는 것(B)은 가치를 낮춰 보는 것이며, 아이디어를 거절하는 것(D)은 커지는 지속가능성 기대를 무시하는 것이다.
2174 | A project manager is closing a large infrastructure project. What sustainability-related activity should be included in the project closure? | Only document the project's financial performance. | Archive all sustainability documents without review. | Conduct a sustainability assessment documenting environmental impact metrics, lessons learned on sustainable practices, and recommendations for future projects. | Transfer sustainability responsibilities to the operations team without documentation. |  | C | The correct answer is C. Closure is the point to capture what the project achieved and learned, including on sustainability. A sustainability assessment that records environmental impact metrics, lessons learned on sustainable practices, and recommendations for future projects preserves that knowledge. Documenting only financial performance (A) ignores sustainability, archiving without review (B) loses the lessons, and handing over without documentation (D) leaves operations without the information they need. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Predictive | Traditional Plan-Driven | Process | Develop Integrated PM Plan | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 프로젝트 관리자가 대형 인프라 프로젝트를 종료하고 있다. 프로젝트 종료에 포함해야 할 지속가능성 관련 활동은 무엇인가? | 프로젝트의 재무 성과만 문서화한다 | 검토 없이 모든 지속가능성 문서를 보관한다 | 환경 영향 지표, 지속가능성 교훈, 향후 프로젝트 권고를 문서화하는 지속가능성 평가를 실시한다 | 문서화 없이 운영 팀에 지속가능성 책임을 이관한다 |  | C | 정답은 C이다. 종료 단계는 지속가능성을 포함해 프로젝트가 이룬 것과 배운 것을 정리하는 시점이다. 환경 영향 지표, 지속가능한 관행에 대한 교훈, 향후 프로젝트를 위한 권고를 기록하는 지속가능성 평가를 하면 그 지식이 보존된다. 재무 성과만 문서화하는 것(A)은 지속가능성을 무시하고, 검토 없이 보관하는 것(B)은 교훈을 잃으며, 문서 없이 운영팀에 넘기는 것(D)은 운영에 필요한 정보를 주지 않는다.
2175 | A project sponsor asks the project manager to reduce the project's environmental sustainability measures to cut costs by 10%. What should the PM do? | Explain the long-term costs of reduced sustainability (regulatory risks, reputation damage, lifecycle costs), present alternative cost-reduction options, and escalate if needed. | Immediately comply with the sponsor's request. | Reduce sustainability measures but don't document the change. | Ignore the sponsor's request and maintain all sustainability measures. |  | A | The correct answer is A. The project manager should advocate for sustainability with facts: explain the long-term costs of cutting it, such as regulatory risk, reputational damage, and lifecycle costs, and offer other ways to save 10%, so the sponsor can make an informed decision. Complying immediately (B) skips that analysis, cutting measures without documentation (C) is not transparent, and ignoring the sponsor (D) disregards their authority. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Integrate Sustainability | Manage Stakeholder Engagement | Sustainability | 프로젝트 스폰서가 비용 절감을 위해 환경 지속가능성 조치를 줄이라고 요청할 때 PM은 무엇을 해야 하는가? | 지속가능성 감소의 장기 비용(규제 리스크, 평판 손상, 수명주기 비용)을 설명하고 대안을 제안한다 | 스폰서의 요청을 즉시 따른다 | 지속가능성 조치를 줄이되 변경을 문서화하지 않는다 | 스폰서의 요청을 무시하고 모든 지속가능성 조치를 유지한다 |  | A | 정답은 A이다. 프로젝트 관리자는 사실에 근거해 지속가능성을 옹호해야 한다. 규제 리스크, 평판 손상, 생애주기 비용 등 지속가능성을 줄였을 때의 장기 비용을 설명하고, 10%를 절감할 다른 방안을 제시해 스폰서가 근거 있는 결정을 내리게 해야 한다. 즉시 따르는 것(B)은 이런 분석을 건너뛰고, 문서화 없이 줄이는 것(C)은 투명하지 않으며, 스폰서의 요청을 무시하는 것(D)은 그의 권한을 무시하는 것이다.
2176 | Which of the following BEST represents the 'Integrate Sustainability' principle from PMBOK 8th Edition? | Project managers should consider environmental, social, and economic impacts when planning, executing, and closing projects, making sustainability part of decision-making. | Sustainability is an optional consideration that only applies to environmental projects. | Sustainability is solely the responsibility of the organization's CSR department. | Sustainability only means reducing paper usage in project documentation. |  | A | The correct answer is A. The Integrate Sustainability principle means considering environmental, social, and economic impacts throughout planning, execution, and closure, and treating sustainability as a core project value. It is not optional or limited to environmental projects (B), not solely a CSR department responsibility (C), and far broader than reducing paper use (D). | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | PMBOK 8판의 '지속가능성 통합' 원칙을 가장 잘 나타내는 것은? | PM은 프로젝트 계획, 실행, 전달 시 환경, 사회, 경제적 영향을 고려해야 한다 | 지속가능성은 환경 프로젝트에만 적용되는 선택적 고려사항이다 | 지속가능성은 조직의 CSR 부서만의 책임이다 | 지속가능성은 프로젝트 문서의 종이 사용 줄이기만을 의미한다 |  | A | 정답은 A이다. '지속가능성 통합' 원칙은 계획·실행·종료 전반에 걸쳐 환경·사회·경제적 영향을 고려하고, 지속가능성을 프로젝트의 핵심 가치로 삼는 것이다. 선택 사항이거나 환경 프로젝트에만 해당하는 것(B)이 아니며, CSR 부서만의 책임(C)도 아니고, 종이 사용을 줄이는 것(D)보다 훨씬 넓은 개념이다.
2177 | A construction project team identifies that using recycled concrete would reduce environmental impact by 40% but increase material costs by 8% and add 2 weeks to the schedule. How should the PM handle this trade-off? | Use recycled concrete only for non-structural elements. | Conduct a triple bottom line analysis (economic, environmental, social), present the findings to the governance board, and recommend based on organizational sustainability commitments. | Reject recycled concrete since it increases costs and schedule. | Use recycled concrete without informing the sponsor about the cost and schedule impact. |  | B | The correct answer is B. Recycled concrete reduces environmental impact by 40% but raises cost by 8% and adds two weeks, a real trade-off. A triple bottom line analysis of economic, environmental, and social effects gives the governance board a complete basis for deciding. Limiting it to non-structural elements (A) or rejecting it (C) decides without analysis, and using it without informing the sponsor (D) hides cost and schedule impacts. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 건설 프로젝트 팀이 재활용 콘크리트를 쓰면 환경 영향을 40% 줄일 수 있지만, 자재비가 8% 늘고 일정이 2주 늘어난다는 것을 확인했다. 프로젝트 관리자는 이 트레이드오프를 어떻게 처리해야 하는가? | 비구조적 요소에만 재활용 콘크리트를 사용한다 | 트리플 보텀 라인(경제·환경·사회) 분석을 수행해 결과를 거버넌스 위원회에 보고하고, 조직의 지속가능성 약속에 근거해 권고한다. | 비용과 일정이 증가하므로 재활용 콘크리트를 거부한다 | 비용과 일정 영향을 알리지 않고 재활용 콘크리트를 사용한다 |  | B | 정답은 B이다. 재활용 콘크리트는 환경 영향을 40% 줄이지만 원가를 8% 높이고 일정을 2주 늘리므로 실제 트레이드오프가 있다. 경제·환경·사회 영향을 함께 보는 트리플 보텀 라인 분석을 하면 거버넌스 위원회가 판단할 완전한 근거를 얻는다. 비구조 요소에만 쓰는 것(A)이나 거부하는 것(C)은 분석 없이 결정하는 것이고, 스폰서에게 알리지 않고 쓰는 것(D)은 원가와 일정 영향을 숨기는 것이다.
2178 | A project manager is developing a risk register for a renewable energy project. What type of risk is UNIQUE to sustainable projects? | Schedule delays. | Stakeholder conflict. | Budget overruns. | Greenwashing risk—where sustainability claims made by the project are exaggerated or unverifiable, leading to reputational and regulatory consequences. |  | D | The correct answer is D. Schedule delays (A), stakeholder conflict (B), and budget overruns (C) can occur on any project. Greenwashing risk, where the project's sustainability claims are exaggerated or cannot be verified, is specific to projects with sustainability goals and can lead to reputational and regulatory consequences. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | General | Risk & Issue Management | Business Environment | Plan and Manage Risk | Risk | Planning | Be an Accountable Leader | Identify Risks | Sustainability | 프로젝트 관리자가 재생에너지 프로젝트의 리스크 관리대장을 작성하고 있다. 지속가능성 프로젝트에만 있는 고유한 리스크 유형은 무엇인가? | 일정 지연 | 이해관계자 갈등 | 예산 초과 | 그린워싱 리스크—프로젝트의 지속가능성 주장이 과장되거나 검증 불가능하여 평판과 규제 리스크를 초래 |  | D | 정답은 D이다. 일정 지연(A), 이해관계자 갈등(B), 예산 초과(C)는 어떤 프로젝트에서도 생길 수 있다. 그린워싱 리스크, 즉 프로젝트의 지속가능성 주장이 과장되거나 검증할 수 없는 경우는 지속가능성 목표가 있는 프로젝트에 고유한 리스크이며 평판과 규제상의 결과를 낳을 수 있다.
2179 | An organization requires all projects to report their carbon emissions as part of project performance reporting. The PM is unsure how to measure this. What is the BEST approach? | Delegate the measurement to the finance department. | Report zero emissions since the project is primarily office-based. | Establish a carbon measurement baseline, identify key emission sources specific to the project, use recognized standards (such as GHG Protocol), and track emissions throughout the project lifecycle. | Estimate carbon emissions based on general industry averages. |  | C | Accurate carbon measurement requires a structured approach: establishing baselines, identifying project-specific emission sources, using recognized standards like the GHG Protocol, and continuous tracking. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 한 조직이 모든 프로젝트에 프로젝트 성과 보고의 일부로 탄소 배출량을 보고하도록 요구한다. 프로젝트 관리자는 이를 어떻게 측정해야 할지 확신이 없다. 가장 좋은 접근 방식은 무엇인가? | 재무부서에 측정을 위임한다 | 사무실 기반 프로젝트이므로 배출량 제로를 보고한다 | 탄소 측정 기준선을 설정하고, 프로젝트 고유의 주요 배출원을 파악하며, GHG 프로토콜 같은 공인 표준을 사용해 프로젝트 생애주기 전반에 걸쳐 배출량을 추적한다. | 일반적 산업 평균에 기반하여 탄소 배출량을 추정한다 |  | C | 정확한 탄소 측정은 구조화된 접근이 필요하다: 기준선 설정, 프로젝트별 배출원 식별, GHG 프로토콜 같은 인정된 표준 사용, 지속적 추적. 재무 위임(A)은 부적절하다. 제로 보고(B)는 부정확하다. 산업 평균(D)은 프로젝트별 정확성이 부족하다.
2180 | A project team is designing a new office building. The architect proposes green building certification (LEED). The client says sustainability is nice but not a priority. How should the PM position sustainability? | Drop green certification since the client doesn't prioritize it. | Present the business case for green certification including long-term energy savings, higher property values, tenant attraction, and regulatory preparedness, letting the client make an informed decision. | Implement only the cheapest sustainability features. | Include green certification without telling the client to avoid debate. |  | B | The correct answer is B. The client does not see sustainability as a priority, so the project manager should connect it to the client's own interests with a business case: long-term energy savings, higher property value, tenant attraction, and regulatory readiness. Dropping it (A) loses those benefits without analysis, implementing only the cheapest features (C) may not deliver real value, and adding it without telling the client (D) is not transparent. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | Predictive | Traditional Plan-Driven | People | Engage Stakeholders | Stakeholders | Planning | Focus on Value | Plan Stakeholder Engagement | Sustainability | 프로젝트 팀이 새 사무용 건물을 설계하고 있다. 건축가는 친환경 건축 인증(LEED)을 제안한다. 고객은 지속가능성이 좋긴 하지만 우선순위는 아니라고 말한다. 프로젝트 관리자는 지속가능성을 어떻게 제시해야 하는가? | 클라이언트가 우선시하지 않으므로 그린 인증을 포기한다 | 장기 에너지 절감, 자산 가치 상승, 입주사 유치, 규제 대비 효과를 포함한 친환경 인증의 비즈니스 케이스를 제시하고, 고객이 충분한 정보를 바탕으로 결정하게 한다. | 가장 저렴한 지속가능성 기능만 구현한다 | 논쟁을 피하기 위해 클라이언트에게 알리지 않고 그린 인증을 포함한다 |  | B | 정답은 B이다. 고객은 지속가능성을 우선순위로 보지 않으므로, 프로젝트 관리자는 장기 에너지 절감, 자산 가치 상승, 임차인 유치, 규제 대비 등 고객 자신의 이익과 연결한 비즈니스 케이스를 제시해야 한다. 인증을 포기하는 것(A)은 분석 없이 그 효익을 잃고, 가장 싼 기능만 넣는 것(C)은 실질적인 가치를 주지 못할 수 있으며, 고객에게 알리지 않고 넣는 것(D)은 투명하지 않다.
2181 | A manufacturing project produces significant waste. The PM implements a waste reduction program that decreases waste by 30% but slows production by 5%. How should this be reported to stakeholders? | Report only the production slowdown as a concern. | Report both the environmental benefit (30% waste reduction) and the production impact (5% slowdown) transparently, along with plans to optimize the balance. | Report only the positive waste reduction achievement. | Wait until both metrics improve before reporting. |  | B | The correct answer is B. Stakeholders can only make good decisions if they see the full picture. Transparently reporting both the 30% waste reduction and the 5% production slowdown, with plans to optimize, builds trust. Reporting only the slowdown (A) or only the benefit (C) gives a distorted view, and waiting until both improve (D) withholds information stakeholders need now. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Plan and Manage Communication | Stakeholders | Monitoring & Controlling | Integrate Sustainability | Monitor Communications | Sustainability | 한 제조 프로젝트에서 폐기물이 많이 발생한다. 프로젝트 관리자가 폐기물 감축 프로그램을 시행해 폐기물을 30% 줄였지만 생산 속도는 5% 느려졌다. 이를 이해관계자에게 어떻게 보고해야 하는가? | 생산 둔화만 우려로 보고한다 | 환경 효익(폐기물 30% 감소)과 생산 영향(5% 둔화)을 모두 투명하게 보고하고, 둘 사이의 균형을 최적화할 계획도 함께 제시한다. | 긍정적 폐기물 감소 성과만 보고한다 | 두 지표 모두 개선될 때까지 보고를 기다린다 |  | B | 정답은 B이다. 이해관계자는 전체 그림을 볼 때만 좋은 결정을 내릴 수 있다. 폐기물 30% 감소와 생산 5% 둔화를 모두 투명하게 보고하고 개선 계획을 함께 제시하면 신뢰가 쌓인다. 생산 둔화만(A) 또는 효익만(C) 보고하는 것은 왜곡된 정보를 주고, 둘 다 나아질 때까지 기다리는 것(D)은 지금 필요한 정보를 주지 않는 것이다.
2182 | A project team is evaluating vendors for a supply chain project. One vendor has lower costs but poor ESG (Environmental, Social, Governance) ratings. Another vendor has higher costs but excellent ESG ratings. What evaluation criteria should the PM use? | Include ESG criteria as weighted factors in the vendor evaluation scorecard alongside cost, quality, and delivery performance. | Exclude ESG from vendor evaluation as it's not relevant to procurement. | Select the vendor with the highest ESG rating regardless of cost. | Select the vendor with the lowest cost regardless of ESG. |  | A | The correct answer is A. Vendor selection should balance several factors. Including ESG criteria as weighted factors alongside cost, quality, and delivery performance lets the evaluation reflect both financial and sustainability considerations in a transparent, consistent way. Excluding ESG (B) ignores growing organizational and regulatory expectations, and choosing on ESG alone (C) or cost alone (D) ignores the trade-offs. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트 팀이 공급망 프로젝트의 벤더를 평가하고 있다. 한 벤더는 비용이 낮지만 ESG(환경·사회·지배구조) 등급이 나쁘다. 다른 벤더는 비용이 높지만 ESG 등급이 우수하다. 프로젝트 관리자는 어떤 평가 기준을 사용해야 하는가? | 비용, 품질, 납기와 함께 ESG 기준을 가중 요소로 벤더 평가 스코어카드에 포함한다 | ESG는 조달과 관련이 없으므로 벤더 평가에서 제외한다 | 비용에 관계없이 ESG 등급이 가장 높은 벤더를 선택한다 | ESG에 관계없이 비용이 가장 낮은 벤더를 선택한다 |  | A | 정답은 A이다. 공급업체 선정은 여러 요소의 균형을 맞춰야 한다. 원가, 품질, 납기 성과와 함께 ESG 기준을 가중 요소로 평가표에 넣으면 재무와 지속가능성 측면을 투명하고 일관되게 반영할 수 있다. ESG를 빼는 것(B)은 커지는 조직·규제상의 기대를 무시하고, ESG만(C) 또는 원가만(D) 보고 고르는 것은 트레이드오프를 무시하는 것이다.
2183 | A project manager is leading a digital transformation project. How can sustainability be integrated into a software project? | Sustainability doesn't apply to software projects. | Consider server energy efficiency, optimize code for reduced computational resources, minimize data storage waste, and design for digital accessibility and inclusion. | Only use recycled hardware. | Print project documents on recycled paper. |  | B | The correct answer is B. Software projects also have environmental and social impacts. Sustainability can be integrated by considering server energy efficiency, optimizing code to use fewer computational resources, minimizing data storage waste, and designing for digital accessibility. Saying sustainability does not apply (A) is incorrect, and using recycled hardware (C) or printing on recycled paper (D) are narrow measures that miss the main impacts of software. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 디지털 전환 프로젝트에서 지속가능성을 소프트웨어 프로젝트에 어떻게 통합할 수 있는가? | 지속가능성은 소프트웨어 프로젝트에 적용되지 않는다 | 서버 에너지 효율, 코드 최적화로 계산 자원 감소, 데이터 낭비 최소화, 디지털 접근성을 고려한다 | 재활용 하드웨어만 사용한다 | 재활용 종이에 프로젝트 문서를 인쇄한다 |  | B | 정답은 B이다. 소프트웨어 프로젝트에도 환경적·사회적 영향이 있다. 서버 에너지 효율을 고려하고, 연산 자원을 덜 쓰도록 코드를 최적화하며, 데이터 저장 낭비를 줄이고, 디지털 접근성을 고려해 설계하면 지속가능성을 통합할 수 있다. 지속가능성이 해당되지 않는다는 것(A)은 틀렸고, 재활용 하드웨어 사용(C)이나 재생지 인쇄(D)는 소프트웨어의 주요 영향을 놓치는 좁은 조치이다.
2184 | A project's environmental impact assessment reveals that a planned activity will damage a local wetland. The activity is on the critical path. What should the PM do? | Proceed but plan to restore the wetland after the project. | Cancel the entire project. | Proceed with the activity since it's on the critical path and delays are unacceptable. | Evaluate alternative approaches that avoid wetland damage, assess schedule and cost impacts of each alternative, and present options to the governance board. |  | D | The correct answer is D. Damaging a wetland has serious environmental and regulatory consequences, so even a critical path activity must be reconsidered. The project manager should evaluate alternatives that avoid the damage, assess their schedule and cost impacts, and present the options to the governance body. Proceeding and restoring later (A) or proceeding because of the schedule (C) accepts avoidable harm, and cancelling the whole project (B) is premature before alternatives are explored. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Compliance | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 환경 영향 평가에서 계획된 활동이 지역 습지를 손상시킬 것임이 밝혀졌다. 이 활동은 주공정선에 있다. PM은 무엇을 해야 하는가? | 진행하되 프로젝트 후 습지를 복원할 계획을 세운다 | 전체 프로젝트를 취소한다 | 주공정선에 있고 지연이 불가하므로 활동을 진행한다 | 습지 손상을 피하는 대안 접근법을 평가하고, 각 대안의 일정 및 비용 영향을 평가하여 이해관계자에게 제시한다 |  | D | 정답은 D이다. 습지를 훼손하면 심각한 환경·규제상의 결과가 따르므로, 주공정 활동이라도 다시 검토해야 한다. 프로젝트 관리자는 훼손을 피하는 대안을 평가하고, 각 대안의 일정·원가 영향을 분석해 거버넌스 기구에 선택지를 제시해야 한다. 진행한 뒤 나중에 복원하는 것(A)이나 일정 때문에 진행하는 것(C)은 피할 수 있는 피해를 받아들이는 것이고, 프로젝트 전체를 취소하는 것(B)은 대안을 찾아보기 전이라 성급하다.
2185 | A project team has reduced paper usage by 90% through digital workflows. The PM wants to report this as a sustainability achievement. What additional context should be included? | Also report the energy consumption of digital infrastructure (cloud storage, servers, devices) to provide a complete environmental picture. | Report only the paper reduction percentage. | Report the cost savings from reduced paper purchases. | Compare with other projects' paper usage. |  | A | The correct answer is A. Going digital reduces paper, but digital infrastructure such as cloud storage, servers, and devices also consumes energy. Reporting that energy use alongside the paper reduction gives a complete and honest environmental picture. Reporting only the paper percentage (B) can overstate the benefit, cost savings (C) are not an environmental measure, and comparing with other projects (D) does not address the missing data. | Process | Manage Communications | Stakeholders | Effectively Engage with Stakeholders | General | General PM Principles | People | Plan and Manage Communication | Stakeholders | Monitoring & Controlling | Integrate Sustainability | Monitor Communications | Sustainability | 프로젝트 팀이 디지털 워크플로를 도입해 종이 사용을 90% 줄였다. 프로젝트 관리자는 이를 지속가능성 성과로 보고하려 한다. 어떤 추가 맥락을 함께 제시해야 하는가? | 전체 환경 상황을 제공하기 위해 디지털 인프라(클라우드 스토리지, 서버, 디바이스)의 에너지 소비도 보고한다 | 종이 감소 비율만 보고한다 | 종이 구매 감소에 따른 비용 절감을 보고한다 | 다른 프로젝트의 종이 사용과 비교한다 |  | A | 정답은 A이다. 디지털 전환으로 종이는 줄었지만 클라우드 저장소, 서버, 기기 같은 디지털 인프라도 에너지를 쓴다. 종이 절감과 함께 이 에너지 사용량을 보고해야 완전하고 정직한 환경 성과를 보여 줄 수 있다. 종이 절감률만 보고하는 것(B)은 효익을 과장할 수 있고, 비용 절감(C)은 환경 지표가 아니며, 다른 프로젝트와 비교하는 것(D)은 빠진 데이터를 채우지 못한다.
2186 | A project team is implementing a circular economy approach in a product design project. What does this mean for project scope? | Circular economy only applies to manufacturing projects. | The project should use only recycled materials. | The scope includes designing for product longevity, repairability, recyclability, and responsible end-of-life disposal from the initial design phase. | The project only needs to deliver the product; end-of-life considerations are out of scope. |  | C | The correct answer is C. A circular economy approach considers the whole product lifecycle from the start. The scope must include designing for longevity, repairability, recyclability, and responsible end-of-life handling. It is not limited to manufacturing projects (A), it is broader than using only recycled materials (B), and treating end-of-life as out of scope (D) contradicts the approach. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Predictive-Agile Blend | Process | Develop and Manage Scope | Scope | Planning | Integrate Sustainability | Define Scope | Sustainability | 순환 경제 접근법을 제품 설계 프로젝트에 적용하는 것은 범위에 무엇을 의미하는가? | 순환 경제는 제조 프로젝트에만 적용된다 | 프로젝트는 재활용 재료만 사용해야 한다 | 범위에 제품 수명, 수리 가능성, 재활용 가능성, 책임 있는 수명 종료 설계가 포함된다 | 프로젝트는 제품만 전달하면 되고 수명 종료 고려는 범위 밖이다 |  | C | 정답은 C이다. 순환 경제 접근은 처음부터 제품의 전체 생애주기를 고려한다. 범위에는 내구성, 수리 가능성, 재활용 가능성, 책임 있는 폐기를 고려한 설계가 포함되어야 한다. 이는 제조 프로젝트에만 해당하는 것(A)이 아니고, 재활용 소재만 쓰는 것(B)보다 넓으며, 폐기 단계를 범위 밖으로 보는 것(D)은 이 접근과 모순된다.
2187 | A project manager is developing a sustainability-focused project. The sponsor asks how to measure project sustainability performance. What framework should the PM recommend? | Track only financial ROI. | Implement a sustainability balanced scorecard that includes environmental KPIs (carbon emissions, waste, energy), social KPIs (safety, diversity, community impact), and economic KPIs (lifecycle cost, value delivery). | Measure sustainability qualitatively through annual surveys. | Use standard earned value management metrics only. |  | B | The correct answer is B. Sustainability performance has environmental, social, and economic dimensions, so it needs a balanced set of measures. A sustainability balanced scorecard with KPIs such as carbon emissions, waste, and energy; safety and diversity; and cost and value covers all of them. Financial ROI alone (A) and standard EVM (D) miss environmental and social results, and annual qualitative surveys (C) are too infrequent and imprecise to manage performance. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트 관리자가 지속가능성 중심의 프로젝트를 추진하고 있다. 스폰서는 프로젝트의 지속가능성 성과를 어떻게 측정할지 묻는다. 프로젝트 관리자는 어떤 프레임워크를 권해야 하는가? | 재무 ROI만 추적한다 | 환경 KPI(탄소 배출, 폐기물, 에너지), 사회 KPI(안전, 다양성, 지역사회 영향), 경제 KPI(생애주기 원가, 가치 인도)를 포함하는 지속가능성 균형성과표를 도입한다. | 연간 설문을 통해 지속가능성을 정성적으로 측정한다 | 표준 EVM 지표만 사용한다 |  | B | 정답은 B이다. 지속가능성 성과에는 환경·사회·경제 측면이 있으므로 균형 잡힌 지표 세트가 필요하다. 탄소 배출·폐기물·에너지, 안전·다양성, 원가·가치 같은 KPI를 담은 지속가능성 균형성과표는 이 모든 측면을 다룬다. 재무 ROI만 보는 것(A)과 일반 EVM 지표만 쓰는 것(D)은 환경·사회 성과를 놓치고, 연 1회 정성 설문(C)은 성과를 관리하기에 너무 드물고 부정확하다.
2188 | A project team discovers that a key project component has a significantly higher carbon footprint than initially estimated. The project is 60% complete. What should the PM do? | Continue as planned since the project is too far along to change. | Raise a change request to evaluate lower-carbon alternatives for the remaining work, assess schedule and cost implications, and update the sustainability plan. | Halt the project immediately until a green alternative is found. | Offset the carbon through tree planting without changing the project. |  | B | The correct answer is B. Even at 60% complete, the remaining work may offer chances to reduce the carbon footprint. A change request lets the team evaluate lower-carbon alternatives for that work, assess schedule and cost impacts, and update the plan through proper governance. Continuing unchanged (A) ignores a significant problem, halting the project (C) is excessive, and relying only on offsets (D) avoids reducing the actual impact. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Predictive-Agile Blend | Process | Develop Integrated PM Plan | Governance | Monitoring & Controlling | Integrate Sustainability | Monitor and Control Project Performance | Sustainability | 프로젝트 60% 완료 시 핵심 구성요소의 탄소 발자국이 초기 추정보다 크게 높음이 발견되었다. PM은 무엇을 해야 하는가? | 프로젝트가 너무 진행되어 변경할 수 없으므로 계획대로 계속한다 | 잔여 작업의 저탄소 대안을 평가하는 변경 요청을 제기하고 일정 및 비용 영향을 평가한다 | 녹색 대안을 찾을 때까지 프로젝트를 즉시 중단한다 | 프로젝트를 변경하지 않고 나무 심기로 탄소를 상쇄한다 |  | B | 정답은 B이다. 60% 진행된 시점이라도 남은 작업에서 탄소 발자국을 줄일 기회가 있을 수 있다. 변경 요청을 통해 남은 작업에 대한 저탄소 대안을 평가하고, 일정·원가 영향을 분석하며, 적절한 거버넌스로 계획을 갱신할 수 있다. 계획대로 계속하는 것(A)은 중대한 문제를 무시하고, 프로젝트를 중단하는 것(C)은 과하며, 나무 심기 같은 상쇄에만 기대는 것(D)은 실제 영향을 줄이지 않는 것이다.
2189 | A project manager needs to select a project delivery approach for a sustainable building project. The sustainability requirements are evolving as new green technologies emerge. Which approach is MOST appropriate? | A hybrid approach that uses predictive planning for structural elements and agile iterations for sustainability features that may evolve as green technologies advance. | A purely predictive (waterfall) approach with all requirements defined upfront. | A fully agile approach with no upfront planning. | Delay the project until all green technologies are finalized. |  | A | The correct answer is A. Structural elements need stable, upfront planning, while sustainability features may change as new green technologies emerge. A hybrid approach uses predictive planning for the structure and agile iterations for the evolving features. A purely predictive approach (B) cannot absorb the changes, a fully agile approach (C) does not suit structural work, and delaying the project (D) is impractical because the technologies keep evolving. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Hybrid | Tailored Approach | Process | Develop Integrated PM Plan | Governance | Initiating | Adopt a Holistic View | Develop Project Charter | Sustainability | 프로젝트 관리자가 지속가능 건축 프로젝트의 인도 방식을 선택해야 한다. 새로운 친환경 기술이 등장하면서 지속가능성 요구사항이 계속 변하고 있다. 가장 적합한 접근 방식은 무엇인가? | 구조 요소에 예측형 계획, 지속가능성 기능에 애자일 이터레이션을 사용하는 하이브리드 접근법 | 모든 요구사항을 사전 정의하는 순수 예측형(폭포수) 접근법 | 사전 계획 없는 완전한 애자일 접근법 | 모든 녹색 기술이 확정될 때까지 프로젝트를 지연한다 |  | A | 정답은 A이다. 구조 요소는 안정적인 사전 계획이 필요하고, 지속가능성 기능은 새 친환경 기술이 등장하면서 바뀔 수 있다. 하이브리드 접근은 구조에는 예측형 계획을, 변하는 기능에는 애자일 이터레이션을 적용한다. 순수 예측형(B)은 변화를 흡수하지 못하고, 완전한 애자일(C)은 구조 작업에 맞지 않으며, 기술이 계속 바뀌므로 프로젝트를 미루는 것(D)은 비현실적이다.
2190 | A project's stakeholder analysis reveals that a local community group is concerned about the project's environmental impact. The group is not a contractual stakeholder. Should the PM engage them? | No, only contractual stakeholders need to be engaged. | Engage them only through legal representatives. | Only engage them if they file a formal complaint. | Yes, proactively engage the community group, understand their concerns, share environmental mitigation plans, and establish ongoing communication channels. |  | D | The correct answer is D. Stakeholders include everyone affected by the project, not only contractual parties. The community group's concerns can influence the project's success, so the project manager should engage them proactively, understand their concerns, share mitigation plans, and keep communication open. Ignoring them (A), engaging only through lawyers (B), or waiting for a formal complaint (C) increases conflict and risk. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Integrate Sustainability | Manage Stakeholder Engagement | Sustainability | 프로젝트의 이해관계자 분석에서 한 지역 주민 단체가 프로젝트의 환경 영향을 우려하고 있는 것으로 나타났다. 이 단체는 계약상 이해관계자가 아니다. 프로젝트 관리자는 이들을 참여시켜야 하는가? | 아니오, 계약 이해관계자만 참여시키면 된다 | 법적 대리인을 통해서만 참여시킨다 | 공식 불만을 제기하는 경우에만 참여시킨다 | 그렇다. 주민 단체를 선제적으로 참여시켜 우려를 파악하고, 환경 영향 완화 계획을 공유하며, 지속적인 소통 채널을 마련한다. |  | D | 정답은 D이다. 이해관계자에는 계약 당사자뿐 아니라 프로젝트의 영향을 받는 모든 사람이 포함된다. 지역 주민 단체의 우려는 프로젝트 성공에 영향을 줄 수 있으므로, 프로젝트 관리자는 이들을 선제적으로 참여시키고, 우려를 이해하며, 완화 계획을 공유하고, 소통 창구를 계속 열어 두어야 한다. 무시하는 것(A), 변호사를 통해서만 소통하는 것(B), 공식 민원이 들어올 때까지 기다리는 것(C)은 갈등과 리스크를 키운다.
2191 | An IT project manager is migrating on-premise servers to a cloud provider. Which sustainability consideration should be included in the vendor selection criteria? | The cloud provider's renewable energy usage, data center energy efficiency (PUE rating), carbon offset programs, and sustainability certifications. | The cloud provider's office location and building design. | Whether the cloud provider uses the latest hardware. | Only the cloud provider's pricing model. |  | A | The correct answer is A. Data centers consume a large amount of energy, so a cloud provider's renewable energy use, data center efficiency (such as its PUE rating), carbon programs, and sustainability certifications are the relevant sustainability criteria. Office location and building design (B) do not reflect the service's footprint, having the latest hardware (C) is not itself a sustainability measure, and pricing alone (D) ignores sustainability. | Process | Plan & Manage Procurement | Project Work | Be a Diligent, Respectful, and Caring Steward | Agile | Agile General Practices | Process | Plan and Manage Procurement | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | IT 프로젝트 관리자가 사내 서버를 클라우드 제공업체로 이전하고 있다. 벤더 선정 기준에 어떤 지속가능성 고려 사항을 포함해야 하는가? | 클라우드 제공업체의 재생에너지 사용률, 데이터센터 에너지 효율(PUE 등급), 탄소 상쇄 프로그램, 지속가능성 인증 | 클라우드 제공자의 사무실 위치와 건물 설계 | 클라우드 제공자가 최신 하드웨어를 사용하는지 | 클라우드 제공자의 가격 모델만 |  | A | 정답은 A이다. 데이터센터는 에너지를 많이 쓰므로, 클라우드 제공업체의 재생에너지 사용, 데이터센터 효율(PUE 등급 등), 탄소 프로그램, 지속가능성 인증이 적절한 지속가능성 기준이다. 사무실 위치와 건물 설계(B)는 서비스의 환경 부담을 반영하지 않고, 최신 하드웨어 사용 여부(C)는 그 자체로 지속가능성 지표가 아니며, 가격만 보는 것(D)은 지속가능성을 무시한다.
2192 | A project manager is planning team travel for a distributed project. How can sustainability be incorporated into travel planning? | Only consider travel costs, not environmental impact. | Cancel all team meetings to avoid travel completely. | Allow unlimited travel since face-to-face meetings are more productive. | Prioritize virtual meetings, offset necessary travel emissions, choose sustainable transportation options, and batch in-person meetings to minimize total travel. |  | D | The correct answer is D. Sustainable travel planning balances the value of in-person collaboration with environmental responsibility: prioritizing virtual meetings, batching necessary in-person meetings, choosing lower-impact transportation, and offsetting unavoidable emissions. Considering only cost (A) ignores the environment, cancelling all meetings (B) harms collaboration, and allowing unlimited travel (C) ignores both cost and impact. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Planning | Integrate Sustainability | Determine Budget | Sustainability | 프로젝트 관리자가 분산 프로젝트의 팀 출장을 계획하고 있다. 출장 계획에 지속가능성을 어떻게 반영할 수 있는가? | 환경 영향이 아닌 출장 비용만 고려한다 | 출장을 완전히 피하기 위해 모든 팀 회의를 취소한다 | 대면 회의가 더 생산적이므로 무제한 출장을 허용한다 | 가상 회의를 우선하고, 꼭 필요한 출장의 배출량은 상쇄하며, 지속가능한 교통수단을 선택하고, 대면 회의를 몰아서 잡아 전체 출장을 최소화한다. |  | D | 정답은 D이다. 지속가능한 출장 계획은 대면 협업의 가치와 환경 책임의 균형을 맞추는 것이다. 가상 회의를 우선하고, 꼭 필요한 대면 회의는 모아서 하며, 환경 부담이 적은 교통수단을 고르고, 피할 수 없는 배출은 상쇄한다. 비용만 고려하는 것(A)은 환경을 무시하고, 모든 회의를 취소하는 것(B)은 협업을 해치며, 출장을 무제한 허용하는 것(C)은 비용과 영향을 모두 무시한다.
2193 | A project delivers a product that meets all functional requirements but has a high energy consumption rate during operation. From a PMBOK 8th Edition perspective, is the project successful? | Not entirely—PMBOK 8th Edition's sustainability principle suggests that project success should also consider the product's long-term environmental impact during its operational lifecycle. | Yes, operational energy consumption is not the project team's responsibility. | Yes, because all functional requirements are met. | No, the project is a complete failure. |  | A | The correct answer is A. Meeting functional requirements is necessary but not the whole picture: from a sustainability perspective, project success also considers the product's long-term environmental impact, such as high operating energy use. Saying operational energy is not the team's concern (B) or that meeting requirements is enough (C) ignores the principle, while calling the project a complete failure (D) overstates it. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 한 프로젝트가 모든 기능 요구사항을 충족하는 제품을 인도했지만, 이 제품은 운영 중 에너지 소비율이 높다. PMBOK 8판 관점에서 이 프로젝트는 성공한 것인가? | 완전히 그렇지는 않다. PMBOK 8판의 지속가능성 원칙에 따르면 프로젝트 성공은 운영 생애주기 동안 제품이 미치는 장기적 환경 영향도 고려해야 한다. | 예, 운영 에너지 소비는 프로젝트 팀의 책임이 아니다 | 예, 모든 기능 요구사항이 충족되었으므로 | 아니오, 프로젝트는 완전한 실패이다 |  | A | 정답은 A이다. 기능 요구사항 충족은 필요하지만 전부는 아니다. 지속가능성 관점에서 프로젝트 성공은 운영 중 높은 에너지 사용처럼 제품의 장기적 환경 영향도 고려한다. 운영 에너지는 팀의 책임이 아니라는 것(B)이나 요구사항만 충족하면 된다는 것(C)은 이 원칙을 무시하고, 완전한 실패라고 하는 것(D)은 지나친 평가이다.
2194 | A project team working on an agile software project wants to implement 'green sprints'—dedicated sprints focused solely on reducing the application's environmental footprint. What should the Scrum Master recommend? | Sustainability should never be part of sprint work. | Only address sustainability in the final sprint before release. | Dedicate every 5th sprint exclusively to sustainability improvements. | Integrate sustainability improvements into the regular backlog alongside feature work, applying the same prioritization criteria based on business and environmental value. |  | D | The correct answer is D. Isolating sustainability into special sprints treats it as separate from normal work. Integrating sustainability improvements into the regular backlog and prioritizing them with the same business and environmental value criteria keeps continuous attention on them. Excluding sustainability (A), saving it for the final sprint (B), or reserving every fifth sprint (C) delays or fragments the work. | Process | Plan & Manage Scope | Delivery | Focus on Value | Agile | Scrum | Process | Develop and Manage Scope | Scope | Planning | Integrate Sustainability | Define Scope | Sustainability | 애자일 소프트웨어 프로젝트 팀이 애플리케이션의 환경 발자국을 줄이는 데만 집중하는 '그린 스프린트'를 도입하고 싶어 한다. 스크럼 마스터는 무엇을 권해야 하는가? | 지속가능성은 스프린트 작업의 일부가 되어서는 안 된다 | 릴리스 전 마지막 스프린트에서만 지속가능성을 다룬다 | 매 5번째 스프린트를 지속가능성 개선에 전용한다 | 지속가능성 개선 항목을 기능 작업과 함께 일반 백로그에 통합하고, 비즈니스 가치와 환경 가치에 근거한 동일한 우선순위 기준을 적용한다. |  | D | 정답은 D이다. 지속가능성을 별도 스프린트로 떼어 내면 일상 작업과 분리된 것으로 다루게 된다. 지속가능성 개선 항목을 일반 백로그에 넣고 비즈니스·환경 가치라는 같은 기준으로 우선순위를 정하면 지속적으로 관심을 유지할 수 있다. 지속가능성을 아예 빼는 것(A), 마지막 스프린트로 미루는 것(B), 다섯 번째 스프린트마다 따로 두는 것(C)은 작업을 늦추거나 조각낸다.
2195 | During risk identification for a new facility construction project, the team identifies climate change impacts (flooding, extreme heat) as potential risks. How should these be categorized? | Categorize them as force majeure and exclude from risk management. | Only consider them if the project is in a known high-risk area. | Document them in the risk register as external environmental risks, assess probability and impact using climate data, and develop appropriate response strategies (avoid, mitigate, transfer). | Ignore them since they are acts of nature and uncontrollable. |  | C | The correct answer is C. Climate impacts such as flooding and extreme heat are external environmental risks that can be assessed and managed. They should be documented in the risk register, their probability and impact evaluated using climate data, and responses planned. Treating them as force majeure and excluding them (A), considering them only in known high-risk areas (B), or ignoring them as uncontrollable (D) leaves the project exposed. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Adopt a Holistic View | Identify Risks | Sustainability | 신규 시설 건설 프로젝트의 리스크 식별 중에 팀이 기후 변화의 영향(홍수, 폭염)을 잠재적 리스크로 식별했다. 이 리스크들은 어떻게 분류해야 하는가? | 불가항력으로 분류하고 리스크 관리에서 제외한다 | 프로젝트가 알려진 고위험 지역에 있는 경우에만 고려한다 | 리스크 관리대장에 외부 환경 리스크로 기록하고, 기후 데이터로 발생 확률과 영향을 평가하며, 적절한 대응 전략(회피, 완화, 전가)을 수립한다. | 자연재해이며 통제 불가능하므로 무시한다 |  | C | 정답은 C이다. 홍수와 폭염 같은 기후 영향은 평가하고 관리할 수 있는 외부 환경 리스크이다. 리스크 관리대장에 기록하고, 기후 데이터로 발생 확률과 영향을 평가하며, 대응을 계획해야 한다. 불가항력으로 보고 제외하는 것(A), 알려진 고위험 지역에서만 고려하는 것(B), 통제할 수 없다며 무시하는 것(D)은 프로젝트를 리스크에 노출시킨다.
2196 | A project manager is leading a product launch project. Marketing wants to promote the product as 'eco-friendly.' The PM knows the product meets some sustainability criteria but not all. What should the PM advise? | Recommend that marketing claims be specific, verifiable, and accurately reflect the product's actual sustainability achievements to avoid greenwashing. | Reject all sustainability marketing claims. | Let the marketing department handle messaging without PM involvement. | Approve the marketing claim since the product meets some criteria. |  | A | The correct answer is A. The product meets some sustainability criteria but not all, so a broad 'eco-friendly' claim risks greenwashing. The project manager should advise that claims be specific, verifiable, and accurate about what the product actually achieves. Rejecting all claims (B) discards legitimate achievements, leaving it entirely to marketing (C) ignores the project manager's knowledge, and approving the broad claim (D) invites reputational and regulatory risk. | People | Collaborate with Stakeholders | Stakeholders | Effectively Engage with Stakeholders | General | Stakeholder & Communication Mgmt | People | Engage Stakeholders | Stakeholders | Executing | Be an Accountable Leader | Manage Stakeholder Engagement | Sustainability | 프로젝트 관리자가 제품 출시 프로젝트를 이끌고 있다. 마케팅 부서는 제품을 '친환경'으로 홍보하고 싶어 한다. 프로젝트 관리자는 제품이 일부 지속가능성 기준은 충족하지만 전부 충족하지는 않는다는 것을 알고 있다. 프로젝트 관리자는 어떻게 조언해야 하는가? | 마케팅 주장이 구체적이고, 검증 가능하며, 제품의 실제 환경 성과를 정확히 반영하도록 권고한다 | 모든 지속가능성 마케팅 주장을 거부한다 | PM 관여 없이 마케팅 부서가 메시지를 처리하게 한다 | 제품이 일부 기준을 충족하므로 마케팅 주장을 승인한다 |  | A | 정답은 A이다. 제품은 일부 지속가능성 기준만 충족하므로 포괄적인 '친환경' 주장은 그린워싱 위험이 있다. 프로젝트 관리자는 제품이 실제로 달성한 내용에 대해 구체적이고 검증 가능하며 정확하게 표현하도록 조언해야 한다. 모든 주장을 거부하는 것(B)은 정당한 성과까지 버리고, 마케팅에 전부 맡기는 것(C)은 프로젝트 관리자의 지식을 활용하지 않으며, 포괄적 주장을 승인하는 것(D)은 평판·규제 리스크를 부른다.
2197 | An organization is developing sustainability KPIs for its project portfolio. Which KPI set is MOST comprehensive for tracking sustainability across projects? | A multi-dimensional set including carbon footprint, water usage, waste diversion rate, energy efficiency, supply chain sustainability score, social impact metrics, and sustainable procurement percentage. | Only carbon emissions per project. | Employee satisfaction with sustainability programs. | Only financial savings from green initiatives. |  | A | The correct answer is A. Sustainability has environmental, social, and economic dimensions, so a portfolio needs a multi-dimensional KPI set, such as carbon footprint, water use, waste diversion, energy efficiency, supply chain sustainability, social impact, and sustainable procurement. Tracking only carbon (B), only employee satisfaction (C), or only financial savings (D) covers a single dimension and misses the rest. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 한 조직이 프로젝트 포트폴리오의 지속가능성 KPI를 개발하고 있다. 여러 프로젝트에 걸쳐 지속가능성을 추적하기에 가장 포괄적인 KPI 세트는 무엇인가? | 탄소 발자국, 물 사용량, 폐기물 재활용률, 에너지 효율, 공급망 지속가능성 점수, 사회적 영향 지표, 지속가능 조달 비율을 포함하는 다차원 세트 | 프로젝트당 탄소 배출만 | 지속가능성 프로그램에 대한 직원 만족도 | 녹색 이니셔티브로 인한 재무 절감만 |  | A | 정답은 A이다. 지속가능성에는 환경·사회·경제 측면이 있으므로 포트폴리오에는 탄소 발자국, 물 사용량, 폐기물 재활용률, 에너지 효율, 공급망 지속가능성, 사회적 영향, 지속가능 조달 같은 다차원 KPI가 필요하다. 탄소만(B), 직원 만족도만(C), 재무 절감만(D) 추적하는 것은 한 측면만 다루고 나머지를 놓친다.
2198 | A project manager is closing a 2-year infrastructure project. What sustainability deliverable should be included in the project handover to operations? | A list of sustainability regulations that apply to the facility. | Only the standard operations manual. | A sustainability operations guide including environmental monitoring procedures, energy management protocols, waste management plans, and sustainability performance baselines for the operations team to maintain. | A one-time environmental audit report. |  | C | The correct answer is C. For sustainable practices to continue after handover, operations needs practical guidance: environmental monitoring procedures, energy management protocols, waste management plans, and sustainability performance baselines. A list of regulations (A) does not say how to comply, the standard manual alone (B) omits sustainability, and a one-time audit report (D) does not support ongoing management. | Process | Integrate Project Planning Activities | Planning | Recognize, Evaluate, and Respond to System Interactions | Predictive | Traditional Plan-Driven | Process | Develop Integrated PM Plan | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 프로젝트 관리자가 2년짜리 인프라 프로젝트를 종료하고 있다. 운영 부서로 인계할 때 포함해야 할 지속가능성 인도물은 무엇인가? | 시설에 적용되는 지속가능성 규정 목록 | 표준 운영 매뉴얼만 | 운영팀이 유지해야 할 환경 모니터링 절차, 에너지 관리 프로토콜, 폐기물 관리 계획, 지속가능성 성과 기준선을 담은 지속가능성 운영 가이드 | 일회성 환경 감사 보고서 |  | C | 정답은 C이다. 인계 후에도 지속가능한 관행이 이어지려면 운영팀에 실질적인 지침이 필요하다. 환경 모니터링 절차, 에너지 관리 프로토콜, 폐기물 관리 계획, 지속가능성 성과 기준선이 담긴 운영 가이드를 넘겨야 한다. 규정 목록(A)은 어떻게 준수할지 알려 주지 않고, 표준 운영 매뉴얼만(B)으로는 지속가능성이 빠지며, 일회성 감사 보고서(D)는 지속적인 관리를 뒷받침하지 못한다.
2199 | A project team is using a hybrid approach for a green building project. The team finds that sustainability requirements keep evolving as new environmental regulations are announced. How should the PM manage this? | Switch entirely to an agile approach mid-project. | Freeze all sustainability requirements at the start of the project. | Maintain a dynamic sustainability backlog that is regularly updated based on regulatory changes, with formal change impact assessments for requirements affecting the predictive scope. | Ignore new regulations until the project is complete. |  | C | The correct answer is C. Sustainability requirements keep changing with new regulations, so they need a flexible yet governed approach. A dynamic sustainability backlog updated as regulations change, combined with formal change impact assessments for items that affect the predictive scope, balances adaptability and control. Switching entirely to agile (A) is disruptive, freezing requirements (B) risks non-compliance, and ignoring new regulations (D) is not acceptable. | Process | Plan & Manage Scope | Delivery | Focus on Value | Hybrid | Tailored Approach | Process | Develop and Manage Scope | Scope | Monitoring & Controlling | Integrate Sustainability | Control Scope | Sustainability | 프로젝트 팀이 친환경 건축 프로젝트에 하이브리드 방식을 쓰고 있다. 새 환경 규제가 발표될 때마다 지속가능성 요구사항이 계속 바뀐다. 프로젝트 관리자는 이를 어떻게 관리해야 하는가? | 프로젝트 중간에 완전한 애자일 접근법으로 전환한다 | 프로젝트 시작 시 모든 지속가능성 요구사항을 동결한다 | 규제 변화에 따라 정기적으로 갱신되는 동적 지속가능성 백로그를 유지하되, 예측형 범위에 영향을 주는 요구사항은 공식 변경 영향 평가를 거친다. | 프로젝트가 완료될 때까지 새 규제를 무시한다 |  | C | 정답은 C이다. 지속가능성 요구사항이 새 규제에 따라 계속 바뀌므로 유연하면서도 통제된 방식이 필요하다. 규제 변화에 맞춰 갱신하는 동적 지속가능성 백로그를 운영하고, 예측형 범위에 영향을 주는 항목은 공식 변경 영향 평가를 거치면 적응성과 통제의 균형을 맞출 수 있다. 완전히 애자일로 바꾸는 것(A)은 혼란을 주고, 요구사항을 동결하는 것(B)은 규정 미준수 위험이 있으며, 새 규제를 무시하는 것(D)은 받아들일 수 없다.
2200 | A project manager discovers that the project's supply chain includes a tier-2 supplier using child labor. This was not identified during initial procurement planning. What should the PM do FIRST? | Document the issue for the lessons learned report at project closure. | Ask the tier-1 supplier to handle the issue without the PM's involvement. | Continue since the tier-2 supplier is not a direct contract partner. | Immediately notify the procurement team and organizational leadership, initiate an investigation, and evaluate alternative suppliers to address the social sustainability violation. |  | D | The correct answer is D. Child labor anywhere in the supply chain is a serious ethical and legal issue that requires immediate action, even at tier 2. The project manager should notify procurement and leadership, start an investigation, and evaluate alternative suppliers. Waiting for lessons learned (A) delays action, leaving it to the tier-1 supplier (B) avoids responsibility, and continuing because the supplier is not a direct contract partner (C) ignores the violation. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | Procurement & Contract Mgmt | Business Environment | Plan and Manage Compliance | Governance | Executing | Be an Accountable Leader | Direct and Manage Project Work | Sustainability | 프로젝트 관리자는 프로젝트 공급망에 아동 노동을 사용하는 2차 협력업체가 있다는 것을 발견했다. 이는 초기 조달 계획 때 파악되지 않았다. 프로젝트 관리자가 가장 먼저 해야 할 일은 무엇인가? | 프로젝트 종료 시 교훈 보고서에 문제를 문서화한다 | 1차 공급자에게 PM 관여 없이 문제를 처리하도록 요청한다 | 2차 공급자가 직접 계약 파트너가 아니므로 계속한다 | 즉시 조달팀과 조직 경영진에 알리고, 조사를 시작하며, 사회적 지속가능성 위반에 대응하기 위해 대체 공급업체를 검토한다. |  | D | 정답은 D이다. 공급망 어디에서든 아동 노동은 즉각 조치가 필요한 심각한 윤리적·법적 문제이며, 2차 협력업체라도 마찬가지이다. 프로젝트 관리자는 조달팀과 경영진에 알리고, 조사를 시작하며, 대체 공급업체를 검토해야 한다. 교훈 정리 때까지 기다리는 것(A)은 조치를 늦추고, 1차 공급업체에 맡기는 것(B)은 책임을 회피하며, 직접 계약 상대가 아니라는 이유로 계속하는 것(C)은 위반을 무시하는 것이다.
2201 | A project team proposes using biodegradable packaging for the project's product deliverables. Testing reveals the biodegradable option degrades product protection by 10%. How should the PM approach this trade-off? | Delay the decision until more testing is available. | Evaluate whether the 10% degradation is within acceptable limits for the product type, explore hybrid packaging solutions, and involve quality and sustainability teams in the decision. | Use biodegradable packaging regardless of protection impact. | Choose conventional packaging since product protection is paramount. |  | B | The correct answer is B. The biodegradable packaging improves sustainability but reduces protection by 10%, so the trade-off needs evaluation. The project manager should check whether that reduction is acceptable for the product, explore hybrid packaging solutions, and involve quality assurance. Delaying for more testing (A) postpones a decision that can be analyzed now, and always choosing either the biodegradable (C) or conventional option (D) ignores the trade-off. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | General | General PM Principles | Process | Plan and Optimize Quality | Governance | Executing | Embed Quality | Direct and Manage Project Work | Sustainability | 생분해성 포장이 제품 보호를 10% 저하시킬 때 PM은 무엇을 해야 하는가? | 더 많은 테스트가 가능할 때까지 결정을 지연한다 | 10% 저하가 제품 유형에 허용 범위 내인지 평가하고, 하이브리드 포장을 탐색하며, 비용-편익 분석을 실시한다 | 보호 영향에 관계없이 생분해성 포장을 사용한다 | 제품 보호가 최우선이므로 기존 포장을 선택한다 |  | B | 정답은 B이다. 생분해 포장은 지속가능성을 높이지만 보호 성능을 10% 떨어뜨리므로 트레이드오프를 평가해야 한다. 프로젝트 관리자는 그 저하가 해당 제품에 허용 가능한 수준인지 확인하고, 혼합형 포장 방안을 찾아보며, 품질보증팀을 참여시켜야 한다. 추가 테스트를 이유로 결정을 미루는 것(A)은 지금 분석할 수 있는 결정을 늦추고, 생분해(C)나 기존 포장(D) 중 하나를 무조건 고르는 것은 트레이드오프를 무시하는 것이다.
2202 | A project manager notices that remote team members have significantly lower carbon footprints compared to office-based team members. How can this insight be leveraged? | Include remote work policies as a sustainability strategy, track carbon savings from reduced commuting, and use the data to support organizational sustainability reporting. | Only allow remote work for team members with long commutes. | Ignore the data since work arrangements are not a PM responsibility. | Force all team members to work remotely. |  | A | The correct answer is A. The lower carbon footprint of remote workers is a measurable sustainability benefit. Including remote work in the sustainability strategy, tracking carbon savings from reduced commuting, and using the data in organizational sustainability reporting captures that value. Restricting remote work to long commutes (B) is arbitrary, ignoring the data (C) misses the insight, and forcing everyone to work remotely (D) ignores other needs. | People | Engage & Support Virtual Teams | Team | Create a Collaborative Project Team Environment | Agile | Agile General Practices | People | Lead the Project Team | Resources | Executing | Integrate Sustainability | Develop Team | Sustainability | 프로젝트 관리자는 원격 근무 팀원들의 탄소 발자국이 사무실 근무 팀원보다 훨씬 적다는 것을 알게 되었다. 이 통찰을 어떻게 활용할 수 있는가? | 원격 근무 정책을 지속가능성 전략에 포함하고, 통근 감소에 따른 탄소 절감량을 추적하며, 이 데이터를 조직의 지속가능성 보고에 활용한다. | 긴 통근 팀원에게만 원격 근무를 허용한다 | 근무 형태는 PM 책임이 아니므로 데이터를 무시한다 | 모든 팀원에게 원격 근무를 강제한다 |  | A | 정답은 A이다. 원격 근무자의 낮은 탄소 발자국은 측정 가능한 지속가능성 효익이다. 원격 근무를 지속가능성 전략에 포함하고, 통근 감소에 따른 탄소 절감량을 추적하며, 이 데이터를 조직의 지속가능성 보고에 활용하면 그 가치를 살릴 수 있다. 통근 거리가 긴 사람에게만 허용하는 것(B)은 근거가 없고, 데이터를 무시하는 것(C)은 통찰을 놓치며, 모두에게 원격 근무를 강요하는 것(D)은 다른 요구를 무시하는 것이다.
2203 | An organization wants to embed sustainability into its project management methodology. What is the MOST effective approach? | Integrate sustainability considerations into every phase of the project lifecycle—from business case and charter to planning, execution, monitoring, and closure. | Add sustainability training to the annual PM conference. | Hire a Chief Sustainability Officer and make them responsible. | Create a separate sustainability checklist that PMs complete at project end. |  | A | The correct answer is A. Embedding sustainability means making it part of how every project is run, from the business case and charter through planning, execution, monitoring, and closure. Annual training (B) raises awareness but does not change the methodology, assigning responsibility to a single executive (C) keeps it outside the project, and an end-of-project checklist (D) makes it an afterthought. | Business Environment | Support Organizational Change | Project Work | Enable Change to Achieve the Envisioned Future State | General | General PM Principles | Business Environment | Support Organizational Change | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 조직이 프로젝트 관리 방법론에 지속가능성을 내재화하고자 한다. 가장 효과적인 접근법은? | 비즈니스 케이스부터 종료까지 프로젝트 수명주기의 모든 단계에 지속가능성 고려사항을 통합한다 | 연례 PM 컨퍼런스에 지속가능성 교육을 추가한다 | 최고 지속가능성 책임자(CSO)를 고용하여 책임을 맡긴다 | PM이 프로젝트 종료 시 완료하는 별도의 지속가능성 체크리스트를 만든다 |  | A | 정답은 A이다. 지속가능성을 내재화한다는 것은 비즈니스 케이스와 헌장부터 계획, 실행, 감시, 종료까지 모든 프로젝트 운영 방식의 일부로 만드는 것이다. 연례 교육(B)은 인식을 높이지만 방법론을 바꾸지 못하고, 최고지속가능경영책임자 한 사람에게 맡기는 것(C)은 지속가능성을 프로젝트 밖에 두며, 종료 시점의 체크리스트(D)는 사후 고려에 그친다.
2204 | A project uses water-intensive processes. The project is located in a region experiencing drought. What should the PM include in the risk register? | Water risk is an operational concern, not a project risk. | Only schedule risk from potential water restrictions. | Water scarcity risk including regulatory restrictions, community opposition, reputational impact, increased water costs, and alternative water-sourcing strategies. | Only financial risk from increased water costs. |  | C | The correct answer is C. In a drought region, a water-intensive project faces water scarcity risk with several dimensions: regulatory restrictions, community opposition, reputational damage, higher water costs, and the need for alternative sources. Treating it as an operational issue (A), or recording only the schedule (B) or financial (D) dimension, understates the exposure. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Integrate Sustainability | Identify Risks | Sustainability | 프로젝트가 물 집약적 공정을 사용한다. 프로젝트가 가뭄을 겪고 있는 지역에 위치한다. PM이 리스크 등록부에 무엇을 포함해야 하는가? | 물 리스크는 운영상 관심사이지 프로젝트 리스크가 아니다 | 잠재적 물 사용 제한으로 인한 일정 리스크만 | 규제 제한, 지역사회 반대, 평판 영향, 보험 등을 포함하는 물 부족 리스크 | 물 비용 증가로 인한 재무 리스크만 |  | C | 정답은 C이다. 가뭄 지역에서 물을 많이 쓰는 프로젝트는 여러 측면의 물 부족 리스크를 안고 있다. 규제상 제한, 지역사회의 반대, 평판 손상, 물값 상승, 대체 수원의 필요성이 그것이다. 운영상의 문제로 보는 것(A)이나 일정(B) 또는 재무(D) 측면만 기록하는 것은 노출된 리스크를 과소평가하는 것이다.
2205 | A project manager is developing a scope statement for a wind farm project. Which sustainability consideration should be included that goes beyond traditional scope management? | Only the land acquisition requirements. | The project's net environmental impact including bird migration patterns, noise impact on nearby communities, visual landscape impact, and decommissioning plans for end-of-life turbines. | Only the energy output projections. | Only the number and capacity of wind turbines. |  | B | The correct answer is B. Sustainable scope management for a wind farm goes beyond energy output to include the project's net environmental and social impact: bird migration, noise for nearby communities, visual landscape impact, and decommissioning at end of life. Land acquisition (A), energy projections (C), and turbine numbers (D) are traditional scope elements that leave out these sustainability considerations. | Process | Plan & Manage Scope | Delivery | Focus on Value | Predictive | Traditional Plan-Driven | Process | Develop and Manage Scope | Scope | Planning | Integrate Sustainability | Define Scope | Sustainability | PM이 풍력 발전 프로젝트의 범위 기술서를 개발 중이다. 어떤 지속가능성 고려사항이 범위에 포함되어야 하는가? | 토지 취득 요구사항만 | 조류 이동 패턴, 인근 지역사회 소음 영향 등을 포함하는 프로젝트의 순 환경 영향 | 에너지 출력 전망만 | 풍력 터빈의 수와 용량만 |  | B | 정답은 B이다. 풍력 단지의 지속가능한 범위 관리는 발전량을 넘어, 철새 이동 경로, 인근 주민에 대한 소음, 경관 영향, 수명 종료 시 해체 계획 등 프로젝트의 순(純) 환경·사회 영향까지 포함한다. 토지 확보 요건(A), 발전량 예측(C), 터빈 수와 용량(D)은 전통적인 범위 요소로, 이런 지속가능성 고려 사항을 빠뜨린다.
2206 | A project team wants to implement a 'sustainability retrospective' at the end of each project phase. What topics should be covered? | Sustainability retrospectives are unnecessary—standard retrospectives are sufficient. | Only review whether the project stayed within the sustainability budget. | Review environmental performance metrics, identify sustainability lessons learned, recognize green achievements, and plan sustainability improvements for the next phase. | Only discuss what went wrong with sustainability efforts. |  | C | The correct answer is C. A sustainability retrospective should look at the full picture: environmental performance metrics, sustainability lessons learned, recognition of green achievements, and improvement plans for the next phase. Saying standard retrospectives are enough (A) risks overlooking sustainability, reviewing only the budget (B) is too narrow, and discussing only what went wrong (D) misses successes worth repeating. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Monitoring & Controlling | Integrate Sustainability | Monitor and Control Project Performance | Sustainability | 프로젝트 팀이 각 프로젝트 단계 종료 시 '지속가능성 회고'를 시행하고자 한다. 어떤 주제를 다루어야 하는가? | 지속가능성 회고는 불필요하다—표준 회고로 충분하다 | 프로젝트가 지속가능성 예산 내에 있었는지만 검토한다 | 환경 성과 지표 검토, 지속가능성 교훈 식별, 녹색 성과 인정, 개선 계획 수립 | 지속가능성 노력에서 잘못된 점만 논의한다 |  | C | 정답은 C이다. 지속가능성 회고는 전체 그림을 봐야 한다. 환경 성과 지표, 지속가능성 교훈, 친환경 성과에 대한 인정, 다음 단계의 개선 계획을 다룬다. 일반 회고로 충분하다고 하는 것(A)은 지속가능성을 놓칠 위험이 있고, 예산만 검토하는 것(B)은 너무 좁으며, 잘못된 점만 논의하는 것(D)은 반복할 만한 성공을 놓친다.
2207 | A project budget includes a 5% sustainability premium for eco-friendly materials. During execution, budget pressure mounts and the sponsor suggests eliminating this premium. What approach should the PM take? | Protect the sustainability budget at all costs, even if other deliverables are cut. | Present a value analysis showing the long-term benefits of the sustainability investment, explore creative cost optimization in other areas, and propose alternatives that maintain sustainability commitments. | Accept the cut but don't update the sustainability plan. | Immediately eliminate the sustainability premium. |  | B | The correct answer is B. The project manager should advocate for the sustainability investment with value-based arguments, showing its long-term benefits, while also looking for savings elsewhere, so the sponsor can make an informed decision. Protecting it at all costs (A) ignores real budget constraints, accepting the cut without updating the plan (C) leaves the plan inaccurate, and eliminating it immediately (D) skips the analysis. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | General | Cost & Resource Management | Process | Plan and Manage Finance | Finance | Monitoring & Controlling | Integrate Sustainability | Control Costs | Sustainability | 프로젝트 예산에 친환경 자재를 위한 5% 지속가능성 프리미엄이 포함되어 있다. 실행 중 예산 압박이 가중된다. PM은 무엇을 해야 하는가? | 다른 인도물이 삭감되더라도 지속가능성 예산을 어떤 대가를 치르더라도 보호한다 | 지속가능성 투자의 장기적 이점을 보여주는 가치 분석을 제시하고, 창의적 대안을 탐색한다 | 삭감을 수용하되 지속가능성 계획은 업데이트하지 않는다 | 지속가능성 프리미엄을 즉시 제거한다 |  | B | 정답은 B이다. 프로젝트 관리자는 지속가능성 투자의 장기 효익을 보여 주는 가치 기반 논거로 이를 옹호하면서, 다른 영역에서 절감할 방안도 찾아 스폰서가 근거 있는 결정을 내리게 해야 한다. 무슨 수를 써서라도 지키는 것(A)은 실제 예산 제약을 무시하고, 계획을 갱신하지 않고 삭감을 받아들이는 것(C)은 계획을 부정확하게 만들며, 즉시 없애는 것(D)은 분석을 건너뛴다.
2208 | An organization requires all new projects to submit a Sustainability Impact Assessment (SIA) as part of the project initiation process. What should this assessment include? | Only the estimated carbon emissions of the project. | A statement that the project supports the organization's sustainability goals. | Assessment of the project's potential environmental, social, and economic impacts, identification of sustainability risks and opportunities, proposed mitigation measures, and sustainability KPIs. | Only a list of environmental regulations that apply to the project. |  | C | The correct answer is C. A Sustainability Impact Assessment should cover all three dimensions: potential environmental, social, and economic impacts, the sustainability risks and opportunities, proposed mitigations, and measurable KPIs. Carbon emissions alone (A) cover one environmental measure, a general statement of support (B) has no substance, and a list of regulations (D) does not assess impacts. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | General | General PM Principles | Business Environment | Plan and Manage Compliance | Governance | Initiating | Integrate Sustainability | Develop Project Charter | Sustainability | 조직이 모든 새 프로젝트에 지속가능성 영향 평가(SIA)를 프로젝트 착수의 일부로 제출하도록 요구한다. SIA에 무엇이 포함되어야 하는가? | 프로젝트의 예상 탄소 배출량만 | 프로젝트가 조직의 지속가능성 목표를 지원한다는 성명 | 프로젝트의 잠재적 환경, 사회, 경제적 영향 평가, 리스크 및 기회 식별, 완화 제안, 측정 가능한 KPI 설정 | 프로젝트에 적용되는 환경 규정 목록만 |  | C | 정답은 C이다. 지속가능성 영향 평가는 세 가지 측면을 모두 다뤄야 한다. 잠재적인 환경·사회·경제 영향, 지속가능성 리스크와 기회, 제안하는 완화 방안, 측정 가능한 KPI가 포함되어야 한다. 탄소 배출량만(A)은 환경 지표 하나에 불과하고, 지지한다는 선언(B)은 실질이 없으며, 규정 목록(D)은 영향을 평가하지 않는다.
2209 | A project team is using lean principles to reduce waste in a manufacturing project. They identify that 15% of raw materials are wasted during production. The team proposes investing in precision equipment that reduces waste to 3% but costs 20% more. What should the PM do? | Reject the investment since it increases costs. | Approve the investment immediately without financial analysis. | Implement partial waste reduction measures only. | Calculate the total cost of ownership including material savings, waste disposal cost reduction, environmental compliance benefits, and present a comprehensive business case. |  | D | The correct answer is D. The equipment costs 20% more but cuts waste from 15% to 3%, so the decision needs a total cost of ownership view that includes material savings, lower disposal costs, and environmental compliance benefits, presented as a business case. Rejecting it on upfront cost (A), approving it without analysis (B), or settling for partial measures without evaluation (C) skips the comparison that supports a sound decision. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Agile | Lean | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Sustainability | 프로젝트 팀이 린(lean) 원칙으로 제조 프로젝트의 낭비를 줄이고 있다. 팀은 생산 과정에서 원자재의 15%가 버려진다는 것을 확인했다. 팀은 낭비를 3%로 줄여 주지만 비용이 20% 더 드는 정밀 장비에 투자하자고 제안한다. 프로젝트 관리자는 무엇을 해야 하는가? | 비용이 증가하므로 투자를 거부한다 | 재무 분석 없이 즉시 투자를 승인한다 | 부분적 폐기물 감소 조치만 시행한다 | 자재 절감, 폐기물 처리비 절감, 환경 규정 준수 효익을 포함한 총소유비용을 계산하고, 종합적인 비즈니스 케이스를 제시한다. |  | D | 정답은 D이다. 장비는 20% 더 비싸지만 폐기율을 15%에서 3%로 낮추므로, 자재 절감, 폐기물 처리비 감소, 환경 규정 준수 효익을 포함한 총소유비용 관점에서 판단하고 이를 비즈니스 케이스로 제시해야 한다. 초기 비용만 보고 거절하는 것(A), 분석 없이 승인하는 것(B), 평가 없이 부분 조치만 하는 것(C)은 올바른 결정을 뒷받침할 비교를 건너뛴다.
2210 | A project manager is leading a smart city initiative. Multiple projects within the program have overlapping sustainability goals. How should sustainability be managed across the program? | Establish a program-level sustainability framework with shared KPIs, coordinate cross-project sustainability initiatives, and consolidate sustainability reporting for the program. | Assign sustainability to the largest project only. | Let each project manage sustainability independently. | Create a separate sustainability project within the program. |  | A | The correct answer is A. When several projects in a program share sustainability goals, managing them at program level avoids duplication and maximizes impact. A program-level framework with shared KPIs, coordinated cross-project initiatives, and consolidated reporting achieves this. Assigning it to the largest project (B) leaves others out, managing it independently (C) causes duplication and gaps, and a separate sustainability project (D) disconnects it from the work. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Planning | Adopt a Holistic View | Develop Project Management Plan | Sustainability | PM이 스마트 시티 이니셔티브를 이끌고 있다. 프로그램 내 여러 프로젝트가 중복되는 지속가능성 목표를 가지고 있다. PM은 무엇을 해야 하는가? | 공유 KPI가 있는 프로그램 수준 지속가능성 프레임워크를 수립하고, 프로젝트 간 지속가능성 이니셔티브를 조정한다 | 가장 큰 프로젝트에만 지속가능성을 할당한다 | 각 프로젝트가 독립적으로 지속가능성을 관리하도록 한다 | 프로그램 내에 별도의 지속가능성 프로젝트를 만든다 |  | A | 정답은 A이다. 프로그램 안의 여러 프로젝트가 지속가능성 목표를 공유한다면, 프로그램 차원에서 관리해야 중복을 피하고 효과를 극대화할 수 있다. 공통 KPI를 갖춘 프로그램 수준의 체계, 프로젝트 간 지속가능성 활동 조율, 통합 보고가 이를 가능하게 한다. 가장 큰 프로젝트에만 맡기는 것(B)은 나머지를 배제하고, 각자 관리하는 것(C)은 중복과 공백을 낳으며, 별도 지속가능성 프로젝트를 만드는 것(D)은 실제 작업과 단절시킨다.
2211 | A project's life cycle assessment (LCA) reveals that the operating phase accounts for 80% of the product's total environmental impact. The project team focused sustainability efforts primarily on the construction phase. What should the PM do? | Shift sustainability focus to include operational efficiency measures, design for lower operational impact, and establish sustainability monitoring protocols for the operating phase. | Complete the project as planned and recommend operational changes separately. | Accept the finding and document it for lessons learned. | The operating phase is outside the project's responsibility. |  | A | The correct answer is A. The lifecycle assessment shows that 80% of the impact occurs during operation, so focusing only on construction misses most of it. The project should broaden its sustainability focus to operational efficiency, design for lower operating impact, and set up monitoring for the operating phase. Finishing as planned (B) or only documenting the finding (C) ignores the evidence, and calling operations outside the project's responsibility (D) overlooks that design decisions drive operating impact. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Hybrid | Predictive-Agile Blend | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트의 전과정평가(LCA) 결과, 제품의 전체 환경 영향 중 80%가 운영 단계에서 발생하는 것으로 나타났다. 그러나 프로젝트 팀은 지속가능성 노력을 주로 건설 단계에 집중해 왔다. 프로젝트 관리자는 무엇을 해야 하는가? | 운영 효율 대책을 포함하도록 지속가능성 초점을 넓히고, 운영 중 영향이 적도록 설계하며, 운영 단계의 지속가능성 모니터링 프로토콜을 수립한다. | 계획대로 프로젝트를 완료하고 별도로 운영 변경을 권고한다 | 결과를 수용하고 교훈으로 문서화한다 | 운영 단계는 프로젝트 책임 범위 밖이다 |  | A | 정답은 A이다. 전과정평가 결과 영향의 80%가 운영 단계에서 생기므로, 건설 단계에만 집중하면 대부분을 놓치게 된다. 지속가능성 초점을 운영 효율로 넓히고, 운영 중 영향이 적도록 설계하며, 운영 단계 모니터링을 마련해야 한다. 계획대로 마무리하는 것(B)이나 결과를 기록만 하는 것(C)은 근거를 무시하고, 운영은 프로젝트의 책임 밖이라는 것(D)은 설계 결정이 운영 영향을 좌우한다는 점을 간과한다.
2212 | A project team is developing a mobile application. How can the 'Integrate Sustainability' principle be applied to a purely digital product? | Optimize the app for energy efficiency (battery usage), minimize data transfer, design for device longevity (support older devices), and ensure digital accessibility for all user groups. | Sustainability doesn't apply to mobile applications. | Only use green-certified hosting providers. | Include a sustainability page in the app's documentation. |  | A | The correct answer is A. Even a purely digital product has environmental and social impacts. Optimizing battery and energy use, minimizing data transfer, supporting older devices to extend their life, and ensuring accessibility apply the sustainability principle to an app. Saying sustainability does not apply (B) is incorrect, green hosting alone (C) addresses only one aspect, and a documentation page (D) does not change the product. | Process | Plan & Manage Quality | Delivery | Build Quality into Processes and Deliverables | Agile | Agile General Practices | Process | Plan and Optimize Quality | Governance | Planning | Integrate Sustainability | Develop Project Management Plan | Sustainability | 프로젝트 팀이 모바일 앱을 개발 중이다. 순수 디지털 프로젝트에 '지속가능성 통합' 원칙을 어떻게 적용할 수 있는가? | 에너지 효율성(배터리 사용)을 위해 앱을 최적화하고, 데이터 전송을 최소화하며, 기기 수명을 위해 설계하고, 접근성을 보장한다 | 지속가능성은 모바일 앱에 적용되지 않는다 | 녹색 인증 호스팅 제공자만 사용한다 | 앱 문서에 지속가능성 페이지를 포함한다 |  | A | 정답은 A이다. 순수 디지털 제품에도 환경적·사회적 영향이 있다. 배터리와 에너지 사용을 최적화하고, 데이터 전송을 줄이며, 오래된 기기를 지원해 기기 수명을 늘리고, 접근성을 보장하면 앱에 지속가능성 원칙을 적용할 수 있다. 지속가능성이 해당되지 않는다는 것(B)은 틀렸고, 친환경 호스팅만 쓰는 것(C)은 한 측면만 다루며, 문서에 지속가능성 페이지를 넣는 것(D)은 제품 자체를 바꾸지 못한다.
2213 | A project manager is asked to quantify the social return on investment (SROI) of a community development project. What should be included in the SROI calculation? | Only the number of beneficiaries. | The project's NPV calculated with standard discount rates. | Only the financial investment in the project. | Monetary value of social outcomes (jobs created, health improvements, education access, community well-being, reduced inequality) relative to the investment made. |  | D | The correct answer is D. Social return on investment compares the monetized value of social outcomes, such as jobs created, health improvements, education access, community well-being, and reduced inequality, with the investment made. The number of beneficiaries (A) is an output, not a value, a standard NPV (B) captures only financial returns, and the investment amount alone (C) is just one side of the ratio. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Monitoring & Controlling | Focus on Value | Monitor and Control Project Performance | Sustainability | PM이 커뮤니티 개발 프로젝트의 사회적 투자수익률(SROI)을 정량화하도록 요청받았다. SROI에 무엇이 포함되어야 하는가? | 수혜자 수만 | 표준 할인율로 계산된 프로젝트의 순현재가치(NPV) | 프로젝트의 재무 투자만 | 일자리 창출, 건강 개선, 교육 접근, 커뮤니티 안녕을 포함하는 사회적 성과의 금전적 가치 |  | D | 정답은 D이다. 사회적 투자수익률(SROI)은 일자리 창출, 건강 개선, 교육 접근성, 지역사회 복지, 불평등 감소 같은 사회적 성과를 화폐 가치로 환산해 투자액과 비교한다. 수혜자 수(A)는 가치가 아니라 산출물이고, 표준 NPV(B)는 재무 수익만 반영하며, 투자액만으로는(C) 비율의 한쪽에 불과하다.
2214 | A project team identifies an opportunity to reuse 40% of materials from a decommissioned facility for the new project. This would reduce costs by 12% and waste by 60%. What risk should the PM also consider? | Only the reputational risk of using 'secondhand' materials. | Quality and safety risks of reused materials, including structural integrity, contamination, regulatory compliance for reused components, and compatibility with new specifications. | Only the schedule risk of sorting and preparing reused materials. | No risks—reuse is always beneficial. |  | B | The correct answer is B. Reusing materials brings sustainability and cost benefits, but it also carries quality and safety risks: structural integrity, contamination, regulatory compliance for reused components, and compatibility with new specifications. Reputational (A) and schedule (C) risks are narrower concerns, and assuming reuse carries no risk (D) is unrealistic. | Process | Assess & Manage Risks | Uncertainty | Optimize Risk Responses | Predictive | Traditional Plan-Driven | Business Environment | Plan and Manage Risk | Risk | Planning | Embed Quality | Identify Risks | Sustainability | 프로젝트 팀이 해체된 시설의 자재 40%를 새 프로젝트에 재사용할 기회를 발견했다. 이렇게 하면 원가는 12%, 폐기물은 60% 줄어든다. 프로젝트 관리자가 함께 고려해야 할 리스크는 무엇인가? | 중고 자재 사용의 평판 리스크만 | 구조적 건전성, 오염, 재사용 부재의 규제 준수, 새 사양과의 호환성 등 재사용 자재의 품질·안전 리스크 | 재사용 자재 분류 및 준비의 일정 리스크만 | 리스크 없음—재사용은 항상 유익하다 |  | B | 정답은 B이다. 자재 재사용은 지속가능성과 원가 측면의 효익이 있지만, 구조적 건전성, 오염, 재사용 부재의 규정 준수, 새 사양과의 호환성 같은 품질·안전 리스크도 따른다. 평판(A)과 일정(C) 리스크는 더 좁은 우려이고, 재사용에 리스크가 없다고 보는 것(D)은 비현실적이다.
2215 | A project governance board wants to include sustainability criteria in the project go/no-go decision framework. What criterion is MOST important to add? | The percentage of recycled materials planned for use. | The project's net sustainability impact assessment—measuring expected environmental, social, and economic effects against organizational sustainability targets and thresholds. | Whether the project team has sustainability certifications. | Whether the project uses renewable energy. |  | B | The correct answer is B. A go/no-go decision needs a comprehensive view, so the most important sustainability criterion is a net impact assessment that measures the expected environmental, social, and economic effects against the organization's sustainability targets. The percentage of recycled materials (A) and use of renewable energy (D) are single measures, and team certifications (C) do not indicate the project's impact. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Initiating | Integrate Sustainability | Develop Project Charter | Sustainability | 프로젝트 거버넌스 위원회가 프로젝트 진행/중단(Go/No-go) 의사결정 프레임워크에 지속가능성 기준을 포함하고자 한다. 어떤 기준이 가장 효과적인가? | 재활용 자재 사용 비율 | 예상 환경, 사회, 경제적 영향을 측정하는 프로젝트의 순 지속가능성 영향 평가 | 프로젝트 팀의 지속가능성 인증 보유 여부 | 프로젝트의 재생 에너지 사용 여부 |  | B | 정답은 B이다. 진행/중단 결정에는 포괄적인 관점이 필요하므로, 가장 중요한 지속가능성 기준은 조직의 지속가능성 목표에 비춰 예상되는 환경·사회·경제적 영향을 측정하는 순(純) 영향 평가이다. 재활용 자재 비율(A)과 재생에너지 사용 여부(D)는 단일 지표이고, 팀의 자격증 보유 여부(C)는 프로젝트의 영향을 보여 주지 않는다.
2216 | During a project, new environmental regulations are enacted that require the project's deliverables to meet stricter emission standards. The project is 45% complete. What is the MOST appropriate action? | Complete the project under the original standards and claim grandfathering. | Conduct a gap analysis between current deliverables and new standards, raise a change request for necessary modifications, and update the project plan including potentially reworking completed items. | Halt the project until legal provides a definitive interpretation. | Apply the new standards only to the remaining 55% of work. |  | B | The correct answer is B. New emission standards apply to the deliverables, so the project manager should analyze the gap between current deliverables and the new standards, raise a change request for the necessary modifications, and update the plan, including possible rework of completed items. Claiming grandfathering (A) assumes an exemption without basis, halting the project (C) is excessive, and applying the standards only to remaining work (D) may leave completed deliverables non-compliant. | Business Environment | Plan & Manage Project Compliance | Project Work | Be a Diligent, Respectful, and Caring Steward | Predictive | Baseline & Change Control | Business Environment | Plan and Manage Compliance | Governance | Monitoring & Controlling | Be an Accountable Leader | Monitor and Control Project Performance | Sustainability | 프로젝트 진행 중에 프로젝트 인도물이 더 엄격한 배출 기준을 충족해야 한다는 새 환경 규제가 시행되었다. 프로젝트는 45% 완료된 상태다. 가장 적절한 조치는 무엇인가? | 원래 기준으로 프로젝트를 완료하고 기존권(grandfathering)을 주장한다 | 현재 인도물과 새 기준 간 격차 분석을 수행하고, 필요한 수정에 대한 변경 요청을 제기하며, 완료된 항목의 재작업 가능성까지 포함해 프로젝트 계획을 갱신한다. | 법무팀이 확정적 해석을 제공할 때까지 프로젝트를 중단한다 | 남은 55% 작업에만 새 기준을 적용한다 |  | B | 정답은 B이다. 새 배출 기준이 인도물에 적용되므로, 프로젝트 관리자는 현재 인도물과 새 기준의 격차를 분석하고, 필요한 수정에 대한 변경 요청을 제기하며, 완료된 항목의 재작업 가능성까지 포함해 계획을 갱신해야 한다. 기존 기준 적용(유예)을 주장하는 것(A)은 근거 없이 예외를 가정하고, 프로젝트를 중단하는 것(C)은 과하며, 남은 작업에만 새 기준을 적용하는 것(D)은 완료된 인도물이 규정에 맞지 않게 남을 수 있다.
2217 | A project team is developing sustainability training for project managers in the organization. What topic should be given the HIGHEST priority? | How to write sustainability reports. | How to calculate carbon offsets. | How to obtain green certifications for the organization. | How to integrate sustainability thinking into everyday project decisions—from scope definition and procurement to risk management and stakeholder engagement. |  | D | The correct answer is D. Sustainability becomes real when it shapes everyday decisions, so the highest priority is teaching project managers to integrate sustainability thinking into scope, procurement, risk, stakeholder engagement, and other processes. Writing reports (A), calculating offsets (B), and obtaining certifications (C) are useful but specialized skills that do not change how projects are run day to day. | People | Ensure Team Members Are Adequately Trained | Team | Create a Collaborative Project Team Environment | General | General PM Principles | People | Help Ensure Knowledge Transfer | Resources | Executing | Integrate Sustainability | Acquire Resources | Sustainability | 프로젝트 팀이 조직의 프로젝트 관리자를 위한 지속가능성 교육을 개발 중이다. 가장 높은 우선순위를 받아야 하는 주제는? | 지속가능성 보고서 작성법 | 탄소 상쇄 계산법 | 조직을 위한 녹색 인증 획득법 | 범위 정의부터 조달까지 일상적 프로젝트 결정에 지속가능성 사고를 통합하는 방법 |  | D | 정답은 D이다. 지속가능성은 일상적인 결정에 반영될 때 실질이 생기므로, 가장 우선할 주제는 범위, 조달, 리스크, 이해관계자 참여 등 모든 프로세스에 지속가능성 사고를 녹이는 방법이다. 보고서 작성(A), 탄소 상쇄 계산(B), 인증 취득(C)은 유용하지만 전문적인 기술이며, 프로젝트를 일상적으로 운영하는 방식을 바꾸지는 못한다.
2218 | A project manager is leading a data center construction project. The client wants the data center to achieve a Power Usage Effectiveness (PUE) of 1.2 or lower. During design, the team realizes this requires innovative cooling systems that add significant cost. What should the PM recommend? | Present a lifecycle cost analysis showing that lower PUE reduces long-term energy costs, potentially offsetting the upfront investment, and explore different innovative cooling options with varying cost-benefit profiles. | Tell the client that PUE 1.2 is technologically impossible. | Accept the additional cost without analysis. | Lower the PUE target to reduce costs. |  | A | The correct answer is A. A lower PUE means lower energy use for decades of operation, which may offset the higher upfront cost of innovative cooling. A lifecycle cost analysis that shows this, together with alternative cooling options at different cost-benefit levels, gives the client a sound basis to decide. Calling the target impossible (B) is inaccurate, accepting the cost without analysis (C) skips due diligence, and lowering the target (D) gives up the client's goal without exploring options. | Process | Plan & Manage Budget & Resources | Planning | Be a Diligent, Respectful, and Caring Steward | Predictive | Traditional Plan-Driven | Process | Plan and Manage Finance | Finance | Planning | Focus on Value | Determine Budget | Sustainability | 프로젝트 관리자가 데이터센터 건설 프로젝트를 이끌고 있다. 고객은 데이터센터의 전력사용효율(PUE)이 1.2 이하가 되기를 원한다. 설계 중에 팀은 이를 위해 상당한 비용이 추가되는 혁신적 냉각 시스템이 필요하다는 것을 깨달았다. 프로젝트 관리자는 무엇을 권해야 하는가? | 낮은 PUE가 장기 에너지 비용을 줄여 초기 투자를 상쇄할 수 있음을 보여 주는 생애주기 원가 분석을 제시하고, 비용 대비 효익이 서로 다른 여러 혁신 냉각 방안을 검토한다. | 고객에게 PUE 1.2는 기술적으로 불가능하다고 말한다 | 분석 없이 추가 비용을 수용한다 | 비용 절감을 위해 PUE 목표를 낮춘다 |  | A | 정답은 A이다. 낮은 PUE는 수십 년 운영 기간 동안 에너지 사용을 줄여 혁신 냉각 시스템의 높은 초기 비용을 상쇄할 수 있다. 이를 보여 주는 생애주기 원가 분석과 함께 비용 대비 효익이 서로 다른 냉각 대안을 제시하면, 고객이 판단할 근거가 생긴다. 목표 달성이 불가능하다고 말하는 것(B)은 사실과 다르고, 분석 없이 비용을 받아들이는 것(C)은 검토를 건너뛰며, 목표를 낮추는 것(D)은 선택지를 찾아보지 않고 고객의 목표를 포기하는 것이다.
2219 | A project team completes a sustainable product that significantly exceeds environmental performance targets. The PM wants to leverage this success. What is the MOST strategic action? | Document the sustainability best practices, share them across the organization's project portfolio, and use the results to strengthen future project business cases for sustainability investments. | Move on to the next project without documenting the achievement. | Request a budget increase for the next project based on this success. | Publish the results on social media immediately. |  | A | Leveraging sustainability success strategically means documenting best practices for organizational learning, sharing across the portfolio, and using evidence to support future sustainability investments. | Business Environment | Evaluate & Deliver Project Benefits & Value | Delivery | Focus on Value | General | General PM Principles | Business Environment | Define and Establish Governance | Governance | Closing | Integrate Sustainability | Close Project or Phase | Sustainability | 프로젝트 팀이 환경 성과 목표를 크게 초과하는 지속가능한 제품을 완성했다. PM이 이 성공을 활용하고자 한다. PM은 무엇을 해야 하는가? | 지속가능성 모범 사례를 문서화하고, 조직의 프로젝트 포트폴리오 전반에 공유하며, 향후 지속가능성 투자를 지원하는 근거로 사용한다 | 성과를 문서화하지 않고 다음 프로젝트로 넘어간다 | 이 성공을 기반으로 다음 프로젝트의 예산 증가를 요청한다 | 소셜 미디어에 즉시 결과를 공개한다 |  | A | 지속가능성 성공을 전략적으로 활용하는 것은 조직 학습을 위해 모범 사례를 문서화하고, 포트폴리오 전반에 공유하며, 미래 지속가능성 투자를 지원하는 근거로 사용하는 것을 의미한다. 미문서화(B)는 교훈을 낭비한다. 예산 증가 요청(C)은 직접적 연결이 부족하다. 즉시 공개(D)는 조직 승인 없이 성급하다.
2220 | A project manager is overseeing an agile project with 80 user stories divided into four iterations. Each user story is valued at US$75. At the end of the second iteration, the actual expenditure is US$2,800 and 35 user stories have been completed. Which statement accurately describes the project status? | The project is over budget and behind schedule. | The project is under budget and ahead of schedule. | The project is on budget and on schedule. | The project is over budget and ahead of schedule. |  | A | BAC = 80 × $75 = $6,000. Planned stories after 2 iterations = 40. PV = $3,000. EV = (6000/80)×35 = $2,625. AC = $2,800. CV = EV-AC = -$175 (over budget). SV = EV-PV = -$375 (behind schedule). The project is over budget and behind schedule. | [13 empty] | 프로젝트 관리자가 사용자 스토리 80개를 이터레이션 4회로 나눈 애자일 프로젝트를 관리하고 있다. 사용자 스토리 1개의 가치는 US$75이다. 두 번째 이터레이션이 끝난 시점에 실제 지출은 US$2,800이고 완료된 사용자 스토리는 35개이다. 프로젝트 상태를 정확하게 설명한 것은? | 프로젝트가 예산 초과이며 일정 지연 상태이다. | 프로젝트가 예산 절감이며 일정 선행 상태이다. | 프로젝트가 예산과 일정에 모두 부합한다. | 프로젝트가 예산 초과이며 일정 선행 상태이다. |  | A | BAC = 80 × $75 = $6,000. 2개 이터레이션 후 계획 스토리 = 40개. PV = $3,000. EV = (6000/80)×35 = $2,625. AC = $2,800. CV = EV - AC = -$175 (예산 초과). SV = EV - PV = -$375 (일정 지연). 따라서 프로젝트는 예산 초과이며 일정 지연 상태이다.
2221 | An agile team is working on a project containing 120 user stories spread across six iterations. Each user story has an estimated value of US$40. At the end of the third iteration, 65 user stories have been delivered with an actual cost of US$2,400. What is the current project status? | The project is under budget and ahead of schedule. | The project is over budget and behind schedule. | The project is under budget and behind schedule. | The project is on budget and ahead of schedule. |  | A | BAC = 120 × $40 = $4,800. Planned stories after 3 iterations = 60. PV = (4800/120)×60 = $2,400. EV = (4800/120)×65 = $2,600. AC = $2,400. CV = EV-AC = $200 (under budget). SV = EV-PV = $200 (ahead of schedule). The project is under budget and ahead of schedule. | [13 empty] | 한 애자일 팀이 6개의 이터레이션에 걸쳐 분배된 120개의 사용자 스토리로 구성된 프로젝트를 진행하고 있다. 각 사용자 스토리의 추정 가치는 미화 40달러이다. 세 번째 이터레이션 종료 시점에 65개의 사용자 스토리가 완료되었으며 실제 비용은 미화 2,400달러이다. 현재 프로젝트 상태는 무엇인가? | 프로젝트가 예산 절감이며 일정 선행 상태이다. | 프로젝트가 예산 초과이며 일정 지연 상태이다. | 프로젝트가 예산 절감이지만 일정 지연 상태이다. | 프로젝트가 예산에 부합하지만 일정 선행 상태이다. |  | A | BAC = 120 × $40 = $4,800. 3개 이터레이션 후 계획 스토리 = 60개. PV = (4800/120)×60 = $2,400. EV = (4800/120)×65 = $2,600. AC = $2,400. CV = EV - AC = $200 (예산 절감). SV = EV - PV = $200 (일정 선행). 따라서 프로젝트는 예산 절감이며 일정 선행 상태이다.
2222 | A project is being monitored using earned value analysis. The estimate to complete (ETC) work is assumed to be performed at the same cumulative CPI as incurred to date. Currently, EV = 200 person/days, PV = 220 person/days, AC = 250 person/days, and BAC = 400 person/days. What is the estimate at completion (EAC)? | 400 person/days | 450 person/days | 500 person/days | 550 person/days |  | C | When future work is expected at the same CPI: EAC = BAC/CPI. CPI = EV/AC = 200/250 = 0.80. EAC = 400/0.80 = 500 person/days. The project is experiencing cost overruns (CPI < 1), so the estimate at completion is higher than the original budget. | [13 empty] | 한 프로젝트가 획득가치 분석으로 모니터링되고 있다. 잔여 작업의 완료 추정치(ETC)는 현재까지 발생한 누적 CPI와 동일한 비율로 수행될 것으로 가정한다. 현재 EV = 200 인일, PV = 220 인일, AC = 250 인일, BAC = 400 인일이다. 완료 시점 추정치(EAC)는? | 400 인일 | 450 인일 | 500 인일 | 550 인일 |  | C | 향후 작업이 동일 CPI로 진행될 때: EAC = BAC / CPI. CPI = EV/AC = 200/250 = 0.80. EAC = 400/0.80 = 500 인일. CPI < 1이므로 비용 초과가 발생하고 있으며, 따라서 완료 시점 추정치는 원래 예산보다 높다.
2223 | A construction project has the following earned value metrics: BAC = $500,000, EV = $180,000, AC = $200,000, PV = $210,000. If future work is expected to be performed at the budgeted rate, what is the EAC? | $520,000 | $530,000 | $540,000 | $555,556 |  | A | When future work is at budgeted rate: EAC = AC + (BAC - EV) = $200,000 + ($500,000 - $180,000) = $200,000 + $320,000 = $520,000. This formula assumes the remaining work will be completed at the originally planned cost rate despite past variances. | [13 empty] | 한 건설 프로젝트의 획득가치 지표는 다음과 같다: BAC = $500,000, EV = $180,000, AC = $200,000, PV = $210,000. 향후 작업이 예산 비율대로 수행될 것으로 예상된다면 EAC는 얼마인가? | $520,000 | $530,000 | $540,000 | $555,556 |  | A | 향후 작업이 예산 비율대로 진행될 때: EAC = AC + (BAC - EV) = $200,000 + ($500,000 - $180,000) = $200,000 + $320,000 = $520,000. 이 공식은 과거 변동에도 불구하고 잔여 작업이 원래 계획된 비용 비율로 완료된다고 가정한다.
2224 | A project manager reviews the following data at month 6: PV = $300,000, EV = $270,000, AC = $290,000. What are the CPI and SPI, and what do they indicate? | CPI = 0.93, SPI = 0.90; the project is over budget and behind schedule. | CPI = 1.07, SPI = 0.90; the project is under budget and behind schedule. | CPI = 0.93, SPI = 1.11; the project is over budget and ahead of schedule. | CPI = 1.03, SPI = 0.93; the project is under budget and behind schedule. |  | A | CPI = EV/AC = 270,000/290,000 = 0.93 (< 1 = over budget). SPI = EV/PV = 270,000/300,000 = 0.90 (< 1 = behind schedule). Both indices are below 1, indicating the project is over budget and behind schedule. | [13 empty] | 한 프로젝트 관리자가 6개월 차에 다음 데이터를 검토한다: PV = $300,000, EV = $270,000, AC = $290,000. CPI와 SPI는 각각 얼마이며 무엇을 의미하는가? | CPI = 0.93, SPI = 0.90; 프로젝트가 예산 초과 및 일정 지연 상태이다. | CPI = 1.07, SPI = 0.90; 프로젝트가 예산 절감 및 일정 지연 상태이다. | CPI = 0.93, SPI = 1.11; 프로젝트가 예산 초과 및 일정 선행 상태이다. | CPI = 1.03, SPI = 0.93; 프로젝트가 예산 절감 및 일정 지연 상태이다. |  | A | CPI = EV/AC = 270,000/290,000 = 0.93 (< 1 = 예산 초과). SPI = EV/PV = 270,000/300,000 = 0.90 (< 1 = 일정 지연). 두 지표 모두 1보다 작으므로 프로젝트는 예산 초과 및 일정 지연 상태이다.
2225 | A project has a BAC of $600,000. At the current status point, EV = $240,000 and AC = $280,000. What is the To-Complete Performance Index (TCPI) based on BAC? | 0.89 | 1.00 | 1.06 | 1.13 |  | D | TCPI(BAC) = (BAC - EV) / (BAC - AC) = ($600,000 - $240,000) / ($600,000 - $280,000) = $360,000 / $320,000 = 1.125 ≈ 1.13. A TCPI > 1 means the team must perform better than planned to finish within the original budget. | [13 empty] | 한 프로젝트의 BAC가 $600,000이다. 현재 시점에서 EV = $240,000, AC = $280,000이다. BAC 기준 잔여 성과 지수(TCPI)는 얼마인가? | 0.89 | 1.00 | 1.06 | 1.13 |  | D | TCPI(BAC) = (BAC - EV) / (BAC - AC) = ($600,000 - $240,000) / ($600,000 - $280,000) = $360,000 / $320,000 = 1.125 ≈ 1.13. TCPI > 1은 원래 예산 내에 완료하려면 팀이 계획보다 더 좋은 성과를 내야 함을 의미한다.
2226 | At the end of quarter 2, a project shows: PV = $150,000, EV = $165,000, AC = $160,000. Which statement is correct? | Cost variance is $5,000 favorable and schedule variance is $15,000 favorable. | Cost variance is -$5,000 unfavorable and schedule variance is $15,000 favorable. | Cost variance is $10,000 favorable and schedule variance is -$15,000 unfavorable. | Cost variance is -$10,000 unfavorable and schedule variance is $5,000 favorable. |  | A | CV = EV - AC = $165,000 - $160,000 = $5,000 (positive = favorable/under budget). SV = EV - PV = $165,000 - $150,000 = $15,000 (positive = favorable/ahead of schedule). The project is performing well on both cost and schedule dimensions. | [13 empty] | 2분기 종료 시점에 한 프로젝트의 지표는 다음과 같다: PV = $150,000, EV = $165,000, AC = $160,000. 다음 중 옳은 설명은? | 비용 차이 $5,000 호조, 일정 차이 $15,000 호조이다. | 비용 차이 -$5,000 부진, 일정 차이 $15,000 호조이다. | 비용 차이 $10,000 호조, 일정 차이 -$15,000 부진이다. | 비용 차이 -$10,000 부진, 일정 차이 $5,000 호조이다. |  | A | CV = EV - AC = $165,000 - $160,000 = $5,000 (양수 = 호조/예산 절감). SV = EV - PV = $165,000 - $150,000 = $15,000 (양수 = 호조/일정 선행). 프로젝트는 비용과 일정 양쪽 모두에서 양호한 성과를 보이고 있다.
2227 | A project has a total budget (BAC) of $800,000 and is planned to be 50% complete by month 8. At the end of month 8, the project is actually 45% complete with $380,000 spent. What are the PV, EV, and AC? | PV = $400,000, EV = $360,000, AC = $380,000 | PV = $360,000, EV = $400,000, AC = $380,000 | PV = $380,000, EV = $360,000, AC = $400,000 | PV = $400,000, EV = $380,000, AC = $360,000 |  | A | PV = BAC × planned % = $800,000 × 50% = $400,000. EV = BAC × actual % complete = $800,000 × 45% = $360,000. AC = actual expenditure = $380,000. This shows the project is behind schedule (EV < PV) and over budget (AC > EV). | [13 empty] | 한 프로젝트의 총 예산(BAC)은 $800,000이며 8개월 차에 50% 완료되도록 계획되어 있다. 8개월 차 종료 시점에 실제로는 45%가 완료되었으며 $380,000이 지출되었다. PV, EV, AC는 각각 얼마인가? | PV = $400,000, EV = $360,000, AC = $380,000 | PV = $360,000, EV = $400,000, AC = $380,000 | PV = $380,000, EV = $360,000, AC = $400,000 | PV = $400,000, EV = $380,000, AC = $360,000 |  | A | PV = BAC × 계획 % = $800,000 × 50% = $400,000. EV = BAC × 실제 완료 % = $800,000 × 45% = $360,000. AC = 실제 지출 = $380,000. 이 결과는 EV < PV이므로 일정 지연이며 AC > EV이므로 예산 초과임을 보여준다.
2228 | A project has the following activities: Activity A (Duration: 3 days, no predecessor), Activity B (Duration: 5 days, predecessor: A), Activity C (Duration: 4 days, predecessor: A), Activity D (Duration: 2 days, predecessors: B and C), Activity E (Duration: 6 days, predecessor: D). What is the total duration of the critical path? | 14 days | 15 days | 16 days | 17 days |  | C | The correct answer is C. Path A→B→D→E = 3 + 5 + 2 + 6 = 16 days, and path A→C→D→E = 3 + 4 + 2 + 6 = 15 days. The critical path is the longest path, A→B→D→E, at 16 days. 15 days (B) is the shorter, non-critical path, and 14 days (A) and 17 days (D) do not match any path through the network. | [13 empty] | 한 프로젝트의 활동은 다음과 같다: 활동 A (기간: 3일, 선행 없음), 활동 B (기간: 5일, 선행: A), 활동 C (기간: 4일, 선행: A), 활동 D (기간: 2일, 선행: B와 C), 활동 E (기간: 6일, 선행: D). 주공정의 총 기간은? | 14일 | 15일 | 16일 | 17일 |  | C | 정답은 C이다. 경로 A→B→D→E = 3 + 5 + 2 + 6 = 16일, 경로 A→C→D→E = 3 + 4 + 2 + 6 = 15일이다. 주공정은 가장 긴 경로인 A→B→D→E로 16일이다. 15일(B)은 더 짧은 비주공정 경로이고, 14일(A)과 17일(D)은 네트워크의 어느 경로와도 맞지 않는다.
2229 | In a project network, Activity X has an Early Start (ES) of Day 5, Early Finish (EF) of Day 12, Late Start (LS) of Day 8, and Late Finish (LF) of Day 15. What is the total float for Activity X? | 0 days | 3 days | 5 days | 7 days |  | B | The correct answer is B. Total float = LS − ES = 8 − 5 = 3 days, which equals LF − EF = 15 − 12 = 3 days. Activity X can be delayed by up to 3 days without delaying the project end date. Zero float (A) would mean it is on the critical path, and 5 days (C) and 7 days (D) are the activity's early start and duration, not its float. | [13 empty] | 한 프로젝트 네트워크에서 활동 X의 빠른 시작(ES)은 5일째, 빠른 종료(EF)는 12일째, 늦은 시작(LS)은 8일째, 늦은 종료(LF)는 15일째이다. 활동 X의 총 여유(Total Float)는? | 0일 | 3일 | 5일 | 7일 |  | B | 정답은 B이다. 총 여유 = LS − ES = 8 − 5 = 3일이며, LF − EF = 15 − 12 = 3일과 같다. 활동 X는 프로젝트 종료일을 늦추지 않고 최대 3일까지 지연될 수 있다. 여유 0일(A)은 주공정에 있다는 뜻이고, 5일(C)과 7일(D)은 각각 활동의 조기 시작일과 기간이지 여유가 아니다.
2230 | A Scrum team is analyzing the burndown chart on day four of a 15-day sprint. The burndown chart shows that the actual remaining work is significantly above the ideal trend line. What should the team do? | Add more team members to increase velocity. | Discuss the situation during the daily standup and identify impediments. | Extend the sprint duration to complete all user stories. | Remove user stories from the sprint backlog immediately. |  | B | When the burndown chart shows actual work above the ideal line, it indicates the team is falling behind. The appropriate first action is to discuss this during the daily standup meeting to identify impediments and find solutions. Adding members (A) contradicts agile principles, extending sprints (C) violates timeboxing, and removing stories (D) should only happen after team discussion with the Product Owner. | [13 empty] | 한 스크럼 팀이 15일짜리 스프린트의 4일째에 번다운 차트를 분석하고 있다. 번다운 차트는 실제 잔여 작업이 이상적인 추세선보다 상당히 위에 있음을 보여준다. 팀은 무엇을 해야 하는가? | 속도(velocity)를 높이기 위해 팀원을 추가한다. | 일일 스탠드업에서 상황을 논의하고 장애물을 식별한다. | 모든 사용자 스토리를 완료하기 위해 스프린트 기간을 연장한다. | 즉시 스프린트 백로그에서 사용자 스토리를 제거한다. |  | B | 번다운 차트가 실제 작업이 이상선보다 위에 있음을 보여줄 때, 이는 팀이 진척이 늦어지고 있음을 의미한다. 적절한 첫 조치는 일일 스탠드업에서 이를 논의하여 장애물을 식별하고 해결책을 찾는 것이다. 팀원 추가(A)는 애자일 원칙에 어긋나며, 스프린트 연장(C)은 타임박싱 원칙에 위배되고, 스토리 제거(D)는 제품 책임자와 팀 논의 후에만 이루어져야 한다.
2231 | The team user story delivery rate has been declining over the past three sprints. The velocity chart shows: Sprint 1 = 42 points, Sprint 2 = 38 points, Sprint 3 = 31 points. What should the Scrum Master do first? | Report the declining velocity to the project sponsor. | Facilitate a focused retrospective to identify root causes of the decline. | Reduce the number of story points committed in the next sprint. | Reassign team members to improve productivity. |  | B | A declining velocity trend suggests underlying issues that need to be understood before taking action. The Scrum Master should facilitate a focused retrospective to identify root causes. Simply reducing commitments (C) treats the symptom, not the cause. Reporting to sponsors (A) or reassigning members (D) may be premature without understanding why velocity is declining. | [13 empty] | 지난 세 번의 스프린트 동안 팀의 사용자 스토리 인도율이 감소하고 있다. 속도 차트는 다음과 같다: 스프린트 1 = 42 포인트, 스프린트 2 = 38 포인트, 스프린트 3 = 31 포인트. 스크럼 마스터는 먼저 무엇을 해야 하는가? | 속도 감소를 프로젝트 스폰서에게 보고한다. | 집중 회고를 진행하여 감소의 근본 원인을 파악한다. | 다음 스프린트에 약속하는 스토리 포인트 수를 줄인다. | 생산성 향상을 위해 팀원을 재배정한다. |  | B | 속도 감소 추세는 조치 전에 이해되어야 할 근본 문제가 있음을 시사한다. 스크럼 마스터는 집중 회고를 진행하여 근본 원인을 파악해야 한다. 단순히 약속을 줄이는 것(C)은 증상만 다루며 원인을 다루지 않는다. 스폰서 보고(A)나 팀원 재배정(D)은 속도 감소 이유를 이해하기 전에는 시기상조이다.
2232 | A project manager reviews the earned value S-curve graph and notices that the EV line is below the PV line but above the AC line. What does this indicate about the project? | The project is behind schedule and over budget. | The project is ahead of schedule and under budget. | The project is behind schedule but under budget. | The project is ahead of schedule but over budget. |  | C | When EV < PV, the project is behind schedule (less value earned than planned). When EV > AC, the project is under budget (more value earned than money spent). Therefore, the project is behind schedule but under budget. The project manager should focus on schedule recovery actions. | [13 empty] | 한 프로젝트 관리자가 획득가치 S-곡선 그래프를 검토한 결과, EV 선이 PV 선보다 아래에 있지만 AC 선보다는 위에 있음을 발견했다. 이는 프로젝트에 대해 무엇을 의미하는가? | 프로젝트가 일정 지연이며 예산 초과 상태이다. | 프로젝트가 일정 선행이며 예산 절감 상태이다. | 프로젝트가 일정 지연이지만 예산 절감 상태이다. | 프로젝트가 일정 선행이지만 예산 초과 상태이다. |  | C | EV < PV이면 프로젝트가 일정 지연 상태이다(계획보다 적게 가치 획득). EV > AC이면 프로젝트가 예산 절감 상태이다(지출액보다 많은 가치 획득). 따라서 프로젝트는 일정 지연이지만 예산 절감 상태이다. 프로젝트 관리자는 일정 회복 조치에 집중해야 한다.
2233 | Match each team behavior on the left with the correct Tuckman Ladder stage on the right: (1) Team members challenge the leader and each other → ___; (2) Team functions as a unit with mutual trust → ___; (3) Team members get to know each other and establish ground rules → ___; (4) Team establishes working relationships and norms → ___. | (1) Storming, (2) Performing, (3) Forming, (4) Norming | (1) Forming, (2) Norming, (3) Storming, (4) Performing | (1) Norming, (2) Performing, (3) Forming, (4) Storming | (1) Storming, (2) Norming, (3) Forming, (4) Performing |  | A | Tuckman Ladder stages: Forming (getting to know each other), Storming (conflicts and power struggles), Norming (establishing working relationships), Performing (functioning as a cohesive unit). The behaviors match: challenging = Storming, mutual trust = Performing, getting acquainted = Forming, establishing norms = Norming. | [13 empty] | 왼쪽의 각 팀 행동을 오른쪽의 올바른 터크만(Tuckman) 사다리 단계와 매칭하시오: (1) 팀원들이 리더와 서로에게 도전한다 → ___; (2) 팀이 상호 신뢰를 가지고 하나의 단위로 작동한다 → ___; (3) 팀원들이 서로 알게 되고 기본 규칙을 정한다 → ___; (4) 팀이 작업 관계와 규범을 확립한다 → ___. | (1) Storming, (2) Performing, (3) Forming, (4) Norming | (1) Forming, (2) Norming, (3) Storming, (4) Performing | (1) Norming, (2) Performing, (3) Forming, (4) Storming | (1) Storming, (2) Norming, (3) Forming, (4) Performing |  | A | 터크만 사다리 단계: Forming(서로 알아가기), Storming(갈등과 권력 다툼), Norming(작업 관계 확립), Performing(응집된 단위로 기능). 행동 매칭: 도전 = Storming, 상호 신뢰 = Performing, 친해지기 = Forming, 규범 확립 = Norming. 따라서 답은 A이다.
2234 | Match the communication method to the most appropriate scenario: (1) Interactive communication → ___; (2) Push communication → ___; (3) Pull communication → ___. | (1) Video conference for urgent decision, (2) Email status report, (3) Project repository for reference documents | (1) Email status report, (2) Project repository, (3) Video conference | (1) Project repository, (2) Video conference, (3) Email status report | (1) Email status report, (2) Video conference, (3) Project repository |  | A | Interactive communication (real-time, two-way) is best for urgent decisions via video conference or meetings. Push communication (one-way, sent to recipients) fits email reports. Pull communication (recipients access when needed) suits project repositories and knowledge bases. This aligns with PMBOK communication methods classification. | [13 empty] | 커뮤니케이션 방식을 가장 적절한 시나리오와 매칭하시오: (1) 인터랙티브(상호작용) 커뮤니케이션 → ___; (2) 푸시 커뮤니케이션 → ___; (3) 풀 커뮤니케이션 → ___. | (1) 긴급 결정을 위한 화상 회의, (2) 이메일 상태 보고서, (3) 참고 문서를 위한 프로젝트 저장소 | (1) 이메일 상태 보고서, (2) 프로젝트 저장소, (3) 화상 회의 | (1) 프로젝트 저장소, (2) 화상 회의, (3) 이메일 상태 보고서 | (1) 이메일 상태 보고서, (2) 화상 회의, (3) 프로젝트 저장소 |  | A | 인터랙티브 커뮤니케이션(실시간, 양방향)은 화상 회의나 회의를 통한 긴급 결정에 가장 적합하다. 푸시 커뮤니케이션(일방향, 수신자에게 발송)은 이메일 보고서가 적합하다. 풀 커뮤니케이션(수신자가 필요할 때 접근)은 프로젝트 저장소와 지식 베이스가 적합하다. 이는 PMBOK 커뮤니케이션 방식 분류와 일치한다.
2235 | Match each project characteristic to the most suitable development approach: (1) Well-defined requirements with regulatory compliance → ___; (2) Evolving requirements with frequent customer feedback needed → ___; (3) Core architecture is fixed but features evolve based on market response → ___. | (1) Predictive, (2) Agile, (3) Hybrid | (1) Agile, (2) Predictive, (3) Hybrid | (1) Hybrid, (2) Agile, (3) Predictive | (1) Predictive, (2) Hybrid, (3) Agile |  | A | Predictive (waterfall) works best for well-defined, stable requirements especially in regulated environments. Agile suits evolving requirements where frequent feedback drives development. Hybrid combines both — using predictive for the stable core architecture while applying agile for feature development that responds to market changes. | [13 empty] | 각 프로젝트 특성을 가장 적합한 개발 접근법과 매칭하시오: (1) 잘 정의된 요구사항 + 규제 준수 → ___; (2) 진화하는 요구사항으로 빈번한 고객 피드백 필요 → ___; (3) 핵심 아키텍처는 고정되지만 시장 반응에 따라 기능이 진화 → ___. | (1) 예측형, (2) 애자일, (3) 하이브리드 | (1) 애자일, (2) 예측형, (3) 하이브리드 | (1) 하이브리드, (2) 애자일, (3) 예측형 | (1) 예측형, (2) 하이브리드, (3) 애자일 |  | A | 예측형(워터폴)은 잘 정의되고 안정적인 요구사항, 특히 규제 환경에 가장 적합하다. 애자일은 빈번한 피드백이 개발을 주도하는 진화하는 요구사항에 적합하다. 하이브리드는 두 가지를 결합한다 — 안정적인 핵심 아키텍처에는 예측형을, 시장 변화에 반응하는 기능 개발에는 애자일을 적용한다. 따라서 정답은 A이다.
2236 | A project shows the following EVM data after 3 months. The project manager is reviewing the cost performance. What is the Cost Performance Index (CPI)? ¦ Metric ¦ Value ¦ ¦---¦---¦ ¦ Planned Value (PV) ¦ $50,000 ¦ ¦ Earned Value (EV) ¦ $40,000 ¦ ¦ Actual Cost (AC) ¦ $50,000 ¦ ¦ Budget at Completion (BAC) ¦ $200,000 ¦ | 0.80 (under budget) | 0.80 (over budget) | 1.00 (on budget) | 1.25 (under budget) |  | B | The correct answer is B. CPI = EV / AC = $40,000 / $50,000 = 0.80. A CPI below 1.0 means the project is over budget: for every dollar spent, only 80 cents of value is earned. Option A has the right number but the wrong interpretation, 1.00 (C) would mean on budget, and 1.25 (D) inverts the formula (AC / EV). | Process | Manage budget and resources | Delivery | Tailoring | Predictive |  | Process | Manage budget and resources | Delivery | Cost Management | Tailoring | Monitoring & Controlling |  | 프로젝트가 3개월 후 다음과 같은 EVM 데이터를 보여줍니다. 비용 성과 지수(CPI)는? ¦ 지표 ¦ 값 ¦ ¦---¦---¦ ¦ 계획 가치 (PV) ¦ $50,000 ¦ ¦ 획득 가치 (EV) ¦ $40,000 ¦ ¦ 실제 비용 (AC) ¦ $50,000 ¦ ¦ 완료 시 예산 (BAC) ¦ $200,000 ¦ | 0.80 (예산 미만) | 0.80 (예산 초과) | 1.00 (예산대로) | 1.25 (예산 미만) |  | B | 정답은 B이다. CPI = EV / AC = $40,000 / $50,000 = 0.80이다. CPI가 1.0보다 작으면 예산 초과로, 1달러를 쓸 때마다 80센트의 가치만 얻는다는 뜻이다. 보기 A는 수치는 맞지만 해석이 틀렸고, 1.00(C)은 예산대로라는 뜻이며, 1.25(D)는 공식을 거꾸로(AC / EV) 계산한 값이다.
2237 | Review the following RACI matrix for a project deliverable. The team is confused about who has the final say. Who should make the final decision? ¦ Activity ¦ Sponsor ¦ PM ¦ Lead Dev ¦ Tester ¦ ¦---¦---¦---¦---¦---¦ ¦ Approve final design ¦ A ¦ R ¦ C ¦ I ¦ ¦ Code implementation ¦ I ¦ A ¦ R ¦ C ¦ ¦ Acceptance testing ¦ I ¦ A ¦ C ¦ R ¦ | Sponsor (for design), PM (for code & testing) | PM for everything | Lead Dev because they're closest to the work | Decision is made collectively by the team |  | A | The correct answer is A. In a RACI chart, the 'A' (Accountable) person has the final say, and there is only one per activity. The table shows the sponsor as A for approving the final design and the PM as A for code implementation and acceptance testing. The PM is not accountable for everything (B), the lead developer is Responsible rather than Accountable for code (C), and decisions are not collective (D). | People | Define team ground rules | Team | Stewardship | Predictive |  | People | Define team ground rules | Team | Roles & Responsibilities | Stewardship | Planning |  | 프로젝트 산출물의 다음 RACI 매트릭스를 검토하십시오. 팀이 최종 결정권자가 누구인지 혼동하고 있습니다. 누가 최종 결정을 내려야 합니까? ¦ 활동 ¦ 스폰서 ¦ PM ¦ 리드 개발자 ¦ 테스터 ¦ ¦---¦---¦---¦---¦---¦ ¦ 최종 디자인 승인 ¦ A ¦ R ¦ C ¦ I ¦ ¦ 코드 구현 ¦ I ¦ A ¦ R ¦ C ¦ ¦ 인수 테스트 ¦ I ¦ A ¦ C ¦ R ¦ | 디자인은 스폰서, 코드와 테스트는 PM | 모든 항목에서 PM | 리드 개발자가 가장 가깝게 작업하므로 | 팀이 집단적으로 결정 |  | A | 정답은 A이다. RACI 차트에서 'A'(Accountable, 최종 책임자)가 최종 결정권을 가지며, 활동마다 한 명만 있다. 표에서 최종 설계 승인의 A는 스폰서이고, 코드 구현과 인수 테스트의 A는 PM이다. PM이 모든 활동의 A는 아니며(B), 리드 개발자는 코드 구현의 R(실행 책임자)이지 A가 아니고(C), 결정이 팀 공동으로 내려지는 것도 아니다(D).
2238 | Given the following activity duration table, what is the critical path length? ¦ Activity ¦ Predecessor ¦ Duration (days) ¦ ¦---¦---¦---¦ ¦ A ¦ - ¦ 5 ¦ ¦ B ¦ A ¦ 7 ¦ ¦ C ¦ A ¦ 3 ¦ ¦ D ¦ B ¦ 4 ¦ ¦ E ¦ C ¦ 6 ¦ ¦ F ¦ D, E ¦ 2 ¦ | 16 days (A→C→E→F) | 18 days (A→B→D→F) | 14 days (A→B→F) | 20 days (A→B→C→E→F) |  | B | The correct answer is B. Path A→B→D→F = 5 + 7 + 4 + 2 = 18 days, and path A→C→E→F = 5 + 3 + 6 + 2 = 16 days. The critical path is the longest, A→B→D→F, at 18 days. 16 days (A) is the shorter path, A→B→F (C) skips predecessor D, and A→B→C→E→F (D) is not a valid sequence because C depends only on A. | Process | Plan and manage schedule | Planning | Tailoring | Predictive |  | Process | Plan and manage schedule | Planning | Schedule Management | Tailoring | Planning |  | 다음 활동 소요시간 표를 보고 임계경로(Critical Path)의 길이는? ¦ 활동 ¦ 선행 ¦ 기간(day) ¦ ¦---¦---¦---¦ ¦ A ¦ - ¦ 5 ¦ ¦ B ¦ A ¦ 7 ¦ ¦ C ¦ A ¦ 3 ¦ ¦ D ¦ B ¦ 4 ¦ ¦ E ¦ C ¦ 6 ¦ ¦ F ¦ D, E ¦ 2 ¦ | 16일 (A→C→E→F) | 18일 (A→B→D→F) | 14일 (A→B→F) | 20일 (A→B→C→E→F) |  | B | 정답은 B이다. 경로 A→B→D→F = 5 + 7 + 4 + 2 = 18일, 경로 A→C→E→F = 5 + 3 + 6 + 2 = 16일이다. 주공정은 가장 긴 A→B→D→F로 18일이다. 16일(A)은 더 짧은 경로이고, A→B→F(C)는 선행 활동 D를 건너뛰며, A→B→C→E→F(D)는 C가 A에만 의존하므로 유효한 순서가 아니다.
2239 | Review the following risk register. Which risk should the PM address FIRST? ¦ Risk ID ¦ Description ¦ Probability ¦ Impact ¦ ¦---¦---¦---¦---¦ ¦ R1 ¦ Vendor delay in component delivery ¦ 0.5 ¦ $50,000 ¦ ¦ R2 ¦ Key developer leaving ¦ 0.2 ¦ $200,000 ¦ ¦ R3 ¦ Scope creep from stakeholder ¦ 0.7 ¦ $30,000 ¦ ¦ R4 ¦ Compliance audit failure ¦ 0.1 ¦ $500,000 ¦ | R1 (vendor delay in component delivery) | R2 (key developer leaving) | R3 (scope creep from stakeholder) | R4 (compliance audit failure) |  | D | Expected monetary value (EMV) = probability × impact. R1 = 0.5 × $50,000 = $25,000; R2 = 0.2 × $200,000 = $40,000; R3 = 0.7 × $30,000 = $21,000; R4 = 0.1 × $500,000 = $50,000. R4 has the highest EMV ($50,000), so it should be addressed first. Prioritizing by probability alone (R3) or by the frequency of occurrence ignores the size of the impact, and R2 ranks below R4 once both probability and impact are considered. | Process | Plan and manage project compliance | Uncertainty | Risk | Predictive |  | Process | Manage risk | Uncertainty | Risk Management | Risk | Planning |  | 다음 위험 등록부를 검토하십시오. PM이 가장 먼저 다뤄야 할 위험은? ¦ 위험 ID ¦ 설명 ¦ 확률 ¦ 영향 ¦ ¦---¦---¦---¦---¦ ¦ R1 ¦ 부품 납기 지연 ¦ 0.5 ¦ $50,000 ¦ ¦ R2 ¦ 핵심 개발자 이탈 ¦ 0.2 ¦ $200,000 ¦ ¦ R3 ¦ 이해관계자의 범위 변경 ¦ 0.7 ¦ $30,000 ¦ ¦ R4 ¦ 컴플라이언스 감사 실패 ¦ 0.1 ¦ $500,000 ¦ | R1 (부품 납기 지연) | R2 (핵심 개발자 이탈) | R3 (이해관계자의 범위 변경) | R4 (컴플라이언스 감사 실패) |  | D | 기대금전가치(EMV) = 확률 × 영향이다. R1 = 0.5 × $50,000 = $25,000, R2 = 0.2 × $200,000 = $40,000, R3 = 0.7 × $30,000 = $21,000, R4 = 0.1 × $500,000 = $50,000이다. EMV가 가장 큰 R4($50,000)를 가장 먼저 다뤄야 한다. 확률(R3)이나 발생 빈도만 보고 우선순위를 정하면 영향의 크기를 놓치게 되며, 확률과 영향을 함께 고려하면 R2는 R4보다 순위가 낮다.
2240 | Review the following stakeholder register. Which engagement strategy is MOST appropriate for the CFO? ¦ Stakeholder ¦ Power ¦ Interest ¦ Current ¦ Desired ¦ ¦---¦---¦---¦---¦---¦ ¦ CFO ¦ High ¦ Low ¦ Resistant ¦ Supportive ¦ ¦ End Users ¦ Low ¦ High ¦ Neutral ¦ Supportive ¦ ¦ Vendor ¦ Med ¦ Med ¦ Supportive ¦ Supportive ¦ | Keep informed (regular updates) | Manage closely (high effort, frequent engagement) | Monitor (minimum effort) | Keep satisfied (high power, low interest — manage to avoid blocking) |  | D | The correct answer is D. On the power-interest grid, the CFO has high power and low interest, which places them in 'keep satisfied': manage their needs so they do not block the project, without requiring detailed involvement. 'Keep informed' (A) is for low power and high interest, 'manage closely' (B) is for high power and high interest, and 'monitor' (C) is for low power and low interest. | People | Engage and support stakeholders | Stakeholders | Stakeholders | Predictive |  | People | Engage and support stakeholders | Stakeholders | Stakeholder Engagement | Stakeholders | Initiating |  | 다음 이해관계자 등록부를 검토하십시오. CFO에 대한 가장 적절한 참여 전략은? ¦ 이해관계자 ¦ 영향력 ¦ 관심 ¦ 현재 ¦ 목표 ¦ ¦---¦---¦---¦---¦---¦ ¦ CFO ¦ High ¦ Low ¦ 저항 ¦ 지지 ¦ ¦ End Users ¦ Low ¦ High ¦ 중립 ¦ 지지 ¦ ¦ Vendor ¦ Med ¦ Med ¦ 지지 ¦ 지지 ¦ | 정보 유지 (정기 업데이트) | 긴밀 관리 (고노력, 잦은 소통) | 최소 모니터링 | 만족 유지 (영향력 高 / 관심 低 — 차단 방지) |  | D | 정답은 D이다. 권력-관심도 그리드에서 CFO는 권력이 높고 관심이 낮으므로 '만족 유지' 영역에 속한다. 프로젝트를 막지 않도록 요구를 관리하되 상세한 참여를 요구하지는 않는다. '정보 제공'(A)은 권력이 낮고 관심이 높은 경우, '밀착 관리'(B)는 둘 다 높은 경우, '모니터링'(C)은 둘 다 낮은 경우에 해당한다.
2241 | The resource histogram shows weekly developer demand. Maximum available developers = 5. What is the PM's BEST action? ¦ Week ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ ¦---¦---¦---¦---¦---¦---¦---¦ ¦ Required Devs ¦ 3 ¦ 4 ¦ 7 ¦ 6 ¦ 3 ¦ 2 ¦ | Continue as planned, hire temp staff in weeks 3-4 | Apply resource leveling — extend project duration | Apply resource smoothing — preserve critical path, level non-critical | Cancel deliverables in weeks 3-4 |  | C | The correct answer is C. Demand exceeds the five available developers in weeks 3 and 4. Resource smoothing redistributes work within available float so the resource limit is respected without changing the critical path or end date, so it should be tried first. Resource leveling (B) can extend the duration and is used only when smoothing is not enough, hiring temporary staff (A) adds cost before optimizing, and cancelling deliverables (D) gives up scope. | Process | Plan and manage resources | Planning | Optimization | Predictive |  | Process | Plan and manage resources | Planning | Resource Management | Optimization | Planning |  | 리소스 히스토그램이 주별 개발자 수요를 보여줍니다. 가용 최대 개발자 = 5명. PM의 최선의 조치는? ¦ 주 ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ ¦---¦---¦---¦---¦---¦---¦---¦ ¦ 필요 개발자 ¦ 3 ¦ 4 ¦ 7 ¦ 6 ¦ 3 ¦ 2 ¦ | 원안대로, 3-4주차 임시 인력 채용 | 리소스 평준화 — 일정 연장 | 리소스 평활화 — 임계경로 유지, 비임계경로만 분산 | 3-4주차 산출물 취소 |  | C | 정답은 C이다. 3~4주차의 필요 인원이 가용 개발자 5명을 넘는다. 자원 평활화는 여유 시간 안에서 작업을 재배치해 주공정과 종료일을 바꾸지 않고 자원 한도를 지키므로 먼저 시도해야 한다. 자원 평준화(B)는 기간을 늘릴 수 있어 평활화로 부족할 때만 쓰고, 임시 인력 채용(A)은 최적화 전에 비용부터 늘리며, 인도물 취소(D)는 범위를 포기하는 것이다.
2242 | Review the daily defect rate. UCL=10, LCL=2, Mean=6. Which day requires investigation per the Rule of Seven? ¦ Day ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ ¦---¦---¦---¦---¦---¦---¦---¦---¦---¦ ¦ Defects ¦ 7 ¦ 8 ¦ 7 ¦ 8 ¦ 7 ¦ 9 ¦ 8 ¦ 7 ¦ | Day 6 (highest value 9) | Day 8 (process now appears stable) | Day 7 (7 consecutive points above mean — Rule of Seven trigger) | No investigation needed — all within control limits |  | C | The correct answer is C. Under the rule of seven, seven or more consecutive points on the same side of the mean indicate a non-random trend, even if all points are within control limits. Every day is above the mean of 6, so the trigger is reached on day 7. A single high value on day 6 (A) is not the trigger, the process is drifting rather than stable on day 8 (B), and being within control limits (D) does not rule out a trend. | Process | Plan and manage quality | Delivery | Quality | Predictive |  | Process | Manage quality | Delivery | Quality Management | Quality | Monitoring & Controlling |  | 일별 결함률을 검토하십시오. UCL=10, LCL=2, 평균=6. '7의 법칙(Rule of Seven)'에 따라 조사가 필요한 날은? ¦ 일 ¦ 1 ¦ 2 ¦ 3 ¦ 4 ¦ 5 ¦ 6 ¦ 7 ¦ 8 ¦ ¦---¦---¦---¦---¦---¦---¦---¦---¦---¦ ¦ 결함 ¦ 7 ¦ 8 ¦ 7 ¦ 8 ¦ 7 ¦ 9 ¦ 8 ¦ 7 ¦ | 6일 (최고 9) | 8일 (안정화) | 7일 (평균 위 7회 연속 — 7의 법칙 발동) | 조사 불필요 — 모두 관리한계 내 |  | C | 정답은 C이다. 7의 법칙에 따르면 평균의 같은 쪽에 7개 이상의 점이 연속되면, 모든 점이 관리 한계 안에 있더라도 무작위가 아닌 추세가 있다는 뜻이다. 모든 날이 평균 6보다 위에 있으므로 7일째에 조사 기준에 도달한다. 6일째의 단일 최고값(A)은 기준이 아니고, 8일째는 공정이 안정된 것이 아니라 한쪽으로 치우치는 중이며(B), 관리 한계 안이라는 것(D)만으로 추세를 배제할 수 없다.
2243 | Review the issue log. Per the SOP (Standard Operating Procedure), any issue open longer than 14 days must be escalated; critical issues are handled directly by the PM as the owner. Which issue requires escalation per the SOP? ¦ ID ¦ Description ¦ Severity ¦ Age (days) ¦ Owner ¦ ¦---¦---¦---¦---¦---¦ ¦ I1 ¦ Test environment unstable ¦ Medium ¦ 5 ¦ Tester ¦ ¦ I2 ¦ Customer reported security gap ¦ Critical ¦ 1 ¦ PM ¦ ¦ I3 ¦ Translation error in UI ¦ Low ¦ 12 ¦ Developer ¦ ¦ I4 ¦ Vendor invoice missing ¦ Medium ¦ 20 ¦ PM ¦ | I1 — Medium severity | I2 — Critical, but only 1 day old, give time | I3 — Low severity but stale | I4 — Aged 20 days regardless of severity |  | D | The correct answer is D. Under the stated SOP, any issue open longer than 14 days must be escalated, while critical issues are handled directly by the PM as the owner. I4 has been open for 20 days, which exceeds the 14-day limit, so it must be escalated regardless of its medium severity. I2 is critical but is already being handled by the PM and is only 1 day old. I1 (5 days) and I3 (12 days) are still within the limit. | Process | Manage project issues | Delivery | Stewardship | Predictive |  | Process | Manage project issues | Delivery | Issue Management | Stewardship | Monitoring & Controlling |  | SOP(표준 운영 절차)에 따르면 14일을 넘겨 열려 있는 이슈는 에스컬레이션해야 하며, 치명적 이슈는 담당자인 PM이 직접 처리한다. 이슈 로그를 검토하라. SOP에 따라 에스컬레이션해야 하는 이슈는? ¦ ID ¦ 설명 ¦ 심각도 ¦ 경과(day) ¦ 소유자 ¦ ¦---¦---¦---¦---¦---¦ ¦ I1 ¦ 테스트 환경 불안정 ¦ Medium ¦ 5 ¦ 테스터 ¦ ¦ I2 ¦ 고객 보안 결함 보고 ¦ Critical ¦ 1 ¦ PM ¦ ¦ I3 ¦ UI Translation error ¦ Low ¦ 12 ¦ 개발자 ¦ ¦ I4 ¦ vendor 청구서 누락 ¦ Medium ¦ 20 ¦ PM ¦ | I1 — 중간 심각도 | I2 — Critical이지만 1일, 시간 필요 | I3 — 낮은 심각도지만 오래됨 | I4 — 심각도 무관 20일 경과 |  | D | 정답은 D이다. 제시된 SOP에 따르면 14일을 넘겨 열려 있는 이슈는 에스컬레이션해야 하고, 치명적 이슈는 담당자인 PM이 직접 처리한다. I4는 20일째 열려 있어 14일 기준을 넘었으므로, 심각도가 중간이더라도 에스컬레이션해야 한다. I2는 치명적이지만 이미 PM이 처리 중이고 1일밖에 지나지 않았다. I1(5일)과 I3(12일)은 아직 기준 이내이다.
2244 | Review the weighted vendor scoring. Which vendor should be selected? ¦ Criteria (Weight) ¦ Vendor A ¦ Vendor B ¦ Vendor C ¦ ¦---¦---¦---¦---¦ ¦ Cost (40%) ¦ 70 ¦ 90 ¦ 60 ¦ ¦ Quality (35%) ¦ 90 ¦ 70 ¦ 95 ¦ ¦ Schedule (25%) ¦ 80 ¦ 60 ¦ 85 ¦ | Vendor A | Vendor B | Vendor C | None of the vendors; re-issue the RFP |  | A | Apply the weights to each vendor's scores and select the highest total. Vendor A = 70×0.40 + 90×0.35 + 80×0.25 = 28 + 31.5 + 20 = 79.5. Vendor B = 90×0.40 + 70×0.35 + 60×0.25 = 36 + 24.5 + 15 = 75.5. Vendor C = 60×0.40 + 95×0.35 + 85×0.25 = 24 + 33.25 + 21.25 = 78.5. Vendor A has the highest weighted score, so it should be selected. Choosing by a single criterion (lowest cost for B, highest quality or schedule score for C) ignores the agreed weighting, and there is no basis for rejecting all vendors (D) when a clear winner exists. | Process | Plan and manage procurement | Delivery | Tailoring | Predictive |  | Process | Manage procurement | Delivery | Procurement Management | Tailoring | Planning |  | 가중 vendor 점수표를 검토하십시오. 어떤 vendor를 선택해야 합니까? ¦ 평가기준 (가중치) ¦ vendor A ¦ vendor B ¦ vendor C ¦ ¦---¦---¦---¦---¦ ¦ 비용 (40%) ¦ 70 ¦ 90 ¦ 60 ¦ ¦ 품질 (35%) ¦ 90 ¦ 70 ¦ 95 ¦ ¦ 일정 (25%) ¦ 80 ¦ 60 ¦ 85 ¦ | Vendor A | Vendor B | Vendor C | 어느 업체도 선정하지 않고 제안요청서(RFP)를 다시 발행한다 |  | A | 각 업체의 점수에 가중치를 적용해 총점이 가장 높은 업체를 선정한다. Vendor A = 70×0.40 + 90×0.35 + 80×0.25 = 28 + 31.5 + 20 = 79.5, Vendor B = 90×0.40 + 70×0.35 + 60×0.25 = 36 + 24.5 + 15 = 75.5, Vendor C = 60×0.40 + 95×0.35 + 85×0.25 = 24 + 33.25 + 21.25 = 78.5이다. 가중 점수가 가장 높은 Vendor A를 선정해야 한다. 원가가 가장 낮은 B나 품질·일정 점수가 가장 높은 C처럼 기준 하나만 보고 고르면 합의된 가중치를 무시하게 되며, 분명한 1위가 있으므로 모든 업체를 탈락시킬(D) 근거도 없다.
2245 | Review monthly burn rate against the cost baseline. What is the CRITICAL action? ¦ Month ¦ Baseline ¦ Actual ¦ Variance ¦ ¦---¦---¦---¦---¦ ¦ 1 ¦ $20,000 ¦ $22,000 ¦ +$2,000 ¦ ¦ 2 ¦ $20,000 ¦ $25,000 ¦ +$5,000 ¦ ¦ 3 ¦ $20,000 ¦ $28,000 ¦ +$8,000 ¦ | Continue — variance is small relative to total budget | Update the cost baseline immediately | Investigate the increasing trend, perform root cause analysis, then decide on corrective action | Submit a change request to increase budget |  | C | The correct answer is C. The variance is growing each month (+$2,000, +$5,000, +$8,000), which is a trend rather than random noise. The project manager should investigate the cause and perform root cause analysis before deciding on corrective action. Continuing because the variance seems small (A) ignores the trend, changing the baseline (B) hides it, and requesting more budget (D) is premature before the cause is known. | Process | Plan and manage budget and resources | Measurement | Stewardship | Predictive |  | Process | Manage budget and resources | Measurement | Cost Management | Stewardship | Monitoring & Controlling |  | 월별 소진율을 비용 기준선과 비교 검토하십시오. CRITICAL한 조치는? ¦ 월 ¦ 기준선 ¦ 실제 ¦ 차이 ¦ ¦---¦---¦---¦---¦ ¦ 1 ¦ $20,000 ¦ $22,000 ¦ +$2,000 ¦ ¦ 2 ¦ $20,000 ¦ $25,000 ¦ +$5,000 ¦ ¦ 3 ¦ $20,000 ¦ $28,000 ¦ +$8,000 ¦ | 총 예산 대비 작으니 지속 | 비용 기준선을 즉시 갱신 | 증가 추세 조사 → 근본 원인 분석 → 시정 조치 결정 | 예산 증액 변경요청 즉시 제출 |  | C | 정답은 C이다. 편차가 매월 커지고 있으므로(+$2,000, +$5,000, +$8,000) 무작위 변동이 아니라 추세이다. 프로젝트 관리자는 시정 조치를 정하기 전에 원인을 조사하고 근본 원인 분석을 해야 한다. 편차가 작아 보인다고 계속하는 것(A)은 추세를 무시하고, 기준선을 바꾸는 것(B)은 추세를 숨기며, 원인을 알기 전에 예산 증액을 요청하는 것(D)은 성급하다.
2246 | Review lessons learned register. Which lesson should be SHARED ORGANIZATION-WIDE first? ¦ ID ¦ Phase ¦ Lesson ¦ Reusability ¦ ¦---¦---¦---¦---¦ ¦ L1 ¦ Init ¦ Skipped sponsor alignment, project drifted ¦ Med ¦ ¦ L2 ¦ Plan ¦ Underestimated test data prep by 40% ¦ High ¦ ¦ L3 ¦ Exec ¦ Vendor onboarding template saved 2 wks ¦ High ¦ ¦ L4 ¦ Close ¦ Held remote retro with poor tooling ¦ Low ¦ | L1 (avoid future drift) | L2 (avoid future estimation errors) | L3 (replicate the template — positive lesson, high reusability) | L4 (improve retro tooling) |  | C | Lessons to be shared organization-wide first should combine high reusability with a clear, immediately applicable benefit. L3 (a vendor onboarding template that saved two weeks) is highly reusable and gives other projects a ready-made practice they can adopt right away, so it should be shared first. L2 is also highly reusable and valuable, but it describes an estimation error to avoid rather than a ready-to-use asset. L1 has only medium reusability, and L4 has low reusability. | Business Environment | Engage with knowledge transfer | Delivery | Stewardship | Predictive |  | Business Environment | Engage with knowledge transfer | Delivery | Knowledge Management | Stewardship | Closing |  | 교훈 등록부를 검토하십시오. 조직 전체에 가장 먼저 공유해야 할 교훈은? ¦ ID ¦ 단계 ¦ 교훈 ¦ 재사용성 ¦ ¦---¦---¦---¦---¦ ¦ L1 ¦ 착수 ¦ 스폰서 정렬 누락으로 프로젝트 표류 ¦ Med ¦ ¦ L2 ¦ 기획 ¦ 테스트 데이터 준비 40% 과소추정 ¦ High ¦ ¦ L3 ¦ 실행 ¦ vendor 온보딩 템플릿으로 2주 단축 ¦ High ¦ ¦ L4 ¦ 종료 ¦ 원격 회고가 도구 부실로 비효율 ¦ Low ¦ | L1 (추후 표류 방지) | L2 (추후 추정 오류 방지) | L3 (템플릿 복제 — 긍정 교훈, 높은 재사용성) | L4 (회고 도구 개선) |  | C | 조직 전체에 먼저 공유할 교훈은 재사용성이 높으면서 바로 적용할 수 있는 효익이 분명해야 한다. L3(2주를 절약한 벤더 온보딩 템플릿)는 재사용성이 높고, 다른 프로젝트가 즉시 가져다 쓸 수 있는 관행이므로 가장 먼저 공유해야 한다. L2도 재사용성이 높고 가치 있지만, 바로 쓸 수 있는 자산이 아니라 피해야 할 산정 오류를 설명한다. L1은 재사용성이 중간이고, L4는 재사용성이 낮다.
2247 | Use the P/I matrix to score risks (P × I = score). Which risk requires a DETAILED response plan (score ≥ 0.18)? ¦ Risk ¦ P ¦ I ¦ Score ¦ ¦---¦---¦---¦---¦ ¦ R1 ¦ 0.3 ¦ 0.4 ¦ 0.12 ¦ ¦ R2 ¦ 0.5 ¦ 0.4 ¦ 0.20 ¦ ¦ R3 ¦ 0.7 ¦ 0.2 ¦ 0.14 ¦ ¦ R4 ¦ 0.1 ¦ 0.8 ¦ 0.08 ¦ | R1 only | R2 only (score 0.20 ≥ 0.18) | R2 and R3 | All risks need detailed plans |  | B | The correct answer is B. Only R2 has a score (0.5 × 0.4 = 0.20) at or above the 0.18 threshold, so only R2 needs a detailed response plan. R1 (0.12), R3 (0.14), and R4 (0.08) are below the threshold and go on a watch list. Options A and C include risks below the threshold, and D ignores the threshold entirely. | Process | Manage risk | Uncertainty | Risk | Predictive |  | Process | Manage risk | Uncertainty | Risk Management | Risk | Planning |  | 확률/영향 매트릭스로 위험 점수를 산출(P × I). 상세 대응계획이 필요한(점수 ≥ 0.18) 위험은? ¦ 위험 ¦ P ¦ I ¦ 점수 ¦ ¦---¦---¦---¦---¦ ¦ R1 ¦ 0.3 ¦ 0.4 ¦ 0.12 ¦ ¦ R2 ¦ 0.5 ¦ 0.4 ¦ 0.20 ¦ ¦ R3 ¦ 0.7 ¦ 0.2 ¦ 0.14 ¦ ¦ R4 ¦ 0.1 ¦ 0.8 ¦ 0.08 ¦ | R1만 | R2만 (0.20 ≥ 0.18) | R2, R3 | 모든 위험 상세 계획 필요 |  | B | 정답은 B이다. 점수가 0.18 기준 이상인 것은 R2(0.5 × 0.4 = 0.20)뿐이므로, R2만 상세한 대응 계획이 필요하다. R1(0.12), R3(0.14), R4(0.08)는 기준 미만이라 감시 목록에 둔다. 보기 A와 C는 기준 미만의 리스크를 포함하고, D는 기준을 아예 무시한다.
2248 | Plot stakeholders on the Power-Interest grid based on the table. Where does the End User Champion belong? ¦ Stakeholder ¦ Power ¦ Interest ¦ ¦---¦---¦---¦ ¦ CEO ¦ 9 ¦ 4 ¦ ¦ End User Champion ¦ 3 ¦ 9 ¦ ¦ Lead Architect ¦ 7 ¦ 8 ¦ ¦ Janitor ¦ 1 ¦ 2 ¦ | Manage closely (high power, high interest) | Keep informed (low power, high interest) | Keep satisfied (high power, low interest) | Monitor only (low power, low interest) |  | B | The correct answer is B. The End User Champion has low power (3) and high interest (9), which places them in 'keep informed': provide regular updates so they stay engaged and feel heard. 'Manage closely' (A) is for high power and high interest, such as the Lead Architect, 'keep satisfied' (C) is for high power and low interest, such as the CEO, and 'monitor' (D) is for low power and low interest. | People | Engage and support stakeholders | Stakeholders | Stakeholders | Predictive |  | People | Engage and support stakeholders | Stakeholders | Stakeholder Engagement | Stakeholders | Initiating |  | 표를 바탕으로 권력-관심 그리드에 이해관계자를 배치. End User Champion의 위치는? ¦ 이해관계자 ¦ 권력 ¦ 관심 ¦ ¦---¦---¦---¦ ¦ CEO ¦ 9 ¦ 4 ¦ ¦ End User Champion ¦ 3 ¦ 9 ¦ ¦ Lead Architect ¦ 7 ¦ 8 ¦ ¦ Janitor ¦ 1 ¦ 2 ¦ | 긴밀 관리 (권력 高 / 관심 高) | 정보 유지 (권력 低 / 관심 高) | 만족 유지 (권력 高 / 관심 低) | 최소 모니터링 (권력 低 / 관심 低) |  | B | 정답은 B이다. 최종 사용자 대표는 권력이 낮고(3) 관심이 높으므로(9) '정보 제공' 영역에 속한다. 정기적으로 정보를 제공해 계속 참여하고 의견이 반영된다고 느끼게 한다. '밀착 관리'(A)는 수석 아키텍트처럼 둘 다 높은 경우, '만족 유지'(C)는 CEO처럼 권력은 높고 관심은 낮은 경우, '모니터링'(D)은 둘 다 낮은 경우에 해당한다.
2249 | Review test coverage matrix. Which gap is MOST critical? ¦ Module ¦ Unit ¦ Integration ¦ UAT ¦ Performance ¦ ¦---¦---¦---¦---¦---¦ ¦ Auth ¦ ✓ ¦ ✓ ¦ ✓ ¦ ✓ ¦ ¦ Payment ¦ ✓ ¦ ✓ ¦ - ¦ ✓ ¦ ¦ Reporting ¦ ✓ ¦ - ¦ ✓ ¦ - ¦ ¦ Admin ¦ ✓ ¦ ✓ ¦ ✓ ¦ - ¦ | Reporting — missing integration test | Payment — missing UAT (user acceptance for monetary functions) | Admin — missing performance test | Reporting — missing performance test |  | B | The correct answer is B. The missing UAT for Payment is the most critical gap: payment handles money, carries regulatory and customer-trust impact, and UAT is where users confirm the function is correct for the business, so the customer cannot accept it without sign-off. The missing integration (A) and performance tests (C, D) for Reporting and Admin are real gaps, but their risk is lower and they can be addressed with less business impact. | Process | Plan and manage quality | Delivery | Quality | Predictive |  | Process | Manage quality | Delivery | Quality Management | Quality | Monitoring & Controlling |  | 테스트 커버리지 매트릭스를 검토하십시오. 가장 치명적인 누락은? ¦ 모듈 ¦ Unit ¦ Integration ¦ UAT ¦ Performance ¦ ¦---¦---¦---¦---¦---¦ ¦ Auth ¦ ✓ ¦ ✓ ¦ ✓ ¦ ✓ ¦ ¦ Payment ¦ ✓ ¦ ✓ ¦ - ¦ ✓ ¦ ¦ Reporting ¦ ✓ ¦ - ¦ ✓ ¦ - ¦ ¦ Admin ¦ ✓ ¦ ✓ ¦ ✓ ¦ - ¦ | Reporting — Integration 누락 | Payment — UAT 누락 (금전 기능 사용자 인수) | Admin — Performance 누락 | Reporting — Performance 누락 |  | B | 정답은 B이다. 결제 기능의 UAT 누락이 가장 치명적인 공백이다. 결제는 돈을 다루고 규제와 고객 신뢰에 영향을 주며, UAT는 사용자가 기능이 업무상 올바른지 확인하는 단계라 승인 없이는 고객이 인수할 수 없다. 보고·관리 기능의 통합 테스트(A)나 성능 테스트(C, D) 누락도 실제 공백이지만 리스크가 더 낮고 업무 영향이 적게 보완할 수 있다.
2250 | Review change request log. Per the Change Control SOP, which CR should be PRESENTED TO CCB FIRST? ¦ CR ID ¦ Type ¦ Cost Impact ¦ Schedule Impact ¦ Status ¦ ¦---¦---¦---¦---¦---¦ ¦ C1 ¦ Defect fix ¦ $0 ¦ 0 days ¦ Approved ¦ ¦ C2 ¦ Scope add ¦ $30,000 ¦ +5 days ¦ Pending ¦ ¦ C3 ¦ Spec clarification ¦ $0 ¦ 0 days ¦ Pending ¦ ¦ C4 ¦ Vendor change ¦ $80,000 ¦ +10 days ¦ Pending ¦ | C1 (smallest impact, easy) | C2 (moderate scope add) | C3 (no impact, just clarification) | C4 (largest impact requires CCB approval first) |  | D | The correct answer is D. Changes with a large cost or schedule impact must be reviewed by the CCB first. C4 is pending and has the largest impact (+$80,000 and +10 days), so it should be taken to the CCB first. C1 (A) is already approved, C3 (C) has no impact and may be handled at a lower level, and C2 (B) has a smaller impact than C4. | Business Environment | Manage project changes | Delivery | Change | Predictive |  | Business Environment | Manage project changes | Delivery | Change Management | Change | Monitoring & Controlling |  | 변경요청 로그를 검토하십시오. 변경 통제 SOP에 따라 CCB에 먼저 제출해야 할 CR은? ¦ CR ID ¦ 유형 ¦ 비용 영향 ¦ 일정 영향 ¦ 상태 ¦ ¦---¦---¦---¦---¦---¦ ¦ C1 ¦ 결함 수정 ¦ $0 ¦ 0일 ¦ 승인 ¦ ¦ C2 ¦ 범위 추가 ¦ $30,000 ¦ +5일 ¦ 대기 ¦ ¦ C3 ¦ 사양 명확화 ¦ $0 ¦ 0일 ¦ 대기 ¦ ¦ C4 ¦ vendor 변경 ¦ $80,000 ¦ +10일 ¦ 대기 ¦ | C1 (영향 최소, 쉬움) | C2 (중간 범위 추가) | C3 (영향 없음, 명확화만) | C4 (최대 영향 — CCB 승인 우선) |  | D | 정답은 D이다. 원가나 일정 영향이 큰 변경은 먼저 CCB의 검토를 받아야 한다. C4는 아직 미승인이며 영향이 가장 크므로(+$80,000, +10일) 가장 먼저 CCB에 올려야 한다. C1(A)은 이미 승인되었고, C3(C)는 영향이 없어 더 낮은 수준에서 처리할 수 있으며, C2(B)는 C4보다 영향이 작다.

## PMBOK 7판 분류기준
3개의 Domain이 있고, 각 Domain별 Task가 있음
PMBOK 7 | 2021 ECO Domain and Task | [5 empty] | Performance Domain | Principle | 구분 | Methodology
| People |  | Process |  | Business Environment |  | Delivery | Be a Diligent, Respectful, and Caring Steward |  | Agile | Predictive | Hybrid | General
| Task | Manage Conflict | Task | Manage Communications | Task | Plan & Manage Compliance | Development Approach & Life Cycle | Build Quality into Processes and Deliverables | Methodology Detail | Agile General Practices | Traditional Plan-Driven | Predictive-Agile Blend | General PM Principles
|  | Lead a Team |  | Assess & Manage Risks |  | Evaluate & Deliver Project Benefits & Value | Measurement | Create a Collaborative Project Team Environment |  | Scrum | WBS/Decomposition | Tailored Approach | Integration & General PM
|  | Support Team Performance |  | Engage Stakeholders |  | Evaluate & Address External Environment Changes | Planning | Demonstrate Leadership Behaviors |  | Kanban | Critical Path/Schedule Mgmt |  | Stakeholder & Communication Mgmt
|  | Empower Team Members |  | Plan & Manage Budget & Resources |  | Support Organizational Change | Project Work | Effectively Engage with Stakeholders |  | Lean | Earned Value Management |  | Risk & Issue Management
|  | Ensure Team Members Are Adequately Trained |  | Plan & Manage Schedule |  |  | Stakeholders | Embrace Adaptability and Resiliency |  | XP |  |  | Scope & Requirements Mgmt
|  | Build a Team |  | Plan & Manage Quality |  |  | Team | Enable Change to Achieve the Envisioned Future State |  | Scaled Agile |  |  | Schedule Management
|  | Address Impediments to Team Performance |  | Plan & Manage Scope |  |  | Uncertainty | Focus on Value |  |  |  |  | Cost & Resource Management
|  | Negotiate Project Agreements |  | Integrate Project Planning Activities |  |  |  | Navigate Complexity |  |  |  |  | Quality Management
|  | Collaborate with Stakeholders |  | Manage Project Changes |  |  |  | Optimize Risk Responses |  |  |  |  | Procurement & Contract Mgmt
|  | Build Shared Understanding |  | Plan & Manage Procurement |  |  |  | Recognize, Evaluate, and Respond to System Interactions |  |  |  |  | Change Management
|  | Engage & Support Virtual Teams |  | Manage Project Artifacts |  |  |  | Tailor Based on Context |  |  |  |  | Baseline & Change Control
|  | Define Team Ground Rules |  | Determine Appropriate PM Methodology
|  | Mentor Relevant Stakeholders |  | Manage Project Issues
|  | Promote Team Performance through EI |  | Plan & Manage Project Closure

## PMBOK 8판 분류기준
3개의 Domain이 있고, 각 Domain별 Task가 있음
PMBOK 8 | 2026 ECO Domain and Task | [5 empty] | Principle | Performance Domain | Focus Area | Process 40 (Performace x Focus) | New Topics | 구분 | Methodology
| People |  | Process |  | Business Environment |  | Adopt a Holistic View | Finance | Closing | Acquire Resources | AI |  | Agile | Predictive | Hybrid | General
| Task | Align Stakeholder Expectations | Task | Develop Integrated PM Plan | Task | Define and Establish Governance | Be an Accountable Leader | Governance | Executing | Close Project or Phase | Digital Transformation | Methodology Detail | Agile General Practices | Traditional Plan-Driven | Predictive-Agile Blend | General PM Principles
|  | Develop a Common Vision |  | Develop and Manage Scope |  | Evaluate External Environment | Build an Empowered Culture | Resources | Initiating | Collect Requirements | Hybrid/Tailoring |  | Scrum | WBS/Decomposition | Tailored Approach | Integration & General PM
|  | Help Ensure Knowledge Transfer |  | Engage Stakeholders |  | Plan and Manage Compliance | Embed Quality | Risk | Monitoring & Controlling | Control Costs | Sustainability |  | Kanban | Critical Path/Schedule Mgmt |  | Stakeholder & Communication Mgmt
|  | Lead the Project Team |  | Evaluate Project Status |  | Support Organizational Change | Focus on Value | Schedule | Planning | Control Quality | Traditional PM |  | Lean | Earned Value Management |  | Risk & Issue Management
|  | Manage Conflicts |  | Manage Project Closure |  |  | Integrate Sustainability | Scope |  | Control Schedule |  |  | XP |  |  | Scope & Requirements Mgmt
|  |  |  | Manage and Control Changes |  |  |  | Stakeholders |  | Control Scope |  |  | Scaled Agile |  |  | Schedule Management
|  |  |  | Plan and Manage Communication | [5 empty] | Create WBS | [5 empty] | Cost & Resource Management
|  |  |  | Plan and Manage Finance | [5 empty] | Define Activities | [5 empty] | Quality Management
|  |  |  | Plan and Manage Procurement | [5 empty] | Define Scope | [5 empty] | Procurement & Contract Mgmt
|  |  |  | Plan and Manage Risk | [5 empty] | Determine Budget | [5 empty] | Change Management
|  |  |  | Plan and Manage Schedule | [5 empty] | Develop Project Charter | [5 empty] | Baseline & Change Control
|  |  |  | Plan and Manage Scope | [5 empty] | Develop Project Management Plan
|  |  |  | Plan and Optimize Quality | [5 empty] | Develop Schedule
|  |  |  | Remove Impediments and Manage Issues | [5 empty] | Develop Team
Direct and Manage Project Work
Estimate Activity Durations
Identify Risks
Identify Stakeholders
Implement Risk Responses
Manage Communications
Manage Project Knowledge
Manage Quality
Manage Stakeholder Engagement
Manage Team
Monitor Communications
Monitor Risks
Monitor Stakeholder Engagement
Monitor and Control Project Performance
Perform Integrated Change Control
Perform Qualitative Risk Analysis
Plan Communications Management
Plan Finance Management
Plan Procurement Management
Plan Resource Management
Plan Risk Management
Plan Scope Management
Plan Stakeholder Engagement
Validate Scope

## WEB 풀이 개발 필요 기능
1 | 유저별 이메일로 로그인 (이메일만 입력하면 로그인 가능)
2 | 관리자가 유저별(이메일) 유효기간 설정 가능
3 | 기본적으로 유효기간 3개월 셋팅
4 | PMP_All_Data의 문제 중에서 여러가지 기준으로 추출
5 | 기준은 PMBOK7판과 PBOK 8판의 분류기준으로 선택 가능
6 | 상위 카테고리 선택 시(All 포함) 하위카테고리 선택 가능
7 | 분류기준 외 오답 중에 고르기, PMP시험기준으로 고르기(7판 기준은 180문항, 8판 기준은 185문항)
8 | 랜덤으로 10개, 30개, 50개, 100개 고르기도 가능
9 | 문제를 풀고, '채점하기' 누르면 채점결과가 나옴
10 | 채점결과 나올때 설명이 정답보기 아래에 나옴 (미리 공간설정)
11 | 번역본 보고 싶으면 번역본 내용이 나오도록 문제/보기/해설 옆에 공간 두고, '번역 보이기' 선택으로 열었다 닫았다 가능한 구조
12 | 유저별 이메일 로그인 시 권한이 없더라도 무료로 50문제 풀어보기 가능(무료판은 50문제 모든문제가 같아야 하고 카테고리, 분류 등은 선택 불가)
13 | 유저별 오타 문제는 별도 데이터베이스에 저장하여 '오답'중에 고르기에서 문제 추출 가능
14 | 오답중에 고르기에서 맞춘 문제는 오답 데이터 베이스에서 삭제
15 | 유저별 정답률 데이터베이스에 두고, 별도 카테고리에서 확인 가능
16 | 정답률은 일자별, 분류기준별 다양하게 볼 수 있어야 함
17 | 모든 유저의 문제별 정답률을 데이터베이스화 하고, 관리자가 필요 시 문제별 정답률 표시 가능하도록 개발만 해놓기
18 | 결제란 만들어만 놓고 활성화 안하기. 나중에 관리자가 활성화 가능하도록 설정
19 | 모바일과 PC에서도 문제 없이 보이도록 개발
20 | 모바일에서 구현하기 어려운것은 PC에서만 가능하다고 표시하기. 문제풀이 모바일에서 반드시 가능
21 | 정답이 1개~3개까지 있으므로 고려해서 개발
22 | 하단에 문의 및 오류 신고하기 안내 (songdoinfo@naver.com)
23 | 카테고리는 문제 풀이, My Status (정답률, 유효기간 등)로 구분
24 | 문제 풀이 카테고리에서 분류기준이 너무 많다면 문제풀이(7판 기준), 문제풀이(8판 기준) 로 구분 가능
25 | 다른 PMP문제풀이 사이트의 우수한 점 있으면 적용해
26 | 채점하기 시 문제 분류기준 나오도록 정보제공